## 01-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-01 | [5 empty] | Project: | 303Collin Street
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
HGP-TRANSMIT-000033 | 0 | 1 | 0 | Rejected- Document Number incorrect -KPTG-CONTADV-000443 | HGP-TRANSMIT-000033 | 1 | 0 | KPTG-CONTADV-000443
INGEN3D-TRANSMIT-000006 | 4 | 0 | 0 | #519 ¦ WF-000247 | INGEN3D-TRANSMIT-000007 | 2 | 0 | For Information and Record
ENF-TRANSMIT-000038 | 3 | 0 | 0 | #511 | HGP-TRANSMIT-000026 | 4 | 0 | KPTG-TRANSMIT-000558
ENF-TRANSMIT-000039 | 9 | 0 | 0 | #513
RDSBIM-TRANSMIT-000025 | 3 | 0 | 0 | #518 ¦ WF-000248
ENF-TRANSMIT-000039 | 9 | 0 | 0 | SME- # 514
INGEN3D-TRANSMIT-000007 | 2 | 0 | 0 | 3D-Model For Record only
HGP-TRANSMIT-000034 | 0 | 1 | 0 | #521 ¦ WF-000249
ENF-TRANSMIT-000040 | 1 | 0 | 0 | #523
ENF-TRANSMIT-000041 | 5 | 0 | 0 | #525
ENF-TRANSMIT-000041 | 5 | 0 | 0 | SME- # 526
Total | 41 | 2 | 0 |  | 3 | 7 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
|  | 0 | 0

## 02-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-02 | [5 empty] | Project: | 303Collin Street
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
OTIS2-TRANSMIT-000021 | 4 | 0 | 0 | #539 ¦ WF-000251 | HGP-TRANSMIT-000028 | 1 | 0 | KPTG-TRANSMIT-000565
OTIS2-TRANSMIT-000022 | 1 | 0 | 0 | #533 ¦ WF-000250 | Carr-TRANSMIT-000073 | 10 | 0 | KPTG-TRANSMIT-000566
HGP-TRANSMIT-000036 | 0 | 7 | 7 | KPTG-TRANSMIT-000590 | Carr-TRANSMIT-000094 | 2 | 0 | KPTG-TRANSMIT-000570
ENF-TRANSMIT-000042 | 1 | 0 | 0 | #543 | Carr-TRANSMIT-000083 | 4 | 0 | KPTG-TRANSMIT-000578
ENF-TRANSMIT-000043 | 11 | 0 | 0 | #542 | Carr-TRANSMIT-000096 | 3 | 0 | KPTG-TRANSMIT-000574
ENF-TRANSMIT-000043 | 11 | 0 | 0 | # 544 SME Review | Carr-TRANSMIT-000096 | 6 | 0 | KPTG-TRANSMIT-000574
GIW-TRANSMIT-000006 | 0 | 1 | 0 | #529 | Carr-TRANSMIT-000072 | 6 | 0 | KPTG-TRANSMIT-000582
GIW-TRANSMIT-000006 | 0 | 1 | 0 | #530 | GIW-TRANSMIT-000006 | 1 | 0 | KPTG-TRANSMIT-000586
ENF-TRANSMIT-000033 | 2 | 0 | 0 | #538 | GIW-TRANSMIT-000006 | 1 | 0 | KPTG-TRANSMIT-000586
ENF-TRANSMIT-000036 | 1 | 0 | 0 | #537 | WSP ANZ-TRANSMIT-000021 | 15 | 0 | KPTG-TRANSMIT-000591
ENF-TRANSMIT-000033 | 2 | 0 | 0 | #536 | WSP ANZ-TRANSMIT-000021 | 1 | 0 | KPTG-TRANSMIT-000591
ENF-TRANSMIT-000036 | 1 | 0 | 0 | #535 | WSP ANZ-TRANSMIT-000021 | 16 | 0 | KPTG-TRANSMIT-000591
ENF-TRANSMIT-000032 | 1 | 0 | 0 | #534 | WSP ANZ-TRANSMIT-000021 | 1 | 0 | KPTG-TRANSMIT-000591
[5 empty] | WSP ANZ-TRANSMIT-000021 | 7 | 0 | KPTG-TRANSMIT-000591
[5 empty] | WSP ANZ-TRANSMIT-000021 | 1 | 0 | KPTG-TRANSMIT-000591
[5 empty] | WSP ANZ-TRANSMIT-000021 | 15 | 0 | KPTG-TRANSMIT-000591
[5 empty] | WSP ANZ-TRANSMIT-000021 | 1 | 0 | KPTG-TRANSMIT-000591
[5 empty] | WSP ANZ-TRANSMIT-000021 | 5 | 0 | KPTG-TRANSMIT-000591
[5 empty] | WSP ANZ-TRANSMIT-000023 | 1 | 0 | KPTG-TRANSMIT-000595
[5 empty] | ENF-TRANSMIT-000034 | 5 | 0 | KPTG-TRANSMIT-000602
[5 empty] | Electro-TRANSMIT-000009 | 6 | 0 | KPTG-TRANSMIT-000606
[5 empty] | Electro-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-000606
[5 empty] | Electro-TRANSMIT-000005 | 5 | 0 | KPTG-TRANSMIT-000610
[5 empty] | Electro-TRANSMIT-000005 | 3 | 0 | KPTG-TRANSMIT-000610
[5 empty] | Carr-TRANSMIT-000092 | 13 | 0 | KPTG-TRANSMIT-000614
[5 empty] | Carr-TRANSMIT-000098 | 7 | 0 | KPTG-TRANSMIT-000618
[5 empty] | Carr-TRANSMIT-000101 | 1 | 0 | KPTG-TRANSMIT-000622
[5 empty] | Carr-TRANSMIT-000100 | 1 | 1 | KPTG-TRANSMIT-000623
[5 empty] | JFS-AU-TRANSMIT-000010 | 1 | 0 | KPTG-TRANSMIT-000630
[5 empty] | GIW-TRANSMIT-000006 | 2 | 0 | Voided
[5 empty] | ENF-TRANSMIT-000032 | 3 | 0 | Voided
[5 empty] | ENF-TRANSMIT-000035 | 1 | 0 | Voided
[5 empty] | ENF-TRANSMIT-000036 | 4 | 0 | SME VOIDED
[5 empty] | ENF-TRANSMIT-000037 | 4 | 0 | SME VOIDED
[5 empty] | ENF-TRANSMIT-000036 | 4 | 0 | Voided
[5 empty] | ENF-TRANSMIT-000033 | 6 | 0 | SME VOIDED
[5 empty] | ENF-TRANSMIT-000037 | 4 | 0 | Voided
[5 empty] | ENF-TRANSMIT-000033 | 6 | 0 | Voided
Total | 35 | 9 | 7 |  | 38 | 174 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
HGP-TRANSMIT-000036 | 2026-10-02 | 7 | 7 | Clarification required from Tradepartner KPTG-TRANSMIT-000590
|  | 7 | 7

## 05-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-05 | [5 empty] | Project: | 303Collin Street
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
Carr-TRANSMIT-000103 | 6 | 0 | 0 | #547 ¦ WF-000255 | HGP-TRANSMIT-000036 | 7 | 0 | Rejected.
HGP-TRANSMIT-000037 | 23 | 0 | 0 | #548 ¦ WF-000254
Omnii-TRANSMIT-000017 | 0 | 1 | 0 | #550 ¦ WF-000256
Total | 29 | 1 | 0 |  | 1 | 7 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
|  | 0 | 0
Project
| Shahir |  | Rakesh
| LINDRUM | AJ | Chapel Street | SP
| MLCSPR | KK | 511SRC | JP
| MWYCCB | SY | NXM3S4 | SHA
| NXD1S2 | NM | NXM3S3 | SHA
| NXM3S2 | NR | Greystar | SP
| MEL05C4 | JP | DISTLV | NM
| MEL11C45 | KK | NXM2S9 | HE
| NXGEO1S1 | NR | NXM3S6 | JP
| 303COL | RSR | NXM3S1D9 | NR

## 06-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-06 | [5 empty] | Project: | 303Collin Street
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
HGP-TRANSMIT-000038 | 0 | 6 | 0 | #552 ¦ WF-000257 | RDSBIM-TRANSMIT-000025 | 3 | 0 | KPTG-TRANSMIT-000639
Total | 0 | 6 | 0 |  | 1 | 3 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
|  | 0 | 0

## 07-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-07 | [5 empty] | Project: | 303Collin Street
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
HGP-TRANSMIT-000040 | 0 | 1 | 0 | #556 ¦ WF-000259 | HGP-TRANSMIT-000021 | 12 | 0 | KPTG-TRANSMIT-000643
HGP-TRANSMIT-000031 | 0 | 3 | 0 | #554 ¦ WF-000258 | HGP-TRANSMIT-000031 | 4 | 0 | Voided-KPTG-TRANSMIT-000642
Total | 0 | 4 | 0 |  | 2 | 16 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
|  | 0 | 0

## 08-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-08 | [5 empty] | Project: | 303Collin Street
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
RDSBIM-TRANSMIT-000026 | 1 | 0 | 0 | Superseded | RDSBIM-TRANSMIT-000026 | 1 | 0 | NA
RDSBIM-TRANSMIT-000027 | 1 | 0 | 0 | #561 ¦ WF-000262
HGP-TRANSMIT-000041 | 4 | 0 | 0 | #558 ¦ WF-000260
ENF-TRANSMIT-000045 | 15 | 0 | 15 | Clarification required from ENF- KPTG-CONTADV-000472
ENF-TRANSMIT-000044 | 1 | 0 | 0 | #563
HGP-TRANSMIT-000007 | 0 | 3 | 0 | #559
Carr-TRANSMIT-000105 | 5 | 0 | 0 | #565 ¦ WF-000261
Total | 27 | 3 | 15 |  | 1 | 1 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
|  | 0 | 0

## 09-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-09 | [5 empty] | Project: | 303Collin Street
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
ENF-TRANSMIT-000046 | 14 | 0 | 0 | Rejected - Incorrect revisions | ENF-TRANSMIT-000045 | 15 | 0 | KPTG-CONTADV-000472
ENF-TRANSMIT-000047 | 2 | 0 | 0 | #567 | ENF-TRANSMIT-000046 | 14 | 0 | KPTG-CONTADV-000474
ENF-TRANSMIT-000048 | 14 | 0 | 0 | #569 | ENF-TRANSMIT-000044 | 1 | 0 | KPTG-CONTADV-000475
HGP-TRANSMIT-000042 | 4 | 0 | 0 | Rejected - Incorrect drawing number | HGP-TRANSMIT-000042 | 4 | 0 | KPTG-CONTADV-000479
HGP-TRANSMIT-000043 | 0 | 1 | 0 | Rejected -Status incorrect | HGP-TRANSMIT-000043 | 1 | 0 | KPTG-CONTADV-000480
HGP-TRANSMIT-000044 | 10 | 0 | 0 | Rejected - Incorrect revisions | HGP-TRANSMIT-000044 | 10 | 0 | KPTG-CONTADV-000481
HGP-TRANSMIT-000045 | 5 | 0 | 0 | Rejected - Incorrec drawing number | HGP-TRANSMIT-000045 | 5 | 0 | KPTG-CONTADV-000482
HGP-TRANSMIT-000046 | 10 | 0 | 0 | #571 ¦ WF-000263 | Carr-TRANSMIT-000111 | 3 | 0 | KPTG-CONTADV-000483
HGP-TRANSMIT-000047 | 0 | 1 | 0 | #573 ¦ WF-000266 | Carr-TRANSMIT-000108 | 5 | 0 | KPTG-CONTADV-000484
HGP-TRANSMIT-000048 | 4 | 0 | 0 | #575 ¦ WF-000265
Carr-TRANSMIT-000106 | 6 | 0 | 0 | #577 ¦ WF-000264
Carr-TRANSMIT-000107 | 16 | 0 | 0 | #583 ¦ WF-000269
Carr-TRANSMIT-000108 | 5 | 0 | 0 | Rejected- Revision History updated incorrectly
Carr-TRANSMIT-000109 | 12 | 0 | 0 | #581 ¦ WF-000268
Carr-TRANSMIT-000110 | 5 | 0 | 0 | #579 ¦ WF-000267
Carr-TRANSMIT-000111 | 0 | 3 | 0 | Rejeted- Incorrect status
Total | 107 | 5 | 0 |  | 9 | 58 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
|  | 0 | 0

## 12-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-12 | [5 empty] | Project: | 303Collin Street
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
RDSBIM-TRANSMIT-000028 | 2 | 0 | 0 | #385 ¦ WF-000270 | HGP-TRANSMIT-000022 | 1 | 0 | KPTG-TRANSMIT-000663
COLDFLOW-TRANSMIT-000003 | 0 | 3 | 0 | Rejected- Incorrect document number | COLDFLOW-TRANSMIT-000003 | 3 | 0 | KPTG-CONTADV-000488
COLDFLOW-TRANSMIT-000004 | 0 | 3 | 0 | Rejected- Incorrect document number | COLDFLOW-TRANSMIT-000004 | 3 | 0 | KPTG-CONTADV-000490
[5 empty] | HGP-TRANSMIT-000029 | 1 | 0 | KPTG-TRANSMIT-000667
Total | 2 | 6 | 0 |  | 4 | 8 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
|  | 0 | 0

## 13-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-13 | [5 empty] | Project: | 303Collin Street
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
RDSBIM-TRANSMIT-000029 | 3 | 0 | 0 | #587 ¦ WF-000271 | RDSBIM-TRANSMIT-000029 | 3 | 0 | Voided
Carr-TRANSMIT-000112 | 0 | 3 | 0 | #589 ¦ WF-000272 | INGEN3D-TRANSMIT-000006 | 0 | 4 | KPTG-DA-000828
Carr-TRANSMIT-000113 | 5 | 0 | 0 | #592 ¦ WF-000273 | WSP ANZ-TRANSMIT-000024 | 1 | 0 | KPTG-CONTADV-000499
COLDFLOW-TRANSMIT-000005 | 0 | 4 | 0 | #593 ¦ WF-000274
WSP ANZ-TRANSMIT-000024 | 5 | 0 | 0 | #596 ¦ WF-000275
WSP ANZ-TRANSMIT-000024 | 6 | 0 | 0 | #598 ¦ WF-000276
WSP ANZ-TRANSMIT-000024 | 1 | 0 | 0 | #600 ¦ WF-000277
WSP ANZ-TRANSMIT-000024 | 6 | 0 | 0 | #602 ¦ WF-000278
WSP ANZ-TRANSMIT-000024 | 2 | 0 | 0 | #604 ¦ WF-000279
WSP ANZ-TRANSMIT-000024 | 0 | 1 | 0 | Rejected - Revision number need to correct
Total | 28 | 8 | 0 |  | 3 | 4 | 4
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
|  | 0 | 0

## 14-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-14 | [5 empty] | Project: | 303Collin Street
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
RDSBIM-TRANSMIT-000030 | 3 | 0 | 0 | #606 ¦ WF-000280 | OTIS2-TRANSMIT-000024 | 1 | 0 | KPTG-CONTADV-000497
OTIS2-TRANSMIT-000023 | 1 | 0 | 0 | #608 ¦ WF-000281 | HGP-TRANSMIT-000050 | 44 | 0 | KPTG-CONTADV-000498
HGP-TRANSMIT-000050 | 44 | 0 | 0 | Rejected - Incorrect drawing status in Aconex | INGEN3D-TRANSMIT-000006 | 4 | 0 | KPTG-TRANSMIT-000676
OTIS2-TRANSMIT-000024 | 0 | 1 | 0 | Rejected | INGEN3D-TRANSMIT-000011 | 8 | 0 | KPTG-CONTADV-000502
OTIS2-TRANSMIT-000025 | 0 | 1 | 0 | #610 ¦ WF-000282 | HGP-TRANSMIT-000025 | 1 | 0 | KPTG-TRANSMIT-000681
INGEN3D-TRANSMIT-000011 | 8 | 0 | 0 | Rejected - Drawing Number incorrect
Total | 56 | 2 | 0 |  | 5 | 58 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
|  | 0 | 0

## 15-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-15 | [5 empty] | Project: | 303Collin Street
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
HGP-TRANSMIT-000052 | 44 | 0 | 0 | #612 ¦ WF-000283 | HGP-TRANSMIT-000023 | 11 | 0 | KPTG-TRANSMIT-000684
Carr-TRANSMIT-000114 | 4 | 0 | 0 | #614 ¦ WF-000284 | HGP-TRANSMIT-000046 | 10 | 0 | KPTG-TRANSMIT-000691
Carr-TRANSMIT-000105 | 4 | 0 | 0 | #615 ¦ | Carr-TRANSMIT-000105 | 5 | 0 | Voided
Carr-TRANSMIT-000115 | 4 | 0 | 0 | #617 ¦ WF-000285 | HGP-TRANSMIT-000046 | 1 | 0 | NA
HGP-TRANSMIT-000046 | 1 | 0 | 0 | #618
Total | 57 | 0 | 0 |  | 4 | 27 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
|  | 0 | 0

## 16-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-16 | [5 empty] | Project: | 303Col
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
RDSBIM-TRANSMIT-000031 | 2 | 0 | 0 | #620 ¦ WF-000287 | HGP-TRANSMIT-000047 | 1 | 0 | KPTG-TRANSMIT-000697
Carr-TRANSMIT-000116 | 6 | 0 | 0 | #622 ¦ WF-000289 | HGP-TRANSMIT-000034 | 1 | 0 | KPTG-TRANSMIT-000701
Carr-TRANSMIT-000117 | 3 | 0 | 0 | #624 ¦ WF-000290 | HGP-TRANSMIT-000041 | 4 | 0 | KPTG-TRANSMIT-000705
Carr-TRANSMIT-000118 | 8 | 0 | 0 | #626 ¦ WF-000291 | HGP-TRANSMIT-000007 | 3 | 0 | KPTG-TRANSMIT-000713
Carr-TRANSMIT-000119 | 10 | 0 | 0 | #628 ¦ WF-000292 | HGP-TRANSMIT-000037 | 23 | 0 | KPTG-TRANSMIT-000709
Carr-TRANSMIT-000120 | 2 | 0 | 0 | #630 ¦ WF-000293 | Carr-TRANSMIT-000112 | 3 | 0 | Voided
Carr-TRANSMIT-000121 | 20 | 0 | 0 | #633 ¦ WF-000295
Carr-TRANSMIT-000112 | 0 | 1 | 0 | #631 ¦ WF-000294
Total | 51 | 1 | 0 |  | 6 | 35 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
|  | 0 | 0