## 01-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-01 | [5 empty] | Project: | 671CHP - Chapel St.
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
| 0 | 0 | 0 |  | RDSBIM-TRANSMIT-000125 671CHP BASEMENT 03 BLOCKWORK PLAN AND ELEVATIONS -880 | 1 | 0 | KPTG-TRANSMIT-002023
[5 empty] | RDSBIM-TRANSMIT-000122 671CHP BASEMENT 04 BLOCKWORK PLAN AND ELEVATIONS -878 | 1 | 0 | KPTG-TRANSMIT-002025
[5 empty] | B Smart-TRANSMIT-000121 Drawings update -939 | 6 | 0 | KPTG-TRANSMIT-002027
[5 empty] | RDSBIM-TRANSMIT-000134 LEVEL 05 -10 (TYPICAL) CONCRETE PROFILE PLAN -935 | 3 | 0 | KPTG-TRANSMIT-002030
[5 empty] | Jangho-TRANSMIT-000133 The calculation report for the 3–18F corner BOX KPTG-WTRAN-001432: Final (WF-000840) | 1 | 0 | KPTG-TRANSMIT-002041
[5 empty] | Jangho-TRANSMIT-000135 Podium GF Shop Drawings Rev - 0 - KPTG-WTRAN-001437: Final (WF-000842) | 35 | 0 | KPTG-TRANSMIT-002032
[5 empty] | IJF-TRANSMIT-000040 PT - Robe Drawings with Inspection Markups -GFMIML-WTRAN-000071: Final (WF-000859) | 9 | 0 | KPTG-TRANSMIT-002033
[5 empty] | IJF-TRANSMIT-000043: PT Study Drawings with Inspection markups GFMIML-WTRAN-000072: Final (WF-000865) | 3 | 0 | KPTG-TRANSMIT-002036
[5 empty] | IJF-TRANSMIT-000038 PT - Drawings Updated with Inspection Notes - GFMIML-WTRAN-000073: Final (WF-000858) | 4 | 0 | KPTG-TRANSMIT-002039
Total | 0 | 0 | 0 |  |  | 63 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
LGCE-TRANSMIT-000089: Level 3 light and power | 2026-09-16 | 2 | 2 | ifc -Tayla to advise - KPTG-IntCorr-001504
ccair-TRANSMIT-000063: Mechanical Services B1 and Ground Shop Drawing IFC [0] | 2026-09-17 | 3 | 3 | IFC-Waiting for Tayla advise-KPTG-IntCorr-001509
ccair-TRANSMIT-000066: Electrical Load Estimation | 2026-09-18 | 1 | 1 | IFC-Waiting for Tayla advise-KPTG-IntCorr-001525
POTTSENG-TRANSMIT-000059 671C: HYDRAULIC SERVICES - BASEMENT 1 & 2 - WATER LAYOUTS | 2026-09-30 | 1 | 2 | IFC - ACC updated - waiting for Kapitol to confirm on the review -KPTG-IntCorr-001610
|  | 7 | 8

## 02-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-02 | [5 empty] | Project: | 671CHP - Chapel St.
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
RDSBIM-TRANSMIT-000135 671CHP LEVEL 18 CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | ACC#950 ¦WF-000897 | ccair-TRANSMIT-000063: Mechanical Services B1 and Ground Shop Drawing IFC [0] | 2 | 0 | IFC - Registered and transmitted - KPTG-TRANSMIT-002045
RDSBIM-TRANSMIT-000136 671CHP COREWALL - GROUND LEVEL TO ROOF | 9 | 0 | 0 | ACC#948 ¦WF-000896
POTTSENG-TRANSMIT-000060: 671C: HYDRAULIC SERVICES - LEVEL 03 & LEVEL 11-20 - DRAINAGE LAYOUTS | 11 | 0 | 0 | IFA - ACC#952 ¦ WF-000898
RDSBIM-TRANSMIT-000137: 671CHP ¦ L04 APT 2.5 INTERNAL FITOUT AND FINISHES PLAN | 7 | 0 | 0 | ACC#954 ¦ WF-000899
POTTSENG-TRANSMIT-000061: 671C: HYDRAULIC SERVICES - LEGEND OF SYMBOLS | 1 | 0 | 1 | Ifi - Waiting for Kapitol advise on the review KPTG-IntCorr-001628
POTTSENG-TRANSMIT-000062: 671C: HYDRAULIC SERVICES - LEVELS 04-10 - DRAINAGE LAYOUTS | 7 | 0 | 0 | ACC#957 ¦WF-000901
Auspan-TRANSMIT-000149: Re: Panel 8PC7E-12 and 10PC7E-12 | 1 | 0 | 1 | ELLA to adviseKPTG-IntCorr-001629
POTTSENG-TRANSMIT-000063: 671C: HYDRAULIC SERVICES - GROUND - WATER LAYOUT | 1 | 0 | 0 | ACC#959 ¦ WF-000902
ccair-TRANSMIT-000071: Mechanical Services L1 shop drawing IFA [B] | 2 | 0 | 0 | ACC#963 ¦ WF-000906
B Smart-TRANSMIT-000122: Purchaser Variations | 9 | 0 | 9 | Kapitol Design Manager to advise on IFI drawings review. KPTG-IntCorr-001630
Total | 51 | 0 | 11 |  |  | 2 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
LGCE-TRANSMIT-000089: Level 3 light and power | 2026-09-16 | 2 | 2 | ifc -Tayla to advise - KPTG-IntCorr-001504
POTTSENG-TRANSMIT-000059 671C: HYDRAULIC SERVICES - BASEMENT 1 & 2 - WATER LAYOUTS | 2026-09-30 | 2 | 2 | IFC - ACC updated - waiting for Kapitol to confirm on the review -KPTG-IntCorr-001610
ccair-TRANSMIT-000063: Mechanical Services B1 and Ground Shop Drawing IFC [0] | 2026-09-17 | 3 | 0 | IFC-Waiting for Tayla advise-KPTG-IntCorr-001509 ACC#961 ¦ WF-000904 for 1 drawing and two are to proceed IFC (Registered and distributed) | KPTG-SADV-005202 - 2 DRAWINGS ok to proceed IFC
ccair-TRANSMIT-000066: Electrical Load Estimation | 2026-09-18 | 1 | 0 | IFC-Waiting for Tayla advise-KPTG-IntCorr-001525 WF-000905 | KPTG-SADV-005203 - proceed to wF
|  | 8 | 4

## 05-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-05 | [5 empty] | Project: | 671CHP - Chapel St.
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
| 0 | 0 | 0 |  |  | 0 | 0
Total | 0 | 0 | 0 |  |  | 0 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
LGCE-TRANSMIT-000089: Level 3 light and power | 2026-09-16 | 2 | 2 | ifc -Tayla to advise - KPTG-IntCorr-001504
POTTSENG-TRANSMIT-000059 671C: HYDRAULIC SERVICES - BASEMENT 1 & 2 - WATER LAYOUTS | 2026-09-30 | 2 | 2 | IFC - ACC updated - waiting for Kapitol to confirm on the review -KPTG-IntCorr-001610
POTTSENG-TRANSMIT-000061: 671C: HYDRAULIC SERVICES - LEGEND OF SYMBOLS | 2026-10-02 | 1 | 1 | Ifi - Waiting for Kapitol advise on the review KPTG-IntCorr-001628
Auspan-TRANSMIT-000149: Re: Panel 8PC7E-12 and 10PC7E-12 | 2026-10-02 | 1 | 1 | ELLA to adviseKPTG-IntCorr-001629
B Smart-TRANSMIT-000122: Purchaser Variations | 2026-10-02 | 9 | 0 | Kapitol Design Manager to advise on IFI drawings review. KPTG-IntCorr-001630 ACC#965 ¦ WF-000907
|  | 15 | 6

## 06-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-06 | [5 empty] | Project: | 671CHP - Chapel St.
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
KALLIBRE-TRANSMIT-000001: Door Frames - Batch 1 - IFA-1 | 28 | 0 | 0 | ACC#967 ¦ WF-000911 | Aloha P-TRANSMIT-000005 Sample and Technical Data Sheets -WF-000891 | 35 | 0 | Review terminated as advised by Kapitol via KPTG-IntCorr-001641
POTTSENG-TRANSMIT-000064: 671C: HYDRAULIC SERVICES - LEVEL 05 - PENETRATION LAYOUT | 1 | 0 | 0 | ACC#969 ¦ WF-000912
Aloha P-TRANSMIT-000005 Sample and Technical Data Sheets | 30 | 0 | 0 | WF-000910
Total | 59 | 0 | 0 |  |  | 35 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
LGCE-TRANSMIT-000089: Level 3 light and power | 2026-09-16 | 2 | 2 | ifc -Tayla to advise - KPTG-IntCorr-001504
POTTSENG-TRANSMIT-000059 671C: HYDRAULIC SERVICES - BASEMENT 1 & 2 - WATER LAYOUTS | 2026-09-30 | 2 | 2 | IFC - ACC updated - waiting for Kapitol to confirm on the review -KPTG-IntCorr-001610
POTTSENG-TRANSMIT-000061: 671C: HYDRAULIC SERVICES - LEGEND OF SYMBOLS | 2026-10-02 | 1 | 1 | Ifi - Waiting for Kapitol advise on the review KPTG-IntCorr-001628
Auspan-TRANSMIT-000149: Re: Panel 8PC7E-12 and 10PC7E-12 | 2026-10-02 | 1 | 1 | ELLA to adviseKPTG-IntCorr-001629
|  | 6 | 6

## 07-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-07 | [5 empty] | Project: | 671CHP - Chapel St.
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
Aloha P-TRANSMIT-000005 Sample and Technical Data Sheets | 5 | 0 | 0 | WF-000913
Total | 5 | 0 | 0 |  |  | 0 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
LGCE-TRANSMIT-000089: Level 3 light and power | 2026-09-16 | 2 | 2 | ifc -Tayla to advise - KPTG-IntCorr-001504
POTTSENG-TRANSMIT-000059 671C: HYDRAULIC SERVICES - BASEMENT 1 & 2 - WATER LAYOUTS | 2026-09-30 | 2 | 2 | IFC - ACC updated - waiting for Kapitol to confirm on the review -KPTG-IntCorr-001610
POTTSENG-TRANSMIT-000061: 671C: HYDRAULIC SERVICES - LEGEND OF SYMBOLS | 2026-10-02 | 1 | 1 | Ifi - Waiting for Kapitol advise on the review KPTG-IntCorr-001628
Auspan-TRANSMIT-000149 Re: Panel 8PC7E-12 and 10PC7E-12 | 2026-10-02 | 1 | 1 | ELLA to adviseKPTG-IntCorr-001629
|  | 6 | 6

## 08-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-08 | [5 empty] | Project: | 671CHP - Chapel St.
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
ccair-TRANSMIT-000074: MSSB Drawings for Approval | 0 | 4 | 0 | Waiting for Kapitol advise : KPTG-IntCorr-001658 Action taken by Kapitol PC - WF-000919 | Auspan-TRANSMIT-000149 Re: Panel 8PC7E-12 and 10PC7E-12 | 1 | 0 | Action taken by project coordinator
LGCE-TRANSMIT-000094 Level 3 light and power | 2 | 0 | 0 | ACC:#977 ¦WF-000918 | LGCE-TRANSMIT-000089: Level 3 light and power | 2 | 0 | Superseded by LGCE-TRANSMIT-000094
Total | 2 | 4 | 0 |  |  | 3 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
POTTSENG-TRANSMIT-000061: 671C: HYDRAULIC SERVICES - LEGEND OF SYMBOLS | 2026-10-02 | 1 | 1 | Ifi - Waiting for Kapitol advise on the review KPTG-IntCorr-001628
Auspan-TRANSMIT-000149 Re: Panel 8PC7E-12 and 10PC7E-12 | 2026-10-02 | 1 | 0 | ELLA to adviseKPTG-IntCorr-001629 | Action taken by project coordinator
POTTSENG-TRANSMIT-000059 671C: HYDRAULIC SERVICES - BASEMENT 1 & 2 - WATER LAYOUTS | 2026-09-30 | 2 | 0 | IFC - ACC updated - waiting for Kapitol to confirm on the review -KPTG-IntCorr-001610 ACC#975 ¦ WF-000917 | IFC internal review initiated.
LGCE-TRANSMIT-000089: Level 3 light and power | 2026-09-16 | 2 | 0 | ifc -Tayla to advise - KPTG-IntCorr-001504 | Superseded by LGCE-TRANSMIT-000094
|  | 6 | 1

## 09-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-09 | [5 empty] | Project: | 671CHP - Chapel St.
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
RDSBIM-TRANSMIT-000138 671CHP LEVEL 05-10 (TYPICAL) CONCRETE PROFILE KEYPLAN | 3 | 0 | 0 | ACC#979 ¦ WF-000921 | RDSBIM-TRANSMIT-000121 671CHP LEVEL 11 CONCRETE PROFILE KEYPLAN AND SECTION #874 | 3 | 0 | KPTG-TRANSMIT-002065
RDSBIM-TRANSMIT-000139 671CHP BASEMENT 01 PARTITION WALL LAYOUT | 1 | 0 | 0 | ACC#981 ¦ WF-000922
RDSBIM-TRANSMIT-000140 671CHP BASEMENT 04 PARTITION WALL LAYOUT | 1 | 0 | 0 | ACC#983 ¦ WF-000923
RDSBIM-TRANSMIT-000141 671CHP BASEMENT 03 PARTITION WALL LAYOUT | 1 | 0 | 0 | ACC#985 ¦ WF-000924
RDSBIM-TRANSMIT-000142 671CHP BASEMENT 02 PARTITION WALL LAYOUT | 1 | 0 | 0 | ACC#987 ¦ WF-000925
POTTSENG-TRANSMIT-000065: 671C - HYDRAULIC SERVICES - GROUND & L01 - DRAINAGE LAYOUT | 2 | 0 | 2 | IFC waiting for advise-KPTG-IntCorr-001667
POTTSENG-TRANSMIT-000066: 671C - HYDRAULIC SERVICES - LEVEL 02 - DRAINAGE LAYOUT | 1 | 0 | 0 | ACC#989 ¦ WF-000926
ccair-TRANSMIT-000078: Mechanical Services B4 to B1 Duct & Pipe IFC | 4 | 0 | 0 | ACC#991 ¦ WF-000927
Total | 14 | 0 | 2 |  |  | 3 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
POTTSENG-TRANSMIT-000061: 671C: HYDRAULIC SERVICES - LEGEND OF SYMBOLS | 2026-10-02 | 1 | 1 | Ifi - Waiting for Kapitol advise on the review KPTG-IntCorr-001628
|  | 1 | 1

## 12-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-12 | [5 empty] | Project: | 671CHP - Chapel St.
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
Jangho-TRANSMIT-000139 L5~L18F cast in channel IFC drawing Rev03 (Jangho-TRANSMIT-000139) | 13 | 0 | 0 | IFC - ACC register updated. Already actioned by Kapitol PC. | Jangho-TRANSMIT-000139 L5~L18F cast in channel IFC drawing Rev03 (Jangho-TRANSMIT-000139) | 13 | 0 | IFC - ACC registe updated. Already actioned by Kapitol PC. KPTG-SADV-005352
KPTG-IntCorr-001675: Fwd: Sample and Technical Data Sheets | 0 | 3 | 0 | Documents are not registered. To initiate workflow, trade partner must transmit via Aconex - KPTG-IntCorr-001681 | KPTG-IntCorr-001675: Fwd: Sample and Technical Data Sheets | 3 | 0 | Documents are not registered. To initiate workflow, trade partner must transmit via Aconex - KPTG-IntCorr-001681
Aloha P-TRANSMIT-000005 Sample and Technical Data Sheets (KPTG-IntCorr-001677) | 30 | 0 | 0 | WF-000928 | Aloha P-TRANSMIT-000005 Sample and Technical Data Sheets -WF-000910 | 30 | 0 | Review terminated as advise - KPTG-IntCorr-001677
Total | 43 | 3 | 0 |  |  | 46 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
POTTSENG-TRANSMIT-000061: 671C: HYDRAULIC SERVICES - LEGEND OF SYMBOLS | 2026-10-02 | 1 | 1 | Ifi - Waiting for Kapitol advise on the review KPTG-IntCorr-001628
POTTSENG-TRANSMIT-000065: 671C - HYDRAULIC SERVICES - GROUND & L01 - DRAINAGE LAYOUT | 2026-10-09 | 2 | 2 | IFC waiting for advise-KPTG-IntCorr-001667
|  | 3 | 3

## 13-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-13 | [5 empty] | Project: | 671CHP - Chapel St.
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
Jangho-TRANSMIT-000142 L5~L20F cast in channel IFC drawing Rev03 | 19 | 0 | 0 | IFC - As advised by kevin Choi, Register and transmit to RDS -KPTG-TRANSMIT-002088 | KPTG-WTRAN-001483: Final (WF-000888) 671 CHP - STR - Interspan SHOP DRAWING REVIEW - IFC - INTSPN-TRANSMIT-000063 L4 Updated plans | 5 | 0 | KPTG-TRANSMIT-002094
Jangho-TRANSMIT-000143 L5~L20F cast in channel IFC drawing Rev03 0 CAD files. | 19 | 0 | 0 | IFC CAD - As advised by kevin Choi, Register and transmit to RDS -KPTG-TRANSMIT-002089 | Jangho-TRANSMIT-000142 L5~L20F cast in channel IFC drawing Rev03 | 19 | 0 | IFC - As advised by kevin Choi, Register and transmit to RDS -KPTG-TRANSMIT-002088
RDSBIM-TRANSMIT-000143 RDS 671 CHP B4 BW IFC | 1 | 0 | 0 | ACC#993 ¦WF-000929 | Jangho-TRANSMIT-000143 L5~L20F cast in channel IFC drawing Rev03 0 CAD files. | 19 | 0 | IFC CAD - As advised by kevin Choi, Register and transmit to RDS -KPTG-TRANSMIT-002089
RDSBIM-TRANSMIT-000144 RDS 671 CHP B3 BW IFC | 1 | 0 | 0 | ACC#995 ¦ WF-000930 | KPTG-WTRAN-001490: Final (WF-000784) Jangho-TRANSMIT-000120 Re: 19‑20F IFA drawings Rev-01 | 31 | 0 | KPTG-TRANSMIT-002095
RDSBIM-TRANSMIT-000145 RDS 671 CHP GL BLOKWORK IFR | 2 | 0 | 0 | IFR ACC#997 ¦WF-000931 | Aloha P-TRANSMIT-000008 Pool IFA Rev B Drawings (KPTG-TRANSMIT-002093) | 26 | 0 | Rejected due to QA issues, DRAFT-015457
RDSBIM-TRANSMIT-000146 RDS 671 CHP B2 BW IFC | 1 | 0 | 0 | ACC#999 ¦WF-000932 | Jangho-TRANSMIT-000128 L3~18 IFC Drawings Rev03 Final KPTG-WTRAN-001491 (WF-000825) | 124 | 0 | KPTG-TRANSMIT-002097
RDSBIM-TRANSMIT-000147 RDS 671 CHP B1 BW IFC | 1 | 0 | 0 | ACC#1001 ¦WF-000933 | RDSBIM-TRANSMIT-000145 RDS 671 CHP GL BLOKWORK ACC#997 | 2 | 0 | Review terminated as advised; RDS is issuing an updated set.
Aloha P-TRANSMIT-000008 Pool IFA Rev B Drawings (KPTG-TRANSMIT-002093) | 26 | 0 | 0 | Rejected due to QA issues, DRAFT-015457 | B Smart-TRANSMIT-000125 updated drawings as per red stick | 61 | 0 | Rejected due to QA issues, DRAFT-015462
Aloha P-TRANSMIT-000009 Pool Tile Sample Sheets | 0 | 3 | 0 | WF-000934
B Smart-TRANSMIT-000125 updated drawings as per red stick | 61 | 0 | 0 | Rejected due to QA issues, DRAFT-015462
cair-TRANSMIT-000082: Fwd: Mechanical Services Ground Duct & Pipe IFC [1] | 1 | 0 | 0 | ACC#1003 ¦ WF-000935
ccair-TRANSMIT-000081 Mechanical Services Core Builders works IFC [1] | 2 | 0 | 0 | ACC#1005 ¦ WF-000936
Total | 134 | 3 | 0 |  |  | 287 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
POTTSENG-TRANSMIT-000061: 671C: HYDRAULIC SERVICES - LEGEND OF SYMBOLS | 2026-10-02 | 1 | 1 | Ifi - Waiting for Kapitol advise on the review KPTG-IntCorr-001628
POTTSENG-TRANSMIT-000065: 671C - HYDRAULIC SERVICES - GROUND & L01 - DRAINAGE LAYOUT | 2026-10-09 | 2 | 2 | IFC waiting for advise-KPTG-IntCorr-001667
|  | 3 | 3

## 14-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-14 | [5 empty] | Project: | 671CHP - Chapel St.
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
RDSBIM-TRANSMIT-000148 671 CHP GROUND FLOOR BLOCKWORK ELEVATIONS | 2 | 0 | 0 | ACC#1009 ¦ WF-000937 | ccair-TRANSMIT-000084: Mechanical Services L04-10 Duct & Pipe IFA | 2 | 0 | Rejected- difference in title- DRAFT-015506
RDSBIM-TRANSMIT-000149 671 CHP LEVEL 11 CONCRETE PROFILE KEYPLAN | 3 | 0 | 0 | ACC#1011 ¦ WF-000938 | B Smart-TRANSMIT-000126: Re: updated drawings as per red stick | 50 | 0 | As advised by the Architect. This transmittal will be superseded
ccair-TRANSMIT-000084: Mechanical Services L04-10 Duct & Pipe IFA | 2 | 0 | 0 | Rejected- difference in title- DRAFT-015506
crossfir-TRANSMIT-000043: Wet Fire - Penetrations Level 11 to up, IFC | 10 | 0 | 10 | IFC waiting for kapitol advise-KPTG-IntCorr-001705 10 Drawings
B Smart-TRANSMIT-000126 Re: updated drawings as per red stick | 50 | 0 | 0 | Waiting for clarification from BSA - on number of drawings.(resubmssion does not include 20 drawings). As advised by the Architect. This transmittal will be superseded
Total | 67 | 0 | 10 |  |  | 52 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
POTTSENG-TRANSMIT-000061: 671C: HYDRAULIC SERVICES - LEGEND OF SYMBOLS | 2026-10-02 | 1 | 1 | Ifi - Waiting for Kapitol advise on the review KPTG-IntCorr-001628
POTTSENG-TRANSMIT-000065: 671C - HYDRAULIC SERVICES - GROUND & L01 - DRAINAGE LAYOUT | 2026-10-09 | 2 | 2 | IFC waiting for advise-KPTG-IntCorr-001667
|  | 3 | 3

## 15-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-15 | [5 empty] | Project: | 671CHP - Chapel St.
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
RDSBIM-TRANSMIT-000150 671 CHP GROUND FLOOR PARTITION WALL PLAN | 3 | 0 | 0 | ACC#1016 ¦WF-000943 | AESG-AU1-TRANSMIT-000006 - F3P1 PERFORMANCE SOLUTION REPORT - WEATHERPROOFING -KPTG-WTRAN-001500: Final (WF-000762) | 1 | 0 | KPTG-TRANSMIT-002115
crossfir-TRANSMIT-000044: Wet Fire - Pumproom and Tank, IFA | 2 | 0 | 0 | Rejected due to incorrect drawing revision- DRAFT-015578 | Jangho-TRANSMIT-000121 Podium 1-2F IFC Drawings Rev-02 KPTG-WTRAN-001502: Final (WF-000781) | 51 | 0 | KPTG-TRANSMIT-002111
B Smart-TRANSMIT-000127 Re: updated drawings as per red stick | 52 | 0 | 0 | IFC - ACC#1013 ¦ WF-000941 | crossfir-TRANSMIT-000044: Wet Fire - Pumproom and Tank, IFA | 2 | 0 | Rejected due to incorrect drawing revision- DRAFT-015578
B Smart-TRANSMIT-000127 updated drawings as per red stick | 9 | 0 | 0 | IFI - ACC#1014 ¦ WF-000942 | B Smart-TRANSMIT-000128 GA - graphic update | 11 | 0 | Rejected due to incorrect drawing titile - DRAFT-015585
B Smart-TRANSMIT-000128 GA - graphic update | 11 | 0 | 0 | Rejected due to incorrect drawing titile - DRAFT-015585 | RDSBIM-TRANSMIT-000148 671 CHP GROUND FLOOR BLOCKWORK ELEVATIONS #1009 | 2 | 0 | KPTG-TRANSMIT-002114
B Smart-TRANSMIT-000129: Re: GA - graphic update | 11 | 0 | 0 | Rejected by Kapitol PM George - KPTG-IntCorr-001716 | B Smart-TRANSMIT-000129: Re: GA - graphic update | 11 | 0 | Rejected by Kapitol PM George - KPTG-IntCorr-001716
crossfir-TRANSMIT-000045 Wet Fire - Pumproom & Tank | 2 | 0 | 0 | ACC#1019 ¦ WF-000946 | Aloha P-TRANSMIT-000010: Re: Pool IFA Rev B Drawings | 3 | 0 | Rejected due to incorrect drawings attached, - DRAFT-015616
Aloha P-TRANSMIT-000010: Re: Pool IFA Rev B Drawings | 3 | 0 | 0 | Rejected due to incorrect drawings attached, - DRAFT-015616
Total | 93 | 0 | 0 |  |  | 81 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
POTTSENG-TRANSMIT-000061: 671C: HYDRAULIC SERVICES - LEGEND OF SYMBOLS | 2026-10-02 | 1 | 1 | Ifi - Waiting for Kapitol advise on the review KPTG-IntCorr-001628
POTTSENG-TRANSMIT-000065: 671C - HYDRAULIC SERVICES - GROUND & L01 - DRAINAGE LAYOUT | 2026-10-09 | 2 | 2 | IFC waiting for advise-KPTG-IntCorr-001667
crossfir-TRANSMIT-000043: Wet Fire - Penetrations Level 11 to up, IFC | 2026-10-14 | 10 | 10 | IFC waiting for kapitol advise-KPTG-IntCorr-001705
|  | 13 | 13

## 16-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-16 | [5 empty] | Project: | 671CHP - Chapel St.
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
ccair-TRANSMIT-000085: Mechanical Services Level 12 IFA [A] | 2 | 0 | 0 | ACC#1021 ¦WF-000947 | ccair-TRANSMIT-000086 Mechanical Services L04-10 Duct & Pipe IFA | 1 | 0 | Rejected due to incomplete resubmision.
ccair-TRANSMIT-000086 Mechanical Services L04-10 Duct & Pipe IFA | 1 | 0 | 0 | Rejected due to incomplete resubmision. DRAFT-015631 | LGCE-TRANSMIT-000105 reed switch | 1 | 0 | Rejected due to incomplete resubmision. DRAFT-015634
LGCE-TRANSMIT-000105 reed switch | 0 | 1 | 0 | Rejected due to incomplete resubmision. DRAFT-015634 | B Smart-TRANSMIT-000122 Purchaser Variations -#965 | 9 | 0 | KPTG-TRANSMIT-002119
B Smart-TRANSMIT-000129 GA - graphic update | 8 | 0 | 0 | IFC - ACC#1023 ¦ WF-000951 | RDSBIM-TRANSMIT-000147 RDS 671 CHP B1 BW IFC - ACC#1001 | 1 | 0 | Review terminated as requsted by RDS to issue updated drawing.
B Smart-TRANSMIT-000129 GA - graphic update | 3 | 0 | 0 | IFI - ACC#1024 ¦ WF-000952
Aloha P-TRANSMIT-000011 Pool IFA Rev B Shop Drawings | 30 | 0 | 0 | WF-000950
LGCE-TRANSMIT-000106: reed switch | 0 | 1 | 0 | WF-000953
ccair-TRANSMIT-000087 Mechanical Services L4-10 Duct & Pipe IFA | 2 | 0 | 0 | ACC#1027 ¦WF-000954
Total | 46 | 2 | 0 |  |  | 12 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
POTTSENG-TRANSMIT-000061: 671C: HYDRAULIC SERVICES - LEGEND OF SYMBOLS | 2026-10-02 | 1 | 1 | Ifi - Waiting for Kapitol advise on the review KPTG-IntCorr-001628
POTTSENG-TRANSMIT-000065: 671C - HYDRAULIC SERVICES - GROUND & L01 - DRAINAGE LAYOUT | 2026-10-09 | 2 | 2 | IFC waiting for advise-KPTG-IntCorr-001667
crossfir-TRANSMIT-000043: Wet Fire - Penetrations Level 11 to up, IFC | 2026-10-14 | 10 | 10 | IFC waiting for kapitol advise-KPTG-IntCorr-001705
|  | 13 | 13