## 01-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-01 | [5 empty] | Project: MEL05C4
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
SMEPS-TRANSMIT-00026 | 0 | 1 | 0 | WF - 000620 | KPTG-IntCorr-000761 | 1 | 0 | KPTG-TRANSMIT-001212
[5 empty] | KPTG-IntCorr-000722 | 1 | 0 | KPTG-TRANSMIT-001214
[5 empty] | KPTG-IntCorr-000755 | 1 | 0 | KPTG-TRANSMIT-001216
[5 empty] | KPTG-IntCorr-000756 | 4 | 0 | KPTG-TRANSMIT-001218
| 0 | 1 | 0 |  |  | 7 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks

## 02-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-02 | [5 empty] | Project: MEL05C4
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
0 | 0 | 0 | 0 |  | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks

## 05-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-05 | [5 empty] | Project: MEL05C4
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
0 | 0 | 0 | 0 |  | 0 | 0 | 0
Total | 0 | 0 | 0 |  | 0 | 0 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks

## 06-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-06 | [5 empty] | Project: MEL05C4
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
SMEPS-TRANSMIT-000263 | 0 | 1 | 0 | WF - 000621 | KPTG-IntCorr-000745 | 1 | 0 | KPTG-TRANSMIT-001220
KPTG-TRANSMIT-001219 | 0 | 1 | 0 | WF - 000622 | SMEPS-TRANSMIT-000258 | 1 | 0 | KPTG-TRANSMIT-001222
SMEPS-TRANSMIT-000264 | 12 | 0 | 0 | AS BUILT | SMEPS-TRANSMIT-000264 | 12 | 0 | AS BUILT
Total | 12 | 2 | 0 |  | 0 | 14 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks

## 07-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-07 | [5 empty] | Project: MEL05C4
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
SMEPS-TRANSMIT-000265 | 11 | 0 | 0 | AS BUILT | SMEPS-TRANSMIT-000265 | 11 | 0 | AS BUILT
SMEPS-TRANSMIT-000266 | 1 | 0 | 0 | WF - 000626 | SMEPS-SUBADVICE-000527 | 1 | 0 | KPTG-TRANSMIT-001224
SES AU-TRANSMIT-000017 | 0 | 0 | 0 | WF - 000624 | SMEPS-TRANSMIT-000268 | 5 | 0 | AS BUILT
SMEPS-TRANSMIT-000267 | 1 | 0 | 0 | WF-000627 | SMEPS-TRANSMIT-000269 | 1 | 0 | AS BUILT
SMEPS-TRANSMIT-000268 | 5 | 0 | 0 | AS BUILT | KPTG-IntCorr-000757 | 1 | 0 | KPTG-TRANSMIT-001229
SMEPS-TRANSMIT-000269 | 1 | 0 | 0 | AS BUILT
SMEPS-TRANSMIT-000270 | 1 | 0 | 0 | WF-000625
SIL-TRANSMIT-000044 | 2 | 0 | 0 | WF - 000628
Total | 22 | 0 | 0 |  | 0 | 19 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks

## 08-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-08 | [5 empty] | Project: MEL05C4
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
SMEPS-TRANSMIT-000271 | 1 | 0 | 0 | AS BUILT | SMEPS-TRANSMIT-000270 | 1 | 0 | KPTG-TRANSMIT-001233
SMEPS-TRANSMIT-000272 | 2 | 0 | 0 | AS BUILT | SMEPS-TRANSMIT-000267 | 1 | 0 | KPTG-TRANSMIT-001236
KPTG-TRANSMIT-001242 | 1 | 0 | 0 | WF-000629 | SMEPS-TRANSMIT-000266 | 1 | 0 | KPTG-TRANSMIT-001239
[5 empty] | SMEPS-TRANSMIT-000271 | 1 | 0 | AS BUILT
[5 empty] | SMEPS-TRANSMIT-000272 | 2 | 0 | AS BUILT
[5 empty] | KPTG-SADV-001629 | 1 | 0 | KPTG-TRANSMIT-001231
[5 empty] | KPTG-TRANSMIT-001219 | 1 | 0 | KPTG-TRANSMIT-001244
Total | 4 | 0 | 0 |  |  | 8 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks

## 09-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-09 | [5 empty] | Project: MEL05C4
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
SMEPS-TRANSMIT-000273 | 1 | 0 | 0 | AS BUILT | SMEPS-TRANSMIT-000273 | 1 | 0 | AS BUILT
SMEPS-TRANSMIT-000274 | 1 | 0 | 0 | AS BUILT | SMEPS-TRANSMIT-000274 | 1 | 0 | AS BUILT
SIL-TRANSMIT-000044 | 0 | 1 | 0 | WF-000630 | KPTG-TRANSMIT-001249 | 1 | 0 | KPTG-TRANSMIT-001249
Total | 2 | 1 | 0 |  |  | 3 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks

## 12-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-12 | [5 empty] | Project: MEL05C4
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
[5 empty] | SES AU-TRANSMIT-000016 | 1 | 0 | KPTG-TRANSMIT-001252
Total | 0 | 0 | 0 |  |  | 1 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks

## 13-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-13 | [5 empty] | Project: MEL05C4
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
SEAPBU-IntCorr-000035 | 0 | 1 | 0 | WF - 000631 | SMEPS-TRANSMIT-000275 | 23 | 0 | AS BUILT
KPTG-SADV-002623 | 0 | 1 | 0 | WF-000632
SMEPS-TRANSMIT-000275 | 23 | 0 | 0 | AS BUILT
Total | 23 | 2 | 0 |  |  | 23 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks

## 14-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-14 | [5 empty] | Project: MEL05C4
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
SMEPS-TRANSMIT-000276 | 1 | 0 | 0 | AS BUILT | SMEPS-TRANSMIT-000276 | 1 | 0 | AS BUILT
Total | 1 | 0 | 0 |  |  | 1 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks

## 15-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-15 | [5 empty] | Project: MEL05C4
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
SMEPS-TRANSMIT-000277 | 0 | 1 | 0 | WF-000634 | SMEPS-TRANSMIT-000278 | 5 | 0 | AS BUILT
SMEPS-TRANSMIT-000278 | 5 | 0 | 0 | AS BUILT
Total | 5 | 1 | 0 |  |  | 5 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks

## 16-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-16 | [5 empty] | Project: MEL05C4
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
KPTG-IntCorr-000797 | 0 | 1 | 0 | WF-000635
KPTG-IntCorr-000802 | 0 | 1 | 0 | WF-000636
KPTG-IntCorr-000798 | 0 | 1 | 0 | WF-000637
Total | 0 | 3 | 0 |  |  | 0 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks