## 01-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-01 | [6 empty] | Project: MWYCCB
Incoming Transmittals |  |  |  |  | InEight.Ref | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks |  | Transmittals | No. of Documents | Pending Number of Documents
Baigents-TRANSMIT-000099 | 2 | 0 | 2 | KPTG-IntCorr-004697 |  | WilsonPD-TRANSMIT-000248 | 1 | 0 | KPTG-TRANSMIT-001820
WilsonPD-TRANSMIT-000248 | 1 | 0 | 0 | KPTG-IntCorr-004700 |  | PMT Sec-TRANSMIT-000061 | 6 | 0 | KPTG-TRANSMIT-001822
PMT Sec-TRANSMIT-000062 | 2 | 0 | 0 | KPTG-IntCorr-004701 |  | PMT Sec-TRANSMIT-000062 | 2 | 0 | KPTG-TRANSMIT-001824
Arco-TRANSMIT-000014 | 2 | 0 | 2 | Kapitol stamp is missing - KPTG-IntCorr-004709
Arco-TRANSMIT-000015 | 2 | 0 | 0 | KPTG-IntCorr-004718
Total | 9 |  | 4 |  |  |  | 9
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Leemark-TRANSMIT-000076 | 2026-09-15 | 21 | 21 | KPTG-IntCorr-004479
CETEC-TRANSMIT-000002 | 2026-09-17 | 1 | 1 | KPTG-IntCorr-004383
WilsonPD-TRANSMIT-000244 | 2026-09-21 | 1 | 1 | KPTG-IntCorr-004421
23

## 02-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-02 | [6 empty] | Project: MWYCCB
Incoming Transmittals |  |  |  |  | InEight.Ref | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks |  | Transmittals | No. of Documents | Pending Number of Documents
RDSBIM-TRANSMIT-000076 | 2 | 0 | 0 | KPTG-IntCorr-004727 |  | D&E-TRANSMIT-000337 | 3 | 0 | KPTG-TRANSMIT-001826
RDSBIM-TRANSMIT-000077 | 3 | 0 | 0 | KPTG-IntCorr-004730
D&E-TRANSMIT-000337 | 3 | 0 | 0 | KPTG-IntCorr-004733
PMT Sec-TRANSMIT-000063 | 1 | 0 | 0 | KPTG-IntCorr-004739
Total | 9 |  | 0 |  |  |  | 3
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Leemark-TRANSMIT-000076 | 2026-09-15 | 21 | 21 | KPTG-IntCorr-004479
CETEC-TRANSMIT-000002 | 2026-09-17 | 1 | 1 | KPTG-IntCorr-004383
WilsonPD-TRANSMIT-000244 | 2026-09-21 | 1 | 1 | KPTG-IntCorr-004421
Baigents-TRANSMIT-000099 | 2026-10-01 | 2 | 2 | KPTG-IntCorr-004697
Arco-TRANSMIT-000014 | 2026-10-01 | 2 | 2 | Kapitol stamp is missing - KPTG-IntCorr-004709
27

## 05-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-05 | [5 empty] | Project: MWYCCB
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
D&E-TRANSMIT-000339 | 5 | 0 | 0 | KPTG-IntCorr-004755 | D&E-TRANSMIT-000340 | 1 | 0 | Sent back to Originator-KPTG-TRANSMIT-001828
WilsonPD-TRANSMIT-000249 | 2 | 0 | 0 | KPTG-IntCorr-004756
D&E-TRANSMIT-000340 | 0 | 1 | 0 | Sent back to Originator-KPTG-TRANSMIT-001828
HGP-TRANSMIT-000074 | 31 | 0 | 0 | KPTG-IntCorr-004764
Total | 38 | 1 | 0 |  |  | 1 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Leemark-TRANSMIT-000076 | 2026-09-15 | 21 | 21 | KPTG-IntCorr-004479
WilsonPD-TRANSMIT-000244 | 2026-09-21 | 1 | 1 | KPTG-IntCorr-004421
Arco-TRANSMIT-000014 | 2026-10-01 | 2 | 2 | Kapitol stamp is missing - KPTG-IntCorr-004709
|  | 24 | 24

## 06-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-06 | [5 empty] | Project: MWYCCB
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
[5 empty] | CETEC-TRANSMIT-000002 | 1 | 0 | KPTG-IntCorr-004761
[5 empty] | Leemark-TRANSMIT-000076 | 21 | 0 | KPTG-IntCorr-004774
[5 empty] | WilsonPD-TRANSMIT-000244 | 1 | 0 | KPTG-IntCorr-004773
[5 empty] | D&E-TRANSMIT-000339 | 5 | 0 | KPTG-TRANSMIT-001830
Total | 0 | 0 | 0 |  |  | 28 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Arco-TRANSMIT-000014 | 2026-10-01 | 2 | 2 | Kapitol stamp is missing - KPTG-IntCorr-004709
|  | 2 | 2

## 07-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-07 | [5 empty] | Project: MWYCCB
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
Leemark-TRANSMIT-000077 | 8 | 0 | 0 | KPTG-IntCorr-004788 | WilsonPD-TRANSMIT-000249 | 2 | 0 | Terminated-KPTG-IntCorr-004783
RDSBIM-TRANSMIT-000078 | 5 | 0 | 0 | KPTG-IntCorr-004782 | M.S.-TRANSMIT-000033 | 28 | 0 | Sent back to Originator-KPTG-TRANSMIT-001833
D&E-TRANSMIT-000343 | 1 | 0 | 0 | KPTG-IntCorr-004785 | Leemark-TRANSMIT-000077 | 8 | 0 | KPTG-TRANSMIT-001835
PMT Sec-TRANSMIT-000064 | 5 | 0 | 5 | KPTG-IntCorr-004786 | WilsonPD-TRANSMIT-000250 | 2 | 0 | Sent back to Originator-KPTG-TRANSMIT-001837
M.S.-TRANSMIT-000033 | 28 | 0 | 0 | Sent back to Originator-KPTG-TRANSMIT-001833
WilsonPD-TRANSMIT-000250 | 2 | 0 | 0 | Sent back to Originator-KPTG-TRANSMIT-001837
Total | 49 | 0 | 5 |  |  | 40 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Arco-TRANSMIT-000014 | 2026-10-01 | 2 | 2 | Kapitol stamp is missing - KPTG-IntCorr-004709
|  | 2 | 2

## 08-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-08 | [5 empty] | Project: MWYCCB
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
M.S.-TRANSMIT-000034 | 9 | 0 | 0 | Sent back to Originator-KPTG-TRANSMIT-001841 | M.S.-TRANSMIT-000034 | 9 | 0 | Sent back to Originator-KPTG-TRANSMIT-001841
M.S.-TRANSMIT-000035 | 28 | 0 | 0 | Sent back to Originator-KPTG-TRANSMIT-001842 | M.S.-TRANSMIT-000036 | 1 | 0 | Sent back to Originator-KPTG-TRANSMIT-001840
M.S.-TRANSMIT-000036 | 1 | 0 | 0 | Sent back to Originator-KPTG-TRANSMIT-001840 | M.S.-TRANSMIT-000035 | 28 | 0 | Sent back to Originator-KPTG-TRANSMIT-001842
WilsonPD-TRANSMIT-000251 | 2 | 0 | 0 | KPTG-IntCorr-004799 | D&E-TRANSMIT-000329 | 6 | 0 | KPTG-TRANSMIT-001843
M.S.-TRANSMIT-000037 | 2 | 0 | 0 | KPTG-IntCorr-004801 | PMT Sec-TRANSMIT-000065 | 1 | 0 | KPTG-IntCorr-004805
M.S.-TRANSMIT-000038 | 1 | 0 | 0 | KPTG-IntCorr-004803
PMT Sec-TRANSMIT-000065 | 1 | 0 | 0 | KPTG-IntCorr-004805
PMT Sec-TRANSMIT-000066 | 1 | 0 | 0 | KPTG-IntCorr-004804
Leemark-TRANSMIT-000079 | 1 | 0 | 0 | KPTG-IntCorr-004806
PMT Sec-TRANSMIT-000067 | 15 | 0 | 0 | KPTG-IntCorr-004807
PMT Sec-TRANSMIT-000068 | 1 | 0 | 0 | KPTG-IntCorr-004808
Total | 62 | 0 | 0 |  |  | 45 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Arco-TRANSMIT-000014 | 2026-10-01 | 2 | 2 | Kapitol stamp is missing - KPTG-IntCorr-004709
PMT Sec-TRANSMIT-000064 | 2026-10-07 | 5 | 5 | KPTG-IntCorr-004786
|  | 7 | 7

## 09-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-09 | [5 empty] | Project: MWYCCB
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
RDSBIM-TRANSMIT-000079 | 5 | 0 | 0 | KPTG-IntCorr-004811 | Baigents-TRANSMIT-000099 | 2 | 0 | KPTG-TRANSMIT-001844
D&E-TRANSMIT-000345 | 0 | 1 | 1 | KPTG-IntCorr-004814 | WilsonPD-TRANSMIT-000252 | 2 | 0 | Sent back to Originator-KPTG-TRANSMIT-001846
WilsonPD-TRANSMIT-000252 | 0 | 2 | 0 | Sent back to Originator-KPTG-TRANSMIT-001846 | WilsonPD-TRANSMIT-000254 | 2 | 0 | Sent back to Originator-KPTG-TRANSMIT-001847
WilsonPD-TRANSMIT-000254 | 0 | 2 | 0 | Sent back to Originator-KPTG-TRANSMIT-001847 | HGP-TRANSMIT-000076 | 1 | 0 | Sent back to Originator-KPTG-TRANSMIT-001848
M.S.-TRANSMIT-000042 | 4 | 0 | 0 | KPTG-IntCorr-004817 | M.S.-TRANSMIT-000046 | 40 | 0 | Sent back to Originator-KPTG-TRANSMIT-001849
M.S.-TRANSMIT-000045 | 4 | 0 | 0 | KPTG-IntCorr-004818 | PMT Sec-TRANSMIT-000063 | 1 | 0 | KPTG-TRANSMIT-001850
HGP-TRANSMIT-000076 | 0 | 1 | 0 | Sent back to Originator-KPTG-TRANSMIT-001848 | D&E-TRANSMIT-000343 | 1 | 0 | KPTG-TRANSMIT-001852
M.S.-TRANSMIT-000046 | 40 | 0 | 0 | Sent back to Originator-KPTG-TRANSMIT-001849 | WilsonPD-TRANSMIT-000251 | 2 | 0 | KPTG-TRANSMIT-001854
WilsonPD-TRANSMIT-000255 | 0 | 2 | 0 | KPTG-IntCorr-004815 | M.S.-TRANSMIT-000042 | 4 | 0 | KPTG-IntCorr-004817
D&E-TRANSMIT-000346 | 1 | 0 | 0 | KPTG-IntCorr-004819 | M.S.-TRANSMIT-000045 | 4 | 0 | KPTG-IntCorr-004818
M.S.-TRANSMIT-000047 | 40 | 0 | 0 | KPTG-IntCorr-004820 | PMT Sec-TRANSMIT-000066 | 1 | 0 | KPTG-TRANSMIT-001856
RDSBIM-TRANSMIT-000080 | 2 | 0 | 0 | KPTG-IntCorr-004822 | RDSBIM-TRANSMIT-000078 | 2 | 0 | Terminated -KPTG-TRANSMIT-001858
RDSBIM-TRANSMIT-000078 | 3 | 0 | 0 | KPTG-IntCorr-004821 | HRA-TRANSMIT-000001 | 2 | 0 | Sent back to Originator-KPTG-TRANSMIT-001859
HRA-TRANSMIT-000001 | 2 | 0 | 0 | Sent back to Originator-KPTG-TRANSMIT-001859 | Leemark-TRANSMIT-000079 | 1 | 0 | KPTG-TRANSMIT-001860
Total | 101 | 8 | 1 |  |  | 65 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Arco-TRANSMIT-000014 | 2026-10-01 | 2 | 2 | Kapitol stamp is missing - KPTG-IntCorr-004709
PMT Sec-TRANSMIT-000064 | 2026-10-07 | 5 | 5 | KPTG-IntCorr-004786
|  | 7 | 7

## 12-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-12 | [5 empty] | Project: MWYCCB
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
M.S.-TRANSMIT-000037 | 2 | 0 | 0 | KPTG-IntCorr-004837 | M.S.-TRANSMIT-000037 | 2 | 0 | Terminated
M.S.-TRANSMIT-000038 | 1 | 0 | 0 | KPTG-IntCorr-004838 | M.S.-TRANSMIT-000038 | 1 | 0 | Terminated
M.S.-TRANSMIT-000047 | 40 | 0 | 0 | KPTG-IntCorr-004839 | M.S.-TRANSMIT-000047 | 40 | 0 | Terminated
Baigents-TRANSMIT-000100 | 1 | 0 | 0 | KPTG-IntCorr-004847 | Arco-TRANSMIT-000014 | 2 | 0 | KPTG-TRANSMIT-001863
[5 empty] | Baigents-TRANSMIT-000100 | 1 | 0 | KPTG-TRANSMIT-001865
[5 empty] | SMEPS-TRANSMIT-000293 | 2 | 0 | KPTG-TRANSMIT-001866
[5 empty] | SMEPS-TRANSMIT-000302 | 3 | 0 | KPTG-TRANSMIT-001868
Total | 44 | 0 | 0 |  |  | 51 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PMT Sec-TRANSMIT-000064 | 2026-10-07 | 5 | 5 | KPTG-IntCorr-004786
D&E-TRANSMIT-000345 | 2026-10-09 | 1 | 0 | KPTG-IntCorr-004814
|  | 6 | 5

## 13-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-13 | [5 empty] | Project: MWYCCB
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
HRA-TRANSMIT-000002 | 4 | 0 | 0 | Sent back to Originator-KPTG-TRANSMIT-001873 | HRA-TRANSMIT-000002 | 4 | 0 | Sent back to Originator-KPTG-TRANSMIT-001873
[5 empty] | RDSBIM-TRANSMIT-000077 | 3 | 0 | Terminated-KPTG-TRANSMIT-001874
[5 empty] | RDSBIM-TRANSMIT-000069 | 2 | 0 | KPTG-TRANSMIT-001875
Total | 4 | 0 | 0 |  |  | 9 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PMT Sec-TRANSMIT-000064 | 2026-10-07 | 5 | 5 | KPTG-IntCorr-004786
D&E-TRANSMIT-000345 | 2026-10-09 | 1 | 1 | KPTG-IntCorr-004814
|  | 6 | 6

## 14-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-14 | [5 empty] | Project: MWYCCB
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
DCN165 Drawings - ARC | 95 | 0 | 0 | Mail from lawden-#509 | RDSBIM-TRANSMIT-000080 | 2 | 0 | KPTG-TRANSMIT-001878
WilsonPD-TRANSMIT-000256 | 0 | 1 | 0 | KPTG-TRANSMIT-001879 | WilsonPD-TRANSMIT-000256 | 1 | 0 | KPTG-TRANSMIT-001879
HRA-TRANSMIT-000003 | 4 | 0 | 0 | KPTG-IntCorr-004883
Total | 99 | 1 | 0 |  |  | 3 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PMT Sec-TRANSMIT-000064 | 2026-10-07 | 5 | 5 | KPTG-IntCorr-004786
D&E-TRANSMIT-000345 | 2026-10-09 | 1 | 1 | KPTG-IntCorr-004814
|  | 6 | 6

## 15-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-15 | [5 empty] | Project: MWYCCB
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
RDSBIM-TRANSMIT-000081 | 2 | 0 | 0 | KPTG-IntCorr-004884 | RDSBIM-TRANSMIT-000082 | 2 | 0 | Sent back to Originator-KPTG-TRANSMIT-001880
RDSBIM-TRANSMIT-000082 | 2 | 0 | 0 | Sent back to Originator-KPTG-TRANSMIT-001880
WilsonPD-TRANSMIT-000257 | 0 | 1 | 0 | KPTG-IntCorr-004885
DCN165 Drawings ELC | 22 | 0 | 0 | Mail From Lawden - #512
DCN165 Drawings MEC | 7 | 0 | 0 | Mail From Lawden - #513
DCN165 Drawings HYD | 4 | 0 | 0 | Mail From Lawden - #514
DCN165 Drawings FIR | 11 | 0 | 0 | Mail From Lawden - #515
Total | 48 | 1 | 0 |  |  | 2 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PMT Sec-TRANSMIT-000064 | 2026-10-07 | 5 | 5 | KPTG-IntCorr-004786
D&E-TRANSMIT-000345 | 2026-10-09 | 1 | 1 | KPTG-IntCorr-004814
|  | 6 | 6

## 16-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-16 | [5 empty] | Project: MWYCCB
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
SMEPS-TRANSMIT-000305 | 0 | 4 | 0 | Sent back to Originator-KPTG-TRANSMIT-001882 | DCN165 Drawings FIR | 11 | 0 | KPTG-TRANSMIT-001881
SMEPS-TRANSMIT-000306 | 0 | 2 | 0 | Sent back to Originator-KPTG-TRANSMIT-001883 | SMEPS-TRANSMIT-000305 | 4 | 0 | Sent back to Originator-KPTG-TRANSMIT-001882
SMEPS-TRANSMIT-000307 | 1 | 0 | 0 | KPTG-IntCorr-004896 | SMEPS-TRANSMIT-000306 | 2 | 0 | Sent back to Originator-KPTG-TRANSMIT-001883
Total | 1 | 6 | 0 |  |  | 17 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PMT Sec-TRANSMIT-000064 | 2026-10-07 | 5 | 5 | KPTG-IntCorr-004786
D&E-TRANSMIT-000345 | 2026-10-09 | 1 | 1 | KPTG-IntCorr-004814
|  | 6 | 6