## 16-10-26
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-16 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
TIVINTL-TRANSMIT-000022 | 206 | 0 | 0 | #1501, WF-001484, WF-001485 | WAM-TRANSMIT-000880 | 17 | 0 | KPTG-TRANSMIT-004417
ccair-TRANSMIT-000044 | 5 | 0 | 0 | #1504, WF-001486 | KALLIBRE-TRANSMIT-000008 | 4 | 0 | KPTG-TRANSMIT-004420
RDSBIM-TRANSMIT-000136 | 5 | 0 | 0 | #1505, WF-001487 | ccair-TRANSMIT-000042 | 1 | 0 | KPTG-TRANSMIT-004424
KRAU-FA-SMP-001 | 0 | 1 | 0 | WF-001488 | L.E.S.-TRANSMIT-000108 | 9 | 0 | KPTG-TRANSMIT-004427: rejected
L.E.S.-TRANSMIT-000107 | 0 | 12 | 0 | WF-001490 | L.E.S.-TRANSMIT-000106 | 2 | 0 | rejected: KPTG-TRANSMIT-004426
L.E.S.-TRANSMIT-000105 | 0 | 2 | 0 | WF-001489
L.E.S.-TRANSMIT-000109 | 31 | 0 | 0 | #1507, WF-001491
L.E.S.-TRANSMIT-000108 | 9 | 0 | 0 | rejectedKPTG-TRANSMIT-004427
L.E.S.-TRANSMIT-000106 | 0 | 2 | 0 | rejected: KPTG-TRANSMIT-004426
ccair-TRANSMIT-000045 | 0 | 1 | 0 | WF-001492
PCForm-TRANSMIT-000351 | 2 | 0 | 0 | #1511
PCForm-TRANSMIT-000352 | 3 | 0 | 0 | #1509
12 | 261 | 18 | 0 |  | 5 | 33 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
Jangho-TRANSMIT-000358 | 2026-09-17 | 1 | 1 | Jaanbir to clarify
Firesafe-TRANSMIT-000027 | 2026-10-02 | 6 | 6 | JOHN TO CLARITY
Kone-VIC-TRANSMIT-000007 | 2026-09-28 | 48 | 48 | JOHN TO CLARITY
ZLH P/L-TRANSMIT-000002 | 2026-09-28 | 3 | 3 | Michael to clarify
L.E.S.-TRANSMIT-000101 | 2026-10-15 | 1 | 1 | JOHN TO CLARITY | KPTG-IntCorr-001554
A.P.E-TRANSMIT-000008 | 2026-10-15 | 4 | 4 | Dima | KPTG-IntCorr-001556
OPTCO-TRANSMIT-000003 | 2026-10-12 | 1 | 1 | JOHN TO CLARITY
65
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757
KPTG-WTRAN-002921 | Final (WF-001351) DISTLV¦ SAMPLE & TECH DATA I CONSULTANT REVIEW ¦ HYD ¦ G&CHyd-TRANSMIT-000030 - HYD TECH DATA - Cleaners Sink

## 15-10-26
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-15 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
Jangho-TRANSMIT-000377 | 15 | 0 | 0 | #1486 | G&CHyd-TRANSMIT-000041 | 2 | 0 | REJECTED: KPTG-TRANSMIT-004416
RDSBIM-TRANSMIT-000134 | 2 | 0 | 0 | #1482 | RDSBIM-TRANSMIT-000134 | 2 | 0 | KPTG-TRANSMIT-004407
RDSBIM-TRANSMIT-000135 | 4 | 0 | 0 | #1485, WF-001479 | WAM-TRANSMIT-000880 | 1 | 0 | KPTG-TRANSMIT-004414
L.E.S.-TRANSMIT-000102 | 10 | 0 | 0 | #1488 | Jaycon-TRANSMIT-000005 | 1 | 0 | Rejected:
WAM-TRANSMIT-000882 | 12 | 0 | 0 | #1497, WF-001483
Axiom-TRANSMIT-000036 | 11 | 0 | 0 | #1490, WF-001481
G&CHyd-TRANSMIT-000041 | 0 | 2 | 0 | REJECTED: KPTG-TRANSMIT-004416
Jaycon-TRANSMIT-000005 | 15 | 0 | 0 | #1493
Jaycon-TRANSMIT-000005 | 1 | 0 | 0 | Rejected:
WAM-TRANSMIT-000883 | 13 | 0 | 0 | #1495, WF-001482
L.E.S.-TRANSMIT-000101 | 1 | 0 | 1 | KPTG-IntCorr-001554
A.P.E-TRANSMIT-000008 | 4 | 0 | 4 | KPTG-IntCorr-001556
12 | 88 | 2 | 5 |  | 4 | 6 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 0 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
Jangho-TRANSMIT-000358 | 2026-09-17 | 1 | 1 | Jaanbir to clarify
Firesafe-TRANSMIT-000027 | 2026-10-02 | 6 | 6 | JOHN TO CLARITY
Kone-VIC-TRANSMIT-000007 | 2026-09-28 | 48 | 48 | JOHN TO CLARITY
ZLH P/L-TRANSMIT-000002 | 2026-09-28 | 3 | 3 | Michael to clarify
L.E.S.-TRANSMIT-000101 | 2026-10-15 | 1 | 1 | JOHN TO CLARITY | KPTG-IntCorr-001554
A.P.E-TRANSMIT-000008 | 2026-10-15 | 4 | 4 | Dima | KPTG-IntCorr-001556
60
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757
KPTG-WTRAN-002921 | Final (WF-001351) DISTLV¦ SAMPLE & TECH DATA I CONSULTANT REVIEW ¦ HYD ¦ G&CHyd-TRANSMIT-000030 - HYD TECH DATA - Cleaners Sink

## 14-10-26
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-14 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
Jangho-TRANSMIT-000376 | 0 | 1 | 0 | WF-001472 | BIMF-TRANSMIT-000035 | 4 | 0 | KPTG-TRANSMIT-004404 rejected
RDSBIM-TRANSMIT-000130 | 5 | 0 | 0 | #1471 | RDSBIM-TRANSMIT-000129 | 4 | 0 | KPTG-TRANSMIT-004394 rejected
BIMF-TRANSMIT-000035 | 4 | 0 | 0 | KPTG-TRANSMIT-004404 rejected | RDSBIM-TRANSMIT-000126 | 2 | 0 | KPTG-TRANSMIT-004391
RDSBIM-TRANSMIT-000129 | 4 | 0 | 0 | KPTG-TRANSMIT-004394 rejected | ccair-TRANSMIT-000042 | 1 | 0 | KPTG-TRANSMIT-004396
RDSBIM-TRANSMIT-000131 | 5 | 0 | 0 | #1473 | WAM-TRANSMIT-000879 | 28 | 0 | KPTG-TRANSMIT-004398
L.E.S.-TRANSMIT-000100 | 11 | 0 | 0 | #1475 | A.P.E-TRANSMIT-000006 | 4 | 0 | replaced A.P.E-TRANSMIT-000007
ccair-TRANSMIT-000043 | 1 | 0 | 0 | #1477 | Jaycon-TRANSMIT-000004 | 16 | 0 | rejected : KPTG-TRANSMIT-004393
A.P.E-TRANSMIT-000006 | 4 | 0 | 0 | replaced A.P.E-TRANSMIT-000007 | A.P.E-TRANSMIT-000007 | 4 | 0 | rejected: KPTG-TRANSMIT-004402
Jaycon-TRANSMIT-000004 | 16 | 0 | 0 | rejected : KPTG-TRANSMIT-004393
A.P.E-TRANSMIT-000007 | 4 | 0 | 0 | rejected: KPTG-TRANSMIT-004402
10 | 54 | 1 | 0 |  | 8 | 63 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 0 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
Jangho-TRANSMIT-000358 | 2026-09-17 | 1 | 1 | Jaanbir to clarify
Firesafe-TRANSMIT-000027 | 2026-10-02 | 6 | 6 | JOHN TO CLARITY
Kone-VIC-TRANSMIT-000007 | 2026-09-28 | 48 | 48 | JOHN TO CLARITY
ZLH P/L-TRANSMIT-000002 | 2026-09-28 | 3 | 3 | Michael to clarify
59
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757
KPTG-WTRAN-002921 | Final (WF-001351) DISTLV¦ SAMPLE & TECH DATA I CONSULTANT REVIEW ¦ HYD ¦ G&CHyd-TRANSMIT-000030 - HYD TECH DATA - Cleaners Sink

## 13-10-26
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-13 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
RDSBIM-TRANSMIT-000127 | 3 | 0 | 0 | #1465 | Jangho-TRANSMIT-000374 | 1 | 0 | TERMINATED - KPTG-IntCorr-001540
NUBRIK-FA-SMP-002, NUBRIK-FA-SMP-003 AND NUBRIK-FA-SMP-004 | 0 | 3 | 0 | WF-001464 | RDSBIM-TRANSMIT-000127 | 3 | 0 | KPTG-TRANSMIT-004375
Jangho-TRANSMIT-000374 | 0 | 1 | 0 | WF-001466 | L.E.S.-TRANSMIT-000099 | 2 | 0 | KPTG-TRANSMIT-004387
Jangho-TRANSMIT-000375 | 0 | 1 | 0 | WF-001468
L.E.S.-TRANSMIT-000098 | 9 | 0 | 0 | #1469
L.E.S.-TRANSMIT-000099 | 0 | 2 | 0 | KPTG-TRANSMIT-004387
Jangho-TRANSMIT-000354 | 0 | 1 | 0 | WF-001471
7 | 12 | 8 | 0 |  | 3 | 6 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 0 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
Jangho-TRANSMIT-000358 | 2026-09-17 | 1 | 1 | Jaanbir to clarify
Firesafe-TRANSMIT-000027 | 2026-10-02 | 6 | 6 | JOHN TO CLARITY
Kone-VIC-TRANSMIT-000007 | 2026-09-28 | 48 | 48 | JOHN TO CLARITY
ZLH P/L-TRANSMIT-000002 | 2026-09-28 | 3 | 3 | Michael to clarify
59
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757
KPTG-WTRAN-002921 | Final (WF-001351) DISTLV¦ SAMPLE & TECH DATA I CONSULTANT REVIEW ¦ HYD ¦ G&CHyd-TRANSMIT-000030 - HYD TECH DATA - Cleaners Sink

## 12-10-26
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-12 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
ArcadiaL-TRANSMIT-000010 | 48 | 0 | 0 | KPTG-TRANSMIT-004351 | ArcadiaL-TRANSMIT-000010 | 48 | 0 | KPTG-TRANSMIT-004351
RDSBIM-TRANSMIT-000125 | 6 | 0 | 0 | #1463 | L.E.S.-TRANSMIT-000027 - CLIENT APPROVED | 8 | 0 | KPTG-TRANSMIT-004368
RDSBIM-TRANSMIT-000126 | 2 | 0 | 0 | #1459 | BIMF-TRANSMIT-000032 | 4 | 0 | KPTG-TRANSMIT-004354
WAM-TRANSMIT-000881 | 1 | 0 | 0 | #1467 | ccair-TRANSMIT-000031 | 7 | 0 | KPTG-TRANSMIT-004356
ArcadiaL-TRANSMIT-000011 | 48 | 0 | 0 | #1461 | ccair-TRANSMIT-000030 | 2 | 0 | KPTG-TRANSMIT-004358
INGEN3D-TRANSMIT-000276 | 8 | 0 | 0 | WF-001462 | ccair-TRANSMIT-000032 | 1 | 0 | KPTG-TRANSMIT-004360
OPTCO-TRANSMIT-000003 | 0 | 1 | 1 | KPTG-IntCorr-001535 | BIMF-TRANSMIT-000034 | 2 | 0 | KPTG-TRANSMIT-004362
[5 empty] | ccair-TRANSMIT-000038 | 3 | 0 | KPTG-TRANSMIT-004364
[5 empty] | ccair-TRANSMIT-000028 | 1 | 0 | KPTG-TRANSMIT-004370
[5 empty] | Jangho-TRANSMIT-000367 | 15 | 0 | KPTG-TRANSMIT-004372
7 | 113 | 1 | 1 |  | 10 | 91 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 0 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
Jangho-TRANSMIT-000358 | 2026-09-17 | 1 | 1 | Jaanbir to clarify
Firesafe-TRANSMIT-000027 | 2026-10-02 | 6 | 6 | JOHN TO CLARITY
Kone-VIC-TRANSMIT-000007 | 2026-09-28 | 48 | 48 | JOHN TO CLARITY
ZLH P/L-TRANSMIT-000002 | 2026-09-28 | 3 | 3 | Michael to clarify
59
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757
KPTG-WTRAN-002921 | Final (WF-001351) DISTLV¦ SAMPLE & TECH DATA I CONSULTANT REVIEW ¦ HYD ¦ G&CHyd-TRANSMIT-000030 - HYD TECH DATA - Cleaners Sink

## 09-10-26
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-09 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
L.E.S.-TRANSMIT-000095 | 16 | 0 | 0 | #1455 | G&CHyd-TRANSMIT-000029 | 1 | 0 | KPTG-TRANSMIT-004327
L.E.S.-TRANSMIT-000096 | 11 | 0 | 0 | KPTG-TRANSMIT-004346 : rejected | Axiom-TRANSMIT-000032 | 12 | 0 | KPTG-TRANSMIT-004329
ccair-TRANSMIT-000042 | 0 | 2 | 0 | WF-001452 | Axiom-TRANSMIT-000033 | 2 | 0 | KPTG-TRANSMIT-004330
AXM-FAC-SMP-001 | 0 | 1 | 0 | WF-001453 | Axiom-TRANSMIT-000034 | 1 | 0 | KPTG-TRANSMIT-004329
G&CHyd-TRANSMIT-000040 | 0 | 6 | 0 | KPTG-TRANSMIT-004347 : rejected | L.E.S.-TRANSMIT-000096 | 11 | 0 | KPTG-TRANSMIT-004346 : rejected
Jangho-TRANSMIT-000374 | 0 | 1 | 0 | WF-001454 | Jaycon-TRANSMIT-000001 | 17 | 0 | KPTG-TRANSMIT-004333,KPTG-TRANSMIT-004336
L.E.S.-TRANSMIT-000097 | 6 | 0 | 0 | #1457, WF-001455 | WAM-TRANSMIT-000878 | 1 | 0 | KPTG-TRANSMIT-004340
INGEN3D-TRANSMIT-000274 | 9 | 0 | 0 | rejected: KPTG-TRANSMIT-004348 | WAM-TRANSMIT-000877 | 1 | 0 | KPTG-TRANSMIT-004342
INGEN3D-TRANSMIT-000275 | 2 | 0 | 0 | KPTG-TRANSMIT-004349 - distributed - No Longer in use | G&CHyd-TRANSMIT-000040 | 6 | 0 | KPTG-TRANSMIT-004347 : rejected
[5 empty] | INGEN3D-TRANSMIT-000274 | 9 | 0 | rejected: KPTG-TRANSMIT-004348
[5 empty] | INGEN3D-TRANSMIT-000275 | 2 | 0 | KPTG-TRANSMIT-004349 - distributed - No Longer in use
9 | 44 | 10 | 0 |  | 11 | 63 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 0 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
Jangho-TRANSMIT-000358 | 2026-09-17 | 1 | 1 | Jaanbir to clarify
Firesafe-TRANSMIT-000027 | 2026-10-02 | 6 | 6 | JOHN TO CLARITY
Kone-VIC-TRANSMIT-000007 | 2026-09-28 | 48 | 48 | JOHN TO CLARITY
ZLH P/L-TRANSMIT-000002 | 2026-09-28 | 3 | 3 | Michael to clarify
59
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757
KPTG-WTRAN-002921 | Final (WF-001351) DISTLV¦ SAMPLE & TECH DATA I CONSULTANT REVIEW ¦ HYD ¦ G&CHyd-TRANSMIT-000030 - HYD TECH DATA - Cleaners Sink

## 08-10-26
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-08 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
Jangho-TRANSMIT-000372 | 16 | 0 | 0 | #1444 | RDSBIM-TRANSMIT-000118 | 4 | 0 | KPTG-TRANSMIT-004302
L.E.S.-TRANSMIT-000092 | 11 | 0 | 0 | KPTG-TRANSMIT-004317 | WAM-TRANSMIT-000876 | 1 | 0 | KPTG-TRANSMIT-004304
TIVINTL-TRANSMIT-000021 | 61 | 0 | 0 | #1447 | L.E.S.-TRANSMIT-000092 | 11 | 0 | KPTG-TRANSMIT-004317
KRAU-FA-SMP-001 | 0 | 1 | 0 | WF-001448 | PCForm-TRANSMIT-000336 | 10 | 0 | KPTG-TRANSMIT-004306
KALLIBRE-TRANSMIT-000008 | 4 | 0 | 0 | #1448, WF-001449 | RDSBIM-TRANSMIT-000123 | 7 | 0 | KPTG-TRANSMIT-004308
L.E.S.-TRANSMIT-000093 | 16 | 0 | 0 | KPTG-TRANSMIT-004316 | L.E.S.-TRANSMIT-000093 | 16 | 0 | KPTG-TRANSMIT-004316
Jangho-TRANSMIT-000373 | 7 | 0 | 0 | #1451 WF-001456 | ccair-TRANSMIT-000021 | 2 | 0 | KPTG-TRANSMIT-004310
Jangho-TRANSMIT-000371 | 139 | 0 | 0 | #1451 WF-001456 | ccair-TRANSMIT-000026 | 3 | 0 | KPTG-TRANSMIT-004311
L.E.S.-TRANSMIT-000094 | 7 | 0 | 0 | #1453, WF-001451 | ccair-TRANSMIT-000040 | 1 | 0 | KPTG-TRANSMIT-004314
9 | 261 | 1 | 0 |  | 9 | 55 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
Jangho-TRANSMIT-000358 | 2026-09-17 | 1 | 1 | Jaanbir to clarify
Firesafe-TRANSMIT-000027 | 2026-10-02 | 6 | 6 | JOHN TO CLARITY
Kone-VIC-TRANSMIT-000007 | 2026-09-28 | 48 | 48 | JOHN TO CLARITY
ZLH P/L-TRANSMIT-000002 | 2026-09-28 | 3 | 3 | Michael to clarify
61
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757
KPTG-WTRAN-002921 | Final (WF-001351) DISTLV¦ SAMPLE & TECH DATA I CONSULTANT REVIEW ¦ HYD ¦ G&CHyd-TRANSMIT-000030 - HYD TECH DATA - Cleaners Sink

## 07-10-26
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-07 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
RDSBIM-TRANSMIT-000124 | 6 | 0 | 0 | #1433 | RDSBIM-TRANSMIT-000104 | 5 | 0 | KPTG-TRANSMIT-004283
Deca-TRANSMIT-000003 | 0 | 7 | 0 | WF-001442 | RDSBIM-TRANSMIT-000121 | 6 | 0 | KPTG-TRANSMIT-004284
Firesafe-TRANSMIT-000028 | 6 | 0 | 0 | #1435 | RDSBIM-TRANSMIT-000105 | 5 | 0 | KPTG-TRANSMIT-004287
AF&S-TRANSMIT-000010 | 23 | 0 | 0 | KPTG-TRANSMIT-004289 | AF&S-TRANSMIT-000010 | 23 | 0 | KPTG-TRANSMIT-004289: rejected
Axiom-TRANSMIT-000035 | 10 | 0 | 0 | #1437 | L.E.S.-TRANSMIT-000090 | 11 | 0 | KPTG-TRANSMIT-004290: rejected
L.E.S.-TRANSMIT-000090 | 11 | 0 | 0 | KPTG-TRANSMIT-004290 | Jangho-TRANSMIT-000371 | 146 | 0 | KPTG-TRANSMIT-004296: rejected
L.E.S.-TRANSMIT-000091 | 2 | 0 | 0 | #1439 | RDSBIM-TRANSMIT-000119 | 5 | 0 | KPTG-TRANSMIT-004291
Jangho-TRANSMIT-000371 | 146 | 0 | 0 | KPTG-TRANSMIT-004296 | RDSBIM-TRANSMIT-000117 | 5 | 0 | KPTG-TRANSMIT-004294
WAM-TRANSMIT-000880 | 17 | 0 | 0 | #1441, WF-001458
WAM-TRANSMIT-000880 | 1 | 0 | 0 | #1442, WF-001457
10 | 222 | 7 | 0 |  | 8 | 206 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
Jangho-TRANSMIT-000358 | 2026-09-17 | 1 | 1 | Jaanbir to clarify
Firesafe-TRANSMIT-000027 | 2026-10-02 | 6 | 6 | JOHN TO CLARITY
Kone-VIC-TRANSMIT-000007 | 2026-09-28 | 48 | 48 | JOHN TO CLARITY
ZLH P/L-TRANSMIT-000002 | 2026-09-28 | 3 | 3 | Michael to clarify
61
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757
KPTG-WTRAN-002921 | Final (WF-001351) DISTLV¦ SAMPLE & TECH DATA I CONSULTANT REVIEW ¦ HYD ¦ G&CHyd-TRANSMIT-000030 - HYD TECH DATA - Cleaners Sink

## 06-10-26
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-06 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
ccair-TRANSMIT-000039 | 3 | 0 | 0 | #1424 | WAM-TRANSMIT-000875 | 24 | 0 | KPTG-TRANSMIT-004269
ccair-TRANSMIT-000040 | 1 | 0 | 0 | #1426 | Deca-TRANSMIT-000002 | 7 | 0 | rejected: KPTG-TRANSMIT-004273
Deca-TRANSMIT-000002 | 0 | 7 | 0 | rejected: KPTG-TRANSMIT-004273 | RDSBIM-TRANSMIT-000098 | 4 | 0 | KPTG-TRANSMIT-004272
L.E.S.-TRANSMIT-000088 | 33 | 0 | 0 | #1428 | L.E.S.-TRANSMIT-000089 | 3 | 0 | rejected: KPTG-TRANSMIT-004276
DECA-ST-SMP-007 (Teams msg Nich) | 0 | 1 | 0 | WF-001438 | BIMF-TRANSMIT-000030 | 4 | 0 | KPTG-TRANSMIT-004274
L.E.S.-TRANSMIT-000089 | 3 | 0 | 0 | rejected: KPTG-TRANSMIT-004276 | L.E.S.-TRANSMIT-000078 | 9 | 0 | KPTG-TRANSMIT-004277
WAM-TRANSMIT-000879 | 28 | 0 | 0 | #1431 | PCForm-TRANSMIT-000344 | 11 | 0 | rejected : KPTG-TRANSMIT-004279
TTW-TRANSMIT-000176 | 0 | 1 | 0 | WF-001439 | PCForm-TRANSMIT-000343 | 6 | 0 | rejected: KPTG-TRANSMIT-004280
PCForm-TRANSMIT-000344 | 11 | 0 | 0 | rejected : KPTG-TRANSMIT-004279 | PCForm-TRANSMIT-000342 | 22 | 0 | rejected: KPTG-TRANSMIT-004281
PCForm-TRANSMIT-000342 | 22 | 0 | 0 | rejected: KPTG-TRANSMIT-004281
PCForm-TRANSMIT-000343 | 6 | 0 | 0 | rejected: KPTG-TRANSMIT-004280
11 | 107 | 9 | 0 |  | 9 | 90 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
Jangho-TRANSMIT-000358 | 2026-09-17 | 1 | 1 | Jaanbir to clarify
Firesafe-TRANSMIT-000027 | 2026-10-02 | 6 | 6 | JOHN TO CLARITY
Kone-VIC-TRANSMIT-000007 | 2026-09-28 | 48 | 48 | JOHN TO CLARITY
ZLH P/L-TRANSMIT-000002 | 2026-09-28 | 3 | 3 | Michael to clarify
61
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757
KPTG-WTRAN-002921 | Final (WF-001351) DISTLV¦ SAMPLE & TECH DATA I CONSULTANT REVIEW ¦ HYD ¦ G&CHyd-TRANSMIT-000030 - HYD TECH DATA - Cleaners Sink

## 05-10-26
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-05 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
BP8 - Building Permits | 0 | 19 | 0 | Forwarded to all parties | WAM-TRANSMIT-000873 | 4 | 0 | KPTG-TRANSMIT-004242
BP9 - Building Permits | 0 | 5 | 0 | Forwarded to all parties | L.E.S.-TRANSMIT-000079 | 2 | 0 | KPTG-TRANSMIT-004244
Deca-TRANSMIT-000001 | 0 | 7 | 0 | KPTG-TRANSMIT-004262 | L.E.S.-TRANSMIT-000077 | 2 | 0 | KPTG-TRANSMIT-004247
DECA-ST-SMP-005 | 0 | 1 | 0 | WF-001432 | L.E.S.-TRANSMIT-000073 | 8 | 0 | KPTG-TRANSMIT-004251
WAM-TRANSMIT-000877 | 1 | 0 | 0 | #1420 | L.E.S.-TRANSMIT-000072 | 6 | 0 | KPTG-TRANSMIT-004253
WAM-TRANSMIT-000878 | 1 | 0 | 0 | #1422 | DECA-ST-SMP-005 | 1 | 0 | WF-001432
[5 empty] | Deca-TRANSMIT-000001 | 7 | 0 | KPTG-TRANSMIT-004262
[5 empty] | BP8 - Building Permits | 19 | 0 | KPTG-TRANSMIT-004246
[5 empty] | BP9 - Building Permits | 5 | 0 | KPTG-TRANSMIT-004255
6 | 2 | 32 | 0 |  | 9 | 54 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
Jangho-TRANSMIT-000358 | 2026-09-17 | 1 | 1 | Jaanbir to clarify
Firesafe-TRANSMIT-000027 | 2026-10-02 | 6 | 6 | JOHN TO CLARITY
Kone-VIC-TRANSMIT-000007 | 2026-09-28 | 48 | 48 | JOHN TO CLARITY
ZLH P/L-TRANSMIT-000002 | 2026-09-28 | 3 | 3 | Michael to clarify
61
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757
KPTG-WTRAN-002921 | Final (WF-001351) DISTLV¦ SAMPLE & TECH DATA I CONSULTANT REVIEW ¦ HYD ¦ G&CHyd-TRANSMIT-000030 - HYD TECH DATA - Cleaners Sink

## 02-10-26
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-02 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
WAM-TRANSMIT-000875 | 24 | 0 | 0 | #1402 WF-001423 | RDSBIM-TRANSMIT-000120 | 1 | 0 | KPTG-TRANSMIT-004232
RDSBIM-TRANSMIT-000122 | 4 | 0 | 0 | #1409 WF-001426 | KALLIBRE-TRANSMIT-000004 | 6 | 0 | KPTG-TRANSMIT-004234
RDSBIM-TRANSMIT-000123 | 7 | 0 | 0 | #1404 WF-001424 | RDSBIM-TRANSMIT-000124 | 6 | 0 | KPTG-TRANSMIT-004236 rejected
RDSBIM-TRANSMIT-000124 | 6 | 0 | 0 | KPTG-TRANSMIT-004236 rejected | TIVINTL-TRANSMIT-000016 | 61 | 0 | KPTG-TRANSMIT-004239 rejected
TIVINTL-TRANSMIT-000016 | 61 | 0 | 0 | KPTG-TRANSMIT-004239 rejected | RDSBIM-TRANSMIT-000116 | 2 | 0 | KPTG-TRANSMIT-004237
TIVINTL-TRANSMIT-000018 | 22 | 0 | 0 | #1410 | AF&S-TRANSMIT-000009 | 22 | 0 | KPTG-TRANSMIT-004240 rejected
TIVINTL-TRANSMIT-000019 | 74 | 0 | 0 | #1416 - WF-001430
TIVINTL-TRANSMIT-000020 | 100 | 0 | 0 | #1418
TIVINTL-TRANSMIT-000017 | 100 | 0 | 0 | #1412
Firesafe-TRANSMIT-000027 | 6 | 0 | 6 | KPTG-IntCorr-001485
WAM-TRANSMIT-000876 | 1 | 0 | 0 | #1414
AF&S-TRANSMIT-000009 | 22 | 0 | 0 | KPTG-TRANSMIT-004240 rejected
12 | 427 | 0 | 6 |  | 6 | 98 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
Jangho-TRANSMIT-000358 | 2026-09-17 | 1 | 1 | Jaanbir to clarify
Firesafe-TRANSMIT-000027 | 2026-10-02 | 6 | 6 | JOHN TO CLARITY
Kone-VIC-TRANSMIT-000007 | 2026-09-28 | 48 | 48 | JOHN TO CLARITY
ZLH P/L-TRANSMIT-000002 | 2026-09-28 | 3 | 3 | Michael to clarify
61
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757
KPTG-WTRAN-002921 | Final (WF-001351) DISTLV¦ SAMPLE & TECH DATA I CONSULTANT REVIEW ¦ HYD ¦ G&CHyd-TRANSMIT-000030 - HYD TECH DATA - Cleaners Sink

## 01-10-26
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-01 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
Jangho-TRANSMIT-000368 | 15 | 0 | 0 | KPTG-TRANSMIT-004218 | Jangho-TRANSMIT-000368 | 15 | 0 | KPTG-TRANSMIT-004218
Jangho-TRANSMIT-000369 | 0 | 1 | 0 | WF-001418 | G&CHyd-TRANSMIT-000037 | 1 | 0 | KPTG-TRANSMIT-004205
PCForm-TRANSMIT-000336 | 10 | 0 | 0 | #1396 | G&CHyd-TRANSMIT-000036 | 2 | 0 | KPTG-TRANSMIT-004206
ccair-TRANSMIT-000038 | 3 | 0 | 0 | #1398 | BIMF-TRANSMIT-000029 | 4 | 0 | KPTG-TRANSMIT-004208
Firesafe-TRANSMIT-000024 | 14 | 0 | 0 | #1400 | Jangho-TRANSMIT-000340 | 1 | 0 | KPTG-TRANSMIT-004211
TIVINTL-TRANSMIT-000013 | 22 | 0 | 0 | KPTG-TRANSMIT-004220 | Firesafe-TRANSMIT-000026 | 3 | 0 | KPTG-TRANSMIT-004212
TIVINTL-TRANSMIT-000014 | 74 | 0 | 0 | KPTG-TRANSMIT-004222 | Civilex-TRANSMIT-000118 | 1 | 0 | KPTG-TRANSMIT-004215
TIVINTL-TRANSMIT-000015 | 114 | 0 | 0 | KPTG-TRANSMIT-004223 | WAM-TRANSMIT-000869 | 22 | 0 | KPTG-TRANSMIT-004216
TIVINTL-TRANSMIT-000010 | 61 | 0 | 0 | KPTG-TRANSMIT-004229 | TIVINTL-TRANSMIT-000013 | 22 | 0 | KPTG-TRANSMIT-004220
TIVINTL-TRANSMIT-000012 | 152 | 0 | 0 | KPTG-TRANSMIT-004227 | TIVINTL-TRANSMIT-000014 | 74 | 0 | KPTG-TRANSMIT-004222
Jangho-TRANSMIT-000370 | 147 | 0 | 0 | KPTG-TRANSMIT-004226 | WAM-TRANSMIT-000870 | 2 |  | KPTG-TRANSMIT-004216
[5 empty] | TIVINTL-TRANSMIT-000015 | 114 | 0 | KPTG-TRANSMIT-004223
[5 empty] | TIVINTL-TRANSMIT-000010 | 61 | 0 | KPTG-TRANSMIT-004229
[5 empty] | TIVINTL-TRANSMIT-000012 | 152 | 0 | KPTG-TRANSMIT-004227
[5 empty] | Jangho-TRANSMIT-000370 | 147 | 0 | KPTG-TRANSMIT-004226
11 | 612 | 1 | 0 |  | 15 | 621 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
Jangho-TRANSMIT-000358 | 2026-09-17 | 1 | 1 | Jaanbir to clarify
4
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757
KPTG-WTRAN-002921 | Final (WF-001351) DISTLV¦ SAMPLE & TECH DATA I CONSULTANT REVIEW ¦ HYD ¦ G&CHyd-TRANSMIT-000030 - HYD TECH DATA - Cleaners Sink

## 30-09
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-09-30 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
BIMF-TRANSMIT-000034 | 2 | 0 | 0 | #1387 | Jangho-TRANSMIT-000348 | 156 | 0 | KPTG-TRANSMIT-004186
Jangho-TRANSMIT-000365 | 0 | 1 | 0 | KPTG-TRANSMIT-004190 | Jangho-TRANSMIT-000365 | 1 | 0 | KPTG-TRANSMIT-004190
RDSBIM-TRANSMIT-000121 | 6 | 0 | 0 | #1388 ¦ WF-001412 | L.E.S.-TRANSMIT-000081 | 1 | 0 | KPTG-TRANSMIT-004191
Jangho-TRANSMIT-000366 | 0 | 1 | 0 | WF-001411 | RDSBIM-TRANSMIT-000117 | 4 | 0 | KPTG-TRANSMIT-004193
L.E.S.-TRANSMIT-000087 | 12 | 0 | 0 | #1390 | KALLIBRE-TRANSMIT-000006 | 9 | 0 | Rejected - KPTG-TRANSMIT-004195
KALLIBRE-TRANSMIT-000006 | 9 | 0 | 0 | Rejected - KPTG-TRANSMIT-004195 | KPTG-WTRAN-002990 | 1 | 0 | KPTG-TRANSMIT-004200DECA-ST-SMP-006 -PLACED IN WORKFLOW AS MENTIONED IN TEAMS
KALLIBRE-TRANSMIT-000007 | 9 | 0 | 0 | #1392 | Axiom-TRANSMIT-000034 | 1 | 0 | KPTG-TRANSMIT-004201
KPTG-WTRAN-002990 | 0 | 1 | 0 | WF-001394 | Jangho-TRANSMIT-000364 | 20 | 0 | KPTG-TRANSMIT-004202
Axiom-TRANSMIT-000034 | 1 | 0 | 0 | Rejected - Previous revision under review
Jangho-TRANSMIT-000367 | 15 | 0 | 0 | #1394
10 | 54 | 3 | 0 |  | 8 | 193 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
Jangho-TRANSMIT-000358 | 2026-09-17 | 1 | 1 | Jaanbir to clarify
4
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757
KPTG-WTRAN-002921 | Final (WF-001351) DISTLV¦ SAMPLE & TECH DATA I CONSULTANT REVIEW ¦ HYD ¦ G&CHyd-TRANSMIT-000030 - HYD TECH DATA - Cleaners Sink

## 29-09
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-09-29 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
RDSBIM-TRANSMIT-000118 | 4 | 0 | 0 | #1377 | RDSBIM-TRANSMIT-000112 | 2 | 0 | KPTG-TRANSMIT-004181
RDSBIM-TRANSMIT-000119 | 5 | 0 | 0 | #1380 | KALLIBRE-TRANSMIT-000003 | 10 | 0 | KPTG-TRANSMIT-004182
RDSBIM-TRANSMIT-000120 | 1 | 0 | 0 | #1382 | G&CHyd-TRANSMIT-000038 | 4 | 0 | KPTG-TRANSMIT-004183
G&CHyd-TRANSMIT-000038 | 0 | 10 | 0 | WF-001409
G&CHyd-TRANSMIT-000038 | 0 | 4 | 0 | KPTG-TRANSMIT-004183
5 | 10 | 14 | 0 |  | 3 | 16 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
Jangho-TRANSMIT-000358 | 2026-09-17 | 1 | 1 | Jaanbir to clarify
4
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757
KPTG-WTRAN-002921 | Final (WF-001351) DISTLV¦ SAMPLE & TECH DATA I CONSULTANT REVIEW ¦ HYD ¦ G&CHyd-TRANSMIT-000030 - HYD TECH DATA - Cleaners Sink

## 28-09
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-09-24 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
KALLIBRE-TRANSMIT-000004 | 6 | 0 | 0 | # 1373 | L.E.S.-TRANSMIT-000060 | 2 | 0 | KPTG-TRANSMIT-004149
1 | 6 | 0 | 0 |  | 1 | 2 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
Jangho-TRANSMIT-000358 | 2026-09-17 | 1 | 1 | Jaanbir to clarify
4
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757
KPTG-WTRAN-002921 | Final (WF-001351) DISTLV¦ SAMPLE & TECH DATA I CONSULTANT REVIEW ¦ HYD ¦ G&CHyd-TRANSMIT-000030 - HYD TECH DATA - Cleaners Sink

## 24-09
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-09-24 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
Jaycon-TRANSMIT-000002 | 17 | 0 | 0 | rejected : KPTG-TRANSMIT-004121 | WAM-TRANSMIT-000872 | 4 | 0 | ejected KPTG-TRANSMIT-004108
G&CHyd-TRANSMIT-000037 | 0 | 1 | 0 | WF-001395 | ccair-TRANSMIT-000022 | 1 | 0 | KPTG-TRANSMIT-004122
Jangho-TRANSMIT-000363 | 0 | 1 | 0 | rejected: KPTG-TRANSMIT-004125 | Jangho-TRANSMIT-000363 | 1 | 0 | REJECTED: KPTG-TRANSMIT-004125
WAM-TRANSMIT-000873 | 4 | 0 | 0 | #1385, WF-001400 | L.E.S.-TRANSMIT-000048 | 10 | 0 | KPTG-TRANSMIT-004123
G&CHyd-TRANSMIT-000036 | 0 | 2 | 0 | WF-001397 | L.E.S.-TRANSMIT-000038 | 1 | 0 | KPTG-TRANSMIT-004126
L.E.S.-TRANSMIT-000085 | 6 | 0 | 0 | Rejected - Incorrect trade partner code | ccair-TRANSMIT-000020 | 1 | 0 | KPTG-TRANSMIT-004127
L.E.S.-TRANSMIT-000086 | 8 | 0 | 0 | #1360 | L.E.S.-TRANSMIT-000085 | 6 | 0 | REJECTED: KPTG-TRANSMIT-004117
ZLH P/L-TRANSMIT-000001 | 0 | 3 | 0 | rejected: KPTG-TRANSMIT-004129 | Axiom-TRANSMIT-000026 | 16 | 0 | KPTG-TRANSMIT-004105
[5 empty] | Axiom-TRANSMIT-000030 | 14 | 0 | KPTG-TRANSMIT-004109
[5 empty] | WAM-TRANSMIT-000850 | 12 | 0 | KPTG-TRANSMIT-004099
[5 empty] | WAM-TRANSMIT-000863 | 1 | 0 | KPTG-TRANSMIT-004099
[5 empty] | Jaycon-TRANSMIT-000002 | 17 | 0 | rejected : KPTG-TRANSMIT-004121
[5 empty] | ZLH P/L-TRANSMIT-000001 | 3 | 0 | rejected: KPTG-TRANSMIT-004129
[5 empty] | WAM-TRANSMIT-000864 | 8 | 0 | KPTG-TRANSMIT-004102
[5 empty] | G&CHyd-TRANSMIT-000030 | 4 | 0 | KPTG-TRANSMIT-004137
[5 empty] | JANGHO-FAC-SMP-026,27,28,29,30,31,41,77,78,104 - FACADE SAMPLES | 5 | 0 | KPTG-TRANSMIT-004139
[5 empty] | L.E.S.-TRANSMIT-000068 | 4 | 0 | KPTG-TRANSMIT-004142
[5 empty] | G&CHyd-TRANSMIT-000018 WF-1220 | 1 | 0 | KPTG-TRANSMIT-004144
[5 empty] | L.E.S.-TRANSMIT-000069 | 8 | 0 | KPTG-TRANSMIT-004146
[5 empty] | WAM-TRANSMIT-000871 | 4 | 0 | KPTG-TRANSMIT-004130
[5 empty] | RDSBIM-TRANSMIT-000113 | 4 | 0 | KPTG-TRANSMIT-004133
[5 empty] | PCForm-TRANSMIT-000314 | 2 | 0 | KPTG-TRANSMIT-004135
8 | 35 | 7 | 0 |  | 22 | 127 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
Jangho-TRANSMIT-000358 | 2026-09-17 | 1 | 1 | Jaanbir to clarify
4
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757
KPTG-WTRAN-002921 | Final (WF-001351) DISTLV¦ SAMPLE & TECH DATA I CONSULTANT REVIEW ¦ HYD ¦ G&CHyd-TRANSMIT-000030 - HYD TECH DATA - Cleaners Sink

## 23-09
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-09-23 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
RDSBIM-TRANSMIT-000113 | 4 | 0 | 0 | REPLACED BY RDSBIM-TRANSMIT-000114 | L.E.S.-TRANSMIT-000075 - #1323 | 4 | 0 | KPTG-TRANSMIT-004074
RDSBIM-TRANSMIT-000114 | 4 | 0 | 0 | # 1350, WF-001387 | WAM-TRANSMIT-000867 | 10 | 0 | KPTG-TRANSMIT-004083
L.E.S.-TRANSMIT-000082 | 78 | 0 | 0 | #1352, WF-001388 | Jangho-TRANSMIT-000343 acc 1346 | 39 | 0 | KPTG-TRANSMIT-004076
L.E.S.-TRANSMIT-000083 | 187 | 0 | 0 | # 1354, | RDSBIM-TRANSMIT-000110 | 6 | 0 | KPTG-TRANSMIT-004080
Jaycon-TRANSMIT-000001 | 0 | 17 | 0 | KPTG-IntCorr-001440 - john to clarify - WF-001393 | L.E.S.-TRANSMIT-000047 | 4 | 0 | KPTG-TRANSMIT-004086
Firesafe-TRANSMIT-000026 | 0 | 3 | 0 | WF-001389 | D&E-TRANSMIT-000019 | 1 | 0 | KPTG-TRANSMIT-004087
Axiom-TRANSMIT-000033 | 2 | 0 | 0 | REJECTED: KPTG-TRANSMIT-004096 | ccair-TRANSMIT-000034 | 1 | 0 | KPTG-TRANSMIT-004093
Axiom-TRANSMIT-000032 | 13 | 0 | 0 | REJECTED: KPTG-TRANSMIT-004097 | OveArup-TRANSMIT-000046 | 1 | 0 | KPTG-TRANSMIT-004089
Jangho-TRANSMIT-000361 | 18 | 0 | 0 | #1356, WF-001401 | RDSBIM-TRANSMIT-000113 | 4 | 0 | REPLACED BY RDSBIM-TRANSMIT-000114
ccair-TRANSMIT-000021 | 2 | 0 | 0 | #1347, WF-001385 | Axiom-TRANSMIT-000033 | 2 | 0 | REJECTED: KPTG-TRANSMIT-004096
ccair-TRANSMIT-000026 | 3 | 0 | 0 | #1347, WF-001385 | Axiom-TRANSMIT-000032 | 13 | 0 | REJECTED: KPTG-TRANSMIT-004097
WAM-TRANSMIT-000872 | 4 | 0 | 0 | process tomorrow - rejected KPTG-TRANSMIT-004108 | G&CHyd-TRANSMIT-000033 | 1 | 0 | REPLACED BY G&CHyd-TRANSMIT-000034
L.E.S.-TRANSMIT-000084 | 0 | 1 | 0 | process tomorrow - WF-001396
G&CHyd-TRANSMIT-000034 | 0 | 17 | 0 | process tomorrow
G&CHyd-TRANSMIT-000033 | 0 | 1 | 0 | REPLACED BY G&CHyd-TRANSMIT-000034
15 | 315 | 39 | 0 |  | 12 | 86 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
Jangho-TRANSMIT-000358 | 2026-09-17 | 1 | 1 | Jaanbir to clarify
PCForm-TRANSMIT-000329 | 2026-09-16 | 28 | 0 | Jarrod to clarify
WAM-TRANSMIT-000862 | 2026-09-11 | 27 | 0 | JOHN TO CLARIFY
4
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757

## 22-09
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-09-22 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
BIMF-TRANSMIT-000032 | 4 | 0 | 0 | #1345, WF-001381 | ccair-TRANSMIT-000026 - acc 1253 | 3 | 0 | KPTG-TRANSMIT-004064
G&CHyd-TRANSMIT-000035 | 0 | 12 | 0 | WF-001382 | Firesafe-TRANSMIT-000021 | 1 | 0 | KPTG-TRANSMIT-004065
L.E.S.-TRANSMIT-000081 | 0 | 1 | 0 | WF-001383 | WAM-TRANSMIT-000865 ACC 1309 | 3 | 0 | KPTG-TRANSMIT-004067
Jangho-TRANSMIT-000343 | 39 | 0 | 0 | #1346, WF-001386 | G&CHyd-TRANSMIT-000005 | 9 | 0 | KPTG-TRANSMIT-004070
[5 empty] | Jangho-TRANSMIT-000332 ACC 1203 | 21 | 0 | KPTG-TRANSMIT-004062
[5 empty] | L.E.S.-TRANSMIT-000070 | 1 | 0 | KPTG-TRANSMIT-004072
4 | 43 | 13 | 0 |  | 6 | 38 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
Jangho-TRANSMIT-000358 | 2026-09-17 | 1 | 1 | Jaanbir to clarify
PCForm-TRANSMIT-000329 | 2026-09-16 | 28 | 0 | Jarrod to clarify
WAM-TRANSMIT-000862 | 2026-09-11 | 27 | 0 | JOHN TO CLARIFY
4
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757

## 21-09
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-09-21 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
RDSBIM-TRANSMIT-000112 | 2 | 0 | 0 | #1339, WF-001377 | PCForm-TRANSMIT-000332 | 5 | 0 | KPTG-TRANSMIT-004046 | Y
L.E.S.-TRANSMIT-000079 | 6 | 0 | 0 | already processed and closed L.E.S. TRN # 72 | OveArup-TRANSMIT-000046 | 36 | 0 | KPTG-TRANSMIT-004044 | y
L.E.S.-TRANSMIT-000079 | 2 | 0 | 0 | #1341, WF-001378 | Jangho-TRANSMIT-000338 | 15 | 0 | KPTG-TRANSMIT-004042 | y
L.E.S.-TRANSMIT-000078 | 9 | 0 | 0 | #1343, WF-001379 | RDSBIM-TRANSMIT-000111 | 8 | 0 | KPTG-TRANSMIT-004048 | y
RDSBIM-TRANSMIT-000111 | 8 | 0 | 0 | # 1337, WF-001376 | Jangho-TRANSMIT-000339 | 12 | 0 | KPTG-TRANSMIT-004040 | y
RDSBIM-TRANSMIT-000110 | 6 | 0 | 0 | #1335, WF-001380 | INGEN3D-TRANSMIT-000271 | 2 | 0 | KPTG-TRANSMIT-004053 | NA
[5 empty] | ccair-TRANSMIT-000023 | 1 | 0 | KPTG-TRANSMIT-004055 | NA
[5 empty] | L.E.S.-TRANSMIT-000005 | 3 | 0 | KPTG-TRANSMIT-004057 | NA
[5 empty] | L.E.S.-TRANSMIT-000076 | 9 | 0 | rejected: KPTG-TRANSMIT-004030 | NA
[5 empty] | BIMF-TRANSMIT-000031 | 2 | 0 | already processed rcvd BIMF Trn#28 | NA
[5 empty] | L.E.S.-TRANSMIT-000079 | 6 | 0 | already processed and closed L.E.S. TRN # 72 | NA
[5 empty] | WAM-TRANSMIT-000862 | 27 | 0 | KPTG-TRANSMIT-004059 rejected | NA
6 | 33 | 0 | 0 |  | 12 | 126 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
Jangho-TRANSMIT-000358 | 2026-09-17 | 1 | 1 | Jaanbir to clarify
PCForm-TRANSMIT-000329 | 2026-09-16 | 28 | 0 | Jarrod to clarify
WAM-TRANSMIT-000862 | 2026-09-11 | 27 | 0 | JOHN TO CLARIFY
4
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757
L.E.S.-TRANSMIT-000070
Jangho-TRANSMIT-000332 | 21 | 0
ccair-TRANSMIT-000023 | CLARIFY IF RQRD

## 18-09
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-09-18 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
RDSBIM-TRANSMIT-000108 | 4 | 0 | 0 | Replaced by 109 | L.E.S.-TRANSMIT-000057 | 6 | 0 | KPTG-TRANSMIT-004009 | y
RDSBIM-TRANSMIT-000109 | 4 | 0 | 0 | # 1311,WF-001363 | KALLIBRE-TRANSMIT-000001 | 25 | 0 | KPTG-TRANSMIT-004017 | y
WAM-TRANSMIT-000869 | 21 | 0 | 0 | #1321, WF-001370 | RDSBIM-TRANSMIT-000100 | 2 | 0 | KPTG-TRANSMIT-004015 | no
BIMF-TRANSMIT-000030 | 4 | 0 | 0 | #1316, WF-001362 | RDSBIM-TRANSMIT-000107 | 1 | 0 | KPTG-TRANSMIT-004013 | y
L.E.S.-TRANSMIT-000072 | 6 | 0 | 0 | #1325, WF-001369 | RDSBIM-TRANSMIT-000109 | 4 | 0 | KPTG-TRANSMIT-004019 | y
L.E.S.-TRANSMIT-000073 | 8 | 0 | 0 | #1327, WF-001371 | JANGHO-FAC-SMP-026,27,28,29,30,31,41,77,78,104 Final (WF-001325) | 5 | 0 | KPTG-TRANSMIT-004026 | na
BIMF-TRANSMIT-000031 | 2 | 0 | 0 | already processed rcvd BIMF Trn#28 | Jangho-TRANSMIT-000331 | 1 | 0 | KPTG-TRANSMIT-004027 | na
L.E.S.-TRANSMIT-000075 | 4 | 0 | 0 | #1323, WF-001367 | Jangho-TRANSMIT-000330 | 1 | 0 | KPTG-TRANSMIT-004029 | na
L.E.S.-TRANSMIT-000076 | 9 | 0 | 0 | rejected: KPTG-TRANSMIT-004030 | PCForm-TRANSMIT-000330 - Lvl 1 | 5 | 0 | KPTG-TRANSMIT-004022 | Y
L.E.S.-TRANSMIT-000077 | 2 | 0 | 0 | #1331, WF-001373 | PCForm-TRANSMIT-000330 - Lvl 2 | 5 | 0 | KPTG-TRANSMIT-004022 | Y
WAM-TRANSMIT-000870 | 2 | 0 | 0 | #1321, WF-001370 | PCForm-TRANSMIT-000330 - Lvl 4 | 5 | 0 | KPTG-TRANSMIT-004022 | Y
PCForm-TRANSMIT-000332 | 5 | 0 | 0 | #1333, WF-001375 | RDSBIM-TRANSMIT-000108 | 4 | 0 | Replaced by 109 | y
WAM-TRANSMIT-000871 | 4 | 0 | 0 | #1329, WF-001372
KALLIBRE-TRANSMIT-000003 | 10 | 0 | 0 | #1320, WF-001374
14 | 85 | 0 | 0 |  | 12 | 64 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
Jangho-TRANSMIT-000358 | 2026-09-17 | 1 | 1 | Jaanbir to clarify
PCForm-TRANSMIT-000329 | 2026-09-16 | 28 | 28 | Jarrod to clarify
WAM-TRANSMIT-000862 | 2026-09-11 | 27 | 27 | JOHN TO CLARIFY
59
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757

## 17-09
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-09-17 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
G&CHyd-TRANSMIT-000011 - client | 0 | 1 | 0 | WF-001353 | WF-001230 - G&CHyd-TRANSMIT-000017 | 1 | 0 | Received revised doc - G&CHyd-TRANSMIT-000031
L.E.S.-TRANSMIT-000070 - B1 ARGO-1200 [A] | 0 | 1 | 0 | WF-001354 | WF-001328 - L.E.S.-TRANSMIT-000070 | 1 | 0 | TERMINATED AND REISSUED - WF-1354
RDSBIM-TRANSMIT-000107 | 1 | 0 | 0 | # 1305, WF-001357 | RDSBIM-TRANSMIT-000106 | 6 | 0 | KPTG-TRANSMIT-003985 | y
WAM-TRANSMIT-000868 | 0 | 1 | 0 | WF-001361 | L.E.S.-TRANSMIT-000065 | 4 | 0 | KPTG-TRANSMIT-003991
ccair-TRANSMIT-000034 | 0 | 1 | 0 | WF-001360 | L.E.S.-TRANSMIT-000066 | 2 | 0 | KPTG-TRANSMIT-003989
WAM-TRANSMIT-000867 | 10 | 0 | 0 | # 1307, WF-001355 | L.E.S.-TRANSMIT-000056 | 1 | 0 | KPTG-TRANSMIT-003988
PCForm-TRANSMIT-000330 - Lvl 1 | 5 | 0 | 0 | # 1314 | Firesafe-TRANSMIT-000019 | 2 | 0 | KPTG-TRANSMIT-003987
PCForm-TRANSMIT-000330 - Lvl 2 | 5 | 0 | 0 | # 1313 | PCForm-TRANSMIT-000306 | 5 | 0 | KPTG-TRANSMIT-004007
PCForm-TRANSMIT-000330 - Lvl 4 | 5 | 0 | 0 | # 1312 | L.E.S.-TRANSMIT-000061 | 5 | 0 | KPTG-TRANSMIT-003995
Jangho-TRANSMIT-000355 | 0 | 1 | 0 | replaced by Jangho-TRANSMIT-000357 | BIMF-TRANSMIT-000026 | 2 | 0 | KPTG-TRANSMIT-003996
Jangho-TRANSMIT-000357 | 0 | 1 | 0 | WF-001358 | L.E.S.-TRANSMIT-000062 | 8 | 0 | KPTG-TRANSMIT-003993
Jangho-TRANSMIT-000356 | 0 | 1 | 0 | replaced by Jangho-TRANSMIT-000357 | INGEN3D-TRANSMIT-000270 | 2 | 0 | KPTG-TRANSMIT-003998
WAM-TRANSMIT-000865 | 3 | 0 | 0 | #1309 | INGEN3D-TRANSMIT-000269 | 1 | 0 | KPTG-TRANSMIT-004000
Jangho-TRANSMIT-000358 | 0 | 1 | 1 | KPTG-IntCorr-001402 - Jaan to confirm | INGEN3D-TRANSMIT-000268 | 2 | 0 | KPTG-TRANSMIT-004002
G&CHyd-TRANSMIT-000031 | 0 | 1 | 0 | WF-001359 | Jangho-TRANSMIT-000355 | 1 | 0 | replaced by Jangho-TRANSMIT-000357
[5 empty] | Jangho-TRANSMIT-000356 | 1 | 0 | replaced by Jangho-TRANSMIT-000357
15 | 29 | 9 | 1 |  | 16 | 44 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
4
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757

## 16-09
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-09-16 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
INGEN3D-TRANSMIT-000271 | 2 | 0 | 0 | WF-001335 | Civilex-TRANSMIT-000117 | 5 | 0 | KPTG-TRANSMIT-003969
RDSBIM-TRANSMIT-000103 | 4 | 0 | 0 | #1289, WF-001336 | Jangho-TRANSMIT-000350 | 1 | 0 | rejected: KPTG-TRANSMIT-003941
RDSBIM-TRANSMIT-000104 | 5 | 0 | 0 | #1292, WF-001340 | G&CHyd-TRANSMIT-000031 | 1 | 0 | rejected: KPTG-TRANSMIT-003967
RDSBIM-TRANSMIT-000105 | 5 | 0 | 0 | # 1293, WF-001341 | ccair-TRANSMIT-000030 | 1 | 0 | replaced by TRN#32
Jangho-TRANSMIT-000349 | 0 | 1 | 0 | WF-001344 | Firesafe-TRANSMIT-000025 | 3 | 0 | rejected: KPTG-TRANSMIT-003972
Jangho-TRANSMIT-000350 | 0 | 1 | 0 | rejected: KPTG-TRANSMIT-003941 | RDSBIM-TRANSMIT-000103 | 4 | 0 | KPTG-TRANSMIT-003965
Jangho-TRANSMIT-000351 | 0 | 1 | 0 | WF-001345 | Jangho-TRANSMIT-000354 | 1 | 0 | rejected: KPTG-TRANSMIT-003966
Jangho-TRANSMIT-000352 | 0 | 1 | 0 | WF-001346 | WAM-TRANSMIT-000854 | 26 | 0 | KPTG-TRANSMIT-003963
Jangho-TRANSMIT-000354 | 0 | 1 | 0 | rejected: KPTG-TRANSMIT-003966 | WAM-TRANSMIT-000859 | 9 | 0 | KPTG-TRANSMIT-003961
G&CHyd-TRANSMIT-000031 | 0 | 1 | 0 | rejected: KPTG-TRANSMIT-003967 | Jangho-TRANSMIT-000343 | 119 | 0 | KPTG-TRANSMIT-003946
G&CHyd-TRANSMIT-000030 | 0 | 4 | 0 | WF-001351
PCForm-TRANSMIT-000329 | 28 | 0 | 28 | KPTG-IntCorr-001395 - clarification requested
ccair-TRANSMIT-000032 | 1 | 0 | 0 | #1297, WF-001347
WAM-TRANSMIT-000866 | 0 | 1 | 0 | WF-001352
RDSBIM-TRANSMIT-000106 | 6 | 0 | 0 | # 1298,
BIMF-TRANSMIT-000029 | 4 | 0 | 0 | # 1302, WF-001350
Firesafe-TRANSMIT-000025 | 0 | 3 | 0 | rejected: KPTG-TRANSMIT-003972
WAM-TRANSMIT-000864 | 8 | 0 | 0 | # 1300, WF-001348
18 | 63 | 14 | 28 |  | 10 | 170 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
3
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757

## 15-09
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-09-15 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
INGEN3D-TRANSMIT-000271 | 2 | 0 | 0 | WF-001335 | PCForm-TRANSMIT-000311 - LVL 7 | 5 | 0 | KPTG-TRANSMIT-003921
RDSBIM-TRANSMIT-000103 | 4 | 0 | 0 | #1289, WF-001336 | PCForm-TRANSMIT-000311 - LVL 8, 9 | 6 | 0 | KPTG-TRANSMIT-003924
RDSBIM-TRANSMIT-000104 | 5 | 0 | 0 | #1292, WF-001340 | PCForm-TRANSMIT-000311 - LVL 10 | 5 | 0 | KPTG-TRANSMIT-003927
RDSBIM-TRANSMIT-000105 | 5 | 0 | 0 | # 1293, WF-001341 | ArcadiaL-TRANSMIT-000009 | 7 | 0 | KPTG-TRANSMIT-003931
ccair-TRANSMIT-000031 | 7 | 0 | 0 | #1294, WF-001342 | Jangho-TRANSMIT-000342 | 1 | 0 | KPTG-TRANSMIT-003928
L.E.S.-TRANSMIT-000064 | 0 | 1 | 0 | WF-001343 | L.E.S.-TRANSMIT-000048 | 8 | 0 | KPTG-TRANSMIT-003929
Jangho-TRANSMIT-000349 | 0 | 1 | 0 | WF-001344 | L.E.S.-TRANSMIT-000064 | 1 | 0 | WF-001343
Jangho-TRANSMIT-000350 | 0 | 1 | 0 | rejected: KPTG-TRANSMIT-003941 | RDSBIM-TRANSMIT-000090 | 5 | 0 | KPTG-TRANSMIT-003944
Jangho-TRANSMIT-000351 | 0 | 1 | 0 | WF-001345 | RDSBIM-TRANSMIT-000101 | 4 | 0 | KPTG-TRANSMIT-003949
Jangho-TRANSMIT-000352 | 0 | 1 | 0 | WF-001346 | RDSBIM-TRANSMIT-000102 | 2 | 0 | KPTG-TRANSMIT-003951
[5 empty] | Jangho-TRANSMIT-000350 | 1 | 0 | rejected: KPTG-TRANSMIT-003941
[5 empty] | RDSBIM-TRANSMIT-000091 | 5 | 0 | KPTG-TRANSMIT-003947
10 | 23 | 5 | 0 |  | 12 | 50 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
3
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757

## 10-09
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-09-10 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
Axiom-TRANSMIT-000030 | 14 | 0 | 0 | # 1262, WF-001319 | Jangho-TRANSMIT-000304 | 18 | 0 | KPTG-TRANSMIT-003885
DECA-ST-SMP-004, DECA-ST-SMP-005 | 0 | 2 | 0 | WF-001323 | WAM-TRANSMIT-000851 | 56 | 0 | KPTG-TRANSMIT-003893
RDSBIM-TRANSMIT-000100 | 2 | 0 | 0 | #1264, WF-001324 | RDSBIM-TRANSMIT-000092 | 1 | 0 | KPTG-TRANSMIT-003894
JANGHO-FAC-SMP-026,27,28,29,30,31,41,77,78,104 | 0 | 10 | 0 | WF-001325 | Jangho-TRANSMIT-000071 | 1 | 0 | KPTG-TRANSMIT-003895
INGEN3D-TRANSMIT-000268 | 2 | 0 | 0 | WF-001320 | WAM-TRANSMIT-000860 | 1 | 0 | RE-ISSUED TRN#861
INGEN3D-TRANSMIT-000269 | 1 | 0 | 0 | WF-001321
INGEN3D-TRANSMIT-000270 | 2 | 0 | 0 | WF-001322
ccair-TRANSMIT-000028 | 1 | 0 | 0 | #1266 , WF-001326
WAM-TRANSMIT-000860 | 1 | 0 | 0 | RE-ISSUED TRN#861
WAM-TRANSMIT-000860 | 2 | 0 | 0 | #1268, WF-001327
WAM-TRANSMIT-000861 | 1 | 0 | 0 | #1268, WF-001327
L.E.S.-TRANSMIT-000070 | 0 | 1 | 0 | WF-001328
12 | 26 | 13 | 0 |  | 5 | 77 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
3
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757

## 09-09
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-09-09 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
OveArup-TRANSMIT-000046 | 36 | 0 | 0 | #1260, WF-001313 | PCForm-TRANSMIT-000303 | 4 | 0 | KPTG-TRANSMIT-003851
OveArup-TRANSMIT-000046 | 0 | 1 | 0 | WF-001314 | Jangho-TRANSMIT-000333 | 81 | 0 | KPTG-TRANSMIT-003849
Diadem-TRANSMIT-000003 | 0 | 1 | 0 | KPTG-TRANSMIT-003880 rejected | WAM-TRANSMIT-000848 | 36 | 0 | KPTG-TRANSMIT-003845
L.E.S.-TRANSMIT-000069 | 0 | 8 | 0 | WF-001316 | PCForm-TRANSMIT-000311 - LVL 6 | 5 | 0 | KPTG-TRANSMIT-003860
L.E.S.-TRANSMIT-000068 | 0 | 4 | 0 | WF-001315 | INGEN3D-TRANSMIT-000260 | 2 | 0 | KPTG-TRANSMIT-003868
PCForm-TRANSMIT-000325 | 0 | 1 | 0 | WF-001311 | INGEN3D-TRANSMIT-000258 | 1 | 0 | KPTG-TRANSMIT-003870
L.E.S.-TRANSMIT-000020 | 0 | 9 | 0 | WF-001317 | INGEN3D-TRANSMIT-000256 | 2 | 0 | KPTG-TRANSMIT-003872
Axiom-TRANSMIT-000029 | 16 | 0 | 0 | REJECTED: KPTG-TRANSMIT-003850 | Jangho-TRANSMIT-000334 | 44 | 0 | KPTG-TRANSMIT-003849
Traf Grp-TRANSMIT-000013 | 4 | 0 | 0 | REJECTED: KPTG-TRANSMIT-003848 | RDSBIM-TRANSMIT-000096 | 4 | 0 | KPTG-TRANSMIT-003878
[5 empty] | RDSBIM-TRANSMIT-000099 | 1 | 0 | KPTG-TRANSMIT-003878
[5 empty] | G&CHyd-TRANSMIT-000025 | 2 | 0 | KPTG-TRANSMIT-003874
[5 empty] | G&CHyd-TRANSMIT-000026 | 2 | 0 | KPTG-TRANSMIT-003876
[5 empty] | G&CHyd-TRANSMIT-000017 | 2 | 0 | KPTG-TRANSMIT-003866
[5 empty] | G&CHyd-TRANSMIT-000016 | 1 | 0 | KPTG-TRANSMIT-003864
[5 empty] | PCForm-TRANSMIT-000311 - LVL 5 | 5 | 0 | KPTG-TRANSMIT-003862
[5 empty] | Axiom-TRANSMIT-000029 | 16 | 0 | REJECTED: KPTG-TRANSMIT-003850
[5 empty] | Traf Grp-TRANSMIT-000013 | 4 | 0 | REJECTED: KPTG-TRANSMIT-003848
[5 empty] | Diadem-TRANSMIT-000003 | 1 | 0 | KPTG-TRANSMIT-003880 rejected
9 | 56 | 24 | 0 |  | 18 | 213 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
3
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757

## 08-09
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-09-08 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
Firesafe-TRANSMIT-000021 | 0 | 1 | 0 | WF-001304 | L.E.S.-TRANSMIT-000060 | 15 | 0 | KPTG-TRANSMIT-003825
KALLIBRE-TRANSMIT-000002 | 4 | 0 | 0 | #1251, WF-001305 | Jangho-TRANSMIT-000259 | 1 | 0 | KPTG-TRANSMIT-003827
RDSBIM-TRANSMIT-000099 | 1 | 0 | 0 | # 1252, submitted along with RDS-96 - WF-001306 | Jangho-TRANSMIT-000260 | 1 | 0 | KPTG-TRANSMIT-003830
ccair-TRANSMIT-000026 | 3 | 0 | 0 | #1253, WF-001307 | Jangho-TRANSMIT-000311 | 1 | 0 | KPTG-TRANSMIT-003832
Axiom-TRANSMIT-000026 | 16 | 0 | 0 | #1255, WF-001308 | NUBRIK-FA-SMP-002 (WF-001148) | 1 | 0 | KPTG-TRANSMIT-003834
PCForm-TRANSMIT-000323 | 0 | 1 | 0 | rejected: KPTG-TRANSMIT-003840 | NUBRIK-FA-SMP-004 (WF-001150) | 1 | 0 | KPTG-TRANSMIT-003835
WAM-TRANSMIT-000859 | 9 | 0 | 0 | #1257, | NUBRIK-FA-SMP-003 (WF-001149) | 1 | 0 | KPTG-TRANSMIT-003836
Jangho-TRANSMIT-000345 | 0 | 1 | 0 | rejected: KPTG-TRANSMIT-003844 | Axiom-TRANSMIT-000024 | 1 | 0 | KPTG-TRANSMIT-003837
L.E.S.-TRANSMIT-000067 | 0 | 4 | 0 | KPTG-TRANSMIT-003843 REJECTED | AUS-ST-SMP-004 (WF-000820) | 1 | 0 | KPTG-TRANSMIT-003839
[5 empty] | PCForm-TRANSMIT-000323 | 1 | 0 | rejected: KPTG-TRANSMIT-003840
[5 empty] | Teams message - Nicholas(WF-001245) | 2 | 0 | KPTG-TRANSMIT-003841
[5 empty] | Jangho-TRANSMIT-000345 | 1 | 0 | rejected: KPTG-TRANSMIT-003844
[5 empty] | L.E.S.-TRANSMIT-000067 | 4 | 0 | KPTG-TRANSMIT-003843 REJECTED
9 | 33 | 7 | 0 |  | 13 | 31 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
3
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757

## 07-09
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-09-07 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
RDSBIM-TRANSMIT-000096 | 4 | 0 | 0 | #1240, WF-001301 | WAM-TRANSMIT-000852 | 1 | 0 | KPTG-TRANSMIT-003818
RDSBIM-TRANSMIT-000097 | 2 | 0 | 0 | #1241, WF-001302 | WAM-TRANSMIT-000858 | 11 | 0 | KPTG-TRANSMIT-003819
Jangho-TRANSMIT-000341 | 0 | 1 | 0 | WF-001295 | ccair-TRANSMIT-000025 | 3 | 0 | rejected: KPTG-TRANSMIT-003823
Jangho-TRANSMIT-000342 | 0 | 1 | 0 | WF-001296 | Jangho-TRANSMIT-000344 | 7 | 0 | KPTG-TRANSMIT-003822 rejected
Jangho-TRANSMIT-000343 | 119 | 0 | 0 | # 1244, WF-001298 | Jangho-TRANSMIT-000333, 334
Jangho-TRANSMIT-000344 | 7 | 0 | 0 | KPTG-TRANSMIT-003822
ccair-TRANSMIT-000025 | 3 | 0 | 0 | rejected: KPTG-TRANSMIT-003823
RDSBIM-TRANSMIT-000098 | 4 | 0 | 0 | #1247, WF-001303
8 | 139 | 2 | 0 |  | 5 | 22 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
3
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757

## 04-09
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-09-04 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
Bradley mail - FRV 34803 report | 0 | 1 | 0 | registered and forwarded to all parties - KPTG-TRANSMIT-003792 | Bradley mail - FRV 34803 report | 1 | 0 | registered and forwarded to all parties - KPTG-TRANSMIT-003792
ccair-TRANSMIT-000023 | 0 | 1 | 0 | WF-001289 | INGEN3D-TRANSMIT-000251, INGEN3D-TRANSMIT-000266 | 15 | 0 | KPTG-TRANSMIT-003801
G&CHyd-TRANSMIT-000026 | 0 | 2 | 0 | WF-001290 | RDSBIM-TRANSMIT-000094 | 2 | 0 | KPTG-TRANSMIT-003800
ccair-TRANSMIT-000022 | 0 | 1 | 0 | WF-001291 | RDSBIM-TRANSMIT-000095 | 5 | 0 | KPTG-TRANSMIT-003803
G&CHyd-TRANSMIT-000024 | 0 | 1 | 0 | WF-001288 | L.E.S.-TRANSMIT-000059 | 3 | 0 | KPTG-TRANSMIT-003805
G&CHyd-TRANSMIT-000025 | 0 | 2 | 0 | WF-001287 | Jangho-TRANSMIT-000298 | 20 | 0 | KPTG-TRANSMIT-003795
KALLIBRE-TRANSMIT-000001 | 25 | 0 | 0 | #1234, WF-001292 | Firesafe-TRANSMIT-000020 | 1 | 0 | REJECTED : KPTG-TRANSMIT-003799
Jangho-TRANSMIT-000338 | 15 | 0 | 15 | # 1246, WF-001299
Jangho-TRANSMIT-000339 | 12 | 0 | 12 | # 1245, WF-001297
Jangho-TRANSMIT-000340 | 0 | 1 | 0 | WF-001293
Firesafe-TRANSMIT-000019 | 2 | 0 | 0 | #1232, WF-001294
Firesafe-TRANSMIT-000020 | 0 | 1 | 0 | REJECTED : KPTG-TRANSMIT-003799
12 | 54 | 10 | 27 |  | 7 | 47 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
3
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757

## 03-09
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-09-03 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
Jangho-TRANSMIT-000329 | 0 | 1 | 0 | WF-001280 | DECA-ST-SMP-003 | 1 | 0 | KPTG-TRANSMIT-003773
RDSBIM-TRANSMIT-000094 | 2 | 0 | 0 | # 1222, WF-001281 | BIMF-TRANSMIT-000023 | 1 | 0 | KPTG-TRANSMIT-003775
WAM-TRANSMIT-000858 | 11 | 0 | 0 | # 1224, WF-001282 | BIMF-TRANSMIT-000024 | 10 | 0 | KPTG-TRANSMIT-003776
L.E.S.-TRANSMIT-000065 | 4 | 0 | 0 | # 1226, WF-001283 | BIMF-TRANSMIT-000022 | 3 | 0 | KPTG-TRANSMIT-003774
INGEN3D-TRANSMIT-000249 | 1 | 0 | 0 | WF-001284 | Firesafe-TRANSMIT-000017 | 1 | 0 | KPTG-TRANSMIT-003786
RDSBIM-TRANSMIT-000095 | 5 | 0 | 0 | # 1229, WF-001285 | ccair-TRANSMIT-000021 - IFA | 2 | 0 | KPTG-TRANSMIT-003790
L.E.S.-TRANSMIT-000066 | 2 | 0 | 2 | KPTG-IntCorr-001328 John to Confirm - # 1230 | BIMF-TRANSMIT-000025 | 2 | 0 | KPTG-TRANSMIT-003777
[5 empty] | ccair-TRANSMIT-000021- IFC | 1 | 0 | KPTG-TRANSMIT-003788
[5 empty] | INGEN3D-TRANSMIT-000249 | 1 | 0 | KPTG-TRANSMIT-003780
7 | 25 | 1 | 2 |  | 9 | 22 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
3
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
Jangho-TRANSMIT-000298
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757

## 02-09
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-09-02 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
WAM-TRANSMIT-000857 | 17 | 0 | 0 | rejected: KPTG-TRANSMIT-003754 | Jangho-TRANSMIT-000287 | 1 | 0 | VOIDED by Jaanbir, Drawings terminated from DC w/flow
L.E.S.-TRANSMIT-000064 | 0 | 1 | 0 | WF-001278 | EFWC-TRANSMIT-000004 | 4 | 0 | KPTG-TRANSMIT-003755
WAM-TRANSMIT-000856 | 1 | 0 | 0 | rejected: KPTG-TRANSMIT-003771 | RDSBIM-TRANSMIT-000083 | 7 | 0 | KPTG-TRANSMIT-003768
[5 empty] | WAM-TRANSMIT-000857 | 17 | 0 | rejected: KPTG-TRANSMIT-003754
[5 empty] | Jangho-TRANSMIT-000328 | 1 | 0 | KPTG-TRANSMIT-003767
[5 empty] | Jangho-TRANSMIT-000324 | 1 | 0 | KPTG-TRANSMIT-003766
[5 empty] | Jangho-TRANSMIT-000323 | 1 | 0 | KPTG-TRANSMIT-003765
[5 empty] | Jangho-TRANSMIT-000318 | 1 | 0 | KPTG-TRANSMIT-003764
[5 empty] | Jangho-TRANSMIT-000317 | 1 | 0 | KPTG-TRANSMIT-003763
[5 empty] | Firesafe-TRANSMIT-000018 | 1 | 0 | KPTG-TRANSMIT-003760
[5 empty] | L.E.S.-TRANSMIT-000058 | 3 | 0 | KPTG-TRANSMIT-003759
[5 empty] | RDSBIM-TRANSMIT-000093 | 6 | 0 | KPTG-TRANSMIT-003761
[5 empty] | Jangho-TRANSMIT-000292 | 1 | 0 | VOIDED by Jaanbir, Drawings terminated from DC w/flow
3 | 18 | 1 | 0 |  | 13 | 45 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
3
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp
Jangho-TRANSMIT-000298
G&CHyd-TRANSMIT-000009 | 1 | 0 | KPTG-TRANSMIT-003757

## 01-09
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-09-01 | [5 empty] | Project: | DISTLV
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000314 | 2 | 0 | 0 | #1217, WF-001279 | Jangho-TRANSMIT-000210 | 1 | 0 | KPTG-TRANSMIT-003740
DECA-ST-SMP-003 | 0 | 1 | 0 | WF-001275 | NGEN3D-TRANSMIT-000255 | 8 | 0 | KPTG-TRANSMIT-003736
Axiom-TRANSMIT-000024 | 0 | 1 | 0 | WF-001274 | INGEN3D-TRANSMIT-000263 | 9 | 0 | KPTG-TRANSMIT-003738
RDSBIM-TRANSMIT-000093 | 6 | 0 | 0 | #1214, WF-001277 | BIMF-TRANSMIT-000021 | 1 | 0 | KPTG-TRANSMIT-003742
L.E.S.-TRANSMIT-000027 | 0 | 9 | 0 | WF-001276 | RDSBIM-TRANSMIT-000087 | 4 | 0 | KPTG-TRANSMIT-003744
[5 empty] | WAM-TRANSMIT-000847 | 1 | 0 | KPTG-TRANSMIT-003746
[5 empty] | WAM-TRANSMIT-000855 | 1 | 0 | KPTG-TRANSMIT-003749
5 | 8 | 11 | 0 |  | 7 | 25 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
PCForm-TRANSMIT-000278 | 2026-07-20 | 2 | 2 | Jarrod to clarify
Jangho-TRANSMIT-000295 | 2026-08-03 | 1 | 1 | Jaanbir to clarify
3
KPTG-WTRAN-002318 - Jangho-TRANSMIT-000190 | 1 | 0 | hold - no client stamp KPTG-IntCorr-001197
KPTG-WTRAN-002322 | 1 | 0 | KPTG-IntCorr-001198 hold no client stamp