## 01-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-01 | [5 empty] | Project: | M3S6
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
SMEPS-TRANSMIT-000031 | 2 | 0 | 0 | #1129 | Civilex-TRANSMIT-000014 | 3 | 0 | KPTG-TRANSMIT-001729
INGEN3D-TRANSMIT-000020 | 143 | 0 | 0 | Rejected | Bianco-TRANSMIT-000001 | 2 | 0 | KPTG-TRANSMIT-001731
[5 empty] | RDSDG-TRANSMIT-000013 | 1 | 0 | KPTG-TRANSMIT-001733
[5 empty] | SMEPS-TRANSMIT-000029 | 1 | 0 | KPTG-TRANSMIT-001734
[5 empty] | INGEN3D-TRANSMIT-000020 | 143 | 0 | KPTG-SADV-001023
[5 empty] | Aurecon-TRANSMIT-000161 | 12 | 0 | KPTG-TRANSMIT-001700
[5 empty] | SMEPS-TRANSMIT-000027 | 3 | 0 | KPTG-TRANSMIT-001715
[5 empty] | SMEPS-TRANSMIT-000028 | 1 | 0 | KPTG-TRANSMIT-001717
Total | 145 | 0 | 0 |  | Total | 166 | 0
Pending Transmittals
Transmittals | Date | No. of Documents | Pending Number of Documents | Remarks | Report - send again 01-10-2026

## 02-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-02 | [5 empty] | Project: | M3S6
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
NXT-TRANSMIT-000597 | 0 | 1 | 0 | Distribution only. | KPTG-TRANSMIT-000323 | 17 | 0 | KPTG-TRANSMIT-001738
STRBCK-TRANSMIT-000012 | 1 | 0 | 0 | Rejected | NXT-TRANSMIT-000563 | 5 | 0 | KPTG-TRANSMIT-001739
STRBCK-TRANSMIT-000013 | 2 | 0 | 0 | Rejected | NXT-TRANSMIT-000570 | 22 | 0 | KPTG-TRANSMIT-001740
RDSBIM-TRANSMIT-000030 | 1 | 0 | 0 | #1136 | ACCCA-TRANSMIT-000030 | 2 | 0 | KPTG-TRANSMIT-001744
INGEN3D-TRANSMIT-000021 | 143 | 0 | 0 | Rejcted | NXT-TRANSMIT-000597 | 1 | 0 | KPTG-TRANSMIT-001726
ACCCA-TRANSMIT-000031 | 48 | 0 | 0 | WF -000374 | STRBCK-TRANSMIT-000012 | 1 | 0 | KPTG-TRANSMIT-001737
Baigents-TRANSMIT-000066 | 128 | 0 | 0 | #1137 | STRBCK-TRANSMIT-000013 | 2 | 0 | KPTG-TRANSMIT-001736
[5 empty] | INGEN3D-TRANSMIT-000021 | 143 | 0 | KPTG-TRANSMIT-001728
Total | 323 | 1 | 0 |  | Total | 193 | 0
Pending Transmittals
Transmittals | Date | No. of Documents | Pending Number of Documents | Remarks

## 05-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-05 | [5 empty] | Project: | M3S6
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
4DW-TRANSMIT-000114 | 7 | 0 | 0 | #1143 | ACCCA-TRANSMIT-000026 | 9 | 0 | KPTG-TRANSMIT-001753
PTA-TRANSMIT-000054 | 3 | 0 | 0 | #1145 | NXT-TRANSMIT-000593 | 1 | 0 | KPTG-TRANSMIT-001723
4DW-TRANSMIT-000115 | 21 | 0 | 0 | #1148 | TTW-TRANSMIT-000049 | 1 | 0 | KPTG-TRANSMIT-001767
RDSDG-TRANSMIT-000013 | 2 | 0 | 0 | #1151 | TTW-TRANSMIT-000050 | 1 | 0 | KPTG-TRANSMIT-001719
D&E-TRANSMIT-000070 | 103 | 0 | 0 | #1158 | NXT-TRANSMIT-000586 | 2 | 0 | KPTG-TRANSMIT-001714
SMEPS-TRANSMIT-000032 | 2 | 0 | 0 | # 1131 | Aurecon-TRANSMIT-000159 | 1 | 0 | KPTG-TRANSMIT-001676
TTW-TRANSMIT-000051 | 0 | 1 | 0 | #1133 | SMEPS-TRANSMIT-000026 | 1 | 0 | KPTG-TRANSMIT-001765
NXT-TRANSMIT-000593 | 1 | 0 | 0 | Rejected | RDSDG-TRANSMIT-000014 | 1 | 0 | KPTG-TRANSMIT-001759
NXT-TRANSMIT-000594 | 1 | 0 | 0 | WF - 000367 | Baigents-TRANSMIT-000056 | 34 | 0 | KPTG-TRANSMIT-001761
NXT-TRANSMIT-000596 | 1 | 0 | 0 | WF - 000368 | RDSDG-TRANSMIT-000012 | 1 | 0 | KPTG-TRANSMIT-001764
KPTG-TRANSMIT-001462 | 3 | 0 | 0 | #1134 | KPTG-TRANSMIT-001443 | 1 | 0 | KPTG-TRANSMIT-001768
Civilex-TRANSMIT-000015 | 3 | 0 | 0 | #1160 | KPTG-TRANSMIT-001462 | 3 | 0 | WF Restarted.
Civilex-TRANSMIT-000016 | 1 | 0 | 0 | #1162
Total | 148 | 1 | 0 |  | Total | 56 | 0
Pending Transmittals
Transmittals | Date | No. of Documents | Pending Number of Documents | Remarks

## 6-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-06 | [5 empty] | Project: | M3S6
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
4DW-TRANSMIT-000116 | 2 | 0 | 0 | #1166 | ACCCA-TRANSMIT-000031 | 4 | 44 | KPTG-TRANSMIT-001776
STRBCK-TRANSMIT-000014 | 0 | 2 | 0 | #1172 | RDSBIM-TRANSMIT-000031 | 1 | 0 | KPTG-TRANSMIT-001777
STRBCK-TRANSMIT-000015 | 0 | 1 | 0 | #1170 | Bee Eng-TRANSMIT-000002 | 29 | 0 | KPTG-TRANSMIT-001778
KBGA-TRANSMIT-000023 | 1 | 0 | 0 | #1170 | Bee Eng-TRANSMIT-000003 | 20 | 0 | KPTG-TRANSMIT-001779
KBGA-TRANSMIT-000022 | 0 | 0 | 0 | #1168 | Baigents-TRANSMIT-000057 | 20 | 0 | KPTG-TRANSMIT-001774
NXT-TRANSMIT-000600 | 1 | 0 | 0 | WF - 000378
RDSBIM-TRANSMIT-000031 | 1 | 0 | 0 | Rejected
Bee Eng-TRANSMIT-000002 | 29 | 0 | 0 | Rejected
Bee Eng-TRANSMIT-000003 | 20 | 0 | 0 | Rejected
Total | 54 | 3 | 0 |  | Total | 81 | 44
Pending Transmittals
Transmittals | Date | No. of Documents | Pending Number of Documents | Remarks

## 07-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-07 | [5 empty] | Project: | M3S6
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
SMEPS-TRANSMIT-000026 | 1 | 0 | 0 | #1176 | NXT-TRANSMIT-000603 | 25 | 0 | No longer in use.
NXT-TRANSMIT-000603 | 25 | 0 | 0 | No longer in use. | NXT-TRANSMIT-000606 | 25 | 0 | No longer in use.
NXT-TRANSMIT-000606 | 25 | 0 | 0 | No longer in use. | NXT-TRANSMIT-000618 | 1 | 0 | No longer in use.
NXT-TRANSMIT-000618 | 1 | 0 | 0 | No longer in use. | NXT-TRANSMIT-000616 | 1 | 0 | No longer in use.
NXT-TRANSMIT-000616 | 1 | 0 | 0 | No longer in use. | RDSBIM-TRANSMIT-000032 | 1 | 0 | KPTG-TRANSMIT-001780
NXT-TRANSMIT-000621 | 1 | 0 | 1 | KPTG-IntCorr-000685 | Aurecon-WTRAN-000038 | 3 | 0 | KPTG-TRANSMIT-001783
NXT-TRANSMIT-000622 | 3 | 0 | 0 | WF - 000384 | ACCCA-TRANSMIT-000032 | 18 | 0 | KPTG-TRANSMIT-001782
NXT-TRANSMIT-000624 | 29 | 0 | 0 | WF - 000385 | Lat-TRANSMIT-000031 | 2 | 0 | No Longer in Use
NXT-TRANSMIT-000625 | 0 | 1 | 0 | WF - 000386 | Lat-TRANSMIT-000032 | 2 | 0 | No Longer in Use
RDSBIM-TRANSMIT-000032 | 1 | 0 | 0 | Rejected | STRBCK-TRANSMIT-000007 | 2 | 0 | KPTG-TRANSMIT-001788
NXT-TRANSMIT-000601 | 1 | 0 | 1 | KPTG-IntCorr-000684 | SMEPS-TRANSMIT-000026 | 1 | 0 | KPTG-TRANSMIT-001791
Archacce-TRANSMIT-000004 | 1 | 0 | 1 | KPTG-IntCorr-000688
NXT-TRANSMIT-000602 | 1 | 0 | 0 | KPTG-IntCorr-000686
Baigents-TRANSMIT-000067 | 68 | 0 | 0 | #1178
Lat-TRANSMIT-000031 | 2 | 0 | 0 | No Longer in Use
Lat-TRANSMIT-000032 | 2 | 0 | 0 | No Longer in Use
ACCCA-TRANSMIT-000033 | 6 | 0 | 0 | WF-000387
ACCCA-TRANSMIT-000032 | 18 | 0 | 0 | Rejected
Total | 186 | 1 | 3 |  | Total | 81 | 0
Pending Transmittals
Transmittals | Date | No. of Documents | Pending Number of Documents | Remarks

## 08-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-08 | [5 empty] | Project: | M3S6
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
Lat-TRANSMIT-000034 | 3 | 0 | 0 | No longer in use. | Lat-TRANSMIT-000034 | 3 | 0 | No longer in use.
DCN-TRANSMIT-000025 | 2 | 0 | 0 | No longer in use. | DCN-TRANSMIT-000025 | 2 | 0 | No longer in use.
DCN-TRANSMIT-000026 | 2 | 0 | 0 | No longer in use. | DCN-TRANSMIT-000026 | 2 | 0 | No longer in use.
NXT-TRANSMIT-000623 | 23 | 0 | 23 | KPTG-IntCorr-000687 | SMEPS-TRANSMIT-000032 | 2 | 0 | KPTG-TRANSMIT-001801
INGEN3D-TRANSMIT-000022 | 127 | 0 | 0 | #1181 | SMEPS-TRANSMIT-000031 | 2 | 0 | KPTG-TRANSMIT-001799
INGEN3D-TRANSMIT-000022 | 11 | 0 | 0 | #1183 | NXT-TRANSMIT-000591 | 1 | 0 | KPTG-TRANSMIT-001795
Baigents-TRANSMIT-000068 | 4 | 0 | 0 | #1189 | KBGA-TRANSMIT-000020 | 1 | 0 | KPTG-TRANSMIT-001803
Baigents-TRANSMIT-000069 | 124 | 0 | 0 | #1191 | NXT-TRANSMIT-000571 | 1 | 0 | KPTG-TRANSMIT-001797
RDSBIM-TRANSMIT-000033 | 1 | 0 | 0 | #1181
Total | 297 | 0 |  |  |  | 14 | 0
Pending Transmittals
Transmittals | Date | No. of Documents | Pending Number of Documents | Remarks
NXT-TRANSMIT-000601 | 2026-10-07 | 1 | 1 | KPTG-IntCorr-000684
Archacce-TRANSMIT-000004 | 2026-10-07 | 1 | 1 | KPTG-IntCorr-000688
NXT-TRANSMIT-000602 | 2026-10-07 | 1 | 1 | KPTG-IntCorr-000686
NXT-TRANSMIT-000621 | 2026-10-07 | 1 | 1 | KPTG-IntCorr-000685

## 09-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-09 | [5 empty] | Project: | M3S6
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
NXT-TRANSMIT-000627 | 0 | 1 | 1 | KPTG-IntCorr-000696 | KPTG-TRANSMIT-001811 | 37 | 0 | KPTG-TRANSMIT-001812
KPTG-TRANSMIT-001811 | 37 | 0 | 0 | Only Dustribution | ACCCA-TRANSMIT-000029 | 8 | 0 | KPTG-TRANSMIT-001826
4DW-TRANSMIT-000118 | 1 | 0 | 0 | # 1197 | RDSDG-TRANSMIT-000013 | 2 | 0 | KPTG-TRANSMIT-001828
RDSBIM-TRANSMIT-000034 | 1 | 0 | 0 | #1185 | NXT-TRANSMIT-000631 | 5 | 0 | KPTG-TRANSMIT-001830
RDSBIM-TRANSMIT-000035 | 1 | 0 | 0 | #1187
NXT-TRANSMIT-000601 | 20 | 0 | 0 | #1200
NXT-TRANSMIT-000601 | 12 | 0 | 0 | #1202
NXT-TRANSMIT-000601 | 19 | 0 | 0 | #1205
NXT-TRANSMIT-000601-AIR | 4 | 0 | 0 | #1215
NXT-TRANSMIT-000601-Security | 1 | 0 | 0 | #1214
NXT-TRANSMIT-000601-IW | 2 | 0 | 0 | #1213
NXT-TRANSMIT-000601-SFN | 22 | 0 | 0 | #1212
NXT-TRANSMIT-000601-DUCT | 4 | 0 | 0 | #1211
NXT-TRANSMIT-000601-ROOF | 6 | 0 | 0 | #1210
NXT-TRANSMIT-000630 | 0 | 3 | 0 | WF - 000409
NXT-TRANSMIT-000631 | 5 | 0 | 0 | Only Dustribution
NXT-TRANSMIT-000632 | 2 | 0 | 0 | WF- 000410
Total | 137 | 1 | 1 |  |  | 52 | 0
Pending Transmittals
Transmittals | Date | No. of Documents | Pending Number of Documents | Remarks
NXT-TRANSMIT-000601 | 2026-10-07 | 1 | 1 | KPTG-IntCorr-000684
Archacce-TRANSMIT-000004 | 2026-10-07 | 1 | 1 | KPTG-IntCorr-000688
NXT-TRANSMIT-000602 | 2026-10-07 | 1 | 1 | KPTG-IntCorr-000686
NXT-TRANSMIT-000621 | 2026-10-07 | 1 | 1 | KPTG-IntCorr-000685
NXT-TRANSMIT-000623 | 2026-10-08 | 23 | 23 | KPTG-IntCorr-000687

## 12-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-12 | [5 empty] | Project: | M3S6
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
4DW-TRANSMIT-000120 | 16 | 0 | 0 | #1218 | RDSBIM-TRANSMIT-000030 | 1 | 0 | KPTG-TRANSMIT-001845
4DW-TRANSMIT-000121 | 5 | 0 | 0 | #1220 | RDSBIM-TRANSMIT-000033 | 1 | 0 | KPTG-TRANSMIT-001847
KPTG-TRANSMIT-001821 | 0 | 1 | 0 | #1223 | RDSBIM-TRANSMIT-000034 | 1 | 0 | KPTG-TRANSMIT-001849
Archacce-TRANSMIT-000004 | 1 | 0 | 0 | #1225 | RDSBIM-TRANSMIT-000035 | 1 | 0 | KPTG-TRANSMIT-001851
INGEN3D-TRANSMIT-000024 - precast | 9 | 0 | 0 | #1243 | KBGA-TRANSMIT-000023 | 1 | 0 | KPTG-TRANSMIT-001855
PTA-TRANSMIT-000055 | 76 | 5 | 0 | #1228 ,1229 | STRBCK-TRANSMIT-000011 | 1 | 0 | KPTG-TRANSMIT-001857
INGEN3D-TRANSMIT-000024 - Plinth | 91 | 0 | 0 | #1232 | STRBCK-TRANSMIT-000015 | 1 | 0 | KPTG-TRANSMIT-001859
[5 empty] | ACCCA-TRANSMIT-000031 | 48 | 0 | KPTG-TRANSMIT-001854
Total | 198 | 6 | 0 |  |  | 55 | 0
Pending Transmittals
Transmittals | Date | No. of Documents | Pending Number of Documents | Remarks
NXT-TRANSMIT-000601 | 2026-10-07 | 1 | 1 | KPTG-IntCorr-000684
NXT-TRANSMIT-000602 | 2026-10-07 | 1 | 1 | KPTG-IntCorr-000686
NXT-TRANSMIT-000621 | 2026-10-07 | 1 | 1 | KPTG-IntCorr-000685
NXT-TRANSMIT-000623 | 2026-10-08 | 23 | 23 | KPTG-IntCorr-000687

## 13-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-13 | [5 empty] | Project: | M3S6
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
Baigents-TRANSMIT-000070 | 78 | 0 | 0 | Rejected | Baigents-TRANSMIT-000070 | 78 | 0 | KPTG-SADV-001073
RDSBIM-TRANSMIT-000036 | 3 | 0 | 0 | #1234 | NXT-TRANSMIT-000634 | 1 | 0 | KPTG-TRANSMIT-001862
NXT-TRANSMIT-000633 | 118 | 0 | 0 | WF- 000412 | NXT-TRANSMIT-000637 | 13 | 0 | KPTG-TRANSMIT-001864
NXT-TRANSMIT-000634 | 1 | 0 | 0 | Rejected
NXT-TRANSMIT-000635 | 25 | 0 | 0 | WF- 000413
NXT-TRANSMIT-000636 | 1 | 0 | 0 | WF-000414
NXT-TRANSMIT-000637 | 13 | 0 | 0 | Distribution only.
Baigents-TRANSMIT-000071 | 20 | 0 | 0 | #1236
Baigents-TRANSMIT-000072 | 20 | 0 | 0 | #1237
Baigents-TRANSMIT-000073 | 3 | 0 | 0 | # 1242
NXT-TRANSMIT-000638 | 2 | 0 | 0 | WF- 000417
Total | 284 | 0 | 0 |  |  | 92 | 0
Pending Transmittals
Transmittals | Date | No. of Documents | Pending Number of Documents | Remarks
NXT-TRANSMIT-000602 | 2026-10-07 | 1 | 1 | KPTG-IntCorr-000686
NXT-TRANSMIT-000621 | 2026-10-07 | 1 | 1 | KPTG-IntCorr-000685
NXT-TRANSMIT-000623 | 2026-10-08 | 23 | 23 | KPTG-IntCorr-000687
TOTAL |  | 25 | 25

## 14-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-14 | [5 empty] | Project: | M3S6
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
D&E-TRANSMIT-000093 | 13 | 0 | 0 | #1247 | SMEPS-TRANSMIT-000023 | 1 | 0 | KPTG-TRANSMIT-001873
D&E-TRANSMIT-000092 | 16 | 0 | 0 | #1249 | Baigents-TRANSMIT-000071 | 20 | 0 | KPTG-TRANSMIT-001868
DCN-TRANSMIT-000030 | 1 | 0 | 0 | WF-00423 | Baigents-TRANSMIT-000072 | 20 | 0 | KPTG-TRANSMIT-001874
RDSBIM-TRANSMIT-000037 | 1 | 0 | 0 | #1257 | PTA-TRANSMIT-000055 | 5 | 0 | KPTG-TRANSMIT-001876
ACCCA-TRANSMIT-000032 - HVL | 16 | 0 | 0 | WF-000418 | ACCCA-TRANSMIT-000027 | 7 | 0 | KPTG-TRANSMIT-001877
ACCCA-TRANSMIT-000032-TEL | 4 | 0 | 0 | WF-000419
RDSBIM-TRANSMIT-000038 | 1 | 0 | 0 | #1260
Total | 52 | 0 | 0 |  |  | 53 | 0
Pending Transmittals
Transmittals | Date | No. of Documents | Pending Number of Documents | Remarks
NXT-TRANSMIT-000602 | 2026-10-07 | 1 | 1 | KPTG-IntCorr-000686
NXT-TRANSMIT-000621 | 2026-10-07 | 1 | 1 | KPTG-IntCorr-000685
NXT-TRANSMIT-000623 | 2026-10-08 | 23 | 23 | KPTG-IntCorr-000687
TOTAL |  | 25 | 25

## 15-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-15 | [5 empty] | Project: | M3S6
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
RDSDG-TRANSMIT-000015 | 2 | 0 | 0 | 1263 | KPTG-TRANSMIT-001462 | 4 | 0 | KPTG-TRANSMIT-001887
[5 empty] | ACCCA-TRANSMIT-000026 | 6 | 0 | KPTG-TRANSMIT-001890
[5 empty] | Bianco-TRANSMIT-000002 | 29 | 0 | KPTG-TRANSMIT-001892
[5 empty] | Baigents-TRANSMIT-000060 | 109 | 0 | KPTG-TRANSMIT-001893
Total | 2 | 0 | 0 |  |  | 148 | 0
Pending Transmittals
Transmittals | Date | No. of Documents | Pending Number of Documents | Remarks
NXT-TRANSMIT-000602 | 2026-10-07 | 1 | 1 | KPTG-IntCorr-000686
NXT-TRANSMIT-000621 | 2026-10-07 | 1 | 1 | KPTG-IntCorr-000685
NXT-TRANSMIT-000623 | 2026-10-08 | 23 | 23 | KPTG-IntCorr-000687
TOTAL |  | 25 | 25

## 16-10
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-16 | [5 empty] | Project: | M3S6
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
Civilex-TRANSMIT-000017 | 5 | 0 | 5 | KPTG-IntCorr-000711 | KBGA-TRANSMIT-000024 | 1 | 0 | KPTG-TRANSMIT-001897
KBGA-TRANSMIT-000024 | 1 | 0 | 0 | Rejected | NXT-TRANSMIT-000642 | 1 | 0 | KPTG-TRANSMIT-001900
Baigents-TRANSMIT-000074 | 128 | 0 | 0 | 1267 | NXT-TRANSMIT-000645 | 29 | 0 | KPTG-TRANSMIT-001901
NXT-TRANSMIT-000641 | 4 | 0 | 0 | WF-000425
NXT-TRANSMIT-000642 | 1 | 0 | 0 | Rejected
NXT-TRANSMIT-000645 | 29 | 0 | 0 | Rejected
NXT-TRANSMIT-000646 | 6 | 0 | 0 | WF-000426
NXT-TRANSMIT-000648 | 38 | 0 | 0 | WF - 000427
ACCCA-TRANSMIT-000013 | 78 | 0 | 0 | WF - 000428
Total | 290 | 0 | 5 |  |  | 31 | 0
Pending Transmittals
Transmittals | Date | No. of Documents | Pending Number of Documents | Remarks
NXT-TRANSMIT-000602 | 2026-10-07 | 1 | 1 | KPTG-IntCorr-000686
NXT-TRANSMIT-000621 | 2026-10-07 | 1 | 1 | KPTG-IntCorr-000685
NXT-TRANSMIT-000623 | 2026-10-08 | 23 | 23 | KPTG-IntCorr-000687
TOTAL |  | 25 | 25