## 01-10-2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-01 | [6 empty] | Project: | LINDRUM
Incoming Transmittals | [5 empty] | Close out
Sl No. | Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
1 | fjc-TRANSMIT-000226 | 1 | 0 | 0 | KPTG-IntCorr-001477 - As per direction from Ash, we only update the register and distribute everyone. | Highbu-TRANSMIT-000065 | 1 | 0 | KPTG-TRANSMIT-003235
2 | fjc-TRANSMIT-000227 | 21 | 0 | 0 | #782 | fjc-TRANSMIT-000224 | 21 | 0 | KPTG-SADV-006082
3 | fjc-TRANSMIT-000227 | 0 | 1 | 0 | WF-000988 | fjc-TRANSMIT-000226 | 1 | 0 | KPTG-IntCorr-001477
4 | fjc-TRANSMIT-000227 | 1 | 0 | 0 | KPTG-SADV-006098 - Drawing No Longer in Use | fjc-TRANSMIT-000227 | 1 | 0 | KPTG-SADV-006098
5 | INDS-TRANSMIT-000055 | 14 | 0 | 14 | KPTG-IntCorr-001475 - requested guidance, but no resonance yet.
Total | 5 | 37 | 1 | 14 |  | 4 | 24 | 0
Pending Transmittals
Sl No. | Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
1
2
Total | 0 |  | 0 | 0

## 02-10-2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-02 | [6 empty] | Project: | LINDRUM
Incoming Transmittals | [5 empty] | Close out
Sl No. | Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
1 | fjc-TRANSMIT-000228 | 1 | 0 | 0 | KPTG-TRANSMIT-003244- NO LONGER IN USE | INDS-TRANSMIT-000054 | 1 | 0 | KPTG-SADV-006115
2 | KPTG-TRANSMIT-003243 | 32 | 0 | 0 | #786 | RDSBIM-TRANSMIT-000255 | 1 | 0 | KPTG-SADV-006114
3 | KPTG-TRANSMIT-002989 | 6 | 0 | 0 | WF-000991 | KPTG-TRANSMIT-003208 | 30 | 0 | KPTG-IntCorr-001478
4 | NXES-TRANSMIT-000081 | 1 | 0 | 0 | KPTG-IntCorr-001480-As per direction from Ashlin ,we terminate the WF | INDS-TRANSMIT-000055 | 14 | 0 | KPTG-IntCorr-001481
5 | NXES-TRANSMIT-000081 | 1 | 0 | 0 | #785 | fjc-TRANSMIT-000228 | 1 | 0 | KPTG-TRANSMIT-003244
6 | fjc-TRANSMIT-000229 | 1 | 0 | 0 | KPTG-TRANSMIT-003250-NO LONGER IN USE | NXES-TRANSMIT-000081 | 1 | 0 | KPTG-IntCorr-001480
7 | fjc-TRANSMIT-000230 | 1 | 0 | 0 | KPTG-TRANSMIT-003252 - NO LONGER IN USE | fjc-TRANSMIT-000229 | 1 | 0 | KPTG-TRANSMIT-003250
8 | fjc-TRANSMIT-000231 | 1 | 0 | 0 | KPTG-TRANSMIT-003255- NO LONGER IN USE | fjc-TRANSMIT-000230 | 1 | 0 | KPTG-TRANSMIT-003252
9 | NXES-TRANSMIT-000082 | 3 | 0 | 0 | #787 | fjc-TRANSMIT-000231 | 1 | 0 | KPTG-TRANSMIT-003255
10 | PRDoors-IntCorr-000018 | 6 | 0 | 0 | WF-000994
Total | 10 | 53 | 0 | 0 |  | 9 | 51 | 0
Pending Transmittals
Sl No. | Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
1
2
Total | 0 |  | 0 | 0

## 05-10-2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-05 | [6 empty] | Project: | LINDRUM
Incoming Transmittals | [5 empty] | Close out
Sl No. | Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
1 | IGS--TRANSMIT-000043 | 0 | 1 | 0 | KPTG-IntCorr-001486-As per direction from Ashlin, we only update the register and issue out everyone. | KPTG-TRANSMIT-002989 | 6 | 0 | KPTG-IntCorr-001485
2 | Novas-TRANSMIT-000011 | 0 | 1 | 0 | WF-000995 | IGS--TRANSMIT-000043 | 1 | 0 | KPTG-IntCorr-001486-As per direction from Ashlin, we only update the register and issue out everyone.
3 | IGS--TRANSMIT-000042 | 58 | 0 | 0 | KPTG-SADV-006134-current revision previous revision same,revision date,tittle incorrect | KPTG-IntCorr-001254 | 1 | 0 | KPTG-IntCorr-001488-As per direction Brentyn, we terminate the WF-000868.
4 | IGS--TRANSMIT-000044 | 0 | 1 | 0 | KPTG-IntCorr-001490-As per direction from Ashlin, we only update the register and issue out everyone. | IGS--TRANSMIT-000042 | 58 | 0 | KPTG-SADV-006134-current revision previous revision same,revision date,tittle incorrect
5 | Auscool-TRANSMIT-000126 | 1 | 0 | 0 | KPTG-IntCorr-001491-As per direction from Ashlin, we only update the register and issue out everyone. | IGS--TRANSMIT-000044 | 1 | 0 | KPTG-IntCorr-001490-As per direction from Ashlin, we only update the register and issue out everyone.
6 | 42636706-TRANSMIT-000030 | 2 | 0 | 0 | WF-000996 | Auscool-TRANSMIT-000126 | 1 | 0 | KPTG-IntCorr-001491-As per direction from Ashlin, we only update the register and issue out everyone.
[6 empty] | PRDoors-IntCorr-000014 | 8 | 0 | KPTG-TRANSMIT-003275
Total | 6 | 61 | 3 | 0 |  | 7 | 76 | 0
Pending Transmittals
Sl No. | Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
1
2
Total | 0 |  | 0 | 0

## 06-10-2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-06 | [6 empty] | Project: | LINDRUM
Incoming Transmittals | [5 empty] | Close out
Sl No. | Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
1 | Highbu-TRANSMIT-000068 | 7 | 0 | 7 | KPTG-IntCorr-001496 - requested guidance, but no resonance yet. | INDS-TRANSMIT-000056 | 5 | 0 | KPTG-IntCorr-001492 - As per direction from Ashlin, we only update the register and issue out everyone.
2 | INDS-TRANSMIT-000056 | 5 | 0 | 0 | KPTG-IntCorr-001492 - As per direction from Ashlin, we only update the register and issue out everyone. | IGS--TRANSMIT-000042 | 58 | 0 | KPTG-SADV-006134-current revision previous revision same,revision date,tittle incorrect
3 | IGS--TRANSMIT-000042 | 58 | 0 | 0 | KPTG-SADV-006134-current revision previous revision same,revision date,tittle incorrect
Total | 3 | 70 | 0 | 7 |  | 2 | 63 | 0
Pending Transmittals
Sl No. | Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
1
2
Total | 0 |  | 0 | 0

## 07-10-2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-07 | [6 empty] | Project: | LINDRUM
Incoming Transmittals | [5 empty] | Close out
Sl No. | Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
1 | KPTG-INTCOM-000427 | 1 | 0 | 0 | WF-000998 - KPTG-IntCorr-001502 - As per direction from Charlie, we uploaded the document | NXES-TRANSMIT-000082 | 3 | 0 | KPTG-SADV-006167
2 | [5 empty] | fjc-TRANSMIT-000227 | 21 | 0 | KPTG-SADV-006193
3 | [5 empty] | NXES-TRANSMIT-000072 | 9 | 0 | KPTG-IntCorr-001501
Total | 1 | 1 | 0 | 0 |  | 3 | 33 | 0
Pending Transmittals
Sl No. | Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
1 | Highbu-TRANSMIT-000068 | 46301 | 7 | 7 | KPTG-IntCorr-001496 - requested guidance, but no resonance yet.
2
Total | 1 |  | 7 | 7

## 08-10-2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-08 | [6 empty] | Project: | LINDRUM
Incoming Transmittals | [5 empty] | Close out
Sl No. | Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
1 | Highbu-TRANSMIT-000068 | 1 | 0 | 0 | KPTG-SADV-006168 - The document revision, date, and status appear to be incorrect. | Highbu-TRANSMIT-000068 | 6 | 0 | KPTG-IntCorr-001499 - As per direction from AShlin,we only update the register and distribute everyone.
2 | RDSBIM-TRANSMIT-000256 | 1 | 0 | 0 | #791 | Highbu-TRANSMIT-000068 | 1 | 0 | KPTG-SADV-006168 - The document revision, date, and status appear to be incorrect.
3 | Auscool-TRANSMIT-000127 | 2 | 0 | 0 | #793
4 | 42636706-TRANSMIT-000031 | 0 | 1 | 0 | WF-001000
5 | 42636706-TRANSMIT-000027 | 0 | 2 | 0 | WF-001002
6 | fjc-TRANSMIT-000233 | 9 | 0 | 0 | #792
Total | 6 | 13 | 3 | 0 |  | 2 | 7 | 0
Pending Transmittals
Sl No. | Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
1
2
Total | 0 |  | 0 | 0

## 09-10-2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-09 | [6 empty] | Project: | LINDRUM
Incoming Transmittals | [5 empty] | Close out
Sl No. | Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
1 | NXES-TRANSMIT-000082 | 3 | 0 | 0 | WF-001004 |  |  |  | 151 WF Templates Created.
Total | 1 | 3 | 0 | 0 |  | 0 | 0 | 0
Pending Transmittals
Sl No. | Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
1
2
Total | 0 |  | 0 | 0

## 12-10-2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-12 | [6 empty] | Project: | LINDRUM
Incoming Transmittals | [5 empty] | Close out
Sl No. | Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
1 | 42636706-TRANSMIT-000032 | 1 | 0 | 0 | KPTG-SADV-006239 - Revison,revision date are incorrect,The previous revision is missing in the History Box. | PRDoors-IntCorr-000016 | 5 | 0 | KPTG-TRANSMIT-003306
2 | 42636706-TRANSMIT-000033 | 1 | 0 | 0 | KPTG-SADV-006240 - Document no, tittle, revision incorrect. history box previous revision missing. | PRDoors-IntCorr-000018 | 6 | 0 | KPTG-TRANSMIT-003308
3 | 42636706-TRANSMIT-000034 | 1 | 0 | 0 | KPTG-SADV-006244 - Document no, revision, tittle are missing. revision history box previous revision is missing. | 42636706-TRANSMIT-000027 | 2 | 0 | KPTG-TRANSMIT-003304
4 | INDS-TRANSMIT-000057 | 1 | 0 | 0 | 794 | 42636706-TRANSMIT-000032 | 1 | 0 | KPTG-SADV-006239
| fjc-TRANSMIT-000234 | 6 | 0 | 0 | 795 | 42636706-TRANSMIT-000033 | 1 | 0 | KPTG-SADV-006240
| SYNACC-TRANSMIT-000013 | 2 | 0 | 2 | KPTG-IntCorr-001509 - requested guidance, but no resonance yet. | 42636706-TRANSMIT-000034 | 1 | 0 | KPTG-SADV-006244
| 42636706-TRANSMIT-000035 | 1 | 0 | 1 | KPTG-IntCorr-001510 - requested guidance, but no resonance yet. | fjc-TRANSMIT-000233 | 9 | 0 | KPTG-SADV-006241
Total | 7 | 13 | 0 | 3 |  | 7 | 25 | 0
Pending Transmittals
Sl No. | Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
1
2
Total | 0 |  | 0 | 0

## 13-10-2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-13 | [6 empty] | Project: | LINDRUM
Incoming Transmittals | [5 empty] | Close out
Sl No. | Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
1 | fjc-TRANSMIT-000235 | 6 | 0 | 0 | 797 | Novas-TRANSMIT-000011 | 1 | 0 | KPTG-TRANSMIT-003323
2 | fjc-TRANSMIT-000236 | 8 | 0 | 0 | 798 | 42636706-TRANSMIT-000031 | 1 | 0 | KPTG-TRANSMIT-003321
3 | [5 empty] | RDSBIM-TRANSMIT-000256 | 1 | 0 | KPTG-SADV-006273
4 | [5 empty] | NXES-TRANSMIT-000082 | 3 | 0 | KPTG-TRANSMIT-003309
[6 empty] | fjc-TRANSMIT-000235 | 6 | 0 | KPTG-SADV-006275
Total | 2 | 14 | 0 | 0 |  | 5 | 12 | 0
Pending Transmittals
Sl No. | Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
1
2
Total | 0 |  | 0 | 0

## 14-10-2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-14 | [6 empty] | Project: | LINDRUM
Incoming Transmittals | [5 empty] | Close out
Sl No. | Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
1 | PRDoors-IntCorr-000020 | 6 | 0 | 0 | KPTG-SADV-006297 - The required details are not included within the drawing. | fjc-TRANSMIT-000227 | 1 | 0 | KPTG-TRANSMIT-003333
2 | NXES-TRANSMIT-000085 | 9 | 0 | 0 | WF-001011 | fjc-TRANSMIT-000234 | 6 | 0 | KPTG-SADV-006299
3 | Metzone-TRANSMIT-000059 | 92 | 0 | 0 | KPTG-SADV-006298 - The title in Aconex is different from the title shown within the document. | SYNACC-TRANSMIT-000013 | 2 | 0 | KPTG-IntCorr-001517
4 | [5 empty] | PRDoors-IntCorr-000020 | 6 | 0 | KPTG-SADV-006297
5 | [5 empty] | Metzone-TRANSMIT-000059 | 92 | 0 | KPTG-SADV-006298
Total | 3 | 107 | 0 | 0 |  | 5 | 107 | 0
Pending Transmittals
Sl No. | Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
1
2
Total | 0 |  | 0 | 0

## 15-10-2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-15 | [6 empty] | Project: | LINDRUM
Incoming Transmittals | [5 empty] | Close out
Sl No. | Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
1 | RDSBIM-TRANSMIT-000257 | 1 | 0 | 0 | #799 | 42636706-TRANSMIT-000030 | 2 | 0 | KPTG-TRANSMIT-003339
2 | NXES-TRANSMIT-000085 | 0 | 9 | 0 | WF-001016 | fjc-TRANSMIT-000236 | 8 | 0 | KPTG-SADV-006327
3 | Metzone-TRANSMIT-000060 | 92 | 0 | 0 | WF-001014 | NXES-TRANSMIT-000085 | 9 | 0 | KPTG-IntCorr-001519
Total | 3 | 93 | 9 | 0 |  | 3 | 19 | 0
Pending Transmittals
Sl No. | Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
1
2
Total | 0 |  | 0 | 0

## 16-10-2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-16 | [6 empty] | Project: | LINDRUM
Incoming Transmittals | [5 empty] | Close out
Sl No. | Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
1 | RDSBIM-TRANSMIT-000258 | 5 | 0 | 0 | #800 | NXES-TRANSMIT-000081 | 1 | 0 | KPTG-SADV-006346
2 | Auscool-TRANSMIT-000128 | 3 | 0 | 0 | #801 | 42636706-TRANSMIT-000035 | 1 | 0 | KPTG-SADV-006347
3 | Auscool-TRANSMIT-000128 | 2 | 0 | 0 | #801
4 | NXES-TRANSMIT-000086 | 2 | 0 | 0 | #802
5 | NXES-TRANSMIT-000087 | 2 | 0 | 0 | #803
6 | NXES-TRANSMIT-000088 | 2 | 0 | 0 | #804
7 | NXES-TRANSMIT-000088 | 2 | 0 | 0 | WF-001022
Total | 7 | 18 | 0 | 0 |  | 2 | 2 | 0
Pending Transmittals
Sl No. | Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
1
2
Total | 0 |  | 0 | 0