## 01.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-01 | [5 empty] | Project: | MEL11
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
SES AU-TRANSMIT-000116 MEL11 - O&M MANUAL-Draft | 0 | 1 | 0 | Rejected: Request to issue in pdf format:KPTG-TRANSMIT-001276 | SES AU-TRANSMIT-000116-MEL11 - O&M MANUALDraft | 1 | 0 | KPTG-TRANSMIT-001276
SES AU-TRANSMIT-000117- MEL11 - O&M MANUAL-Draft | 0 | 1 | 0 | WF-000500 | Arc Plas-TRANSMIT-000008 Arc - OM MANUAL - Ceilings & Partitions - Revised | 1 | 0 | KPTG-TRANSMIT-001277
TATE_-TRANSMIT-000042 Re: Action Required: Populate O&M - MEL11C45 | 0 | 1 | 0 | WF-000501 | TATE_-TRANSMIT-000041 -Re: O&M - MEL11C45 | 1 | 0 | KPTG-TRANSMIT-001280
EFP-TRANSMIT-000046- APPROVED DRAWINGS UPDATED IFC | 9 | 0 | 0 | Rejected: duplicate drawing:KPTG-TRANSMIT-001281 | EFP-TRANSMIT-000046- APPROVED DRAWINGS UPDATED IFC | 9 | 0 | KPTG-TRANSMIT-001281
4 | 9 | 3 | 0 |  | 4 | 12
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks

## 02.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-02 | [5 empty] | Project: | MEL11
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
WilsonPD-TRANSMIT-000012- Hydraulic Services - MEL 11 Tank 3 - As Built | 1 | 0 | 0 | WF-000502 | ETNInd-TRANSMIT-000033 Fwd: MEL11-COLO4 FAT Report Update | 8 | 0 | KPTG-TRANSMIT-001283
1 | 1 | 0 | 0 |  | 1 | 8
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks

## 05.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-05 | [5 empty] | Project: | MEL11
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
Entire M-TRANSMIT-000097- DX Unit Technical Data - System Schematic Included | 0 | 1 | 0 | WF-000503
1 | 0 | 1 | 0 |  | 0 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks

## 06.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-06 | [5 empty] | Project: | MEL11
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
SES AU-TRANSMIT-000114-: HAC Prototype Report - Rev 2 - Camera Installation- Height 2650 mm | 0 | 1 | 0 | WF-000504(workflow resubmitted) | VinageC-TRANSMIT-000001 Internal Wayfinding Signage Shop Drawings | 1 | 1 | KPTG-TRANSMIT-001287
KPTG-IntCorr-000855 Energisation Plan | 0 | 1 | 0 | WF-000505
VinageC-TRANSMIT-000001 Internal Wayfinding Signage Shop Drawings | 1 | 0 | 0 | Rejected: Combined pdf-KPTG-TRANSMIT-001287
3 | 1 | 2 | 0 |  | 1 | 1
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks

## 07.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-07 | [5 empty] | Project: | MEL11
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
VinageC-TRANSMIT-000002 Updated Shop Drawings | 3 | 0 | 0 | Rejected: Document numbering is incorrect: KPTG-IntCorr-000861 | VinageC-TRANSMIT-000002 Updated Shop Drawings | 3 | 0 | KPTG-IntCorr-000861
VinageC-TRANSMIT-000003 Update Shop Drawings | 1 | 0 | 0 | Rejected: Document numbering is incorrect:KPTG-TRANSMIT-001289- | VinageC-TRANSMIT-000003 Update Shop Drawings | 1 | 0 | KPTG-TRANSMIT-001289
VinageC-TRANSMIT-000004 Update Shop Drawings Revised | 1 | 0 | 0 | Rejected: Document numbering is incorrect:KPTG-TRANSMIT-001290 | VinageC-TRANSMIT-000004 Update Shop Drawings Revised | 1 | 0 | KPTG-TRANSMIT-001290
3 | 5 | 0 | 0 |  | 3 | 5
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks

## 08.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-08 | [5 empty] | Project: | MEL11
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
VinageC-TRANSMIT-000005 Internal Wayfiding Signage Drawings updated | 4 | 0 | 0 | WF-000506
1 | 4 | 0 | 0 |  | 0 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks

## 09.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-09 | [5 empty] | Project: | MEL11
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
EFP-TRANSMIT-000047 GENERATOR ENCLOUSE - FIRE PROTECTION SHOP DRAWINGS | 2 | 0 | 0 | Rejected: Incorrect Drawing status: KPTG-TRANSMIT-001292 | EFP-TRANSMIT-000047 GENERATOR ENCLOUSE - FIRE PROTECTION SHOP DRAWINGS | 2 | 0 | Rejected: Incorrect Drawing status: KPTG-TRANSMIT-001292
EFP-TRANSMIT-000048 FIRE SERVICES SHOP DRAWINGS ISSUED IFC | 9 | 0 | 0 | WF-000507 | TATE_-TRANSMIT-000042- Re: Action Required: Populate O&M - MEL11C45 | 1 | 0 | KPTG-TRANSMIT-001293
2 | 11 | 0 | 0 |  | 2 | 3
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks

## 12.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-12 | [5 empty] | Project: | MEL11
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
ETNInd-TRANSMIT-000034 Eaton ¦ COLO 5 ¦ L1 FAT Report | 0 | 8 | 0 | WF-000508 | ETNInd-TRANSMIT-000035 Eaton ¦ COLO 5 ¦ Pre-Shipping Inspection | 8 | 0 | Rejected:KPTG-TRANSMIT-001294
ETNInd-TRANSMIT-000035 Eaton ¦ COLO 5 ¦ Pre-Shipping Inspection | 0 | 8 | 0 | Rejected: Incorrect Document Numbering:KPTG-TRANSMIT-001294
KPTG-IntCorr-000868 Urgent put in Workflow-CEI cable test report | 0 | 1 | 0 | WF-000509
KPTG-IntCorr-000868 Urgent put in Workflow-SSCR REPORT | 0 | 2 | 0 | WF-000510
KPTG-IntCorr-000868 Urgent put in Workflow | 0 | 3 | 0 | WF-000511
5 | 0 | 22 | 0 |  | 1 | 8
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks

## 13.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-13 | [5 empty] | Project: | MEL11
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
SES AU-TRANSMIT-000118 | 2 | 0 | 0 | WF-000512 | Entire M-TRANSMIT-000096 | 6 | 0 | KPTG-TRANSMIT-001295
Entire M-TRANSMIT-000098 | 6 | 0 | 0 | WF-000516 | Entire M-TRANSMIT-000096 | 8 | 0 | KPTG-TRANSMIT-001298
Entire M-TRANSMIT-000098 | 4 | 0 | 0 | WF-000517
3 | 12 | 0 | 0 |  | 2 | 14
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks

## 14.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-13 | [5 empty] | Project: | MEL11
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
Appselec-TRANSMIT-000148 | 3 | 0 | 0 | WF-000518 | SES AU-TRANSMIT-000117 | 1 | 0 | KPTG-TRANSMIT-001301
EFP-TRANSMIT-000049 | 2 | 0 | 0 | WF-000519 | SES AU-TRANSMIT-000118 | 2 | 0 | KPTG-TRANSMIT-001304
ETNInd-TRANSMIT-000036 | 0 | 8 | 0 | KPTG-IntCorr-000880 | PenskePS-TRANSMIT-000016 | 9 | 0 | KPTG-TRANSMIT-001307
PenskePS-TRANSMIT-000016 | 0 | 9 | 0 | KPTG-TRANSMIT-001307 | Appselec-TRANSMIT-000154 | 1 | 0 | KPTG-SADV-002447
Appselec-TRANSMIT-000154 | 0 | 1 | 0 | KPTG-SADV-002447
5 | 5 | 18 | 0 |  | 4 | 13
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
SES AU-TRANSMIT-000114-: HAC Prototype Report - Rev 2 - Camera Installation- Height 2650 mm | 2026-10-14 | 1 | 1 | No Kapitol stamp KPTG-IntCorr-000878
ETNInd-TRANSMIT-000032 | 2026-10-13 | 1 | 1 | No Kapitol stamp KPTG-IntCorr-000879

## 15.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-15 | [5 empty] | Project: | MEL11
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
Appselec-TRANSMIT-000155 | 0 | 1 | 0 | KPTG-SADV-002461 | Appselec-TRANSMIT-000155 | 1 | 0 | KPTG-SADV-002461
EFP-TRANSMIT-000050 | 0 | 1 | 0 | DRAFT-006117 | EFP-TRANSMIT-000050 | 1 | 0 | KPTG-SADV-002460
SIL-TRANSMIT-000042 | 0 | 2 | 0 | DRAFT-006118 | SIL-TRANSMIT-000042 | 2 | 0 | KPTG-SADV-002458
3 | 0 | 4 | 0 |  | 3 | 4
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
SES AU-TRANSMIT-000114 | 2026-10-13 | 1 | 1 | No Kapitol stamp KPTG-IntCorr-000878
ETNInd-TRANSMIT-000032 | 2026-10-13 | 1 | 1 | No Kapitol stamp KPTG-IntCorr-000879

## 16.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-16 | [5 empty] | Project: | MEL11C45
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
EFP-TRANSMIT-000051- FIRE SERVICES SHOP DRAWINGS UPDATED | 8 | 0 | 0 | WF-000520 | Appselec-TRANSMIT-000156 MEL11-APPSELEC-E-PLN-001 | 1 | 0 | KPTG-TRANSMIT-001309
SIL-TRANSMIT-000043 -MEL11 COLO4-5 LVS & UPM Operation & Maintenance Manual | 0 | 2 | 0 | WF-000522 | ETNInd-TRANSMIT-000035 Re: Eaton ¦ COLO 5 ¦ Pre-Shipping Inspection | 8 | 0 | KPTG-TRANSMIT-001310
Appselec-TRANSMIT-000156 MEL11-APPSELEC-E-PLN-001 | 0 | 1 | 0 | Rejected: Incorrect Document number | SES AU-TRANSMIT-000114 Re: HAC Prototype Report - Rev 2 - Camera Installation- Height 2650 mm | 1 | 0 | KPTG-TRANSMIT-001312
Appselec-TRANSMIT-000157 COLO4 CEI BENEFICIAL USE FIBRE TEST RESULTS | 0 | 4 | 0 | WF-000521 | ETNInd-TRANSMIT-000032 -MEL11 COLO4/COLO5 O&M Manual | 1 | 0 | KPTG-TRANSMIT-001314
ETNInd-TRANSMIT-000035 Re: Eaton ¦ COLO 5 ¦ Pre-Shipping Inspection | 0 | 8 | 0 | Transmitted to client & AE Team: KPTG-TRANSMIT-001310
Appselec-TRANSMIT-000153 MEL11C45 Fibre Optic Cable Schedules (As-Built) | 0 | 3 | 3 | Clarification Required: KPTG-TRANSMIT-001311
6 | 8 | 18 | 3 |  | 4 | 11
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks