## 01.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-01 | [5 empty] | Project: | MLCSPR
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
NXES-TRANSMIT-000100- Nexus Tech Data Sheets - Resubmission | 0 | 15 | 0 | WORKFLOW IS RESUBMITTED:WF-001256 | P & R-TRANSMIT-000123 Stage 2 - Setout Drawings | 6 | 0 | KPTG-TRANSMIT-003586
RDSBIM-TRANSMIT-000154 -MLCSPR -INDOOR SPORTS CENTRE LEVEL 02 CONCRETE PROFILE PLAN | 7 | 0 | 0 | #707 | BTWA-TRANSMIT-000100 Re: Stage 2 - Facade Glass | 3 | 0 | KPTG-TRANSMIT-003588
P & R-TRANSMIT-000123 Stage 2 - Setout Drawings | 6 | 0 | 0 | Rejected: Revision history of drawing does not match with previous: KPTG-TRANSMIT-003586 | Highbu-TRANSMIT-000169 Re-transmitting approved sample as request by Kapitol | 1 | 0 | KPTG-SADV-006676
BTWA-TRANSMIT-000109 MLC Stage 2 - Internal Frame Type 1 | 0 | 1 | 0 | WF-001257 | Highbu-TRANSMIT-000172 Hot water plant submission | 1 | 0 | KPTG-SADV-006677
Highbu-TRANSMIT-000169 Re-transmitting approved sample as request by Kapitol | 0 | 1 | 0 | Requested to resubmit-KPTG-SADV-006676 | MCGC-TRANSMIT-000017 MCGC - LANDSCAPE DRAWING UPDATES | 8 | 0 | KPTG-SADV-006678
Highbu-TRANSMIT-000170 Recently approved hydraulic sample resubmitted - KP request | 0 | 1 | 0 | WF-001258 | Auspan-TRANSMIT-000141 Precast shop drawings for construction. Columns on level 2 stage 2. Normal columns. | 13 | 0 | KPTG-TRANSMIT-003589
Highbu-TRANSMIT-000171 Resubmission of previous approved samples | 0 | 1 | 0 | WF-001259 | Auspan-TRANSMIT-000146 Precast shop drawings for approval. Stage 2 Premium level 2. | 24 | 0 | KPTG-SADV-006660
Highbu-TRANSMIT-000172 Hot water plant submission | 0 | 1 | 0 | Rejected:Document number in the covering sheet needs to be updated:KPTG-SADV-006677 | Auspan-TRANSMIT-000142- Precast shop drawings for construction. Columns on level 2 stage 2. Normal columns | 1 | 0 | KPTG-TRANSMIT-003591
MCGC-TRANSMIT-000017 MCGC - LANDSCAPE DRAWING UPDATES | 8 | 0 | 0 | Title Bloc and Drawing status needs to be updated:KPTG-SADV-006678
Auspan-TRANSMIT-000146 Precast shop drawings for approval. Stage 2 Premium level 2. | 24 | 0 | 0 | Rejected: Revision date mentioned in the register is incorrect:KPTG-SADV-006660
Auspan-TRANSMIT-000147 Re: Precast shop drawings for approval. Stage 2 Premium level 2. | 1 | 0 | 0 | #713
11 | 46 | 20 | 0 |  | 8 | 57
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
BTWA-TRANSMIT-000105 Re: MLC Stage 2 - Both colour options | 28.09.2026 | 1 | 1 | Review of one of documents is stil in review:KPTG-TRANSMIT-003559

## 02.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-02 | [5 empty] | Project: | MLCSPR
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
ARCH-TRANSMIT-000199 MLC - SPR - ISC - Drawings update | 5 | 0 | 0 | #725 | NXES-TRANSMIT-000082 Re: Electrical Penetration Layout | 3 | 0 | KPTG-TRANSMIT-003602
ARCH-TRANSMIT-000200 MLC - SPR - ISC - Wall drawings updated | 4 | 0 | 0 | #715 | NXES-TRANSMIT-000088 Re: ISC Roof Electrical Layout | 3 | 0 | KPTG-TRANSMIT-003604
MCGC-TRANSMIT-000017 MCGC - LANDSCAPE DRAWING UPDATES | 8 | 0 | 0 | #717 | Best.-TRANSMIT-000012 Stage 2 Signage | 0 | 99 | KAPITOL ADVICE AWAITS: KPTG-IntCorr-008940
ARCH-TRANSMIT-000201 MLC - SPR - updated GA Drawings | 6 | 0 | 0 | #719
ARCH-TRANSMIT-000202 MLC - SPR - ISC - updated Facade drawings | 4 | 0 | 0 | #721
ARCH-TRANSMIT-000203 -MLC - SPR - ISC - Updated CPP- | 3 | 0 | 0 | #723
Highbu-TRANSMIT-000173 Hot water plant sample | 0 | 1 | 0 | WF-001267
BTWA-TRANSMIT-000110 Requires confirmation-: MLC Stage 2 - Internal sample submission | 0 | 6 | 6 | Kapitol Advice awaits: KPTG-SADV-006686
P & R-TRANSMIT-000124 CPEF-01 Carpark Fan IFC | 0 | 1 | 0 | WF-001268
9 | 30 | 8 | 6 |  | 3 | 6 | 99
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
BTWA-TRANSMIT-000105 Re: MLC Stage 2 - Both colour options | 28.09.2026 | 1 | 1 | Review of one of documents is stil in review:KPTG-TRANSMIT-003559

## 05.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-05 | [5 empty] | Project: | MLCSPR
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
P & R-TRANSMIT-000125 ISC - Updated MEC Penetrations | 2 | 0 | 0 | #729 | BTWA-TRANSMIT-000104 MLC Stage 2 - Final external glass sample | 1 | 0 | KPTG-TRANSMIT-003610
MCGC-TRANSMIT-000018- External Stairs set-out dimensions & RL request. | 1 | 0 | 0 | #727 | NXES-TRANSMIT-000090-Level 02 & 03 Emergency Lighting Calculation | 2 | 0 | KPTG-TRANSMIT-003607
[5 empty] | NXES-TRANSMIT-000098- PV Solar Shop Drawings | 5 | 0 | KPTG-TRANSMIT-003608
[5 empty] | Best.-TRANSMIT-000012 Re: Stage 2 Signage | 99 | 0 | KPTG-TRANSMIT-003611
[5 empty] | P & R-TRANSMIT-000108 Re: Mechanical Shop Drawing Update | 5 | 0 | KPTG-TRANSMIT-003613
[5 empty] | BTWA-TRANSMIT-000108 | 0 | 4 | Kapitol Advice -Awaits-KPTG-IntCorr-008943
[5 empty] | PROLMC-TRANSMIT-000040 : MLC stage 2 Sample Retransmitted | 0 | 1 | Kapitol Advice awaits: KPTG-IntCorr-008944
[5 empty] | M.S.-TRANSMIT-000086 | 0 | 22 | Review is partially completed: Kapitol Advice awaits: KPTG-IntCorr-008945
2 | 3 | 0 | 0 |  | 8 | 112 | 27
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
BTWA-TRANSMIT-000110 Requires confirmation-: MLC Stage 2 - Internal sample submission | 02.10.2026 | 6 | 6 | Kapitol Advice awaits: KPTG-SADV-006686

## 06.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-06 | [5 empty] | Project: | MLCSPR
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
ARCH-TRANSMIT-000204 MLC - SPR - ISC - Joinery update | 5 | 0 | 0 | #731 | BTWA-TRANSMIT-000108 -MLC Stage 2 - Sample submission | 4 | 0 | KPTG-SADV-006721 (workflow terminated & Resubmitted)
BTWA-TRANSMIT-000108 -MLC Stage 2 - Sample submission | 0 | 4 | 0 | WF-001273 | PROLMC-TRANSMIT-000040 -MLC stage 2 Sample Retransmitted | 1 | 0 | KPTG-SADV-006722 (workflow terminated & resubmitted)
PROLMC-TRANSMIT-000040 -MLC stage 2 Sample Retransmitted | 0 | 1 | 0 | WF-001274 | P & R-TRANSMIT-000126 | 1 | 0 | Rejected: same revision still in review: KPTG-SADV-006735
Auspan-TRANSMIT-000150 & for approval. Level 3. Premium Precast Panels. | 5 | 0 | 0 | WF-001275
Auspan-TRANSMIT-000149 Precast shop drawings | 6 | 0 | 0 | WF-001275 (Workflow combined)
Auspan-TRANSMIT-000150 &Auspan-TRANSMIT-000149 Precast shop drawings for approval. Level 3. Premium Precast Panels | 3 | 0 | 0 | #733
M.S.-TRANSMIT-000106 Sample sheet for FEK02 | 0 | 1 | 0 | WF-001276
P & R-TRANSMIT-000126 | 0 | 1 | 0 | Rejected: same revision still in review: KPTG-SADV-006735
Auspan-TRANSMIT-000148 - Precast shop drawings for construction. Columns on level 2 stage 2. Normal columns. | 4 | 0 | 0 | WF-001277
9 | 23 | 7 | 0 |  | 3 | 6 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
BTWA-TRANSMIT-000110 Requires confirmation-: MLC Stage 2 - Internal sample submission | 02.10.2026 | 6 | 6 | Kapitol Advice awaits: KPTG-SADV-006686
M.S.-TRANSMIT-000086 | 05.10.2026 | 22 | 22 | Review is partially completed: Kapitol Advice awaits: KPTG-IntCorr-008945

## 07.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-06 | [5 empty] | Project: | MLCSPR
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000151-Precast Column Dowel Plans | 1 | 0 | 0 | Rejected: Requested to reissue as " For approval:KPTG-SADV-006741 | Auspan-TRANSMIT-000151-Precast Column Dowel Plans | 1 | 0 | KPTG-SADV-006741
KYFP-TRANSMIT-000014 Wet Fire penetration drawings | 2 | 0 | 0 | Rejected: Document numbering is incorrect: KPTG-SADV-006742 | KYFP-TRANSMIT-000014 Wet Fire penetration drawings | 2 | 0 | KPTG-SADV-006742
NXES-TRANSMIT-000101 Electrical Penetration Layout | 2 | 0 | 0 | #737 | P & R-TRANSMIT-000127 Stage 2 MSSB - IFA | 2 | 0 | KPTG-SADV-006744
NXES-TRANSMIT-000101 Electrical Penetration Layout | 1 | 0 | 0 | #736 | ARCH-TRANSMIT-000204 Re: MLC - SPR - ISC - Joinery update | 5 | 0 | KPTG-TRANSMIT-003620
Auspan-TRANSMIT-000152-Precast Column Dowel Plans | 1 | 0 | 0 | WF-001280 | AdntCons-TRANSMIT-000018 Re: Latest Dry fire docs | 3 | 0 | KPTG-TRANSMIT-003624
P & R-TRANSMIT-000127 Stage 2 MSSB - IFA | 0 | 2 | 0 | Rejected:Incorrect document Numbering-KPTG-SADV-006744 | M.S.-TRANSMIT-000086 Re: Sample Sheets | 22 | 0 | KPTG-TRANSMIT-003626
NXES-TRANSMIT-000102-: Nexus Tech Data Sheets - Resubmission | 0 | 3 | 0 | WF-001283 | P & R-TRANSMIT-000125 Re: ISC - Updated MEC Penetrations | 2 | 0 | KPTG-TRANSMIT-003627
[5 empty] | NXES-TRANSMIT-000101 Re: Electrical Penetration Layout | 2 | 0 | KPTG-TRANSMIT-003629
[5 empty] | BTWA-TRANSMIT-000107 MLC Stage 2 - Rev C Shop drawing reissue | 0 | 26 | KPTG-IntCorr-008979
7 | 7 | 5 | 0 |  | 9 | 39 | 26
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
BTWA-TRANSMIT-000110 Requires confirmation-: MLC Stage 2 - Internal sample submission | 02.10.2026 | 6 | 6 | Kapitol Advice awaits: KPTG-SADV-006686

## 08.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-08 | [5 empty] | Project: | MLCSPR
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
0 | 0 | 0 | 0 | 0 | Auspan-TRANSMIT-000145 Resubmit precast shop drawings for approval due to architectural design change. | 2 | 0 | workflow terminated:KPTG-SADV-006774
1 | 0 | 0 | 0 |  | 1 | 2 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
BTWA-TRANSMIT-000110 Requires confirmation-: MLC Stage 2 - Internal sample submission | 02.10.2026 | 6 | 6 | Kapitol Advice awaits: KPTG-SADV-006686
BTWA-TRANSMIT-000107 MLC Stage 2 - Rev C Shop drawing reissue | 07.02.2026 | 26 | 26 | KPTG-IntCorr-008979

## 09.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-09 | [5 empty] | Project: | MLCSPR
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
ADP-TRANSMIT-000041 ADP MEL3393 - Updated Fire Protection Reg126 | 0 | 1 | 0 | updated document register, and transmitted to concerned trade partners: KPTG-TRANSMIT-003635 | Auspan-TRANSMIT-000147 Precast shop drawings for approval. Stage 2 Premium level 2. | 1 | 0 | workflow terminated:KPTG-SADV-006797
Fredon T-TRANSMIT-000040 AV Shop Drawings Complete IFC | 7 | 0 | 0 | #740 | ADP-TRANSMIT-000041 ADP MEL3393 - Updated Fire Protection Reg126 | 1 | 0 | KPTG-TRANSMIT-003635
Fredon T-TRANSMIT-000039 AV Shop Drawings for Approval | 4 | 0 | 0 | #742 | NXES-TRANSMIT-000087 ISC CONDUIT MARKUP FOR SCOREBOARD SYSTEM | 1 | 0 | KPTG-TRANSMIT-003637
P & R-TRANSMIT-000129 IFA Resubmission Pack | 8 | 0 | 0 | Rejected: Revisions are not updated:KPTG-SADV-006804 | NXES-TRANSMIT-000096 Security Layout- As IFA | 4 | 0 | KPTG-TRANSMIT-003638
Auspan-TRANSMIT-000153 Precast shop drawings for approval. Premium Precast panels. | 24 | 0 | 0 | WF-001287 | P & R-TRANSMIT-000129 IFA Resubmission Pack | 8 | 0 | KPTG-SADV-006804
Auspan-TRANSMIT-000154-Precast shop drawings for approval. Premium Precast panels. | 1 | 0 | 0 | workflow combined WF-001287 | BTWA-TRANSMIT-000107 MLC Stage 2 - Rev C Shop drawing reissue | 26 | 0 | KPTG-IntCorr-009004
BTWA-TRANSMIT-000107- MLC Stage 2 - Rev C Shop drawing reissue | 26 | 0 | 0 | WORKFLOW RESUBMITTED#:738
7 | 70 | 1 | 0 |  | 6 | 41 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
BTWA-TRANSMIT-000110 Requires confirmation-: MLC Stage 2 - Internal sample submission | 02.10.2026 | 6 | 6 | Kapitol Advice awaits: KPTG-SADV-006686

## 12.10.2026 (
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-12 | [5 empty] | Project: | MLCSPR
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
ARCH-TRANSMIT-000205 MLC - SPR - ISC - A2700 - Detail Wall section series update | 3 | 0 | 0 | #745 | BTWA-TRANSMIT-000107 MLC Stage 2 - Rev C Shop drawing reissue | 26 | 0 | Workflow Terminated & resubmitted: KPTG-TRANSMIT-003649
BTWA-TRANSMIT-000107 MLC Stage 2 - Rev C Shop drawing reissue | 26 | 0 | 0 | Workflow Resubmitted: #746 | Auspan-TRANSMIT-000145- precast shop drawings for approval due to architectural design change. | 12 | 0 | KPTG-TRANSMIT-003643
ECBS-TRANSMIT-000083 MLC Stage 2 - Tech Data | 0 | 12 | 0 | WF-001289 | BTWA-TRANSMIT-000107 MLC Stage 2 - Rev C Shop drawing reissue | 26 | 0 | KPTG-TRANSMIT-003652
BTWA-TRANSMIT-000112 MLC Curtain wall - Cast in Calcs - Stage 2 | 0 | 1 | 0 | Rejected: Incorrect Document Number | BTWA-TRANSMIT-000112 MLC Curtain wall - Cast in Calcs - Stage 2 | 1 | 0 | Rejected: KPTG-SADV-006823
BTWA-TRANSMIT-000113--MLC Curtain wall - Cast in Calcs - Stage 2 | 0 | 1 | 0 | WF-001291 | Auspan-TRANSMIT-000143 precast shop drawings for approval. Premium Precast | 12 | 0 | KPTG-TRANSMIT-003650
Auspan-TRANSMIT-000155 Precast lid shop drawing for approval. Premium Precast | 1 | 0 | 0 | WF-001292
Auspan-TRANSMIT-000156 Precast lid shop drawing for approval. Premium Precast | 1 | 0 | 0 | WF-001292 workflow combined
7 | 31 | 14 | 0 |  | 5 | 77 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
BTWA-TRANSMIT-000110 Requires confirmation-: MLC Stage 2 - Internal sample submission | 02.10.2026 | 6 | 6 | Kapitol Advice awaits: KPTG-SADV-006686

## 13.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-13 | [5 empty] | Project: | MLCSPR
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000157 | 12 | 0 | 0 | WF-001294 | Highbu-TRANSMIT-000167 | 3 | 0 | KPTG-TRANSMIT-003654
BTWA-TRANSMIT-000110 | 0 | 1 | 0 | WF-001295 | ARCH-TRANSMIT-000203 | 3 | 0 | KPTG-TRANSMIT-003656
2 | 12 | 1 | 0 |  | 2 | 6 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
BTWA-TRANSMIT-000110 Requires confirmation-: MLC Stage 2 - Internal sample submission | 02.10.2026 | 6 | 6 | Kapitol Advice awaits: KPTG-SADV-006686

## 14.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-14 | [5 empty] | Project: | MLCSPR
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
BTWA-TRANSMIT-000115 | 7 | 0 | 0 | #752 | Highbu-TRANSMIT-000167 | 5 | 0 | KPTG-TRANSMIT-003659
BTWA-TRANSMIT-000116 | 0 | 1 | 0 | WF-001298 | ARCH-TRANSMIT-000205 | 3 | 0 | KPTG-TRANSMIT-003662
[5 empty] | BTWA-TRANSMIT-000113 | 1 | 0 | KPTG-TRANSMIT-003664
2 | 7 | 1 | 0 |  | 3 | 9 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
BTWA-TRANSMIT-000110 Requires confirmation-: MLC Stage 2 - Internal sample submission | 02.10.2026 | 6 | 6 | Kapitol Advice awaits: KPTG-SADV-006686
SC-TRANSMIT-000060 | 2026-10-14 | 117 | 117 | No Stamp-KPTG-IntCorr-009036
Fredon T-TRANSMIT-000040 | 2026-10-14 | 7 | 7 | No Stamp - KPTG-IntCorr-009037
Auspan-TRANSMIT-000150 | 2026-10-14 | 9 | 9 | No Stamp-IntCorr-009038

## 15.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-15 | [5 empty] | Project: | MLCSPR
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000158 | 14 | 0 | 0 | WF-001299 | BTWA-TRANSMIT-000116 | 1 | 0 | Terminated-KPTG-TRANSMIT-003666
RDSBIM-TRANSMIT-000155 | 5 | 0 | 5 | KPTG-IntCorr-009050 | BTWA-TRANSMIT-000123 | 1 | 0 | KPTG-TRANSMIT-003667
BTWA-TRANSMIT-000123 | 0 | 1 | 0 | KPTG-TRANSMIT-003667 | Auspan-TRANSMIT-000149 | 5 | 0 | KPTG-TRANSMIT-003669
BTWA-TRANSMIT-000124 | 0 | 1 | 0 | KPTG-TRANSMIT-003671 | Auspan-TRANSMIT-000150 | 4 | 0 | KPTG-TRANSMIT-003668
NXES-TRANSMIT-000103 | 4 | 0 | 0 | #757 | BTWA-TRANSMIT-000124 | 1 | 0 | KPTG-TRANSMIT-003671
ARCH-TRANSMIT-000202 | 2 | 0 | 0 | #755 | ARCH-TRANSMIT-000202 | 4 | 0 | Terminated
ARCH-TRANSMIT-000207 | 7 | 0 | 0 | KPTG-TRANSMIT-003672 | ARCH-TRANSMIT-000207 | 7 | 0 | KPTG-TRANSMIT-003672
7 | 32 | 2 | 5 |  | 7 | 23 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
BTWA-TRANSMIT-000110 Requires confirmation-: MLC Stage 2 - Internal sample submission | 02.10.2026 | 6 | 6 | Kapitol Advice awaits: KPTG-SADV-006686
SC-TRANSMIT-000060 | 2026-10-14 | 117 | 117 | No Stamp-KPTG-IntCorr-009036
Fredon T-TRANSMIT-000040 | 2026-10-14 | 7 | 7 | No Stamp - KPTG-IntCorr-009037
KPTG-WTRAN-002364 | 2026-10-15 | 4 | 4 | No Stamp, Different status-KPTG-IntCorr-009045

## 16.10.2026
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-16 | [5 empty] | Project: | MLCSPR
Incoming Transmittals |  |  |  |  | Close out
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents | Remarks
ECBS-TRANSMIT-000085 MLC Stage 2 - Empire Tech Data | 0 | 9 | 0 | Transmitted to all trade partners for information:KPTG-TRANSMIT-003673 | ECBS-TRANSMIT-000083 MLC Stage 2 - Tech Data | 12 | 0 | Workflow terminated:KPTG-IntCorr-009059
ECBS-TRANSMIT-000085 MLC Stage 2 - Empire Tech Data | 0 | 2 | 0 | WF-001303 | Highbu-TRANSMIT-000166- HP-PM-SMP-053 - Civil drainage pipework 225mm & 300mm sample submission | 1 | 0 | workflow terminated & Resubmitted: KPTG-IntCorr-009064
BTWA-TRANSMIT-000128 MLC Stage 2 - Thermal calcs | 0 | 1 | 0 | WF-001304 | BTWA-TRANSMIT-000128 : MLC Stage 2 - Thermal calcs | 1 | 0 | KPTG-TRANSMIT-003677
ARCH-TRANSMIT-000208 MLC - SPR - ISC - Precast Panel elevation | 1 | 0 | 0 | #759 | Auspan-TRANSMIT-000152-Precast Column Dowel Plans | 1 | 0 | KPTG-TRANSMIT-003680
Highbu-TRANSMIT-000166- HP-PM-SMP-053 - Civil drainage pipework 225mm & 300mm sample submission | 0 | 1 | 0 | WF-001306 | NXES-TRANSMIT-000076 Nexus Tech Data - 123 and 201 | 1 | 0 | KPTG-TRANSMIT-003682
RDSBIM-TRANSMIT-000156- RDS - MLCSPR2 - CPN - IFC-#761 | 8 | 0 | 0 | #761 | P & R-TRANSMIT-000113- Updated CPEF-01 & Fan Schedule for IFC | 1 | 0 | KPTG-TRANSMIT-003683
KPTG-IntCorr-009063 Nexus Technical Submittals | 0 | 1 | 0 | WF-001308 | P & R-TRANSMIT-000122 P&R Tech Data bug fix up | 6 | 0 | KPTG-TRANSMIT-003685
SC-TRANSMIT-000060- -Indoor Sports IFC-III | 117 | 0 | 0 | WF-001309: workflow resubmitted | NXES-TRANSMIT-000100 Nexus Tech Data Sheets - Resubmission | 10 | 0 | KPTG-TRANSMIT-003687
RDSBIM-TRANSMIT-000155- MLCSPR ¦ INDOOR SPORTS CENTRE LEVEL 03 CONCRETE PROFILE PLAN-#763 | 5 | 0 | 0 | #763 | SC-TRANSMIT-000060 -Indoor Sports IFC-II | 113 | 0 | KPTG-TRANSMIT-003689
ARCH-TRANSMIT-000209 MLC - SPR - ISC - rectified attachments | 6 | 0 | 0 | #767 | SC-TRANSMIT-000060 Indoor Sports IFC-IV | 110 | 0 | KPTG-TRANSMIT-003691
ARCH-TRANSMIT-000210 MLC - SPR - ISC - Concrete drawing update | 3 | 0 | 0 | #769 | P & R-TRANSMIT-000118 -VRF STAGE 2 Amended 10.09.26 | 1 | 0 | KPTG-TRANSMIT-003693
ARCH-TRANSMIT-000211 MLC - SPR - ISC - A2712 update | 1 | 0 | 0 | #771 | Auspan-TRANSMIT-000148 - Precast shop drawings for construction. Columns on level 2 stage 2. Normal columns. | 4 | 0 | KPTG-TRANSMIT-003695
[5 empty] | SC-TRANSMIT-000060- Indoor Sports IFC-II | 83 | 0 | KPTG-TRANSMIT-003697
[5 empty] | SC-TRANSMIT-000060 -Indoor Sports IFC-III | 3 | 0 | KPTG-TRANSMIT-003699
[5 empty] | ECBS-TRANSMIT-000085 MLC Stage 2 - Empire Tech Data | 9 | 0 | KPTG-TRANSMIT-003673
[5 empty] | Fredon T-TRANSMIT-000040 AV Shop Drawings Complete IFC | 7 | 0 | KPTG-TRANSMIT-003704
[5 empty] | ARCH-TRANSMIT-000208 Re: MLC - SPR - ISC - Precast Panel elevation | 1 | 0 | KPTG-TRANSMIT-003706
12 | 141 | 14 | 0 |  | 17 | 364 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
BTWA-TRANSMIT-000110 Requires confirmation-: MLC Stage 2 - Internal sample submission | 02.10.2026 | 6 | 6 | Kapitol Advice awaits: KPTG-SADV-006686