## 10-16
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-16 | [5 empty] | Project: NXD1S2
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
ZIA-TRANSMIT-000084 | 0 | 21 | 0 | KPTG-IntCorr-003124: rejected | Endfire-TRANSMIT-000088 | 25 | 0 | KPTG-TRANSMIT-004474
Hames-TRANSMIT-000166 | 264 | 0 | 0 | KPTG-IntCorr-003125 : rejected | ZIA-TRANSMIT-000084 | 21 | 0 | KPTG-IntCorr-003124: rejected
Endfire-TRANSMIT-000088 | 25 | 0 | 0 | WF-001312 | Hames-TRANSMIT-000166 | 264 | 0 | KPTG-IntCorr-003125 : rejected
| 289 | 21 | 0 |  |  | 310 | 0
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
SKS Tech-TRANSMIT-000227 | 2026-10-02 | 1 | 1
VAE-Grp-TRANSMIT-000193 | 2026-09-25 | 1 | 1 | pending with Roy
Jordan-TRANSMIT-000136 | 2026-09-28 | 1 | 1 | pending with Hugh
3
SKS Tech-TRANSMIT-000212

## 10-15
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-15 | [5 empty] | Project: NXD1S2
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
SKS Tech-TRANSMIT-000260 | 6 | 0 | 0 | WF-001351 | SKS Tech-TRANSMIT-000222 | 13 | 0 | KPTG-TRANSMIT-004469
VAE-Grp-TRANSMIT-000196 | 1 | 0 | 0 | WF-001353 | VAE-Grp-TRANSMIT-000188 | 1 | 0 | voided
VAE-Grp-TRANSMIT-000199 | 0 | 6 | 0 | WF-001354 | VAE-Grp-TRANSMIT-000194 | 15 | 0 | voided
VAE-Grp-TRANSMIT-000202 | 0 | 6 | 0 | VAE-Grp-TRANSMIT-000199 - REPEATED | PARR-TRANSMIT-000073 | 1 | 0 | KPTG-TRANSMIT-004473
VAE-Grp-TRANSMIT-000207 | 0 | 6 | 0 | VAE-Grp-TRANSMIT-000199 - REPEATED | VAE-Grp-TRANSMIT-000202 | 6 | 0 | VAE-Grp-TRANSMIT-000199
ZIA-TRANSMIT-000081 | 0 | 1 | 0 | WF-001355 | VAE-Grp-TRANSMIT-000207 | 6 | 0 | VAE-Grp-TRANSMIT-000199
ZIA-TRANSMIT-000082 | 0 | 1 | 0 | rejected: KPTG-IntCorr-003117 | ZIA-TRANSMIT-000082 | 1 | 0 | rejected: KPTG-IntCorr-003117
| 7 | 20 | 0 |  |  | 43 | 0
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
SKS Tech-TRANSMIT-000227 | 2026-10-02 | 1 | 1
VAE-Grp-TRANSMIT-000193 | 2026-09-25 | 1 | 1 | pending with Roy
Jordan-TRANSMIT-000136 | 2026-09-28 | 1 | 1 | pending with Hugh
3
SKS Tech-TRANSMIT-000212

## 10-14
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-14 | [5 empty] | Project: NXD1S2
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
SKS Tech-TRANSMIT-000256 | 14 | 0 | 0 | #1380 | SKS Tech-TRANSMIT-000250 | 14 | 0 | KPTG-TRANSMIT-004446
SKS Tech-TRANSMIT-000257 | 2 | 0 | 0 | WF-001350 | SKS Tech-TRANSMIT-000224 | 8 | 0 | KPTG-TRANSMIT-004450
SKS Tech-TRANSMIT-000258 | 0 | 16 | 0 | KPTG-IntCorr-003103 - Hugh to clarify - forward to all parties - KPTG-TRANSMIT-004465 | SKS Tech-TRANSMIT-000204 | 1 | 0 | DRAFT-014680
SKS Tech-TRANSMIT-000259 | 0 | 6 | 0 | KPTG-IntCorr-003104 - Hugh to clarify - KPTG-TRANSMIT-004464 forward to all parties | CRSol-TRANSMIT-000058 | 12 | 0 | DRAFT-014681
NXT-WTRAN-000357 | 3 | 0 | 0 | wf-1329 | NXT-WTRAN-000357 | 3 | 0 | KPTG-TRANSMIT-004455
[5 empty] | SKS Tech-TRANSMIT-000235 | 2 | 0 | KPTG-TRANSMIT-004457
| 19 | 22 | 0 |  |  | 40 | 0
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
SKS Tech-TRANSMIT-000227 | 2026-10-02 | 1 | 1
VAE-Grp-TRANSMIT-000193 | 2026-09-25 | 1 | 1 | pending with Roy
Jordan-TRANSMIT-000136 | 2026-09-28 | 1 | 1 | pending with Hugh
3
SKS Tech-TRANSMIT-000212

## 10-13
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-13 | [5 empty] | Project: NXD1S2
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
SKS Tech-TRANSMIT-000254 | 1 | 0 | 0 | WF-001348 | SKS Tech-TRANSMIT-000201 - 1321 | 3 | 0 | KPTG-SADV-004455
SKS Tech-TRANSMIT-000255 | 0 | 14 | 0 | Already register updated with No Longer in Use version - hence no action | SKS Tech-TRANSMIT-000224 | 2 | 0 | KPTG-TRANSMIT-004440
GunAus-TRANSMIT-000014 | 17 | 0 | 0 | WF-001349 | SKS Tech-TRANSMIT-000234 | 1 | 0 | KPTG-TRANSMIT-004436
PARR-TRANSMIT-000077 | 0 | 1 | 0 | rejected: KPTG-TRANSMIT-004445 | PARR-TRANSMIT-000075 | 1 | 0 | KPTG-TRANSMIT-004432
[5 empty] | SKS Tech-TRANSMIT-000232 | 1 | 0 | KPTG-TRANSMIT-004428
[5 empty] | PARR-TRANSMIT-000077 | 1 | 0 | rejected: KPTG-TRANSMIT-004445
[5 empty] | SKS Tech-TRANSMIT-000255 | 14 | 0 | Already register updated with No Longer in Use version - hence no action
[5 empty] | Jordan-TRANSMIT-000132 | 5 | 0 | KPTG-TRANSMIT-004424
| 18 | 15 | 0 |  |  | 28 | 0
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
SKS Tech-TRANSMIT-000227 | 2026-10-02 | 1 | 1
VAE-Grp-TRANSMIT-000193 | 2026-09-25 | 1 | 1 | pending with Roy
Jordan-TRANSMIT-000136 | 2026-09-28 | 1 | 1 | pending with Hugh
3
SKS Tech-TRANSMIT-000212

## 10-12
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-12 | [5 empty] | Project: NXD1S2
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
NIL | 0 | 0 | 0 |  | VAE-Grp-TRANSMIT-000192 | 1 | 0 | KPTG-TRANSMIT-004416
[5 empty] | SKS Tech-TRANSMIT-000237 | 1 | 0 | KPTG-TRANSMIT-004420
| 0 | 0 | 0 |  |  | 2 | 0
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
SKS Tech-TRANSMIT-000227 | 2026-10-02 | 1 | 1
VAE-Grp-TRANSMIT-000193 | 2026-09-25 | 1 | 1 | pending with Roy
Jordan-TRANSMIT-000136 | 2026-09-28 | 1 | 1 | pending with Hugh
3
SKS Tech-TRANSMIT-000212

## 10-09
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-09 | [5 empty] | Project: NXD1S2
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
SKS Tech-TRANSMIT-000237 | 1 | 0 | 0 | #1372 | SKS Tech-TRANSMIT-000240 | 1 | 0 | KPTG-TRANSMIT-004406
SKS Tech-TRANSMIT-000240 | 0 | 1 | 0 | REGISTER UPDATED - FRWD TO ALL PARTIES - KPTG-TRANSMIT-004406 | SKS Tech-TRANSMIT-000239 | 1 | 0 | KPTG-TRANSMIT-004409
SKS Tech-TRANSMIT-000239 | 0 | 1 | 0 | REGISTER UPDATED - FRWD TO ALL PARTIES - KPTG-TRANSMIT-004409 | SKS Tech-TRANSMIT-000241 | 2 | 0 | KPTG-TRANSMIT-004409
SKS Tech-TRANSMIT-000241 | 0 | 2 | 0 | REGISTER UPDATED - FRWD TO ALL PARTIES - KPTG-TRANSMIT-004409 | SKS Tech-TRANSMIT-000242 | 2 | 0 | KPTG-TRANSMIT-004409
SKS Tech-TRANSMIT-000242 | 0 | 2 | 0 | REGISTER UPDATED - FRWD TO ALL PARTIES - KPTG-TRANSMIT-004409 | SKS Tech-TRANSMIT-000244 | 1 | 0 | SKS Tech-TRANSMIT-000239
SKS Tech-TRANSMIT-000244 | 0 | 1 | 0 | ALREADY PROCESSED - TRN#239 | SKS Tech-TRANSMIT-000245 | 1 | 0 | SKS Tech-TRANSMIT-000240
SKS Tech-TRANSMIT-000245 | 0 | 1 | 0 | ALREADY PROCESSED - TRN#240 | SKS Tech-TRANSMIT-000246 | 2 | 0 | SKS Tech-TRANSMIT-000241
SKS Tech-TRANSMIT-000246 | 0 | 2 | 0 | ALREADY PROCESSED - TRN#241 | SKS Tech-TRANSMIT-000247 | 2 | 0 | SKS Tech-TRANSMIT-000242
SKS Tech-TRANSMIT-000247 | 0 | 2 | 0 | ALREADY PROCESSED - TRN#242 | SKS Tech-TRANSMIT-000248 | 3 | 0 | KPTG-TRANSMIT-004412
SKS Tech-TRANSMIT-000248 | 0 | 3 | 0 | REGISTER UPDATED - FRWD TO ALL PARTIES - KPTG-TRANSMIT-004412 | SKS Tech-TRANSMIT-000249 | 4 | 0 | No longer in use - not in our register - hence no action
SKS Tech-TRANSMIT-000249 | 0 | 4 | 0 | No longer in use - not in our register - hence no action | 4Ki-TRANSMIT-000015 | 11 | 0 | terminated - new revision 4Ki-tran-16
SKS Tech-TRANSMIT-000250 | 14 | 0 | 0 | #1374
SKS Tech-TRANSMIT-000252 | 3 | 0 | 0 | WF-001338
SKS Tech-TRANSMIT-000253 | 5 | 0 | 0 | WF-001342
TCL-TRANSMIT-000006 | 7 | 0 | 0 | #1376
4Ki-TRANSMIT-000015 | 11 | 0 | 0 | terminated - new revision 4Ki-tran-16
4Ki-TRANSMIT-000016 | 11 | 0 | 0 | WF-001341
Hames-TRANSMIT-000165 | 1 | 0 | 0 | #1378
| 53 | 19 | 0 |  |  | 30 | 0
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
SKS Tech-TRANSMIT-000227 | 2026-10-02 | 1 | 1
VAE-Grp-TRANSMIT-000193 | 2026-09-25 | 1 | 1 | pending with Roy
Jordan-TRANSMIT-000136 | 2026-09-28 | 1 | 1 | pending with Hugh
3
SKS Tech-TRANSMIT-000212

## 10-08
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-08 | [5 empty] | Project: NXD1S2
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
SKS Tech-TRANSMIT-000224 | 2 | 0 | 0 | #1368 WF-001332 | NIL | 0 | 0
SKS Tech-TRANSMIT-000224 | 8 | 0 | 0 | #1370 WF-001333
SKS Tech-TRANSMIT-000235 | 1 | 0 | 0 | WF-001334
SKS Tech-TRANSMIT-000235 | 2 | 0 | 0 | WF-001335
VAE-Grp-TRANSMIT-000195 | 1 | 0 | 0 | WF-001336
| 14 | 0 | 0 |  |  | 0 | 0
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
SKS Tech-TRANSMIT-000227 | 2026-10-02 | 1 | 1
Jordan-TRANSMIT-000135 | 2026-09-22 | 7 | 0 | MORE CLARIFICATION FROM IBRAHIM - WF-001330
VAE-Grp-TRANSMIT-000193 | 2026-09-25 | 1 | 1 | pending with Roy
Jordan-TRANSMIT-000136 | 2026-09-28 | 1 | 1 | pending with Hugh
SKS Tech-TRANSMIT-000217 | 2026-09-30 | 1 | 0 | pending with Ibby - WF-001326
SKS Tech-TRANSMIT-000218 | 2026-09-30 | 1 | 0 | pending with Ibby - WF-001324
3
SKS Tech-TRANSMIT-000212

## 10-07
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-07 | [5 empty] | Project: NXD1S2
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
SKS Tech-TRANSMIT-000236 | 0 | 1 | 0 | WF-001323 | KPTG-IntCorr-003026 | 14 | 0 | Register updated
KPTG-IntCorr-003017 | 0 | 3 | 0 | WF-001327 | 4Ki-TRANSMIT-000014 | 11 | 0 | rejected: KPTG-TRANSMIT-004403
KPTG-IntCorr-003026 | 0 | 14 | 0 | Register updated
4Ki-TRANSMIT-000014 | 11 | 0 | 0 | rejected: KPTG-TRANSMIT-004403
| 11 | 18 | 0 |  |  | 25 | 0
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
SKS Tech-TRANSMIT-000227 | 2026-10-02 | 1 | 1
Jordan-TRANSMIT-000135 | 2026-09-22 | 7 | 0 | MORE CLARIFICATION FROM IBRAHIM - WF-001330
VAE-Grp-TRANSMIT-000193 | 2026-09-25 | 1 | 1 | pending with Roy
Jordan-TRANSMIT-000136 | 2026-09-28 | 1 | 1 | pending with Hugh
SKS Tech-TRANSMIT-000217 | 2026-09-30 | 1 | 0 | pending with Ibby - WF-001326
SKS Tech-TRANSMIT-000218 | 2026-09-30 | 1 | 0 | pending with Ibby - WF-001324
3
SKS Tech-TRANSMIT-000212

## 10-06
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-06 | [5 empty] | Project: NXD1S2
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
SKS Tech-TRANSMIT-000232 | 1 | 0 | 0 | #1362, WF-001331 | SKS Tech-TRANSMIT-000221 | 4 | 0 | KPTG-TRANSMIT-004397
SKS Tech-TRANSMIT-000233 | 13 | 0 | 0 | WF-001319 | SKS Tech-TRANSMIT-000235 | 16 | 0 | REJECTED: KPTG-TRANSMIT-004401
PARR-TRANSMIT-000074 | 2 | 0 | 0 | WF-001320 | Rinco-TRANSMIT-000029 | 237 | 0 | rejected: KPTG-TRANSMIT-004402
PARR-TRANSMIT-000075 | 1 | 0 | 0 | #1364, WF-001321
SKS Tech-TRANSMIT-000234 | 1 | 0 | 0 | #1366, WF-001322
SKS Tech-TRANSMIT-000235 | 16 | 0 | 0 | REJECTED: KPTG-TRANSMIT-004401
Rinco-TRANSMIT-000029 | 237 | 0 | 0 | rejected: KPTG-TRANSMIT-004402
| 271 | 0 | 0 |  |  | 257 | 0
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
SKS Tech-TRANSMIT-000227 | 2026-10-02 | 1 | 1
Jordan-TRANSMIT-000135 | 2026-09-22 | 7 | 7 | MORE CLARIFICATION FROM IBRAHIM
VAE-Grp-TRANSMIT-000193 | 2026-09-25 | 1 | 1 | pending with Roy
Jordan-TRANSMIT-000136 | 2026-09-28 | 1 | 1 | pending with Hugh
SKS Tech-TRANSMIT-000217 | 2026-09-30 | 1 | 1 | pending with Ibby
SKS Tech-TRANSMIT-000218 | 2026-09-30 | 1 | 1 | pending with Ibby
12
SKS Tech-TRANSMIT-000212

## 10-05
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-05 | [5 empty] | Project: NXD1S2
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
SKS Tech-TRANSMIT-000230 | 1 | 0 | 0 | rejected : KPTG-TRANSMIT-004386 | SKS Tech-TRANSMIT-000230 | 1 | 0 | rejected : KPTG-TRANSMIT-004386
SKS Tech-TRANSMIT-000229 | 13 | 0 | 0 | # 1360 | SKS Tech-TRANSMIT-000228 | 3 | 0 | rejected : KPTG-TRANSMIT-004388
SKS Tech-TRANSMIT-000231 | 0 | 4 | 0 | WF-001316 | SKS Tech-TRANSMIT-000229 | 13 | 0 | KPTG-TRANSMIT-004389
SKS Tech-TRANSMIT-000228 | 3 | 0 | 0 | rejected : KPTG-TRANSMIT-004388 | SKS Tech-TRANSMIT-000227 | 1 | 0 | KPTG-TRANSMIT-004393
| 17 | 4 | 0 |  |  | 18 | 0
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
SKS Tech-TRANSMIT-000227 | 2026-10-02 | 1 | 1
Jordan-TRANSMIT-000135 | 2026-09-22 | 7 | 7 | MORE CLARIFICATION FROM IBRAHIM
VAE-Grp-TRANSMIT-000193 | 2026-09-25 | 1 | 1 | pending with Roy
Jordan-TRANSMIT-000136 | 2026-09-28 | 1 | 1 | pending with Hugh
SKS Tech-TRANSMIT-000217 | 2026-09-30 | 1 | 1 | pending with Ibby
SKS Tech-TRANSMIT-000218 | 2026-09-30 | 1 | 1 | pending with Ibby
12
SKS Tech-TRANSMIT-000212

## 10-02
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-02 | [5 empty] | Project: NXD1S2
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
SKS Tech-TRANSMIT-000225 | 39 | 0 | 0 | WF-001310 | PARR-TRANSMIT-000066 | 17 | 0 | KPTG-TRANSMIT-004375
SKS Tech-TRANSMIT-000226 | 13 | 0 | 0 | #1356 | SKS Tech-TRANSMIT-000226 | 13 | 0 | KPTG-TRANSMIT-004379
Endfire-TRANSMIT-000088 | 25 | 0 | 0 | WF-001312 | Jordan-TRANSMIT-000137 | 14 | 0 | rejected :KPTG-TRANSMIT-004383
Jordan-TRANSMIT-000137 | 14 | 0 | 0 | rejected :KPTG-TRANSMIT-004383 | SKS Tech-TRANSMIT-000223 | 2 | 0 | KPTG-TRANSMIT-004384
SKS Tech-TRANSMIT-000227 | 1 | 0 | 0 | # 1358
SKS Tech-TRANSMIT-000227 | 1 | 0 | 1 | Harry/Hugh to confirm - KPTG-IntCorr-002979
| 93 | 0 | 1 |  |  | 46 | 0
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
SKS Tech-TRANSMIT-000227 | 2026-10-02 | 1 | 1
Jordan-TRANSMIT-000135 | 2026-09-22 | 7 | 7 | MORE CLARIFICATION FROM IBRAHIM
VAE-Grp-TRANSMIT-000193 | 2026-09-25 | 1 | 1 | pending with Roy
Jordan-TRANSMIT-000136 | 2026-09-28 | 1 | 1 | pending with Hugh
SKS Tech-TRANSMIT-000217 | 2026-09-30 | 1 | 1 | pending with Ibby
SKS Tech-TRANSMIT-000218 | 2026-09-30 | 1 | 1 | pending with Ibby
12
SKS Tech-TRANSMIT-000212

## 10-01
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-01 | [5 empty] | Project: NXD1S2
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
SKS Tech-TRANSMIT-000223 | 2 | 0 |  | #1350 | SKS Tech-TRANSMIT-000224 | 12 |  | rejected: KPTG-TRANSMIT-004368
SKS Tech-TRANSMIT-000222 | 13 | 0 | 0 | KPTG-IntCorr-002954: Hugh to confirm WF-001309 | KPTG-WTRAN-002547 | 1 |  | KPTG-TRANSMIT-004369
Endfire-TRANSMIT-000087 | 7 | 0 |  | #1353
SKS Tech-TRANSMIT-000224 | 12 | 0 |  | rejected: KPTG-TRANSMIT-004368
KPTG-IntCorr-002926 | 0 | 3 |  | WF-001308
| 34 | 3 | 0 |  |  | 13 | 0
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
0