## 1
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-01 | [5 empty] | Project: | NXM3S4
Incoming Transmittals |  |  |  |  | Close out Transmittals
Transmittal No. | No. of Drawings | No. of Technical data | Pending No. of Documents | Remarks | Transmittal No. | No. of DOCUMENTS | Pending No. of Documents | Remarks
D&E-TRANSMIT-001110 |  | 1 |  | KPTG-DA-008965 | ARCST-TRANSMIT-000317 | 135 |  | KPTG-TRANSMIT-022601
SKS Tech-TRANSMIT-000238 |  | 1 |  | KPTG-DA-008966 | ARCST-TRANSMIT-000323 | 125 |  | KPTG-TRANSMIT-022568
D&E-TRANSMIT-001111 |  | 1 |  | WF-007102 | ARCST-TRANSMIT-000318 | 168 |  | KPTG-TRANSMIT-022609
SKS Tech-TRANSMIT-000240 | 8 |  |  | 4543 | ARCST-TRANSMIT-000322 | 116 |  | KPTG-TRANSMIT-022560
SKS Tech-TRANSMIT-000237 |  | 1 |  | WF-007104 | ARCST-TRANSMIT-000325 | 132 |  | KPTG-TRANSMIT-022589
Nilsen3-TRANSMIT-000297 | 1 |  |  | 4545 | ARCST-TRANSMIT-000327 | 156 |  | KPTG-TRANSMIT-022581
SMEPS-TRANSMIT-000423 | 4 |  |  | 4549 | ARCST-TRANSMIT-000339 | 4 |  | KPTG-TRANSMIT-022547
SMEPS-TRANSMIT-000423 | 4 |  |  | 4550 | SMEPS-TRANSMIT-000347 | 3 |  | KPTG-TRANSMIT-022511
SKS Tech-TRANSMIT-000239 |  | 1 |  | KPTG-TRANSMIT-022546 | ARCST-TRANSMIT-000348 | 187 |  | KPTG-TRANSMIT-022529
D&E-TRANSMIT-001113 |  | 1 |  | WF-007138 | ARCST-TRANSMIT-000346 | 154 |  | KPTG-TRANSMIT-022525
CTAGroup-TRANSMIT-000002 | 20 |  |  | KPTG-TRANSMIT-022579 | SMEPS-TRANSMIT-000355 | 9 |  | KPTG-TRANSMIT-022517
[5 empty] | ARCST-TRANSMIT-000354 | 142 |  | KPTG-TRANSMIT-022505
[5 empty] | ARCST-TRANSMIT-000357 | 158 |  | KPTG-TRANSMIT-022530
[5 empty] | ARCST-TRANSMIT-000362 | 32 |  | KPTG-TRANSMIT-022580
[5 empty] | ARCST-TRANSMIT-000367 | 168 |  | KPTG-TRANSMIT-022500
[5 empty] | ARCST-TRANSMIT-000370 | 126 |  | KPTG-TRANSMIT-022486
[5 empty] | ARCST-TRANSMIT-000371 | 132 |  | KPTG-TRANSMIT-022493
[5 empty] | SMEPS-TRANSMIT-000383 | 1 |  | KPTG-TRANSMIT-022542
[5 empty] | SMEPS-TRANSMIT-000389 | 1 |  | KPTG-TRANSMIT-022538
[5 empty] | SMEPS-TRANSMIT-000391 | 1 |  | KPTG-TRANSMIT-022509
[5 empty] | ARCST-TRANSMIT-000397 | 44 |  | KPTG-TRANSMIT-022478
[5 empty] | Diadem-TRANSMIT-000028 | 11 |  | KPTG-TRANSMIT-022561
[5 empty] | D&E-TRANSMIT-001084 | 1 |  | KPTG-TRANSMIT-022483
[5 empty] | TTW-TRANSMIT-000229 | 1 |  | KPTG-TRANSMIT-022521
[5 empty] | ADP-TRANSMIT-000450 | 1 |  | KPTG-TRANSMIT-022548
[5 empty] | D&E-TRANSMIT-001110 | 1 |  | KPTG-DA-008965
[5 empty] | SKS Tech-TRANSMIT-000238 | 1 |  | KPTG-DA-008966
[5 empty] | SKS Tech-TRANSMIT-000239 | 1 |  | KPTG-TRANSMIT-022546
[5 empty] | ARCST-TRANSMIT-000358 | 117 |  | KPTG-TRANSMIT-022556
[5 empty] | CTAGroup-TRANSMIT-000002 | 20 |  | KPTG-TRANSMIT-022579
TOTAL | 37 | 6 | 0 |  | TOTAL | 2148
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
TOTAL

## 2
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-02 | [5 empty] | Project: | NXM3S4
Incoming Transmittals |  |  |  |  | Close out Transmittals
Transmittal No. | No. of Drawings | No. of Technical data | Pending No. of Documents | Remarks | Transmittal No. | No. of DOCUMENTS | Pending No. of Documents | Remarks
KPTG-WTRAN-013614 | 1 |  |  | WF-007140 | ARCST-TRANSMIT-000356 | 136 |  | KPTG-TRANSMIT-022641
SKS Tech-TRANSMIT-000241 |  | 1 |  | WF-007141 | ARCST-TRANSMIT-000368 | 141 |  | KPTG-TRANSMIT-022645
SKS Tech-TRANSMIT-000242 |  | 2 |  | WF-007142 | D&E-TRANSMIT-001079 | 1 |  | KPTG-TRANSMIT-022650
KPTG-WTRAN-013617 |  | 1 |  | WF-007143 | DS-TRANSMIT-000127 | 27 |  | KPTG-TRANSMIT-022666
prime ts-TRANSMIT-000003 |  | 9 |  | WF-007145
D&E-TRANSMIT-001114 |  | 1 |  | WF-007146
D&E-TRANSMIT-001115 |  | 1 |  | WF-007147
HDRAus-TRANSMIT-000584 | 15 |  |  | 4570
DS-TRANSMIT-000127 | 27 |  |  | KPTG-TRANSMIT-022666
TOTAL | 43 | 15 | 0 |  | TOTAL | 305
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
TOTAL

## 5
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-05 | [5 empty] | Project: | NXM3S4
Incoming Transmittals |  |  |  |  | Close out Transmittals
Transmittal No. | No. of Drawings | No. of Technical data | Pending No. of Documents | Remarks | Transmittal No. | No. of DOCUMENTS | Pending No. of Documents | Remarks
Altaire-TRANSMIT-000135 | 1 |  |  | 4574 | PFP PL-TRANSMIT-000117 | 1 |  | KPTG-TRANSMIT-022671
PFP PL-TRANSMIT-000117 | 1 |  |  | KPTG-TRANSMIT-022671 | SMEPS-TRANSMIT-000425 | 4 |  | KPTG-DA-009028
SMEPS-TRANSMIT-000425 | 4 |  |  | KPTG-DA-009028 | CRSol-TRANSMIT-000085 | 19 |  | KPTG-TRANSMIT-022684
D&E-TRANSMIT-001117 | 22 |  |  | KPTG-DA-009032 | PROLMC-TRANSMIT-000046 | 9 |  | KPTG-TRANSMIT-022708
CTAGroup-RTRFI-000002 | 20 |  |  | KPTG-DA-009021 | ZIA-TRANSMIT-000114 | 1 |  | KPTG-TRANSMIT-022682
D&E-TRANSMIT-001116 | 1 |  |  | KPTG-TRANSMIT-022680 | ZIA-TRANSMIT-000184 | 1 |  | KPTG-TRANSMIT-022681
SKS Tech-TRANSMIT-000243 |  | 1 |  | KPTG-DA-009020 | D&E-TRANSMIT-001101 | 3 |  | KPTG-TRANSMIT-022672
ZIA-TRANSMIT-000194 |  | 1 |  | KPTG-TRANSMIT-022712 | D&E-TRANSMIT-001117 | 22 |  | KPTG-DA-009032
[5 empty] | CTAGroup-RTRFI-000002 | 20 |  | KPTG-DA-009021
[5 empty] | D&E-TRANSMIT-001116 | 1 |  | KPTG-TRANSMIT-022680
[5 empty] | SKS Tech-TRANSMIT-000243 | 1 |  | KPTG-DA-009020
[5 empty] | Mirage D-TRANSMIT-000024 | 10 |  | KPTG-TRANSMIT-022697
[5 empty] | SMEPS-TRANSMIT-000322 | 1 |  | KPTG-TRANSMIT-022692
[5 empty] | ZIA-TRANSMIT-000194 | 1 |  | KPTG-TRANSMIT-022712
TOTAL | 49 | 2 | 0 |  | TOTAL | 94
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
TOTAL

## 6
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-06 | [5 empty] | Project: | NXM3S4
Incoming Transmittals |  |  |  |  | Close out Transmittals
Transmittal No. | No. of Drawings | No. of Technical data | Pending No. of Documents | Remarks | Transmittal No. | No. of DOCUMENTS | Pending No. of Documents | Remarks
D&E-TRANSMIT-001118 |  | 1 |  | KPTG-DA-009038 | SMEPS-TRANSMIT-000345 | 3 |  | KPTG-TRANSMIT-022736
D&E-TRANSMIT-001119 |  | 1 |  | WF-007161 | SMEPS-TRANSMIT-000354 | 2 |  | KPTG-TRANSMIT-022744
ZIA-TRANSMIT-000196 | 3 |  |  | 4587 | SKS Tech-TRANSMIT-000228 | 4 |  | ⁠KPTG-TRANSMIT-022734
Nilsen3-TRANSMIT-000299 | 1 |  |  | 4579 | ZIA-TRANSMIT-000191 | 1 |  | KPTG-TRANSMIT-022723
D&E-TRANSMIT-001120 |  | 1 |  | WF-007167 | ZIA-TRANSMIT-000190 | 9 |  | KPTG-TRANSMIT-022730
D&E-TRANSMIT-001121 |  | 2 |  | WF-007169 | SKS Tech-TRANSMIT-000230 | 1 |  | KPTG-TRANSMIT-022742
Nilsen3-TRANSMIT-000298 |  | 1 |  | KPTG-TRANSMIT-022729 | Nilsen3-TRANSMIT-000294 | 1 |  | KPTG-TRANSMIT-022717
ZIA-TRANSMIT-000195 | 3 |  |  | 4577 | ZIA-TRANSMIT-000195 | 3 |  | KPTG-DA-009060
DS-TRANSMIT-000129 | 1 |  |  | KPTG-DA-009062 | SKS Tech-TRANSMIT-000234 | 1 |  | KPTG-TRANSMIT-022722
ADP-TRANSMIT-000452 | 1 |  |  | 4581 | D&E-TRANSMIT-001118 | 1 |  | KPTG-DA-009038
ADP-TRANSMIT-000452 | 7 |  |  | 4583 | Nilsen3-TRANSMIT-000298 | 1 |  | KPTG-TRANSMIT-022729
ADP-TRANSMIT-000452 | 2 |  |  | 4585 | DS-TRANSMIT-000129 | 1 |  | KPTG-DA-009062
DS-TRANSMIT-000128 | 3 |  |  | KPTG-DA-009068 | DS-TRANSMIT-000128 | 3 |  | KPTG-DA-009068
ASV-TRANSMIT-000203 |  | 1 |  | WF-007166 | SMEPS-TRANSMIT-000363 | 2 |  | KPTG-TRANSMIT-022750
TOTAL | 21 | 7 | 0 |  | TOTAL | 33
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
TOTAL

## 7
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-07 | [5 empty] | Project: | NXM3S4
Incoming Transmittals |  |  |  |  | Close out Transmittals
Transmittal No. | No. of Drawings | No. of Technical data | Pending No. of Documents | Remarks | Transmittal No. | No. of DOCUMENTS | Pending No. of Documents | Remarks
Altaire-TRANSMIT-000136 | 1 |  |  | 4591 | NXT-TRANSMIT-001681 | 5 |  | ⁠KPTG-TRANSMIT-022800
DS-TRANSMIT-000130 | 1 |  |  | 4589 | HDRAus-TRANSMIT-000584 | 15 |  | KPTG-TRANSMIT-022801
ADP-TRANSMIT-000454 |  | 1 |  | KPTG-DA-009079 | ZIA-TRANSMIT-000196 | 3 |  | KPTG-DA-009078
KPTG-TRANSMIT-022727 | 12 |  |  | 4594 | ADP-TRANSMIT-000454 | 1 |  | KPTG-DA-009079
CTAGroup-TRANSMIT-000003 | 15 |  |  | 4597 | ADP-TRANSMIT-000453 | 2 |  | KPTG-TRANSMIT-022779
ADP-TRANSMIT-000453 |  | 2 |  | KPTG-TRANSMIT-022779 | SMEPS-TRANSMIT-000426 | 1 |  | KPTG-DA-009091
SMEPS-TRANSMIT-000426 |  | 1 |  | KPTG-DA-009091 | D&E-TRANSMIT-001123 | 2 |  | KPTG-IntCorr-019697
PFP PL-TRANSMIT-000117 | 1 |  |  | 4596 | ADP-TRANSMIT-000455 | 1 |  | KPTG-TRANSMIT-022793
D&E-TRANSMIT-001123 |  | 2 |  | KPTG-IntCorr-019697 | ZIA-TRANSMIT-000198 | 3 |  | KPTG-DA-009093
Nilsen3-TRANSMIT-000300 |  | 1 |  | WF-007190 | ADP-TRANSMIT-000456 | 1 |  | KPTG-TRANSMIT-022784
ADP-TRANSMIT-000455 |  | 1 |  | KPTG-TRANSMIT-022793
ZIA-TRANSMIT-000198 | 3 |  |  | KPTG-DA-009093
ADP-TRANSMIT-000456 |  | 1 |  | KPTG-TRANSMIT-022784
TOTAL | 33 | 9 | 0 |  | TOTAL | 34
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
TOTAL

## 8
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-08 | [5 empty] | Project: | NXM3S4
Incoming Transmittals |  |  |  |  | Close out Transmittals
Transmittal No. | No. of Drawings | No. of Technical data | Pending No. of Documents | Remarks | Transmittal No. | No. of DOCUMENTS | Pending No. of Documents | Remarks
D&E-TRANSMIT-001124 |  | 1 |  | KPTG-IntCorr-019714 | SKS Tech-TRANSMIT-000180 | 4 |  | KPTG-TRANSMIT-022809
D&E-TRANSMIT-001125 |  | 1 |  | KPTG-IntCorr-019715 | D&E-TRANSMIT-001096 | 4 |  | KPTG-TRANSMIT-022833
D&E-TRANSMIT-001126 |  | 1 |  | KPTG-RFI-010047 | KPTG-WTRAN-013387 | 6 |  | KPTG-TRANSMIT-022841
D&E-TRANSMIT-001127 |  | 1 |  | KPTG-TRANSMIT-022805 | Nilsen3-TRANSMIT-000293 | 7 |  | KPTG-TRANSMIT-022824
DS-TRANSMIT-000131 | 3 |  |  | 4599 | ADP-TRANSMIT-000452 | 1 |  | KPTG-TRANSMIT-022837
D&E-TRANSMIT-001128 |  | 1 |  | KPTG-IntCorr-019732 | D&E-TRANSMIT-001124 | 1 |  | KPTG-IntCorr-019714
D&E-TRANSMIT-001129 |  | 1 |  | KPTG-TRANSMIT-022829 | D&E-TRANSMIT-001125 | 1 |  | KPTG-IntCorr-019715
SKS Tech-TRANSMIT-000244 | 8 |  |  | 4604 | D&E-TRANSMIT-001126 | 1 |  | KPTG-RFI-010047
ZIA-TRANSMIT-000201 | 3 |  |  | 4602 | D&E-TRANSMIT-001127 | 1 |  | KPTG-TRANSMIT-022805
ZIA-TRANSMIT-000202 | 1 |  |  | 4605 | D&E-TRANSMIT-001128 | 1 |  | KPTG-IntCorr-019732
ADP-TRANSMIT-000458 | 2 |  |  | KPTG-DA-009114 | D&E-TRANSMIT-001129 | 1 |  | KPTG-TRANSMIT-022829
SMEPS-TRANSMIT-000428 |  | 1 |  | KPTG-DA-009115 | ADP-TRANSMIT-000458 | 2 |  | KPTG-DA-009114
SMEPS-TRANSMIT-000427 |  | 1 |  | KPTG-DA-009117 | SMEPS-TRANSMIT-000428 | 1 |  | KPTG-DA-009115
[5 empty] | SMEPS-TRANSMIT-000427 | 1 |  | KPTG-DA-009117
[5 empty] | Nilsen3-TRANSMIT-000225 | 1 |  | KPTG-TRANSMIT-022819
TOTAL | 17 | 8 | 0 |  | TOTAL | 33
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
TOTAL

## 9
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-09 | [5 empty] | Project: | NXM3S4
Incoming Transmittals |  |  |  |  | Close out Transmittals
Transmittal No. | No. of Drawings | No. of Technical data | Pending No. of Documents | Remarks | Transmittal No. | No. of DOCUMENTS | Pending No. of Documents | Remarks
RDSBIM-TRANSMIT-000325 | 3 |  |  | 4607 | D&E-TRANSMIT-000794 | 2 |  | KPTG-TRANSMIT-022867
ADP-TRANSMIT-000459 |  | 2 |  | KPTG-TRANSMIT-022852 | ARCST-TRANSMIT-000391 | 29 |  | KPTG-TRANSMIT-022857
ZIA-TRANSMIT-000197 |  | 1 |  | KPTG-DA-009129 | HDRAus-TRANSMIT-000582 | 17 |  | KPTG-TRANSMIT-022859
Altaire-TRANSMIT-000137 |  | 1 |  | KPTG-IntCorr-019784 | KPTG-TRANSMIT-022727 | 12 |  | NA
ZIA-TRANSMIT-000203 |  | 1 |  | WF-007236 | ADP-TRANSMIT-000459 | 2 |  | KPTG-TRANSMIT-022852
D&E-TRANSMIT-001130 |  | 1 |  | KPTG-DA-009140 | ZIA-TRANSMIT-000197 | 1 |  | KPTG-DA-009129
SMEPS-TRANSMIT-000429 | 4 |  |  | KPTG-DA-009142 | Altaire-TRANSMIT-000137 | 1 |  | KPTG-IntCorr-019784
ARCST-TRANSMIT-000307 | 1 |  |  | WF-007239 | D&E-TRANSMIT-001130 | 1 |  | KPTG-DA-009140
Altaire-TRANSMIT-000138 |  | 1 |  | KPTG-DA-009141 | SMEPS-TRANSMIT-000429 | 1 |  | KPTG-DA-009142
ADP-TRANSMIT-000460 |  | 1 |  | KPTG-TRANSMIT-022873 | ARCST-TRANSMIT-000294 | 8 |  | KPTG-TRANSMIT-022863
HDRAus-TRANSMIT-000589 | 20 |  |  | 4607 | Altaire-TRANSMIT-000138 | 1 |  | KPTG-DA-009141
ZIA-TRANSMIT-000204 |  | 1 |  | KPTG-IntCorr-019806 | ADP-TRANSMIT-000460 | 1 |  | KPTG-TRANSMIT-022873
[5 empty] | ZIA-TRANSMIT-000204 | 1 |  | KPTG-IntCorr-019806
TOTAL | 28 | 9 | 0 |  | TOTAL | 77
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
TOTAL

## 12
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-12 | [5 empty] | Project: | NXM3S4
Incoming Transmittals |  |  |  |  | Close out Transmittals
Transmittal No. | No. of Drawings | No. of Technical data | Pending No. of Documents | Remarks | Transmittal No. | No. of DOCUMENTS | Pending No. of Documents | Remarks
D&E-TRANSMIT-001117 | 18 |  |  | 4616 | Rinco-TRANSMIT-000007 | 5 |  | KPTG-TRANSMIT-022948
SMEPS-TRANSMIT-000429 | 4 |  |  | KPTG-DA-009142 | D&E-TRANSMIT-000902 | 1 |  | KPTG-TRANSMIT-022890
D&E-TRANSMIT-001133 | 4 |  |  | 4618 | D&E-TRANSMIT-000907 | 1 |  | KPTG-TRANSMIT-022886
D&E-TRANSMIT-001135 |  | 1 |  | KPTG-DA-009161 | Tradetec-TRANSMIT-000487 | 1 |  | KPTG-TRANSMIT-022919
D&E-TRANSMIT-001136 |  | 1 |  | WF-007245 | Lclad-TRANSMIT-000005 | 8 |  | KPTG-TRANSMIT-022930
D&E-TRANSMIT-001137 |  | 1 |  | WF-007246 | PFP PL-TRANSMIT-000113 | 3 |  | KPTG-TRANSMIT-022879
D&E-TRANSMIT-001139 |  | 1 |  | WF-007248 | ZIA-TRANSMIT-000192 | 1 |  | KPTG-TRANSMIT-022940
SMEPS-TRANSMIT-000429 | 4 |  |  | 4614 | SKS Tech-TRANSMIT-000240 | 8 |  | KPTG-TRANSMIT-022949
KPTG-WTRAN-013785 | 4 |  |  | 4619 | SMEPS-TRANSMIT-000423 | 4 |  | KPTG-TRANSMIT-022959
ADP-TRANSMIT-000461 |  | 1 |  | ⁠KPTG-TRANSMIT-022958 | SMEPS-TRANSMIT-000423 | 4 |  | KPTG-TRANSMIT-022896
D&E-TRANSMIT-001134 |  | 1 |  | KPTG-DA-009176 | D&E-TRANSMIT-001115 | 1 |  | KPTG-IntCorr-019829
Altaire-TRANSMIT-000139 |  | 1 |  | WF-007241 | ADP-TRANSMIT-000452 | 7 |  | KPTG-TRANSMIT-022963
SMEPS-TRANSMIT-000430 |  | 1 |  | WF-007244 | ADP-TRANSMIT-000452 | 2 |  | KPTG-TRANSMIT-022944
HDRAus-TRANSMIT-000591 | 4 |  |  | KPTG-DA-009164 | HDRAus-TRANSMIT-000589 | 20 |  | KPTG-TRANSMIT-022968
SKS Tech-TRANSMIT-000245 |  | 1 |  | KPTG-TRANSMIT-022972 | D&E-TRANSMIT-001135 | 1 |  | KPTG-DA-009161
OveArup-TRANSMIT-000222 |  | 1 |  | KPTG-TRANSMIT-022934 | ADP-TRANSMIT-000461 | 1 |  | ⁠KPTG-TRANSMIT-022958
[5 empty] | D&E-TRANSMIT-001134 | 1 |  | KPTG-DA-009176
[5 empty] | HDRAus-TRANSMIT-000591 | 4 |  | KPTG-DA-009164
[5 empty] | SKS Tech-TRANSMIT-000245 | 1 |  | KPTG-TRANSMIT-022972
[5 empty] | OveArup-TRANSMIT-000222 | 1 |  | KPTG-TRANSMIT-022934
TOTAL | 38 | 10 | 0 |  | TOTAL | 75
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
TOTAL

## 13
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-13 | [5 empty] | Project: | NXM3S4
Incoming Transmittals |  |  |  |  | Close out Transmittals
Transmittal No. | No. of Drawings | No. of Technical data | Pending No. of Documents | Remarks | Transmittal No. | No. of DOCUMENTS | Pending No. of Documents | Remarks
Altaire-TRANSMIT-000140 | 2 |  |  | 4626 | SKS Tech-TRANSMIT-000184 | 1 |  | KPTG-TRANSMIT-022982
SMEPS-TRANSMIT-000421 | 1 |  |  | KPTG-DA-009182 | KPTG-WTRAN-013288 | 16 |  | NA
D&E-TRANSMIT-001141 | 4 |  |  | 4622 | D&E-TRANSMIT-001139 | 1 |  | NA
SKS Tech-TRANSMIT-000246 | 3 |  |  | 4624 | KPTG-WTRAN-013785 | 4 |  | KPTG-TRANSMIT-023003
D&E-TRANSMIT-001142 |  | 1 |  | WF-007263 | SMEPS-TRANSMIT-000421 | 1 |  | KPTG-DA-009182
Nilsen3-TRANSMIT-000301 | 2 |  |  | 4628 | SMEPS-TRANSMIT-000422 | 1 |  | KPTG-DA-009196
SMEPS-TRANSMIT-000422 | 1 |  |  | KPTG-DA-009196 | ADP-TRANSMIT-000463 | 2 |  | KPTG-TRANSMIT-022995
Nilsen3-TRANSMIT-000301 | 2 |  |  | 4630 | BVPI-TRANSMIT-000013 | 1 |  | NA
ADP-TRANSMIT-000463 |  | 2 |  | KPTG-TRANSMIT-022995 | ADP-TRANSMIT-000465 | 19 |  | KPTG-DA-009206
BVPI-TRANSMIT-000013 |  | 1 |  | NA | ADP-TRANSMIT-000464 | 17 |  | KPTG-DA-009207
Syfon1-TRANSMIT-000015 | 4 |  |  | 4632
KPTG-WTRAN-013288 | 16 |  |  | 4639
ACG-TRANSMIT-000139 | 4 |  |  | 4634
ADP-TRANSMIT-000462 | 1 |  |  | 4636
SKS Tech-TRANSMIT-000219 | 1 |  |  | 4638
ADP-TRANSMIT-000465 | 19 |  |  | KPTG-DA-009206
ADP-TRANSMIT-000464 | 17 |  |  | KPTG-DA-009207
TOTAL | 77 | 4 | 0 |  | TOTAL | 63
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
TOTAL

## 14
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-14 | [5 empty] | Project: | NXM3S4
Incoming Transmittals |  |  |  |  | Close out Transmittals
Transmittal No. | No. of Drawings | No. of Technical data | Pending No. of Documents | Remarks | Transmittal No. | No. of DOCUMENTS | Pending No. of Documents | Remarks
SMEPS-TRANSMIT-000432 |  | 1 |  | KPTG-DA-009227 | ZIA-TRANSMIT-000188 | 1 |  | NA | Terminated as per Damian Lauricella request - new revision with comments actioned ready to be issued
ADP-TRANSMIT-000466 | 19 |  |  | KPTG-DA-009232 | ACG-TRANSMIT-000138 | 14 |  | KPTG-DA-009223 | Voided requested by Kazimir
D&E-TRANSMIT-001144 | 4 |  |  | 4641 | SKS Tech-TRANSMIT-000235 | 19 |  | NA | Voided requested by Kazimir
D&E-TRANSMIT-001145 | 2 |  |  | KPTG-DA-009213 | ZIA-TRANSMIT-000201 | 3 |  | KPTG-TRANSMIT-023021
SKS Tech-TRANSMIT-000247 | 0 | 1 |  | KPTG-DA-009220 | ZIA-TRANSMIT-000202 | 1 |  | KPTG-TRANSMIT-023025
Diadem-TRANSMIT-000028 | 1 |  |  | 4642 | SMEPS-TRANSMIT-000432 | 1 |  | KPTG-DA-009227
SKS Tech-TRANSMIT-000248 | 19 |  |  | 4644 | ADP-TRANSMIT-000466 | 19 |  | KPTG-DA-009232
ZIA-TRANSMIT-000205 |  | 1 |  | KPTG-DA-009226 | D&E-TRANSMIT-001145 | 2 |  | KPTG-DA-009213
ADP-TRANSMIT-000467 | 17 |  |  | KPTG-DA-009247 | SKS Tech-TRANSMIT-000247 | 1 |  | KPTG-DA-009220
ACG-TRANSMIT-000141 | 13 |  |  | KPTG-DA-009233 | ZIA-TRANSMIT-000205 | 1 |  | KPTG-DA-009226
[5 empty] | ACG-TRANSMIT-000141 | 13 |  | KPTG-DA-009233
[5 empty] | ADP-TRANSMIT-000467 | 17 |  | KPTG-DA-009247
TOTAL | 75 | 3 | 0 |  | TOTAL | 92
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
TOTAL

## 15
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-15 | [5 empty] | Project: | NXM3S4
Incoming Transmittals |  |  |  |  | Close out Transmittals
Transmittal No. | No. of Drawings | No. of Technical data | Pending No. of Documents | Remarks | Transmittal No. | No. of DOCUMENTS | Pending No. of Documents | Remarks
D&E-TRANSMIT-001147 | 2 |  |  | KPTG-TRANSMIT-023032 | SKS Tech-TRANSMIT-000227 | 1 |  | KPTG-TRANSMIT-023072
Nilsen3-TRANSMIT-000303 | 2 |  |  | 4649 | Nilsen3-TRANSMIT-000301 | 2 |  | KPTG-DA-009250 TEL- Voided as per requested from fabian-Nilsen have uploaded the wrong file and need to re-transmit M3-TEL-NIL-SDRG-C-0400-3213
ACG-TRANSMIT-000143 | 2 |  |  | KPTG-DA-009248 | KPTG-WTRAN-013809 | 16 |  | As per Jan- Documents are Reinitiated for Stamping
ACG-TRANSMIT-000144 | 13 |  |  | KPTG-DA-009245 | ADP-TRANSMIT-000462 | 1 |  | KPTG-TRANSMIT-023064
SMEPS-TRANSMIT-000436 |  | 2 |  | WF-007281 | D&E-TRANSMIT-001147 | 2 |  | KPTG-TRANSMIT-023032
ARCST-TRANSMIT-000307 |  | 1 |  | KPTG-DA-009263 | ACG-TRANSMIT-000143 | 2 |  | KPTG-DA-009248
ACG-TRANSMIT-000145 | 14 |  |  | 4651 | ACG-TRANSMIT-000144 | 13 |  | KPTG-DA-009245
D&E-TRANSMIT-001148 |  | 1 |  | KPTG-DA-009263 | ARCST-TRANSMIT-000307 | 1 |  | KPTG-DA-009263
Ardon-TRANSMIT-000073 |  | 1 |  | WF-007283 | D&E-TRANSMIT-001148 | 1 |  | KPTG-DA-009263
KPTG-WTRAN-013809 | 16 |  |  | 4647 | SMEPS-TRANSMIT-000433 | 2 |  | KPTG-DA-009249
KPTG-WTRAN-013809 | 16 |  |  | 4647 | SMEPS-TRANSMIT-000434 | 1 |  | KPTG-DA-009250
RDSBIM-TRANSMIT-000326 | 3 |  |  | 4664 | PARR-TRANSMIT-000228 | 3 |  | KPTG-DA-009256
ADP-TRANSMIT-000468 | 1 |  |  | 4653
ADP-TRANSMIT-000468 | 5 |  |  | 4655
ADP-TRANSMIT-000468 | 5 |  |  | 4657
ADP-TRANSMIT-000468 | 5 |  |  | 4659
ADP-TRANSMIT-000468 | 6 |  |  | 4662
ADP-TRANSMIT-000468 | 5 |  |  | 4666
SMEPS-TRANSMIT-000433 |  | 2 |  | KPTG-DA-009249
SMEPS-TRANSMIT-000434 |  | 1 |  | KPTG-DA-009250
PARR-TRANSMIT-000228 | 2 | 1 |  | KPTG-DA-009256
SMEPS-TRANSMIT-000435 |  | 1 |  | WF-007279
TOTAL | 97 | 10 | 0 |  | TOTAL | 45
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
TOTAL

## 16
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-10-16 | [5 empty] | Project: | NXM3S4
Incoming Transmittals |  |  |  |  | Close out Transmittals
Transmittal No. | No. of Drawings | No. of Technical data | Pending No. of Documents | Remarks | Transmittal No. | No. of DOCUMENTS | Pending No. of Documents | Remarks
ARCST-TRANSMIT-000307 | 1 |  |  | WF-007292 | SMEPS-TRANSMIT-000323 | 1 |  | KPTG-TRANSMIT-023077
ZIA-TRANSMIT-000206 |  | 1 |  | KPTG-DA-009275 | SMEPS-TRANSMIT-000350 | 1 |  | KPTG-TRANSMIT-023086
D&E-TRANSMIT-001149 | 1 |  |  | 4668 | D&E-TRANSMIT-000997 | 1 |  | KPTG-TRANSMIT-023081
SMEPS-TRANSMIT-000430 |  | 1 |  | WF-007293 | SMEPS-TRANSMIT-000430 | 1 |  | As instructed by Ellie-Terminated -The document will be submitted for review using the new template.
D&E-TRANSMIT-001150 | 5 |  |  | ⁠KPTG-DA-009287 | ZIA-TRANSMIT-000206 | 1 |  | KPTG-DA-009275
HDRAus-TRANSMIT-000594 | 17 |  |  | 4670 | D&E-TRANSMIT-001150 | 5 |  | ⁠KPTG-DA-009287
TOTAL | 24 | 2 | 0 |  | TOTAL | 10
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
TOTAL