## 3-08
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-08-03 | [5 empty] | Project: | 352-MAC - Greystar
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
JCBa-TRANSMIT-000160: Updated Architectural Documentation - GA Plans | 81 | 0 | 0 | ACC#1635 ¦ WF-000771 - 1 Drawing(23-122_A-2200-5) added from JCBa-TRANSMIT-000159 | JCBa-TRANSMIT-000154 Updated Architectural Documentation - SSPs, Sections, Detail Plans & RCPs, Detail Elevations -1498 | 81 | 0 | KPTG-TRANSMIT-003053
Auspan-TRANSMIT-000571: Precast shop drawings for approval. Level 4 zone 4. | 5 | 0 | 0 | ACC#1631 ¦ WF-000769 | JCBa-TRANSMIT-000156 Updated Architectural Documentation - Detail RCPs & Common Area Joinery Details -1533 | 2 | 0 | KPTG-TRANSMIT-003058
Auspan-TRANSMIT-000572: Precast shop drawings for construction. Level 3. | 12 | 0 | 12 | IFC - Waiting for Kim advise - KPTG-IntCorr-001175 - 12 Drawings | Auspan-TRANSMIT-000555 Resubmit zone 5 level 3 panel 3P5056 for approval -1573 | 1 | 0 | KPTG-TRANSMIT-003061
Auspan-TRANSMIT-000572: Precast shop drawings for construction. Level 3. | 1 | 0 | 0 | Rejected - Difference in drawing status -DRAFT-010889- 1 drawing | Auspan-TRANSMIT-000573: Precast shop drawings for construction. Level 4. | 2 | 0 | Rejected - Difference revision code - DRAFT-010913 - 2 Drawings
Auspan-TRANSMIT-000573: Precast shop drawings for construction. Level 4. | 13 | 0 | 13 | IFC - Waiting for Kim advise -KPTG-IntCorr-001180 - 13 Drawings | Auspan-TRANSMIT-000572: Precast shop drawings for construction. Level 3. | 1 | 0 | Rejected - Difference in drawing status -DRAFT-010889- 1 drawing
Auspan-TRANSMIT-000573: Precast shop drawings for construction. Level 4. | 2 | 0 | 0 | Rejected - Difference revision code - DRAFT-010913 - 2 Drawings
Auspan-TRANSMIT-000574: Precast shop drawings for construction. Level 5. | 5 | 0 | 5 | IFC - Waiting for Kim advise -KPTG-IntCorr-001181
Auspan-TRANSMIT-000575: Resubmit precast panel 3P5065 for approval. Stair landing updated | 1 | 0 | 0 | ACC#1638 ¦ WF-000773
Total | 120 | 0 | 30 |  |  | 87 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000429: Update IFCed precast shop drawings. Level 1 zone 4, 5 | 2026-06-26 | 2 | 2 | IFC - QC OK - Kapitol PC Kim to confirm - KPTG-IntCorr-000778 - ON HOLD AS ADVISED BY KIM | ON HOLD AS ADVISED BY KIM
Auspan-TRANSMIT-000441 Precast shop drawings for construction. Level 6. | 2026-06-30 | 34 | 34 | IFC - Waiting for advise KPTG-IntCorr-000804 | Pending services coordination
Auspan-TRANSMIT-000464: Precast shop drawings for construction. 5P2018 | 2026-07-03 | 1 | 1 | IFC - Waiting for Kapitol PC advise - KPTG-IntCorr-000856 (QC done) | ON HOLD AS ADVISED BY KIM KPTG-IntCorr-000863
Auspan-TRANSMIT-000489: Precast shop drawings for construction. Level 4. | 2026-07-10 | 46 | 46 | IFC - Waiting for Kim advise - KPTG-IntCorr-000928 qc done
Auspan-TRANSMIT-000494: Update IFCed shop drawings. Level 3. | 2026-07-13 | 30 | 11 | IFC - Waiting for Kim advise -KPTG-IntCorr-000936 | KPTG-IntCorr-001130 - 11 are pending to update -KPTG-IntCorr-001140
Auspan-TRANSMIT-000496: Update IFCed shop drawings. Levels 5, 6. | 2026-07-13 | 6 | 6 | IFC - Waiting for Kim advise- KPTG-IntCorr-000947 | Panel are on Hold - as advised KPTG-IntCorr-000967
Auscool-TRANSMIT-000067: Basement - IFC Drawings | 2026-07-21 | 1 | 1 | Zone 2 to 5 are Ok to update register and transmit. Zone 1 is on hold - KPTG-TRANSMIT-002881
Auspan-TRANSMIT-000538: Precast shop drawings for construction. Level 5. | 2026-07-23 | 20 | 20 | IFC - Waiting for Kim advise -KPTG-IntCorr-001086
Auspan-TRANSMIT-000545: Level 5 precast shop drawings for construction | 2026-07-24 | 28 | 28 | IFC - Waiting for Kim advise -KPTG-IntCorr-001095 - 28 Drawings
Auspan-TRANSMIT-000547: Re: RFI: Panel weight 0G368 | 2026-07-24 | 2 | 2 | Waiting for Kim advise-KPTG-IntCorr-001101
Auspan-TRANSMIT-000553: Precast shop drawings for construction. Level 4 | 2026-07-27 | 25 | 25 | IFC - Waiting for Kim advise- KPTG-IntCorr-001107
Auspan-TRANSMIT-000556: Update already IFCed shop drawings | 2026-07-27 | 2 | 2 | IFC - Waiting for Kim advise-KPTG-IntCorr-001112
Auspan-TRANSMIT-000557: Update IFCed precast shop drawings. level 3 | 2026-07-27 | 3 | 3 | IFC - Waiting for Kim advise-KPTG-IntCorr-001117
Auspan-TRANSMIT-000558 Update IFCed precast shpo drawings | 2026-07-28 | 4 | 4 | Waiting for Kim advise-KPTG-IntCorr-001137
Auspan-TRANSMIT-000561: Update IFCed precast shop drawings. Levels 2, 3. | 2026-07-29 | 6 | 6 | IFC - Waiting for Kim advise-KPTG-IntCorr-001152
M.2-TRANSMIT-000069 Electrical Services Lighting layouts - L00, L01 & Typical L02-05 | 2026-07-30 | 10 | 10 | QC done - waiting for advise KPTG-IntCorr-001164 | Internal review
Auspan-TRANSMIT-000563: Precast shop drawings for construction. Level 4 | 2026-07-30 | 2 | 2 | IFC - Waiting for Kim advise- KPTG-IntCorr-001163
Auspan-TRANSMIT-000565 Re: Panel 3P4027 - Update | 2026-07-31 | 1 | 1 | IFC - Kapitol to advise - KPTG-IntCorr-001168
Auspan-TRANSMIT-000566 Precast shop drawings for construction. Level 3. | 2026-07-31 | 5 | 5 | IFC - Kapitol to advise - KPTG-IntCorr-001170
Auspan-TRANSMIT-000567: Precast shop drawings for construction. Level 4 | 2026-07-31 | 28 | 28 | IFC - Waiting for Kim advise- KPTG-IntCorr-001169 - 28 Drawings
Total |  | 256 | 237

## 4-08
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-08-04 | [5 empty] | Project: | 352-MAC - Greystar
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
Auspan-TRANSMIT-000576: Update IFCed shop drawings. Level 3 | 2 | 0 | 2 | IFC - Waiting for Oliver advise- KPTG-IntCorr-001188 | KETE-TRANSMIT-000032: Kete - Updated Revision Status IFC Drawings | 11 | 0 | IFC - Register and transmit as advised by Alex Mc - KPTG-TRANSMIT-003067
Auspan-TRANSMIT-000577: Precast shop drawings for construction. Levels 4, 5 | 17 | 0 | 17 | IFC - Waiting for Oliver advise -KPTG-IntCorr-001187 | Auspan-TRANSMIT-000565 Re: Panel 3P4027 - Update | 1 | 0 | IFC Update registe and distribute KPTG-TRANSMIT-003068
KETE-TRANSMIT-000032: Kete - Updated Revision Status IFC Drawings | 11 | 0 | 0 | IFC - Register and transmit as advised by Alex Mc - KPTG-TRANSMIT-003067 | Auspan-TRANSMIT-000553: Precast shop drawings for construction. Level 4 | 25 | 0 | 21 are OK to IFC - Update registe and distribute KPTG-TRANSMIT-003070 4 are rejected by PC- KPTG-SADV-003925
PCForm-TRANSMIT-000107 Updated Screen Drawings - Reduced Overhang | 5 | 0 | 0 | Register upated as advised by Kapitol DM. | Auspan-TRANSMIT-000557: Update IFCed precast shop drawings. level 3 | 3 | 0 | IFC Update registe and distribute KPTG-TRANSMIT-003072
IJF-TRANSMIT-000006 Re: Joinery - Prototype Drawings | 44 | 0 | 0 | ACC#1653 ¦ WF-000775 | Auspan-TRANSMIT-000558 Update IFCed precast shpo drawings | 4 | 0 | IFC Update registe and distribute KPTG-TRANSMIT-003074
Rinco-TRANSMIT-000066: Structural drawings Issued for Construction | 17 | 0 | 0 | ACC#1656 ¦ WF-000776 | Auspan-TRANSMIT-000561: Update IFCed precast shop drawings. Levels 2, 3. | 6 | 0 | 4 are ok to IFC Update registe and distribute KPTG-TRANSMIT-003076 2 Rejected -DRAFT-010943
[5 empty] | Auspan-TRANSMIT-000563: Precast shop drawings for construction. Level 4 | 2 | 0 | IFC Update registe and distribute KPTG-TRANSMIT-003084
[5 empty] | Auspan-TRANSMIT-000566 Precast shop drawings for construction. Level 3. | 5 | 0 | 2 are OK to IFC IFC Update registe and distribute - KPTG-IntCorr-001178 The other 3 drawings have been up rev'd - KPTG-IntCorr-001178
[5 empty] | Auspan-TRANSMIT-000572: Precast shop drawings for construction. Level 3. | 12 | 0 | IFC Update registe and distribute KPTG-TRANSMIT-003091 2 are rejected. -DRAFT-010947
[5 empty] | PCForm-TRANSMIT-000107 Updated Screen Drawings - Reduced Overhang | 5 | 0 | Register updated.
[5 empty] | Auspan-TRANSMIT-000541 Resubmit shop drawings for approval. Zone 3 and 5 level 4 -1563 | 1 | 0 | KPTG-TRANSMIT-003080
[5 empty] | Auspan-TRANSMIT-000560 Resubmit precast shop drawings for approval -1585 | 2 | 0 | KPTG-TRANSMIT-003081
[5 empty] | Auspan-TRANSMIT-000539 Resubmit shop drawing 4P4034 for approval -1556 | 1 | 0 | KPTG-TRANSMIT-003086
[5 empty] | Auspan-TRANSMIT-000524 Resubmit precast shop drawings for approval. Panel 4P5058 -1535 | 2 | 0 | KPTG-TRANSMIT-003095
[5 empty] | Auspan-TRANSMIT-000427 Precast shop drawings for approval. Zone 4, 5 level 5 -1351 | 32 | 0 | KPTG-TRANSMIT-003098
[5 empty] | Auspan-TRANSMIT-000460 Precast shop drawings for approval. Levels 5, 6 -1406 | 35 | 0 | KPTG-TRANSMIT-003102
[5 empty] | Auspan-TRANSMIT-000498 Re Zone 2 Panel Changes - Hoist Location closed -1477 | 20 | 0 | KPTG-TRANSMIT-003107
[5 empty] | Auspan-TRANSMIT-000501 Update precast shop drawing 1P4002 - 1479 | 1 | 0 | KPTG-TRANSMIT-003110
[5 empty] | Auspan-TRANSMIT-000564 Resubmit precast shop drawings for approval -1606 | 2 | 0 | KPTG-TRANSMIT-003113
Total | 96 | 0 | 19 |  |  | 170 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000429: Update IFCed precast shop drawings. Level 1 zone 4, 5 | 2026-06-26 | 2 | 2 | IFC - QC OK - Kapitol PC Kim to confirm - KPTG-IntCorr-000778 - ON HOLD AS ADVISED BY KIM | ON HOLD AS ADVISED BY KIM
Auspan-TRANSMIT-000441 Precast shop drawings for construction. Level 6. | 2026-06-30 | 34 | 34 | IFC - Waiting for advise KPTG-IntCorr-000804 | Pending services coordination
Auspan-TRANSMIT-000464: Precast shop drawings for construction. 5P2018 | 2026-07-03 | 1 | 1 | IFC - Waiting for Kapitol PC advise - KPTG-IntCorr-000856 (QC done) | ON HOLD AS ADVISED BY KIM KPTG-IntCorr-000863
Auspan-TRANSMIT-000489: Precast shop drawings for construction. Level 4. | 2026-07-10 | 46 | 46 | IFC - Waiting for Kim advise - KPTG-IntCorr-000928 qc done
Auspan-TRANSMIT-000494: Update IFCed shop drawings. Level 3. | 2026-07-13 | 30 | 11 | IFC - Waiting for Kim advise -KPTG-IntCorr-000936 | KPTG-IntCorr-001130 - 11 are pending to update -KPTG-IntCorr-001140
Auspan-TRANSMIT-000496: Update IFCed shop drawings. Levels 5, 6. | 2026-07-13 | 6 | 6 | IFC - Waiting for Kim advise- KPTG-IntCorr-000947 | Panel are on Hold - as advised KPTG-IntCorr-000967
Auscool-TRANSMIT-000067: Basement - IFC Drawings | 2026-07-21 | 1 | 1 | Zone 2 to 5 are Ok to update register and transmit. Zone 1 is on hold - KPTG-TRANSMIT-002881
Auspan-TRANSMIT-000538: Precast shop drawings for construction. Level 5. | 2026-07-23 | 20 | 20 | IFC - Waiting for Kim advise -KPTG-IntCorr-001086
Auspan-TRANSMIT-000545: Level 5 precast shop drawings for construction | 2026-07-24 | 28 | 28 | IFC - Waiting for Kim advise -KPTG-IntCorr-001095 - 28 Drawings
Auspan-TRANSMIT-000547: Re: RFI: Panel weight 0G368 | 2026-07-24 | 2 | 2 | Waiting for Kim advise-KPTG-IntCorr-001101
Auspan-TRANSMIT-000556: Update already IFCed shop drawings | 2026-07-27 | 2 | 2 | IFC - Waiting for Kim advise-KPTG-IntCorr-001112
Auspan-TRANSMIT-000567: Precast shop drawings for construction. Level 4 | 2026-07-31 | 28 | 28 | IFC - Waiting for Kim advise- KPTG-IntCorr-001169 - 28 Drawings
Auspan-TRANSMIT-000573: Precast shop drawings for construction. Level 4. | 2026-08-03 | 13 | 13 | IFC - Waiting for Kim advise -KPTG-IntCorr-001180 - 13 Drawings
Auspan-TRANSMIT-000574: Precast shop drawings for construction. Level 5. | 2026-08-03 | 5 | 5 | IFC - Waiting for Kim advise -KPTG-IntCorr-001181
Auspan-TRANSMIT-000565 Re: Panel 3P4027 - Update | 2026-07-31 | 1 | 0 | IFC - Kapitol to advise - KPTG-IntCorr-001168 | Ok to proceed IFC - KPTG-IntCorr-001186
Auspan-TRANSMIT-000553: Precast shop drawings for construction. Level 4 | 2026-07-27 | 25 | 0 | IFC - Waiting for Kim advise- KPTG-IntCorr-001107 | 20 are OK TO IFC - KPTG-IntCorr-001185 Please IFC panel 4P1042 as well
Auspan-TRANSMIT-000557: Update IFCed precast shop drawings. level 3 | 2026-07-27 | 3 | 0 | IFC - Waiting for Kim advise-KPTG-IntCorr-001117 | ok to proceed IFC - KPTG-IntCorr-001184
Auspan-TRANSMIT-000558 Update IFCed precast shpo drawings | 2026-07-28 | 4 | 0 | Waiting for Kim advise-KPTG-IntCorr-001137 | OK TO IFC - KPTG-IntCorr-001183
Auspan-TRANSMIT-000561: Update IFCed precast shop drawings. Levels 2, 3. | 2026-07-29 | 6 | 0 | IFC - Waiting for Kim advise-KPTG-IntCorr-001152 | 4 are OK to IFC. KPTG-IntCorr-001182 2 are Rejected.
Auspan-TRANSMIT-000563: Precast shop drawings for construction. Level 4 | 2026-07-30 | 2 | 0 | IFC - Waiting for Kim advise- KPTG-IntCorr-001163 | OK TO IFC - KPTG-IntCorr-001179
Auspan-TRANSMIT-000566 Precast shop drawings for construction. Level 3. | 2026-07-31 | 5 | 0 | IFC - Kapitol to advise - KPTG-IntCorr-001170 | 2 are OK TO IFC - The other 3 drawings have been up rev'd - KPTG-IntCorr-001178
Auspan-TRANSMIT-000572: Precast shop drawings for construction. Level 3. | 2026-08-03 | 12 | 0 | IFC - Waiting for Kim advise - KPTG-IntCorr-001175 - 12 Drawings | 9 are OK to Transmit - KPTG-IntCorr-001176 3 are rejected.
M.2-TRANSMIT-000069 Electrical Services Lighting layouts - L00, L01 & Typical L02-05 | 2026-07-30 | 10 | 0 | QC done - waiting for advise KPTG-IntCorr-001164 ACC#1643 ¦ WF-000774 | Internal review
Total |  | 286 | 199

## 5-08
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-08-05 | [5 empty] | Project: | 352-MAC - Greystar
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
Auspan-TRANSMIT-000578: Update level 3 precast shop drawings | 2 | 0 | 2 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001198 | Auscool-TRANSMIT-000069 level 2 - level 7 - precast penetration -1547 | 6 | 0 | KPTG-TRANSMIT-003118
Auspan-TRANSMIT-000579: Update IFCed level 4 precast shop drawings. | 5 | 0 | 5 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001199 | Auspan-TRANSMIT-000576: Update IFCed shop drawings. Level 3 | 2 | 0 | KPTG-TRANSMIT-003124 | TO UPDATE ACC
Total | 7 | 0 | 7 |  |  | 8 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000429: Update IFCed precast shop drawings. Level 1 zone 4, 5 | 2026-06-26 | 2 | 2 | IFC - QC OK - Kapitol PC Kim to confirm - KPTG-IntCorr-000778 - ON HOLD AS ADVISED BY KIM | ON HOLD AS ADVISED BY KIM
Auspan-TRANSMIT-000441 Precast shop drawings for construction. Level 6. | 2026-06-30 | 34 | 34 | IFC - Waiting for advise KPTG-IntCorr-000804 | Pending services coordination
Auspan-TRANSMIT-000464: Precast shop drawings for construction. 5P2018 | 2026-07-03 | 1 | 1 | IFC - Waiting for Kapitol PC advise - KPTG-IntCorr-000856 (QC done) | ON HOLD AS ADVISED BY KIM KPTG-IntCorr-000863
Auspan-TRANSMIT-000489: Precast shop drawings for construction. Level 4. | 2026-07-10 | 46 | 46 | IFC - Waiting for Kim advise - KPTG-IntCorr-000928 qc done
Auspan-TRANSMIT-000494: Update IFCed shop drawings. Level 3. | 2026-07-13 | 11 | 11 | IFC - Waiting for Kim advise -KPTG-IntCorr-000936 | KPTG-IntCorr-001130 - 11 are pending to update -KPTG-IntCorr-001140
Auspan-TRANSMIT-000496: Update IFCed shop drawings. Levels 5, 6. | 2026-07-13 | 6 | 6 | IFC - Waiting for Kim advise- KPTG-IntCorr-000947 | Panel are on Hold - as advised KPTG-IntCorr-000967
Auscool-TRANSMIT-000067: Basement - IFC Drawings | 2026-07-21 | 1 | 1 | Zone 2 to 5 are Ok to update register and transmit. Zone 1 is on hold - KPTG-TRANSMIT-002881
Auspan-TRANSMIT-000538: Precast shop drawings for construction. Level 5. | 2026-07-23 | 20 | 20 | IFC - Waiting for Kim advise -KPTG-IntCorr-001086
Auspan-TRANSMIT-000545: Level 5 precast shop drawings for construction | 2026-07-24 | 28 | 28 | IFC - Waiting for Kim advise -KPTG-IntCorr-001095 - 28 Drawings
Auspan-TRANSMIT-000547: Re: RFI: Panel weight 0G368 | 2026-07-24 | 2 | 2 | Waiting for Kim advise-KPTG-IntCorr-001101
Auspan-TRANSMIT-000556: Update already IFCed shop drawings | 2026-07-27 | 2 | 2 | IFC - Waiting for Kim advise-KPTG-IntCorr-001112
Auspan-TRANSMIT-000567: Precast shop drawings for construction. Level 4 | 2026-07-31 | 28 | 28 | IFC - Waiting for Kim advise- KPTG-IntCorr-001169 - 28 Drawings
Auspan-TRANSMIT-000573: Precast shop drawings for construction. Level 4. | 2026-08-03 | 13 | 13 | IFC - Waiting for Kim advise -KPTG-IntCorr-001180 - 13 Drawings
Auspan-TRANSMIT-000574: Precast shop drawings for construction. Level 5. | 2026-08-03 | 5 | 5 | IFC - Waiting for Kim advise -KPTG-IntCorr-001181
Auspan-TRANSMIT-000577: Precast shop drawings for construction. Levels 4, 5 | 2026-08-04 | 17 | 17 | IFC - Waiting for Oliver advise -KPTG-IntCorr-001187
Auspan-TRANSMIT-000576: Update IFCed shop drawings. Level 3 | 2026-08-04 | 2 | 0 | IFC - Waiting for Oliver advise- KPTG-IntCorr-001188 | KPTG-IntCorr-001202 - IFC Reegister and transmit
Total |  | 218 | 216

## 6-08
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-08-06 | [5 empty] | Project: | 352-MAC - Greystar
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
RDSBIM-TRANSMIT-000092 GREYSTAR LEVEL 05 CONCRETE PROFILE PLAN | 6 | 0 | 0 | ACC#1660 ¦ WF-000777 | Auspan-TRANSMIT-000581 352 - Level 2 Dowel Layout | 3 | 0 | IFC-Update Register and Transmit -KPTG-TRANSMIT-003129
POTTSENG-TRANSMIT-000061 GMAC: HYDRAULIC SERVICES - PENETRATION - LEVEL 01 - ZONE 3 LAYOUT | 1 | 0 | 0 | Rejected due to incorrect revisIon. DRAFT-011141 | RDSBIM-TRANSMIT-000087 GREYSTAR LEVEL 03 CONCRETE PROFILE PLAN | 6 | 0 | Review void as requested by RDS and advised by Kapitol DM.
Auspan-TRANSMIT-000580 Re: Zone 3 RFi 70. Resubmit shop drawings level 5 for approval | 3 | 0 | 0 | ACC#1662 ¦WF-000778 | RDSBIM-TRANSMIT-000089 GREYSTAR LEVEL 04 CONCRETE PROFILE PLAN | 5 | 0 | Review void as requested by RDS and advised by Kapitol DM.
Auspan-TRANSMIT-000581 352 - Level 2 Dowel Layout | 3 | 0 | 0 | IFC - Oliver to advise - KPTG-IntCorr-001204 please transmit IFC -KPTG-TRANSMIT-003129 | RDSBIM-TRANSMIT-000090 GREYSTAR LEVEL 04 CONCRETE PROFILE KEY PLAN | 1 | 0 | Review void as requested by RDS and advised by Kapitol DM.
POTTSENG-TRANSMIT-000062: GMAC: HYDRAULIC SERVICES - PENETRATION - LEVEL 02 - ZONE 5 LAYOUT | 1 | 0 | 0 | ACC#1665 ¦ WF-000779 | POTTSENG-TRANSMIT-000061 GMAC: HYDRAULIC SERVICES - PENETRATION - LEVEL 01 - ZONE 3 LAYOUT | 1 | 0 | Rejected due to incorrect revisIon. DRAFT-011141
Auspan-TRANSMIT-000582: Update IFCed precast shop drawings. level 3 | 2 | 0 | 2 | IFC - Oliver to advise - KPTG-IntCorr-001205
Auspan-TRANSMIT-000584: Re: Update IFCed shop drawings. Level 3. | 1 | 0 | 1 | IFC - Oliver to advise - KPTG-IntCorr-001208
Total | 17 | 0 | 3 |  |  | 16 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000429: Update IFCed precast shop drawings. Level 1 zone 4, 5 | 2026-06-26 | 2 | 2 | IFC - QC OK - Kapitol PC Kim to confirm - KPTG-IntCorr-000778 - ON HOLD AS ADVISED BY KIM | ON HOLD AS ADVISED BY KIM
Auspan-TRANSMIT-000441 Precast shop drawings for construction. Level 6. | 2026-06-30 | 34 | 34 | IFC - Waiting for advise KPTG-IntCorr-000804 | Pending services coordination
Auspan-TRANSMIT-000464: Precast shop drawings for construction. 5P2018 | 2026-07-03 | 1 | 1 | IFC - Waiting for Kapitol PC advise - KPTG-IntCorr-000856 (QC done) | ON HOLD AS ADVISED BY KIM KPTG-IntCorr-000863
Auspan-TRANSMIT-000489: Precast shop drawings for construction. Level 4. | 2026-07-10 | 46 | 46 | IFC - Waiting for Kim advise - KPTG-IntCorr-000928 qc done
Auspan-TRANSMIT-000494: Update IFCed shop drawings. Level 3. | 2026-07-13 | 11 | 11 | IFC - Waiting for Kim advise -KPTG-IntCorr-000936 | KPTG-IntCorr-001130 - 11 are pending to update -KPTG-IntCorr-001140
Auspan-TRANSMIT-000496: Update IFCed shop drawings. Levels 5, 6. | 2026-07-13 | 6 | 6 | IFC - Waiting for Kim advise- KPTG-IntCorr-000947 | Panel are on Hold - as advised KPTG-IntCorr-000967
Auscool-TRANSMIT-000067: Basement - IFC Drawings | 2026-07-21 | 1 | 1 | Zone 2 to 5 are Ok to update register and transmit. Zone 1 is on hold - KPTG-TRANSMIT-002881
Auspan-TRANSMIT-000538: Precast shop drawings for construction. Level 5. | 2026-07-23 | 20 | 20 | IFC - Waiting for Kim advise -KPTG-IntCorr-001086
Auspan-TRANSMIT-000545: Level 5 precast shop drawings for construction | 2026-07-24 | 28 | 28 | IFC - Waiting for Kim advise -KPTG-IntCorr-001095 - 28 Drawings
Auspan-TRANSMIT-000547: Re: RFI: Panel weight 0G368 | 2026-07-24 | 2 | 2 | Waiting for Kim advise-KPTG-IntCorr-001101
Auspan-TRANSMIT-000556: Update already IFCed shop drawings | 2026-07-27 | 2 | 2 | IFC - Waiting for Kim advise-KPTG-IntCorr-001112
Auspan-TRANSMIT-000567: Precast shop drawings for construction. Level 4 | 2026-07-31 | 28 | 28 | IFC - Waiting for Kim advise- KPTG-IntCorr-001169 - 28 Drawings
Auspan-TRANSMIT-000573: Precast shop drawings for construction. Level 4. | 2026-08-03 | 13 | 13 | IFC - Waiting for Kim advise -KPTG-IntCorr-001180 - 13 Drawings
Auspan-TRANSMIT-000574: Precast shop drawings for construction. Level 5. | 2026-08-03 | 5 | 5 | IFC - Waiting for Kim advise -KPTG-IntCorr-001181
Auspan-TRANSMIT-000577: Precast shop drawings for construction. Levels 4, 5 | 2026-08-04 | 17 | 17 | IFC - Waiting for Oliver advise -KPTG-IntCorr-001187
Auspan-TRANSMIT-000578: Update level 3 precast shop drawings | 2026-08-05 | 2 | 2 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001198
Auspan-TRANSMIT-000579: Update IFCed level 4 precast shop drawings. | 2026-08-05 | 5 | 5 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001199
Total |  | 223 | 223

## 7-08
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-08-07 | [5 empty] | Project: | 352-MAC - Greystar
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
RDSBIM-TRANSMIT-000093: 352MAC ¦ LEVEL 02 CONCRETE PROFILE PLAN ZONE 5 | 1 | 0 | 0 | ACC#1668 ¦ WF-000780 | ArcadiaL-TRANSMIT-000003: Landscape Architectural - IFC Updates to Easement | 4 | 0 | Rejected due to incorrect drawing status - DRAFT-011181
RDSBIM-TRANSMIT-000094 GREYSTAR LEVEL 03 CONCRETE PROFILE PLAN ZONE 5 | 1 | 0 | 0 | ACC#1674 ¦ WF-000785
RDSBIM-TRANSMIT-000087 GREYSTAR LEVEL 03 CONCRETE PROFILE PLAN | 5 | 0 | 0 | IFC -Review was terminated and re-initiated. ACC#1674 ¦ WF-000786
RDSBIM-TRANSMIT-000095: GREYSTAR LEVEL 04 CONCRETE PROFILE PLAN ZONE 5 | 1 | 0 | 0 | ACC#1692 ¦WF-000782
RDSBIM-TRANSMIT-000090 GREYSTAR LEVEL 04 CONCRETE PROFILE KEY PLAN | 1 | 0 | 0 | IFC -Review was terminated and re-initiated. ACC#1692 ¦WF-000784
RDSBIM-TRANSMIT-000089 GREYSTAR LEVEL 04 CONCRETE PROFILE PLAN | 4 | 0 | 0 | IFC - Review was terminated and re-initiated. ACC#1692 ¦WF-000783
Auspan-TRANSMIT-000585: Re: level 2 - level 7 - precast penetration. Update IFCed precast shop drawings. | 6 | 0 | 6 | IFC - Waiting for Oliver advise-KPTG-IntCorr-0012
Auspan-TRANSMIT-000586: Precast shop drawings for construction. Level 3. | 3 | 0 | 3 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001212
Auspan-TRANSMIT-000587: Precast shop drawings for construction. Level 4. | 5 | 0 | 5 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001213
Auspan-TRANSMIT-000588: Precast shop drawings for construction. Levels 5, 6. | 35 | 0 | 35 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001209
Auspan-TRANSMIT-000589: Precast shop drawings for approval. Level 5 | 5 | 0 | 0 | ACC#1670 ¦ WF-000781
JCBa-TRANSMIT-000163: Updated Architectural Documentation - Waterproofing Plans & Facade Assembly Sections | 10 | 0 | 0 | ACC#1676 ¦ WF-000787
Auspan-TRANSMIT-000590: Update panel 3P4012 | 1 | 0 | 1 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001214
ArcadiaL-TRANSMIT-000003: Landscape Architectural - IFC Updates to Easement | 4 | 0 | 0 | Rejected due to incorrect drawing status
Total | 82 | 0 | 50 |  |  | 4 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000429: Update IFCed precast shop drawings. Level 1 zone 4, 5 | 2026-06-26 | 2 | 2 | IFC - QC OK - Kapitol PC Kim to confirm - KPTG-IntCorr-000778 - ON HOLD AS ADVISED BY KIM | ON HOLD AS ADVISED BY KIM
Auspan-TRANSMIT-000441 Precast shop drawings for construction. Level 6. | 2026-06-30 | 34 | 34 | IFC - Waiting for advise KPTG-IntCorr-000804 | Pending services coordination
Auspan-TRANSMIT-000464: Precast shop drawings for construction. 5P2018 | 2026-07-03 | 1 | 1 | IFC - Waiting for Kapitol PC advise - KPTG-IntCorr-000856 (QC done) | ON HOLD AS ADVISED BY KIM KPTG-IntCorr-000863
Auspan-TRANSMIT-000489: Precast shop drawings for construction. Level 4. | 2026-07-10 | 46 | 46 | IFC - Waiting for Kim advise - KPTG-IntCorr-000928 qc done
Auspan-TRANSMIT-000494: Update IFCed shop drawings. Level 3. | 2026-07-13 | 11 | 11 | IFC - Waiting for Kim advise -KPTG-IntCorr-000936 | KPTG-IntCorr-001130 - 11 are pending to update -KPTG-IntCorr-001140
Auspan-TRANSMIT-000496: Update IFCed shop drawings. Levels 5, 6. | 2026-07-13 | 6 | 6 | IFC - Waiting for Kim advise- KPTG-IntCorr-000947 | Panel are on Hold - as advised KPTG-IntCorr-000967
Auscool-TRANSMIT-000067: Basement - IFC Drawings | 2026-07-21 | 1 | 1 | Zone 2 to 5 are Ok to update register and transmit. Zone 1 is on hold - KPTG-TRANSMIT-002881
Auspan-TRANSMIT-000538: Precast shop drawings for construction. Level 5. | 2026-07-23 | 20 | 20 | IFC - Waiting for Kim advise -KPTG-IntCorr-001086
Auspan-TRANSMIT-000545: Level 5 precast shop drawings for construction | 2026-07-24 | 28 | 28 | IFC - Waiting for Kim advise -KPTG-IntCorr-001095 - 28 Drawings
Auspan-TRANSMIT-000547: Re: RFI: Panel weight 0G368 | 2026-07-24 | 2 | 2 | Waiting for Kim advise-KPTG-IntCorr-001101
Auspan-TRANSMIT-000556: Update already IFCed shop drawings | 2026-07-27 | 2 | 2 | IFC - Waiting for Kim advise-KPTG-IntCorr-001112
Auspan-TRANSMIT-000567: Precast shop drawings for construction. Level 4 | 2026-07-31 | 28 | 28 | IFC - Waiting for Kim advise- KPTG-IntCorr-001169 - 28 Drawings
Auspan-TRANSMIT-000573: Precast shop drawings for construction. Level 4. | 2026-08-03 | 13 | 13 | IFC - Waiting for Kim advise -KPTG-IntCorr-001180 - 13 Drawings
Auspan-TRANSMIT-000574: Precast shop drawings for construction. Level 5. | 2026-08-03 | 5 | 5 | IFC - Waiting for Kim advise -KPTG-IntCorr-001181
Auspan-TRANSMIT-000577: Precast shop drawings for construction. Levels 4, 5 | 2026-08-04 | 17 | 17 | IFC - Waiting for Oliver advise -KPTG-IntCorr-001187
Auspan-TRANSMIT-000578: Update level 3 precast shop drawings | 2026-08-05 | 2 | 2 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001198
Auspan-TRANSMIT-000579: Update IFCed level 4 precast shop drawings. | 2026-08-05 | 5 | 5 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001199
Auspan-TRANSMIT-000582: Update IFCed precast shop drawings. level 3 | 2026-08-06 | 2 | 2 | IFC - Oliver to advise - KPTG-IntCorr-001205
Auspan-TRANSMIT-000584: Re: Update IFCed shop drawings. Level 3. | 2026-08-06 | 1 | 1 | IFC - Oliver to advise - KPTG-IntCorr-001208
Total |  | 226 | 226

## 10-08
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-08-10 | [5 empty] | Project: | 352-MAC - Greystar
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
Auspan-TRANSMIT-000591: Precast shop drawings for construction. Level 4 | 1 | 0 | 1 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001225 | Auspan-TRANSMIT-000464: Precast shop drawings for construction. 5P2018 | 1 | 0 | Rejected by Kapitol PC - KPTG-SADV-004086
Auspan-TRANSMIT-000592: Precast shop drawings for construction. Level 5 | 47 | 0 | 47 | Waiting for Oliver advise-KPTG-IntCorr-001219 | Auspan-TRANSMIT-000547: Re: RFI: Panel weight 0G368 | 2 | 0 | KPTG-TRANSMIT-003153
Auspan-TRANSMIT-000593: Precast shop drawings for construction. Level 4. | 9 | 0 | 9 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001222 | Auspan-TRANSMIT-000556: Update already IFCed shop drawings | 2 | 0 | KPTG-TRANSMIT-003155
Auspan-TRANSMIT-000595: Precast shop drawings for approval. Zone 4, 5 level 7. | 38 | 0 | 0 | IFA - ACC#1678 ¦ WF-000788 | Auspan-TRANSMIT-000582: Update IFCed precast shop drawings. level 3 | 2 | 0 | KPTG-TRANSMIT-003145
Auspan-TRANSMIT-000595: Precast shop drawings for approval. Zone 4, 5 level 7. | 4 | 0 | 0 | Rejected - difference in title and wrong attachment- DRAFT-011217 | Auspan-TRANSMIT-000585: Re: level 2 - level 7 - precast penetration. Update IFCed precast shop drawings. | 6 | 0 | KPTG-TRANSMIT-003147
Auspan-TRANSMIT-000596: Re: GMAC - Level 3 Additional precast penetrations | 3 | 0 | 3 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001224 | Auspan-TRANSMIT-000588: Precast shop drawings for construction. Levels 5, 6. | 35 | 0 | 24 Ok to porceed -KPTG-TRANSMIT-003151 11 Rejected by Kapitol PC. --KPTG-SADV-004075
KPTG-IntCorr-001221 Electrical Services Penetration layouts - Ground - Level 6 | 11 | 0 | 0 | ACC#1679 ¦ WF-000789 | Auspan-TRANSMIT-000590: Update panel 3P4012 | 1 | 0 | KPTG-TRANSMIT-003170
KPTG-IntCorr-001220 : Auscool AC selections | 3 | 0 | 0 | Returned due to no document number - KPTG-IntCorr-001227 | Auspan-TRANSMIT-000595: Precast shop drawings for approval. Zone 4, 5 level 7. | 4 | 0 | Rejected - difference in title and wrong attachment- DRAFT-011217
POTTSENG-TRANSMIT-000064: GMAC: HYDRAULIC SERVICES - PENETRATION - LEVEL 01 - ZONE 3 LAYOUT | 1 | 0 | 0 | ACC#1683 ¦ WF-000790 | KPTG-IntCorr-001220 : Auscool AC selections | 3 | 0 | Returned due to no document number - KPTG-IntCorr-001227
POTTSENG-TRANSMIT-000063: GMAC: HYDRAULIC SERVICES - PENETRATION - LEVEL 02 - ZONE 1 LAYOUT | 1 | 0 | 0 | ACC#1685 ¦ WF-000791 | INDS-TRANSMIT-000057 L2 to L7 Zone 3 - Added Peno | 1 | 0 | Review Void as advised by Kapitol PC- Brentyan "They need to update the drawing".
POTTSENG-TRANSMIT-000065: GMAC: HYDRAULIC SERVICES - PENETRATION - LEVELS 03-05 - ZONES 1-5 LAYOUTS | 15 | 0 | 0 | ACC#1687 ¦ WF-000792 | Auspan-TRANSMIT-000580 Zone 3 RFi 70 Resubmit shop drawings level 5 for approval -1662 | 2 | 0 | KPTG-TRANSMIT-003157
INDS-TRANSMIT-000059: L2 to L7 Zone 3 - Typical Floor Penetration Layout | 1 | 0 | 0 | ACC#1693 ¦ WF-000793 | Auspan-TRANSMIT-000534 Precast shop drawings for approval. Zone 1, 2 level 6 -1553 | 10 | 0 | KPTG-TRANSMIT-003160
Auspan-TRANSMIT-000594: Update IFCed precast shop drawings. Levels 3, 4, 5. | 8 | 0 | 8 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001232 | Auspan-TRANSMIT-000519 Re Precast shop drawings for approval. Levels 4, 5, 6 zone 4, 5 -1520 | 12 | 0 | KPTG-TRANSMIT-003163
[5 empty] | Auspan-TRANSMIT-000521 Precast shop drawings for approval. Levels 4, 5, 6 zone 4, 5 -1528 | 1 | 0 | KPTG-TRANSMIT-003166
Total | 142 | 0 | 68 |  |  | 82 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000429: Update IFCed precast shop drawings. Level 1 zone 4, 5 | 2026-06-26 | 2 | 2 | IFC - QC OK - Kapitol PC Kim to confirm - KPTG-IntCorr-000778 - ON HOLD AS ADVISED BY KIM | ON HOLD AS ADVISED BY KIM
Auspan-TRANSMIT-000441 Precast shop drawings for construction. Level 6. | 2026-06-30 | 34 | 34 | IFC - Waiting for advise KPTG-IntCorr-000804 | Pending services coordination
Auspan-TRANSMIT-000489: Precast shop drawings for construction. Level 4. | 2026-07-10 | 46 | 46 | IFC - Waiting for Kim advise - KPTG-IntCorr-000928 qc done
Auspan-TRANSMIT-000494: Update IFCed shop drawings. Level 3. | 2026-07-13 | 11 | 11 | IFC - Waiting for Kim advise -KPTG-IntCorr-000936 | KPTG-IntCorr-001130 - 11 are pending to update -KPTG-IntCorr-001140
Auspan-TRANSMIT-000496: Update IFCed shop drawings. Levels 5, 6. | 2026-07-13 | 6 | 6 | IFC - Waiting for Kim advise- KPTG-IntCorr-000947 | Panel are on Hold - as advised KPTG-IntCorr-000967
Auscool-TRANSMIT-000067: Basement - IFC Drawings | 2026-07-21 | 1 | 1 | Zone 2 to 5 are Ok to update register and transmit. Zone 1 is on hold - KPTG-TRANSMIT-002881
Auspan-TRANSMIT-000538: Precast shop drawings for construction. Level 5. | 2026-07-23 | 20 | 20 | IFC - Waiting for Kim advise -KPTG-IntCorr-001086
Auspan-TRANSMIT-000545: Level 5 precast shop drawings for construction | 2026-07-24 | 28 | 28 | IFC - Waiting for Kim advise -KPTG-IntCorr-001095 - 28 Drawings
Auspan-TRANSMIT-000567: Precast shop drawings for construction. Level 4 | 2026-07-31 | 28 | 28 | IFC - Waiting for Kim advise- KPTG-IntCorr-001169 - 28 Drawings
Auspan-TRANSMIT-000573: Precast shop drawings for construction. Level 4. | 2026-08-03 | 13 | 13 | IFC - Waiting for Kim advise -KPTG-IntCorr-001180 - 13 Drawings
Auspan-TRANSMIT-000574: Precast shop drawings for construction. Level 5. | 2026-08-03 | 5 | 5 | IFC - Waiting for Kim advise -KPTG-IntCorr-001181
Auspan-TRANSMIT-000577: Precast shop drawings for construction. Levels 4, 5 | 2026-08-04 | 17 | 17 | IFC - Waiting for Oliver advise -KPTG-IntCorr-001187
Auspan-TRANSMIT-000578: Update level 3 precast shop drawings | 2026-08-05 | 2 | 2 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001198
Auspan-TRANSMIT-000579: Update IFCed level 4 precast shop drawings. | 2026-08-05 | 5 | 5 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001199
Auspan-TRANSMIT-000584: Re: Update IFCed shop drawings. Level 3. | 2026-08-06 | 1 | 1 | IFC - Oliver to advise - KPTG-IntCorr-001208
Auspan-TRANSMIT-000586: Precast shop drawings for construction. Level 3. | 2026-08-07 | 3 | 3 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001212
Auspan-TRANSMIT-000587: Precast shop drawings for construction. Level 4. | 2026-08-07 | 5 | 5 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001213
Auspan-TRANSMIT-000588: Precast shop drawings for construction. Levels 5, 6. | 2026-08-07 | 35 | 0 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001209 | KPTG-SADV-004075 - 24 Ok to proceed IFC - 11 are rejected.
Auspan-TRANSMIT-000590: Update panel 3P4012 | 2026-08-07 | 1 | 0 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001214 | KPTG-SADV-004068 - Proceed IFC.
Auspan-TRANSMIT-000464: Precast shop drawings for construction. 5P2018 | 2026-07-03 | 1 | 0 | IFC - Waiting for Kapitol PC advise - KPTG-IntCorr-000856 (QC done) | Rejected - KPTG-SADV-004086
Auspan-TRANSMIT-000547: Re: RFI: Panel weight 0G368 | 2026-07-24 | 2 | 0 | Waiting for Kim advise-KPTG-IntCorr-001101 | Transmit for INFO only - KPTG-IntCorr-001216
Auspan-TRANSMIT-000556: Update already IFCed shop drawings | 2026-07-27 | 2 | 0 | IFC - Waiting for Kim advise-KPTG-IntCorr-001112 | KPTG-IntCorr-001217 - Proceed IFC
Auspan-TRANSMIT-000582: Update IFCed precast shop drawings. level 3 | 2026-08-06 | 2 | 0 | IFC - Oliver to advise - KPTG-IntCorr-001205 | KPTG-SADV-004081 - OK to IFC
Auspan-TRANSMIT-000585: Re: level 2 - level 7 - precast penetration. Update IFCed precast shop drawings. | 2026-08-07 | 6 | 0 | IFC - Waiting for Oliver advise-KPTG-IntCorr-0012 | KPTG-SADV-004079 - OK to IFC
Total |  | 276 | 227

## 11-08
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-08-11 | [5 empty] | Project: | 352-MAC - Greystar
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
Auspan-TRANSMIT-000597: Re: GMAC - Level 3 Additional precast penetrations | 13 | 0 | 0 | ACC#1695 ¦ WF-000795 | JCBa-TRANSMIT-000160 Updated Architectural Documentation - GA Plans | 81 | 0 | Review terminated as advised by Kapitol DM. "Please unlock the JCB door schedule, ga plans, partition plans and partition detail sections.
Auspan-TRANSMIT-000597: Re: GMAC - Level 3 Additional precast penetrations | 2 | 0 | 0 | Rejected- Difference in document number and status - DRAFT-011290 | Auscool-TRANSMIT-000071 level 1 - precast penetration - 1551 | 1 | 0 | KPTG-TRANSMIT-003176
Auspan-TRANSMIT-000598: Precast shop drawings for constructon. Zone 3 levels 4, 5. | 7 | 0 | 7 | IIFC - Waiting for Oliver advise-KPTG-IntCorr-001235 | LVPG-TRANSMIT-000035 LVPG - Stormwater Tech Data Submittals -WF-000676 | 2 | 0 | Review terminated as advised by Kapitol PC - Brentyn; To initiate a review with Fyfe.
LVPG-TRANSMIT-000035 LVPG - Stormwater Tech Data Submittals | 0 | 2 | 0 | As advised by Brent, WF-000794 | M.2-TRANSMIT-000070 Electrical Services Power & Comms layouts - L00-L07 -1629 | 25 | 0 | KPTG-TRANSMIT-003182
JCBa-TRANSMIT-000164: Updated Architectural Documentation - Partition Plans & Partition Detail Sections | 44 | 0 | 0 | ACC#1697 ¦ WF-000796 | Auspan-TRANSMIT-000574: Precast shop drawings for construction. Level 5. | 5 | 0 | Rejected by Kapitol PC. KPTG-SADV-004151
Auscool-TRANSMIT-000073: Ground Floor - Zone 1 and 3 IFA drawings | 2 | 0 | 0 | Rejected- Difference in revision code- DRAFT-011333 | Auspan-TRANSMIT-000597: Re: GMAC - Level 3 Additional precast penetrations | 2 | 0 | Rejected- Difference in document number and status - DRAFT-011290
POTTSENG-TRANSMIT-000066: GMAC: HYDRAULIC SERVICES - PENETRATION - LEVEL 02 - ZONE 4 LAYOUT | 1 | 0 | 0 | IFC- ACC#1699 ¦ WF-000797
Total | 69 | 2 | 7 |  |  | 116 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000429: Update IFCed precast shop drawings. Level 1 zone 4, 5 | 2026-06-26 | 2 | 2 | IFC - QC OK - Kapitol PC Kim to confirm - KPTG-IntCorr-000778 - ON HOLD AS ADVISED BY KIM | ON HOLD AS ADVISED BY KIM
Auspan-TRANSMIT-000441 Precast shop drawings for construction. Level 6. | 2026-06-30 | 34 | 34 | IFC - Waiting for advise KPTG-IntCorr-000804 | Pending services coordination
Auspan-TRANSMIT-000489: Precast shop drawings for construction. Level 4. | 2026-07-10 | 46 | 46 | IFC - Waiting for Kim advise - KPTG-IntCorr-000928 qc done
Auspan-TRANSMIT-000494: Update IFCed shop drawings. Level 3. | 2026-07-13 | 11 | 11 | IFC - Waiting for Kim advise -KPTG-IntCorr-000936 | KPTG-IntCorr-001130 - 11 are pending to update -KPTG-IntCorr-001140
Auspan-TRANSMIT-000496: Update IFCed shop drawings. Levels 5, 6. | 2026-07-13 | 6 | 6 | IFC - Waiting for Kim advise- KPTG-IntCorr-000947 | Panel are on Hold - as advised KPTG-IntCorr-000967
Auscool-TRANSMIT-000067: Basement - IFC Drawings | 2026-07-21 | 1 | 1 | Zone 2 to 5 are Ok to update register and transmit. Zone 1 is on hold - KPTG-TRANSMIT-002881
Auspan-TRANSMIT-000538: Precast shop drawings for construction. Level 5. | 2026-07-23 | 20 | 20 | IFC - Waiting for Kim advise -KPTG-IntCorr-001086
Auspan-TRANSMIT-000545: Level 5 precast shop drawings for construction | 2026-07-24 | 28 | 28 | IFC - Waiting for Kim advise -KPTG-IntCorr-001095 - 28 Drawings
Auspan-TRANSMIT-000573: Precast shop drawings for construction. Level 4. | 2026-08-03 | 13 | 13 | IFC - Waiting for Kim advise -KPTG-IntCorr-001180 - 13 Drawings
Auspan-TRANSMIT-000577: Precast shop drawings for construction. Levels 4, 5 | 2026-08-04 | 17 | 17 | IFC - Waiting for Oliver advise -KPTG-IntCorr-001187
Auspan-TRANSMIT-000579: Update IFCed level 4 precast shop drawings. | 2026-08-05 | 5 | 5 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001199
Auspan-TRANSMIT-000586: Precast shop drawings for construction. Level 3. | 2026-08-07 | 3 | 3 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001212
Auspan-TRANSMIT-000592: Precast shop drawings for construction. Level 5 | 2026-08-10 | 47 | 47 | Waiting for Oliver advise-KPTG-IntCorr-001219
Auspan-TRANSMIT-000594: Update IFCed precast shop drawings. Levels 3, 4, 5. | 2026-08-10 | 8 | 8 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001232
Auspan-TRANSMIT-000574: Precast shop drawings for construction. Level 5. | 2026-08-03 | 5 | 0 | IFC - Waiting for Kim advise -KPTG-IntCorr-001181 | KPTG-SADV-004151 - Rejected
Auspan-TRANSMIT-000567: Precast shop drawings for construction. Level 4 | 2026-07-31 | 28 | 28 | IFC - Waiting for Kim advise- KPTG-IntCorr-001169 - 28 Drawings | KPTG-SADV-004145 - proceed as attached in the site advise | No done
Auspan-TRANSMIT-000578: Update level 3 precast shop drawings | 2026-08-05 | 2 | 2 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001198 | KPTG-IntCorr-001243 - Proceed IFC | No done
Auspan-TRANSMIT-000584: Re: Update IFCed shop drawings. Level 3. | 2026-08-06 | 1 | 1 | IFC - Oliver to advise - KPTG-IntCorr-001208 | KPTG-SADV-004147 - Proceed IFC | No done
Auspan-TRANSMIT-000587: Precast shop drawings for construction. Level 4. | 2026-08-07 | 5 | 5 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001213 | KPTG-SADV-004148 - IFC except 4P5041 | no done
Auspan-TRANSMIT-000591: Precast shop drawings for construction. Level 4 | 2026-08-10 | 1 | 1 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001225 | KPTG-IntCorr-001230 - Proceed IFC | No done
Auspan-TRANSMIT-000593: Precast shop drawings for construction. Level 4. | 2026-08-10 | 9 | 9 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001222 | KPTG-IntCorr-001241 - proceed IFC except 4P5050 | No done
Auspan-TRANSMIT-000596: Re: GMAC - Level 3 Additional precast penetrations | 2026-08-10 | 3 | 3 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001224 | KPTG-IntCorr-001231 - proceed IFC | No done
Total |  | 295 | 290

## 12-08
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-08-12 | [5 empty] | Project: | 352-MAC - Greystar
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
Auspan-TRANSMIT-000602: Re: Precast shop drawings for approval. Zone 4, 5 level 7 | 4 | 0 | 0 | ACC#1708 ¦ WF-000798 | Auspan-TRANSMIT-000567: Precast shop drawings for construction. Level 4 | 28 | 0 | 22 OK TO IFC- KPTG-TRANSMIT-003185; 1 Drawing Updated; 5 Rejected as advised by Kapitol PC.KPTG-SADV-004145 Published
Auscool-TRANSMIT-000074: Re: Ground Floor - Zone 1 and 3 IFA drawings | 2 | 0 | 0 | ACC#1710 ¦ WF-000799 | Auspan-TRANSMIT-000578: Update level 3 precast shop drawings | 2 | 0 | Registerd and transmitted KPTG-TRANSMIT-003187
M.2-TRANSMIT-000073 Revised Lighting Tech Data | 0 | 24 | 0 | WF-000800 | Auspan-TRANSMIT-000584: Re: Update IFCed shop drawings. Level 3. | 1 | 0 | Registerd and transmitted KPTG-TRANSMIT-003189
Auspan-TRANSMIT-000600 Update IFCed precast shop drawings. | 18 | 0 | 18 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001249 | Auspan-TRANSMIT-000587: Precast shop drawings for construction. Level 4. | 5 | 0 | 4 OK TO IFC-KPTG-TRANSMIT-003191; 1 Rejected as advised by Kapitol PC.KPTG-SADV-004148
Auspan-TRANSMIT-000600 Update IFCed precast shop drawings. | 2 | 0 | 0 | Rejected -Difference in revision-DRAFT-011397 | Auspan-TRANSMIT-000591: Precast shop drawings for construction. Level 4 | 1 | 0 | IFC- Registerd and transmitted KPTG-TRANSMIT-003193
Auspan-TRANSMIT-000599: Precast shop drawings for construction. | 3 | 0 | 3 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001250 | Auspan-TRANSMIT-000593: Precast shop drawings for construction. Level 4. | 9 | 0 | IFC- Registerd and transmitted KPTG-TRANSMIT-003195 1 Rejected as advised by Kapitol PC.KPTG-SADV-004141
Auspan-TRANSMIT-000603 Re: Precast shop drawings for construction. Level 4. | 1 | 0 | 1 | IFC - waiting for advise - KPTG-IntCorr-001251 | Auspan-TRANSMIT-000596: Re: GMAC - Level 3 Additional precast penetrations | 3 | 0 | IFC- Registerd and transmitted KPTG-TRANSMIT-003197
Auspan-TRANSMIT-000604: Re: GMAC - L4 Additional precast penetrations | 1 | 0 | 0 | Rejected due to incorrect revision history - DRAFT-011408 | Auspan-TRANSMIT-000600 Update IFCed precast shop drawings. | 2 | 0 | Rejected -Difference in revision-DRAFT-011397
[5 empty] | Auspan-TRANSMIT-000570 Level 4 precast shop drawings for Approval -1618 | 2 | 0 | KPTG-TRANSMIT-003203
[5 empty] | Auspan-TRANSMIT-000575 Resubmit precast panel 3P5065 for approval -1638 | 1 | 0 | KPTG-TRANSMIT-003206
[5 empty] | Auspan-TRANSMIT-000604: Re: GMAC - L4 Additional precast penetrations | 1 | 0 | Rejected due to incorrect revision history - DRAFT-011408
Total | 31 | 24 | 22 |  |  | 55 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000429: Update IFCed precast shop drawings. Level 1 zone 4, 5 | 2026-06-26 | 2 | 2 | IFC - QC OK - Kapitol PC Kim to confirm - KPTG-IntCorr-000778 - ON HOLD AS ADVISED BY KIM | ON HOLD AS ADVISED BY KIM
Auspan-TRANSMIT-000441 Precast shop drawings for construction. Level 6. | 2026-06-30 | 34 | 34 | IFC - Waiting for advise KPTG-IntCorr-000804 | Pending services coordination
Auspan-TRANSMIT-000489: Precast shop drawings for construction. Level 4. | 2026-07-10 | 46 | 46 | IFC - Waiting for Kim advise - KPTG-IntCorr-000928 qc done | KPTG-SADV-004174 - proseed as per the attachment | No done
Auspan-TRANSMIT-000494: Update IFCed shop drawings. Level 3. | 2026-07-13 | 11 | 11 | IFC - Waiting for Kim advise -KPTG-IntCorr-000936 | KPTG-IntCorr-001130 - 11 are pending to update -KPTG-IntCorr-001140
Auspan-TRANSMIT-000496: Update IFCed shop drawings. Levels 5, 6. | 2026-07-13 | 6 | 6 | IFC - Waiting for Kim advise- KPTG-IntCorr-000947 | Panel are on Hold - as advised KPTG-IntCorr-000967
Auscool-TRANSMIT-000067: Basement - IFC Drawings | 2026-07-21 | 1 | 1 | Zone 2 to 5 are Ok to update register and transmit. Zone 1 is on hold - KPTG-TRANSMIT-002881
Auspan-TRANSMIT-000538: Precast shop drawings for construction. Level 5. | 2026-07-23 | 20 | 20 | IFC - Waiting for Kim advise -KPTG-IntCorr-001086
Auspan-TRANSMIT-000545: Level 5 precast shop drawings for construction | 2026-07-24 | 28 | 28 | IFC - Waiting for Kim advise -KPTG-IntCorr-001095 - 28 Drawings
Auspan-TRANSMIT-000573: Precast shop drawings for construction. Level 4. | 2026-08-03 | 13 | 13 | IFC - Waiting for Kim advise -KPTG-IntCorr-001180 - 13 Drawings
Auspan-TRANSMIT-000577: Precast shop drawings for construction. Levels 4, 5 | 2026-08-04 | 17 | 17 | IFC - Waiting for Oliver advise -KPTG-IntCorr-001187 | Please refer to the attached - KPTG-SADV-004180 | No done
Auspan-TRANSMIT-000579: Update IFCed level 4 precast shop drawings. | 2026-08-05 | 5 | 5 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001199
Auspan-TRANSMIT-000586: Precast shop drawings for construction. Level 3. | 2026-08-07 | 3 | 3 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001212 | Proceed IFC - KPTG-IntCorr-001252 | No done
Auspan-TRANSMIT-000592: Precast shop drawings for construction. Level 5 | 2026-08-10 | 47 | 47 | Waiting for Oliver advise-KPTG-IntCorr-001219
Auspan-TRANSMIT-000594: Update IFCed precast shop drawings. Levels 3, 4, 5. | 2026-08-10 | 8 | 8 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001232
Auspan-TRANSMIT-000598: Precast shop drawings for constructon. Zone 3 levels 4, 5. | 2026-08-11 | 7 | 7 | IIFC - Waiting for Oliver advise-KPTG-IntCorr-001235
Auspan-TRANSMIT-000574: Precast shop drawings for construction. Level 5. | 2026-08-03 | 5 | 0 | IFC - Waiting for Kim advise -KPTG-IntCorr-001181 | KPTG-SADV-004151 - Rejected
Auspan-TRANSMIT-000567: Precast shop drawings for construction. Level 4 | 2026-07-31 | 28 | 0 | IFC - Waiting for Kim advise- KPTG-IntCorr-001169 - 28 Drawings | KPTG-SADV-004145 - proceed as attached in the site advise
Auspan-TRANSMIT-000578: Update level 3 precast shop drawings | 2026-08-05 | 2 | 0 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001198 | KPTG-IntCorr-001243 - Proceed IFC
Auspan-TRANSMIT-000584: Re: Update IFCed shop drawings. Level 3. | 2026-08-06 | 1 | 0 | IFC - Oliver to advise - KPTG-IntCorr-001208 | KPTG-SADV-004147 - Proceed IFC
Auspan-TRANSMIT-000587: Precast shop drawings for construction. Level 4. | 2026-08-07 | 5 | 0 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001213 | KPTG-SADV-004148 - IFC except 4P5041
Auspan-TRANSMIT-000591: Precast shop drawings for construction. Level 4 | 2026-08-10 | 1 | 0 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001225 | KPTG-IntCorr-001230 - Proceed IFC
Auspan-TRANSMIT-000593: Precast shop drawings for construction. Level 4. | 2026-08-10 | 9 | 0 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001222 | KPTG-IntCorr-001241 - proceed IFC except 4P5050
Auspan-TRANSMIT-000596: Re: GMAC - Level 3 Additional precast penetrations | 2026-08-10 | 3 | 0 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001224 | KPTG-IntCorr-001231 - proceed IFC
Total |  | 302 | 248

## 13-08
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-08-13 | [5 empty] | Project: | 352-MAC - Greystar
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
JCBa-TRANSMIT-000165: Updated Architectural Documentation - GA Plans, Door Schedule & Door Elevations | 48 | 0 | 0 | ACC#1715 ¦WF-000802 | Auspan-TRANSMIT-000486 Precast shop drawings for approval. Levels 5, 6 zone 3 -1460 | 51 | 0 | KPTG-TRANSMIT-003213 3 drawings terminated.
LVPG-TRANSMIT-000046 LVPG-HY-TECH-069 - 100mm Stainless Allthrough | 0 | 1 | 0 | Rejected due to incorrect document number - DRAFT-011451 | Auspan-TRANSMIT-000518 Precast shop drawings for approval. Levels 4, 5, 6 zone 4, 5 -1512 | 59 | 0 | KPTG-TRANSMIT-003218
IJF-TRANSMIT-000006 Re Joinery - Prototype Drawings | 1 | 0 | 0 | 1 drawing review is re-initiated. ACC#1713 ¦WF-000801 | IJF-TRANSMIT-000006 Re Joinery - Prototype Drawings -ACC#1653 | 44 | 0 | KPTG-TRANSMIT-003209 I drawing terminated, and initiated review again.
JCBa-TRANSMIT-000165: Door Schedule | 0 | 1 | 0 | ACC#1717 ¦WF-000803 | Auspan-TRANSMIT-000489: Precast shop drawings for construction. Level 4. | 46 | 0 | 38 are ok to IFC -KPTG-TRANSMIT-003226; 5 Rejected by Kapitol PC.KPTG-SADV-004174; 3 are already updated and distributed
Auspan-TRANSMIT-000605: Re: Architectural Documentation - Return & Precast Return External Elevations | 7 | 0 | 7 | ifc - Witing for confirmation from Oliver -KPTG-IntCorr-001265 | Auspan-TRANSMIT-000577: Precast shop drawings for construction. Levels 4, 5 | 17 | 0 | 8 are ok to IFC-KPTG-TRANSMIT-003228 ; 8 Rejected by Kapitol PC.KPTG-SADV-004180; 1 Drawing updated and distributed
Auspan-TRANSMIT-000606: Re: Removal of Wet Joint - HB | 20 | 0 | 20 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001266 | Auspan-TRANSMIT-000586: Precast shop drawings for construction. Level 3. | 3 | 0 | IFC registered and transmit KPTG-TRANSMIT-003231
Auspan-TRANSMIT-000606: Re: Removal of Wet Joint - HB | 1 | 0 | 0 | Rejected due to incorrect drawing revision hisotory. DRAFT-011461 | LVPG-TRANSMIT-000046 LVPG-HY-TECH-069 - 100mm Stainless | 1 | 0 | Rejected due to incorrect document number - DRAFT-011451
Auspan-TRANSMIT-000607: Re: Removal of Wet Joint - HB | 1 | 0 | 1 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001267 | KPTG-IntCorr-001221 Electrical Services Penetration layouts - Ground - Level 6 | 11 | 0 | KPTG-WTRAN-001460 - Trade partner superseded the drawings, and distributed.
Auspan-TRANSMIT-000608 Update IFCed precast shop drawings. Level 3. | 4 | 0 | 4 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001268 | Auscool-TRANSMIT-000075: MSSB Load Table & Schematics | 2 | 0 | Rejected due to lack of document number -DRAFT-011490
Auspan-TRANSMIT-000609: Update IFCed shop drawings. Levels 4, 5. Panels are still the same. Just add note for class 2 finish. | 8 | 0 | 8 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001269 | Auspan-TRANSMIT-000603 Re: Precast shop drawings for construction. Level 4. | 1 | 0 | IFC registered and transmit KPTG-TRANSMIT-003224
Auspan-TRANSMIT-000610: Re: Update IFCed precast shop drawings. | 9 | 0 | 9 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001270 | Auspan-TRANSMIT-000599: Precast shop drawings for construction. | 3 | 0 | IFC registered and transmit KPTG-TRANSMIT-003222
JCBa-TRANSMIT-000165 -Door schedule and elevations. ARC - SME REVIEW | 5 | 0 | 0 | ACC#1718 | Auspan-TRANSMIT-000606: Re: Removal of Wet Joint - HB | 1 | 0 | Rejected due to incorrect drawing revision hisotory. DRAFT-011461
IJF-TRANSMIT-000009: Joinery - Prototype Drawings - Rev C2 | 38 | 0 | 0 | ACC#1724 ¦ WF-000805
Auspan-TRANSMIT-000611: Re: GMAC - L4 Additional precast penetrations - Drawing QA error | 3 | 0 | 3 | ifc - Witing for confirmation from Oliver KPTG-IntCorr-001272
PCForm-TRANSMIT-000108: Level 2 & 3 propping plans | 6 | 0 | 6 | IFC - Michael to advise - KPTG-IntCorr-001274
Auscool-TRANSMIT-000075: MSSB Load Table & Schematics | 0 | 2 | 0 | Rejected due to lack of document number -DRAFT-011490
M.2-TRANSMIT-000074: Electrical Services - Level 00 External lighting layout | 1 | 0 | 0 | ACC#1730 ¦ WF-000806
M.2-TRANSMIT-000075: Electrical Services - B1, Ground and Level 6 lighting layouts | 15 | 0 | 0 | ACC#1735 ¦WF-000808
M.2-TRANSMIT-000076: Electrical Services - B1, L00, L02-05, L06 & L07 Power & comms layouts | 25 | 0 | 0 | ACC#1738 ¦ WF-000809
M.2-TRANSMIT-000077 Electrical Services - B1-Level 6 Cabletray & Penetration layouts | 25 | 0 | 0 | ACC#1742 ¦ WF-000810
M.2-TRANSMIT-000078: Electrical Services - Level 7 Cabletray & Penetration layouts | 5 | 0 | 0 | ACC#1733 ¦WF-000807
Auspan-TRANSMIT-000486 Precast shop drawings for approval | 2 | 0 | 0 | ACC #1720
Auspan-TRANSMIT-000518 Precast shop drawings for approval | 3 | 0 | 0 | ACC #1720
Total | 227 | 4 | 58 |  |  | 239 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000429: Update IFCed precast shop drawings. Level 1 zone 4, 5 | 2026-06-26 | 2 | 2 | IFC - QC OK - Kapitol PC Kim to confirm - KPTG-IntCorr-000778 - ON HOLD AS ADVISED BY KIM | ON HOLD AS ADVISED BY KIM
Auspan-TRANSMIT-000441 Precast shop drawings for construction. Level 6. | 2026-06-30 | 34 | 34 | IFC - Waiting for advise KPTG-IntCorr-000804 | Pending services coordination
Auspan-TRANSMIT-000494: Update IFCed shop drawings. Level 3. | 2026-07-13 | 11 | 11 | IFC - Waiting for Kim advise -KPTG-IntCorr-000936 | KPTG-IntCorr-001130 - 11 are pending to update -KPTG-IntCorr-001140
Auspan-TRANSMIT-000496: Update IFCed shop drawings. Levels 5, 6. | 2026-07-13 | 6 | 6 | IFC - Waiting for Kim advise- KPTG-IntCorr-000947 | Panel are on Hold - as advised KPTG-IntCorr-000967
Auscool-TRANSMIT-000067: Basement - IFC Drawings | 2026-07-21 | 1 | 1 | Zone 2 to 5 are Ok to update register and transmit. Zone 1 is on hold - KPTG-TRANSMIT-002881
Auspan-TRANSMIT-000538: Precast shop drawings for construction. Level 5. | 2026-07-23 | 20 | 20 | IFC - Waiting for Kim advise -KPTG-IntCorr-001086
Auspan-TRANSMIT-000545: Level 5 precast shop drawings for construction | 2026-07-24 | 28 | 28 | IFC - Waiting for Kim advise -KPTG-IntCorr-001095 - 28 Drawings
Auspan-TRANSMIT-000573: Precast shop drawings for construction. Level 4. | 2026-08-03 | 13 | 13 | IFC - Waiting for Kim advise -KPTG-IntCorr-001180 - 13 Drawings
Auspan-TRANSMIT-000579: Update IFCed level 4 precast shop drawings. | 2026-08-05 | 5 | 5 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001199
Auspan-TRANSMIT-000592: Precast shop drawings for construction. Level 5 | 2026-08-10 | 47 | 47 | Waiting for Oliver advise-KPTG-IntCorr-001219
Auspan-TRANSMIT-000594: Update IFCed precast shop drawings. Levels 3, 4, 5. | 2026-08-10 | 8 | 8 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001232
Auspan-TRANSMIT-000598: Precast shop drawings for constructon. Zone 3 levels 4, 5. | 2026-08-11 | 7 | 7 | IIFC - Waiting for Oliver advise-KPTG-IntCorr-001235
Auspan-TRANSMIT-000600 Update IFCed precast shop drawings. | 2026-08-12 | 18 | 18 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001249
Auspan-TRANSMIT-000599: Precast shop drawings for construction. | 2026-08-12 | 3 | 0 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001250 | Please ifc KPTG-IntCorr-001256
Auspan-TRANSMIT-000603 Re: Precast shop drawings for construction. Level 4. | 2026-08-12 | 1 | 0 | IFC - waiting for advise - KPTG-IntCorr-001251 | Please IFC -KPTG-IntCorr-001255
Auspan-TRANSMIT-000489: Precast shop drawings for construction. Level 4. | 2026-07-10 | 46 | 0 | IFC - Waiting for Kim advise - KPTG-IntCorr-000928 qc done | KPTG-SADV-004174 - proseed as per the attachment
Auspan-TRANSMIT-000577: Precast shop drawings for construction. Levels 4, 5 | 2026-08-04 | 17 | 0 | IFC - Waiting for Oliver advise -KPTG-IntCorr-001187 | Please refer to the attached - KPTG-SADV-004180
Auspan-TRANSMIT-000586: Precast shop drawings for construction. Level 3. | 2026-08-07 | 3 | 0 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001212 | Proceed IFC - KPTG-IntCorr-001252
Total |  | 270 | 200

## 14-08
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-08-14 | [5 empty] | Project: | 352-MAC - Greystar
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
Rinco-TRANSMIT-000068 Structural updated fence drawing | 1 | 0 | 0 | ACC#1745 ¦ WF-000811 | Auspan-TRANSMIT-000589 Precast shop drawings for approval. Level 5 -#1670 | 5 | 0 | 4 drawings closed and 1 drawing review terminated and superseded KPTG-TRANSMIT-003239
Auscool-TRANSMIT-000077: updated document number | 0 | 1 | 1 | Brent to advise -KPTG-IntCorr-001282 | Auspan-TRANSMIT-000613: Precast shop drawings for construction. Levels 4, 5. | 2 | 0 | Rejected - Difference in revision and status- DRAFT-011506
Auscool-TRANSMIT-000078: updated document number mssb schematics | 0 | 1 | 1 | Brent to advise KPTG-IntCorr-001284 | JCBa-TRANSMIT-000166: Re: Updated Architectural Documentation - GA Plans, Door Schedule & Door Elevations | 1 | 0 | Native fle, updated register only.
Auspan-TRANSMIT-000613: Precast shop drawings for construction. Levels 4, 5. | 39 | 0 | 39 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001280 | PCForm-TRANSMIT-000108: Level 2 & 3 propping plans | 6 | 0 | Update register - KPTG-IntCorr-001281
Auspan-TRANSMIT-000613: Precast shop drawings for construction. Levels 4, 5. | 2 | 0 | 0 | Rejected - Difference in revision and status- DRAFT-011506 | Auspan-TRANSMIT-000615: Re: Panel Weight Issue - 2P5065 | 2 | 0 | Rejected by Kapitol PC. KPTG-SADV-004235
JCBa-TRANSMIT-000166: Re: Updated Architectural Documentation - GA Plans, Door Schedule & Door Elevations | 0 | 1 | 0 | Native fle, updated register only. | M.2-TRANSMIT-000080: Apartment DB Shop Drawings | 3 | 0 | Rejected due to incomplete titile and drawing number error. DRAFT-011543
Auspan-TRANSMIT-000615: Re: Panel Weight Issue - 2P5065 | 2 | 0 | 0 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001283 Rejected by Kapitol PC. KPTG-SADV-004235
POTTSENG-TRANSMIT-000067: GMAC: HYDRAULIC SERVICES - DRAINAGE - LEVELS 01-04 - ZONES 1-5 LAYOUTS | 10 | 0 | 0 | ACC#1747 ¦ WF-000812
KPTG-TRANSMIT-003235: Re: Balustrade & Screen Shop Drawing Details IFA | 7 | 0 | 0 | ACC#1751 ¦ WF-000813
M.2-TRANSMIT-000080: Apartment DB Shop Drawings | 3 | 0 | 0 | Rejected due to incomplete titile and drawing number error. DRAFT-011543
Total | 64 | 3 | 41 |  |  | 19 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000429: Update IFCed precast shop drawings. Level 1 zone 4, 5 | 2026-06-26 | 2 | 2 | IFC - QC OK - Kapitol PC Kim to confirm - KPTG-IntCorr-000778 - ON HOLD AS ADVISED BY KIM | ON HOLD AS ADVISED BY KIM
Auspan-TRANSMIT-000441 Precast shop drawings for construction. Level 6. | 2026-06-30 | 34 | 34 | IFC - Waiting for advise KPTG-IntCorr-000804 | Pending services coordination
Auspan-TRANSMIT-000494: Update IFCed shop drawings. Level 3. | 2026-07-13 | 11 | 11 | IFC - Waiting for Kim advise -KPTG-IntCorr-000936 | KPTG-IntCorr-001130 - 11 are pending to update -KPTG-IntCorr-001140
Auspan-TRANSMIT-000496: Update IFCed shop drawings. Levels 5, 6. | 2026-07-13 | 6 | 6 | IFC - Waiting for Kim advise- KPTG-IntCorr-000947 | Panel are on Hold - as advised KPTG-IntCorr-000967
Auscool-TRANSMIT-000067: Basement - IFC Drawings | 2026-07-21 | 1 | 1 | Zone 2 to 5 are Ok to update register and transmit. Zone 1 is on hold - KPTG-TRANSMIT-002881
Auspan-TRANSMIT-000538: Precast shop drawings for construction. Level 5. | 2026-07-23 | 20 | 20 | IFC - Waiting for Kim advise -KPTG-IntCorr-001086
Auspan-TRANSMIT-000545: Level 5 precast shop drawings for construction | 2026-07-24 | 28 | 28 | IFC - Waiting for Kim advise -KPTG-IntCorr-001095 - 28 Drawings
Auspan-TRANSMIT-000573: Precast shop drawings for construction. Level 4. | 2026-08-03 | 13 | 13 | IFC - Waiting for Kim advise -KPTG-IntCorr-001180 - 13 Drawings
Auspan-TRANSMIT-000579: Update IFCed level 4 precast shop drawings. | 2026-08-05 | 5 | 5 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001199
Auspan-TRANSMIT-000592: Precast shop drawings for construction. Level 5 | 2026-08-10 | 47 | 47 | Waiting for Oliver advise-KPTG-IntCorr-001219
Auspan-TRANSMIT-000594: Update IFCed precast shop drawings. Levels 3, 4, 5. | 2026-08-10 | 8 | 8 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001232
Auspan-TRANSMIT-000598: Precast shop drawings for constructon. Zone 3 levels 4, 5. | 2026-08-11 | 7 | 7 | IIFC - Waiting for Oliver advise-KPTG-IntCorr-001235
Auspan-TRANSMIT-000600 Update IFCed precast shop drawings. | 2026-08-12 | 18 | 18 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001249
Auspan-TRANSMIT-000605: Re: Architectural Documentation - Return & Precast Return External Elevations | 2026-08-13 | 7 | 7 | ifc - Witing for confirmation from Oliver -KPTG-IntCorr-001265
Auspan-TRANSMIT-000606: Re: Removal of Wet Joint - HB | 2026-08-13 | 20 | 20 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001266
Auspan-TRANSMIT-000607: Re: Removal of Wet Joint - HB | 2026-08-13 | 1 | 1 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001267
Auspan-TRANSMIT-000608 Update IFCed precast shop drawings. Level 3. | 2026-08-13 | 4 | 4 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001268
Auspan-TRANSMIT-000609: Update IFCed shop drawings. Levels 4, 5. Panels are still the same. Just add note for class 2 finish. | 2026-08-13 | 8 | 8 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001269
Auspan-TRANSMIT-000610: Re: Update IFCed precast shop drawings. | 2026-08-13 | 9 | 9 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001270
Auspan-TRANSMIT-000611: Re: GMAC - L4 Additional precast penetrations - Drawing QA error | 2026-08-13 | 3 | 3 | ifc - Witing for confirmation from Oliver KPTG-IntCorr-001272
PCForm-TRANSMIT-000108: Level 2 & 3 propping plans | 2026-08-13 | 6 | 0 | IFC - Michael to advise - KPTG-IntCorr-001274 | Update register - KPTG-IntCorr-001281
Total |  | 258 | 252

## 17-08
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-08-17 | [5 empty] | Project: | 352-MAC - Greystar
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
Auspan-TRANSMIT-000616: Re: Precast shop drawings for construction. Levels 4, 5 | 9 | 0 | 9 | FC - Waiting for Oliver advise-KPTG-IntCorr-001287 | Auspan-TRANSMIT-000617: Update IFCed precast shop drawing. There is no change to the panels | 1 | 0 | Rejected - Difference in revision- DRAFT-011548
Auspan-TRANSMIT-000617: Update IFCed precast shop drawing. There is no change to the panels | 7 | 0 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001288 7 Drawings | INDS-TRANSMIT-000060: Wet Fire - Level 2 | 5 | 0 | Transmittal superseded - by INDS-TRANSMIT-000061
Auspan-TRANSMIT-000617: Update IFCed precast shop drawing. There is no change to the panels | 1 | 0 | 0 | Rejected - Difference in revision- DRAFT-011548
Auspan-TRANSMIT-000618: Update IFCed precast shop drawings | 4 | 0 | 4 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001289
Auspan-TRANSMIT-000619: Precast shop drawings for approval. Level 7 zone 4, 5. | 51 | 0 | 51 | IFA ACC issues , cannot capture title
Auspan-TRANSMIT-000619: Precast shop drawings for approval. Level 7 zone 4, 5. | 4 | 0 | 4 | IFA ACC issues , cannot capture title
Auspan-TRANSMIT-000620: Update IFCed precast shop drawings. | 2 | 0 | 2 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001290
INDS-TRANSMIT-000060: Wet Fire - Level 2 | 5 | 0 | 0 | Transmittal superseded - by INDS-TRANSMIT-000061
INDS-TRANSMIT-000061: Wet Fire - Level 2 | 5 | 0 | 5 | ACC issues , cannot capture title
INDS-TRANSMIT-000062: Wet Fire - Level 3 | 5 | 0 | 5 | ACC issues , cannot capture title
Auspan-TRANSMIT-000621: Update IFCed precast shop drawings. | 3 | 0 | 3 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001291
Total | 96 | 0 | 90 |  |  | 6 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000429: Update IFCed precast shop drawings. Level 1 zone 4, 5 | 2026-06-26 | 2 | 2 | IFC - QC OK - Kapitol PC Kim to confirm - KPTG-IntCorr-000778 - ON HOLD AS ADVISED BY KIM | ON HOLD AS ADVISED BY KIM
Auspan-TRANSMIT-000441 Precast shop drawings for construction. Level 6. | 2026-06-30 | 34 | 34 | IFC - Waiting for advise KPTG-IntCorr-000804 | Pending services coordination
Auspan-TRANSMIT-000494: Update IFCed shop drawings. Level 3. | 2026-07-13 | 11 | 11 | IFC - Waiting for Kim advise -KPTG-IntCorr-000936 | KPTG-IntCorr-001130 - 11 are pending to update -KPTG-IntCorr-001140
Auspan-TRANSMIT-000496: Update IFCed shop drawings. Levels 5, 6. | 2026-07-13 | 6 | 6 | IFC - Waiting for Kim advise- KPTG-IntCorr-000947 | Panel are on Hold - as advised KPTG-IntCorr-000967
Auscool-TRANSMIT-000067: Basement - IFC Drawings | 2026-07-21 | 1 | 1 | Zone 2 to 5 are Ok to update register and transmit. Zone 1 is on hold - KPTG-TRANSMIT-002881
Auspan-TRANSMIT-000538: Precast shop drawings for construction. Level 5. | 2026-07-23 | 20 | 20 | IFC - Waiting for Kim advise -KPTG-IntCorr-001086
Auspan-TRANSMIT-000545: Level 5 precast shop drawings for construction | 2026-07-24 | 28 | 28 | IFC - Waiting for Kim advise -KPTG-IntCorr-001095 - 28 Drawings
Auspan-TRANSMIT-000573: Precast shop drawings for construction. Level 4. | 2026-08-03 | 13 | 13 | IFC - Waiting for Kim advise -KPTG-IntCorr-001180 - 13 Drawings
Auspan-TRANSMIT-000579: Update IFCed level 4 precast shop drawings. | 2026-08-05 | 5 | 5 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001199
Auspan-TRANSMIT-000592: Precast shop drawings for construction. Level 5 | 2026-08-10 | 47 | 47 | Waiting for Oliver advise-KPTG-IntCorr-001219
Auspan-TRANSMIT-000594: Update IFCed precast shop drawings. Levels 3, 4, 5. | 2026-08-10 | 8 | 8 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001232
Auspan-TRANSMIT-000598: Precast shop drawings for constructon. Zone 3 levels 4, 5. | 2026-08-11 | 7 | 7 | IIFC - Waiting for Oliver advise-KPTG-IntCorr-001235
Auspan-TRANSMIT-000600 Update IFCed precast shop drawings. | 2026-08-12 | 18 | 18 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001249
Auspan-TRANSMIT-000605: Re: Architectural Documentation - Return & Precast Return External Elevations | 2026-08-13 | 7 | 7 | ifc - Witing for confirmation from Oliver -KPTG-IntCorr-001265
Auspan-TRANSMIT-000606: Re: Removal of Wet Joint - HB | 2026-08-13 | 20 | 20 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001266
Auspan-TRANSMIT-000607: Re: Removal of Wet Joint - HB | 2026-08-13 | 1 | 1 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001267
Auspan-TRANSMIT-000608 Update IFCed precast shop drawings. Level 3. | 2026-08-13 | 4 | 4 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001268
Auspan-TRANSMIT-000609: Update IFCed shop drawings. Levels 4, 5. Panels are still the same. Just add note for class 2 finish. | 2026-08-13 | 8 | 8 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001269
Auspan-TRANSMIT-000610: Re: Update IFCed precast shop drawings. | 2026-08-13 | 9 | 9 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001270
Auspan-TRANSMIT-000611: Re: GMAC - L4 Additional precast penetrations - Drawing QA error | 2026-08-13 | 3 | 3 | ifc - Witing for confirmation from Oliver KPTG-IntCorr-001272
Auscool-TRANSMIT-000077: updated document number | 2026-08-14 | 1 | 1 | Brent to advise -KPTG-IntCorr-001282
Auscool-TRANSMIT-000078: updated document number mssb schematics | 2026-08-14 | 1 | 1 | Brent to advise KPTG-IntCorr-001284
Auspan-TRANSMIT-000613: Precast shop drawings for construction. Levels 4, 5. | 2026-08-14 | 39 | 39 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001280
Total |  | 293 | 293

## 18-08
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-08-18 | [5 empty] | Project: | 352-MAC - Greystar
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
RDSBIM-TRANSMIT-000096 GREYSTAR L02 PARTITION IFR SUBMISSION | 6 | 0 | 0 | ACC#1761 ¦ WF-000817 | Auspan-TRANSMIT-000619: Precast shop drawings for approval. Level 7 zone 4, 5. | 4 | 0 | Rejected - Difference in title -DRAFT-011563
Auspan-TRANSMIT-000622: Resubmit shop drawings for approval. | 2 | 0 | 0 | ACC#1756 ¦ WF-000815 | RDSBIM-TRANSMIT-000087 GREYSTAR LEVEL 03 CONCRETE PROFILE PLAN - ACC#1674 | 6 | 0 | Review Terminated as requested by RDS to update the drawings.
Auspan-TRANSMIT-000623: Precast shop drawings for construction. Levels 3 and 4 zone 4, 5 | 7 | 0 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001297 | RDSBIM-TRANSMIT-000089 GREYSTAR LEVEL 04 CONCRETE PROFILE PLAN - ACC# 1672 | 6 | 0 | Review Terminated as requested by RDS to update the drawings.
Auspan-TRANSMIT-000624: Precast shop drawings for construction. Levels 3, 5, 6. | 21 | 0 | 21 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001292 | RDSBIM-TRANSMIT-000092 GREYSTAR ¦ LEVEL 05 CONCRETE PROFILE PLAN - ACC#1660 | 6 | 0 | Review Terminated as requested by RDS to update the drawings.
Auspan-TRANSMIT-000625: Update IFCed precast shop drawings. No change to the panels. | 2 | 0 | 2 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001301 KPTG-SADV-004297 - Proceed IFC | Auspan-TRANSMIT-000598: Precast shop drawings for constructon. Zone 3 levels 4, 5. | 7 | 0 | All rejected by Oliver - KPTG-SADV-004285 -
INDS-TRANSMIT-000063: Dry Fire - Level 2 | 5 | 0 | 0 | ACC#1764 ¦ WF-000819
RDSBIM-TRANSMIT-000097: GREYSTAR ¦ LEVEL 03 CONCRETE PROFILE PLAN | 6 | 0 | 0 | ACC#1768 ¦ WF-000820
RDSBIM-TRANSMIT-000098: GREYSTAR ¦ LEVEL 04 CONCRETE PROFILE PLAN | 6 | 0 | 0 | ACC#1770 ¦ WF-000821
RDSBIM-TRANSMIT-000099 GREYSTAR LEVEL 05 CONCRETE PROFILE PLAN | 6 | 0 | 0 | ACC#1772 ¦ WF-000822
Total | 61 | 0 | 30 |  |  | 29 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000429: Update IFCed precast shop drawings. Level 1 zone 4, 5 | 2026-06-26 | 2 | 2 | IFC - QC OK - Kapitol PC Kim to confirm - KPTG-IntCorr-000778 - ON HOLD AS ADVISED BY KIM | ON HOLD AS ADVISED BY KIM
Auspan-TRANSMIT-000441 Precast shop drawings for construction. Level 6. | 2026-06-30 | 34 | 34 | IFC - Waiting for advise KPTG-IntCorr-000804 | Pending services coordination
Auspan-TRANSMIT-000494: Update IFCed shop drawings. Level 3. | 2026-07-13 | 11 | 11 | IFC - Waiting for Kim advise -KPTG-IntCorr-000936 | KPTG-IntCorr-001130 - 11 are pending to update -KPTG-IntCorr-001140 KPTG-SADV-004278 -Proceed IFC | not done
Auspan-TRANSMIT-000496: Update IFCed shop drawings. Levels 5, 6. | 2026-07-13 | 6 | 6 | IFC - Waiting for Kim advise- KPTG-IntCorr-000947 | Panel are on Hold - as advised KPTG-IntCorr-000967
Auscool-TRANSMIT-000067: Basement - IFC Drawings | 2026-07-21 | 1 | 1 | Zone 2 to 5 are Ok to update register and transmit. Zone 1 is on hold - KPTG-TRANSMIT-002881
Auspan-TRANSMIT-000538: Precast shop drawings for construction. Level 5. | 2026-07-23 | 20 | 20 | IFC - Waiting for Kim advise -KPTG-IntCorr-001086
Auspan-TRANSMIT-000545: Level 5 precast shop drawings for construction | 2026-07-24 | 28 | 28 | IFC - Waiting for Kim advise -KPTG-IntCorr-001095 - 28 Drawings
Auspan-TRANSMIT-000573: Precast shop drawings for construction. Level 4. | 2026-08-03 | 13 | 13 | IFC - Waiting for Kim advise -KPTG-IntCorr-001180 - 13 Drawings
Auspan-TRANSMIT-000579: Update IFCed level 4 precast shop drawings. | 2026-08-05 | 5 | 5 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001199 | KPTG-SADV-004283 - Refer to the attached comments | not done
Auspan-TRANSMIT-000592: Precast shop drawings for construction. Level 5 | 2026-08-10 | 47 | 47 | Waiting for Oliver advise-KPTG-IntCorr-001219
Auspan-TRANSMIT-000594: Update IFCed precast shop drawings. Levels 3, 4, 5. | 2026-08-10 | 8 | 8 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001232 | KPTG-IntCorr-001302 - Proceed IFC | not done
Auspan-TRANSMIT-000600 Update IFCed precast shop drawings. | 2026-08-12 | 18 | 18 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001249
Auspan-TRANSMIT-000605: Re: Architectural Documentation - Return & Precast Return External Elevations | 2026-08-13 | 7 | 7 | ifc - Witing for confirmation from Oliver -KPTG-IntCorr-001265
Auspan-TRANSMIT-000606: Re: Removal of Wet Joint - HB | 2026-08-13 | 20 | 20 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001266
Auspan-TRANSMIT-000607: Re: Removal of Wet Joint - HB | 2026-08-13 | 1 | 1 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001267
Auspan-TRANSMIT-000608 Update IFCed precast shop drawings. Level 3. | 2026-08-13 | 4 | 4 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001268
Auspan-TRANSMIT-000609: Update IFCed shop drawings. Levels 4, 5. Panels are still the same. Just add note for class 2 finish. | 2026-08-13 | 8 | 8 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001269
Auspan-TRANSMIT-000610: Re: Update IFCed precast shop drawings. | 2026-08-13 | 9 | 9 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001270
Auspan-TRANSMIT-000611: Re: GMAC - L4 Additional precast penetrations - Drawing QA error | 2026-08-13 | 3 | 3 | ifc - Witing for confirmation from Oliver KPTG-IntCorr-001272
Auscool-TRANSMIT-000077: updated document number | 2026-08-14 | 1 | 1 | Brent to advise -KPTG-IntCorr-001282
Auscool-TRANSMIT-000078: updated document number mssb schematics | 2026-08-14 | 1 | 1 | Brent to advise KPTG-IntCorr-001284
Auspan-TRANSMIT-000613: Precast shop drawings for construction. Levels 4, 5. | 2026-08-14 | 39 | 39 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001280
Auspan-TRANSMIT-000616: Re: Precast shop drawings for construction. Levels 4, 5 | 2026-08-17 | 9 | 9 | FC - Waiting for Oliver advise-KPTG-IntCorr-001287
Auspan-TRANSMIT-000617: Update IFCed precast shop drawing. There is no change to the panels | 2026-08-17 | 7 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001288 7 Drawings
Auspan-TRANSMIT-000618: Update IFCed precast shop drawings | 2026-08-17 | 4 | 4 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001289
Auspan-TRANSMIT-000620: Update IFCed precast shop drawings. | 2026-08-17 | 2 | 2 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001290
Auspan-TRANSMIT-000621: Update IFCed precast shop drawings. | 2026-08-17 | 3 | 3 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001291
INDS-TRANSMIT-000061: Wet Fire - Level 2 | 2026-08-17 | 5 | 0 | ACC#1758 ¦WF-000816
INDS-TRANSMIT-000062: Wet Fire - Level 3 | 2026-08-17 | 5 | 0 | ACC#1762 ¦(WF-000818
Auspan-TRANSMIT-000619: Precast shop drawings for approval. Level 7 zone 4, 5. | 2026-08-17 | 55 | 0 | IFA ACC issues , cannot capture title ACC#1754 ¦ (WF-000814)
Auspan-TRANSMIT-000598: Precast shop drawings for constructon. Zone 3 levels 4, 5. | 2026-08-11 | 7 | 0 | IIFC - Waiting for Oliver advise-KPTG-IntCorr-001235 | KPTG-SADV-004285 - All rejected
Total |  | 383 | 311

## 19-08
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-08-19 | [5 empty] | Project: | 352-MAC - Greystar
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
Auspan-TRANSMIT-000626: Update IFCed precast shop drawings. Level 3. | 5 | 0 | 0 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001305 Proceed IFC - KPTG-IntCorr-001322 | Auspan-TRANSMIT-000494: Update IFCed shop drawings. Level 3. | 11 | 0 | IFC Registered and transmitted KPTG-TRANSMIT-003252
Auspan-TRANSMIT-000627: Update IFCed precast shop drawings. Level 4 | 14 | 0 | 14 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001306 | Auspan-TRANSMIT-000579: Update IFCed level 4 precast shop drawings. | 5 | 0 | 1 OK TO IFC-KPTG-TRANSMIT-003254, 3 Rejected as advised by Kapitol PC-KPTG-SADV-004283, 1 Superseded
Auspan-TRANSMIT-000628: Update IFC precast shop drawings. Level 5. | 12 | 0 | 12 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001307 | Auspan-TRANSMIT-000594: Update IFCed precast shop drawings. Levels 3, 4, 5. | 8 | 0 | IFC Registered and transmitted KPTG-TRANSMIT-003256,
Auspan-TRANSMIT-000629: Update IFC precast shop drawings. Level 6. | 6 | 0 | 6 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001309 | Auspan-TRANSMIT-000625: Update IFCed precast shop drawings. No change to the panels. | 2 | 0 | IFC Registered and transmitted KPTG-TRANSMIT-003250
INDS-TRANSMIT-000064: Dry Fire - Level 3 | 5 | 0 | 0 | ACC#1778 ¦ WF-000823 | Auspan-TRANSMIT-000568 Precast shop drawings for approval. Level 4 zone 4 -1627 | 7 | 0 | KPTG-TRANSMIT-003261
INDS-TRANSMIT-000065: Dry Fire - Level 4 | 5 | 0 | 0 | IFA- ACC#1780 ¦ WF-000824 | Auspan-TRANSMIT-000626: Update IFCed precast shop drawings. Level 3 | 5 | 0 | KPTG-TRANSMIT-003264
PCForm-TRANSMIT-000115: Rigid Scaffold Set IFC | 0 | 8 | 0 | As advised by Kapitol PC , No review required- KPTG-TRANSMIT-003248 | PCForm-TRANSMIT-000115: Rigid Scaffold Set IFC | 8 | 0 | As advised by Kapitol PC , No review required- KPTG-TRANSMIT-003248
Total | 47 | 8 | 32 |  |  | 46 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000429: Update IFCed precast shop drawings. Level 1 zone 4, 5 | 2026-06-26 | 2 | 2 | IFC - QC OK - Kapitol PC Kim to confirm - KPTG-IntCorr-000778 - ON HOLD AS ADVISED BY KIM | ON HOLD AS ADVISED BY KIM
Auspan-TRANSMIT-000441 Precast shop drawings for construction. Level 6. | 2026-06-30 | 34 | 34 | IFC - Waiting for advise KPTG-IntCorr-000804 | Pending services coordination
Auspan-TRANSMIT-000496: Update IFCed shop drawings. Levels 5, 6. | 2026-07-13 | 6 | 6 | IFC - Waiting for Kim advise- KPTG-IntCorr-000947 | Panel are on Hold - as advised KPTG-IntCorr-000967
Auscool-TRANSMIT-000067: Basement - IFC Drawings | 2026-07-21 | 1 | 1 | Zone 2 to 5 are Ok to update register and transmit. Zone 1 is on hold - KPTG-TRANSMIT-002881
Auspan-TRANSMIT-000538: Precast shop drawings for construction. Level 5. | 2026-07-23 | 20 | 20 | IFC - Waiting for Kim advise -KPTG-IntCorr-001086
Auspan-TRANSMIT-000545: Level 5 precast shop drawings for construction | 2026-07-24 | 28 | 28 | IFC - Waiting for Kim advise -KPTG-IntCorr-001095 - 28 Drawings
Auspan-TRANSMIT-000573: Precast shop drawings for construction. Level 4. | 2026-08-03 | 13 | 13 | IFC - Waiting for Kim advise -KPTG-IntCorr-001180 - 13 Drawings
Auspan-TRANSMIT-000592: Precast shop drawings for construction. Level 5 | 2026-08-10 | 47 | 47 | Waiting for Oliver advise-KPTG-IntCorr-001219
Auspan-TRANSMIT-000600 Update IFCed precast shop drawings. | 2026-08-12 | 18 | 18 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001249
Auspan-TRANSMIT-000605: Re: Architectural Documentation - Return & Precast Return External Elevations | 2026-08-13 | 7 | 7 | ifc - Witing for confirmation from Oliver -KPTG-IntCorr-001265
Auspan-TRANSMIT-000606: Re: Removal of Wet Joint - HB | 2026-08-13 | 20 | 20 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001266
Auspan-TRANSMIT-000607: Re: Removal of Wet Joint - HB | 2026-08-13 | 1 | 1 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001267
Auspan-TRANSMIT-000608 Update IFCed precast shop drawings. Level 3. | 2026-08-13 | 4 | 4 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001268
Auspan-TRANSMIT-000609: Update IFCed shop drawings. Levels 4, 5. Panels are still the same. Just add note for class 2 finish. | 2026-08-13 | 8 | 8 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001269
Auspan-TRANSMIT-000610: Re: Update IFCed precast shop drawings. | 2026-08-13 | 9 | 9 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001270
Auspan-TRANSMIT-000611: Re: GMAC - L4 Additional precast penetrations - Drawing QA error | 2026-08-13 | 3 | 3 | ifc - Witing for confirmation from Oliver KPTG-IntCorr-001272
Auscool-TRANSMIT-000077: updated document number | 2026-08-14 | 1 | 1 | Brent to advise -KPTG-IntCorr-001282
Auscool-TRANSMIT-000078: updated document number mssb schematics | 2026-08-14 | 1 | 1 | Brent to advise KPTG-IntCorr-001284
Auspan-TRANSMIT-000613: Precast shop drawings for construction. Levels 4, 5. | 2026-08-14 | 39 | 39 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001280
Auspan-TRANSMIT-000616: Re: Precast shop drawings for construction. Levels 4, 5 | 2026-08-17 | 9 | 9 | FC - Waiting for Oliver advise-KPTG-IntCorr-001287
Auspan-TRANSMIT-000617: Update IFCed precast shop drawing. There is no change to the panels | 2026-08-17 | 7 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001288 7 Drawings
Auspan-TRANSMIT-000618: Update IFCed precast shop drawings | 2026-08-17 | 4 | 4 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001289
Auspan-TRANSMIT-000620: Update IFCed precast shop drawings. | 2026-08-17 | 2 | 2 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001290
Auspan-TRANSMIT-000621: Update IFCed precast shop drawings. | 2026-08-17 | 3 | 3 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001291
Auspan-TRANSMIT-000623: Precast shop drawings for construction. Levels 3 and 4 zone 4, 5 | 2026-08-18 | 7 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001297
Auspan-TRANSMIT-000624: Precast shop drawings for construction. Levels 3, 5, 6. | 2026-08-18 | 21 | 21 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001292
Auspan-TRANSMIT-000625: Update IFCed precast shop drawings. No change to the panels. | 2026-08-18 | 2 | 0 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001301 | KPTG-SADV-004297 - Proceed IFC
Auspan-TRANSMIT-000494: Update IFCed shop drawings. Level 3. | 2026-07-13 | 11 | 0 | IFC - Waiting for Kim advise -KPTG-IntCorr-000936 | KPTG-IntCorr-001130 - 11 are pending to update -KPTG-IntCorr-001140 KPTG-SADV-004278 -Proceed IFC
Auspan-TRANSMIT-000579: Update IFCed level 4 precast shop drawings. | 2026-08-05 | 5 | 0 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001199 | KPTG-SADV-004283 - Refer to the attached comments
Auspan-TRANSMIT-000594: Update IFCed precast shop drawings. Levels 3, 4, 5. | 2026-08-10 | 8 | 0 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001232 | KPTG-IntCorr-001302 - Proceed IFC
Total |  | 341 | 315

## 20-08
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-08-19 | [5 empty] | Project: | 352-MAC - Greystar
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
Auspan-TRANSMIT-000630 Update IFCed precast shop drawings. Level 3 | 1 | 0 | 1 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001330 | INDS-TRANSMIT-000053 L4 to L7 - Zone & Zone 5 -1623 | 8 | 0 | KPTG-TRANSMIT-003266
Auspan-TRANSMIT-000631: Precast shop drawings for construction. Level 4 | 7 | 0 | 7 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001329 | INDS-TRANSMIT-000056 Dry Fire - Ground -1626 | 5 | 0 | KPTG-TRANSMIT-003269
Auspan-TRANSMIT-000632: Precast shop drawings for construction. Level 5, 6 | 19 | 0 | 19 | IFC- Waiting for Oliver advise- KPTG-IntCorr-001328 | Rinco-TRANSMIT-000068 Structural updated fence drawing -1745 | 1 | 0 | KPTG-TRANSMIT-003273
Auspan-TRANSMIT-000632: Precast shop drawings for construction. Level 5, 6 | 2 | 0 | 0 | Rejected- difference in revision -DRAFT-011728 | Auspan-TRANSMIT-000632: Precast shop drawings for construction. Level 5, 6 | 2 | 0 | Rejected- difference in revision-DRAFT-011728
Auspan-TRANSMIT-000633: Re: Precast shop drawings for approval. Level 7 zone 4, 5 | 4 | 0 | 0 | ACC#1783 ¦ WF-000825 | IJF-TRANSMIT-000009 Joinery - Prototype Drawings - Rev C2 -1724 | 38 | 0 | KPTG-TRANSMIT-003279
POTTSENG-TRANSMIT-000068: GMAC: HYDRAULIC SERVICES - PENETRATION - LEVEL 02 - ZONE 3 LAYOUT | 1 | 0 | 0 | ACC#1785 ¦ WF-000826 | Auscool-TRANSMIT-000064 Re Missed Precast Penetrations – Mark-up for Review -1506 | 5 | 0 | KPTG-TRANSMIT-003282 2 are terminated already
Auspan-TRANSMIT-000630 Update IFCed precast shop drawings. Level 3 | 1 | 0 | 0 | Rejected- difference in title - DRAFT-011739 | Auscool-TRANSMIT-000064 Missed Precast Penetrations – Mark-up for Review - IFA -1508 | 21 | 0 | KPTG-TRANSMIT-003285 6 are terminated already
Auspan-TRANSMIT-000635: Panel 3P5065 | 1 | 0 | 1 | IFC- Waiting for Oliver advise KPTG-IntCorr-001331 | M.2-TRANSMIT-000069 Electrical Services Lighting layouts - L00, L01 & Typical L02-05 -1643 | 10 | 0 | KPTG-TRANSMIT-003288
POTTSENG-TRANSMIT-000069 GMAC HYDRAULIC SERVICES - DRAINAGE - GROUND - ZONES 1-5 LAYOUTS | 5 | 0 | 0 | ACC#1788 ¦WF-000827 | Auscool-TRANSMIT-000078: updated document number mssb schematics | 1 | 0 | Rejected to update document type tp The data - DRAFT-011762
Auspan-TRANSMIT-000636: Update IFCed shop drawing 3P5065 | 1 | 0 | 0 | IFC- Waiting for Oliver advise KPTG-IntCorr-001333 proceed IFC - KPTG-IntCorr-001334 | Auspan-TRANSMIT-000636: Update IFCed shop drawing 3P5065 | 1 | 0 | IFC Register and Transmit KPTG-TRANSMIT-003291
POTTSENG-TRANSMIT-000070 GMAC HYDRAULIC SERVICES - PENETRATION - LEVEL 02 - ZONE 2 LAYOUT | 1 | 0 | 0 | ACC#1790 ¦ WF-000828
Total | 43 | 0 | 28 |  |  | 92 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000429: Update IFCed precast shop drawings. Level 1 zone 4, 5 | 2026-06-26 | 2 | 2 | IFC - QC OK - Kapitol PC Kim to confirm - KPTG-IntCorr-000778 - ON HOLD AS ADVISED BY KIM | ON HOLD AS ADVISED BY KIM
Auspan-TRANSMIT-000441 Precast shop drawings for construction. Level 6. | 2026-06-30 | 34 | 34 | IFC - Waiting for advise KPTG-IntCorr-000804 | Pending services coordination
Auspan-TRANSMIT-000496: Update IFCed shop drawings. Levels 5, 6. | 2026-07-13 | 6 | 6 | IFC - Waiting for Kim advise- KPTG-IntCorr-000947 | Panel are on Hold - as advised KPTG-IntCorr-000967
Auscool-TRANSMIT-000067: Basement - IFC Drawings | 2026-07-21 | 1 | 1 | Zone 2 to 5 are Ok to update register and transmit. Zone 1 is on hold - KPTG-TRANSMIT-002881
Auspan-TRANSMIT-000538: Precast shop drawings for construction. Level 5. | 2026-07-23 | 20 | 20 | IFC - Waiting for Kim advise -KPTG-IntCorr-001086
Auspan-TRANSMIT-000545: Level 5 precast shop drawings for construction | 2026-07-24 | 28 | 28 | IFC - Waiting for Kim advise -KPTG-IntCorr-001095 - 28 Drawings
Auspan-TRANSMIT-000573: Precast shop drawings for construction. Level 4. | 2026-08-03 | 13 | 13 | IFC - Waiting for Kim advise -KPTG-IntCorr-001180 - 13 Drawings
Auspan-TRANSMIT-000592: Precast shop drawings for construction. Level 5 | 2026-08-10 | 47 | 47 | Waiting for Oliver advise-KPTG-IntCorr-001219
Auspan-TRANSMIT-000600 Update IFCed precast shop drawings. | 2026-08-12 | 18 | 18 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001249
Auspan-TRANSMIT-000605: Re: Architectural Documentation - Return & Precast Return External Elevations | 2026-08-13 | 7 | 7 | ifc - Witing for confirmation from Oliver -KPTG-IntCorr-001265
Auspan-TRANSMIT-000606: Re: Removal of Wet Joint - HB | 2026-08-13 | 20 | 20 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001266
Auspan-TRANSMIT-000607: Re: Removal of Wet Joint - HB | 2026-08-13 | 1 | 1 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001267
Auspan-TRANSMIT-000608 Update IFCed precast shop drawings. Level 3. | 2026-08-13 | 4 | 4 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001268
Auspan-TRANSMIT-000609: Update IFCed shop drawings. Levels 4, 5. Panels are still the same. Just add note for class 2 finish. | 2026-08-13 | 8 | 8 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001269
Auspan-TRANSMIT-000610: Re: Update IFCed precast shop drawings. | 2026-08-13 | 9 | 9 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001270
Auspan-TRANSMIT-000611: Re: GMAC - L4 Additional precast penetrations - Drawing QA error | 2026-08-13 | 3 | 3 | ifc - Witing for confirmation from Oliver KPTG-IntCorr-001272
Auscool-TRANSMIT-000077: updated document number | 2026-08-14 | 1 | 1 | Brent to advise -KPTG-IntCorr-001282
Auspan-TRANSMIT-000613: Precast shop drawings for construction. Levels 4, 5. | 2026-08-14 | 39 | 39 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001280
Auspan-TRANSMIT-000616: Re: Precast shop drawings for construction. Levels 4, 5 | 2026-08-17 | 9 | 9 | FC - Waiting for Oliver advise-KPTG-IntCorr-001287
Auspan-TRANSMIT-000617: Update IFCed precast shop drawing. There is no change to the panels | 2026-08-17 | 7 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001288 7 Drawings
Auspan-TRANSMIT-000618: Update IFCed precast shop drawings | 2026-08-17 | 4 | 4 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001289
Auspan-TRANSMIT-000620: Update IFCed precast shop drawings. | 2026-08-17 | 2 | 2 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001290
Auspan-TRANSMIT-000621: Update IFCed precast shop drawings. | 2026-08-17 | 3 | 3 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001291
Auspan-TRANSMIT-000623: Precast shop drawings for construction. Levels 3 and 4 zone 4, 5 | 2026-08-18 | 7 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001297
Auspan-TRANSMIT-000624: Precast shop drawings for construction. Levels 3, 5, 6. | 2026-08-18 | 21 | 21 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001292
Auspan-TRANSMIT-000627: Update IFCed precast shop drawings. Level 4 | 2026-08-19 | 14 | 14 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001306
Auspan-TRANSMIT-000628: Update IFC precast shop drawings. Level 5. | 2026-08-19 | 12 | 12 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001307
Auspan-TRANSMIT-000629: Update IFC precast shop drawings. Level 6. | 2026-08-19 | 6 | 6 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001309
Auscool-TRANSMIT-000078: updated document number mssb schematics | 2026-08-14 | 1 | 0 | Brent to advise KPTG-IntCorr-001284 | Rejected to update document type tp The data - DRAFT-011762
Total |  | 347 | 346

## 21-08
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-08-21 | [5 empty] | Project: | 352-MAC - Greystar
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
Auspan-TRANSMIT-000637 Re: Precast SD Audit. Level 3 Zone 3. | 7 | 0 | 7 | QC OK ifc - waiting for Oliver advise - KPTG-IntCorr-001338 - | RDSBIM-TRANSMIT-000093 352MAC LEVEL 02 CONCRETE PROFILE PLAN ZONE 5 -1668 | 1 | 0 | KPTG-TRANSMIT-003293
Auspan-TRANSMIT-000638 Re: Precast SD Audit. Levels 3, 4 Zone 1, 2. | 13 | 0 | 13 | QC OK ifc - waiting for Oliver advise - KPTG-IntCorr-001339
Auspan-TRANSMIT-000639: Re: Precast SD Audit. Level 3 zone 4,5. | 17 | 0 | 17 | QC OK ifc - waiting for Oliver advise - KPTG-IntCorr-001340
Auscool-TRANSMIT-000079 Greystar Kensington MSSB Schematics | 0 | 1 | 1 | Waiting for Kapitol advise - KPTG-IntCorr-001337
Auspan-TRANSMIT-000640: Update IFCed precast shop drawings. | 30 | 0 | 30 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001342
POTTSENG-TRANSMIT-000071: GMAC: HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONE 5 LAYOUT | 1 | 0 | 0 | ACC#1793 ¦ WF-000829
M.2-TRANSMIT-000086 Electrical Services Basement & Level 00 Cabletray and Penetrations | 10 | 0 | 0 | ACC#1799 ¦ WF-000831
Auspan-TRANSMIT-000641: Re: 2P349 - NLB? Update IFCed precast shop drawings. | 4 | 0 | 4 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001345
POTTSENG-TRANSMIT-000072: GAMC: HYDRAULIC SERVICES - WATER - GROUND TO LEVEL 05 - ZONES 1-5 LAYOUTS | 15 | 0 | 0 | ACC#1797 ¦ WF-000830
IJF-TRANSMIT-000011: Joinery prototype drawings - Rev C3 | 7 | 0 | 0 | ACC#1803 ¦ WF-000832
Total | 104 | 1 | 72 |  |  | 1 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000429: Update IFCed precast shop drawings. Level 1 zone 4, 5 | 2026-06-26 | 2 | 2 | IFC - QC OK - Kapitol PC Kim to confirm - KPTG-IntCorr-000778 - ON HOLD AS ADVISED BY KIM | ON HOLD AS ADVISED BY KIM
Auspan-TRANSMIT-000441 Precast shop drawings for construction. Level 6. | 2026-06-30 | 34 | 34 | IFC - Waiting for advise KPTG-IntCorr-000804 | Pending services coordination
Auspan-TRANSMIT-000496: Update IFCed shop drawings. Levels 5, 6. | 2026-07-13 | 6 | 6 | IFC - Waiting for Kim advise- KPTG-IntCorr-000947 | Panel are on Hold - as advised KPTG-IntCorr-000967
Auscool-TRANSMIT-000067: Basement - IFC Drawings | 2026-07-21 | 1 | 1 | Zone 2 to 5 are Ok to update register and transmit. Zone 1 is on hold - KPTG-TRANSMIT-002881
Auspan-TRANSMIT-000538: Precast shop drawings for construction. Level 5. | 2026-07-23 | 20 | 20 | IFC - Waiting for Kim advise -KPTG-IntCorr-001086
Auspan-TRANSMIT-000545: Level 5 precast shop drawings for construction | 2026-07-24 | 28 | 28 | IFC - Waiting for Kim advise -KPTG-IntCorr-001095 - 28 Drawings
Auspan-TRANSMIT-000573: Precast shop drawings for construction. Level 4. | 2026-08-03 | 13 | 13 | IFC - Waiting for Kim advise -KPTG-IntCorr-001180 - 13 Drawings
Auspan-TRANSMIT-000592: Precast shop drawings for construction. Level 5 | 2026-08-10 | 47 | 47 | Waiting for Oliver advise-KPTG-IntCorr-001219
Auspan-TRANSMIT-000600 Update IFCed precast shop drawings. | 2026-08-12 | 18 | 18 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001249
Auspan-TRANSMIT-000605: Re: Architectural Documentation - Return & Precast Return External Elevations | 2026-08-13 | 7 | 7 | ifc - Witing for confirmation from Oliver -KPTG-IntCorr-001265
Auspan-TRANSMIT-000606: Re: Removal of Wet Joint - HB | 2026-08-13 | 20 | 20 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001266
Auspan-TRANSMIT-000607: Re: Removal of Wet Joint - HB | 2026-08-13 | 1 | 1 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001267
Auspan-TRANSMIT-000608 Update IFCed precast shop drawings. Level 3. | 2026-08-13 | 4 | 4 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001268
Auspan-TRANSMIT-000609: Update IFCed shop drawings. Levels 4, 5. Panels are still the same. Just add note for class 2 finish. | 2026-08-13 | 8 | 8 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001269
Auspan-TRANSMIT-000610: Re: Update IFCed precast shop drawings. | 2026-08-13 | 9 | 9 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001270
Auspan-TRANSMIT-000611: Re: GMAC - L4 Additional precast penetrations - Drawing QA error | 2026-08-13 | 3 | 3 | ifc - Witing for confirmation from Oliver KPTG-IntCorr-001272
Auscool-TRANSMIT-000077: updated document number | 2026-08-14 | 1 | 1 | Brent to advise -KPTG-IntCorr-001282
Auspan-TRANSMIT-000613: Precast shop drawings for construction. Levels 4, 5. | 2026-08-14 | 39 | 39 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001280
Auspan-TRANSMIT-000616: Re: Precast shop drawings for construction. Levels 4, 5 | 2026-08-17 | 9 | 9 | FC - Waiting for Oliver advise-KPTG-IntCorr-001287
Auspan-TRANSMIT-000617: Update IFCed precast shop drawing. There is no change to the panels | 2026-08-17 | 7 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001288 7 Drawings
Auspan-TRANSMIT-000618: Update IFCed precast shop drawings | 2026-08-17 | 4 | 4 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001289
Auspan-TRANSMIT-000620: Update IFCed precast shop drawings. | 2026-08-17 | 2 | 2 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001290
Auspan-TRANSMIT-000621: Update IFCed precast shop drawings. | 2026-08-17 | 3 | 3 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001291
Auspan-TRANSMIT-000623: Precast shop drawings for construction. Levels 3 and 4 zone 4, 5 | 2026-08-18 | 7 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001297
Auspan-TRANSMIT-000624: Precast shop drawings for construction. Levels 3, 5, 6. | 2026-08-18 | 21 | 21 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001292
Auspan-TRANSMIT-000627: Update IFCed precast shop drawings. Level 4 | 2026-08-19 | 14 | 14 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001306
Auspan-TRANSMIT-000628: Update IFC precast shop drawings. Level 5. | 2026-08-19 | 12 | 12 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001307
Auspan-TRANSMIT-000629: Update IFC precast shop drawings. Level 6. | 2026-08-19 | 6 | 6 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001309
Auspan-TRANSMIT-000630 Update IFCed precast shop drawings. Level 3 | 2026-08-20 | 1 | 1 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001330
Auspan-TRANSMIT-000631: Precast shop drawings for construction. Level 4 | 2026-08-20 | 7 | 7 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001329
Auspan-TRANSMIT-000632: Precast shop drawings for construction. Level 5, 6 | 2026-08-20 | 19 | 19 | IFC- Waiting for Oliver advise- KPTG-IntCorr-001328
Auspan-TRANSMIT-000635: Panel 3P5065 | 2026-08-20 | 1 | 1 | IFC- Waiting for Oliver advise KPTG-IntCorr-001331
Total |  | 374 | 374

## 24-08
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-08-24 | [5 empty] | Project: | 352-MAC - Greystar
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
INDS-TRANSMIT-000066: Wet Fire - Ground Zone 1, 2 & 4 | 3 | 0 | 1 | IFC- Waiting for Julianne and Brent advise-KPTG-IntCorr-001350 ACC#1809 ¦ WF-000835 | Auspan-TRANSMIT-000608 Update IFCed precast shop drawings. Level 3. | 4 | 0 | IFC- KPTG-TRANSMIT-003302, 3 Rejected as advised by Kapitol PC. KPTG-IntCorr-001349
INDS-TRANSMIT-000067: Wet Fire - Level 1 | 5 | 0 | 0 | IFC- ACC#1807 ¦ WF-000834 | Auspan-TRANSMIT-000609: Update IFCed shop drawings. Levels 4, 5. Panels are still the same. Just add note for class 2 finish. | 8 | 0 | IFC - Update register and trasmit- KPTG-TRANSMIT-003304,
Auspan-TRANSMIT-000642: Resubmit precast shop drawings for approval. | 7 | 0 | 0 | IFA- ACC#1805 ¦ WF-000833 | Auspan-TRANSMIT-000627: Update IFCed precast shop drawings. Level 4 | 14 | 0 | 10 OK TO IFC- KPTG-TRANSMIT-003306, 4 Rejected as advised by Kapitol PC. KPTG-IntCorr-001347
Auspan-TRANSMIT-000643: Precast shop drawings for construction. Level 3 | 3 | 0 | 3 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001353 | Auspan-TRANSMIT-000638 Re: Precast SD Audit. Levels 3, 4 Zone 1, 2. | 13 | 0 | 3 OK TO IFC- KPTG-TRANSMIT-003308, 10 No action required. as advised by Kapitol PC. KPTG-IntCorr-001346
Auspan-TRANSMIT-000644: Precast shop drawings for construction. Level 4 | 7 | 0 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001359 | RDSBIM-TRANSMIT-000097 GREYSTAR LEVEL 03 CONCRETE PROFILE PLAN - 1768 | 6 | 0 | KPTG-TRANSMIT-003299
Auspan-TRANSMIT-000645: Precast shop drawings for construction. Level 5. | 4 | 0 | 4 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001360
Auspan-TRANSMIT-000646: Precast shop drawings for construction. Level 6. | 45 | 0 | 45 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001351
Auscool-TRANSMIT-000080 AC Schedules | 0 | 1 | 0 | WF-000836
Auscool-TRANSMIT-000081: Ac Selections | 0 | 1 | 0 | WF-000837
PSGANZ-TRANSMIT-000007 Tech Data | 0 | 11 | 0 | WF-000838
Total | 74 | 13 | 60 |  |  | 45 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000429: Update IFCed precast shop drawings. Level 1 zone 4, 5 | 2026-06-26 | 2 | 2 | IFC - QC OK - Kapitol PC Kim to confirm - KPTG-IntCorr-000778 - ON HOLD AS ADVISED BY KIM | ON HOLD AS ADVISED BY KIM
Auspan-TRANSMIT-000441 Precast shop drawings for construction. Level 6. | 2026-06-30 | 34 | 34 | IFC - Waiting for advise KPTG-IntCorr-000804 | Pending services coordination
Auspan-TRANSMIT-000496: Update IFCed shop drawings. Levels 5, 6. | 2026-07-13 | 6 | 6 | IFC - Waiting for Kim advise- KPTG-IntCorr-000947 | Panel are on Hold - as advised KPTG-IntCorr-000967
Auscool-TRANSMIT-000067: Basement - IFC Drawings | 2026-07-21 | 1 | 1 | Zone 2 to 5 are Ok to update register and transmit. Zone 1 is on hold - KPTG-TRANSMIT-002881
Auspan-TRANSMIT-000538: Precast shop drawings for construction. Level 5. | 2026-07-23 | 20 | 20 | IFC - Waiting for Kim advise -KPTG-IntCorr-001086
Auspan-TRANSMIT-000545: Level 5 precast shop drawings for construction | 2026-07-24 | 28 | 28 | IFC - Waiting for Kim advise -KPTG-IntCorr-001095 - 28 Drawings
Auspan-TRANSMIT-000573: Precast shop drawings for construction. Level 4. | 2026-08-03 | 13 | 13 | IFC - Waiting for Kim advise -KPTG-IntCorr-001180 - 13 Drawings
Auspan-TRANSMIT-000592: Precast shop drawings for construction. Level 5 | 2026-08-10 | 47 | 47 | Waiting for Oliver advise-KPTG-IntCorr-001219
Auspan-TRANSMIT-000600 Update IFCed precast shop drawings. | 2026-08-12 | 18 | 18 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001249
Auspan-TRANSMIT-000605: Re: Architectural Documentation - Return & Precast Return External Elevations | 2026-08-13 | 7 | 7 | ifc - Witing for confirmation from Oliver -KPTG-IntCorr-001265
Auspan-TRANSMIT-000606: Re: Removal of Wet Joint - HB | 2026-08-13 | 20 | 20 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001266
Auspan-TRANSMIT-000607: Re: Removal of Wet Joint - HB | 2026-08-13 | 1 | 1 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001267
Auspan-TRANSMIT-000610: Re: Update IFCed precast shop drawings. | 2026-08-13 | 9 | 9 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001270
Auspan-TRANSMIT-000611: Re: GMAC - L4 Additional precast penetrations - Drawing QA error | 2026-08-13 | 3 | 3 | ifc - Witing for confirmation from Oliver KPTG-IntCorr-001272
Auscool-TRANSMIT-000077: updated document number | 2026-08-14 | 1 | 1 | Brent to advise -KPTG-IntCorr-001282
Auspan-TRANSMIT-000613: Precast shop drawings for construction. Levels 4, 5. | 2026-08-14 | 39 | 39 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001280
Auspan-TRANSMIT-000616: Re: Precast shop drawings for construction. Levels 4, 5 | 2026-08-17 | 9 | 9 | FC - Waiting for Oliver advise-KPTG-IntCorr-001287
Auspan-TRANSMIT-000617: Update IFCed precast shop drawing. There is no change to the panels | 2026-08-17 | 7 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001288 7 Drawings
Auspan-TRANSMIT-000618: Update IFCed precast shop drawings | 2026-08-17 | 4 | 4 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001289
Auspan-TRANSMIT-000620: Update IFCed precast shop drawings. | 2026-08-17 | 2 | 2 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001290
Auspan-TRANSMIT-000621: Update IFCed precast shop drawings. | 2026-08-17 | 3 | 3 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001291
Auspan-TRANSMIT-000623: Precast shop drawings for construction. Levels 3 and 4 zone 4, 5 | 2026-08-18 | 7 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001297
Auspan-TRANSMIT-000624: Precast shop drawings for construction. Levels 3, 5, 6. | 2026-08-18 | 21 | 21 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001292
Auspan-TRANSMIT-000628: Update IFC precast shop drawings. Level 5. | 2026-08-19 | 12 | 12 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001307
Auspan-TRANSMIT-000629: Update IFC precast shop drawings. Level 6. | 2026-08-19 | 6 | 6 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001309
Auspan-TRANSMIT-000630 Update IFCed precast shop drawings. Level 3 | 2026-08-20 | 1 | 1 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001330
Auspan-TRANSMIT-000631: Precast shop drawings for construction. Level 4 | 2026-08-20 | 7 | 7 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001329
Auspan-TRANSMIT-000632: Precast shop drawings for construction. Level 5, 6 | 2026-08-20 | 19 | 19 | IFC- Waiting for Oliver advise- KPTG-IntCorr-001328
Auspan-TRANSMIT-000635: Panel 3P5065 | 2026-08-20 | 1 | 1 | IFC- Waiting for Oliver advise KPTG-IntCorr-001331
Auspan-TRANSMIT-000637 Re: Precast SD Audit. Level 3 Zone 3. | 2026-08-21 | 7 | 7 | QC OK ifc - waiting for Oliver advise - KPTG-IntCorr-001338 -
Auspan-TRANSMIT-000639: Re: Precast SD Audit. Level 3 zone 4,5. | 2026-08-21 | 17 | 17 | QC OK ifc - waiting for Oliver advise - KPTG-IntCorr-001340
Auscool-TRANSMIT-000079 Greystar Kensington MSSB Schematics | 2026-08-21 | 1 | 1 | Waiting for Kapitol advise - KPTG-IntCorr-001337
Auspan-TRANSMIT-000640: Update IFCed precast shop drawings. | 2026-08-21 | 30 | 30 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001342
Auspan-TRANSMIT-000641: Re: 2P349 - NLB? Update IFCed precast shop drawings. | 2026-08-21 | 4 | 4 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001345
Auspan-TRANSMIT-000608 Update IFCed precast shop drawings. Level 3. | 2026-08-13 | 4 | 0 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001268 | KPTG-IntCorr-001349 -Please only transmit 3P5053
Auspan-TRANSMIT-000609: Update IFCed shop drawings. Levels 4, 5. Panels are still the same. Just add note for class 2 finish. | 2026-08-13 | 8 | 0 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001269 | KPTG-IntCorr-001348 - Please IFC
Auspan-TRANSMIT-000627: Update IFCed precast shop drawings. Level 4 | 2026-08-19 | 14 | 0 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001306 | KPTG-IntCorr-001347 -Please IFC panels without comments on the attached
Auspan-TRANSMIT-000638 Re: Precast SD Audit. Levels 3, 4 Zone 1, 2. | 2026-08-21 | 13 | 0 | QC OK ifc - waiting for Oliver advise - KPTG-IntCorr-001339 | please ifc -KPTG-IntCorr-001346
Total |  | 446 | 407

## 25-08
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-08-25 | [5 empty] | Project: | 352-MAC - Greystar
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
Rinco-TRANSMIT-000069: Structural drawings Issued for Construction | 6 | 0 | 0 | ACC#1815 ¦ WF-000839 | Auspan-TRANSMIT-000643 Precast shop drawings for construction. Level 3 | 1 | 0 | KPTG-IntCorr-001356- IFC- 1 drawing only - Drawing superseded by Auspan-TRANSMIT-000648
Auspan-TRANSMIT-000648: Update IFCed precast shop drawings for construction due to penos added. | 2 | 0 | 0 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001366 KPTG-IntCorr-001368 -IFC L3 & L4 drawings only. | RDSBIM-TRANSMIT-000098 GREYSTAR LEVEL 04 CONCRETE PROFILE PLAN -1770 | 6 | 0 | KPTG-TRANSMIT-003312
Auspan-TRANSMIT-000647: Re: L4 IFC Drawings | 46 | 0 | 0 | Rejected- Difference in revision- KPTG-SADV-004453 - 2 Drawings 22 are OK TO IFC -KPTG-TRANSMIT-003330, 22 are rejected advised by Kapitol PC-KPTG-IntCorr-001367 | JCBa-TRANSMIT-000104 Architectural Documentation - Joinery Details & Materials & Finishes - 1610 | 1 | 0 | KPTG-TRANSMIT-003318
Auspan-TRANSMIT-000649 Re: Zone 1 RFi 91. Update IFCed shop drawings. Penos for overflow added | 4 | 0 | 4 | IFC waiting for Kapitol advise - KPTG-IntCorr-001372 | RDSBIM-TRANSMIT-000088 GREYSTAR GROUND FLOOR STAIR MID LANDING LAYOUT -1616 | 1 | 0 | KPTG-TRANSMIT-003315
Auspan-TRANSMIT-000648: Update IFCed precast shop drawings for construction due to penos added. | 2 | 0 | 2 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001366 | JCBa-TRANSMIT-000163 Updated Architectural Documentation - Waterproofing Plans & Facade Assembly Sections -1676 | 10 | 0 | KPTG-TRANSMIT-003321
[5 empty] | RDSBIM-TRANSMIT-000079 GREYSTAR BASEMENT LEVEL PARTITION WAL -1404 | 7 | 0 | KPTG-TRANSMIT-003332
[5 empty] | POTTSENG-TRANSMIT-000062 GMAC HYDRAULIC SERVICES - PENETRATION - LEVEL 02 - ZONE 5 LAYOUT -1665 | 1 | 0 | KPTG-TRANSMIT-003324
[5 empty] | Auspan-TRANSMIT-000551 Re Resubmit shop drawings for approval. Zone 3 and 5 level 4 1569 | 1 | 0 | KPTG-TRANSMIT-003329
[5 empty] | Auspan-TRANSMIT-000648: Update IFCed precast shop drawings for construction due to penos added. | 2 | 0 | Registered and Transmitted -KPTG-TRANSMIT-003328
[5 empty] | Auspan-TRANSMIT-000647: Re: L4 IFC Drawings | 46 | 0 | Rejected- Difference in revision- KPTG-SADV-004453 - 2 Drawings 22 are OK TO IFC -KPTG-TRANSMIT-003330, 22 are rejected advised by Kapitol PC-KPTG-IntCorr-001367 Published -22 Total 46
Total | 60 | 0 | 6 |  |  | 76 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000429: Update IFCed precast shop drawings. Level 1 zone 4, 5 | 2026-06-26 | 2 | 2 | IFC - QC OK - Kapitol PC Kim to confirm - KPTG-IntCorr-000778 - ON HOLD AS ADVISED BY KIM | ON HOLD AS ADVISED BY KIM
Auspan-TRANSMIT-000441 Precast shop drawings for construction. Level 6. | 2026-06-30 | 34 | 34 | IFC - Waiting for advise KPTG-IntCorr-000804 | Pending services coordination
Auspan-TRANSMIT-000496: Update IFCed shop drawings. Levels 5, 6. | 2026-07-13 | 6 | 6 | IFC - Waiting for Kim advise- KPTG-IntCorr-000947 | Panel are on Hold - as advised KPTG-IntCorr-000967
Auscool-TRANSMIT-000067: Basement - IFC Drawings | 2026-07-21 | 1 | 1 | Zone 2 to 5 are Ok to update register and transmit. Zone 1 is on hold - KPTG-TRANSMIT-002881
Auspan-TRANSMIT-000538: Precast shop drawings for construction. Level 5. | 2026-07-23 | 20 | 20 | IFC - Waiting for Kim advise -KPTG-IntCorr-001086
Auspan-TRANSMIT-000545: Level 5 precast shop drawings for construction | 2026-07-24 | 28 | 28 | IFC - Waiting for Kim advise -KPTG-IntCorr-001095 - 28 Drawings
Auspan-TRANSMIT-000573: Precast shop drawings for construction. Level 4. | 2026-08-03 | 13 | 13 | IFC - Waiting for Kim advise -KPTG-IntCorr-001180 - 13 Drawings
Auspan-TRANSMIT-000592: Precast shop drawings for construction. Level 5 | 2026-08-10 | 47 | 47 | Waiting for Oliver advise-KPTG-IntCorr-001219
Auspan-TRANSMIT-000600 Update IFCed precast shop drawings. | 2026-08-12 | 18 | 18 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001249
Auspan-TRANSMIT-000605: Re: Architectural Documentation - Return & Precast Return External Elevations | 2026-08-13 | 7 | 7 | ifc - Witing for confirmation from Oliver -KPTG-IntCorr-001265
Auspan-TRANSMIT-000606: Re: Removal of Wet Joint - HB | 2026-08-13 | 20 | 20 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001266
Auspan-TRANSMIT-000607: Re: Removal of Wet Joint - HB | 2026-08-13 | 1 | 1 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001267
Auspan-TRANSMIT-000610: Re: Update IFCed precast shop drawings. | 2026-08-13 | 9 | 9 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001270
Auspan-TRANSMIT-000611: Re: GMAC - L4 Additional precast penetrations - Drawing QA error | 2026-08-13 | 3 | 3 | ifc - Witing for confirmation from Oliver KPTG-IntCorr-001272
Auscool-TRANSMIT-000077: updated document number | 2026-08-14 | 1 | 1 | Brent to advise -KPTG-IntCorr-001282
Auspan-TRANSMIT-000613: Precast shop drawings for construction. Levels 4, 5. | 2026-08-14 | 39 | 39 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001280
Auspan-TRANSMIT-000616: Re: Precast shop drawings for construction. Levels 4, 5 | 2026-08-17 | 9 | 9 | FC - Waiting for Oliver advise-KPTG-IntCorr-001287
Auspan-TRANSMIT-000617: Update IFCed precast shop drawing. There is no change to the panels | 2026-08-17 | 7 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001288 7 Drawings
Auspan-TRANSMIT-000618: Update IFCed precast shop drawings | 2026-08-17 | 4 | 4 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001289
Auspan-TRANSMIT-000620: Update IFCed precast shop drawings. | 2026-08-17 | 2 | 2 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001290
Auspan-TRANSMIT-000621: Update IFCed precast shop drawings. | 2026-08-17 | 3 | 3 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001291
Auspan-TRANSMIT-000623: Precast shop drawings for construction. Levels 3 and 4 zone 4, 5 | 2026-08-18 | 7 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001297
Auspan-TRANSMIT-000624: Precast shop drawings for construction. Levels 3, 5, 6. | 2026-08-18 | 21 | 21 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001292
Auspan-TRANSMIT-000628: Update IFC precast shop drawings. Level 5. | 2026-08-19 | 12 | 12 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001307
Auspan-TRANSMIT-000629: Update IFC precast shop drawings. Level 6. | 2026-08-19 | 6 | 6 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001309
Auspan-TRANSMIT-000630 Update IFCed precast shop drawings. Level 3 | 2026-08-20 | 1 | 1 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001330
Auspan-TRANSMIT-000631: Precast shop drawings for construction. Level 4 | 2026-08-20 | 7 | 7 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001329
Auspan-TRANSMIT-000632: Precast shop drawings for construction. Level 5, 6 | 2026-08-20 | 19 | 19 | IFC- Waiting for Oliver advise- KPTG-IntCorr-001328
Auspan-TRANSMIT-000635: Panel 3P5065 | 2026-08-20 | 1 | 1 | IFC- Waiting for Oliver advise KPTG-IntCorr-001331
Auspan-TRANSMIT-000637 Re: Precast SD Audit. Level 3 Zone 3. | 2026-08-21 | 7 | 7 | QC OK ifc - waiting for Oliver advise - KPTG-IntCorr-001338 -
Auspan-TRANSMIT-000639: Re: Precast SD Audit. Level 3 zone 4,5. | 2026-08-21 | 17 | 17 | QC OK ifc - waiting for Oliver advise - KPTG-IntCorr-001340
Auscool-TRANSMIT-000079 Greystar Kensington MSSB Schematics | 2026-08-21 | 1 | 1 | Waiting for Kapitol advise - KPTG-IntCorr-001337
Auspan-TRANSMIT-000640: Update IFCed precast shop drawings. | 2026-08-21 | 30 | 30 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001342
Auspan-TRANSMIT-000641: Re: 2P349 - NLB? Update IFCed precast shop drawings. | 2026-08-21 | 4 | 4 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001345
INDS-TRANSMIT-000066: Wet Fire - Ground Zone 1, 2 & 4 | 2026-08-24 | 3 | 1 | IFC- Waiting for Julianne and Brent advise-KPTG-IntCorr-001350 - 1 drawings ins on Hold ACC#1809 ¦ WF-000835
Auspan-TRANSMIT-000643: Precast shop drawings for construction. Level 3 | 2026-08-24 | 3 | 2 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001353 | KPTG-IntCorr-001356- IFC- 1 drawing only - Drawing superseded by Auspan-TRANSMIT-000648
Auspan-TRANSMIT-000644: Precast shop drawings for construction. Level 4 | 2026-08-24 | 7 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001359
Auspan-TRANSMIT-000645: Precast shop drawings for construction. Level 5. | 2026-08-24 | 4 | 4 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001360
Auspan-TRANSMIT-000646: Precast shop drawings for construction. Level 6. | 2026-08-24 | 45 | 45 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001351
Total |  | 469 | 466
472

## 26-08
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-08-26 | [5 empty] | Project: | 352-MAC - Greystar
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
Auspan-TRANSMIT-000650: Precast shop drawings for construction. Level 3. | 2 | 0 | 0 | FC- Waiting for Oliver advise-KPTG-IntCorr-001375 - No Action required. | Auspan-TRANSMIT-000655: Resubmit shop drawings for approval | 1 | 0 | Rejected - difference in status - KPTG-SADV-004498
Auspan-TRANSMIT-000651: Update IFCed precast shop drawings due to penos added. Level 4. | 7 | 0 | 7 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001377 | JCBa-TRANSMIT-000165 Updated Architectural Documentation - GA Plans, Door Schedule & Door Elevations -1715 | 48 | 0 | KPTG-TRANSMIT-003335
Auspan-TRANSMIT-000652: Precast shop drawings for construction. Level 5. | 21 | 0 | 21 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001378 | POTTSENG-TRANSMIT-000064 GMAC HYDRAULIC SERVICES - PENETRATION - LEVEL 01 - ZONE 3 LAYOUT -1683 | 1 | 0 | KPTG-TRANSMIT-003338
Auspan-TRANSMIT-000653: Precast shop drawings for construction. Level 6 | 2 | 0 | 2 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001379 | Auspan-TRANSMIT-000650: Precast shop drawings for construction. Level 3. | 2 | 0 | FC- Waiting for Oliver advise-KPTG-IntCorr-001375 - No Action required. - KPTG-IntCorr-001376
Auspan-TRANSMIT-000654: Update IFCed precast shop drawings. Level 4. | 6 | 0 | 6 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001381 | Rinco-TRANSMIT-000066 Structural drawings Issued for Construction -ACC#1656 | 17 | 0 | KPTG-TRANSMIT-003339
Auspan-TRANSMIT-000655: Resubmit shop drawings for approval | 6 | 0 | 0 | IFA - ACC#1819 ¦ WF-000840 | POTTSENG-TRANSMIT-000066 GMAC HYDRAULIC SERVICES - PENETRATION - LEVEL 02 - ZONE 4 LAYOUT -1699 | 1 | 0 | KPTG-TRANSMIT-003349
Auspan-TRANSMIT-000655: Resubmit shop drawings for approval | 1 | 0 | 0 | Rejected - difference in status - KPTG-SADV-004498 | POTTSENG-TRANSMIT-000065 GMAC HYDRAULIC SERVICES - PENETRATION - LEVELS 03-05 - ZONES 1-5 LAYOUTS -1687 | 15 | 0 | KPTG-TRANSMIT-003343
M.2-TRANSMIT-000088: Carprark Ramp Lighting Lux Reports | 1 | 0 | 1 | For Information - to be confirmed by Kapitol. KPTG-IntCorr-001380 | Rinco-TRANSMIT-000065 L2 to L7 Drawings Update for RFI -1575 | 82 | 0 | KPTG-TRANSMIT-003350
Rinco-TRANSMIT-000070: Structural drawings Issued for Construction | 6 | 0 | 0 | ACC#1821 ¦WF-000841 | M.2-TRANSMIT-000075 Electrical Services - B1, Ground and Level 6 lighting layouts -1735 | 15 | 0 | KPTG-TRANSMIT-003353
[5 empty] | IJF-TRANSMIT-000011 Joinery prototype drawings - Rev C3 -1803 | 7 | 0 | KPTG-TRANSMIT-003346
Total | 52 | 0 | 37 |  |  | 189 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000429: Update IFCed precast shop drawings. Level 1 zone 4, 5 | 2026-06-26 | 2 | 2 | IFC - QC OK - Kapitol PC Kim to confirm - KPTG-IntCorr-000778 - ON HOLD AS ADVISED BY KIM | ON HOLD AS ADVISED BY KIM
Auspan-TRANSMIT-000441 Precast shop drawings for construction. Level 6. | 2026-06-30 | 34 | 34 | IFC - Waiting for advise KPTG-IntCorr-000804 | Pending services coordination
Auspan-TRANSMIT-000496: Update IFCed shop drawings. Levels 5, 6. | 2026-07-13 | 6 | 6 | IFC - Waiting for Kim advise- KPTG-IntCorr-000947 | Panel are on Hold - as advised KPTG-IntCorr-000967
Auscool-TRANSMIT-000067: Basement - IFC Drawings | 2026-07-21 | 1 | 1 | Zone 2 to 5 are Ok to update register and transmit. Zone 1 is on hold - KPTG-TRANSMIT-002881
Auspan-TRANSMIT-000538: Precast shop drawings for construction. Level 5. | 2026-07-23 | 20 | 20 | IFC - Waiting for Kim advise -KPTG-IntCorr-001086
Auspan-TRANSMIT-000545: Level 5 precast shop drawings for construction | 2026-07-24 | 28 | 28 | IFC - Waiting for Kim advise -KPTG-IntCorr-001095 - 28 Drawings
Auspan-TRANSMIT-000573: Precast shop drawings for construction. Level 4. | 2026-08-03 | 13 | 13 | IFC - Waiting for Kim advise -KPTG-IntCorr-001180 - 13 Drawings
Auspan-TRANSMIT-000592: Precast shop drawings for construction. Level 5 | 2026-08-10 | 47 | 47 | Waiting for Oliver advise-KPTG-IntCorr-001219
Auspan-TRANSMIT-000600 Update IFCed precast shop drawings. | 2026-08-12 | 18 | 18 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001249
Auspan-TRANSMIT-000605: Re: Architectural Documentation - Return & Precast Return External Elevations | 2026-08-13 | 7 | 7 | ifc - Witing for confirmation from Oliver -KPTG-IntCorr-001265
Auspan-TRANSMIT-000606: Re: Removal of Wet Joint - HB | 2026-08-13 | 20 | 20 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001266
Auspan-TRANSMIT-000607: Re: Removal of Wet Joint - HB | 2026-08-13 | 1 | 1 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001267
Auspan-TRANSMIT-000610: Re: Update IFCed precast shop drawings. | 2026-08-13 | 9 | 9 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001270
Auspan-TRANSMIT-000611: Re: GMAC - L4 Additional precast penetrations - Drawing QA error | 2026-08-13 | 3 | 3 | ifc - Witing for confirmation from Oliver KPTG-IntCorr-001272
Auscool-TRANSMIT-000077: updated document number | 2026-08-14 | 1 | 1 | Brent to advise -KPTG-IntCorr-001282
Auspan-TRANSMIT-000613: Precast shop drawings for construction. Levels 4, 5. | 2026-08-14 | 39 | 39 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001280
Auspan-TRANSMIT-000616: Re: Precast shop drawings for construction. Levels 4, 5 | 2026-08-17 | 9 | 9 | FC - Waiting for Oliver advise-KPTG-IntCorr-001287
Auspan-TRANSMIT-000617: Update IFCed precast shop drawing. There is no change to the panels | 2026-08-17 | 7 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001288 7 Drawings
Auspan-TRANSMIT-000618: Update IFCed precast shop drawings | 2026-08-17 | 4 | 4 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001289
Auspan-TRANSMIT-000620: Update IFCed precast shop drawings. | 2026-08-17 | 2 | 2 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001290
Auspan-TRANSMIT-000621: Update IFCed precast shop drawings. | 2026-08-17 | 3 | 3 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001291
Auspan-TRANSMIT-000623: Precast shop drawings for construction. Levels 3 and 4 zone 4, 5 | 2026-08-18 | 7 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001297
Auspan-TRANSMIT-000624: Precast shop drawings for construction. Levels 3, 5, 6. | 2026-08-18 | 21 | 21 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001292
Auspan-TRANSMIT-000628: Update IFC precast shop drawings. Level 5. | 2026-08-19 | 12 | 12 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001307
Auspan-TRANSMIT-000629: Update IFC precast shop drawings. Level 6. | 2026-08-19 | 6 | 6 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001309
Auspan-TRANSMIT-000630 Update IFCed precast shop drawings. Level 3 | 2026-08-20 | 1 | 1 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001330
Auspan-TRANSMIT-000631: Precast shop drawings for construction. Level 4 | 2026-08-20 | 7 | 7 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001329
Auspan-TRANSMIT-000632: Precast shop drawings for construction. Level 5, 6 | 2026-08-20 | 19 | 19 | IFC- Waiting for Oliver advise- KPTG-IntCorr-001328
Auspan-TRANSMIT-000635: Panel 3P5065 | 2026-08-20 | 1 | 1 | IFC- Waiting for Oliver advise KPTG-IntCorr-001331
Auspan-TRANSMIT-000637 Re: Precast SD Audit. Level 3 Zone 3. | 2026-08-21 | 7 | 7 | QC OK ifc - waiting for Oliver advise - KPTG-IntCorr-001338 -
Auspan-TRANSMIT-000639: Re: Precast SD Audit. Level 3 zone 4,5. | 2026-08-21 | 17 | 17 | QC OK ifc - waiting for Oliver advise - KPTG-IntCorr-001340
Auscool-TRANSMIT-000079 Greystar Kensington MSSB Schematics | 2026-08-21 | 1 | 1 | Waiting for Kapitol advise - KPTG-IntCorr-001337
Auspan-TRANSMIT-000640: Update IFCed precast shop drawings. | 2026-08-21 | 30 | 30 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001342
Auspan-TRANSMIT-000641: Re: 2P349 - NLB? Update IFCed precast shop drawings. | 2026-08-21 | 4 | 4 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001345
INDS-TRANSMIT-000066: Wet Fire - Ground Zone 1, 2 & 4 | 2026-08-24 | 3 | 1 | IFC- Waiting for Julianne and Brent advise-KPTG-IntCorr-001350 - 1 drawings ins on Hold ACC#1809 ¦ WF-000835
Auspan-TRANSMIT-000643: Precast shop drawings for construction. Level 3 | 2026-08-24 | 3 | 2 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001353 | KPTG-IntCorr-001356- IFC- 1 drawing only - Drawing superseded by Auspan-TRANSMIT-000648
Auspan-TRANSMIT-000644: Precast shop drawings for construction. Level 4 | 2026-08-24 | 7 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001359
Auspan-TRANSMIT-000645: Precast shop drawings for construction. Level 5. | 2026-08-24 | 4 | 4 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001360
Auspan-TRANSMIT-000646: Precast shop drawings for construction. Level 6. | 2026-08-24 | 45 | 45 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001351
Auspan-TRANSMIT-000649 Re: Zone 1 RFi 91. Update IFCed shop drawings. Penos for overflow added | 2026-08-25 | 4 | 4 | IFC waiting for Kapitol advise - KPTG-IntCorr-001372
Auspan-TRANSMIT-000648: Update IFCed precast shop drawings for construction due to penos added. | 2026-08-25 | 2 | 2 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001366
Total |  | 475 | 472
509

## 27-08
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-08-27 | [5 empty] | Project: | 352-MAC - Greystar
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
Auspan-TRANSMIT-000656: Precast panel 5P1034 for construction | 1 | 0 | 1 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001387 | Auspan-TRANSMIT-000651: Update IFCed precast shop drawings due to penos added. Level 4. | 7 | 0 | 6 are registered and Transmit - KPTG-TRANSMIT-003357 Please IFC all except 4P5011 -KPTG-IntCorr-001384
Auspan-TRANSMIT-000657: Re: Resubmit shop drawings for approval. | 1 | 0 | 0 | ACC#1824 ¦ WF-000842 | KPTG-TRANSMIT-003235 Balustrade & Screen Shop Drawing Details IFA -1751 | 7 | 0 | KPTG-TRANSMIT-003368
Auspan-TRANSMIT-000658: Re: Corbel - Zone 4 | 2 | 0 | 2 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001388 | JCBa-TRANSMIT-000164 Updated Architectural Documentation - Partition Plans & Partition Detail Sections -1697 | 44 | 0 | KPTG-TRANSMIT-003365
INDS-TRANSMIT-000068: L2 to L7 Zone 2 - Typical Floor Penetration Layout | 1 | 0 | 0 | ACC#1827 ¦ WF-000844 | KPTG-IntCorr-001394: IJF approved samples - register documents | 14 | 0 | KPTG-TRANSMIT-003361
Auspan-TRANSMIT-000659: Re: Elevation 05 | 3 | 0 | 3 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001393 | ArcadiaL-TRANSMIT-000004: Landscape Architectural -Eastern 2-way Road IFC drawings | 3 | 0 | Rejected due to incorrect revison - KPTG-DA-001833
Auspan-TRANSMIT-000660: Re: Corbel - Zone 4 | 3 | 0 | 3 | IFC 0 waiting for Oliver advise - KPTG-IntCorr-001392 | JCBa-TRANSMIT-000168: Updated Architectural Documentation - Joinery Details & Joinery Schedules | 5 | 0 | Rejected due to incorrect revison - DRAFT-012153
KPTG-IntCorr-001394: IJF approved samples - register documents | 14 | 0 | 0 | KPTG-TRANSMIT-003361 - Update register and transmit to Kapitol PC - Faye.
ArcadiaL-TRANSMIT-000004: Landscape Architectural -Eastern 2-way Road IFC drawings | 3 | 0 | 0 | Rejected due to incorrect revison - KPTG-DA-001833
JCBa-TRANSMIT-000168: Updated Architectural Documentation - Joinery Details & Joinery Schedules | 5 | 0 | 0 | Rejected due to incorrect revisIon - DRAFT-012153
Total | 33 | 0 | 9 |  |  | 80 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000429: Update IFCed precast shop drawings. Level 1 zone 4, 5 | 2026-06-26 | 2 | 2 | IFC - QC OK - Kapitol PC Kim to confirm - KPTG-IntCorr-000778 - ON HOLD AS ADVISED BY KIM | ON HOLD AS ADVISED BY KIM
Auspan-TRANSMIT-000441 Precast shop drawings for construction. Level 6. | 2026-06-30 | 34 | 34 | IFC - Waiting for advise KPTG-IntCorr-000804 | Pending services coordination
Auspan-TRANSMIT-000496: Update IFCed shop drawings. Levels 5, 6. | 2026-07-13 | 6 | 6 | IFC - Waiting for Kim advise- KPTG-IntCorr-000947 | Panel are on Hold - as advised KPTG-IntCorr-000967
Auscool-TRANSMIT-000067: Basement - IFC Drawings | 2026-07-21 | 1 | 1 | Zone 2 to 5 are Ok to update register and transmit. Zone 1 is on hold - KPTG-TRANSMIT-002881
Auspan-TRANSMIT-000538: Precast shop drawings for construction. Level 5. | 2026-07-23 | 20 | 20 | IFC - Waiting for Kim advise -KPTG-IntCorr-001086
Auspan-TRANSMIT-000545: Level 5 precast shop drawings for construction | 2026-07-24 | 28 | 28 | IFC - Waiting for Kim advise -KPTG-IntCorr-001095 - 28 Drawings
Auspan-TRANSMIT-000573: Precast shop drawings for construction. Level 4. | 2026-08-03 | 13 | 13 | IFC - Waiting for Kim advise -KPTG-IntCorr-001180 - 13 Drawings
Auspan-TRANSMIT-000592: Precast shop drawings for construction. Level 5 | 2026-08-10 | 47 | 47 | Waiting for Oliver advise-KPTG-IntCorr-001219
Auspan-TRANSMIT-000600 Update IFCed precast shop drawings. | 2026-08-12 | 18 | 18 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001249
Auspan-TRANSMIT-000605: Re: Architectural Documentation - Return & Precast Return External Elevations | 2026-08-13 | 7 | 7 | ifc - Witing for confirmation from Oliver -KPTG-IntCorr-001265
Auspan-TRANSMIT-000606: Re: Removal of Wet Joint - HB | 2026-08-13 | 20 | 20 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001266
Auspan-TRANSMIT-000607: Re: Removal of Wet Joint - HB | 2026-08-13 | 1 | 1 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001267
Auspan-TRANSMIT-000610: Re: Update IFCed precast shop drawings. | 2026-08-13 | 9 | 9 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001270
Auspan-TRANSMIT-000611: Re: GMAC - L4 Additional precast penetrations - Drawing QA error | 2026-08-13 | 3 | 3 | ifc - Witing for confirmation from Oliver KPTG-IntCorr-001272
Auspan-TRANSMIT-000613: Precast shop drawings for construction. Levels 4, 5. | 2026-08-14 | 39 | 39 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001280
Auspan-TRANSMIT-000616: Re: Precast shop drawings for construction. Levels 4, 5 | 2026-08-17 | 9 | 9 | FC - Waiting for Oliver advise-KPTG-IntCorr-001287
Auspan-TRANSMIT-000617: Update IFCed precast shop drawing. There is no change to the panels | 2026-08-17 | 7 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001288 7 Drawings
Auspan-TRANSMIT-000618: Update IFCed precast shop drawings | 2026-08-17 | 4 | 4 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001289
Auspan-TRANSMIT-000620: Update IFCed precast shop drawings. | 2026-08-17 | 2 | 2 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001290
Auspan-TRANSMIT-000621: Update IFCed precast shop drawings. | 2026-08-17 | 3 | 3 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001291
Auspan-TRANSMIT-000623: Precast shop drawings for construction. Levels 3 and 4 zone 4, 5 | 2026-08-18 | 7 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001297
Auspan-TRANSMIT-000624: Precast shop drawings for construction. Levels 3, 5, 6. | 2026-08-18 | 21 | 21 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001292
Auspan-TRANSMIT-000628: Update IFC precast shop drawings. Level 5. | 2026-08-19 | 12 | 12 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001307
Auspan-TRANSMIT-000629: Update IFC precast shop drawings. Level 6. | 2026-08-19 | 6 | 6 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001309
Auspan-TRANSMIT-000630 Update IFCed precast shop drawings. Level 3 | 2026-08-20 | 1 | 1 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001330
Auspan-TRANSMIT-000631: Precast shop drawings for construction. Level 4 | 2026-08-20 | 7 | 7 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001329
Auspan-TRANSMIT-000632: Precast shop drawings for construction. Level 5, 6 | 2026-08-20 | 19 | 19 | IFC- Waiting for Oliver advise- KPTG-IntCorr-001328
Auspan-TRANSMIT-000635: Panel 3P5065 | 2026-08-20 | 1 | 1 | IFC- Waiting for Oliver advise KPTG-IntCorr-001331
Auspan-TRANSMIT-000637 Re: Precast SD Audit. Level 3 Zone 3. | 2026-08-21 | 7 | 7 | QC OK ifc - waiting for Oliver advise - KPTG-IntCorr-001338 -
Auspan-TRANSMIT-000639: Re: Precast SD Audit. Level 3 zone 4,5. | 2026-08-21 | 17 | 17 | QC OK ifc - waiting for Oliver advise - KPTG-IntCorr-001340
Auscool-TRANSMIT-000079 Greystar Kensington MSSB Schematics | 2026-08-21 | 1 | 1 | Waiting for Kapitol advise - KPTG-IntCorr-001337
Auspan-TRANSMIT-000640: Update IFCed precast shop drawings. | 2026-08-21 | 30 | 30 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001342
Auspan-TRANSMIT-000641: Re: 2P349 - NLB? Update IFCed precast shop drawings. | 2026-08-21 | 4 | 4 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001345
INDS-TRANSMIT-000066: Wet Fire - Ground Zone 1, 2 & 4 | 2026-08-24 | 3 | 1 | IFC- Waiting for Julianne and Brent advise-KPTG-IntCorr-001350 - 1 drawings ins on Hold ACC#1809 ¦ WF-000835
Auspan-TRANSMIT-000643: Precast shop drawings for construction. Level 3 | 2026-08-24 | 3 | 2 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001353 | KPTG-IntCorr-001356- IFC- 1 drawing only - Drawing superseded by Auspan-TRANSMIT-000648
Auspan-TRANSMIT-000644: Precast shop drawings for construction. Level 4 | 2026-08-24 | 7 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001359
Auspan-TRANSMIT-000645: Precast shop drawings for construction. Level 5. | 2026-08-24 | 4 | 4 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001360
Auspan-TRANSMIT-000646: Precast shop drawings for construction. Level 6. | 2026-08-24 | 45 | 45 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001351
Auspan-TRANSMIT-000649 Re: Zone 1 RFi 91. Update IFCed shop drawings. Penos for overflow added | 2026-08-25 | 4 | 4 | IFC waiting for Kapitol advise - KPTG-IntCorr-001372
Auspan-TRANSMIT-000648: Update IFCed precast shop drawings for construction due to penos added. | 2026-08-25 | 2 | 2 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001366
Auspan-TRANSMIT-000652: Precast shop drawings for construction. Level 5. | 2026-08-26 | 21 | 21 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001378
Auspan-TRANSMIT-000653: Precast shop drawings for construction. Level 6 | 2026-08-26 | 2 | 2 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001379
Auspan-TRANSMIT-000654: Update IFCed precast shop drawings. Level 4. | 2026-08-26 | 6 | 6 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001381
M.2-TRANSMIT-000088: Carprark Ramp Lighting Lux Reports | 2026-08-26 | 1 | 1 | For Information - to be confirmed by Kapitol. KPTG-IntCorr-001380
Auspan-TRANSMIT-000651: Update IFCed precast shop drawings due to penos added. Level 4. | 2026-08-26 | 7 | 0 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001377 | Please IFC all except 4P5011 -KPTG-IntCorr-001384
Auscool-TRANSMIT-000077: updated document number | 2026-08-14 | 1 | 0 | Brent to advise -KPTG-IntCorr-001282 WF-000843 | KPTG-IntCorr-001391 - send to Stantec for review.
Total |  | 512 | 501
510

## 28-08
KPG ¦ RDS ¦ DOCUMENT CONTROLLER DAILY REPORT
Date: | 2026-08-28 | [5 empty] | Project: | 352-MAC - Greystar
Incoming Transmittals |  |  |  |  | Close out |  |  | Remarks
Transmittals | No. of Drawings | No. of Technical data | Pending Number of Documents | Remarks | Transmittals | No. of Documents | Pending Number of Documents
IJF-TRANSMIT-000013: Joinery - Kitchen Drawings - Delivery 2 | 116 | 0 | 0 | Rejected - difference in status and titles- DRAFT-012159 | Auspan-TRANSMIT-000662: Precast dowel layout for level 3 up. | 12 | 0 | Rejected due to drawing QA issues. - DRAFT-012157
Auspan-TRANSMIT-000662: Precast dowel layout for level 3 up. | 12 | 0 | 0 | Rejected due to drawing QA issues. - DRAFT-012157 | IJF-TRANSMIT-000013: Joinery - Kitchen Drawings - Delivery 2 | 116 | 0 | Rejected - difference in status and titles- DRAFT-012159
Rinco-TRANSMIT-000071: Structural drawings Issued for Construction | 11 | 0 | 0 | ACC#1829 ¦ WF-000846 | POTTSENG-TRANSMIT-000071 GMAC HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONE 5 LAYOUT | 1 | 0 | Review void as requested -KPTG-SADV-004555
IJF-TRANSMIT-000014: Joinery Drawings - Kitchens - Delivery 2 | 116 | 0 | 0 | ACC#1833 ¦ WF-000848 | POTTSENG-TRANSMIT-000073: GMAC: HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONES 1-5 LAYOUTS | 4 | 0 | Rejected One drawing PDF is missing- KPTG-SADV-004555
POTTSENG-TRANSMIT-000073: GMAC: HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONES 1-5 LAYOUTS | 4 | 0 | 0 | Rejected One drawing PDF is missing- KPTG-SADV-004555 | Auspan-TRANSMIT-000592: Precast shop drawings for construction. Level 5 | 47 | 0 | 29 ARE OK TO IFC- KPTG-TRANSMIT-003370 4 Drawings are updated and superseeded 14 are Rejected advised by Kapitol PC: KPTG-IntCorr-001401
POTTSENG-TRANSMIT-000074: GMAC: HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONES 1--5 LAYOUTS | 5 | 0 | 0 | ACC#1831 ¦WF-000847 | Auspan-TRANSMIT-000545: Level 5 precast shop drawings for construction | 28 | 0 | 22 ARE OK TO IFC- KPTG-TRANSMIT-003372 6 are Rejected advised by Kapitol PC:KPTG-IntCorr-001400
IJF-TRANSMIT-000015: JO202 - Prototype Drawomh | 1 | 0 | 0 | ACC#1839 ¦ WF-000850
M.2-TRANSMIT-000089: Electrical Services Typical apartment show drawings | 69 | 0 | 0 | ACC#1837 ¦WF-000849
Total | 334 | 0 | 0 |  |  | 208 | 0
Pending Transmittals
Transmittals | Date: | No. of Documents | Pending Number of Documents | Remarks
Auspan-TRANSMIT-000429: Update IFCed precast shop drawings. Level 1 zone 4, 5 | 2026-06-26 | 2 | 2 | IFC - QC OK - Kapitol PC Kim to confirm - KPTG-IntCorr-000778 - ON HOLD AS ADVISED BY KIM | ON HOLD AS ADVISED BY KIM
Auspan-TRANSMIT-000441 Precast shop drawings for construction. Level 6. | 2026-06-30 | 34 | 34 | IFC - Waiting for advise KPTG-IntCorr-000804 | Pending services coordination
Auspan-TRANSMIT-000496: Update IFCed shop drawings. Levels 5, 6. | 2026-07-13 | 6 | 6 | IFC - Waiting for Kim advise- KPTG-IntCorr-000947 | Panel are on Hold - as advised KPTG-IntCorr-000967
Auscool-TRANSMIT-000067: Basement - IFC Drawings | 2026-07-21 | 1 | 1 | Zone 2 to 5 are Ok to update register and transmit. Zone 1 is on hold - KPTG-TRANSMIT-002881
Auspan-TRANSMIT-000538: Precast shop drawings for construction. Level 5. | 2026-07-23 | 20 | 20 | IFC - Waiting for Kim advise -KPTG-IntCorr-001086
Auspan-TRANSMIT-000573: Precast shop drawings for construction. Level 4. | 2026-08-03 | 13 | 13 | IFC - Waiting for Kim advise -KPTG-IntCorr-001180 - 13 Drawings
Auspan-TRANSMIT-000605: Re: Architectural Documentation - Return & Precast Return External Elevations | 2026-08-13 | 7 | 7 | ifc - Witing for confirmation from Oliver -KPTG-IntCorr-001265
Auspan-TRANSMIT-000606: Re: Removal of Wet Joint - HB | 2026-08-13 | 20 | 20 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001266
Auspan-TRANSMIT-000607: Re: Removal of Wet Joint - HB | 2026-08-13 | 1 | 1 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001267
Auspan-TRANSMIT-000610: Re: Update IFCed precast shop drawings. | 2026-08-13 | 9 | 9 | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001270
Auspan-TRANSMIT-000611: Re: GMAC - L4 Additional precast penetrations - Drawing QA error | 2026-08-13 | 3 | 3 | ifc - Witing for confirmation from Oliver KPTG-IntCorr-001272
Auspan-TRANSMIT-000613: Precast shop drawings for construction. Levels 4, 5. | 2026-08-14 | 39 | 39 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001280
Auspan-TRANSMIT-000616: Re: Precast shop drawings for construction. Levels 4, 5 | 2026-08-17 | 9 | 9 | FC - Waiting for Oliver advise-KPTG-IntCorr-001287
Auspan-TRANSMIT-000617: Update IFCed precast shop drawing. There is no change to the panels | 2026-08-17 | 7 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001288 7 Drawings
Auspan-TRANSMIT-000618: Update IFCed precast shop drawings | 2026-08-17 | 4 | 4 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001289
Auspan-TRANSMIT-000620: Update IFCed precast shop drawings. | 2026-08-17 | 2 | 2 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001290
Auspan-TRANSMIT-000621: Update IFCed precast shop drawings. | 2026-08-17 | 3 | 3 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001291
Auspan-TRANSMIT-000623: Precast shop drawings for construction. Levels 3 and 4 zone 4, 5 | 2026-08-18 | 7 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001297
Auspan-TRANSMIT-000624: Precast shop drawings for construction. Levels 3, 5, 6. | 2026-08-18 | 21 | 21 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001292
Auspan-TRANSMIT-000628: Update IFC precast shop drawings. Level 5. | 2026-08-19 | 12 | 12 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001307
Auspan-TRANSMIT-000629: Update IFC precast shop drawings. Level 6. | 2026-08-19 | 6 | 6 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001309
Auspan-TRANSMIT-000630 Update IFCed precast shop drawings. Level 3 | 2026-08-20 | 1 | 1 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001330
Auspan-TRANSMIT-000631: Precast shop drawings for construction. Level 4 | 2026-08-20 | 7 | 7 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001329
Auspan-TRANSMIT-000632: Precast shop drawings for construction. Level 5, 6 | 2026-08-20 | 19 | 19 | IFC- Waiting for Oliver advise- KPTG-IntCorr-001328
Auspan-TRANSMIT-000635: Panel 3P5065 | 2026-08-20 | 1 | 1 | IFC- Waiting for Oliver advise KPTG-IntCorr-001331
Auspan-TRANSMIT-000637 Re: Precast SD Audit. Level 3 Zone 3. | 2026-08-21 | 7 | 7 | QC OK ifc - waiting for Oliver advise - KPTG-IntCorr-001338 -
Auspan-TRANSMIT-000639: Re: Precast SD Audit. Level 3 zone 4,5. | 2026-08-21 | 17 | 17 | QC OK ifc - waiting for Oliver advise - KPTG-IntCorr-001340
Auscool-TRANSMIT-000079 Greystar Kensington MSSB Schematics | 2026-08-21 | 1 | 1 | Waiting for Kapitol advise - KPTG-IntCorr-001337
Auspan-TRANSMIT-000640: Update IFCed precast shop drawings. | 2026-08-21 | 30 | 30 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001342
Auspan-TRANSMIT-000641: Re: 2P349 - NLB? Update IFCed precast shop drawings. | 2026-08-21 | 4 | 4 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001345
INDS-TRANSMIT-000066: Wet Fire - Ground Zone 1, 2 & 4 | 2026-08-24 | 3 | 1 | IFC- Waiting for Julianne and Brent advise-KPTG-IntCorr-001350 - 1 drawings ins on Hold ACC#1809 ¦ WF-000835
Auspan-TRANSMIT-000643: Precast shop drawings for construction. Level 3 | 2026-08-24 | 3 | 2 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001353 | KPTG-IntCorr-001356- IFC- 1 drawing only - Drawing superseded by Auspan-TRANSMIT-000648
Auspan-TRANSMIT-000644: Precast shop drawings for construction. Level 4 | 2026-08-24 | 7 | 7 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001359
Auspan-TRANSMIT-000645: Precast shop drawings for construction. Level 5. | 2026-08-24 | 4 | 4 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001360
Auspan-TRANSMIT-000646: Precast shop drawings for construction. Level 6. | 2026-08-24 | 45 | 45 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001351
Auspan-TRANSMIT-000649 Re: Zone 1 RFi 91. Update IFCed shop drawings. Penos for overflow added | 2026-08-25 | 4 | 4 | IFC waiting for Kapitol advise - KPTG-IntCorr-001372
Auspan-TRANSMIT-000648: Update IFCed precast shop drawings for construction due to penos added. | 2026-08-25 | 2 | 2 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001366
Auspan-TRANSMIT-000652: Precast shop drawings for construction. Level 5. | 2026-08-26 | 21 | 21 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001378
Auspan-TRANSMIT-000653: Precast shop drawings for construction. Level 6 | 2026-08-26 | 2 | 2 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001379
Auspan-TRANSMIT-000654: Update IFCed precast shop drawings. Level 4. | 2026-08-26 | 6 | 6 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001381
M.2-TRANSMIT-000088: Carprark Ramp Lighting Lux Reports | 2026-08-26 | 1 | 1 | For Information - to be confirmed by Kapitol. KPTG-IntCorr-001380
Auspan-TRANSMIT-000656: Precast panel 5P1034 for construction | 2026-08-27 | 1 | 1 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001387
Auspan-TRANSMIT-000658: Re: Corbel - Zone 4 | 2026-08-27 | 2 | 2 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001388
Auspan-TRANSMIT-000659: Re: Elevation 05 | 2026-08-27 | 3 | 3 | IFC- Waiting for Oliver advise-KPTG-IntCorr-001393
Auspan-TRANSMIT-000600 Update IFCed precast shop drawings. | 2026-08-12 | 18 | 18 | IFC - Waiting for Oliver advise-KPTG-IntCorr-001249 | KPTG-IntCorr-001402 - Please see attached and proceeed | NOT DONE
Auspan-TRANSMIT-000660: Re: Corbel - Zone 4 | 2026-08-27 | 3 | 3 | IFC 0 waiting for Oliver advise - KPTG-IntCorr-001392 | Please IFC L3 Only - KPTG-IntCorr-001398 | NOT DONE
Auspan-TRANSMIT-000592: Precast shop drawings for construction. Level 5 | 2026-08-10 | 47 | 0 | Waiting for Oliver advise-KPTG-IntCorr-001219 | KPTG-IntCorr-001401 -Please IFC drawings without comments
Auspan-TRANSMIT-000545: Level 5 precast shop drawings for construction | 2026-07-24 | 28 | 0 | IFC - Waiting for Kim advise -KPTG-IntCorr-001095 - 28 Drawings | KPTG-IntCorr-001400 -Please ifc drawings without comments on the attached
Total |  | 513 | 435
435