## query (1)
Project | Receipt Date (RDS) | Transmittals (RDS) | Title | Issuer (RDS) | Description (RDS) | Drawings (RDS) | Technical data (RDS) | Pending (RDS) | Pending Reference (RDS) | RDS QA Check | WF Transmit Date (RDS) | ACX workflow (RDS) | ACC/ BIM360 workflow (RDS) | Planned Completion Date (RDS) | Days overdue (RDS) | RDS Remarks | WF Completion Date (RDS) | TRN Close-out Date (RDS) | TRN Close-out Ref. (RDS) | TRN Close-out Status (RDS) | Total Close-out Documents (RDS) | Published to SHEETS (RDS) | Item Type | Path
NXM3S3 | 2025-12-01 | Civilex-TRANSMIT-000163 |  | Trade Partner | Stage 3 - Sample Submission SlimDeck 22KVA Switch Room Building / Updated document Number | 0 | 1 | 0 |  | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. | [5 empty] | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-01 | Stowe-A-TRANSMIT-000388 | NA | Trade Partner | Stowe - Tech 1Data Submission - Exit and Emergency Lighting | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-24 | BLUESF-TRANSMIT-000011 | N/A | Trade Partner | M2-STR-BSF-SDRG-1101-P6 PRECAST DRAWINGS IFA | 15 | 0 | 0 | NA | REJECTED |  | N/A | N/A |  |  | Wrong uploading and Title guide- KPTG-TRANSMIT-000439 |  | 2025-12-29 | KPTG-TRANSMIT-000439 | Closed | 15 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-09 | JCBa-TRANSMIT-000130 | NA | Consultant | Partition Plans IFC: Second, Sixth, Seventh Floor and Roof Level | 20 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 1175 | 2026-06-11 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-002457 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-09 | RDSBIM-TRANSMIT-000022 | NA | Trade Partner | MEL11C45 ¦ PARTITION WALL LAYOUT L02 COLO5B | 3 | 0 | 0 | NA | APPROVED | 2026-06-09 | WF-000305 | NA | 2026-06-11 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-000851 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-09 | JCBa-TRANSMIT-000131 | NA | Consultant | Communal Wet Area Plans IFC | 6 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 1177 | 2026-06-11 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-002358 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-09 | D&E-TRANSMIT-000802 | NA | Trade Partner | Fwd: NXM3S4 - Level 1 - CHW Pipe Layout Zones 8 to 10 - Issued For Construction | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For Distribution |  | 2026-06-09 | KPTG-TRANSMIT-018335 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-09 | Auspan-TRANSMIT-000363 | NA | Trade Partner | Precast shop drawings for approval. Level 4 | 42 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 1179 | 2026-06-16 |  | 1 Drawing Already terminated | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-002978 | Closed | 42 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-09 | ENF-TRANSMIT-000017 | NA | Consultant | Structural Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 230 | 2026-06-15 |  | Review Voided - Latest Drawings received from ENF |  | 2026-06-10 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-09 | ENF-TRANSMIT-000019 | NA | Consultant | Structural drawing | 3 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 229 | 2026-06-15 |  | Actual Received date 6/1/2026 |  |  |  | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-09 | Stowe-A-TRANSMIT-000604 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - COMMS LAYOUT - EXTERNAL | 1 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 4268 | 2026-06-18 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-09 | Auspan-TRANSMIT-000362 | NA | Trade Partner | Resubmit precast shop drawings for approval | 4 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 1181 | 2026-06-16 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-002302 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-09 | INTRFRM-TRANSMIT-000073 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 12) | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-000191 | NA | 2026-06-17 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-000818 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-24 | BLUESF-TRANSMIT-000012 | N/A | Trade Partner | M2-STR-BSF-SDRG-1101- GA DRAWINGS IFA | 21 | 0 | 0 | N/A | REJECTED |  | N/A | N/A |  |  | Wrong uploading and title guide- KPTG-TRANSMIT-000440 |  | 2025-12-29 | KPTG-TRANSMIT-000440 | Closed | 21 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-09 | KPTG-TRANSMIT-018334 | NA | Trade Partner | M3 S2 - PSUB OMM | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-005958 | NA | 2026-06-22 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-019662 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-09 | KPTG-TRANSMIT-018337 | NA | Trade Partner | M3 S2 - Cooling Tower OMM | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-005959 | NA | 2026-06-22 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-018753 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-09 | SRA-PMQ-TRANSMIT-000006 | NA | Trade Partner | DataStruct Installation Instructions | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-000192 | NA | 2026-06-17 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-000849 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-09 | Auspan-TRANSMIT-000360 | NA | Trade Partner | Precast shop drawings for construction | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Precast drawings- No review, Updated register and distributed (KPTG-TRANSMIT-002176) |  | 2026-06-09 | KPTG-TRANSMIT-002176 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-09 | SRA-PMQ-TRANSMIT-000007 | NA | Trade Partner | Re: Ceiling Detail Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 269 | 2026-06-15 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-000906 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-09 | D&E-TRANSMIT-000804 | NA | Trade Partner | NXM3S4 - Level 1 - Mechanical Duct Layout - Zone 8 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC DRAWING |  | 2026-06-09 | KPTG-TRANSMIT-018370 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | Jangho-TRANSMIT-000146 | NA | Trade Partner | Extrusion color Duralloy Surfmist-Matt Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-000671 | NA | 2026-06-25 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002932 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | Jangho-TRANSMIT-000147 | NA | Trade Partner | Extrusion color Duratec Zeus Dune-Matt Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-000672 | NA | 2026-06-25 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002929 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-09 | KPTG-IntCorr-000472 | NA | Trade Partner | SMEPS-TRANSMIT-000225 - SME Samples for review | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF - 000460 | NA | 2026-06-15 |  | NA | 2026-06-15 | 2026-06-15 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | Jangho-TRANSMIT-000148 | NA | Trade Partner | Extrusion color Duratec Eternity Copper Metallic Kinetic- Matt Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-000673 | NA | 2026-06-25 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002927 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-10 | TTW-TRANSMIT-000003 | NA | Consultant | F3P1 Performance Based Design Brief Rev 2 | 0 | 1 | 0 |  | APPROVED | [7 empty] | 2025-12-10 |  | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-09 | KPTG-IntCorr-000473 | NA | Trade Partner | Substitution Request - TYPE J CABLE | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF - 000461 | NA | 2026-06-15 |  | NA | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-001017 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | Jangho-TRANSMIT-000149 | NA | Trade Partner | Extrusion color Electro Pale Bronze Kinetic-Flat Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-000674 | NA | 2026-06-25 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002925 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | Jangho-TRANSMIT-000150 | NA | Trade Partner | Extrusion color Duratec Elements Weathered Steel-Flat Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-000675 | NA | 2026-06-25 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002923 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | Jangho-TRANSMIT-000151 | NA | Trade Partner | Mortar Sample Submission Option 1 | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-000676 | NA | 2026-06-25 |  |  | 2026-06-25 | 2026-06-09 | KPTG-TRANSMIT-002193 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | Jangho-TRANSMIT-000152 | NA | Trade Partner | Mortar Sample Submission Option 2 | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-000677 | NA | 2026-06-25 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-002968 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | Jangho-TRANSMIT-000153 | NA | Trade Partner | Mortar Sample Submission Option 3 | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-000678 | NA | 2026-06-25 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-002971 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-06-09 | Nilsen3-TRANSMIT-000180 | NA | Trade Partner | M3-Stage 3 Control Cable wiring schedule | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-005961 | NA | 2026-06-12 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-019054 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-09 | PenskePS-TRANSMIT-000018 | NA | Trade Partner | MEL05-COLO4 - Updated FAT Reports | 0 | 8 | 0 | NA | APPROVED | 2026-06-09 | WF - 000462 | NA | 2026-06-15 |  | NA | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-001018 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-09 | D&E-TRANSMIT-000009 | NA | Trade Partner | Penetration drawings - Ground & Level 01 | 8 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 176 | 2026-06-17 |  |  | 2026-06-30 | 2026-07-01 | KPTG-TRANSMIT-000396 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-09 | 4DW-TRANSMIT-000042 | NA | Consultant | Structural Documentation: Block 1 - Precast walls issued with Construction updates. | 4 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 178 | 2026-06-17 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-05 | NXT-TRANSMIT-001162 / ABB-TRANSMIT-000019 | NA | Trade Partner | Secondary drawings for M3-22-HVSB-A, B, D, R for approval | 1 | 0 | 0 | NA | APPROVED | 2026-01-05 | WF-003690 |  | 2026-01-10 |  |  |  | 2026-01-09 | KPTG-TRANSMIT-011315 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-09 | KALLIBRE-TRANSMIT-000013 | NA | Trade Partner | Vinyl Skirting Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-000309 | NA | 2026-06-15 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-000903 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-09 | Highbu-TRANSMIT-000150 | NA | Trade Partner | Updated drawing | 1 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 303 | 2026-06-10 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-002964 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-09 | Stowe-A-TRANSMIT-000605 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - Data Hall Containment - ABS-01 | 35 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 4272 | 2026-06-12 |  | Terminated as directed Jaison for submitting updated documents. | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-018844 | Closed | 35 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-09 | HGP-TRANSMIT-000058 | NA | Trade Partner | Re: L1 INTERNAL DRAWINGS | 30 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 313 | 2026-06-16 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-09 | ENF-TRANSMIT-000020 | NA | Consultant | Structural drawings | 12 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 237 | 2026-06-16 |  | Transmittal ENF-TRANSMIT-000020 has been closed and superseded by ENF-TRANSMIT-000024 Review 237 Voided and Re initiated with 247. |  | 2026-06-10 | KPTG-DA-000340 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-09 | ENF-TRANSMIT-000021 | NA | Consultant | Structural drawings | 1 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 239 | 2026-06-16 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-09 | Auspan-TRANSMIT-000364 | NA | Trade Partner | Precast shop drawings for construction. Level 4. | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected. Drawing must be submitted for Approval. DRAFT-008159 |  | 2026-06-09 | DRAFT-008159 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-09 | Stowe-A-TRANSMIT-000606 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - TYPICAL MAIN DISTRIBUTION BOARD SCHEMATICS | 1 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 4270 | 2026-06-22 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-09 | COMAQU-TRANSMIT-000030 | NA | Trade Partner | As Built Drawings | 22 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As Bulit Drawing, transmitted to trade partners:KPTG-TRANSMIT-002963 |  | 2026-06-09 | KPTG-TRANSMIT-002963 | Closed | 22 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-05 | CRSol-TRANSMIT-000069 | NA | Trade Partner | Ceiling Drawings Issued for Approval - C1 - updated file name | 10 | 0 | 0 | NA | APPROVED | 2026-01-05 | NA | 1704 | 2026-01-14 |  | As per requested by Steven - WF- terminated |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-09 | Auspan-TRANSMIT-000073 | NA | Trade Partner | Shop drawing 7P02 issued for construction | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001037 - As per instruction from Ashlin we only update register and distribute everyone | 2026-06-09 | 2026-06-09 | KPTG-IntCorr-001037 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-09 | CRSol-TRANSMIT-000089 | NA | Trade Partner | M3S2 - DHB6 - SMW, As-Built Drawings | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Issues with revision number and revision history. |  | 2026-06-09 | KPTG-SADV-005793 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-09 | D&E-TRANSMIT-000803 | NA | Trade Partner | NXM3S2 - Chilled Water & SFN Water Schematic - Ground Floor - Mech Corridor & Data Hall B4 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 4274 | 2026-06-16 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-019089 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-09 | 4DW-TRANSMIT-000043 | NA | Consultant | Structural Documentation: General coordination update issue. | 48 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 184 | 2026-06-17 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-000424 | Closed | 48 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-09 | ACCCA-TRANSMIT-000004 | NA | Trade Partner | Electrical Pit Approval | 16 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 183 | 2026-06-17 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-000524 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-09 | PTA-TRANSMIT-000005 | NA | Consultant | Revised North elevation precast panel joint - For Coordination | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update register only |  | 2026-06-09 | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-09 | RDSBIM-TRANSMIT-000009 | NA | Trade Partner | GROUND LEVEL ¦CPP-BLOCK 1¦ IFR¦ FOR SUBMISSION | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Document Number mismatching |  | 2026-06-09 | KPTG-SADV-000210 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-09 | KPTG-TRANSMIT-018384 | NA | Trade Partner | Proline Detail M | 1 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 3473 | 2026-06-24 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-019339 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-09 | ARCST-TRANSMIT-000302 | NA | Trade Partner | Roof Stairs - Office & Link Bridge (Stair 1, 4 & 5) Issued for Approval | 44 | 0 | 0 | NA | APPROVED | 2026-06-09 | WF-005960 | NA | 2026-06-17 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-021049 | Closed | 44 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-09 | SMEPS-IntCorr-000300 | NA | Trade Partner | Telecom Labelling Schedule | 0 | 2 | 0 | NA | APPROVED | 2026-06-09 | WF - 000463 | NA | 2026-06-16 |  | NA | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-000996 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-05 | CRSol-TRANSMIT-000070 | NA | Trade Partner | Ceiling Drawings Issued for Approval - Zone C2 | 10 | 0 | 0 | NA | APPROVED | 2026-01-05 | NA | 1705 / 1811 | 2026-01-28 |  | The workflow has been resubmitted as requested - Steven | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-014646 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-09 | RDSBIM-TRANSMIT-000215 | NA | Trade Partner | LEVEL 15 & ROOF RCP LAYOUT | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - only for distribution. | 2026-06-09 | 2026-06-09 | DRAFT-018680 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-09 | SES AU-TRANSMIT-000051 | NA | Trade Partner | SECURITY- ACCESS CONTROL RISER SCHEDULE - COLO 4 & 5 - IFC | 1 | 0 | 0 | NA | APPROVED | 2026-06-09 | WF-000310 | NA | 2026-06-11 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-000883 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-09 | SES AU-TRANSMIT-000052 | NA | Trade Partner | SECURITY - IFC Tech Data | 0 | 8 | 0 | NA | APPROVED | 2026-06-09 | WF-000311 | NA | 2026-06-12 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-000888 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-09 | SES AU-TRANSMIT-000053 | NA | Trade Partner | MEL11-SESAU-Z-TDS-35-0- CAMERA INDOOR DOME | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Document is no longer in use. KPTG-TRANSMIT-000869 | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-000869 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-09 | SES AU-TRANSMIT-000054 | NA | Trade Partner | SECURITY- PATCH PANEL-IFC | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-000312) | NA | 2026-06-12 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-000890 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-09 | SES AU-TRANSMIT-000055 | NA | Trade Partner | SECURITY- Containtment Plans and Network Connection Diagram-IFC | 4 | 0 | 0 | NA | APPROVED | 2026-06-09 | WF-000313 | NA | 2026-06-12 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-000885 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-09 | KALLIBRE-TRANSMIT-000014 | NA | Trade Partner | Door By Door Hardware Schedule IFC | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision of this document is wrong:KPTG-IntCorr-000542 |  | 2026-06-09 | KPTG-IntCorr-000542 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-09 | ETNInd-TRANSMIT-000018 | NA | Trade Partner | MEL11 COLO4 COLO5 L2&L3 EPMS SCRIPTS IFC | 0 | 26 | 0 | NA | APPROVED | 2026-06-09 | WF-000308 | NA | 2026-06-10 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-001126 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-09 | ETNInd-TRANSMIT-000020 | NA | Trade Partner | Foreseer EPMS Documentation for Information | 0 | 18 | 0 | NA | APPROVED | 2026-06-09 | WF-000307 | NA | 2026-06-10 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-001129 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-09 | RDSBIM-TRANSMIT-000145 | NA | Trade Partner | MLCSPR ¦ STAGE 2 ¦ RETENTION PLAN AND ELEVATIONS ¦ FOR SUBMISSION | 5 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 305 | 2026-06-12 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-003240 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-05 | CRSol-TRANSMIT-000072 | NA | Trade Partner | Ceiling Drawings Issued for Approval - Zone C3 | 10 | 0 | 0 | NA | APPROVED | 2026-01-05 | NA | 1706 / 1812 | 2026-01-28 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-014650 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-09 | DLTS-TRANSMIT-000022 | NA | Trade Partner | S9-Northern Awning-IFA Issue | 28 | 0 | 0 | NA | APPROVED | 2026-06-09 | WF-000896 | NA | 2026-06-19 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-005189 | Closed | 28 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-09 | DLTS-TRANSMIT-000016 | NA | Trade Partner | S9-Antenna room-IFA Issue | 73 | 0 | 0 | NA | APPROVED | 2026-06-08 | WF-000887 | NA | 2026-06-15 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-004627 | Closed | 73 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-09 | DLTS-TRANSMIT-000020 | NA | Trade Partner | Antenna room-IFA Issue-Updated Dcouments | 16 | 0 | 0 | NA | APPROVED | 2026-06-09 | WF-000887 | NA | 2026-06-15 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-004629 | Closed | 16 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-09 | DLTS-TRANSMIT-000021 | NA | Trade Partner | S9-Glazing Frame Support-IFA Issue-08062026 | 9 | 0 | 0 | NA | APPROVED | 2026-06-09 | WF-000889 | NA | 2026-06-18 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-005187 | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-09 | Nilsen3-TRANSMIT-000033 | NA | Trade Partner | Nilsen Sample's #3 | 0 | 6 | 0 | NA | APPROVED | 2026-06-09 | WF-000888 | NA | 2026-06-16 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-004452 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-09 | VIA Arch-TRANSMIT-000154 | NA | Consultant | M2 - S9 - 11 Building Permit Issue | 18 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 1049 | 2026-06-12 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-003679 | Closed | 18 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-09 | VIA Arch-TRANSMIT-000156 | NA | Consultant | M2 S9-11 Signage Plans, Door Schedules & Details | 10 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 1052 | 2026-06-12 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-003748 | Closed | 10 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-09 | ZIA-TRANSMIT-000005 | NA | Trade Partner | M2 S9,10,11 CSMS FDS Submission (FOA-1) | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-000894 | NA | 2026-06-19 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-004845 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-09 | KPTG-IntCorr-001164 | NA | Trade Partner | M2 S9-11 Revised Generator Enclosure Drgs. | 3 | 0 | 0 | NA | APPROVED | 2026-06-09 | WF-000895 | NA | 2026-06-19 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-10 | ENF-TRANSMIT-000017 | NA | Consultant | Structural Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 240 | 2026-06-17 |  | Actual received date 22-05-2026 |  |  |  | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-05 | HDRAus-TRANSMIT-000350 | NA | Consultant | HDRAus-TRANSMIT-000350 Eave gutter outrigger & Admin Comms Riser | 6 | 0 | 0 | NA | APPROVED | 2026-01-05 | NA | 1710 | 2026-01-07 |  |  |  | 2026-01-15 | KPTG-TRANSMIT-011507 | Closed | 6 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-10 | PCForm-TRANSMIT-000173 | NA | Trade Partner | Re: Stair 05 shop drawings | 4 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect revision Bee Eng-TRANSMIT-000015 |  | 2026-06-10 | KPTG-RFI-008312 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-10 | SKS Tech-TRANSMIT-000157 | NA | Trade Partner | Sections and Isometrics take off box to PDU | 2 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 3475 | 2026-06-13 |  | As instructed by Damian, the workflow has been terminated. The trade partner will submit a new revision. |  | 2026-07-17 | NA | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-10 | JCBa-TRANSMIT-000133 | NA | Consultant | Apartment Type Updates for IFC | 29 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 1184 | 2026-06-12 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-002463 | Closed | 29 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-10 | KALLIBRE-TRANSMIT-000005 | NA | Trade Partner | Door & Wall System Tech Data | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Document number is incorrect |  | 2026-06-10 | KPTG-TRANSMIT-000995 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-10 | SMEPS-TRANSMIT-000047 | NA | Trade Partner | Inground Elec site plan FOA-7 | 1 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 1060 | 2026-06-16 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-004415 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | TTW-TRANSMIT-000169 | NA | Trade Partner | Civil Updated Drawing | 6 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 749 | 2026-06-11 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-002435 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | TTW-TRANSMIT-000160 | NA | Trade Partner | Updated Civil Design & Stormwater | 4 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 749 | 2026-06-11 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-002436 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | INGEN3D-TRANSMIT-000099 | NA | Trade Partner | Level 9-11 - Precast Columns - IFC | 49 | 0 | 0 | NA | APPROVED | 2026-06-09 | WF-000666 | NA |  |  |  | 2026-06-12 | 2026-06-15 | KPTG-TRANSMIT-002273 | Closed | 49 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | INGEN3D-TRANSMIT-000100 | NA | Trade Partner | Level 9-11 - PC0439 - No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | no longer in use - distributed - KPTG-TRANSMIT-002159 |  | 2026-06-09 | KPTG-TRANSMIT-002159 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | RDSBIM-TRANSMIT-000046 | NA | Trade Partner | MEZZANINE CONCRETE PROFILE PLAN PART 4 | 4 | 0 | 0 | NA | APPROVED | 2026-06-09 | WF-000681 | 747, | 2026-06-16 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-002333 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-12 | D&E-TRANSMIT-000288 | NA | Trade Partner | REPORT - Cooling Tower Waffle Pad - Acoustic Report | 0 | 1 | 0 | NA | APPROVED | 2025-12-15 | WF-000852 | NA | 2025-12-22 |  |  | 2026-01-05 | 2026-01-05 | KPTG-TRANSMIT-002254 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | Jangho-TRANSMIT-000142 | NA | Trade Partner | Tower Visual Mock-UP Shop Drawing_Rev:A | 21 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 755 | 2026-06-18 |  | REJECTED: QA ERROR-KPTG-IntCorr-000770 | 2026-07-09 | 2026-07-10 | KPTG-TRANSMIT-002808 | Closed | 21 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | Jangho-TRANSMIT-000154 | NA | Trade Partner | Sliding Door AS Standard Requirements | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-000684 | NA | 2026-06-18 |  |  | 2026-06-12 | 2026-06-12 | KPTG-TRANSMIT-002255 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-10 | Auspan-TRANSMIT-000365 | NA | Trade Partner | Precast shop drawings for approval. Level 3 | 12 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 1186 | 2026-06-17 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-002341 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | Jangho-TRANSMIT-000155 | NA | Trade Partner | Issues Thermal Report FT07 For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-000685 | NA | 2026-06-18 |  |  | 2026-06-12 | 2026-06-12 | KPTG-TRANSMIT-002258 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | Jangho-TRANSMIT-000156 | NA | Trade Partner | Issues the Thermal Report of FT01 for approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-000686 | NA | 2026-06-18 |  |  | 2026-06-18 | 2026-06-10 | KPTG-TRANSMIT-002209 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | Jangho-TRANSMIT-000157 | NA | Trade Partner | Issues the Thermal Report of FT02 for approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-000687 | NA | 2026-06-18 |  |  | 2026-06-17 | 2026-06-12 | KPTG-TRANSMIT-002260 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | Jangho-TRANSMIT-000159 | NA | Trade Partner | FT01 & FT02 Syetem Concept Drawing _PDF file _Rev:A | 28 | 0 | 0 | NA | APPROVED | 2026-06-09 | NA | 751 | 2026-06-19 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-002508 | Closed | 28 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | INGEN3D-TRANSMIT-000101 | NA | Trade Partner | Level 12-14 - Precast Columns - IFA | 1 | 0 | 0 | NA | APPROVED | 2026-06-09 | WF-000682 | NA | 2026-06-26 |  |  | 2026-06-29 | 2026-06-19 | KPTG-TRANSMIT-002367 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | INGEN3D-TRANSMIT-000102 | NA | Trade Partner | Mortar Sample Submission Option 3 | 61 | 0 | 0 | NA | APPROVED | 2026-06-09 | WF-000683 | NA | 2026-06-26 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-002556 | Closed | 61 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-05 | DS-TRANSMIT-000085 | NA | Trade Partner | L01 H/L Water and Roof Drainage - Issued for approval | 6 | 0 | 0 | NA | REJECTED |  |  |  | 2026-01-07 |  | Requested the originator to change the revision number. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | Traf Grp-TRANSMIT-000010 | NA | Consultant | Traffic Engineering Review for Secondary Consent Application | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-000667 | NA | 2026-06-10 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-002233 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | Traf Grp-CADV-000034 | NA | Consultant | raffic Engineering Review for Secondary Consent Application | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-000668 | NA | 2026-06-10 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-002225 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-10 | SRA-PMQ-TRANSMIT-000008 | NA | Trade Partner | (WF-000192) ARC - SRA - TD - IFA - CONSULTANT REVIEW - SRA-PMQ-TRANSMIT-000006-DataStruct Installation Instructions | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Title mismatch, |  | 2026-06-10 | KPTG-SADV-000606 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-10 | OveArup-TRANSMIT-000182 | NA | Consultant | Fwd: M3 Stage 4 Fire Engineering Report Issue 1.0 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-06-10 | KPTG-TRANSMIT-018458 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-01 | ADP-TRANSMIT-000332 | NA | Consultant | ADP MEL4780 - HY Drawings (Status change only) | 9 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 3397 | 2026-06-10 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018460 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-10 | SKS Tech-TRANSMIT-000158 | NA | Trade Partner | Cover sheet and drawing index | 1 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 3477 | 2026-06-19 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-10 | Civilex-TRANSMIT-000263 | NA | Trade Partner | Stage 2 - Rooftop Planter Box - Updated Naming | 1 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 4276 | 2026-06-17 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-018828 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-10 | POTTSENG-TRANSMIT-000048 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - PENETRATION - GROUND - ZONE 4 LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 1189 | 2026-06-17 |  | Review terminated as advised by Kapitol DM. | 2026-06-12 | 2026-06-12 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-10 | D&E-TRANSMIT-000264 | NA | Trade Partner | Mechanical Chiller Lifting Plan | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Cover page is missing and document revision is incorrect. |  | 2026-06-10 | KPTG-TRANSMIT-000996 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | Traf Grp-CADV-000034 | NA | Consultant | Traffic Engineering Reports for Secondary Consent | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-000669 | NA | 2026-06-10 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-002227 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-01 | Stowe-A-TRANSMIT-000387 | NA | Trade Partner | Tech Data Submission - LSS-B1 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-06 | DS-TRANSMIT-000086 | NA | Trade Partner | L01 H-L Water and Roof Drainage - Revision update | 6 | 0 | 0 | NA | APPROVED | 2026-01-06 | NA | 1721 | 2026-01-14 |  |  |  | 2026-01-15 | KPTG-TRANSMIT-011497 | Closed | 6 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | Traf Grp-CADV-000034 | NA | Consultant | Traffic Engineering Reports for Secondary Consent | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-000670 | NA | 2026-06-10 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-002229 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | Jangho-TRANSMIT-000158 | NA | Trade Partner | Tower Visual Mock-UP Shop Drawing_Rev:A | 1 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 755 | 2026-06-18 |  |  | 2026-07-09 | 2026-07-10 | KPTG-TRANSMIT-002808 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-10 | Jangho-TRANSMIT-000163 | NA | Trade Partner | Tower Visual Mock-UP Shop Drawing_Rev:A | 1 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 755 | 2026-06-18 |  |  | 2026-07-09 | 2026-07-10 | KPTG-TRANSMIT-002808 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-10 | Auspan-TRANSMIT-000368 | NA | Trade Partner | Re: Precast shop drawings for approval. Level 4. - DC QC Error | 3 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 1191 | 2026-06-17 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-002489 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-10 | SKS Tech-TRANSMIT-000160 | NA | Trade Partner | Lighting Schedule | 1 | 0 | 0 | NA | REJECTED | [5 empty] | INCORRECT DOCUMENT NUMBER TYPE |  | 2026-06-10 | KPTG-RFI-008316 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-10 | ENF-TRANSMIT-000024 | NA | Consultant | Structural drawings | 14 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 247 | 2026-06-17 |  | Voided- Updated drawings received from the consultant |  | 2026-06-12 | KPTG-DA-000349 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-03 | 4Ki-TRANSMIT-000011 | NA | Trade Partner | Shop Drawings For Approval - JNR001, JNR004, JNR014, JNR015 | 1 | 0 | 0 | NA | APPROVED | 2026-06-04 | WF-001104 | NA | 2026-06-09 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-003884 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-10 | Entire M-TRANSMIT-000063 | NA | Trade Partner | Mechanical coversheet - drawing index IFA | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status is wrong, requested to resubmit:KPTG-IntCorr-000553 |  | 2026-06-10 | KPTG-IntCorr-000553 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-10 | Entire M-TRANSMIT-000059 | NA | Trade Partner | Mechanical drawings - Issued for construction | 1 | 0 | 0 | NA | APPROVED | 2026-06-10 | WF-000314 | NA | 2026-06-12 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-000871 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-10 | Civilex-TRANSMIT-000264 | NA | Trade Partner | Sample Submission - Stage 1 - Concrete Curing Compound (Fosroc-Concure-CR) | 0 | 1 | 0 | NA | APPROVED | 2026-06-10 | WF-005977 | NA | 2026-06-16 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-019181 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-06 | HDRAus-TRANSMIT-000351 | NA | Consultant | HDRAus-TRANSMIT-000351 DHC1 and C2 RCP Reissue | 1 | 0 | 0 | NA | APPROVED | 2026-01-06 | NA | 1723 | 2026-01-08 |  |  |  | 2026-01-15 | KPTG-TRANSMIT-011498 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-10 | D&E-TRANSMIT-000265 | SPARK-CRFI-KPG-000497 | Trade Partner | Mechanical Services Level-01 Ductwork & Pipework Seismic Drawings | 9 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 314 | 2026-06-17 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-001005 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-10 | SKS Tech-TRANSMIT-000161 | NA | Trade Partner | Lighting Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-06-10 | WF-005978 | NA | 2026-07-06 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-018846 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-10 | ADP-TRANSMIT-000344 | NA | Consultant | Re: MEL4780 - S4 - Electrical Drawings | 3 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | The IFC was submitted without the IFA |  | 2026-06-10 | KPTG-RFI-008320 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-10 | M.S.-TRANSMIT-000070 | NA | Trade Partner | Zone 1 Shop drawings | 2 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 310 | 2026-06-12 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-003010 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-10 | SKS Tech-TRANSMIT-000159 | NA | Trade Partner | Equipment Layout | 7 | 0 | 0 | NA | REJECTED | [5 empty] | IFA approval is pending. submitted IFC drawings |  | 2026-06-10 | KPTG-RFI-008322 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-10 | INTRFRM-TRANSMIT-000074 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 15) | 0 | 1 | 0 | NA | APPROVED | 2026-06-10 | WF-000194 | NA | 2026-06-18 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-000814 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-10 | SES AU-TRANSMIT-000056 | NA | Trade Partner | Security- L2 COLO 4 and L1 COLO5 Floor Plan - IFC Rev 3 | 2 | 0 | 0 | NA | APPROVED | 2026-06-10 | WF-000315 | NA | 2026-06-12 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-000895 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-10 | WilsonPD-TRANSMIT-000011 | NA | Trade Partner | NXGEO1 - Wilson Sample Resubmission | 0 | 1 | 0 | NA | APPROVED | 2026-06-10 | WF-000195 | NA | 2026-06-18 |  |  | 2026-06-12 | 2026-06-12 | KPTG-TRANSMIT-000798 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-10 | Entire M-TRANSMIT-000026 | NA | Trade Partner | Pumps - Issued For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-10 | WF-000196 | NA | 2026-06-18 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-000887 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-10 | KPTG-IntCorr-000478 | NA | Trade Partner | MEL06-UMS BOM Telecom WF | 0 | 1 | 0 | NA | APPROVED | 2026-06-10 | WF - 000464 | NA | 2026-06-13 |  | NA | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-001007 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-05 | ARCST-TRANSMIT-000169 | NA | Trade Partner | Stage 4 - C2 Switchroom Upper Gantry Grating - Issued for Approval | 119 | 0 | 0 | NA | APPROVED | 2026-01-05 | WF-003699 | NA | 2026-01-27 |  | Due to an error encountered while attaching the document, it could not be sent through the mother transmittal. Hence, the document has been shared separately via closeout mail. |  | 2026-02-20 | KPTG-TRANSMIT-013263 | Closed | 119 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-10 | ccair-TRANSMIT-000122 | NA | Trade Partner | VSD Schedule for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-10 | WF - 001041 | NA | 2026-06-17 |  | NA | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-003116 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-10 | RDSBIM-TRANSMIT-000205 | NA | Trade Partner | 511SRC ¦ LEVEL 09 RCP KEY PLAN AND LAYOUT | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC only for distribution. |  | 2026-06-10 | KPTG-TRANSMIT-003042 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-24 | WilsonPD-TRANSMIT-000181 | SPARK-CRFI-KPG-000648 | Trade Partner | Grates for Approval | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-000998 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-10 | RDSBIM-TRANSMIT-000206 | NA | Trade Partner | 511SRC ¦ LEVEL 08 RCP KEY PLAN AND LAYOUT - RDSBIM-TRANSMIT-000206 | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - distribution only. |  | 2026-06-10 | KPTG-TRANSMIT-003040 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-10 | RDSBIM-TRANSMIT-000216 | NA | Trade Partner | NA | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | NA |  | 2026-06-10 | KPTG-TRANSMIT-003043 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-10 | Entire M-TRANSMIT-000064 | NA | Trade Partner | Mechanical coversheet - drawing index IFA | 1 | 0 | 0 | NA | APPROVED | 2026-06-10 | WF-000316 | NA | 2026-06-16 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-000937 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-10 | JCBa-TRANSMIT-000250 | NA | Consultant | Red Stick Reviews (Issued for Construction Documents) JCBa-TRANSMIT-000250 - L9 Laundry Wall Detail Change | 48 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 576 | 2026-06-12 |  | NA | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-003092 | Closed | 48 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-10 | ccair-TRANSMIT-000118 | NA | Trade Partner | Updated Level 14 Mechanical Shop Drawings - IFC | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC- only for distribution. |  | 2026-06-10 | KPTG-TRANSMIT-003044 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-02 | WilsonPD-TRANSMIT-000009 | NA | Trade Partner | NXGEO1 - Wilson Fixture Samples for approval | 0 | 12 | 0 | NA | APPROVED | 2026-06-02 | WF-000179 | NA | 2026-06-12 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-001018 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-05 | ARCST-TRANSMIT-000168 | NA | Trade Partner | Stage 4 - C2 Gantry Roof & Secondary Steel - Issued for Review | 133 | 0 | 0 | NA | APPROVED | 2026-01-05 | WF-003696 | NA | 2026-01-26 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-013461 | Closed | 133 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-29 | WilsonPD-TRANSMIT-000006 | NA | Trade Partner | NEXGEO1 - WPD Samples for Approval | 0 | 2 | 0 | NA | APPROVED | 2026-05-29 | WF-000172 | NA | 2026-06-08 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001061 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-26 | VERTIV-TRANSMIT-000021 | NA | Trade Partner | NEXT DC GE 01 _ MATERIAL SUBMISSION _ POWER CABLES AND CABLE TRAY & TRUNKING (FOA-1) | 0 | 1 | 0 | NA | APPROVED | 2026-05-26 | WF-000157 | NA | 2026-06-03 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-000865 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-10 | VAE-Grp-TRANSMIT-000171 | NA | Trade Partner | MECHANICAL - REVISED LG, GR, L1-3 LAYOUTS | 5 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 1287 | 2026-06-12 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-003997 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-10 | ADP-TRANSMIT-000078 | NA | Consultant | GE1 Earthing Design Report | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For Information, Only updation required. |  | 2026-06-10 | KPTG-TRANSMIT-000787 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-10 | VERTIV-TRANSMIT-000028 | NA | Trade Partner | Next DC - GE1 - CRAC IFA Documentation | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Issues with document number, title, revision, drawings status etc. |  | 2026-06-10 | KPTG-SADV-000616 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-10 | ADP-TRANSMIT-000345 | NA | Consultant | ADP MEL4780 - FUEL Drawings (Status change only) | 11 | 0 | 0 | NA | APPROVED | [5 empty] | Received the documents with the updated status |  | 2026-06-10 | KPTG-TRANSMIT-018519 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-10 | VERTIV-TRANSMIT-000029 | NA | Trade Partner | NextDC - GE1 - CRAC IFA Tech Data Documentation | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Issue with Document number, title etc. |  | 2026-06-10 | KPTG-SADV-000615 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-10 | KPTG-TRANSMIT-018527 | NA | Trade Partner | M3 S2 - CRS O&M | 0 | 1 | 0 | NA | APPROVED | 2026-06-03 | WF-006004 | NA | 2026-06-23 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-019305 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-10 | Civilex-TRANSMIT-000265- | NA | Trade Partner | Sample Submission - Pavement Concrete mix design (Pronto) | 0 | 1 | 0 | NA | APPROVED | 2026-06-10 | WF-005982 | NA | 2026-06-25 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-10 | HDRAus-TRANSMIT-000502 | NA | Consultant | RAIN GARDEN'S DRAWING UPDATE | 3 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 4279 | 2026-06-12 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-018722 | Open | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-06 | HDRAus-TRANSMIT-000352 | NA | Consultant | M3 Stage 4 - Updated GA plan - Ground Floor - Sheet 1201 | 1 | 0 | 0 | NA | APPROVED | 2026-01-05 | NA | WF-003700 | 2026-01-08 |  |  |  | 2026-01-15 | KPTG-TRANSMIT-011505 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-10 | D&E-TRANSMIT-000806 | NA | Trade Partner | NXM3S2 - Chilled Water & SFN Water Schematics - Ground & First Floor + Condensing Roof & Upper Roof - Issued For Construction | 4 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 4281 | 2026-06-17 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-019085 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-10 | Civilex-TRANSMIT-000266 | NA | Trade Partner | Sample Submission - Stage 2 - Concrete Curing Compound (Fosroc-Concure-CR) | 0 | 1 | 0 | NA | APPROVED | 2026-06-10 | WF-005987 | NA | 2026-06-16 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-019133 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-10 | Civilex-TRANSMIT-000267 | NA | Trade Partner | Stage 2 - sample submission - Civil Pavement Concrete Mix Design - HyTec | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Wrong discipline inside document. |  | 2026-06-10 | KPTG-SADV-005811 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-10 | Nilsen3-TRANSMIT-000181 | NA | Trade Partner | Re: Nilsen IFC- Drawings | 6 | 0 | 0 | NA | REJECTED | 2026-06-10 | [6 empty] | 2026-06-10 | KPTG-RFI-008324 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-10 | D&E-TRANSMIT-000808 | NA | Trade Partner | NXM3S4 - Ground - CHW Pipe Layout - Zone 6 - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 3485 | 2026-06-19 |  |  | 2026-07-24 | 2026-07-24 | ⁠KPTG-TRANSMIT-019946 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-10 | ADP-TRANSMIT-000343 | NA | Consultant | MEL4780 - S4 - HYD Updated Drawings | 10 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 3487 | 2026-06-10 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-10 | ADP-TRANSMIT-000343 | NA | Consultant | MEL4780 - S4 - HYD Updated Drawings | 10 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 3488 | 2026-06-24 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-020493 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-10 | KPTG-TRANSMIT-002523 | NA | Trade Partner | South VIG Glass Submission | 0 | 1 | 0 | NA | APPROVED | 2026-06-10 | WF-000789 | NA | 2026-06-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-10 | INGEN3D-TRANSMIT-000103 | NA | Trade Partner | Level 14-16 - Precast Columns - IFA | 45 | 0 | 0 | NA | APPROVED | 2026-06-10 | WF-000693 | NA | 2026-06-26 |  |  |  | 2026-07-10 | KPTG-TRANSMIT-002812 | Closed | 45 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-06 | LTEPRCST-TRANSMIT-000144 | NA | Trade Partner | NEXTDC STAGE 4 - CORE 01-09 LIDS ISSUED FOR APPROVAL | 8 | 0 | 0 | NA | APPROVED | 2026-01-06 | WF-003701 | NA | 2026-01-30 |  |  |  | 2026-02-04 | KPTG-TRANSMIT-012452 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-10 | INGEN3D-TRANSMIT-000104 | NA | Trade Partner | Level 14-16 - Precast Columns - IFA | 2 | 0 | 0 | NA | APPROVED | 2026-06-10 | WF-000693 | NA | 2026-06-26 |  |  |  | 2026-07-10 | KPTG-TRANSMIT-002812 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-10 | 4DW-TRANSMIT-000044 | NA | Consultant | Structural Documentation: General coordination update issue. | 1 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 186 | 2026-06-18 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-000423 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-10 | RDSBIM-TRANSMIT-000010 | NA | Trade Partner | GROUND LEVEL ¦CPP-BLOCK 1¦ IFR¦ FOR SUBMISSION | 2 | 0 | 0 | KPTG-IntCorr-000164 | APPROVED | 2026-07-13 | NA | 372 | 2026-07-21 |  | Voided- resubmitted |  | 2026-07-13 | NA | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-10 | Civilex-TRANSMIT-000006 | NA | Trade Partner | Stage 6 Foundation/Piling Design | 1 | 5 | 0 | NA | REJECTED |  | NA | NA |  |  | Report- wrong Naming Convention, Drawing submitted-#192 |  | 2026-06-10 | KPTG-SADV-000219 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-10 | Civilex-TRANSMIT-000007 | NA | Trade Partner | Sample Submission Concrete Mix Design (Piling) | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Wrong Cover sheet |  | 2026-06-10 | KPTG-SADV-000218 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-10 | TTW-TRANSMIT-000038 | NA | Consultant | Stage 6 Sitewide Contour Plan | 1 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 194 | 2026-06-18 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-000232 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-10 | 4DW-TRANSMIT-000045 | NA | Consultant | Structural Documentation: NLB precast walls updates. | 3 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 189 | 2026-06-18 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-000784 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-10 | ELLISAIR-TRANSMIT-000056 | NA | Trade Partner | IFA - VSD ULH | 0 | 1 | 0 | NA | APPROVED | 2026-06-10 | WF-000898 | NA | 2026-06-15 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-004468 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-10 | Building Permit Drawings - Electrical | NA | Consultant | Building Permit Drawings - Electrical | 83 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 1064 | 2026-06-16 |  |  | 2026-07-29 | 2026-07-29 | KPTG-DA-004016 | Closed | 83 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-10 | Nilsen3-TRANSMIT-000031 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 3 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 1066 | 2026-06-17 |  | Drawings resubmitted for Aurecon review as advised by Project Coordinator (ACC review # 1145) | 2026-06-17 | 2026-06-17 | KPTG-IntCorr-001256 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-17 | OveArup-TRANSMIT-000017 | NA | Consultant | ELECTRICAL SERVICES - Early Works - Layouts | 6 | 0 | 0 | NA | APPROVED | 2025-12-17 | NA | 160 | 2026-01-13 |  |  | 2026-01-30 | 2026-01-30 | KPTG-TRANSMIT-000357 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-11 | Rinco-TRANSMIT-000054 | NA | Consultant | GFZ4 PT plan update | 1 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 1193 | 2026-06-18 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-002361 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-11 | RDSBIM-TRANSMIT-000047 | NA | Trade Partner | LEVEL 02 ¦ CPP ¦ FOR REVIEW AND SUBMISSION | 6 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 757 | 2026-06-19 |  |  | 2026-07-02 | 2026-07-03 | KPTG-TRANSMIT-002678 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-11 | PFP PL-TRANSMIT-000005 | NA | Trade Partner | Level 2 Wet Fire Layout IFC | 1 | 0 | 0 | NA | APPROVED | 2026-06-11 | WF - 000465 | NA | 2026-06-15 |  | NA | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-000974 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-10 | Auspan-TRANSMIT-000367 | NA | Trade Partner | Precast shop drawings for construction. Level 3 | 27 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC- No review, Updated register and distributed (KPTG-TRANSMIT-002212) |  | 2026-06-11 | KPTG-TRANSMIT-002212 | Closed | 27 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-10 | Auspan-TRANSMIT-000366 | NA | Trade Partner | Update already IFCed shop drawings. Level 2 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC- No review required, update register and distribute - KPTG-TRANSMIT-002207 |  | 2026-06-10 | KPTG-TRANSMIT-002207 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-10 | JCBa-TRANSMIT-000134 | NA | Consultant | Partition and Facade Assembly Drawings for IFC | 18 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 1199 | 2026-06-15 |  | Review voided and new review initiated.ACC#1212 | 2026-06-11 | 2026-06-11 | NA | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-10 | JCBa-TRANSMIT-000136 | NA | Consultant | Reflected Ceiling Plan Updates: IFC | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Michael Harris, No Review; updated register only. |  | 2026-06-10 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-10 | ccair-TRANSMIT-000020 | NA | Trade Partner | Mechanical Services B1 shop and Builders works drawing IFA [B] | 2 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 549 | 2026-06-10 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001258 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-11 | RDSBIM-TRANSMIT-000068 | NA | Trade Partner | GREYSTAR ¦ L01 ¦ CPP ¦ IFC ¦ FOR SUBMISSION | 7 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 1203 | 2026-06-18 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-002262 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-17 | OveArup-TRANSMIT-000017 | NA | Consultant | FIRE SERVICES - Early Works - Layouts | 12 | 0 | 0 | NA | APPROVED | 2025-12-17 | NA | 163 | 2026-01-13 |  |  | 2026-01-30 | 2026-01-30 | KPTG-TRANSMIT-000361 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-11 | SES AU-TRANSMIT-000057 | NA | Trade Partner | Security - Tech Data - AUTO TRANSFER SWITCH | 0 | 1 | 0 | NA | APPROVED | 2026-06-11 | WF-000317) | NA | 2026-06-18 |  |  | 2026-06-12 | 2026-06-12 | KPTG-TRANSMIT-000881 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-11 | D&E-TRANSMIT-000810 | NA | Trade Partner | NXM3S4 - Ground - Plinth & Equipment Layout Zones - Issued For Construction | 7 | 0 | 0 | NA | REJECTED | [5 empty] | Two documents were rejected at FOA-1 review. We have now received FC-2 for all documents |  | 2026-06-11 | KPTG-RFI-008334 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-11 | SKS Tech-TRANSMIT-000162 | NA | Trade Partner | Cover sheet and drawing index | 1 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | #3490 | 2026-06-14 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-11 | SMEPS-TRANSMIT-000228 | NA | Trade Partner | SME Samples for Uprev | 0 | 11 | 0 | NA | APPROVED | 2026-06-11 | WF - 000467 | NA | 2026-06-15 |  | NA | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-001003 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-11 | Entire M-TRANSMIT-000065 | NA | Trade Partner | VCDs Technical Data Rev 1 IFC | 0 | 1 | 0 | NA | APPROVED | 2026-06-11 | WF-000318 | NA | 2026-06-16 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-000877 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-11 | Schindle-TRANSMIT-000029 | NA | Trade Partner | Lift C3 - Landing Frame - FOA -1 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect document number , title |  | 2026-06-11 | KPTG-RFI-008337 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-11 | Auspan-TRANSMIT-000374 | NA | Trade Partner | Resubmit precast panel 1P5011 for approval | 1 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 1205 | 2026-06-18 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-002419 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-11 | ECBS-TRANSMIT-000023 | NA | Trade Partner | TechData Gyprock Rigitone Matrix 15mm Round_For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-11 | WF-001111 | NA | 2026-06-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-11 | SMEPS-TRANSMIT-000229 | NA | Trade Partner | Electrical Technical data. | 0 | 4 | 0 | NA | APPROVED | 2026-06-11 | WF - 000468 | NA | 2026-06-15 |  | NA | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-000999 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-10 | Civilex-TRANSMIT-000006-DWG | NA | Trade Partner | Stage 6 Foundation/Piling Design | 1 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 192 | 2026-06-17 |  | Voided |  | 2026-07-17 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-17 | OveArup-TRANSMIT-000017 | NA | Consultant | MECHANICAL SERVICES - Early Works - Layouts | 7 | 0 | 0 | NA | APPROVED | 2025-12-17 | NA | 168 | 2026-01-13 |  |  | 2026-01-30 | 2026-01-30 | KPTG-TRANSMIT-000365 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-11 | Stowe-A-TRANSMIT-000607 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - Communication Device Layout | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Different statuses |  | 2026-06-11 | KPTG-SADV-005835 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-11 | Auspan-TRANSMIT-000375 | NA | Trade Partner | Precast shop drawings for approval. Levels 3, 4 | 8 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 1207 | 2026-06-18 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-002434 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-11 | KALLIBRE-TRANSMIT-000015 | NA | Trade Partner | Door By Door Hardware Schedule IFC | 0 | 1 | 0 | NA | APPROVED | 2026-06-11 | WF-000319 | NA | 2026-06-12 |  |  |  | 2026-06-11 | KPTG-IntCorr-000562 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-11 | VERTIV-TRANSMIT-000030 | NA | Trade Partner | NEXT DC GE 01 _ MATERIAL SUBMISSION _ FIRE STOPPING ROXTEC (FOA-1) | 0 | 1 | 0 | NA | APPROVED | 2026-06-11 | WF-000198 | NA | 2026-06-22 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001337 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-11 | VERTIV-TRANSMIT-000031 | NA | Trade Partner | NEXT DC GE 01 _ MATERIAL SUBMISSION _ FIRE STOPPING PENETRATION SEALING (FOA-1) | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with document number. |  | 2026-06-11 | KPTG-SADV-000630 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-11 | KALLIBRE-TRANSMIT-000016 | NA | Trade Partner | 11.40.202 Shop Drawing | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Drawing does not valid information-KPTG-IntCorr-000561 |  | 2026-06-11 | KPTG-IntCorr-000561 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-11 | INDS-TRANSMIT-000033 | NA | Trade Partner | Wet Fire - Basement Zone 2 & 5 | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC-No review, Register updated and distributed (KPTG-TRANSMIT-002221) |  | 2026-06-11 | KPTG-TRANSMIT-002221 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-11 | Ardon-TRANSMIT-000040 | NA | Trade Partner | Stage 4 Roof Frame Shop Drawings | 20 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 3494 | 2026-06-15 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-018971 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-11 | PCForm-TRANSMIT-000175 | NA | Trade Partner | S4 Precast Caulking Tech Data Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | INCORRECT REVISION |  | 2026-06-11 | KPTG-RTRFI-004686 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-11 | ZIA-TRANSMIT-000098 | NA | Trade Partner | Re: CSMS Clash Report | 5 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-RFI-008342 - Revision number incorrect. | 2026-06-11 | 2026-06-11 | KPTG-RFI-008342 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-17 | OveArup-TRANSMIT-000017 | NA | Consultant | HYDRAULIC SERVICES - Early Works - Layouts | 6 | 0 | 0 | NA | APPROVED | 2025-12-17 | NA | 170 | 2026-01-13 |  |  | 2026-01-30 | 2026-01-30 | KPTG-TRANSMIT-000369 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-11 | Firesafe-TRANSMIT-000011 | NA | Trade Partner | level 2 car park | 2 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 759 | 2026-06-18 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-002268 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-11 | JCBa-TRANSMIT-000136 | NA | Consultant | Reflected Ceiling Plan Updates: IFC | 5 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 1211 | 2026-06-15 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-002475 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-11 | VERTIV-TRANSMIT-000032 | NA | Trade Partner | NEXT DC GE 01 _ MATERIAL SUBMISSION _ GPO and Switches (FOA-1) | 0 | 1 | 0 | NA | APPROVED | 2026-06-11 | WF-000199 | NA | 2026-06-22 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-000891 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-11 | Civilex-TRANSMIT-000102 | NA | Trade Partner | FirePro FR - Water based, ﬁre-rated, ﬂexible intumescent sealant | 0 | 1 | 0 | NA | APPROVED | 2026-06-11 | WF-000697 | NA | 2026-06-17 |  | In review |  | 2026-07-09 | WF-000902 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-11 | SRA-PMQ-TRANSMIT-000009 | NA | Trade Partner | Resubmiting douments | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Title of the Document is mismatching |  | 2026-06-11 | KPTG-SADV-000624 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-11 | Auscool-TRANSMIT-000048 | NA | Trade Partner | level 2 - IFA Shop Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 1214 | 2026-06-18 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-002502 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-11 | WilsonPD-TRANSMIT-000075 | NA | Trade Partner | Stage 9 Level 2 Sewer and Stormwater IFA | 1 | 0 | 0 | NA | APPROVED | 2026-06-11 | WF-000913 | 1074 | 2026-06-18 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-004587 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-11 | Nilsen3-TRANSMIT-000035 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 7 | 0 | 0 | NA | APPROVED | 2026-06-11 |  | 1070 | 2026-06-18 |  | Drawings resubmitted for Aurecon review as advised by Project coordinator (ACC # 1146) | 2026-06-17 | 2026-06-17 | KPTG-IntCorr-001257 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-11 | PSGANZ-TRANSMIT-000012 | NA | Trade Partner | Fire Detection tech. data submission | 0 | 1 | 0 | NA | APPROVED | 2026-06-11 | WF-000200 | NA | 2026-06-22 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001333 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-11 | INTRFRM-TRANSMIT-000076 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 15) | 0 | 1 | 0 | NA | APPROVED | 2026-06-11 | WF-000201 | NA | 2026-06-22 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-000833 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-01 | Stowe-A-TRANSMIT-000383 | NA | Trade Partner | Stowe - Tech Data Submission - AHF | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-19 | WAM-TRANSMIT-000020 | NA | Consultant | WAM ARCH - 95% DD Facade Plans and Window Schedule | 31 | 0 | 0 | NA | APPROVED | 2025-12-19 | NA | 172 | 2026-01-15 |  | 3drawings QA error - DRAFT-002294 awaiting approval | 2026-01-20 | 2026-01-20 | KPTG-TRANSMIT-000300 | Closed | 31 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-11 | Entire M-TRANSMIT-000028 | NA | Trade Partner | Expansion Tanks & Automatic Refill Units - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-11 | WF-000202 | NA | 2026-06-22 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001588 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-11 | KALLIBRE-TRANSMIT-000006 | NA | Trade Partner | Updated Door Docs Numbering | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Incorrect project name |  | 2026-06-11 | KPTG-TRANSMIT-001001 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-11 | ZIA-TRANSMIT-000009 | NA | Trade Partner | Re: M2 S10,11 CSMS SLA & DP SENSOR LOCATION Submission (FOA-1) | 5 | 0 | 0 | NA | APPROVED | 2026-06-11 | WF-000916 | 1076 | 2026-06-18 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-004438 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-06-11 | vdmcons-TRANSMIT-000019 | NA | Trade Partner | D14 M3 Stage 3 GIS Building - Shop Drawings & 3D IFC Model - Swithcboard Steel Changes - IFF - 2026-06-11 | 7 | 0 | 0 | NA | APPROVED | 2026-06-15 | WF-006030 | NA | 2026-06-26 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-018783 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-11 | Civilex-TRANSMIT-000268 | NA | Trade Partner | Stage 2 - sample submission - Civil Pavement Concrete Mix Design - HyTec | 0 | 1 | 0 | NA | APPROVED | 2026-06-11 | WF-005992 | NA | 2026-06-17 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-019344 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-11 | Omnii-TRANSMIT-000005 | NA | Consultant | Fire Engineering Performance-Based Design Brief Revision E | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect document number |  | 2026-06-11 | KPTG-DA-000345 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-11 | PROLMC-TRANSMIT-000026 | SPARK-CRFI-KPG-000607 | Trade Partner | 8mm Acoustic Screen Shop Drawings | 6 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 315 | 2026-06-18 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-001609 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-11 | D&E-TRANSMIT-000809 | NA | Trade Partner | NXM3S2 - Level 01 - Mechanical Pipe Layout - Zone 1 & 2 - As Built | 2 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 4283 | 2026-06-16 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-018754 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-11 | D&E-TRANSMIT-000811 | NA | Trade Partner | Re: NXM3S2 - LEVEL 01 - DATAHALL 5 SFN UNION AND BOLT TORQUE MAP - Issued For Construction | 1 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due ifc directly submiitted |  | 2026-06-11 | KPTG-SADV-005838 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-19 | TTW-TRANSMIT-000064 | NA | Consultant | TTW Civil - Updated CAD DWG | 8 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | discrepancies with pdf - KPTG-DA-000470 |  | 2026-01-12 | TTW-IntCorr-000116 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-11 | Civilex-TRANSMIT-000269 | NA | Trade Partner | -Stage 2 - sample submission - Landscape Materials | 0 | 1 | 0 | NA | APPROVED | 2026-06-11 | WF-005999 | NA | 2026-06-18 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-018679 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-11 | CRSol-TRANSMIT-000090 | NA | Trade Partner | -M3S2-DHB6- SMW | 8 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 4287 | 2026-06-25 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-11 | ACG-TRANSMIT-000094 | NA | Trade Partner | M3 S2 - SP5 ACG As-Built Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 4285 | 2026-06-16 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-019506 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-11 | WAM-TRANSMIT-000800 | NA | Consultant | WAM ARCH - Development Summary and Apartment Matrix | 2 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 761 | 2026-06-14 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-002683 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-11 | 4DW-TRANSMIT-000046 | NA | Consultant | Issued for Certification: NLB Walls - Northern Feature Precast | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Already submitted |  | 2026-06-11 | NA | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-11 | Auspan-TRANSMIT-000372 | NA | Trade Partner | transmit panel 0G5003 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC- No review required, update register and distribute - KPTG-TRANSMIT-002210 |  | 2026-06-11 | KPTG-TRANSMIT-002210 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-11 | Auspan-TRANSMIT-000373 | NA | Trade Partner | Resubmit shop drawing for approval. Level 2 panel 2P5018 | 1 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 1195 | 2026-06-18 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-002422 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-11 | Auspan-TRANSMIT-000370 | NA | Trade Partner | Precast shop drawings for construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC- No review required, update register and distribute - KPTG-TRANSMIT-002223 |  | 2026-06-11 | KPTG-TRANSMIT-002223 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-11 | Auspan-TRANSMIT-000371 | NA | Trade Partner | Precast fish plate FP4 and FP5 for post fixed panels for review | 0 | 2 | 0 | KPTG-IntCorr-000673 | APPROVED | 2026-06-12 | WF-000601 | NA | 2026-06-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-11 | Auspan-TRANSMIT-000376 | NA | Trade Partner | L1 - SHIP LAP CHECK FOR PERIMETER PANELS. Update IFCed precast shop drawings | 4 | 0 | 0 | KPTG-IntCorr-000679 | APPROVED |  | NA | NA |  |  | IFC - Kapitol PC Kim to Confirm -KPTG-IntCorr-000679. As advised by KIM proceed 1 and reject 3 drawings- KPTG-IntCorr-000716. 1 drawing Register updated and distributed - KPTG-TRANSMIT-002317 |  | 2026-06-17 | KPTG-TRANSMIT-002317 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-06 | HDRAus-TRANSMIT-000353 | NA | Consultant | Rack Layout - C1, C2, C4-C12 | 3 | 0 | 0 | NA | APPROVED | 2026-01-06 | NA | 1729 | 2026-01-09 |  |  |  | 2026-01-15 | KPTG-TRANSMIT-011489 | Closed | 3 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-11 | Auscool-TRANSMIT-000047 | na | Trade Partner | - BASEMET TO LEVEL 7 - TUNDISH LOCATIONS | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect drawing number DRAFT-008280 |  | 2026-06-11 | DRAFT-008280 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-11 | JCBa-TRANSMIT-000135 | NA | Consultant | : Partition Detail Sections IFC (updated) | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | drawings Superseded with JCBa-TRANSMIT-000137 |  | 2026-06-11 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-11 | JCBa-TRANSMIT-000137 | NA | Consultant | Partition Detail Sections: IFC (updated) | 18 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 1212 | 2026-06-15 |  | Updated drawings from Previous transmittal JCBa-TRANSMIT-000134 & 00135. Review void for JCBa-TRANSMIT-000134 and combined review initiated with JCBa-TRANSMIT-000137. | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-002460 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-11 | Aurecon-TRANSMIT-000108 | NA | Consultant | SME review-Electrical specification | 0 | 1 | 0 | NA | APPROVED | 2026-06-11 | NA | 191 | 2026-06-17 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-000552 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-11 | NXT-TRANSMIT-000348 | NA | Client | Traffic Reports - NXT-TRANSMIT-000348 | 0 | 3 | 0 | NA | APPROVED | 2026-06-11 | NA | 190 | 2026-06-17 |  |  | 2026-07-02 | 2026-07-03 | KPTG-TRANSMIT-000429 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-16 | Inhabit-TRANSMIT-000015 | NA | Trade Partner | FP.06 ¦ PODIUM ENTRY GRC CLADDING & FRAMELESS GLAZING | 5 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001060 - Document number format, alignment, status are incorrect. KPTG-IntCorr-001074 - As per instruction from Ashlin, the documents have been superseded.We have updated only the document register and transmitted it to all parties. | 2026-06-16 | 2026-06-16 | KPTG-IntCorr-001074 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-11 | B Smart-TRANSMIT-000079 | NA | Consultant | Architecture Drawing Facade Elevation_A09 Elevation | 1 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 554 | 2026-06-16 |  | Review voided to update the drawings by Kapitol. | 2026-06-19 | 2026-06-19 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-11 | B Smart-TRANSMIT-000080 | NA | Consultant | Updated drawings for IFC | 7 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 556 | 2026-06-16 |  | Review void by Kapitol PC. |  | 2026-06-23 | NA | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-11 | WAM-TRANSMIT-000799 | NA | Consultant | Material Finishes and FFE Schedule Update | 0 | 2 | 0 | NA | APPROVED | 2026-06-11 | WF-000695 | NA | 2026-06-14 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-002482 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-11 | L.E.S.-TRANSMIT-000005 | NA | Trade Partner | Carpark Level 2 and 3 light fitting data sheets - IFA | 0 | 3 | 0 | NA | APPROVED | 2026-06-11 | WF-000698 | NA | 2026-06-16 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-002287 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-06 | SMEPS-TRANSMIT-000130 | NA | Trade Partner | Re: M3 STAGE 3 GIS - ELEC SHOP DRAWINGS - AS BUILT | 1 | 0 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-11 | INGEN3D-TRANSMIT-000105" | NA | Trade Partner | Level 15-17 - Precast Columns - IFA (11-06-2026) | 49 | 0 | 0 | NA | APPROVED | 2026-06-11 | WF-000700 | NA | 2026-06-29 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-002541 | Closed | 49 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-14 | KPTG-TRANSMIT-001768 | NA | Client | Citipower Preliminary Indoor Substation Drawings | 11 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 644 | 2026-06-05 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-002251 | Open | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-11 | DLTS-TRANSMIT-000023 | NA | Trade Partner | S9-Roof Canopy-IFA Issue | 67 | 0 | 0 | NA | APPROVED | 2026-06-11 | WF-000905 | NA | 2026-06-16 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-004626 | Closed | 67 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-11 | PFP PL-TRANSMIT-000008 | NA | Trade Partner | S9 Level 2 Dwg & Calc IFA | 1 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 1068 | 2026-06-17 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-004636 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-11 | WilsonPD-TRANSMIT-000062 | NA | Trade Partner | Hebel Block Rod Anchor Chemset | 0 | 1 | 0 | NA | APPROVED | 2026-06-11 | WF-000907 | NA | 2026-06-16 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-004334 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-11 | WilsonPD-TRANSMIT-000073 | NA | Trade Partner | Syphonic Drainage Drawings for Approval | 12 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 1072 | 2026-06-16 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-004554 | Closed | 12 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-11 | WilsonPD-TRANSMIT-000074 | NA | Trade Partner | BUTTERFLY VALVES | 0 | 1 | 0 | NA | APPROVED | 2026-06-11 | WF-000908 | NA | 2026-06-22 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-004540 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-11 | PROLMC-GCOR-000006 | NA | Trade Partner | Sample Technical Data Sheet Submission | 0 | 6 | 0 | NA | APPROVED | 2026-06-11 | WF-000923 | NA | 2026-06-18 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-004538 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-11 | VIA Arch-TRANSMIT-000162 | NA | Consultant | M2 S11 & S9 Finish Plan Updates | 5 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 1078 | 2026-06-16 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-004017 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-07 | ARCST-TRANSMIT-000170 | NA | Trade Partner | Stage 4 - C2 Upper Gantry Handrails | 41 | 0 | 0 | NA | APPROVED | 2026-01-07 | WF-003709 | NA | 2026-01-28 |  |  |  | 2026-01-20 | KPTG-TRANSMIT-011747 | Closed | 41 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-11 | VIA Arch-TRANSMIT-000163 | NA | Consultant | M2 S9-11 Procurement Balustrade & Movement Joint Packages | 19 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 1080 | 2026-06-16 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-003926 | Closed | 19 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-11 | ELLISAIR-TRANSMIT-000057 | NA | Trade Partner | Expansion & ARU [1] | 0 | 1 | 0 | NA | APPROVED | 2026-06-11 | WF-000918 | NA | 2026-06-17 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-004703 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-11 | ELLISAIR-TRANSMIT-000058 | NA | Trade Partner | Springs tech data | 0 | 1 | 0 | NA | APPROVED | 2026-06-11 | WF-000919 | NA | 2026-06-17 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-004476 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-12 | KPTG-TRANSMIT-000981 | NA | Trade Partner | Startup and Energisation Plans - issued for approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-12 | WF - 000471 | NA | 2026-06-16 |  | NA | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-001067 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-12 | M.S.-TRANSMIT-000071 | NA | Trade Partner | Zone 2 Shop drawings. | 6 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-SADV-004624: Wrong Document numbering |  | 2026-06-12 | KPTG-SADV-004624 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-12 | Auspan-TRANSMIT-000377 | NA | Trade Partner | Precast dowel layout zone 1, 2 level 1 | 1 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 1217 | 2026-06-19 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-002437 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-12 | ECBS-TRANSMIT-000019 | NA | Trade Partner | CM01 - Armstrong Metalworks Open Cell (100 x 100mm) tech data for approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-12 | WF - 001043 | NA | 2026-06-15 |  | File supersede and WF terminated. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-12 | JCI-TRANSMIT-000030 | NA | Trade Partner | Alarm Updates To DoO | 0 | 2 | 0 | NA | APPROVED | 2026-06-12 | WF - 000473 | NA | 2026-06-16 |  | NA | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-001015 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-12 | Auscool-TRANSMIT-000049 | NA | Trade Partner | Re: BASEMET TO LEVEL 7 - TUNDISH LOCATIONS | 4 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 1219 | 2026-06-19 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-002412 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-12 | RDSBIM-TRANSMIT-000011 | NA | Trade Partner | NXGE01 ¦ PARTITION WALL LAYOUT ¦ IFR ¦ FOR SUBMISSION | 5 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 272 | 2026-06-17 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-000885 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-07 | ARCST-TRANSMIT-000171 | NA | Trade Partner | Stage 4 - C2 Switchroom Upper Gantry Primary Steel - Issued for Approval | 175 | 0 | 0 | NA | APPROVED | 2026-01-07 | WF-003710 | NA | 2026-01-28 |  |  |  | 2026-02-10 | The workflow has been terminated as per requested by Lola W | Closed | 175 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-12 | Auspan-TRANSMIT-000364 | NA | Trade Partner | Precast shop drawings for construction. Level 4. | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC: No review needed, updated register and distributed (KPTG-TRANSMIT-002228) |  | 2026-06-12 | KPTG-TRANSMIT-002228 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-12 | SRA-PMQ-TRANSMIT-000010 | NA | Trade Partner | Resubmission | 0 | 3 | 0 | NA | APPROVED | 2026-06-12 | WF-000204 | NA | 2026-06-23 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001406 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-12 | Jangho-TRANSMIT-000165 | NA | Trade Partner | Glass Sample Submission (GL-01 Option 3) | 0 | 1 | 0 | NA | APPROVED | 2026-06-12 | WF-000703 | NA | 2026-06-30 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-003142 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-12 | SES AU-TRANSMIT-000058 | NA | Trade Partner | Security - Type 1A Single Line Schematics - IFA | 3 | 0 | 0 | NA | APPROVED | 2026-06-12 | WF-000321 | NA | 2026-06-17 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-000947 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | ADP-TRANSMIT-000344 | NA | Consultant | MEL4780 - S4 - Electrical Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | #3500 | 2026-06-16 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-020674 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | Rinco-TRANSMIT-000007 | NA | Trade Partner | Structural Drawings - General notes, Precast Lids & Stair + REG126 - IFC | 5 | 0 | 0 | NA | APPROVED | 2026-06-12 | WF-006003 | NA | 2026-06-25 |  |  |  | 2026-06-16 | KPTG-IntCorr-014664 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-12 | WGAVIC-TRANSMIT-000139 | NA | Consultant | M2 - Structural Ground Floor Details Update - Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 1082 | 2026-06-19 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-004529 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | D&E-TRANSMIT-000814 | NA | Trade Partner | Fwd: ACC Issue #16644 - SFN system volume & expansion calculations | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-08-03 | KPTG-TRANSMIT-020309 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-12 | WGAVIC-TRANSMIT-000140 | NA | Consultant | M2 - Structural Stage 11 Facade - Issued for Certification | 2 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 1085 | 2026-06-19 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-004650 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-12 | ZLH P/L-TRANSMIT-000001 | NA | Trade Partner | Proposed Material - Design & Sample - ZLH | 0 | 8 | 0 | NA | REJECTED | [5 empty] | Issue with Document number, Revision and Cover sheet. |  | 2026-06-12 | KPTG-SADV-000636 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-07 | Entire M-TRANSMIT-000025 | NA | Trade Partner | Mechanical Fixing and Supports Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-01-07 | WF-003714 |  | 2026-01-20 |  |  |  | 2026-01-14 | KPTG-TRANSMIT-011422 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | PARR-TRANSMIT-000190 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - UPDATED IFC DRAWINGS | 8 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-06-12 | KPTG-TRANSMIT-018581 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | D&E-TRANSMIT-000813 | NA | Trade Partner | ISSUED FOR APPROVAL - SFN & CHW SCHEMATICS | 9 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 3510 | 2026-06-24 |  | As instructed by Ellie S- Terminated. D&E need to make updates before ARUP review |  | 2026-07-17 | NA | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | PARR-TRANSMIT-000191 | NA | Trade Partner | Re: P2685 - NDC M3 - Stage 4 - Battery Rooms - CONTROL SYSTEM DRAWINGS - IFC | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-06-12 | NXT-PA-005231 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-12 | WGAVIC-TRANSMIT-000141 | NA | Consultant | M2 - Stage 10 Level 1 and 2 Slabs, Stage 11 Level 1 Slab - Issued for Construction | 15 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 1088 | 2026-06-19 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-004825 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | SMEPS-TRANSMIT-000304 | NA | Trade Partner | SME - IFC Sample submissions | 0 | 8 | 0 | NA | APPROVED | [5 empty] | IFC Techdata distributed to all |  | 2026-06-12 | KPTG-TRANSMIT-018584 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | NXT-TRANSMIT-001615 | NA | Trade Partner | Fwd: P2685 - NDC M3 - Stage 4 - Battery Rooms - CONTROL SYSTEM DRAWINGS - IFC | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-06-12 | KPTG-TRANSMIT-018588 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-12 | WGAVIC-TRANSMIT-000143 | NA | Consultant | M2 - Stage 2 Tank Slab Update - Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 1090 | 2026-06-19 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-004659 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-06-12 | ASV-TRANSMIT-000179 | NA | Trade Partner | Fwd: Hydraulic Sample - Copper Pipe Lagging | 0 | 1 | 0 | NA | APPROVED | 2026-06-12 | WF-006005 | NA | 2026-06-30 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-019080 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-12 | WGAVIC-TRANSMIT-000144 | NA | Consultant | M2 - Stage 9 Loading Dock Slab Level 1 - Issued for Construction | 2 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 1092 | 2026-06-19 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-004663 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-12 | WGAVIC-TRANSMIT-000146 | NA | Consultant | M2 - Steelwork Package - Supplementary Issue - Issued for Construction | 3 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 1096 | 2026-06-19 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-004670 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-07 | WGAVIC-TRANSMIT-000038 | NA | Consultant | Incorrect Upload - No Longer In Use | 2 | 0 | 0 | NA | APPROVED | [5 empty] | Drawings marked as No Longer in Use |  | 2026-01-07 |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | D&E-TRANSMIT-000815 | NA | Trade Partner | NXM3S4 - Upper Roof Level - CHW & CCW Pipe Layout - Zone 9 - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 3503 | 2026-06-24 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-12 | WGAVIC-TRANSMIT-000147 | NA | Consultant | M2 - Stage 9-11 Structural Specification - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-06-12 | NA | 1098 | 2026-06-19 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-004674 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-12 | L.E.S.-TRANSMIT-000009 | NA | Trade Partner | Floor box tech data & Substation DB shop drawing | 0 | 4 | 0 | NA | APPROVED | 2026-06-12 | WF-000704 | NA | 2026-06-16 |  |  | 2026-06-17 | 2026-06-18 | KPTG-TRANSMIT-002354 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | D&E-TRANSMIT-000816 | NA | Trade Partner | ISSUED FOR APPROVAL - DH C1 CHW & SFN SCHEMATIC | 1 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 3508 | 2026-06-17 |  | As instructed by Ellie S- Terminated. D&E need to make updates before ARUP review |  | 2026-07-17 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-12 | WGAVIC-TRANSMIT-000148 | NA | Consultant | M2 - Loading Dock - Issued for Construction | 7 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 1100 | 2026-06-19 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-004678 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-12 | L.E.S.-TRANSMIT-000010 | NA | Trade Partner | Level 2 carpark Lights - IFA | 2 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 764 | 2026-06-22 |  |  | 2026-06-14 | 2026-06-22 | KPTG-TRANSMIT-002383 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-12 | ENF-TRANSMIT-000026 | NA | Consultant | Structural Drawings | 15 | 0 | 0 | NA | REJECTED | [5 empty] | Multiple status drawings submitted under single transmittal |  | 2026-06-12 | KPTG-DA-000348 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-12 | ENF-TRANSMIT-000027 | NA | Consultant | Structural Drawings | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Information Only |  | 2026-06-12 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-12 | ENF-TRANSMIT-000028 | NA | Consultant | Structural drawings | 14 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 249 | 2026-06-19 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-19 | KETE-TRANSMIT-000026 | NA | Trade Partner | thermal report | 0 | 1 | 0 | NA | APPROVED | 2025-12-19 | WF-000667 | 782 | 2025-12-26 |  |  | 2026-01-12 | 2026-01-12 | KPTG-TRANSMIT-002376 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-12 | Civilex-TRANSMIT-000103 | NA | Trade Partner | Kerb Concrete Mix Design | 0 | 1 | 0 | NA | APPROVED | 2026-06-12 | WF-000706 | NA | 2026-06-23 |  |  | 2026-06-19 | 2026-06-26 | KPTG-TRANSMIT-002513 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | Nilsen3-TRANSMIT-000182 | NA | Trade Partner | Nilsen Shop Drawing - TYPICAL PDU SCHEMATIC FOA | 1 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | #3512 | 2026-06-15 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-12 | RDSBIM-TRANSMIT-000206 | NA | Trade Partner | LINDRUM ¦ LEVEL 11,13,15,17,19,21,23,25,27 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001061 - As per instruction from Ashlin, we have only updated the register and transmitted it to all parties. | 2026-06-12 | 2026-06-12 | KPTG-IntCorr-001061 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-12 | RDSBIM-TRANSMIT-000207 | NA | Trade Partner | LINDRUM ¦ CPP ¦ L-12,14,16,18,20,22,24&26 ¦ IFC ¦ SUBMISSION | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001062 - As per instruction from Ashlin, we have only updated the register and transmitted it to all parties. | 2026-06-12 | 2026-06-12 | KPTG-IntCorr-001062 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | D&E-TRANSMIT-000817 | NA | Trade Partner | Fwd: NXM3S4 - Level 1 - Plinth & Equipment Layout - Zones - Issued For Construction | 8 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-06-12 | KPTG-TRANSMIT-018605 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-12 | L.E.S.-TRANSMIT-000011 | NA | Trade Partner | Level 5 slab penetrations IFA | 2 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 766 | 2026-06-22 |  |  | 2026-06-21 | 2026-06-22 | KPTG-TRANSMIT-002405 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-12 | Civilex-TRANSMIT-000106 | NA | Trade Partner | Orange Geofab | 0 | 1 | 0 | NA | APPROVED | 2026-06-12 | WF-000708 | NA | 2026-06-23 |  |  | 2026-06-16 | 2026-06-16 | KPTG-WTRAN-001433 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-12 | SMEPS-TRANSMIT-000004 | NA | Trade Partner | Shop Drawings: Communications | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with title. |  | 2026-06-12 | KPTG-SADV-000641 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-12 | Civilex-TRANSMIT-000104 | NA | Trade Partner | SN8 AGI | 0 | 1 | 0 | NA | APPROVED | 2026-06-12 | WF-000709 | NA | 2026-06-23 |  |  | 2026-06-19 | 2026-06-16 | KPTG-TRANSMIT-002320 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | D&E-TRANSMIT-000818 | NA | Trade Partner | NXM3S4 - Level 1 - SFN Pipe Layout - Zones - Issued For Construction | 10 | 0 | 0 | NA | APPROVED | [5 empty] | For distribution |  | 2026-06-12 | KPTG-TRANSMIT-018606 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-19 | VAE-Grp-TRANSMIT-000095 | NA | Trade Partner | MECHANICAL - MCC SCHEDULE & FIRE MATRIX | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | FC DOCUMENTS - Register Updated |  | 2025-12-19 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-12 | MAYFLD-TRANSMIT-000453 | NA | Trade Partner | 100222-000596: M3 Stage 2 - ED Room - Architectural As Built Drawings | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As Built, only for updating in Aconex and ACC and distribution. |  | 2026-06-12 | KPTG-TRANSMIT-018602 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-12 | M.2-TRANSMIT-000040 | NA | Trade Partner | Electrical Services Lighting & Cabletray shop drawings | 10 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 1224 | 2026-06-19 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-002981 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | HDRAus-TRANSMIT-000503 | NA | Consultant | Re. M3 Stage 4 - Document upload - PDF and CAD | 5 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 3505 | 2026-06-16 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-018653 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-12 | MAYFLD-TRANSMIT-000454 | NA | Trade Partner | 100222-000597: M3 Stage 2 - EE Room - Architectural As Built Drawings | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As Built Document, only for updating in Aconex, ACC and distribution. |  | 2026-06-12 | KPTG-TRANSMIT-018596 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-12 | MAYFLD-TRANSMIT-000456 | NA | Trade Partner | 100222-000599: M3 Stage 2 - EO Room - Architectural As Built Drawings | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As Built document, only for updating in Aconex, ACC and distribution/ |  | 2026-06-12 | KPTG-TRANSMIT-018595 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-12 | KALLIBRE-TRANSMIT-000007 | SPARK-CRFI-KPG-000715 | Trade Partner | Door and wall systems Tech Data | 0 | 3 | 0 | NA | APPROVED | [9 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | ZIA-TRANSMIT-000099 | NA | Trade Partner | Fwd: CSMS Clash Report | 5 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 3520 | 2026-06-25 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-019825 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | ZIA-TRANSMIT-000100 | NA | Trade Partner | Re: M3S4 Control Cable Sample Data Submission | 0 | 2 | 0 | NA | REJECTED |  | NA | NA |  |  | rejected due wrong document naming |  | 2026-06-12 | KPTG-RTRFI-004707 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-12 | VOGUE-TRANSMIT-000018 | NA | Trade Partner | CONCRETE SAMPLES REV 2 | 0 | 2 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect drawing no. |  |  | DRAFT-018819 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | ASV-TRANSMIT-000180 | NA | Trade Partner | Hydraulic Sample Internal Sewer Magflows | 0 | 1 | 0 | NA | APPROVED | 2026-06-12 | WF-006011 | NA | 2026-06-24 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-018853 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-01 | Stowe-A-TRANSMIT-000391 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - EARTHING - 01.12.2025 | 8 | 0 | 0 | KPTG-DA-003681 | REJECTED | [5 empty] | Difference in status inside and outside the document |  | 2025-12-05 |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-19 | RDSBIM-TRANSMIT-000041 | NA | Trade Partner | LEVEL 01 PARTITION WALL PLAN AND ELEVATION | 3 | 0 | 0 | NA | APPROVED | 2025-12-19 | WF-000674 | 784 | 2025-12-25 |  |  | 2026-01-29 | 2026-01-30 | KPTG-TRANSMIT-002633 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-12 | Civilex-TRANSMIT-000105 | NA | Trade Partner | Xypex Material Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-12 | WF-000711 | NA | 2026-06-18 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-002305 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | Nilsen3-TRANSMIT-000183 | NA | Trade Partner | Re: Nilsen Shop Drawing Small power layout Roof Updated | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | the revision number in the Aconex transmittal register and inside the drawing seems different. |  | 2026-06-12 | KPTG-SADV-005868 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | ZIA-TRANSMIT-000101 | NA | Trade Partner | Re: M3S4 Control Cable Sample Data Submission | 0 | 2 | 0 | NA | APPROVED | 2026-06-12 | WF-006012 | NA | 2026-06-25 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-019269 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-12 | MAYFLD-TRANSMIT-000455 | NA | Trade Partner | 100222-000598: M3 Stage 2 - EN Room - Architectural As Built Drawings | 10 | 0 | 0 | KPTG-IntCorr-014552 | APPROVED | [5 empty] | As Built for updating in ACC, Aconex and distribution only. | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-018691 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | Ardon-TRANSMIT-000041 | NA | Trade Partner | Resubmitted Shop Drawings | 20 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 3518 | 2026-06-24 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-018958 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | Ardon-TRANSMIT-000042 | NA | Trade Partner | Stage 4 Chiller Door Room Sets | 11 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 3519 | 2026-06-24 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-018975 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | PCForm-TRANSMIT-000178 | NA | Trade Partner | S4 Precast Caulking Tech Data Approval | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Revision date is incorrect |  | 2026-06-12 | KPTG-RFI-008376 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | D&E-TRANSMIT-000819 | NA | Trade Partner | Fwd: NXM3S4 - Ground & Level 1 - Mechanical Duct Layout Zones - Issued For Construction | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distributuion |  | 2026-06-12 | KPTG-TRANSMIT-018609 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | ZIA-TRANSMIT-000102 | NA | Trade Partner | Re (WF-005885) M3 - S4 DOCUMENT CONTROL REVIEW - S4- IFA - CSMS - CONSULTANT REVIEW-SHOP DRAWING - ZIA-TRANSMIT-000095 M3S4 CSMS OS & ORMB | 6 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 3522 | 2026-06-25 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020153 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-12 | Auspan-TRANSMIT-000378 | NA | Trade Partner | Precast shop drawings for construction. Level 4 | 20 | 0 | 0 | KPTG-IntCorr-000685 | APPROVED |  | NA | NA |  |  | IFC - Kpaitol PC Kim to Confirm -KPTG-IntCorr-000685 19 Drawings registered and transmitted - KPTG-TRANSMIT-002387; One drawing to be resubmitted for Approval - DRAFT-008690 |  | 2026-06-22 | KPTG-TRANSMIT-002387 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-19 | RDSBIM-TRANSMIT-000042 | NA | Trade Partner | ROOF CONCRETE PROFILE PLAN | 2 | 0 | 0 | NA | APPROVED | 2025-12-19 | NA | 787 | 2025-12-25 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-002870 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-12 | POTTSENG-TRANSMIT-000049 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - PENETRATION - GROUND - ZONE 4 LAYOUT | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC- No review required, Register and transmit : KPTG-TRANSMIT-002232 |  | 2026-06-12 | KPTG-TRANSMIT-002232 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-12 | INDS-TRANSMIT-000034 | NA | Trade Partner | : Floor Penetration layout - IFC | 11 | 0 | 0 | KPTG-IntCorr-000697 | APPROVED |  | NA | NA |  |  | IFC- No review required, Register and transmit : KPTG-TRANSMIT-002244 |  | 2026-06-15 | KPTG-TRANSMIT-002244 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-12 | INDS-TRANSMIT-000035 | NA | Trade Partner | : Basement to Level 7 - Precast Peno - IFC | 32 | 0 | 0 | KPTG-IntCorr-000697 | APPROVED |  | NA | NA |  |  | IFC- No review required, Register and transmit : KPTG-TRANSMIT-002246 |  | 2026-06-15 | KPTG-TRANSMIT-002246 | Closed | 32 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-12 | INDS-TRANSMIT-000036 | NA | Trade Partner | : Wet Fire - Schematic - IFC | 1 | 0 | 0 | KPTG-IntCorr-000697 | APPROVED |  | NA | NA |  |  | IFC- No review required, Register and transmit : KPTG-TRANSMIT-002248 |  | 2026-06-15 | KPTG-TRANSMIT-002248 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-12 | INDS-TRANSMIT-000037 | NA | Trade Partner | Hydraulic Calcs | 0 | 2 | 0 | KPTG-IntCorr-000697 | APPROVED |  | NA | NA |  |  | IFC- No review required, Register and transmit : KPTG-TRANSMIT-002252 |  | 2026-06-15 | KPTG-TRANSMIT-002252 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-12 | KALLIBRE-TRANSMIT-000001 | NA | Trade Partner | Toilet Partition Shop Drawings - IFA | 0 | 6 | 0 | NA | REJECTED |  | NA | NA |  |  | Drawing Title and no in corrected. |  |  | KPTG-TRANSMIT-003052 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-12 | WGAVIC-TRANSMIT-000149 | NA | Consultant | M2 - North Retaining Wall - Issued for Construction | 3 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 1108 | 2026-06-19 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-004682 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-12 | HDRAus-TRANSMIT-000504 | NA | Trade Partner | M3 SW - Document upload - PDF and CAD | 4 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 4292 | 2026-06-17 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-019997 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-12 | SMEPS-TRANSMIT-000005 | NA | Trade Partner | Shop Drawing submission: Electrical | 12 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-06-12 | DRAFT-002710 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-12 | WGAVIC-TRANSMIT-000150 | NA | Consultant | M2 - Stair Flights - Issued for Construction | 8 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 1110 | 2026-06-19 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-004687 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-08 | NXT-TRANSMIT-001177 Reference Number EAEGROUP-TRANSMIT-000053 | NA | Trade Partner | M3-ELC-EAE-SDRG-C-0401-0001 | 1 | 0 | 0 | NA | APPROVED | 2026-01-08 | WF-003715 | NA | 2026-01-26 |  |  |  | 2026-01-14 | NXT-WTRAN-001549 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-12 | KALLIBRE-TRANSMIT-000018 | NA | Trade Partner | Door By Door Hardware Schedule IFC | 0 | 1 | 0 | NA | APPROVED | 2026-06-12 | WF-000322 | NA | 2026-06-18 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-000921 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-12 | KALLIBRE-TRANSMIT-000018 | NA | Trade Partner | Door By Door Hardware Schedule IFC | 0 | 1 | 0 | NA | APPROVED | 2026-06-12 | WF-000323 | NA | 2026-06-15 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-000887 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-12 | KPTG-TRANSMIT-001105 | NA | Trade Partner | 671 CHP - Facade Cast-in Brackets | 16 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 558 | 2026-06-19 |  | Review void as advised by Kapitol DM. |  | 2026-08-03 | NA | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-12 | KALLIBRE-TRANSMIT-000019 | NA | Trade Partner | Door Hardware Tech Data with Cover Sheets | 0 | 35 | 0 | NA | APPROVED | 2026-06-12 | WF-000324 | NA | 2026-06-18 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-000928 | Closed | 35 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-12 | KALLIBRE-TRANSMIT-000017 | NA | Trade Partner | Door Tech Data | 0 | 4 | 0 | NA | REJECTED |  | NA | NA |  |  | COVERING SHEET HAS NOT BEEN PROPERLY UPDATED: Documents Rejected:KPTG-IntCorr-000565 |  | 2026-06-12 | KPTG-IntCorr-000565 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-15 | KETE-TRANSMIT-000136 | NA | Trade Partner | Kete - Updated Podium Drawings | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001063 - REQUESTED GUIDENCE,BUT NO RESPONSE RECEIVED YET. KPTG-IntCorr-001065 - As per direction from Ashlin, we only update the document register and transmit to all parties. | 2026-06-15 | 2026-06-15 | KPTG-IntCorr-001065 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-12 | NXT-TRANSMIT-000402 | NA | Client | M3S6 - Barkers Fencing Design | 3 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 196 | 2026-06-22 |  |  | 2026-06-15 | 2026-06-15 | NA | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-12 | ACCCA-TRANSMIT-000006 | NA | Trade Partner | HYDRAULIC FOR APPROVAL | 12 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 202 | 2026-06-22 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-000531 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-12 | PTA-TRANSMIT-000006 | NA | Consultant | Concrete Profile Plan _Block 1 - For Review | 3 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 198 | 2026-06-12 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-000210 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-19 | VAE-Grp-TRANSMIT-000096 | NA | Trade Partner | MECH - MCC DRAWINGS | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | FC DOCUMENTS - Register Updated |  | 2025-12-19 | NA | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | HDRAus-TRANSMIT-000506 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 2 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 3529 | 2026-06-16 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-018650 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | D&E-TRANSMIT-000821 | NA | Trade Partner | Re: ISSUED FOR CONSTRUCTION - UPPER ROOF LEVEL - CHW & CCW PIPE LAYOUTS | 4 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | NA |  |  | IFC seeked for information |  | 2026-06-12 | KPTG-IntCorr-014555 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | HDRAus-TRANSMIT-000505 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 15 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 3532 | 2026-06-16 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-018790 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | D&E-TRANSMIT-000820 | NA | Trade Partner | Re ISSUED FOR APPROVAL - UPPER ROOF LEVEL - COOLING TOWER SECTIONS | 2 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 3528 | 2026-06-16 |  | The 1 document is under review. |  | 2026-08-10 | KPTG-TRANSMIT-020474 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-12 | PCForm-TRANSMIT-000180 | NA | Trade Partner | -Re: S4 Precast Caulking Tech Data Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-12 | WF-006021 | NA | 2026-06-25 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-12 | HGP-TRANSMIT-000004 | NA | Trade Partner | Glazing Calculations | 0 | 1 | 0 | NA | APPROVED | 2026-06-12 | WF-000920 | NA | 2026-06-17 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-004699 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-12 | Nilsen3-TRANSMIT-000038 | NA | Trade Partner | Nilsen Sample submissions #4 | 0 | 1 | 0 | NA | APPROVED | 2026-06-12 | WF-000924 | NA | 2026-06-17 |  |  | 2026-06-12 | 2026-06-12 | KPTG-TRANSMIT-004205 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-12 | DIH-TRANSMIT-000001 | NA | Trade Partner | Updated Hydraulic Layouts & Penetrations | 5 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 1095 | 2026-06-18 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-004419 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-12 | Busduct Shop Drawings (Outlook mail) | N | Trade Partner | Busduct Shop Drawings (Outlook mail) | 21 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 1086 | 2026-06-17 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-12 | ELLISAIR-TRANSMIT-000060 | NA | Trade Partner | Air Schematic drawings issued for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 1104 | 2026-06-19 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-004498 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-19 | KPTG-TRANSMIT-002344 | 284 | Consultant | ENVIRONMENTAL ACOUSTICS REPORT | 1 | 0 | 0 | NA | APPROVED | 2026-01-05 | NA | 794 | 2026-01-09 |  |  | 2026-01-14 | 2026-01-14 | KPTG-TRANSMIT-002403 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-12 | ELLISAIR-TRANSMIT-000062 | NA | Trade Partner | Revised Air Schematic drawings issued for Approval | 2 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 1104 | 2026-06-19 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-004499 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-12 | ELLISAIR-TRANSMIT-000061 | NA | Trade Partner | Ground Floor Loading Duct and Pipe layout drawing issued for Approval. | 1 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 1105 | 2026-06-19 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-12 | ELLISAIR-TRANSMIT-000063 | NA | Trade Partner | Condenser Water Schematics drawings issued for Approval | 4 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 1106 | 2026-06-19 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-004642 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-12 | INGEN3D-TRANSMIT-000080 | NA | Trade Partner | Dwg - PC397-1- TTW Commented copy for RDS Review | 1 | 0 | 0 | NA | APPROVED | 2026-06-12 | WF-000710 | NA | 2026-06-15 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-002337 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-12 | OveArup-TRANSMIT-000039 | NA | Trade Partner | Certificate for Early Works | 0 | 2 | 0 | NA | APPROVED | 2026-06-12 | WF-000712 | NA | 2026-06-18 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002939 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-12 | Jangho-TRANSMIT-000166 | NA | Trade Partner | Issues the Thermal Report of FT01 for approval | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | As instructed by Jaanbir - fwrded to TTW for info. |  | 2026-06-12 | KPTG-TRANSMIT-002266 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-12 | Hollow-TRANSMIT-000018 | NA | Trade Partner | L3 plant room precast structure - PC beams 04- Shop drawings, issued for Construction | 2 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 767 | 2026-06-22 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-002587 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-12 | ELLISAIR-TRANSMIT-000064 | NA | Trade Partner | Ground Floor Zone 3 and 4 Duct drawings issued for Approval. | 3 | 0 | 0 | NA | APPROVED | 2026-06-12 | NA | 1112 | 2026-06-19 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-004646 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-15 | KALLIBRE-TRANSMIT-000020 | NA | Trade Partner | Door Tech Data - Updated Cover Sheets | 0 | 4 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected:No Technical data attached with covering sheet-KPTG-IntCorr-000569 |  | 2026-06-15 | KPTG-IntCorr-000569 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-15 | Auspan-TRANSMIT-000379 | NA | Trade Partner | Update precast cast in plate layout ground floor zone 1 | 1 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 1226 | 2026-06-22 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-002492 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-19 | RDSBIM-TRANSMIT-000040 | NA | Trade Partner | LEVEL 03 PARTITION WALL PLAN AND ELEVATION | 3 | 0 | 0 | NA | APPROVED | 2025-12-19 | WF-000669 | 788 | 2025-12-25 |  |  | 2026-01-15 | 2026-01-15 | KPTG-TRANSMIT-002455 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-15 | INTERSIG-TRANSMIT-000003 | NA | Trade Partner | 26-004 Assemble Coburg - WAYFINDING SIGNAGE | 1 | 0 | 0 | NA | APPROVED | 2026-06-15 | WF - 001045 | NA | 2026-06-19 |  | NA | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-003088 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-15 | WilsonPD-TRANSMIT-000076 | NA | Trade Partner | Stage 9 Level 1 & 2 Shop Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 1118 | 2026-06-22 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-004570 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-15 | Hollow-TRANSMIT-000019 | NA | Trade Partner | L3 plant room precast structure - Planks and Slabs - Shop drawings, issued for Construction | 9 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 769 | 2026-06-22 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-002585 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-15 | Auspan-TRANSMIT-000381 | NA | Trade Partner | Resubmit precast shop drawings for approval. Level 1 | 3 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 1228 | 2026-06-22 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-002425 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-15 | SMEPS-TRANSMIT-000230 | NA | Trade Partner | MEL05C4 Elec Seismic Design | 23 | 0 | 0 | NA | REJECTED | [5 empty] | Rev mismatch. |  | 2026-06-15 | KPTG-TRANSMIT-000989 | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-15 | KALLIBRE-TRANSMIT-000001 | NA | Trade Partner | Toilet Partition Shop Drawings - IFA | 6 | 0 | 0 | NA | APPROVED | 2026-06-15 | WF - 000557 | NA | 2026-06-17 |  | NA | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-003084 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-15 | Auspan-TRANSMIT-000382 | NA | Trade Partner | Precast shop drawings for approval. Level 2 | 8 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 1230 | 2026-06-22 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-002428 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-15 | Jangho-TRANSMIT-000167 | NA | Trade Partner | Podium Level 1~2 Floor Plan Shop Drawing_Rev 02 | 4 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 771 | 2026-06-23 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-002374 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-15 | M.S.-TRANSMIT-000072 | NA | Trade Partner | Zone 2 Shop drawings | 6 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 317 | 2026-06-22 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-003011 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-15 | D&E-TRANSMIT-000824 | NA | Trade Partner | Fwd: NXM3S4 - Ground - Mechanical Duct Layout - Zone 8 & IW Tank Room - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-06-15 | KPTG-TRANSMIT-018615 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-19 | Hames-TRANSMIT-000092 | NA | Consultant | RCP & RLS UPDATES | 99 | 0 | 0 | KPTG-TRANSMIT-002372 - 5 docs rejected | APPROVED | 2025-12-19 | WF-000677 | 790 | 2025-12-25 |  |  | 2026-01-15 | 2026-01-15 | KPTG-TRANSMIT-002407 | Closed | 94 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-15 | Jangho-TRANSMIT-000169 | NA | Trade Partner | Structural Calculation For Podium Level 1~2 Cast in Channel | 0 | 1 | 0 | NA | APPROVED | 2026-06-15 | WF-000716 | NA | 2026-06-17 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-002327 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-15 | ARCH-TRANSMIT-000159 | NA | Consultant | MLC - SPR - ISC - L2 CPP | 1 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 314 | 2026-06-18 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-002995 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-15 | Auspan-TRANSMIT-000383 | NA | Trade Partner | Precast shop drawings for approval. Level 3 | 9 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 1232 | 2026-06-22 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-002431 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-15 | RDSBIM-TRANSMIT-000057 | NA | Trade Partner | MCC ¦ LEVEL 01 FINISHES ¦ MALE END OF TRIP ¦ IFA ¦ SUBMISSION | 2 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 316 | 2026-06-22 |  | Actual received date - 12/06/2026 |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-15 | Nilsen3-TRANSMIT-000040 | NA | Trade Partner | Sample updated- Tinned Copper Lugs | 0 | 1 | 0 | NA | APPROVED | 2026-06-15 | WF-000954 | NA | 2026-06-25 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-004886 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-15 | Nilsen3-TRANSMIT-000041 | NA | Trade Partner | Nilsen Sample - E/D2 Electrolight | 0 | 1 | 0 | NA | APPROVED | 2026-06-15 | WF-000955 | NA | 2026-06-26 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-004890 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-15 | SCG2014-TRANSMIT-000029 | NA | Consultant | SCG IFT-4 security pack | 35 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 1124 | 2026-06-22 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-004533 | Closed | 35 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-15 | RDSBIM-TRANSMIT-000058 | NA | Trade Partner | MCC ¦ L01 CPP ¦ IFC ¦ FOR SUBMISSION | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Revision is incorrect |  | 2026-06-15 | KPTG-TRANSMIT-001002 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-15 | INDS-TRANSMIT-000039 | NA | Trade Partner | Wet Fire - Ground | 5 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 1234 | 2026-06-22 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-002452 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-15 | SMEPS-TRANSMIT-000224 | SPARK-CRFI-KPG-000329 | Trade Partner | NEL-CNT-SME-2990-ELC-SAM-0016 UPS-01 (A), UPS-02 (B), UPS-03 (B) | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-001434 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-05 | RDSBIM-TRANSMIT-000043 | NA | Trade Partner | LEVEL 04 PARTITION WALL KEYPLAN AND ELEVATION | 3 | 0 | 0 | NA | APPROVED | 2026-01-05 | NA | 796 | 2026-01-09 |  |  | 2026-01-21 | 2026-01-21 | KPTG-TRANSMIT-002531 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-15 | Appselec-TRANSMIT-000121 | NA | Trade Partner | EzyStrut Communications Trunking IFA | 0 | 1 | 0 | NA | APPROVED | 2026-06-15 | WF-000325 | na | 2026-06-19 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-000920 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-16 | D&E-TRANSMIT-000223 | SPARK-CRFI-KPG-000490 | Trade Partner | MWYCCB - ROOF & LEVEL 1 / DUCTWORK - PIPEWORK & RCP LAYOUT ZONES - Issued For Approval | 0 | 0 | 0 | NA | APPROVED | [6 empty] | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-001003 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-15 | Nilsen3-TRANSMIT-000184 | NA | Trade Partner | Nilsen Shop Drawing Small power layout Roof Updated | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-06-15 | KPTG-TRANSMIT-018622 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-15 | D&E-TRANSMIT-000822 | NA | Trade Partner | NXM3S4 - Upper Roof Level - Cooling Tower Sections - Sheet 2 of 4 - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 3538 | 2026-06-19 |  |  |  | 2026-06-17 | KPTG-TRANSMIT-018752 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-15 | D&E-TRANSMIT-000823 | NA | Trade Partner | MCC Schedules IFA Reg G. | 0 | 1 | 0 | NA | APPROVED | 2026-06-15 | WF-006022 | NA | 2026-07-09 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-020413 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-15 | Nilsen3-TRANSMIT-000045 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 1126 | 2026-06-22 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-004873 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-15 | RDSBIM-TRANSMIT-000276 | NA | Trade Partner | NXM3S4 ¦ LEVEL 01 ¦ C-1-054 CLEANERS ¦ IFA ¦ FOR SUBMISSION | 1 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 3542 | 2026-06-19 |  | Terminated as instructed by lachlan |  | 2026-08-11 | KPTG-TRANSMIT-020491 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-15 | SMEPS-TRANSMIT-000307 | NA | Trade Partner | IFC Sample submissions | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For Distribution |  | 2026-06-17 | KPTG-TRANSMIT-018747 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-15 | WilsonPD-TRANSMIT-000078 | NA | Trade Partner | Stage 2 Level 2 Water Supply | 1 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 1132 | 2026-06-22 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-004564 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-15 | INDS-TRANSMIT-000038 | NA | Trade Partner | Balcony Sprinkler Layout - Typical | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC- No review required, Register and transmit : KPTG-TRANSMIT-002254 |  | 2026-06-15 | KPTG-TRANSMIT-002254 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-05 | RDSBIM-TRANSMIT-000044 | NA | Trade Partner | LEVEL 05 PARTITION WALL KEYPLAN AND ELEVATIONS | 2 | 0 | 0 | NA | APPROVED | 2026-01-05 | NA | 798 | 2026-01-09 |  |  | 2026-01-21 | 2026-01-21 | KPTG-TRANSMIT-002535 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-15 | HDRAus-TRANSMIT-000508 | NA | Consultant | M3 Stage 4 - Document upload - PDF Locked drawing manual upload | 1 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 3537 | 2026-06-15 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-018887 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-15 | SMEPS-TRANSMIT-000306 | NA | Trade Partner | Re: SME - IFA Sample submissions | 3 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED DUE TO WRONG NAMING |  | 2026-06-15 | KPTG-RTRFI-004735 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-15 | SMEPS-TRANSMIT-000308 | NA | Trade Partner | SME - IFA Sample submissions | 1 | 0 | 0 | NA | APPROVED | 2026-06-15 | WF-006026 | NA | 2026-06-24 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-15 | PARR-TRANSMIT-000192 | NA | Trade Partner | Re: P2680 - NDC M3 Stage 4 - Fuel - FUNCTIONAL DESCRIPTION | 0 | 1 | 0 | 0 | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-014639 no action required |  | 2026-06-15 | KPTG-IntCorr-014638 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-15 | Auspan-TRANSMIT-000386 | NA | Trade Partner | Precast shop drawings for approval. Level 4 | 25 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 1240 | 2026-06-22 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-002860 | Closed | 25 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-15 | HDRAus-TRANSMIT-000510 | NA | Consultant | M3 Stage 4 - Document upload - PDF Locked drawing manual upload (12-06-26) | 0 | 1 | 0 | NA | APPROVED | 2026-06-15 | NA | 3543 | 2026-06-25 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-018889 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-15 | SMEPS-TRANSMIT-000309 | NA | Trade Partner | Re: SME - IFA Sample submissions | 0 | 3 | 0 | NA | REJECTED | [5 empty] | due to incorrect title |  | 2026-06-15 | KPTG-RTRFI-004738 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-15 | D&E-TRANSMIT-000827 | NA | Trade Partner | NXM3S4 - Level 1 - Mechanical Duct Layout - Zone 9 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For Distribution |  | 2026-06-15 | KPTG-TRANSMIT-018631 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-15 | ZLH P/L-TRANSMIT-000002 | NA | Trade Partner | Re: Proposed Material - Design & Sample - ZLH | 0 | 12 | 0 | NA | REJECTED | [5 empty] | Issue with status, reason and document number inside the document. |  | 2026-06-15 | KPTG-SADV-000658 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-15 | Entire M-TRANSMIT-000067 | NA | Trade Partner | Mechanical Commissioning Plan Revision 3 | 0 | 1 | 0 | NA | APPROVED | 2026-06-15 | WF-000326 | NA | 2026-06-19 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-000968 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-05 | VAE-Grp-TRANSMIT-000097 | NA | Trade Partner | MECH - MCC DRAWINGS | 0 | 4 | 0 | NA | APPROVED |  | NA | NA |  |  | FC DOCUMENTS - Register Updated |  | 2026-01-05 | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-15 | SMEPS-IntCorr-000305 | NA | Trade Partner | MEL05C4 BU Temp Power Plan | 1 | 0 | 0 | NA | APPROVED | 2026-06-15 | WF - 000475 | NA | 2026-06-18 |  | Terminated | 2026-06-18 | 2026-06-18 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-15 | ZLH P/L-TRANSMIT-000003 | NA | Trade Partner | Re: Proposed Material - Design & Sample - ZLH | 0 | 5 | 0 | NA | REJECTED | [5 empty] | Issue with Reason, Document status and Document number inside the document. |  | 2026-06-15 | KPTG-SADV-000652 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-15 | Ardon-TRANSMIT-000044 | NA | Trade Partner | Stage 4 Door Hardware for Approval | 0 | 26 | 0 | NA | REJECTED | [5 empty] | documents number mismatch error |  |  | KPTG-TRANSMIT-018630 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-15 | VERTIV-TRANSMIT-000033 | NA | Trade Partner | NEXT DC GE01 _ REPORT SUBMISSION _ LIGHTING SIMULATION REPORT (FOA-1) | 0 | 1 | 0 | NA | APPROVED | 2026-06-15 | WF-000205 | NA | 2026-06-24 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-000938 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-15 | RDSBIM-TRANSMIT-000002 | NA | Trade Partner | 303COL ¦ BASEMENT 1 DDA EOT LAYOUT & ELEVATIONS ¦ IFR | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status mismatch |  | 2026-06-15 | KPTG-DA-000354 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-15 | RDSBIM-TRANSMIT-000003 | NA | Trade Partner | 303COL ¦ BASEMENT 2 CPP ¦ IFR | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status mismatch |  | 2026-06-15 | KPTG-DA-000355 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-15 | VERTIV-TRANSMIT-000034 | NA | Trade Partner | NEXT DC GE 01 _ MATERIAL SUBMISSION _ PAINT SYSTEM (FOA-1) | 0 | 1 | 0 | NA | APPROVED | 2026-06-15 | WF-000206 | NA | 2026-06-24 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-000882 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-15 | WAM-TRANSMIT-000801 | NA | Consultant | WAM ARCH - A16.021 update - KPTG-RFI-001111. | 1 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 773 | 2026-06-17 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-002329 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-15 | Entire M-TRANSMIT-000068 | NA | Trade Partner | Request for IFC Drawings Incorporating AE Comments | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Revision of one documentwere found wrong, requested to resubmit:KPTG-IntCorr-000574 |  | 2026-06-15 | KPTG-IntCorr-000574 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-15 | VERTIV-TRANSMIT-000035 | NA | Trade Partner | NEXT DC GE 01 _ MATERIAL SUBMISSION _ SRC & EARTHING (FOA-1) | 0 | 2 | 0 | NA | APPROVED | 2026-06-15 | WF-000207 | NA | 2026-06-24 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-001744 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-01 | Tradetec-TRANSMIT-000276 | NA | Trade Partner | Penstock Valve - Tech Data - Stage 2 | 0 | 1 | 0 | NA | APPROVED | 2025-12-01 | WF-003451 | NA | 2025-12-12 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-05 | VAE-Grp-TRANSMIT-000098 | NA | Trade Partner | MECH COMMISSIONING PLAN | 0 | 1 | 0 | Further Clarification required - KPTG-IntCorr-000825 | APPROVED |  | NA | NA |  |  | Retransmitted VAE-trn 115 |  | 2026-01-05 | VAE-Grp-TRANSMIT-000115 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-15 | VERTIV-TRANSMIT-000036 | NA | Trade Partner | NEXT DC GE 01 _ MATERIAL SUBMISSION _ INTERNAL LIGHT & BATTERY CONTROL PANEL (FOA-1) | 0 | 1 | 0 | NA | APPROVED | 2026-06-15 | WF-000208 | NA | 2026-06-24 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-000944 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-15 | Appselec-TRANSMIT-000122 | NA | Trade Partner | WESCO BILL OF MATERIALS (ZTN NETWORK) - COLO4 & COLO5 - Issued For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-15 | WF-000327 | NA | 2026-06-19 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-000971 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-15 | D&E-TRANSMIT-000828 | NA | Trade Partner | NXM3S4 - Roof - Mech Elec Layout Zones - Issued For Approval | 5 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 3548 | 2026-06-19 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-020387 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-15 | Appselec-TRANSMIT-000123 | NA | Trade Partner | AHU Isolator Tech Data | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected: Discipline code of document is found wrong, requested to resubmit:KPTG-IntCorr-000575 |  | 2026-06-15 | KPTG-IntCorr-000575 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-15 | WAM-TRANSMIT-000802 | NA | Consultant | WAM ARCH - A16.052 update - KPTG-RFI-001101 | 1 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 775 | 2026-06-17 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-002313 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-06-15 | WPD-TRANSMIT-000090 | NA | Trade Partner | Hydraulic Services - B08 - As Built | 1 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 415 | 2026-06-24 |  |  | 2026-07-23 | 2026-07-23 | DRAFT-010431 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-15 | Auspan-TRANSMIT-000387 | NA | Trade Partner | Precast shop drawings for approval. Level 5 | 48 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 1242 | 2026-06-22 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-002994 | Closed | 48 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-15 | Entire M-TRANSMIT-000029 | NA | Trade Partner | VRF Airconditioning FOA-2 | 0 | 1 | 0 | NA | APPROVED | 2026-06-15 | WF-000209 | NA | 2026-06-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-15 | ACG-TRANSMIT-000095 | NA | Trade Partner | Re: M3 Stage 2 Camera FOV Register | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document number. |  | 2026-06-15 | KPTG-RTRFI-004737 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-15 | Civilex-TRANSMIT-000270 | NA | Trade Partner | Stage 1 Swale Restoration Landscape Plan Revision F | 1 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 4294 | 2026-06-24 |  | Terminated as advised by Charlie Johnstone for submitting the updated document. | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-019974 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-05 | SKS Tech-TRANSMIT-000119 | NA | Trade Partner | TELECOMMUNICATIONS SUBMITTAL | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Rejected - |  | 2026-01-05 | KPTG-IntCorr-000826 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-15 | Stowe-A-TRANSMIT-000608 | NA | Trade Partner | Re: STOWE - DRAWING SUBMISSION - As-built | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Reject due to difference in revision date |  | 2026-06-15 | KPTG-SADV-005901 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-15 | Stowe-A-TRANSMIT-000609 | NA | Trade Partner | Re: STOWE - DRAWING SUBMISSION - Communication Device Layout | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Reject due to difference in revision date |  | 2026-06-15 | KPTG-SADV-005902 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-15 | Ardon-TRANSMIT-000046 | NA | Trade Partner | Stage 4 Chiller Door Room Sets - Remaining Doors | 3 | 0 | 0 | NA | REJECTED | [5 empty] | document number is mismatch in the Aconex register |  | 2026-06-15 | KPTG-IntCorr-014651 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-15 | Stowe-A-TRANSMIT-000610 | NA | Trade Partner | Re: STOWE - DRAWING SUBMISSION - Communication Device Layout | 5 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due to status difference |  | 2026-06-15 | KPTG-SADV-005903 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-15 | ACG-TRANSMIT-000096 | NA | Trade Partner | M3 Stage 2 Camera FOV Register | 0 | 1 | 0 | NA | APPROVED | 2026-06-15 | WF-006031 | NA | 2026-06-24 |  | workflow against the document is now terminated by Henry |  | 2026-08-05 | KPTG-TRANSMIT-020376 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-15 | Auspan-TRANSMIT-000385 | NA | Trade Partner | Precast dowel layout zones 3, 4, 5 level 1 for approval | 2 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 1245 | 2026-06-22 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-002613 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-15 | Ardon-TRANSMIT-000045 | NA | Trade Partner | Stage 4 Door Hardware for Approval | 0 | 4 | 0 | NA | APPROVED | 2026-06-15 | WF-006033 | NA | 2026-06-19 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-019004 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-29 | Baigents-TRANSMIT-000209 | NA | Trade Partner | LVL 5 Void Handrail | 0 | 2 | 0 | NA | APPROVED | 2026-06-03 | WF-001100 | NA | 2026-06-15 |  | Incoming processed by luke | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-003919 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-15 | StantecA-TRANSMIT-000302 | NA | Consultant | Hydraulic Services Reg 126 | 1 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - No review, register updated and distributed-KPTG-TRANSMIT-002259 |  | 2026-06-15 | KPTG-TRANSMIT-002259 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-01 | Baigents-TRANSMIT-000210 | NA | Trade Partner | Handrail & Balustrade FOA-2 | 0 | 4 | 0 | NA | APPROVED | 2026-06-03 | WF-001099 | NA | 2026-06-05 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-003923 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-05 | SKS Tech-TRANSMIT-000120 | NA | Trade Partner | TELECOMMUNICATIONS SUBMITTAL | 0 | 15 | 0 | NA | APPROVED |  | NA | NA |  |  | FC DOCUMENTS - Register Updated |  | 2026-01-05 | NA | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-15 | ASV-TRANSMIT-000182 | NA | Trade Partner | Re: Stage 2 - Hydraulic As-built Drawings - Drainage | 5 | 0 | 0 | NA | REJECTED | [5 empty] | documents are already under review |  | 2026-06-15 | KPTG-SADV-005916 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-15 | SMEPS-TRANSMIT-000006 | NA | Trade Partner | Re: Shop Drawings: Communications | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with title. |  | 2026-06-15 | KPTG-SADV-000654 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-15 | SMEPS-TRANSMIT-000007 | NA | Trade Partner | Re: Shop Drawing submission: Electrical | 11 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 274 | 2026-06-19 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001059 | Closed | 11 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-15 | Entire M-TRANSMIT-000030 | NA | Trade Partner | VSDs - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-15 | WF-000211 | NA | 2026-06-24 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000937 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-15 | HDRAus-TRANSMIT-000511 | NA | Consultant | Concrete Profile Plan C1 - L1 Slab Penetration | 1 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 3550 | 2026-06-19 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-018888 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-15 | Metzone-TRANSMIT-000028 | NA | Trade Partner | Ground and L1 Steel drawings IFC | 32 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-SADV-004503 - DOCUMENT NUMBER,STATUS,ALIGNMENT INCORRECT | 2026-06-15 | 2026-06-15 | KPTG-SADV-004503 | Closed | 32 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-15 | KPTG-TRANSMIT-002541 | NA | Trade Partner | Signage Shopdrawings | 0 | 1 | 0 | NA | APPROVED | 2026-06-15 | WF-000792 | NA | 2026-06-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-15 | NXT-TRANSMIT-001617 | NA | Trade Partner | NXT-TRANSMIT-001617 | 0 | 1 | 0 | NA | APPROVED | 2026-06-15 | WF-006035 | NA | 2026-07-01 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-019554 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-15 | Airpor2-TRANSMIT-000001 | NA | Trade Partner | Roller shutter tech data | 0 | 4 | 0 | NA | REJECTED | [5 empty] | Issue with document number, title, revision number, no cover sheet etc. |  | 2026-06-15 | KPTG-SADV-000659 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-15 | Airpor2-TRANSMIT-000002 | NA | Trade Partner | Roller Shutter shop drawings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document number, revision number, title, status etc. |  | 2026-06-15 | KPTG-TRANSMIT-000810 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-06 | VAE-Grp-TRANSMIT-000099 | NA | Trade Partner | MECH ELEC TRAY LAYOUT - L4 & L5 - DAY 1 | 4 | 0 | 0 | NA | APPROVED | 2026-01-06 | NA | 800 | 2026-01-12 |  |  | 2026-01-15 | 2026-01-15 | KPTG-TRANSMIT-002463 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-03 | Carr-TRANSMIT-000068 | NA | Consultant | Town Planning Update - Schedule of Changes and Development Summary | 0 | 1 | 0 | NA | APPROVED | 2026-06-03 | NA | 223 | 2026-06-09 |  | Review Voided as advised By Renee |  | 2026-08-05 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-15 | SMEPS-TRANSMIT-000051 | NA | Trade Partner | SINGLE/DUAL OUTPUT STRING LV SLDs & STAGE 10 and 11 DAY 1 LINE UP CABLE SCHEDULES {IFA A} | 5 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 1114 | 2026-06-19 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-004865 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-15 | PFP PL-TRANSMIT-000010 | NA | Trade Partner | Tech -Data Temp pump and tank | 0 | 2 | 0 | NA | APPROVED | 2026-06-15 | WF-000959 | NA | 2026-06-26 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-005253 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-15 | PFP PL-TRANSMIT-000009 | NA | Trade Partner | S9 GF DH 21 IFA | 1 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 1116 | 2026-06-19 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-004616 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-15 | AXIS-NSW-TRANSMIT-000013 | NA | Trade Partner | M2-HYD-AXS-TD-0000-0031 - Rainwater Outlets | 0 | 1 | 0 | NA | APPROVED | 2026-06-15 | WF-000947 | NA | 2026-06-24 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-005068 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-15 | Eneraque-TRANSMIT-000029 | NA | Trade Partner | CSMS Points list & Control Cable (LV) & 2H Fire Rating Certificate Submission | 0 | 2 | 0 | NA | APPROVED | 2026-06-15 | WF-000952 | NA | 2026-06-25 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-006393 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-15 | Nilsen3-TRANSMIT-000039 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 6 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 1121 | 2026-06-22 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-004869 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-15 | Nilsen3-TRANSMIT-000039 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 1122 | 2026-06-22 |  |  | 2026-07-03 | 2026-07-03 | Nilsen3-TRANSMIT-000039 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-15 | Nilsen3-TRANSMIT-000043 | NA | Trade Partner | Nilsen Sample submissions #5 | 0 | 12 | 0 | NA | APPROVED | 2026-06-15 | WF-000957 | NA | 2026-06-26 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-005088 | Closed | 12 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-07 | VAE-Grp-TRANSMIT-000100 | NA | Trade Partner | Mechanical Services - HVAC LAYOUT & BUILDERS WORKS - LOWER GROUND LEVEL - DAY 1 | 3 | 0 | 0 | NA | APPROVED | 2026-01-07 | NA | 802 | 2026-01-09 |  |  | 2026-01-15 | 2026-01-15 | KPTG-TRANSMIT-002467 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-15 | ASV-TRANSMIT-000066 | NA | Trade Partner | Hydraulic Shop Drawings for Construction | 2 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 1129 | 2026-06-22 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-005177 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-15 | Auspan-TRANSMIT-000384 | NA | Trade Partner | Update IFCed precast shop drawings. | 11 | 0 | 0 | KPTG-IntCorr-000701 | APPROVED |  | NA | NA |  |  | IFC - Waiting for KIM approval. KPTG-IntCorr-000701 5 are not OK to proceed; to be resubmitted DRAFT-008718. 6 are ok to proceed IFC. ( Register updated and distributed KPTG-TRANSMIT-002399) |  | 2026-06-23 | KPTG-TRANSMIT-002399) | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-15 | Auspan-TRANSMIT-000380: | NA | Trade Partner | Re: Precast shop drawings for construction. Level 3 | 2 | 0 | 0 | KPTG-IntCorr-000702 | REJECTED |  | NA | NA |  |  | IFC - Waiting for KIM approval. KPTG-IntCorr-000702 Rejected due to incorrect attachment |  | 2026-06-17 | DRAFT-008498 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-15 | ASV-TRANSMIT-000067 | NA | Trade Partner | External Tank Layout for Review | 1 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 1130 | 2026-06-22 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-005061 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-15 | M.2-TRANSMIT-000042 | NA | Trade Partner | Electrical Services typical apartment layouts | 50 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect drawing numbering format. DRAFT-008395 |  | 2026-06-15 | DRAFT-008395 | Closed | 50 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-15 | M.2-TRANSMIT-000043 | NA | Trade Partner | Electrical Services FTTP shop drawings | 25 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 1428 | 2026-06-24 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-002347 | Closed | 25 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-15 | Auspan-TRANSMIT-000388 | NA | Trade Partner | : Update 1P1007 for construction | 1 | 0 | 0 | KPTG-IntCorr-000703 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Approval KPTG-IntCorr-000703 - Kim sent to the Trade Partner |  | 2026-06-19 | KPTG-TRANSMIT-002295 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-15 | Auspan-TRANSMIT-000389 | NA | Trade Partner | Precast shop drawings for construction. Level 1. 1P5009 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC- Register and distribute -KPTG-TRANSMIT-002265 |  | 2026-06-15 | KPTG-TRANSMIT-002265 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-15 | KPTG-TRANSMIT-001114: | NA | Trade Partner | Wet Fire - Tank & Pumproom - Specials | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to drawing number is not correct. KPTG-IntCorr-000713 |  | 2026-06-15 | KPTG-IntCorr-000713 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-15 | Baigents-TRANSMIT-000005 | NA | Trade Partner | Block 1 - LG/G Precast Panels - IFA | 74 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 200 | 2026-06-22 |  | Voided-Requested by Zoe for split by document |  | 2026-06-17 | NA | Closed | 74 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-07 | PARR-TRANSMIT-000027 | NA | Trade Partner | Fuel Services - BULK FUEL SCHEMATIC | 1 | 0 | 0 | NA | APPROVED | 2026-01-07 | NA | 804 | 2026-01-09 |  |  | 2026-01-13 | 2026-01-13 | KPTG-TRANSMIT-002394 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-15 | Civilex-TRANSMIT-000008 | NA | Trade Partner | Updated Stage 6 Foundation/Piling Design | 0 | 8 | 0 | NA | REJECTED |  | NA | NA |  |  | Wrongly uploaded |  | 2026-06-15 | KPTG-SADV-000234 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-15 | Civilex-TRANSMIT-000009 | NA | Trade Partner | Sample Submission Concrete Mix Design (Piling) | 0 | 1 | 0 | NA | APPROVED | 2026-06-15 | NA | 208 | 2026-06-23 |  |  | 2026-06-19 | 2026-06-22 | KPTG-TRANSMIT-000263 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-15 | PTA-TRANSMIT-000007 | NA | Consultant | Revised North elevation precast panel joint - For Coordination | 1 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 206 | 2026-06-23 |  |  | 2026-06-18 | 2026-06-19 | KPTG-TRANSMIT-000249 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-15 | ACCCA-TRANSMIT-000005 | NA | Trade Partner | Electrical Pit Approval | 12 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 204 | 2026-06-23 |  | Voided requested by Muskan sharma |  | 2026-07-06 | NA | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-15 | RDSBIM-TRANSMIT-000146 | NA | Trade Partner | MLCSPR ¦ STAGE 2 ¦ CARPARK NORTH ¦ FOR SUBMISSION | 8 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 316 | 2026-06-18 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-002994 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-16 | VOGUE-TRANSMIT-000019 | NA | Trade Partner | CONCRETE SAMPLE RESUBMISSION | 0 | 4 | 0 |  | APPROVED | 2026-06-16 | WF - 001047 | NA | 2026-06-19 |  | NA | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-003078 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-16 | Appselec-TRANSMIT-000124 | NA | Trade Partner | AHU Isolator Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF-000328 | NA | 2026-06-22 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-000927 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-16 | Appselec-TRANSMIT-000120 | NA | Trade Partner | Wesco BOM (Phones) & AFL BOM (ZTN) - Issued For Construction | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Rejeted: wrong Revision , requested to resubmit-KPTG-IntCorr-000585 |  | 2026-06-16 | KPTG-IntCorr-000585 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-16 | Appselec-TRANSMIT-000125 | NA | Trade Partner | Tech Data No Longer In Use | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Tech data no longer in Use: Updated document register& Transmitted to all:KPTG-TRANSMIT-000899 |  | 2026-06-16 | KPTG-TRANSMIT-000899 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-16 | Auspan-TRANSMIT-000390 | NA | Trade Partner | Re: Precast shop drawings for approval. Level 2 | 2 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 1251 | 2026-06-23 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-002616 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-07 | SKS Tech-TRANSMIT-000121 | NA | Trade Partner | for construction submittals - electrical | 0 | 15 | 0 | NA | APPROVED |  | NA | NA |  |  | FC DOCUMENTS - Register Updated |  | 2026-01-07 | NA | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-16 | SMEPS-SUBADVICE-000249 | NA | Trade Partner | MEL05C4 Electrical Labelling Schedule. | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF - 000477 | NA | 2026-06-22 |  | NA | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-001030 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-16 | RDSBIM-TRANSMIT-000070 | NA | Trade Partner | GREYSTAR LEVEL 02 CONCRETE PROFILE PLAN | 6 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 1253 | 2026-06-23 |  | Review Void as advised by Project DM. Updated drawings are coming. | 2026-06-25 | 2026-06-25 | NA | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-16 | Altaire-TRANSMIT-000012 | NA | Trade Partner | MEL05C4 - Fire Cx Plan | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF - 000478 | NA | 2026-06-18 |  | NA | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-001011 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-16 | SES AU-TRANSMIT-000059 | NA | Trade Partner | AUTO TRANSFER SWITCH - PDUMH32HVATNET | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF-000329 | NA | 2026-06-22 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-000924 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-16 | Ardon-TRANSMIT-000047 | NA | Trade Partner | Re: Stage 4 Chiller Door Room Sets - Remaining Doors | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Missing files |  | 2026-06-16 | KPTG-RFI-008417 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-16 | VERTIV-TRANSMIT-000037 | NA | Trade Partner | NEXT DC GE 01 _ MATERIAL SUBMISSION _ BUS DUCT (FOA-1) | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF-000212 | NA | 2026-06-25 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-000890 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-16 | SES AU-TRANSMIT-000060 | NA | Trade Partner | MEL11‑SESAU‑Z‑TDS‑55‑0-AUTO TRANSFER SWITCH- NO LONGER IN USE | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Tech data no longer in Use: Updated document register& Transmitted to all:KPTG-TRANSMIT-000901 |  | 2026-06-16 | KPTG-TRANSMIT-000901 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-16 | Auspan-TRANSMIT-000392 | NA | Trade Partner | Resubmit precast shop drawings for approval. Level 2. | 3 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 1255 | 2026-06-23 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-002566 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-16 | SES AU-TRANSMIT-000061 | NA | Trade Partner | SECURITY - LEVEL 1 COLO 5 FLOOR PLAN Rev 4 | 1 | 0 | 0 | NA | APPROVED | 2026-06-16 | WF-000330 | NA | 2026-06-18 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-000945 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-16 | ZLH P/L-TRANSMIT-000004 | NA | Trade Partner | Re: Proposed Material - Design & Sample - ZLH | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF-000213 | NA | 2026-06-25 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-000831 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-08 | Entire M-TRANSMIT-000026 | NA | Trade Partner | Fire Matrix Rev B Issued for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-01-08 | WF-003716 |  | 2026-01-21 |  |  |  | 2026-01-15 | KPTG-TRANSMIT-011456 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-16 | SMEPS-TRANSMIT-000008 | NA | Trade Partner | Re: Shop Drawings: Communications | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Partial submission of a rejected transmittal. |  | 2026-06-16 | KPTG-TRANSMIT-000811 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-16 | SES AU-TRANSMIT-000062 | NA | Trade Partner | LEVEL 1 CAMERA LAYOUT PLAN - COLO 5 - Rev 4 | 1 | 0 | 0 | NA | APPROVED | 2026-06-16 | WF-000331 | NA | 2026-06-18 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-000943 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-16 | INTRFRM-TRANSMIT-000078 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 16) | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF-000214 | NA | 2026-06-25 |  |  | 2026-06-17 | 2026-06-18 | KPTG-TRANSMIT-000822 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-16 | Entire M-TRANSMIT-000069 | NA | Trade Partner | Updated Mechanical Section drawings | 2 | 0 | 0 | NA | APPROVED | 2026-06-16 | WF-000332 | NA | 2026-06-19 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-000912 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-16 | D&E-TRANSMIT-000829 | NA | Trade Partner | NXM3S4 - Upper Roof CHW Pipe Layout Zones + Chiller Roof - Builders Works Layout Zones - Issued For Construction | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | FOR DISTRIBUTION |  | 2026-06-16 | KPTG-TRANSMIT-018659 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-16 | Entire M-TRANSMIT-000070 | NA | Trade Partner | Request for IFC Drawings Incorporating AE Comments | 0 | 3 | 0 | NA | APPROVED | 2026-06-16 | WF-000333 | NA | 2026-06-19 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-000909 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-15 | INGEN3D-TRANSMIT-000107 | NA | Trade Partner | Level 11-13 - Precast Columns - New IFA | 3 | 0 | 0 | NA | APPROVED | 2026-06-15 | WF-000723 | NA | 2026-06-17 |  |  | 2026-07-01 | 2026-07-01 | NA - Work flow Terminated as instructed | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-15 | SC-TRANSMIT-000004 | NA | Trade Partner | Tec Grout Technical datasheet | 0 | 1 | 0 | NA | APPROVED | 2026-06-15 | WF-000717 | NA | 2026-06-17 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-002497 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-15 | INGEN3D-TRANSMIT-000106 | NA | Trade Partner | Level 16-18 - Precast Columns - IFA | 35 | 0 | 0 | NA | APPROVED | 2026-06-15 | WF-000722 | NA | 2026-07-02 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-002715 | Closed | 35 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-15 | G&CHyd-TRANSMIT-000004 | NA | Trade Partner | HYD Tech Data | 0 | 17 | 0 | NA | REJECTED | [5 empty] | rejected : QA ERROR IN REVISION AND DOC.NO FIELDS |  | 2026-06-15 | KPTG-TRANSMIT-002299 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-08 | Entire M-TRANSMIT-000028 | NA | Trade Partner | Mechanical Switchboard Drawings Issued for Approval | 2 | 0 | 0 | NA | APPROVED | 2026-01-08 | WF-003717 |  | 2026-01-26 |  |  |  | 2026-01-15 | KPTG-TRANSMIT-011460 / KPTG-TRANSMIT-011461 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-15 | G&CHyd-TRANSMIT-000005 | NA | Trade Partner | HYD Tech Data | 0 | 21 | 0 | NA | APPROVED | 2026-06-15 | WF-000721 | NA | 2026-06-23 |  | Again submitted for architectural review | 2026-06-25 | 2026-06-25 | WF-000808 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-16 | Entire M-TRANSMIT-000071 | NA | Trade Partner | Waffle Pad Technical Data Rev 1 IFC | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF-000334 | NA | 2026-06-19 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-000906 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-16 | SMEPS-TRANSMIT-000009 | NA | Trade Partner | Re: Shop Drawings: Communications | 3 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 276 | 2026-06-22 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-001162 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-16 | TTW-TRANSMIT-000187 | NA | Consultant | M3 Stage 2 Civil Drawings - Rain Garden Updates | 15 | 0 | 0 | NA | APPROVED | [5 empty] | SUPERSEDED BY TTW-TRANSMIT-000188 |  | 2026-06-16 | KPTG-TRANSMIT-018666 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-16 | Rinco-TRANSMIT-000007 | NA | Trade Partner | Structural Drawings - General notes, Precast Lids & Stair + REG126 - IFC | 5 | 0 | 0 | NA | APPROVED | 2026-06-16 | WF-006036 | NA | 2026-06-23 |  | as instructed by Finlay in KPTG-IntCorr-014664 , Workflow template changed |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-16 | ARCH-TRANSMIT-000160 | NA | Consultant | MLC - SPR - ISC - Precast Facade Elevation | 1 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 319 | 2026-06-19 |  |  | 2026-06-19 | 2026-06-19 | KPTG-SADV-004685 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-16 | Highbu-TRANSMIT-000153 | NA | Trade Partner | IFA water drawing | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Revision of this document is wrong:KPTG-SADV-004652 |  | 2026-06-16 | KPTG-SADV-004652 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-16 | L.E.S.-TRANSMIT-000012 | NA | Trade Partner | Power outlets and Switches | 5 | 0 | 0 | NA | APPROVED | 2026-06-16 | WF-000726 | NA | 2026-06-19 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-002572 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-16 | D&E-TRANSMIT-000831 | NA | Trade Partner | NXM3S4 - Roof Level - Chiller Room 2 Layout - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 3553 | 2026-06-20 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-019754 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-16 | TTW-TRANSMIT-000188 | NA | Consultant | M3 Stage 2 Civil Drawings - Rain Garden Updates | 15 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 4296 | 2026-06-18 |  | Terminated as directed by Charlie for submitting the updated document. | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-018694 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-08 | SMEPS-TRANSMIT-000131 | NA | Trade Partner | Stage 4 - Inground Site Plan Electrical Services (C06) | 1 | 0 | 0 | NA | APPROVED | 2026-01-08 | [6 empty] | 2026-01-16 | As per requested by Charlie - Terminated | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-16 | RDSBIM-TRANSMIT-000277 | NA | Trade Partner | NXM3S4 ¦ GROUND FLOOR ¦ C-G-054 ACC ¦ IFC¦ FOR SUBMISSION | 1 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 3555 | 2026-06-20 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-019458 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-16 | Ardon-TRANSMIT-000048 | NA | Trade Partner | Stage 4 Chiller Door Room Sets - Remaining Doors | 3 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 3557 | 2026-06-28 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-018979 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-24 | PMT Sec-TRANSMIT-000003 | SPARK-CRFI-KPG-000617 | Trade Partner | PMT Tech Data | 0 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-001011 | Closed | 28 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-16 | D&E-TRANSMIT-000832 | NA | Trade Partner | NXM3S4 - Ground - Mechanical Duct Layout - Zone 8 & IW Tank Room - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | FOR DISTRIBUTION |  | 2026-06-16 | KPTG-TRANSMIT-018671 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-16 | RDSBIM-TRANSMIT-000004 | NA | Trade Partner | 303COL ¦ BASEMENT 2 CPP ¦ IFR | 1 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 258 | 2026-06-22 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-000210 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-16 | RDSBIM-TRANSMIT-000005 | NA | Trade Partner | 303COL ¦ BASEMENT 1 DDA EOT LAYOUT & ELEVATIONS ¦ IFR | 1 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 259 | 2026-06-22 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-000294 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-16 | Entire M-TRANSMIT-000047 | NA | Trade Partner | DX Battery Room issued for approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF - 000479 | NA | 2026-06-22 |  | NA | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-001019 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-15 | Ardon-TRANSMIT-000044 | NA | Trade Partner | Stage 4 Door Hardware for Approval | 0 | 22 | 0 | NA | APPROVED | 2026-06-16 | WF-006043 | NA | 2026-06-20 |  | 14 documents still under review | 2026-06-24 | 2026-06-24 | ⁠KPTG-TRANSMIT-019020 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-16 | INTRFRM-TRANSMIT-000080 | NA | Trade Partner | Geelong Edge - Hydraulic Tech Data (Submission 4) | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF-000216 | NA | 2026-06-25 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-000873 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-16 | INTRFRM-TRANSMIT-000079 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 17) | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF-000217 | NA | 2026-06-25 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-000826 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-01 | Tradetec-TRANSMIT-000275 | NA | Trade Partner | Stage 2 - IFC Shop Drawing - LVP05, CP09, CP10 | 3 | 0 | 0 | NA | APPROVED | 2025-12-01 | NA | 3384 | 2025-12-02 |  |  | 2025-12-02 | 2025-12-02 | KPTG-TRANSMIT-010521 | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-08 | Entire M-TRANSMIT-000027 | NA | Trade Partner | HVSB Mechanical Drawings Issued for Construction | 5 | 0 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-16 | PARR-TRANSMIT-000193 | NA | Trade Partner | P2649 - KPG NDC M3 - Stage 2 - Fuel - DFS OMM | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF-006039 | NA | 2026-06-29 |  | Terminated as directed by William Duffield. | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-018875 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-06-16 | Nilsen3-TRANSMIT-000186 | NA | Trade Partner | Re: M3-HV-NIL-SA-S-0301-0057 Stage 3 Meter Panel Enclosure | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-06-16 | KPTG-RFI-008428 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-16 | D&E-TRANSMIT-000833 | NA | Trade Partner | Mechanical O&M Manual - Issued for information | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Error in status, Revision etc. |  | 2026-06-16 | KPTG-SADV-005937 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-03 | KPTG-WTRAN-002203 | NA | Trade Partner | Kattsafe Guardrail | 0 | 1 | 0 | NA | APPROVED | 2026-06-03 | WF-001098 | NA | 2026-06-08 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-003936 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-16 | Altaire-TRANSMIT-000110 | NA | Trade Partner | Next DC M3 S2 O&M SP5 & SP7 | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF-006044 | NA | 2026-06-29 |  | Terminated as advised by William Duffileld. | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-018876 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-06-16 | WPD-TRANSMIT-000092 | NA | Trade Partner | Re: M3 Stage-3 SCADA ROPs 3A & 3B | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-06-16 | DRAFT-010177 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-16 | WilsonPD-TRANSMIT-000202 | SPARK-CRFI-KPG-000618 | Trade Partner | Hydraulic Services - Roof Level - Drainage & Water Layouts | 2 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 317 | 2026-06-23 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-001315 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-16 | ASV-TRANSMIT-000183 | NA | Trade Partner | Hydraulic Sample - Waterless Trap | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF-006045 | NA | 2026-06-26 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-019292 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-16 | VIA Arch-TRANSMIT-000164 | NA | Consultant | Balustrade type updates to Arch Drawings | 16 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 1138 | 2026-06-23 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-003929 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-16 | Civilex-TRANSMIT-000010 | NA | Trade Partner | Updated Stage 6 Foundation/Piling Design Transmittal | 0 | 8 | 0 | NA | REJECTED | [5 empty] | wrong Naming convention |  | 2026-06-16 | KPTG-SADV-000266 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-22 | RDSBIM-TRANSMIT-000130 | NA | Trade Partner | LINDRUM ¦ BASEMENT B1 TO LEVEL 01 COREWALL CONCRETE PROFILE PLAN ELEVATIONS | 2 | 0 | 0 | NA | APPROVED | 2025-12-30 |  | 500 | 2026-01-06 |  |  | 2026-01-19 | 2026-01-19 | KPTG-SADV-002655 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-16 | Baigents-TRANSMIT-000006 | NA | Trade Partner | Block 01 - West Elevation - Ground level precast panels IFA | 18 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 210 | 2026-06-24 |  | void |  | 2026-06-05 | NA | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-16 | ARJAY-TRANSMIT-000016 | NA | Trade Partner | Arjay Sheds - Lunchroom Layout | 1 | 0 | 0 | NA | REJECTED | [5 empty] | submitted without title block |  | 2026-06-16 | KPTG-SADV-000265 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-16 | vdmcons-TRANSMIT-000139 | NA | Trade Partner | Fwd: ME25 1004: D121 511-537 Sydney Rd Coburg -Shop Drawings & 3D IFC Model - L03 East Pavilion Re-Design - Re-IFF - 2026-06-16 | 13 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Updated register only. |  | 2026-06-16 | KPTG-TRANSMIT-003059 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-16 | Altaire-TRANSMIT-000014 | NA | Trade Partner | MEL05 - Fire Matrix IFA | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF - 000481 | NA | 2026-06-22 |  | NA | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-001029 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-16 | INTERSIG-TRANSMIT-000004 | NA | Trade Partner | 26-004 Assemble Coburg - PROTOTYPES | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF - 001048 | NA | 2026-06-22 |  | NA | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-003064 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-16 | VIA Arch-TRANSMIT-000165 | NA | Consultant | M2 S9 S10 Finishes & Concrete Profile updates | 7 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 1140 | 2026-06-23 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-003963 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-16 | MAYFLD-TRANSMIT-000457 | NA | Trade Partner | 100222-000600: M3 Stage 2 - EG Room - Architectural As Built Drawings | 11 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with title inside the document for one of the drawings. (0709) |  | 2026-06-16 | KPTG-SADV-005938 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-16 | MAYFLD-TRANSMIT-000458 | NA | Trade Partner | 100222-000601: M3 Stage 2 - EI Room - Architectural As Built Drawings | 11 | 0 | 0 | NA | APPROVED | [5 empty] | As Built, only for updating in ACC, Aconex and distribution. |  | 2026-06-16 | KPTG-TRANSMIT-018698 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-16 | SMEPS-TRANSMIT-000010 | NA | Trade Partner | Techdata: Fire Sealing | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with document number and revision number. |  | 2026-06-16 | DRAFT-002784 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-16 | ETNInd-TRANSMIT-000023 | NA | Trade Partner | COLO4 UPS FAT Reports | 0 | 8 | 0 | NA | REJECTED | [5 empty] | Document status were found wrong, requested to resubmit:KPTG-IntCorr-000593 |  | 2026-06-16 | :KPTG-IntCorr-000593 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-22 | RDSBIM-TRANSMIT-000131 | NA | Trade Partner | LINDRUM ¦ LEVEL 2 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Duplication of drawings |  | 2026-01-06 | KPTG-IntCorr-000615 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-16 | MAYFLD-TRANSMIT-000459 | NA | Trade Partner | 100222-000602: M3 Stage 2 - EJ Room - Architectural As Built Drawings | 11 | 0 | 0 | NA | APPROVED | [5 empty] | As Builts, for updating in ACC and Aconex and for distribution. |  | 2026-06-16 | KPTG-TRANSMIT-018701 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-16 | MAYFLD-TRANSMIT-000460 | NA | Trade Partner | 100222-000603:M3 Stage 2 - EL Room - Architectural As Built Drawings | 11 | 0 | 0 | NA | APPROVED | [5 empty] | As Built, For updating in Aconex, ACC and for distribution only. |  | 2026-06-16 | KPTG-TRANSMIT-018705 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-16 | ZLH P/L-TRANSMIT-000005 | NA | Trade Partner | Re: Proposed Material - Design & Sample - ZLH | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF-000218 | NA | 2026-06-25 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-16 | KPTG-DA-007111 | NA | Trade Partner | Re: Post Tension Roof - Zone C1 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong document naming |  | 2026-06-16 | KPTG-TRANSMIT-018670 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-16 | PARR-TRANSMIT-000194 | NA | Trade Partner | Re: P2680 - NDC M3 Stage 4 - Fuel - BF RETIC LAYOUT/SECTIONS/BUILDERS WORKS PENETRATIONS L1 - C1 | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected for INVALIS STATUS IN REVISION HISTORY |  | 2026-06-16 | KPTG-RTRFI-004768 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-16 | ZIA-TRANSMIT-000103 | NA | Trade Partner | M3S4 Network Toplogy (FOA-3) | 3 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 3560 | 2026-06-16 |  | PLACED IN WORKFLOW As instructed by Damian in KPTG-IntCorr-016208, Workflow terminated |  | 2026-07-15 | KPTG-IntCorr-016208 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-16 | D&E-TRANSMIT-000834 | NA | Trade Partner | Re: NXM3S4 - Ground - Mechanical Duct Layout - Zone 6 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | [5 empty] | For Distribution |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-16 | PCForm-TRANSMIT-000183 | NA | Trade Partner | Re: Post Tension Roof - Zone C1 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due to incorrect document name |  | 2026-06-16 | KPTG-RFI-008426 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-16 | PCForm-TRANSMIT-000182 | NA | Trade Partner | Re: Post Tension Roof - Zone C1 | 1 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-06-16 | KPTG-TRANSMIT-018670 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-16 | PCForm-TRANSMIT-000184 | NA | Trade Partner | Re: Post Tension Roof | 1 | 0 | 0 | NA | APPROVED | 2026-06-16 | WF-006046 | NA | 2026-06-24 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-22 | RDSBIM-TRANSMIT-000132 | NA | Trade Partner | LINDRUM ¦ LEVEL 2 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-01-06 |  | 501 | 2026-01-09 |  |  | 2026-01-20 | 2026-01-20 | KPTG-SADV-002662 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-16 | Auspan-TRANSMIT-000391 | NA | Trade Partner | Re: Precast shop drawings for construction. Level 2. - 2P5084-1 | 1 | 0 | 0 | KPTG-IntCorr-000704 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kapitol advise - KPTG-IntCorr-000704 |  | 2026-06-17 | KPTG-TRANSMIT-002319 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-16 | Rinco-TRANSMIT-000055 | NA | Consultant | GF PT adjustment for congestion issue | 3 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 1257 | 2026-06-18 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-002364 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-16 | Rinco-TRANSMIT-000056 | NA | Consultant | GF additional top mesh | 4 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 1259 | 2026-06-18 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-002367 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-16 | Auspan-TRANSMIT-000393 | NA | Trade Partner | : Precast shop drawings for construction. Levels 1, 2. | 7 | 0 | 0 | KPTG-IntCorr-000705 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kapitol advise KPTG-IntCorr-000705 IFC - 6 Register updated and distributed KPTG-TRANSMIT-002396 1 rejected for resubmit IFA - DRAFT-008712 All OK to proceed IFC KPTG-TRANSMIT-002449 |  | 2026-06-23 | KPTG-TRANSMIT-002396, KPTG-TRANSMIT-002449 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-16 | M.2-TRANSMIT-000046 | NA | Trade Partner | Electrical Services Typical apartment shop drawings | 50 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 1265 | 2026-06-25 |  |  |  | 2026-06-26 | KPTG-TRANSMIT-002466 | Closed | 50 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-16 | Auspan-TRANSMIT-000395 | NA | Trade Partner | Re: RFI: Ship Lap Join to External Panels Confirmation. Update IFCed precast shop drawings. | 13 | 0 | 0 | KPTG-IntCorr-000711 | APPROVED |  | NA | NA |  |  | IFC - Waiting for confirmation - KPTG-IntCorr-000711 Rejected by Kapitol PC- DRAFT-008810 | 2026-06-24 | 2026-06-24 | DRAFT-008810 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-16 | Auspan-TRANSMIT-000396 | NA | Trade Partner | : Re: Zone 1 RFi 68 urgent. Update IFCed shop drawings | 4 | 0 | 0 | KPTG-IntCorr-000712 | APPROVED |  | NA | NA |  |  | IFC - Waiting for confirmation - KPTG-IntCorr-000712 IFC - Register updated and distributed KPTG-TRANSMIT-002404 (Two drawings updated, Two drawings returned) DRAFT-008742 |  | 2026-06-23 | KPTG-TRANSMIT-002404 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-16 | Rinco-TRANSMIT-000057 | NA | Consultant | PMJ detail update | 4 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 1263 | 2026-06-18 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-002478 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-18 | POTTSENG-TRANSMIT-000042 | NA | Trade Partner | GMAC HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONE 1 | 1 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 1261 | 2026-06-24 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-002356 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-16 | PROLMC-TRANSMIT-000038 | NA | Trade Partner | AS Built Transmittal | 17 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As Bulit, Updated to document register and transmitted to trade partners |  | 2026-06-16 | KPTG-TRANSMIT-002979 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-30 | RDSBIM-TRANSMIT-000133 | NA | Trade Partner | LINDRUM ¦ LEVEL 03 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-01-06 |  | 502 | 2026-01-09 |  |  | 2026-01-20 | 2026-01-20 | KPTG-SADV-002667 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-16 | IVS-TRANSMIT-000001 | NA | Trade Partner | Crane Base Footing - Issued for Construction | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Document Number is required correction: KPTG-SADV-004646 |  | 2026-06-16 | KPTG-SADV-004646 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-16 | Syfon1-TRANSMIT-000025 | NA | Trade Partner | Syfon Penetration Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 321 | 2026-06-30 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-003113 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-16 | fjc-TRANSMIT-000155 | NA | Consultant | Drawing Updates | 11 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-SADV-004512 - The document number and revision are different inside and outside the document. | 2026-06-16 | 2026-06-16 | KPTG-SADV-004512 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-16 | fjc-TRANSMIT-000156 | NA | Consultant | Drawing Updates | 11 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 668 | 2026-06-22 |  |  | 2026-06-16 | 2026-06-16 | KPTG-SADV-004530 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-17 | Metzone-TRANSMIT-000030 | NA | Trade Partner | Ground and L1 Steel drawings IFC | 32 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004535 - The document number is incorrect. | 2026-06-17 | 2026-06-17 | KPTG-SADV-004535 | Closed | 32 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-16 | SYNACC-TRANSMIT-000005 | NA | Trade Partner | Transmittal - Facade Access Drawings - P-01 | 3 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-SADV-004529 - The document number is incorrect, and the revision numbers inside and outside the document do not match. | 2026-06-16 | 2026-06-16 | KPTG-SADV-004529 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-16 | crossfir-TRANSMIT-000017 | NA | Trade Partner | Wet Fire - Penetrations Level 01 to 03, IFC | 3 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 560 | 2026-06-24 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-001242 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-16 | crossfir-TRANSMIT-000019 | NA | Trade Partner | Wet Fire - Pumproom and Tank - Specials | 2 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 562 | 2026-06-24 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-001192 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-16 | DLTS-TRANSMIT-000024 | NA | Trade Partner | S9-Upper Gantry-Re-IFA Issue | 29 | 0 | 0 | NA | APPROVED | 2026-06-16 | WF-000962 | NA | 2026-06-18 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-004322 | Closed | 29 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-16 | DLTS-TRANSMIT-000026 | NA | Trade Partner | S9-GF Stairs-IFA Issue-16062026 | 28 | 0 | 0 | NA | APPROVED | 2026-06-16 | WF-000965 | NA | 2026-06-25 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-005200 | Closed | 28 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-18 | D&E-TRANSMIT-000319 | NA | Trade Partner | Flushing Procedure - Issued for Review | 0 | 1 | 0 | NA | APPROVED | 2025-12-18 | WF-003661 | NA | [6 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-16 | WilsonPD-TRANSMIT-000055 | NA | Trade Partner | TRENCH GRATE | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF-000963 | NA | 2026-06-19 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-004411 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-16 | SME Review Stage 9 Door Schedule | NA | Consultant | Stage 9 Door Schedule | 5 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 1134 | 2026-06-26 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-16 | SME Review Stage 10 Door Schedule | NA | Consultant | SME Review Stage 10 Door Schedule | 5 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 1135 | 2026-07-10 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-16 | SME Review Stage 11 Door Schedule | NA | Consultant | SME Review Stage 11 Door Schedule | 5 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 1136 | 2026-07-03 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-16 | DCN-TRANSMIT-000014 | NA | Trade Partner | Link Bridge - Cladding Rev 3 | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF-000964 | NA | 2026-06-19 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-005315 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-16 | SMEPS-TRANSMIT-000048 | NA | Trade Partner | Subcircuit Cabling Submission | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF-000966 | NA | 2026-06-29 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-005089 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-21 | Nilsen3-TRANSMIT-000117 | NA | Trade Partner | Fwd: OVERALL EARTHING SCHEMATIC and Energisation | 1 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 3565 | 2026-06-23 |  | Resubmitted for review as requested by Damian | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-019934 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-17 | SKS Tech-TRANSMIT-000164 | NA | Trade Partner | M3-ELC-SKS-SA-C-4000-0031 Fire Rating Material IFC | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect Reference number |  | 2026-06-17 | KPTG-IntCorr-014739 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-17 | SKS Tech-TRANSMIT-000165 | NA | Trade Partner | Fire Rating Material | 0 | 1 | 0 | NA | APPROVED | 2026-06-17 | WF-006048 | NA | 2026-07-13 |  | As instructed by Damian , this workflow terminated and distributed to all | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-018738 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-17 | RDSBIM-TRANSMIT-000071 | NA | Trade Partner | GREYSTAR¦ L06 CPP IFR GREYSTAR LEVEL 06 CONCRETE PROFILE PLAN | 6 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 1419 | 2026-06-24 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-18 | Stowe-A-TRANSMIT-000418 | NA | Trade Partner | STOWE - DATA HALL EARTHING LAYOUT - 18.12.2025 | 7 | 0 | 0 | NA | APPROVED | 2025-12-18 | NA | 3535 |  |  |  | 2026-01-29 | 2026-01-29 | KPTG-TRANSMIT-012166 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-17 | KETE-TRANSMIT-000137 | NA | Trade Partner | Kete - L10 Updated Cast-in Channel and Concrete Profile | 1 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 669 | 2026-06-24 |  |  | 2026-06-24 | 2026-06-24 | KPTG-SADV-004636 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-17 | RDSBIM-TRANSMIT-000012 | NA | Trade Partner | NXGE01 ¦ GROUND ¦ CPP ¦ IFC ¦ FOR SUBMISSION | 4 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 278 | 2026-06-24 |  | NA | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-000981 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-17 | RDSBIM-TRANSMIT-000278 | NA | Trade Partner | NXM3S4 ¦ GROUND FLOOR ¦ C-G-022 ACC ¦ IFC¦ FOR SUBMISSION | 1 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 3567 | 2026-06-22 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-019193 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-17 | D&E-TRANSMIT-000835 | NA | Trade Partner | NXM3S4 - Roof Level - Chiller Room 3 Layout - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 3569 | 2026-06-22 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-019758 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-17 | Auspan-TRANSMIT-000394 | NA | Trade Partner | Precast shop drawings for approval. Level 5 | 13 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 1271 | 2026-06-24 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-002806 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-17 | D&E-TRANSMIT-000836 | NA | Trade Partner | NXM3S4 - Ground - Mechanical Duct Layout - Zone 7 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-06-17 | KPTG-TRANSMIT-018715 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-17 | Entire M-TRANSMIT-000031 | NA | Trade Partner | VRF Airconditioning FOA-2 - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-17 | WF - 000220 | NA | 2026-06-23 |  | NA | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-000964 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-17 | INDS-TRANSMIT-000042 | NA | Trade Partner | Wet Fire, Schematic | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001078 - As per direction from Mark, we only update register and transmit to all parties. | 2026-06-17 | 2026-06-17 | KPTG-IntCorr-001078 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-17 | D&E-TRANSMIT-000837 | NA | Trade Partner | NXM3S4 - Roof Level - CHW Pipe Layout Zones - Issued For Construction | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For Distribution |  | 2026-06-17 | KPTG-TRANSMIT-018716 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-19 | WSP ANZ-TRANSMIT-000031 | NA | Consultant | WSP - Building Services Documents - Issue for Building Permit-COM | 4 | 0 | 0 | NA | APPROVED | 2026-01-08 |  | 160 | 2026-01-12 |  | As per KG advise, this review is not relevant as these drawings will get revised due to major design change |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-17 | ELLISAIR-TRANSMIT-000071 | NA | Trade Partner | Stage 9 Ground floor Zone 2 Duct & Pipe layout drawings issued for Approval (Date amended on drawing). | 2 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 1143 | 2026-06-24 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-004723 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-17 | Nilsen3-TRANSMIT-000150 | NA | Trade Partner | Cable Cleats | 0 | 0 | 0 | NA | APPROVED | 2026-06-17 | WF-006051 | NA | 2026-07-13 |  | During the previous WF review, the document was uploaded incorrectly by the reviewer. Therefore, the document has been superseded and resubmitted for review |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-17 | INTRFRM-TRANSMIT-000082 | NA | Trade Partner | Geelong Edge - Civil Tech Data (Submission 4) - INTRFRM-TRANSMIT-000082 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document no is incorrect. |  | 2026-06-17 | KPTG-TRANSMIT-000817 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-17 | KALLIBRE-TRANSMIT-000021 | NA | Trade Partner | Door Tech Data | 0 | 4 | 0 | NA | APPROVED | 2026-06-17 | WF-000336 | NA | 2026-06-24 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-000958 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-17 | KPTG-IntCorr-014750 | NA | Trade Partner | NXM3S4 - Level 1 - Plinth & Equipment Layout Zones - Issued For Construction | 15 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 3575 | 2026-06-29 |  | As instructed by Ellie, the transmittals D&E-TRANSMIT-000810 & D&E-TRANSMIT-000817 have been combined and submitted under this workflow | 2026-06-23 | 2026-06-23 | ⁠KPTG-TRANSMIT-018989,KPTG-TRANSMIT-018995 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-16 | PCForm-TRANSMIT-000232 | NA | Trade Partner | Level 2 - Revision D | 4 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 780 | 2026-06-25 |  |  | 2026-06-30 | 2026-07-01 | KPTG-TRANSMIT-002597 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-17 | WilsonPD-TRANSMIT-000081 | NA | Trade Partner | Stage 11 Ground Floor Water Supply | 1 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 1149 | 2026-06-24 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-005001 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-17 | ABB-TRANSMIT-000046 | NA | Trade Partner | Fwd: M3-C Stage 4/Ph1 - AU-10025007 - PDU Test Reports & ITPs | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | NXT-TRANSMIT-001624 For distribution |  | 2026-06-17 | KPTG-TRANSMIT-018727 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-06-17 | INSULPAK-TRANSMIT-000022 | NA | Trade Partner | Insulpak As Built Drawings | 13 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-06-17 | DRAFT-010192 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-19 | WSP ANZ-TRANSMIT-000031 | NA | Consultant | WSP - Building Services Documents - Issue for Building Permit-HYD | 97 | 0 | 0 | NA | APPROVED | 2026-01-08 |  | 163 | 2026-01-12 |  | As per KG advise, this review is not relevant as these drawings will get revised due to major design change |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-17 | Baigents-TRANSMIT-000005-Pour 1&2 | NA | Trade Partner | Block 1 - LG/G Precast Panels - IFA | 16 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 213 | 2026-06-25 |  | Actual submission Date 15-06-2026 | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-000287 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-17 | Baigents-TRANSMIT-000005-Pour 3&4 | NA | Trade Partner | Block 1 - LG/G Precast Panels - IFA | 14 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 214 | 2026-06-25 |  | Actual submission Date 15-06-2026 | 2026-06-30 | 2026-07-01 | KPTG-TRANSMIT-000392 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-17 | Baigents-TRANSMIT-000005 pour 5&6 | NA | Trade Partner | Block 1 - LG/G Precast Panels - IFA | 12 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 215 | 2026-06-25 |  | Actual submission Date 15-06-2026,Voided requested by Zoe |  | 2026-07-01 | NA | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-17 | SMEPS-TRANSMIT-000011 | NA | Trade Partner | Techdata: Fire Sealing | 0 | 1 | 0 | NA | APPROVED | 2026-06-17 | WF - 000223 | NA | 2026-06-23 |  | NA | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-000951 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-17 | ZLH P/L-TRANSMIT-000006 | NA | Trade Partner | Proposed Material - Design & Sample - ZLH | 0 | 1 | 0 | NA | APPROVED | 2026-06-17 | WF - 000224 | NA | 2026-06-23 |  | NA | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001380 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-06-17 | INSULPAK-TRANSMIT-000021 | NA | Trade Partner | Re: Insulpak As Built Drawings | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-06-17 | DRAFT-010193 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-06-17 | WPD-TRANSMIT-000092 | NA | Trade Partner | Fwd: Powerpack - O&M Manual Submission | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-06-17 | DRAFT-010194 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-17 | Entire M-TRANSMIT-000048 | NA | Trade Partner | Waffle Pad Technical Data Rev A IFA | 0 | 1 | 0 | NA | REJECTED | [5 empty] | TD rejected. |  | 2026-06-17 | KPTG-SADV-001654 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-17 | Appselec-TRANSMIT-000120 | NA | Trade Partner | Wesco BOM (Phones) & AFL BOM (ZTN) - Issued For Construction | 0 | 2 | 0 | NA | APPROVED | 2026-06-17 | WF-000335 | NA | 2026-06-18 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-000916 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-17 | 4DW-TRANSMIT-000047 | NA | Consultant | Structural Documentation: Link Bridge - Stage 04 to Stage 06 update | 1 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 212 | 2026-06-25 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-000422 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-19 | WSP ANZ-TRANSMIT-000031 |  | Consultant | WSP - Building Services Documents - Issue for Building Permit-VRT | 6 | 0 | 0 | NA | APPROVED | 2026-01-08 |  | 165 | 2026-01-12 |  | As per KG advise, this review is not relevant as these drawings will get revised due to major design change |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-17 | NXT-TRANSMIT-000410 | NA | Client | FIE Switch room Interface Matrix | 0 | 1 | 0 | KPTG-IntCorr-000188 | APPROVED |  | NA | NA |  |  | For information |  | 2026-06-22 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-17 | Appselec-TRANSMIT-000126 | NA | Trade Partner | MEL11C45 - Communications Shop Drawings - IFC | 23 | 0 | 0 | NA | APPROVED | 2026-06-17 | WF-000337 | NA | 2026-06-19 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-000931 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-17 | WAM-TRANSMIT-000803 | NA | Consultant | IFC_A12 CSP - Level 1 Updates | 2 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 784 | 2026-06-19 |  | VOID - RESISSUED VIA WAM-TRANSMIT-000806 | 2026-06-19 | 2026-06-19 | WAM-TRANSMIT-000806 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-17 | TTW-TRANSMIT-000189 | NA | Trade Partner | Re: M3 Stage 2 Civil Drawings - Rain Garden Updates | 17 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due incorrect revision number | 2026-06-17 | 2026-06-17 | KPTG-DA-007154 | Closed | 17 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-17 | Firesafe-TRANSMIT-000014 | NA | Trade Partner | revised Car Park Drawings IFA | 2 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 788 | 2026-06-25 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-002487 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-17 | Nilsen3-TRANSMIT-000188 | NA | Trade Partner | OVERALL HV SCHEMATIC Drawings updated | 1 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 3578 | 2026-07-01 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-020585 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-17 | Baigents-TRANSMIT-000006 | NA | Trade Partner | Block 1 Ground Precast Panels -Issued for Approval | 50 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 216 | 2026-06-25 |  | Actual submission date-16-06-2026Voided requested by zoe for spliting |  | 2026-06-24 | NA | Closed | 50 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-17 | D&E-TRANSMIT-000838 | NA | Trade Partner | Re: NXM3S4 - Ground - CHW Pipe Layout - Zone 7 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC DOCUMENT FOR DISTRIBUTION |  | 2026-06-17 | KPTG-IntCorr-014785 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-17 | WAM-TRANSMIT-000804 | NA | Consultant | A09 Overall Plans - Ground, Mezzanine, L1, L2, L3 & L11 - IFC Updates. | 6 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 790 | 2026-06-20 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-002430 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-17 | P & R-TRANSMIT-000090 | NA | Trade Partner | P&R O&M and AS-BUILTS 17/06 | 16 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Revision of As Built Drawing are incorrect, requested to resubmit: KPTG-SADV-004667 |  | 2026-06-17 | KPTG-SADV-004667 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-01 | CRSol-TRANSMIT-000061 | NA | Trade Partner | M3S2 DHB5 Issued for Construction | 11 | 0 | 0 | NA | APPROVED | 2025-12-01 | NA | 3382 | 2025-12-08 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-04 | CRSol-TRANSMIT-000041 | NA | Trade Partner | Ground Floor SMW Penetrations | 1 | 0 | 0 | NA | APPROVED | 2025-12-07 | NA | 703 | 2025-12-11 |  | Document bulk superseded to make correction in document number and status (Revise and Resubmit) | 2025-12-17 | 2026-01-05 | KPTG-TRANSMIT-002352 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-17 | COMAQU-TRANSMIT-000030 | NA | Trade Partner | As Built Drawings | 22 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 322 | 2026-06-22 |  |  | 2026-06-23 | 2026-06-23 | KPTG-SADV-004703 | Closed | 22 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-17 | INTRFRM-TRANSMIT-000083 | NA | Trade Partner | Geelong Edge - Civil Tech Data (Submission 4) - | 0 | 1 | 0 | NA | APPROVED | 2026-06-17 | WF - 000222 | NA | 2026-06-24 |  | NA | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-000834 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-17 | INTRFRM-TRANSMIT-000081 | NA | Trade Partner | Geelong Edge - Hydraulic Tech Data (Submission 5) | 0 | 1 | 0 | NA | APPROVED | 2026-06-17 | WF -000221 | NA | 2026-06-23 |  | NA | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-000869 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-17 | ZLH P/L-TRANSMIT-000007 | NA | Trade Partner | Proposed Material - Design & Sample - ZLH | 0 | 1 | 0 | NA | APPROVED | 2026-06-17 | WF - 000225 | NA | 2026-06-22 |  | Terminated by Christorpher Mutimer by mistake | 2026-06-30 | 2026-06-30 | KPTG-IntCorr-000262 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-17 | INTRFRM-TRANSMIT-000084 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 18) | 0 | 1 | 0 | NA | APPROVED | 2026-06-17 | WF - 000226 | NA | 2026-06-23 |  | NA | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-000841 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-16 | INGEN3D-TRANSMIT-000108 | NA | Trade Partner | I3D-389 District Living - Ground Floor - Precast Panels - IFA (16-06-2026) | 19 | 0 | 0 | NA | APPROVED | 2026-06-16 | WF-000724 | NA | 2026-06-23 |  |  | 2026-06-23 | 2026-06-16 | KPTG-TRANSMIT-002338 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-16 | INGEN3D-TRANSMIT-000109 | NA | Trade Partner | I3D-389 District Living - Level 9-11 - PC0397-1 - IFC (16-06-2026) | 1 | 0 | 0 | NA | APPROVED | 2026-06-16 | WF-000727 | NA | 2026-06-24 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-002479 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-16 | Civilex-TRANSMIT-000106 | NA | Trade Partner | Orange Geofab | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF-000725 | NA | 2026-06-18 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-17 | Baigents-TRANSMIT-000215 | NA | Trade Partner | L5 ramp steel for approval. | 3 | 0 | 0 | KPTG-TRANSMIT-003944 | APPROVED |  | NA | NA |  |  | No action confirmed by Luke - KPTG-IntCorr-001490 |  | 2026-06-18 | KPTG-IntCorr-001490 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-16 | PCForm-TRANSMIT-000231 | NA | Trade Partner | Fwd: Level 3 - reuploading drawings | 6 | 0 | 0 | NA | APPROVED | 2026-06-16 | NA | 779 | 2026-06-25 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-002558 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-19 | WSP ANZ-TRANSMIT-000031 | NA | Consultant | WSP - Building Services Documents - Issue for Building Permit-TEL | 58 | 0 | 0 | NA | APPROVED | 2026-01-08 |  | 167 | 2026-01-12 |  | As per KG advise, this review is not relevant as these drawings will get revised due to major design change |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-16 | Jangho-TRANSMIT-000166 | NA | Trade Partner | Re: Issues the Thermal Report of FT01 for approval | 1 | 0 | 0 | NA | APPROVED | 2026-06-16 | WF-000728 | NA | 2026-06-24 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-002566 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-17 | PCForm-TRANSMIT-000233 | NA | Trade Partner | Transfer slab 65mpa Partial pour mix for approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-17 | WF-000729 | NA | 2026-06-22 |  |  | 2026-06-29 | 2026-06-26 | KPTG-TRANSMIT-002514 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-17 | INGEN3D-TRANSMIT-000110 | NA | Trade Partner | I3D-389 District Living - Level 13-15 - PC0522-8 & PC0531-5 - New IFA (16-06-2026) | 2 | 0 | 0 | NA | APPROVED | 2026-06-17 | WF-000730 | NA | 2026-07-07 |  |  | 2026-07-01 | 2026-07-01 | NA - Work flow Terminated as instructed | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-17 | INGEN3D-TRANSMIT-000111 | NA | Trade Partner | I3D-389 District Living - Level 17-19 - Precast Columns - IFA (16-06-2026) | 44 | 0 | 0 | NA | APPROVED | 2026-06-17 | WF-000731 | NA | 2026-07-07 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-002701 | Closed | 44 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-17 | INGEN3D-TRANSMIT-000112 | NA | Trade Partner | I3D-389 District Living - Level 15-17 - PC0522-9 & PC0531-6 - New IFA (16-06-2026) | 2 | 0 | 0 | NA | APPROVED | 2026-06-17 | WF-000732 | NA | 2026-07-07 |  |  | 2026-07-01 | 2026-07-01 | NA - Work flow Terminated as instructed | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-10 | Jangho-TRANSMIT-000168 | NA | Trade Partner | 011_Podium Level 1~2 Cast in Channel Shop Drawing_Rev02 | 8 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 785 | 2026-06-25 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-17 | Nilsen3-TRANSMIT-000031 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 3 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 1145 | 2026-06-24 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-004510 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-17 | Nilsen3-TRANSMIT-000035 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 7 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 1146 | 2026-06-24 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-004597 | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-17 | DLTS-TRANSMIT-000027 | NA | Trade Partner | S10-L1 H Frames-IFA Issue | 35 | 0 | 0 | NA | APPROVED | 2026-06-17 | WF-000975 | NA | 2026-06-26 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-005190 | Closed | 35 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-17 | Auspan-TRANSMIT-000397 | NA | Trade Partner | Precast shop drawing 0G1083 issued for construction | 1 | 0 | 0 | KPTG-IntCorr-000723 | APPROVED |  | NA | NA |  |  | IFC - waiting for Kapitol Advise - KPTG-IntCorr-000723 Rejected - Kapitol PC returned to Auspan KPTG-SADV-003015 |  | 2026-06-19 | KPTG-SADV-003015 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-09 | OveArup-TRANSMIT-000150 | NA | Consultant | Stage 3 HV Interim Supply Drawings Update | 4 | 1 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-17 | Entire M-TRANSMIT-000049 | NA | Trade Partner | Waffle Pad Technical Data Rev B IFA | 0 | 1 | 0 | NA | APPROVED | 2026-06-17 | WF - 000483 | NA | 2026-06-26 |  | NA | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-001040 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-17 | PCForm-TRANSMIT-000075 | NA | Trade Partner | : IFC Stair Form Drawings | 36 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 1273 | 2026-06-25 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-002851 | Closed | 36 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-17 | POTTSENG-TRANSMIT-000020 | NA | Trade Partner | 671C: HYDRAULIC SERVICES - BASEMENT 1 - LEVEL 4 & LEVEL 5 - 20 CORE WALL - PENETRATION LAYOUT | 2 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 567 | 2026-06-24 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001269 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-17 | Jangho-TRANSMIT-000078 | NA | Trade Partner | L3~18 shop drawing Rev01 | 101 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 565 | 2026-06-24 |  | Review terminated as advised by Ben cox -Review complete KPTG-SADV-002946 |  | 2026-07-30 | KPTG-SADV-002946 | Closed | 101 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-17 | POTTSENG-TRANSMIT-000021 | NA | Trade Partner | 671C: HYDRAULIC SERVICES - BASEMENT 1 - PENETRATION LAYOUT | 2 | 0 | 0 | KPTG-IntCorr-000743 | APPROVED | 2026-06-17 | NA | NA |  |  | IFC- Waiting for advise from Tayla KPTG-IntCorr-000743 As advised No these do not need another review, Update register. |  | 2026-06-18 | NA | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-17 | B Smart-TRANSMIT-000084 | NA | Consultant | : Door Schedule A30.000[B] | 0 | 1 | 0 | NA | APPROVED | 2026-06-17 | WF-000495 | NA | 2026-06-19 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-17 | Carr-TRANSMIT-000017 | NA | Consultant | 80% DD Architectural Drawing Issue (Schedules FFE, FIN, FUR) | 0 | 3 | 0 | NA | APPROVED | 2026-06-17 | NA | 260 | 2026-06-24 |  | Actual received date 27-03-2026 | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000144 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-17 | DLTS-TRANSMIT-000028 | NA | Trade Partner | S9-North Eave Gutter-IFC Issue | 25 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Need to revise KPTG-SADV-005058 |  | 2026-06-17 | KPTG-SADV-005058 | Closed | 25 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-25 | Jangho-TRANSMIT-000110 | NA | Trade Partner | PODIUM SHOP DRAWING (1F~5F) -01 | 1 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 668 | 2026-06-05 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-002156 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-17 | WilsonPD-TRANSMIT-000080 | NA | Trade Partner | Drawings for Construction | 3 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-06-17 | KPTG-SADV-005049 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-18 | PARR-TRANSMIT-000106 | NA | Trade Partner | P2649 - KPG NDC M3 - Stage 2 - Fuel - BFS SCHEMATIC | 1 | 0 | 0 | NA | APPROVED | 2025-12-18 | NA | 3533 | 2025-12-25 |  |  | 2026-03-11 | 2026-03-12 | KPTG-TRANSMIT-014243 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-17 | ELLISAIR-TRANSMIT-000070 | NA | Trade Partner | Stage 9 Ground floor Zone 1 Duct layout drawings issued for Approval. | 2 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 1147 | 2026-06-24 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-004719 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-25 | Jangho-TRANSMIT-000110 | NA | Trade Partner | PODIUM SHOP DRAWING (1F~5F) -01 | 3 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 669 | 2026-06-08 |  |  | 2026-06-18 | 2026-06-19 | KPTG-TRANSMIT-002364 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-22 | Jangho-TRANSMIT-000108 | NA | Trade Partner | 008 _PODIUM SHOP DRAWING (1F~5F) -01 | 3 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 669 | 2026-06-08 |  |  | 2026-06-18 | 2026-06-19 | KPTG-TRANSMIT-002364 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-17 | Kone-VIC-TRANSMIT-000003 | NA | Trade Partner | Kone - VT Drawings | 49 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 791 | 2026-06-26 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-002594 | Closed | 49 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-17 | Firesafe-TRANSMIT-000013 | NA | Trade Partner | revised Car Park Drawings IFA | 2 | 0 | 0 | NA | REJECTED | [5 empty] | REPLACED BY Firesafe-TRANSMIT-000014 |  | 2026-06-17 | Firesafe-TRANSMIT-000014 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-17 | Jangho-TRANSMIT-000168 | NA | Trade Partner | Podium Level 1~2 Cast in Channel Shop Drawing_Rev02 | 8 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 785 | 2026-06-26 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-002511 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-17 | Jangho-TRANSMIT-000173 | NA | Trade Partner | Podium Level 1~2 Cast in Channel Shop Drawing_Rev02 | 1 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 785 | 2026-06-26 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-002511 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-17 | PCForm-TRANSMIT-000234 | NA | Trade Partner | 50mpa mix design - Transfer slab | 0 | 1 | 0 | NA | APPROVED | 2026-06-17 | WF-000742 | NA | 2026-06-26 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-003029 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-17 | OveArup-TRANSMIT-000040 | NA | Trade Partner | Certificate-of-Compliance-for-proposed-building-work (R126) - Electrical Early Works | 0 | 1 | 0 | NA | APPROVED | 2026-06-17 | WF-000741 | NA | 2026-06-26 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002936 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-17 | OveArup-TRANSMIT-000040 | NA | Trade Partner | Electrical Services Cover Sheet and Drawing List Early Works | 1 | 0 | 0 | NA | APPROVED | 2026-06-17 | NA | 793 | 2026-06-26 |  |  | 2026-06-21 | 2026-06-22 | KPTG-TRANSMIT-002412 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-18 | NXT-TRANSMIT-001154 | NA | Client | 000569-100222 NEXT DC M3 - FIRE SCHEMATICS - AS BUILT - EM; EJ & ED ROOM | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As Built |  | 2025-12-18 | KPTG-TRANSMIT-011087 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-17 | Arc Plas-TRANSMIT-000013 | NA | Trade Partner | INS05 & 06 - Insulation Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-06-17 | WF-000974 | NA | 2026-06-26 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-004973 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-17 | PROLMC-TRANSMIT-000002 | NA | Trade Partner | Box Gutter Shop Drawing IFA | 3 | 0 | 0 | NA | APPROVED | 2026-06-17 | WF-000973 | NA | 2026-06-22 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-004654 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-18 | KALLIBRE-TRANSMIT-000022 | NA | Trade Partner | Additional 7x Door Frames Shop Drawings IFA | 7 | 0 | 0 | NA | APPROVED | 2026-06-18 | WF-000338 | NA | 2026-06-24 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-000949 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-18 | SKS Tech-TRANSMIT-000167 | NA | Trade Partner | Re: Gripple channel nut tech data | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect Reference number |  | 2026-06-18 | KPTG-RFI-008470 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-17 | RDSBIM-TRANSMIT-000208 | NA | Trade Partner | LINDRUM ¦ CPP ¦ L-06_CPP ¦ IFC ¦ SUBMISSION | 1 | 0 | 0 | KPTG-IntCorr-001084 | APPROVED | 2026-06-18 | NA | 670 | 2026-06-23 |  | KPTG-IntCorr-001084 - Requested guidance, but no response received yet. KPTG-IntCorr-001092 - As per direction from ashlin RDS new drawing to be submitted. Hence we void the workflow #672 18-06-2026 | 2026-06-18 | 2026-06-18 | KPTG-IntCorr-001092 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-18 | Jangho-TRANSMIT-000174 | NA | Trade Partner | Extrusion color Dulux Electro Medium Bronze Kinetic - Flat | 0 | 1 | 0 | NA | APPROVED | 2026-06-18 | WF-000743 | NA | 2026-07-06 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-18 | SMEPS-TRANSMIT-000231 | NA | Trade Partner | MEL05C4 Elec Seismic Design | 23 | 0 | 0 | NA | APPROVED | 2026-06-18 | WF - 000484 | NA | 2026-06-25 |  | NA | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-001041 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-18 | ETNInd-TRANSMIT-000024 | NA | Trade Partner | MEL11-COLO4 UPS Pre-Shipment Reports | 0 | 8 | 0 | NA | APPROVED |  | NA | NA |  |  | As per the instruction, Just transmitted to MSFT Team: KPTG-TRANSMIT-000919 |  | 2026-06-18 | KPTG-TRANSMIT-000919 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-18 | PCForm-TRANSMIT-000235 | NA | Trade Partner | Updated Level 1 Rincovitch Drawings | 6 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 795 | 2026-06-26 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-002626 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-18 | RDSBIM-TRANSMIT-000209 | NA | Trade Partner | LINDRUM ¦ BLOCKWORK-ELEVATION ¦ MEZZANINE LEVEL ¦ IFR ¦ SUBMISSION | 1 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 671 | 2026-06-25 |  |  | 2026-06-30 | 2026-06-30 | KPTG-SADV-004714 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-09 | RDSBIM-TRANSMIT-000173 | NA | Trade Partner | NXM3S4 ¦ GROUND FLOOR-C-G-052 CLEANER FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-01-09 |  | 1838 | 2026-01-23 |  |  |  | 2026-01-20 | KPTG-TRANSMIT-011723 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-06-18 | INSULPAK-TRANSMIT-000024 | NA | Trade Partner | Re: HFF As Built Shop Drawings | 11 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect revision number |  | 2026-06-18 | DRAFT-010203 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-18 | 4DW-TRANSMIT-000048 | NA | Consultant | Structural Documentation: Block 1 - Precast walls issued with Construction updates | 3 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 218 | 2026-06-26 |  |  | 2026-07-22 | 2026-07-23 | KPTG-TRANSMIT-000680 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-06-18 | INSULPAK-TRANSMIT-000023 | NA | Trade Partner | Re: As Built Shop drawings | 8 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect revision number |  | 2026-06-18 | DRAFT-010204 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-18 | Lat-TRANSMIT-000011 | NA | Consultant | Landscape Issued For Tender Site Plan DWG (IFT-2) | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Cad file distribution |  | 2026-06-18 | KPTG-TRANSMIT-000235 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-18 | RDSBIM-TRANSMIT-000059 | NA | Trade Partner | MCC ¦ LEVEL 01 FINISHES ¦ DRYING ROOM ¦ IFA ¦ SUBMISSION | 1 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 318 | 2026-06-25 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-18 | KALLIBRE-TRANSMIT-000008 | NA | Trade Partner | Door Frame Shop Drawings IFA / IFC | 59 | 0 | 0 | NA | REJECTED | [5 empty] | Multiple status drawings and incorrect revision |  | 2026-06-18 | KPTG-TRANSMIT-001018 | Closed | 59 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-18 | SMEPS-TRANSMIT-000314 | NA | Trade Partner | Drawing Transmittal | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Revision not updated, already received the same revision previously |  | 2026-06-18 | KPTG-RFI-008477 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-06-18 | SMEPS-TRANSMIT-000310 | NA | Trade Partner | Fwd: 22kv Switchroom | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Registration updated – the coordinator will inform Andy if further action is required |  | 2026-06-18 | KPTG-TRANSMIT-018775 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-06-18 | KPTG-TRANSMIT-018770 | NA | Trade Partner | Building - Basement Containment Layout - Update for Review (IFC) | 1 | 0 | 0 | NA | APPROVED | 2026-06-18 | WF-006060 | NA | 2026-07-01 |  |  |  | 2026-06-19 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-18 | SMEPS-TRANSMIT-000315 | NA | Trade Partner | Drawing Transmittal | 1 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 3580 | 2026-06-27 |  |  |  | 2026-08-21 | KPTG-TRANSMIT-020815 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-09 | IVS-TRANSMIT-000307 | NA | Consultant | Stage 4 - Roof Zone C3 CJ update (Revised Construction Issue) | 4 | 0 | 0 | NA | APPROVED | 2026-01-09 |  | 1741 | 2026-01-13 |  |  |  | 2026-01-15 | KPTG-TRANSMIT-011485 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-18 | WilsonPD-TRANSMIT-000083 | NA | Trade Partner | Re: Drawings for Construction | 3 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 1151 | 2026-06-24 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-004814 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-18 | WilsonPD-TRANSMIT-000084 | NA | Trade Partner | S11 Level 2 slab penertrations | 1 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 1153 | 2026-06-25 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-005005 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-18 | D&E-TRANSMIT-000839 | NA | Trade Partner | NXM3S4 - Ground - Mechanical Duct Layout - Zone 7 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-06-18 | KPTG-TRANSMIT-018777 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-18 | EAEGROUP-TRANSMIT-000100 | NA | Trade Partner | Updated Shop Drawing Revision - Block C3 HI | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As instructed by Rohit, IFC drawing distributed to border team |  | 2026-06-18 | KPTG-TRANSMIT-018781 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-18 | Diadem-TRANSMIT-000026 | NA | Consultant | NEXTDC M3 Wayfinding Package | 89 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 4304 | 2026-06-25 |  |  |  | 2026-08-25 | KPTG-TRANSMIT-020912 | Closed | 89 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-18 | Auspan-TRANSMIT-000399 | NA | Trade Partner | Precast shop drawings for approval. Level 3 | 4 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 1275 | 2026-06-25 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-002619 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-16 | ZLH P/L-TRANSMIT-000004 | NA | Trade Partner | Re: Proposed Material - Design & Sample - ZLH | 0 | 14 | 0 | NA | APPROVED | 2026-06-16 | WF-000213 | NA | 2026-06-25 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001389 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-18 | MAYFLD-TRANSMIT-000457 | NA | Trade Partner | 100222-000600: M3 Stage 2 - EG Room - Architectural As Built Drawings | 11 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As Built, for updating in Aconex, ACC and distribution only. |  | 2026-06-18 | KPTG-TRANSMIT-018785 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-18 | Nilsen3-TRANSMIT-000192 | NA | Trade Partner | STAGE 4- IFC -GENERAL ELECTRICAL & COMMS - CONSULTANT REVIEW-SHOP DRAWING - Nilsen3-TRANSMIT-000129 Nilsen Shop Drawings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect subject line |  | 2026-06-18 | KPTG-RFI-008479 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-21 | Danlai-TRANSMIT-000003 | NA | Trade Partner | Technical Data | 0 | 2 | 0 | NA | APPROVED | 2026-05-21 | WF-000145 | NA | 2026-05-29 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-000853 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-01-09 | SMPS-TRANSMIT-000101 | NA | Trade Partner | DB Schedules | 0 | 13 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-18 | Entire M-TRANSMIT-000032 | NA | Trade Partner | FOA-2 - OAP | 0 | 1 | 0 | NA | APPROVED | 2026-06-18 | WF-000227 | NA | 2026-06-29 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-18 | SKS Tech-TRANSMIT-000168 | NA | Trade Partner | Gripple channel nut tech data | 0 | 1 | 0 | NA | APPROVED | 2026-06-18 | WF-006063 | NA | 2026-06-23 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-019616 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-18 | ACG-TRANSMIT-000020 | NA | Trade Partner | CCTV Pole | 0 | 1 | 0 | NA | APPROVED | 2026-06-18 | WF-001115 | NA | 2026-06-25 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-004042 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-18 | Nilsen3-TRANSMIT-000191 | NA | Trade Partner | Nilsen Shop Drawings - IFC | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong Revision and status |  | 2026-06-18 | KPTG-RFI-008485 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-18 | ZLH P/L-TRANSMIT-000008 | NA | Trade Partner | Sample-Plasterboard GAL C3 Screw Sample (FOA-01) | 0 | 1 | 0 | NA | APPROVED | 2026-06-18 | WF-000228 | NA | 2026-06-29 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-000955 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-18 | Diadem-TRANSMIT-000009 | NA | Consultant | Wayfinding Package: Status | 95 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 1156 | 2026-06-25 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-004794 | Closed | 95 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-18 | D&E-TRANSMIT-000266 | SPARK-CRFI-KPG-000473 | Trade Partner | MWYCCB - LEVEL 1 - PLINTH LAYOUT ZONE 8 & ZONE 9 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 319 | 2026-06-25 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-001325 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-18 | KPTG-IntCorr-014863 | NA | Trade Partner | DOOR HARDAWRE SCHEDULE | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-06-18 | KPTG-RFI-008488 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-18 | NXT-TRANSMIT-001627 | NA | Trade Partner | Fwd: Upload of QA_ITP End of Line Documentation for Stage 4 phase 2 units | 18 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution - BACAU-TRANSMIT-000093 |  | 2026-06-18 | KPTG-TRANSMIT-018795 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-18 | FNSTR8-TRANSMIT-000017 | NA | Trade Partner | IFC Shop Drawings | 21 | 0 | 0 | NA | REJECTED | [5 empty] | Internal Correspondence - KPTG-IntCorr-014832 rejected due to incorrect revision number |  | 2026-06-18 | KPTG-RFI-008482 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-18 | NXT-TRANSMIT-001155 | NA | Client | 000569-100222 AS BUILT L&P and Mechanical Junction boxes | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2025-12-18 | KPTG-TRANSMIT-011079 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-18 | WSP ANZ-TRANSMIT-000016 | NA | Consultant | WSP - Electrical drawings for Approval | 14 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 262 | 2026-06-25 |  | Actual Received date 02-06-2026 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-18 | SMEPS-IntCorr-000325 | NA | Trade Partner | Telecom Labelling Schedule | 0 | 2 | 0 | NA | APPROVED | 2026-06-18 | WF - 000485 | NA | 2026-06-25 |  | NA | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-001034 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-18 | JCBa-TRANSMIT-000262 | NA | Consultant | IFC - BTR latest drawings | 13 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC distribution to RDS | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-003038 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-18 | ZIA-TRANSMIT-000097 | NA | Trade Partner | M3S4 ORMB Sample (Drawings) for Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Wrong revision mentioned inside the document |  | 2026-06-18 | KPTG-RFI-008489 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-18 | SMEPS-TRANSMIT-000311 | NA | Trade Partner | Drawing Transmittal | 1 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 4307 | 2026-06-25 |  |  | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-019857 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-06-18 | Tradetec-TRANSMIT-000457 | NA | Trade Partner | Re: Tech Data, Stage 2, Thermal Flowable Concrete | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect revision |  | 2026-06-18 | KPTG-RFI-008491 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-06-18 | INSULPAK-TRANSMIT-000025 | NA | Trade Partner | Re: HFF MSSB AS BUILT Drawings | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect revision number |  | 2026-06-18 | DRAFT-010209 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-06-18 | INSULPAK-TRANSMIT-000026 | NA | Trade Partner | Re: Power Pack MSSB As Built drawings | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect revision number |  | 2026-06-18 | DRAFT-010211 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-18 | SMEPS-TRANSMIT-000317 | NA | Trade Partner | SME - IFC Sample submissions | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-06-18 | KPTG-TRANSMIT-018798 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-18 | NXT-TRANSMIT-001156 | NA | Client | 000570-100222 AS BUILT - Lighting calculations | 0 | 14 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2025-12-18 | KPTG-TRANSMIT-011075 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-18 | L.E.S.-TRANSMIT-000014 | NA | Trade Partner | Existing level 2 generator relocation - IFA | 1 | 0 | 0 | NA | REJECTED | [5 empty] | QA error |  | 2026-06-18 | KPTG-TRANSMIT-002360 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-18 | Altaire-TRANSMIT-000113 | NA | Trade Partner | FOA Dry Fire Fuel Compound | 1 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 4309 | 2026-06-25 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-019654 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-18 | WAM-TRANSMIT-000805 | NA | Consultant | A12 CSP L2, L3 & 4 - IFC Updates. | 6 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 797 | 2026-06-22 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-002622 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-18 | M.2-TRANSMIT-000048 | NA | Trade Partner | Electrical Services Ground and Level 01 Power & comms layouts | 10 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 1277 | 2026-06-25 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-002469 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-18 | D&E-TRANSMIT-000843 | NA | Trade Partner | NXM3S4 - Ground - Mechanical Duct Layout - Zone 8 & IW Tank Room - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-06-18 | KPTG-TRANSMIT-018807 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-18 | Nilsen3-TRANSMIT-000193 | NA | Trade Partner | HV Roof containment drawings re-issue | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Revision of the document has already been received title different |  | 2026-06-18 | KPTG-RFI-008496 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-18 | Stowe-A-TRANSMIT-000615 | NA | Trade Partner | STOWE - COMMISSIONING IMPLEMENTATION PLAN - AS-BUILT | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-06-18 | KPTG-TRANSMIT-018808 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-18 | WSP ANZ-TRANSMIT-000017 | NA | Consultant | WSP - Updated Electrical Services drawing for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 264 | 2026-06-25 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-18 | Stowe-A-TRANSMIT-000616 | NA | Trade Partner | STOWE - TECH DATA SUBMISSION - SEISMIC EQUIPMENT - 18.06.2026 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Mismatch in revision. |  | 2026-06-18 | KPTG-TRANSMIT-018815 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-18 | Stowe-A-TRANSMIT-000617 | NA | Trade Partner | STOWE - TECH DATA SUBMISSION - SEISMIC EQUIPMENT - REV E - UPDATED | 0 | 1 | 0 | NA | APPROVED | 2026-06-18 | WF-006066 | NA | 2026-06-30 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-019259 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-01 | Stowe-A-TRANSMIT-000386 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - LIGHTING CONTROL - LEVEL 1 - 01.12.2025 | 2 | 0 | 0 | NA | APPROVED | 2025-12-01 | NA | 3380 | 2025-12-04 |  |  |  | 2025-12-04 | KPTG-TRANSMIT-010598 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-18 | NXT-TRANSMIT-001159 | NA | Client | 100222-000571 - AS BUILT DOCUMENTS | 12 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2025-12-18 | KPTG-TRANSMIT-011093 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-18 | MAYFLD-TRANSMIT-000461 | NA | Trade Partner | 100222-000604 - EF As Built Structural drawings | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As Built, For updating in ACC, Aconex and distribution only. |  | 2026-06-18 | KPTG-TRANSMIT-018816 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-18 | MAYFLD-TRANSMIT-000462 | NA | Trade Partner | 100222-000605 EH - As Built Drawings issued for information | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As Built, for updating Aconex, ACC and distribution only. |  | 2026-06-18 | KPTG-TRANSMIT-018819 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-18 | MAYFLD-TRANSMIT-000464 | NA | Trade Partner | 100222-000607 - EM As Built drawings issued for information | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As Built, for updating Aconex, ACC and distribution only. |  | 2026-06-18 | KPTG-TRANSMIT-018822 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-18 | MAYFLD-TRANSMIT-000465 | NA | Trade Partner | Re: 100222-000607 - EM As Built drawings issued for information - Status and Rev Date Correction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As Built, for updating Aconex, ACC and distribution only. |  | 2026-06-18 | KPTG-TRANSMIT-018822 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-18 | MAYFLD-TRANSMIT-000463 | NA | Trade Partner | 100222-000606 EK As built drawings issued for information | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As Built, for updating Aconex, ACC and distribution only. |  | 2026-06-18 | KPTG-TRANSMIT-018824 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-18 | Stowe-A-TRANSMIT-000619 | NA | Trade Partner | Stowe - Tech Data - IFA - FIRE RATED JUNCTION BOXES LIFTS - AS PER KPTG-SADV-005347 | 0 | 1 | 0 | NA | APPROVED | 2026-06-18 | WF-006582 | NA | 2026-08-06 |  | Reissued WF as Arup attached wrong file. |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-18 | Appselec-TRANSMIT-000127 | NA | Trade Partner | Communications Trunking Rev 6 Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-06-18 | WF-000339 | NA | 2026-06-25 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-001017 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-18 | Stowe-A-TRANSMIT-000618 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - EXTERNAL LIGHTING - FC-03 | 1 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 4316 | 2026-06-25 |  | Terminated by Fabian for submitting the updated document. | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-020086 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-18 | D&E-TRANSMIT-000841 | NA | Trade Partner | SFN Scripts - Issued for Construction | 0 | 13 | 0 | NA | REJECTED | [5 empty] | Issues with revision number, direct IFC submission without IFA. |  | 2026-06-18 | KPTG-SADV-006032 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-18 | Ardon-TRANSMIT-000049 | NA | Trade Partner | Priority Batch 5 Shop Drawings | 32 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 3586 | 2026-06-22 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-019113 | Closed | 32 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-18 | PARR-TRANSMIT-000107 | NA | Trade Partner | P2649 - KPG NDC M3 - Stage 2 - Fuel - CX L2, L3, L4 and Commissioning Plan | 0 | 20 | 0 | NA | APPROVED |  | WF-003679 | NA | 2026-01-15 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-18 | KPTG-TRANSMIT-018805 | NA | Trade Partner | M3 S2 - PMJ Cover O&M | 0 | 1 | 0 | NA | APPROVED | 2026-06-18 | WF-006072 | NA | 2026-06-30 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-019298 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-18 | D&E-TRANSMIT-000842 | NA | Trade Partner | Fwd: NXM3S4 - Ground - CHW Pipe Layout Zones - Issued For Construction | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | only for distribution |  | 2026-06-18 | KPTG-TRANSMIT-018794 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-18 | CNGC-TRANSMIT-000003 | NA | Trade Partner | Re: CGC_Procurement _TDS | 4 | 0 | 0 | NA | REJECTED | [5 empty] | SO MANY MISTAKES IN ACONEX SUBMITTION AND INSIDE DRAWING |  | 2026-06-18 | KPTG-RFI-008492 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-18 | Schindle-TRANSMIT-000030 | NA | Trade Partner | Re: C3 Lift Reveal drawing for review | 4 | 0 | 0 | NA | REJECTED | [5 empty] | ALL READY WE HAVE THIS REV |  | 2026-06-18 | KPTG-RFI-008495 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-18 | ARCST-TRANSMIT-000304 | NA | Trade Partner | Generator PMJ beams - Issued for Fabrication | 4 | 0 | 0 | NA | APPROVED | 2026-06-18 | WF-006069 | NA | 2026-06-30 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-18 | SMEPS-TRANSMIT-000316 | NA | Trade Partner | IFA Sample submissions | 0 | 4 | 0 | NA | APPROVED | 2026-06-18 | WF-006069 | NA | 2026-07-08 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-18 | ARCST-TRANSMIT-000305 | NA | Trade Partner | C1 East Lower Gantry - Issued for Fabrication | 138 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect Revision histroy and titles |  | 2026-06-18 | KPTG-RFI-008503 | Closed | 138 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-18 | Auspan-TRANSMIT-000398 | NA | Trade Partner | Precast shop drawings for construction. | 26 | 0 | 0 | KPTG-IntCorr-000730 | APPROVED |  | NA | NA |  |  | IFC - Waiting for advice from KIM - KPTG-IntCorr-000730 8 are OK to proceed IFC KPTG-TRANSMIT-002440; 18 Rejected as advised by Kapitol PC. KPTG-IntCorr-000770 | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-002440 | Closed | 26 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-18 | M.2-TRANSMIT-000047 | NA | Trade Partner | : Electrical Services Level 2 - 7 Lighting layouts | 15 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to incorrect drawing status. DRAFT-008559 |  | 2026-06-18 | DRAFT-008559 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-18 | RBG-TRANSMIT-000063 | NA | Consultant | Blockwork structural drawings - issued for construction | 5 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 569 | 2026-06-22 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-001674 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-18 | D&E-TRANSMIT-000320 | NA | Trade Partner | MaxCool FD - Issued for review | 0 | 1 | 0 | NA | APPROVED | 2025-12-18 | WF-003671 | NA | 2026-01-01 |  |  | 2026-01-27 | 2026-01-27 | KPTG-TRANSMIT-011901 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-18 | Highbu-TRANSMIT-000052 | NA | Trade Partner | Level 6 Penetration Layout | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004569 - The status is different inside and outside. | 2026-06-18 | 2026-06-18 | KPTG-SADV-004569 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-18 | fjc-TRANSMIT-000157 | NA | Consultant | Drawing Updates - Wall Types/Details | 6 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004573 - THE REVISION NUMBER IS INCORRECT | 2026-06-18 | 2026-06-18 | KPTG-SADV-004573 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-18 | P & R-TRANSMIT-000091 | NA | Trade Partner | MLC As-Built - Revisions Change | 14 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 326 | 2026-06-24 |  |  | 2026-06-22 | 2026-06-22 | 14 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-18 | NXT-TRANSMIT-000413 | NA | Client | M3 Expansion - Lanco Pack | 2 | 0 | 0 | KPTG-IntCorr-000193 | APPROVED |  | NA | NA |  |  | Distributed |  | 2026-06-22 | KPTG-TRANSMIT-000319 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-18 | TTW-TRANSMIT-000040 | NA | Consultant | M3 Stage 6 F3P1 Performance Based Design Brief | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Wrong Naming convention |  | 2026-06-18 | KPTG-DA-000404 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-18 | TTW-TRANSMIT-000042-drg | NA | Consultant | Facade Updated Drawing and PBDB | 16 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 223 | 2026-06-26 |  | TTW-TRANSMIT-000041 superseded | 2026-06-30 | 2026-07-01 | KPTG-TRANSMIT-000388 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-18 | TTW-TRANSMIT-000042-tech | NA | Consultant | Facade Updated Drawing and PBDB | 0 | 1 | 0 | NA | REJECTED | [5 empty] | TTW-TRANSMIT-000041 superseded |  | 2026-06-18 | KPTG-DA-000415 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-18 | Lat-TRANSMIT-000012 | NA | Consultant | Expansion - Stony Creek Retaining Wall Landscape Concept Package (IFI-1) | 0 | 1 | 0 | KPTG-IntCorr-000200 | APPROVED |  | NA | NA |  |  | Wrong Naming Convention |  | 2026-06-29 | KPTG-DA-000519 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-18 | 4DW-TRANSMIT-000049 | NA | Consultant | Issued with Construction updates: Precast walls & Foundations - Block 1 | 14 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 229 | 2026-06-26 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-000759 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-18 | 4DW-TRANSMIT-000050 | NA | Consultant | Structural Documentation: Precast Core Walls naming rectification. | 7 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 225 | 2026-06-26 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-000783 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-09 | IVS-TRANSMIT-000308 | NA | Consultant | Stage 4 - Chiller Room Zone C1 (Certification Issue) | 4 | 0 | 0 | NA | APPROVED | 2026-01-09 |  | 1743 | 2026-01-13 |  |  |  | 2026-01-15 | KPTG-TRANSMIT-011477 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-18 | WGAVIC-TRANSMIT-000007 | NA | Consultant | S6 Civil Stormwater Drawings and Certificate - Issued for Construction | 9 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 227 | 2026-06-26 |  |  | 2026-06-29 | 2026-06-30 | KPTG-TRANSMIT-000372 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-18 | NXT-TRANSMIT-000415 | NA | Client | M3 Stage 6 - Renders | 0 | 5 | 0 | NA | APPROVED |  | NA | NA |  |  | Information only |  | 2026-06-18 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-18 | DCN-TRANSMIT-000015 | NA | Trade Partner | Link Bridge - Window Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-06-18 | WF-000987 | NA | 2026-07-07 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-005304 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-18 | DLTS-TRANSMIT-000029 | NA | Trade Partner | S9-HV Room-IFA Issue | 112 | 0 | 0 | NA | APPROVED | 2026-06-18 | WF-000988 | NA | 2026-06-30 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-005319 | Closed | 112 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-18 | ELLISAIR-TRANSMIT-000072 | NA | Trade Partner | CSTR MCC | 0 | 1 | 0 | NA | APPROVED | 2026-06-18 | WF-000976 | NA | 2026-06-30 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-004990 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-18 | SES AU-TRANSMIT-000001 | NA | Trade Partner | Security Samples | 0 | 25 | 0 | NA | APPROVED | 2026-06-18 | WF-000977 | NA | 2026-06-25 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-005581 | Closed | 25 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-18 | WGAVIC-TRANSMIT-000153 | NA | Consultant | M2 - Stage 11 Lift Lobby Subfloor and Roof - Issued for Certification | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Need to revise KPTG-DA-003215 |  | 2026-06-18 | KPTG-DA-003215 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-18 | VIA Arch-TRANSMIT-000166 | NA | Consultant | UPDATED ARCHITECTURAL DOCUMENTATION | 49 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 1158 | 2026-06-23 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-004015 | Closed | 49 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-18 | VIA Arch-TRANSMIT-000167 | NA | Consultant | M2 Procurement FFE | 7 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 1160 | 2026-06-25 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-004019 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-18 | SMEPS-TRANSMIT-000053 | NA | Trade Partner | STAGE 9-11 Overall Site Earthing & Lightning Protection Layout (FOA-2) | 1 | 0 | 0 | NA | APPROVED | 2026-06-18 | WF-000995 | 1162 | 2026-06-27 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-005019 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-18 | HDRAus-TRANSMIT-000347 | NA | Consultant | M3 TP Meeting Record | 10 | 0 | 0 | NA | REJECTED | [5 empty] | Document number format inside and outside the documents is not as per the project standards |  | 2025-12-18 | KPTG-DA-004027 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-18 | L.E.S.-TRANSMIT-000013 | NA | Consultant | Carpark lux calculations IFA | 0 | 2 | 0 | KPTG-IntCorr-000825 | APPROVED | 2026-06-23 | WF-000781 | NA | 2026-06-26 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-002574 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-18 | L.E.S.-TRANSMIT-000005 | NA | Consultant | Carpark Level 2 and 3 light fitting data sheets - IFA | 0 | 3 | 0 | NA | APPROVED | 2026-06-18 | WF-000745 | NA | 2026-06-23 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-18 | INGEN3D-TRANSMIT-000113 | NA | Consultant | Ground Floor to Level 1 - Precast Panels - IFC | 23 | 0 | 0 | NA | APPROVED | 2026-06-18 | WF-000747 | NA | 2026-06-29 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-002549 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-18 | INGEN3D-TRANSMIT-000114 | NA | Consultant | Level 18-20 - Precast Columns - IFA | 35 | 0 | 0 | NA | APPROVED | 2026-06-18 | WF-000748 | NA | 2026-07-06 |  |  | 2026-07-09 | 2026-07-10 | KPTG-TRANSMIT-002810 | Closed | 35 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-18 | INGEN3D-TRANSMIT-000115 | NA | Consultant | Ground Floor to Level 1 - Precast Panels - Revised IFC | 10 | 0 | 0 | NA | APPROVED | 2026-06-18 | WF-000749 | NA | 2026-06-26 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-002537 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-18 | INGEN3D-TRANSMIT-000116 | NA | Consultant | Ground Floor to Level 1 - PW1002-1 - No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer in Use - Forward to all tradepartners - |  | 2026-06-18 | KPTG-TRANSMIT-002363 | Open | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-18 | INGEN3D-TRANSMIT-000117 | NA | Consultant | Level 19-21 - Precast Columns - IFA | 39 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | NA | 2026-07-06 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002863 | Closed | 69 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-19 | Nilsen3-TRANSMIT-000203 | NA | Trade Partner | Nilsen Shop Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 3591 | 2026-06-28 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-020691 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-19 | Entire M-TRANSMIT-000050 | NA | Trade Partner | DX Split Battery Room Functional Description Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-19 | WF - 000486 | NA | 2026-06-26 |  | NA | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-001026 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-19 | VERTIV-TRANSMIT-000038 | NA | Trade Partner | NEXT DC GE 01 _ MATERIAL SUBMIISSION _ BUS DUCT (FOA-1) | 0 | 1 | 0 | NA | APPROVED | 2026-06-19 | WF-000229 | NA | 2026-06-30 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000931 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-18 | Stowe-A-TRANSMIT-000419 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - 110VDC SCHEMATIC - 18.12.2025 | 1 | 0 | 0 | NA | APPROVED | 2025-12-18 | NA | 3540 | 2025-12-25 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-19 | Detail-TRANSMIT-000011 | NA | Trade Partner | Re: DOOR HARDAWRE SCHEDULE | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-06-19 | KPTG-RFI-008507 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-19 | RDSBIM-TRANSMIT-000060 | SPARK-CRFI-KPG-000380 | Trade Partner | MCC ¦ L01 CPP ¦ IFC ¦ FOR SUBMISSION | 2 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 320 | 2026-06-26 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-001370 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-19 | KPTG-TRANSMIT-000877 | NA | Trade Partner | Western Painting Services Tech Data (Submission) | 0 | 8 | 0 | NA | REJECTED | [5 empty] | Issue with Revision number and document status. |  | 2026-06-19 | KPTG-SADV-000694 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-19 | WAM-TRANSMIT-000806 | NA | Consultant | A12 CSP Level 1 - Updates | 2 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 799 | 2026-06-23 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-002617 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-19 | M.2-TRANSMIT-000050 | NA | Trade Partner | Electrical Services Level 02-07 Lighting shop drawings | 15 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 1281 | 2026-06-26 |  |  | 2026-07-17 | 2026-07-17 | ⁠KPTG-TRANSMIT-002837 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-19 | RDSBIM-TRANSMIT-000048 | NA | Trade Partner | CORE 03 GROUND FLOOR TO L02 ¦ IFC - SUBMISSION | 4 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 801 | 2026-06-29 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-002741 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-19 | D&E-TRANSMIT-000844 | NA | Trade Partner | NXM3S2 - GROUND FLOOR - DATAHALL 1 SFN UNION AND BOLT TORQUE MAP - Issued For Construction | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Submitting IFC without IFA. |  | 2026-06-19 | KPTG-SADV-006042 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-19 | Auspan-TRANSMIT-000400 | NA | Trade Partner | Re: Precast shop drawings for approval. Level 5 | 1 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 1283 | 2026-06-26 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002816 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-19 | INDS-TRANSMIT-000040 | NA | Trade Partner | Revised Dry Fire - Ground | 5 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 1285 | 2026-06-26 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-002472 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-19 | D&E-TRANSMIT-000845 | NA | Trade Partner | NXM3S4 - Ground & Level 1 - SFN Pipe Layout TORQUE MAP Sheets - Issued For Information | 29 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | FOR DISTRIBUTION |  | 2026-06-19 | KPTG-TRANSMIT-018837 | Closed | 29 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-18 | Stowe-A-TRANSMIT-000420 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - WHIP STACKING LAYOUT - 18.12.2025 | 1 | 0 | 0 | NA | APPROVED | 2025-12-18 | NA | 3547 | 2025-12-25 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-19 | L.E.S.-TRANSMIT-000015 | NA | Trade Partner | Existing Level 2 Generator relocation IFA resubmission | 5 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 803 | 2026-06-29 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-002897 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-19 | JCBa-TRANSMIT-000138 | NA | Consultant | Partition Details: IFC | 4 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 1287 | 2026-07-03 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-002679 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-19 | RDSBIM-TRANSMIT-000072 | NA | Trade Partner | GREYSTAR ¦ L01 ¦ CPP ¦ IFC ¦ FOR SUBMISSION | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Drawings- No review, updated register and distributed (KPTG-TRANSMIT-002327) |  | 2026-06-19 | KPTG-TRANSMIT-002327 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-19 | FNSTR8-TRANSMIT-000018 | NA | Trade Partner | For Approval - Shop Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 3594 | 2026-07-01 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-019348 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-19 | ADP-TRANSMIT-000355 | NA | Consultant | MEL4561 - M3S2 - Extinguishers Updates | 9 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 4318 | 2026-06-23 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-019491 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-19 | INDS-TRANSMIT-000041 | NA | Trade Partner | Dry Fire - BASEMENT | 5 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 1289 | 2026-06-26 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-002637 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-19 | SKS Tech-TRANSMIT-000171 | NA | Trade Partner | Equipment Layout | 7 | 0 | 0 | NA | REJECTED |  |  | NA |  |  | Please note that the IFC submission cannot be processed now, as the IFA approval has not yet been received. |  | 2026-06-19 | KPTG-RFI-008509 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-19 | Baigents-TRANSMIT-000085 | SPARK-CRFI-KPG-000135 | Trade Partner | Site Storage Steel - Package 1 - Issued for Construction | 43 | 0 | 0 | NA | APPROVED | 2026-06-19 |  | 321 | 2026-06-26 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-001317 | Closed | 43 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-19 | Nilsen3-TRANSMIT-000193 | NA | Trade Partner | HV Roof containment drawings re-issue | 1 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 3596 | 2026-07-01 |  | terminated as instructed by Duncan Cameron - Terminated the designer to re-issue them |  | 2026-08-21 | KPTG-TRANSMIT-020821 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-19 | FNSTR8-TRANSMIT-000019 | NA | Trade Partner | IFC Shop Drawings Update | 3 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 3895 | 2026-06-24 |  | As per Kiona advice the document placed with in combined with documents FNSTR8-TRANSMIT-000017 |  | 2026-06-19 | KPTG-TRANSMIT-018860 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-18 | Stowe-A-TRANSMIT-000421 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - LIGHTNING PROTECTION ROOF PLANT - 18.12.2025 | 1 | 0 | 0 | NA | APPROVED |  | NA | 3545 | 2025-12-29 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-012597 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-19 | WAM-TRANSMIT-000807 | NA | Consultant | IFC - A12 CSP Level 5 & 6 Updates | 4 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 807 | 2026-06-23 |  |  | 2026-07-06 | 2026-07-07 | KPTG-TRANSMIT-002729 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-19 | MAYFLD-TRANSMIT-000466 | NA | Trade Partner | 100222-000600: M3 Stage 2 - EG Room - Architectural As Built Drawings - Corrected Drawing | 11 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As Builts, for updating Aconex, ACC and for distribution only. |  | 2026-06-19 | KPTG-TRANSMIT-018850 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-19 | SMEPS-TRANSMIT-000013 | NA | Trade Partner | Techdata: HV Cable | 0 | 1 | 0 | NA | APPROVED | 2026-06-19 | WF-000230 | NA | 2026-06-30 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000927 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-19 | 4DW-TRANSMIT-000186 | NA | Consultant | Structural Documentation - Retention update | 6 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 328 | 2026-06-24 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-003025 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-19 | Appselec-TRANSMIT-000128 | NA | Trade Partner | AHU Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-06-19 | WF-000340 | NA | 2026-06-19 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-000964 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-19 | D&E-TRANSMIT-000847 | NA | Trade Partner | Fwd: NXM3S4 - Ground - CHW Pipe Layout Zone 5 & Zone 7 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Ifc document for distribution completed build sheet |  | 2026-06-19 | KPTG-TRANSMIT-018857 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-19 | D&E-TRANSMIT-000847 | NA | Trade Partner | Fwd: NXM3S4 - Ground - CHW Pipe Layout Zone 5 & Zone 7 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC DOCUMENT AS PER ELLI DISTRIBUTED |  | 2026-06-19 | KPTG-TRANSMIT-018857 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-09 | INGEN3D-TRANSMIT-000101 | NA | Trade Partner | Level 12-14 - Precast Columns - IFA | 35 | 0 | 0 | NA | APPROVED | 2026-06-09 | WF-000682 | NA | 2026-06-26 |  |  | 2026-07-13 | 2026-07-14 | KPTG-TRANSMIT-002871 | Closed | 35 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-19 | D&E-TRANSMIT-000848 | NA | Trade Partner | Heat Exchangers - Issued for Construction | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect document number |  | 2026-06-19 | KPTG-RFI-008512 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-18 | NXT-TRANSMIT-001160 | NA | Client | 000572-100222 AS BUILT - L&P and Mechanical Junction Box | 8 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As Built | 2025-12-18 |  | KPTG-TRANSMIT-011090 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-19 | TATE_-TRANSMIT-000029 | NA | Trade Partner | Issue uploading drawings | 10 | 0 | 0 | NA | APPROVED | 2026-06-19 | WF-000341 | NA | 2026-06-23 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-000934 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-19 | ACCCA-TRANSMIT-000001 | NA | Trade Partner | Electrical Pit Approval | 6 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 228 | 2026-06-29 |  |  | 2026-07-22 | 2026-07-23 | KPTG-TRANSMIT-000679 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-19 | KPTG-TRANSMIT-001023 | NA | Trade Partner | Load Bank Plan - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-19 | WF - 000487 | NA | 2026-06-25 |  | NA | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-001044 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-06-18 | SMEPS-TRANSMIT-000310 | NA | Trade Partner | Building - Basement Containment Layout - Update for Review (IFC) | 1 | 0 | 0 | NA | APPROVED | 2026-06-19 | WF-006081 | NA | 2026-07-02 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-019223 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-19 | D&E-TRANSMIT-000849 | NA | Trade Partner | Fwd: Heat Exchangers - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-06-19 | KPTG-TRANSMIT-018862 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-19 | Tradetec-TRANSMIT-000458 | NA | Trade Partner | Tech Data - Site wide - Aurora 80mpa Slurry | 0 | 1 | 0 | NA | APPROVED | 2026-06-19 | WF-006082 | NA | 2026-06-26 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-19 | D&E-TRANSMIT-000846 | NA | Trade Partner | NXM3S4 - Upper Roof Level - Cooling Tower Sections - Sheet 1 of 4 - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 3601 | 2026-06-23 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-020001 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-22 | SMEPS-TRANSMIT-000232 | NA | Trade Partner | EXTERNAL EPMS BAS ROUTING LAYOUT | 3 | 0 | 0 | NA | APPROVED | 2026-06-22 | WF - 000489 | NA | 2026-06-26 |  | NA | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-001036 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-19 | SMEPS-TRANSMIT-000014 | NA | Trade Partner | Techdata: Cable Calculations | 0 | 1 | 0 | NA | APPROVED | 2026-06-19 | WF-000231 | NA | 2026-06-30 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-001102 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-19 | SMEPS-TRANSMIT-000015 | NA | Trade Partner | Techdata: Lightning | 0 | 1 | 0 | NA | APPROVED | 2026-06-19 | WF-000232 | NA | 2026-06-30 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-001141 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-18 | HDRAus-TRANSMIT-000348 | NA | Consultant | M3_S2_Building Permit Related Drawings | 7 | 0 | 0 | NA | REJECTED | [5 empty] | Stage 2 and Sitewide documents in the same transmittals. Documents with different status in a single transmittal |  | 2025-12-19 | KPTG-DA-004033 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-19 | Jangho-TRANSMIT-000177 | NA | Trade Partner | Tower A&B Level 10~16 Shop Drawing_Rev 02_For Approval | 34 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 809 | 2026-06-29 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-002680 | Closed | 34 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-19 | D&E-TRANSMIT-000267 | SPARK-CRFI-KPG-000525 & SPARK-CRFI-KPG-000315 | Trade Partner | MWYCCB - LEVEL 1 - RCP LAYOUT + PENETRATION LAYOUT ZONE 2 & 4 MECHANICAL SERVICES - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 322 | 2026-06-26 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-001329 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-19 | FNSTR8-TRANSMIT-000017 | NA | Trade Partner | IFC Shop Drawings | 21 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 3603 | 2026-06-23 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-019550 | Closed | 21 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-19 | Axiom-TRANSMIT-000037 | NA | Trade Partner | L9 Roof Setout Plan IFC, MB10 IFC and MB10 Gate IFA | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC- Acnox Update only. |  | 2026-06-19 | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-19 | Appselec-TRANSMIT-000129 | NA | Trade Partner | MEL11C45 - COLO 5 Electrical Shop Drawings - IFC | 7 | 0 | 0 | NA | APPROVED | 2026-06-19 | WF-000342 | NA | 2026-06-23 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-000984 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-19 | WAM-TRANSMIT-000808 | NA | Consultant | Drawings A14 and A75 Series for Construction updated | 26 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 811 | 2026-06-22 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-002423 | Closed | 26 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-19 | Metzone-TRANSMIT-000031 | NA | Trade Partner | Error Documents No Longer In Use | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Documents are no longer in use. | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-002578 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-06-19 | Tradetec-TRANSMIT-000459 | NA | Trade Partner | Re: Tech Data, Stage 3, Thermal Flowable Concrete | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect revision number |  | 2026-06-19 | KPTG-RFI-008517 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-19 | WAM-TRANSMIT-000809 | NA | Consultant | A12 CSP - Level 11 to 16 - IFC | 12 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 813 | 2026-06-22 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-002426 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-19 | TTW-TRANSMIT-000191 | NA | Consultant | M3 Stage 4 Building C Civil Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 3605 | 2026-06-23 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-020714 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-01 | Stowe-A-TRANSMIT-000384 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - LUMINAIRE SCHEDULE - 01.12.2025 | 1 | 0 | 0 | NA | APPROVED |  | NA | 3377 | 2025-12-08 |  |  |  | 2025-12-04 | KPTG-TRANSMIT-010609 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-18 | D&E-TRANSMIT-000321 | NA | Trade Partner | D&E-TRANSMIT-000321 | 0 | 1 | 0 | NA | APPROVED | 2025-12-18 | WF-003677 | NA | 2026-01-01 |  |  |  | 2026-01-27 | KPTG-TRANSMIT-011948 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-19 | Metzone-TRANSMIT-000033 | NA | Trade Partner | Error Documents No Longer In Use | 73 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | documents are No Longer In Use | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-002581 | Closed | 73 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-19 | 4DW-TRANSMIT-000053 | NA | Consultant | Issued with Construction updates: Precast walls & Foundations - Block 1 | 6 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 231 | 2026-06-29 |  | 4DW-TRANSMIT-000051 & 4DW-TRANSMIT-000052 superseded | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-000758 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-19 | Highbu-TRANSMIT-000053 | NA | Trade Partner | Level 06 Pentrations | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001093 - as per direction from Mark ,we only update register and distribute architect and trade partners. | 2026-06-19 | 2026-06-19 | KPTG-IntCorr-001093 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-19 | KALLIBRE-TRANSMIT-000024 | NA | Trade Partner | Re: Final (WF-000324) TECHNICAL DATA ¦ CONSULTANT REVIEW ¦ ARC¦ KALLIBRE ¦ IFA ¦¦-V1-KALLIBRE-TRANSMIT-000019 - Door Hardware Tech Data with Cover Sheet | 0 | 4 | 0 | NA | APPROVED | 2026-06-19 | WF-000343 | NA | 2026-06-25 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-000965 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-26 | Metzone-TRANSMIT-000034 | NA | Trade Partner | Fwd: Ground and L1 Steel drawings IFC | 32 | 0 | 0 | KPTG-IntCorr-001094 | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001094 - Requested guidance, but no resonance received yet. KPTG-IntCorr-001110-as per direction from ashlin we only update regiter an issue to everyone. | 2026-06-26 | 2026-06-26 | KPTG-IntCorr-001110 | Closed | 32 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-19 | PCForm-TRANSMIT-000239 | NA | Trade Partner | Mezzanine - updated slab drawings | 6 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 815 | 2026-06-29 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-002615 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-19 | D&E-TRANSMIT-000850 | NA | Trade Partner | Re: DX & VRF Air Conditioning - Issued for Construction | 2 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due to mismatch in rev number |  | 2026-06-19 | KPTG-RFI-008518 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-19 | D&E-TRANSMIT-000851 | NA | Trade Partner | Re: DX & VRF Air Conditioning - Issued for Construction | 2 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due mismatch in Aconex and inside drawing |  | 2026-06-19 | KPTG-RFI-008519 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-19 | Jangho-TRANSMIT-000179 | NA | Trade Partner | Podium Level 3 Floor Plan Shop Drawing_PDF_Rev 02_For Approval | 2 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 817 | 2026-06-29 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-002782 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-19 | Baigents-TRANSMIT-000218 | NA | Trade Partner | Glazing Steel FOA-1 | 15 | 0 | 0 | KPTG-TRANSMIT-003946 | APPROVED | 2026-06-22 | WF-001116 | NA | 2026-06-22 |  | Clarification from Luke | 2026-06-22 | 2026-06-23 | KPTG-TRANSMIT-003968 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-18 | HDRAus-TRANSMIT-000349 | NA | Consultant | M3_S2_Changing from For Review to For Construction in Drawing Register | 1 | 0 | 0 | NA | APPROVED |  | NA | 3553 | 2025-12-22 |  |  | 2026-01-12 | 2026-01-12 | KPTG-TRANSMIT-011353 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-19 | HDRAus-TRANSMIT-000512 | NA | Consultant | Re: M3 Stage 4 - Document upload - PDF and CAD | 26 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision |  | 2026-06-19 | KPTG-RFI-008520 | Closed | 26 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-19 | D&E-TRANSMIT-000818 | NA | Trade Partner | NXM3S4 - Level 1 - SFN Pipe Layout - Zones - Issued For Construction | 10 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 3606 | 2026-06-30 |  |  |  | 2026-08-11 | KPTG-TRANSMIT-020509 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-19 | KPTG-IntCorr-014934 | NA | Trade Partner | COMBINED DRAWINGS - | 20 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 3607 - 3749 | 2026-06-30 |  | As instructed by Ellie, - Terminated D&E need to make IFC drawing updates COMBINED DRAWINGS PLACED WF AS PER REQUESTED BY ELI S |  | 2026-07-17 | NA | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-19 | D&E-TRANSMIT-000821 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - UPPER ROOF LEVEL - CHW & CCW PIPE LAYOUTS | 4 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 3608 | 2026-07-03 |  | The WF has been terminated as requested by Ellie |  | 2026-07-03 | NA | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-19 | D&E-TRANSMIT-000829 | D&E-TRANSMIT-000829 | Trade Partner | Fwd: NXM3S4 - Upper Roof CHW Pipe Layout Zones + Chiller Roof - Builders Works Layout Zones - Issued For Construction | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | ONLY FOR DISTRIBUTION |  | 2026-06-19 | KPTG-TRANSMIT-018877 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-25 | SMEPS-TRANSMIT-000293 | NA | Trade Partner | 22KV - Earthing shop drawings. | 0 | 0 | 0 | NA | APPROVED | 2026-05-25 | WF-005812 | NA | 2026-05-28 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-018878 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-25 | SMEPS-TRANSMIT-000293 | NA | Trade Partner | 22KV - Earthing shop drawings. | 0 | 0 | 0 | NA | APPROVED | 2026-05-25 | WF-005812 | NA | 2026-05-28 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-018879 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-06-01 | Nilsen3-TRANSMIT-000178 | NA | Trade Partner | Nilsen Shop Drawings - Issued for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-06-01 | WF-005904 | NA | 2026-06-05 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-018881 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-19 | M.2-TRANSMIT-000049 | NA | Trade Partner | Electrical Services - Lighting Shop drawing QA fixes | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Transmittal is superseded by M.2-TRANSMIT-000050. No action required - DRAFT-008605 |  | 2026-06-19 | DRAFT-008605 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-18 | Stowe-A-TRANSMIT-000422 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - NEUTRAL EARTHING SCHEMATICS - 18.12.2025 | 2 | 0 | 0 | NA | APPROVED | 2025-12-19 | NA | 3555 | 2025-12-26 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-19 | Auspan-TRANSMIT-000402 | NA | Trade Partner | : Precast shop drawings for construction | 25 | 0 | 0 | KPTG-IntCorr-000740 | APPROVED |  | NA | NA |  |  | IFC - QC done - no issues - Kim to confirm -KPTG-IntCorr-000740 18 registered and Transmitted - KPTG-TRANSMIT-002528 6 are rejected as commented by KIM -DRAFT-009120 1 Drawing (1P5057 superseded already) |  | 2026-06-30 | KPTG-TRANSMIT-002528 | Closed | 25 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-19 | Auspan-TRANSMIT-000403 | NA | Trade Partner | All shop drawings for zone 3 ground floor for construction | 92 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Register and transmit - Note: except 3 drawings all are existing revisions already updated in the register and transmitted. KPTG-TRANSMIT-002330, KPTG-TRANSMIT-002331 |  | 2026-06-19 | KPTG-TRANSMIT-002331 | Closed | 92 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-19 | RDSBIM-TRANSMIT-000073 671 | NA | Trade Partner | CHP BLOCKWORK BASEMENT B04 IFA SUBMISSION | 1 | 0 | 0 | KPTG-IntCorr-000762 | APPROVED | 2026-06-22 | NA | 580 | 2026-06-29 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-001509 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-19 | Jangho-TRANSMIT-000081 | NA | Trade Partner | 19-20F shop drawing Rev00 | 55 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 572 | 2026-06-26 |  | Review void as advised by Kapitol DM. |  | 2026-08-03 | NA | Closed | 55 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-19 | B Smart-TRANSMIT-000085 | NA | Consultant | Architecture Drawing _Facade Elevation_A09 Elevations | 2 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 575 | 2026-06-23 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-001297 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-19 | POTTSENG-TRANSMIT-000022 | NA | Trade Partner | 671C: HYDRAULIC SERVICES - GROUND - PENETRATION LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 577 | 2026-06-25 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-001196 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-19 | WGAVIC-TRANSMIT-000007-Tec | NA | Consultant | S6 Civil Stormwater Certificate | 0 | 1 | 0 | KPTG-IntCorr-000205 | APPROVED |  | NA | NA |  |  | ACC update only |  | 2026-06-29 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-19 | Jangho-TRANSMIT-000175 | NA | Trade Partner | Tower A&B Level 6~9 Shop Drawing_Rev 02 | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | SUPERSEDED BY TRN 176 |  | 2026-06-19 | Jangho-TRANSMIT-000176 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-19 | Jangho-TRANSMIT-000175 | NA | Trade Partner | Tower A&B Level 6~9 Shop Drawing_Rev 02 | 68 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 819 | 2026-06-29 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-002551 | Closed | 68 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-19 | Jangho-TRANSMIT-000176 | NA | Trade Partner | Tower A&B Level 6~9 Shop Drawing_Rev 02 | 10 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 819 | 2026-06-29 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-002553 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-19 | D&E-TRANSMIT-000325 | NA | Trade Partner | NXM3S2 - LOWER GROUND / GROUND / LEVEL 1 & ROOF BUILDERS WORKS - Issued For Construction | 7 | 0 | 0 | NA | APPROVED |  | NA | 3557 | 2025-12-26 |  |  |  | 2026-01-23 | KPTG-TRANSMIT-011857 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-19 | Jangho-TRANSMIT-000176 | NA | Trade Partner | Tower A&B Level 6~9 Shop Drawing_Rev 02 | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | SUPERSEDED BY TRN 177 |  | 2026-06-19 | Jangho-TRANSMIT-000177 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-19 | INGEN3D-TRANSMIT-000119 | NA | Trade Partner | Level 20-22 - Precast Columns - IFA | 19 | 0 | 0 | NA | APPROVED | 2026-06-19 | WF-000762 | NA | 2026-07-08 |  |  | 2026-07-08 | 2026-07-09 | KPTG-TRANSMIT-002800 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-19 | INGEN3D-TRANSMIT-000120 | NA | Trade Partner | Level 14-16 - PC0539-3 - New IFA (19-06-2026) | 1 | 0 | 0 | NA | APPROVED | 2026-06-19 | WF-000763 | NA | 2026-06-26 |  |  | 2026-07-01 | 2026-07-01 | NA - Work flow Terminated as instructed | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-19 | INGEN3D-TRANSMIT-000121 | NA | Trade Partner | Level 18-20 - PC0710 - New IFA (19-06-2026) | 1 | 0 | 0 | NA | APPROVED | 2026-06-19 | WF-000764 | NA | 2026-06-26 |  |  | 2026-07-01 | 2026-07-01 | NA - Work flow Terminated as instructed | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-19 | NXT-TRANSMIT-000416-com | NA | Client | In ground services IFCN | 5 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 233 | 2026-06-29 |  |  | 2026-06-29 | 2026-06-30 | KPTG-TRANSMIT-000368 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-19 | NXT-TRANSMIT-000416-elc | NA | Client | In ground services IFCN | 4 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 235 | 2026-06-29 |  |  | 2026-06-29 | 2026-06-30 | KPTG-TRANSMIT-000364 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-19 | NXT-TRANSMIT-000416-fid | NA | Client | In ground services IFCN | 1 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 237 | 2026-06-29 |  |  | 2026-06-29 | 2026-06-30 | KPTG-TRANSMIT-000360 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-19 | NXT-TRANSMIT-000416-fip | NA | Client | In ground services IFCN | 1 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 239 | 2026-06-29 |  |  | 2026-06-29 | 2026-06-30 | KPTG-TRANSMIT-000356 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-19 | NXT-TRANSMIT-000416-hyd | NA | Client | In ground services IFCN | 7 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 242 | 2026-06-29 |  |  | 2026-06-29 | 2026-06-30 | KPTG-TRANSMIT-000353 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-19 | NXT-TRANSMIT-000416-tel | NA | Client | In ground services IFCN | 2 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 244 | 2026-06-29 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-000481 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-19 | Tradetec-TRANSMIT-000314 | NA | Trade Partner | Tech Data - Site Wide - Soilworx Class 3 Crushed Rock | 0 | 1 | 0 | NA | APPROVED | 2025-12-19 | WF-003686 | NA | 2026-01-19 |  |  | 2026-01-12 | 2026-01-12 | KPTG-TRANSMIT-011722 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-19 | Baigents-TRANSMIT-000217 | NA | Trade Partner | Level 5 Ramp FC-1 | 4 | 0 | 0 | NA | APPROVED | [5 empty] | rejected : QA Error in Status |  | 2026-06-19 | KPTG-IntCorr-001516 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-19 | WilsonPD-TRANSMIT-000087 | NA | Trade Partner | Stage 9 Level 3 Drainage | 1 | 0 | 0 | NA | APPROVED | 2026-06-19 | NA | 1164 | 2026-06-26 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-005012 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-19 | Nilsen3-TRANSMIT-000048 | NA | Trade Partner | Emergency Exit Controller Sample updated | 0 | 1 | 0 | NA | APPROVED | 2026-06-19 | WF-000994 | NA | 2026-06-26 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-005598 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-19 | Nilsen3-TRANSMIT-000046 | NA | Trade Partner | Nilsen Sample submissions #6 | 0 | 17 | 0 | NA | APPROVED | 2026-06-19 | WF-000996 | NA | 2026-07-01 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-006661 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-06 | Eneraque-TRANSMIT-000012 | NA | Trade Partner | Eneraque - Full Fuel Programme | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | WF-000636 | NA | 2026-05-09 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-004480 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-19 | Eneraque-TRANSMIT-000030 | NA | Trade Partner | Updated Basket Strainer Datasheet | 0 | 1 | 0 | NA | APPROVED | 2026-06-19 | WF-000997 | NA | 2026-06-26 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-004924 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-22 | D&E-TRANSMIT-000852 | NA | Trade Partner | Fwd: DX & VRF Air conditioning - Issued for construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-06-22 | KPTG-TRANSMIT-018884 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-22 | RDSBIM-TRANSMIT-000147 | NA | Trade Partner | MLCSPR ¦ STAGE 2 ¦ RCP ¦ ISC L03 ¦ FOR SUBMISSION | 7 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 330 | 2026-06-25 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-003108 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-22 | Detail-TRANSMIT-000012 | NA | Trade Partner | Re: DOOR HARDAWRE SCHEDULE | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-06-22 | KPTG-IntCorr-014949 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-22 | JCBa-TRANSMIT-000139 | NA | Consultant | PARTITION DETAIL REFERENCE PLANS- IFC | 5 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 1292 | 2026-06-29 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-002509 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-19 | D&E-TRANSMIT-000326 | NA | Trade Partner | NXM3S2 - ROOF LEVEL - CHILLER ROOMS, MECHANICAL DUCT LAYOUT - ZONES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2025-12-19 | NA | 3559 | 2025-12-26 |  |  | 2026-01-23 | 2026-01-23 | KPTG-TRANSMIT-011848 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-22 | EFP-TRANSMIT-000029 | NA | Trade Partner | FIRE SERVICES SHOP DRAWINGS UPDATED AS CLOUDED | 4 | 0 | 0 | NA | APPROVED | 2026-06-22 | WF-000344 | NA | 2026-06-23 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-000940 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-22 | SSem-TRANSMIT-000006 | NA | Trade Partner | Assemble SRC_Signage & Wayfinding_Documentation | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | NA | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-003110 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-22 | KALLIBRE-TRANSMIT-000007 | NA | Trade Partner | Fire Caulk Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-06-22 | WF - 000490 | NA | 2026-06-26 |  | NA | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-001062 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-22 | JCBa-TRANSMIT-000140 | NA | Consultant | Architectural Documentation - Door Schedule, Door & Window Elevations | 4 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 1294 | 2026-06-29 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-002515 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-22 | Detail-TRANSMIT-000013 | NA | Trade Partner | DOOR HARDAWRE SCHEDULE | 0 | 1 | 0 | NA | APPROVED |  | NA | 3610 | 2026-07-01 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-018924 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-22 | Tradetec-TRANSMIT-000460 | NA | Trade Partner | Tech Data - Stage 2 - P8 Pits | 0 | 1 | 0 | NA | APPROVED | 2026-06-22 | WF-006092 | NA | 2026-06-25 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-018920 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-22 | Entire M-TRANSMIT-000033 | NA | Trade Partner | Water Treatment Equipment - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-22 | WF-000233 | NA | 2026-07-01 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001584 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-22 | RDSBIM-TRANSMIT-000073 | NA | Trade Partner | GREYSTAR¦ L01 CPP IFC GREYSTAR LEVEL 02 KEYPLAN PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 1296 | 2026-06-29 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-002499 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-22 | Entire M-TRANSMIT-000034 | NA | Trade Partner | Mechanical Roof Penetration Drawings FOA-2 | 4 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 280 | 2026-06-26 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-000969 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-22 | M.2-TRANSMIT-000051 | NA | Trade Partner | Electrical Services Ground lighting layouts | 5 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 1298 | 2026-06-29 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-002887 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-19 | HDRAus-TRANSMIT-000348 | NA | Consultant | M3_S2_Building Permit Related Drawings | 7 | 0 | 0 | NA | REJECTED | [5 empty] | Stage 2 and Sitewide documents in the same transmittal. Documents with different status in a single transmittal. |  | 2025-12-19 | KPTG-DA-004033 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-22 | HDRAus-TRANSMIT-000513 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD (Updated Revision) | 3 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 3612 | 2026-06-24 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-019580 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-22 | M.2-TRANSMIT-000052 | NA | Trade Partner | Electrical Services Level lighting layouts | 5 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 1300 | 2026-06-29 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-002902 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-22 | WilsonPD-TRANSMIT-000013 | NA | Trade Partner | NXGEO1 - Gutter Sample resubmission | 0 | 1 | 0 | NA | APPROVED | 2026-06-22 | WF-000235 | NA | 2026-07-01 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-22 | Rinco-TRANSMIT-000058 | NA | Consultant | GF concrete section for truck ramp | 9 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 1302 | 2026-06-29 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-002496 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-22 | ARCST-TRANSMIT-000306 | NA | Trade Partner | Stair 6a - Issued for Approval | 12 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect title |  | 2026-06-22 | KPTG-RFI-008528 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-22 | SMEPS-TRANSMIT-000319 | NA | Trade Partner | Re: SME - IFC Sample submissions | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Incorrect revision number |  | 2026-06-22 | KPTG-RFI-008529 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-22 | Civilex-TRANSMIT-000271 | NA | Trade Partner | Stage 2 - sample submission - Irrigation System | 0 | 5 | 0 | NA | APPROVED | 2026-06-22 | WF-006093 | NA | 2026-07-08 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-019005 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-22 | SMEPS-TRANSMIT-000320 | NA | Trade Partner | SME - IFC Sample submissions | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | CONFIRMATION ASKED |  | 2026-06-22 | KPTG-TRANSMIT-018897 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-22 | SMEPS-TRANSMIT-000318 | NA | Trade Partner | SME - IFA Sample submissions | 0 | 2 | 0 | NA | APPROVED | 2026-06-22 | WF-006096 | NA | 2026-06-26 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-22 | Auspan-TRANSMIT-000408 | NA | Trade Partner | Update panel 1P2015 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC - No review, updated register and distributed (⁠KPTG-TRANSMIT-002380) |  | 2026-06-22 | ⁠KPTG-TRANSMIT-002380 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-01-09 | KEECEPRO-TRANSMIT-000009 | NA | Trade Partner | 600x600 Comms Pit Data Sheet | 9 | 0 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-22 | SMEPS-TRANSMIT-000321 | NA | Trade Partner | SME - IFA Sample submissions | 0 | 1 | 0 | NA | APPROVED | 2026-06-22 | WF-006098 | NA | 2026-07-16 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-22 | POTTSENG-TRANSMIT-000052 | NA | Trade Partner | GMAC: HYD - DRAINAGE - LEVEL 02-04 & WATER - LEVEL 02-05 - ZONE 1-5 LAYOUTS | 10 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 1305 | 2026-06-29 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002833 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-22 | ADP-TRANSMIT-000081 | NA | Consultant | ADP MEL4680 - Updated IFC Drawings (EL.,COMMS & CSMS) and EL R126 | 33 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with revision number and different type of drawing. |  | 2026-06-22 | KPTG-DA-000884 | Closed | 34 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-22 | D&E-TRANSMIT-000854 | NA | Trade Partner | SFN Scripts - Issued for Approval | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Issue with revision number and mixed status submission. |  | 2026-06-22 | KPTG-TRANSMIT-018899 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-22 | TURN--TRANSMIT-000007 | NA | Trade Partner | 303 Collins St - Steel PFC Strengthening Shop Drawings for Basement. | 19 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing submission not complied with submission standard. |  | 2026-06-22 | KPTG-DA-000374 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-22 | WAM-TRANSMIT-000811 | NA | Consultant | Re: A12 CSP Mezzanine Level - updates | 1 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 822 | 2026-06-24 |  |  | 2026-07-06 | 2026-07-07 | KPTG-TRANSMIT-002726 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-22 | D&E-TRANSMIT-000855 | NA | Trade Partner | SFN Scripts - Issued for Construction | 0 | 2 | 0 | NA | APPROVED | 2026-06-22 | WF-006103 | NA | 2026-07-01 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-22 | SPECAUTO-TRANSMIT-000001 | NA | Trade Partner | CSMS Outstation Hardware Procurement Approval | 0 | 13 | 0 | NA | APPROVED | 2026-06-22 | WF-000236 | NA | 2026-07-01 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-001180 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-22 | KALLIBRE-TRANSMIT-000009 | NA | Trade Partner | Motorway Door Frame Shop Drawings IFA/IFC | 60 | 0 | 0 | NA | REJECTED | [5 empty] | Multiple drawing status IFA/IFC | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-001320 | Closed | 60 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-01-09 | KEECEPRO-TRANSMIT-000008 | NA | Trade Partner | Inground Shop Drawings | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision number |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-22 | NXT-PA-005454 | NA | Trade Partner | Fwd: Updated Shop Drawing Revision - Block C1 & C2 UI Catcher | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | EAEGROUP-TRANSMIT-000101 FOR DISTRIBUTION |  | 2026-06-22 | KPTG-TRANSMIT-018907 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-22 | ARCH-TRANSMIT-000048 | NA | Consultant | Architectural drawings for BP | 13 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings to be marked as no longer in use. Correct number to be superseded. Revision number inside a document needs to be corrected. |  | 2026-06-22 | KPTG-DA-000885 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-22 | Tradetec-TRANSMIT-000461 | NA | Trade Partner | Tech Data - Stage 2 - Convic Class C P8 lid | 0 | 1 | 0 | NA | APPROVED | 2026-06-22 | WF-006104 | NA | 2026-06-29 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-018940 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-22 | ARCST-TRANSMIT-000309 | NA | Trade Partner | Re: C2 Fire Room Roof Framing - Issued for Approval | 19 | 0 | 0 | NA | REJECTED | [5 empty] | REVISION OF ONE DRAWING ALREADY RECEIVED THEY SUBMITTED AGAIN |  | 2026-06-22 | KPTG-RFI-008538 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-06-22 | INSULPAK-TRANSMIT-000027 | NA | Trade Partner | HFF MSSB As Builts | 1 | 0 | 0 | NA | APPROVED |  | NA | 416 | 2026-07-03 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-22 | ARCST-TRANSMIT-000307 | NA | Trade Partner | C1 Cbiller Base Framing - Issued for Construction | 136 | 0 | 0 | NA | REJECTED | [5 empty] | IFC drawings have been received before obtaining the required IFA approval. |  | 2026-06-22 | KPTG-RFI-008539 | Closed | 136 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-22 | ADP-TRANSMIT-000083 | NA | Trade Partner | ADP MEL4680 - Electrical Reg 126 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with revision number. |  | 2026-06-22 | KPTG-TRANSMIT-000884 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-06-22 | INSULPAK-TRANSMIT-000028 | NA | Trade Partner | Power Pack MSSB As BuiltS | 1 | 0 | 0 | NA | APPROVED |  | NA | 417 | 2026-07-03 |  |  | 2026-07-23 | 2026-07-23 | DRAFT-010432 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-22 | Baigents-TRANSMIT-000007 | NA | Trade Partner | Precast Beam Prototype IFA | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Kapitol information only |  | 2026-06-22 | NA | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-22 | EUKAI-TRANSMIT-000016 | NA | Consultant | Transport Documentation | 24 | 0 | 0 | NA | REJECTED | [5 empty] | Revision not mentioned in drawing |  | 2026-06-22 | Awaiting approval | Closed | 24 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-19 | Altaire-TRANSMIT-000048 | NA | Trade Partner | Dry Fire IFC Shop Drawings - New Revision | 14 | 0 | 0 | NA | REJECTED | [5 empty] | Different revision numbers inside and outside. |  | 2025-12-19 | KPTG-DA-004034 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-22 | PTA-TRANSMIT-000008 | NA | Consultant | Revised Fire Stairs 1 to 7 - For Review | 7 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 246 | 2026-06-30 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-000421 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-22 | HDRAus-TRANSMIT-000514 | NA | Trade Partner | Rain Garden Updates | 3 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 4321 | 2026-06-29 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-020017 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-22 | PTA-TRANSMIT-000009 | NA | Consultant | Architectural GA Plan Issue - For Coordination | 17 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 250 | 2026-07-01 |  |  | 2026-07-02 | 2026-07-03 | KPTG-TRANSMIT-000432 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-22 | PTA-TRANSMIT-000010 | NA | Consultant | Block 1 Trench Grate, office slab and hob walls update in CPP - For Coordination | 2 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 252 | 2026-06-30 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-000414 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-22 | NXT-TRANSMIT-000422 | NA | Client | In ground services IFCN | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Already submitted |  | 2026-06-22 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-22 | TTW-TRANSMIT-000043 | NA | Consultant | Facade F3P1 PBDB naming update | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For information |  | 2026-06-22 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-22 | ADP-TRANSMIT-000084 | NA | Consultant | ADP MEL4680 - Updated IFC Drawings-CSMS | 8 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 286 | 2026-06-25 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-001023 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-22 | ADP-TRANSMIT-000084 | NA | Consultant | ADP MEL4680 - Updated IFC Drawings - ELC | 16 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 285 | 2026-06-25 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-001055 | Closed | 16 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-22 | ADP-TRANSMIT-000084 | NA | Consultant | ADP MEL4680 - Updated IFC Drawings - TEL | 9 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 284 | 2026-06-25 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-001005 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-11-21 | Stowe-A-SUBADVICE-000301 | NA | Trade Partner | L2 Comment Register | 0 | 2 | 0 | NA | APPROVED | 2025-12-02 | WF-003472 | NA | 2025-12-11 |  |  | 2026-02-12 | 2026-02-12 | KPTG-TRANSMIT-012779 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-09 | HDRAus-TRANSMIT-000354 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 13 | 0 | 0 | NA | APPROVED | [7 empty] | 2026-01-15 | KPTG-TRANSMIT-011332 | Closed | 13 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-22 | KALLIBRE-TRANSMIT-000010 | NA | Trade Partner | Motorway Door Frame Shop Drawings IFA | 20 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status inside drawing and in aconex seem different |  | 2026-06-22 | KPTG-TRANSMIT-001321 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-22 | D&E-TRANSMIT-000856 | NA | Trade Partner | SFN Scripts - Issued for Approval | 0 | 3 | 0 | NA | APPROVED | 2026-06-22 | WF-006106 | NA | 2026-07-01 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-22 | Nilsen3-TRANSMIT-000198 | NA | Trade Partner | M3 Stage 2 ROPS 2C & 2D Functional Description | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with revision number. |  | 2026-06-22 | KPTG-TRANSMIT-018891 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-22 | KALLIBRE-TRANSMIT-000011 | SPARK-CRFI-KPG-000623 | Trade Partner | Motorway Door Frame Shop Drawings IFC | 40 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 323 | 2026-06-29 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001393 | Closed | 40 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-22 | D&E-TRANSMIT-000853 | NA | Trade Partner | Roof Level - Chiller Room 4 Layout - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 3616 | 2026-07-02 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-019748 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-22 | DS-TRANSMIT-000121 | NA | Trade Partner | HYD shop drawings - EEWS Updates | 22 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 3619 | 2026-07-08 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-15 | D&E-TRANSMIT-000857 | NA | Trade Partner | Roof Level - Chilled Room Sections - Sheet 2 of 5 - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 3621 | 2026-07-01 |  |  | 2026-07-27 | 2026-07-27 | ⁠KPTG-TRANSMIT-020010 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-22 | ARCST-TRANSMIT-000308 | NA | Trade Partner | Re: C2 Chiller Base Framing - Issued for Construction | 98 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to some mistakes on the aconex and inside drawing |  | 2026-06-22 | KPTG-RFI-008543 | Closed | 98 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-22 | D&E-TRANSMIT-000852 | NA | Trade Partner | DX & VRF Air conditioning - Issued for construction | 0 | 2 | 0 | NA | APPROVED | 2026-06-22 | WF-006108 | NA | 2026-07-08 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-020441 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-22 | D&E-TRANSMIT-000849 | NA | Trade Partner | Heat Exchangers - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-06-22 | WF-006109 | NA | 2026-07-02 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-019889 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-17 | OveArup-TRANSMIT-000143 | NA | Trade Partner | M3 Stage 2 Structures _Site Inspect Report_S16 Switchroom and S17 South RW | 0 | 2 | 0 | NA | REJECTED | [7 empty] | 2025-12-19 | KPTG-DA-004035 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-22 | Baigents-TRANSMIT-000220 | NA | Trade Partner | Level 5 Ramp Beams FC-1 | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | fc doc send to all parties |  | 2026-06-22 | KPTG-TRANSMIT-003964 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-22 | Endfire-TRANSMIT-000079 | NA | Trade Partner | FIRE SERVICES - COMMISSIONING PLAN | 0 | 1 | 0 | NA | APPROVED | 2026-06-22 | WF-001119 | NA |  |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-004015 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-22 | RDSBIM-TRANSMIT-000210 | NA | Trade Partner | LINDRUM ¦ CPP ¦ L-06 ¦ IFC ¦ SUBMISSION | 1 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 672 | 2026-06-25 |  |  | 2026-06-24 | 2026-06-24 | KPTG-SADV-004638 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-22 | KPTG-INTCOM-000350 | NA | Trade Partner | Epoxy | 0 | 1 | 0 | NA | APPROVED | 2026-06-22 | WF-000798 | NA | 2026-06-24 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-002602 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-22 | INGEN3D-TRANSMIT-000122 | NA | Trade Partner | PC0504 & PC0709 - Revised & New IFA (19-06-2026) | 2 | 0 | 0 | NA | APPROVED | 2026-06-22 | WF-000767 | NA | 2026-07-08 |  |  | 2026-07-01 | 2026-07-01 | NA - Work flow Terminated as instructed | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-22 | INGEN3D-TRANSMIT-000123 | NA | Trade Partner | Level 21-23 - Precast Columns - IFA (22-06-2026) | 26 | 0 | 0 | NA | APPROVED | 2026-06-22 | WF-000768 | NA | 2026-07-08 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-003097 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-22 | INGEN3D-TRANSMIT-000124 | NA | Trade Partner | Level 22 - Precast Columns - IFA (22-06-2026) | 19 | 0 | 0 | NA | APPROVED | 2026-06-22 | WF-000769 | NA | 2026-06-24 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-003047 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-22 | Jangho-TRANSMIT-000180 | NA | Trade Partner | Structural Calculation For 3F and Above Channel Embedded Calculation_Rev 02 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | REJECTED BY COORDINATOR |  | 2026-06-22 | KPTG-SADV-003261 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-22 | Jangho-TRANSMIT-000181 | NA | Trade Partner | Podium Level 3 Cast in Channel Shop Drawing_PDF_Rev 01 | 5 | 0 | 0 | NA | REJECTED | [5 empty] | rejected: QA ERROR STATUS FIELD |  | 2026-06-22 | KPTG-TRANSMIT-002429 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-22 | Jangho-TRANSMIT-000182 | NA | Trade Partner | Structural Calculation For Tower Shop Drawing At 6F-16F_Rev 02_For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-22 | WF-000771 | NA | 2026-07-02 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-002651 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-09 | HDRAus-TRANSMIT-000355 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 13 | 0 | 0 | NA | APPROVED | 2026-01-09 |  | 1745 | 2026-01-13 |  |  |  | 2026-01-15 | KPTG-TRANSMIT-011481 | Closed | 13 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-22 | OveArup-TRANSMIT-000041 ELC | NA | Consultant | Electrical, fire and hydraulic services IFC | 40 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 827 | 2026-06-24 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-002712 | Closed | 40 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-22 | OveArup-TRANSMIT-000041 FIR | NA | Consultant | Electrical, fire and hydraulic services IFC | 5 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 828 | 2026-06-24 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-002709 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-22 | OveArup-TRANSMIT-000041 HYD | NA | Consultant | Electrical, fire and hydraulic services IFC | 6 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 829 | 2026-06-24 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-002706 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-22 | OveArup-TRANSMIT-000041 - CALC | NA | Consultant | Electrical, fire and hydraulic services IFC | 0 | 5 | 0 | NA | APPROVED | 2026-06-22 | WF-000776 | 822 | 2026-06-24 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002943 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-22 | OveArup-TRANSMIT-000041 - CER | NA | Consultant | Electrical, fire and hydraulic services IFC | 1 | 3 | 0 | NA | APPROVED | 2026-06-22 | WF-000777 | NA | 2026-06-24 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002933 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-22 | WAM-TRANSMIT-000812 | NA | Consultant | Electrical, fire and hydraulic services IFC | 1 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED : STATUS FIELD ERROR |  | 2026-06-22 | KPTG-TRANSMIT-002439 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-22 | PCForm-TRANSMIT-000242 | NA | Trade Partner | Zincote sample submission | 0 | 1 | 0 | NA | APPROVED | 2026-06-22 | WF-000775 | NA | 2026-06-26 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-003346 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-22 | PCForm-TRANSMIT-000243 | NA | Trade Partner | Pavecure W sample submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | REJECTED: DOC NO ERROR |  | 2026-06-22 | KPTG-TRANSMIT-002437 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-22 | L.E.S.-TRANSMIT-000016 | NA | Trade Partner | Cable Pits Technical Data | 0 | 2 | 0 | NA | APPROVED | 2026-06-22 | WF-000778 |  | 2026-06-26 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-002570 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-22 | PCForm-TRANSMIT-000247 | NA | Trade Partner | Level 2 update drawings | 6 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED: DOC NO ERROR |  | 2026-06-22 | KPTG-TRANSMIT-002439 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-19 | ARCST-TRANSMIT-000166 | NA | Trade Partner | Stage 2 - Lower Ground Additional Stairs - Issued for Review | 78 | 0 | 0 | NA | APPROVED | 2025-12-22 | WF-003688 | NA | 2026-01-07 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-22 | Auspan-TRANSMIT-000404: | NA | Trade Partner | Update IFCed precast shop drawings for construction. Level 1. | 11 | 0 | 0 | KPTG-IntCorr-000744 | APPROVED |  | NA | NA |  |  | IFC - Kim to Confirm - KPTG-IntCorr-000744 4 are rejected as commented by Kim -KPTG-SADV-003188 3 drawings already superseded. And 4 registered and transmitted. KPTG-TRANSMIT-002530 |  | 2026-06-30 | KPTG-TRANSMIT-002530 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-22 | Auspan-TRANSMIT-000405 | NA | Trade Partner | : Precast shop drawings for construction. Level 2 | 15 | 0 | 0 | KPTG-IntCorr-000745 | APPROVED |  | NA | NA |  |  | IFC - Kim to Confirm - KPTG-IntCorr-000745 KPTG-IntCorr-000794 4 are ok to proceed; Register & Transmit KPTG-TRANSMIT-002535 11 are to be rejected as per comments and returned DRAFT-009135 |  | 2026-07-01 | KPTG-TRANSMIT-002535 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-22 | Auspan-TRANSMIT-000406: | NA | Trade Partner | Precast shop drawings for construction. Level 3, 4 | 66 | 0 | 0 | KPTG-IntCorr-000746 | APPROVED |  | NA | NA |  |  | IFC - Kim to Confirm -KPTG-IntCorr-000746 18 = Ok to proceed; Register and transmit - KPTG-TRANSMIT-002541 47 - Returned to Auspan. As advised by KIM (36 on Hold) -DRAFT-009187 1 Rejected -DRAFT-009189 |  | 2026-07-01 | KPTG-TRANSMIT-002541 | Closed | 66 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-22 | Auspan-TRANSMIT-000407 | NA | Trade Partner | : Update panel 2P342 | 1 | 0 | 0 | KPTG-IntCorr-000747 | REJECTED |  | NA | NA |  |  | IFC - Kim to Confirm KPTG-IntCorr-000747 Rejected by Project Coordinator. KPTG-SADV-003167 |  | 2026-06-30 | KPTG-SADV-003167 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-22 | RDSBIM-TRANSMIT-000074 671 | NA | Trade Partner | CHP CPP BASEMENT 1 IFC SUBMISSION | 3 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 579 | 2026-06-29 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-001668 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-22 | RDSBIM-TRANSMIT-000075 | NA | Trade Partner | 671 CHP BLOCKWORK BASEMENT B03 IFA SUBMISSION | 1 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 582 | 2026-06-29 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-001512 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-22 | WSP ANZ-TRANSMIT-000083 | NA | Consultant | CSMS SOW update | 0 | 1 | 0 | NA | APPROVED | 2026-06-22 | NA | 1170 | 2026-06-25 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-004808 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-22 | HGP-TRANSMIT-000007 | NA | Trade Partner | Sample Transmittal Rev B | 0 | 8 | 0 | NA | APPROVED | 2026-06-22 | WF-001016 | NA | 2026-07-01 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-005072 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-22 | WilsonPD-TRANSMIT-000090 | NA | Trade Partner | Updated Leak Detection Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-06-22 | WF-001013 | NA | 2026-07-01 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-005427 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-22 | WilsonPD-TRANSMIT-000091 | NA | Trade Partner | Trap Priming device tech data | 0 | 1 | 0 | NA | APPROVED | 2026-06-22 | WF-001014 | NA | 2026-07-01 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-005423 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-19 | VIA Arch-TRANSMIT-000036 | NA | Consultant | Architectural WIP 70% Issue | 129 | 0 | 0 | NA | APPROVED | 2026-01-09 |  | 170 | 2026-01-16 |  | As per KG advise, this review is not relevant as these drawings will get revised due to major design change |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-22 | Nilsen3-TRANSMIT-000050 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 2 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 1173 | 2026-06-26 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-005031 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-22 | Nilsen3-TRANSMIT-000050 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 2 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 1174 | 2026-06-26 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-005211 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-23 | Auspan-TRANSMIT-000411 | NA | Trade Partner | Precast shop drawings for approval. Level 2 | 8 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 1309 | 2026-06-30 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-002622 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-23 | RDSBIM-TRANSMIT-000280 | NA | Trade Partner | RDS NXM3S4 PRECAST WALL ELEVATION IFC FOR SUBMISSION | 23 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 3624 | 2026-06-25 |  | terminated as per requested by elli salmon |  | 2026-06-23 | KPTG-TRANSMIT-018988 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-23 | Auspan-TRANSMIT-000410 | NA | Trade Partner | Resubmit precast shop drawings for approval. Level 1 zone 4, 5 | 2 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 1311 | 2026-06-30 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-002547 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-23 | Altaire-TRANSMIT-000114 | NA | Trade Partner | M3 Commissioning Workflow Stage 3 and Stage 4 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Ref Number is Missing |  | 2026-06-23 | KPTG-RFI-008555 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-23 | Auspan-TRANSMIT-000412 | NA | Trade Partner | Precast shop drawings for approval. Levels 4, 5 | 1 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 1314 | 2026-06-30 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002817 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-23 | SKS Tech-TRANSMIT-000172 | NA | Trade Partner | Fwd: Submain schedule no longer in use | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | NLIU |  | 2026-06-23 | KPTG-TRANSMIT-018945 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-23 | Tradetec-TRANSMIT-000462 | NA | Trade Partner | IFC - Stage 4 - CP32, LVP35 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | IFA and IFC have been submitted in the same transmittal. |  | 2026-06-23 | KPTG-RFI-008556 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-23 | SKS Tech-TRANSMIT-000173 | NA | Trade Partner | Fwd: Legend & General notes no longer in use | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | NLIU |  | 2026-06-23 | KPTG-TRANSMIT-018946 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-09 | VIA Arch-TRANSMIT-000038 | NA | Consultant | Architectural WIP 70% Issue | 8 | 0 | 0 | NA | APPROVED | 2026-01-09 |  | 170 | 2026-01-16 |  | As per KG advise, this review is not relevant as these drawings will get revised due to major design change |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-23 | RDSBIM-TRANSMIT-000279 | NA | Trade Partner | NXM3S4 - LEVEL 01 - C-1-044 ACC WC - IFC - FOR SUBMISSION | 1 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 3626 | 2026-06-25 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-019457 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-23 | KALLIBRE-TRANSMIT-000012 | SPARK-CRFI-KPG-000623 | Trade Partner | Re: Door Frame Shop Drawings IFC | 1 | 0 | 0 | KPTG-IntCorr-003274 | APPROVED | 2026-06-23 | NA | 324 | 2026-06-30 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001390 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-23 | D&E-TRANSMIT-000860 | NA | Trade Partner | NXM3S4 - Ground - CHW Pipe Layout + Industrial Water Tank Layouts - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 3631 | 2026-07-02 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-020538 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-23 | NXT-TRANSMIT-001631 | NA | Trade Partner | Fwd: P2685 - NDC M3 - Stage 4 - Battery Rooms - DAMPER AND FAN SCHEDULE | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-06-23 | KPTG-TRANSMIT-018948 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-23 | PARR-TRANSMIT-000196 | NA | Trade Partner | Fwd: P2685 - NDC M3 - Stage 4 - Battery Rooms - DAMPER AND FAN SCHEDULE | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-06-23 | KPTG-TRANSMIT-018948<br> | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-23 | KALLIBRE-TRANSMIT-000013 | NA | Trade Partner | Door Frame Shop Drawings IFA | 20 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status in title block incorrecr |  | 2026-06-23 | KPTG-TRANSMIT-001322 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-23 | Auspan-TRANSMIT-000413 | NA | Trade Partner | : Resubmit precast shop drawing 4P303 for approval. | 1 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 1316 | 2026-06-30 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-002623 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-23 | Auspan-TRANSMIT-000409 | NA | Trade Partner | Precast shop drawings for construction | 42 | 0 | 0 | KPTG-IntCorr-000760 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise- KPTG-IntCorr-000760 19 are OK to proceed -KPTG-IntCorr-000812 ; Register and Transmit. KPTG-TRANSMIT-002531. 24 rejected as per Kim's comments and returned to Auspan -DRAFT-009129 1 drawing already superseded. |  | 2026-07-01 | KPTG-TRANSMIT-002531 | Closed | 42 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-23 | Auspan-TRANSMIT-000409 | NA | Trade Partner | Precast shop drawings for construction | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Rejected due to QC issues - DRAFT-008736 |  | 2026-06-23 | DRAFT-008736 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-05 | INGEN3D-TRANSMIT-000694 | NA | Consultant | I3D-378 Next DC M3 Stage 4 - Acoustic Wall - IFA Checked (04-03-2026 | 6 | 0 | 0 | NA | APPROVED | 2026-03-05 | WF-004634 | NA | 2026-06-12 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-018950 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-09 | SKS Tech-TRANSMIT-000122 | NA | Trade Partner | 110V DC Battery Charger System | 0 | 1 | 0 | NA | APPROVED | 2026-01-09 | WF-000683 | NA | 2026-01-15 |  |  | 2026-01-16 | 2026-01-16 | KPTG-WTRAN-001352 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-23 | Nilsen3-TRANSMIT-000051 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 2 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 1177 | 2026-06-30 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-005122 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-23 | BIMF-TRANSMIT-000002 | NA | Trade Partner | Re: Level 4 Hydraulic Setouts | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Revision and drawing status different as per Aconex submission and drawing. |  | 2026-06-23 | KPTG-TRANSMIT-002454 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-23 | PCForm-TRANSMIT-000248 | NA | Trade Partner | Re: XL 65mpa 700 spread mix design for approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document number error |  | 2026-06-23 | KPTG-TRANSMIT-002451 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-23 | Ardon-TRANSMIT-000051 | NA | Trade Partner | Priority 6 Door Frame Shop Drawings | 34 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 3629 | 2026-07-05 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-019175 | Closed | 34 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-23 | KALLIBRE-TRANSMIT-000014 | SPARK-CRFI-KPG-000623 | Trade Partner | Re: Door Frame Shop Drawings IFA | 20 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 325 | 2026-06-30 |  | IFA, No Ineight review. Bim360 review closed and transmitted as per Chelsea advise | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-001395 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-23 | INTRFRM-TRANSMIT-000086 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 19) | 0 | 2 | 0 | NA | APPROVED | 2026-06-23 | WF-000238 | NA | 2026-07-02 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-000901 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-23 | SES AU-TRANSMIT-000064 | NA | Trade Partner | SECURITY- SCEC LAYOUTS - IFC | 3 | 0 | 0 | NA | APPROVED | 2026-06-23 | WF-000345 | NA | 2026-06-25 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000978 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-23 | Entire M-TRANSMIT-000073 | NA | Trade Partner | -Mechanical coversheet - IFC | 1 | 0 | 0 | NA | APPROVED | 2026-06-23 | WF-000346 | NA | 2026-06-26 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-000953 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-23 | TATE_-TRANSMIT-000030 | NA | Trade Partner | Re: Issue uploading drawings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Revision needs to be updated:KPTG-IntCorr-000609 |  | 2026-06-23 | KPTG-IntCorr-000609 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-12 | RDSBIM-TRANSMIT-000178 | NA | Trade Partner | NXM3S4 ¦ GROUND FLOOR-C-G-064 UNISEX WC FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-01-12 |  | 1749 | 2026-01-16 |  | The register has been updated. We are waiting for a response from the Kapitol team. |  | 2026-01-20 | KPTG-TRANSMIT-011733 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-23 | WilsonPD-TRANSMIT-000014 | NA | Trade Partner | Hydraulic Services Layouts For Approval | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status, Revision date and title mismatch. |  | 2026-06-23 | KPTG-SADV-000715 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-23 | SES AU-TRANSMIT-000063 | NA | Trade Partner | SCEC LAYOUT - Reticulation Pathways | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Document Numbering is incorrect:KPTG-IntCorr-000610 |  | 2026-06-23 | :KPTG-IntCorr-000610 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-23 | Entire M-TRANSMIT-000072 | NA | Trade Partner | Mechanical coversheet - IFC | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Attachment of Drawings is wrong:KPTG-IntCorr-000611 |  | 2026-06-23 | :KPTG-IntCorr-000611 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-06-23 | INSULPAK-TRANSMIT-000029 | NA | Trade Partner | Power Pack As Builts | 8 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 418 | 2026-07-06 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-06-23 | INSULPAK-TRANSMIT-000030 | NA | Trade Partner | HFF As Builts | 11 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 419 | 2026-07-06 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-23 | Eneraque-TRANSMIT-000032 | NA | Trade Partner | Pump Skid Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-06-23 | WF-001033 | 1179 | 2026-06-30 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-005446 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-23 | Eneraque-TRANSMIT-000033 | NA | Trade Partner | Stage 9 Ground Level Pipework Layout Fuel Storage Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-06-23 | WF-001034 | 1181 | 2026-06-30 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-005541 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-23 | M.2-TRANSMIT-000054 | NA | Trade Partner | Electrical Services Level 02-05 Penetration layouts | 5 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 1319 | 2026-06-30 |  | Review void as requested by trade partner to update the drawings and as advised by Kapitol PC, Drawings superseded via TN#M.2-TRANSMIT-000055 | 2026-06-24 | 2026-06-24 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-23 | PCForm-TRANSMIT-000249 | NA | Trade Partner | Pavecure amended Doc no. | 0 | 1 | 0 | NA | APPROVED | 2026-06-23 | WF-000780 | NA | 2026-06-26 |  |  | 2026-06-26 | 2026-07-01 | KPTG-TRANSMIT-002635 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-23 | Civilex-TRANSMIT-000107 | NA | Trade Partner | Re: Trench Grate | 0 | 1 | 0 | NA | APPROVED | 2026-06-23 | WF-000782 | NA | 2026-07-02 |  | In workflow for WAM review | 2026-07-07 | 2026-07-07 | WF-000898 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-12 | RDSBIM-TRANSMIT-000179 | NA | Trade Partner | NXM3S4 ¦ GROUND FLOOR-C-G-056 MALE WC-FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-01-12 |  | 1750 | 2026-01-16 |  | The register has been updated. We are waiting for a response from the Kapitol team. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-23 | ADP-TRANSMIT-000085 | NA | Consultant | ADP MEL4680 - Electrical Reg 126 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For updation only. |  | 2026-06-23 | KPTG-TRANSMIT-000886 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-23 | Jangho-TRANSMIT-000183 | NA | Trade Partner | Re: Structural Calculation For 3F and Above Channel Embedded Calculation_Rev 02 | 0 | 1 | 0 | NA | APPROVED | 2026-06-23 | WF-000779 | NA | 2026-07-02 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-002652 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-23 | POTTSENG-TRANSMIT-000053 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - PENETRATION - LEVELS 03-05 - ZONES 1-5 LAYOUTS | 15 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 1323 | 2026-06-30 |  |  |  | 2026-07-17 | KPTG-TRANSMIT-002841 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-23 | INGEN3D-TRANSMIT-000125 | NA | Trade Partner | I3D-389 District Living - Level 12-14 - PC0711 - New IFA (23-06-2026) | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Revision difference |  | 2026-06-23 | DRAFT-012136 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-23 | WAM-TRANSMIT-000813 | NA | Consultant | Facade details on CAD format as requested. | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | CAD Files send to all parties |  | 2026-06-23 | KPTG-TRANSMIT-002457 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-23 | Nilsen3-TRANSMIT-000205 | NA | Trade Partner | Re: Nilsen Shop Drawings - IFC | 13 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due revision mistakes |  | 2026-06-23 | KPTG-RFI-008566 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-23 | Altaire-TRANSMIT-000115 | NA | Trade Partner | Fwd: NEXTDC M3S4 - Dry Fire Cx Plan (For Construction) | 0 | 1 | 0 | NA | APPROVED | 2026-06-23 | NA | NA |  |  | ONLY FOR DISTRIBUTION |  | 2026-06-23 | KPTG-TRANSMIT-018967 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-23 | Civilex-TRANSMIT-000272 | NA | Trade Partner | Stage 4 - sample submission - Crash Barrier | 0 | 1 | 0 | NA | APPROVED | 2026-06-23 | WF-006114 | NA | 2026-07-08 |  |  | 2026-07-13 | 2026-07-13 | ⁠KPTG-TRANSMIT-019609 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-23 | INGEN3D-TRANSMIT-000715 | NA | Consultant | Re: I3D-378 Next DC M3 Stage 4 - Acoustic Wall - LP2018, PW1922, PW1925 & PW1935 - IFC | 3 | 0 | 0 | NA | APPROVED | 2026-06-23 | WF-006113 | NA | 2026-07-08 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-23 | D&E-TRANSMIT-000858 | NA | Trade Partner | Re: IW Pumps Acoustic Report - Issued for Review | 0 | 1 | 0 | NA | REJECTED | [5 empty] | rejected due to missing of document details |  | 2026-06-23 | KPTG-RFI-008559 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-12 | W TITE-TRANSMIT-000006 | NA | Trade Partner | M3-WPF-WTW-TD-S-0301-0001-Tremco Tremproof 250GC | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number- |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-23 | 4DW-TRANSMIT-000057 | NA | Consultant | Issued for Certification: Level 1 Block 1 Floor Design | 9 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 256 | 2026-07-01 |  | 4DW-TRANSMIT-000054 superseded | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-000757 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-23 | 4DW-TRANSMIT-000058 | NA | Consultant | Structural Documentation: NLB Feature Precast Walls (Issued for Construction). | 2 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 258 | 2026-07-01 |  | 4DW-TRANSMIT-000055&56 -superseded | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-000756 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-23 | PTA-TRANSMIT-000011 | NA | Consultant | Revised Fire Stairs 8 to 11 - For Review | 4 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 260 | 2026-07-01 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-000988 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-23 | PTA-CRFI-000036-Safetech | NA | Trade Partner | Loading Dock Review | 8 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 263 | 2026-07-01 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-000612 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-23 | JCBa-TRANSMIT-000141 | NA | Consultant | : Door Schedule | 1 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 1321 | 2026-06-25 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-002495 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-23 | RDSBIM-TRANSMIT-000077 | NA | Trade Partner | 671 CHP CPP GROUND FLOOR IFA SUBMISSION | 4 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 584 | 2026-06-30 |  | Review voided to issue updated drawings by RDS | 2026-06-25 | 2026-06-25 | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-23 | RDSBIM-TRANSMIT-000076 | NA | Trade Partner | 671 CHP BLOCKWORK BASEMENT B02 IFA SUBMISSION | 1 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 586 | 2026-06-30 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-001651 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-23 | INGEN3D-TRANSMIT-000126 | NA | Trade Partner | Level 14-16 - PC0522-10 & PC539-4 - New IFA (23-06-2026) | 2 | 0 | 0 | NA | APPROVED | 2026-06-23 | WF-000783 | NA | 2026-07-10 |  |  | 2026-07-01 | 2026-07-01 | Work flow Terminated as instructed | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-23 | INGEN3D-TRANSMIT-000127 | NA | Trade Partner | Level 16-18 - PC0522-11 & PC0539-5 - New IFA (23-06-2026) | 2 | 0 | 0 | NA | APPROVED | 2026-06-23 | WF-000784 | NA | 2026-07-10 |  |  | 2026-07-01 | 2026-07-01 | Work flow Terminated as instructed | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-23 | KPTG-TRANSMIT-002591 | NA | Trade Partner | Fwd: Drainage and Water Drawings - IFA | 35 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 674 | 2026-06-23 |  |  | 2026-07-09 | 2026-07-09 | KPTG-SADV-004860 | Closed | 35 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-01 | RDSBIM-TRANSMIT-000011 | NA | Trade Partner | 671CHP LEVEL 02 CONCRETE PROFILE PLAN AND SECTION | 3 | 0 | 0 | NA | APPROVED | 2025-12-01 | WF-000244 | NA | 2025-12-03 |  | Review void as advised during a meeting with Kapitol DM & PCs. Review Reinitiated on 27-01-26 27/2/25 as advised by KAPITOL PC, ACC review 231 is VOID and initiated ACC review - WF-000244 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-02 | TTW-TRANSMIT-000141 | NA | Client | Stage 2 Drainage Longsections | 2 | 0 | 0 | NA | APPROVED |  | NA | 3399 | 2025-12-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-11 | Auspan-TRANSMIT-000034 | NA | Trade Partner | Precast shop drawings for construction. | 19 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing need to be updated (KPTG-SADV-000576) |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-17 | KPTG-TRANSMIT-002561 | NA | Trade Partner | Sample for Review | 0 | 1 | 0 | NA | APPROVED | 2026-06-17 | WF-000795 | NA | 2026-06-19 |  |  | 2026-06-23 | 2026-06-23 | KPTG-IntCorr-001097 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-23 | fjc-TRANSMIT-000158 | NA | Trade Partner | Architecturals - L6 + L10 CPP | 2 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 673 | 2026-06-26 |  |  | 2026-06-24 | 2026-06-24 | KPTG-SADV-004641 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-23 | KPTG-CONTADV-000196 | NA | Trade Partner | MEL05C4 BU Cleanliness and Maintenance Plan | 0 | 2 | 0 | NA | APPROVED | 2026-06-23 | WF - 000492 | NA | 2026-06-30 |  | NA | 2026-06-24 | 2026-06-24 | KPTG-WTRAN-000897 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-25 | KPTG-IntCorr-000516 | NA | Trade Partner | HAC Review (Elec) | 0 | 1 | 0 | NA | APPROVED | 2026-06-25 | WF - 000502 | NA | 2026-06-30 |  | NA | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001076 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-25 | KPTG-IntCorr-000517 | NA | Trade Partner | HAC Review (Telecom) | 0 | 1 | 0 | NA | APPROVED | 2026-06-25 | WF - 000503 | NA | 2026-06-30 |  | NA | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-001137 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-25 | KPTG-IntCorr-000518 | NA | Trade Partner | HAC Review (Security) | 0 | 1 | 0 | NA | APPROVED | 2026-06-25 | WF - 000505 | NA | 2026-06-30 |  | NA | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-001098 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-25 | KPTG-IntCorr-000519 | NA | Trade Partner | HAC Review (Fire) | 0 | 3 | 0 | NA | APPROVED | 2026-06-25 | WF - 000506 | NA | 2026-06-30 |  | NA | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-001092 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-25 | KPTG-IntCorr-000520 | NA | Trade Partner | HAC Review (BAS) | 0 | 1 | 0 | NA | APPROVED | 2026-06-25 | WF - 000507 | NA | 2026-06-30 |  | NA | 2026-06-25 | 2026-06-25 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-23 | KPTG-IntCorr-000521 | NA | Trade Partner | Kapitol Cx Plan - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF - 000498 | NA | 2026-06-30 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-23 | KPTG-IntCorr-000523 | NA | Trade Partner | BU Cleanliness and Maintenance Plan | 0 | 1 | 0 | NA | APPROVED | 2026-06-23 | WF - 000492 | NA | 2026-06-30 |  | NA | 2026-06-25 | 2026-06-25 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-12 | ARCST-TRANSMIT-000173 | NA | Trade Partner | Stage 4 - C3 Gantry Roof`& Secondary Steel - Issued for Approval doc-124 | 124 | 0 | 0 | NA | REJECTED | [5 empty] | The documents do not have the correct revision history date |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-23 | KPTG-IntCorr-000524 | NA | Trade Partner | Kapitol Cx Plan - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-23 | WF - 000498 | NA | 2026-06-30 |  | NA | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-001115 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-23 | SMEPS-IntCorr-000329 | NA | Trade Partner | MEL05C4 BU Temp Power Plan | 0 | 1 | 0 | NA | APPROVED | 2026-06-23 | WF - 000491 | NA | 2026-06-30 |  | Terminated | 2026-06-23 | 2026-06-23 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-23 | DLTS-TRANSMIT-000030 | NA | Trade Partner | HV Room 2-IFA Issue | 111 | 0 | 0 | NA | APPROVED | 2026-06-23 | WF-001025 | NA | 2026-07-02 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-005351 | Closed | 111 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-23 | DLTS-TRANSMIT-000032 | NA | Trade Partner | S9-North Eave Gutter-Updated Documents | 23 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, updated register and distributed |  | 2026-06-23 | KPTG-TRANSMIT-004620 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-23 | ELLISAIR-TRANSMIT-000077 | NA | Trade Partner | Heat Exchangers | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC, No review required, updated and distributed |  | 2026-06-23 | KPTG-TRANSMIT-004604 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-23 | SMEPS-TRANSMIT-000054 | NA | Trade Partner | SME Bracket Sample Submittal | 0 | 7 | 0 | NA | APPROVED | 2026-06-23 | WF-001036 | NA | 2026-07-02 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-005294 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-23 | ELLISAIR-TRANSMIT-000076 | NA | Trade Partner | Functional Description | 0 | 1 | 0 | NA | APPROVED | 2026-06-23 | WF-001020 | NA | 2026-07-03 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-005567 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-23 | WilsonPD-TRANSMIT-000093 | NA | Trade Partner | Equipment IFC | 0 | 9 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC, No review required. Updated register and distributed |  | 2026-06-23 | KPTG-TRANSMIT-004623 | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-23 | PROLMC-GCOR-000006 | NA | Trade Partner | Sample Technical Data Sheet Submission | 0 | 1 | 0 | NA | APPROVED | 2026-06-23 | WF-001028 | NA | 2026-07-02 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-004735 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-24 | RDSBIM-TRANSMIT-000217 | NA | Trade Partner | ¦ L03 EXTERNAL AREA CPP ¦ IFC | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Distribution only. |  | 2026-06-24 | KPTG-TRANSMIT-003079 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-12 | vdmcons-TRANSMIT-000014 | N/A | Trade Partner | ME25 1144: D10 - M3 Stage 3 GIS Building - M3 Stage 3 Switch Room - Shop Drawings & 3D IFC Model - IFF - 2026-01-12 | 1 | 0 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-24 | SKS Tech-TRANSMIT-000176 | NA | Trade Partner | Re: Updated Lighting report | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Reference number is missing |  | 2026-06-24 | KPTG-RFI-008567 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-24 | TATE_-TRANSMIT-000032 | NA | Trade Partner | Re: Issue uploading drawings | 1 | 0 | 0 | NA | APPROVED | 2026-06-24 | WF-000347 | NA | 2026-06-26 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-000961 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-24 | Auspan-TRANSMIT-000416 | NA | Trade Partner | Precast shop drawings for approval. Level 4, 5 | 36 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 1325 | 2026-07-01 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-002869 | Closed | 36 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-24 | JCBa-TRANSMIT-000142 | NA | Consultant | Architectural Documentation - Misc Interior drawings | 4 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 1327 | 2026-06-26 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-002521 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | RDSBIM-TRANSMIT-000049 | NA | Trade Partner | DISTLV ¦ GROUND LEVEL ¦ IFC ¦ SUBMISSION | 7 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 833 | 2026-06-27 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-002609 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-24 | SES AU-TRANSMIT-000065 | NA | Trade Partner | SECURITY - COLO 5 RACK ELEVATIONS | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Wrong Attachment:KPTG-IntCorr-000615 |  | 2026-06-24 | :KPTG-IntCorr-000615 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | WAM-TRANSMIT-000814 | NA | Consultant | A41 - Updates and IFC | 4 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 835 | 2026-06-27 |  | Drawings are Retransmitted by WAM-TRANSMIT-000817 |  | 2026-06-25 | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-24 | RDSBIM-TRANSMIT-000074 | NA | Trade Partner | GREYSTAR ¦ GF ¦ ZONE 3 ¦ CPP ¦ IFC ¦ FOR SUBMISSION | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Drawing - no review, updated register and distributed (KPTG-TRANSMIT-002416) |  | 2026-06-24 | KPTG-TRANSMIT-002416 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-24 | Auspan-TRANSMIT-000414 | NA | Trade Partner | Update IFCed precast shop drawings for construction | 18 | 0 | 0 | KPTG-IntCorr-000766 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise- KPTG-IntCorr-000766 KPTG-SADV-003106 |  | 2026-06-25 | KPTG-SADV-003106 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-24 | Ardon-TRANSMIT-000052 | NA | Trade Partner | Priority 7 Door Frame Shop Drawings | 37 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 3633 | 2026-07-06 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-019385 | Closed | 37 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-12 | W TITE-TRANSMIT-000007 | NA | Trade Partner | Tremco Tremproof 250GC | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect revision number |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-24 | Auspan-TRANSMIT-000415 | NA | Trade Partner | Resubmit precast shop drawings for approval. Level 1 zone 3. 1P348 and 1P349 | 2 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 1330 | 2026-07-01 |  | Rejected by Reviewer. | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-002628 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-24 | SKS Tech-TRANSMIT-000179 | NA | Trade Partner | Legend and General notes | 1 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 3695 | 2026-07-06 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-02 | SKS Tech-TRANSMIT-000154 | NA | Trade Partner | Re: UpRev busduct layout for datahalls | 4 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 3406 | 2026-06-09 |  | As requested by Damian- Terminated |  | 2026-06-24 | KPTG-TRANSMIT-019000 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-24 | 4DW-TRANSMIT-000188 | NA | Consultant | Structural Documentation - Landscape updates | 2 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 334 | 2026-06-29 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-003035 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-24 | PFP PL-TRANSMIT-000091 | NA | Trade Partner | Mech Corridor Under Duct Sprinkler Dwg Updates | 6 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 3637 | 2026-07-03 |  |  |  | 2026-06-29 | As requested by Ellie, - Terminated KPTG-IntCorr-015362 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-24 | WilsonPD-TRANSMIT-000015 | NA | Trade Partner | HYDRAULIC SERVICES LAYOUTS ISSUED FOR APPROVAL | 8 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 288 | 2026-07-01 |  | Terminated as directed by Chri Doh for submitting updated document. | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-000990 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-24 | RDSBIM-TRANSMIT-000281 | NA | Trade Partner | NXM3S4 - LEVEL-1-C-1-047 FEMALE WC FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 3639 | 2026-06-26 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-019459 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-24 | ZIA-TRANSMIT-000061 | NA | Trade Partner | CSMS Cable Schedule | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected, QA error |  | 2026-06-24 | KPTG-IntCorr-001541 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-24 | TURN--TRANSMIT-000008 | NA | Trade Partner | Steel PFC Shop Drawings Rev 1 | 19 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings incorrectly registered in Aconex |  | 2026-06-24 | KPTG-DA-000381 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-24 | RDSBIM-TRANSMIT-000061 | SPARK-CRFI-KPG-000362 | Trade Partner | MWYCCB ¦ SITE STORAGE BUILDING GF & LEVEL 01 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 326 | 2026-07-01 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-001352 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-12 | ARCST-TRANSMIT-000172 | NA | Trade Partner | SHOP DRAWING ¦ CONSULTANT REVIEW ¦ IFA ¦ ROOF STEEL WORKFLOW | 11 | 0 | 0 | NA | APPROVED | 2026-01-12 | WF-004611 | NA | 2026-02-13 |  |  |  | 2026-03-10 | KPTG-TRANSMIT-014075 | Open | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-24 | D&E-TRANSMIT-000270 | SPARK-CRFI-KPG-000313 | Trade Partner | MWYCCB - GROUND LEVEL + SCHEMATICS - Issued For Construction | 3 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 327 | 2026-07-01 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-001331 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | PCForm-TRANSMIT-000252 | NA | Trade Partner | Fwd: 65mpa 650 spread mix for approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Title difference in ACONEX and inside the document |  | 2026-06-24 | KPTG-TRANSMIT-002491 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | L.E.S.-TRANSMIT-000017 | NA | Trade Partner | Transmittal - SLD MSB, MDB, Load centre IFA | 3 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 831 | 2026-07-01 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-002679 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | Jangho-TRANSMIT-000185 | NA | Trade Partner | Window Hardware Sample Submission（Snap shut） | 0 | 1 | 0 | NA | APPROVED | 2026-06-24 | WF-000786 | NA | 2026-07-10 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-002660 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | Jangho-TRANSMIT-000186 | NA | Trade Partner | Siliding Door Sample Submission（Anti-collision block） | 0 | 1 | 0 | NA | APPROVED | 2026-06-24 | WF-000787 | NA | 2026-07-10 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-002661 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | Jangho-TRANSMIT-000187 | NA | Trade Partner | Siliding Door Sample Submission（Handle） | 0 | 1 | 0 | NA | APPROVED | 2026-06-24 | WF-000788 | NA | 2026-07-10 |  |  | 2026-07-06 | 2026-07-01 | KPTG-TRANSMIT-002613 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-24 | D&E-TRANSMIT-000271 | SPARK-CRFI-KPG-000572 | Trade Partner | MWYCCB - LEVEL 1 - RCP LAYOUT + MECH.ELEC LAYOUT SHEETS - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 328 | 2026-07-01 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-001333 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | Jangho-TRANSMIT-000188 | NA | Trade Partner | Siliding Door Sample Submission（Siliding roller） | 0 | 1 | 0 | NA | APPROVED | 2026-06-24 | WF-000789 | NA | 2026-07-10 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-002695 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-24 | SKS Tech-TRANSMIT-000180 | NA | Trade Partner | Busduct Layout - Catcher | 4 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 3646 | 2026-07-06 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | Jangho-TRANSMIT-000189 | NA | Trade Partner | Siliding Door Sample Submission（Latch） | 0 | 1 | 0 | NA | APPROVED | 2026-06-24 | WF-000790 | NA | 2026-07-10 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-002699 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-12 | KPTG-TRANSMIT-000468 | NA | Consultant | NEXTDC-M2-Stages-9-12-Environmental-Acoustics-Spatial-Design-Report-(R5) | 0 | 1 | 0 | NA | APPROVED | 2026-01-12 |  | 172 | 2026-01-19 |  |  |  |  | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-17 | Jangho-TRANSMIT-000190 | NA | Trade Partner | Siliding Door Sample Submission（Transmission rod） | 0 | 1 | 0 | NA | APPROVED | 2026-06-24 | WF-000791 | NA | 2026-07-10 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-002697 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | Jangho-TRANSMIT-000191 | NA | Trade Partner | Siliding Door Sample Submission（Handle lock） | 0 | 1 | 0 | NA | APPROVED | 2026-06-24 | WF-000792 | NA | 2026-07-10 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-002633 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-06 | Jangho-TRANSMIT-000192 - CLIENT REVIEW | NA | Trade Partner | Re: Extrusion color Dulux Electro Medium Bronze Kinetic - Flat（PC-02-Powder of Akzo) | 0 | 1 | 0 | NA | APPROVED | 2026-07-06 | WF-000876 | NA | 2026-07-13 |  |  | 2026-08-13 | 2026-08-14 | KPTG-TRANSMIT-003398 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-24 | PARR-TRANSMIT-000194 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - BF RETIC LAYOUT-SECTIONS-BUILDERS WORKS PENETRATIONS L1 - C1 | 3 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 3643 | 2026-07-03 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-15 | Ardon-TRANSMIT-000045 | NA | Trade Partner | Stage 4 Door Hardware for Approval | 0 | 0 | 0 | NA | APPROVED | 2026-06-15 | WF-006033 | NA | 2026-06-19 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-24 | Altaire-TRANSMIT-000116 | NA | Trade Partner | Stage 2 Fire Matrix Excel IFC-7 | 0 | 1 | 0 | NA | APPROVED | 2026-06-24 | WF-006124 | NA | 2026-07-08 |  | Terminated for updating document | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-019124 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-24 | Auspan-TRANSMIT-000417 | NA | Trade Partner | Re: 352MAC: L1 Panel Shop Drawings w/o finish | 5 | 0 | 0 | KPTG-IntCorr-000767 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise- KPTG-IntCorr-000767 All are ok to proceed IFC KPTG-TRANSMIT-002446 |  | 2026-06-25 | KPTG-TRANSMIT-002446 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-24 | Auspan-TRANSMIT-000417 | NA | Trade Partner | Re: 352MAC: L1 Panel Shop Drawings w/o finish | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to difference in document number -DRAFT-008800 |  | 2026-06-24 | DRAFT-008800 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-24 | Nilsen3-TRANSMIT-000206 | NA | Trade Partner | Nilsen Shop Drawings Electrical - IFC | 10 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 3644 | 2026-06-29 |  | terminated as instructed byDuncan Cameron - Terminated the designer to re-issue them |  | 2026-08-21 | KPTG-TRANSMIT-020820 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-24 | Nilsen3-TRANSMIT-000206 | NA | Trade Partner | Nilsen Shop Drawings Telecommunications - IFC | 3 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 3648 | 2026-06-29 |  | terminated as instructed byDuncan Cameron - Terminated the designer to re-issue them |  | 2026-08-21 | KPTG-TRANSMIT-020819 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-12 | INGEN3D-TRANSMIT-000677 | NA | Trade Partner | I3D-378 Next DC M3 Stage 4 - Ground Floor Fuel Tanks - Precast Panels - Batch 2 - IFC (12-01-2026) | 23 | 0 | 0 | NA | APPROVED | 2026-01-12 | WF-003743 |  | 2026-01-19 |  | As requested by Finlay, the workflow has been terminated and the previous revision has been submitted for review. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-24 | VERTIV-TRANSMIT-000039 | NA | Trade Partner | Next DC - GE1 - CRAC Documentation | 0 | 4 | 0 | NA | APPROVED | 2026-06-24 | WF-000240 | NA | 2026-07-01 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-001108 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-24 | INTERSIG-TRANSMIT-000005 | NA | Trade Partner | Assemble Coburg - STATUTORY SIGNAGE - | 0 | 1 | 0 | NA | APPROVED | 2026-06-24 | WF - 0001055 | NA | 2026-06-30 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-24 | ccair-TRANSMIT-000124 | NA | Trade Partner | MSSB drawings for approval | 0 | 3 | 0 | NA | APPROVED | 2026-06-24 | WF - 01054 | NA | 2026-06-30 |  | NA | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-003117 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-24 | ccair-TRANSMIT-000125 | NA | Trade Partner | MSSB Drawings IFC | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - only for distribution. |  | 2026-06-24 | KPTG-TRANSMIT-003082 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-24 | SMEPS-TRANSMIT-000323 | SMEPS-TRANSMIT-000323 | Trade Partner | SMEPS-TRANSMIT-000323 | 1 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 3650 | 2026-07-06 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-24 | Auspan-TRANSMIT-000104 | NA | Trade Partner | Precast marking plan and elevations for Primium Precast panels. | 3 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 336 | 2026-07-03 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-003105 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-23 | SKS Tech-TRANSMIT-000181 | NA | Trade Partner | Busduct Layout - Primary | 4 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 3652 | 2026-06-29 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-24 | SMEPS-IntCorr-000332 | NA | Trade Partner | Fibre - Loss Budget | 0 | 1 | 0 | NA | APPROVED | 2026-06-24 | WF - 000501 | NA | 2026-06-30 |  | NA | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-001050 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-24 | Aurecon-TRANSMIT-000117 | NA | Consultant | In ground services IFCN | 6 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 266 | 2026-07-02 |  |  | 2026-06-29 | 2026-06-30 | KPTG-TRANSMIT-000349 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-24 | fjc-TRANSMIT-000159 | NA | Trade Partner | Drawing Updates - Wall Type Setout Mezz | 3 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 675 | 2026-06-29 |  |  | 2026-06-29 | 2026-06-29 | KPTG-SADV-004707 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-12 | Archacce-TRANSMIT-000001 | NA | Consultant | NMX2S9-11_Access & DDA Report & Markups | 0 | 1 | 0 | NA | APPROVED | 2026-01-12 |  | 174 | 2026-01-19 |  |  |  | 2026-01-22 | KPTG-TRANSMIT-000551 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-23 | SMEPS-TRANSMIT-000234 | NA | Trade Partner | WAP tech data approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-23 | WF-000497 | NA | 2026-06-29 |  | NA | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-001039 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-24 | SKS Tech-TRANSMIT-000183 | NA | Trade Partner | Data hall small power IFC | 4 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 3654 | 2026-06-29 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-24 | D&E-TRANSMIT-000272 | SPARK-CRFI-KPG-000315 | Trade Partner | MWYCCB - LEVEL 1 - PENETRATION LAYOUT ZONE 6 & ZONE 7 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 329 | 2026-07-01 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-001335 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-24 | D&E-TRANSMIT-000862 | NA | Trade Partner | NXM3S2 - GROUND FLOOR - DATAHALL 1 SFN UNION AND BOLT TORQUE MAP - Issued For Construction | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Directly issued IFC without IFA submission. |  | 2026-06-24 | KPTG-SADV-006131 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-24 | TTW-TRANSMIT-000192 | NA | Consultant | M3 Stage 1 Civil Drawing - HVM Bollards | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with revision date and document number inside the document. |  | 2026-06-24 | KPTG-DA-007260 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-06-24 | WPD-TRANSMIT-000094 | NA | Trade Partner | Re: HFF - Syfonic Drainage - As-Builts | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision number |  | 2026-06-24 | DRAFT-010249 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-16 | KPTG-IntCorr-006018 | NA | Client | Fencing Sample and Techdata | 0 | 1 | 0 | NA | APPROVED | 2026-03-16 | WF-000876 | NA | 2026-03-18 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-003013 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-24 | PTA-TRANSMIT-000012 | NA | Consultant | Fire Egress Stairs Update - Issue for coordination | 8 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 268 | 2026-07-02 |  |  | 2026-07-31 | 2026-08-03 | KPTG-TRANSMIT-000806 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-24 | NXT-TRANSMIT-000425 | NA | Client | Stage 6 IT Line Up Switchroom Drawings & Tech Data | 12 | 50 | 0 | NA | APPROVED | [5 empty] | No Action Required |  | 2026-06-24 | NA | Closed | 62 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-06-24 | Nilsen3-TRANSMIT-000207 | NA | Trade Partner | Nilsen HV Shop Drawings - IFC | 6 | 0 | 0 | NA | APPROVED | 2026-06-24 | WF-006133 | NA | 2026-06-29 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-019624 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-01-12 | KEECEPRO-TRANSMIT-000010 | NA | Trade Partner | Inground Shop Drawings - Amended | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-24 | SMEPS-TRANSMIT-000322 | NA | Trade Partner | SME - IFA Sample submissions | 0 | 1 | 0 | NA | APPROVED | 2026-06-24 | WF-006132 | NA | 2026-07-20 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-09 | Normark-TRANSMIT-000045 | NA | Trade Partner | Samples information - Soft Landscape- SP05 Revised sample sheet | 0 | 1 | 0 | NA | APPROVED | 2026-02-19 | WF-000837 | NA | 2026-03-23 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-003015 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-24 | D&E-TRANSMIT-000863 | NA | Trade Partner | NXM3S2 - Chilled Water & SFN Water Schematic - First Floor - Mech Corridor & Data Hall B8 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 4323 | 2026-07-01 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-019065 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | WAM-TRANSMIT-000815 | NA | Consultant | Common Areas Wet Areas 80%DD | 6 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 837 | 2026-06-27 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-002639 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-24 | Baigents-TRANSMIT-000216 | NA | Trade Partner | Lobby Handrail FOA-1 | 0 | 1 | 0 | NA | APPROVED | 2026-06-18 | WF-001114 | NA | 2026-06-24 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-003976 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-24 | SKS Tech-TRANSMIT-000182 | NA | Trade Partner | Submain Cable Schedule | 0 | 2 | 0 | NA | APPROVED | 2026-06-24 | WF-006134 | NA | 2026-07-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-24 | SMEPS-TRANSMIT-000017 | NA | Trade Partner | Techdata: HV Arrestors & Termination Kits | 0 | 2 | 0 | NA | APPROVED | 2026-06-24 | WF-000241 | NA | 2026-07-07 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-001764 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-24 | ARCH-TRANSMIT-000051 | NA | Consultant | No longer in use documents | 12 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer in Use, updated the register. |  | 2026-06-24 | KPTG-TRANSMIT-000905 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-24 | Civilex-TRANSMIT-000011 | NA | Trade Partner | Stage 6 Foundation/Piling Design - Updated Naming Convention | 1 | 7 | 0 | KPTG-IntCorr-000225 | APPROVED | 2026-08-05 | NA | 615 | 2026-08-13 |  | 1 drawing submitted and 7 document uploaded on ACC |  |  |  | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | ARCST-TRANSMIT-000281 | NA | Trade Partner | C2 West Roof Walkway - Issued for Approval | 0 | 0 | 0 | NA | APPROVED | 2026-05-12 | WF-005669 | NA | 2026-05-18 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-019027 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-01-12 | KEECEPRO-TRANSMIT-000009 | NA | Trade Partner | 600x600 Comms Pit Data Sheet | 0 | 1 | 0 | NA | APPROVED |  | WF-000334 |  | 2026-01-15 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-24 | ARCH-TRANSMIT-000050 | NA | Consultant | Updated drawings for Building Permit | 13 | 1 | 0 | NA | APPROVED | 2026-06-24 | NA | 290 | 2026-06-29 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-000959 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-24 | HDRAus-TRANSMIT-000515 | NA | Consultant | Link Bridge Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 3657 | 2026-06-29 |  |  | 2026-07-07 | 2026-07-07 | ⁠KPTG-TRANSMIT-019408 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-24 | Facx-TRANSMIT-000018 | NA | Trade Partner | FX - Updated IFC Package | 29 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document number, revision number and revision date. |  | 2026-06-24 | KPTG-SADV-006139 | Closed | 29 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-24 | ECBS-TRANSMIT-000044 - ECBS-TRANSMIT-000032 | NA | Trade Partner | Shop Drawings For Approval (Batch 2: 15dwgs) | 45 | 0 | 0 | NA | APPROVED | 2026-06-24 | WF-006125 | NA | 2026-07-08 |  | The WF has been terminated as requested by Peter |  | 2026-07-09 | NA | Closed | 45 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | Jangho-TRANSMIT-000196 | NA | Trade Partner | Re: Podium Level 3~5 Cast in Channel Shop Drawing_PDF_Rev 01_Review | 11 | 0 | 0 | NA | REJECTED | [5 empty] | Title difference and Rev. Errors |  | 2026-06-24 | KPTG-TRANSMIT-002494 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-24 | SKS Tech-TRANSMIT-000177 | NA | Trade Partner | Re: Updated lighting report | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected due to missing of document number |  | 2026-06-24 | KPTG-RFI-008580 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-24 | SKS Tech-TRANSMIT-000178 | NA | Trade Partner | Re: Submain cable schedule | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | NO NEED TO PROCESS THEY NEED TO UPDATE DRAWING AND CLOSEDOUT THE TRANSMITTAL FOR THAT |  | 2026-06-24 | KPTG-TRANSMIT-019016 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-24 | KPTG-IntCorr-015081 | NA | Trade Partner | Re: SME Doc register | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | DAMIAN SHARED A EXCEL FILE FOR CHECKING CORRECT REVEW STATUS OF ELC-SME DRAWING TOTAL 119 DOCUMENTS CHECKED FOR FURTHER PROCESS |  | 2026-06-24 | KPTG-IntCorr-015123 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-24 | Schindle-TRANSMIT-000030 | NA | Trade Partner | C3 Lift Reveal drawing for review | 0 | 1 | 0 | NA | APPROVED | 2026-06-24 | WF-006136 | NA | 2026-07-10 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-24 | PCForm-TRANSMIT-000077: | NA | Trade Partner | Updated Level 1 Zone 2 FW Design | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Drawing QC issues, awaiting advise from Design Manager - KPTG-IntCorr-000763 No Action required.KPTG-IntCorr-000765 |  | 2026-06-24 | KPTG-IntCorr-000765 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-02 | KPTG-IntCorr-007339 | NA | Trade Partner | URGENT: Upload & Transmit Documents | 0 | 3 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-01-12 | B Smart-TRANSMIT-000045 | NA | Consultant | IFC Drawing Packages | 103 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect drawing status on the drawing sheets. |  | 2026-01-12 | KPTG-DA-000867 | Closed | 103 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-24 | M.2-TRANSMIT-000055 | NA | Trade Partner | Electrical Services Level 2-5 Penetration layouts | 5 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 1332 | 2026-07-01 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-002768 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-24 | B Smart-TRANSMIT-000086 | NA | Consultant | GF,L1,L2 CPP revised IFC | 3 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 588 | 2026-07-01 |  | Review Void as advised by DM - Consultant to update drawings. | 2026-06-30 | 2026-06-30 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-24 | crossfir-TRANSMIT-000020 | NA | Trade Partner | Wet Fire - Ground Floor Penetration, IFC | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required, register and distribute - KPTG-TRANSMIT-001181 |  | 2026-06-24 | KPTG-TRANSMIT-001181 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-24 | ccair-TRANSMIT-000023 | NA | Trade Partner | Mechanical Services Ground floor builders works drawing IFA [B] | 1 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 590 | 2026-07-01 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001260 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-24 | Bianco-TRANSMIT-000002 | NA | Trade Partner | 1369- 671 CHAPEL STREET (FOR APPROVAL) | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect drawing number KPTG-SADV-002560 |  | 2026-06-24 | KPTG-SADV-002560 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-24 | Bianco-TRANSMIT-000003 | NA | Trade Partner | Re: 1369- 671 CHAPEL STREET (FOR APPROVAL) | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect drawing number KPTG-SADV-002560 |  | 2026-06-24 | KPTG-SADV-002560 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-24 | Bianco-TRANSMIT-000004 | NA | Trade Partner | 671 CHAPEL STREET_SHOP DRAWING_FOR APPROVAL | 9 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | WF-000514 | 2026-07-01 |  | Review void as drawings updated. |  | 2026-07-22 | NA | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | INGEN3D-TRANSMIT-000128 | NA | Trade Partner | Level 11-13 - Precast Columns - IFA (04-06-2026) | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Drawings Superseded closed out by KPTG-IntCorr-000847 |  | 2026-06-24 | KPTG-IntCorr-000847 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | INGEN3D-TRANSMIT-000129 | NA | Trade Partner | Level 12-14 - Precast Columns - IFA (08-06-2026) | 12 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Drawings Superseded closed out by KPTG-IntCorr-000849 |  | 2026-06-24 | KPTG-IntCorr-000849 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | INGEN3D-TRANSMIT-000129 | NA | Trade Partner | Level 12-14 - Precast Columns - IFA (08-06-2026) | 2 | 0 | 0 | NA | APPROVED | 2026-06-24 | WF-000798 | NA | 2026-07-11 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-003032 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-01-12 | INGEN3D-TRANSMIT-000017 | NA | Trade Partner | I3D-386 Hanwha Stage 2 - Zone 2 - CP208, LB209 & CP210 - New IFA | 4 | 0 | 0 | NA | APPROVED | [5 empty] | Awaiting response from KP team |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | INGEN3D-TRANSMIT-000130 | NA | Trade Partner | Level 13-15 - Precast Columns - IFA (09-06-2026) | 11 | 0 | 0 | NA | APPROVED | 2026-06-24 | WF-000797 | NA | 2026-07-11 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-003045 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | INGEN3D-TRANSMIT-000130 | NA | Trade Partner | Level 13-15 - Precast Columns - IFA (09-06-2026) | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Already revised, hence closed out - KPTG-IntCorr-000846 |  | 2026-06-24 | KPTG-IntCorr-000846 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | INGEN3D-TRANSMIT-000131 | NA | Trade Partner | Level 11-13 - Precast Columns - New IFA (15-06-2026) | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Already revised, hence closed out - KPTG-IntCorr-000844 |  | 2026-06-24 | KPTG-IntCorr-000844 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | INGEN3D-TRANSMIT-000132 | NA | Trade Partner | Level 12-14 - PC0504 & PC0709 - Revised & New IFA (19-06-2026) | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Already revised, hence closed out - KPTG-IntCorr-000843 |  | 2026-06-24 | KPTG-IntCorr-000843 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | INGEN3D-TRANSMIT-000133 | NA | Trade Partner | Level 12-14 - PC0711 - New IFA (23-06-2026) | 2 | 0 | 0 | NA | APPROVED | 2026-06-24 | WF-000796 | NA | 2026-07-11 |  |  | 2026-07-01 | 2026-07-01 | Work flow Terminated as instructed | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | L.E.S.-TRANSMIT-000018 | NA | Trade Partner | Slab penetrations level 6 to 10 - IFA | 6 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 839 | 2026-06-30 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002847 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | L.E.S.-TRANSMIT-000019 | NA | Trade Partner | L.E.S.-TRANSMIT-000019 | 4 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 841 | 2026-06-30 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-003175 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | Jangho-TRANSMIT-000190 | NA | Trade Partner | Siliding Door Sample Submission（Transmission rod） | 0 | 1 | 0 | NA | APPROVED | 2026-06-24 | WF-000791 | NA | 2026-07-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | Civilex-TRANSMIT-000108 | NA | Trade Partner | HY-TEC Ground Slab Concrete Mix Design | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | No action refer KPTG-SADV-003337 |  | 2026-06-24 | KPTG-SADV-003337 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | Civilex-TRANSMIT-000109 | NA | Trade Partner | MultiFlex Joints | 0 | 1 | 0 | NA | APPROVED | 2026-06-24 | WF-000802 | NA | 2026-06-29 |  |  | 2026-06-30 | 2026-07-01 | KPTG-TRANSMIT-002600 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-01-12 | RBG-TRANSMIT-000046 | NA | Consultant | Structural Drawings for Stairs and Lobby Slabs - Issued for Certification | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Issued for Information, Waiting for Kapitol Avise KPTG-IntCorr-000288 No review required. update register. |  | 2026-01-13 | KPTG-IntCorr-000290 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-24 | Auscool-TRANSMIT-000095 | NA | Trade Partner | Mechanical Shop Drawing updates | 5 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  | 2026-06-24 | 2026-06-24 | KPTG-SADV-004649 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-24 | BTWA-TRANSMIT-000088 | NA | Trade Partner | MLCSPR2 - Glass and Profile submission | 3 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 338 | 2026-07-08 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-003141 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-24 | Highbu-TRANSMIT-000155 | NA | Trade Partner | Revised drawing | 1 | 0 | 0 | NA | APPROVED | 2026-06-24 | NA | 340 | 2026-06-29 |  | Workflow needs to be resubmitted: KPTG-TRANSMIT-003046 |  | 2026-07-06 | KPTG-TRANSMIT-003046 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-24 | Ardon-TRANSMIT-000003 | NA | Trade Partner | Level 1 Switch Room Frames | 5 | 0 | 0 | NA | APPROVED | 2026-06-24 | WF-001038 | NA | 2026-07-03 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-09 | BBC P.-TRANSMIT-000015 | NA | Trade Partner | BBC Paint sample submission | 0 | 8 | 0 | NA | APPROVED |  | WF-001026 | NA | 2026-06-24 |  |  |  | 2026-06-24 | KPTG-TRANSMIT-004731 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-25 | KPTG-IntCorr-000625 | NA | Client | Screed material tech data | 0 | 1 | 0 | NA | APPROVED | 2026-06-25 | WF-000348 | NA | 2026-07-01 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-000999 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-25 | RDSBIM-TRANSMIT-000006 | NA | Trade Partner | 303COL ¦ BASEMENT 1 - EOT 1 ¦ IFR ¦ SUBMISSION | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Project code is not as mentioned in the Des pro. |  | 2026-06-25 | KPTG-DA-000384 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-25 | RDSBIM-TRANSMIT-000007 | NA | Trade Partner | 303COL ¦ BASEMENT 1 - EOT 2 ¦ IFR ¦ SUBMISSION | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Project code is not as mentioned in the Des pro. |  | 2026-06-25 | KPTG-DA-000383 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-25 | Entire M-TRANSMIT-000074 | NA | Trade Partner | Hanger Fixing Technical Data Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-06-25 | WF-000349 | NA | 2026-06-30 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-000974 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-01-12 | B Smart-TRANSMIT-000046 | NA | Consultant | 671CHP - A03 Basement Drawings issue for information | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Issued for information, Waiting for Kapitol Avise KPTG-IntCorr-000289. No review required, for Information only. |  | 2026-01-16 | KPTG-IntCorr-000296 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-25 | Appselec-TRANSMIT-000130 | NA | Trade Partner | MEL11C45 - Communications Shop Drawings - IFC | 2 | 0 | 0 | NA | APPROVED | 2026-06-25 | WF-000350 | NA | 2026-06-30 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-000991 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-25 | Baigents-TRANSMIT-000007 | NA | Trade Partner | Precast Beam Prototype IFA | 7 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 270 | 2026-07-03 |  | Actual Submission Date 22-06-2026-Voided requested by Zoe |  | 2026-07-02 | NA | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-25 | Auspan-TRANSMIT-000418 | NA | Trade Partner | Precast shop drawings for approval. Zone 1 levels 7, 8. | 46 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 1336 | 2026-07-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-25 | Auspan-TRANSMIT-000418 | NA | Trade Partner | Precast shop drawings for approval. Zone 1 levels 7, 8 | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - Difference in document number and revision history is blank (DRAFT-008845) |  | 2026-06-25 | DRAFT-008845 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-25 | INTRFRM-TRANSMIT-000091 | NA | Trade Partner | Geelong Edge - Electrical Tech Data (Submission 7) - External Plant Area HV Pits | 0 | 1 | 0 | NA | APPROVED | 2026-06-25 | WF-000243 | NA | 2026-07-08 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-001009 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-25 | D&E-TRANSMIT-000864 | NA | Trade Partner | Re: Stage 4 - Fire matrix IFC-4 Transmittal | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The title is missing from the document. I would like to kindly request you to add the title and resubmit the document |  | 2026-06-25 | KPTG-RFI-008590 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-25 | JCBa-TRANSMIT-000143 | NA | Consultant | Architectural Documentation - Updated Retail Windows Types & Details | 3 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 1339 | 2026-06-29 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-002562 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-25 | SMEPS-TRANSMIT-000226 | NA | Trade Partner | NEL-CNT-SME-2801-BSE-SCH-0001, NEL-CNT-SME-2801-BSE-SDG-0024,0034,0035.0036,0036,0037,0038,0039,0188,1110 | 10 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status inside drawing and in aconex seem different |  | 2026-06-25 | KPTG-TRANSMIT-001327 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-25 | SMEPS-TRANSMIT-000227 | SPARK-CRFI-KPG-000284 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0025 | 1 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 330 | 2026-07-02 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-001343 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-25 | D&E-TRANSMIT-000866 | NA | Trade Partner | NXM3S4 - Roof Level - Chiller Room 6 Layout - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 3660 | 2026-06-07 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020127 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-01-12 | RBG-TRANSMIT-000047 | NA | Consultant | : Structural Drawing S06-00043 - Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-01-12 | WF-000114 | 197 | 2026-01-15 |  |  |  | 2026-01-22 | KPTG-TRANSMIT-000316 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-10 | ADP-TRANSMIT-000341 | NA | Consultant | MEL4780 - S4 - Electrical - SITEWIDE SCADA SYSTEM BLOCK SCHEMATIC | 1 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 3483 | 2026-06-14 |  | As requested by Damian - Terminated ADP will issue a new revision now |  | 2026-06-25 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-25 | D&E-TRANSMIT-000867 | NA | Trade Partner | NXM3S4 - Level 1 - CHW Pipe Layout - Zone 7 & 8 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-06-25 | ⁠KPTG-TRANSMIT-019039 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-25 | D&E-TRANSMIT-000273 | SPARK-CRFI-KPG-000473 | Trade Partner | MWYCCB - GROUND LEVEL & LEVEL 1 - PLINTH LAYOUT ZONES - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 331 | 2026-07-02 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-001345 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-25 | NXT-TRANSMIT-001633 | NA | Trade Partner | M3 S4 - RPP PDU Project - Label & Nameplate Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-06-25 | WF-006142 | NA | 2026-07-08 |  | ABB-TRANSMIT-000047 | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-019373 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-25 | WPDS-TRANSMIT-000002 | NA | Trade Partner | Tech data | 0 | 8 | 0 | NA | REJECTED | [5 empty] | Issue with revision number, document status and mismatch of title. |  | 2026-06-25 | KPTG-SADV-000734 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-25 | ACG-TRANSMIT-000100 | NA | Trade Partner | M3 Stage 4 - Cable Schedule | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect document number |  | 2026-06-25 | KPTG-RFI-008594 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-25 | INTRFRM-TRANSMIT-000092 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 20) | 0 | 1 | 0 | NA | APPROVED | 2026-06-25 | WF-000244 | NA | 2026-07-08 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000915 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-25 | ADP-TRANSMIT-000356 | NA | Consultant | Re: MEL4780 - M3 S4 - Electrical Drawings | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision number |  | 2026-06-25 | KPTG-RFI-008595 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-25 | Civilex-TRANSMIT-000274 | NA | Trade Partner | Stage 2 - sample submission - Irrigation System - Rev: FOA-B | 0 | 5 | 0 | NA | APPROVED | 2026-06-25 | WF-006147 | NA | 2026-07-30 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-019097 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-25 | Auscool-TRANSMIT-000052 | NA | Trade Partner | basement - zone 2 - IFA drawing | 1 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 1343 | 2026-07-02 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-002695 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-12 | IVS-TRANSMIT-000310 | NA | Trade Partner | Stage 4 - GF Office Pit (Construction Issue) | 4 | 0 | 0 | NA | APPROVED | [7 empty] | 2026-01-16 | KPTG-TRANSMIT-011527 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-25 | PFP PL-TRANSMIT-000092 | NA | Trade Partner | Roof Plant Wet Fire Layouts IFA | 2 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 3665 | 2026-06-30 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-019744 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-25 | ACG-TRANSMIT-000104 | NA | Trade Partner | M3 Stage 4 - Cable Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-06-25 | WF-006146 | NA | 2026-07-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-25 | SMEPS-IntCorr-000335 | NA | Trade Partner | Re: MEL05C4 BU Temp Power Plan | 0 | 1 | 0 | NA | APPROVED | 2026-06-25 | WF - 000502 | NA | 2026-07-01 |  | NA | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-001066 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-25 | BIMF-TRANSMIT-000003 | NA | Trade Partner | Re: Level 4 Hydraulic Setouts | 2 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 845 | 2026-07-02 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-002677 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-25 | SMEPS-TRANSMIT-000324 | NA | Trade Partner | Revised Jemena Easement Shopdrawing - 25.06.2026 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with title and revision. |  | 2026-06-25 | KPTG-SADV-006166 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-25 | INGEN3D-TRANSMIT-000134 | NA | Trade Partner | I3D-389 District Living - Level 15-17 - PC0528-3 - New IFA (25-06-2026) | 1 | 0 | 0 | NA | APPROVED | 2026-06-25 | WF-000805 | NA | 2026-07-14 |  |  | 2026-07-01 | 2026-07-01 | Work flow Terminated as instructed | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-25 | Civilex-TRANSMIT-000110 | NA | Trade Partner | Asphalt Mix Design | 0 | 1 | 0 | NA | APPROVED | 2026-06-25 | WF-000806 | NA | 2026-07-07 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-002770 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-25 | Baigents-TRANSMIT-000007 | NA | Trade Partner | Water Tank Stairs (C11 to C14) - Issued for Approval | 77 | 0 | 0 | NA | APPROVED | 2026-06-25 | WF-006148 | NA | 2026-07-13 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-019766 | Closed | 77 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-25 | WAM-TRANSMIT-000817 | NA | Consultant | Updates and IFC | 4 | 0 | 0 | NA | APPROVED | 2026-06-25 |  | NA | 2026-06-28 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-002636 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-25 | TTW-TRANSMIT-000193 | NA | Trade Partner | M3 Stage 1 Civil Drawing - HVM Bollards | 1 | 0 | 0 | NA | APPROVED | [5 empty] | Document in TTW-TRANSMIT-000193 is superseded by TTW-TRANSMIT-000194. |  | 2026-06-25 | KPTG-TRANSMIT-019042 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-19 | RDSBIM-TRANSMIT-000027 |  | Trade Partner | MWYCCB ¦ LANDSCAPE PAVEMENT KEY PLAN | 3 | 0 | 0 | NA | APPROVED | 2026-01-12 | WF-000116 | 81 | 2026-01-19 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-25 | Stowe-A-TRANSMIT-000623 | NA | Trade Partner | STOWE - Drawing Submission - Light & Power As-builts | 16 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document number, new revision updated as fresh document instead superseding on top of previous review. |  | 2026-06-25 | KPTG-SADV-006169 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-25 | SMEPS-TRANSMIT-000228 | SPARK-CRFI-KPG-000284 | Trade Partner | Re: NEL-CNT-SME-2801-BSE-SCH-0001, NEL-CNT-SME-2801-BSE-SDG-0024,0034,0035.0036,0036,0037,0038,0039,0188,1110 | 10 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 332 | 2026-07-02 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-001347 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-25 | ARCST-TRANSMIT-000310 | NA | Trade Partner | Stair 6a Issued for Review | 12 | 0 | 0 | NA | APPROVED | 2026-06-25 | WF-006149 | NA | 2026-06-29 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-020971 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-25 | KALLIBRE-TRANSMIT-000002 | NA | Trade Partner | Toilet Partitions - Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-06-25 | WF - 001056 | NA | 2026-07-01 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-003123 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-25 | TTW-TRANSMIT-000194 | NA | Consultant | M3 Stage 1 Civil Drawing - HVM Bollards | 1 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 4325 | 2026-06-29 |  | Terminated as advised by Charlie Johnstone for submitting update document. |  | 2026-07-21 | KPTG-TRANSMIT-019841 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-25 | WAM-TRANSMIT-000816 | NA | Consultant | A00 Cover Sheet Updated | 1 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 847 | 2026-06-28 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-002605 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-25 | EAEGROUP-TRANSMIT-000102 | NA | Trade Partner | Fwd: Updated Shop Drawing Revision - Block C3 HA, HB, HD, HE, HF | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-06-25 | KPTG-TRANSMIT-019044 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-25 | Baigents-TRANSMIT-000223 | NA | Trade Partner | L5 Void Handrail FC-1 | 22 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - FORWARDED TO ALL PARTIES - |  | 2026-06-25 | KPTG-TRANSMIT-003984 | Closed | 22 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-25 | ZIA-TRANSMIT-000106 | NA | Trade Partner | Re: M3 Stage 4 - Functional Design Specification | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The document is missing a revision number |  | 2026-06-25 | KPTG-RFI-008599 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-29 | RDSBIM-TRANSMIT-000028 |  | Trade Partner | MWYCCB ¦ GROUND FLOOR CULVERT DETAILS | 1 | 0 | 0 | NA | APPROVED | 2026-01-12 | WF-000113 | 78 | 2026-01-19 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-25 | Auspan-TRANSMIT-000422 | NA | Trade Partner | Precast cast in plate layouts for zone 3 | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - Difference in documents title - DRAFT-008893 |  | 2026-06-25 | DRAFT-008893 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-25 | WPDS-TRANSMIT-000003 | NA | Trade Partner | Western painting tech data submission | 0 | 8 | 0 | NA | APPROVED | 2026-06-25 | WF-000245 | NA | 2026-07-08 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-001501 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-25 | G&CHyd-TRANSMIT-000005 | NA | Trade Partner | HYD Tech Data | 0 | 12 | 0 | NA | APPROVED | 2026-06-25 | WF-000808 | NA | 2026-06-29 |  | Again submitted for client review | 2026-07-02 | 2026-07-02 | WF-000864 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-25 | WilsonPD-TRANSMIT-000099 | NA | Trade Partner | Stage 9 level 1 and 3 for construction | 3 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 1189 | 2026-07-01 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-005023 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-25 | Hames-TRANSMIT-000162 | NA | Consultant | Updated Sheets | 1 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 1292 | 2026-06-29 |  |  | 2026-08-05 | 2026-08-06 | KPTG-TRANSMIT-004224 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-25 | ARCST-TRANSMIT-000307 | NA | Trade Partner | C1 Cbiller Base Framing - Issued for Construction | 136 | 0 | 0 | NA | APPROVED | 2026-06-25 | WF-006155 | NA | 2026-06-30 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-25 | VAE-Grp-IntCorr-000961 | NA | Trade Partner | NXD1S2 - Commissioning of Cooling Towers | 0 | 3 | 0 | NA | APPROVED | 2026-06-25 | 1121 | NA | 2026-06-30 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-004023 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-25 | ARCST-TRANSMIT-000312 | NA | Trade Partner | GF & L1 Speed Panel Posts - Issued for Approval | 15 | 0 | 0 | NA | APPROVED | 2026-06-25 | WF-006154 | NA | 2026-07-17 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-25 | NXT-TRANSMIT-000410 | NA | Client | FIE Switch room Interface Matrix | 0 | 1 | 0 | NA | APPROVED | 2026-06-25 | NA | 272 | 2026-07-03 |  | Actual Submission date 17-06-2026 | 2026-06-29 | 2026-06-30 | KPTG-TRANSMIT-000344 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-25 | SMEPS-TRANSMIT-000018 | NA | Trade Partner | Shop Drawings: Communications Submission 3 | 3 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 292 | 2026-07-01 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-001170 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-06 | RDSBIM-TRANSMIT-000029 |  | Trade Partner | MWYCCB ¦ GROUND FLOOR PARTITION WALL KEY PLAN AND LAYOUT | 5 | 0 | 0 | NA | APPROVED | 2026-01-12 | WF-000114 | 79 | 2026-01-19 |  | Workflow terminated as per Jed's advise |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-25 | SES AU-TRANSMIT-000066 | NA | Trade Partner | SECURITY - COLO 5 RACK ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-06-25 | WF-000351 | NA | 2026-06-29 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-000981 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-25 | ARCST-TRANSMIT-000305 | NA | Trade Partner | C1 East Lower Gantry - Issued for Fabrication | 138 | 0 | 0 | NA | APPROVED | 2026-06-25 | WF-006157 | NA | 2026-06-30 |  | 136 are still under review |  | 2026-07-03 | KPTG-TRANSMIT-019314 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-25 | SES AU-TRANSMIT-000067 | NA | Trade Partner | SECURITY - SCEC Single Line Schematics - IFA | 3 | 0 | 0 | Kapitol Advice awaits: KPTG-IntCorr-000630 | REJECTED | [5 empty] | Drawing status needs to be IFC, Not approval. KPTG-IntCorr-000630 |  | 2026-06-25 | SES AU-IntCorr-000093, KPTG-IntCorr-000630 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-25 | NXT-TRANSMIT-000425-KPTG-DA-000462 | NA | Client | Stage 6 IT Line Up Switchroom Drawings & Tech Data | 12 | 50 | 0 | NA | APPROVED | [5 empty] | Forma Updated |  | 2026-06-25 | NA | Closed | 62 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-25 | Leemark-TRANSMIT-000045 | NA | Trade Partner | MCC - Fire Proection Layout - Ground Floor Zone 7 - IFC | 1 | 0 | 0 | NA | REJECTED | [5 empty] | previous revision not included in history block |  | 2026-06-25 | KPTG-TRANSMIT-001341 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-25 | Auspan-TRANSMIT-000423 | NA | Trade Partner | Re: Update IFCed precast shop drawings for construction. Level 1 | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise- KPTG-IntCorr-000777 As advised by PC, No Action required. |  | 2026-06-26 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-25 | Auspan-TRANSMIT-000424 | NA | Trade Partner | Re: Update IFCed precast shop drawings for construction. Level 2 | 7 | 0 | 0 | KPTG-IntCorr-000777 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise- KPTG-IntCorr-000777 3 are OK to proceed IFC KPTG-TRANSMIT-002537; 4 Rejected as advised by Kapitol PC(KPTG-IntCorr-000797) . DRAFT-009137 |  | 2026-07-01 | KPTG-TRANSMIT-002537 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-25 | SMEPS-TRANSMIT-000019 | NA | Trade Partner | Shop Drawing: Electrical Submission 3 | 14 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document number and title. |  | 2026-06-25 | KPTG-SADV-000741 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-25 | Auspan-TRANSMIT-000425 | NA | Trade Partner | Re: Update IFCed precast shop drawings for construction. Levels 3, 4 | 6 | 0 | 0 | KPTG-IntCorr-000777 | REJECTED |  | NA | NA |  |  | IFC - Waiting for Kim advise- KPTG-IntCorr-000777 Rejected by Kapitol PC. KPTG-IntCorr-001123 |  | 2026-07-28 | KPTG-IntCorr-001123 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-25 | Stowe-A-TRANSMIT-000624 | NA | Trade Partner | Stowe - DH 5 + 6 Containment As-builts | 12 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document number. Uploaded documents as new document instead of superseding previous revision. |  | 2026-06-25 | KPTG-SADV-006190 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-12 | StantecA-TRANSMIT-000290 | NA | Consultant | StantecA-TRANSMIT-000290 Electrical Drawings Update | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required. Update register and issue to transmit to consultants. |  | 2026-01-12 | KPTG-TRANSMIT-000366 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-25 | B Smart-TRANSMIT-000087 | NA | Consultant | A11 revised IFC | 2 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 594 | 2026-06-29 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-001340 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-25 | PenskePS-TRANSMIT-000014 | NA | Trade Partner | MEL11 COLO4 GPC - FAT Reports and Austhorisation to ship docs for approval | 0 | 9 | 0 | NA | REJECTED | [5 empty] | Rejected: Document number and title are same:KPTG-IntCorr-000629 |  | 2026-06-25 | KPTG-IntCorr-000629 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-25 | SES AU-TRANSMIT-000068 | NA | Trade Partner | SECURITY - COLO 4 AND 5 CABLING DIAGRAM - IFA | 2 | 0 | 0 | NA | APPROVED | 2026-06-25 | WF-000352 | NA | 2026-07-01 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-000987 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-25 | Highbu-TRANSMIT-000055 | NA | Trade Partner | Tower Hydraulic Penetration Layouts | 20 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001106 - AS PER DIRECTION FROM Mark, we only update document register and sent to RDS, FJC. | 2026-06-25 | 2026-06-25 | KPTG-IntCorr-001106 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-25 | 4DW-TRANSMIT-000099 | NA | Trade Partner | Puddle Pour Update | 3 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 677 | 2026-06-30 |  |  | 2026-07-02 | 2026-07-02 | KPTG-SADV-004773 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-25 | Auscool-TRANSMIT-000095 | NA | Trade Partner | Mechanical Shop Drawing updates | 5 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 676 | 2026-07-02 |  |  | 2026-07-23 | 2026-07-23 | KPTG-SADV-005066 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-25 | SES AU-TRANSMIT-000069 | NA | Trade Partner | SECURITY - Riser Schedules - IFA | 2 | 0 | 0 | NA | APPROVED | 2026-06-25 | WF-000353 | NA | 2026-07-01 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-000988 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-25 | Hames-TRANSMIT-000163 | NA | Consultant | Updated Ceiling Info | 1 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 1294 | 2026-06-29 |  |  | 2026-08-05 | 2026-08-06 | KPTG-TRANSMIT-004220 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-25 | ZIA-TRANSMIT-000108 | NA | Trade Partner | Re: M3S2 CSMS UCOP-SLA & Batt-SLA Roof Level Zone B1&B2 Revision Submission | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with revision date. |  | 2026-06-25 | KPTG-SADV-006194 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-25 | SES AU-TRANSMIT-000070 | NA | Trade Partner | SECURITY - LEVEL 1 COLO 5 Floor Plan | 1 | 0 | 0 | NA | APPROVED | 2026-06-25 | WF-000354 | NA | 2026-06-29 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-001002 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-02 | ARCST-TRANSMIT-000140 | NA | Trade Partner | Green Wall Framing - Issued for Fabrication | 77 | 0 | 0 | NA | APPROVED | 2025-12-02 | WF-003473 | NA | 2025-12-09 |  |  |  | 2026-01-05 | KPTG-TRANSMIT-011193 | Closed | 77 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-05 | SMEPS-TRANSMIT-000097 | SPARK-CRFI-KPG-000504 | Trade Partner | IFA - Sub-Main Cable Schedule & Containment Layout Details | 2 | 0 | 0 | NA | APPROVED | 2026-01-12 | WF-000117 | 82 | 2026-01-19 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-000535 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-01 | Syfon1-TRANSMIT-000010 | NA | Trade Partner | Syfon shop drawings IFC | 6 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 3676 | 2026-07-09 |  | 4 DRAWINGS TERMINATED AS PER REQUEST FROM MAX L ANDOTHERE ARE PLACED NEW WF |  |  |  | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-25 | ZIA-TRANSMIT-000107 | NA | Trade Partner | Re: M3 Stage 4 - Device Register | 0 | 1 | 0 | NA | REJECTED | [5 empty] | REVISION MISTAKE |  | 2026-06-25 | KPTG-TRANSMIT-019057 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-25 | Tradetec-TRANSMIT-000464 | NA | Trade Partner | Stage 4 - Pit IFA's - HVP23,24,25 | 3 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 3675 | 2026-07-09 |  |  |  | 2026-06-29 | NA | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-25 | PARR-TRANSMIT-000198 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - PUMP ROOM AB GA & ELEVATIONS - FOA-2 | 4 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 3672 | 2026-07-09 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-020983 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-25 | ADP-TRANSMIT-000357 | NA | Consultant | MEL4780 - M3 S4 - Electrical Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 3669 | 2026-07-09 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-019635 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-25 | ARCST-TRANSMIT-000308 | NA | Trade Partner | Re: C2 Chiller Base Framing | 98 | 0 | 0 | NA | APPROVED | 2026-06-25 | WF-006150 | NA | 2026-07-09 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-25 | D&E-TRANSMIT-000864 | NA | Trade Partner | Re: Stage 4 - Fire matrix IFC-4 Transmittal | 0 | 1 | 0 | NA | APPROVED | 2026-06-25 | WF-006143 | NA | 2026-07-10 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-019874 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-25 | RDSBIM-TRANSMIT-000076 | NA | Trade Partner | GREYSTAR GF Z03 CPP IFC FOR SUBMISSION | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Review - Update register and distribute - KPTG-TRANSMIT-002444 |  | 2026-06-25 | KPTG-TRANSMIT-002444 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-25 | Auspan-TRANSMIT-000420 | NA | Trade Partner | Update IFCed precast shop drawings. Level 2 zone 5 | 2 | 0 | 0 | KPTG-IntCorr-000771 | REJECTED |  | NA | NA |  |  | IFC - Waiting for Kim advise - KPTG-IntCorr-000771 Rejected by Kapitol Project Coordinator - KPTG-SADV-003112 |  | 2026-06-26 | KPTG-SADV-003112 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-25 | Auspan-TRANSMIT-000419 | NA | Trade Partner | : Update precast cast in plate layout zone 4, 5 | 3 | 0 | 0 | KPTG-IntCorr-000772 | REJECTED |  | NA | NA |  |  | IFC - Waiting for Kim advise - KPTG-IntCorr-000772 Rejected as advised by Project Coordinator - DRAFT-009048 |  | 2026-06-30 | DRAFT-009048 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-12 | SMEPS-TRANSMIT-000098 | SPARK-CRFI-KPG-000329 | Trade Partner | UPS Tech Data | 0 | 1 | 0 | KPTG-IntCorr-001219 | APPROVED | [7 empty] | 2026-01-22 | KPTG-TRANSMIT-000362 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-25 | Auspan-TRANSMIT-000393 | NA | Trade Partner | Precast shop drawings for construction. Levels 1, 2. | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Register and transmit KPTG-TRANSMIT-002450 |  | 2026-06-25 | KPTG-TRANSMIT-002450 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-25 | Auspan-TRANSMIT-000421 | NA | Trade Partner | Auspan-TRANSMIT-000421: Re: Precast shop drawings for construction. - Kapitol Comments | 3 | 0 | 0 | KPTG-IntCorr-000776 | REJECTED |  | NA | NA |  |  | IFC - Waiting for approval-from KIM- KPTG-IntCorr-000776 Rejected by Project Coordinator KPTG-SADV-003168 |  | 2026-06-30 | KPTG-SADV-003168 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-25 | ALU-TRANSMIT-000001 | NA | Trade Partner | Balustrade & Screen Shop Drawing Details IFA | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to QC issues DRAFT-008905 |  | 2026-06-25 | DRAFT-008905 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-25 | Jangho-TRANSMIT-000197 | NA | Trade Partner | Podium Level 4~5 Floor Plan Shop Drawing_PDF_Rev 02_For Approval | 4 | 0 | 0 | KPTG-IntCorr-000858 | APPROVED | 2026-06-26 | NA | 853 | 2026-07-02 |  | Need Jaanbir's confirmation |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-25 | INGEN3D-TRANSMIT-000135 | NA | Trade Partner | Level 10-12 - Precast Columns - IFC | 42 | 0 | 0 | NA | APPROVED | 2026-06-25 | WF-000809 | NA | 2026-07-06 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-25 | INGEN3D-TRANSMIT-000136 | NA | Trade Partner | HYD Tech Data | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer in Use - forwarded to all TP |  | 2026-06-25 | KPTG-TRANSMIT-002510 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-25 | RBG-TRANSMIT-000064 | NA | Consultant | : Revised structural drawings for core walls to capture penetrations | 5 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 596 | 2026-06-30 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-001306 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-25 | crossfir-TRANSMIT-000021 | NA | Trade Partner | Wet Fire - Penetrations Level 04 to 10, IFC | 6 | 0 | 0 | KPTG-IntCorr-000804 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Tayla -KPTG-IntCorr-000804 | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-001207 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-25 | M.S.-TRANSMIT-000073 | NA | Trade Partner | J91 Bin unit - Updated IFC shop drawing | 2 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 343 | 2026-07-01 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-003027 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-12 | HGP-TRANSMIT-000033 |  | Trade Partner | Facade Calculation Report IFC curtain wall HER | 0 | 1 | 0 | KPTG-IntCorr-001223 | APPROVED |  | NA | NA |  |  | Superseded with latest revision |  | 2026-07-07 | KPTG-TRANSMIT-001391 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-25 | M.S.-TRANSMIT-000074 | NA | Trade Partner | J50 Reception Counter Updated IFA Shop Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 345 | 2026-07-03 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-003034 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-25 | ZIA-TRANSMIT-000062 | NA | Consultant | Cx L3 Tests - CSMS Network Switches | 0 | 8 | 0 | NA | APPROVED | 2026-06-25 | WF-001123 | NA | 2026-06-30 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-004169 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-25 | SIL-TRANSMIT-000034 | NA | Trade Partner | MEL11 COLO4-5 PDU Assembly Verification Report | 0 | 2 | 0 | KPTG-IntCorr-000627 | APPROVED | [5 empty] | KAPITOL ADVICE AWAITS:KPTG-IntCorr-000627 |  |  | KPTG-IntCorr-000627 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-25 | Nilsen3-TRANSMIT-000053 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 3 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 1193 | 2026-06-28 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-005215 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-25 | WilsonPD-TRANSMIT-000095 | NA | Trade Partner | Industrial Water Equipment for Approval | 0 | 3 | 0 | NA | APPROVED | 2026-06-25 | WF-001044 | NA | 2026-07-06 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-005432 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-25 | SCG2014-TRANSMIT-000031 | NA | Consultant | IFT-5 Security Drawing Updates | 2 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 1194 | 2026-07-03 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-004877 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-25 | SCG2014-TRANSMIT-000032 | NA | Consultant | IFT-5 Security Drawing Updates | 1 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 1194 | 2026-07-03 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-004881 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-25 | WilsonPD-TRANSMIT-000098 | NA | Trade Partner | HYDRAULIC SERVICES STAGE 9 NORTH FACADE SECTION | 1 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 1187 | 2026-07-02 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-004941 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-25 | ELLISAIR-TRANSMIT-000084 | NA | Trade Partner | VSD | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC, No review required, Updated and distributed |  | 2026-06-25 | KPTG-TRANSMIT-004804 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-25 | EAE Busduct shop drawings Stage 11 (Outlook) | NA | Trade Partner | EAE Busduct shop drawings Stage 11 (Outlook) | 33 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 1191 | 2026-07-02 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-005080 | Closed | 33 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-12 | Schindle-TRANSMIT-000005 |  | Trade Partner | NEL - Lift Interior Drawing - IFA | 1 | 0 | 0 | NA | REJECTED | [8 empty] | KPTG-TRANSMIT-000320 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-25 | TURN--TRANSMIT-000009 | NA | Trade Partner | Steel PFC Shop Drawings Rev 1 - Naming Conventions Amended | 19 | 0 | 0 |  | APPROVED | 2026-06-26 | NA | 272 | 2026-07-06 |  | Pending 2 drawings, under review with Armaan ( Kapitol) | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-000215 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-26 | Jangho-TRANSMIT-000197 | NA | Trade Partner | Podium Level 4~5 Floor Plan Shop Drawing_PDF_Rev 02_For Approval | 4 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 853 | 2026-07-08 |  |  | 2026-07-09 | 2026-07-10 | KPTG-TRANSMIT-002807 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-26 | RDSBIM-TRANSMIT-000077 | NA | Trade Partner | GREYSTAR ¦ L07 ¦ CPP ¦ IFR ¦ FOR SUBMISSION | 6 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 1345 | 2026-07-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-26 | Jangho-TRANSMIT-000199 | NA | Trade Partner | Re: FT01&FT02 PMU Comparison Report | 0 | 1 | 0 | NA | APPROVED | 2026-06-26 | WF-000810 | NA | 2026-07-07 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-002693 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-26 | RDSBIM-TRANSMIT-000078 | NA | Trade Partner | GREYSTAR ¦ L02 ¦ CPP ¦ IFC ¦ FOR SUBMISSION | 6 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 1347 | 2026-07-03 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-002600 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-26 | RDSBIM-TRANSMIT-000008 | NA | Trade Partner | 303COL ¦ BASEMENT 1 - EOT 1 ¦ IFR ¦ SUBMISSION | 2 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 270 | 2026-06-30 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-000293 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-26 | Jangho-TRANSMIT-000198 | NA | Trade Partner | Re: Updated 671 PMU drawing and test proposals for District Dockland for review | 0 | 3 | 0 | NA | REJECTED | [5 empty] | QA - REV. ERROR |  | 2026-06-26 | KPTG-TRANSMIT-002520 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-26 | RDSBIM-TRANSMIT-000009 | NA | Trade Partner | 303COL ¦ BASEMENT 1 - EOT 2 ¦ IFR ¦ SUBMISSION | 2 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 271 | 2026-06-30 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-000292 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-26 | Jangho-TRANSMIT-000200 | NA | Trade Partner | Re: FT07&FT09 PMU Comparison Report | 0 | 1 | 0 | NA | REJECTED | [5 empty] | QA - STATUS ERROR |  | 2026-06-26 | KPTG-TRANSMIT-002521 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-26 | RDSBIM-TRANSMIT-000050 | NA | Trade Partner | DISTLV ¦ LEVEL 01 ¦ CPP ¦ IFC ¦ SUBMISSION | 4 | 0 | 0 | ifc new process - Currently hold - will process tomorrow | APPROVED | 2026-06-29 | NA | 863 | 2026-07-03 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-002589 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-15 | StantecA-TRANSMIT-000286 | NA | Consultant | Updated IFC Documents - Electrical and Hydraulic - Stantec - HYD | 88 | 0 | 0 | NA | APPROVED | 2025-12-15 | WF-000100 | 199 | 2025-12-18 |  |  |  | 2026-01-12 | KPTG-TRANSMIT-000383 | Closed | 88 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-26 | SMEPS-TRANSMIT-000020 | NA | Trade Partner | Re: Shop Drawing: Electrical Submission 3 | 13 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 294 | 2026-07-02 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001060 | Closed | 13 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-26 | SIL-TRANSMIT-000035 | NA | Trade Partner | Loadbank Busway Li 4000A Routing COLO5 | 1 | 0 | 0 | NA | APPROVED | 2026-06-26 | WF-000355 | NA | 2026-07-02 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-001048 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-26 | RDSBIM-TRANSMIT-000051 | NA | Trade Partner | DISTLV ¦ LEVEL 01 ¦ CPP ¦ IFC ¦ SUBMISSION | 4 | 0 | 0 | ifc new process - Currently hold - will process tomorrow | APPROVED | 2026-06-29 | NA | 864 | 2026-07-03 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-002583 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-26 | RDSBIM-TRANSMIT-000052 | NA | Trade Partner | DISTLV ¦ LEVEL 04 CPP ¦ FOR SUBMISSION | 6 | 0 | 0 | ifc new process - Currently hold - will process tomorrow | APPROVED | 2026-06-29 | NA | 865 | 2026-07-02 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-002816 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-26 | Schindle-TRANSMIT-000019 | NA | Trade Partner | Schindler Drawings Transmittal | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Actual received date 25/06/2026 same revision submitted IFA not received Multiple pages in drawing different drawing status in a transmittal |  | 2026-06-26 | KPTG-TRANSMIT-001342 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-26 | BIMF-TRANSMIT-000004 | NA | Trade Partner | Mez Hydraulic Setout Building A, Rev A | 1 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 858 | 2026-07-03 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-002674 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-26 | SMEPS-IntCorr-000340 | NA | Trade Partner | Cell 1 CEI test results | 0 | 1 | 0 | NA | APPROVED | 2026-06-26 | WF - 000508 | NA | 2026-07-03 |  | NA | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-001047 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-26 | SMEPS-TRANSMIT-000235 | NA | Trade Partner | Earth bracket - comms brasket tech data sheet approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-26 | WF - 000509 | NA | 2026-07-03 |  | NA | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-001053 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-26 | Auspan-TRANSMIT-000427 | NA | Trade Partner | Precast shop drawings for approval. Zone 4, 5 level 5 | 32 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 1351 | 2026-07-03 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003098 | Closed | 32 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-26 | HDRAus-TRANSMIT-000516 | NA | Consultant | M3 Stage 4 - Document upload | 4 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 3678 | 2026-06-30 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-019571 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-15 | StantecA-TRANSMIT-000286 | NA | Consultant | Updated IFC Documents - Electrical and Hydraulic - Stantec - ELE | 22 | 0 | 0 | NA | APPROVED | 2025-12-15 | WF-000101 | 201 | 2025-12-18 |  | Workflow terminated. |  | 2025-12-16 | KPTG-TRANSMIT-000342 | Closed | 22 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-26 | Auspan-TRANSMIT-000427 | NA | Trade Partner | Precast shop drawings for approval. Zone 4, 5 level 5 | 4 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to difference in document number, title and revision- DRAFT-008915 |  | 2026-06-26 | DRAFT-008915 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-26 | Schindle-TRANSMIT-000013 | NA | Trade Partner | MLC - Schindler Lift 2 Drawings for Approval | 4 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 347 | 2026-07-02 |  | WF VOIDED.ADP REVIEW NEEDS |  | 2026-06-26 |  | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-26 | Entire M-TRANSMIT-000075 | NA | Trade Partner | Leak Detection Issued for Approval Rev B | 0 | 1 | 0 | NA | APPROVED | 2026-06-26 | WF-000356 | NA | 2026-07-02 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-001055 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-26 | Auspan-TRANSMIT-000426 | NA | Trade Partner | Precast shop drawing for approval. Panel 3P4057 | 1 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 1353 | 2026-07-03 |  | Rejected by Reviewer | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-002632 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-26 | WAM-TRANSMIT-000818 | NA | Consultant | WAM ARCH - Facade package updates | 40 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 860 | 2026-06-30 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-002823 | Closed | 40 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-26 | PenskePS-TRANSMIT-000015 | NA | Trade Partner | MEL11 COLO4 GPC - FAT Reports and Austhorisation to ship docs for approval | 0 | 9 | 0 | NA | APPROVED | 2026-06-26 | WF-000357 | NA | 2026-07-02 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-001025 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-26 | SES AU-TRANSMIT-000071 | NA | Trade Partner | SCEC Cable Reticulation Drawings | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No longer in Use, Just Updated document register.KPTG-IntCorr-000631 |  | 2026-06-26 | KPTG-IntCorr-000631 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-26 | SES AU-TRANSMIT-000072 | NA | Trade Partner | SECURITY - SCEC TYPE 1A Shop Drawings - IFC | 4 | 0 | 0 | NA | APPROVED | 2026-06-26 | WF-000358 | NA | 2026-06-30 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-001012 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-26 | Stowe-A-TRANSMIT-000629 | NA | Trade Partner | Stowe - AS Builts | 19 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 4327 | 2026-07-01 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-019189 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-26 | WGAVIC-TRANSMIT-000151 | NA | Consultant | M2 - Stages 9 & 10 Removal of Switchroom Setdown - Issued for Construction | 5 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 1205 | 2026-07-03 |  |  | 2026-07-09 | 2026-07-09 | KPTG-DA-003627 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-12 | JCBa-TRANSMIT-000047 | NA | Consultant | IFC_GA, SSP | 44 | 0 | 0 | NA | APPROVED | 2026-01-12 | WF-000116 | 226 | 2026-01-15 |  |  |  | 2026-01-22 | KPTG-TRANSMIT-000457 | Closed | 44 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-26 | WGAVIC-TRANSMIT-000152 | NA | Consultant | M2 - Stage 9 HV Room - Clarifications - Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 1208 | 2026-07-03 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-005651 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-26 | INTRFRM-TRANSMIT-000093 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 21) | 0 | 4 | 0 | NA | APPROVED | 2026-06-26 | WF-000247 | NA | 2026-07-07 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-26 | WGAVIC-TRANSMIT-000155 | NA | Consultant | M2 - Stage 11 Level 2 Equipment Layout - Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 1210 | 2026-07-03 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-005655 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-26 | RDSBIM-TRANSMIT-000282 | NA | Trade Partner | NXM3S4 LEVEL 01 C-1-019 ACC WC IFC FOR SUBMISSION | 1 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 3680 | 2026-06-30 |  | Terminated as instructed by lachlan |  | 2026-08-11 | KPTG-TRANSMIT-020492 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-26 | WGAVIC-TRANSMIT-000156 | NA | Consultant | M2 - Stage 9 Level 2 Concrete - Issued for Construction | 4 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 1212 | 2026-07-03 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-005659 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-26 | Civilex-TRANSMIT-000111 | NA | Trade Partner | Updated Above Ground OSD Tank | 3 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 862 | 2026-07-08 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-003224 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-26 | SKS Tech-TRANSMIT-000186 | NA | Trade Partner | Equipment Layout for approval | 7 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 3682 | 2026-07-08 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-26 | D&E-TRANSMIT-000869 | NA | Trade Partner | Re: ISSUED FOR APPROVAL - ROOF LEVEL CHILLER ROOMS 9 & 10 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-06-26 | KPTG-RFI-008614 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-26 | SMEPS-TRANSMIT-000325 | NA | Trade Partner | Revised Jemena Shopdrawing - 25.06.2026 | 2 | 0 | 0 | NA | APPROVED | 2026-06-26 | WF-006168 | NA | 2026-06-26 |  | Terminated as directed by Charlie Johnstone for submitting updated document. | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-019484 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-26 | Ardon-TRANSMIT-000053 | NA | Trade Partner | Priority 8 Door Frame Shop Drawings | 36 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 3684 | 2026-07-01 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-019354 | Closed | 36 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-12 | JCBa-TRANSMIT-000048 | NA | Consultant | IFC_GA, SSP - L03-6 | 44 | 0 | 0 | NA | APPROVED | 2026-01-12 | WF-000117 | 228 | 2026-01-15 |  |  |  | 2026-01-15 | KPTG-TRANSMIT-000408 | Closed | 44 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-26 | WRAP-TRANSMIT-000071 | NA | Trade Partner | Updated Ground Floor BTR (services) | 16 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 578 | 2026-07-01 |  | NA | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-003104 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-26 | D&E-TRANSMIT-000873 | NA | Trade Partner | SFN Pipework Flushing Procedure - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-26 | WF-006171 | NA | 2026-07-22 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-26 | D&E-TRANSMIT-000874 | NA | Trade Partner | OAF Fan Static Sensor Technical Data - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-26 | WF-006173 | NA | 2026-07-22 |  |  | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-019854 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-26 | VIA Arch-TRANSMIT-000171 | NA | Consultant | ARCH UPDATED DRAWINGS 12.06.2026 | 49 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 1217 | 2026-07-03 |  |  | 2026-07-24 | 2026-07-24 | KPTG-DA-003929 | Closed | 49 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-26 | NXT-TRANSMIT-001644 | NA | Trade Partner | M3 Stage 2-4 - PPR Annex. W Incident Notification Guide Update | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution only. |  | 2026-06-26 | KPTG-TRANSMIT-019077 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-26 | SMEPS-TRANSMIT-000229 | SPARK-CRFI KPG-000388 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0613 | 1 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 333 | 2026-07-03 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-001350 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-26 | D&E-TRANSMIT-000274 | NA | Trade Partner | Rejected Mechanical Drawings with D&E comments addressing AWJV comments | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Already received and reviewed |  | 2026-06-26 | KPTG-TRANSMIT-001349 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-26 | Entire M-TRANSMIT-000035 | NA | Trade Partner | FOA-2 Pump Submission | 0 | 1 | 0 | NA | APPROVED | 2026-06-26 | WF-000249 | NA | 2026-07-09 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-26 | D&E-TRANSMIT-000870 | NA | Trade Partner | BMS Functional Description - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Distribution only. |  | 2026-06-26 | KPTG-TRANSMIT-019081 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-26 | INGEN3D-TRANSMIT-000140 | NA | Trade Partner | Re: I3D-389 District Living - Level 9-11 - Precast Walls - IFA (26-06-2026) | 9 | 0 | 0 | NA | APPROVED | 2026-06-29 | WF-000832 | NA | 2026-07-07 |  | submitted along with 144 TRN | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-003102 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-31 | RDSBIM-TRANSMIT-000008 | NA | Trade Partner | GREYSTAR ¦ BASEMENT FLOOR CONCRETE PROFILE KEY PLAN | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect drawing status. |  | 2026-01-12 | KPTG-SADV-000503 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-26 | INGEN3D-TRANSMIT-000137 | NA | Trade Partner | I3D-389 District Living - Level 6-8 - Precast Walls - IFA (26-06-2026) | 7 | 0 | 0 | NA | APPROVED | 2026-06-26 | WF-000815 | NA | 2026-07-15 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003249 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-26 | INGEN3D-TRANSMIT-000138 | NA | Trade Partner | I3D-389 District Living - Level 7-9 - Precast Walls - IFA (26-06-2026) | 8 | 0 | 0 | NA | APPROVED | 2026-06-26 | WF-000816 | NA | 2026-07-13 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-003191 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-26 | INGEN3D-TRANSMIT-000139 | NA | Trade Partner | I3D-389 District Living - Level 8-10 - Precast Walls - IFA (26-06-2026) | 10 | 0 | 0 | NA | APPROVED | 2026-06-26 | WF-000817 | NA | 2026-07-13 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-003193 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-26 | Entire M-TRANSMIT-000036 | NA | Trade Partner | FOA-2 - Return Design Brief | 0 | 1 | 0 | NA | APPROVED | 2026-06-26 | WF-000250 | NA | 2026-07-09 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-000948 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-26 | HDRAus-TRANSMIT-000517 | NA | Consultant | M3 SW - Document upload - PDF and CAD | 1 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 4332 | 2026-06-30 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-020784 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-26 | INGEN3D-TRANSMIT-000142 | NA | Trade Partner | I3D-389 District Living - Level 10-11 - Precast Walls - IFA (26-06-2026) | 10 | 0 | 0 | NA | APPROVED | 2026-06-26 | WF-000818 | NA | 2026-07-13 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-003195 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-26 | Schindle-TRANSMIT-000014 | NA | Trade Partner | Re: Schindler updated Drawing | 1 | 0 | 0 | KPTG-IntCorr-008430 | APPROVED | [5 empty] | Kapitol Advice Awaits: KPTG-IntCorr-008430, it is already in review:354# KPTG-TRANSMIT-003030 |  | 2026-06-26 | KPTG-IntCorr-008430,KPTG-TRANSMIT-003030 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-26 | D&E-TRANSMIT-000872 | NA | Trade Partner | SFN Scripts - Issued for Approval | 0 | 13 | 0 | NA | REJECTED | [5 empty] | Document number and revision number mismatch |  | 2026-06-26 | KPTG-RFI-008631 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-26 | Tradetec-TRANSMIT-000466 | NA | Trade Partner | Tech Data - Jemena Easement Fill Material - IFA | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Issue with revision number. |  | 2026-06-26 | KPTG-SADV-006216 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-26 | Tradetec-TRANSMIT-000467 | NA | Trade Partner | Shop Drawing - Stage 2 - CE TRENCH RUN | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with Document number, revision and title. |  | 2026-06-26 | KPTG-SADV-006217 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-09 | RDSBIM-TRANSMIT-000009 | NA | Trade Partner | GREYSTAR ¦ FORMATION LEVEL LAYOUT KEYPLAN, LAYOUT AND SECTIONS | 8 | 0 | 0 | NA | APPROVED | 2026-01-12 | WF-000118 | 230 | 2026-01-15 |  |  |  | 2026-01-16 | KPTG-TRANSMIT-000417 | Closed | 8 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-26 | SKS Tech-TRANSMIT-000184 | NA | Trade Partner | Roof level lighting report | 0 | 1 | 0 | NA | APPROVED | 2026-06-26 | WF-006163 | NA | 2026-07-08 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-26 | ACG-TRANSMIT-000105 | NA | Trade Partner | M3 Stage 4 - External Drawing | 2 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 3686 | 2026-07-09 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-019884 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-26 | DLTS-TRANSMIT-000001 | NA | Trade Partner | Fire Room-IFA Issue | 21 | 0 | 0 | NA | APPROVED | 2026-06-26 | WF-006177 | NA | 2026-07-10 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-26 | Tradetec-TRANSMIT-000465 | NA | Trade Partner | IFC - Stage 4 - LVP 35, CP32 | 2 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 3689 | 2026-07-10 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-019328 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-26 | DLTS-TRANSMIT-000002 | NA | Trade Partner | Southern Stairs-IFA Issue | 30 | 0 | 0 | NA | APPROVED | 2026-06-26 | WF-006176 | NA | 2026-07-11 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-020967 | Closed | 30 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-26 | D&E-TRANSMIT-000871 | NA | Trade Partner | Fwd: ISSUED FOR CONSTRUCTION - CHW PIPE LAYOUTS | 3 | 0 | 0 | NA | APPROVED | [5 empty] | ONLY FOR DISTRIBUTION |  | 2026-06-26 | KPTG-TRANSMIT-019101 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-26 | HDRAus-TRANSMIT-000518 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 8 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 3696 | 2026-07-10 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-019400 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-26 | SMEPS-TRANSMIT-000326 | NA | Trade Partner | SME - IFC Documentation | 44 | 0 | 0 | NA | REJECTED | [5 empty] | Document revision and title mismatch |  | 2026-06-26 | KPTG-RFI-008632 | Closed | 44 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-26 | ZIA-TRANSMIT-000109 | NA | Trade Partner | M3S2 CSMS UCOP-SLA & Batt-SLA Roof Level Zone B1&B2 Revision Submission | 2 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 4330 | 2026-07-01 |  |  | 2026-07-06 | 2026-06-29 | KPTG-TRANSMIT-019129 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | ARCST-TRANSMIT-000268 | NA | Trade Partner | Chemical Store Roof - Issued for Re-Approval | 0 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-019102 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-01 | Civilex-TRANSMIT-000162 | NA | Client | Southern Retaining Wall SGE Documents RevE | 2 | 0 | 0 | NA | APPROVED | 2025-12-02 | NA | 3397 | 2025-12-04 |  |  |  | 2025-12-10 | KPTG-TRANSMIT-010785 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-12 | Auspan-TRANSMIT-000038 | NA | Trade Partner | Precast shop drawings for approval. Zone 1, 2. | 40 | 0 | 0 | NA | APPROVED | 2026-01-12 | WF-000119 | 232 | 2026-01-19 |  |  |  | 2026-01-30 | KPTG-TRANSMIT-000502 | Closed | 40 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-26 | Teams message Ibrahim - Service Cmx Plans | NA | Trade Partner | Service Cmx Plans - CSMS | 0 | 1 | 0 | Documents currently under w/flow. Need clarification<br> | APPROVED | 2026-06-30 | WF-001129 | NA | 2026-07-03 |  | Documents currently under w/flow. Need clarification |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-26 | Teams message Ibrahim - MEC | NA | Trade Partner | MEC | 0 | 1 | 0 | NA | APPROVED | 2026-06-26 | WF-001124 | NA | 2026-06-30 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-004167 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-26 | Teams message Ibrahim - ELE | NA | Trade Partner | ELE | 0 | 1 | 0 | NA | APPROVED | 2026-06-26 | WF-001125 | NA | 2026-06-30 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-004165 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-26 | Teams Message - Eaton ITP | NA | Trade Partner | Eaton ITP | 0 | 6 | 0 | NA | APPROVED | 2026-06-26 | WF-001126 | NA | 2026-06-30 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-26 | Teams Message - SKS ITP | NA | Trade Partner | SKS ITP | 0 | 15 | 0 | NA | APPROVED | 2026-06-26 | WF-001127 | NA | 2026-06-30 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-26 | Teams Message - SKS ITP | NA | Trade Partner | SKS ITP | 0 | 14 | 0 | Documents currently under w/flow. Need clarification<br> | APPROVED | 2026-06-30 | WF-001131 | NA | 2026-07-02 |  | Documents currently under w/flow. Need clarification |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-26 | Teams Message - Hydraulics ITP | NA | Trade Partner | Hydraulics ITP | 0 | 5 | 0 | NA | APPROVED | 2026-06-26 | WF-001128 | NA | 2026-06-30 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-26 | Baigents-TRANSMIT-000224 | NA | Trade Partner | 2026-06-26 L5 Platform Handrail FOA-2 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected by Luke |  | 2026-06-26 | KPTG-IntCorr-001564 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-26 | fjc-TRANSMIT-000161 | NA | Consultant | Architecturals - Facade Setout / Mezz | 17 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 679 | 2026-07-01 |  |  | 2026-06-29 | 2026-06-29 | KPTG-SADV-004706 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-26 | fjc-TRANSMIT-000162 | NA | Consultant | Architecturals - update to ARC-FJC-72160 | 1 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 680 | 2026-07-01 |  |  | 2026-06-29 | 2026-06-29 | KPTG-SADV-004705 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-12 | Kone-VIC-TRANSMIT-000001 | NA | Trade Partner | Lift 1-2, 3-4, 5 & Good Lift layout drawings for review and approval | 4 | 0 | 0 | NA | APPROVED | 2026-01-15 | WF-000129 | NA | 2026-01-23 |  | Incorrect drawing number; TP did not follow Despro -1 - KPTG-SADV-000511. As advised by Kapitol PC, this submission made an exception and an Aconex workflow initiated for review. KPTG-IntCorr-000221. |  | 2026-02-03 | KPTG-WTRAN-000303 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-26 | KPTG-WTRAN-001494 | NA | Trade Partner | Tuckpointing South Facade - (T&P, T&P, KG) | 0 | 1 | 0 | NA | APPROVED | 2026-04-24 | WF-000772 | NA | 2026-04-29 |  | THERE IS NO MOTHER TRANSMITTAL FOR THIS DOCUMENT CHARLIE DIRECT UPLOAD THE DOCUMENT IN ACONEX.AS PER HIS ADVICE WE CREATED WF IN 24-04-2026. | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-002613 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-26 | JCBa-TRANSMIT-000144 | NA | Consultant | Structural Setout Plans for IFC: Level 8 | 5 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 1349 | 2026-07-03 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-002578 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-26 | Auspan-TRANSMIT-000428 | NA | Trade Partner | Update cast in plate layout for zone 4, 5. | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to Document QC error - DRAFT-008910 |  | 2026-06-26 | DRAFT-008910 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-26 | JFS-AU-TRANSMIT-000001 | NA | Consultant | Facade Weatherproofing PBDB and Facade Wind Pressure Report | 0 | 1 | 0 | NA | APPROVED | 2026-06-26 | NA | 276 | 2026-07-03 |  | Redstick Review | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-000227 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-26 | Auspan-TRANSMIT-000429 | NA | Trade Partner | : Update IFCed precast shop drawings. Level 1 zone 4, 5 | 2 | 0 | 2 | KPTG-IntCorr-000778 | APPROVED |  | NA | NA |  |  | IFC - QC OK - Kapitol PC Kim to confirm - KPTG-IntCorr-000778 - ON HOLD AS ADVISED BY KIM |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-26 | Auspan-TRANSMIT-000430 | NA | Trade Partner | Update IFCed precast shop drawings due to penos added. Zone 1, 2, 5 level 2. | 4 | 0 | 0 | KPTG-IntCorr-000779 | APPROVED |  | NA | NA |  |  | IFC -Kapitol PC Kim to confirm - KPTG-IntCorr-000779 IFC 3 drawings Update register and transmit - KPTG-TRANSMIT-002589 1 drawings already superseded. |  | 2026-07-06 | KPTG-TRANSMIT-002589 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-26 | Auspan-TRANSMIT-000431 | NA | Trade Partner | Precast shop drawings for construction. Levels 3, 4, 5. | 4 | 0 | 0 | KPTG-IntCorr-000780 | APPROVED |  | NA | NA |  |  | IFC - QC OK Kapitol PC Kim to confirm - KPTG-IntCorr-000780 1 OK to proceed; Register and transmit - KPTG-TRANSMIT-002611 3 rejected, 4 on Hold - DRAFT-009420 |  | 2026-07-06 | KPTG-TRANSMIT-002611 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-26 | JFS-AU-TRANSMIT-000001 | NA | Consultant | Facade Weatherproofing PBDB and Facade Wind Pressure Report | 0 | 1 | 0 | NA | APPROVED | 2026-06-26 | NA | 277 | 2026-07-03 |  | Redstick Review | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-000227 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-26 | JCBa-TRANSMIT-000145 | NA | Consultant | : Updated Architectural Documentation - Joinery Details and Kitchen & Robe Joinery Schedules | 4 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 1355 | 2026-06-30 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-002680 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-26 | JFS-AU-TRANSMIT-000001 | NA | Consultant | SME REVIEW - Facade Weatherproofing PBDB and Facade Wind Pressure Report (IFA) | 0 | 1 | 0 | NA | APPROVED | 2026-06-26 | NA | 274 | 2026-07-03 |  | SME REVIEW | 2026-07-16 | 2026-07-16 | KPTG-IntCorr-000234 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-12 | Kone-VIC-TRANSMIT-000002 | NA | Trade Partner | Lift Shop Drawings | 4 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-01-12 | KPTG-SADV-000511 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-26 | JFS-AU-TRANSMIT-000001 | NA | Consultant | SME REVIEW - Facade Weatherproofing PBDB and Facade Wind Pressure Report (IFI) | 0 | 1 | 0 | NA | APPROVED | 2026-06-26 | NA | 275 | 2026-07-03 |  | SME REVIEW | 2026-07-16 | 2026-07-16 | KPTG-IntCorr-000234 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-26 | NXT-TRANSMIT-000427 | NA | Client | M3S6 - Barkers Fencing Design | 1 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 277 | 2026-07-06 |  |  | 2026-07-21 | 2026-07-22 | KPTG-TRANSMIT-000655 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-26 | NXT-TRANSMIT-000428 | NA | Client | Site Expansion - PPR Annex. W Incident Notification Guide Update | 0 | 1 | 0 | NA | APPROVED | 2026-06-26 | NA | 279 | 2026-07-06 |  |  | 2026-07-21 | 2026-07-22 | KPTG-TRANSMIT-000654 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-26 | PTA-TRANSMIT-000013 | NA | Consultant | General Architectural Update - Issue for Coordination | 5 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 281 | 2026-07-06 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-000480 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-26 | KPTG-TRANSMIT-000323-SME | NA | Consultant | Architecture (Stairs, Elevations & Block 1 CPP | 17 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 285 | 2026-07-06 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-000551 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-26 | KPTG-TRANSMIT-000323-NEXTDC Review | NA | Consultant | Architecture (Stairs, Elevations & Block 1 CPP | 17 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 287 | 2026-07-06 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-26 | Civilex-TRANSMIT-000012 | NA | Trade Partner | Sample Submission - Concrete Mix Design for Piling | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Without Cover sheet submission |  | 2026-06-26 | Awaiting approval | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-26 | RBG-TRANSMIT-000005 | NA | Trade Partner | TC7 IFC drawings | 2 | 0 | 0 | KPTG-IntCorr-000240 | APPROVED |  | NA | NA |  |  | Update register only |  | 2026-07-01 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-26 | 4DW-TRANSMIT-000059 | NA | Consultant | Structural Documentation: Block 2 - Precast walls issued with Certification updates. | 6 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 283 | 2026-07-06 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-000755 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-26 | WilsonPD-TRANSMIT-000100 | NA | Trade Partner | HYDRAULIC SERVICES STAGE 9 LEVEL 2 - SEWER & STORMWATER LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 1218 | 2026-06-30 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-005083 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-12 | Auspan-TRANSMIT-000040 | NA | Trade Partner | Re: Update precast dowel layout for zone 4, 5 | 2 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-01-12 | KPTG-TRANSMIT-000379 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-26 | WilsonPD-TRANSMIT-000101 | NA | Trade Partner | HYDRAULIC SERVICES STAGE 9 LEVEL 2 - WATER SUPPLY LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 1216 | 2026-06-30 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-005027 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-26 | Tradetec-TRANSMIT-000147 | NA | Trade Partner | Hauff-Technik Polymer Flange | 0 | 1 | 0 | NA | APPROVED | 2026-06-26 | WF-001060 | NA | 2026-07-08 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-005492 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-26 | VIA Arch-TRANSMIT-000168 | NA | Consultant | S9-11 Door Schedule and Signage Plans | 13 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 1198 | 2026-07-03 |  |  | 2026-07-14 | 2026-07-14 | KPTG-DA-003703 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-26 | VIA Arch-TRANSMIT-000169 | NA | Consultant | M2 S9 West Elevation - IFBP-5 | 1 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 1201 | 2026-07-03 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-005206 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-26 | VIA Arch-TRANSMIT-000170 | NA | Consultant | M2 S9 Building Permit & All Stage Procurement | 19 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 1202 | 2026-07-03 |  |  | 2026-07-14 | 2026-07-14 | KPTG-DA-003704 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-26 | Ardon-TRANSMIT-000004 | NA | Trade Partner | Ground Level Shop Drawings | 26 | 0 | 0 | NA | APPROVED | 2026-06-26 | WF-001057 | NA | 2026-07-07 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-005431 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-26 | CRSol-TRANSMIT-000013 | NA | Trade Partner | CRS - Structural Ceiling -Stage 9 - DH21 &DH24 Shop Drawing IFA - REV 3 - CD09 Changes | 13 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 1196 | 2026-07-03 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-005272 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-26 | B Smart-TRANSMIT-000089 | NA | Consultant | A16 bathroom and kitchen drawings | 25 | 0 | 0 | NA | APPROVED | 2026-06-27 | NA | 598 | 2026-06-30 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-001293 | Closed | 25 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-12 | Auspan-TRANSMIT-000041 | NA | Trade Partner | Resubmit precast shop drawings for approval. | 15 | 0 | 0 | NA | APPROVED | 2026-01-12 | WF-000120 | 234 | 2026-01-19 |  |  |  | 2026-02-04 | KPTG-TRANSMIT-000546 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-05 | KPTG-TRANSMIT-000162-NEXTDC | NA | Consultant | ACC Workflows Required - NEXTDC | 47 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | 174 | 2026-06-12 |  |  | 2026-07-02 | 2026-07-03 | KPTG-DA-000573 | Closed | 47 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-26 | JCBa-TRANSMIT-000263 | NA | Consultant | Building Permit Issue | 22 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 579 | 2026-07-01 |  | NA | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-003089 | Closed | 22 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-29 | SMEPS-TRANSMIT-000328 | NA | Trade Partner | Re: SME - IFC Documentation | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Some of the drawings are missing |  | 2026-06-29 | KPTG-IntCorr-015318 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-29 | Tradetec-TRANSMIT-000468 | NA | Trade Partner | Tech Data - Jemena Easement Fill Material - IFA | 0 | 2 | 0 | NA | APPROVED | 2026-06-29 | WF-006231 | NA | 2026-07-10 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-019276 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-29 | INGEN3D-TRANSMIT-000143 | NA | Trade Partner | I3D-389 District Living - Level 11-12 - Precast Walls - IFA (26-06-2026) | 10 | 0 | 0 | NA | APPROVED | 2026-06-29 | WF-000831 | NA | 2026-07-15 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-29 | Jangho-TRANSMIT-000202 | NA | Trade Partner | Window Wall PMU Shop Drawing_Rev 01_For Approval | 12 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 867 | 2026-07-06 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-002821 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-29 | KALLIBRE-TRANSMIT-000003 | NA | Trade Partner | LKR-01 Sample/TDS | 0 | 1 | 0 | NA | APPROVED | 2026-06-29 | WF - 001059 | NA | 2026-07-03 |  | NA | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-003115 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-29 | Tradetec-TRANSMIT-000469 | NA | Trade Partner | Shop Drawing - Stage 2 - CE TRENCH RUN | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with Document number. |  | 2026-06-29 | KPTG-SADV-006225 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-29 | Rinco-TRANSMIT-000059 | NA | Consultant | Roof Structural Steelwork | 4 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 1358, 1364 | 2026-07-01 |  | Not published; SME Review is open. | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002720 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-02 | JCBa-TRANSMIT-000146 | NA | Consultant | Thermal Performance Plans: Updated IFC | 2 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1396 | 2026-07-06 |  | Review voided to update the drawing. Superseded by JCBa-TRANSMIT-000148 | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002712 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-12 | RDSBIM-TRANSMIT-000010 | NA | Trade Partner | GREYSTAR BASEMENT FLOOR CONCRETE PROFILE KEY PLAN | 9 | 0 | 0 | NA | APPROVED | 2026-01-12 | WF-000121 | 236 | 2026-01-15 |  |  |  | 2026-01-16 | KPTG-TRANSMIT-000418 | Closed | 9 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-29 | Nilsen3-TRANSMIT-000054 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 4 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 1236 | 2026-07-06 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-005278 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-29 | Jangho-TRANSMIT-000204 | NA | Trade Partner | Re: FT13 System Concept Drawing_Rev 02_PDF_For Approval | 18 | 0 | 0 | NA | REJECTED | [5 empty] | Revision not updated |  | 2026-06-29 | KPTG-TRANSMIT-002561 | Closed | 18 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-29 | JCI-TRANSMIT-000020 | NA | Trade Partner | BAS Document Transmittal | 22 | 0 | 0 | NA | APPROVED | 2026-06-29 | WF-000359 | NA | 2026-07-02 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-001022 | Closed | 22 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-29 | Entire M-TRANSMIT-000076 | NA | Trade Partner | Mechanical BAS drawing updates | 6 | 0 | 0 | NA | APPROVED | 2026-06-29 | WF-000360 | NA | 2026-07-02 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001032 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-29 | INGEN3D-TRANSMIT-000145 | NA | Trade Partner | I3D-389 District Living - Level 18-20 - PC0613-3 - New IFA (29-09-2026) | 1 | 0 | 0 | NA | APPROVED | 2026-06-29 | WF-000834 | NA | 2026-07-15 |  |  | 2026-07-01 | 2026-07-01 | NA- Work flow Terminated as instructed | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-29 | INGEN3D-TRANSMIT-000146 | NA | Trade Partner | I3D-389 District Living - Level 13-14 - Precast Walls - IFA (29-06-2026) | 10 | 0 | 0 | NA | APPROVED | 2026-06-29 | WF-000835 | NA | 2026-07-15 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-29 | INGEN3D-TRANSMIT-000147 | NA | Trade Partner | I3D-389 District Living - Level 12-13 - Precast Walls - IFA (29-06-2026 | 12 | 0 | 0 | NA | REJECTED | [5 empty] | Title difference |  | 2026-06-29 | KPTG-TRANSMIT-002562 | Closed | 12 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-29 | Auspan-TRANSMIT-000434 | NA | Trade Partner | Precast shop drawings for construction. Level 2. | 14 | 0 | 0 | KPTG-IntCorr-000786 | APPROVED | [5 empty] | IFC - Waiting for Kim advise- KPTG-IntCorr-000786 KPTG-IntCorr-000852 - 5 drawings rejected. 9 are OK to proceed - Register and transmit KPTG-TRANSMIT-002591 |  | 2026-07-06 | KPTG-TRANSMIT-002591 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-29 | Auspan-TRANSMIT-000434 | NA | Trade Partner | Precast shop drawings for construction. Level 2. | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | IFC - Rejected due to same revision number as per latest version. DRAFT-008979 |  | 2026-06-29 | DRAFT-008979 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-29 | Nilsen3-TRANSMIT-000208 | NA | Trade Partner | Nilsen Shop Drawings - IFC | 5 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 3699 | 2026-07-08 |  | This workflow contains 2 out of the total 5 drawings terminated as instructed byDuncan Cameron - Terminated the designer to re-issue them |  | 2026-08-21 | KPTG-TRANSMIT-020818 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-20 | CRSol-TRANSMIT-000068 | NA | Trade Partner | Ceiling Drawings Issued for Approval - C1 / C2 / C3 | 10 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect document number |  | 2025-12-22 | KPTG-DA-004036 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-29 | Nilsen3-TRANSMIT-000208 | NA | Trade Partner | Nilsen Shop Drawings - IFC | 5 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 3700 | 2026-07-08 |  | This workflow contains 3 out of the total 5 drawings Terminated as instructed by Duncan Cameron - Terminated the designer to re-issue them |  | 2026-08-21 | KPTG-TRANSMIT-020818 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-29 | JCI-TRANSMIT-000021 | NA | Trade Partner | BAS Document Transmittal | 1 | 0 | 0 | NA | APPROVED | 2026-06-29 | WF-000361 | NA | 2026-07-02 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001041 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-29 | INGEN3D-TRANSMIT-000148 | NA | Trade Partner | I3D-389 District Living - Level 14-15 - Precast Walls - IFA (29-06-2026) | 10 | 0 | 0 | NA | APPROVED | 2026-06-29 | WF-000836 | NA | 2026-07-15 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-003305 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-29 | RDSBIM-TRANSMIT-000218 | NA | Trade Partner | LEVEL 03 EAST & WEST PAVILION ROOF LAYOUT AND SECTIONS | 4 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 583 | 2026-07-06 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-29 | BIMF-TRANSMIT-000005 | NA | Trade Partner | Mez Hydraulic Setout Building B | 1 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 870 | 2026-07-06 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-002900 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-29 | Auspan-TRANSMIT-000436 | NA | Trade Partner | Resubmit panel 1P4056 for approval. Priority. | 1 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 1363 | 2026-07-06 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-002629 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-29 | ACG-TRANSMIT-000106 | NA | Consultant | M3 - Stage 4 Shop Drawings - IFA Revision | 14 | 0 | 0 | NA | REJECTED | [5 empty] | Revision of the documents not updated |  | 2026-06-29 | KPTG-RFI-008636 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-29 | SMEPS-TRANSMIT-000021 | NA | Trade Partner | Shop Drawings: Electrical (Submission 4) | 1 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 296 | 2026-07-03 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001058 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-29 | Entire M-TRANSMIT-000037 | NA | Trade Partner | FOA-2 VSDs | 0 | 1 | 0 | NA | APPROVED | 2026-06-29 | WF-000253 | NA | 2026-07-10 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-000949 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-29 | D&E-TRANSMIT-000875 | NA | Trade Partner | ISSUED FOR APPROVAL - ROOF LEVEL - CHILLER ROOM 8 LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 3702 | 2026-06-11 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020119 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-29 | RDSBIM-TRANSMIT-000171 | NA | Trade Partner | NXM3S2 ¦ GROUND FLOOR B-G-096 & B-G-014 FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2025-12-30 | NA | 3591 | 2026-01-08 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-29 | KPTG-IntCorr-000537 | NA | Trade Partner | Security Workflow MEL05C4-SEC-Z-TDS-260 | 0 | 1 | 0 | NA | APPROVED | 2026-06-29 | WF - 000510 | NA | 2026-07-06 |  | NA | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-001059 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-29 | Auspan-TRANSMIT-000433 | NA | Trade Partner | Precast shop drawings for construction. Panel 1P5048 | 1 | 0 | 0 | KPTG-IntCorr-000787 | APPROVED | [5 empty] | IFC - Waiting for Kim advise- KPTG-IntCorr-000787 No action, drawing superseded with Auspan-TRANSMIT-000454 |  | 2026-07-06 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-29 | SMEPS-TRANSMIT-000330 | NA | Trade Partner | Re: SME - IFA Sample submissions | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-06-29 | KPTG-IntCorr-015343 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-29 | SKS Tech-TRANSMIT-000187 | NA | Trade Partner | Lighting Compliance Conformance Report | 0 | 2 | 0 | NA | APPROVED | 2026-06-29 | WF-006187 | NA | 2026-07-23 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-29 | D&E-TRANSMIT-000877 | NA | Trade Partner | Re: Cx Plan - Rev B - Issued for Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The document reference number and revision number are missing from the document. |  | 2026-06-29 | KPTG-RFI-008640 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-29 | Ardon-TRANSMIT-000054 | NA | Trade Partner | Priority 9 Door Frame Shop Drawings | 24 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | The documents number mismatch Rejected |  | 2026-06-29 | KPTG-RFI-008639 | Closed | 24 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-18 | WSP ANZ-TRANSMIT-000017 | NA | Consultant | SME REVIEW - WSP - Updated Electrical Services drawing for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 266 | 2026-06-25 |  |  | 2026-06-29 | 2026-06-29 | KPTG-IntCorr-000212 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-29 | Auspan-TRANSMIT-000435 | NA | Trade Partner | Precast shop drawings for construction. Levels 3, 4. | 5 | 0 | 0 | KPTG-IntCorr-000792 | APPROVED | [5 empty] | IFC - Waiting for Kim advise- KPTG-IntCorr-000792 4 are OK to Proceed KPTG-TRANSMIT-002609 1 Rejected and 7 on Hold - DRAFT-009419 |  | 2026-07-06 | KPTG-TRANSMIT-002609 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-29 | Auspan-TRANSMIT-000435 | NA | Trade Partner | Precast shop drawings for construction. Levels 3, 4. | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to difference in document number and revision seems same as latest version -DRAFT-009012 |  | 2026-06-29 | DRAFT-009012 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-29 | SC-TRANSMIT-000005 | NA | Trade Partner | Re: Chemset & Primer Technical datasheet | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Title and document number difference |  | 2026-06-29 | KPTG-TRANSMIT-002560 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-05 | RDSBIM-TRANSMIT-000172 | NA | Trade Partner | NXM3S2 ¦ GROUND FLOOR-B-G-033 CLEANERS-FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-01-06 | NA | 3601 | 2026-01-15 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-29 | NXT-TRANSMIT-001647 | NA | Trade Partner | ABB PDUs - AU-10025007 - M3-CStage 4/Ph1 - Certificate of Conformance | 0 | 1 | 0 | NA | APPROVED | 2026-06-29 | WF-006189 | NA | 2026-07-10 |  | ABB-TRANSMIT-000048 |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-29 | DS-TRANSMIT-000122 | NA | Trade Partner | HYD As Built Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 4334 | 2026-07-02 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020212 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-29 | D&E-TRANSMIT-000878 | NA | Trade Partner | Fwd: Mechanical SFN Discharge Register - Issued for Review | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-06-29 | KPTG-TRANSMIT-019120 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-29 | KPTG-IntCorr-015351 | NA | Trade Partner | C3 Chiller Base Framing - Issued for Construction | 97 | 0 | 0 | NA | APPROVED | 2026-06-29 | WF-006188 | NA | 2026-07-04 |  | As instructed by Lola documents received in ARCST-TRANSMIT-000299 are under this workflow |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-29 | Jangho-TRANSMIT-000069 | NA | Trade Partner | Alum sheet color Dulux Electro Medium Bronze Kinetic - Flat Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-06-29 | WF-000822 | NA | 2026-07-07 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-29 | Jangho-TRANSMIT-000071 | NA | Trade Partner | Alum sheet color Dulux Duralloy Surfmist - Matt Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-06-29 | WF-000823 | NA | 2026-07-07 |  |  | 2026-08-21 | 2026-08-21 | WF-001210 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-29 | Jangho-TRANSMIT-000072 | NA | Trade Partner | Alum sheet color Dulux Duratec Zeus Dune - Matt Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-06-29 | WF-000824 | NA | 2026-07-07 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-003462 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-29 | Jangho-TRANSMIT-000073 | NA | Trade Partner | Alum sheet color Dulux Duratec Eternity Copper Metallic Kinetic - Matt Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-06-29 | WF-000825 | NA | 2026-07-07 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-003465 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-29 | Jangho-TRANSMIT-000070 | NA | Trade Partner | Alum sheet color Dulux Electro Pale Bronze Kinetic - Flat Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-06-29 | WF-000826 | NA | 2026-07-07 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-003467 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-29 | SMEPS-TRANSMIT-000059 | NA | Trade Partner | STAGE 11-GROUND, LV1, LV2 & LV3 LIGHTING LAYOUT | 4 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 1238 | 2026-07-06 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-005286 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-05 | NXT-TRANSMIT-001164 | NA | Client | 000573-100222 AS BUILT Lighting Control Board & ED L&P BOM, Max Demand | 0 | 4 | 0 | NA | APPROVED |  | NA | NA |  |  | As Built |  | 2026-01-06 | KPTG-TRANSMIT-011257 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-29 | M.2-TRANSMIT-000056 | NA | Trade Partner | Electrical Services Level 2 - 7 Power & Comms layouts | 15 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 1366 | 2026-07-06 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-002569 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-29 | Jangho-TRANSMIT-000074 | NA | Trade Partner | Alum sheet color Dulux Duratec Elements Weathered Steel - Flat Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-06-29 | WF-000827 | NA | 2026-07-07 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-003469 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-29 | Ardon-TRANSMIT-000055 | NA | Trade Partner | Priority 10 Door Frame Shop Drawings | 24 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 3704 | 2026-07-03 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-019414 | Closed | 24 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-29 | IVS-TRANSMIT-000369 | NA | Consultant | Re: Stage 4 - Ground Floor Steel Stair Part Plans Construction Issue | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect submission - Marked as confidential file |  | 2026-06-29 | KPTG-RFI-008642 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-06-29 | HIP-TRANSMIT-000029 | NA | Trade Partner | Re: Reissuing - Switch Room Steel - IFC Drawings - MP with Correct Title Name | 9 | 0 | 0 | NA | REJECTED | [5 empty] | The IFA has not been reviewed. |  | 2026-06-29 | DRAFT-010272 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-29 | Tradetec-TRANSMIT-000470 | NA | Trade Partner | Shop Drawing - Stage 2 - CE TRENCH RUN | 1 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 4336 | 2026-07-08 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-29 | HGP-TRANSMIT-000059 | SPARK-CRFI-KPG-000098 | Trade Partner | EXTERNAL WINDOW SHOP DRAWINGS | 18 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 334 | 2026-07-06 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-001364 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-06-29 | SMPS-TRANSMIT-000119 | NA | Trade Partner | Re: Hanwha Power Pack – O&M Manual Submission | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision number |  | 2026-06-29 | DRAFT-010273 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-29 | INGEN3D-TRANSMIT-000149 | NA | Trade Partner | I3D-389 District Living - Level 17-19 - PC0579-2 - New IFA (29-06-2026) | 1 | 0 | 0 | NA | APPROVED | 2026-06-29 | WF-000838 | NA | 2026-07-09 |  |  | 2026-07-01 | 2026-07-01 | NA - Work flow Terminated as instructed | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-12 | DbyP-TRANSMIT-000001 | NA | Consultant | Pidgeon Ward 80% Signage Update | 0 | 1 | 0 | NA | APPROVED | 2026-05-15 | NA | 124 | 2026-05-21 |  |  | 2026-07-15 | 2026-07-15 | KPTG-IntCorr-000232 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-10-03 | Facx-TRANSMIT-000001 | NA | Trade Partner | Curtainwall Details -IFA-Rev 01 | 9 | 0 | 0 | NA | APPROVED |  | NA | 2892 |  |  | Reviewed stopped between as requested by Dean Antony in Teams. |  |  | KPTG-TRANSMIT-010508 | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-12 | RDSBIM-TRANSMIT-000045 | NA | Trade Partner | LEVEL 01 RCP KEY PLAN AND LAYOUT | 5 | 0 | 0 | NA | APPROVED | 2026-01-12 | NA | 806 | 2026-01-14 |  |  | 2026-01-21 | 2026-01-21 | KPTG-TRANSMIT-002539 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-29 | Ardon-TRANSMIT-000056 | NA | Trade Partner | Priority 9 Door Frame Shop - Re-transmittal | 24 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 3707 | 2026-07-11 |  |  | 2026-07-07 | 2026-07-07 | ⁠KPTG-TRANSMIT-019418 | Closed | 24 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-29 | D&E-TRANSMIT-000876 | NA | Trade Partner | Re: Stage 2 Fire Matrix Excel IFC-8 | 0 | 1 | 0 | NA | APPROVED | 2026-06-29 | WF-006194 | NA | 2026-07-13 |  | Terminated by Melisa for submitting the updated documents. | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020189 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-29 | INGEN3D-TRANSMIT-000150 | NA | Trade Partner | I3D-389 District Living - Level 15-16 - Precast Walls - IFA (29-06-2026) | 10 | 0 | 0 | NA | APPROVED | 2026-06-29 | [5 empty] | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-003323 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-01 | WIP Package- Facade | NA | Consultant | SME REVIEW - IND - FAC - Facade Performance Specification | 0 | 1 | 0 | NA | APPROVED | 2026-06-01 | NA | 167 | 2026-06-08 |  | Review Closed - No need any distribution as advised by Renee 8-07-2026 | 2026-07-08 |  | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-29 | Entire M-TRANSMIT-000039 | NA | Trade Partner | FOA-2 Intumescent Fire Dampers | 0 | 1 | 0 | NA | APPROVED | 2026-06-29 | WF-000254 | NA | 2026-07-10 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001605 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-01 | WIP Package Facade | NA | Consultant | SME REVIEW - IND - FAC - Weatherproofing Performance Based Design Brief | 0 | 1 | 0 | NA | APPROVED | 2026-06-01 | NA | 168 | 2026-06-08 |  | Review Voided as advised by Renee 08-07-2026 ( Indesco old documents) |  | 2026-07-08 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-22 | Carr-TRANSMIT-000059 | NA | Consultant | Updated Facade Docs for Coordination | 17 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 171 | 2026-06-08 |  | Review Voided as discussed with Renee, Updated drawings received from Carr on 01-07-2026 |  | 2026-07-01 | NA | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-02 | WSP ANZ-TRANSMIT-000016 | NA | Consultant | SME REVIEW - WSP - Electrical, Specifications for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | NA | 202 | 2026-06-09 |  |  | 2026-06-29 | 2026-06-29 | KPTG-IntCorr-000212 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-02 | WSP ANZ-TRANSMIT-000016 | NA | Consultant | SME REVIEW - WSP - Electrical drawings for Approval | 14 | 0 | 0 | NA | APPROVED | 2026-06-18 | NA | 265 | 2026-06-25 |  |  | 2026-06-29 | 2026-06-29 | KPTG-IntCorr-000212 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-03 | WIP Package - Specialist Lighting | NA | Consultant | SME REVIEW - LIGHTING CONTROL FUNCTIONALITY BRIEF | 0 | 1 | 0 | NA | APPROVED | 2026-06-03 | NA | 216 | 2026-06-11 |  |  | 2026-06-29 | 2026-06-29 | KPTG-IntCorr-000212 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-12 | RDSBIM-TRANSMIT-000046 | NA | Trade Partner | LEVEL 02 RCP KEY PLAN AND LAYOUT | 5 | 0 | 0 | NA | APPROVED | 2026-01-12 | NA | 808 | 2026-01-14 |  |  | 2026-01-21 | 2026-01-21 | KPTG-TRANSMIT-002543 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-29 | SPECAUTO-TRANSMIT-000002 | NA | Trade Partner | CSMS Cabling Procurement Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-29 | WF-000255 | NA | 2026-07-10 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-001106 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-03 | WIP Package - Specialist Lighting | NA | Consultant | SME REVIEW - LIGHTING SPECIFICATION | 0 | 1 | 0 | NA | APPROVED | 2026-06-03 | NA | 214 | 2026-06-09 |  |  | 2026-06-29 | 2026-06-29 | KPTG-IntCorr-000212 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-03 | WIP Package - Specialist Lighting | NA | Consultant | SME REVIEW - SL - IFT - LUMINAIRE SCHEDULE | 0 | 1 | 0 | NA | APPROVED | 2026-06-03 | NA | 212 | 2026-06-09 |  |  | 2026-06-29 | 2026-06-29 | KPTG-IntCorr-000212 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-29 | JCBa-TRANSMIT-000264 | NA | Consultant | L09 Terraces | 10 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 584 | 2026-07-02 |  | NA | 2026-07-02 | 2026-07-02 | KPTG-DA-002957 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-29 | SPECAUTO-TRANSMIT-000003 | NA | Trade Partner | CSMS Outstation Panel General Arrangement and Schematic Shop Drawings | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Shop drawings register as Technical Data. |  | 2026-06-29 | DRAFT-003095 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-29 | KPTG-TRANSMIT-001054 | NA | Trade Partner | OFCI BAS Colo 4 Damper Actuator Schedule - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-29 | WF - 000511 | NA | 2026-07-03 |  | NA | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-001064 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-29 | D&E-TRANSMIT-000275 | SPARK-CRFI-KPG-000491, SPARK-CRFI-KPG-000466 & SPARK-CRFI-KPG-000490 | Trade Partner | ISSUED FOR CONSTRUCTION - LEVEL 1 & ROOF DUCTWORK LAYOUTS | 7 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 335 | 2026-07-06 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-001417 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-29 | VERTIV-TRANSMIT-000040 | NA | Trade Partner | NEXT DC GE 01 _ ARCHITECTURAL DRAWINGS (FOA-1 & FOA-2) | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document number inside documents and in aconex submission, revision date. |  | 2026-06-29 | KPTG-SADV-000767 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-29 | NXT-TRANSMIT-000372-SEC | NA | Client | Facade Scope | 0 | 3 | 0 | NA | APPROVED | 2026-06-29 | NA | 286 | 2026-07-06 |  |  | 2026-06-30 | 2026-07-01 | KPTG-TRANSMIT-000384 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-29 | NXT-TRANSMIT-000372-ACO | NA | Client | Facade Scope | 0 | 2 | 0 | NA | APPROVED | 2026-06-29 | NA | 288 | 2026-07-06 |  |  | 2026-06-30 | 2026-07-01 | KPTG-TRANSMIT-000380 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-12 | RDSBIM-TRANSMIT-000047 | NA | Trade Partner | LEVEL 03 RCP KEY PLAN AND LAYOUT | 5 | 0 | 0 | NA | APPROVED | 2026-01-12 | NA | 814 | 2026-01-14 |  |  | 2026-01-21 | 2026-01-21 | KPTG-TRANSMIT-002547 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-29 | NXT-TRANSMIT-000372-HEZ | NA | Client | Facade Scope | 0 | 2 | 0 | NA | APPROVED | 2026-06-29 | NA | 290 | 2026-07-06 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-000479 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-29 | NXT-TRANSMIT-000372-ESD | NA | Client | Facade Scope | 0 | 1 | 0 | NA | APPROVED | 2026-06-29 | NA | 292 | 2026-07-06 |  |  | 2026-06-30 | 2026-07-01 | KPTG-TRANSMIT-000376 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-29 | RDSBIM-TRANSMIT-000011 | NA | Trade Partner | GROUND LEVEL BLOCK 1 ¦ CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | KPTG-IntCorr-000248 | APPROVED | 2026-07-13 | NA | 376 | 2026-07-21 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-000754 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-29 | ACCCA-TRANSMIT-000007 | NA | Trade Partner | STORM WATER PIT APPROVAL | 15 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 295 | 2026-07-06 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-000412 | Closed | 15 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-29 | EFP-TRANSMIT-000030 | NA | Trade Partner | EFP Hydraulic Sprinkler Calculations | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | ISSUED FOR INFORMATION. UPDATED TO DOCUMENT REGISTER ONLY |  | 2026-06-29 | KPTG-IntCorr-000636 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-29 | D&E-TRANSMIT-000015 | NA | Trade Partner | ISSUED FOR APPROVAL - BUILDERS WORK LAYOUTS | 6 | 0 | 0 | KPTG-IntCorr-000249 | APPROVED | 2026-07-17 | NA | 450 | 2026-07-27 |  | Void-Requested by Sacheen |  | 2026-08-03 | NA | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-29 | PTA-TRANSMIT-000014 | NA | Consultant | STAGE 6 - Architectural Drawings Package in CAD | 183 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | CAD file distribution |  | 2026-06-29 | KPTG-TRANSMIT-000341 | Closed | 183 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-29 | Appselec-TRANSMIT-000131 | NA | Trade Partner | Appselec Tech Data For Approval | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Rejected: wrong document numbering:KPTG-IntCorr-000637 |  | 2026-06-29 | KPTG-IntCorr-000637 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-29 | CRSol-TRANSMIT-000091 | NA | Trade Partner | M3S2 - DHB5 - SMW - As-Built Drawings - Rev-ABS-01 | 8 | 0 | 0 | NA | REJECTED | [5 empty] | As Built submission without submitting IFA and IFC |  | 2026-06-29 | KPTG-SADV-006244 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-29 | INDS-TRANSMIT-000042 | NA | Trade Partner | Updated Fire Peno Drawings | 4 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | IFC - Rejected due to Drawing status is not clearly mentioned inside the shop drawing sheet. DRAFT-008957 |  | 2026-06-29 | DRAFT-008957 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-12 | SKS Tech-TRANSMIT-000123 | NA | Trade Partner | White Rhino Load Bank Connection Panel | 0 | 1 | 0 | NA | REJECTED | [5 empty] | QA Rejected Ref: KPTG-IntCorr-000841 |  | 2026-01-12 | KPTG-IntCorr-000841 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-29 | Auspan-TRANSMIT-000432 | NA | Trade Partner | Precast shop drawings for construction. Level 1 zone 4, 5 | 4 | 0 | 0 | KPTG-IntCorr-000801 | APPROVED | [5 empty] | IFC - Waiting for Kim advise- KPTG-IntCorr-000801 IFC Update regiser and transmit - KPTG-TRANSMIT-002594 |  | 2026-07-06 | KPTG-TRANSMIT-002594 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-29 | RDSBIM-TRANSMIT-000012 | NA | Trade Partner | LEVEL 01 BLOCK 1 ¦ CONCRETE PROFILE PLAN AND SECTIONS | 2 | 0 | 0 | KPTG-IntCorr-000247 | APPROVED | 2026-07-13 | NA | 374 | 2026-07-21 |  | Voided Drawings revised |  | 2026-07-14 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-29 | Baigents-TRANSMIT-000008 | NA | Trade Partner | Block 01 - Precast Columns PC2 - PC45 IFA | 44 | 0 | 0 | KPTG-IntCorr-000246 | APPROVED | 2026-07-01 | NA | 303 | 2026-07-08 |  | Actual submission date-29-06-2026 | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-000530 | Closed | 44 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-29 | ADP-TRANSMIT-000090 | NA | Consultant | ADP MEL4680 - Hydraulic Drawings & Specification - Issue for Construction | 11 | 1 | 0 | NA | APPROVED | 2026-06-29 | NA | 298 | 2026-07-02 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-001036 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-29 | ADP-TRANSMIT-000091 | NA | Consultant | ADP MEL4680 - Electrical Services - Lighting Schedule | 1 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 300 | 2026-07-02 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-000965 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | Nilsen3-TRANSMIT-000145 | NA | Trade Partner | Cable Cleats | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF-006051 | NA | 2026-05-28 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-019118 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-29 | SMEPS-TRANSMIT-000329 | NA | Trade Partner | SME - IFC Documentation | 41 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 3709 | 2026-06-29 |  | TOTAL 44 DOCUMENTS IN THIS TRANSIMITTAL 41 DOCUMENT -ELC AND 3 TEL |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-29 | SMEPS-TRANSMIT-000329 | NA | Trade Partner | SME - IFC Documentation | 3 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 3708 | 2026-07-10 |  | TOTAL 44 DOCUMENTS IN THIS TRANSIMITTAL 41 DOCUMENT -ELC AND 3 TEL |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-29 | Tradetec-TRANSMIT-000471 | NA | Trade Partner | IFA - Stage 4 | 1 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 3712 | 2026-07-10 |  | As requested by Charlie - Terminated - (for submitting new revision.) |  | 2026-07-07 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-29 | ZLH P/L-TRANSMIT-000009 |  | Trade Partner | Cortek Light Gauge Steel 3D Model & Shop Drawings - ZLH | 5 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with drawing number, revision, title, revision date, history, title block. |  | 2026-06-29 | DRAFT-003098 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-12 | Hames-TRANSMIT-000093 | NA | Consultant | PHASE 1 - RCP AND ROOM LAYOUTS | 5 | 0 | 0 | NA | APPROVED | 2026-01-12 | NA | 811 | 2026-01-14 |  |  | 2026-01-15 | 2026-01-15 | KPTG-TRANSMIT-002408 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-29 | GunAus-TRANSMIT-000001 | NA | Trade Partner | SpeedStile FP Glide - Speed Gate Datasheet | 0 | 1 | 0 | NA | APPROVED | 2026-06-29 | WF-000258 | NA | 2026-07-10 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-001196 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-29 | Entire M-TRANSMIT-000038 | NA | Trade Partner | Fan & Roof Cowls - Issued For Construction Incl. Fan Static Calculations | 0 | 1 | 0 | NA | REJECTED | [5 empty] | No need to FC revision unless request by Kapitol or Client, Resubmission FOA only. |  | 2026-06-29 | KPTG-SADV-000765 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-29 | RDSBIM-TRANSMIT-000078 | NA | Trade Partner | 671 CHP ¦ CPP ¦ GROUND ¦ IFC ¦ SUBMISSION | 6 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 600 | 2026-07-01 |  | Review Void as RDS to update the drawings. |  | 2026-07-06 | NA | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-29 | INDS-TRANSMIT-000043 | NA | Trade Partner | Ground Zone 1 Floor Penetration Layout | 1 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 1370 | 2026-07-06 |  | Rejected by reviewer | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-002640 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-29 | ZIA-TRANSMIT-000111 | NA | Trade Partner | Re: M3 Stage 4 - Functional Design Specification | 0 | 1 | 0 | NA | REJECTED | [5 empty] | MISSING OF REVISION NUMBER |  | 2026-06-29 | KPTG-TRANSMIT-019134 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-29 | ZIA-TRANSMIT-000063 | NA | Trade Partner | CSMS - Cable Schedule | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | FC doc send to all parties |  | 2026-06-29 | KPTG-TRANSMIT-003998 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-29 | ARCST-GCOR-000034 | NA | Trade Partner | Material Tech Data Sheets | 0 | 3 | 0 | NA | APPROVED | 2026-06-29 | WF-001077 | NA | 2026-07-01 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-005870 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-29 | ZIA-TRANSMIT-000012 | NA | Trade Partner | M2 S9,10,11 CSMS FDS Submission (FOA-2) | 0 | 1 | 0 | NA | APPROVED | 2026-06-28 | WF-001078 | NA | 2026-07-08 |  | Workflow terminated as advised by James upon request from Orise (ZIA-GCOR-000005) |  | 2026-07-07 | ZIA-GCOR-000005 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-29 | Arc Plas-TRANSMIT-000014 | NA | Trade Partner | Revised Cortek Frame Sample | 0 | 1 | 0 | NA | APPROVED | 2026-06-29 | WF-001079 | NA | 2026-07-07 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-005162 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-29 | ELLISAIR-TRANSMIT-000086 | NA | Trade Partner | Revised Level 2 Zone 1 Ductwork Layout drawing issued for Approval. | 1 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 1234 | 2026-07-03 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-005413 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-12 | VAE-Grp-TRANSMIT-000101 | NA | Trade Partner | Mechanical Services - HVAC LAYOUT & BUILDERS WORKS - L4 & L5 DAY 1 | 8 | 0 | 0 | NA | APPROVED | 2026-01-12 | NA | 813 | 2026-01-14 |  |  | 2026-01-15 | 2026-01-15 | KPTG-TRANSMIT-002471 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-29 | DLTS-TRANSMIT-000039 | NA | Trade Partner | S11-Eave Gutter Frames-IFA Issue | 48 | 0 | 0 | NA | APPROVED | 2026-06-29 | WF-001082 | NA | 2026-07-08 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-005322 | Closed | 48 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-29 | DLTS-TRANSMIT-000040 | NA | Trade Partner | S11-Glazing Frame Support-IFA Issue | 31 | 0 | 0 | NA | APPROVED | 2026-06-29 | WF-001083 | NA | 2026-07-08 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-005305 | Closed | 31 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-29 | KPTG-TRANSMIT-002617 | NA | Trade Partner | Heritage Glass East/West | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  |  | 2026-06-29 | 2026-06-29 | KPTG-IntCorr-001112 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-29 | KPTG-IntCorr-001113 | NA | Trade Partner | HERITAGE GLASS | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  |  | 2026-06-29 | 2026-06-29 | KPTG-IntCorr-001114 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-25 | DLTS-TRANSMIT-000035 | NA | Trade Partner | S10-Cooling Tower HD Bolts-IFA Issue | 3 | 0 | 0 | NA | APPROVED | 2026-06-26 | WF-001053 | NA |  |  | Workflow terminated as the drawings were updated and resubmitted via DLTS-TRANSMIT-000043 |  | 2026-06-29 | KPTG-IntCorr-001406 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-29 | KPTG-IntCorr-001115 | NA | Trade Partner | Re: HERITAGE GLASS | 0 | 1 | 0 | NA | APPROVED | 2026-06-29 | WF-000809 | NA | 2026-07-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-26 | DLTS-TRANSMIT-000036 | NA | Trade Partner | S11-Cooling Tower HD Bolts-IFA issue | 3 | 0 | 0 | NA | APPROVED | 2026-06-26 | WF-001054 | NA |  |  | Workflow has been terminated as the drawings were resubmitted by Delta via DLTS-TRANSMIT-000044 |  | 2026-06-29 | KPTG-IntCorr-001407 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-29 | KPTG-TRANSMIT-002622 | NA | Trade Partner | Re: Deletion of Secondary Steel for Level 10 Balustrade | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001121 - as per direction from Ashlin, we only update register and transmit to all parties. | 2026-06-29 | 2026-06-29 | KPTG-IntCorr-001121 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-29 | DLTS-TRANSMIT-000043 | NA | Trade Partner | S10-HD Bolts-IFA Issue | 3 | 0 | 0 | NA | APPROVED | 2026-06-29 | WF-001084 | NA | 2026-07-08 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-005309 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-29 | DLTS-TRANSMIT-000044 | NA | Trade Partner | S11-HD Bolts-IFA Issue | 3 | 0 | 0 | NA | APPROVED | 2026-06-29 | WF-001085 | NA | 2026-07-08 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-005142 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-25 | RDSBIM-TRANSMIT-000133 | NA | Trade Partner | LEVEL 02 RCP KEY PLAN & LAYOU | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties |  |  |  | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-29 | SMEPS-TRANSMIT-000058 | NA | Trade Partner | STAGE 11-GROUND, LV1, LV2 & LV3 LIGHTING LAYOUT | 4 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Need to revise the drawings KPTG-SADV-005524 |  | 2026-06-29 | KPTG-SADV-005524 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-29 | Eneraque-TRANSMIT-000036 | NA | Trade Partner | ENE - Crane Lift Plan & Calculations (BST Installation) and Tank Hold-Down Anchor Calculations | 0 | 2 | 0 | NA | APPROVED | 2026-06-29 | WF-001088 | NA | 2026-07-09 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-05 | ZIA-TRANSMIT-000004 | NA | Trade Partner | M2S9,10,11 CSMS Sample Data Submission (FOA-1) | 0 | 19 | 0 | NA | APPROVED | 2026-06-05 | WF-000879 | NA | 2026-06-17 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-004932 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-30 | WGAVIC-TRANSMIT-000159 | NA | Consultant | M2 - Blockwall Details and Retaining Walls - Issued for Certification | 4 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 1240 | 2026-07-07 |  |  | 2026-07-16 | 2026-07-16 | KPTG-DA-003750 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-30 | Carr-TRANSMIT-000070 | NA | Consultant | Architectural Docs IFA | 51 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing Status incorrect |  | 2026-06-30 | KPTG-DA-000406 | Closed | 51 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-30 | Carr-TRANSMIT-000071 | NA | Consultant | Architectural Issue for Coordination | 27 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings incorrectly registered in Aconex |  | 2026-06-30 | KPTG-DA-000404 | Closed | 27 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-30 | KPTG-TRANSMIT-001055 | NA | Trade Partner | FAT Reports - Issued for Approval | 0 | 105 | 0 | NA | APPROVED | 2026-06-30 | WF - 000513 | NA | 2026-07-06 |  | NA | 2026-07-06 | 2026-07-06 | KPTG-WTRAN-000938 | Closed | 105 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-29 | INGEN3D-TRANSMIT-000144 | NA | Trade Partner | Level 9-11 - Precast Walls - IFA (26-06-2026) | 1 | 0 | 0 | NA | APPROVED | 2026-06-29 | WF-000832 | NA | 2026-07-07 |  | submitted along with 140 TRN | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-003102 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-29 | L.E.S.-TRANSMIT-000009 | NA | Trade Partner | Floor box tech data & Substation DB shop drawing | 0 | 4 | 0 | NA | APPROVED | 2026-06-29 | WF-000830 | NA | 2026-07-07 |  | 1 document not reviewed by WAM | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-003437 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-25 | RDSBIM-TRANSMIT-000134 | NA | Trade Partner | LEVEL 00 PARTITION WALL PLAN | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties |  |  |  | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-29 | Jangho-TRANSMIT-000206 | NA | Trade Partner | Updated 671 PMU drawing and test proposals for District Dockland for review | 0 | 2 | 0 | NA | APPROVED | 2026-06-29 | WF-000837 | NA | 2026-07-13 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-30 | KPTG-TRANSMIT-014924 | NA | Trade Partner | SP3 Ardon O&M Manual | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | WF-006200 | NA | 2026-07-03 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-019180 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-30 | Jangho-TRANSMIT-000208 | NA | Trade Partner | Siliding Door Sample Submission（Handle MLS02） | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | WF-000850 | NA | 2026-07-17 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-002914 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-30 | Jangho-TRANSMIT-000209 | NA | Trade Partner | Glass Sample Submission (GL-03 Option 3) | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | WF-000842 | NA | 2026-07-17 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-003169 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-30 | Jangho-TRANSMIT-000210 | NA | Trade Partner | Glass Sample Submission (GL-10 Option 3) | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | WF-000843 | NA | 2026-07-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-30 | Jangho-TRANSMIT-000211 | NA | Trade Partner | Gasket Sample Submission (Gasket Opition 1) | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | WF-000844 | NA | 2026-07-17 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002919 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-30 | INGEN3D-TRANSMIT-000151 | NA | Trade Partner | 3D-389 District Living - Level 19-21 - Precast Columns - IFA (29-06-2026) | 8 | 0 | 0 | NA | APPROVED | 2026-06-30 | WF-000852 | NA | 2026-07-16 |  |  | 2026-07-01 | 2026-07-01 | NA- Work flow Terminated as instructed | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-30 | Jangho-TRANSMIT-000212 | NA | Trade Partner | Gasket Sample Submission (Gasket Opition 2) | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | WF-000846 | NA | 2026-07-17 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002917 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-30 | Jangho-TRANSMIT-000213 | NA | Trade Partner | Gasket Sample Submission (Gasket Opition 3) | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | WF-000847 | NA | 2026-07-17 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-002599 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-30 | Jangho-TRANSMIT-000214 | NA | Trade Partner | Weather Sealant Sample Submission (Weather Sealant Color Card) | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | WF-000848 | NA | 2026-07-17 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-002969 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-25 | RDSBIM-TRANSMIT-000135 | N/A | Trade Partner | LEVEL 10 PARTITION WALL KEY PLAN AND LAYOUT | 6 | 0 | 0 | NA | APPROVED | 2026-01-12 | WF-000856 | 519 | 2026-01-16 |  |  | 2026-01-27 | 2026-01-27 | KPTG-TRANSMIT-002633 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-30 | KPTG-TRANSMIT-015466 | NA | Trade Partner | Structural Steel O&M Manual - Review | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | Structural Steel O&M Manual - Review | NA | 2026-07-06 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-019677 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-30 | Jangho-TRANSMIT-000215 | NA | Trade Partner | Mini VMU Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | WF-000849 | NA | 2026-07-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-30 | SPECAUTO-TRANSMIT-000003 | NA | Trade Partner | CSMS Outstation Panel General Arrangement and Schematic Shop Drawings | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | WF-000259 | NA | 2026-07-13 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-001172 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-30 | EAEGROUP-TRANSMIT-000103 | NA | Trade Partner | Updated Shop Drawing Revision - Block C3 HF | 1 | 0 | 0 | NA | APPROVED | 2026-06-30 | WF-006202 | NA | 2026-07-13 |  | As per NDC- No action required |  | 2026-06-30 | NXT-PA-005591 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-30 | Nilsen3-TRANSMIT-00020 | NA | Trade Partner | M3 Stage-4 ROP 4A and 4B I/O List (HVSB-V board) | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | WF-006203 | NA | 2026-07-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-30 | Airpor2-TRANSMIT-000003 | NA | Trade Partner | Shop drawing and roller shutter tech data | 1 | 4 | 0 | NA | REJECTED | [5 empty] | Issue with title, no coversheet, mixed submission. revision difference. |  | 2026-06-30 | KPTG-SADV-000772 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-30 | D&E-TRANSMIT-000276 | SPARK-CRFI-KPG-000473 | Trade Partner | MWYCCB - LEVEL 1 - PLINTH LAYOUT ZONE 8 & ZONE 9 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 336 | 2026-07-07 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-001419 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-30 | Nilsen3-TRANSMIT-000211 | NA | Trade Partner | Re: M3 Stage-4 ROP 4A and 4B Functional Description (HVSB-V board) | 0 | 1 | 0 |  | APPROVED | 2026-06-30 | WF-006205 | NA | 2026-07-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-30 | ACG-TRANSMIT-000107 | NA | Consultant | M3 - S4 ACG Shop Drawings IFA-7 | 14 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 3714 | 2026-07-08 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-020779 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-30 | RDSBIM-TRANSMIT-000283 | NA | Trade Partner | GROUND FLOOR-C-G-073 UNISEX WC FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | REJECTED | [5 empty] | The review status needs to be corrected |  | 2026-06-30 | KPTG-RFI-008659 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-31 | RDSBIM-TRANSMIT-000136 | NA | Trade Partner | LEVEL 03 RCP KEY PLAN & LAYOUT | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties |  |  |  | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-30 | INGEN3D-TRANSMIT-000152 | NA | Trade Partner | Re: I3D-389 District Living - Level 12-13 - Precast Walls - IFA (29-06-2026) | 12 | 0 | 0 | NA | APPROVED | 2026-06-30 | WF-000853 | NA | 2026-07-16 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-003325 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-30 | RDSBIM-TRANSMIT-000213 | NA | Trade Partner | INDRUM ¦ LEVEL 02 PARTITION WALL LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 681 | 2026-07-03 |  |  | 2026-07-09 | 2026-07-09 | KPTG-SADV-004853 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-30 | DCN-TRANSMIT-000020 | NA | Trade Partner | Structural Design Report -- M2S9 Link Bridge | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC, No review required. Updated register and distributed |  | 2026-06-30 | KPTG-TRANSMIT-004985 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-30 | POTTSENG-TRANSMIT-000054 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONE 5 LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 1372 | 2026-07-07 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002834 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-30 | BIMF-TRANSMIT-000006 | NA | Trade Partner | Level 4 Drainage Plans For Approval | 2 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 872 | 2026-07-07 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-002901 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-30 | KPTG-TRANSMIT-015523 | NA | Trade Partner | Roller Shutter O&M - Review | 0 | 1 | 0 | NA | APPROVED | 2026-06-23 | WF-006207 | NA | 2026-07-03 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-019178 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-30 | SMEPS-TRANSMIT-000060 | NA | Trade Partner | STAGE 9-11 Overall Electrical Inground Site Layout (FC-1) | 1 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 1245 | 2026-07-07 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-005290 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-30 | Appselec-TRANSMIT-000132 | NA | Trade Partner | Earth Clip Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | WF-000362 | NA | 2026-07-06 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-001006 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-30 | Appselec-TRANSMIT-000133 | NA | Trade Partner | Earth Clip No Longer In Use | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | No longer in use. Just updated our Document Register.KPTG-IntCorr-000642 |  | 2026-06-30 | KPTG-IntCorr-000642 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-30 | ZLH P/L-TRANSMIT-000007 | NA | Trade Partner | Proposed Material - Design & Sample - ZLH | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | WF-000260 | NA | 2026-07-13 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001397 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-02 | Facx-TRANSMIT-000005 | NA | Trade Partner | Green Screen Rev-1 | 7 | 0 | 0 | NA | APPROVED |  | NA | 3395 | 2025-12-11 |  |  |  | 2026-02-16 | KPTG-TRANSMIT-012951 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-31 | RDSBIM-TRANSMIT-000137 | NA | Trade Partner | LEVEL 03 RCP KEY PLAN & LAYOUT | 10 | 0 | 0 | NA | APPROVED |  | NA |  |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties |  |  |  | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-30 | Appselec-TRANSMIT-000131 | NA | Trade Partner | Appselec Tech Data For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | WF-000363 | NA | 2026-07-06 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-001004 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-30 | ELLISAIR-TRANSMIT-000095 | NA | Trade Partner | Revised Level 2 Duct & Pipe layout drawing issued for Approval. | 1 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 1247 | 2026-07-07 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-005417 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-30 | Auspan-TRANSMIT-000441 | NA | Trade Partner | Precast shop drawings for construction. Level 6. | 34 | 0 | 34 | KPTG-IntCorr-000804 | APPROVED | [5 empty] | IFC - Waiting for Kim advise - KPTG-IntCorr-000804 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-30 | Auspan-TRANSMIT-000441 | NA | Trade Partner | Precast shop drawings for construction. Level 6. | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to same revision as latest- DRAFT-009089 |  | 2026-06-30 | DRAFT-009089 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-30 | ARCST-TRANSMIT-000316 | NA | Trade Partner | C2 Cooling Tower Roof Framing - Issued for Construction | 135 | 0 | 0 | NA | REJECTED | [5 empty] | IFC received prior to IFA; title mismatch |  | 2026-06-30 | KPTG-RFI-008665 | Closed | 135 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-30 | Auspan-TRANSMIT-000443 | NA | Trade Partner | Resend shop drawings for construction. Level 1 | 9 | 0 | 0 | KPTG-IntCorr-000805 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise- KPTG-IntCorr-000805 IFC- Update register and transmit - KPTG-TRANSMIT-002526 |  | 2026-06-30 | KPTG-TRANSMIT-002526 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-30 | DS-TRANSMIT-000123 | NA | Trade Partner | HYD As built Drawings | 8 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 4338 | 2026-07-03 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-019197 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-30 | INGEN3D-TRANSMIT-000153 | NA | Trade Partner | I3D-389 District Living - Level 15-17 - Precast Columns - IFC (30-06-2026) | 41 | 0 | 0 | NA | APPROVED | 2026-06-30 | WF-000854 | NA | 2026-07-16 |  |  | 2026-07-09 | 2026-07-10 | WF-000935 | Closed | 41 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-30 | Auspan-TRANSMIT-000442 | NA | Trade Partner | Re: Update cast in plate layout for zone 4, 5. | 3 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to difference in document titles - DRAFT-009097 |  | 2026-06-30 | DRAFT-009097 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-30 | ARCST-TRANSMIT-000315 | NA | Trade Partner | C1 Cooling Tower Upper Gantry - Issued for Construction | 169 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | The documents titles mismatch Rejected |  | 2026-06-30 | KPTG-RFI-008666 | Closed | 169 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-31 | RDSBIM-TRANSMIT-000138 | NA | Trade Partner | LEVEL 02 PARTITION WALL PLAN | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties |  |  |  | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-30 | L.E.S.-TRANSMIT-000012 | NA | Trade Partner | Power outlets and Switches | 0 | 5 | 0 | NA | APPROVED | 2026-06-30 | WF-000855 | NA | 2026-07-02 |  |  | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-003070, KPTG-TRANSMIT-003078 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-30 | PCForm-TRANSMIT-000256 | NA | Trade Partner | Fwd: Level 3 & Level 4 - updated drawings | 6 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 901 | 2026-07-14 |  |  | 2026-07-28 | 2026-07-31 | KPTG-TRANSMIT-003199 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-30 | KPTG-IntCorr-003323 | NA | Consultant | Re: Aluminium Skirting | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per Moj's advise issue to all trades KPTG-TRANSMIT-001366 |  | 2026-06-30 | KPTG-TRANSMIT-001366 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-30 | D&E-TRANSMIT-000880 | NA | Trade Partner | NXM3S4 - Roof Level - Chiller Room 7 Layout - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 3270 | 2026-07-12 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020115 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-30 | Civilex-TRANSMIT-000275 | NA | Trade Partner | Stage 2 - sample submission - Sika Antisol E Curing Compound | 0 | 1 | 0 | NA | APPROVED | 2026-07-06 | WF-006268 | NA | 2026-07-10 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-019721 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-30 | WAM-TRANSMIT-000819 | NA | Consultant | A72 - IFC Door Schedule | 9 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 874 | 2026-07-03 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002838 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-30 | Entire M-TRANSMIT-000051 | NA | Trade Partner | Battery Room Schematics Issued for Approval | 4 | 0 | 0 | NA | APPROVED | 2026-06-30 | WF - 000514 | NA | 2026-07-06 |  | NA | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-001056 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-30 | SRA-PMQ-TRANSMIT-000011 | NA | Trade Partner | Tech Data for tiles | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Issue with document number. |  | 2026-06-30 | KPTG-TRANSMIT-000973 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-30 | Carr-TRANSMIT-000072 | NA | Consultant | Architecture Issue for Coordination (Re-transmitted with Corrections) | 27 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 279 | 2026-07-06 |  | Review Voided- Updated drawings received from the consultant |  | 2026-07-22 | NA | Closed | 27 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-30 | Carr-TRANSMIT-000073 | NA | Consultant | Basement Level drawings -Issued for Approval - Drawing Status Correction | 19 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 283 | 2026-07-06 |  | This workflow has been voided due to revisions made to some of the associated drawings from Carr. The remaining drawings will be re-initiated separately under a new workflow. |  | 2026-08-27 | NA | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-09 | RDSBIM-TRANSMIT-000139 | NA | Trade Partner | LEVEL 08 RCP KEY PLAN AND LAYOUT | 10 | 0 | 0 | NA | APPROVED | 2026-01-09 | WF-000853 | 520 | 2026-01-15 |  |  | 2026-01-27 | 2026-01-27 | KPTG-TRANSMIT-002634 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-30 | Carr-TRANSMIT-000073 | NA | Consultant | Ground floor and Upper level drawings -Issued for Approval - Drawing Status Correction | 19 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 284 | 2026-07-06 |  | Review Voided - 3 Nos Updated drawings received from Carr. and re Initiated under Review #333 |  | 2026-08-10 | NA | Closed | 19 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-30 | Carr-TRANSMIT-000073 | NA | Consultant | Interior drawings -Issued for Approval - Drawing Status Correction | 13 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 285 | 2026-07-06 |  | This workflow has been voided due to revisions made to some of the associated drawings from Carr. The remaining drawings will be re-initiated separately under a new workflow. |  | 2026-08-27 | NA | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-30 | Auspan-TRANSMIT-000444 | NA | Trade Partner | Re: RFI: Post fix panel - 1P5058 | 2 | 0 | 0 | KPTG-IntCorr-000809 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise- KPTG-IntCorr-000809 1 Accepted; Register and transmitted - KPTG-TRANSMIT-002545 1 Rejected. - KPTG-SADV-003204 |  | 2026-07-01 | KPTG-TRANSMIT-002545 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-30 | Leemark-TRANSMIT-000046 | NA | Trade Partner | MCC - Fire Proection Layout - FDCIE-01 & SHCIE-01- IFA | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status is missing inside the drawing |  | 2026-06-30 | KPTG-TRANSMIT-001367 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-30 | Auspan-TRANSMIT-000444 | NA | Trade Partner | Re: RFI: Post fix panel - 1P5058 | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to difference in title -DRAFT-009105 |  | 2026-06-30 | DRAFT-009105 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-30 | ADP-TRANSMIT-000093 | NA | Consultant | ADP MEL4680 - Telecommunications Specification [FC-2] | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | NA | 302 | 2026-07-03 |  | specification | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-001032 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-30 | ADP-TRANSMIT-000358 | NA | Consultant | Fwd: ADP MEL4780 - CFD Report Switchroom FG [03] | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-06-30 | KPTG-TRANSMIT-019167 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-30 | KALLIBRE-TRANSMIT-000004 | NA | Trade Partner | IFA - Toilet Partition Shop Drawings | 6 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Transmittal rejected due to Wong Document no. |  | 2026-06-30 | KPTG-IntCorr-001923 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-30 | ADP-TRANSMIT-000094 | NA | Consultant | ADP MEL4680 - CSMS Spec and schedules | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Issue with document number inside the document. |  | 2026-06-30 | KPTG-TRANSMIT-000979 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-30 | INGEN3D-TRANSMIT-000155 | NA | Trade Partner | I3D-389 District Living - Level 13-15 - Precast Columns - IFC (30-06-2026) | 64 | 0 | 0 | NA | REJECTED | [5 empty] | Title difference |  | 2026-06-30 | PTG-TRANSMIT-002592 | Closed | 64 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-09 | RDSBIM-TRANSMIT-000140 | NA | Trade Partner | LEVEL 11 TOWER A PARTITION LAYOUT (L11 to L13 TYPICAL) | 2 | 0 | 0 | NA | APPROVED | 2026-01-09 | WF-000854 | 521 | 2026-01-21 |  |  | 2026-01-27 | 2026-01-27 | KPTG-TRANSMIT-002636 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-30 | ZIA-TRANSMIT-000112 | NA | Trade Partner | M3 Stage 4 - Device Register | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect document number, title |  | 2026-06-30 | KPTG-RFI-008670 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-30 | ASV-TRANSMIT-000185 | NA | Trade Partner | Hydraulic Sample Submission - External Trench Grates | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | WF-006216 | NA | 2026-07-10 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-019784 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-30 | PARR-TRANSMIT-000199 | NA | Trade Partner | P2649 - KPG NDC M3 - Stage 2 - Fuel - DFS FUNCTIONAL DESCRIPTION | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | As Built, for distribution only. |  | 2026-06-30 | KPTG-TRANSMIT-019171 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-30 | M.2-TRANSMIT-000058 | NA | Trade Partner | Electrical Services FTTP layouts | 25 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 1374 | 2026-07-07 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-002575 | Closed | 25 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-30 | ZLH P/L-TRANSMIT-000010 | NA | Trade Partner | Re: NXGE01 - Proposed Siniat Partition Wall Types in Lieu of CSR / Gyprock Systems | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Supersede by ZLH P/L-TRANSMIT-000011. |  | 2026-06-30 | KPTG-TRANSMIT-000984 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-30 | M.2-TRANSMIT-000059 | NA | Trade Partner | Electrical Services Basement. L00 & L01 Power and Comms layouts | 15 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 1376 | 2026-07-07 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-002641 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-30 | ZLH P/L-TRANSMIT-000011 | NA | Trade Partner | Re: NXGE01 - Proposed Siniat Partition Wall Types in Lieu of CSR / Gyprock Systems | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | WF-000262 | NA | 2026-07-13 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001384 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-30 | ZLH P/L-TRANSMIT-000012 | NA | Trade Partner | ICCONS TIDS Metal Anchor for IN03 Insulation Board at Internal Soffit - ZLH | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | WF-000263 | NA | 2026-07-13 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-001447 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-30 | JCBa-TRANSMIT-000265 | NA | Consultant | Building Permit RFI's | 26 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 585 | 2026-07-03 |  | NA | 2026-07-02 | 2026-07-02 | KPTG-DA-002954 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-30 | Entire M-TRANSMIT-000041 | NA | Trade Partner | Mechanical Schematics - FOA | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Issues with document number, title, revision date. |  | 2026-06-30 | KPTG-SADV-000781 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-12 | KPTG-TRANSMIT-002558 | NA | Trade Partner | DDA back rest assist - updated spec | 0 | 1 | 0 | NA | APPROVED | 2026-01-12 | WF-000858 | NA | 2026-01-16 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-30 | ADP-TRANSMIT-000095 | NA | Trade Partner | ADP MEL4680 - Fire Protection Specification | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with Document number and revision inside the document. |  | 2026-06-30 | KPTG-DA-000943 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-30 | HDRAus-TRANSMIT-000519 | NA | Consultant | M3 Stage 4 - Document upload - PDF (Locked Drawings) - HDRAus-IntCorr-000581 | 4 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 3722 | 2026-07-04 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-019232 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-30 | EAEGROUP-TRANSMIT-000105 | NA | Trade Partner | O&M Documents for Stage 2 EAE IP68 CCR and IP55 KX Busduct | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Issue with document number, revision number. |  | 2026-06-30 | KPTG-SADV-006282 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-30 | Endfire-TRANSMIT-000080 | NA | Trade Partner | EndFire IFC Drawings2 | 2 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 1296 | 2026-07-02 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-004072 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-30 | Ardon-TRANSMIT-000057 | NA | Trade Partner | Priority 11 Door Frame Shop Drawings | 50 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 3725 | 2026-07-12 |  |  | 2026-07-10 | 2026-07-10 | ⁠KPTG-TRANSMIT-019557 | Closed | 50 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-30 | ZLH P/L-TRANSMIT-000013 | NA | Trade Partner | Cortek Light Gauge Steel 3D Model & Shop Drawings - ZLH | 52 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with document number, revision, title block, title, revision date, history inside the drawings. |  | 2026-06-30 | KPTG-SADV-000780 | Closed | 53 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-30 | Endfire-TRANSMIT-000080 | NA | Trade Partner | Endfire-TRANSMIT-000080-FIP | 1 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 1298 | 2026-07-02 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-004068 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-30 | WGAVIC-TRANSMIT-000008 | NA | Consultant | Civil Stormwater Drawings and Certificate - Reissued for Construction | 9 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 297 | 2026-07-06 |  |  | 2026-07-02 | 2026-07-03 | KPTG-TRANSMIT-000439 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-30 | WGAVIC-TRANSMIT-000008-SME | NA | Consultant | Civil Stormwater Drawings and Certificate - Reissued for Construction | 9 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 298 | 2026-07-07 |  |  | 2026-07-21 | 2026-07-22 | KPTG-TRANSMIT-000653 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-30 | WGAVIC-TRANSMIT-000008-NDC | NA | Consultant | Civil Stormwater Drawings and Certificate - Reissued for Construction | 10 | 0 | 0 | NA | APPROVED | 2026-06-29 | NA | 301 | 2026-07-15 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-12 | KPTG-TRANSMIT-002559 | NA | Trade Partner | Bette 1500mm drop in bathtub with waste - rev 2 | 0 | 1 | 0 | NA | APPROVED | 2026-01-12 | WF-000859 | NA | 2026-01-16 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-30 | Baigents-TRANSMIT-000009 | NA | Trade Partner | Remaining Grid 2 Level 01 Precast beams IFA | 11 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong revision |  | 2026-06-30 | Awaiting approval | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-30 | Civilex-TRANSMIT-000013 | NA | Trade Partner | Sample Submission - Concrete mix design (Piling) | 0 | 1 | 0 | NA | APPROVED | 2026-06-29 | NA | 300 | 2026-07-06 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-000408 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-30 | ACCCA-TRANSMIT-000008 | NA | Trade Partner | Electrical Pit Approval | 14 | 0 | 0 | NA | REJECTED | [5 empty] | 6 drawings rejected without mention the drawing number in sheet- 8 drawings submitted |  | 2026-06-30 | Awaiting approval | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-30 | ARCST-TRANSMIT-000319 | NA | Trade Partner | C2 Cooling Tower Upper Gantry - Issued for Construction | 125 | 0 | 0 | NA | REJECTED | [5 empty] | The documents titles mismatch Rejected |  | 2026-06-30 | KPTG-TRANSMIT-019201 | Closed | 125 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-30 | ZIA-TRANSMIT-000111 | NA | Trade Partner | Re: M3 Stage 4 - Functional Design Specification | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | WF-006208 | NA | 2026-07-09 |  |  |  | 2026-07-29 | KPTG-TRANSMIT-020206 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-30 | SKS Tech-TRANSMIT-000189 | NA | Trade Partner | Comms containment earthing layout | 4 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 3716 | 2026-07-16 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-020877 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-30 | PFP PL-TRANSMIT-000095 | NA | Trade Partner | Additional Wall & Floor Wet Fire Penetrations | 2 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 3718 | 2026-07-10 |  | As instructed by Ellie Salmon - Terminated (Need to be put onto structural drawings for Innovis to review.) |  | 2026-07-09 | NA | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-30 | PARR-TRANSMIT-000201 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - HUMIDITY & TEMPERATURE TRANSMITTERS | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | WF-006215 | NA | 2026-07-11 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-019790 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-30 | PARR-TRANSMIT-000202 | NA | Trade Partner | Re: P2685 - NDC M3 - Stage 4 - Battery Rooms - CERTIFICATE OF COMPLIENCE-ELECTRICAL WORK | 0 | 1 | 0 | NA | REJECTED | [5 empty] | REJECTED DUE MISSING OF DOCUMENT DETAILS INSDE THE DOCUMENT |  | 2026-06-30 | KPTG-TRANSMIT-019157 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-30 | D&E-TRANSMIT-000879 | NA | Trade Partner | Fwd: NXM3S4 - Level 1 - CHW Pipe Layout - Zone 9 & 10 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC DOCUMENT FOR CONFIRMATION |  | 2026-06-30 | KPTG-TRANSMIT-019186 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-12 | KPTG-TRANSMIT-002565 | NA | Trade Partner | bottle trap BTR-01 - rev 2 | 0 | 1 | 0 | NA | APPROVED | 2026-01-12 | WF-000860 | NA | 2026-01-16 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-30 | RDSBIM-TRANSMIT-000214 | NA | Trade Partner | LINDRUM ¦ GROUND LEVEL - BLOCK WALL ELEVATION PLAN AND ELEVATION | 2 | 0 | 0 | KPTG-IntCorr-001126 | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001126 - Requested guidance, but no response received yet. KPTG-IntCorr-001132 - As per direction from Charlie, we only update document register and issue to DECA. | 2026-07-01 | 2026-07-01 | KPTG-IntCorr-001132 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-30 | NXT-PA-005606 | NA | Trade Partner | Re: P2685 - NDC M3 - Stage 4 - Battery Rooms - CERTIFICATE OF COMPLIENCE-ELECTRICAL WORK | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | ONLY FOR DISTRIBUTION |  | 2026-06-30 | KPTG-TRANSMIT-019188 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-30 | RDSBIM-TRANSMIT-000212 | NA | Trade Partner | LINDRUM ¦ LEVEL 03 PARTITION WALL LAYOUT | 1 | 0 | 0 | KPTG-IntCorr-001127 | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-001127 - As per direction from Mark, we hold this transmittal. KPTG-IntCorr-001137 - As per direction from Mark,we take No action is being taken because those documents are for resubmission. | 2026-07-01 | 2026-07-01 | KPTG-IntCorr-001137 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-30 | KETE-TRANSMIT-000138 | NA | Trade Partner | Kete - Updated Podium Detail to Address KPTG-SADV-004604 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001128 - In KPTG-TRANSMIT-002622, action has already been taken for this document. As per your instruction, we only need to update the register and transmit it to all parties. Please refer to KPTG-IntCorr-001121. | 2026-06-30 | 2026-06-30 | KPTG-IntCorr-001128 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-30 | INGEN3D-TRANSMIT-000154 | NA | Trade Partner | Level 15-17 - Precast Columns - No Longer In Use | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer in Use - KPTG-TRANSMIT-002591 |  | 2026-06-30 | KPTG-TRANSMIT-002591 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-30 | INGEN3D-TRANSMIT-000156 | NA | Trade Partner | Level 13-15 - Precast Columns - No Longer In Use | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer in Use - KPTG-TRANSMIT-002593 |  | 2026-06-30 | KPTG-TRANSMIT-002593 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-30 | SES AU-TRANSMIT-000002 | NA | Trade Partner | Security - Ground S9 & External Security | 3 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 1241 | 2026-07-07 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-006295 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-30 | M.S.-TRANSMIT-000075 | NA | Trade Partner | IFC Shop drawing for J91 Bin Cupboard & J92 Fire Hydrant Cupboard | 3 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 351 | 2026-07-03 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-003071 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-30 | M.S.-TRANSMIT-000076 | NA | Trade Partner | Updated J92 - Fire Hydrant Cupboard Shop drawing | 1 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 351 | 2026-07-03 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-003071 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-30 | M.S.-TRANSMIT-000077 | NA | Trade Partner | Updated IFA shop drawing for J93 Circulation Joinery | 2 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 356 | 2026-07-08 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-003075 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-22 | Resonate-TRANSMIT-000005 | N/A | Consultant | 80%DD Acoustic Report | 1 | 0 | 0 | KPTG-IntCorr-000189 | APPROVED | 2026-01-13 | WF-000093 | NA | 2026-01-19 |  |  | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-000627 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-30 | P & R-TRANSMIT-000092 | NA | Trade Partner | IFA - CARPARK NORTH DUCT LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 355 | 2026-07-09 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-30 | Schindle-TRANSMIT-000013 | NA | Trade Partner | MLC - Schindler Lift 2 Drawings for Approval | 6 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 421 | 2026-07-09 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-003130 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-30 | Schindle-TRANSMIT-000014 | NA | Trade Partner | Schindler updated Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 354 | 2026-07-09 |  |  | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-003133 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-30 | DCN-TRANSMIT-000021 | NA | Trade Partner | M2 - BRIDGE LINK ARCHITECTURALS - CONSTRUCTION ISSUE FC[3] | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, updated register and distributed |  | 2026-06-30 | KPTG-TRANSMIT-005047 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-30 | Auspan-TRANSMIT-000439 | NA | Trade Partner | Precast shop drawings for construction. Level 3 | 2 | 0 | 0 | KPTG-IntCorr-000802 | REJECTED |  | NA | NA |  |  | IFC - Waiting for advise- KPTG-IntCorr-000802 Rejected by Kapitol Project Coordinator -DRAFT-009421 |  | 2026-07-06 | DRAFT-009421 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-30 | Auspan-TRANSMIT-000440 | NA | Trade Partner | : Precast shop drawings for construction. Level 4 | 1 | 0 | 0 | KPTG-IntCorr-000803 | REJECTED |  | NA | NA |  |  | IFC - Waiting for adviseKPTG-IntCorr-000803 KPTG-IntCorr-001125 - Rejected by PC |  | 2026-07-28 | KPTG-IntCorr-001125 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-30 | M.2-TRANSMIT-000057 | NA | Trade Partner | Electrical Services Typical apartment layouts | 50 | 0 | 0 | KPTG-IntCorr-000806 | REJECTED |  | NA | NA |  |  | IFC - IFA is not approved; waiting for approval. - KPTG-IntCorr-000806 Rejected due to IFA is not approved- DRAFT-009185 |  | 2026-07-01 | DRAFT-009185 | Closed | 50 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-25 | crossfir-TRANSMIT-000021 | NA | Trade Partner | Wet Fire - Penetrations Level 04 to 10, IFC | 1 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 602 | 2026-07-07 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001263 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-30 | ELLISAIR-TRANSMIT-000094 | NA | Trade Partner | Level 2 CCW Typical Pumping Module String - Pipework General Arrangement Layout drawing issued for Construction. | 1 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 1249 | 2026-07-07 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-005513 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-30 | VIA Arch-TRANSMIT-000172 | NA | Consultant | Updated concrete plan, security office joinery and ceiling details | 4 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 1251 | 2026-07-07 |  |  | 2026-07-16 | 2026-07-16 | KPTG-DA-003751 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-22 | WAM-TRANSMIT-000074 | N/A | Consultant | Concrete Setout Plans - 95%DD update | 49 | 0 | 0 | NA | APPROVED | 2026-01-06 | NA | 184 | 2026-01-09 |  | 40 docs revised via TX76 - 9 in review | 2026-01-14 | 2026-01-14 | KPTG-TRANSMIT-000282 | Closed | 49 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-30 | VIA Arch-TRANSMIT-000173 | NA | Consultant | M2 S9-S11 - BUILDING PERMIT ISSUE | 7 | 0 | 0 | NA | APPROVED | 2026-06-30 | NA | 1253 | 2026-07-07 |  |  | 2026-07-14 | 2026-07-14 | KPTG-DA-003705 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-30 | Arc Plas-TRANSMIT-000016 | NA | Trade Partner | Updated Wall Insulation Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | WF-001094 | NA | 2026-07-07 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-005163 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-30 | ZIA-TRANSMIT-000045 | NA | Trade Partner | COMMISSIONING PLAN | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | WF-001129 | NA | 2026-07-02 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-004157 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-30 | Teams Message - HYDRAULIC Commissioning Manual | NA | Trade Partner | HYDRAULIC Commissioning Manual | 0 | 1 | 0 | NA | APPROVED | 2026-06-30 | WF-001130 | NA | 2026-07-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-30 | Teams Message - SKS ITP | NA | Trade Partner | ELECTRICAL SERVICES - ITP' s | 0 | 14 | 0 | NA | APPROVED | 2026-06-30 | WF-001131 | NA | 2026-07-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-01 | INGEN3D-TRANSMIT-000157 | NA | Trade Partner | I3D-389 District Living - Level 16-17 - Precast Walls - IFA (30-06-2026) | 10 | 0 | 0 | NA | APPROVED | 2026-07-01 | WF-000856 | NA | 2026-07-17 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003254 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-01 | INGEN3D-TRANSMIT-000158 | NA | Trade Partner | I3D-389 District Living - Level 17-18 - Precast Walls & Cast-in Dowel - IFA (30-06-2026) | 11 | 0 | 0 | NA | APPROVED | 2026-07-01 | WF-000857 | NA | 2026-07-17 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-003295 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-01 | RDSBIM-TRANSMIT-000053 | NA | Trade Partner | DISTLV ¦ LEVEL 01 CONCRETE PROFILE PLAN ¦ IFC ¦ SUBMISSION | 4 | 0 | 0 | NA | APPROVED | 2026-07-01 | NA | 878 | 2026-07-04 |  |  | 2026-07-02 | 2026-07-03 | KPTG-TRANSMIT-002672 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-01 | RDSBIM-TRANSMIT-000215 | NA | Trade Partner | LINDRUM ¦ LEVEL 10 UPPER TERRACE CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-07-01 | NA | 682 | 2026-07-04 |  | KPTG-IntCorr-001134 - As per direction from Ashlin, we terminate the workflow. | 2026-07-01 | 2026-07-01 | KPTG-IntCorr-001134 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-01 | INGEN3D-TRANSMIT-000159 | NA | Trade Partner | Re: I3D-389 District Living - Level 13-15 - Precast Columns - IFC (30-06-2026) | 64 | 0 | 0 | NA | APPROVED | 2026-07-01 | WF-000859 | NA | 2026-07-09 |  |  | 2026-07-09 | 2026-07-10 | WF-000943 | Closed | 64 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-23 | WAM-TRANSMIT-000075 | N/A | Consultant | 60%DD Common Area Updates | 6 | 0 | 0 | NA | APPROVED | 2026-01-06 | NA | 183 | 2026-01-09 |  |  | 2026-01-28 | 2026-01-28 | KPTG-TRANSMIT-000330 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-01 | Entire M-TRANSMIT-000042 | NA | Trade Partner | Return Design Brief - Resubmission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision FOA-2 is already there. nee to uprev to FOA-3 |  | 2026-07-01 | KPTG-IntCorr-000264 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-01 | Entire M-TRANSMIT-000043 | NA | Trade Partner | VRF Airconditioning FOA-3 | 0 | 1 | 0 | NA | APPROVED | 2026-07-01 | WF-000265 | NA | 2026-07-14 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-001189 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-01 | Auspan-TRANSMIT-000451 | NA | Trade Partner | Re: Precast shop drawings for approval. Zone 1 | 9 | 0 | 0 | NA | APPROVED | 2026-07-01 | NA | 1382 | 2026-07-08 |  |  | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-002947 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-01 | Auspan-TRANSMIT-000451 | NA | Trade Partner | Re: Precast shop drawings for approval. Zone 1 | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to difference in document number -DRAFT-009131 |  | 2026-07-01 | DRAFT-009131 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-01 | DLTS-TRANSMIT-000003 | NA | Trade Partner | Gutter Bridge-IFA Issue | 12 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect Document Number |  | 2026-07-01 | KPTG-DA-007333 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-15 | VERTIV-TRANSMIT-000036 | NA | Trade Partner | NEXT DC GE 01 _ MATERIAL SUBMISSION _ INTERNAL LIGHT & BATTERY CONTROL PANEL (FOA-1) | 0 | 1 | 0 | NA | APPROVED | 2026-06-15 | WF-000208 | NA | 2026-06-24 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-000988 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-01 | SMEPS-TRANSMIT-000237 | NA | Trade Partner | Re: Final (WF-000489) SHOP DRAWING ¦ CONSULTANT REVIEW ¦ TL ¦ SME ¦ IFA ¦ SMEPS-TRANSMI | 3 | 0 | 0 | NA | APPROVED | 2026-07-01 | WF - 000515 | NA | 2026-07-07 |  | NA | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-001070 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-01 | NXT-TRANSMIT-001650 | NA | Trade Partner | Fwd: O&M Documents for Stage 4 EAE IP68 CCR and IP55 KX Busduct | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | EAEGROUP-TRANSMIT-000106 For distribution |  | 2026-07-01 | KPTG-TRANSMIT-019205 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-01 | Altaire-TRANSMIT-000118 | NA | Trade Partner | DHB5 and DHB6 As-Built Revision Post Cintoo Alignment | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Latest FC revision is rejected. FC revision to be resubmitted and get approved prior to As built submission. |  | 2026-07-01 | KPTG-SADV-006296 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-01 | CRSol-TRANSMIT-000092 | NA | Trade Partner | Re: M3S4 CRS CLN Drawings - Updated Drawings - IFC | 45 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect title and reference number |  | 2026-07-01 | KPTG-DA-007338 | Closed | 45 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-02 | KPTG-IntCorr-000717 | NA | Trade Partner | Internal Roller Doors | 3 | 0 | 0 | NA | APPROVED | 2025-12-02 | WF-000581 | NA | 2025-12-06 |  |  | 2025-12-09 | 2025-12-09 | SCG2014-WTRAN-000007, KPTG-WTRAN-001187 - Sent prepared close out mail to Nick as Email dtd 10/12/2025 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-23 | WAM-TRANSMIT-000076 | N/A | Consultant | Demolition plans and Concrete Setout Plans - 95%DD update | 45 | 0 | 0 | NA | APPROVED | 2026-01-06 | NA | 195 | 2026-01-16 |  |  | 2026-01-28 | 2026-01-28 | KPTG-TRANSMIT-000327 | Closed | 45 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-01 | Tradetec-TRANSMIT-000473 | NA | Trade Partner | IFA - Stage 4 - LVP 50,55 | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per Charlie - No action required |  | 2026-07-01 | KPTG-IntCorr-015467 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-01 | Auspan-TRANSMIT-000445 | NA | Trade Partner | Update marking plan level 2 zone 3 | 1 | 0 | 0 | KPTG-IntCorr-000817 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise - KPTG-IntCorr-000817 OK to proceed IFC KPTG-IntCorr-000828, No review needed, updated register and distributed KPTG-TRANSMIT-002555 |  | 2026-07-02 | KPTG-TRANSMIT-002555 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-01 | SMEPS-IntCorr-00034 | NA | Trade Partner | Cell 1 CEI test results | 0 | 2 | 0 | NA | APPROVED | 2026-07-01 | WF - 000516 | NA | 2026-07-07 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-01 | Auspan-TRANSMIT-000447 | NA | Trade Partner | Precast shop drawings for construction. Level 1 | 1 | 0 | 0 | KPTG-IntCorr-000818 | APPROVED | [5 empty] | IFC - Waiting for Kim advise-KPTG-IntCorr-000818 Ok to proceed as IFC, UPDATED REGISTER AND DISTRIBUTED -KPTG-TRANSMIT-002661 |  | 2026-07-08 | KPTG-TRANSMIT-002661 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-01 | Entire M-TRANSMIT-000077 | NA | Trade Partner | Mechanical Seismic Design Rev 1 IFC | 0 | 1 | 0 | NA | REJECTED | [5 empty] | REVISION NEEDS UPDATION:KPTG-IntCorr-000647 |  | 2026-07-01 | KPTG-IntCorr-000647 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-01 | D&E-TRANSMIT-000881 | NA | Trade Partner | ISSUED AS BUILT & HANDOVER - LEVEL 01 MECHANICAL LAYOUTS - ZONES 1&2 | 2 | 0 | 0 | NA | APPROVED | 2026-07-01 | NA | 4340 | 2026-07-06 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-019487 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-01 | INGEN3D-TRANSMIT-000160 | NA | Trade Partner | I3D-389 District Living - Level 18-19 - Precast Walls - IFA (01-07-2026) | 10 | 0 | 0 | NA | APPROVED | 2026-07-01 | WF-000860 | NA | 2026-07-17 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-003274 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-01 | ARCST-TRANSMIT-000317 | NA | Trade Partner | C2 Coolig Tower Roof - Issued for Construction | 135 | 0 | 0 | NA | APPROVED | 2026-07-01 | WF-006222 | NA | 2026-08-09 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-01 | Auspan-TRANSMIT-000448 | NA | Trade Partner | Precast shop drawings for construction. Level 2 | 7 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected by Project Coordinator - KPTG-SADV-003205 3 Drawings rejected due to difference in document number and submission of already transmitted drawing -DRAFT-009146 - |  | 2026-07-01 | KPTG-SADV-003205 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-05 | TTW-TRANSMIT-000065 | N/A | Consultant | Structural Documentation - Issued for Construction | 19 | 0 | 0 | NA | APPROVED | 2026-01-06 | NA | 185 | 2026-01-08 |  |  | 2026-01-15 | 2026-01-15 | KPTG-TRANSMIT-000285 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-01 | WilsonPD-TRANSMIT-000204 | SPARK-CRFI-KPG-000436 | Trade Partner | Hydraulic Services - Updated Level 1 Zone B Water Layout | 1 | 0 | 0 | NA | APPROVED | 2026-07-01 | NA | 337 | 2026-07-08 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-001404 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-01 | SMEPS-TRANSMIT-000022 | NA | Trade Partner | Tech Data: Exit and Emergencies | 0 | 7 | 0 | NA | APPROVED | 2026-07-01 | WF-000266 | NA | 2026-07-14 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-001756 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-01 | ZIA-TRANSMIT-000058 | NA | Trade Partner | Cx L3 Test Documents | 0 | 25 | 0 | KPTG-IntCorr-001391 | APPROVED | 2026-06-04 | WF-001106 | NA | 2026-06-10 |  | Terminated by Ibrahim on 11-06-2026 - No approval required | 2026-06-11 | 2026-06-11 | NA | Closed | 25 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-01 | SMEPS-TRANSMIT-000023 | NA | Trade Partner | Techdata: Vertigo Fixing | 0 | 1 | 0 | NA | APPROVED | 2026-07-01 | WF-000267 | NA | 2026-07-14 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-001869 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-01 | ZIA-TRANSMIT-000065 | NA | Trade Partner | Cx Level 3 - HV Test Documents | 0 | 11 | 0 | KPTG-IntCorr-001599 | APPROVED | 2026-07-06 | WF-001141 | NA | 2026-07-09 |  | clarification from ibrahim | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-004147 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-01 | NXT-TRANSMIT-001649 | NA | Trade Partner | O&M Documents for Stage 2 EAE IP68 CCR and IP55 KX Busduct | 0 | 2 | 0 | NA | APPROVED | [5 empty] | For updating and distribution only. |  | 2026-07-01 | KPTG-TRANSMIT-019209 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-01 | Entire M-TRANSMIT-000078 | NA | Trade Partner | Mechanical Seismic Design Rev 1 IFC | 0 | 1 | 0 | NA | APPROVED | 2026-07-01 | WF-000364 | NA | 2026-07-03 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001038 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-01 | Auspan-TRANSMIT-000449 | NA | Trade Partner | Precast shop drawings for construction. Level 3 | 7 | 0 | 0 | KPTG-IntCorr-000822 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise -KPTG-IntCorr-000822 3 are OK to proceed IFC KPTG-TRANSMIT-002557; 4 Rejected as advised by Kapitol PC. KPTG-IntCorr-000836 |  | 2026-07-02 | KPTG-TRANSMIT-002557, DRAFT-009256 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-01 | L.E.S.-TRANSMIT-000020 | NA | Trade Partner | Internal Lighting Tech Data Sheets for Review | 0 | 25 | 0 | NA | APPROVED | 2026-07-21 | WF-001000 | NA | 2026-07-28 |  | Document number mentioned inside the document seem to different as per Aconex submission. So 3 Rejected - 22 submitted | 2026-08-13 | 2026-08-14 | KPTG-TRANSMIT-002621, WF-001153 | Closed | 22 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-01 | SES AU-TRANSMIT-000073 | NA | Trade Partner | SECURITY - Riser Schedules - IFC | 2 | 0 | 0 | NA | APPROVED | 2026-07-01 | WF-000365 | NA | 2026-07-03 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-001028 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-13 | NXT-TRANSMIT-001150 | NA | Consultant | Cooling Tower 13Q Shop Drawings | 9 | 0 | 0 | NA | APPROVED | 2026-01-13 | WF-003749 |  | 2026-01-27 |  |  |  | 2026-01-20 | NXT-WTRAN-001571 | Closed | 9 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-01 | Nilsen3-TRANSMIT-000055 | NA | Trade Partner | Nilsen Sample EX5 Emergency fitting | 0 | 1 | 0 | NA | APPROVED | 2026-07-01 | WF-001097 | NA | 2026-07-13 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-005436 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-01 | Leemark-TRANSMIT-000048 | NA | Trade Partner | MCC - OVERALL FIRE DETECTION SCHEMATIC - IFA | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status inside the drawing and in Aconex seem different |  | 2026-07-01 | KPTG-TRANSMIT-001369 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-01 | Entire M-TRANSMIT-000044 | NA | Trade Partner | Return Design Brief - FOA-3 | 0 | 1 | 0 | NA | APPROVED | 2026-07-01 | WF-000268 | NA | 2026-07-14 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-001131 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-01 | PARR-TRANSMIT-000203 | NA | Trade Partner | Fwd: P2671 - NDC M3 Stage 4 - Enclosures - REVIT FILE | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-01 | KPTG-TRANSMIT-019217 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-01 | SES AU-TRANSMIT-000074 | NA | Trade Partner | SECURITY - Cabling Diagram - IFA | 2 | 0 | 0 | NA | APPROVED | 2026-07-01 | WF-000366 | NA | 2026-07-06 |  | Review out come wrongly attached:KPTG-IntCorr-000656 |  | 2026-07-03 | KPTG-IntCorr-000656 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-01 | SMEPS-TRANSMIT-000025 | NA | Trade Partner | Re: Techdata: BTUs | 0 | 1 | 0 | NA | APPROVED | 2026-07-01 | WF-000269 | NA | 2026-07-14 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-001011 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-01 | SMEPS-TRANSMIT-000024 | NA | Trade Partner | Techdata: BTUs | 0 | 1 | 0 | NA | APPROVED | [5 empty] | Superseded by SMEPS-TRANSMIT-000025 |  | 2026-07-01 | SMEPS-SUBADVICE-000032 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-01 | Carr-TRANSMIT-000072 | NA | Consultant | SME REVIEW - Facade Drawings for coordination | 17 | 0 | 0 | NA | APPROVED | 2026-07-01 | NA | 286 | 2026-07-07 |  | SME REVIEW | 2026-07-16 | 2026-07-16 | KPTG-IntCorr-000234 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-01 | Entire M-TRANSMIT-000045 | NA | Trade Partner | Points List - FOA-1 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with document number. |  | 2026-07-01 | KPTG-SADV-000789 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-01 | SPECAUTO-TRANSMIT-000004 | NA | Trade Partner | CSMS Network Topology | 0 | 1 | 0 | NA | APPROVED | 2026-07-01 | WF-000270 | NA | 2026-07-14 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-001513 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-13 | RDSBIM-TRANSMIT-000184 | NA | Trade Partner | NXM3S4 ¦ GROUND FLOOR-C-G-057 FEMALE WC FLOOR FINISHES LAYOUT AND ELEVATION | 1 | 0 | 0 | NA | APPROVED | 2026-01-13 |  | 1756 | 2026-01-17 |  |  |  | 2026-01-22 | KPTG-TRANSMIT-011797 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-01 | LANSA-TRANSMIT-000108 | NA | Trade Partner | Wtaer & Drainage Drawings with Ground Floor BTR Changes | 6 | 0 | 0 | NA | APPROVED | 2026-07-01 | NA | 588 | 2026-07-06 |  | NA | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-003273 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-01 | Auspan-TRANSMIT-000450 | NA | Trade Partner | Re: Update cast in plate layout for zone 4, 5 | 3 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to difference in document title -DRAFT-009168 |  | 2026-07-01 | DRAFT-009168 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-01 | ARCST-TRANSMIT-000323 | NA | Trade Partner | C2 Cooling Tower Upper Gantry - Issued for Construction | 125 | 0 | 0 | NA | APPROVED | 2026-07-01 | WF-006225 | NA | 2026-07-09 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-07-01 | Nilsen3-TRANSMIT-000212 | NA | Trade Partner | Fwd: Nilsen Shop Drawings - IFC | 11 | 0 | 0 | NA | APPROVED | 2026-07-01 | WF-006226 | NA | 2026-08-06 |  | As per Tom Z. IFC does not need to be reviewed. |  | 2026-07-02 | KPTG-CONTADV-009060 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-01 | Stowe-A-TRANSMIT-000630 | NA | Trade Partner | Stowe - Drawing Update - As Builts | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status inside and in Aconex seem different |  | 2026-07-01 | KPTG-SADV-006303 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-07-01 | Nilsen3-TRANSMIT-000213 | NA | Trade Partner | Nilsen Shop Drawings - IFA | 3 | 0 | 0 | NA | APPROVED | 2026-07-01 | WF-006227 | NA | 2026-08-06 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-019904 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-01 | Entire M-TRANSMIT-000047 | NA | Trade Partner | Schematics FOA | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Different in drawing title. |  | 2026-07-01 | KPTG-SADV-000794 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-07-01 | TTW-TRANSMIT-000195 | NA | Consultant | Fwd: M3 Stage 3 Civil Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-07-01 | WF-006241 | NA | 2026-07-06 |  | The register has been updated. If any further action is required, the coordinator will inform. |  | 2026-07-13 | KPTG-TRANSMIT-019570 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-01 | Entire M-TRANSMIT-000046 | NA | Trade Partner | Mechanical Fixings & Supports FOA-1 | 0 | 1 | 0 | NA | APPROVED | 2026-07-01 | WF-000271 | NA | 2026-07-14 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-001710 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-01 | ADP-TRANSMIT-000096 | NA | Consultant | ADP MEL4680 - CSMS Spec and schedules | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Issue with document number inside the drawings. |  | 2026-07-01 | KPTG-DA-000951 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-13 | SMEPS-TRANSMIT-000134 | NA | Trade Partner | L1, L1E - L2E & EX1 | 0 | 3 | 0 | NA | APPROVED | 2026-01-13 | WF-003752 |  | 2026-01-26 |  |  |  | 2026-01-15 | KPTG-TRANSMIT-011459 | Closed | 3 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-01 | INGEN3D-TRANSMIT-000161 | NA | Trade Partner | Re: I3D-389 District Living - Level 13-15 - PC0522-8 & PC0531-5 - New IFA (16-06-2026) | 3 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Drawings are the same copy of already issued drawings |  | 2026-07-01 | KPTG-TRANSMIT-002628 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-01 | PCForm-TRANSMIT-000262 | NA | Trade Partner | 0025 - Sample submission - 65mpa 180 slump | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Date error in the document and in the register |  | 2026-07-01 | KPTG-TRANSMIT-002634 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-01 | ADP-TRANSMIT-000097 | NA | Trade Partner | ADP MEL4680 - Fire Protection Specification | 0 | 1 | 0 | NA | APPROVED | 2026-07-01 | NA | 304 | 2026-07-06 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-001013 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-01 | Auspan-TRANSMIT-000452 | NA | Trade Partner | Re: Precast shop drawings for construction. Level 6 | 1 | 0 | 0 | KPTG-IntCorr-000833 | REJECTED | [5 empty] | IFC - Waiting for Kim advise -KPTG-IntCorr-000833 KPTG-IntCorr-001127 - Rejected by PC |  | 2026-07-28 | KPTG-IntCorr-001127 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-01 | ZIA-TRANSMIT-000013 | NA | Trade Partner | M2 Stage 9 CSMS SLA and DP Layout and Cabling | 3 | 0 | 0 | NA | APPROVED | 2026-07-01 | NA | 1259 | 2026-07-07 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-006355 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-01 | D&E-TRANSMIT-000885 | NA | Trade Partner | Fwd: NXM3S4 - Roof Level - Chiller Room Layouts + Sections Sheets - Issued For Construction | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-01 | KPTG-TRANSMIT-019226 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-01 | DLTS-TRANSMIT-000004 | NA | Trade Partner | Gutter Bridge-IFA Issue | 12 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with document number. |  | 2026-07-01 | KPTG-SADV-006313 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-01 | Auspan-TRANSMIT-000453 | NA | Trade Partner | Re: Update IFCed precast shop drawings for construction. Level 1 | 1 | 0 | 0 | KPTG-IntCorr-000834 | APPROVED | [5 empty] | IFC - Waiting for Kim advise -KPTG-IntCorr-000834 Update panel 1P5058 was sent via Auspan-TRANSMIT-000444; Registered and transmitted (KPTG-IntCorr-000837) |  | 2026-07-06 | KPTG-IntCorr-000837 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-01 | Stowe-A-TRANSMIT-000631 | NA | Trade Partner | STOWE - Drawing update - As-builts | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Revision inside the drawing and in Aconex seem different |  | 2026-07-01 | KPTG-SADV-006317 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-01 | ECBS-TRANSMIT-000047 | NA | Trade Partner | Fan Wall Unit Steel- Revised Drawing IFC (Batch 2: 47 drawings) | 47 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect Status |  | 2026-07-01 | KPTG-DA-007351 | Closed | 47 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-13 | NXT-TRANSMIT-001182 | NA | Consultant | M3 ST-4 XDU - Vertiv documents submissions (IFC) | 9 | 0 | 0 | NA | APPROVED | 2026-01-13 | WF-003753 |  | 2026-01-27 |  |  |  | 2026-01-20 | KPTG-TRANSMIT-011713 | Closed | 9 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-01 | Entire M-TRANSMIT-000079 | NA | Trade Partner | Commissioning Management Plan Rev 4 Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-01 | WF-000367 | NA | 2026-07-03 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-000996 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-01 | Civilex-TRANSMIT-000277 | NA | Trade Partner | Stage 2 - sample submission - Irrigation System / FOA -C | 0 | 3 | 0 | NA | APPROVED | 2026-07-01 | WF-006228 | NA | 2026-07-06 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-019255 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-01 | ARCST-TRANSMIT-000322 | NA | Trade Partner | C3 Cooling Tower Upper Gantry - Issued for Construction | 116 | 0 | 0 | NA | REJECTED | [5 empty] | IFC received prior to IFA |  | 2026-07-01 | KPTG-RFI-008696 | Closed | 116 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-01 | DLTS-TRANSMIT-000005 | NA | Trade Partner | Eave Gutter Bridge-IFA Issue | 12 | 0 | 0 | NA | APPROVED | 2026-07-01 | WF-006230 | NA | 2026-07-20 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-020227 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-01 | CRSol-TRANSMIT-000092 | NA | Trade Partner | Re: M3S4 CRS CLN Drawings - Revised and Updated - IFC | 45 | 0 | 0 | NA | REJECTED | [5 empty] | The IFA for the drawings has not been received |  | 2026-07-01 | KPTG-DA-007354 | Closed | 45 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-01 | Civilex-TRANSMIT-000276 | NA | Trade Partner | Stage 2 - sample submission - Fosroc Concure X90 | 0 | 1 | 0 | NA | APPROVED | 2026-07-01 | WF-006220 | NA | 2026-07-07 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-019720 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-01 | D&E-TRANSMIT-000884 | NA | Trade Partner | ISSUED AS INSTALLED & HANDOVER - LEVEL 01 - MECHANICAL DUCT LAYOUT - ZONE 1&2 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | As Built submission for FOA rejected document. |  | 2026-07-01 | KPTG-SADV-006318 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-01 | ccair-TRANSMIT-000003 | NA | Trade Partner | 20260701-Mechanical Penetration drawings for review GF to Level 4 | 6 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | QA Error - Doc.No, Revision |  | 2026-07-01 | KPTG-TRANSMIT-002631 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-01 | D&E-TRANSMIT-000883 | NA | Trade Partner | Fwd: Fans Technical Data - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | [5 empty] | IFC ONLY FOR DISTRIBUTION |  | 2026-07-01 | KPTG-TRANSMIT-019208 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-01 | D&E-TRANSMIT-000882 | NA | Trade Partner | Fwd: MaxCool Functional Description - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | [5 empty] | ONLY FOR DISTRIBUTION |  | 2026-07-01 | KPTG-TRANSMIT-019207 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2026-01-13 | Nilsen3-TRANSMIT-000099 | NA | Trade Partner | Nilsen Shop Drawings Cable Containment- As-Builts | 5 | 0 | 0 | NA | APPROVED | [5 empty] | As-Built drawings, No review required. Distributed to the Project Team |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-01 | ARCST-TRANSMIT-000318 | NA | Trade Partner | - C1 Cooling Tower Upper Gantry - Issued for Construction | 169 | 0 | 0 | NA | APPROVED | 2026-07-01 | WF-006223 | NA | 2026-07-22 |  | One Document Terminated ,As instructed by Lola in KPTG-IntCorr-017258 |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-01 | RDSBIM-TRANSMIT-000284 | NA | Trade Partner | GROUND FLOOR-C-G-073 UNISEX WC FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-07-01 | NA | 3732 | 2026-07-22 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-019505 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-01 | ARCST-TRANSMIT-000321 | NA | Trade Partner | Re: C3 Cooling Tower Roof - Issued for Construction | 129 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due ifa rejected submitted for ifc |  | 2026-07-01 | KPTG-RFI-008702 | Closed | 129 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-01 | Tradetec-TRANSMIT-000474 | NA | Trade Partner | Re: IFA - Stage 4 - LVP50 to 55 | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to wrong document number in the drawing |  | 2026-07-01 | KPTG-RFI-008703 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-01 | Nilsen3-TRANSMIT-000214 | NA | Trade Partner | Re: Nilsen Sample switched socket outlet | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect revision number |  | 2026-07-01 | KPTG-RFI-008704 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-01 | crossfir-TRANSMIT-000023 | NA | Trade Partner | : Wet Fire - Tan as per discussion meeting | 2 | 0 | 0 | KPTG-IntCorr-000861 | APPROVED |  | NA | NA |  |  | Tayla to advise - KPTG-IntCorr-000861 |  | 2026-07-03 | No this does not need to go into another review. | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-01 | KETE-TRANSMIT-000044 | NA | Trade Partner | Auto door&DDA door drawing updated | 34 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected (KPTG-TRANSMIT-003098) |  | 2026-07-01 | NA | Closed | 34 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-01 | Baigents-TRANSMIT-000009 | NA | Trade Partner | Remaining Grid 2 Level 01 Precast beams IFA | 11 | 0 | 0 | NA | APPROVED | 2026-07-01 | NA | 305 | 2026-07-08 |  | Actual submission 30-06-2026-Requested by Tim | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-000529 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-01 | RDSBIM-TRANSMIT-000219 | NA | Trade Partner | LEVEL 00 GYM & CO-WORKSPACE FLOOR FINISHES | 4 | 0 | 0 | NA | APPROVED | 2026-07-01 | NA | 589 | 2026-07-08 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-003159 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-01 | RDSBIM-TRANSMIT-000220 | NA | Trade Partner | LEVEL 09 TOWER A PAVILION ROOF LAYOUT AND SECTIONS ¦ IFR ¦ FOR SUBMISSION | 4 | 0 | 0 | NA | APPROVED | 2026-07-01 | NA | 590 | 2026-07-08 |  | NA | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-003105 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-12 | RDSBIM-TRANSMIT-000096 | NA | Trade Partner | MLC ¦ AQUATIC CENTER LEVEL 01 INTERNAL SCREED LAYOUT | 9 | 0 | 0 | NA | APPROVED | 2026-01-12 |  | 389 | 2026-01-19 |  |  |  | 2026-01-19 | KPTG-SADV-003403 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-01 | RDSBIM-TRANSMIT-000013 | NA | Trade Partner | LOWER ROOF CONCRETE PROFILE PLAN | 2 | 0 | 0 | NA | APPROVED | 2026-07-01 | NA | 309 | 2026-07-08 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-000478 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-01 | PTA-TRANSMIT-000015 | NA | Consultant | NextDC M3 S6 - PTA Arch Documentation issued_CAD | 183 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | CAD file -distribution |  | 2026-07-01 | KPTG-TRANSMIT-000403 | Closed | 183 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-01 | PCForm-TRANSMIT-000259 | NA | Trade Partner | Level 4 formwork design sections | 1 | 0 | 0 | KPTG-IntCorr-000909 | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-000983 - NO FURTHER ACTION |  | 2026-07-13 | KPTG-IntCorr-000983 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-01 | PCForm-TRANSMIT-000258 | NA | Trade Partner | Level 4 formwork design REV C | 1 | 0 | 0 | KPTG-IntCorr-000908 | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-000983 - NO FURTHER ACTION |  | 2026-07-13 | KPTG-IntCorr-000983 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-01 | RDSBIM-TRANSMIT-000216 | NA | Trade Partner | LINDRUM ¦ LEVEL 04 PARTITION WALL LAYOUT | 1 | 0 | 0 | KPTG-IntCorr-001136 | APPROVED | 2026-07-03 | NA | 684 | 2026-07-08 |  | KPTG-IntCorr-001136 - requested guidance, but no response received yet | 2026-07-09 | 2026-07-09 | KPTG-SADV-004854 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-01 | SYNACC-TRANSMIT-000006 | NA | Trade Partner | Transmittal - IFA - Level 10 Monorail | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-001138 - as per direction from Ashlin, we No action is being taken on this transmittal. Also please note the document number and revision is incorrect. | 2026-07-01 | 2026-07-01 | KPTG-IntCorr-001138 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | SME-688 | NA | Consultant | SME REVIEW OF STEEL STRUCTURAL DRAWINGS | 19 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 688 | 2026-06-15 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-002603 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | SME-689 | NA | Consultant | WET AREA AND BATHROOM DETAILS | 9 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 689 | 2026-06-08 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-002602 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-01 | Arc Plas-TRANSMIT-000005 | NA | Trade Partner | Ceiling - Metal Tile | 0 | 1 | 0 | NA | APPROVED | 2026-07-01 | WF-001096 | NA | 2026-08-08 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-005198 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-01 | Nilsen3-TRANSMIT-000056 | NA | Trade Partner | Nilsen Sample submissions #7 | 0 | 2 | 0 | NA | APPROVED | 2026-07-01 | WF-001101 | NA | 2026-07-08 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-005357 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-12 | Danlai-TRANSMIT-000004 | NA | Trade Partner | Resubmit - DC-AR-TEC-004 | 0 | 1 | 0 | NA | APPROVED | 2026-01-12 | WF-000700 |  | 2026-01-15 |  |  |  | 2026-01-19 | KPTG-TRANSMIT-002113 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-01 | Arc Plas-TRANSMIT-000017 | NA | Trade Partner | Fastwall - Temporary Infill Panel - Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-07-01 | WF-001098 | NA | 2026-07-08 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-005181 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-01 | PROLMC-TRANSMIT-000003 | NA | Trade Partner | Sample Technical Data Sheet Submission | 0 | 3 | 0 | NA | APPROVED | 2026-07-01 | WF-001099 | NA | 2026-07-07 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-005249 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-01 | Endfire-TRANSMIT-000079 | NA | Trade Partner | FIRE SERVICES - COMMISSIONING PLAN | 0 | 1 | 0 | NA | APPROVED | 2026-07-01 | WF-001134 | NA | 2026-07-03 |  | As per Ibrahim's Teams Msg |  | 2026-07-20 | KPTG-TRANSMIT-004113 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-01 | SMEPS-TRANSMIT-000057 | NA | Trade Partner | M2 Stage 9-11 - SME Technical Data Submissions | 0 | 3 | 0 | NA | APPROVED | 2026-07-01 | WF-001107 | NA | 2026-07-08 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-005602 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-01 | SMEPS-TRANSMIT-000056 | NA | Trade Partner | GF Containment Drawings - ELC | 1 | 0 | 0 | NA | APPROVED | 2026-07-01 | NA | 1260 | 2026-07-08 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-005724 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-01 | SMEPS-TRANSMIT-000056 | NA | Trade Partner | GF Containment Drawings - TEL | 1 | 0 | 0 | NA | APPROVED | 2026-07-01 | NA | 1261 | 2026-07-08 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-006360 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-01 | ELLISAIR-TRANSMIT-000097 | NA | Trade Partner | Fans stage 10 & 11 | 0 | 1 | 0 | NA | APPROVED | 2026-07-01 | WF-001104 | NA | 2026-07-13 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-005854 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-01 | ELLISAIR-TRANSMIT-000098 | NA | Trade Partner | PAU (AHU) | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, No review required. Updated register and distributed |  | 2026-07-01 | KPTG-TRANSMIT-005103 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-01 | ELLISAIR-TRANSMIT-000099 | NA | Trade Partner | Flexible duct | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, Updated register and distributed |  | 2026-07-01 | KPTG-TRANSMIT-005106 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-01 | ELLISAIR-TRANSMIT-000100 | NA | Trade Partner | Ground floor Link Bridge Duct & Pipe layout drawing issued for Construction | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Need to revise, KPTG-SADV-005761 |  | 2026-07-01 | KPTG-SADV-005761 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-12 | ARCH-TRANSMIT-000128 | NA | Consultant | MLC - SPR - Endorsed Town Planning drawing | 22 | 0 | 0 | NA | APPROVED | [5 empty] | Updated Document Register only |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-01 | ELLISAIR-TRANSMIT-000101 | NA | Trade Partner | Side Stream Filtration | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Need to revise |  | 2026-07-01 | KPTG-SADV-005762 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-01 | ASV-TRANSMIT-000072 | NA | Trade Partner | External Tank Farm for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-07-01 | NA | 1263 | 2026-07-06 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-006365 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-01 | ASV-TRANSMIT-000073 | NA | Trade Partner | Stage 6 Hydraulic/Fire/Drainage Services for Review | 1 | 0 | 0 | NA | APPROVED | 2026-07-01 | NA | 1264 | 2026-07-06 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-006369 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-02 | INGEN3D-TRANSMIT-000162 | NA | Trade Partner | I3D-389 District Living - Level 19-20 - Precast Walls - IFA (01-07-2026) | 10 | 0 | 0 | NA | APPROVED | 2026-07-02 | WF-000861 | NA | 2026-07-20 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-003292 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-02 | INGEN3D-TRANSMIT-000163 | NA | Trade Partner | I3D-389 District Living - Level 20-21 - Precast Walls - IFA (01-07-2026) | 7 | 0 | 0 | NA | APPROVED | 2026-07-02 | WF-000862 | NA | 2026-07-20 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003268 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-01 | PARR-TRANSMIT-000061 | NA | Trade Partner | FUEL SERVICES - COMMISSIONING PLAN | 0 | 1 | 0 | NA | APPROVED | 2026-07-01 | WF-001135 | NA | 2026-07-03 |  | As per Ibrahim's Teams Msg |  | 2026-07-23 | KPTG-TRANSMIT-004151 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-01 | KPTG-IntCorr-001568 | NA | Trade Partner | HYD SERVICES - COMMISSIONING PLAN | 0 | 1 | 0 | NA | APPROVED | 2026-07-01 | WF-001136 | NA | 2026-07-03 |  | As per Ibrahim's Teams Msg |  | 2026-07-23 | KPTG-TRANSMIT-004149 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-02 | TTW-TRANSMIT-000170 | NA | Consultant | Updated Civil IFC Drawings | 16 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 880 | 2026-07-06 |  |  | 2026-07-27 | 2026-07-28 | KPTG-TRANSMIT-003126 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-02 | Rinco-TRANSMIT-000060 | NA | Consultant | Level 1 drawings update | 22 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1388 | 2026-07-04 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002749 | Closed | 22 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-02 | L.E.S.-TRANSMIT-000021 | NA | Trade Partner | Updates internal lighting tech data sheets for review | 0 | 2 | 0 | NA | APPROVED | 2026-07-02 | WF-000866 | NA | 2026-07-09 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-002882 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-02 | PARR-TRANSMIT-000021 | NA | Trade Partner | Fuel Services - BULK FUEL SCHEMATIC | 1 | 0 | 0 | NA | APPROVED | 2025-12-02 | NA | 679 | 2025-12-04 |  |  | 2025-12-03 | 2025-12-05 | KPTG-TRANSMIT-002168 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-13 | Auspan-TRANSMIT-000035 | NA | Trade Partner | Update already IFCed L shape shop drawings. Key joint details added. | 21 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-SADV-000593 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-02 | Auspan-TRANSMIT-000455 | NA | Trade Partner | Update precast cast in plate level 3-Zone 4&5 | 1 | 0 | 0 | KPTG-IntCorr-000838 | APPROVED | [5 empty] | IFC - Waiting for Kim advise-KPTG-IntCorr-000838 OK to proceed as IFC KPTG-TRANSMIT-002596 |  | 2026-07-06 | KPTG-TRANSMIT-002596 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-02 | Appselec-TRANSMIT-000134 | NA | Trade Partner | AHU Isolator For Approval Rev 3 | 0 | 1 | 0 | NA | APPROVED | 2026-07-02 | WF-000368 | NA | 2026-07-08 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-001009 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-02 | VERTIV-TRANSMIT-000041 | NA | Trade Partner | NEXT DC GE 01 _ ARCHITECTURAL DRAWINGS (FOA-1 & FOA-2) | 9 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 306 | 2026-07-08 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-001147 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-02 | Resonate-TRANSMIT-000014 | NA | Consultant | BCA Acoustic Report | 0 | 1 | 0 | NA | REJECTED | [5 empty] | REGISTER AS A DUPLICATE ENTRY - HENCE REJECTED |  | 2026-07-08 | KPTG-TRANSMIT-002766 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-02 | ARCH-TRANSMIT-000052 | NA | Consultant | Building Permit Documentation | 7 | 2 | 0 | NA | REJECTED | [5 empty] | Issue with Revision Date. |  | 2026-07-02 | DRAFT-003205 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-02 | NXT-PA-005641 | NA | Trade Partner | P2671 - NDC M3 Stage 4 - Enclosures - REVIT FILE | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-02 | KPTG-TRANSMIT-019241 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-02 | PROLMC-TRANSMIT-000036 | NA | Trade Partner | Re: Proline Shop drawing details Dog boxes, Door hoods and Gland plates | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect status |  | 2026-07-02 | KPTG-DA-007358 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-02 | Entire M-TRANSMIT-000048 | NA | Trade Partner | BMS Points List - Naming Convention Corrected FOA-1 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect Document number inside the document. |  | 2026-07-02 | KPTG-SADV-000813 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-02 | Auspan-TRANSMIT-000456 | NA | Trade Partner | Re: Precast shop drawings for approval. Zone 4, 5 level 5 | 3 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1390 | 2026-07-09 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002820 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-02 | Auspan-TRANSMIT-000456 | NA | Trade Partner | Re: Precast shop drawings for approval. Zone 4, 5 level 5 | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to difference in document number - DRAFT-009235 |  | 2026-07-02 | DRAFT-009235 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-30 | RDSBIM-TRANSMIT-000134 | NA | Trade Partner | LINDRUM ¦ LEVEL 02 TO LEVEL 05 COREWALL CONCRETE PROFILE PLAN ELEVATIONS | 2 | 0 | 0 | NA | APPROVED | 2026-01-12 |  | 504 | 2026-01-20 |  |  | 2026-01-29 | 2026-01-29 | KPTG-SADV-002775 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-02 | Nilsen3-TRANSMIT-000216 | NA | Trade Partner | Nilsen Sample switched socket outlet | 0 | 1 | 0 | NA | APPROVED | 2026-07-02 | WF-006232 | NA | 2026-07-28 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-02 | Entire M-TRANSMIT-000049 | NA | Trade Partner | Industrial Water System - FOA-2 Submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with document status. |  | 2026-07-02 | KPTG-SADV-000817 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-02 | Entire M-TRANSMIT-000050 | NA | Trade Partner | Mechanical Security Grille detail FOA | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect document number, missing revision, revision date, drawings status, revision history. |  | 2026-07-02 | KPTG-SADV-000814 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | VIA Arch-TRANSMIT-000174 | NA | Consultant | ANTENA ROOM WEST DETAILS | 2 | 2 | 0 | NA | APPROVED | 2026-07-02 | NA | 1266 | 2026-07-09 |  |  | 2026-07-14 | 2026-07-14 | KPTG-DA-003706 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-02 | SKS Tech-TRANSMIT-000190 | NA | Trade Partner | PDU, BACOP + BOB schematic for approval | 2 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 3736 | 2026-07-14 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | VIA Arch-TRANSMIT-000175 | NA | Consultant | M2 - S9-11 - BUILDING PERMIT ISSUE | 12 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1268 | 2026-07-09 |  |  | 2026-07-14 | 2026-07-14 | KPTG-DA-003707 | Closed | 12 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | VIA Arch-TRANSMIT-000176 | NA | Consultant | Update drawing toilet signage | 1 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1270 | 2026-07-09 |  |  | 2026-07-14 | 2026-07-14 | KPTG-DA-003708 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | VIA Arch-TRANSMIT-000177 | NA | Consultant | Updated drawings | 12 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1272 | 2026-07-09 |  |  | 2026-07-14 | 2026-07-14 | KPTG-DA-003709 | Closed | 12 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-02 | Resonate-TRANSMIT-000015 | NA | Consultant | 100% DD Acoustic Report | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-000913 | NA | 2026-07-13 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002861 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | VIA Arch-TRANSMIT-000178 | NA | Consultant | S9-S11 Door Hardware Schedule | 0 | 3 | 0 | NA | APPROVED | 2026-07-02 | NA | 1274 | 2026-07-09 |  |  | 2026-08-03 | 2026-08-03 | KPTG-DA-004066 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-31 | RDSBIM-TRANSMIT-000135 | NA | Trade Partner | LINDRUM ¦ LEVEL 04 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-01-12 |  | 505 | 2026-01-19 |  |  | 2026-01-23 | 2026-01-23 | KPTG-SADV-002712 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-02 | ETNInd-TRANSMIT-000023 | NA | Trade Partner | COLO4 UPS FAT Reports | 0 | 8 | 0 | NA | APPROVED | 2026-07-02 | WF-000369 | NA | 2026-07-08 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-001094 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-02 | JCBa-TRANSMIT-000147 | NA | Consultant | Ground and L5 RCP Updates for IFC | 8 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1393 | 2026-07-06 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-002684 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-02 | L.E.S.-TRANSMIT-000022 | NA | Trade Partner | LNT-EL-SMP-017 Tech data sheet for review | 0 | 1 | 0 | NA | APPROVED | 2026-07-02 | WF-000866 | NA | 2026-07-09 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-002881 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | VIA Arch-TRANSMIT-000179 | NA | Consultant | M2 S9-S11 - BUILDING PERMIT ISSUE - UPDATED DRGS | 7 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1276 | 2026-07-09 |  |  | 2026-07-16 | 2026-07-16 | KPTG-DA-003752 | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-02 | SKS Tech-TRANSMIT-000191 | NA | Trade Partner | IFC SLD's | 16 | 0 | 0 | NA | APPROVED | 2026-07-02 | 3739 | NA | 2026-07-11 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | VIA Arch-TRANSMIT-000180 | NA | Consultant | M2 S9-S11 - Concrete Profile Drawing Updates | 3 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1278 | 2026-07-09 |  |  | 2026-07-16 | 2026-07-16 | KPTG-DA-003753 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-02 | ARCST-TRANSMIT-000322 | NA | Trade Partner | C3 Cooling Tower Upper Gantry - Issued for Construction | 116 | 0 | 0 | NA | APPROVED | 2026-07-02 | WF-006235 | NA | 2026-07-10 |  | As instructed by Lola in KPTG-RTRFI-005027 |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | ARCST-TRANSMIT-000281 | NA | Trade Partner | C2 West Roof Walkway - Issued for Approval | 0 | 0 | 0 | NA | APPROVED | 2026-05-12 | WF-005669 | NA | 2026-05-27 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-019245 | Closed | 89 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | VIA Arch-TRANSMIT-000181 | NA | Consultant | Updated drawings | 9 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1280 | 2026-07-09 |  |  | 2026-07-17 | 2026-07-17 | KPTG-DA-003786 | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-02 | G&CHyd-TRANSMIT-000005 | NA | Trade Partner | HYD Tech Data | 0 | 12 | 0 | NA | APPROVED | 2026-07-02 | WF-000864 | NA | 2026-07-06 |  | CLIENT REVIEW | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-002884 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-01 | RDSBIM-TRANSMIT-000136 | NA | Trade Partner | LINDRUM ¦ LEVEL 06 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-01-12 |  | 506 | 2026-01-19 |  |  | 2026-01-23 | 2026-01-23 | KPTG-SADV-002713 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | VIA Arch-TRANSMIT-000182 | NA | Consultant | M2 S9 - S11 - BUILDING PERMIT DRAWING UPDATES | 3 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1282 | 2026-07-09 |  |  | 2026-07-16 | 2026-07-16 | KPTG-DA-003755 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | VIA Arch-TRANSMIT-000183 | NA | Consultant | Updated Exterior Finishes Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-07-02 | NA | 1248 | 2026-07-09 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-005673 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-02 | D&E-TRANSMIT-000278 | NA | Trade Partner | Mechanical Services BMS Topology | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision date is incorrect |  | 2026-07-02 | KPTG-TRANSMIT-001373 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-02 | JCBa-TRANSMIT-000148 | NA | Consultant | Thermal Performance Plans: Updated IFC | 2 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1396 | 2026-07-06 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002715 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | VIA Arch-TRANSMIT-000184 | NA | Consultant | M2 S9 - S11 - BUILDING PERMIT DRAWING UPDATES | 7 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1287 | 2026-07-09 |  |  | 2026-07-16 | 2026-07-16 | KPTG-DA-003756 | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-02 | D&E-TRANSMIT-000279 | NA | Trade Partner | Fwd: Mechanical BMS points List - For Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision date is incorrect |  | 2026-07-02 | KPTG-TRANSMIT-001374 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | VIA Arch-TRANSMIT-000185 | NA | Consultant | Updated Drawings | 17 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1289 | 2026-07-09 |  |  | 2026-07-16 | 2026-07-16 | KPTG-DA-003758 | Closed | 17 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-02 | EFP-TRANSMIT-000031 | NA | Trade Partner | EFP Tech Data Alternative | 0 | 1 | 0 | NA | APPROVED | 2026-07-02 | WF-000370 | NA | 2026-07-09 |  | workflow resubmitted: WF-000386 |  | 2026-07-09 | KPTG-WTRAN-000749 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-20 | ARCST-TRANSMIT-000262 | NA | Trade Partner | C1 Cooling Tower Roof Stairs - Issued for Approval | 0 | 0 | 0 | NA | APPROVED | 2026-04-20 | WF-005358 | NA | 2026-05-14 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-019251 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-02 | KALLIBRE-TRANSMIT-000006 | NA | Trade Partner | IFA - Mailbox Shopdrawings and numbers | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to wrong document. |  | 2026-07-02 | KPTG-SADV-007867 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-01 | RDSBIM-TRANSMIT-000137 | NA | Trade Partner | LINDRUM ¦ LEVEL 07 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-01-12 |  | 507 | 2026-01-19 |  |  | 2026-01-23 | 2026-01-23 | KPTG-SADV-002717 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | VIA Arch-TRANSMIT-000186 | NA | Consultant | STAGE 9 BUILDING PERMIT UPDATES | 6 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1291 | 2026-07-09 |  |  | 2026-07-16 | 2026-07-16 | KPTG-DA-003762 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-02 | KPTG-IntCorr-000655 | NA | Trade Partner | Re: Screed material tech data- | 0 | 1 | 0 | NA | APPROVED | 2026-07-02 | WF-000371 | NA | 2026-07-03 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-001014 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-02 | Stowe-A-TRANSMIT-000632 | NA | Trade Partner | STOWE - As Built drawings update | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Document that doesnt approved in FOA and FC submitted as As Built directly. |  | 2026-07-02 | KPTG-SADV-006342 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | VIA Arch-TRANSMIT-000187 | NA | Consultant | CD-09 Customer changes and Data Hall Fitout | 13 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1293 | 2026-07-09 |  |  | 2026-07-14 | 2026-07-14 | KPTG-DA-003710 | Closed | 13 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-02 | INGEN3D-TRANSMIT-000164 | NA | Trade Partner | I3D-389 District Living - Level 21-22 - Precast Walls - IFA (02-07-2026) | 7 | 0 | 0 | NA | APPROVED | 2026-07-02 | WF-000867 | NA | 2026-07-20 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003259 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-02 | SMEPS-IntCorr-000346 | NA | Trade Partner | SMEPS-IntCorr-000346 | 0 | 2 | 0 | NA | APPROVED | 2026-07-02 | WF - 000517 | NA | 2026-07-08 |  | NA | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-001074 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | VIA Arch-TRANSMIT-000188 | NA | Consultant | Stage 9 Signage Plans and Details | 4 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1296 | 2026-07-09 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-005678 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | VIA Arch-TRANSMIT-000189 | NA | Consultant | CD-09 Customer changes and Data Hall Fitout - Revision Updated | 2 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1298 | 2026-07-09 |  |  | 2026-07-16 | 2026-07-16 | KPTG-DA-003766 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-02 | PCForm-TRANSMIT-000263 | NA | Trade Partner | Stair Form Fire Rail Sample | 0 | 1 | 0 | NA | REJECTED | [5 empty] | STATUS DIFFERENCE |  | 2026-07-02 | KPTG-TRANSMIT-002654 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-02 | Altaire-TRANSMIT-000119 | NA | Trade Partner | DHB5 and DHB6 As-Built Revision Post Cintoo Alignment | 1 | 0 | 0 | NA | APPROVED | [5 empty] | Issue with drawing status inside the document, document became multipage document in latest revision. |  | 2026-07-02 | KPTG-SADV-006344 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-05 | RDSBIM-TRANSMIT-000138 | NA | Trade Partner | LINDRUM ¦ LEVEL 05 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-01-12 |  | 508 | 2026-01-19 |  |  | 2026-01-23 | 2026-01-23 | KPTG-SADV-002716 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | VIA Arch-TRANSMIT-000190 | NA | Consultant | M2 S9-S11 - INTERNAL SWITCHROOM ELEVATIONS - IFBP-1 | 1 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1300 | 2026-07-09 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-005697 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-02 | D&E-TRANSMIT-000886 | NA | Trade Partner | NXM3S2 - Lower Ground - Fuel Tank Pump Room Layout - Issued For Construction | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Latest available version in our register is FOA-01 which is rejected. need to resubmit FOA revision prior to FC. |  | 2026-07-02 | KPTG-SADV-006345 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | VIA Arch-TRANSMIT-000191 | NA | Consultant | M2 S10 & S11 - Concrete Profile Plans Level 2 - IFBP | 3 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1302 | 2026-07-09 |  |  | 2026-07-09 | 2026-07-16 | KPTG-DA-003774 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-02 | SC-TRANSMIT-000010 | NA | Trade Partner | Secondary Steel IFA Drawings | 56 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status is missing. Drawing revision is incorrect Drawing title inside drawing and in Aconex seem different |  | 2026-07-02 | KPTG-TRANSMIT-001375 | Closed | 56 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-02 | KPTG-WTRAN-011771 | NA | Trade Partner | HAC Labels | 0 | 1 | 0 | NA | APPROVED | 2026-07-02 | WF-006238 | NA | 2026-07-23 |  | As instructed by Peter - Terminated-This is because we are proceeding with a different supplier |  | 2026-07-07 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | VIA Arch-TRANSMIT-000192 | NA | Consultant | M2 S9-S11 - BUILDING PERMIT | 3 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1304 | 2026-07-09 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-005473 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-02 | Auspan-TRANSMIT-000454 | NA | Trade Partner | Re: RFI: PENO THROUGH GROUT TUBE PANEL 2P5073. Update IFCed precast shop drawings | 6 | 0 | 0 | KPTG-IntCorr-000843, KPTG-IntCorr-000844 | APPROVED | [5 empty] | IFC - Waiting for Kim advise- KPTG-IntCorr-000843, KPTG-IntCorr-000844 5 are OK to proceed, Register and Transmit - KPTG-TRANSMIT-002607 1 Reject. DRAFT-009416 |  | 2026-07-06 | KPTG-TRANSMIT-002607 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-02 | D&E-TRANSMIT-000887 | NA | Trade Partner | NXM3S4 - Upper Roof & Roof + Level 1 - CHW Pipe Layout Zones - Issued For Construction | 7 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision , status |  | 2026-07-02 | KPTG-RFI-008716 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | DLTS-TRANSMIT-000049 | NA | Trade Partner | S11-Cooling Tower-IFA Issue (Part-1) | 198 | 0 | 0 | NA | APPROVED | 2026-07-02 | WF-001115 | NA | 2026-07-14 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-005705 | Closed | 198 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | DLTS-TRANSMIT-000049 | NA | Trade Partner | S11-Cooling Tower-IFA Issue (Part-2) | 81 | 0 | 0 | NA | APPROVED | 2026-07-02 | WF-001116 | NA | 2026-07-14 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-005705 | Closed | 81 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-13 | SMEPS-TRANSMIT-000133 | NA | Trade Partner | GIS - GF Power As Built | 1 | 0 | 0 | NA | APPROVED | 2026-01-13 |  |  |  |  | GIS - GF Power As Built |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | VIA Arch-TRANSMIT-000193 | NA | Consultant | Data Hall - Updated drawings | 16 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1306 | 2026-07-09 |  |  | 2026-07-14 | 2026-07-14 | KPTG-DA-003711 | Closed | 16 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-02 | Auspan-TRANSMIT-000457 | NA | Trade Partner | Update IFCed precast shop drawings | 2 | 0 | 0 | KPTG-IntCorr-000845 | APPROVED | [5 empty] | IFC - Waiting for Kim advise-KPTG-IntCorr-000845 IFC Register and Transmit -KPTG-TRANSMIT-002657 |  | 2026-07-08 | KPTG-TRANSMIT-002657 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-02 | Auspan-TRANSMIT-000457 | NA | Trade Partner | Update IFCed precast shop drawings | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to difference in document number -DRAFT-009272 |  | 2026-07-02 | DRAFT-009272 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | VIA Arch-TRANSMIT-000194 | NA | Consultant | S9 L2 Door Schedule Update | 1 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1308 | 2026-07-09 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-005480 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-02 | D&E-TRANSMIT-000281 | NA | Trade Partner | Mechanical Services BMS Functional Description - For Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision date is incorrect |  | 2026-07-02 | KPTG-TRANSMIT-001376 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-02 | KALLIBRE-TRANSMIT-000007 | NA | Trade Partner | Mailbox Numbers | 0 | 1 | 0 | NA | APPROVED | 2026-07-02 | WF - 001067 | NA | 2026-07-09 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-02 | EAEGROUP-TRANSMIT-000107 | NA | Trade Partner | KPTG-DA-007372 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Document reference number is missing |  | 2026-07-02 | KPTG-DA-007372 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-02 | KALLIBRE-TRANSMIT-000009 | NA | Trade Partner | Mailbox Colour Samples | 0 | 1 | 0 | NA | APPROVED | 2026-07-02 | WF - 001068 | NA | 2026-07-09 |  | NA | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-003161 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-02 | Auspan-TRANSMIT-000458 | NA | Trade Partner | Re: Precast shop drawings for apporval. Zone 1 | 2 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1398 | 2026-07-09 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002736 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-02 | Omnii-TRANSMIT-000006 | NA | Consultant | FIRE ENGINEERING PERFORMANCE BASED DESIGN BRIEF Revision E | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision history does not update properly |  | 2026-07-02 | KPTG-DA-000413 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-08 | RDSBIM-TRANSMIT-000139 | NA | Trade Partner | LINDRUM ¦ LEVEL 08 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-01-12 |  | 509 | 2026-01-19 |  |  | 2026-01-23 | 2026-01-23 | KPTG-SADV-002721 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-02 | Rinco-TRANSMIT-000062 | NA | Consultant | Fwd: Propping sequence | 1 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1400 | 2026-07-06 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002755 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-02 | Carr-TRANSMIT-000074 | NA | Consultant | Wet Areas Package | 5 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 291 | 2026-07-09 |  | This workflow has been voided due to revisions made to some of the associated drawings from Carr. The remaining drawings will be re-initiated separately under a new workflow. |  | 2026-08-27 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-02 | ADP-TRANSMIT-000098 | NA | Consultant | ADP MEL4680 - CSMS Spec and schedules | 0 | 3 | 0 | NA | APPROVED | 2026-07-02 | NA | 308 | 2026-07-07 |  | Specifications and schdules | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-001028 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-02 | BACAU-TRANSMIT-000004 | NA | Trade Partner | BAC Shop drawings | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with Document number, title, orientation mistake in drawing. |  | 2026-07-02 | KPTG-SADV-000819 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | ARCST-TRANSMIT-000271 | NA | Trade Partner | Fwd: Stair 3 & 6 - Issued for Approval | 0 | 0 | 0 | NA | APPROVED |  | WF-005550 | NA |  |  |  |  | 2026-07-02 | KPTG-TRANSMIT-019265 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-02 | VERTIV-TRANSMIT-000014 | NA | Trade Partner | NEXT DC GE01 _ MATERIAL SUBMISSION _ FIRE SUPPRESSION AND DETECTION SYSTEM (FOA-1) | 0 | 1 | 0 | NA | APPROVED | 2026-07-02 | WF-000277 | NA | 2026-07-09 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-001237 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-02 | SMEPS-IntCorr-000347 | NA | Trade Partner | Request for Fibre and Copper Test Results | 0 | 4 | 0 | NA | APPROVED | 2026-07-02 | WF - 000518 | NA | 2026-07-09 |  | WF Terminated. file superseded. | 2026-07-06 | 2026-07-06 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-02 | Entire M-TRANSMIT-000051 | NA | Trade Partner | Mechanical Schematics FOA | 5 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 310 | 2026-07-08 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001417 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-02 | D&E-TRANSMIT-000878 | NA | Trade Partner | Re: Mechanical SFN Discharge Register - Issued for Review | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | NEED TO SEND THAT DOCUMENT IN PDF FORMAT |  | 2026-07-02 | KPTG-RFI-008712 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-09 | RDSBIM-TRANSMIT-000140 | NA | Trade Partner | LINDRUM ¦ LEVEL 09 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-01-12 |  | 510 | 2026-01-19 |  |  | 2026-01-23 | 2026-01-23 | KPTG-SADV-002724 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-02 | ECBS-TRANSMIT-000057 | NA | Trade Partner | Re: Fan Wall Unit Steel- Revised Drawing IFC (Batch 2: 47 drawings) | 47 | 0 | 0 | NA | REJECTED | [5 empty] | DUE TO INCOORECT TITLE MENTIONED ON SUBMISSION |  | 2026-07-02 | KPTG-RFI-008720 | Closed | 47 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-02 | Tradetec-TRANSMIT-000475 | NA | Trade Partner | IFA - Stage 4 - LVP50 to 55 - #3747 | 6 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 3747 | 2026-07-23 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-019794 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-02 | PROLMC-TRANSMIT-000037 | NA | Trade Partner | Re Proline Shop drawing details Dog boxes Door hoods and Gland plates | 5 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 3752 | 2026-07-16 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-019719 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-02 | Endfire-TRANSMIT-000081 | NA | Trade Partner | Water Mist Layout Level 4 and 5 IFC Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1300 | 2026-07-06 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-004064 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-02 | ZIA-TRANSMIT-000068 | NA | Trade Partner | CSMS - Cx L3 Test Documents | 0 | 3 | 0 | KPTG-TRANSMIT-004028 | APPROVED | 2026-07-06 | WF-001142 | NA | 2026-07-09 |  | clarification from ibrahim | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-004145 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-02 | SKS Tech-TRANSMIT-000194 | NA | Trade Partner | HV POWER SYSTEMS AND PROTECTION RELAY FOR CONSTRUCTION | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | FC doc send to all parties |  | 2026-07-02 | KPTG-TRANSMIT-004029 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-02 | KPTG-TRANSMIT-004027 | NA | Client | Workstation Desk D2 | 0 | 1 | 0 | NA | APPROVED | 2026-07-02 | WF-001138 | NA | 2026-07-08 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-02 | Stowe-A-TRANSMIT-000633 | NA | Trade Partner | Stowe - Drawing update - As Built | 2 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 4343 | 2026-07-07 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-019499 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-02 | Schindle-TRANSMIT-000031 | NA | Trade Partner | M3 S2 - Schindler - O & M Manual | 0 | 1 | 0 | NA | APPROVED | 2026-07-02 | WF-006245 | NA | 2026-07-10 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-019612 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-02 | PTA-TRANSMIT-000016-DRG | NA | Consultant | PTA Arch Documentation issued_Pdf - 20260701 | 178 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 313 | 2026-07-10 |  | 63 drawing submitted02-07-2026, remaining are already submitted | 2026-07-07 | 2026-07-07 | NA | Closed | 63 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-13 | Entire M-TRANSMIT-000029 | NA | Trade Partner | Damper Technical Data Rev 3 Issued for approval | 0 | 1 | 0 | NA | APPROVED | 2026-01-13 | WF-003757 |  | 2026-01-29 |  | The register has been updated. If any further action is required, the coordinator will inform. |  | 2026-01-14 | KPTG-TRANSMIT-011425 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-02 | PTA-TRANSMIT-000016-SCH | NA | Consultant | PTA Arch Documentation issued_Pdf - 20260701 | 0 | 5 | 0 | NA | APPROVED | 2026-07-02 | NA | 315 | 2026-07-10 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-000477 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-02 | OveArup-TRANSMIT-000014 | NA | Consultant | Stage 6 Fire Engineering Brief | 0 | 1 | 0 | NA | APPROVED | 2026-07-02 | NA | 312 | 2026-07-10 |  | Voided requested by will |  | 2026-07-02 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-02 | Baigents-TRANSMIT-000010 | NA | Trade Partner | Remaining Block 01 Precast Beams IFA | 112 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 317 | 2026-07-10 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-000515 | Closed | 112 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-02 | RDSBIM-TRANSMIT-000217 | NA | Trade Partner | LINDRUM ¦ LEVEL 10 UPPER TERRACE CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 683 | 2026-07-07 |  |  | 2026-07-22 | 2026-07-22 | KPTG-SADV-005059 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-02 | INDS-TRANSMIT-000045 | NA | Trade Partner | Wet Fire - Ground & Mezzanine - Amended as per Arch changes | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  | 2026-07-02 | 2026-07-02 | KPTG-SADV-004768 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-02 | IGS--TRANSMIT-000039 | NA | Consultant | Revised Fire Services Layouts | 13 | 0 | 0 | KPTG-IntCorr-001147 | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001147 - REQUESTED GUIDANCE, BUT NO RESPONANCE KPTG-SADV-004776 - revision,date ,tittle are incorrect | 2026-07-03 | 2026-07-03 | KPTG-SADV-004776 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-02 | KETE-TRANSMIT-000139 | NA | Trade Partner | GL04 sample form updated | 0 | 1 | 0 | KPTG-IntCorr-001148 | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-001148 - REQUESTED GUIDANCE, BUT NO RESPONSE RECEIVED YET. KPTG-SADV-004792 - tittle,revision,rev date are incorrect. | 2026-07-06 | 2026-07-06 | KPTG-SADV-004792 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-02 | KETE-TRANSMIT-000140 | NA | Trade Partner | Kete - Pigtails for Facade Access | 5 | 0 | 0 | KPTG-IntCorr-001149 | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-001149 - REQUESTED GUIDANCE, BUT NO RESPONSE RECEIVED YET. KPTG-SADV-004793 - TITTLE INCORRECT. | 2026-07-06 | 2026-07-06 | KPTG-SADV-004793 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-02 | KETE-TRANSMIT-000141 | NA | Trade Partner | Kete - Updated Elevation to incorporate Mech Duct - Builder's Work | 3 | 0 | 0 | KPTG-IntCorr-001150 | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001158 - as per direction from ashlin,we only update register and transmit to all. | 2026-07-06 | 2026-07-06 | KPTG-IntCorr-001158 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | ASV-TRANSMIT-000074 | NA | Trade Partner | Stage 9 Loading Dock Trench Grate & Frame | 0 | 1 | 0 | NA | APPROVED | 2026-07-02 | WF-001124 | NA | 2026-07-15 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-005257 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-02 | Endfire-TRANSMIT-000044 | NA | Trade Partner | Dry Fire Layout - Level 1 | 1 | 0 | 0 | NA | APPROVED | 2025-12-02 | NA | 673 | 2025-12-08 |  |  | 2025-12-17 | 2025-12-18 | KPTG-TRANSMIT-002331 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-13 | Entire M-TRANSMIT-000030 | NA | Trade Partner | Security Grilles Technical Data issued for approval | 0 | 1 | 0 | NA | APPROVED | 2026-01-13 | WF-003758 / WF-003806 |  | 2026-01-28 |  | The workflow has been restarted as per requested by Kian - 15/1/2026 - WF-003806 |  | 2026-01-14 | KPTG-TRANSMIT-011424 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | ELLISAIR-TRANSMIT-000102 | NA | Trade Partner | Revised Level 1 Zone 3 and 4 Duct & Pipe layout drawings issued for Approval | 2 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 1294 | 2026-07-09 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-005517 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | BTBM-TRANSMIT-000003 | NA | Trade Partner | Better Built Masonary - Technical Data Submission | 0 | 4 | 0 | NA | APPROVED | 2026-07-02 | WF-001113 | NA | 2026-07-08 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-005614 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-02 | L.E.S.-TRANSMIT-000021 | NA | Trade Partner | Updates internal lighting tech data sheets for review | 0 | 1 | 0 | NA | REJECTED | [5 empty] | document numbering error, REJECTED : KPTG-TRANSMIT-002643 |  | 2026-07-02 | KPTG-TRANSMIT-002643 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-25 | G&CHyd-TRANSMIT-000005 | NA | Trade Partner | HYD Tech Data | 0 | 9 | 0 | NA | APPROVED | 2026-06-25 | WF-000808 | NA | 2026-06-29 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-002656 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-02 | SME-884 | NA | Trade Partner | IFC Door Schedule | 9 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 885 | 2026-07-16 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-003353 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-02 | SME-885 | NA | Trade Partner | APARTMENTS - INTERIOR PLAN DETAILS FACADE 01-02 | 4 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 885 | 2026-07-16 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-003130 | Open | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-02 | PSGANZ-TRANSMIT-000011 | NA | Trade Partner | Fire Detection tech. data submission | 0 | 8 | 0 | NA | APPROVED | 2026-06-02 | WF-000180 | NA | 2026-06-10 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-001001 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-03 | G&CHyd-TRANSMIT-000009 | NA | Trade Partner | Re: HYD Tech Data | 0 | 8 | 0 | NA | REJECTED | [5 empty] | Difference in document number and revision |  | 2026-07-03 | KPTG-TRANSMIT-002671 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-03 | KALLIBRE-TRANSMIT-000025 | NA | Trade Partner | IFA - Extra 7x door frames | 7 | 0 | 0 | NA | APPROVED | 2026-07-03 | WF-000372 | NA | 2026-07-09 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-001069 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-13 | Tradetec-TRANSMIT-000318 | NA | Trade Partner | Stage 4 - IFA Drawing - CP38 | 1 | 0 | 0 | NA | APPROVED | 2026-01-13 |  | 1758 | 2026-01-21 |  |  |  | 2026-02-02 | KPTG-TRANSMIT-012318 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-03 | BIMF-TRANSMIT-000007 | NA | Trade Partner | Level 1 Hydraulic Setout - Building A | 1 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 887 | 2026-07-10 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-03 | PCForm-TRANSMIT-000264 | NA | Trade Partner | Stair Form Fire Rail Sample - attempt 2 | 0 | 1 | 0 | NA | APPROVED | 2026-07-03 | WF-000869 | NA | 2026-07-08 |  |  | 2026-07-07 | 2026-07-08 | KPTG-TRANSMIT-002765 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-03 | EAEGROUP-TRANSMIT-000108 | NA | Trade Partner | O&M Documents for Stage 2 EAE IP68 CCR and IP55 KX Busduct IFI-02 | 0 | 2 | 0 | NA | APPROVED | [5 empty] | For information, updating and distribution only as directed by client. With corrected document number. |  | 2026-07-03 | KPTG-TRANSMIT-019280 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-02 | WAM-TRANSMIT-000820 | NA | Trade Partner | Not in Use document status update | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | NO LONGER IN USE - FORWARDED TO ALL PARTIES - KPTG-TRANSMIT-002657 |  | 2026-07-03 | KPTG-TRANSMIT-002657 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-03 | Entire M-TRANSMIT-000052 | NA | Trade Partner | Industrial Water System - FOA-2 | 0 | 1 | 0 | NA | APPROVED | 2026-07-03 | WF-000278 | NA | 2026-07-16 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001601 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-03 | JFS-AU-TRANSMIT-000002 | NA | Consultant | Facade Performance Specification | 0 | 1 | 0 | NA | APPROVED | 2026-07-03 | NA | 293 | 2026-07-10 |  | Received last night | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-000231 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-03 | Entire M-TRANSMIT-000053 | NA | Trade Partner | BMS Points List - Resubmitted | 0 | 1 | 0 | NA | APPROVED | 2026-07-03 | WF-000279 | NA | 2026-07-16 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-001204 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-03 | JFS-AU-TRANSMIT-000002 | NA | Consultant | SME - REVIEW - Facade Performance Specification | 0 | 1 | 0 | NA | APPROVED | 2026-07-03 | NA | 294 | 2026-07-10 |  | SME REVIEW | 2026-07-16 | 2026-07-16 | KPTG-IntCorr-000234 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-03 | RDSBIM-TRANSMIT-000218 | NA | Trade Partner | LINDRUM ¦ LEVEL 11 TO LEVEL 27 & ROOF COREWALL CONCRETE PROFILE | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001151 - As per direction from Ashlin, we only update register and transmit out to everyone. | 2026-07-03 | 2026-07-03 | KPTG-IntCorr-001151 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-13 | ADP-TRANSMIT-000150 | NA | Consultant | S4 ¦ ADP MEL4780 - Battery Room Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-01-14 |  | 1767 /1768 | 2026-01-18 |  | The register has been updated. If any further action is required, the coordinator will inform. -KPTG-TRANSMIT-011402 |  |  | KPTG-TRANSMIT-012072 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-03 | JCBa-TRANSMIT-000149 | NA | Consultant | Updated Structural Setout Plans: IFC | 31 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to difference in revision number - DRAFT-009295 |  | 2026-07-03 | DRAFT-009295 | Closed | 31 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-03 | AdntCons-TRANSMIT-000015 | NA | Trade Partner | Current stage 2 Wet Fire docs | 2 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 358 | 2026-07-13 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-003266 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-03 | JCBa-TRANSMIT-000150 | NA | Consultant | Architectural Documentation - Door Schedule, Door & Window Elevations and Door Frame Profiles | 47 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 1402 | 2026-07-07 |  | Review void as advised by Kapitol DM. Updated GA plans expected. | 2026-07-13 | 2026-07-13 | NA | Closed | 47 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-03 | SES AU-TRANSMIT-000074 | NA | Trade Partner | SECURITY - Cabling Diagram - IFA | 2 | 0 | 0 | NA | APPROVED | 2026-07-03 | WF-000373 | NA | 2026-07-06 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-001020 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-03 | D&E-TRANSMIT-000888 | NA | Trade Partner | NXM3S4 - Upper Roof / Roof & Level 1 - CHW Pipe Layout Zones - Issued For Construction | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For Distribution |  | 2026-07-03 | KPTG-TRANSMIT-019283 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-02 | RDSBIM-TRANSMIT-000079 | NA | Trade Partner | 671CHP ¦ GROUND LEVEL TO ROOF CORE WALL LAYOUT AND ELEVATION | 8 | 0 | 0 | NA | APPROVED | 2026-07-02 | NA | 609 | 2026-07-09 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001254 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-02 | B Smart-TRANSMIT-000090 | NA | Consultant | CPP GF-L2 update | 3 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 606 | 2026-07-06 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-001300 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-02 | LVPG-TRANSMIT-000035 | NA | Trade Partner | LVPG - Stormwater Tech Data Submittals | 0 | 2 | 0 | NA | APPROVED | 2026-07-02 | WF-000676 |  | 2026-07-09 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-25 | Tradetec-TRANSMIT-000464 | NA | Trade Partner | Stage 4 - Pit IFA's - HVP23,24,25 | 3 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 3782 | 2026-07-15 |  |  |  | 2026-07-28 | KPTG-TRANSMIT-020089 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-02 | Auscool-TRANSMIT-000044 | NA | Trade Partner | Samples Submission | 0 | 9 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-07-02 | -DRAFT-009273 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-13 | Auspan-TRANSMIT-000037 | NA | Trade Partner | GF shop drawings issued for construction | 2 | 0 | 0 | NA | APPROVED | 2026-01-13 |  | 511 | 2026-01-20 |  |  | 2026-01-16 | 2026-01-16 | KPTG-SADV-002637 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-03 | Stowe-A-TRANSMIT-000634 | NA | Trade Partner | Stowe - Drawing Update - As built - DH Tiers 3 & 4 | 12 | 0 | 0 | NA | REJECTED | [5 empty] | Same pack and same revision resubmitted again. |  | 2026-07-03 | KPTG-SADV-006378 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-03 | KPTG-TRANSMIT-019274 | NA | Trade Partner | Proline Remaining Tech data | 0 | 3 | 0 | NA | APPROVED | 2026-07-03 | WF-006248 | NA | 2026-07-31 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-03 | Tradetec-TRANSMIT-000476 | NA | Trade Partner | IFA - Stage 4 - HVP20, HVP22, HVP26 | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision, title is within the document number |  | 2026-07-03 | ⁠KPTG-RFI-008745 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-03 | D&E-TRANSMIT-000889 | NA | Trade Partner | NXM3S4 - Roof Level Switchroom - Mechanical Duct Layout Zones - Issued For Construction | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-03 | KPTG-TRANSMIT-019297 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-03 | Altaire-TRANSMIT-000017 | NA | Trade Partner | M2 Stage 9-11 - Altaire Technical Data Transmittal (FC-A) (2) | 0 | 28 | 0 | NA | APPROVED | [5 empty] | IFC Tech Data, No review required, updated register & distributed |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-03 | RDSBIM-TRANSMIT-000286 | NA | Trade Partner | NXM3S4 ¦ GROUND FLOOR-C-G-023 CLEANERS-FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 3764 | 2026-07-08 |  |  |  | 2026-08-31 | KPTG-TRANSMIT-021131 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-03 | D&E-TRANSMIT-000890 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - GROUND FLOOR - DATA HALL 3 SFN UNION & BOLT TORQUE MAP | 1 | 0 | 0 | NA | REJECTED | [5 empty] | FC submission without FOA. |  | 2026-07-03 | KPTG-SADV-006387 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-03 | Entire M-TRANSMIT-000054 | NA | Trade Partner | Security Grille Detail FOA | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document number, revision and revision date. |  | 2026-07-03 | KPTG-SADV-000821 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-03 | ccair-TRANSMIT-000004 | NA | Trade Partner | 20260703_Mechanical Penetration drawings for review GF to Level 4 | 6 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 889 | 2026-07-10 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-003096 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-03 | Nilsen3-TRANSMIT-000057 | NA | Trade Partner | Nilsen samples IFC | 0 | 11 | 0 | NA | REJECTED | [5 empty] | Difference in status |  | 2026-07-03 | KPTG-SADV-005847 | Closed | 11 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-13 | Auspan-TRANSMIT-000038 | NA | Trade Partner | Revised GF shop drawings issued for approval | 7 | 0 | 0 | NA | APPROVED | 2026-01-13 |  | 512 | 2026-01-20 |  |  | 2026-01-20 | 2026-01-20 | KPTG-SADV-002675 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-16 | ZLH P/L-TRANSMIT-000004 | NA | Trade Partner | Re: Proposed Material - Design & Sample - ZLH | 0 | 2 | 0 | NA | APPROVED | 2026-06-16 | WF-000213 | NA | 2026-06-25 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-001010 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-03 | Civilex-TRANSMIT-000278 | NA | Trade Partner | Stage 2 - sample submission - Size 10mm Type N+25% Rap Asphalt | 0 | 1 | 0 | NA | APPROVED | 2026-07-03 | WF-006251 | NA | 2026-07-09 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-019343 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-03 | Altaire-TRANSMIT-000018 | NA | Trade Partner | NEXTDC M2S11 - Shop Drawings (FC-A) (1) | 4 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 1312 | 2026-07-10 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-005450 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-03 | Arc Plas-TRANSMIT-000012 | NA | Trade Partner | Plasterboard Samples - Proposed Knauf Systems | 0 | 4 | 0 | NA | APPROVED | 2026-07-03 | WF-001121 | NA | 2026-07-09 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-006377 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-03 | ADP-TRANSMIT-000359 | NA | Consultant | MEL4780 - M3S4 - Updated Electrical Drawings | 4 | 0 | 0 | NA | REJECTED | [5 empty] | incorrect document number |  | 2026-07-03 | KPTG-RFI-008751 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-03 | ZIA-TRANSMIT-000016 | NA | Trade Partner | Re: M2 Stage 9, 10 and 11 Network Topology | 1 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 1314 | 2026-07-10 |  | Workflow has been terminated as requested by Project Coordinator upon request from Trade partner |  | 2026-07-30 | ZIA-GCOR-000009 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-03 | Jangho-TRANSMIT-000218 | NA | Trade Partner | Re: FT13 System Concept Drawing_Rev 02_PDF_For Approval | 18 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 892 | 2026-07-10 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-002993 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-03 | CDL-TRANSMIT-000041 | NA | Trade Partner | KPA Stage 2 Documentation | 5 | 5 | 0 | NA | REJECTED | [5 empty] | Document Numbering is incorrect, requested to resubmit: KPTG-SADV-005159 |  | 2026-07-03 | KPTG-SADV-005159 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-03 | ADP-TRANSMIT-000099 | NA | Trade Partner | ADP MEL4680 - Comms Updated Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 312 | 2026-07-08 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-001040 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-13 | Altaire-TRANSMIT-000054 / Altaire-TRANSMIT-000049 | NA | Trade Partner | Re: NEXTDC M3S4 Dry Fire Tech Data (For Approval) | 0 | 28 | 0 | NA | APPROVED | 2026-01-13 | WF-003760 |  | 2026-02-03 |  |  |  |  | KPTG-TRANSMIT-013064 | Closed | 28 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-03 | KPTG-TRANSMIT-019308 | NA | Trade Partner | STAGE 4 HDR DOCUMENTS | 683 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As requested by Finaly the drawings have been transmitted to Survey Connect |  | 2026-07-03 | KPTG-TRANSMIT-019308 | Closed | 683 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-03 | Highbu-TRANSMIT-000056 | NA | Trade Partner | Highbu-TRANSMIT-000056 | 5 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004782 - status and revision are different inside and out are different. | 2026-07-03 | 2026-07-03 | KPTG-SADV-004782 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-03 | D&E-TRANSMIT-000891 | NA | Trade Partner | NXM3S2 - Level 01 - Mechanical Duct Layout - Zone 3 & 4 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 4345 | 2026-07-16 |  | Also note that as requested by William and Confirmed by Jan, revised D&E drawing with adjustment to as-built are ok to supersede the previous FC drawings which are rejected in status, are acceptable. | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-019933 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-03 | SMEPS-SUBADVICE-000324 | NA | Trade Partner | Request for Fibre and Copper Test Results | 0 | 2 | 0 | NA | APPROVED | 2026-07-03 | WF - 000519 | NA | 2026-07-09 |  | WF Terminated. file superseded. | 2026-07-06 | 2026-07-06 |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-03 | DLTS-TRANSMIT-000006 | NA | Trade Partner | Fire Room-IFA Issue | 21 | 0 | 0 | NA | APPROVED | 2026-07-03 | WF-006253 | NA | 2026-07-22 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-03 | M.S.-TRANSMIT-000019 | NA | Trade Partner | Revised Shop Drawings for Approval | 24 | 0 | 0 | NA | REJECTED | [5 empty] | Originator code error |  | 2026-07-03 | KPTG-TRANSMIT-001377 | Closed | 24 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-03 | TTW-TRANSMIT-000171 | NA | Consultant | BP4 Structural Drawing Issue | 6 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 894 | 2026-07-07 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-002746 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-03 | Leemark-TRANSMIT-000049 | NA | Trade Partner | MCC - Fire Proection Layout - GROUND LEVEL- IFA | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status inside the drawing and Aconex seem different |  | 2026-07-03 | KPTG-TRANSMIT-001378 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-03 | RDSBIM-TRANSMIT-000223 | NA | Trade Partner | 511SRC ¦ BATHROOM TYPE BLB-01 FINISHES LAYOUT & ELEVATIONS (TYPICAL) | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Distribution only. |  | 2026-07-03 | KPTG-TRANSMIT-003111 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-03 | WAM-TRANSMIT-000821 | NA | Consultant | A71_Internal Glazing Elevation | 1 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 896 | 2026-07-06 |  |  | 2026-07-06 | 2026-07-07 | KPTG-TRANSMIT-002723 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-01-13 | KEECEPRO-TRANSMIT-000011 | NA | Trade Partner | Re Inground Shop Drawings - Amended - ELC | 5 | 0 | 0 | NA | APPROVED |  |  | 266/267 | 2026-01-19 |  |  |  | 2026-01-16 | DRAFT-008285 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-03 | RDSBIM-TRANSMIT-000224 | NA | Trade Partner | 511SRC ¦ BATHROOM TYPE BB-01 FINISHES LAYOUT & ELEVATIONS (TYPICAL) | 2 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | NA |  |  | IFC- dictribution only. |  | 2026-07-03 | KPTG-TRANSMIT-003112 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-03 | ZLH P/L-TRANSMIT-000014 | NA | Trade Partner | Proposed Material - Design & Sample - ZLH | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Same document, Same revision is already under review. Hence considering the transmittal as closed. |  | 2026-07-03 | KPTG-TRANSMIT-001016 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-03 | 4DW-TRANSMIT-000191 | NA | Consultant | Structural Documentation - Retention updates | 5 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 362 | 2026-07-08 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-003092 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-03 | Nilsen3-TRANSMIT-000059 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 3 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 1319 | 2026-07-10 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-005764 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-03 | RED Fire-TRANSMIT-000011 | NA | Trade Partner | Fire Engineering Report - Version 2 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Difference in status |  | 2026-07-03 | KPTG-TRANSMIT-002681 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-03 | Nilsen3-TRANSMIT-000059 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 1320 | 2026-07-10 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-006370 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-03 | M.S.-TRANSMIT-000021 | NA | Trade Partner | Revised Shop Drawings for Approval | 32 | 0 | 0 | Need clarification - KPTG-IntCorr-003390 | APPROVED | [5 empty] | Originator code changed, Document recieved under this transmittal will be resubmitted with new code - KPTG-SADV-005782 |  | 2026-07-08 | KPTG-SADV-005782 | Closed | 32 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-03 | RDSBIM-TRANSMIT-000013 | NA | Trade Partner | NXGE01 ¦ GROUND FLOOR PARTITION WALL PLAN AND ELEVATIONS | 5 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 314 | 2026-07-09 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001069 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-03 | CEDWA-TRANSMIT-000011 | NA | Consultant | Updated Civil Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 1302 | 2026-07-07 |  |  | 2026-08-05 | 2026-08-06 | KPTG-TRANSMIT-004208 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-03 | Entire M-TRANSMIT-000055 | NA | Trade Partner | FOA-3 = VSD Submission | 0 | 1 | 0 | NA | APPROVED | 2026-07-03 | WF-000282 | NA | 2026-07-16 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-01-12 | SMPS-TRANSMIT-000100 | NA | Trade Partner | EMIC As-Built | 18 | 0 | 0 | NA | APPROVED | 2026-01-13 |  | 268 | 2026-01-19 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-03 | D&E-TRANSMIT-000893 | NA | Trade Partner | NXM3S4 - Level 1 - CHW Pipe Layout - Zone 10 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-03 | KPTG-TRANSMIT-019312 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-03 | D&E-TRANSMIT-000892 | NA | Trade Partner | NXM3S4 - Upper Roof Level - CHW & CCW Pipe Layout Zones - Issued For Construction | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-03 | KPTG-TRANSMIT-019313 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-03 | Auspan-TRANSMIT-000460 | NA | Trade Partner | Precast shop drawings for approval. Levels 5, 6 | 35 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 1406 | 2026-07-10 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003102 | Closed | 35 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-03 | KPTG-TRANSMIT-000981 | NA | Trade Partner | Startup and Energisation Plans - issued for approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-26 | WF - 000471 | NA | 2026-07-03 |  | NA | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-001067 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-03 | Carr-TRANSMIT-000075 | NA | Consultant | FFE and Finishes Schedules | 0 | 2 | 0 | NA | APPROVED | 2026-07-03 | NA | 298 | 2026-07-10 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-03 | Carr-TRANSMIT-000076 | NA | Consultant | Wall and Floor Finishes Details | 4 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 297 | 2026-07-10 |  | This workflow has been voided due to revisions made to some of the associated drawings from Carr. The remaining drawings will be re-initiated separately under a new workflow. |  | 2026-08-27 | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-03 | Carr-TRANSMIT-000077 | NA | Consultant | Revit Models for Information | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Revit Models for information only |  | 2026-07-03 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-03 | HDRAus-TRANSMIT-000521 | NA | Consultant | Re: M3 Stage 4 - Document upload - PDF and CAD | 11 | 0 | 0 | NA | REJECTED | [5 empty] | The IFA for the following document has not been received for review. |  | 2026-07-03 | M3-ARC-HDR-DRG-C-0400-1983 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-03 | HDRAus-TRANSMIT-000520 | NA | Consultant | M3 SW - Document upload - PDF and CAD | 2 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 4348 | 2026-07-07 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-020797 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-03 | VERTIV-TRANSMIT-000042 | NA | Trade Partner | Next DC GE01 _ Technical Data _ Cooling Load Calculation & CFD Analysis Report (FOA-2) | 0 | 1 | 0 | NA | APPROVED | 2026-07-03 | WF-000283 | NA | 2026-07-16 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001594 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-01-12 | SMPS-TRANSMIT-000099 | NA | Trade Partner | PH2 and B08 As Builts | 25 | 0 | 0 | NA | APPROVED | 2026-01-13 |  | 269 | 2026-01-19 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-03 | ADP-TRANSMIT-000101 | NA | Consultant | ADP MEL4680 - Fire Services Specification | 0 | 1 | 0 | NA | APPROVED | 2026-07-03 | NA | 316 | 2026-07-07 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-001045 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-03 | ADP-TRANSMIT-000362 | NA | Consultant | Re: ADP - M3S4 Load Calculations Report | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect revision number |  | 2026-07-03 | KPTG-DA-007396 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-03 | Altaire-TRANSMIT-000120 | NA | Trade Partner | Re: DHB5 and DHB6 As-Built Revision Post Cintoo Alignment | 1 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 4350 | 2026-07-10 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-019529 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-03 | EAEGROUP-TRANSMIT-000109 | NA | Trade Partner | EAEGROUP-TRANSMIT-000109 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong attachment |  | 2026-07-03 | KPTG-TRANSMIT-019306 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-03 | IGS--TRANSMIT-000040 | NA | Consultant | Revised Level 1 Lighting Layout | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004789 -revision incorrect | 2026-07-03 | 2026-07-03 | KPTG-SADV-004789 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-03 | SMEPS-TRANSMIT-000331 | NA | Trade Partner | SME - IFC Documentation | 6 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 3759 | 2026-07-16 |  |  |  |  | NA | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-03 | SMEPS-TRANSMIT-000332 | NA | Trade Partner | SME - IFC Documentation | 6 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 3761 | 2026-07-23 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-021041 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-03 | SMEPS-TRANSMIT-000334 | NA | Trade Partner | SME - IFC Documentation | 4 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 3763 | 2026-07-16 |  | Workflow terminated, Instructed by Damian |  | 2026-07-23 | NA | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-03 | Tradetec-TRANSMIT-000464 | NA | Trade Partner | Stage 4 - Pit IFA's - HVP23,24,25 | 3 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 3768 | 2026-07-16 |  | The WF has been changed |  |  |  | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-03 | ADP-TRANSMIT-000361 | NA | Consultant | M3S4 - Updated Electrical & FID Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 3788,3790 | 2026-07-16 |  | 2 ELC AND 2FID |  | 2026-07-28 | KPTG-TRANSMIT-020093 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-13 | RDSBIM-TRANSMIT-000011 | NA | Trade Partner | GREYSTAR ¦ GROUND FLOOR CONCRETE PROFILE KEY PLAN AND SECTION | 10 | 0 | 0 | NA | APPROVED | 2026-01-13 | WF-000122 | 238 | 2026-01-16 |  |  |  | 2026-02-19 | KPTG-TRANSMIT-000663 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-03 | ADP-TRANSMIT-000360 | NA | Consultant | Re: ADP - CAN - Fire Water Storage | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect revision number |  | 2026-07-03 | KPTG-TRANSMIT-019316 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-03 | PROLMC-TRANSMIT-000038 | NA | Trade Partner | Proline Shop drawing Switch Room Door Flashing and Pressure Flashing Detail | 2 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 3776 | 2026-07-16 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-019786 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-03 | Tradetec-TRANSMIT-000477 | NA | Trade Partner | IFA - Stage 4 - HVP20, HVP22, HVP26 | 3 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 3783 | 2026-07-17 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-020097 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-03 | SMEPS-TRANSMIT-000333 | NA | Trade Partner | SME - IFA Documentation | 1 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 3779 | 2026-07-08 |  |  |  | 2026-08-04 | KPTG-TRANSMIT-020349 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-03 | RDSBIM-TRANSMIT-000285 | NA | Trade Partner | NXM3S4 ¦ LEVEL 01-C-1-020 CLEANER FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 3781 | 2026-07-08 |  |  |  | 2026-08-31 | KPTG-TRANSMIT-021130 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-03 | OveArup-TRANSMIT-000014-DES | NA | Consultant | Stage 6 Fire Engineering Brief | 0 | 1 | 0 | NA | APPROVED | 2026-07-03 | NA | 318 | 2026-07-13 |  | Actual submission 02-07-2026 | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-000663 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-03 | 4DW-TRANSMIT-000060 | NA | Consultant | Block 2 - Precast walls, Stair cores, Lift cores, Foundations issued with Certification updates. | 16 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 321 | 2026-07-13 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-000782 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-03 | Baigents-TRANSMIT-000006 | NA | Trade Partner | Block 1 Ground Precast Panels -Issued for Approval | 18 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 319 | 2026-07-13 |  | Actual submission 16-06-2026 | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-000528 | Closed | 18 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-03 | ACCCA-TRANSMIT-000009 | NA | Trade Partner | STORMWATER PITS FOR APPROVAL | 8 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-07-03 | KPTG-TRANSMIT-000440 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-03 | OveArup-TRANSMIT-000015 | NA | Consultant | Stage 6 A2G2 Application Cover Letter | 0 | 1 | 0 | KPTG-IntCorr-000263 | APPROVED |  | NA | NA |  |  | Updated in Forma and distribution |  | 2026-07-07 | KPTG-TRANSMIT-000464 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-02 | Endfire-TRANSMIT-000045 | NA | Trade Partner | Dry Fire Layout_Level 2 | 1 | 0 | 0 | NA | APPROVED | 2025-12-02 | NA | 673 | 2025-12-08 |  |  | 2025-12-17 | 2025-12-18 | KPTG-TRANSMIT-002331 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-13 | StantecA-TRANSMIT-000292 | NA | Consultant | Updated IFC Documents - Hydraulic - Stantec | 92 | 0 | 0 | NA | APPROVED | 2026-01-13 | WF-000123 | 240 | 2026-01-16 |  |  |  | 2026-01-22 | KPTG-TRANSMIT-000454 | Closed | 92 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-03 | Baigents-TRANSMIT-000011 | NA | Trade Partner | STAGE 06 SPEED PANEL MODEL FOA-1 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Model |  | 2026-07-03 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-03 | ACCCA-TRANSMIT-000010 | NA | Trade Partner | Electrical Pit Approval | 6 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 323 | 2026-07-13 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-03 | 4DW-TRANSMIT-000061 | NA | Consultant | Issued with Certification updates: Precast walls, NLB walls & Foundations - Block 2 | 18 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 325 | 2026-07-13 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-03 | RBG-TRANSMIT-000006 | NA | Trade Partner | Crane Base Drawings IFC | 12 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update register only |  | 2026-07-03 | NA | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-03 | D&E-TRANSMIT-000018 | NA | Trade Partner | ISSUED FOR APPROVAL - CHW & SFN PIPEWORK LAYOUTS | 9 | 0 | 0 | KPTG-IntCorr-000264 | APPROVED | 2026-07-17 | NA | 452 | 2026-07-27 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-03 | 4DW-TRANSMIT-000062 | NA | Consultant | Block 1 - Ground Floor Construction updates. | 6 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 327 | 2026-07-13 |  |  | 2026-07-31 | 2026-08-03 | KPTG-TRANSMIT-000805 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-03 | Auspan-TRANSMIT-000459 | NA | Trade Partner | Re: 1P018 and 1P019 and 2P1001. Update precast shop drawings for construction. | 3 | 0 | 0 | KPTG-IntCorr-000853 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kapitol PC advise - KPTG-IntCorr-000853 (QC done) |  | 2026-07-08 | KPTG-TRANSMIT-002655 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-03 | RDSBIM-TRANSMIT-000079 | NA | Trade Partner | GREYSTAR BASEMENT LEVEL PARTITION WALL | 7 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 1404 | 2026-07-10 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-003332 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-03 | PCForm-TRANSMIT-000079 | NA | Trade Partner | : GF and Level 1 Propping Plans | 6 | 0 | 0 | KPTG-IntCorr-00085 | APPROVED |  | NA | NA |  |  | Waiting for DM advise - KPTG-IntCorr-00085 No action required. -KPTG-DA-001551 |  | 2026-07-08 | KPTG-DA-001551 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-03 | Auspan-TRANSMIT-000461 | NA | Trade Partner | : Precast cast in plate layout levels 3, 4, 5, 6 zone 1, 2 for construction. | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to drawings title issues - DRAFT-009345 |  | 2026-07-03 | DRAFT-009345 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-13 | KPA M&C-TRANSMIT-000011 | NA | Consultant | Typical Site Retention Details | 1 | 0 | 0 | NA | APPROVED | 2026-01-13 | WF-000125 | 245 | 2026-01-16 |  |  |  | 2026-01-16 | KPTG-TRANSMIT-000421 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-03 | Auspan-TRANSMIT-000462 | NA | Trade Partner | Re: Panel 0G3107 – Overflow Setout | 1 | 0 | 0 | KPTG-IntCorr-000854 | APPROVED |  | NA | NA |  |  | Precast IFC - no review, Updated register and transmitted - KPTG-TRANSMIT-002689 |  | 2026-07-09 | KPTG-TRANSMIT-002689 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-03 | Auspan-TRANSMIT-000463 | NA | Trade Partner | : Precast shop drawings for construction. Levels 1, 2 | 4 | 0 | 0 | KPTG-IntCorr-000855 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kapitol PC advise - KPTG-IntCorr-000855 (QC done) 2 are OK to proceed as IFC KPTG-TRANSMIT-002605 2 Rejected as advised by Kapitol PC. KPTG-IntCorr-000862- DRAFT-009404 |  | 2026-07-06 | KPTG-TRANSMIT-002605 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-03 | Auspan-TRANSMIT-000464 | NA | Trade Partner | : Precast shop drawings for construction. 5P2018 | 1 | 0 | 0 | KPTG-IntCorr-000856 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kapitol PC advise - KPTG-IntCorr-000856 (QC done) rejected as advised by Kapitol PC-KPTG-SADV-004086 |  | 2026-08-10 | KPTG-SADV-004086 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-03 | IJF-TRANSMIT-000002 | NA | Trade Partner | Prototype Joinery Drawings for Apartments 4.07 & 4.08 | 27 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect drawing number -KPTG-SADV-002802 |  | 2026-07-03 | KPTG-SADV-002802 | Closed | 27 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-03 | IJF-TRANSMIT-000003 | NA | Trade Partner | Prototype Joinery Drawings for Apartments 4.07 & 4.08 | 27 | 0 | 0 | NA | REJECTED | [5 empty] | No Action required; drawing will be superseded due to incorrect drawing number and as dicussed with Clare Lu -KPTG-IntCorr-000877 |  | 2026-07-03 | KPTG-IntCorr-000877 | Closed | 27 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-03 | ZIA-TRANSMIT-000067 | NA | Trade Partner | CSMS - Layer 2 TOR Network Switch | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | fc - send to all parties - KPTG-TRANSMIT-004034 |  | 2026-07-03 | KPTG-TRANSMIT-004034 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-03 | DLTS-TRANSMIT-000050 | NA | Trade Partner | S10-North&South Eave Gutter-IFA Issue | 45 | 0 | 0 | NA | APPROVED | 2026-07-03 | WF-001117 | NA | 2026-07-14 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-005469 | Closed | 45 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-03 | DLTS-TRANSMIT-000051 | NA | Trade Partner | S11-Cooling Tower Grating-IFA Issue | 128 | 0 | 0 | NA | APPROVED | 2026-07-03 | WF-001118 | NA | 2026-07-14 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-005484 | Closed | 128 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-03 | DLTS-TRANSMIT-000052 | NA | Trade Partner | S11-L2 H Frames-IFA Issue | 32 | 0 | 0 | NA | APPROVED | 2026-07-03 | WF-001130 | NA | 2026-07-14 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-005374 | Closed | 32 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-13 | KPTG-TRANSMIT-011377 | NA | Trade Partner | Tremco Tremproof 250GC | 1 | 0 | 0 | NA | APPROVED | 2026-01-13 | WF-003759 |  | 2026-01-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-03 | Nilsen3-TRANSMIT-000058 | NA | Trade Partner | Nilsen Sample submissions #8 | 0 | 1 | 0 | NA | APPROVED | 2026-07-03 | WF-001122 | NA | 2026-07-15 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-005594 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-03 | M.S.-TRANSMIT-000079 | NA | Trade Partner | Update J50 Reception Shop drawings | 5 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 360 | 2026-07-07 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-003063 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-03 | ARCH-TRANSMIT-000163 | NA | Consultant | MLC - SPR - ISC - Capping Beam update | 7 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 364 | 2026-07-08 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-003049 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-03 | Jangho-TRANSMIT-000219 | NA | Trade Partner | Structural Calculation For FT13 System Concept Drawing_Rev 02 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Difference in Revision |  | 2026-07-03 | KPTG-TRANSMIT-002686 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-03 | HVHD-TRANSMIT-000016 | NA | Trade Partner | NCC Section J Report | 0 | 1 | 0 | NA | APPROVED | 2026-07-03 | WF-000874 | NA | 2026-07-06 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002857 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-03 | KPTG-SADV-005639 | NA | Trade Partner | M2 S9-11 Generator Enclosure Documents | 5 | 0 | 0 | NA | APPROVED | 2026-07-03 | WF-001133 | NA | 2026-07-14 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-006151 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-03 | SMEPS-TRANSMIT-000061 | NA | Trade Partner | STAGE 9-11 Overall Site Earthing & Lightning Protection Layout (FC-1) | 1 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 1310 | 2026-07-08 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-005508 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-03 | SMEPS-TRANSMIT-000062 | NA | Trade Partner | SINGLE OUTPUT LV SINGLE LINE DIAGRAM STRING MA - PF | 18 | 0 | 0 | NA | APPROVED | 2026-07-03 | NA | 1317 | 2026-07-10 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-005894 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-06 | Hames-TRANSMIT-000125 | NA | Consultant | Issue of Certifier Updates | 15 | 0 | 0 | NA | APPROVED | 2026-06-22 | NA | 1290 | 2026-06-24 |  |  | 2026-08-05 | 2026-08-06 | KPTG-TRANSMIT-004228 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-04 | Hames-TRANSMIT-000160 | NA | Consultant | PHASE 1 - FIRE TANK HARDSTAND & STAIR 05 | 8 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 1281 | 2026-06-08 |  |  | 2026-08-05 | 2026-08-06 | KPTG-TRANSMIT-004236 | Closed | 8 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-12 | ARCST-TRANSMIT-000177 | NA | Trade Partner | Stage 4 - C3 Gantry Roof`& Secondary Steel - Issued for Approval | 124 | 0 | 0 | NA | APPROVED | 2026-01-12 | WF-003748 | NA | 2026-02-02 |  |  | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-013851 | Closed | 124 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-06 | Nilsen3-TRANSMIT-000060 | NA | Trade Partner | Nilsen Sample submissions #9 | 0 | 5 | 0 | NA | APPROVED | 2026-07-06 | WF-001136 | NA | 2026-07-15 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-005306 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-06 | WAM-TRANSMIT-000822 | NA | Consultant | WAM ARCH - Area Sheets Updates with Notes | 2 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 898 | 2026-07-09 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-003660 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-06 | Highbu-TRANSMIT-000155 | NA | Trade Partner | Revised drawing | 1 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 365 | 2026-07-10 |  | ACC WORKFLOW-365 TERMINATED: KPTG-SADV-005702 |  | 2026-08-04 | KPTG-SADV-005702 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-06 | Entire M-TRANSMIT-000056 | NA | Trade Partner | Ground floor - Mechanical Ductwork & Equipment Layouts - FOA-01 | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Title is mismatched in Aconex submission for all drawings. Issue with revision number and revision history. |  | 2026-07-06 | KPTG-SADV-000827 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-06 | Appselec-TRANSMIT-000135 | NA | Trade Partner | EzyStrut Trunking Tech Data IFC | 0 | 1 | 0 | NA | APPROVED | 2026-07-06 | WF-000374 | NA | 2026-07-09 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001035 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-06 | Appselec-TRANSMIT-000136 | NA | Trade Partner | MEL11C45 - Electrical Shop Drawings Update re-IFC | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: As per the Direction from Mr. Jack cassidy, Drawings need updation:KPTG-SADV-001383 |  | 2026-07-06 | KPTG-SADV-001383 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-06 | Appselec-TRANSMIT-000137 | NA | Trade Partner | MEL11C45 - Electrical Shop Drawings Update re-IFC | 3 | 0 | 0 | NA | APPROVED | 2026-07-06 | WF-000377 | NA | 2026-07-09 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-001051 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-06 | Auspan-TRANSMIT-000407 | NA | Trade Partner | Update panel 2P342 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Update register and transmit - KPTG-TRANSMIT-002587 |  | 2026-07-06 | KPTG-TRANSMIT-002587 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-06 | JCBa-TRANSMIT-000151 | NA | Consultant | Fire Safety Certificate Drawings: IFC | 7 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 1411 | 2026-07-08 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002709 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-06 | WilsonPD-TRANSMIT-000009 | NA | Trade Partner | MEL11 Tank - Wilson Tech Data for Review | 0 | 8 | 0 | NA | REJECTED | [5 empty] | Document numbering are incorrect, requested to resubmit:KPTG-IntCorr-000658 |  | 2026-07-06 | KPTG-IntCorr-000658 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-12 | ARCST-TRANSMIT-000175 | NA | Trade Partner | C1 Roof Walkway HD Bolts - Issued for Review | 5 | 0 | 0 | NA | APPROVED | 2026-01-12 | WF-003747 |  | 2026-02-02 |  |  |  | 2026-02-19 | KPTG-TRANSMIT-013204 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-06 | ACCCA-TRANSMIT-000008-DRG | NA | Trade Partner | Electrical Pit Approval | 8 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 329 | 2026-07-14 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-000476 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-06 | Entire M-TRANSMIT-000057 | NA | Trade Partner | Ground Floor - Pipework Layouts - FOA-1 | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with revision number and revision history. |  | 2026-07-06 | KPTG-SADV-000830 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-06 | Jangho-TRANSMIT-000230 | NA | Trade Partner | Brick Sample Submission（Tan Brick Option 3） | 0 | 1 | 0 | NA | APPROVED | 2026-07-06 | WF-000879 | NA | 2026-07-22 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-002913 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-06 | Jangho-TRANSMIT-000229 | NA | Trade Partner | Brick Sample Submission（Red Brick Option 4） | 0 | 1 | 0 | NA | APPROVED | 2026-07-06 | WF-000878 | NA | 2026-07-22 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-002912 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-06 | Airpor2-TRANSMIT-000004 | NA | Trade Partner | Rolelr Shutter shop drawing | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Mismatch in title, revision date, history not updated. |  | 2026-07-06 | KPTG-SADV-000829 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-06 | Jangho-TRANSMIT-000227 | NA | Trade Partner | Re: FT07&FT09 PMU Comparison Report | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Difference in revision history box |  | 2026-07-06 | KPTG-TRANSMIT-002718 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-06 | Jangho-TRANSMIT-000226 | NA | Trade Partner | Test proposal for window wall systme of District docklands | 0 | 1 | 0 | NA | APPROVED | 2026-07-06 | WF-000888 | NA | 2026-07-09 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-002802 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-06 | Airpor2-TRANSMIT-000005 | NA | Trade Partner | Roller Shutter Tech Data | 0 | 4 | 0 | NA | REJECTED | [5 empty] | Mismatch in title, revision number, discipline, location not specified. |  | 2026-07-06 | KPTG-SADV-000828 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-06 | Jangho-TRANSMIT-000224 | NA | Trade Partner | Podium Level 1~2 Cast in Channel Shop Drawing_PDF_Rev 03_Review | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Error in status of the documents |  | 2026-07-06 | KPTG-TRANSMIT-002720 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-12 | IVS-TRANSMIT-000310 | NA | Trade Partner | Stage 4 - GF Office Pit (Construction Issue) From Mr Camilo Pinto - Innovis | 4 | 0 | 0 | NA | APPROVED | 2026-01-12 |  | 1752 | 2026-01-15 |  |  |  | 2026-01-16 | KPTG-TRANSMIT-011527 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-20 | SKS Tech-TRANSMIT-000186 | NA | Trade Partner | for construction status | 2 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 1305 | 2026-07-08 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-004080 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-06 | Jangho-TRANSMIT-000223 | NA | Trade Partner | Re: Podium Level 3~5 Cast in Channel Shop Drawing_PDF_Rev 01_Review | 11 | 0 | 0 | NA | REJECTED | [5 empty] | ERROR IN STATUS OF DOCUMENTS |  | 2026-07-06 | KPTG-TRANSMIT-002721 | Closed | 11 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-06 | Jangho-TRANSMIT-000222 | NA | Trade Partner | Structural Calculation For Channel Embedded Calculation 6F~10F_Rev 01 For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-06 | WF-000880 | NA | 2026-07-15 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-002879 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-06 | INTRFRM-TRANSMIT-000094 | NA | Trade Partner | Geelong Edge - Civil Tech Data (Submission 5) | 0 | 1 | 0 | NA | APPROVED | 2026-07-06 | WF-000285 | NA | 2026-07-15 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-001259 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-06 | RDSBIM-TRANSMIT-000287 | NA | Trade Partner | NXM3S4 ¦GROUND FLOOR TO ROOF PRECAST WALL ¦ IFC ¦ FOR SUBMISSION 3785 | 23 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 3786 | 2026-07-09 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-019368 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-06 | Jangho-TRANSMIT-000221 | NA | Trade Partner | Re: Structural Calculation For FT13 System Concept Drawing_Rev 02 | 0 | 1 | 0 | NA | APPROVED | 2026-07-06 | WF-000881 | NA | 2026-07-15 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-002877 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-06 | INDS-TRANSMIT-000044 | NA | Trade Partner | Updated Peno drawings | 4 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 1414 | 2026-07-13 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-002764 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-06 | ELLISAIR-TRANSMIT-000104 | NA | Trade Partner | BMS Graphics - Sample | 0 | 1 | 0 | NA | APPROVED | 2026-07-06 | WF-001139 | NA | 2026-07-16 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-005619 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-04 | KPTG-IntCorr-014279 | NA | Trade Partner | Re: Final (WF-005343) S4 ¦ SAMPLE AND TECH DATA - CONSULTANT REVIEW - FACAD WORKFLOW - as per requested by ned crummy(17-4-2026) | 0 | 1 | 0 | NA | APPROVED | 2026-06-04 | WF-005938 | NA | 2026-07-06 |  | As instructed by Renee | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-019332 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-01-12 | SMPS-TRANSMIT-000098 | NA | Trade Partner | Chamber As Builts | 11 | 0 | 0 | NA | APPROVED | 2026-01-13 |  | 270 | 2026-01-19 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-06 | WilsonPD-TRANSMIT-000010 | NA | Trade Partner | Action Requires:MEL11 Tank - Wilson Tech Data for Review | 0 | 8 | 0 | NA | APPROVED | 2026-07-06 | WF-000378 | NA | 2026-07-09 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-001091 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-06 | Detail-TRANSMIT-000016 | NA | Trade Partner | Detail-TRANSMIT-000016 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-07-06 | KPTG-DA-007413 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-06 | SES AU-TRANSMIT-000075 | NA | Trade Partner | SECURITY - CABLING DIAGRAM - IFC | 2 | 0 | 0 | NA | APPROVED | 2026-07-06 | WF-000379 | NA | 2026-07-08 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-001030 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-06 | ArcadiaL-TRANSMIT-000002 | NA | Consultant | Landscape Architectural Updates - For Review and Coordination | 54 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 1416 | 2026-07-08 |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-003026 | Closed | 54 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-06 | CDL-TRANSMIT-000042 | NA | Trade Partner | 11 | 11 | 0 | 0 | NA | REJECTED | [5 empty] | INCORRECT DOCUMENT NAMING:KPTG-IntCorr-008501 |  | 2026-07-06 | KPTG-IntCorr-008501 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-06 | INDS-TRANSMIT-000046 | NA | Trade Partner | Wet Fire - Ground & Mezzanine | 2 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 685 | 2026-07-13 |  |  | 2026-07-23 | 2026-07-23 | KPTG-SADV-005067 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-06 | INDS-TRANSMIT-000045 | NA | Trade Partner | Wet Fire - Ground | 5 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 1418 | 2026-07-09 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-002783 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-06 | VOGUE-TRANSMIT-000020 | NA | Trade Partner | 511SRC pre start items | 0 | 3 | 0 | NA | APPROVED | 2026-07-06 | WF - 001069 | NA | 2026-07-10 |  | NA | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-003196 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-06 | VOGUE-TRANSMIT-000021 | NA | Trade Partner | PV07 Resubmission | 0 | 2 | 0 | NA | APPROVED | 2026-07-06 | WF - 01070 | NA | 2026-07-10 |  | NA | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-003195 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-06 | CDL-TRANSMIT-000043 | NA | Trade Partner | Action Requires -Re: KPA Stage 2 Documentation-367# | 6 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 367 | 2026-07-15 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-003080 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-07 | Schindle-TRANSMIT-000004 | SPARK-CRFI-KPG-000505 | Trade Partner | Schindler Lifts - Full Depth Frame Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-01-15 | WF-000221 | 87 | 2026-01-22 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-000458 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-06 | ADP-TRANSMIT-000364 | NA | Consultant | ADP-TRANSMIT-000364 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect document reference number |  | 2026-07-06 | KPTG-DA-007415 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-06 | ADP-TRANSMIT-000363 | NA | Consultant | ADP - M3S4 Load Calculations Report | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For Distribution |  | 2026-07-06 | KPTG-TRANSMIT-019365 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-06 | Auspan-TRANSMIT-000465 | NA | Trade Partner | Update precast shop drawings for construction. Levels 2, 3 | 6 | 0 | 0 | KPTG-IntCorr-000870 | APPROVED | [5 empty] | IFC - Waiting for Kim advise-KPTG-IntCorr-000870 KPTG-IntCorr-000899 - 4 are ok to proceed; KPTG-TRANSMIT-002663 2 are not rejected.- DRAFT-009553 |  | 2026-07-08 | KPTG-TRANSMIT-002663 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-06 | Auspan-TRANSMIT-000465 | NA | Trade Partner | Update precast shop drawings for construction. Levels 2, 3 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to difference in drawing status- DRAFT-009392 |  | 2026-07-06 | DRAFT-009392 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-06 | Leemark-TRANSMIT-000050 | SPARK-CRFI-KPG-000317 | Trade Partner | MCC - MCC Carpark Calculation Package - IFA | 0 | 1 | 0 | NA | APPROVED | 2026-07-06 | NA | NA | 2026-07-10 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-001575 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-06 | WilsonPD-TRANSMIT-000106 | NA | Trade Partner | Stage 11 ground floor sewer and stormwater layout | 1 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 1324 | 2026-07-13 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-005400 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-06 | D&E-TRANSMIT-000895 | NA | Trade Partner | NXM3S4 - Level 1 - CHW Pipe Layout - Zone 8 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-06 | KPTG-TRANSMIT-019372 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-06 | Auspan-TRANSMIT-000467 | NA | Trade Partner | Re: Z5 SPANDRELS - L3 & 4 DELETE | 4 | 0 | 0 | KPTG-IntCorr-000874 | APPROVED | 2026-07-08 | NA | ACC#1438 | 2026-07-15 |  | DELETED Drawings- Waiting for Kim advise-KPTG-IntCorr-000874 | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002745 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-06 | SC-TRANSMIT-000006 | NA | Trade Partner | Chemset & Primer Technical datasheet | 0 | 2 | 0 | NA | APPROVED | 2026-07-06 | WF-000882 | NA | 2026-07-08 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002849 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-12 | RDSBIM-TRANSMIT-000030 |  | Trade Partner | MWYCCB ¦ LEVEL 01 PARTITION WALL KEY PLAN AND LAYOUT | 5 | 0 | 0 | NA | APPROVED | 2026-01-13 | WF-000118 | 83 | 2026-01-20 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-06 | SMEPS-TRANSMIT-000026 | NA | Trade Partner | Techdata: Communications | 0 | 2 | 0 | NA | APPROVED | 2026-07-06 | WF-000286 | NA | 2026-07-17 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001418, KPTG-TRANSMIT-001424 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-06 | ELLISAIR-TRANSMIT-000106 | NA | Trade Partner | PVC | 0 | 1 | 0 | NA | APPROVED | 2026-07-06 | WF-001142 | NA | 2026-07-16 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-005618 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-06 | SMEPS-TRANSMIT-000027 | NA | Trade Partner | Tech data: Communications | 0 | 2 | 0 | NA | APPROVED | 2026-07-06 | WF-000287 | NA | 2026-07-17 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-001748 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-06 | IVS-TRANSMIT-000370 | NA | Consultant | Stage 4 - Office Canopy Level 1 (Revised Construction Issue) | 1 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 3793 | 2026-07-08 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-019401 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-06 | ZLH P/L-TRANSMIT-000015 | NA | Trade Partner | Proposed Steel Sheet - ZLH | 0 | 1 | 0 | NA | APPROVED | 2026-07-06 | WF-000288 | NA | 2026-07-17 |  | transmittal is superseded by ZLH P/L-TRANSMIT-000016 |  | 2026-07-06 | KPTG-TRANSMIT-001054 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-06 | Baigents-TRANSMIT-000089 | SPARK-CRFI-KPG-000135 | Trade Partner | Revised Site Storage Stair - IFC | 3 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 338 | 2026-07-10 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001386 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-06 | Auspan-TRANSMIT-000466 | NA | Trade Partner | Re: Precast shop drawings for construction. Levels 1, 2. - IFC Transmittal Advise | 1 | 0 | 0 | KPTG-IntCorr-000876 | APPROVED | [5 empty] | IFC - Waiting for Kim advise-KPTG-IntCorr-000876 IFC - Registered and transmitted . KPTG-TRANSMIT-002650 |  | 2026-07-08 | KPTG-TRANSMIT-002650 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-07-06 | SMPS-TRANSMIT-000122 | NA | Trade Partner | Hanwha Power Pack – O&M Manual Submission | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision number |  | 2026-07-06 | DRAFT-010315 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-07-06 | SMPS-TRANSMIT-000121 | NA | Trade Partner | Hanwha Power Pack – O&M Manual Submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect revision number |  | 2026-07-06 | DRAFT-010316 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-06 | D&E-TRANSMIT-000894 | NA | Trade Partner | Functional Description - Issued for Apprvoal | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect revision |  | 2026-07-06 | KPTG-DA-007420 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-13 | Baigents-TRANSMIT-000062 |  | Trade Partner | MCC Precast Lift Core Plans - IFC | 3 | 0 | 0 | NA | APPROVED | 2026-01-13 | WF-000119 | 84 | 2026-01-20 |  | Bim360 review terminated by Lawden Constructed |  | 2026-08-25 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-06 | D&E-TRANSMIT-000282 | SPARK-CRFI-KPG-000470 & SPARK-CRFI-KPG-000646 | Trade Partner | Mechanical Services BMS Documents - For Approval | 0 | 3 | 0 | NA | APPROVED | 2026-07-06 | NA | NA | 2026-07-10 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-001473 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-06 | KPTG-TRANSMIT-001071 | NA | Trade Partner | Penske - FAT Reports - Issued for Approval | 0 | 116 | 0 | NA | APPROVED | 2026-07-06 | WF - 000521 | NA | 2026-07-10 |  | NA | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-001090 | Closed | 116 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-06 | ARCH-TRANSMIT-000054 | NA | Consultant | Re: Building Permit Documentation | 7 | 2 | 0 | NA | APPROVED | 2026-07-06 | NA | 319 | 2026-07-17 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001065 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-07-06 | WPD-TRANSMIT-000095 | NA | Trade Partner | Hydraulic Services - B18 - As Builts | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision number |  | 2026-07-06 | DRAFT-010318 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-06 | ADP-TRANSMIT-000365 | NA | Consultant | ADP - CAN - Fire Water Storage | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For Distribution |  | 2026-07-06 | ⁠KPTG-TRANSMIT-019378 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-06 | ARCH-TRANSMIT-000053 | NA | Consultant | Building Permit Documentation | 5 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 320 | 2026-07-09 |  | Superseded by ARCH-TRANSMIT-000054 |  | 2026-07-06 | KPTG-TRANSMIT-001053 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-25 | SMEPS-IntCorr-000343 | NA | Trade Partner | Cell 1 CEI test results | 0 | 2 | 0 | NA | APPROVED | 2026-06-25 | WF - 000508 | NA | 2026-07-06 |  | NA | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-001075 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-07-06 | WPD-TRANSMIT-000096 | NA | Trade Partner | Re: HFF - Wilson PD O&M Manual Submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The reference number and revision number are missing |  | 2026-07-06 | DRAFT-010319 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-06 | PTA-TRANSMIT-000017 | NA | Consultant | Concrete Profile Plan Penos Update - Issue for Coordination | 9 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 331 | 2026-07-14 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-000989 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-06 | BIMF-TRANSMIT-000009 | NA | Trade Partner | L1 Hyd Setout Building B | 1 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 900 | 2026-07-12 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2025-12-01 | WEBBAUST-TRANSMIT-000058 |  | Consultant | WEBB - B08 Powerpack Test 100% DD | 5 | 0 | 0 |  | APPROVED | [5 empty] | The register/ACC has been updated. If any further action is required, the coordinator will inform. | [6 empty] | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-02 | Endfire-TRANSMIT-000046 | NA | Trade Partner | Dry fire Layout - Level 3 | 1 | 0 | 0 | NA | APPROVED | 2025-12-02 | NA | 673 | 2025-12-08 |  |  | 2025-12-17 | 2025-12-18 | KPTG-TRANSMIT-002331 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-13 | D&E-TRANSMIT-000328 | NA | Trade Partner | Fwd: HEX, IW Tanks, CHW & CDW Pumps - Issued for Approval | 0 | 3 | 0 | NA | APPROVED | 2026-01-14 | WF-003780 |  | 2026-02-04 |  | The register has been updated. If any further action is required, the coordinator will inform. |  | 2026-02-06 | KPTG-TRANSMIT-012552 | Open | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-06 | Ardon-TRANSMIT-000046 | NA | Trade Partner | Updated CM-02 Timber Veneer Sample | 0 | 1 | 0 | NA | APPROVED | 2026-07-06 | WF - 001071 | NA | 2026-07-10 |  | NA | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-003214 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-06 | ARCST-TRANSMIT-000326 | NA | Trade Partner | Re: C3 East Roof Walkway - Issued for Construction | 136 | 0 | 0 | NA | REJECTED | [5 empty] | The IFA has not been received |  | 2026-07-06 | KPTG-DA-007421 | Closed | 136 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-06 | ARCST-TRANSMIT-000325 | NA | Trade Partner | C2 East Lower Gantry - Issued for Construction | 132 | 0 | 0 | NA | REJECTED | [5 empty] | The IFA has not been received |  | 2026-07-06 | KPTG-DA-007423 | Closed | 132 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-06 | ZLH P/L-TRANSMIT-000016 | NA | Trade Partner | Proposed Steel Sheet - ZLH | 0 | 1 | 0 | NA | APPROVED | 2026-07-06 | WF-000290 | NA | 2026-07-17 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001393 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-06 | ARCST-TRANSMIT-000327 | NA | Trade Partner | Re: C1 West Roof Walkway - Issued for Construction | 156 | 0 | 0 | NA | REJECTED | [5 empty] | The IFA has not been received |  | 2026-07-06 | KPTG-DA-007424 | Closed | 156 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-06 | PTA-TRANSMIT-000018 | NA | Consultant | Precast External Elevation Mech Penos - Issue for Coordination | 3 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 333 | 2026-07-14 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-000991 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-06 | Jangho-TRANSMIT-000225 | NA | Trade Partner | Re: Tower Level 6~10 Cast in Channel Shop Drawing_PDF_Rev 01_Review | 12 | 0 | 0 | NA | REJECTED | [5 empty] | STATUS DIFFERENCE |  | 2026-07-06 | KPTG-TRANSMIT-002719 | Closed | 12 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-06 | 4DW-TRANSMIT-000063 | NA | Consultant | Level 1 & Roof concrete outlines updates & gutter framing | 14 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 335 | 2026-07-14 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-000781 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-06 | D&E-TRANSMIT-000283 | SPARK-CRFI-KPG-000491 & SPARK-CRFI-KPG-000313 | Trade Partner | MWYCCB - LEVEL 1 PIPEWORK LAYOUT ZONES + CHILLED & HEATING HOT WATER SCHEMATICS - Issued For Construction | 3 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 339 | 2026-07-10 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-001421 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-06 | ARCST-TRANSMIT-000328 | NA | Trade Partner | Mech Corridor Wall Steel - Issued for Approval | 7 | 0 | 0 | NA | APPROVED | 2026-07-06 | WF-006273 | NA | 2026-07-17 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-13 | RDSBIM-TRANSMIT-000141 | NA | Trade Partner | ROOF CONCRETE PROFILE KEY PLAN | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties |  |  |  | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-06 | ARCST-TRANSMIT-000329 | NA | Trade Partner | Re: Stair 12 &13 - Issued for Approval | 19 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to revisions required in some documents that were already received. |  | 2026-07-06 | KPTG-RFI-008783 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-02 | ZIA-TRANSMIT-000068 | NA | Trade Partner | CSMS - Cx L3 Test Documents | 0 | 1 | 0 | KPTG-TRANSMIT-004028 | APPROVED |  | NA | NA |  |  | clarification from ibrahim - FORWARDED FOR INFO TO NEXTDC |  | 2026-07-07 | KPTG-TRANSMIT-004043 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-26 | Teams message Ibrahim - Service Cmx Plans | NA | Trade Partner | Service Cmx Plans - HYDRAULIC | 0 | 1 | 0 | Documents currently under w/flow. Need clarification<br> | APPROVED | 2026-06-30 | WF-001130 | NA | 2026-07-03 |  | Documents currently under w/flow. Need clarification |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-26 | Teams message Ibrahim - Service Cmx Plans | NA | Trade Partner | Service Cmx Plans - FIRE | 0 | 1 | 0 | Documents currently under w/flow. Need clarification<br> | APPROVED | 2026-07-01 | WF-001134 | NA | 2026-07-06 |  | Documents currently under w/flow. Need clarification |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-26 | Teams message Ibrahim - Service Cmx Plans | NA | Trade Partner | Service Cmx Plans - FUEL | 0 | 1 | 0 | Documents currently under w/flow. Need clarification<br> | APPROVED | 2026-07-01 | WF-001135 | NA | 2026-07-06 |  | Documents currently under w/flow. Need clarification |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-26 | Teams message Ibrahim - Service Cmx Plans | NA | Trade Partner | Service Cmx Plans | 0 | 1 | 0 | Documents currently under w/flow. Need clarification<br> | APPROVED | 2026-07-19 | WF-001166 | NA | 2026-07-22 |  | Documents currently under w/flow. Need clarification WF-001078 | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-004174 | Open | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-26 | Teams message Ibrahim - Service Cmx Plans | NA | Trade Partner | Service Cmx Plans | 0 | 1 | 0 | Documents currently under w/flow. Need clarification<br> | APPROVED |  | NA | NA |  |  | Documents currently under w/flow. Need clarification |  | 2026-07-21 | KPTG-IntCorr-001706 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | PCForm-TRANSMIT-000265 | NA | Trade Partner | L1, L4 & L5 to L11 - Lvl 1 | 2 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 903 | 2026-07-12 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-002907 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-06 | LVPG-TRANSMIT-000038 | NA | Trade Partner | Reflex (water, Hot water, Recycled) | 0 | 1 | 0 | NA | APPROVED | 2026-07-06 | WF-000682 | NA | 2026-07-13 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-06 | LVPG-TRANSMIT-000040 | NA | Trade Partner | - Stainless Mains water reticulation pipework | 0 | 1 | 0 | NA | APPROVED | 2026-07-06 | WF-000684 | NA | 2026-07-13 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-13 | RDSBIM-TRANSMIT-000142 | NA | Trade Partner | LEVEL 15 CONCRETE PROFILE PLAN | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties |  |  |  | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-06 | INDS-TRANSMIT-000046 | NA | Trade Partner | Dry Fire - Ground | 5 | 0 | 0 | KPTG-IntCorr-000878 | APPROVED |  | NA | NA |  |  | waiting for advise from Julianne, KPTG-IntCorr-000878 Rejected due to incorrect drawing number. DRAFT-009476 |  | 2026-07-07 | DRAFT-009476 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-06 | Auscool-TRANSMIT-000055 | NA | Trade Partner | Samples Submission | 0 | 9 | 0 | NA | APPROVED | 2026-07-06 | WF-000688 | NA | 2026-07-13 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-29 | Auspan-TRANSMIT-000435 | NA | Trade Partner | Precast shop drawings for construction. Levels 3, 4 | 7 | 0 | 0 | KPTG-IntCorr-000866 | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-000865 7 on Hold - DRAFT-009419 No action - Drawings are superseded- and transmitted via Auspan-TRANSMIT-000527 |  | 2026-07-29 | NA | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-26 | Auspan-TRANSMIT-000431 | NA | Trade Partner | : Precast shop drawings for construction. Levels 3, 4, 5. | 4 | 0 | 0 | KPTG-IntCorr-000866 | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-000866 4 on Hold as advised by Kapitol PC. IFC - 2 are Registered and Transmit KPTG-TRANSMIT-002973 2 already superseded. |  | 2026-07-28 | KPTG-TRANSMIT-002973 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-06 | RDSBIM-TRANSMIT-000080 | NA | Trade Partner | 671CHP LEVEL 01 CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 611 | 2026-07-13 |  | Review Void as RDS to update the drawings. |  | 2026-07-06 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-06 | IJF-TRANSMIT-000004 | NA | Trade Partner | Updated Prototype Joinery Drawings for Apt 4.07 & 4.08 | 37 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to incorrect drawing number and title. KPTG-SADV-002836 |  | 2026-07-06 | KPTG-SADV-002836 | Closed | 37 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-06 | RDSBIM-TRANSMIT-000081 | NA | Trade Partner | 671 CHP GROUND FLOOR CONCRETE PROFILE KEY PLAN IFC SUBMISSION | 6 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 613 | 2026-07-13 |  | Review Void as RDS to update the drawings. |  | 2026-07-06 | NA | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | PCForm-TRANSMIT-000265 | NA | Trade Partner | L1, L4 & L5 to L11 - Lvl 8 | 1 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 908 | 2026-07-12 |  |  | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-002998 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-06 | ELLISAIR-TRANSMIT-000103 | NA | Trade Partner | Side stream Filtration & Water Treatment | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Need to revise - KPTG-SADV-005904 |  | 2026-07-06 | KPTG-SADV-005904 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-13 | RDSBIM-TRANSMIT-000143 | NA | Trade Partner | LEVEL 09 RCP KEY PLAN AND LAYOUT | 6 | 0 | 0 | NA | APPROVED | 2026-01-13 | WF-000869 | 522 | 2026-01-19 |  |  | 2026-01-27 | 2026-01-27 | KPTG-TRANSMIT-002637 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-06 | ELLISAIR-TRANSMIT-000105 | NA | Trade Partner | Side Stream Filtration & Water Treatment | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, updated register and distributed. |  | 2026-07-06 | KPTG-TRANSMIT-005263 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-06 | WilsonPD-TRANSMIT-000105 | NA | Trade Partner | Stage 9 ground floor sewer and stormwater layout | 1 | 0 | 0 | NA | APPROVED | 2026-07-06 | NA | 1322 | 2026-07-09 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-005396 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-06 | ZIA-TRANSMIT-000017 | NA | Trade Partner | M2 Stage 9, 10 & 11 CSMS Layer 2 Ethernet Switch (FOA-2) | 0 | 1 | 0 | NA | APPROVED | 2026-07-06 | WF-001143 | NA | 2026-07-16 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-07 | RDSBIM-TRANSMIT-000119 | NA | Trade Partner | MLCSPR -OUTDOOR COURT LEVEL 02 CONCRETE PROFILE PLAN SHEET 7 | 1 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 369 | 2026-07-10 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-003185 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-07 | Auscool-TRANSMIT-000096 | NA | Trade Partner | CCW Anchor Design | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004811 - document no format incorrect. | 2026-07-07 | 2026-07-07 | KPTG-SADV-004811 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-07 | SKS Tech-TRANSMIT-000192 | NA | Trade Partner | SKS Tech-TRANSMIT-000192 | 0 | 1 | 0 | NA | APPROVED | 2026-07-07 | WF-006276 | NA | 2026-07-28 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-07 | Highbu-TRANSMIT-000057 | NA | Trade Partner | Amended Hydraulic Transmittal | 5 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004812 - tittle and status are different inside and outside. | 2026-07-07 | 2026-07-07 | KPTG-SADV-004812 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-07 | CDL-TRANSMIT-000042 | NA | Trade Partner | KPA Stage 2 Documentation | 0 | 5 | 0 | NA | APPROVED | 2026-07-07 | WF-001031 | NA | 2026-07-15 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-11-27 | ECBS-TRANSMIT-000030 | NA | Trade Partner | Revised Sarking tech data for review | 0 | 1 | 0 | NA | APPROVED | 2025-11-27 | WF-000623 | NA | 2025-12-04 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-003054 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-07 | ARCST-TRANSMIT-000330 | NA | Trade Partner | Lift Lobby - Issued for Construction | 68 | 0 | 0 | NA | APPROVED | 2026-07-07 | WF-006275 | NA | 2026-07-15 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-13 | Tradetec-TRANSMIT-000321 | NA | Trade Partner | Stage 4 - IFA - CP36 | 1 | 0 | 0 | NA | APPROVED | 2026-01-13 |  | 1764 | 2026-01-21 |  |  |  | 2026-01-23 | KPTG-TRANSMIT-011832 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-07 | TTW-TRANSMIT-000044 | NA | Consultant | Civil Technical Specification | 0 | 1 | 0 | NA | APPROVED | 2026-07-07 | NA | 338 | 2026-07-15 |  |  | 2026-08-18 | 2026-08-19 | KPTG-TRANSMIT-001008 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-07 | S.T.S-TRANSMIT-000004 | NA | Trade Partner | Loading Dock Review | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-07-07 | Awaiting approval | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-07 | HGP-TRANSMIT-000008 | NA | Trade Partner | Updated Glazing Shop drawings | 20 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 1328 | 2026-07-14 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-005525 | Closed | 20 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-07 | ASV-TRANSMIT-000187 | NA | Trade Partner | Fwd: Syfon's As-Built drawings for Stage 2 | 4 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 4353 | 2026-07-10 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020208 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-07 | HGP-TRANSMIT-000060 | NA | Trade Partner | Transmittal-IFC Shop Drawing FT01 Curtain Wall | 101 | 0 | 0 | NA | REJECTED | [5 empty] | Document attached is incorrect and date inside drawing and in Aconex seem different |  | 2026-07-07 | KPTG-TRANSMIT-001385 | Closed | 101 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-07 | Stowe-A-TRANSMIT-000635 | NA | Trade Partner | Stowe - Drawing Update - As built - DH Tiers 3 & 4 | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Issues with Title. |  | 2026-07-07 | KPTG-SADV-006430 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-07 | ADP-TRANSMIT-000104 | NA | Consultant | ADP MEL 4680 - Updated HYD Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 322 | 2026-07-10 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001321 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-29 | Jangho-TRANSMIT-000206 | NA | Trade Partner | Updated 671 PMU drawing and test proposals for District Dockland for review | 0 | 1 | 0 | NA | APPROVED | 2026-06-29 |  |  | 2026-07-07 |  |  | 2026-07-09 | 2026-07-07 | KPTG-TRANSMIT-002749 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-07 | ARCST-TRANSMIT-000325 | NA | Trade Partner | C2 East Lower Gantry - Issued for Construction | 132 | 0 | 0 | NA | APPROVED | 2026-07-07 | WF-006278 | NA | 2026-07-15 |  | As instructed by Lola in KPTG-RTRFI-005099 |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-07 | Highbu-TRANSMIT-000058 | NA | Trade Partner | Re: Amended Hydraulic Transmittal | 5 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 686 | 2026-07-14 |  |  | 2026-07-23 | 2026-07-23 | KPTG-SADV-005068 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-05 | NXT-TRANSMIT-001165 | NA | Client | 000574-100222 - Documents issued for use | 0 | 2 | 0 | NA | APPROVED | 2026-01-06 | WF-005512 | NA | 2026-05-05 |  | Terminated as directed by Rohit Hendricks through NXT-PA-004503 | 2026-05-01 | 2026-05-01 | KPTG-DA-006313 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-07 | Nilsen3-TRANSMIT-000051 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 1254 | 2026-07-07 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-005282 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-07 | SKS Tech-TRANSMIT-000193 | NA | Trade Partner | Lighting Control Layout Roof - IFC | 3 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 3796 | 2026-07-16 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-07 | Entire M-TRANSMIT-000058 | NA | Trade Partner | Refrigeration Pipework & Cable Tray | 0 | 1 | 0 | NA | APPROVED | 2026-07-07 | WF-000292 | NA | 2026-07-20 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001593 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-07 | Nilsen3-TRANSMIT-000222 | NA | Trade Partner | Nilsen Shop Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 3798 | 2026-07-16 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-07 | ZIA-TRANSMIT-000114 | NA | Trade Partner | M3 Stage 4 - Device Register | 0 | 1 | 0 | NA | APPROVED | 2026-07-07 | WF-006281 | NA | 2026-07-28 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-07 | KALLIBRE-TRANSMIT-000026 | NA | Trade Partner | Updated door by door hardware schedule | 0 | 1 | 0 | NA | APPROVED | 2026-07-07 | WF-000380 | NA | 2026-07-08 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001044 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-07 | Nilsen3-TRANSMIT-000224 | NA | Trade Partner | Fwd: Nilsen Generator enclosure cable containment Shop drawings. | 2 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 3801 | 2026-07-16 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-07 | PARR-TRANSMIT-000204 | NA | Trade Partner | PARR-TRANSMIT-000204 Fwd: P2685 - NDC M3 - Stage 4 - Battery Rooms - CERTIFICATE OF FIRE DOOR | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-07 | KPTG-TRANSMIT-019398 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | RDSBIM-TRANSMIT-000054 | NA | Trade Partner | GROUND FLOOR TO LEVEL 09 STAIR CORE 04 CONCRETE PROFILE PLAN AND SECTION ELEVATION | 3 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 915 | 2026-07-14 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-002905 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-07 | RDSBIM-TRANSMIT-000288 | NA | Trade Partner | NXM3S4 ¦ LEVEL-1-C-1-055 CLEANERS FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 3804 | 2026-07-10 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-019518 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-05 | NXT-TRANSMIT-001165 | NA | Client | 000574-100222 - Documents issued for use | 1 | 0 | 0 | NA | APPROVED | 2026-01-06 | WF-003706 | NA | 2026-01-09 |  | Due to VPN issues close out processed on 10/04/2026 | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-015685 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | RDSBIM-TRANSMIT-000055 | NA | Trade Partner | LEVEL 09 TO LEVEL 18 STAIR CORE 04 CONCRETE PROFILE PLAN ¦ IFA ¦ SUBMISSION | 3 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 917 | 2026-07-14 |  |  | 2026-07-17 | 2026-07-20 | KPTG-TRANSMIT-002977 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-07 | Appselec-TRANSMIT-000138 | NA | Trade Partner | MEL11C45 - Communications Shop Drawings - IFC | 2 | 0 | 0 | NA | APPROVED | 2026-07-07 | WF-000381 | NA | 2026-07-10 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-001054 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-30 | PCForm-TRANSMIT-000256 | NA | Trade Partner | Level 3 & Level 4 - updated drawings | 4 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 911 | 2026-07-13 |  | updated 4 documents received from PCForm-TRANSMIT-000265 | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002957 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-07 | D&E-TRANSMIT-000896 | NA | Trade Partner | NXM3S4 - CHW & CT SCHEMATIC - ROOF C1-C2 & C3 SHEETS - Issued for Approval | 6 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 3802 | 2026-07-16 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-020542 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-07 | Civilex-TRANSMIT-000279 | NA | Trade Partner | Stage 2 - sample submission - Planter Box - Rev D | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with Revision and revision date. |  | 2026-07-07 | KPTG-SADV-006431 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | PCForm-TRANSMIT-000265 | NA | Trade Partner | L1, L4 & L5 to L11 - Lvl 4 | 5 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 911 | 2026-07-13 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002957 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-01 | Syfon1-TRANSMIT-000010 | NA | Trade Partner | Syfon shop drawings IFC | 5 | 0 | 0 | NA | APPROVED | 2026-06-25 | NA | 3805 | 2026-07-16 |  | The latest revision of the M3-HYD-SYF-SDRG-C-0401-3010 has been received so WF 3676 terminated and 5 of them placed in review |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-07 | Leemark-TRANSMIT-000051 | SPARK-CRFI-KPG-000365 | Trade Partner | MCC - LEVEL 1 ZONE 5-7 FIRE PROTECTION LAYOUT - IFC | 3 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 340 | 2026-07-14 |  |  | 2026-07-10 | 2026-07-14 | KPTG-TRANSMIT-001443 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | PCForm-TRANSMIT-000265 | NA | Trade Partner | L1, L4 & L5 to L11 - Lvl 7,Lvl 9, Lvl 10, Lvl 11 | 4 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 914 | 2026-07-13 |  |  | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-002996 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | PCForm-TRANSMIT-000265 | NA | Trade Partner | L1, L4 & L5 to L11 - Lvl 5 , Lvl 6 | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | QA error |  | 2026-07-07 | KPTG-TRANSMIT-002760 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-05 | NXT-TRANSMIT-001166 | NA | Client | 000575-100222 Next DC M3 - As Built- First Fix EI/EK/EM/EO/EQ/ER | 0 | 6 | 0 | NA | APPROVED |  | NA | NA |  |  | As Built |  | 2026-01-06 | KPTG-TRANSMIT-011263 | Closed | 6 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-07 | Civilex-TRANSMIT-000280 | NA | Trade Partner | Stage 2 - sample submission - eMesh Fibre Concrete - Pronto | 0 | 1 | 0 | NA | APPROVED | 2026-07-07 | WF-006284 | NA | 2026-07-13 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-019734 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-07 | Syfon1-TRANSMIT-000013 | NA | Trade Partner | Syfon updated Western Elevation | 1 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 3809 | 2026-07-16 |  |  |  | 2026-07-29 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-07 | ADP-TRANSMIT-000106 | NA | Consultant | ADP MEL4680 - Electrical Spec and Reg 126 | 0 | 2 | 0 | NA | APPROVED | [5 empty] | Documents resubmitted in ADP-TRANSMIT-000107 |  | 2026-07-07 | KPTG-IntCorr-000279 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-07 | Syfon1-TRANSMIT-000012 | NA | Trade Partner | Syfon updated Zones C2 and C3 drawings | 4 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 3810 | 2026-07-16 |  | As instructed by Finn Jenkins - Terminated |  | 2026-07-29 | NA | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-07 | Schindle-TRANSMIT-000002 | SPARK-CRFI-KPG-000305 | Trade Partner | Schindler Updated lift drawings for Review | 1 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | NA | 2026-07-07 |  | Actual received date - 17/11/2025 | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001388 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-07 | CRSol-TRANSMIT-000015 | NA | Trade Partner | Re: CRS - Structural Ceiling -Stage 9 - DH21 &DH24 Shop Drawing IFA - REV 3 - CD09 Changes | 13 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 1331 | 2026-07-14 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-005503 | Closed | 13 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-07 | ADP-TRANSMIT-000105 | NA | Trade Partner | ADP MEL4680 - Updated Electrical Drawings | 49 | 0 | 0 | NA | REJECTED | [5 empty] | REVISION MISMATCH BTW ACONEX AND INSIDE DRAWING |  | 2026-07-07 | KPTG-DA-000986 | Closed | 49 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-07-07 | Nilsen3-TRANSMIT-000220 | NA | Trade Partner | Re: M3 Stage-3 HVSB additional signage and safety labels | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-07-07 | KPTG-DA-007439 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-07 | HGP-TRANSMIT-000062 | SPARK-CRFI-KPG-000153 | Trade Partner | CURTAIN WALL IFC CALCULATION REPORTS | 0 | 1 | 0 | NA | APPROVED | 2026-07-07 | NA | NA | 2026-07-14 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001391 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-05 | NXT-TRANSMIT-001167 | NA | Client | 000576-100222 - document issued for use | 0 | 1 | 0 | NA | APPROVED | 2026-01-06 | WF-005513 | NA | 2026-05-05 |  | Terminated as advised by Rohit Hendricks in NXT-PA-004503 | 2026-05-01 | 2026-05-01 | KPTG-DA-006313 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-07 | D&E-TRANSMIT-000897 | NA | Trade Partner | Citric Acid 10% wt/wt Passivation Mixture - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-07 | WF-006287 | NA | 2026-07-28 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-020308 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-07 | SES AU-TRANSMIT-000076 | NA | Trade Partner | Re: Securitas HAC Prototype | 1 | 0 | 0 | NA | REJECTED | [5 empty] | WRONG DOCUMENT NUMBERING: KPTG-IntCorr-000659 |  | 2026-07-07 | KPTG-IntCorr-000659 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-07 | Stowe-A-TRANSMIT-000636 | NA | Trade Partner | Stowe - Asbuilts Updated | 4 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 4355 | 2026-07-10 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-019495 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | Civilex-TRANSMIT-000107 | NA | Trade Partner | Anti-Slip Trench Grate | 0 | 1 | 0 | NA | APPROVED | 2026-07-07 | WF-000898 | NA | 2026-07-14 |  | IN WORKFLOW FOR WAM REVIEW | 2026-07-09 | 2026-07-24 | KPTG-TRANSMIT-003069 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-07 | Tradetec-TRANSMIT-000479 | NA | Trade Partner | IFC - Stage 4 - LVP 49 | 1 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 3814 | 2026-07-16 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-019595 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-07 | SKS Tech-TRANSMIT-000194 | NA | Trade Partner | Labels UpRev | 1 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 3813 | 2026-07-16 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-07 | Baigents-TRANSMIT-000012 | NA | Trade Partner | Block 1 - East & West Wall - Precast Shop Drawings - Issued For Construction | 40 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 340 | 2026-07-15 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-000499 | Closed | 40 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-07 | ARCST-TRANSMIT-000326 | NA | Trade Partner | C3 East Roof Walkway - Issued for Construction | 136 | 0 | 0 | NA | APPROVED | 2026-07-07 | WF-006290 | NA | 2026-07-13 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-07 | ADP-TRANSMIT-000107 | NA | Trade Partner | Re: ADP MEL4680 - Electrical Spec and Reg 126 | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect revision number in inside document |  | 2026-07-07 | KPTG-SADV-000841 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-07 | SMEPS-TRANSMIT-000335 | NA | Trade Partner | SME - IFC Documentation Submission | 2 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 3817 | 2026-07-16 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-020673 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-13 | WSP ANZ-TRANSMIT-000033 | NA | Consultant | MSB-XX-2 MCCB count and ratings | 3 | 0 | 0 | NA | APPROVED | [5 empty] | No review required, drawings already approved (KPTG-TRANSMIT-000404 ) |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-07 | SMEPS-TRANSMIT-000336 | NA | Trade Partner | Fwd: SME - IFA Documentation | 1 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 3818 | 2026-07-16 |  |  |  | 2026-08-14 | KPTG-TRANSMIT-020608 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-07 | P & R-TRANSMIT-000093 | NA | Trade Partner | P&R - Tech Data for IFA | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Wrong Document numbering & Non Attachement of Covering sheet:KPTG-SADV-005196 |  | 2026-07-07 | KPTG-SADV-005196 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-07 | Baigents-TRANSMIT-000013 | NA | Trade Partner | Block 1 - Precast Dowel & Marking Plans - Issued for Construction | 5 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 342 | 2026-07-15 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-000602 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-07 | KALLIBRE-TRANSMIT-000005 | NA | Trade Partner | IFA - Toilet Partitions | 6 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to wrong document Rejected (KPTG-TRANSMIT-003119) |  | 2026-07-07 | KPTG-TRANSMIT-003119 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-07 | SMEPS-TRANSMIT-000238 | NA | Trade Partner | SME Tech Data for Uprev | 0 | 13 | 0 | NA | APPROVED | 2026-07-07 | WF - 000523 | NA | 2026-07-09 |  | NA | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001078 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-07 | ARCST-TRANSMIT-000331 | NA | Trade Partner | Staur 12 & 13 - Issued for Approval | 19 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect title |  | 2026-07-07 | ⁠KPTG-DA-007446 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-07 | SMEPS-TRANSMIT-000239 | NA | Trade Partner | Fwd: SMEPS-TRANSMIT-000239 - EXTERNAL EPMS BAS ROUTING LAYOUT | 3 | 0 | 0 | NA | APPROVED | 2026-07-07 | WF - 000524 | NA | 2026-07-09 |  | NA | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001081 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-07 | ADP-TRANSMIT-000108 | NA | Consultant | ADP MEL4680 - Updated Electrical Drawings | 49 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 325 | 2026-07-21 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-001122 | Closed | 49 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-07 | Civilex-TRANSMIT-000282 | NA | Trade Partner | Stage 2 - sample submission - Planter Box - rev D - Updated naming | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with Revision date, revision history, |  | 2026-07-07 | KPTG-SADV-006445 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-02 | VAE-Grp-TRANSMIT-000074 | NA | Trade Partner | Mechanical Services - LEVEL 01 HVAC LAYOUT, MECH ELEC TRAY & BUILDERS WORKS | 6 | 0 | 0 | NA | APPROVED | 2025-12-02 | NA | 675 | 2025-12-06 |  |  | 2025-12-04 | 2025-12-06 | KPTG-TRANSMIT-002192 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-07 | NXT-TRANSMIT-001173 | NA | Client | 100222-NEXT DC M3- FIRE SYSTEM SCHEMATICS- EH ROOM-AS BUILT | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-01-07 | KPTG-TRANSMIT-011274 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | WAM-TRANSMIT-000823 | NA | Consultant | A9 Series and A10 Series plans | 46 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 919 | 2026-07-10 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-002818 | Closed | 46 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-07 | D&E-TRANSMIT-000022 | NA | Trade Partner | LEVEL 1 BUILDERS WORK LAYOUT - ZONE 2 (DH8) | 1 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 344 | 2026-07-15 |  | Void-Requested by Sacheen |  | 2026-08-03 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-07 | ARCST-TRANSMIT-000327 | NA | Trade Partner | C1 West Roof Walkway - Issued for Construction | 156 | 0 | 0 | NA | APPROVED | 2026-07-07 | WF-006292 | NA | 2026-07-13 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-07 | Tradetec-TRANSMIT-000480 | NA | Trade Partner | IFA - Stage 4 - LVP 39, HVP 35, HVP 41, HVP 42 | 4 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 3823 | 2026-07-13 |  |  | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-019956 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-08 | SRA-PMQ-TRANSMIT-000012 | NA | Trade Partner | Updated Structural Ceiling Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 327 | 2026-07-24 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-001098 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-08 | Entire M-TRANSMIT-000059 | NA | Trade Partner | Re: BMS Equipment - Issued for Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | We noticed that the attached IFA technical data is missing the required document details within the document |  | 2026-07-08 | KPTG-SADV-000854 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-07 | ZIA-TRANSMIT-000070 | NA | Trade Partner | CSMS - Sample Document - FC | 0 | 5 | 0 | NA | APPROVED |  | NA | NA |  |  | fc - send to all parties - KPTG-TRANSMIT-004041 |  | 2026-07-07 | KPTG-TRANSMIT-004041 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-07 | Omnii-TRANSMIT-000007 | NA | Consultant | Fire Engineering Performance-Based Design Brief Revision E | 0 | 1 | 0 | NA | APPROVED | 2026-07-07 | NA | 300 | 2026-07-14 |  | Latest version under review #347 | 2026-08-21 | 2026-08-21 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-07 | 4DW-TRANSMIT-000193 | NA | Trade Partner | Structural Documentation - Column updates | 7 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 372 | 2026-07-10 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-003098 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-08 | ACG-TRANSMIT-000034 | NA | Trade Partner | M3 - S2 ACG Document Tidy | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | No longer in use |  | 2026-01-08 | KPTG-TRANSMIT-011295 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-06 | ZIA-TRANSMIT-000069 | NA | Trade Partner | CSMS - Ground Level Outstation Location | 1 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 1307 | 2026-07-13 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-07 | POTTSENG-TRANSMIT-000025 | NA | Trade Partner | 671C: HYDRAULIC SERVICES - BASEMENT 1 - WATER LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 617 | 2026-07-14 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-001395 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-07 | POTTSENG-TRANSMIT-000026 | NA | Trade Partner | : 671C: HYDRAULIC SERVICES - BASEMENT 2 - WATER LAYOUT | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required. - KPTG-IntCorr-000899 |  | 2026-07-07 | KPTG-IntCorr-000899 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-07 | POTTSENG-TRANSMIT-000027 | NA | Trade Partner | 671C: HYDRAULIC SERVICES - GROUND - PENETRATION LAYOUT | 1 | 0 | 0 | KPTG-IntCorr-000901 | APPROVED |  | NA | NA |  |  | No Review required as advised - KPTG-IntCorr-000903 |  | 2026-07-08 | KPTG-IntCorr-000903 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-07 | B Smart-TRANSMIT-000091 | NA | Consultant | GF & Porte Cochere RCPs | 2 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 624 | 2026-07-09 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-001365 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-07 | B Smart-TRANSMIT-000092 | NA | Consultant | : Remaining drawings issued for Construction | 12 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 622 | 2026-07-09 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-001303 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-07 | RDSBIM-TRANSMIT-000082 | NA | Trade Partner | 671 CHP GROUND FLOOR CONCRETE PROFILE KEY PLAN IFC SUBMISSION | 6 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 615 | 2026-07-14 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-001273 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-07 | POTTSENG-TRANSMIT-000030 | NA | Trade Partner | 671C: HYDRAULIC SERVICES - BASEMENT 2-4 - DRAINAGE LAYOUTS | 3 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 620 | 2026-07-14 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-001397 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-07 | POTTSENG-TRANSMIT-000029 | NA | Trade Partner | 671C: HYDRAULIC SERVICES - BASEMENT 1 - DRAINAGE LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 626 | 2026-07-14 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-001396 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-07 | POTTSENG-TRANSMIT-000028 | NA | Trade Partner | 671C: HYDRAULIC SERVICES - GROUND - PENETRATION LAYOUT | 1 | 0 | 0 | KPTG-IntCorr-000902 | APPROVED |  | NA | NA |  |  | Tayla to advise :KPTG-IntCorr-000902 No review required as advised by PC Tayla . KPTG-IntCorr-000945.Registered and transmitted. |  | 2026-07-10 | KPTG-IntCorr-000945 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-08 | ZIA-TRANSMIT-000038 | NA | Trade Partner | M3S2 CSMS ORMB Location (FOA-2) | 4 | 0 | 0 | NA | APPROVED | 2026-01-08 | WF-003719 | NA | 2026-01-20 |  |  |  | 2026-01-21 | KPTG-TRANSMIT-011749 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-07 | Auspan-TRANSMIT-000468 | NA | Trade Partner | : Re: Update precast shop drawings for approval. Levels 2, 3 | 2 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 1425 | 2026-07-14 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002742 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-07 | Auspan-TRANSMIT-000469 | NA | Trade Partner | : Update already IFCed shop drawings for construction. | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised via KPTG-IntCorr-000884 by Kim ,3 are ok to Register and Transmit KPTG-TRANSMIT-002635 |  | 2026-07-07 | KPTG-TRANSMIT-002635 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-07 | Auspan-TRANSMIT-000469: | NA | Trade Partner | Update already IFCed shop drawings for construction. | 2 | 0 | 0 | NA | REJECTED | [5 empty] | IFC- As advised via KPTG-IntCorr-000884 by Kim ,2 are rejected and returned to Auspan. |  | 2026-07-07 | KPTG-IntCorr-000884 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-07 | Auspan-TRANSMIT-000470 | NA | Trade Partner | Z5 SPANDRELS - L3 & 4 DELETE | 3 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 1427 | 2026-07-14 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002739 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-07 | Rinco-TRANSMIT-000063 | NA | Consultant | L1Z4 PMJ detail update | 6 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 1430 | 2026-07-09 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002752 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-07 | PCForm-TRANSMIT-000081 | NA | Trade Partner | Updated Level 1 Zone 1 FW Design | 3 | 0 | 0 | KPTG-IntCorr-000890 | APPROVED |  | NA | NA |  |  | Waiting for DM advise - KPTG-IntCorr-000890 update register; No other action required. -KPTG-DA-001551 |  | 2026-07-08 | KPTG-DA-001551 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | INGEN3D-TRANSMIT-000171 | NA | Trade Partner | Level 11-13 - Precast Columns & Cast in Dowel - IFC | 42 | 0 | 0 | KPTG-IntCorr-000943 | APPROVED | 2026-07-09 | WF-000908 | NA | 2026-07-20 |  | Nich to clarify |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-07 | SMEPS-TRANSMIT-000063 | NA | Trade Partner | Stage 10 & 11 Day 1 Line Up Cable Schedules | 3 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 1335 | 2026-07-13 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-005741 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | Diadem-TRANSMIT-000001 | NA | Trade Partner | Wayfinding documents for client review | 0 | 2 | 0 | NA | REJECTED |  | NA | NA |  |  | QA ERROR |  | 2026-07-07 | KPTG-TRANSMIT-002764 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | INGEN3D-TRANSMIT-000172 | NA | Trade Partner | Level 11-13 - Precast Columns - No Longer in Use | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer In Use |  | 2026-07-07 | KPTG-TRANSMIT-002761 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-13 | PCForm-TRANSMIT-000032 | NA | Trade Partner | Jumpform Concrete Envelopes & Wall elevations - Issued for construction - Stage 9 (2,3,4) & Stage 10 (5 & 8) | 1 | 0 | 0 | NA | APPROVED |  | WF-000128 |  | 2026-01-19 |  |  | 2026-01-22 | 2026-01-22 | KPTG-TRANSMIT-000568 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | INGEN3D-TRANSMIT-000173 | NA | Trade Partner | Level 16-18 - Precast Columns - IFC | 32 | 0 | 0 | KPTG-IntCorr-000944 | APPROVED | 2026-07-09 | WF-000909 | NA | 2026-07-20 |  | Nich to clarify |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | INGEN3D-TRANSMIT-000174 | NA | Trade Partner | Level 16-18 - Precast Columns - No Longer in Use | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer In Use |  | 2026-07-07 | KPTG-TRANSMIT-002762 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | INGEN3D-TRANSMIT-000134 | NA | Trade Partner | Level 15-17 - PC0528-3 - New IFA | 1 | 0 | 0 | NA | APPROVED | 2026-07-07 | WF-000894 | NA | 2026-07-23 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-002891 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | INGEN3D-TRANSMIT-000165 | NA | Trade Partner | Level 11-13 - Precast Columns - New IFA | 5 | 0 | 0 | KPTG-IntCorr-000925 | APPROVED | 2026-07-07 | WF-000893 | NA | 2026-07-23 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-002887 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | INGEN3D-TRANSMIT-000165 | NA | Trade Partner | Level 11-13 - Precast Columns - New IFA | 2 | 0 | 0 | KPTG-IntCorr-000925 | REJECTED |  | NA | NA |  |  | Column Elevation - In review : Rejected |  | 2026-07-07 | EMAIL DTD 09/07/2026 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | INGEN3D-TRANSMIT-000166 | NA | Trade Partner | Level 15-17 - PC0522-9 & PC0531-6 - New IFA | 4 | 0 | 0 | NA | APPROVED | 2026-07-07 | WF-000894 | NA | 2026-07-23 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-002893 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | INGEN3D-TRANSMIT-000175 | NA | Trade Partner | Level 17-19 - Precast Columns - IFC | 42 | 0 | 0 | KPTG-IntCorr-000945 | APPROVED | 2026-07-09 | WF-000910 | NA | 2026-07-20 |  | Nich to clarify | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-003137 | Closed | 42 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | INGEN3D-TRANSMIT-000176 | NA | Trade Partner | Level 17-19 - PC0584 - No Longer in Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer In Use |  | 2026-07-07 | KPTG-TRANSMIT-002763 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | INGEN3D-TRANSMIT-000177 | NA | Trade Partner | Level 11-13 - PC0476 - Revised IFC | 1 | 0 | 0 | KPTG-IntCorr-000946 | APPROVED | 2026-07-09 | WF-000908 | NA | 2026-07-17 |  | Nich to clarify |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-07 | SMEPS-TRANSMIT-000064 | NA | Trade Partner | STAGE 11-GROUND FLOOR POWER LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 1337 | 2026-07-13 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-005745 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-13 | HDRAus-TRANSMIT-000356 | NA | Consultant | CHILLER ROOM - ARCHITECTURE | 6 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-TRANSMIT-011409 -The revision date is incorrect. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | INGEN3D-TRANSMIT-000178 | NA | Trade Partner | Level 13-15 - PC0522-8 & PC0531-5 - New IFA | 5 | 0 | 0 | KPTG-IntCorr-000947 | APPROVED | 2026-07-09 | WF-000921 | NA | 2026-07-20 |  | Nich to clarify - 2 - Column Elevation for referance - 3 submitted | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002853 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | INGEN3D-TRANSMIT-000179 | NA | Trade Partner | Level 15-17 - PC0528-3 - New IFA | 2 | 0 | 0 | KPTG-IntCorr-000948 | APPROVED |  | NA | NA |  |  | Nich to clarify - Drawings already locked by another w/flow - WF-000854 ,WF-000894 hence no further action |  | 2026-07-09 | EMAIL DTD 9/7/2026 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | INGEN3D-TRANSMIT-000180 | NA | Trade Partner | Level 16-18 - PC0522-11 & PC0539-5 - New IFA | 3 | 0 | 0 | NA | APPROVED | 2026-07-07 | WF-000899 | NA | 2026-07-23 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-002895 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-07 | INGEN3D-TRANSMIT-000181 | NA | Trade Partner | Level 17-19 - PC0579-2 - New IFA | 2 | 0 | 0 | NA | APPROVED | 2026-07-07 | WF-000900 | NA | 2026-07-23 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-07 | ZIA-TRANSMIT-000018 | NA | Trade Partner | CSMS Functional Design Specifications | 0 | 1 | 0 | NA | APPROVED | 2026-07-07 | WF-001157 | NA | 2026-07-18 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-006392 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-07 | SMEPS-TRANSMIT-000065 | NA | Trade Partner | STAGE 10 & 11 PENETRATION LAYOUTS | 5 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 1339 | 2026-07-14 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-005749 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-07 | Year-GCOR-000009 | NA | Trade Partner | Clear Concrete Sealer - CON-I-07 | 0 | 1 | 0 | NA | APPROVED | 2026-07-07 | WF-001150 | NA | 2026-07-14 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-07 | KPTG-IntCorr-001491 | NA | Trade Partner | S9-11 Mayfield Switchboard drawings | 69 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 1329 | 2026-07-14 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-006093 | Closed | 69 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-07 | ASV-TRANSMIT-000075 | NA | Trade Partner | CIVIL STORMWATER SITE PLAN | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Need to revise KPTG-SADV-005996 |  | 2026-07-07 | KPTG-SADV-005996 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-07 | WilsonPD-TRANSMIT-000107 | NA | Trade Partner | S9 Level 1 Sewer and stormwater layout | 1 | 0 | 0 | NA | APPROVED | 2026-07-07 | NA | 1333 | 2026-07-11 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-005404 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-13 | Altaire-TRANSMIT-000053 | NA | Trade Partner | NEXTDC M3S4 - Dry Fire Ground Shop Drawings (For Approval) (1)- | 3 | 0 | 0 | NA | APPROVED | 2026-01-13 |  | 1762 | 2026-01-21 |  |  |  | 2026-01-19 | KPTG-TRANSMIT-011572 | Closed | 3 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-07 | Ardon-TRANSMIT-000005 | NA | Trade Partner | Propose of change - Door Hardware | 0 | 2 | 0 | NA | APPROVED | 2026-07-07 | WF-001154 | NA | 2026-07-16 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-18 | DLTS-TRANSMIT-000029 | NA | Trade Partner | S9-HV Room-IFA Issue | 1 | 0 | 0 | NA | APPROVED | 2026-06-18 | WF-000988 | NA | 2026-06-30 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-005352 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-08 | ELLISAIR-TRANSMIT-000108 | NA | Trade Partner | Expansion & ARU | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, No review required, updated register & distributed |  | 2026-07-08 | KPTG-TRANSMIT-005336 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-08 | ELLISAIR-TRANSMIT-000109 | NA | Trade Partner | Auto Refill & Expansion | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, No review required, updated register & distributed |  | 2026-07-08 | KPTG-TRANSMIT-005339 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-08 | ECBS-TRANSMIT-000058 | NA | Trade Partner | Re: Siniat Wall Type and Ceiling Type Proposal | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect reference Number |  | 2026-07-08 | KPTG-DA-007461 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-08 | ECBS-TRANSMIT-000059 | NA | Trade Partner | Re: Siniat Wall Type and Ceiling Type Proposal Summary | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect reference Number |  | 2026-07-08 | KPTG-DA-007460 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-08 | Auspan-TRANSMIT-000471 | NA | Trade Partner | Re: Resubmit precast shop drawings for approval. Level 1 zone 3. 1P348 and 1P349 | 2 | 0 | 0 | NA | APPROVED | 2026-07-08 | NA | 1434 | 2026-07-15 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-002665 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-08 | Civilex-TRANSMIT-000102 | NA | Trade Partner | FirePro FR - Water based, ﬁre-rated, ﬂexible intumescent sealant | 0 | 1 | 0 | NA | APPROVED | 2026-07-08 | WF-000902 | NA | 2026-07-13 |  | WF-000902,IN WORKFLOW FOR TTW+WAM |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-08 | PCForm-TRANSMIT-000264 | NA | Trade Partner | Stair Form Fire Rail Sample - attempt 2 | 0 | 1 | 0 | NA | APPROVED | 2026-07-08 | WF-000903 | NA | 2026-07-13 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-002799 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-08 | KPTG-IntCorr-000557 | NA | Trade Partner | Appendix A - COLO4 - Security Plan | 0 | 1 | 0 | NA | APPROVED | 2026-07-08 | WF - 000525 | NA | 2026-07-14 |  | NA | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-001087 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-14 | ADP-TRANSMIT-000151 | NA | Consultant | Fwd: S4 ¦ ADP MEL4780 - Battery Room Drawings & Schenatics (FIP) | 4 | 0 | 0 | NA | APPROVED | 2026-01-14 |  | 1766 | 2026-01-18 |  | The register has been updated. If any further action is required, the coordinator will inform. |  | 2026-01-28 | KPTG-TRANSMIT-012064 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-08 | SMEPS-TRANSMIT-000240 | NA | Trade Partner | MEL05C4 Elec Seismic Design - SMEPS-TRANSMIT-000240 | 23 | 0 | 0 | NA | APPROVED | 2026-07-08 | WF - 000526 | NA | 2026-07-10 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-001084 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-08 | ADP-TRANSMIT-000109 | NA | Consultant | ADP MEL4680 - Electrical Spec and Reg 126 | 0 | 2 | 0 | NA | APPROVED | 2026-07-08 | NA | 329 | 2026-07-13 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-001084 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-08 | Auspan-TRANSMIT-000475 | NA | Trade Partner | Precast shop drawings for construction. Level 1 | 10 | 0 | 0 | KPTG-IntCorr-000907 | APPROVED | [5 empty] | IFC - Waiting for Kim advise -KPTG-IntCorr-000895 8 are OK to proceed IFC KPTG-TRANSMIT-002676 1 Rejected as advised by Kapitol PC. KPTG-IntCorr-000905 - DRAFT-009588 Transmitted - KPTG-TRANSMIT-002691 |  | 2026-07-08 | KPTG-TRANSMIT-002676 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-08 | Auspan-TRANSMIT-000475 | NA | Trade Partner | Precast shop drawings for construction. Level 1 | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to same revision as latest and difference in doc number - KPTG-SADV-003371 |  | 2026-07-08 | KPTG-SADV-003371 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-08 | SES AU-TRANSMIT-000077 | NA | Trade Partner | Securitas HAC Prototype | 1 | 0 | 0 | NA | APPROVED | 2026-07-08 | WF-000382 | NA | 2026-07-09 |  | workflow Terminated.KPTG-SADV-001392 |  | 2026-07-08 | KPTG-SADV-001392 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-07-08 | WPD-TRANSMIT-000092 | NA | Trade Partner | Powerpack - O&M Manual Submission | 0 | 1 | 0 | NA | APPROVED | 2026-07-08 | NA | 423 | 2026-07-14 |  | As instructed by Isaiah - Terminated |  | 2026-07-27 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-08 | Auspan-TRANSMIT-000476 | NA | Trade Partner | Precast shop drawings for construction. Level 2 | 6 | 0 | 0 | KPTG-IntCorr-000896 | APPROVED | [5 empty] | IFC - Waiting for Kim advise - KPTG-IntCorr-000896 3 are OK to proceed IFC KPTG-TRANSMIT-002674 3 Rejected as advised by Kapitol PC. KPTG-IntCorr-000902 - DRAFT-009575 |  | 2026-07-08 | KPTG-TRANSMIT-002674 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-08 | ASV-TRANSMIT-000188 | NA | Trade Partner | Hydraulic Asset Labels | 0 | 1 | 0 | NA | APPROVED | 2026-07-08 | WF-006296 | NA | 2026-07-20 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-019643 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-08 | Hollow-TRANSMIT-000021 | NA | Trade Partner | HCC Proposed Grout Submissions | 0 | 2 | 0 | NA | APPROVED | 2026-07-08 | WF-000904 | NA | 2026-07-10 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-002866 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-08 | SMEPS-TRANSMIT-000337 | NA | Trade Partner | Revised Jemena Easement Shopdrawing - 08.07.2026 | 2 | 0 | 0 | NA | APPROVED | 2026-07-08 | WF-006297 | NA | 2026-07-16 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-020021 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-13 | Altaire-TRANSMIT-000053 | NA | Trade Partner | NEXTDC M3S4 - Dry Fire Ground Shop Drawings (For Approval) (1)-3 | 3 | 0 | 0 | NA | APPROVED | 2026-01-13 |  | 1762 | 2026-01-21 |  |  |  | 2026-01-19 | KPTG-TRANSMIT-011572 | Closed | 3 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-08 | Auspan-TRANSMIT-000477 | NA | Trade Partner | Precast shop drawings for construction. Levels 3, 4 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to Difference in revision number -DRAFT-009534 |  | 2026-07-08 | DRAFT-009534 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-08 | Auspan-TRANSMIT-000477 | NA | Trade Partner | Precast shop drawings for construction. Levels 3, 4 | 7 | 0 | 0 | KPTG-IntCorr-000897 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise - KPTG-IntCorr-000897 IFC - 4 Register and transmit - KPTG-TRANSMIT-002976 3 already superseded and transmitted |  | 2026-07-28 | KPTG-TRANSMIT-002976 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-08 | RDSBIM-TRANSMIT-000225 | NA | Trade Partner | LEVEL 00 CONCRETE PROFILE PLAN & ELEVATIONS - | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - only for distribution. |  | 2026-07-08 | KPTG-TRANSMIT-003122 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-08 | SMEPS-TRANSMIT-000338 | NA | Trade Partner | SME -IFA - Documentation | 1 | 0 | 0 | NA | REJECTED | [5 empty] | same revision of the document received via SMEPS-TRANSMIT-000336 |  | 2026-07-08 | KPTG-DA-007466 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-08 | Auspan-TRANSMIT-000478 | NA | Trade Partner | Re: Precast shop drawings for construction. Levels 1, 2 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to same revision as latest- DRAFT-009540 |  | 2026-07-08 | DRAFT-009540 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-08 | DS-TRANSMIT-000124 | NA | Trade Partner | Updated as-built water drawings to include asset tags | 5 | 0 | 0 | NA | APPROVED | 2026-07-08 | NA | 4358 | 2026-07-13 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-020253 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-08 | HGP-TRANSMIT-000061 | NA | Trade Partner | IFA-LOUVRES SHOP DRAWING FOR APPROVAL | 17 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing title, Revision & date are incorrect. |  | 2026-07-08 | KPTG-TRANSMIT-001394 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-08 | SES AU-TRANSMIT-000003 | NA | Trade Partner | Security - S9 Level 1 Floor plan | 1 | 0 | 0 | NA | APPROVED | 2026-07-08 | NA | 1341 | 2026-07-15 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-006296 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-08 | INTRFRM-TRANSMIT-000100 | NA | Trade Partner | Geelong Edge - Electrical Tech Data (Submission 8) - External Plant Area HV Pits FOA-2 | 0 | 1 | 0 | NA | APPROVED | 2026-07-08 | WF-000296 | NA | 2026-07-21 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-001505 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-08 | ADP-TRANSMIT-000366 | NA | Consultant | ADP - CAN-M02 Water Supply to Site | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-08 | KPTG-TRANSMIT-019445 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-14 | D&E-TRANSMIT-000330 | NA | Trade Partner | NXM3S4 - LEGEND AND GENERAL NOTES - Issued For Approval / Review | 1 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-TRANSMIT-011411 - The reference number is incorrect |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-08 | Civilex-TRANSMIT-000283 | NA | Trade Partner | Stage 2 - sample submission - Hytec Mix Design - Rev FOA-F | 0 | 1 | 0 | NA | APPROVED | 2026-07-08 | WF-006300 | NA | 2026-07-14 |  |  | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-019970 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-08 | Auspan-TRANSMIT-000473 | NA | Trade Partner | Update precast cast in plate layout zone 3 | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to difference in title -DRAFT-009543 |  | 2026-07-08 | DRAFT-009543 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-08 | RDSBIM-TRANSMIT-000148 | NA | Trade Partner | MLCSPR ¦ SPORTS CENTRE WEST - LANDSCAPE PLAN- | 3 | 0 | 0 | NA | APPROVED | 2026-07-08 | NA | 377 | 2026-07-13 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003308 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-10 | KPTG-IntCorr-004812 | NA | Trade Partner | Crafted Stainless Alternative Step Techdata | 0 | 1 | 0 | NA | APPROVED | 2026-02-11 | WF-000819 | NA | 2026-02-18 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-003065 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-08 | BIMF-TRANSMIT-000010 | NA | Trade Partner | Level 1 Drainage Plan Building A | 1 | 0 | 0 | NA | APPROVED | 2026-07-08 | NA | 922 | 2026-07-14 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-003345 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-10 | KPTG-IntCorr-004767 | NA | Trade Partner | Crafted Stainless Additional Sample/Tech data resubmission | 0 | 1 | 0 | NA | APPROVED | 2026-02-10 | WF-000814 | NA | 2026-02-18 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-003067 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-08 | Civilex-TRANSMIT-000284 | NA | Trade Partner | Civilex-TRANSMIT-000284-Stage 2 - sample submission - Planter Box | 1 | 0 | 0 | NA | APPROVED | 2026-07-08 | NA | 4360 | 2026-07-15 |  |  | 2026-07-08 | 2026-07-08 | KPTG-IntCorr-015856 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-08 | ECBS-TRANSMIT-000061 | NA | Trade Partner | Re: Siniat Wall Type and Ceiling Type Proposal and Summary | 0 | 2 | 0 | NA | REJECTED | [5 empty] | The document reference number is missing. |  | 2026-07-08 | KPTG-DA-007474 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-08 | INDS-TRANSMIT-000047 | NA | Trade Partner | Wet Fire - Level 1 | 5 | 0 | 0 | NA | APPROVED | 2026-07-08 | NA | 1441 | 2026-07-13 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-002892 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-08 | SES AU-TRANSMIT-000079 | NA | Trade Partner | Securitas HAC Prototype | 1 | 0 | 0 | NA | APPROVED | 2026-07-08 | WF-000383 | NA | 2026-07-13 |  | As per the direction from the Mr Hisham, we have terminated the workflow:WF-000383:KPTG-IntCorr-000674 |  | 2026-07-14 | KPTG-IntCorr-000674 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-14 | NXT-TRANSMIT-001185 / ADEPW-TRANSMIT-000003 | NA | Trade Partner | Fwd: ADE Power Acoustic Generator Enclosure GA Submission | 4 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-003770 |  | 2026-01-30 |  |  |  | 2026-01-19 | KPTG-WTRAN-006940 KPTG-WTRAN-006941 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-26 | PFP PL-TRANSMIT-000093 | NA | Trade Partner | Updated Switch Room Wet Fire Mains Dwgs | 3 | 0 | 0 | NA | APPROVED | 2026-06-26 | NA | 3826 | 2026-07-17 |  | Terminated as requested |  | 2026-08-24 | KPTG-DA-008243 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-08 | D&E-TRANSMIT-000899 | NA | Trade Partner | Functional Description - Issued for Review | 0 | 1 | 0 | NA | APPROVED | 2026-07-08 | WF-006304 | NA | 2026-07-29 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-020296 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-08 | PROLMC-TRANSMIT-000040 | NA | Trade Partner | Re: Proline lift core shop drawing details | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect status |  | 2026-07-08 | KPTG-DA-007476 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-08 | Danlai-TRANSMIT-000006 | NA | Trade Partner | Technical Data | 0 | 3 | 0 | NA | APPROVED | 2026-07-08 | WF-000297 | NA | 2026-07-21 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-001558 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-08 | Danlai-TRANSMIT-000007 | NA | Trade Partner | Technical Data | 0 | 1 | 0 | NA | APPROVED | 2026-07-08 | WF-000298 | NA | 2026-07-21 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-001554 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-08 | ECBS-TRANSMIT-000062 | NA | Trade Partner | Re: C6 & C12 Drawing IFC (31 drawings) | 31 | 0 | 0 | NA | REJECTED | [5 empty] | The IFA for these drawings has not been received for review |  |  | KPTG-DA-007479 | Closed | 31 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-08 | ZIA-TRANSMIT-000117 | NA | Trade Partner | Stage2 - CSMS Cable Sample for Cable rough-in between Penstock Panel to Lower ground OS-B0-02 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision number and Title missing inside the document. |  | 2026-07-08 | KPTG-SADV-006461 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-08 | HGP-TRANSMIT-000063 | NA | Trade Partner | TRANSMITTAL-IFC SHOP DRAWING UPDATE CURTAIN WALL | 101 | 0 | 0 | NA | REJECTED | [5 empty] | Error in attached drawing, with review stamp, Incorrect date, |  | 2026-07-08 | KPTG-TRANSMIT-001397 | Closed | 101 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-08 | Auspan-TRANSMIT-000479 | NA | Trade Partner | Re: Precast shop drawings for construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC Drawing, no review -updated register and distributed - KPTG-TRANSMIT-002671 |  | 2026-07-08 | KPTG-TRANSMIT-002671 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-08 | D&E-TRANSMIT-000284 | NA | Trade Partner | MWYCCB - GROUND LEVEL - DUCTWORK LAYOUT ZONE 1 & ZONE 3 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected by coordinator to submit as IFA |  | 2026-07-08 | KPTG-SADV-005845 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-02 | SKS Tech-TRANSMIT-000097 | NA | Trade Partner | ELECTRICAL SERVICES-PENETRATIONS LAYOUT-DAY 1-LEVEL 4 | 1 | 0 | 0 | NA | APPROVED | 2025-12-02 | NA | 669 | 2025-12-04 |  |  | 2025-12-03 | 2025-12-04 | KPTG-TRANSMIT-002153 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-05 | TTW-TRANSMIT-000066 | N/A | Consultant | Structural Documentation - Issued for Certification | 10 | 0 | 0 | NA | APPROVED | 2026-01-06 | NA | 176 | 2026-01-12 |  |  | 2026-01-14 | 2026-01-14 | KPTG-TRANSMIT-000276 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-08 | D&E-TRANSMIT-000900 | NA | Trade Partner | NXM3S4 - INDUSTRIAL WATER & FOH & BOF AIR SCHEMATICS - Issued For Construction | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-08 | KPTG-TRANSMIT-019481 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-08 | SKS Tech-TRANSMIT-000195 | NA | Trade Partner | Sections and Isometrics Typical Switchroom | 1 | 0 | 0 | NA | APPROVED | 2026-07-08 | NA | 3829 | 2026-07-17 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-08 | NXT-TRANSMIT-001658 | NA | Client | Fwd: M3 Stg 2 - L1 check reports | 0 | 18 | 0 | NA | REJECTED | [5 empty] | Issue with document number, Revision. Details missing inside the document. |  | 2026-07-08 | KPTG-DA-007480 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-08 | M.2-TRANSMIT-000061 | NA | Trade Partner | Electrical Services FTTP Shop drawings | 25 | 0 | 0 | NA | APPROVED | 2026-07-08 | NA | 1445 | 2026-07-15 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-002765 | Closed | 25 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-08 | P & R-TRANSMIT-000094 | NA | Trade Partner | P&R - Tech Data for IFA Amended 08/07 | 0 | 3 | 0 | NA | APPROVED | 2026-07-08 | WF-001034 | NA | 2026-07-10 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-003120 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-08 | Civilex-TRANSMIT-000285 | NA | Trade Partner | Stage 2 - sample submission - eMesh Fibre Concrete - Hytec | 0 | 1 | 0 | NA | APPROVED | 2026-07-08 | WF-006306 | NA | 2026-07-14 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-019699 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-08 | D&E-TRANSMIT-000902 | NA | Trade Partner | Commissioning Plan - Issued for approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-08 | WF-006311 | 0 | 2026-07-08 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-07-08 | WPD-TRANSMIT-000098 | NA | Trade Partner | Hydraulic Services - B18 - Updated As Builts | 4 | 0 | 0 | NA | APPROVED | 2026-07-08 | NA | 427 | 2026-07-21 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-08 | M.S.-TRANSMIT-000024 | NA | Trade Partner | No longer in use shop drawings | 32 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer in Use - Register upated |  | 2026-07-08 | KPTG-SADV-005852 | Closed | 32 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-08 | M.S.-TRANSMIT-000023 | NA | Trade Partner | No longer in use shop drawings | 32 | 0 | 0 | NA | REJECTED | [5 empty] | Already received M.S.-TRANSMIT-000024 |  | 2026-07-08 | KPTG-SADV-005851 | Closed | 32 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-14 | ABB-TRANSMIT-000013 | NA | Trade Partner | Fwd: Primary drawings for M3-22-HVSB-B for contruction | 1 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-003776 |  | 2026-01-30 |  | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-08 | SMEPS-TRANSMIT-000339 | NA | Trade Partner | STAGE 2 - ELECTRICAL INGROUND LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-07-08 | NA | 4363 | 2026-07-21 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-08 | SMEPS-SUBADVICE-000331 | NA | Trade Partner | C1 test results | 0 | 18 | 0 | NA | APPROVED | 2026-07-08 | WF - 000539 | NA | 2026-07-14 |  | NA | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-001106 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-08 | CNGC-TRANSMIT-000005 | NA | Trade Partner | CGC_Procurement _TDS | 0 | 4 | 0 | NA | APPROVED | 2026-07-08 | WF-006310 | NA | 2026-07-13 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-08 | Civilex-TRANSMIT-000286 | NA | Trade Partner | Stage 2 - sample submission - Planter Box - Rev D | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with Revision. |  | 2026-07-08 | KPTG-SADV-006467 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-08 | D&E-TRANSMIT-000903 | NA | Trade Partner | BMS Points List - Issued for Construction | 0 | 1 | 0 | NA | REJECTED | [5 empty] | FC revision submitted without FR gets approved. Previous FR revision is reviewed with Status Revise and Resubmit. |  | 2026-07-08 | KPTG-SADV-006470 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-08 | ADP-TRANSMIT-000367 | NA | Consultant | ADP MEL 4780 - Updated in ground Electrical Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-07-08 | NA | 3833 | 2026-07-13 |  |  | 2026-07-31 | 2026-07-30 | KPTG-TRANSMIT-020238 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-08 | VinageC-TRANSMIT-000002 | NA | Trade Partner | Re: Signage | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The document reference number and revision number have not been assigned correctly. Please update them and resubmit the document |  | 2026-07-08 | KPTG-DA-007490 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-08 | TTW-TRANSMIT-000045 DWG | NA | Consultant | Facade drawing-For Tender | 16 | 0 | 0 | NA | APPROVED | 2026-07-08 | NA | 350 | 2026-07-16 |  |  | 2026-07-21 | 2026-07-22 | KPTG-TRANSMIT-000650 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-08 | TTW-TRANSMIT-000045-SPE | NA | Consultant | Facade specification-For Tender | 0 | 1 | 0 | NA | APPROVED | 2026-07-08 | NA | 352 | 2026-07-16 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-000573 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-08 | WGAVIC-TRANSMIT-000009 | NA | Consultant | Civil Grading Plans - Issued for Construction | 2 | 0 | 0 | NA | APPROVED | 2026-07-08 | NA | 348 | 2026-07-16 |  |  | 2026-07-23 | 2026-07-24 | KPTG-TRANSMIT-000700 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-14 | ABB-TRANSMIT-000014 | NA | Trade Partner | Fwd: Primary drawings for M3-22-HVSB-D for contruction | 1 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-003777 |  | 2026-01-30 |  | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-08 | D&E-TRANSMIT-000023 | NA | Trade Partner | LEVEL 1 CHW PIPEWORK LAYOUTS ZONE 11 & 9 | 2 | 0 | 0 | KPTG-IntCorr-000276 | APPROVED | 2026-07-17 | NA | 454 | 2026-07-27 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-08 | 4DW-TRANSMIT-000064 | NA | Consultant | Block 1 - Precast walls issued with Construction updates | 4 | 0 | 0 | NA | APPROVED | 2026-07-08 | NA | 354 |  |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-000780 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-08 | 4Ki-TRANSMIT-000012 | NA | Trade Partner | Shop Drawings For Approval - JNR001, JNR004, JNR014, JNR015 | 1 | 0 | 0 | NA | APPROVED | 2026-07-08 | WF-001146 | NA | 2026-07-13 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-004181 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-08 | GIW-TRANSMIT-000003 | NA | Consultant | J1V3 Report and ESD Markup | 0 | 2 | 0 | NA | APPROVED | 2026-07-08 | NA | 303 | 2026-07-15 |  | Voided- Updated document received from GIW |  | 2026-08-31 | KPTG-CONTADV-000328 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-08 | TURN--TRANSMIT-000009 | NA | Consultant | Steel PFC Shop Drawings Rev 1 | 2 | 0 | 0 | NA | APPROVED | 2026-07-08 | NA | 301 | 2026-07-10 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-000220 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-07-08 | WPD-TRANSMIT-000097 | NA | Trade Partner | Re: HFF - Wilson PD O&M Manual Submission | 0 | 1 | 0 | KAPITOL-INTCOR-001252 | APPROVED |  | NA | NA |  |  | Waiting for a response from Alex |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-08 | Auscool-TRANSMIT-000101 | NA | Trade Partner | CCW Anchor Design For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-08 | WF-000818 | NA | 2026-07-14 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-002857 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-08 | Auspan-TRANSMIT-000472 | NA | Trade Partner | : Precast shop drawings for construction. | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC -KPTG-IntCorr-000888 ok to transmit all EXCEPT 1P333 (to be superseded) 1 drawing Rejected; DRAFT-009519 2 drawings updated and transmitted -KPTG-TRANSMIT-002648 |  | 2026-07-08 | KPTG-TRANSMIT-002648 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-08 | Auspan-TRANSMIT-000474 | NA | Trade Partner | : Resubmit precast shop drawings for approval. Panel 1P4056 | 1 | 0 | 0 | NA | APPROVED | 2026-07-08 | NA | 1432 | 2026-07-15 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-002668 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-09 | RDSBIM-TRANSMIT-000010 | N/A | Trade Partner | LEVEL 02 CONCRETE PROFILE PLAN AND SECTIONS | 6 | 0 | 0 | NA | APPROVED | 2026-01-12 | NA | 190 | 2026-01-14 |  |  | 2026-02-03 | 2026-02-03 | KPTG-TRANSMIT-000406 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-08 | Auspan-TRANSMIT-000480 | NA | Trade Partner | Re: Update precast cast in plate layout zone 3 | 5 | 0 | 0 | KPTG-IntCorr-000904 | APPROVED |  | NA | NA |  |  | IFC Waiting for KIM advise - KPTG-IntCorr-000904 Drawings superseded via Auspan-TRANSMIT-000485 |  | 2026-07-20 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-08 | SES AU-TRANSMIT-000078 | NA | Trade Partner | SECURITY - COLO 4 AND 5 QA SECTIONS | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Drawing status needs to be For Approval:KPTG-SADV-001418 |  | 2026-07-08 | KPTG-SADV-001418 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-08 | Auscool-TRANSMIT-000103 | NA | Trade Partner | Smoke Damper For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-08 | WF-000820 | NA | 2026-07-14 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-08 | Auscool-TRANSMIT-000098 | NA | Trade Partner | CCW Anchor Design For Approval | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-001165-DOCUMENT NO INCORRECT | 2026-07-08 | 2026-07-08 | KPTG-IntCorr-001165 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-08 | Auscool-TRANSMIT-000099 | NA | Trade Partner | Smoke Damper For Approval | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004835 - DOCUMENT NO INCORRECT | 2026-07-08 | 2026-07-08 | KPTG-SADV-004835 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-08 | Auscool-TRANSMIT-000100 | NA | Trade Partner | Fire Damper Tech Data For Approval | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004836 - DOCUMENT NO INCORRECT | 2026-07-08 | 2026-07-08 | KPTG-SADV-004836 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-08 | RDSBIM-TRANSMIT-000083 | NA | Trade Partner | 671CHP LEVEL 01 CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | KPTG-IntCorr-000913 | APPROVED | 2026-07-09 | NA | 641 | 2026-07-16 |  | Kapitol to advise -KPTG-IntCorr-000913 |  | 2026-07-24 | KPTG-TRANSMIT-001418 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-08 | LGCE-TRANSMIT-000050 | NA | Trade Partner | Ground floor IFC light and power | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to QC Error - KPTG-IntCorr-000907 |  | 2026-07-08 | KPTG-IntCorr-000907 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-08 | LGCE-TRANSMIT-000053 | NA | Trade Partner | Level 3 light and power | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to QC Error - KPTG-IntCorr-000908 |  | 2026-07-08 | KPTG-IntCorr-000908 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-09 | RDSBIM-TRANSMIT-000011 | N/A | Trade Partner | GROUND FLOOR TO LEVEL 09 STAIR CORE 1 CONCRETE PROFILE PLAN SECTION AND ELEVATION | 8 | 0 | 0 | NA | APPROVED | 2026-01-13 | NA | 191 | 2026-01-16 |  |  | 2026-02-12 | 2026-02-12 | KPTG-TRANSMIT-000432 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-08 | LGCE-TRANSMIT-000054 | NA | Trade Partner | Ground floor light and power | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to QC Error - KPTG-IntCorr-000909 |  | 2026-07-08 | KPTG-IntCorr-000909 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-08 | POTTSENG-TRANSMIT-000031 | NA | Trade Partner | : 671C: HYDRAULIC SERVICES - LEVEL 02 - PENETRATION LAYOUT | 2 | 0 | 0 | KPTG-IntCorr-000914 | APPROVED | [5 empty] | Tayla to confirm KPTG-IntCorr-000914 No review required. - KPTG-IntCorr-000915 |  | 2026-07-09 | KPTG-IntCorr-000915 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-08 | IJF-TRANSMIT-000005 | NA | Trade Partner | Prototype Drawings for Approval | 37 | 0 | 0 | NA | APPROVED | 2026-07-16 | WF-000587 | NA | 2026-07-15 |  | WF-000562 terminated on 16-07-26 as advised by PC. and initiated another workflow - WF-000587 | 2026-07-20 | 2026-07-20 | KPTG-WTRAN-000911 | Closed | 37 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-08 | Jordan-TRANSMIT-000131 | NA | Trade Partner | Revised Hydraulic Reticulation Shop Drawings | 7 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Document No. Error |  | 2026-07-08 | KPTG-IntCorr-001674 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-08 | Baigents-TRANSMIT-000226 | NA | Trade Partner | L5 Handrail for construction | 22 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | fc doc send to all parties |  | 2026-07-08 | KPTG-TRANSMIT-004049 | Closed | 22 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-08 | Baigents-TRANSMIT-000227 | NA | Trade Partner | Lobby Handrail FC-1 | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | fc doc send to all parties |  | 2026-07-08 | KPTG-TRANSMIT-004052 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-08 | WDes-TRANSMIT-000056 | NA | Trade Partner | Civil - Revised Public Domain Drawings | 56 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | NA | 2026-07-24 |  | NA | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-003199 | Closed | 56 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-08 | KALLIBRE-TRANSMIT-000010 | NA | Trade Partner | IFA - Mailbox Colour Samples | 0 | 4 | 0 | NA | APPROVED | 2026-07-08 | WF - 001072 | NA | 2026-07-15 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-08 | KPTG-IntCorr-001527 M2 S9-11 Battery Room Electrical Tech Data | NA | Trade Partner | M2 S9-11 Battery Room Electrical Tech Data | 0 | 11 | 0 | NA | APPROVED | 2026-07-08 | WF-001171 | NA | 2026-07-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-08 | KPTG-IntCorr-001528 | NA | Trade Partner | M2 S9-11 Battery Room Revised Electrical Drawings | 8 | 0 | 0 | NA | APPROVED | 2026-07-08 | NA | 1345 | 2026-07-11 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-006148 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-12 | TTW-TRANSMIT-000068 | N/A | Consultant | Civil Drawing Updates | 3 | 0 | 0 |  | REJECTED | [5 empty] | rejected : cad and pdf revision errors |  | 2026-01-13 | KPTG-DA-000488 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-18 | SES AU-TRANSMIT-000001 | NA | Trade Partner | Security Samples | 0 | 5 | 0 | NA | APPROVED | 2026-06-18 | WF-000977 | NA | 2026-06-25 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-005356 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-08 | PROLMC-TRANSMIT-000004 | NA | Trade Partner | Proline Box Gutter Shop Drawings IFC Approval | 3 | 0 | 0 | NA | APPROVED | 2026-07-08 | WF-001164 | NA | 2026-07-15 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-005736 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-08 | Eneraque-TRANSMIT-000037 | NA | Trade Partner | ENE - Fill Cabinet Wiring Diagrams | 2 | 0 | 0 | NA | APPROVED | 2026-07-08 | NA | 1343 | 2026-07-15 |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-006232 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | BTBM-TRANSMIT-000003 | NA | Trade Partner | Better Built Masonry Tech data | 0 | 1 | 0 | NA | APPROVED | 2026-07-02 | WF-001113 | NA | 2026-07-08 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-005347 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-09 | RDSBIM-TRANSMIT-000062 | NA | Trade Partner | MWYCCB ¦ L01 RCP KEY PLAN AND LAYOUT | 5 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 341 | 2026-07-16 |  | Terminated As per Peter advise Reason: To Update latest drawings |  | 2026-08-28 | KPTG-IntCorr-004204 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-09 | SES AU-TRANSMIT-000080 | NA | Trade Partner | SECURITY - COLO 4 AND 5 QA Sections | 3 | 0 | 0 | NA | APPROVED | 2026-07-09 | WF-000384 | NA | 2026-07-14 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-001058 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-09 | PMT Sec-TRANSMIT-000024 | NA | Trade Partner | NEL-CNT-PMT-2801-SEC-SAM-0001.Rev 3 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Actual submitted date-07/07/2026 |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-09 | SMEPS-TRANSMIT-000066 | NA | Trade Partner | STAGE 11-LEVEL 1 & 2 POWER LAYOUTS | 2 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 1347 | 2026-07-16 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-005768 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-09 | PMT Sec-TRANSMIT-000025 | NA | Trade Partner | NEL-CNT-PMT-2801-SEC-SAM-0017 Rev 2 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Actual submitted date 07/07/2026 Revision date is incorrect |  | 2026-07-09 | KPTG-TRANSMIT-001398 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-09 | SMEPS-TRANSMIT-000067 | NA | Trade Partner | Stage 9-11 Jemena Easement Plan & Sections | 1 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 1348 | 2026-07-16 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-13 | KETE-TRANSMIT-000108 | NA | Trade Partner | Kete - Updated IFC Podium Shop Drawing | 61 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-000560 |  | 2026-01-19 |  |  |  | 2026-02-04 | KPTG-TRANSMIT-001729 | Closed | 60 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-09 | PMT Sec-TRANSMIT-000026 | NA | Trade Partner | NEL-CNT-PMT-2801-SEC-SAM-0022 Rev 2 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision inside document and in Aconex seem different Revision date is incorerct |  | 2026-07-09 | KPTG-TRANSMIT-001399 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-09 | RDSBIM-TRANSMIT-000289 | NA | Trade Partner | NXM3S4 ¦ ROOF PARTITION WALL KEY PLAN AND ELEVATION | 2 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 3835 | 2026-07-15 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-020027 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-09 | SMEPS-TRANSMIT-000023 | NA | Trade Partner | Solar Design | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF - 001073 | NA | 2026-07-15 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-09 | SMEPS-TRANSMIT-000241 | NA | Trade Partner | MEL05C4 Electrical Labelling Schedule. | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF -000540 | NA | 2026-07-15 |  | NA | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-001116 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-09 | SRA-PMQ-TRANSMIT-000013 | NA | Trade Partner | Update Ceiling Tile Documents | 0 | 3 | 0 | NA | APPROVED | 2026-07-09 | WF-000299 | NA | 2026-07-22 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001402 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-09 | Auspan-TRANSMIT-000481 | NA | Trade Partner | Re: Zone 1 RFi 71. Update IFCed shop drawings. | 13 | 0 | 0 | KPTG-IntCorr-000909 | APPROVED | [5 empty] | IFC - Waiting for Kim advise - KPTG-IntCorr-000909 12 Drawings registered and transmitted - KPTG-TRANSMIT-002702 1 drawing rejected as advised by PC. DRAFT-009668. |  | 2026-07-10 | KPTG-TRANSMIT-002702 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-09 | Auspan-TRANSMIT-000481 | NA | Trade Partner | Re: Zone 1 RFi 71. Update IFCed shop drawings. | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to difference in revision code, title and status - DRAFT-009595 |  | 2026-07-09 | DRAFT-009595 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-09 | NXT-PA-005779 | NA | Trade Partner | Re: Updated Shop Drawing Revision - All Block C1 | 14 | 0 | 0 | NA | APPROVED | 2026-07-09 | WF-006314 | NA | 2026-07-22 |  | EAEGROUP-TRANSMIT-000111 From Rohit - All drawings except the loadbank drawing to be put into a WF, Jackson to advise who needs to review, i have CC'ed him in. NXT-PA-005779 | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-020593 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-09 | SIL-TRANSMIT-000036 | NA | Trade Partner | MEL11 COLO4-5 Siemens ATS Documents submission | 0 | 7 | 0 | NA | APPROVED |  | NA | NA |  |  | As per the direction From Mr Ayaan Rahman Kapitol Project Team, We do not initiate workflow for these documents. We just updated our document Register-KPTG-IntCorr-000665 |  | 2026-07-09 | KPTG-IntCorr-000665 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-09 | EAEGROUP-TRANSMIT-000112 | NA | Trade Partner | Updated Shop Drawing Revision - Loadbank & FI & FJ bypass | 2 | 0 | 0 | NA | APPROVED | 2026-07-09 | WF-006315 | NA | 2026-07-22 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-020589 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-13 | KETE-TRANSMIT-000109 | NA | Trade Partner | Submission – IFA shop drawings | 10 | 0 | 0 | NA | APPROVED | 2026-01-13 | WF-000558 |  | 2026-01-19 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-002494 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-09 | PMT Sec-TRANSMIT-000027 | NA | Trade Partner | Security Cabinets Rev 2 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision inside document and in Aconex seem different and revision date is incorrect |  | 2026-07-09 | KPTG-TRANSMIT-001400 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-09 | VERTIV-TRANSMIT-000043 | NA | Trade Partner | NEXT DC GE01 _ MATERIAL SUBMISSION _ LV SWITCHBOARD (FOA-3) | 0 | 1 | 0 | NA | REJECTED | 2026-07-09 | WF-000303 | NA | 2026-07-22 |  | Issue with document status. Proceeded as advised by Chri Doh. | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-001152 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-09 | SIL-TRANSMIT-000034 | NA | Trade Partner | MEL11 COLO4-5 PDU Assembly Verification Report | 0 | 2 | 0 | NA | APPROVED | 2026-07-09 | WF-000385 | NA | 2026-07-13 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-001085 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-09 | Auspan-TRANSMIT-000482 | NA | Trade Partner | Resubmit precast shop drawings for approval. Level 2 | 2 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 1450 | 2026-07-16 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-002796 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-09 | PROLMC-TRANSMIT-000041 | NA | Trade Partner | Proline parapet flashings detail | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect status |  | 2026-07-09 | KPTG-TRANSMIT-019503 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-09 | RDSBIM-TRANSMIT-000014 | NA | Trade Partner | NXGE01 ¦ GROUND FLOOR CONCRETE PROFILE KEY PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 331 | 2026-07-15 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001329 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-30 | Jangho-TRANSMIT-000049 | NA | Trade Partner | Backer rod Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-07-30 | WF-000461 | NA |  |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-002787 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-07-09 | VinageC-TRANSMIT-000003 | NA | Trade Partner | Re: Signage | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect status |  | 2026-07-09 | KPTG-DA-007503 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-09 | PMT Sec-TRANSMIT-000028 | NA | Trade Partner | Security cabinet keylock | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document revision and date is incorrect Actual submitted date 07/07/2026 |  | 2026-07-09 | KPTG-TRANSMIT-001401 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-09 | SMEPS-TRANSMIT-000029 | NA | Trade Partner | Tech Data: Containment and Unistrut | 0 | 2 | 0 | NA | APPROVED | 2026-07-09 | WF-000301 | NA | 2026-07-22 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-001752 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-13 | ARCH-TRANSMIT-000129 | NA | Consultant | MLC - SPR - Drawing Update | 5 | 0 | 0 | NA | APPROVED | 2026-01-13 |  | 391 | 2026-01-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-09 | ELLISAIR-TRANSMIT-000111 | NA | Trade Partner | Stage 11 Ground floor Duct Layout drawings issued for Approval. | 8 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 1350 | 2026-07-16 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-006032 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-09 | PMT Sec-TRANSMIT-000029 | NA | Trade Partner | NEL-CNT-PMT-2801-SEC-SAM-0030 Rev 2Dual head Bollard | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document revision and date is incorrect |  | 2026-07-09 | KPTG-TRANSMIT-001402 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-09 | Entire M-TRANSMIT-000060 | NA | Trade Partner | BMS Equipment - Issued for Approval FOA-1 | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-000302 | NA | 2026-07-22 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-001706 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-09 | ccair-TRANSMIT-000129 | NA | Trade Partner | VSD schedule IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - |  | 2026-07-09 | KPTG-TRANSMIT-003130 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-09 | D&E-TRANSMIT-000906 | NA | Trade Partner | Flushing Bypasses - Issued for approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-006316 | NA | 2026-07-15 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-09 | ADP-TRANSMIT-000110 | NA | Trade Partner | ADP MEL4680 - Hydraulic Reg 126 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For updating register only. |  | 2026-07-09 | KPTG-TRANSMIT-001077 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-09 | D&E-TRANSMIT-000905 | NA | Trade Partner | CDW & CHW flushing procedure - Issued for Construction | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision, Title is not mentioned inside the document |  | 2026-07-09 | KPTG-DA-007509 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-09 | VERTIV-TRANSMIT-000044 | NA | Trade Partner | NEXT DC GE01 _ TECHNICAL DATA _ BUS DUCT (FOA-2) | 0 | 1 | 0 | NA | REJECTED | 2026-07-09 | WF-000305 | NA | 2026-07-22 |  | Issue with document status in Aconex submission. Processed as request by Chri Doh |  | 2026-07-22 | KPTG-TRANSMIT-001233 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-09 | M.S.-TRANSMIT-000026 | NA | Trade Partner | Revised Shop Drawings for Approval | 32 | 0 | 0 | NA | REJECTED | [5 empty] | Revision and date inside the document are incorrect |  | 2026-07-09 | KPTG-TRANSMIT-001403 | Closed | 32 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-13 | CLADC-TRANSMIT-000011 | NA | Trade Partner | Updated tech data and hardware list as requested | 0 | 15 | 0 | NA | REJECTED | [5 empty] | Revision of all tech data are incorrect |  | 2026-01-13 | KPTG-SADV-003283 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-09 | ZIA-TRANSMIT-000119 | NA | Trade Partner | Re: Stage2 - CSMS Cable Sample for Cable rough-in between Penstock Panel to Lower ground OS-B0-02 | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-006319 | NA | 2026-07-20 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-020046 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-09 | JCBa-TRANSMIT-000152 | NA | Consultant | IFC: Updated Elevation & Stair Drawings – A-3101, A-3104, A-3108, A-3208, A-3213 & A-4406 | 6 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 1452 | 2026-07-13 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-002800 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-09 | fjc-TRANSMIT-000163 | NA | Consultant | GRC portal WIP Documentation | 3 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 687 | 2026-07-14 |  |  | 2026-07-10 | 2026-07-10 | KPTG-SADV-004886 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-09 | SMEPS-TRANSMIT-000068 | NA | Trade Partner | STAGE 10 - LEVEL 1 & 2 LIGHTING LAYOUTS | 2 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 1352 | 2026-07-16 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-006074 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-09 | Nilsen3-TRANSMIT-000227 | NA | Trade Partner | Nilsen Sample - IFC | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Updated revision date received in Nilsen3-TRANSMIT-000228 |  | 2026-07-09 | KPTG-DA-007513 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-09 | Nilsen3-TRANSMIT-000228 | NA | Trade Partner | Nilsen Sample - IFC | 0 | 1 | 0 | NA | APPROVED | [5 empty] | For distribution | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-019521 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-09 | SMEPS-TRANSMIT-000069 | NA | Trade Partner | STAGE 10 - LEVEL 1 & 2 POWER LAYOUTS | 2 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 1354 | 2026-07-16 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-005883 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-09 | SMEPS-TRANSMIT-000230 | SPARK-CRFI KPG-000388 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0602 | 1 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 342 | 2026-07-16 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-001423 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-02 | SMEPS-TRANSMIT-000239 | NA | Trade Partner | SME - IFC Submission - Telecommunications Drawings | 9 | 0 | 0 | NA | APPROVED | 2025-12-02 | NA | 1276 | 2025-12-11 |  |  | 2026-01-27 | 2026-01-28 | KPTG-TRANSMIT-002355 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-13 | Tensile-IntCorr-000004 | NA | Trade Partner | Re: MLC - Tensile Onboarding | 0 | 4 | 0 | NA | APPROVED | 2026-01-13 | WF-000703 |  | 2026-01-15 |  |  |  | 2026-02-04 | KPTG-TRANSMIT-002301 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-08 | Auscool-TRANSMIT-000102 | NA | Trade Partner | Fire Dmper For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-08 | WF-000819 | NA | 2026-07-14 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-08 | Auscool-TRANSMIT-000097 | NA | Trade Partner | Issued For Approval - Fire & Smoke Damper, CCW Anchor Design | 0 | 3 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004833 - doc no , tittle incorrect | 2026-07-08 | 2026-07-08 | KPTG-SADV-004833 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-09 | EFP-TRANSMIT-000031 | NA | Trade Partner | EFP Tech Data Alternative | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-000386 | NA | 2026-07-15 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-001112 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-09 | Altaire-TRANSMIT-000020 | NA | Trade Partner | NEXTDC M2S11 - Shop Drawings (FC-A) (3) | 2 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 1356 | 2026-07-16 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-005589 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-09 | Civilex-TRANSMIT-000288 | NA | Trade Partner | Stage 2 - sample submission - Planter Box - Rev E | 1 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 4366 | 2026-07-22 |  | Terminated as requested by Originator to submit the updated drawings. Confirmed by Charlie Johnstone. | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-019779 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-07-09 | PSGV-TRANSMIT-000010 | NA | Trade Partner | Re: HFF - O&M manual | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-000515 | NA | 2026-07-20 |  | KAPITOL-TRANSMIT-001362 |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-09 | KALLIBRE-TRANSMIT-000011 | NA | Trade Partner | Mailbox Shop Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-07-09 | WF - 001074 | NA | 2026-07-15 |  | NA | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-003174 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-09 | D&E-TRANSMIT-000907 | NA | Trade Partner | Re: CDW & CHW flushing procedure - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-006322 | NA | 2026-07-14 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-09 | Entire M-TRANSMIT-000061 | NA | Trade Partner | Valves & Valve Actuators - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-000304 | NA | 2026-07-22 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-001697 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-09 | ZIA-TRANSMIT-000019 | NA | Trade Partner | M2 CSMS Layer 2 Ethernet Switch (FOA-3) | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-001184 | NA | 2026-07-21 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-13 | CEDWA-TRANSMIT-000003 | NA | Consultant | Updated Civil Drawings | 3 | 0 | 0 | NA | REJECTED | [5 empty] | QA Rejected - KPTG-IntCorr-000861 |  | 2026-01-13 | KPTG-IntCorr-000861 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-07-09 | VinageC-TRANSMIT-000004 | NA | Trade Partner | Signage | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-006323 | NA | 2026-07-22 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-019703 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-09 | M.S.-TRANSMIT-000027 | NA | Trade Partner | Revised Shop Drawings for Approval | 32 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 343 | 2026-07-16 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-001642 | Closed | 32 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-07-06 | WPD-TRANSMIT-000096<br> | NA | Trade Partner | Re: HFF - Wilson PD O&M Manual Submission | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-000516 | NA | 2026-07-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-07-06 | WPD-TRANSMIT-000096<br> | NA | Trade Partner | Re: HFF - Wilson PD O&M Manual Submission | 0 | 1 | 0 | NA | APPROVED | [9 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-09 | ACG-TRANSMIT-000109 | NA | Trade Partner | M3 - Site Wide - Intercom Mounting Details | 1 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 4368 | 2026-07-20 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-020355 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-09 | ECBS-TRANSMIT-000044 | NA | Trade Partner | Shop Drawings For Approval (Batch 2: 15dwgs) | 45 | 0 | 0 | NA | APPROVED | 2026-07-09 | WF-006325 | NA | 2026-07-22 |  | As instructed by Peter -terminated and placed in new WF |  | 2026-07-10 | NA | Closed | 45 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-09 | Ardon-TRANSMIT-000006 | NA | Trade Partner | Re-submission of Ground Level Shop Drawings | 17 | 0 | 0 | NA | APPROVED | 2026-07-09 | WF-001186 | NA | 2026-07-14 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-09 | JCI-TRANSMIT-000033 | NA | Trade Partner | BAS SAT Test Rev02 | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF - 000541 | NA | 2026-07-15 |  | NA | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-001118 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-09 | Auspan-TRANSMIT-000483 | NA | Trade Partner | Precast shop drawings for construction. Level 1. | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC: No review , Updated register and transmitted: KPTG-TRANSMIT-002693 |  | 2026-07-09 | KPTG-TRANSMIT-002693 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-09 | Caruso-TRANSMIT-000001 | NA | Trade Partner | Blockwork Tech Data | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Issues with document number, revision. |  | 2026-07-09 | KPTG-SADV-006504 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-14 | Altaire-TRANSMIT-000055 | NA | Trade Partner | NEXTDC M3S4 Dry Fire Tech Data (For Approval) | 1 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-003779 |  | 2026-02-04 |  |  |  | 2026-02-16 | KPTG-TRANSMIT-012918 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-09 | ARCST-TRANSMIT-000335 | NA | Trade Partner | Re: C1 Cooling Tower HD Bolts - Issued for Construction | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Reference number is missing |  | 2026-07-09 | KPTG-DA-007521 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-09 | WilsonPD-TRANSMIT-000205 | NA | Trade Partner | Fixtures Approval | 0 | 3 | 0 | NA | REJECTED |  |  | Titile inside document and in Aconex are different and revision is missing |  |  |  |  | 2026-07-09 | KPTG-TRANSMIT-001406 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-09 | ADP-TRANSMIT-000112 | NA | Consultant | ADP MEL4680 - Updated Mechanical Drawings | 28 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 333 | 2026-07-14 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001317 | Closed | 28 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-09 | Civilex-TRANSMIT-000287 | NA | Trade Partner | Stage 2 - sample submission - Planter Box - Rev E | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issues with Revision History. |  | 2026-07-09 | KPTG-SADV-006481 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | Jangho-TRANSMIT-000232 | NA | Trade Partner | Tower Level 6~10 Cast in Channel | 12 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 927 | 2026-07-15 |  |  | 2026-07-17 | 2026-07-20 | KPTG-TRANSMIT-002987 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | Jangho-TRANSMIT-000233 | NA | Trade Partner | Podium Level 3~5 Cast in Channel Shop Drawing | 11 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 930 | 2026-07-15 |  |  | 2026-07-17 | 2026-07-20 | KPTG-TRANSMIT-002981 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | Jangho-TRANSMIT-000234 | NA | Trade Partner | Podium Level 1~2 Cast in Channel Shop Drawing | 2 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 936 | 2026-07-15 |  | 1 Doc rejected-KPTG-TRANSMIT-002790 | 2026-07-17 | 2026-07-20 | KPTG-TRANSMIT-002984 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | Jangho-TRANSMIT-000236 | NA | Trade Partner | Podium Level 1~2 Cast in Channel Shop Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 936 | 2026-07-15 |  |  | 2026-07-17 | 2026-07-20 | KPTG-TRANSMIT-002984 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | BIMF-TRANSMIT-000011 | NA | Trade Partner | Level 1 Drainage Plan, Building B | 1 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 932 | 2026-07-15 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-002904 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | RDSBIM-TRANSMIT-000057 | NA | Trade Partner | GROUND FLOOR TO LEVEL 02 STAIR/LIFT CORE 03 CONCRETE PROFILE PLAN ¦ SECTIONAL ELEVATIONS | 4 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 934 | 2026-07-15 |  |  | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-003081 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-13 | KETE-TRANSMIT-000027 | NA | Trade Partner | updated ground floor louvre drawing | 8 | 0 | 0 | NA | APPROVED | 2026-01-13 | NA | 816 | 2026-01-16 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-002929 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | RDSBIM-TRANSMIT-000058 | NA | Trade Partner | LEVEL 09 TO LEVEL 18 STAIR CORE 04 CONCRETE PROFILE PLAN ¦ SECTIONAL ELEVATIONS | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | rejected : issued via Trn # 59 |  | 2026-07-09 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-09 | RBG-TRANSMIT-000007 | NA | Trade Partner | Crane Base Drawings IFC | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | update register only |  | 2026-07-09 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-09 | RDSBIM-TRANSMIT-000014 | NA | Trade Partner | GROUND LEVEL BLOCK 1 ¦ CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | KPTG-IntCorr-000281 | APPROVED | 2026-07-14 | NA | 385 | 2026-07-22 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-09 | ACCCA-TRANSMIT-000011 | NA | Trade Partner | Electrical Pit Approval | 6 | 0 | 0 | KPTG-IntCorr-000280 | APPROVED | 2026-07-13 | NA | 378 | 2026-07-21 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-000550 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-09 | Baigents-TRANSMIT-000014 | NA | Trade Partner | Panel P21 | 1 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 356 | 2026-07-17 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-000527 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-09 | KPTG-TRANSMIT-000497 | NA | Trade Partner | Beam Concrete Mix Design For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | NA | 359 | 2026-07-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-09 | PTA-TRANSMIT-000020 | NA | Consultant | Staircase Update - Issue For Coordination | 10 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 361 | 2026-07-17 |  | NA | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001006 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-09 | LGCE-TRANSMIT-000056 | NA | Trade Partner | Drawing Update (Ground floor light and power) | 2 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 632 | 2026-07-16 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-001402 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-01-14 | DI-TRANSMIT-000133 | NA | Trade Partner | HFF - For Construction Issue | 44 | 0 | 0 | NA | APPROVED | 2026-01-14 |  | 271 | 2026-01-17 |  |  |  | 2026-01-16 | KAPITOL-TRANSMIT-000988 | Closed | 44 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-09 | LGCE-TRANSMIT-000056 | NA | Trade Partner | Drawing Update ( Level 3 light and power) | 2 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 633 | 2026-07-16 |  |  | 2026-08-07 | 2026-08-14 | KPTG-TRANSMIT-001586 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-09 | ccair-TRANSMIT-000024 | NA | Trade Partner | Mechanical Services L01 Builders works IFA [B] | 1 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 636 | 2026-07-16 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-001494 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-09 | ccair-TRANSMIT-000025 | NA | Trade Partner | Mechanical Services L02 and 03 Builders works IFA [B] | 2 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 637 | 2026-07-16 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-001557 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-09 | RBG-TRANSMIT-000065 | NA | Consultant | Updated structural drawings for steelwork | 2 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 639 | 2026-07-13 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-001457 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-09 | INDS-TRANSMIT-000048 | NA | Trade Partner | Dry Fire - Level 1 | 5 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 1454 | 2026-07-16 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-002897 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-09 | Auscool-TRANSMIT-000057 | NA | Trade Partner | : Condenser & Black Fin Tech Data - Q1692-MECH-SMP-035 | 0 | 1 | 0 | KPTG-IntCorr-000919 | APPROVED | 2026-07-10 | WF-000701 | NA | 2026-07-15 |  | Kapitol PC to advise KPTG-IntCorr-000919 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-09 | KPTG-TRANSMIT-004060 | NA | Client | Meeting room table Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-001149 | NA | [6 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-09 | PARR-TRANSMIT-000063 | NA | Trade Partner | Fuel Services - Cx TEMPLATES - Update | 0 | 5 | 0 | NA | APPROVED | 2026-07-09 | WF-001147 | NA |  |  |  |  | 2026-07-23 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-09 | ZIA-TRANSMIT-000071 | NA | Trade Partner | CSMS - Cx L2 OustationTest Documents | 0 | 8 | 0 | NA | APPROVED | 2026-07-09 | WF-001148 | NA | [6 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-09 | Ardon-SUBRFI-000003 | NA | Trade Partner | Door Hardware - Stage 9 Door By Door for Review | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-001182 | NA | 2026-07-20 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-14 | Entire M-TRANSMIT-000031 | Entire M-TRANSMIT-000031 | Trade Partner | Ductwork Technical Data for approval | 1 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-003788 |  | 2026-01-30 |  |  |  | 2026-01-30 | KPTG-TRANSMIT-012234 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-09 | DLTS-TRANSMIT-000053 / DLTS-TRANSMIT-000007 | NA | Trade Partner | S9-COOLING TOWER PART 1 | 1 | 0 | 0 | NA | APPROVED | 2026-07-09 | WF-001181 | NA | 2026-07-14 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-005607 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-10 | ADP-TRANSMIT-000113 | NA | Consultant | ADP MEL4680 - Mechanical Reg126 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For updating in register only. |  | 2026-07-10 | KPTG-TRANSMIT-001088 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-09 | OTIS2-SUBADVICE-000001 | NA | Trade Partner | New EOT Lift - Shop Drawings & Design | 3 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Submitted drawings not as per the standard also submitted as Subcontractor advise. |  | 2026-07-09 | KPTG-DA-000432 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-09 | RDSBIM-TRANSMIT-000220 | NA | Trade Partner | LINDRUM ¦LEVEL 06 PARTITION WALL LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 668 | 2026-07-14 |  |  | 2026-07-15 | 2026-07-15 | KPTG-SADV-004935 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-10 | PMT Sec-TRANSMIT-000030 | NA | Trade Partner | NEL-CNT-PMT-2801-SEC-SDG-0051 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Attached drawing is previous revision |  | 2026-07-10 | KPTG-TRANSMIT-001407 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-09 | INDS-TRANSMIT-000047 | NA | Trade Partner | Dry Fire - Level 1 | 5 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004847 - document number,tittle,date are incorrect | 2026-07-09 | 2026-07-09 | KPTG-SADV-004847 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-09 | fjc-TRANSMIT-000164 | NA | Trade Partner | Architecturals - Demolition | 2 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 689 | 2026-07-14 |  |  | 2026-07-10 | 2026-07-10 | KPTG-SADV-004887 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-10 | 42636706-TRANSMIT-000016 | NA | Trade Partner | BoH Computer - Sample Data | 0 | 3 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004870 - TITTLE INCORRECT | 2026-07-10 | 2026-07-10 | KPTG-SADV-004870 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-09 | RDSBIM-TRANSMIT-000219 | NA | Trade Partner | LINDRUM ¦ LEVEL 05 PARTITION WALL LAYOUT¦ IFR ¦ SUBMISSION | 1 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 690 | 2026-07-14 |  |  | 2026-07-10 | 2026-07-10 | KPTG-SADV-004888 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-10 | Auspan-TRANSMIT-000485 | NA | Trade Partner | Precast cast in plate layout zone 3 for construction | 5 | 0 | 0 | KPTG-IntCorr-000923 | APPROVED | [5 empty] | IFC - Waiting for Kim advise - KPTG-IntCorr-000923 OK to proceed IFC KPTG-TRANSMIT-002734 |  | 2026-07-13 | KPTG-TRANSMIT-002734 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-14 | NXT-TRANSMIT-001189 / BACAU-TRANSMIT-000049 | NA | Trade Partner | re issue of drawing post review | 7 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-003792) |  | 2026-01-28 |  |  |  | 2026-01-27 | NXT-WTRAN-001589 | Closed | 7 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-08 | SME - 920 | NA | Consultant | LAUNDRY JOINERY | 3 | 0 | 0 | NA | APPROVED | 2026-07-08 | NA | 920 | 2026-07-18 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-003129 | Open | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-10 | VERTIV-TRANSMIT-000045 | NA | Trade Partner | NEXT DC GE01 _ SHOP DRAWINGS _ STRUCTURAL (FOA-1) | 11 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document number, drawings status in document. |  | 2026-07-10 | KPTG-TRANSMIT-001089 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-08 | INGEN3D-TRANSMIT-000183 | NA | Trade Partner | Level 16-18 - Precast Columns - Revised IFC | 4 | 0 | 0 | NA | APPROVED | 2026-07-08 | WF-000909 | NA | 2026-07-17 |  | (Submitted together with Trn#173) |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-07-10 | PSGV-TRANSMIT-000011 | NA | Trade Partner | Re: Powerpack O&M manual | 0 | 1 | 0 | NA | APPROVED | 2026-07-10 | WF-000519 | NA | 2026-07-19 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-08 | INGEN3D-TRANSMIT-000182 | NA | Trade Partner | Level 1 Cast in Dowel CAD | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | CAD FILE REGISTER UPDATED |  | 2026-07-08 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-08 | ccair-TRANSMIT-000005 | NA | Trade Partner | Heat Load Calculation for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-08 | WF-000934 | NA | 2026-07-15 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-002915 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | INGEN3D-TRANSMIT-000185 | NA | Trade Partner | Level 18-20 - Precast Columns - No Longer in Use | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer In Use |  | 2026-07-09 | KPTG-TRANSMIT-002814 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | Jangho-TRANSMIT-000235 | NA | Trade Partner | FT01 & FT02 Syetem Concept Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 928 | 2026-07-15 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002954 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-10 | Nilsen3-TRANSMIT-000063 | NA | Trade Partner | Nilsen Shop Drawings - IFC | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, No review required, updated register & distributed |  | 2026-07-10 | KPTG-TRANSMIT-005456 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | ARCST-TRANSMIT-000339 | NA | Trade Partner | C2 Cooling Tower HD Bolts - Issued for Construction | 4 | 0 | 0 | NA | APPROVED | 2026-07-10 | WF-006327 | NA | 2026-07-20 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-14 | PFP PL-TRANSMIT-000055 | NA | Trade Partner | Technical data issued for review | 7 | 0 | 0 | NA | REJECTED | [5 empty] | The revision number is not mentioned in the documents. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | Jangho-TRANSMIT-000220 | NA | Trade Partner | FT01 & FT02 Syetem Concept Drawing | 24 | 0 | 0 | NA | APPROVED | 2026-07-09 | NA | 928 | 2026-07-15 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002954 | Closed | 24 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | INGEN3D-TRANSMIT-000186 | NA | Trade Partner | Level 18-20 - PC0710 - New IFA | 3 | 0 | 0 | NA | APPROVED | 2026-07-09 | WF-000919 | NA | 2026-07-13 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002851 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | INGEN3D-TRANSMIT-000187 | NA | Trade Partner | Level 18-20 - PC0613-3 - New IFA | 3 | 0 | 0 | NA | APPROVED | 2026-07-09 | WF-000919 | NA | 2026-07-13 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002851 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | INGEN3D-TRANSMIT-000188 | NA | Trade Partner | Level 14-16 - PC0539-3 - New IFA | 3 | 0 | 0 | NA | APPROVED | 2026-07-09 | WF-000922 | NA | 2026-07-17 |  | 2 processed | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002855 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | INGEN3D-TRANSMIT-000189 | NA | Trade Partner | Level 14-16 - PC0522-10 & PC539-4 - New IFA | 5 | 0 | 0 | NA | APPROVED | 2026-07-09 | WF-000922 | NA | 2026-07-17 |  | 3 processed | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002855 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | L.E.S.-TRANSMIT-000023 | NA | Trade Partner | Internal light fittings tech data sheets, for review | 5 | 0 | 0 | NA | APPROVED | 2026-07-09 | WF-000933 | NA | 2026-07-17 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-003368 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | INGEN3D-TRANSMIT-000191 | NA | Trade Partner | Level 14-16 - Precast Columns - No Longer in Use | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer In Use - KPTG-TRANSMIT-002803 |  | 2026-07-09 | KPTG-TRANSMIT-002803 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-10 | PMT Sec-TRANSMIT-000032 | NA | Trade Partner | NEL-CNT-PMT-2801-SEC-SDG-0053 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Same revision received and reviewed |  | 2026-07-10 | KPTG-TRANSMIT-001408 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | Jangho-TRANSMIT-000077 | NA | Trade Partner | Window handle Option 1 LCZS3320M Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-000929 | NA | 2026-07-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-14 | INGEN3D-TRANSMIT-000679 - I3D-378 | NA | Trade Partner | I3D-378 Next DC M3 Stage 4 - Ground Floor (North Office) - Cast in Dowels - IFA Checked (14-01-2026) | 5 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-003796 |  | 2026-02-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-10 | Auspan-TRANSMIT-000486 | NA | Trade Partner | Precast shop drawings for approval. Levels 5, 6 zone 3 | 51 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 1460 | 2026-07-17 |  | 1 Drawing already terminated 2 Terminated, review already completed, missing stamp, initiated another review | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-003213 | Closed | 51 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | Jangho-TRANSMIT-000190 | NA | Trade Partner | Siliding Door Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-000928 | NA | 2026-07-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | Jangho-TRANSMIT-000189 | NA | Trade Partner | Siliding Door Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-000927 | NA | 2026-07-17 |  |  | 2026-08-13 | 2026-08-14 | KPTG-TRANSMIT-003403 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | Jangho-TRANSMIT-000188 | NA | Trade Partner | Siliding Door Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-000926 | NA | 2026-07-17 |  |  | 2026-08-13 | 2026-08-14 | KPTG-TRANSMIT-003400 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | Jangho-TRANSMIT-000185 | NA | Trade Partner | Window Hardware Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-000925 | NA | 2026-07-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | Jangho-TRANSMIT-000186 | NA | Trade Partner | Siliding Door Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-000923 | NA | 2026-07-17 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-003471 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | RED Fire-TRANSMIT-000012 | NA | Trade Partner | Fire Engineering Report - Version 3 | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-000932 | NA | 2026-07-17 |  |  | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-003050 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | PCForm-TRANSMIT-000249 | NA | Trade Partner | Pavecure amended Doc no. | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-000916 | NA | 2026-07-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | PCForm-TRANSMIT-000189 | NA | Trade Partner | Aitken Freeman - Granobond Sample submission | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-000915 | NA | 2026-07-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-10 | VERTIV-TRANSMIT-000046 | NA | Trade Partner | NEXT DC GE 01 _ SHOP DRAWINGS _ MECHANICAL (FOA-1 & FOA-2) | 3 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 335 | 2026-07-16 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001374 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-14 | SMEPS-TRANSMIT-000137 | NA | Trade Partner | Light switch | 0 | 1 | 0 | NA | APPROVED |  | WF-003804 |  | 2026-01-28 |  | The submit line is incorrect. refer - KPTG-IntCorr-008060 (Kian) |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | PCForm-TRANSMIT-000242 | NA | Trade Partner | Zincote sample submission | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-000914 | NA | 2026-07-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | ECBS-TRANSMIT-000044 | NA | Trade Partner | Shop Drawings For Approval (Batch 2: 15dwgs) | 44 | 0 | 0 | NA | APPROVED | 2026-07-10 | WF-006328 | NA | 2026-07-24 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-10 | WRAP-TRANSMIT-000074 | NA | Consultant | Updated Ground, L3 and L9 BTR (services) | 40 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 593 | 2026-07-14 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | Resonate-TRANSMIT-000016 | NA | Trade Partner | Re-transmitting the BCA Acoustic report to supersede M220473RP3 | 0 | 1 | 0 | NA | APPROVED | 2026-07-09 | WF-000912 | NA | 2026-07-17 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002859 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-10 | PMT Sec-TRANSMIT-000033 | SPARK-CRFI-KPG-000631 | Trade Partner | NEL-CNT-PMT-2801-SEC-SDG-0057 | 1 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 344 | 2026-07-17 |  | Revision date is incorrect | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-001506 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | ACG-TRANSMIT-000110 | NA | Trade Partner | Re: M3 Stage 4 Axis Box Camera Sample | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rev is missing |  | 2026-07-10 | KPTG-DA-007528 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-10 | LANSA-TRANSMIT-000107 | NA | Trade Partner | Levels 2-8 Water Services Layouts with Breezeway Hose Taps Added | 20 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-07-10 | KPTG-TRANSMIT-003132 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | RDSBIM-TRANSMIT-000056 | NA | Trade Partner | GROUND FLOOR STAGE 4B3 PARTITION WALL KEY PLAN | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | rejected : issued via Trn # 60 |  | 2026-07-09 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-10 | PMT Sec-TRANSMIT-000034 | SPARK-CRFI-KPG-000629 | Trade Partner | NEL-CNT-PMT-2801-SEC-SDG-0188 | 1 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 355 | 2026-07-17 |  | Revision date is incorrect | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001594 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | ARCST-TRANSMIT-000338 | NA | Trade Partner | C1 Swicthroom Handrails - Issued for Construction | 11 | 0 | 0 | NA | APPROVED | 2026-07-10 | WF-006329 | NA | 2026-07-20 |  |  |  | 2026-07-16 | KPTG-RTRFI-005257 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-02 | SMEPS-TRANSMIT-000240 | NA | Trade Partner | SME - IFC Submission | 2 | 0 | 0 | NA | APPROVED | 2025-12-02 | NA | 1278 | 2025-12-11 |  |  | 2026-01-20 | 2026-01-20 | KPTG-TRANSMIT-002301 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-01-14 | RDSBIM-TRANSMIT-000018 | NA | Trade Partner | 671CHP ¦ LEVEL 03 CONCRETE PROFILE KEYPLAN AND SECTION | 3 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-000243 | NA | 2026-01-19 |  | Review void as advised during a meeting with Kapitol DM & PCs. Review Reinitiated on 27-01-26 27/2/25 as advised by KAPITOL PC, ACC review 232 is VOID and initiated ACC review - WF-000243 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | NXT-TRANSMIT-001660 | NA | Trade Partner | M3 S4 MSB-LB Load Bank Panel IFC Shop Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-07-10 | WF-006330 | NA | 2026-07-23 |  | Q4ECP/L-TRANSMIT-000002, As instructed by Rohit in NXT-PA-005925, the workflow terminated |  | 2026-07-20 | NXT-PA-005925 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-10 | Auscool-TRANSMIT-000056 | NA | Trade Partner | Basement - L1 IFC BW drawings | 14 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to difference in revision number - DRAFT-009681 |  | 2026-07-10 | DRAFT-009681 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-10 | PMT Sec-TRANSMIT-000035 | SPARK-CRFI-KPG-000629 | Trade Partner | NEL-CNT-PMT-2801-SEC-SDG-0201 | 1 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 366 | 2026-07-17 |  | Revision date in Aconex is incorrect | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001596 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-10 | Auspan-TRANSMIT-000487 | NA | Trade Partner | Precast shop drawings for construction. Level 1 | 3 | 0 | 0 | KPTG-IntCorr-000925 | APPROVED | [5 empty] | IFC - Waiting for Kim advise - KPTG-IntCorr-000925 OK to proceed IFC KPTG-TRANSMIT-002730 |  | 2026-07-13 | KPTG-TRANSMIT-002730 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-10 | WilsonPD-TRANSMIT-000111 | NA | Trade Partner | Tech data | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, No review required, updated register & distributed |  | 2026-07-10 | KPTG-TRANSMIT-005460 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-10 | M.S.-TRANSMIT-000081 | NA | Trade Partner | IFC Shop drawings for J50 Reception Counter | 5 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 380 | 2026-07-15 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-003197 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-10 | Auspan-TRANSMIT-000487 | NA | Trade Partner | Precast shop drawings for construction. Level 1 | 1 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-07-10 | DRAFT-009684 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-10 | Auspan-TRANSMIT-000488 | NA | Trade Partner | Precast shop drawings for construction. Levels 2, 3 | 5 | 0 | 0 | KPTG-IntCorr-000927 | APPROVED | [5 empty] | IFC - Waiting for Kim advise - KPTG-IntCorr-000927 All are ok to transmit KPTG-TRANSMIT-002779 |  | 2026-07-15 | KPTG-TRANSMIT-002779 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-10 | RDSBIM-TRANSMIT-000014 | NA | Trade Partner | NXM2S9 ¦ GROUND FLOOR CLEANERS ROOM FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 1360 | 2026-07-14 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-005650 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-10 | PMT Sec-TRANSMIT-000036 | SPARK-CRFI-KPG-000629 | Trade Partner | NEL-CNT-PMT-2801-SEC-SDG-0202 | 1 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 347 | 2026-07-17 |  | Revision date inside the drawing an in Aconex seem different | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001598 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-01-14 | RBG-TRANSMIT-000048 | NA | Consultant | Updated Structural drawing for drawing S02-07021 - Retention Details | 0 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-000118 | 202 | 2026-01-19 |  |  |  | 2026-01-27 | KPTG-TRANSMIT-000336 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-10 | ADP-TRANSMIT-000114 | NA | Consultant | ADP MEL4680 - Electrical Specification | 0 | 1 | 0 | NA | APPROVED | 2026-07-10 | NA | 337 | 2026-07-15 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | NXT-TRANSMIT-001661 | NA | Trade Partner | Fwd: M3 - Stage 4 - LVSB - As Builts | 43 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | The register has been updated. If any further action is required, the coordinator will inform. |  | 2026-07-10 | KPTG-TRANSMIT-019543 | Closed | 43 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-10 | Auspan-TRANSMIT-000489 | NA | Trade Partner | Precast shop drawings for construction. Level 4 | 46 | 0 | 0 | KPTG-IntCorr-000928 | APPROVED | [5 empty] | IFC - Waiting for Kim advise - KPTG-IntCorr-000928 38 are ok to IFC -KPTG-TRANSMIT-003226; 5 Rejected by Kapitol PC. KPTG-SADV-004174; 3 are already updated and distributed |  | 2026-08-13 | KPTG-TRANSMIT-003226 | Closed | 46 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-10 | ENF-TRANSMIT-000030 | NA | Consultant | Structural drawings | 1 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 305 | 2026-07-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-10 | ADP-TRANSMIT-000115 | NA | Consultant | ADP MEL4680 - Mechanical Reg126 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Only for updating register. |  | 2026-07-10 | KPTG-TRANSMIT-001094 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | ARCST-TRANSMIT-000334 | NA | Trade Partner | C3 Switchroom Roof & Secondary Steel - Issued for Construction | 127 | 0 | 0 | NA | REJECTED | [5 empty] | Some documents received in this transmittal have been submitted as IFC for the first time, and the corresponding IFA documents have not been received yet |  | 2026-07-10 | KPTG-DA-007535 | Closed | 127 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-10 | Auspan-TRANSMIT-000490 | NA | Trade Partner | Re-transmit panels 0G3108 and 0G3109 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to same revision as latest version - DRAFT-009694 |  | 2026-07-10 | DRAFT-009694 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-10 | PMT Sec-TRANSMIT-000037 | SPARK-CRFI-KPG-000629 | Trade Partner | NEL-CNT-PMT-2801-SEC-SDG-0203 | 1 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 348 | 2026-07-17 |  | Revision Date inside drawing and in Aconex seem different. | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001601 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-24 | CRSol-TRANSMIT-000011 | NA | Trade Partner | Re: Re-submission of Rejected TD – WF-000693 | 0 | 1 | 0 | NA | APPROVED | 2026-06-24 | WF-001041 | NA | 2026-07-01 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-005465 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | ACG-TRANSMIT-000110 | NA | Trade Partner | M3 Stage 4 Axis Box Camera Sample | 0 | 1 | 0 | NA | APPROVED | 2026-07-10 | WF-006333 | NA | 2026-08-05 | [5 empty] | Open | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-14 | KETE-TRANSMIT-000002 | NA | Trade Partner | Submission – DIP shop drawings | 36 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-000126 | 247 | 2026-01-15 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-000564 | Closed | 36 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | ECBS-TRANSMIT-000063 | NA | Trade Partner | C11 Drawing IFA (17 drawings) | 17 | 0 | 0 | NA | APPROVED | 2026-07-10 | WF-006334 | NA | 2026-07-16 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-020371 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | ARCST-TRANSMIT-000333 | NA | Trade Partner | C1 Switchroom Roof & Secondary Steel - Issued for Construction | 164 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect titles |  | 2026-07-10 | KPTG-RFI-008854 | Closed | 164 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | Nilsen3-TRANSMIT-000230 | NA | Trade Partner | Fwd: Sample 0041 updated | 0 | 1 | 0 | NA | APPROVED | 2026-07-10 | WF-006335 | NA | 2026-07-31 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-10 | Caruso-TRANSMIT-000002 | NA | Trade Partner | Updated Blockwork Tech Data | 0 | 2 | 0 | NA | APPROVED | 2026-07-10 | WF-006336 | NA | 2026-07-22 |  |  | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-019843 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | ECBS-TRANSMIT-000057 | NA | Trade Partner | Re: Fan Wall Unit Steel- Revised Drawing IFC (Batch 2: 47 drawings) | 47 | 0 | 0 | NA | APPROVED | 2026-07-10 | (WF-006332 | NA | 2026-07-24 |  | As instructed by Peter in KPTG-IntCorr-015965 |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | ARCST-TRANSMIT-000332 | NA | Trade Partner | C2 Switchroom Roof & Secondary Steel - Issued for Construction | 136 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect Title , Some documents received in this transmittal have been submitted as IFC for the first time, and the corresponding IFA documents have not been received yet |  | 2026-07-10 | KPTG-DA-007539 | Closed | 136 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | INGEN3D-TRANSMIT-000184 | NA | Trade Partner | Level 18-20 - Precast Columns - IFC | 31 | 0 | 0 | NA | APPROVED | 2026-07-10 | WF-000936 | NA | 2026-07-20 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-003132 | Closed | 31 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | D&E-TRANSMIT-000909 | NA | Trade Partner | C1 & C2 Seismic Drawings - Issued for Approval | 0 | 2 | 0 | NA | REJECTED |  | NA | NA |  |  | Kindly submit the received documents as Technical Data documents |  | 2026-07-10 | KPTG-RFI-008855 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-10 | PMT Sec-TRANSMIT-000038 | SPARK-CRFI-KPG-000629 | Trade Partner | NEL-CNT-PMT-2801-SEC-SDG-0204 | 1 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 349 | 2026-07-17 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001603 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-09 | INGEN3D-TRANSMIT-000190 | NA | Trade Partner | Level 14-16 - Precast Columns - IFC | 31 | 0 | 0 | NA | APPROVED | 2026-07-10 | WF-000942 | NA | 2026-07-21 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-003104 | Closed | 31 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-14 | D&E-TRANSMIT-000078 |  | Trade Partner | MWYCCB - CHILLED WATER & HEATING HOT WATER SCHEMATICS - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-000120 | 85 | 2026-01-21 |  | WF terminated - Latest revision |  | 2026-03-11 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-10 | Normark-TRANSMIT-000056 | NA | Trade Partner | Shop drawing IFC | 5 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 382 | 2026-07-15 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-003111 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-10 | PMT Sec-TRANSMIT-000040 | NA | Trade Partner | Zone 4 Penetration drawing | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing number and title inside the drawing and in Aconex seem different |  | 2026-07-10 | KPTG-TRANSMIT-001414 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-10 | SMEPS-TRANSMIT-000231 | SPARK-CRFI KPG-000388 & SPARK-CRFI-KPG-000291 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0613,1107 | 2 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 350 | 2026-07-17 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-001431 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | SMEPS-TRANSMIT-000344 | NA | Trade Partner | SME - IFC Documentation | 8 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 3843 | 2026-07-19 |  |  |  | 2026-07-15 | NA | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-10 | WilsonPD-TRANSMIT-000207 | NA | Trade Partner | Cleaners Sink Tapware for Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document revision is missing |  | 2026-07-10 | KPTG-TRANSMIT-001415 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | ARCST-TRANSMIT-000337 | NA | Trade Partner | C1 Switchroom Upper Gantry Grating - Issued for Construction | 154 | 0 | 0 | NA | APPROVED | 2026-07-10 | WF-006338 | NA | 2026-07-14 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-10 | SMEPS-TRANSMIT-000232 | NA | Trade Partner | NEL-CNT-SME-2990-ELC-SAM-0018 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Reviewed document is attached |  | 2026-07-10 | KPTG-TRANSMIT-001416 | Open | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-10 | WilsonPD-TRANSMIT-000208 | SPARK-CRFI-KPG-000199 | Trade Partner | Hydraulic Services - General Notes | 1 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 351 | 2026-07-17 |  |  |  | 2026-07-13 | KPTG-TRANSMIT-001428 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | SMEPS-TRANSMIT-000345 | NA | Trade Partner | SME - IFA Documentation | 3 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 3846 | 2026-07-19 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-14 | WilsonPD-TRANSMIT-000138 |  | Trade Partner | WilsonPD-TRANSMIT-000138 | 1 | 0 | 0 | KPTG-IntCorr-001240 | APPROVED | [9 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-10 | RDSBIM-TRANSMIT-000012 | NA | Trade Partner | NXM2S9 ¦ GROUND FLOOR AMENITIES WEST FLOOR FINISH LAYOUT AND ELEVATIONS | 2 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 1361 | 2026-07-17 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-007016 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-10 | RDSBIM-TRANSMIT-000013 | NA | Trade Partner | NXM2S9 ¦ GROUND FLOOR UNISEX WC FLOOR FINISH LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 1362 | 2026-07-17 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-007020 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-10 | D&E-TRANSMIT-000286 | SPARK-CRFI-KPG-000606 | Trade Partner | Motorized Control Valves -In For Construction | 0 | 1 | 0 | NA | APPROVED | 2002-07-10 | NA | NA | 2026-07-10 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-10 | D&E-TRANSMIT-000285 | SPARK-CRFI-KPG-000540 & SPARK-CRFI-KPG-000640 | Trade Partner | Mechanical Thermostat and Coppermate Approved for Construction | 0 | 2 | 0 | NA | APPROVED | 2026-07-10 | NA | NA | 2026-07-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-10 | PFP PL-TRANSMIT-000014 | NA | Trade Partner | Water Mist System Schematic IFA | 1 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 1364 | 2026-07-17 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-005646 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | ARCST-TRANSMIT-000340 | NA | Trade Partner | Re: Chemical Store Base & Roof Framing - Issued for Construction | 12 | 0 | 0 | NA | REJECTED | [5 empty] | The IFA for the documents has not been received |  | 2026-07-10 | KPTG-DA-007529 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | D&E-TRANSMIT-000910 | NA | Trade Partner | BMS Damper Actuators | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Technical data IFC for distribution |  | 2026-07-10 | KPTG-TRANSMIT-019562 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | ARCST-TRANSMIT-000336 | NA | Trade Partner | Re: C1 Switchroom Upper Gantry - Issued for Construction | 160 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-07-10 | KPTG-DA-007534 | Closed | 160 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2026-01-14 | PFP PL-TRANSMIT-000035 | NA | Trade Partner | Updated As-Builts | 7 | 0 | 0 | NA | APPROVED | [5 empty] | As-Builts, No review required, Distributed to project team |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-10 | RDSBIM-TRANSMIT-000059 | NA | Trade Partner | LEVEL 07 TO LEVEL 20 STAIR/LIFT CORE 03 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 938 | 2026-07-16 |  |  | 2026-07-28 | 2026-07-29 | KPTG-TRANSMIT-003161 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-10 | Civilex-TRANSMIT-000102 | NA | Trade Partner | FirePro FR - Water based, ﬁre-rated, ﬂexible intumescent sealant | 0 | 1 | 0 | NA | APPROVED | 2026-07-10 | WF-000937 | NA | 2026-07-14 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-10 | RDSBIM-TRANSMIT-000061 | NA | Trade Partner | GROUND FLOOR STAGE 4B3 PARTITION WALL KEY PLAN | 5 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 940 | 2026-07-12 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002952 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | D&E-TRANSMIT-000908 | NA | Trade Partner | IW Pumps - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Technical data IFC for distribution |  | 2026-07-10 | KPTG-TRANSMIT-019563 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-10 | Stowe-A-TRANSMIT-000638 | NA | Trade Partner | STOWE - Schematic As builts | 23 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected drawings submitted as As built in set. |  | 2026-07-10 | KPTG-SADV-006547 | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-10 | RDSBIM-TRANSMIT-000015 | NA | Trade Partner | NXM3S6 ¦ LEVEL 01 BLOCK 1 ¦ CONCRETE PROFILE PLAN AND SECTIONS | 2 | 0 | 0 | KPTG-IntCorr-000284 | APPROVED | 2026-07-14 | NA | 383 | 2026-07-22 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-10 | PTA-TRANSMIT-000021 | NA | Consultant | Stage 4 - 6 Link Bridge structural framing development | 1 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 364 | 2026-07-20 |  |  | 2026-07-21 | 2026-07-22 | KPTG-TRANSMIT-000649 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-10 | PTA-TRANSMIT-000022 | NA | Consultant | Stage 6 and 7 Barkers Fence and VDA - Master Site Plan | 1 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 366 | 2026-07-20 |  |  | 2026-07-21 | 2026-07-22 | KPTG-TRANSMIT-000648 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-10 | KPTG-TRANSMIT-000506 | NA | Trade Partner | Precast Panel Concrete Mix Design | 0 | 1 | 0 | NA | APPROVED | 2026-07-10 | NA | 368 | 2026-07-20 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-10 | 4DW-TRANSMIT-000066 | NA | Consultant | Issued for Construction: Level 1 Block 1 Floor Design | 9 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 370 | 2026-07-20 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-000779 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2026-01-14 | Nilsen3-TRANSMIT-000126 | NA | Trade Partner | Nilsen As-Builts | 16 | 0 | 0 | NA | APPROVED | [5 empty] | As-Builts, No Review required. Distributed to project team. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-10 | D&E-TRANSMIT-000287 | SPARK-CRFI-KPG-000311 | Trade Partner | Mechanical FCU Static Pressure Calcs - IFC | 0 | 1 | 0 | NA | APPROVED | 2026-07-10 | NA | NA | 2026-07-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-10 | ELLISAIR-TRANSMIT-000117 | NA | Trade Partner | Stage 10 Level 1 Duct and Pipe layouts issued for Approval. | 5 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 1475 | 2026-07-17 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-006073 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-10 | Stowe-A-TRANSMIT-000639 | NA | Trade Partner | STOWE - As Built - Data Hall 1 Containment | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Mistake in title, incorrect revision, incorrect revision date. |  | 2026-07-10 | KPTG-SADV-006548 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-10 | crossfir-TRANSMIT-000001 | NA | Trade Partner | Wet Fire - Block Plans- IFA | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with Document number, revision, drawings status missing, revision date missing. |  | 2026-07-10 | KPTG-SADV-000882 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-29 | SPECAUTO-TRANSMIT-000002 | NA | Trade Partner | CSMS Cabling Procurement Approval | 0 | 2 | 0 | NA | APPROVED | 2026-06-29 | WF-000255 | NA | 2026-07-10 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-001176 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-10 | Auscool-TRANSMIT-000104 | NA | Trade Partner | MSSB Load Table & MSSB Schemtics For Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | KPTG-SADV-004872 -tittle incorrect. | 2026-07-10 | 2026-07-10 | KPTG-SADV-004872 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-10 | 42636706-TRANSMIT-000017 | NA | Trade Partner | Re: BoH Computer - Sample Data | 0 | 3 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004873 - REVISION INCORRECT | 2026-07-10 | 2026-07-10 | KPTG-SADV-004873 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-10 | Auscool-TRANSMIT-000106 | NA | Trade Partner | MSSB drawings For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-10 | WF-000824 | NA | 2026-07-14 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-002771 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-10 | 42636706-TRANSMIT-000018 | NA | Trade Partner | Re: BoH Computer - Sample Data | 0 | 3 | 0 | NA | APPROVED | 2026-07-10 | WF-000825 | NA | 2026-07-15 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-002696 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-10 | ADP-TRANSMIT-000118 | NA | Consultant | ADP MEL4680 - Mechanical Reg 126 and Calc Schedule | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | Updating is Document register only. |  | 2026-07-10 | KPTG-TRANSMIT-001107 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-14 | Auspan-TRANSMIT-000036 | NA | Trade Partner | Precast shop drawings for construction. L shape panels. | 24 | 0 | 0 | NA | APPROVED | [5 empty] | IFC shop drawings, No review required. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-10 | 42636706-TRANSMIT-000019 | NA | Trade Partner | EMS Gateway - Sample Data | 0 | 2 | 0 | NA | APPROVED | 2026-07-10 | WF-000826 | NA | 2026-07-15 |  |  | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-002729 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-10 | 42636706-TRANSMIT-000020 | NA | Trade Partner | IEQ - Sample Data | 0 | 3 | 0 | NA | APPROVED | 2026-07-10 | WF-000827 | NA | 2026-07-13 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-10 | 4DW-TRANSMIT-000100 | NA | Consultant | Masonry Details Update | 1 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 691 | 2026-07-15 |  |  | 2026-07-14 | 2026-07-14 | KPTG-SADV-004933 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-10 | VERTIV-TRANSMIT-000047 | NA | Trade Partner | NEXT DC GE 01 _ SHOP DRAWINGS _ ELECTRICAL (FOA-1 & FOA-2) | 13 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status missing, scale overlapped in drawings status. |  | 2026-07-10 | KPTG-TRANSMIT-001093 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-10 | INGEN3D-TRANSMIT-000193 | NA | Trade Partner | Marking Plans (Precast Column Elevation) - RE-IFA | 12 | 0 | 0 | NA | APPROVED | 2026-07-10 | WF-000941 | NA | 2026-07-12 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-003291 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-10 | BLTEC-TRANSMIT-000003 | NA | Trade Partner | Hot and Cold Plunge Pools FWT drawings | 4 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 944 | 2026-07-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-10 | RDSBIM-TRANSMIT-000060 | NA | Trade Partner | DISTLV ¦ GROUND FLOOR STAGE 4B3 PARTITION WALL KEY PLAN | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Drawings replaced by RDSBIM-TRANSMIT-000061 |  | 2026-07-10 | RDSBIM-TRANSMIT-000061 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-10 | INGEN3D-TRANSMIT-000153 | NA | Trade Partner | Level 15-17 - Precast Columns - IFC (30-06-2026) | 41 | 0 | 0 | NA | APPROVED | 2026-07-10 | WF-000935 | NA | 2026-07-12 |  | (Re-issue with TTW Comment) 1 DRAWING REJECTED (WF935) | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-003321 - | Closed | 41 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-10 | INGEN3D-TRANSMIT-000192 | NA | Trade Partner | Marking Plan (Podium) - CAD Files | 15 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | cad files - register updated |  | 2026-07-10 | NA | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-10 | INGEN3D-TRANSMIT-000159 | NA | Trade Partner | Level 13-15 - Precast Columns - IFC (30-06-2026) | 64 | 0 | 0 | NA | APPROVED | 2026-07-10 | WF-000943 | NA | 2026-07-12 |  | (Re-issue with TTW Comment) | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-003140 | Closed | 63 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-14 | PCForm-TRANSMIT-000033 | NA | Trade Partner | Jumpform Concrete Envelopes & Wall Elevations - Stage 9 - Stair 1 & Lift Core - Issued for construction | 6 | 0 | 0 | NA | APPROVED | [5 empty] | IFC drawings, No review required. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-07-10 | SMPS-TRANSMIT-000123 | NA | Trade Partner | Re: SME O&M - FINAL HANDOVER | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect revision No |  | 2026-07-10 | DRAFT-010355 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-10 | PCForm-TRANSMIT-000083 | NA | Trade Partner | : IFC Acrow Screen Drawings | 21 | 0 | 0 | KPTG-IntCorr-000930 | APPROVED |  | NA | NA |  |  | Kapitol DM to advise KPTG-IntCorr-000930 No review or distribution, this is for internal use |  | 2026-07-21 | NA | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-07-10 | INSULPAK-TRANSMIT-000031 | NA | Trade Partner | Insulpak- Power Pack- OMM Issued For Review | 0 | 1 | 0 | NA | APPROVED | 2026-07-10 | WF-000518 | NA | 2026-07-19 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-10 | Auspan-TRANSMIT-000484: | NA | Trade Partner | Panel 4P303 level 4 for construction. | 1 | 0 | 0 | KPTG-IntCorr-000924 | APPROVED |  | NA | NA |  |  | waiting for Kapitol advise - KPTG-IntCorr-000924 OK to proceed IFC KPTG-TRANSMIT-002725 |  | 2026-07-13 | KPTG-TRANSMIT-002725 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | HDRAus-TRANSMIT-000523 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 20 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 3849 | 2026-07-15 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-019775 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-07-10 | SMEPS-TRANSMIT-000340 | NA | Trade Partner | Electrical Services 22KV - Basement Level - Containment Layout- (FC-4) | 1 | 0 | 0 | NA | APPROVED | 2026-07-10 | WF-006343 | NA | 2026-07-23 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-019705 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-07-10 | SMEPS-TRANSMIT-000341 | NA | Trade Partner | Transmittal – Updated Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-07-10 | WF-006344 | NA | 2026-07-15 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-020554 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-07-10 | SMEPS-TRANSMIT-000342 |  | Trade Partner | Transmittal – Updated Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-07-10 | WF-006345 | NA | 2026-07-15 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-10 | RDSBIM-TRANSMIT-000084 | NA | Trade Partner | RDSBIM-TRANSMIT-000084 671 CHP CPP GROUND FLOOR CONCRETE PROFILE KEY PLAN | 2 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 645 | 2026-07-17 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-001357 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-10 | LGCE-TRANSMIT-000057 | NA | Trade Partner | LGCE-TRANSMIT-000057 push to exit rev 2 | 0 | 1 | 0 | NA | APPROVED | 2026-07-10 | WF-000576 | NA | 2026-07-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-14 | PCForm-TRANSMIT-000034 | NA | Trade Partner | Stage 9 - Stair 2, Stage 10 - Stair 5 & Stage 10 - Stair 8 - Pour Sequence for review | 9 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-000131 |  | 2026-01-21 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-001494 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-10 | crossfir-TRANSMIT-000024 | NA | Trade Partner | Wet Fire - Typical detail, Spr in Balconies | 1 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 643 | 2026-07-17 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-001583 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-22 | Highbu-TRANSMIT-000154 | NA | Trade Partner | ISC - IFA drawings | 3 | 0 | 0 | NA | APPROVED | 2026-06-23 | NA | 332 | 2026-06-30 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-003086 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-10 | ELLISAIR-TRANSMIT-000115 | NA | Trade Partner | Stage 9 Level 1 Link Bridge Duct & Pipe layout drawing issued for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 1476 | 2026-07-17 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-006071 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-10 | ELLISAIR-TRANSMIT-000116 | NA | Trade Partner | Pipework Painting | 0 | 1 | 0 | NA | APPROVED | 2026-07-10 | WF-001188 | NA | 2026-07-22 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-006096 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-13 | KETE-TRANSMIT-000142 | NA | Trade Partner | LD-KETE-FA-SMP-S027 updated | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004892 - the tittle and type are incorrect. | 2026-07-13 | 2026-07-13 | KPTG-SADV-004892 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-13 | RDSBIM-TRANSMIT-000222 | NA | Trade Partner | LINDRUM ¦ LEVEL 08 PARTITION WALL LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 692 | 2026-07-16 |  |  | 2026-07-15 | 2026-07-15 | KPTG-SADV-004939 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-13 | Auspan-TRANSMIT-000494 | NA | Trade Partner | Update IFCed shop drawings. Level 3 | 19 | 0 | 0 | KPTG-IntCorr-000936 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise -KPTG-IntCorr-000936 Drawings superseded via Auspan TN#527 - KPTG-IntCorr-001130 |  | 2026-07-28 | KPTG-IntCorr-001130 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-13 | Auspan-TRANSMIT-000494 | NA | Trade Partner | Update IFCed shop drawings. Level 3 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to difference in document number - KPTG-SADV-003413 |  | 2026-07-13 | KPTG-SADV-003413 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-13 | P & R-TRANSMIT-000095 | NA | Trade Partner | Stage 2 Tundish Locations | 4 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 384 | 2026-07-22 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-003336 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-13 | PMT Sec-TRANSMIT-000041 | NA | Trade Partner | Updated defected drawings | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Actual Received date- 11/07/2026 Drawing number incorrect Drawing Title incomplete |  | 2026-07-13 | KPTG-TRANSMIT-001425 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-02 | SMEPS-TRANSMIT-000241 | NA | Trade Partner | M3 DH78 - Cx Plan Adjustments | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Review not required as confirmed by the commissioning team |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-14 | PCForm-TRANSMIT-000035 | NA | Trade Partner | Stage 9 - Stair 3 & Stair 4 - Pour Sequence for review | 6 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-000130 |  | 2026-01-21 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-001489 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-13 | RDDCPL-TRANSMIT-000003 | NA | Consultant | Facade Specification | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Specification document-Transmitted to all concerned Trade and consultants |  | 2026-07-13 | KPTG-TRANSMIT-003089 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-13 | RDSBIM-TRANSMIT-000221 | NA | Trade Partner | LINDRUM ¦LEVEL 07 PARTITION WALL LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 693 | 2026-07-16 |  |  | 2026-07-15 | 2026-07-15 | KPTG-SADV-004938 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-13 | Auspan-TRANSMIT-000491 | NA | Trade Partner | Precast shop drawings for approval. 7P2002 were split | 2 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 1462 | 2026-07-18 |  |  | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-002955 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-13 | RDSBIM-TRANSMIT-000226 | NA | Trade Partner | PAVILION DDA LAYOUT & ELEVATIONS | 2 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 594 | 2026-07-15 |  | NA | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003224 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-13 | M.S.-TRANSMIT-000082 | NA | Trade Partner | IFC Shop Drawing for J93 joinery | 2 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 386 | 2026-07-16 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-003199 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-13 | LANSA-TRANSMIT-000109 | NA | Trade Partner | Updated Levels 2 & 3 Hyd Drawings with Irrigation Changes | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-07-13 | KPTG-TRANSMIT-003135 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-13 | Auspan-TRANSMIT-000493 | NA | Trade Partner | Update IFCed shop drawings level 2 | 2 | 0 | 0 | KPTG-IntCorr-000939 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise -KPTG-IntCorr-000939 OK to proceed IFC KPTG-TRANSMIT-002728 |  | 2026-07-13 | KPTG-TRANSMIT-002728 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-13 | LANSA-TRANSMIT-000110 | NA | Trade Partner | Updated Ground & Level 09 Hyd Drawings with Irrigation Changes | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | NA |  | 2026-07-13 | KPTG-TRANSMIT-003136 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-13 | Entire M-TRANSMIT-000080 | NA | Trade Partner | Leak Detection Technical Data | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected: Revision in the covering page is not current: KPTG-IntCorr-000671 |  | 2026-07-13 | KPTG-IntCorr-000671 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-13 | PMT Sec-TRANSMIT-000041 | NA | Trade Partner | ACCESS CONTROL 1 OF 2-NEL-CNT-PMT-2801-SEC-SDG-0030 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Actual received date-11/07/2026 Drawing attached is revision A with review stamp |  | 2026-07-13 | KPTG-TRANSMIT-001425 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-01-15 | WPD-TRANSMIT-000056 | NA | Trade Partner | HFF - WPD-HYD-SMP-037 - Sewer Pumpwell Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-01-15 | WF-000341 |  | 2026-01-23 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-13 | Auspan-TRANSMIT-000492 | NA | Trade Partner | Re: Precast shop drawings for construction. Level 1 | 1 | 0 | 0 | KPTG-IntCorr-000942 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise -KPTG-IntCorr-000942 OK to proceed IFC KPTG-TRANSMIT-002732 |  | 2026-07-13 | KPTG-TRANSMIT-002732 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-13 | LANSA-TRANSMIT-000111 | NA | Trade Partner | Upppdated Site Hyd Drawing with Irrigation Changes | 2 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 595 | 2026-07-17 |  | NA | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-003270 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-13 | Auspan-TRANSMIT-000495 | NA | Trade Partner | Update IFCed shop drawings. Level 4 | 11 | 0 | 0 | KPTG-IntCorr-000946 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise -KPTG-IntCorr-000946 10 are OK to proceed IFC KPTG-TRANSMIT-003004 1 Rejected as advised by Kapitol PC. KPTG-IntCorr-001155 - DRAFT-010710 |  | 2026-07-29 | KPTG-TRANSMIT-003004 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-13 | RDSBIM-TRANSMIT-000015 | NA | Trade Partner | NXGE01 ¦ GROUND FLOOR PARTITION WALL PLAN AND ELEVATIONS | 5 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 339 | 2026-07-17 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001325 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-13 | WilsonPD-TRANSMIT-000209 | NA | Trade Partner | Cleaners Sink Tapware for Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision inside document and in Aconex seem different |  | 2026-07-13 | KPTG-TRANSMIT-001427 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-13 | Auspan-TRANSMIT-000496 | NA | Trade Partner | Update IFCed shop drawings. Levels 5, 6 | 6 | 0 | 6 | KPTG-IntCorr-000947 | APPROVED | [5 empty] | IFC - Waiting for Kim advise-KPTG-IntCorr-000947 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-13 | Nilsen3-TRANSMIT-000224 | NA | Trade Partner | Nilsen Generator enclosure cable containment Shop drawings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Document has been received with the same revision and is currently under review |  | 2026-07-13 | KPTG-DA-007551 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-13 | WilsonPD-TRANSMIT-000210 | NA | Trade Partner | Cleaners Sink Tapware - for re-re approval | 0 | 1 | 0 | KPTG-IntCorr-003501 | APPROVED | [7 empty] | 2026-07-17 | KPTG-TRANSMIT-001467 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-13 | Fredon T-TRANSMIT-000018 | NA | Trade Partner | AV Tech Data Subwoofer | 0 | 1 | 0 | NA | APPROVED | 2026-07-13 | WF-001039 | NA | 2026-07-17 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003217 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-13 | D&E-TRANSMIT-000288 | SPARK-CRFI-KPG-000753 | Trade Partner | Mechanical FCU Drains B-Press for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-13 | NA | NA | 2026-07-20 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-001619 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-15 | PFP PL-TRANSMIT-000056 | NA | Trade Partner | Technical data issued for review | 0 | 7 | 0 | NA | REJECTED | [5 empty] | the revision number mentioned inside the documents appears to be different |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-13 | Fredon T-TRANSMIT-000019 | NA | Trade Partner | AV Tech Data 8" Ceiling Speaker | 0 | 1 | 0 | NA | APPROVED | 2026-07-13 | WF-001040 | NA | 2026-07-17 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003215 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-13 | BIMF-TRANSMIT-000012 | NA | Trade Partner | Level 1 Hydraulic Setout, Rev C | 2 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 943 | 2026-07-19 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-003176 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-13 | Fredon T-TRANSMIT-000020 | NA | Trade Partner | AV Tech Data 4Ch Amplifier | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected: No covering sheet is attached: KPTG-SADV-005266 |  | 2026-07-13 | KPTG-SADV-005266 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-13 | Fredon T-TRANSMIT-000021 | NA | Trade Partner | AV Tech Data DSP Core Flex 110 | 0 | 1 | 0 | NA | APPROVED | 2026-07-13 | WF-001041 | NA | 2026-07-17 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-003114 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-13 | Fredon T-TRANSMIT-000022 | NA | Trade Partner | AV tech Data HDMI Receiver | 0 | 1 | 0 | NA | APPROVED | 2026-07-13 | WF-001042 | NA | 2026-07-17 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-003116 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-13 | Ardon-TRANSMIT-000008 | NA | Trade Partner | First Batch of Shop Drawings | 24 | 0 | 0 | NA | APPROVED | 2026-07-13 | WF-001200 | NA | 2026-07-16 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-005893 | Closed | 24 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-13 | INDS-TRANSMIT-000044 | NA | Trade Partner | Dry Fire - Level 12 to Level 27 | 16 | 0 | 0 | KPTG-IntCorr-001185 | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001185- Requested guidance, but no responses received yet. KPTG-IntCorr-001197 - as per direction from mark we ignore the transmittal because the drawings are wrong. | 2026-07-15 | 2026-07-15 | KPTG-IntCorr-001197 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-13 | Fredon T-TRANSMIT-000023 | NA | Trade Partner | AV Tech Data HDMI Transmitter | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected: Submitted Tech data is identical to another Tech Data:KPTG-SADV-005267 |  | 2026-07-13 | KPTG-SADV-005267 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-13 | ELLISAIR-TRANSMIT-000114 | NA | Trade Partner | Stage 9 & 11 L3 Cooling Tower GA Pipework Layouts drawings issued for Approval. | 4 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 1371 | 2026-07-20 |  |  | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-005828 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-13 | Fredon T-TRANSMIT-000024 | NA | Trade Partner | AV Tech Data HDMI Switcher | 0 | 1 | 0 | NA | APPROVED | 2026-07-13 | WF-001043 | NA | 2026-07-17 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-003118 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-15 | SMEPS-TRANSMIT-000138 | NA | Trade Partner | Fwd: Stage 4 - Lightning Protection Layout (C03) | 1 | 0 | 0 | NA | APPROVED | 2026-01-15 |  | 1771 | 2026-01-22 |  | The workflow has been terminated as per requested by Charlie |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-13 | Entire M-TRANSMIT-000081 | NA | Trade Partner | Leak Detection technical Data Updated | 0 | 1 | 0 | NA | APPROVED | 2026-07-13 | WF-000387 | NA | 2026-07-16 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-001060 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-13 | PFP PL-TRANSMIT-000015 | NA | Trade Partner | Hydrant & Hose Reel Schem | 1 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 1373 | 2026-07-20 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-005788 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-13 | HDRAus-TRANSMIT-000524 | NA | Consultant | M3 Stage 4 - Document upload - PDF (Locked Drawings Upload) | 4 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 3851 | 2026-07-16 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-019644 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-13 | BACAU-TRANSMIT-000006 | NA | Trade Partner | BAC Shop drawings | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Issued with Document number, title and fitting issue. |  | 2026-07-13 | KPTG-TRANSMIT-001110 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-13 | INTRFRM-TRANSMIT-000101 | NA | Trade Partner | Geelong Edge - Electrical Tech Data (Submission 9) | 0 | 1 | 0 | NA | APPROVED | 2026-07-13 | WF-000310 | NA | 2026-07-24 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001419 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-13 | Altaire-TRANSMIT-000021 | NA | Trade Partner | NEXTDC M2S11 - Shop Drawings (FC-A) (4) | 2 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 1375 | 2026-07-20 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-005793 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-13 | ELLISAIR-TRANSMIT-000118 | NA | Trade Partner | External ductwork insulation | 0 | 1 | 0 | NA | APPROVED | 2026-07-13 | WF-001204 | NA | 2026-07-23 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-006100 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-13 | Nilsen3-TRANSMIT-000067 | NA | Trade Partner | Nilsen Sample submissions #10 | 0 | 1 | 0 | NA | APPROVED | 2026-07-13 | WF-001205 | NA | 2026-07-23 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-005865 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-13 | Civilex-TRANSMIT-000289 | NA | Trade Partner | Stage 2 - sample submission - Euecy Mulch - Rev FOA-B | 0 | 1 | 0 | NA | APPROVED | 2026-07-13 | WF-006350 | NA | 2026-07-23 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-019678 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-13 | VERTIV-TRANSMIT-000048 | NA | Trade Partner | NEXT DC GE01 _ SHOP DRAWINGS _ ELECTRICAL (FOA-1 & FOA-2) | 13 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 341 | 2026-07-17 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001367 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-14 | RDSBIM-TRANSMIT-000097 | NA | Trade Partner | MLCSPR ¦ AQUATIC CENTER LEVEL 02 INTERNAL FITOUT PLAN AND ELEVATION | 3 | 0 | 0 | NA | APPROVED | 2026-01-14 |  | 392 | 2026-01-16 |  |  |  | 2026-01-19 | KPTG-SADV-003399 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-13 | KALLIBRE-TRANSMIT-000027 | NA | Trade Partner | IFC - Door by Door Schedule Rev 4 | 0 | 1 | 0 | NA | APPROVED | 2026-07-13 | WF-000388 | NA | 2026-07-14 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-001063 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-13 | Civilex-TRANSMIT-000290 | NA | Trade Partner | Stage 2 - sample submission - 4% No Fines Concrete - Pronto | 0 | 1 | 0 | NA | APPROVED | 2026-07-13 | WF-006352 | NA | 2026-07-30 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-020248 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-13 | SMEPS-TRANSMIT-000071 | NA | Trade Partner | LIGHTING CONTROL SCHEMATIC SHEET 2 | 1 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 1377 | 2026-07-20 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-005898 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-13 | Auspan-TRANSMIT-000497 | NA | Trade Partner | Fwd: Zone 3 RFi 58. Update panel 1P349 | 1 | 0 | 0 | KPTG-IntCorr-000951 | APPROVED | [5 empty] | FC - Waiting for Kim advise -KPTG-IntCorr-000951 IFC - Registered and Transmitted KPTG-TRANSMIT-002773 |  | 2026-07-14 | KPTG-TRANSMIT-002773 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-13 | Nilsen3-TRANSMIT-000232 | NA | Trade Partner | Generator control cable sample submissions | 0 | 1 | 0 | NA | APPROVED | 2026-07-13 | WF-006351 | NA | 2026-08-03 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-020409 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-13 | Civilex-TRANSMIT-000291 | NA | Trade Partner | Stage 2 - sample submission - Asphalt - 14 mm N Hot & Warm Mixes | 0 | 1 | 0 | NA | APPROVED | 2026-07-13 | WF-006353 | NA | 2026-07-23 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-019816 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-13 | BACAU-TRANSMIT-000007 | NA | Trade Partner | BAC Shop drawings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Partial submission, Document number. |  | 2026-07-13 | KPTG-TRANSMIT-001112 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-13 | DLTS-TRANSMIT-000054 | NA | Trade Partner | S10-CANOPY-IFA Issue | 59 | 0 | 0 | NA | APPROVED | 2026-07-13 | WF-001207 | NA | 2026-07-15 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-005740 | Closed | 59 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-13 | Airpor2-TRANSMIT-000007 | NA | Trade Partner | Roller Shutter and Motor Tech Data | 0 | 4 | 0 | NA | APPROVED | 2026-07-13 | WF-000312 | NA | 2026-07-30 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-001550 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-13 | SMEPS-TRANSMIT-000072 | NA | Trade Partner | Stage 9-11 Jemena Easement Plan & Sections | 1 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 1381 | 2026-07-20 |  | Workflow has been terminated as discussed with Project coordinator and will resubmit the updated drawing received from SME |  | 2026-07-30 | KPTG-IntCorr-001923 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-14 | Arco-TRANSMIT-000008 | NA | Trade Partner | BIFOLDS - CARPARK ( WEST CARPARK ENTRY D03-A0.11) | 1 | 0 | 0 | NA | REJECTED | [5 empty] | DRAWING IS COBMINED WITH ANOTHER DRAWING, REQUESTED THEM TO RE-ISSUE. |  | 2026-01-14 | KPTG-SADV-003310 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-13 | PARR-TRANSMIT-000205 | NA | Trade Partner | Fwd: P2685 - NDC M3 - Stage 4 - Battery Rooms - ASNZ3000 CERTIFICATE | 0 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-07-13 | KPTG-TRANSMIT-019604 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-13 | ECBS-TRANSMIT-000064 | NA | Trade Partner | Updated Siniat Wall Type and Ceiling Type Proposal and Summary_For Review | 0 | 2 | 0 | NA | APPROVED | 2026-07-13 | WF-006355 | NA | 2026-07-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-13 | SMEPS-TRANSMIT-000043 | SPARK-CRFI-KPG-000265 | Trade Partner | IFA - Rev C - Pit & Pole Schedule | 1 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | NA | 2026-07-20 |  | Actual received date:23/10/2025 | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-001433 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-13 | ccair-TRANSMIT-000131 | NA | Trade Partner | BTR Fans and AC Units for Approval | 0 | 2 | 0 | NA | APPROVED | 2026-07-13 | WF - 001078 | NA | 2026-07-17 |  | NA | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-003220 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-13 | D&E-TRANSMIT-000911 | NA | Trade Partner | C3 Seismic Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-07-13 | WF-006356 | NA | 2026-08-03 |  | As instructed by Ellie |  | 2026-07-29 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-13 | WRAP-TRANSMIT-000076 | NA | Trade Partner | Re: Services BTR.DWFx | 40 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 596 | 2026-07-17 |  | NA | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-003152 | Closed | 40 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-13 | INTERSIG-IntCorr-000001 | NA | Trade Partner | Assemble Coburg - PROTOTYPES | 1 | 0 | 0 | NA | APPROVED | 2026-07-13 | WF - 001079 | NA | 2026-07-17 |  | NA | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-003191 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-13 | SMEPS-TRANSMIT-000347 | NA | Trade Partner | SME - IFA Documentation - Gland Plate Details | 3 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 3854 | 2026-07-17 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-13 | SMEPS-TRANSMIT-000026 | NA | Trade Partner | Solar Design | 9 | 0 | 0 | NA | APPROVED | 2026-07-13 | WF - 001080 | NA | 2026-07-17 |  | NA | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-003152 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-13 | WilsonPD-TRANSMIT-000017 | NA | Trade Partner | Hydraulic Services - Updated Layouts | 2 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 345 | 2026-07-17 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-001184 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-14 | ARCH-TRANSMIT-000130 | NA | Consultant | MLC - SPR - Drawing Update | 6 | 0 | 0 | NA | APPROVED | 2026-01-14 |  | 394 | 2026-01-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-13 | ARCST-TRANSMIT-000341 | NA | Trade Partner | C2 Switchroom Roof & Secondary Steel - Issued for Construction | 193 | 0 | 0 | NA | REJECTED | [5 empty] | Few documents have been received as IFC for the first time. Additionally, some documents submitted as IFC have not yet received IFA approval |  | 2026-07-13 | KPTG-DA-007560 | Closed | 193 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-13 | ASV-TRANSMIT-000069 | NA | Trade Partner | Revised Hydraulic Drawing Set | 5 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 1382 | 2026-07-20 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-007255 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-13 | D&E-TRANSMIT-000909 | NA | Trade Partner | C1 & C2 Seismic Drawings - Issued for Approval | 2 | 0 | 0 | NA | APPROVED | 2026-07-13 | WF-006360 | NA | 2026-07-17 |  | As instructed by Ellie- Terminated |  | 2026-07-29 | NA | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-13 | WAM-TRANSMIT-000824 | NA | Consultant | WAM ARCH - Facade - RFI 1229 and DA 2187 | 8 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 946 | 2026-07-15 |  |  | 2026-07-27 | 2026-07-28 | KPTG-TRANSMIT-003122 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-13 | KETE-TRANSMIT-000044 | NA | Trade Partner | Auto door&DDA door drawing updated | 54 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC- for Distribution only. |  | 2026-07-13 | KPTG-TRANSMIT-003139 | Closed | 54 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-13 | D&E-TRANSMIT-000903 | NA | Trade Partner | BMS Points List - Issued for Construction | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision C revise and resubmit. FC revision submitted without approving For Approval revision. |  | 2026-07-13 | KPTG-SADV-006593 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-22 | SPECAUTO-TRANSMIT-000001 | NA | Trade Partner | CSMS Outstation Hardware Procurement Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-22 | WF-000236 | NA | 2026-07-01 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-001116 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-13 | Airpor2-TRANSMIT-000006 | NA | Trade Partner | Shop drawing Roller Shutte | 1 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 347 | 2026-07-23 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-001693 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-13 | WAM-TRANSMIT-000825 | NA | Consultant | IFC_ A10 LEVEL 04 | 2 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 948 | 2026-07-16 |  |  | 2026-07-27 | 2026-07-28 | KPTG-TRANSMIT-003119 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-13 | JFS-AU-TRANSMIT-000003 | NA | Consultant | Facade Weatherproofing PBDB and Facade Wind Pressure Report | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | Information only, the same document already under review and locked in Aconex. |  | 2026-07-13 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-14 | CLADC-TRANSMIT-000012 | NA | Trade Partner | Resubmitted tech data | 0 | 9 | 0 | NA | APPROVED | 2026-01-14 | WF-000710 | NA | 2026-01-19 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-002666 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-01 | Eneraque-TRANSMIT-000026 | NA | Trade Partner | Fuel Storage Tanks General Arrangement | 1 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 1206 | 2026-07-13 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-005545 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-13 | Stowe-A-TRANSMIT-000640 | NA | Trade Partner | STOWE - As-built Updates - DH 6 containment | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with Revision, revision history, title. |  | 2026-07-13 | KPTG-SADV-006597 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-10 | INGEN3D-TRANSMIT-000700 | NA | Trade Partner | Re: I3D-378 Next DC M3 Stage 4 - Acoustic Wall - LP2018, PW1922, PW1925 & PW1935 - IFC (10-03-2026) | 0 | 4 | 0 | NA | APPROVED | 2026-04-10 | WF-005246 | NA | 2026-04-14 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-019615 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-07-13 | DI-TRANSMIT-000158 | NA | Trade Partner | Fwd: Sit eplan updated - HFF fencing and gates | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | The register has been updated. If any further action is required, the coordinator will inform. |  | 2026-07-13 | DRAFT-010367 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-07-13 | SMEPS-TRANSMIT-000346 | NA | Trade Partner | Updated IFC Drawings - Stage 3 22kV Switchroom (Basement Level) General Light & Power | 2 | 0 | 0 | NA | APPROVED | 2026-07-13 | WF-006361 | NA | 2026-07-16 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-02 | BTBM-TRANSMIT-000003 | NA | Trade Partner | Better Built Masonry sample | 0 | 1 | 0 | NA | APPROVED | 2026-07-02 | WF-001113 | NA | 2026-07-08 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-005530 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-13 | Fredon T-TRANSMIT-000025 | NA | Trade Partner | AV Tech Data - Indoor Courts Scoreboards | 0 | 1 | 0 | NA | APPROVED | 2026-07-13 | WF-001044) | NA | 2026-07-17 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-003104 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-13 | Aurecon-TRANSMIT-000118 | NA | Consultant | Telecommunication Services - Issued for Information | 34 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 380 | 2026-07-21 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-000572 | Closed | 34 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-13 | PTA-TRANSMIT-000023 | NA | Consultant | Building Section Issue for Coordination | 2 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 442 | 2026-07-21 |  |  | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-000641 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-13 | S.T.S-TRANSMIT-000006 | NA | Trade Partner | Loading Dock Review | 0 | 1 | 0 | KPTG-IntCorr-000290 | APPROVED |  | NA | NA |  |  | Review not required |  | 2026-07-14 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-14 | ECBS-TRANSMIT-000051 | NA | Trade Partner | Submission of Ripple Sound RCP Drawings | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Document Number is incorrect, requested them to resubmit |  | 2026-01-14 | KPTG-SADV-003312 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-13 | Auspan-TRANSMIT-000500 | NA | Trade Partner | : Retransmit shop drawings level 1 due to shop drawings | 3 | 0 | 0 | KPTG-IntCorr-000957 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise KPTG-IntCorr-000957 No update same drawing, and was distributed. - KPTG-IntCorr-000966 - |  | 2026-07-16 | KPTG-IntCorr-000966 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-13 | Auspan-TRANSMIT-000499 | NA | Trade Partner | Re: RFI: Zone 5 Core - Panel Changes B/GF (URGENT | 3 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 1471 | 2026-07-21 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-002787 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-13 | M.2-TRANSMIT-000062 | NA | Trade Partner | : Meter Panel Shop Drawings | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to drawing Title, reference and other QA issues. DRAFT-009803 |  | 2026-07-13 | DRAFT-009803 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-13 | Auspan-TRANSMIT-000498 | NA | Trade Partner | : Re: Zone 2 Panel Changes - Hoist Location | 20 | 0 | 0 | KPTG-IntCorr-000956. | APPROVED | 2026-07-14 | NA | 1477 | 2026-07-21 |  | IFC - Waiting for Kim advise KPTG-IntCorr-000956. Review initiated as per kim advice KPTG-IntCorr-000965 | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003107 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-13 | JCBa-TRANSMIT-000150 | NA | Consultant | Architectural Documentation - Door Schedule, Door & Window Elevations and Door Frame Profiles | 6 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 1464 | 2026-07-15 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-002914 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-13 | POTTSENG-TRANSMIT-000056 | NA | Trade Partner | : GMAC: HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONE 2 LAYOUT | 1 | 0 | 0 | KPTG-IntCorr-000958 | APPROVED |  | NA | NA |  |  | waiting for Kapitol PC advise - KPTG-IntCorr-000958 IFC Rejected : IFA revision is not approved. DRAFT-009939 |  | 2026-07-15 | DRAFT-009939 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-13 | CEDWA-TRANSMIT-000012 | NA | Consultant | Updated Civil Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 1310 | 2026-07-15 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-004094 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-13 | Endfire-TRANSMIT-000082 | NA | Trade Partner | ENDFIRE Water Mist FC Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 1312 | 2026-07-15 |  |  | 2026-08-13 | 2026-08-14 | KPTG-TRANSMIT-004257 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-13 | Bianco-TRANSMIT-000005 | NA | Trade Partner | : 671CHP-FOR APPROVAL (B) | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Review required as advised by Kapitol PC. - KPTG-IntCorr-000961 |  | 2026-07-13 | KPTG-IntCorr-000961 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-13 | RDSBIM-TRANSMIT-000085 | NA | Trade Partner | 671CHP ¦ LEVEL 02 CONCRETE PROFILE PLAN AND SECTION | 3 | 0 | 0 | KPTG-IntCorr-000962 | APPROVED | 2026-07-21 | NA | 666 | 2026-07-29 |  | Waiting for advice from Kian, KPTG-IntCorr-000962 | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-001407 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-14 | KPTG-IntCorr-003878-ARCO-ARCH-TEC-01 | NA | Trade Partner | ARCO External Bifold Paint Tech data | 0 | 1 | 0 | NA | APPROVED | 2026-01-14 | WF-000708 |  | 2026-01-19 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-14 | D&E-TRANSMIT-000913 | NA | Trade Partner | SFN - MF, Temp, DP Sensors - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-14 | KPTG-TRANSMIT-019628 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-14 | Entire M-TRANSMIT-000082 | NA | Trade Partner | COLO 4 Condenser relocation | 1 | 0 | 0 | NA | APPROVED | 2026-07-14 | WF-000389 | NA | 2026-07-16 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-001066 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-14 | Entire M-TRANSMIT-000082 | NA | Trade Partner | COLO 4 Condenser relocation | 1 | 0 | 0 | NA | APPROVED | 2026-07-14 | WF-000390 | NA | 2026-07-16 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-001066 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-14 | SES AU-TRANSMIT-000081 | NA | Trade Partner | SECURITY - QA SECTIONS - IFC | 3 | 0 | 0 | NA | APPROVED | 2026-07-14 | WF-000391 | NA | 2026-07-16 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-001076 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-14 | Auspan-TRANSMIT-000502 | NA | Trade Partner | Precast shop drawings for construction. Level 3 | 12 | 0 | 0 | KPTG-IntCorr-000961 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise- KPTG-IntCorr-000961 KPTG-IntCorr-001133 Internal memo from Kim .This transmittal has been superseded - Panels Reviewed in KPTG-IntCorr-001062 |  | 2026-07-28 | KPTG-IntCorr-001062 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-14 | Auspan-TRANSMIT-000502 | NA | Trade Partner | Precast shop drawings for construction. Level 3 | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to difference in revision , status and latest IFA is rejected - DRAFT-009817 |  | 2026-07-14 | DRAFT-009817 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-14 | RDSBIM-TRANSMIT-000023 | NA | Trade Partner | MEL11C45 ¦ LEVEL 02 HAC AISLE ELEVATION | 1 | 0 | 0 | NA | APPROVED | 2026-07-14 | WF-000392 | NA | 2026-07-17 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-001073 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-14 | JCBa-TRANSMIT-000271 | NA | Consultant | Building Permit Issue - L00 & L09 | 48 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 600 | 2026-07-16 |  | NA | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-003159 | Closed | 48 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-13 | G&CHyd-TRANSMIT-000010 | NA | Consultant | HYD TECH DATA 04 | 0 | 33 | 0 | NA | APPROVED | 2026-07-13 | WF-000950 | NA | 2026-07-17 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-003486 | Closed | 33 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-13 | Jangho-TRANSMIT-000238 | NA | Consultant | FT07 & FT-09 Syetem Concept Drawing-_Rev A_For_IFC | 33 | 0 | 0 | KPTG-TRANSMIT-002836 | APPROVED | 2026-07-14 | NA | 954 | 2026-07-20 |  | FC Doc. clarification from Xavier - FIRST ISSUE FC-KPTG-TRANSMIT-002836 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-02 | 4DW-TRANSMIT-000077 | NA | Consultant | Precast Update | 1 | 0 | 0 | NA | APPROVED | 2025-12-02 | NA | 472 | 2025-12-08 |  |  | 2025-12-02 | 2025-12-02 | KPTG-SADV-002325 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-14 | KPTG-IntCorr-003886- ARCO-ARCH-SPD-007-1 & ARCO-ARCH-SPD-007-2 | NA | Trade Partner | BIFOLDS - CARPARK ( WEST CARPARK ENTRY D03-A0.11) SUBMISSION | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Document Number is incorrect, requested them to resubmit. |  | 2026-01-14 | KPTG-IntCorr-003887 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-13 | RDSBIM-TRANSMIT-000062 | NA | Trade Partner | GROUND FLOOR TO LEVEL 09 STAIR CORE 1 CONCRETE PROFILE PLAN SECTION AND ELEVATION | 8 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 950 | 2026-07-20 |  |  | 2026-07-28 | 2026-07-29 | KPTG-TRANSMIT-003159 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-13 | Baigents TC Docs by Email | NA | Consultant | TOWER CRANE OF BAIGENTS | 5 | 0 | 0 | NA | APPROVED | [5 empty] | 1 DOC QA ERROR - JINFORMED JARROD. - REGISTER UPDATED |  | 2026-07-13 | NA | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-13 | EFWC-TRANSMIT-000002 | NA | Consultant | Shop Drawings (Rev. A) - (S2) - Kapitol - V02272 - District Living - 24 Little Docklands Drive, Docklands | 4 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED : KPTG-TRANSMIT-002865 |  | 2026-07-13 | KPTG-TRANSMIT-002865 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-13 | PCForm-TRANSMIT-000264 | NA | Consultant | Stair Form Fire Rail Sample - attempt 2 | 0 | 1 | 0 | NA | APPROVED | 2026-07-13 | WF-000951 | NA | 2026-07-16 |  |  | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-003004 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-13 | INGEN3D-TRANSMIT-000101 | NA | Consultant | Level 12-14 - Precast Columns - IFA (08-06-2026) | 2 | 0 | 0 | NA | APPROVED | 2026-07-13 | WF-000948 | NA | 2026-07-16 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-003037 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-13 | INGEN3D-TRANSMIT-000194 | NA | Consultant | Level 19-21 - Precast Columns - IFA (29-06-2026) | 16 | 0 | 0 | NA | APPROVED | 2026-07-13 | WF-000952 | NA | 2026-07-29 |  |  | 2026-07-20 | 2026-07-21 | KPTG-TRANSMIT-003007 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-14 | SMEPS-TRANSMIT-000233 | NA | Trade Partner | NEL-CNT-SME-2990-ELC-SAM-0077,0078, | 0 | 7 | 0 | NA | REJECTED | [5 empty] | Revision inside the document and in Aconex seem different |  | 2026-07-14 | KPTG-TRANSMIT-001436 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-14 | VERTIV-TRANSMIT-000049 | NA | Trade Partner | NEXT DC GE 01 _ TECHNICAL DATA _ VENTILATION SYSTEM SOO (FOA-1) | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with document and title sheet missing. |  | 2026-07-14 | KPTG-SADV-000918 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-13 | INGEN3D-TRANSMIT-000195 | NA | Consultant | Level 12-14 - PC0504, PC0709 & PC0711 - Revised & New IFA | 4 | 0 | 0 | NA | APPROVED | 2026-07-13 | WF-000953 | NA | 2026-07-29 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-003043 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-14 | KPTG-IntCorr-003890 | NA | Trade Partner | BIFOLDS - CARPARK ( WEST CARPARK ENTRY D03-A0.11) SUBMISSION | 2 | 0 | 0 | NA | APPROVED | 2026-01-14 |  | 395 |  |  | Review is void. updated Drawing is received on 15.01.2026 | 2026-01-19 |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-14 | HIG-TRANSMIT-000012 | NA | Trade Partner | Anti Graffiti Update | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | WF-001045) | NA | 2026-07-17 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-003137 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-14 | DLTS-TRANSMIT-000055 | NA | Trade Partner | S11-HV ROOM-IFA Issue | 85 | 0 | 0 | NA | APPROVED | 2026-07-14 | WF-001212 | NA | 2026-07-16 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-005881 | Closed | 85 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-14 | BIMF-TRANSMIT-000013 | NA | Trade Partner | Level 2 Drainage Plans, Rev A | 2 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 952 | 2026-07-20 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-003509 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-14 | HGP-TRANSMIT-000064 | NA | Trade Partner | Transmittal-Louvres Shop Drawing | 17 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-07-14 | KPTG-TRANSMIT-001437 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-14 | D&E-TRANSMIT-000916 | NA | Trade Partner | Pumps - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | WF-006362 | NA | 2026-08-04 |  | As instructed by Ellie , this Workflow has been terminated |  | 2026-07-14 |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-14 | JCBa-TRANSMIT-000153 | NA | Consultant | Updated Architectural Documentation - General Arrangement Plans, Partition Plans & Partition Detail Sections | 81 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 1475 | 2026-07-16 |  | Review Terminated as advised by Kapitol DM (updated drawings are coming.) |  | 2026-07-23 | NA | Closed | 81 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-14 | Civilex-TRANSMIT-000292 | NA | Trade Partner | Stage 2 - sample submission - No Fines Concrete - Hytec | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | WF-006363 | NA | 2026-07-20 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-019817 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-14 | Auspan-TRANSMIT-000501 | NA | Trade Partner | Update precast shop drawing 1P4002 | 1 | 0 | 0 | KPTG-IntCorr-000962 | APPROVED | 2026-07-14 | NA | 1479 | 2026-07-21 |  | IFC - Waiting for Kim advise-KPTG-IntCorr-000962 Review initiated - KPTG-IntCorr-000968 | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003110 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-14 | Auspan-TRANSMIT-000503 | NA | Trade Partner | Precast shop drawings for construction. Level 4 | 2 | 0 | 0 | KPTG-IntCorr-000963 | REJECTED | [5 empty] | IFC - Waiting for Kim advise-KPTG-IntCorr-000963 Rejected by Project coordinator - KPTG-IntCorr-001153 |  | 2026-07-29 | KPTG-IntCorr-001153 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-13 | VAE-Grp-TRANSMIT-000167 | NA | Trade Partner | MECHANICAL - DETAILS SHEET 6 - ADDITIONAL SECURITY GRILLE TYPES - TITLE CORRECTED | 1 | 0 | 0 | NA | APPROVED | 2026-07-13 | NA | 1308 | 2026-07-17 |  | RE-SUBMITTED FOR SCG APPROVAL | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-004195 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-15 | NXT-TRANSMIT-001190 EAEGROUP-TRANSMIT-000056 | NA | Trade Partner | M3-ELC-EAE-SDRG-C-0401-0001-IFC | 1 | 0 | 0 | NA | APPROVED | 2026-01-15 | WF-003811 |  | 2026-02-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-13 | SKS Tech-TRANSMIT-000196 | NA | Trade Partner | PSUB Cx L2 and ROP commissioning ITP submittal | 0 | 2 | 0 | NA | APPROVED | 2026-07-13 | WF-001151 | NA | 2026-07-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-14 | D&E-TRANSMIT-000914 | NA | Trade Partner | SFN - MF, Temp, DP Sensors - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | [5 empty] | For distribution |  | 2026-07-14 | KPTG-TRANSMIT-019639 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-14 | Stowe-A-TRANSMIT-000641 | NA | Trade Partner | STOWE - Stage 1 Office - IFA | 2 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 4372 | 2026-07-23 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-14 | Civilex-TRANSMIT-000293 | NA | Trade Partner | Stage 2 - sample submission - Agroflex - Draincoil WRta Sock 100x20m | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | WF-006366 | NA | 2026-07-20 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-019906 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-14 | ELLISAIR-TRANSMIT-000119 | NA | Trade Partner | Stage 9 Ground Floor Zone 1 Duct layout drawing issued for Construction. | 1 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 1384 | 2026-07-21 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-006036 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-14 | Nilsen3-TRANSMIT-000062 | NA | Trade Partner | Nilsen Drawings Issued for Construction | 6 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 1387 | 2026-07-21 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-005876 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-14 | WilsonPD-TRANSMIT-000070 | SPARK-CRFI-KPG-000528 | Trade Partner | Tech Data - Multiple | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | NA | NA | 2026-07-14 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-001438 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-14 | ELLISAIR-TRANSMIT-000120 | NA | Trade Partner | Stage 11 Level 01 Duct drawings issued for Approval. | 6 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 1388 | 2026-07-21 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-006040 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-14 | Nilsen3-TRANSMIT-000066 | NA | Trade Partner | Nilsen Sample submissions #7 | 0 | 2 | 0 | NA | APPROVED | 2026-07-14 | WF-001214 | NA | 2026-07-22 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-14 | D&E-TRANSMIT-000290 | SPARK-CRFI-KPG-000313 | Trade Partner | MWYCCB - GROUND LEVEL - PIPEWORK LAYOUT ZONE 6 & ZONE 7 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 352 | 2026-07-14 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-001460 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-14 | RDSBIM-TRANSMIT-000048 | NA | Trade Partner | LEVEL05 - WEBFORGE SETOUT PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-01-14 | NA | 818 | 2026-01-16 |  |  | 2026-01-16 | 2026-01-16 | KPTG-TRANSMIT-002475 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-14 | D&E-TRANSMIT-000915 | NA | Trade Partner | NXM3S4 - Ground - CHW Pipe Layout - Zone 2 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-14 | KPTG-TRANSMIT-019648 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-14 | HAN IND-TRANSMIT-000001 | NA | Trade Partner | Cooling Towers IFA | 22 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with Document number, title, revision number. |  | 2026-07-14 | KPTG-TRANSMIT-001121 | Closed | 22 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-14 | RDSBIM-TRANSMIT-000063 | NA | Trade Partner | DISTLV ¦ LEVEL 01 CONCRETE PROFILE PLAN ¦ IFA | 4 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 956 | 2026-07-23 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-14 | Eneraque-TRANSMIT-000038 | NA | Trade Partner | ENE - Ground Level Pipework Isometric Drawings | 8 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 1390 | 2026-07-21 |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-006236 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-14 | INTRFRM-TRANSMIT-000102 | NA | Trade Partner | External Plant Slab concrete | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | WF-000315 | NA | 2026-07-24 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-001135 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-14 | D&E-TRANSMIT-000917 | NA | Trade Partner | NXM3S4 - Level 1 - CHW Pipe Layout - Zone 2 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-14 | KPTG-TRANSMIT-019653 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-14 | D&E-TRANSMIT-000725 | NA | Trade Partner | Louvres - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | WF-006367 | NA | 2026-07-17 |  | As Instructed by Ellie - Terminated |  | 2026-07-29 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-14 | Nilsen3-TRANSMIT-000065 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 21 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 1394 | 2026-07-21 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-006149 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-14 | ASV-TRANSMIT-000076 | NA | Trade Partner | REVISED CIVIL REVISION DATE | 1 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 1393 | 2026-07-21 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-006837 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-14 | Entire M-TRANSMIT-000083 | NA | Trade Partner | External Sensors and Pressure Pickup | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Drawing Status needs to be " For Approval":KPTG-IntCorr-000675 |  | 2026-07-14 | KPTG-IntCorr-000675 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-14 | RDSBIM-TRANSMIT-000049 | NA | Trade Partner | LEVEL 04 RCP KEY PLAN AND LAYOUT | 5 | 0 | 0 | NA | APPROVED | 2026-01-14 | NA | 820 | 2026-01-16 |  |  | 2026-01-22 | 2026-01-22 | KPTG-TRANSMIT-002570 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-14 | ASV-TRANSMIT-000188 | NA | Trade Partner | Hydraulic Asset Labels | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | WF-006368 | NA | 2026-07-24 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-019738 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-14 | Eneraque-TRANSMIT-000039 | NA | Trade Partner | ENE - Level 2 Pipework Isometric Drawings | 6 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 1396 | 2026-07-21 |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-006244 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-14 | D&E-TRANSMIT-000918 | NA | Trade Partner | NXM3S4 - Level 1 - CHW Pipe Layout - Zone 8 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | [5 empty] | For distribution |  | 2026-07-14 | KPTG-TRANSMIT-019658 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-14 | D&E-TRANSMIT-000259 | NA | Trade Partner | Mechanical Services Commissioning Plan Rev-01 | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | NA | NA | 2026-07-14 |  | Actual received date 29/05/2026 | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-001440 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-14 | SMEPS-TRANSMIT-000073 | NA | Trade Partner | STAGE 9-11 Overall Electrical Inground Site Layout (FC-2) | 1 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 1398 | 2026-07-21 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-006384 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-14 | ASV-TRANSMIT-000189 | NA | Trade Partner | Hydraulic Sample - Round Clean Out | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | WF-006369 | NA | 2026-07-18 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-019771 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-14 | Stowe-A-TRANSMIT-000642 | NA | Trade Partner | STOWE - DH 6 CONTANMENT - AS BUILTS | 3 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 4375 | 2026-07-24 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020202 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-14 | Nilsen3-TRANSMIT-000068 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 2 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 1400 | 2026-07-21 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-14 | NXES-TRANSMIT-000076 | NA | Trade Partner | Nexus Tech Data - 123 and 201 | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | WF-001046 | NA | 2026-07-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-14 | NXES-TRANSMIT-000076 | NA | Trade Partner | Nexus Tech Data - 123 and 201 | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | WF-001047 | NA | 2026-07-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-15 | DS-TRANSMIT-000087 | NA | Trade Partner | GF H L Water and L01 Drainage - Issued for construction | 6 | 0 | 0 | NA | APPROVED | 2026-01-15 | WF-003812 |  | 2026-01-15 |  |  |  | 2026-02-20 | KPTG-TRANSMIT-013279 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-14 | Tradetec-TRANSMIT-000482 | NA | Trade Partner | IFA - Stage 4 - CP20, CP38 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision |  | 2026-07-14 | ⁠KPTG-DA-007575 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-14 | SMEPS-TRANSMIT-000242 - | NA | Trade Partner | SME Electrical Earthing layout IFA 1 | 1 | 0 | 0 | NA | APPROVED | 2026-07-14 | WF - 000543 | NA | 2026-07-20 |  | NA | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-001117 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-14 | Jangho-TRANSMIT-000240 | NA | Trade Partner | Siliding Door Sample Submission（Handle） | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | WF-000958 | NA | 2026-08-06 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002960 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-14 | Eneraque-TRANSMIT-000040 | NA | Trade Partner | ENE : Level 1 Exterior Isometric Pipework Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 1402 | 2026-07-21 |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-006249 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-14 | 4DW-TRANSMIT-000195 | NA | Consultant | Structural Documentation - Crane Base updates | 4 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 389 | 2026-07-17 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-003100 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-14 | fjc-TRANSMIT-000154 | NA | Consultant | Fwd: (WF-000748) Heritage Glass (ARK, Inhabit, FJC, T&P) | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001193 - ALREADY REVISION 3 IN WF. | 2026-07-14 | 2026-07-14 | KPTG-IntCorr-001193 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-14 | Stowe-A-TRANSMIT-000643 | NA | Trade Partner | Re: STOWE - DH 1 - AS BUILTS | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to revision mistakes |  | 2026-07-14 | KPTG-SADV-006620 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-14 | KPTG-TRANSMIT-001100 | NA | Trade Partner | Energisation Plan - Issued For Approval | 0 | 2 | 0 | NA | APPROVED | 2026-07-14 | WF - 000544 | NA | 2026-07-20 |  | NA | 2026-07-14 | 2026-07-20 | KPTG-TRANSMIT-001112 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-14 | D&E-TRANSMIT-000919 | NA | Trade Partner | NXM3S4 - Chiller Roof Builders Works Layout Zone + Roof Level Switchroom - Mechanical Duct - Issued For Construction | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-14 | KPTG-TRANSMIT-019663 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-14 | Entire M-TRANSMIT-000084 | NA | Trade Partner | Updated BAS layouts 1:50 | 8 | 0 | 0 | NA | APPROVED | 2026-07-14 | WF-000393 | NA | 2026-07-17 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-001082 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-15 | PFP PL-TRANSMIT-000057 | NA | Trade Partner | Updated tech data sheets | 0 | 7 | 0 | NA | APPROVED | 2026-01-15 | WF-003815 |  | 2026-02-05 |  |  |  | 2026-01-29 | KPTG-TRANSMIT-012179 | Closed | 7 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-14 | WilsonPD-TRANSMIT-000112 | NA | Trade Partner | Stage 9 Link Bridge Roof Sewer and Stormwater | 1 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 1404 | 2026-07-21 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-006168 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-14 | Entire M-TRANSMIT-000062 | NA | Trade Partner | Air & Dirt Separators - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | WF-000316 | NA | 2026-07-27 |  |  | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-001216 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-14 | KPTG-TRANSMIT-001101 | NA | Trade Partner | Load Bank Plan - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | WF- 000545 | NA | 2026-07-20 |  | NA | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-001130 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-14 | Entire M-TRANSMIT-000085 | NA | Trade Partner | Updated BAS layouts 1:100 | 3 | 0 | 0 | NA | APPROVED | 2026-07-14 | WF-000394 | NA | 2026-07-17 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-001078 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-14 | KPTG-WTRAN-012042 | NA | Trade Partner | (WF-006372) M3 - DOCUMENT CONTROL REVIEW - S4- IFC -MECHANICAL SERVICES - CONSULTANT REVIEW-SHOP DRAWING - Instructed by Ellie Salmon - #3861 | 5 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 3861 | 2026-07-23 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-020578 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-14 | Entire M-TRANSMIT-000063 | NA | Trade Partner | Entire Mechanical Services | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | WF-000317 | NA | 2026-07-24 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001592 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-14 | HGP-TRANSMIT-000011 | NA | Trade Partner | IFC window shop drawings | 20 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 1406 | 2026-07-21 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-005797 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-14 | Baigents-TRANSMIT-000228 | NA | Trade Partner | Outside HV Room Balustrade FC-1 | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-07-14 | KPTG-TRANSMIT-004091 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-14 | SPECAUTO-TRANSMIT-000005 | NA | Trade Partner | Modbus RTU Protocol Cable LSZH | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | WF-000318 | NA | 2026-07-24 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-001517 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-14 | HGP-TRANSMIT-000065 | NA | Trade Partner | Transmittal-Louver Package Shop Drawing IFA Rev03 | 17 | 0 | 0 | NA | REJECTED | [5 empty] | Attached drawing revision is already received No longer in use drawing attached |  | 2026-07-14 | KPTG-TRANSMIT-001445 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-15 | ADP-TRANSMIT-000152 | NA | Consultant | Re: S4 ¦ ADP MEL4780 - Battery Room Drawings & Schenatics (FIP) | 3 | 0 | 0 | NA | APPROVED | 2026-01-15 |  | 1778/1780/1782 | 2026-01-19 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-011595 / KPTG-TRANSMIT-011599 / KPTG-TRANSMIT-012076 | Closed | 3 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-14 | M.2-TRANSMIT-000064 | NA | Trade Partner | Re: MSB shop Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 1481 | 2026-07-21 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-002906 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-14 | KPTG-WTRAN-012046 | NA | Trade Partner | S4 ¦ SAMPLE AND TECH DATA - CONSULTANT REVIEW - MECHANICAL ACOUSTIC -WORKFLOW-LATEST - As instructed by Ellie | 0 | 3 | 0 | NA | APPROVED | 2026-07-14 | WF-006373 | NA | 2026-07-30 |  | As instructed by Ellie Salmon | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-020294 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-14 | Stowe-A-TRANSMIT-000645 | NA | Trade Partner | Stowe - Drawing IFA | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect document status and reason for issue. |  | 2026-07-14 | KPTG-TRANSMIT-019670 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-14 | Nilsen3-TRANSMIT-000069 | NA | Trade Partner | Nilsen Drawings Issued for Construction | 2 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 1409 | 2026-07-21 |  |  | 2026-07-29 | 2026-07-29 | Nilsen3-TRANSMIT-000069 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-14 | Stowe-A-TRANSMIT-000644 | NA | Trade Partner | STOWE - HOUSE CONTAINMENT AS BUILTS | 5 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 4378 | 2026-07-28 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020198 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-14 | Stowe-A-TRANSMIT-000646 | NA | Trade Partner | STOWE - Schematic As Builts | 22 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 4379 | 2026-07-17 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020191 | Closed | 22 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-14 | Stowe-A-TRANSMIT-000647 | NA | Trade Partner | STOWE - DH 5 As-builts | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Resubmission of same revision with us with incorrect revision date. |  | 2026-07-14 | KPTG-SADV-006635 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-14 | Stowe-A-TRANSMIT-000648 | NA | Trade Partner | Re: STOWE - Busduct As-Builts | 5 | 0 | 0 | NA | REJECTED | [5 empty] | AS-BUILT SUBMITTED WITHOUT APPROVAL OF IFC |  | 2026-07-14 | KPTG-TRANSMIT-019672 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-14 | ADP-TRANSMIT-000369 | NA | Trade Partner | Fwd: ADP MEL4561 - CAN - Acoustic Compliance Statement | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For information and updating document register | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-019673 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-18 | SES AU-TRANSMIT-000001 | NA | Trade Partner | Security samples | 0 | 14 | 0 | NA | APPROVED | 2026-06-18 | WF-000977 | NA | 2026-06-25 |  |  | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-005967 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-13 | RDSBIM-TRANSMIT-000144 | NA | Trade Partner | LEVEL 04 PARTITION WALL PLAN | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties |  |  |  | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-14 | Aurecon-TRANSMIT-000119-DRG | NA | Consultant | Fuel Services - LOD300 Issued for Contract | 23 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 390 | 2026-07-22 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-14 | Aurecon-TRANSMIT-000119 | NA | Consultant | Fuel Services - LOD300 Issued for Contract | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | 2026-07-22 |  | Updated on Forma |  | 2026-07-14 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-14 | Aurecon-TRANSMIT-000118-SME | NA | Consultant | Telecommunication Services - Issued for Information | 34 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 386 | 2026-07-22 |  |  | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-000647 | Closed | 34 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-14 | Baigents-TRANSMIT-000015 | NA | Trade Partner | Prototype Precast Beams IFC | 4 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 392 | 2026-07-22 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-000574 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-14 | NXT-TRANSMIT-000437-DRG | NA | Client | Eaton UPS | 4 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 394 | 2026-07-22 |  |  | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-000644 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-14 | NXT-TRANSMIT-000437-SPE | NA | Client | Eaton UPS | 0 | 9 | 0 | NA | APPROVED | 2026-07-14 | NA | 396 | 2026-07-22 |  |  | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-000645 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-14 | NXT-TRANSMIT-000437-DOC | NA | Client | Eaton UPS | 0 | 3 | 0 | NA | APPROVED | 2026-07-14 | NA | 398 | 2026-07-22 |  |  | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-000646 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-14 | NXT-TRANSMIT-000437-SCH | NA | Client | Eaton UPS | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated on ACC |  | 2026-07-14 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-14 | NXT-TRANSMIT-000438 | NA | Client | Vertiv Drawings | 19 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong Naming convention |  | 2026-07-14 | Awaiting approval | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-14 | NXT-TRANSMIT-000439 | NA | Client | LAI PDU Drawings | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong Naming Convention |  | 2026-07-14 | Awaiting approval | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-13 | KPTG-IntCorr-001424 | N/A | Trade Partner | Linkstone sample review workflows | 0 | 7 | 0 | NA | APPROVED | 2026-01-13 | 000862 to 000868 | NA | 2026-01-19 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-14 | Auscool-TRANSMIT-000059 | NA | Trade Partner | : BASEMENT - ZONE 2 - IFC BW DRAWING | 1 | 0 | 0 | KPTG-IntCorr-000972 | APPROVED |  | NA | NA |  |  | Previous rev. IFA is rejected; waiting for advice from Kapitol - KPTG-IntCorr-000972 IFC Rejected : IFA revision is not approved. DRAFT-009937 |  | 2026-07-15 | DRAFT-009937 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-14 | M.2-TRANSMIT-000063 | NA | Trade Partner | Meter Panel Shop Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 1483 | 2026-07-21 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-002984 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-14 | TTW-TRANSMIT-000045-SME | NA | Consultant | Facade drawing-For Tender | 16 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 387 | 2026-07-22 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-14 | Auspan-TRANSMIT-000504 | NA | Trade Partner | : Re: Precast shop drawings for approval. 7P2002 were split. | 2 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 1474 | 2026-07-21 |  |  | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-002956 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-14 | TTW-TRANSMIT-000044-SME | NA | Consultant | Civil Technical Specification | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | NA | 388 | 2026-07-22 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001026 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-14 | IJF-TRANSMIT-000001 | NA | Trade Partner | Joinery - Prototype drawings | 21 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to drawing QA issues . KPTG-SADV-003456 |  | 2026-07-14 | KPTG-SADV-003456 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-14 | Aurecon-TRANSMIT-000122-DRG | NA | Consultant | CSMS Services - LOD300 Issued for Contract | 13 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 402 | 2026-07-22 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-000581 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-14 | Auspan-TRANSMIT-000505 | NA | Trade Partner | : Re: RFI: Amend panel 1P4002 to suit 1P4005 | 1 | 0 | 0 | KPTG-IntCorr-000971 | APPROVED |  | NA | NA |  |  | IFC Waiting for Kim advise- KPTG-IntCorr-000971 |  | 2026-07-22 | KPTG-TRANSMIT-002909 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-14 | Aurecon-TRANSMIT-000122-SCH | NA | Consultant | CSMS Services - LOD300 Issued for Contract | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated on Forma |  | 2026-07-14 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-14 | Auscool-TRANSMIT-000060 | NA | Trade Partner | : Re: Mech - Shop Drawing & Procurement Register | 0 | 19 | 0 | NA | REJECTED |  | NA |  |  |  | Transmittal is superseded with Auscool-TRANSMIT-000062: |  | 2026-07-14 | NA | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-02 | PCForm-TRANSMIT-000051 | NA | Trade Partner | Ground Floor - Issued for Construction (S&I) | 1 | 0 | 0 | KPTG-SADV-002326 | APPROVED |  | NA | NA |  |  | IFC drawing. Updated to Document Register only |  | 2026-01-30 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-13 | ccair-TRANSMIT-000083 | NA | Trade Partner | Riser Core B Mechanical Ductwork Layout - IFC | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties |  |  |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-14 | Aurecon-TRANSMIT-000122-spe | NA | Consultant | CSMS Services - LOD300 Issued for Contract | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | NA | 404 | 2026-07-22 |  |  | 2026-07-22 | 2026-07-23 | KPTG-TRANSMIT-000678 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-14 | Auscool-TRANSMIT-000062 | NA | Trade Partner | :Updated Tech Data | 0 | 19 | 0 | NA | APPROVED | 2026-07-14 | WF-000709 | NA | 2026-07-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-14 | SMEPS-TRANSMIT-000001 | NA | Trade Partner | Electrical Temporary Services Layout | 1 | 0 | 0 | KPTG-IntCorr-000299 | APPROVED |  | NA | NA |  |  | Review not required |  | 2026-07-27 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-14 | crossfir-TRANSMIT-000025 | NA | Trade Partner | Wet Fire - Ground Floor & Level 01, IFA | 2 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 649 | 2026-07-21 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-001612 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-14 | fjc-TRANSMIT-000165 | NA | Consultant | Architecturals - Outsanding EoT Documentation | 17 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004920 - History box, tittle are missing and also the tittle are different inside the document. | 2026-07-14 | 2026-07-14 | KPTG-SADV-004920 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-14 | fjc-TRANSMIT-000166 | NA | Consultant | Drawing Updates | 2 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 694 | 2026-07-20 |  | KPTG-IntCorr-001196 - as per your direction we terminate the wf | 2026-07-14 | 2026-07-14 | KPTG-IntCorr-001196 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-15 | Auspan-TRANSMIT-000506 | NA | Trade Partner | Resubmit shop drawings for level 2, 3 zone 4, 5 for approval | 6 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 1486 | 2026-07-22 |  |  | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-002938 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-14 | ZIA-TRANSMIT-000072 | NA | Trade Partner | CSMS - Cx L2 Plan Documents | 0 | 6 | 0 | NA | APPROVED | 2026-07-14 | WF-001159 | NA | 2026-07-17 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-004185 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-15 | P & R-TRANSMIT-000096 | NA | Trade Partner | Stage 2 - Fan for IFA | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejeted: Document number in the covering sheet is wrong:KPTG-SADV-005321 |  | 2026-07-15 | KPTG-SADV-005321 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-14 | ZIA-TRANSMIT-000073 | NA | Trade Partner | CSMS - Cx L2 ITP Document | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | WF-001159 | NA | 2026-07-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-15 | Altaire-TRANSMIT-000056 | NA | Trade Partner | NEXTDC M3S4 - Dry Fire L1 Shop Drawings C1 & C2 (For Approval) (1) | 2 | 0 | 0 | NA | APPROVED | 2026-01-15 |  | 1775 | 2026-01-23 |  |  |  | 2026-02-12 | KPTG-TRANSMIT-012778 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-15 | ELLISAIR-TRANSMIT-000121 | NA | Trade Partner | Stage 11 Ground Floor & Level 1 Zone 3 and 4 Builders Works drawings issued for Approval. | 4 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 1424 | 2026-07-22 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-006672 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-14 | fjc-TRANSMIT-000166 | NA | Consultant | Drawing Updates | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | WF-000832 | NA | 2026-07-21 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-002855 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-14 | KPTG-IntCorr-001705 | NA | Trade Partner | PARRATECH CX DOCS | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | WF-001155 | NA | 2026-07-17 |  | 1 doc - no action, 5 pending locked in w/flow - (WF-001147) | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-004141 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-14 | KPTG-IntCorr-001706 | NA | Trade Partner | PARRATECH CX DOCS | 0 | 3 | 0 | NA | APPROVED | 2026-07-14 | WF-001157 | NA | 2026-07-16 |  | 1 pending locked in a workflow - WF-001037 | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-004133 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-15 | Rinco-TRANSMIT-000064 | NA | Consultant | Sleeper retaining wall detail update | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Revision code is missing in the drawing -DRAFT-009915 |  | 2026-07-15 | DRAFT-009915 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-15 | fjc-TRANSMIT-000166 | NA | Consultant | Drawing Updates | 1 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 696 | 2026-07-18 |  | There were two drawings in the submission, and I rejected one of them because a new revision has been issued for that drawing. | 2026-07-16 | 2026-07-16 | KPTG-SADV-004978 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-14 | KPTG-IntCorr-001707 | NA | Trade Partner | VERTIV Cx Docs | 0 | 7 | 0 | NA | APPROVED | 2026-07-14 | WF-001158 | NA | 2026-07-16 |  | 1 doc no action | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-004179 | Open | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-14 | KPTG-IntCorr-001708 | NA | Trade Partner | ORISE CX DOCS | 0 | 5 | 0 | NA | APPROVED | 2026-07-14 | WF-001159 | NA | 2026-07-17 |  | 8 docs locked in w/flows - wf-1148 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-14 | KPTG-IntCorr-001710 | NA | Trade Partner | EATON L2 SCRIPTS | 0 | 8 | 0 | NA | APPROVED | 2026-07-14 | WF-001160 | NA | 2026-07-17 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-004177 | Open | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-14 | KPTG-IntCorr-001711 | NA | Trade Partner | EATON LV FD | 0 | 1 | 0 | KPTG-IntCorr-001725 | APPROVED | 2026-07-16 | WF-001162 | NA | 2026-07-23 |  | IBRAHIM TO CONFIRM |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-15 | W TITE-TRANSMIT-000008 | NA | Trade Partner | M3 22kV roof waterproofing membrane | 0 | 2 | 0 | NA | APPROVED | 2026-01-15 | WF-003824 |  | 2026-01-28 |  |  |  | 2026-02-02 | KPTG-TRANSMIT-012342 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-15 | ADP-TRANSMIT-000120 | NA | Trade Partner | ADP MEL4680 - Updated HYD & ELC Reg 126 | 0 | 2 | 0 | NA | APPROVED | [5 empty] | For information and to update the document register. |  | 2026-07-15 | KPTG-TRANSMIT-001132 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-15 | Auspan-TRANSMIT-000507 | NA | Trade Partner | Precast shop drawings for construction. Levels 2, 3, 4 in zones 4, 5 | 15 | 0 | 0 | KPTG-IntCorr-000981 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise- KPTG-IntCorr-000981 10 already superseded. 5 are to be resubmitted -DRAFT-010666 |  | 2026-07-28 | DRAFT-010666 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-15 | NXT-TRANSMIT-000436 | NA | Client | Siemens Tx Kiosks | 1 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 406 | 2026-07-23 |  |  | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-000643 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-15 | Auspan-TRANSMIT-000508 | NA | Trade Partner | Precast shop drawings for construction. Level 2 | 2 | 0 | 0 | KPTG-IntCorr-000982 | APPROVED | [5 empty] | IFC - Waiting for Kim advise - KPTG-IntCorr-000982 KPTG-IntCorr-001006 - Same revision issued via TN#509 |  | 2026-07-17 | KPTG-IntCorr-001006 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-15 | ELLISAIR-TRANSMIT-000122 | NA | Trade Partner | Updated Stage 9 Ground Floor Zone 3 and 4 Builders Works drawings - Rev.1 re-issued for Approval. | 2 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 1425 | 2026-07-22 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-006044 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-15 | P & R-TRANSMIT-000097 | NA | Trade Partner | Stage 2 - Fan for IFA Amended | 0 | 1 | 0 | NA | APPROVED | 2026-07-15 | WF-001050 | NA | 2026-07-23 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-15 | SKS Tech-TRANSMIT-000196 | NA | Trade Partner | Updated IFC Labels | 1 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 3863 | 2026-07-24 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-15 | crossfir-TRANSMIT-000002 | NA | Trade Partner | Wet Fire Block Plan & Dry Fire drawings, IFA | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Mixed discipline submisison. |  | 2026-07-15 | KPTG-SADV-000919 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-15 | Nilsen3-TRANSMIT-000233 | NA | Trade Partner | Sample 0042 HAC Push Buttons re-submissions | 0 | 1 | 0 | NA | APPROVED | 2026-07-15 | WF-006379 | NA | 2026-08-05 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-15 | SMEPS-TRANSMIT-000235 | NA | Trade Partner | Fwd: NEL-CNT-SME-2990-ELC-SAM-0077,0078,0079,0080,0081,0082,0083 | 0 | 7 | 0 | NA | REJECTED | [5 empty] | Document revision inside the document and in Aconex seem different |  | 2026-07-15 | KPTG-TRANSMIT-001448 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-15 | DRLL-TRANSMIT-000061 | NA | Trade Partner | Battery Rooms - Volume Damper Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-01-15 | WF-000870 | NA | 2026-01-22 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-15 | D&E-TRANSMIT-000920 | NA | Trade Partner | NXM3S4 - Roof Level - Chiller Room Layouts - Issued For Approval | 2 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 3865 | 2026-07-24 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020134 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-15 | ADP-TRANSMIT-000121 | NA | Trade Partner | ADP MEL4680 - Updated Mech Reg126 | 0 | 1 | 0 | NA | APPROVED | [5 empty] | For information, updating document register only. |  | 2026-07-15 | KPTG-TRANSMIT-001134 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-15 | Nilsen3-TRANSMIT-000070 | NA | Trade Partner | Nilsen samples IFC | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, No review required, updated register & distributed |  | 2026-07-15 | KPTG-TRANSMIT-005623 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-15 | Nilsen3-TRANSMIT-000071 | NA | Trade Partner | Nilsen Sample submissions #10 | 0 | 1 | 0 | NA | APPROVED | 2026-07-15 | WF-001233 | NA | 2026-07-27 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-006757 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-15 | ECBS-TRANSMIT-000066 | NA | Trade Partner | Updated C6 & C12 Drawing IFA (31 drawings) | 31 | 0 | 0 | NA | APPROVED | 2026-07-15 | WF-006381 | NA | 2026-07-20 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-020360 | Closed | 31 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-15 | FULCHL-TRANSMIT-000015 | NA | Trade Partner | NXT-TRANSMIT-001662 Fuelchief Bulk tank QA docs/ Manufacturers Data Report | 0 | 10 | 0 | NA | APPROVED |  | NA | NA |  |  | For Distribution |  | 2026-07-15 | ⁠KPTG-TRANSMIT-019687 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-15 | Jangho-TRANSMIT-000241 | NA | Trade Partner | Structural Calculation For FT07 & 09 System Concept Drawing_Rev 03 | 0 | 1 | 0 | NA | APPROVED | 2026-07-15 | WF-000961 | NA | 2026-07-17 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-003086 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-15 | D&E-TRANSMIT-000921 | NA | Trade Partner | NXM3S4 - Ground - CHW Pipe Layout Zones - Issued For Construction | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-15 | ⁠KPTG-TRANSMIT-019690 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-15 | ASV-TRANSMIT-000077 | NA | Trade Partner | Below Ground PE to Above ground Copper Flanged Transitions | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected : No title and revision number |  | 2026-07-15 | KPTG-SADV-006371 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-15 | PROLMC-TRANSMIT-000045 | NA | Trade Partner | Proline M3 Stage 4 IFC Shop Drawings | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision |  | 2026-07-15 | KPTG-DA-007594 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-11-26 | LANSA-TRANSMIT-000072 | NA | Trade Partner | Levles 11-14 Hyd Penetrations Issued for Approval | 4 | 0 | 0 | NA | APPROVED | 2026-01-15 | WF-000873 | 483 | 2026-01-20 |  |  | 2026-01-14 | 2026-01-14 | KPTG-TRANSMIT-002596 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-15 | Stowe-A-TRANSMIT-000649 | NA | Trade Partner | STOWE - Roof Lightning - As Built | 2 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 4831 | 2026-07-20 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020186 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-09 | HGP-GCOR-000032 | NA | Trade Partner | Thermal Assessment for Review and Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-15 | WF-001185 | NA | 2026-07-15 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-005625 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-15 | RDSBIM-TRANSMIT-000290 | NA | Trade Partner | NXM3S4 ¦ LEVEL-1-C-1-055 CLEANERS FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 3869 | 2026-07-17 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-020761 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-15 | RDSBIM-TRANSMIT-000291 | NA | Trade Partner | NXM3S4 ¦ GROUND FLOOR-C-G-064 UNISEX WC FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 3871 | 2026-07-17 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020139 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-15 | Aurecon-TRANSMIT-000123-FIP | NA | Consultant | Fire Protection Services - LOD300 Issued for Contract | 31 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 408 | 2026-07-23 |  |  | 2026-07-22 | 2026-07-23 | KPTG-TRANSMIT-000674 | Closed | 31 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-15 | Nilsen3-TRANSMIT-000072 | NA | Trade Partner | Nilsen Sample submissions #11 | 0 | 1 | 0 | NA | APPROVED | 2026-07-15 | WF-001234 | NA | 2026-07-27 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-006753 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-15 | KALLIBRE-TRANSMIT-000012 | NA | Trade Partner | TDS - Laundry Troughs | 0 | 3 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected (KPTG-IntCorr-001995) |  | 2026-07-15 | KPTG-IntCorr-001995 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-15 | POTTSENG-TRANSMIT-000058 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - WATER - GROUND - ZONE 1-5 LAYOUTS | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - Latest version IFA status is rejected -DRAFT-009947 |  | 2026-07-15 | DRAFT-009947 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-15 | Entire M-TRANSMIT-000052 | NA | Trade Partner | Waffle Pad Technical Data Rev C | 0 | 1 | 0 | NA | APPROVED | 2026-07-15 | WF - 000546 | NA | 2026-07-21 |  | NA | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-001113 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-15 | Aurecon-TRANSMIT-000123-FID | NA | Consultant | Fire Protection Services - LOD300 Issued for Contract | 23 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 411 | 2026-07-23 |  |  | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-000642 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-19 | WSP ANZ-TRANSMIT-000031 | NA | Consultant | WSP - Building Services Documents - Issue for Building Permit - FUL | 23 | 0 | 0 | NA | APPROVED | 2026-01-15 |  | 178 | 2026-01-23 |  | As per KG advise, this review is not relevant as these drawings will get revised due to major design change |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-15 | PFP PL-TRANSMIT-000018 | NA | Trade Partner | Generator Room Water Mist System Dwg + Calc IFA | 1 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 1419 | 2026-07-22 |  |  | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-005824 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-15 | D&E-TRANSMIT-000922 | NA | Trade Partner | NXM3S4 - Roof & Upper Roof Levels - Chiller Room + Cooling Tower Sections Sheet - Issued For Construction | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-15 | KPTG-TRANSMIT-019692 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-15 | PFP PL-TRANSMIT-000018 | NA | Trade Partner | Generator Room Water Mist System Dwg + Calc IFA | 0 | 1 | 0 | NA | APPROVED | 2026-07-15 | WF-001236 | NA | 2026-07-27 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-006520 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-15 | PenskePS-TRANSMIT-000002 | NA | Trade Partner | GENERATOR DESIGNS AND DRAWINGS - FOR REVIEW AND APPROVAL | 12 | 0 | 0 | NA | REJECTED | [5 empty] | There is too much Quality issues with the document in almost all aspects of Document QA errors. |  | 2026-07-15 | KPTG-SADV-000909 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-15 | KALLIBRE-TRANSMIT-000013 | NA | Trade Partner | Laundry Trough Tech Data | 0 | 2 | 0 | NA | APPROVED | 2026-07-15 | WF - 001082 | NA | 2026-07-13 |  | NA | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-003213 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-15 | Entire M-TRANSMIT-000086 | NA | Trade Partner | External Sensors and Pressure Pickup | 1 | 0 | 0 | NA | APPROVED | 2026-07-15 | WF-000395 | NA | 2026-07-20 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001111 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-15 | EAEGROUP-TRANSMIT-000005 | NA | Trade Partner | Approval Request – 160 A and 250 A TOB Shop Drawings | 2 | 0 | 0 | NA | REJECTED | [5 empty] | documents appear to be missing the required document details within the drawing. |  | 2026-07-15 | KPTG-SADV-000910 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-15 | PROLMC-TRANSMIT-000046 | NA | Trade Partner | Proline M3 Stage 4 IFC Shop Drawings | 9 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 3873 | 2026-07-24 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-15 | ZIA-TRANSMIT-000103 | NA | Trade Partner | Re: M3S4 Network Topology (FOA-3) | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect status |  | 2026-07-15 | KPTG-TRANSMIT-019693 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-15 | PFP PL-TRANSMIT-000019 | NA | Trade Partner | Stage 9 ground and level 2 IFC | 2 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 1421 | 2026-07-22 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-006052 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-15 | vdmcons-TRANSMIT-000015 | NA | Trade Partner | ME25 1144: D10 - M3 Stage 3 GIS Building - M3 Stage 3 Switch Room - Shop Drawings & 3D IFC Model - IFF - 2025-12-19 | 203 | 0 | 0 | NA | APPROVED | 2026-01-15 | WF-003827 / WF-003888 PART 1 & WF-003889 PART 2 |  | 2026-01-28 |  | As instructed by Max H, three drawings from transmittal VDMCONS-TRANSMIT-000015 have been placed in workflow review. The remaining drawings are registered but not placed in the workflow review.-KPTG-TRANSMIT-011466 The drawings have been submitted for review as required by Max H on 20/01/2026. |  | 2026-01-30 | KPTG-TRANSMIT-012226 | Closed | 203 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-15 | Stowe-A-TRANSMIT-000650 | NA | Trade Partner | STOWE - Roof house containment dwgs | 2 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 4386 | 2026-07-24 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-15 | D&E-TRANSMIT-000923 | NA | Trade Partner | Fans - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For Distribution |  | 2026-07-15 | ⁠KPTG-TRANSMIT-019694 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-15 | Stowe-A-TRANSMIT-000651 | NA | Trade Partner | STOWE - Sectional Detail - IFC | 2 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 4388 | 2026-07-24 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-020351 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-15 | ZIA-TRANSMIT-000125 | NA | Trade Partner | Re: M3S4 Network Topology (FOA-3) | 3 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 3875 | 2026-07-24 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020135 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-15 | POTTSENG-TRANSMIT-000059 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONE 1,3,4 LAYOUTS | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected- Latest version IFA was rejected, now submitted for IFC - DRAFT-009971 |  | 2026-07-15 | DRAFT-009971 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-15 | SKS Tech-TRANSMIT-000197 | NA | Trade Partner | Instrumentation Cables Overall Screened - Multi-Pair Tech data submital | 0 | 1 | 0 | NA | APPROVED | 2026-07-15 | WF-006390 | NA | 2026-08-06 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-15 | Auscool-TRANSMIT-000063 | NA | Trade Partner | Fire Spray Alternative | 0 | 1 | 0 | NA | APPROVED | 2026-07-22 | WF-000736 | NA | 2026-07-29 |  | WF-000714 is terminated and new review Initiated on 22/07/26. | 2026-07-22 |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-15 | SMEPS-TRANSMIT-000034 | NA | Trade Partner | TechData: Bulk Electrical Upload | 0 | 16 | 0 | NA | REJECTED | [5 empty] | Issues with Revisions, Mixed status, minor title mismatch |  | 2026-07-15 | KPTG-SADV-000917 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-15 | Stowe-A-TRANSMIT-000652 | NA | Trade Partner | Lower Ground House Containment As Built | 2 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 4390 | 2026-07-24 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020182 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-15 | ARCH-TRANSMIT-000055 | NA | Consultant | UNISEX WC for BP | 1 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 352 | 2026-07-20 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-001143 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-15 | Auspan-TRANSMIT-000044 | NA | Trade Partner | Precast shop drawings for construction. | 28 | 0 | 0 | NA | APPROVED | 2026-01-15 | WF-000128 | 251 | 2026-01-20 |  |  |  | 2026-01-22 | KPTG-TRANSMIT-000458 | Closed | 28 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-15 | CRSol-TRANSMIT-000016 | NA | Trade Partner | Re: CRS - Tech Data Submission NextDC M2 S9_11 | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected : Revision updated incorrect |  | 2026-07-15 | KPTG-SADV-006380 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-15 | WDes-TRANSMIT-000057 | NA | Consultant | Civil - Public Domain - Issued for Approval - | 14 | 0 | 0 | KPTG-TRANSMIT-003144 | APPROVED | [5 empty] | Awaiting DWFX file(KPTG-TRANSMIT-003144) |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-15 | Ardon-TRANSMIT-000010 | NA | Trade Partner | Balance of Priority 1 Shop Drawings | 31 | 0 | 0 | NA | APPROVED | 2026-07-15 | WF-001239 | NA | 2026-07-20 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-006435 | Closed | 31 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-15 | VERTIV-TRANSMIT-000050 | NA | Trade Partner | Next DC - GE1 - CRAC Documentation | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Difference in title, revision sequence issue. |  | 2026-07-15 | KPTG-SADV-000920 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-15 | Aurecon-TRANSMIT-000124-MEC | NA | Consultant | Mechanical Services - LOD300 Issued for Contract | 40 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 416 | 2026-07-23 |  |  | 2026-07-27 | 2026-07-28 | KPTG-TRANSMIT-000735 | Closed | 40 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-15 | Aurecon-TRANSMIT-000124-SCH | NA | Consultant | Mechanical Services - LOD300 Issued for Contract | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated on Forma |  | 2026-07-15 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-15 | Caruso-TRANSMIT-000003 | NA | Trade Partner | Bulk Grout - Blockwork Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-07-15 | WF-006392 | NA | 2026-07-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-15 | Nilsen3-TRANSMIT-000073 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 1423 | 2026-07-22 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-15 | KPTG-TRANSMIT-000560 | NA | Trade Partner | Precast Panel Concrete Mix Design | 0 | 1 | 0 | NA | APPROVED | 2026-07-15 | NA | 414 | 2026-07-22 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-15 | ZIA-TRANSMIT-000126 | NA | Trade Partner | M3S4 Ground Floor & Level 1 Strobe light and OS location (FOA-1) | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Revision of the document has already been received . |  | 2026-07-15 | KPTG-DA-007600 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-01-15 | RBG-TRANSMIT-000049 | NA | Consultant | Updated Structural Drawings for Precast (GF-Roof) - Revised IFC Issue | 4 | 0 | 0 | NA | APPROVED | 2026-01-15 | WF-000121 | 204 | 2026-01-19 |  | Review terminated as drawings updated. |  | 2026-01-21 | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-15 | WilsonPD-TRANSMIT-000211 |  | Trade Partner | Cleaners Sink IFA | 0 | 1 | 0 | DRAFT-010911 | APPROVED | [5 empty] | WilsonPD-TRANSMIT-000211 has been superseded by WilsonPD-TRANSMIT-000212. |  | 2026-07-17 | KPTG-TRANSMIT-001466 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-15 | Stowe-A-TRANSMIT-000653 | NA | Trade Partner | STOWE - As Built - | 6 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 4392 | 2026-07-24 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-020082 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-15 | TTW-TRANSMIT-000197 | NA | Consultant | M3 Stage 2 Civil Drawings | 8 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 4384 | 2026-07-24 |  | workflow terminated, as instructed by charlie. | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-020257 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-15 | INTRFRM-TRANSMIT-000103 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 23) | 0 | 1 | 0 | NA | APPROVED | 2026-07-15 | WF-000320 | NA | 2026-07-24 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-001157 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-15 | ASV-TRANSMIT-000078 | NA | Trade Partner | PE to Copper PE Transition | 0 | 1 | 0 | NA | APPROVED | 2026-07-15 | WF-001241 | NA | 2026-07-24 |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-006261 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-15 | NXT-TRANSMIT-001658 | NA | Client | Fwd: M3 Stg 2 - L1 check reports | 0 | 18 | 0 | NA | APPROVED | [5 empty] | ONLY FOR DISTRIBUTION |  | 2026-07-15 | KPTG-TRANSMIT-019700 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-07-15 | DI-TRANSMIT-000160 | NA | Trade Partner | HFF 6m Gate 428 | 1 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 428 | 2026-07-19 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-15 | CRSol-TRANSMIT-000017 | NA | Trade Partner | Re: CRS - Tech Data Submission NextDC M2 S9_11 | 0 | 1 | 0 | NA | APPROVED | 2026-07-15 | WF-001244 | NA | 2026-07-28 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-005906 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-15 | ELLISAIR-TRANSMIT-000123 | NA | Trade Partner | Stage 9 L01 Builderswork drawings issued for Approval. | 5 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 1427 | 2026-07-22 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-006265 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-15 | Baigents-TRANSMIT-000018 | NA | Trade Partner | Cast-in Plate and Loose Plate Shop Drawings Issued for Approval | 2 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 421 | 2026-07-23 |  |  | 2026-07-27 | 2026-07-28 | KPTG-TRANSMIT-000741 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-15 | WilsonPD-TRANSMIT-000139 |  | Trade Partner | KPTG-IntCorr-001267 | 0 | 1 | 0 | NA | APPROVED | [9 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-15 | Baigents-TRANSMIT-000017 | NA | Trade Partner | Block 01 - East and West Lower Precast Panels Revised and Re-Issued for Fabrication | 10 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 419 | 2026-07-23 |  |  | 2026-07-16 | 2026-07-17 | KPTG-TRANSMIT-000582 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-15 | 4DW-TRANSMIT-000067 | NA | Consultant | Structural Documentation: NLB Feature Precast Walls issued with Construction updates. | 4 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 423 | 2026-07-23 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-000778 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-15 | Aurecon-TRANSMIT-000125 | NA | Consultant | Electrical Services - LOD300 Issued for Contract | 83 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 437 | 2026-07-23 |  | Voided |  | 2026-07-21 | NA | Closed | 83 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-15 | Aurecon-TRANSMIT-000125-SCH | NA | Client | Electrical Services - LOD300 Issued for Contract | 0 | 1 | 0 | NA | APPROVED |  | NA |  |  |  | Updated on Forma |  | 2026-07-15 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-15 | 42636706-TRANSMIT-000021 | NA | Trade Partner | EMS Communcations SLD | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004954 - REVISION,DATE,STATUS ARE INCORRECT | 2026-07-15 | 2026-07-15 | KPTG-SADV-004954 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-07-15 | Caruso-TRANSMIT-000004 | NA | Trade Partner | Fwd: Blockwork Tech Data - M3 Stage 3 | 0 | 3 | 0 | KPTG-TRANSMIT-019707 | APPROVED | 2026-07-16 | WF-006403 | NA | 2026-08-08 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-019929 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-15 | Metzone-TRANSMIT-000035 | NA | Trade Partner | Fwd: L10 - Steel Shop Drawings (IFA) | 11 | 0 | 0 | KPTG-IntCorr-001199 | APPROVED | [5 empty] | KPTG-IntCorr-001199 - Requested guidance, but no response received yet. KPTG-IntCorr-001199 - As per direction from ashlin,we ignore the transmittal. | 2026-07-17 | 2026-07-17 | KPTG-IntCorr-001199 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-15 | fjc-TRANSMIT-000165 | NA | Trade Partner | Architecturals - Outsanding EoT Documentation | 10 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 697 | 2026-07-20 |  | KPTG-SADV-004920 - History box, tittle are missing and also the tittle are different inside the document. 7 DRAWINGS REJECTED 10 drawing processed. | 2026-07-16 | 2026-07-16 | KPTG-SADV-004979 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-15 | fjc-TRANSMIT-000165 | NA | Trade Partner | Architecturals - Outsanding EoT Documentation | 0 | 1 | 0 | NA | APPROVED | 2026-07-15 | WF-000837 | NA | 2026-07-22 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-002853 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-15 | RDSBIM-TRANSMIT-000080 | NA | Trade Partner | : GREYSTAR ¦LEVEL 01 CONCRETE PROFILE PLAN ZONE 5 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Review required as advised by DM, Register and distribute. KPTG-TRANSMIT-002776 |  | 2026-07-15 | KPTG-TRANSMIT-002776 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-02 | fjc-TRANSMIT-000116 | NA | Consultant | Kete - MEchanical louver sizes and mid-transoms height (Tower) | 1 | 0 | 0 | NA | APPROVED | 2025-12-02 | NA | 473# | 2025-12-05 |  |  | 2025-12-05 | 2025-12-08 | KPTG-SADV-002397 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-15 | WilsonPD-TRANSMIT-000140 |  | Trade Partner | KPTG-IntCorr-001268 | 0 | 1 | 0 | NA | APPROVED | [7 empty] | 2026-02-13 | KPTG-TRANSMIT-000439 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-15 | Auspan-TRANSMIT-000509 | NA | Trade Partner | All level 2 IFC shop drawings. | 243 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update register and Transmit -KPTG-TRANSMIT-002781 |  | 2026-07-15 | KPTG-TRANSMIT-002781 | Closed | 243 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-15 | Fyfe-TRANSMIT-000018 | NA | Trade Partner | Current Documents | 31 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No updates, transmit to all for register update - KPTG-TRANSMIT-002790 |  | 2026-07-15 | KPTG-TRANSMIT-002790 | Closed | 31 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-15 | RDSBIM-TRANSMIT-000081: | NA | Trade Partner | GREYSTAR GROUND FLOOR PARTITION KEY PLAN ZONE 1-5 | 6 | 0 | 0 | KPTG-IntCorr-000995 | APPROVED | 2026-07-16 | NA | 1500 | 2026-07-21 |  | QC done - all ok - Michael to confirm on review - KPTG-IntCorr-000995 Ok to initiate review KPTG-DA-001605 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-15 | KETE-TRANSMIT-000143 | NA | Trade Partner | Glass sample form GL-02d updated | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-001198 - As per direction from Ashlin, I have not taken any action on this transmittal, as Kate needs to resubmit it because the information in the sample form is incorrect. , | 2026-07-15 | 2026-07-15 | KPTG-IntCorr-001198 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-15 | Auspan-TRANSMIT-000241 | NA | Trade Partner | Re: Precast shop drawings for approval. Zone 4, 5. | 1 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 1490 | 2026-07-22 |  | Review voided as per advice from kim |  | 2026-07-20 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-15 | Auspan-TRANSMIT-000510 | NA | Trade Partner | Re: All level 2 IFC shop drawings. | 4 | 0 | 0 | KPTG-IntCorr-000988 | APPROVED |  | NA | NA |  |  | Kim to advise - KPTG-IntCorr-000988 OK to proceed IFC |  | 2026-07-20 | KPTG-TRANSMIT-002854 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-15 | Auscool-TRANSMIT-000061 | NA | Trade Partner | Seismic Calculations | 0 | 1 | 0 | KPTG-IntCorr-000992 | APPROVED |  | NA | NA |  |  | Kapitol PC - to advise KPTG-IntCorr-000992 add to the Aconex doc register under for information. -KPTG-IntCorr-001052 |  | 2026-07-22 | KPTG-IntCorr-001052 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-15 | Ardon-TRANSMIT-000009 | NA | Trade Partner | Sealant Tech Data | 0 | 2 | 0 | NA | APPROVED | 2026-07-15 | WF-001229 | NA | 2026-07-21 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-005889 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-15 | Year-GCOR-000012 | NA | Trade Partner | DEC Group Tech Data Sheet | 0 | 1 | 0 | NA | APPROVED | 2026-07-15 | WF-001231 | NA | 2026-07-23 |  |  | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-005820 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-15 | Arc Plas-SUBADVICE-000019 | NA | Trade Partner | Prefabricated Cortek System - Mechanical Corridor Wall | 119 | 0 | 0 | NA | APPROVED | 2026-07-15 | WF-001232 | NA | 2026-07-27 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-005858 | Closed | 119 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-15 | WilsonPD-TRANSMIT-000141 |  | Trade Partner | KPTG-IntCorr-001269 | 0 | 0 | 0 | NA | APPROVED | [9 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-15 | LGCE-TRANSMIT-000060 | NA | Trade Partner | : Level 4 light and power | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to drawing reference QA issues - KPTG-SADV-003068 |  | 2026-07-15 | KPTG-SADV-003068 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-15 | LGCE-TRANSMIT-000061 | NA | Trade Partner | level 4 light and power | 2 | 0 | 0 | KPTG-IntCorr-000976 | APPROVED | 2026-07-16 | NA | 654 | 2026-07-23 |  | Kapitol PC to advise - KPTG-IntCorr-000976 | 2026-08-21 | 2026-08-21 | LGCE-TRANSMIT-000061 level 4 light and power -654 2 KPTG-TRANSMIT-001640 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-15 | POTTSENG-TRANSMIT-000033 | NA | Trade Partner | 671C: HYDRAULIC SERVICES - LEVEL 03 - PENETRATION LAYOUT | 1 | 0 | 0 | KPTG-IntCorr-000977 | APPROVED |  | NA | NA |  |  | Kapitol PC to advise - KPTG-IntCorr-000977 No review required. KPTG-IntCorr-000979- Register and distribute: KPTG-TRANSMIT-001362 | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-001362 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-15 | crossfir-TRANSMIT-000026 | NA | Trade Partner | : Wet & Dry Fire - Basement 04, 03, 02 - IFC | 7 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to drawing reference QA issues - KPTG-SADV-003067 |  | 2026-07-15 | KPTG-SADV-003067 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-15 | 4DW-TRANSMIT-000196 | NA | Consultant | Structural Documentation - Crane Penetration update | 1 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 391 | 2026-07-18 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-003106 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-16 | SES AU-TRANSMIT-000082 | NA | Trade Partner | COLO4-CELL1-PROTOTYPE ELEVATIONS & DETAILS | 1 | 0 | 0 | NA | APPROVED | 2026-07-16 | WF-000398 | NA | 2026-07-22 |  | wf-000398 is terminated:KPTG-IntCorr-000681 |  | 2026-07-16 | KPTG-IntCorr-000681 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-16 | RDSBIM-TRANSMIT-000082 | NA | Trade Partner | GREYSTAR ¦ LEVEL 02 CONCRETE PROFILE PLAN ZONE 5 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review needed, Register updated and transmitted - KPTG-TRANSMIT-002792 |  | 2026-07-16 | KPTG-TRANSMIT-002792 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-16 | SES AU-TRANSMIT-000083 | NA | Trade Partner | SECURITY SERVICES DRAWING LIST | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Drawing title is not mentioned:KPTG-IntCorr-000680 |  | 2026-07-16 | KPTG-IntCorr-000680 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-16 | RDSBIM-TRANSMIT-000065 | NA | Trade Partner | Fwd: DISTLV ¦ LEVEL 01 CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 961 | 2026-07-23 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003244 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-16 | Entire M-TRANSMIT-000064 | NA | Trade Partner | Updated Fire Matrix | 0 | 1 | 0 | NA | APPROVED | 2026-07-16 | WF - 000321 | NA | 2026-07-22 |  | NA | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-001714 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-15 | WilsonPD-TRANSMIT-000142 |  | Trade Partner | KPTG-IntCorr-001270 | 0 | 1 | 0 | NA | APPROVED | [9 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-16 | Ardon-TRANSMIT-000012 | NA | Trade Partner | Alternative Seal Option | 0 | 1 | 0 | NA | APPROVED | 2026-07-16 | WF-001246 | NA | 2026-07-27 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-006660 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-16 | RDSBIM-TRANSMIT-000067 | NA | Trade Partner | DISTLV - GROUND FLOOR TO LEVEL 06 LIFT CORE 1 CONCRETE PROFILE PLAN AND SECTIONAL ELEVATION | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Difference in title |  | 2026-07-16 | DRAFT-013911 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-15 | Jordan-TRANSMIT-000130 (Teams message ibrahim) | NA | Trade Partner | Hydraulic Commissioning Scripts - HWCP | 0 | 1 | 0 | NA | APPROVED | 2026-07-15 | WF-001161 | NA | 2026-07-20 |  |  |  | 2026-07-23 | KPTG-TRANSMIT-004129 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-15 | 4Ki-TRANSMIT-000008 | NA | Trade Partner | JNR001-FOYER RECEPTION DESK | 1 | 0 | 0 | NA | REJECTED | [5 empty] | DRAWING NUMBER ERROR INSIDE THE DRAWING |  | 2026-07-15 | KPTG-IntCorr-001734 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-16 | VERTIV-TRANSMIT-000051 | NA | Trade Partner | NEXT DC GE01 _ SHOP DRAWING _ STRUCTURAL PACK (FOA-1) | 12 | 0 | 0 | NA | APPROVED | 2026-07-16 | WF-000322 | NA | 2026-07-29 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-001760 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-16 | SES AU-TRANSMIT-000084 | NA | Trade Partner | SECURITY SERVICES DRAWING LIST | 1 | 0 | 0 | NA | APPROVED | 2026-07-16 | WF-000399 | NA | 2026-07-17 |  | workflow WF-000399 against the Document has been terminated. |  | 2026-07-16 | KPTG-IntCorr-000688 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-16 | SMEPS-TRANSMIT-000035 | NA | Trade Partner | Electrical Shop Drawings | 22 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 355 | 2026-07-22 |  | NA | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001309 | Closed | 22 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-16 | RDSBIM-TRANSMIT-000292 | NA | Trade Partner | NXM3S4 ¦ CORE 8 -CONNECTION DETAIL LAYOUT | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For info |  | 2026-07-16 | KPTG-TRANSMIT-019711 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-16 | D&E-TRANSMIT-000924 | NA | Trade Partner | Fwd: NXM3S4 - Upper Roof Level - CHW & CCW Pipe Layout Zones - Issued For Construction | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-16 | KPTG-TRANSMIT-019714 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-16 | Auspan-TRANSMIT-000513 | NA | Trade Partner | Resubmit shop drawings for approval. Level 2 | 5 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 1495 | 2026-07-23 |  | Already updated and transmitted via- TN 529 |  | 2026-07-24 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-19 | WSP ANZ-TRANSMIT-000031 | NA | Consultant | WSP - Building Services Documents - Issue for Building Permit - CSMS | 15 | 0 | 0 | NA | APPROVED | 2026-01-15 |  | 180 | 2026-01-23 |  | As per KG advise, this review is not relevant as these drawings will get revised due to major design change |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-15 | WAM-TRANSMIT-000826 | NA | Trade Partner | A67 Lift Lobby Drawings | 21 | 0 | 0 | NA | APPROVED | 2026-07-15 | NA | 958 | 2026-07-17 |  |  | 2026-07-27 | 2026-07-28 | KPTG-TRANSMIT-003113 | Closed | 21 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-15 | INGEN3D-TRANSMIT-000196 | NA | Trade Partner | Level 20-22 - Precast Columns - IFA (19-06-2026) | 5 | 0 | 0 | NA | APPROVED | 2026-07-15 | WF-000962 | NA | 2026-07-22 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003257 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-15 | INGEN3D-TRANSMIT-000197 | NA | Trade Partner | Level 12-14 - Precast Columns - IFC (15-07-2026) | 31 | 0 | 0 | NA | APPROVED | 2026-07-15 | WF-000963 | NA | 2026-07-22 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-003135 | Closed | 31 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-15 | INGEN3D-TRANSMIT-000198 | NA | Trade Partner | Level 12-14 - Precast Columns - No Longer in Use | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer in Use - Forwarded to All Parties |  | 2026-07-15 | KPTG-TRANSMIT-002889 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-15 | INGEN3D-TRANSMIT-000199 | NA | Trade Partner | PC0528-3, PC0522-9 & PC0531-6 - IFC (15-07-2026) | 3 | 0 | 0 | NA | APPROVED | 2026-07-15 | WF-000964 | NA | 2026-07-22 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-003321 - | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-16 | Auspan-TRANSMIT-000512 | NA | Trade Partner | Precast shop drawings for construction. Level 3 | 8 | 0 | 0 | KPTG-IntCorr-000998 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise - KPTG-IntCorr-000998 No action required - Superseded via - Auspan-TRANSMIT-000527 |  | 2026-07-28 | Auspan-TRANSMIT-000527 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-15 | INGEN3D-TRANSMIT-000200 | NA | Trade Partner | Level 16-18 - PC0522-11 & PC0539-5 - IFC (15-07-2026) | 3 | 0 | 0 | NA | APPROVED | 2026-07-15 | WF-000965 | NA | 2026-07-22 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-15 | INGEN3D-TRANSMIT-000201 | NA | Trade Partner | Level 17-19 - PC0579-2 - IFC (15-07-2026) | 2 | 0 | 0 | NA | APPROVED | 2026-07-15 | WF-000966 | NA | 2026-07-22 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-003144 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-15 | INGEN3D-TRANSMIT-000202 | NA | Trade Partner | Level 11-13 - PC0464-1, PC0464-2 & PC0467-1 - IFC (15-07-2026) | 4 | 0 | 0 | NA | APPROVED | 2026-07-15 | WF-000967 | NA | 2026-07-22 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-16 | Tradetec-TRANSMIT-000484 | NA | Trade Partner | IFA - Stage 4 - CP20, CP38 | 2 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 3881 | 2026-07-25 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-020954 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-14 | WAM-TRANSMIT-000077 | N/A | Consultant | WAM ARCH - 95% DD A22 3D Facade Views | 4 | 0 | 0 | NA | APPROVED | 2026-01-14 | NA | 198 | 2026-01-16 |  |  | 2026-01-28 | 2026-01-28 | KPTG-TRANSMIT-000320 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-16 | ARCST-TRANSMIT-000341 | NA | Trade Partner | C2 Switchroom Roof & Secondary Steel - Issued for Construction | 193 | 0 | 0 | NA | APPROVED | 2026-07-16 | WF-006397 | NA | 2026-07-24 |  | As instructed by lola in KPTG-RTRFI-005252 |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-16 | ZIA-TRANSMIT-000127 | NA | Trade Partner | Fwd: M3S4 Ground Floor & Level 1 Strobe light and OS location (FOA-1) | 6 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 3883 | 2026-07-25 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-020365 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-16 | ARCST-TRANSMIT-000340 | NA | Trade Partner | Chemical Store Base & Roof Framing - Issued for Construction | 12 | 0 | 0 | NA | APPROVED | 2026-07-16 | WF-006399 | NA | 2026-07-24 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-16 | SKS Tech-TRANSMIT-000198 | NA | Trade Partner | Sections and Isometrics Data Halls | 7 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 3886 | 2026-07-25 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-16 | ARCST-TRANSMIT-000334 | NA | Trade Partner | C3 Switchroom Roof & Secondary Steel - Issued for Construction | 127 | 0 | 0 | NA | APPROVED | 2026-07-16 | WF-006398 | NA | 2026-07-24 |  | As instructed by Lola KPTG-IntCorr-016283 |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-16 | HGP-TRANSMIT-000066 | NA | Trade Partner | Transmittal-Louvre Shop Drawings Rev03 | 16 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Revision needs to be changed |  | 2026-07-16 | KPTG-SADV-006002 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-16 | HGP-TRANSMIT-000067 | NA | Trade Partner | Transmittal-Louvre Package shop drawing Rev03 | 17 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Drawing is duplicatesKPTG-TRANSMIT-001462 |  | 2026-07-16 | KPTG-TRANSMIT-001462 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-16 | Stowe-A-TRANSMIT-000654 | NA | Trade Partner | Re: STOWE - Busduct - IFC | 5 | 0 | 0 | NA | REJECTED | [5 empty] | attached document seems two types of issued status in Aconex |  | 2026-07-16 | KPTG-SADV-006677 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-16 | CRSol-TRANSMIT-000018 | NA | Trade Partner | CRS - Structural Ceiling -Stage 9 - DH21 &DH24 Shop Drawing IFA | 12 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 1440 | 2026-07-23 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-005850 | Closed | 12 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-16 | DLTS-TRANSMIT-000056 | NA | Trade Partner | S11-Cooling tower marking plans-Re-IFA | 4 | 0 | 0 | NA | APPROVED | 2026-07-16 | WF-001251 | NA | 2026-07-27 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-005715 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-14 | TTW-TRANSMIT-000070 | N/A | Consultant | Updated FP1.4 PBDB | 1 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-000097 | NA | 2026-01-16 |  |  | 2026-01-21 | 2026-04-19 | KPTG-TRANSMIT-001235 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-16 | PFP PL-TRANSMIT-000020 | NA | Trade Partner | Stage 9 Level 1 IFC | 1 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 1442 | 2026-07-23 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-006056 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-16 | KALLIBRE-TRANSMIT-000014 | NA | Trade Partner | Mailbox Shroud - Ross St | 1 | 0 | 0 | NA | APPROVED | 2026-07-16 | WF - 001083 | NA | 2026-07-22 |  | NA | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-003160 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-16 | JCBa-TRANSMIT-000154 | NA | Consultant | Updated Architectural Documentation - SSPs, Sections, Detail Plans & RCPs, Detail Elevations, Wet Area Details, Apartment Type Plans & RCPs, Junction Details & Joinery Details. | 81 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 1498 | 2026-07-20 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-003053 | Closed | 81 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-16 | G&CHyd-TRANSMIT-000011 | NA | Trade Partner | HYD Tech Data | 0 | 9 | 0 | NA | APPROVED | 2026-07-16 | WF-000969 | NA | 2026-07-21 |  | Doc 15 - revised | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-003507 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-16 | JCBa-TRANSMIT-000154 | NA | Consultant | Updated Architectural Documentation | 0 | 1 | 0 | NA | APPROVED | 2026-07-16 | WF-000718 | NA | 2026-07-23 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-16 | JCBa-TRANSMIT-000154 | NA | Consultant | Updated Architectural Documentation | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to drawing appears to be incomplete & status difference - DRAFT-010037 |  | 2026-07-16 | DRAFT-010037 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-16 | SMEPS-TRANSMIT-000027 | NA | Trade Partner | Gym Lighting Tech data | 0 | 6 | 0 | NA | REJECTED | [5 empty] | Rejected (KPTG-TRANSMIT-00314) |  | 2026-07-16 | KPTG-TRANSMIT-003146 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-16 | Auspan-TRANSMIT-000511 | NA | Trade Partner | Precast shop drawings for construction. Level 2. | 7 | 0 | 0 | KPTG-IntCorr-001002 | APPROVED | [5 empty] | IFC - Waiting for Kim advise - KPTG-IntCorr-001002 |  | 2026-07-17 | KPTG-TRANSMIT-002843 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-16 | PFP PL-TRANSMIT-000097 | NA | Trade Partner | Updated Stage 2 Tactical Fire Plans / Block Plans | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document number, title, revision, revision history, title block etc. |  | 2026-07-16 | KPTG-SADV-006675 | Open | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-15 | PCForm-TRANSMIT-000036 | NA | Trade Partner | Stage 9 - Stair 1 & Lift Core - Jumpform Wall Elevation - Issued for approval | 2 | 0 | 0 | NA | APPROVED | 2026-01-15 | WF-000134 |  | 2026-01-23 |  |  | 2026-02-02 | 2026-02-02 | KPTG-TRANSMIT-000674 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-16 | Stowe-A-TRANSMIT-000655 | NA | Trade Partner | Re: STOWE - IFC documents | 3 | 0 | 0 | NA | REJECTED | [5 empty] | We also noticed that Revision A is missing from the revision history in all the documents included in this transmittal. |  | 2026-07-16 | KPTG-SADV-006688 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-16 | crossfir-TRANSMIT-000003 | NA | Trade Partner | Wet Fire - Block Plan | 1 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 357 | 2026-07-22 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001413 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-16 | MAYFLD-TRANSMIT-000467 | NA | Trade Partner | Revised Installation, operation & Maintenance Manual (IOM) | 0 | 1 | 0 | NA | APPROVED | 2026-07-16 | WF-006404 | NA | 2026-07-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-16 | PARR-TRANSMIT-000207 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - BFS CACO & DB - IFC | 2 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 3890 | 2026-07-25 |  | as instructed by Damian, WF terminated |  | 2026-07-20 | NA | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-16 | WilsonPD-TRANSMIT-000212 | SPARK-CRFI-KPG-000132 | Trade Partner | Cleaners Sink IFA | 0 | 1 | 0 | NA | APPROVED | 2026-07-16 | WF-000558 | NA | 2026-07-23 |  | KPTG-IntCorr-003571-CRFI No has not yet given. | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-001495 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-09 | PARR-TRANSMIT-000208 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - BF DRAWINGS - IFC | 27 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect status -revision |  | 2026-07-16 | KPTG-DA-007618 | Closed | 27 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-16 | Ardon-TRANSMIT-000061 | NA | Trade Partner | Re: Remaining Door Frames | 3 | 0 | 0 | NA | REJECTED | [5 empty] | drawings appear to be missing the required document details within the drawing |  | 2026-07-16 | KPTG-TRANSMIT-019729 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-07-16 | KPTG-WTRAN-012091 | NA | Trade Partner | STORMWATER DRAINAGE | 0 | 3 | 0 | NA | APPROVED | 2026-07-16 | WF-006406 | NA | 2026-07-31 |  | Note: The workflow (WF) has been generated as per the instruction of Asha Newstead. |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-16 | SMEPS-TRANSMIT-000348 | NA | Trade Partner | Transmittal: Electrical Services Containment Drawings - For Approval | 2 | 0 | 0 | NA | APPROVED | 2026-07-16 | WF-006401 | NA | 2026-07-24 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-020324 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-16 | crossfir-TRANSMIT-000004 | NA | Trade Partner | Dry Fire - Issue for Approval | 3 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 359 | 2026-07-22 |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-001427 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-15 | Auspan-TRANSMIT-000037 | NA | Trade Partner | Precast shop drawings for construction. Ground floor columns | 23 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings need to be revised KPTG-SADV-000631 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-16 | SMEPS-TRANSMIT-000349 | NA | Trade Partner | SME - IFA Sample submissions | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Incorrect status |  | 2026-07-16 | KPTG-DA-007617 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-16 | Arco-TRANSMIT-000007 |  | Trade Partner | Submission of shopdrawings - Arco roller shutters and fire shutters | 6 | 0 | 0 | NA | REJECTED | [5 empty] | it is noticed that same revision of all documents has already been transmitted via Arco-TRANSMIT-000006 and reviewed as well.KPTG-TRANSMIT-001463 |  | 2026-07-16 | KPTG-TRANSMIT-001463 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-16 | MAYFLD-TRANSMIT-000468 | NA | Trade Partner | Fwd: 100222-000610: M3 Stage 2 EB Building: Cable Schedule Mechanical Services - As Built | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | FOR DISTRIBUTION ONLY |  | 2026-07-16 | KPTG-TRANSMIT-019731 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-16 | VERTIV-TRANSMIT-000052 | NA | Trade Partner | NextDC - GE1 - CRAC Documentation | 0 | 5 | 0 | NA | APPROVED | 2026-07-16 | WF-000328 | NA | 2026-07-29 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001638 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-16 | JCBa-TRANSMIT-000274 | NA | Consultant | - Building Permit Issue | 4 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 601 | 2026-07-21 |  | NA | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-003219 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-16 | Civilex-TRANSMIT-000296 | NA | Trade Partner | Re: Stage 1 Swale Restoration shop drawing | 1 | 0 | 0 | NA | REJECTED | [5 empty] | document seems document numbering mistake on the submission |  | 2026-07-16 | KPTG-SADV-006698 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-16 | SIL-WTRAN-000001 | NA | Trade Partner | MV Switchboard Schematics - Request for Approval | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with mail type, document number, revision etc. |  | 2026-07-16 | KPTG-SADV-000935 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-16 | ARCST-TRANSMIT-000336<br> | NA | Trade Partner | Re: C1 Switchroom Upper Gantry - Issued for Construction | 160 | 0 | 0 | NA | APPROVED | 2026-07-16 | WF-006408) | NA | 2026-07-24 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-16 | Diadem-TRANSMIT-000013 | NA | Consultant | Updated Wayfinding package | 99 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 1444 | 2026-07-23 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-006547 | Closed | 99 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-16 | Stowe-A-TRANSMIT-000656 | NA | Trade Partner | STOWE - BUSDUCT - IFC | 6 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 4394 | 2026-07-24 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-15 | RDSBIM-TRANSMIT-000012 | N/A | Trade Partner | GROUND FLOOR CONCRETE PROFILE PLAN AND SECTIONS ALONG WITH COMPLETENESS MEASURE | 7 | 0 | 0 | NA | APPROVED | 2026-01-15 | NA | 202 | 2026-01-21 |  |  | 2026-02-12 | 2026-02-12 | KPTG-TRANSMIT-000433 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-16 | SIL-WTRAN-000002 | NA | Trade Partner | MV Switchboard Enclosure - Request for Approval | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document number, revision, transmittal type etc. |  | 2026-07-16 | KPTG-SADV-000936 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-16 | Stowe-A-TRANSMIT-000657 | NA | Trade Partner | Re: STOWE - ASBUILTS - DH 1 | 4 | 0 | 0 | NA | REJECTED | [5 empty] | documents the same revision is already completed REVISION |  | 2026-07-16 | KPTG-TRANSMIT-019742 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-16 | SPECAUTO-TRANSMIT-000006 | NA | Trade Partner | CSMS Outstation Hardware Procurement Approval - Moxa Modbus Gateway | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Title change, revision date not changed. |  | 2026-07-16 | KPTG-SADV-000934 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-16 | Stowe-A-TRANSMIT-000658 | NA | Trade Partner | STOWE - IFC | 1 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 4396 | 2026-07-24 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-16 | INTRFRM-TRANSMIT-000104 | NA | Trade Partner | Geelong Edge - Civil Tech Data (Submission 6) | 0 | 2 | 0 | NA | APPROVED | 2026-07-16 | WF-000329 | NA | 2026-07-27 |  |  | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-001268 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-16 | Nilsen3-TRANSMIT-000064 | NA | Trade Partner | STAGE 9- DATA HALL 21 FWU LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 1446 | 2026-07-23 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-006883 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-16 | SMEPS-TRANSMIT-000052 | NA | Trade Partner | STAGE 11 - Telecoms North Layout | 1 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 1448 | 2026-07-23 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-006361 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-16 | fjc-TRANSMIT-000167 | NA | Consultant | Drawing Updates | 6 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 695 | 2026-07-21 |  |  | 2026-07-16 | 2026-07-16 | KPTG-SADV-004977 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-16 | HGP-TRANSMIT-000069 |  | Trade Partner | Transmittal-Curtain wall shop drawing IFC RevE | 101 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Same revision are already transmitted & reviewed:KPTG-TRANSMIT-001464 |  | 2026-07-16 | KPTG-TRANSMIT-001464 | Closed | 101 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-16 | HGP-TRANSMIT-000068 |  | Trade Partner | TRANSMITTAL-LOUVRE PACKAGE SHOP DRAWING IFA REV03 | 16 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 353 | 2026-07-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-15 | Civilex-TRANSMIT-000016 | N/A | Trade Partner | Micropile Design | 0 | 1 | 0 | NA | APPROVED | 2026-01-15 | WF-000101 | NA | 2026-01-17 |  |  | 2026-01-22 | 2026-01-23 | KPTG-TRANSMIT-000309 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-16 | D&E-TRANSMIT-000291 | SPARK-CRFI-KPG-00754 | Trade Partner | Mechanical Plinths Chemical Anchor | 0 | 1 | 0 | NA | APPROVED | 2026-07-16 | WF-000560 | NA | 2026-07-23 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-16 | SMEPS-TRANSMIT-000236 | SPARK-CRFI-KPG-000181 | Trade Partner | NEL-CNT-SME-2990-ELC-SAM-0077,0078,0079,0080,0081,0082,0083 | 0 | 7 | 0 | NA | APPROVED | 2026-07-16 | WF-000559 | NA | 2026-07-23 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-16 | Aurecon-TRANSMIT-000118-DES | NA | Consultant | Telecommunication Services - Issued for Information | 34 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 430 | 2026-07-22 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-001053 | Closed | 34 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-16 | Aurecon-TRANSMIT-000119-DES | NA | Consultant | Fuel Services - LOD300 Issued for Contract | 23 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 431 | 2026-07-22 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-001052 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-16 | Aurecon-TRANSMIT-000122-DSE | NA | Consultant | CSMS Services - LOD300 Issued for Contract | 13 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 432 | 2026-07-22 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-001051 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-16 | Aurecon-TRANSMIT-000123-FID-DES | NA | Consultant | Fire Protection Services - LOD300 Issued for Contract | 23 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 433 | 2026-07-22 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001026 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-16 | Aurecon-TRANSMIT-000123-FIP-DES | NA | Consultant | Fire Protection Services - LOD300 Issued for Contract | 31 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 434 | 2026-07-22 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-001050 | Closed | 31 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-16 | Aurecon-TRANSMIT-000124-MEC-DES | NA | Consultant | Mechanical Services - LOD300 Issued for Contract | 40 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 435 | 2026-07-22 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-001071 | Closed | 40 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-16 | crossfir-TRANSMIT-000027 | NA | Trade Partner | Dry Fire - B04,03, 02 - IFC | 3 | 0 | 0 | KPTG-IntCorr-000991 | REJECTED |  | NA | NA |  |  | Tayla to confirm review team. KPTG-IntCorr-000991 Don't put them into a review as they have not captured all comments and will need to go back and fix. |  | 2026-07-17 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-16 | NXT-PA-000343 | NA | Client | M3 Stage 6 - Schindler Shop Drawings - Goods Lifts | 4 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 440 | 2026-07-23 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-000742 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-02 | RDSBIM-TRANSMIT-000119 | NA | Trade Partner | LINDRUM ¦ BASEMENT LEVEL CONCRETE PROFILE PLAN AND SECTIONS | 1 | 0 | 0 | NA | APPROVED | 2025-12-02 | NA | 474# | 2025-12-05 |  |  | 2025-12-03 | 2025-12-03 | KPTG-SADV-002335 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-15 | Civilex-TRANSMIT-000017 | N/A | Trade Partner | Humes Stormtrap Detention Tank | 0 | 1 | 0 | NA | APPROVED | 2026-01-15 | WF-000099 | NA | 2026-01-17 |  |  | 2026-01-20 | 2026-01-20 | KPTG-TRANSMIT-000298 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-16 | crossfir-TRANSMIT-000026 | NA | Trade Partner | crossfir-TRANSMIT-000026: Wet Fire - Basement 04, 03, 02 - IFC | 4 | 0 | 0 | KPTG-IntCorr-000992 | REJECTED |  | NA | NA |  |  | Tayla to confirm review team. KPTG-IntCorr-000992. Dont put them into a review as they have not captured all comments and will need to go back and fix. |  | 2026-07-17 | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-16 | B Smart-TRANSMIT-000093 | NA | Trade Partner | : GF general arrangement Plan update | 1 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 656 | 2026-07-21 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-001460 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-16 | Baigents-TRANSMIT-000016 | NA | Trade Partner | Block 01 Level 01 Slimdek support steel IFA | 58 | 0 | 0 | KPTG-IntCorr-000312 | APPROVED |  | NA | NA |  |  | Update register only |  | 2026-07-20 | NA | Closed | 58 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-16 | PTA-TRANSMIT-000024 | NA | Consultant | Fire Compartment Plan - LG, G & Level 1_Issue for Coordination | 1 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 443 | 2026-07-23 |  |  | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-000640 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-16 | Marr Con-TRANSMIT-000003 | NA | Trade Partner | TC7 IFC cast in frame | 1 | 0 | 0 | KPTG-IntCorr-000313 | APPROVED | [5 empty] | No Action required |  | 2026-08-10 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-16 | PTA-TRANSMIT-000026 | NA | Consultant | Fence Line and Retaining Wall Update | 1 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 445 | 2026-07-23 |  | PTA-TRANSMIT-000025 superseded | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-000900 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-16 | EUKAI-TRANSMIT-000017 | NA | Consultant | Preliminary Signage & Linemarking Drawings | 7 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-07-16 | Awaiting approval | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-16 | Aurecon-TRANSMIT-000126 | NA | Consultant | TELECOMMUNICATIONS RETURN SCHEDULES | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated on Forma |  | 2026-07-16 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-16 | Aurecon-TRANSMIT-000125-DSE | NA | Consultant | Electrical Services - LOD300 Issued for Contract | 83 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 438 | 2026-07-22 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-16 | SC-TRANSMIT-000011 |  | Trade Partner | Secondary Steel IFC Drawings | 69 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Drawing Status are incorrect,requested to retranmit:KPTG-TRANSMIT-001465 |  | 2026-07-16 | KPTG-TRANSMIT-001465 | Closed | 69 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-15 | Civilex-TRANSMIT-000018 | N/A | Trade Partner | HumeFilter UPT | 0 | 1 | 0 | NA | APPROVED | 2026-01-15 | WF-000100 | NA | 2026-01-17 |  |  | 2026-01-20 | 2026-01-20 | KPTG-TRANSMIT-000296 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-16 | ARCH-TRANSMIT-000165 | NA | Trade Partner | MLC - SPR - Stage 2 capping beam update | 2 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 393 | 2026-07-21 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-003109 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-16 | Highbu-TRANSMIT-000156 | NA | Trade Partner | ISC - HPS access panels | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected:Attributes in the title bloc are missed:KPTG-SADV-005373 |  | 2026-07-16 | KPTG-SADV-005373 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-16 | Auscool-TRANSMIT-000064: | NA | Trade Partner | Re: Missed Precast Penetrations – Mark-up for Review - IFA | 21 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 1508 | 2026-07-23 |  | KPTG-TRANSMIT-003285 6 are terminated already | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003285 | Closed | 21 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-16 | Auscool-TRANSMIT-000064 | NA | Trade Partner | : Re: Missed Precast Penetrations – Mark-up for Review - IFC | 5 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 1506 | 2026-07-23 |  | KPTG-TRANSMIT-003282 2 are terminated already | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003282 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-16 | IJF-TRANSMIT-000003 | NA | Trade Partner | Joinery - Prototype Drawings | 29 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to combined PDF files. -KPTG-SADV-003524 |  | 2026-07-16 | KPTG-SADV-003524 | Closed | 29 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-16 | Auspan-TRANSMIT-000514 | NA | Trade Partner | : Precast shop drawing 3P4029 for approval | 3 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 1502 | 2026-07-23 |  |  | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-002950 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-16 | Auspan-TRANSMIT-000515: | NA | Trade Partner | Precast panel 2P4057 for approval. | 3 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 1504 | 2026-07-23 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-002872 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-16 | Auspan-TRANSMIT-000516 | NA | Trade Partner | : Re: URGENT: OUTSTANDING L2 PANELS | 5 | 0 | 0 | KPTG-IntCorr-001004 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise .KPTG-IntCorr-001004 IFC update register and transmit KPTG-TRANSMIT-002827 |  | 2026-07-17 | KPTG-TRANSMIT-002827 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-16 | KPTG-IntCorr-001495 | NA | Trade Partner | Nilsen Switchboard Drawings | 40 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 1435 | 2026-07-23 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-16 | KPTG-IntCorr-001515 | NA | Trade Partner | SCADA Documents | 39 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 1410 | 2026-07-21 |  |  | 2026-07-29 | 2026-07-29 | KPTG-DA-004015 | Closed | 39 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-15 | PCForm-TRANSMIT-000035 | N/A | Trade Partner | Jumpform Concrete Envelope Drawings - Raft 1, 2 & 3 | 18 | 0 | 0 | Clarification required - KPTG-IntCorr-000205 | APPROVED |  | NA | NA |  |  | Revised Drawings issued with different dwg no. |  | 2026-02-03 | KPTG-IntCorr-000288 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-16 | Fredon T-TRANSMIT-000026 | NA | Trade Partner | AV Tech Data - LCD Enclosure BBall Courts | 0 | 1 | 0 | NA | APPROVED | 2026-07-16 | WF-001052 | NA | 2026-07-24 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-16 | KPTG-IntCorr-001672 | NA | Trade Partner | SCADA IFC Drawings | 30 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 1438 | 2026-07-23 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-16 | Fredon T-TRANSMIT-000027 | NA | Trade Partner | AV Tech Data - LCD Displays | 0 | 1 | 0 | NA | APPROVED | 2026-07-16 | WF-001053 | NA | 2026-07-24 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-16 | RDSBIM-TRANSMIT-000223 | NA | Trade Partner | LINDRUM ¦ LEVEL 11 TO LEVEL 27 & ROOF COREWALL CONCRETE PROFILE ELEVATION | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001202 - As per direction from Ashlin we only update the register and issue to everyone. | 2026-07-16 | 2026-07-16 | KPTG-IntCorr-001202 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-16 | Auscool-TRANSMIT-000107 | NA | Trade Partner | Commissioning Plan For Approval - Mechanical & BMS | 0 | 2 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004959 - Document no and document type is incorrect | 2026-07-16 | 2026-07-16 | KPTG-SADV-004959 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-16 | 42636706-TRANSMIT-000022 | NA | Trade Partner | Re: EMS Communcations SLD | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004960 Document no incorrect | 2026-07-16 | 2026-07-16 | KPTG-SADV-004960 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-16 | Jangho-TRANSMIT-000244 | NA | Trade Partner | Tower A&B Level 6~16 Shop Drawing | 28 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 963 | 2026-07-22 |  | 1 Doc QA error-KPTG-TRANSMIT-002899 | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-003179 | Closed | 28 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-16 | Jangho-TRANSMIT-000245 | NA | Trade Partner | Tower A&B Level 6~16 Shop Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 963 | 2026-07-22 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-003179 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-16 | Auscool-TRANSMIT-000108 | NA | Trade Partner | Mechanical Commissioning Plan | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004968 - INSIDE DOCUMENT TYPE IS INCORRECT | 2026-07-16 | 2026-07-16 | KPTG-SADV-004968 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-16 | Auscool-TRANSMIT-000109 | NA | Trade Partner | Commissioning Method Statement Building Management Control System | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004967 - INSIDE THE DOCUMENT TYPE IS INCORRECT. | 2026-07-16 | 2026-07-16 | KPTG-SADV-004967 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-15 | TTW-TRANSMIT-000071 | N/A | Consultant | Structural Documentation - Issued for Coordination | 156 | 0 | 0 | NA | APPROVED | 2026-01-15 | WF-000102, WF-000103 | 200 | 2026-01-17 |  |  | 2026-01-16 | 2026-01-16 | KPTG-TRANSMIT-000288 | Closed | 156 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-16 | INGEN3D-TRANSMIT-000203 | NA | Trade Partner | Tower A&B Level 6~16 Shop Drawing | 19 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 963 | 2026-07-22 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-003187 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-16 | INGEN3D-TRANSMIT-000204 | NA | Trade Partner | Tower A&B Level 6~16 Shop Drawing | 4 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 963 | 2026-07-22 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-003146 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-16 | INGEN3D-TRANSMIT-000205 | NA | Trade Partner | Tower A&B Level 6~16 Shop Drawing | 4 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 963 | 2026-07-22 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003261 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-16 | INGEN3D-TRANSMIT-000206 | NA | Trade Partner | Tower A&B Level 6~16 Shop Drawing | 2 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 963 | 2026-07-22 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-003189 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-16 | Jangho-TRANSMIT-000242 | NA | Trade Partner | Alum sheet color Dulux Electro Medium Bronze Kinetic - Flat Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-07-16 | NA | NA | 2026-07-23 |  |  | 2026-08-13 | 2026-08-14 | KPTG-TRANSMIT-003405 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-16 | Jangho-TRANSMIT-000243 | NA | Trade Partner | Tower A&B Level 6~16 Shop Drawing_Rev 03_For Approval | 87 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 969 | 2026-07-23 |  | 9 drawings with QA Errors | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-003165 | Closed | 87 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-16 | NXES-TRANSMIT-000054 | NA | Trade Partner | Nexus - Tech Data Sheet | 0 | 3 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004976 - The tittle inside and outside different,the document type is incorrect | 2026-07-16 | 2026-07-16 | KPTG-SADV-004976 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-16 | Auscool-TRANSMIT-000110 | NA | Trade Partner | Commissioning Plans For Approval | 0 | 2 | 0 | NA | APPROVED | 2026-07-16 | WF-000838 | NA | 2026-07-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-17 | NTERSIG-TRANSMIT-000010 | NA | Trade Partner | 26-004 Assemble Coburg - WAYFINDING SIGNAGE - S.101, S.102, S.103, S.201 | 17 | 0 | 0 | NA | APPROVED | 2026-07-17 | WF-01085 | NA | 2026-07-24 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-17 | ELLISAIR-TRANSMIT-000112 | NA | Trade Partner | Revised Stage 9 Level 1 Zone 1 and 2 drawings issued for Approval. | 3 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 1452 | 2026-07-24 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-006048 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2026-01-15 | PFP PL-TRANSMIT-000036 | NA | Trade Partner | Updated As-Builts Rev ABS-C | 4 | 0 | 0 | NA | APPROVED | [5 empty] | As-Builts, No review required |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-17 | D&E-TRANSMIT-000289 | SPARK-CRFI-KPG-000753 | Trade Partner | Refrigeration Pipes Supports - For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-17 | NA | NA | 2026-07-24 |  | Actual Received date - 16-07-2026 | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-001617 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-17 | TATE_-TRANSMIT-000033 | NA | Trade Partner | Tate - SCEC Pan Penetration Details | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Drawing status needs to be updated:KPTG-IntCorr-000689 |  | 2026-07-17 | KPTG-IntCorr-000689 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-17 | RDSBIM-TRANSMIT-000070 | NA | Trade Partner | LEVEL 05 CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 965 | 2026-07-23 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-003340 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-17 | Altaire-TRANSMIT-000123 | NA | Trade Partner | OMM & As Built Drawing Update | 17 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with Document number, Title, Revision, Revision date, Revision History, progress of status level, mixed submission. |  | 2026-07-17 | KPTG-SADV-006713 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-17 | TATE_-TRANSMIT-000034 | NA | Trade Partner | Tate - SCEC Pan Penetration Details | 1 | 0 | 0 | NA | APPROVED | 2026-07-17 | WF-000402 | NA | 2026-07-21 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-001098 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-17 | SMEPS-TRANSMIT-000350 | NA | Trade Partner | SME - IFA - Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-07-17 | WF-006411 | NA | 2026-08-12 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-17 | Civilex-TRANSMIT-000297 | NA | Trade Partner | Stage 2 - sample submission - eMesh Fibre Concrete - Pronto - Rev FOA-B | 0 | 1 | 0 | NA | APPROVED | 2026-07-17 | WF-006412 | NA | 2026-07-23 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-020343 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-17 | KALLIBRE-TRANSMIT-000015 | NA | Trade Partner | IFA - Locker Shop Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-07-17 | WF - 001086 | NA | 2026-07-24 |  | NA | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-003171 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-17 | RDSBIM-TRANSMIT-000069 | NA | Trade Partner | GROUND FLOOR TO LEVEL 06 LIFT CORE 1 CONCRETE PROFILE PLAN AND SECTIONAL ELEVATIONS | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Rejected - QA error |  | 2026-07-17 | KPTG-TRANSMIT-002942 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-17 | Civilex-TRANSMIT-000298 | NA | Trade Partner | Stage 1 - Swale Restoration | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Mismatch in document title. |  | 2026-07-17 | KPTG-SADV-006715 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2026-01-15 | ACG-TRANSMIT-000030 | NA | Trade Partner | M3 - DHA6 Samples | 0 | 44 | 0 | NA | APPROVED | [5 empty] | IFC Samples, No review required. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-16 | KPTG-IntCorr-001743 | NA | Trade Partner | Loadbank CxL3 Script | 0 | 1 | 0 | NA | APPROVED | 2026-07-16 | WF-001163 | NA | 2026-07-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-17 | Sienergy-TRANSMIT-000001 | NA | Trade Partner | Dry Type Trx GA dwg GE1 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with Document number and Title. |  | 2026-07-17 | DRAFT-003604 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-17 | Arco-TRANSMIT-000007 | NA | Trade Partner | Submission of shopdrawings - Arco roller shutters and fire shutters | 6 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 354 | 2026-07-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-01 | WIP- PACKAGE | NA | Client | PRINCIPAL'S PROJECT REQUIREMENTS (PPR) | 0 | 1 | 0 | NA | APPROVED | 2026-07-01 | NA | 288 | 2026-07-08 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-17 | SKS Tech-TRANSMIT-000199 | NA | Trade Partner | Comms containment FC-02 | 17 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 3893 | 2026-07-26 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-17 | Auspan-TRANSMIT-000518 | NA | Trade Partner | Precast shop drawings for approval. Levels 4, 5, 6 zone 4, 5 | 59 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 1512 | 2026-07-24 |  | 5 Drawings are on another review 3 Have stamp issue, terminated 1 Drawing is already terminated 2 drawings are updated and now it is in IFC |  | 2026-08-13 | KPTG-TRANSMIT-003218 | Closed | 59 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-17 | Auspan-TRANSMIT-000518 | NA | Trade Partner | Precast shop drawings for approval. Levels 4, 5, 6 zone 4, 5 | 13 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to difference in document number, title, status and revision - DRAFT-010107 |  | 2026-07-17 | DRAFT-010107 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-17 | RDSBIM-TRANSMIT-000225 | NA | Trade Partner | LINDRUM ¦ LEVEL 02 PARTITION WALL LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-07-17 | 698 | NA | 2026-07-22 |  |  | 2026-07-31 | 2026-07-31 | KPTG-SADV-005163 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-17 | RDSBIM-TRANSMIT-000068 | NA | Trade Partner | LEVEL 10 TO LEVEL 24 (ROOF) LIFT CORE 01 CONCRETE PROFILE PLAN | 5 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 967 | 2026-07-23 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003246 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-17 | DLTS-TRANSMIT-000057 | NA | Trade Partner | S11-Canopy Part 1-IFA Issue | 75 | 0 | 0 | NA | APPROVED | 2026-07-17 | WF-001264 | NA | 2026-07-21 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-006181 | Closed | 75 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-14 | RDSBIM-TRANSMIT-000141 | NA | Trade Partner | LINDRUM -LEVEL 11 TO LEVEL 27 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-01-15 |  | 514 | 2026-01-22 |  |  | 2026-01-23 | 2026-01-23 | KPTG-SADV-002728 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-17 | OveArup-TRANSMIT-000202 | NA | Trade Partner | Re: M3S4 Regulation 129 Report and Consent | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect ref No. |  | 2026-07-17 | KPTG-DA-007623 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-17 | Ardon-TRANSMIT-000062 | NA | Trade Partner | Remaining Door Frames - Re-submission | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Issued with Revision number, title, direct IFC submission without IFA. |  | 2026-07-17 | KPTG-SADV-006718 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-17 | SMEPS-TRANSMIT-000351 | NA | Trade Partner | Stage 4 Approval Request - Fiber Optic Cables | 0 | 2 | 0 | NA | REJECTED | [5 empty] | No reference number, title, revision, status mentioned inside the document |  | 2026-07-17 | KPTG-DA-007625 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-17 | SKS Tech-TRANSMIT-000200 | NA | Trade Partner | Updated Sections and Isometrics of PDU containment | 2 | 0 | 0 | NA | REJECTED | [5 empty] | REVISION NOT UPDATED |  | 2026-07-17 | KPTG-DA-007629 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-17 | Aurecon-TRANSMIT-000127 | NA | Consultant | Hydraulic Services - LOD300 Issued for Contract | 54 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 448 | 2026-07-27 |  |  | 2026-07-27 | 2026-07-28 | NA | Closed | 54 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-17 | WilsonPD-TRANSMIT-000113 | NA | Trade Partner | Stage 9 North and South facade Section | 1 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 1454 | 2026-07-22 |  | Review voided as requested by Project Coordinator. Revised drawing submitted on # 1492 |  | 2026-07-23 | KPTG-IntCorr-001812 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-17 | PARR-TRANSMIT-000210 | NA | Trade Partner | Re: P2649 - KPG NDC M3 - Stage 2 - Fuel - DFS Drawings - AS-BUILT | 28 | 0 | 0 | NA | REJECTED | [5 empty] | The revision date entered in Aconex does not match the revision date shown inside the drawing. |  | 2026-07-17 | KPTG-SADV-006719 | Closed | 28 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-17 | WilsonPD-TRANSMIT-000114 | NA | Trade Partner | Stage 9 ground floor water supply layout | 1 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 1456 | 2026-07-22 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-005917 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-17 | SMEPS-TRANSMIT-000237 | SPARK-CRFI-KPG-000340 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0101,0103,0104,0106,0108,0109,0110 | 7 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 355 | 2026-07-24 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001520 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-17 | Ardon-TRANSMIT-000063 | NA | Trade Partner | Previously Rejected Door Hardware | 0 | 8 | 0 | NA | REJECTED | [5 empty] | Revision A has already been received |  | 2026-07-17 | KPTG-DA-007627 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-15 | SC-TRANSMIT-000034 | NA | Trade Partner | VQ34 - Syfon Support Steel | 3 | 0 | 0 | NA | APPROVED | 2026-01-15 | 4DW-CADV-000355 |  |  |  | Internal workflow is initiated and completed |  | 2026-01-15 | KPTG-SADV-003323 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-17 | SMEPS-IntCorr-000354 | NA | Trade Partner | MEL06-UMS BOM | 0 | 1 | 0 | NA | APPROVED | 2026-07-17 | WF - 000547 | NA | 2026-07-23 |  | NA | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-001124 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-17 | SMEPS-TRANSMIT-000238 | SPARK-CRFI-KPG-000340 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0102 | 1 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 356 | 2026-07-24 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001522 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-17 | Entire M-TRANSMIT-000065 | NA | Trade Partner | Electric Duct Heaters - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-17 | WF-000330 | NA | 2026-07-30 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-001698 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-17 | WilsonPD-TRANSMIT-000115 | NA | Trade Partner | Stage 9 ground floor sewer and stormwater | 1 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 1458 | 2026-07-22 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-005921 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-17 | Stowe-A-TRANSMIT-000659 | NA | Trade Partner | STOWE - IFC Docs | 3 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 4399 | 2026-07-24 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-020098 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-17 | Eneraque-TRANSMIT-000042 | NA | Trade Partner | ENE - Typical Pipe Supports | 2 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 1460 | 2026-07-24 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-006440, KPTG-TRANSMIT-007307 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-17 | ECBS-TRANSMIT-000067 | NA | Trade Partner | Techdata_ Armstrong Bioguard Acoustic Ceiling Tiles CLG02_For Approval 7-8 | 0 | 1 | 0 | NA | APPROVED | 2026-07-17 | WF-006418 | NA | 2026-08-07 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-17 | Ardon-TRANSMIT-000064 | NA | Trade Partner | Remaining Door Frames - Re-submission | 3 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 4403 | 2026-07-24 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-17 | SMEPS-TRANSMIT-000239 | SPARK-CRFI KPG-000302 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0181,0182,0183,0189 | 4 | 0 | 0 | KPTG-IntCorr-003606 | APPROVED | 2026-07-30 | NA | 384 |  |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001544 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-17 | SMEPS-TRANSMIT-000352 | NA | Trade Partner | SME - IFC - Documentation Submission | 5 | 0 | 0 | NA | REJECTED | [5 empty] | FOA revision of some documents not received |  | 2026-07-17 | KPTG-DA-007628 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-15 | fjc-TRANSMIT-000120 | NA | Consultant | Concrete drawing updates | 12 | 0 | 0 | NA | APPROVED | 2026-01-15 |  | 515 | 2026-01-20 |  |  | 2026-01-29 | 2026-01-29 | KPTG-SADV-002780 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-17 | SMEPS-TRANSMIT-000240 | SPARK-CRFI-KPG-000302 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0184,0185,0186 | 3 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 357 | 2026-07-24 |  | Terminated as per peter advise |  | 2026-08-26 | KPTG-SADV-006706 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-17 | SMEPS-TRANSMIT-000036 | NA | Trade Partner | Tech Data - Bulk Electrical Upload | 0 | 1 | 0 | NA | APPROVED | 2026-07-17 | WF-000331 | NA | 2026-07-30 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-001195 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-17 | Ardon-TRANSMIT-000065 | NA | Trade Partner | Previously Rejected Door Hardware - Re-submission | 0 | 8 | 0 | NA | APPROVED | 2026-07-17 | WF-006421 | NA |  |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-020332 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-17 | PARR-TRANSMIT-000211 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - DIESEL FUEL SYSTEM FUNCTIONAL DESCRIPTION | 0 | 1 | 0 | NA | APPROVED | 2026-07-17 | WF-006423 | NA | 2026-07-29 |  | Kate Madigan submitted this review |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-17 | HDRAus-TRANSMIT-000525 | NA | Trade Partner | M3 SW - Document upload - PDF and CAD | 0 | 1 | 0 | NA | REJECTED | [5 empty] | the attached document for IFC submission seems mistake on the document Naming on the Aconex |  | 2026-07-17 | KPTG-SADV-006720 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-17 | DLTS-TRANSMIT-000058 | NA | Trade Partner | S11-Canopy Part 2-IFA Issue | 81 | 0 | 0 | NA | APPROVED | 2026-07-17 | WF-001271 | NA | 2026-07-21 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-006205 | Closed | 81 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-17 | HDRAus-TRANSMIT-000526 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 9 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 3895 | 2026-07-21 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-019983 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-17 | SMEPS-TRANSMIT-000242 | SPARK-CRFI-KPG-000363 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0121,0122,0123,0124,0125,0126,0127,0128 | 8 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 358 | 2026-07-24 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-001529 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-17 | Civilex-TRANSMIT-000299 | NA | Trade Partner | Stage 1 - Irrigation System Layout | 1 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 4405 | 2026-07-28 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-15 | AdntCons-TRANSMIT-000010 | NA | Trade Partner | Dry Fire Shop Drawings - For Review | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Same Revision is already in workflow. |  | 2026-01-15 | KPTG-IntCorr-003908 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-17 | SMEPS-TRANSMIT-000037 | NA | Trade Partner | Tech Data - Velcro (Comms) | 0 | 1 | 0 | NA | APPROVED | 2026-07-17 | WF-000332 | NA | 2026-07-30 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-001813 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-17 | IVS-TRANSMIT-000371 | NA | Consultant | Stage 4 - Stair C08 Issued for Certification | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision format |  | 2026-07-17 | KPTG-DA-007633 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-17 | Sienergy-TRANSMIT-000002 | NA | Trade Partner | Dry Type Trx GA dwg GE1 | 0 | 1 | 0 | NA | APPROVED | 2026-07-17 | WF-000333 | NA | 2026-07-30 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001633 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-17 | Civilex-TRANSMIT-000300 | NA | Trade Partner | Stage 2 - sample submission - Planter Box - Rev F | 1 | 0 | 0 | NA | REJECTED | [5 empty] | attached documents seem missing of document numbering in the inside drawing. |  | 2026-07-17 | KPTG-SADV-006721 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-17 | BTWA-TRANSMIT-000089 |  | Trade Partner | Aluminium Bracket Location | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Document do not have standerd document attributes:KPTG-SADV-005387 |  | 2026-07-17 | KPTG-SADV-005387 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-17 | ADP-TRANSMIT-000122 | NA | Consultant | ADP MEL4680 - Updated Electrical Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 361 | 2026-07-22 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-001200 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-17 | Arco-TRANSMIT-000008 | NA | Trade Partner | Submission of shopdrawings - Arco SWING AND SLIDING GATES | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing Title in Aconex is incomplete |  | 2026-07-17 | KPTG-TRANSMIT-001468 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-17 | SMEPS-TRANSMIT-000241 | NA | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0187,0188,0190 | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Draiwng status and date incorrect |  | 2026-07-17 | KPTG-TRANSMIT-001469 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-17 | Civilex-TRANSMIT-000301 | NA | Trade Partner | Stage 2 - sample submission - 7mm HBCE - High bitumen content emulsion for superior performance | 0 | 1 | 0 | NA | APPROVED | 2026-07-16 | WF-006428 | NA | 2026-07-24 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-020235 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-17 | RDSBIM-TRANSMIT-000224 | NA | Trade Partner | INDRUM ¦ GROUND LEVEL - BLOCK WALL ELEVATION PLAN AND ELEVATION | 2 | 0 | 0 | KPTG-IntCorr-001210 | APPROVED | 2026-07-20 | NA | 702 | 2026-07-27 |  | KPTG-IntCorr-001210 - REQUESTED GUIDANCE, BUT NO RESPONACE RECEIVED YET. | 2026-08-20 | 2026-08-20 | KPTG-SADV-005344 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2025-11-28 | VIA Arch-TRANSMIT-000012 | NA | Consultant | M3 - DHA6 Line Marking | 2 | 0 | 0 | NA | APPROVED | 2025-12-01 |  | 1267 | 2025-12-04 |  |  |  | 2026-01-16 | KPTG-TRANSMIT-000677 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-10-23 | KETE-TRANSMIT-000088 | NA | Trade Partner | Submission – tower shop drawing | 68 | 0 | 0 | NA | APPROVED | 2025-10-29 | NA | 414 | 2025-11-05 |  |  | 2025-12-02 | 2025-12-02 | KPTG-SADV-002323 | Closed | 68 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-16 | IVS-TRANSMIT-000311 | NA | Consultant | Stage 4 - Cooling Tower & Chiller Room Zone C1 Package (Construction Issue) | 6 | 0 | 0 | NA | APPROVED | 2026-01-16 |  | 1785 | 2026-01-20 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-012068 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-17 | RDSBIM-TRANSMIT-000226 | NA | Trade Partner | LINDRUM ¦ LEVEL 04 PARTITION WALL LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 699 | 2026-07-22 |  |  | 2026-07-31 | 2026-07-31 | KPTG-SADV-005164 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-17 | RDSBIM-TRANSMIT-000227 | NA | Trade Partner | LINDRUM ¦ LEVEL 05 PARTITION WALL LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 700 | 2026-07-22 |  | KPTG-IntCorr-001214 - As per direction from Mark we terminate the workflow #700. | 2026-07-20 | 2026-07-20 | KPTG-IntCorr-001214 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-17 | NXES-TRANSMIT-000055 | NA | Trade Partner | Basement, Ground Floor & Mezz Electrical Shop Drawings | 6 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004992 - Tittle and status are incorrect. | 2026-07-17 | 2026-07-17 | KPTG-SADV-004992 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-17 | NXES-TRANSMIT-000056 | NA | Trade Partner | MATV & PTV SCHEMATIC | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004993 - Document no, drawing alignments are incorrect. | 2026-07-17 | 2026-07-17 | KPTG-SADV-004993 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-17 | NDY-TRANSMIT-000024 | NA | Trade Partner | SUPERFRAME IFC LIGHTING ISSUE | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001218 - As per direction from Ashlin, we only update the register and transmit to all. | 2026-07-17 | 2026-07-17 | KPTG-IntCorr-001218 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-17 | IVS-TRANSMIT-000372 | NA | Consultant | Stage 2 - Southern Retaining Wall Construction Issue (Revised as clouded) | 1 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | #4407 | 2026-07-24 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-019812 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-17 | KALLIBRE-TRANSMIT-000001 | NA | Trade Partner | FOA-1 - Door Frame Shop Drawings | 27 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 363 | 2026-07-23 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001298 | Closed | 27 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-17 | Ardon-TRANSMIT-000013 | NA | Trade Partner | Priority 2 Shop Drawings | 18 | 0 | 0 | NA | APPROVED | 2026-07-17 | WF-001265 | NA | 2026-07-28 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-006436 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-17 | DCN-TRANSMIT-000022 | NA | Trade Partner | Link Bridge Window Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-07-17 | WF-001263 | NA | 2026-07-23 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-17 | ELLISAIR-GCOR-000238 | NA | Trade Partner | CCW riser point load calculations | 0 | 1 | 0 | NA | APPROVED | 2026-07-17 | WF-001262 | NA | 2026-07-23 |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-006260 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-15 | fjc-TRANSMIT-000121 | NA | Consultant | Precast Elevations | 2 | 0 | 0 | NA | APPROVED | 2026-01-15 |  | 516 | 2026-01-22 |  | as per the direction from jake we terminated this work flow on 23-01-2026. | 2026-01-23 | 2026-01-23 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-17 | ARCST-GCOR-000051 | NA | Trade Partner | Material Tech Data Sheets | 0 | 4 | 0 | NA | APPROVED | 2026-07-17 | WF-001259 | NA | 2026-07-22 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-17 | NXES-TRANSMIT-000077 | NA | Trade Partner | Boom Gate Shop Drawings | 7 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Document Numbering and title bloc requires updation:KPTG-SADV-005392 |  | 2026-07-17 | :KPTG-SADV-005392 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-17 | ACCCA-TRANSMIT-000012 | NA | Trade Partner | STORMWATER PITS FOR APPROVAL | 3 | 0 | 0 | KPTG-IntCorr-000325 | APPROVED | 2026-08-03 | Na | 599 | 2026-08-11 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-000888 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-17 | SMEPS-TRANSMIT-000002 | NA | Trade Partner | STAGE 6 - ELECTRICAL SERVICES - OVERALL INGROUND SITE PLAN (FOA-1) | 1 | 0 | 0 | KPTG-IntCorr-000323 | APPROVED | 2026-07-20 | NA | 469 | 2026-07-28 |  |  | 2026-07-22 | 2026-07-23 | KPTG-TRANSMIT-000673 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-17 | SMEPS-TRANSMIT-000003 | NA | Trade Partner | STAGE 6 - TELECOMMUNICATION SERVICES - OVERALL INGROUND SITE PLAN (FOA-1) | 1 | 0 | 0 | KPTG-IntCorr-000324 | APPROVED | 2026-07-21 | NA | 473 | 2026-07-29 |  |  | 2026-07-22 | 2026-07-23 | KPTG-TRANSMIT-000671 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-17 | RBG-TRANSMIT-000008 | NA | Trade Partner | Crane Base Drawings IFC | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | update register only |  | 2026-07-17 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-17 | PTA-TRANSMIT-000028 | NA | Consultant | CPP Trench Grate Update - Issue for Coordination | 6 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 456 | 2026-07-23 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-000777 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-17 | BTWA-TRANSMIT-000091 | NA | Trade Partner | Aluminium Bracket Location | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Document Numbering is incorrect:KPTG-SADV-005393 |  | 2026-07-17 | KPTG-SADV-005393 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-17 | Baigents-TRANSMIT-000019 | NA | Trade Partner | Block 01 Precast Columns & Beams IFC | 171 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 458 | 2026-07-27 |  |  | 2026-07-23 | 2026-07-24 | KPTG-TRANSMIT-000694 | Closed | 171 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-17 | BTWA-TRANSMIT-000090 | NA | Trade Partner | Stage 2 - REV A - Issue for Information drawing set | 39 | 0 | 0 | KPTG-IntCorr-008558 | APPROVED | [5 empty] | Alignment & revision history has not properly done.KPTG-SADV-005415 |  | 2026-07-20 | KPTG-SADV-005415 | Closed | 39 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-15 | Arco-TRANSMIT-000009 | NA | Trade Partner | BIFOLDS - CARPARK ( WEST CARPARK ENTRY D03-A0.11) | 2 | 0 | 0 | NA | APPROVED | 2026-01-15 |  | 396 | 2026-01-20 |  |  |  | 2026-01-21 | KPTG-SADV-003477 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-17 | INDS-TRANSMIT-000050 | NA | Trade Partner | Wet Fire - Ground Zone 3 & 5 | 2 | 0 | 0 | KPTG-IntCorr-001019 | APPROVED |  | NA | NA |  |  | IFC - Waiting for review advise KPTG-IntCorr-001019 Rejected by Kapitol PC - DRAFT-010184 |  | 2026-07-20 | DRAFT-010184 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-17 | INDS-TRANSMIT-000051 | NA | Trade Partner | Wet Fire - Ground Zone 1 & 4 | 2 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 1510 | 2026-07-24 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-002910 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-17 | INDS-TRANSMIT-000049: | NA | Trade Partner | Dry Fire - Basement | 5 | 0 | 0 | KPTG-IntCorr-001018 | APPROVED | 2026-07-20 | NA | 1530 | 2026-07-27 |  | IFC - Waiting for review advise -KPTG-IntCorr-001018 | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-002917 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-17 | RDSBIM-TRANSMIT-000083 | NA | Trade Partner | GREYSTAR GROUND FLOOR CONCRETE PROFILE PLAN ZONE 3 | 2 | 0 | 0 | KPTG-IntCorr-001017 | APPROVED |  | NA | NA |  |  | Kapitol to advise KPTG-IntCorr-001017 Drawing Superseded via RDSBIM-TRANSMIT-000084 |  | 2026-07-20 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-17 | Auspan-TRANSMIT-000517 | NA | Trade Partner | : Precast shop drawings for construction. 2P5058 and 3P5102 | 2 | 0 | 0 | KPTG-IntCorr-001007 | APPROVED |  | NA | NA |  |  | IFC - Waiting for KIM review advise KPTG-IntCorr-001007 ALL OK TO PROCEED AS IFC- KPTG-TRANSMIT-002849 |  | 2026-07-20 | KPTG-TRANSMIT-002849 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-17 | Auspan-TRANSMIT-000411 | NA | Trade Partner | Precast shop drawings for approval. Level 2. | 1 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 1514 | 2026-07-24 |  | Review terminated as advised by Kim. To be updated and resubmitted by Auspan. |  | 2026-07-20 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-17 | IJF-TRANSMIT-000005 | NA | Trade Partner | Joinery - Prototype Drawings | 42 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 1517 | 2026-07-24 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-002988 | Closed | 42 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-17 | 4DW-TRANSMIT-000198 | NA | Consultant | Structural Documentation - Steelwork & Facade Precast Package | 20 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 396 | 2026-07-22 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-003128 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-17 | Bradley Teams Message - 214266-TTW-FAC-RPT-100 | NA | Consultant | 214266-TTW-FAC-RPT-100 | 0 | 1 | 0 | NA | APPROVED | 2026-07-17 | WF-000976 | NA | 2026-07-21 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003241 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-17 | Jangho-TRANSMIT-000246 | NA | Trade Partner | Tower A&B Level 6~16 Shop Drawing_Rev 03_For Approval | 8 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 969 | 2026-07-23 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-003165 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-15 | fjc-TRANSMIT-000122 | NA | Consultant | Precast Elevations | 1 | 0 | 0 | NA | APPROVED | 2026-01-15 |  | 516 | 2026-01-22 |  | as per the direction from jake we terminated this work flow on 23-01-2026. | 2026-01-23 | 2026-01-23 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-17 | Jangho-TRANSMIT-000248 | NA | Trade Partner | Tower A&B Level 6~16 Shop Drawing_Rev 03_For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 969 | 2026-07-23 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-003165 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-17 | Jangho-TRANSMIT-000247 - CAD file | NA | Trade Partner | Tower A&B Level 6~16 Shop Drawing_Rev 03_CAD file _For Information | 125 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Rev cross checked with PDF and send to all TP for info. - |  | 2026-07-17 | KPTG-TRANSMIT-002949 | Closed | 125 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-17 | WAM-TRANSMIT-000827 | NA | Trade Partner | A42 Common Areas_Interior Details | 3 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 971 | 2026-07-21 |  |  | 2026-07-27 | 2026-07-28 | KPTG-TRANSMIT-003110 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-17 | RDSBIM-TRANSMIT-000086 | NA | Trade Partner | : 671CHP ¦ GROUND LEVEL TO ROOF CORE WALL LAYOUT AND ELEVATION | 9 | 0 | 0 | KPTG-IntCorr-000994 | APPROVED | 2026-07-21 | NA | 663 | 2026-07-22 |  | waiting for Kapitol to advise. KPTG-IntCorr-000994 | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-001463 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-17 | RESICOM-TRANSMIT-000011 | NA | Trade Partner | : 671 Chapel - Waste Chute Shop Drawings IFC | 5 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to incorrect Aconex metadata. KPTG-SADV-003110 |  | 2026-07-17 | KPTG-SADV-003110 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-17 | ccair-TRANSMIT-000034 | NA | Trade Partner | Mechanical Services L04 to 11 Buildersworks IFA [B] | 1 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 659 | 2026-07-24 |  | Revise & resubmit | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-001514 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-17 | LGCE-TRANSMIT-000062 | NA | Trade Partner | Basement drawings updates | 3 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to drawing Revision error. KPTG-SADV-003128 |  | 2026-07-17 | KPTG-SADV-003128 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-17 | POTTSENG-TRANSMIT-000034 | NA | Trade Partner | 671C: HYDRAULIC SERVICES - LEVEL 04 - PENETRATION LAYOUT | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Review required as advised by Tayla -Registered and transmit KPTG-TRANSMIT-001376 |  | 2026-07-17 | KPTG-TRANSMIT-001376 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-17 | Bradley Email | NA | Trade Partner | RAISED SAFETY PLATFORMS - CAD & PDF - District Living - Traffic Alignment | 5 | 0 | 0 | NA | APPROVED |  | NA | NA | 2026-07-23 |  | Registered and fwded - KPTG-TRANSMIT-002951 |  | 2026-07-17 | KPTG-TRANSMIT-002951 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-17 | WAM-TRANSMIT-000828 | NA | Trade Partner | A41 - A42 - A43 - A71 - A72 | 9 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 973 | 2026-07-21 |  |  | 2026-07-27 | 2026-07-28 | KPTG-TRANSMIT-003107 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-16 | SMEPS-TRANSMIT-000141 | NA | Trade Partner | M3 S3 GIS - Electrical defects - SME | 2 | 0 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-17 | RDSBIM-TRANSMIT-000071 | NA | Trade Partner | GROUND FLOOR TO LEVEL 06 LIFT CORE 1 CONCRETE PROFILE PLAN AND SECTIONAL ELEVATIONS | 3 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 975 | 2026-07-21 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-003574 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-17 | Jangho-TRANSMIT-000249 | NA | Trade Partner | Brick Sample Submission（Tan Brick Option 3） | 0 | 1 | 0 | NA | APPROVED | 2026-07-17 | NA | 967 | 2026-08-07 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-17 | L.E.S.-TRANSMIT-000024 | NA | Trade Partner | LEVEL 10 TO LEVEL 24 (ROOF) LIFT CORE 01 CONCRETE PROFILE PLAN | 0 | 43 | 0 | NA | REJECTED | [5 empty] | rejected: Sample & Drawings together as well as QA error in Drawings |  | 2026-07-17 | KPTG-TRANSMIT-002959 | Closed | 43 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-17 | INGEN3D-TRANSMIT-000207 | NA | Trade Partner | Ground Floor - Cast in Dowels - IFC (08-04-2026) | 47 | 0 | 0 | NA | APPROVED | 2026-07-17 | WF-000984 | 967 | 2026-07-27 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-17 | INGEN3D-TRANSMIT-000208 | NA | Trade Partner | Level 19-21 - Precast Columns - No Longer in Use | 8 | 0 | 0 | NA | APPROVED |  | NA | NA | 2026-07-23 |  | no longer in use - forwarded to all tp - |  | 2026-07-17 | KPTG-TRANSMIT-002961 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-17 | L.E.S.-TRANSMIT-000025 | NA | Trade Partner | Lighting Transmittal Rev 1 | 0 | 3 | 0 | NA | APPROVED | 2026-07-17 | WF-000985 | NA | 2026-07-23 |  |  | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-003076 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-17 | Jangho-TRANSMIT-000251 | NA | Trade Partner | Tower A&B Level 1~3 Floor Plan Shop Drawing_Rev 03_For Approval | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Replaced by Jangho Trn # 255 |  | 2026-07-21 | Jangho-TRANSMIT-000255 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-17 | WAM-TRANSMIT-000829 | NA | Trade Partner | WAM ARCH - L1 A CSP Update | 1 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 977 | 2026-07-22 |  |  | 2026-07-28 | 2026-07-29 | KPTG-TRANSMIT-003156 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-17 | OveArup-TRANSMIT-000042 | NA | Consultant | Reg 126 certificates - Fire and Hyd | 0 | 2 | 0 | NA | APPROVED | 2026-08-10 | WF-001119 | NA | 2026-08-12 |  | Rev. error in Aconex Register - Accepted as instructed by John | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-003359 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-17 | WAM-TRANSMIT-000830: | NA | Trade Partner | A64 Prototype series _ on CAD format Issue for information | 9 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | NA |  |  | CAD files - compared and forwarded to all TP - KPTG-TRANSMIT-002962 |  | 2026-07-17 | KPTG-TRANSMIT-002962 | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-15 | ECBS-TRANSMIT-000052 | NA | Trade Partner | Resubmission of Ripple Sound RCP as per commented | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong Revision and Title are on the drawings, requested to resubmit |  | 2026-01-15 | KPTG-SADV-003324 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-17 | ZIA-TRANSMIT-000074 | NA | Trade Partner | Samples - SLA & DP Sensor - fc docs | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | FC DOCS - 2 FORWARDED TO ALL PARTIES - (4 FOA-1) docs same revision already exists hence no action) - |  | 2026-07-17 | KPTG-TRANSMIT-004103 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-17 | Hames-TRANSMIT-000164 | NA | Trade Partner | Latest Revisions | 9 | 0 | 0 | NA | APPROVED | 2026-07-17 | NA | 1314 | 2026-07-21 |  |  | 2026-08-05 | 2026-08-06 | KPTG-TRANSMIT-004216 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-17 | procore - 311 | NA | Trade Partner | Earthing Study Rev 6 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Uploaded to Aconex and fwded to all parties |  | 2026-07-21 | KPTG-TRANSMIT-004107 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-20 | SMEPS-TRANSMIT-000074 | NA | Trade Partner | LOAD BANK SCHEMATIC | 1 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 1467 | 2026-07-27 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-006497 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-20 | D&E-TRANSMIT-000872 | NA | Trade Partner | SFN Scripts - Issued for Approval | 0 | 13 | 0 | NA | APPROVED | 2026-07-20 | WF-006431 | NA | 2026-08-13 |  | As instructed by Ellie, KPTG-IntCorr-016434 | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-020655 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-20 | PTA-TRANSMIT-000029 | NA | Consultant | External Precast Elevation - Issue for Coordination | 4 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 461 | 2026-07-28 |  | NA | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-000994 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-20 | Auspan-TRANSMIT-000519 | NA | Trade Partner | Re: Precast shop drawings for approval. Levels 4, 5, 6 zone 4, 5 | 12 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 1520 | 2026-07-25 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-003163 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-20 | Auspan-TRANSMIT-000519 | NA | Trade Partner | Re: Precast shop drawings for approval. Levels 4, 5, 6 zone 4, 5 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - Difference in document number - DRAFT-010160 |  | 2026-07-20 | DRAFT-010160 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-20 | fjc-TRANSMIT-000168 | NA | Consultant | Architecturals - BP6 + BP7 | 31 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 701 | 2026-07-23 |  | KPTG-IntCorr-001231 - As per direction from Ashlin, we terminate the WF and unlocked the documents. | 2026-07-22 | 2026-07-22 | KPTG-IntCorr-001231 | Closed | 31 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-15 | ECBS-TRANSMIT-000053 | NA | Trade Partner | Resubmission for Ripple Sound RCP | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Title of Drawings are mismatched with Document Register |  | 2026-01-15 | KPTG-SADV-003326 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-20 | CDL-TRANSMIT-000044 | NA | Trade Partner | Action Requires -Re: KPA Stage 2 Documentation | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Document Numbering & Revision history are found wrong: KPTG-SADV-005402 |  | 2026-07-20 | KPTG-SADV-005402 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-20 | JCBa-TRANSMIT-000155 | NA | Consultant | Transmittal – Facade Assembly Drawings Issued for Construction | 4 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 1522 | 2026-07-22 |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-003042 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | BIMF-TRANSMIT-000014 | NA | Trade Partner | L3 and L4 Drainage Plans | 4 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 979 | 2026-07-27 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-003281 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-20 | SMEPS-TRANSMIT-000028 | NA | Trade Partner | Gym Lighting Tech Data | 0 | 7 | 0 | NA | APPROVED | 2026-07-20 | WF - 01087 | NA | 2026-07-24 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-20 | RDSBIM-TRANSMIT-000227 | NA | Trade Partner | LEVEL 03 EXTERNAL AREA CONCRETE PROFILE PLAN | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-07-20 | KPTG-TRANSMIT-003150 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-20 | 4DW-TRANSMIT-000200 | NA | Consultant | Structural Documentation - Drawing S102_101 | 1 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 398 | 2026-07-23 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-003161 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-20 | LANSA-TRANSMIT-000110 | NA | Trade Partner | Updated Ground & Level 09 Hyd Drawings with Irrigation Changes | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-07-20 | KPTG-TRANSMIT-003151 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-20 | Aurecon-TRANSMIT-000134 | NA | Consultant | Combined Services - LOD300 Issued for Contract | 23 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 463 | 2026-07-28 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-000726 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | Civilex-TRANSMIT-000113 | NA | Trade Partner | Concrete Mix Design for PC8 | 0 | 1 | 0 | NA | APPROVED | 2026-07-20 | WF-000988 | NA | 2026-07-23 |  |  | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-003054 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-20 | INGEN3D-TRANSMIT-000717 | NA | Trade Partner | I3D-378 Next DC M3 Stage 4 - Link Bridge - Deleted Drawings | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-20 | KPTG-TRANSMIT-019799 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-15 | ECBS-TRANSMIT-000054 | NA | Trade Partner | Resubmission as per Comments on Documents Naming | 3 | 0 | 0 | NA | APPROVED | 2026-01-15 |  | 397 | 2026-01-20 |  |  |  | 2026-02-04 | KPTG-SADV-003612 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | RDSBIM-TRANSMIT-000072 | NA | Trade Partner | LEVEL 07 TO ROOF STAIR/LIFT CORE 02 CONCRETE PROFILE PLAN ¦ SECTIONAL ELEVATIONS | 4 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 981 | 2026-07-28 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-003455 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-20 | NGBSol-TRANSMIT-000001 | NA | Trade Partner | Roof Ductwork Layout - Issued for Approval | 4 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 365 | 2026-07-24 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001372 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-20 | SYNACC-TRANSMIT-000007 | NA | Trade Partner | Transmittal - Level 10 Davits - P-02 | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-005001 - drawing no,date,revision ,status are incorrect. | 2026-07-20 | 2026-07-20 | KPTG-SADV-005001 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-20 | RDSBIM-TRANSMIT-000017 | NA | Trade Partner | NXGE01 ¦ GROUND FLOOR PLANT AREA CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 367 | 2026-07-24 |  | Terminated as advised by Caitlin Grimmet for submitting the updated document. | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-001285 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | RDSBIM-TRANSMIT-000073 | NA | Trade Partner | GROUND FLOOR TO LEVEL 06, 09 STAIR/LIFT CORE 02 CONCRETE PROFILE SECTIONAL ELEVATIONS | 3 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 983 | 2026-07-28 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-003577 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-20 | Auspan-TRANSMIT-000520 | NA | Trade Partner | Precast shop drawings for construction | 21 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review, updated register and distributed - KPTG-TRANSMIT-002847 |  | 2026-07-20 | KPTG-TRANSMIT-002847 | Closed | 21 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-20 | LNCPPL-TRANSMIT-000016 | NA | Trade Partner | Fire Services Site Plan - Inground Shop Drawings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with Drawings status, Revision date. |  | 2026-07-20 | KPTG-SADV-000976 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-20 | 4DW-TRANSMIT-000068 | NA | Consultant | Roof plinths, Lower Roof and Upper Roof steelwork for coordination | 17 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 465 | 2026-07-28 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-000776 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | Civilex-TRANSMIT-000114 | NA | Trade Partner | VonRoll Ecopur Pipe | 0 | 1 | 0 | NA | APPROVED | 2026-07-20 | WF-000990 | NA | 2026-07-23 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-003586 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-17 | SMEPS-TRANSMIT-000036 | NA | Trade Partner | Tech Data - Bulk Electrical Upload | 0 | 22 | 0 | NA | APPROVED | 2026-07-17 | WF-000331 | NA | 2026-07-30 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-001766 | Closed | 22 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-15 | Arco-TRANSMIT-000011 | NA | Trade Partner | bifold door - East carpark | 1 | 0 | 0 | NA | APPROVED | 2026-01-15 |  | 398 | 2026-01-20 |  |  |  | 2026-01-21 | KPTG-SADV-003478 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | RDSBIM-TRANSMIT-000074 | NA | Trade Partner | MEZZANINE FLOOR STAGE 4B3 PARTITION WALL KEY PLAN ¦ LAYOUT | 5 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 985 | 2026-07-22 |  | IR - Internal Review version | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-003235 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-20 | ADP-TRANSMIT-000370 | NA | Consultant | ADP MEL4780 -LV SCCS Report- FC-02 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-20 | KPTG-TRANSMIT-019804 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-20 | P & R-TRANSMIT-000098 | NA | Trade Partner | Re: Amended PAC Unit Tech Data for IFA 20.07 | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Revision of document does not match:KPTG-SADV-005409 |  | 2026-07-20 | KPTG-SADV-005409 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-20 | NXES-TRANSMIT-000058 | NA | Trade Partner | Mezzanine Electrical Layout | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-005003 - revision, tittle are incorrect | 2026-07-20 | 2026-07-20 | KPTG-SADV-005003 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-20 | INGEN3D-TRANSMIT-000716 | NA | Trade Partner | I3D - M3 Stage 4 - Link Bridge - Precast Panels - IFA | 39 | 0 | 0 | NA | REJECTED | [5 empty] | Two diff status in same transmittal, also title not mentioned inside documents |  | 2026-07-20 | KPTG-DA-007637 | Closed | 39 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-20 | ELLISAIR-TRANSMIT-000130 | NA | Trade Partner | Stage 9 Ground Floor Zone 4 drawings issued for Construction. | 2 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 1471 | 2026-07-27 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-006306 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-20 | Civilex-TRANSMIT-000295 | NA | Trade Partner | Updated Drawing Set - Southern Retaining Wall Rev M | 2 | 0 | 0 | NA | APPROVED | 2026-07-20 | WF-006432 | NA | 2026-08-06 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-020903 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-20 | ELLISAIR-TRANSMIT-000131 | NA | Trade Partner | Stage 9 Ground floor Zone 3 Duct layout drawing issued for Construction. | 1 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 1473 | 2026-07-27 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-006310 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-20 | D&E-TRANSMIT-000925 | NA | Trade Partner | Re: NXM3S2 - LEVEL 01 - DATAHALL 7 SFN UNION AND BOLT TORQUE MAP - Issued For Construction | 1 | 0 | 0 | NA | REJECTED | [5 empty] | we have not yet received the IFA document referenced in the attached transmittal |  | 2026-07-20 | KPTG-SADV-006735 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-20 | WilsonPD-TRANSMIT-000213 | NA | Trade Partner | Hydraulic Services Updated Drainage Layout Level 1 Zone A | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status inside the drawing and in Aconex seem different |  | 2026-07-20 | KPTG-TRANSMIT-001470 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-14 | SMEPS-TRANSMIT-000247 | NA | Trade Partner | SME - SHOPDRAWINGS - SEISMIC-ELC | 3 | 0 | 0 | NA | APPROVED | 2026-01-16 | NA | 1336 | 2026-01-21 |  | Voided-It will send through on Aconex |  |  | NA | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-20 | HDRAus-TRANSMIT-000527 | NA | Consultant | M3 SW - Document upload - Internal Finishes Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-07-20 | NA | 4410 | 2026-07-30 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-020030 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-20 | ccair-TRANSMIT-000133 | NA | Trade Partner | Updated shop drawings & dwfx files IFA | 10 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 603 | 2026-07-24 |  | NA | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-003186 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-20 | Schindle-TRANSMIT-000021 | SPARK-CRFI-KPG-000446 | Trade Partner | Schindler - NEL MCC Lift 1 HBU Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 359 | 2026-07-27 |  |  | 2026-07-24 | 2026-07-27 | KPTG-TRANSMIT-001507 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-20 | EAEGROUP-TRANSMIT-000114 | NA | Trade Partner | Updated Shop Drawing Revision - Block C3 | 13 | 0 | 0 | NA | APPROVED | 2026-07-21 | WF-006442 | NA | 2026-08-03 |  |  |  | 2026-07-20 | KPTG-TRANSMIT-019809 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-20 | NXES-TRANSMIT-000057 | NA | Trade Partner | Re: MATV & PTV SCHEMATIC | 2 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 703 | 2026-07-27 |  | KPTG-IntCorr-001215 - As per direction from Mark, this transmittal has been processed. KPTG-IntCorr-001345 - as per the direction from Ashlin we void the WF. | 2026-08-24 | 2026-08-24 | KPTG-IntCorr-001345 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | Jangho-TRANSMIT-000255 | NA | Trade Partner | Tower A&B Level 1~5 Floor Plan Shop Drawing | 10 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 987 | 2026-07-28 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-20 | NXT-TRANSMIT-001667 | NA | Client | M2 S4 Loadbank MSB IFC Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-07-20 | WF-006435 | NA | 2026-07-31 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-020601 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-20 | ARCST-TRANSMIT-000345 | NA | Trade Partner | C1 Cooling Tower Grating - Issued for Construction | 168 | 0 | 0 | NA | REJECTED | [5 empty] | REVISION DIFFERENCE |  | 2026-07-20 | KPTG-DA-007656 | Closed | 168 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-20 | HDRAus-TRANSMIT-000528 | NA | Consultant | M3 SW - Document upload - PDF and CAD (IFA Issue) | 1 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 4412 | 2026-07-30 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-020791 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-20 | Stowe-A-TRANSMIT-000660 | NA | Trade Partner | Re: Stowe - As Builts | 3 | 0 | 0 | NA | APPROVED | [5 empty] | AS PER THEIR REQUEST WE NOT PROCESSING THE DOCUMENT |  | 2026-07-20 | KPTG-TRANSMIT-019810 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-02 | ALC-TRANSMIT-000013 | NA | Consultant | Updated Acoustic Specification - with revised Pod details | 0 | 1 | 0 | NA | APPROVED | 2025-12-02 | WF-000780 | NA | 2025-12-05 | 0 |  | 2025-12-03 | 2025-12-03 | KPTG-TRANSMIT-002459 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-14 | SMEPS-TRANSMIT-000247 | NA | Trade Partner | SME - SHOPDRAWINGS - SEISMIC-TEL | 3 | 0 | 0 | NA | APPROVED | 2026-01-16 | NA | 1338 | 2026-01-21 |  | It will send on Aconex |  |  | NA | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-20 | PARR-TRANSMIT-000214 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - BFCP MODBUS REGISTER | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document number, revision, status is not mentioned inside document |  | 2026-07-20 | KPTG-IntCorr-016494 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-20 | P & R-TRANSMIT-000099 | NA | Trade Partner | Amended PAC Units Stage 2 IFA | 0 | 2 | 0 | NA | APPROVED | 2026-07-20 | WF-001056 | NA | 2026-07-27 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-20 | INGEN3D-TRANSMIT-000718 | NA | Trade Partner | Re: I3D - M3 Stage 4 - Link Bridge - Precast Panels - IFA | 36 | 0 | 0 | NA | APPROVED | 2026-07-20 | WF-006438 | NA | 2026-08-10 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-20 | Entire M-TRANSMIT-000066 | NA | Trade Partner | Ground floor - Mechanical Ductwork & Equipment Layouts - FOA | 4 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 369 | 2026-07-31 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001373 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-20 | WilsonPD-TRANSMIT-000214 | SPARK-CRFI-KPG-000510 | Trade Partner | Hydraulic Services Updated Drainage Layout Level 1 Zone A | 1 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 360 | 2026-07-27 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-001569 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-20 | ZIA-TRANSMIT-000129 | NA | Trade Partner | M3 Stage 4 - IP Device Register | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Title within the document, wrong code in the document number |  | 2026-07-20 | KPTG-DA-007648 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-20 | D&E-TRANSMIT-000927 | NA | Trade Partner | NXM3S4 - Ground & Level 1 - Builders Works Layout Zones - Issued For Construction | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-20 | KPTG-TRANSMIT-019811 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-20 | NXES-TRANSMIT-000059 | NA | Trade Partner | Basement Electrical Layout | 2 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 704 | 2026-07-27 |  |  | 2026-08-28 | 2026-08-28 | KPTG-SADV-005452 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-20 | PTA-TRANSMIT-000027 | NA | Consultant | Partition Plans Work in Progress - Issue for Coordination | 15 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 467 | 2026-07-28 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-000899 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-20 | Schindle-TRANSMIT-000022 | NA | Trade Partner | Schindler Lifts - MCOP & HPI - IFC Drawings | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Same revision already received |  | 2026-07-20 | KPTG-TRANSMIT-001475 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-19 | TTW-TRANSMIT-000004 | NA | Consultant | Facade Drawings - Issued For Information IFI-1/IFI-2 | 17 | 0 | 0 | NA | APPROVED | 2026-01-16 |  | 182 | 2026-01-23 |  |  |  | 2026-01-16 | KPTG-TRANSMIT-000510 | Closed | 17 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-20 | KALLIBRE-TRANSMIT-000028 | NA | Trade Partner | IFC - Extra 7x door frames | 7 | 0 | 0 | NA | REJECTED | [5 empty] | Alignment of drawing are found wrong: KPTG-IntCorr-000703 |  | 2026-07-20 | KPTG-IntCorr-000703 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-20 | RDSBIM-TRANSMIT-000010 | NA | Trade Partner | 303COL ¦ BASEMENT 2 CONCRETE PROFILE ENLARGED PLAN AND SECTIONS | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect drawing number |  | 2026-07-20 | Draft | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-20 | Civilex-TRANSMIT-000303 | NA | Trade Partner | Stage 2 - sample submission - Planter Box - | 1 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 4414 | 2026-07-30 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-020058 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-20 | OveArup-TRANSMIT-000204 | NA | Trade Partner | M3 Stage 4 Regulation 129 FRV Report and Consent | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document number, revision, title are not mentioned inside the document |  | 2026-07-20 | KPTG-DA-007654 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-20 | RDSBIM-TRANSMIT-000011 | NA | Trade Partner | 303COL ¦ BASEMENT 2 CONCRETE PROFILE ENLARGED PLAN AND SECTIONS | 1 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 310 | 2026-07-29 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-20 | RDSBIM-TRANSMIT-000084 | NA | Trade Partner | Re: GREYSTAR ¦ GROUND FLOOR CONCRETE PROFILE PLAN ZONE 3 | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review, updated register and distributed -KPTG-TRANSMIT-002866 |  | 2026-07-20 | KPTG-TRANSMIT-002866 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-20 | NXES-TRANSMIT-000060 | NA | Trade Partner | Re: Mezzanine Electrical Layout | 2 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 705 | 2026-07-27 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-20 | ARCST-TRANSMIT-000348 | NA | Trade Partner | C3 Cooling Tower Handrails & Grating - Issued for Construction | 187 | 0 | 0 | NA | REJECTED | [5 empty] | Revision indifference |  | 2026-07-20 | KPTG-DA-007655 | Closed | 187 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-20 | KBGA-TRANSMIT-000001 | NA | Trade Partner | StormPro tech data for approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | mismatching details in cover sheet |  | 2026-07-20 | Awaiting approval | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-20 | KBGA-TRANSMIT-000002 | NA | Trade Partner | DWV / UPVC tech data for approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | mismatching details in cover sheet |  | 2026-07-20 | Awaiting approval | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-15 | ACG-TRANSMIT-000030 | NA | Trade Partner | M3 - DH7/8 FOV | 0 | 1 | 0 | NA | APPROVED | 2026-01-16 | WF-000874 | NA | 2026-01-29 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-20 | KBGA-TRANSMIT-000003 | NA | Trade Partner | HDPE tech data for approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Mismatching details in Cover sheet |  | 2026-07-20 | KPTG-SADV-000483 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-20 | KALLIBRE-TRANSMIT-000016 | NA | Trade Partner | KALLIBRE-TRANSMIT-000016 | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected - KPTG-TRANSMIT-003160 |  | 2026-07-20 | KPTG-TRANSMIT-003160 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-20 | NXES-TRANSMIT-000061 | NA | Trade Partner | Ground Floor Low Level Lighting, Power & Comms Layout | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-005014 - The revision date is incorrect. | 2026-07-20 | 2026-07-20 | KPTG-SADV-005014 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-20 | WilsonPD-TRANSMIT-000215 | SPARK-CRFI-KPG-000345 | Trade Partner | Hydraulic Services - Updated Water Layout Ground Zone A | 1 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 361 | 2026-07-27 |  |  | 2026-07-24 | 2026-07-27 | KPTG-TRANSMIT-001498 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-20 | SYNACC-TRANSMIT-000008 | NA | Trade Partner | Transmittal - Level 10 Upper - Davits - P-02 | 1 | 0 | 0 | KPTG-IntCorr-001216 | REJECTED |  | NA | NA |  |  | KPTG-SADV-005070 - The drawing number, revision, and revision date are incorrect. | 2026-07-23 | 2026-07-23 | KPTG-SADV-005070 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-20 | RDSBIM-TRANSMIT-000228 | NA | Trade Partner | LINDRUM ¦LEVEL 06 PARTITION WALL LAYOUT | 1 | 0 | 0 | KPTG-IntCorr-001217 | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-001217 - Request to guidance, but no resonance received yet. KPTG-IntCorr-001220 - Revision date incorrect. | 2026-07-21 | 2026-07-21 | KPTG-IntCorr-001220 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-20 | ARCST-TRANSMIT-000344 | NA | Trade Partner | C1 Cooling Tower Handrails - Issued for Construction | 32 | 0 | 0 | NA | REJECTED | [5 empty] | status and title incorrect |  | 2026-07-20 | KPTG-DA-007659 | Closed | 32 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-20 | SMEPS-TRANSMIT-000038 | NA | Trade Partner | Shop Drawings: Communications | 1 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 371 | 2026-07-31 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-001362 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-20 | ARCST-TRANSMIT-000346 | NA | Trade Partner | C2 Cooling Tower Grating - Issued for Construction | 154 | 0 | 0 | NA | REJECTED | [5 empty] | The IFA for the documents has not been received |  | 2026-07-20 | KPTG-DA-007660 | Closed | 154 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-20 | D&E-TRANSMIT-000926 | NA | Trade Partner | Re: SFN Scripts - Issued for Construction | 3 | 0 | 0 | NA | REJECTED | [5 empty] | the attached document M3-MEC-DEA-ITP-B-0201-0027 is currently under review after the approval of review only you can upload IFC document. |  | 2026-07-20 | KPTG-TRANSMIT-019820 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-15 | DRLL-TRANSMIT-000062 | NA | Trade Partner | Battery Room Modules - Air Conditioning Systems Tech data | 0 | 1 | 0 | NA | APPROVED | 2026-01-15 | WF-000868 | NA | 2026-01-23 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-20 | SMEPS-TRANSMIT-000039 | NA | Trade Partner | Shop Drawings: Electrical | 10 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 373 | 2026-07-24 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001313 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-20 | LNCPPL-TRANSMIT-000017 | NA | Trade Partner | HYDRAULIC SERVICES - SITE PLAN INGROUND SERVICES Shop Drawing | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with revision date and drawings status. |  | 2026-07-20 | KPTG-SADV-000975 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-20 | ARCST-TRANSMIT-000347 | NA | Trade Partner | C2 Cooling Tower Handrails - Issued for Construction | 32 | 0 | 0 | NA | REJECTED | [5 empty] | The IFA for the documents has not been received |  | 2026-07-20 | KPTG-DA-007661 | Closed | 32 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | Axiom-TRANSMIT-000005 | NA | Trade Partner | Podium VMU ME11 Balustrade Drawings - Issue for Approval | 2 | 0 | 0 | NA | REJECTED | [5 empty] | QA ERROR - DOC NO, REV. |  | 2026-07-20 | KPTG-TRANSMIT-002989 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | Axiom-TRANSMIT-000006 | NA | Trade Partner | Tower VMU ME12 Balustrade Drawings Option 1 - Issue for Approval | 2 | 0 | 0 | NA | REJECTED | [5 empty] | QA ERROR - DOC NO, REV. |  | 2026-07-20 | KPTG-TRANSMIT-002990 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | Axiom-TRANSMIT-000007 | NA | Trade Partner | Tower VMU ME12 Balustrade Drawings Option 2 - Issue for Approval | 2 | 0 | 0 | NA | REJECTED | [5 empty] | QA ERROR - DOC NO, REV. |  | 2026-07-20 | KPTG-TRANSMIT-002991 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | Jangho-TRANSMIT-000256 | NA | Trade Partner | Structural Calculation For Tower Shop Drawing At 6F-16F_Rev 03_For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-20 | WF-000994 | NA | 2026-07-29 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-003166 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-10 | PROLMC-TRANSMIT-000042 | NA | Trade Partner | Proline parapet flashings detail | 1 | 0 | 0 | NA | APPROVED | 2026-07-10 | NA | 3840 | 2026-07-17 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-019821 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-20 | PTA-TRANSMIT-000030 | NA | Consultant | Master Site Plan CAD update | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | CAD file-Distribution |  | 2026-07-20 | KPTG-TRANSMIT-000617 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-20 | WGAVIC-TRANSMIT-000010 | NA | Consultant | Grading and Stormwater Drawings and Certificate - Issued for Construction | 12 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 471 | 2026-07-28 |  |  | 2026-07-23 | 2026-07-24 | KPTG-TRANSMIT-000699 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-16 | SMEPS-TRANSMIT-000140 | NA | Trade Partner | SME's outstanding sample submission | 0 | 4 | 0 | NA | APPROVED | 2026-01-16 | WF-003835 |  | 2026-01-29 |  |  |  | 2026-01-20 | KPTG-TRANSMIT-011638 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-20 | SMEPS-TRANSMIT-000004 | NA | Trade Partner | ELECTRICAL SERVICES PIT SCHEDULE (FOA-1) | 1 | 0 | 0 | KPTG-IntCorr-000336 | APPROVED |  | NA | 524 | 2026-08-04 |  | NA | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001025 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-20 | MALA-TRANSMIT-000030 | NA | Trade Partner | ISSUE FOR CONSTRUCTION - REV C2 following endorsement | 80 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 605 | 2026-07-23 |  | NA | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-003194 | Closed | 80 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-20 | WDes-TRANSMIT-000057 | NA | Consultant | Civil - Public Domain - Issued for Approval | 56 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 604 | 2026-07-23 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-20 | PCForm-TRANSMIT-000091 | NA | Trade Partner | IFC Stair Form - Updated Handrail | 27 | 0 | 0 | KPTG-IntCorr-001032 | APPROVED |  | NA | NA |  |  | IFC - Michael to advise - KPTG-IntCorr-001032 no review, Just distribute :KPTG-TRANSMIT-002886 |  | 2026-07-21 | KPTG-TRANSMIT-002886 | Closed | 27 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-20 | Auscool-TRANSMIT-000066 | NA | Trade Partner | : Sample Sheet Smoke Dampers | 0 | 1 | 0 | KPTG-IntCorr-001031 | APPROVED | 2026-07-21 | WF-000732 | NA | 2026-07-28 |  | Kapitol to advise: KPTG-IntCorr-001031 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-20 | Auspan-TRANSMIT-000521 | NA | Trade Partner | Precast shop drawings for approval. Levels 4, 5, 6 zone 4, 5. | 1 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 1528 | 2026-07-27 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-003166 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-20 | WilsonPD-TRANSMIT-000116 | NA | Trade Partner | Syfonic drainage-ground level plan stage 9 | 1 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 1469 | 2026-07-23 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-005925 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-20 | WilsonPD-TRANSMIT-000117 | NA | Trade Partner | syfonic drainage-Level 1- stage 9 | 1 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 1469 | 2026-07-23 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-005929 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-20 | WilsonPD-TRANSMIT-000118 | NA | Trade Partner | syfonic draiange Roof Plan-Stage 9 | 1 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 1469 | 2026-07-23 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-005933 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-20 | WilsonPD-TRANSMIT-000119 | NA | Trade Partner | syfonic drainage elevation stage 9 | 1 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 1469 | 2026-07-23 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-005937 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-16 | Entire M-TRANSMIT-000033 | NA | Trade Partner | Mechanical Springs and Mounts Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-01-16 | WF-003836 |  | 2026-01-29 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-20 | WilsonPD-TRANSMIT-000120 | NA | Trade Partner | Valves tech data for construction | 0 | 5 | 0 | NA | APPROVED |  | NA | NA |  |  | IFCs, No review required. Distributed to the project team. |  | 2026-07-20 | KPTG-TRANSMIT-005779 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-20 | RDSBIM-TRANSMIT-000087 | NA | Trade Partner | : 671CHP ¦ LEVEL 03 CONCRETE PROFILE KEYPLAN AND SECTION | 3 | 0 | 0 | KPTG-IntCorr-001004 | APPROVED | 2026-07-21 | NA | 668 | 2026-07-29 |  | Kapitol PC to KPTG-IntCorr-001004 | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-001409 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-20 | POTTSENG-TRANSMIT-000035 | NA | Trade Partner | : 671C: HYDRAULIC SERVICES - LEVELS 05-11 - PENETRATION LAYOUTS | 7 | 0 | 0 | KPTG-IntCorr-001005 | APPROVED | 2026-07-23 | NA | 683 | 2026-07-29 |  | Kapitol PC to KPTG-IntCorr-001005 ACC review is voided update the review team as advised by Tayla. | 2026-07-31 | 2026-07-31 | NA | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-20 | PROLMC-TRANSMIT-000007 | NA | Trade Partner | Updated Sample Datasheets | 0 | 2 | 0 | NA | APPROVED | 2026-07-20 | WF-001281 | NA | 2026-07-23 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-006064 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-20 | Ardon-TRANSMIT-000014 | NA | Trade Partner | Door Hardware Schedule Stage 9 - Detail Door Hardware | 0 | 1 | 0 | NA | APPROVED | 2026-07-20 | WF-001283 | NA | 2026-07-29 |  | Workflow has been terminated as requested by Project coordinator, and revised doc is submitted on WF-001304 |  | 2026-07-23 | KPTG-IntCorr-001816 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-20 | ZIA-TRANSMIT-000020 | NA | Trade Partner | M2 Stage 9, 10 & 11 Sample Submission - Extended Cat6A Cable for Water Plant Equipment | 0 | 1 | 0 | NA | APPROVED | 2026-07-20 | WF-001284 | NA | 2026-07-31 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-21 | SPECAUTO-TRANSMIT-000008 | NA | Trade Partner | CSMS Outstation Hardware Procurement Approval - Moxa Modbus Gateway | 0 | 1 | 0 | NA | APPROVED | 2026-07-22 | WF-000342 | NA | 2026-08-03 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-001509 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-21 | RDSBIM-TRANSMIT-000018 | NA | Trade Partner | NXGE01 ¦ ROOF CONCRETE PROFILE KEY PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 375 | 2026-07-27 |  | Terminated as advised by Caitlin Grimmet for submitting the updated documents. | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-001254 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-21 | Nilsen3-TRANSMIT-000075 | NA | Trade Partner | Nilsen Sample submissions #12 | 0 | 1 | 0 | NA | APPROVED | 2026-07-21 | WF-001286 | NA | 2026-07-31 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-006083 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-16 | SMEPS-TRANSMIT-000142 | NA | Trade Partner | :22KV - Sample register and submittals | 0 | 4 | 0 | NA | APPROVED | 2026-01-16 | WF-003837 |  | 2026-01-29 |  |  |  | 2026-01-29 | KPTG-TRANSMIT-012161 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-21 | DLTS-TRANSMIT-000059 | NA | Trade Partner | S11-Cooling Tower Grating-IFA Issue | 70 | 0 | 0 | NA | APPROVED | 2026-07-21 | WF-001287 | NA | 2026-07-30 |  |  | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-005995 | Closed | 70 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-21 | JCBa-TRANSMIT-000156 | NA | Trade Partner | Updated Architectural Documentation - Detail RCPs & Common Area Joinery Details | 2 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 1533 | 2026-07-23 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-003058 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | PCForm-TRANSMIT-000279 | NA | Trade Partner | Stair Form B3 - For Approval | 2 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 992 | 2026-07-29 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-003569 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-21 | Auspan-TRANSMIT-000524 | NA | Trade Partner | Resubmit precast shop drawings for approval. Panel 4P5058 | 2 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 1535 | 2026-07-28 |  | 1 Drawing already terminated | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003095 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-21 | NXES-TRANSMIT-000062 | NA | Trade Partner | Re: Ground Floor Low Level Lighting, Power & Comms Layout | 2 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 706 | 2026-07-28 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | PCForm-TRANSMIT-000275 | NA | Trade Partner | IFC Stair Form - Building A | 16 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | rejected |  | 2026-07-20 | KPTG-TRANSMIT-002992 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | L.E.S.-TRANSMIT-000027 | NA | Trade Partner | Exit and Emergency Data sheets | 0 | 9 | 0 | NA | APPROVED | 2026-07-20 | WF-000995 | NA | 2026-07-23 |  |  | 2026-08-13 | 2026-08-14 | WF-001154 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | PCForm-TRANSMIT-000276 | NA | Trade Partner | Level 4 Shear | 1 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 990 | 2026-07-27 |  |  | 2026-07-28 | 2026-07-29 | KPTG-TRANSMIT-003154 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-16 | Syfon1-TRANSMIT-000006 | NA | Trade Partner | Syfon's full set of shop drawing of Stage 4, issued for approval | 11 | 0 | 0 | NA | REJECTED | [5 empty] | The drawings have been returned to the originator to update the revision number. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | PCForm-TRANSMIT-000277 | NA | Trade Partner | IFC Stair Form - Building A2 and B | 12 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | rejected |  | 2026-07-20 | KPTG-TRANSMIT-002995 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | PCForm-TRANSMIT-000278 | NA | Trade Partner | Level 4 formwork design plan and section update | 2 | 0 | 2 | KPTG-IntCorr-001029 | APPROVED | [5 empty] | Clarification from jarrod |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-21 | Stowe-A-TRANSMIT-000661 | NA | Trade Partner | As Builts - Facility IT Structured Cabling Reticulation Drawings | 9 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 4416 | 2026-07-24 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020175 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-21 | SMEPS-TRANSMIT-000243 | SPARK-CRFI-KPG-000309 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0201,0202,0203,0204,0205,0206,0207,0208 | 8 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 362 | 2026-07-28 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-21 | KALLIBRE-TRANSMIT-000029 | NA | Trade Partner | IFC - Extra 7x frames (resub) | 7 | 0 | 0 | NA | APPROVED | 2026-07-21 | WF-000404 | NA | 2026-07-24 |  |  | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-001101 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-21 | RDSBIM-TRANSMIT-000229 | NA | Trade Partner | LINDRUM ¦ LEVEL 05 PARTITION WALL LAYOUT | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  | 2026-07-21 | 2026-07-21 | KPTG-IntCorr-001221 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-21 | KPTG-IntCorr-000588 | NA | Trade Partner | Generator EPMS FAT | 0 | 4 | 0 | NA | APPROVED | 2026-07-21 | WF - 000549 | NA | 2026-07-27 |  | NA | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-001143 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-21 | ZIA-TRANSMIT-000130 | NA | Trade Partner | Re: M3 Stage 4 - IP Device Register | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | From Kate: yes I have to send it to all trades first for review |  | 2026-07-21 | KPTG-TRANSMIT-019834 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-21 | D&E-TRANSMIT-000928 | NA | Trade Partner | Fwd: NXM3S4 - Level 1 - Builders Works Layout - Zone 1 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-21 | KPTG-TRANSMIT-019833 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-20 | BVPI-TRANSMIT-000010 | NA | Trade Partner | BVPI-CxL4-ELEC-FPT -BATCH 2 - Revision 0 | 0 | 1 | 0 | NA | APPROVED | 2026-01-16 | WF-000876 | NA | 2026-01-23 |  |  | 2026-01-27 | 2026-01-28 | KPTG-TRANSMIT-002347 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-21 | SMEPS-TRANSMIT-000244 | SPARK-CRFI KPG-000302 | Trade Partner | Re: NEL-CNT-SME-2801-BSE-SDG-0187,0188,0190 | 3 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 363 | 2026-07-28 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-001483 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-21 | Arc Plas-TRANSMIT-000004 | NA | Trade Partner | Re: *Updated Acoustic Infill - Shop Drawing | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-07-21 | KPTG-DA-007668 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-21 | NXT-TRANSMIT-001666 | NA | Client | M3S4 Ring 4,5 & 6 L1 check reports (x12 units) | 0 | 12 | 0 | NA | APPROVED | [5 empty] | FOR DISTRIBUTION |  | 2026-07-21 | KPTG-TRANSMIT-019836 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-21 | WGAVIC-TRANSMIT-000010-SME | NA | Consultant | Grading and Stormwater Drawings and Certificate - Issued for Construction | 12 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 474 | 2026-07-24 |  |  | 2026-07-23 | 2026-07-24 | KPTG-TRANSMIT-000698 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-21 | Arc Plas-TRANSMIT-000005 | NA | Trade Partner | Re: *Updated File - Acoustic Infill Panel - Shop Drawing | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-07-21 | KPTG-DA-007669 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-21 | MAYFLD-TRANSMIT-000469 | NA | Trade Partner | 100222-000611: M3 Stage 2 - Baseframe Fire Rating As Built Drawings | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: No IFC has Issued, Requested to submit:KPTG-SADV-006755 |  | 2026-07-21 | KPTG-SADV-006755 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-21 | Axiom-TRANSMIT-000008 | NA | Trade Partner | VMU Drawings ME12 Option 1 | 2 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 996 | 2026-07-30 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-003017 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-21 | RDSBIM-TRANSMIT-000231 | NA | Trade Partner | Re: LINDRUM ¦LEVEL 06 PARTITION WALL LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 707 | 2026-07-24 |  |  | 2026-08-11 | 2026-08-11 | KPTG-SADV-005265 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-21 | Auspan-TRANSMIT-000525 | NA | Trade Partner | Precast shop drawings for approval. Zone 1, 2 level 6 | 87 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 1537 | 2026-07-28 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-21 | Auspan-TRANSMIT-000525 | NA | Trade Partner | Precast shop drawings for approval. Zone 1, 2 level 6 | 12 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - Difference in document no, title, revision and status. DRAFT-010243 |  | 2026-07-21 | DRAFT-010243 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-09 | RDSBIM-TRANSMIT-000174 | NA | Trade Partner | NXM3S2 ¦ GROUND FLOOR-B-G-003 ACC WC-FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-01-09 | NA | 3613 | 2026-01-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-21 | SKS Tech-TRANSMIT-000203 | NA | Trade Partner | UpRev IFC typical neutral earthing schematic | 1 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 3899 | 2026-07-30 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-30 | PCForm-TRANSMIT-000257 | NA | Trade Partner | Level 2 - Construction status | 4 | 0 | 0 | NA | APPROVED | 2026-07-01 | NA | 882 | 2026-07-21 |  | KPTG-TRANSMIT-002608 | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-003000 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-21 | Axiom-TRANSMIT-000009 | NA | Trade Partner | VMU Drawings ME12 Option 2 | 2 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 998 | 2026-07-30 |  |  | 2026-07-23 | 2026-07-24 | KPTG-TRANSMIT-003035 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-21 | SMEPS-TRANSMIT-000076 | NA | Trade Partner | Typical Switch room AUX-DB (MA-PF) | 0 | 3 | 0 | NA | APPROVED | 2026-07-21 | WF-001291 | NA | 2026-07-31 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-006433 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-21 | TATE_-TRANSMIT-000006 | NA | Trade Partner | MYWCCB - Tate - IFA - Shop Drawings | 2 | 0 | 0 | KPTG-IntCorr-003643 | REJECTED | [5 empty] | Drawing number is incorect |  | 2026-07-24 | KPTG-TRANSMIT-001494 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-21 | Arc Plas-TRANSMIT-000006 | NA | Trade Partner | Re: Updated Doc No. Acoustic Infill - Shop Drawing | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect title |  | 2026-07-21 | KPTG-DA-007672 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-21 | LNCPPL-TRANSMIT-000018 | NA | Trade Partner | Hydraulic Shop Drawings - Site Plan | 1 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 380 | 2026-07-27 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-001249 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-21 | SKS Tech-TRANSMIT-000202 | NA | Trade Partner | Schematics overall LV and typical PDU | 2 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 3901 | 2026-07-30 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-021037 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-21 | Auspan-TRANSMIT-000523 | NA | Trade Partner | Update marking plans for zone 3. Ground floor and level 2 | 2 | 0 | 0 | KPTG-IntCorr-001039 | APPROVED | [5 empty] | IFC - Waiting for Kim advise - KPTG-IntCorr-001039 IFC - Update register and Transmit. KPTG-TRANSMIT-002890 |  | 2026-07-22 | KPTG-TRANSMIT-002890 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-21 | LNCPPL-TRANSMIT-000019 | NA | Trade Partner | Fire Shop Drawings - Site Inground | 1 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 383 | 2026-07-27 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001401 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-11-20 | Kone-VIC-TRANSMIT-000014 | NA | Trade Partner | Updated Lift Car Interior Drawings Lifts 1 to 4 | 4 | 0 | 0 | NA | APPROVED | 2025-11-21 | NA | 453# | 2025-11-28 |  |  | 2025-12-02 | 2025-12-02 | KPTG-SADV-002324 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-09 | RDSBIM-TRANSMIT-000175 | NA | Trade Partner | NXM3S2 ¦ GROUND FLOOR-B-G-082 FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-01-09 | NA | 3613 | 2026-01-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-21 | SMEPS-TRANSMIT-000040 | Na | Trade Partner | Re Legend & Symbols (TEL) FOA-2 | 1 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 384 | 2026-07-30 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-001357 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | INGEN3D-TRANSMIT-000210 | NA | Trade Partner | Level 11-13 - Precast Columns - Revised IFC (20-07-2026) | 12 | 0 | 0 | KPTG-TRANSMIT-003002 | APPROVED | [5 empty] | Clarification from Nicholas - Confirmed send to all parties by Email |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | L.E.S.-TRANSMIT-000028 | NA | Trade Partner | Emergency lighting lux plots | 17 | 0 | 0 | KPTG-IntCorr-001031 | APPROVED | 2026-07-23 | NA | 1020 | 2026-07-30 |  | Clarification from John - Requested AGI Files along with PDF - processed on 23/07 | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-003602 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | L.E.S.-TRANSMIT-000029 | NA | Trade Partner | Ground Floor Power and Comms, Horizontal Penetration IFA | 4 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 994 | 2026-07-28 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-003483 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | Jangho-TRANSMIT-000258 | NA | Trade Partner | Sliding Door handle examples | 0 | 1 | 0 | NA | APPROVED | 2026-07-21 | WF-000997 | NA | 2026-08-04 |  |  | 2026-08-13 | 2026-08-14 | KPTG-TRANSMIT-003410 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | Jangho-TRANSMIT-000259 | NA | Trade Partner | Level 4 formwork design plan and section update | 0 | 1 | 0 | NA | APPROVED | 2026-07-21 | WF-000998 | NA | 2026-08-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | Jangho-TRANSMIT-000260 | NA | Trade Partner | Weather Sealant Sample Submission (Weather Sealant Sample-Dark Grey) | 0 | 1 | 0 | NA | APPROVED | 2026-07-21 | WF-000999 | NA | 2026-08-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-20 | INGEN3D-TRANSMIT-000209 | NA | Trade Partner | Level 4 formwork design plan and section update | 11 | 0 | 0 | NA | APPROVED | 2026-07-21 | WF-001005 | NA | 2026-07-28 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003263 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-21 | Auspan-TRANSMIT-000522 | NA | Trade Partner | Update IFC panel 4P320 | 1 | 0 | 0 | KPTG-IntCorr-001040 | APPROVED | [5 empty] | IFC - Waiting for Kim advise - KPTG-IntCorr-001040 this rev is already in the doc register, no need to transmit. KPTG-IntCorr-001054 |  | 2026-07-22 | KPTG-IntCorr-001054 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-21 | Arc Plas-TRANSMIT-000003 | NA | Trade Partner | Acoustic Infill Shop Drawings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Reference number, title, revision, not mentioned inside document. |  | 2026-07-21 | KPTG-DA-007676 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-09 | RDSBIM-TRANSMIT-000176 | NA | Trade Partner | NXM3S2 ¦ GROUND FLOOR B-G-096 & B-G-014 FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED |  | NA | 3615 | 2026-01-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-21 | Auspan-TRANSMIT-000528 | NA | Trade Partner | Precast shop drawings for construction. Level 4, 5 | 5 | 0 | 0 | KPTG-IntCorr-001043 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise- KPTG-IntCorr-001043 2 are OK to transmit -KPTG-TRANSMIT-003002 3 are rejected by PC KPTG-IntCorr-001156 |  | 2026-07-29 | KPTG-TRANSMIT-003002 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-21 | Entire M-TRANSMIT-000069 | NA | Trade Partner | CHW, CCW, IDW Pipe, Valves & Fittings | 0 | 1 | 0 | NA | APPROVED | 2026-07-21 | WF-000348 | NA | 2026-08-03 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001346 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-21 | ADP-TRANSMIT-000123 | NA | Consultant | ADP MEL4780 - Updated Lighting drawing and Reg126 | 1 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 386 | 2026-07-30 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-001258 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-21 | Aurecon-TRANSMIT-000141 | NA | Consultant | Services Specification Schedules - LOD300 Issued for Contract | 0 | 10 | 0 | NA | REJECTED | [5 empty] | Wrong Naming Convention |  | 2026-07-21 | Awaiting approval | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-21 | ADP-TRANSMIT-000124 | NA | Consultant | ADP MEL4680 - Electrical Reg 126 | 0 | 1 | 0 | NA | APPROVED | 2026-07-21 | NA | 388 | 2026-07-30 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-001242 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-21 | ARCST-TRANSMIT-000348 | NA | Trade Partner | C3 Cooling Tower Handrails & Grating - Issued for Construction | 187 | 0 | 0 | NA | APPROVED | 2026-07-21 | WF-006445 | NA | 2026-07-23 |  | As instructed by Lola in KPTG-IntCorr-016528 |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-21 | RDSBIM-TRANSMIT-000230 | NA | Trade Partner | Re: LINDRUM ¦ LEVEL 05 PARTITION WALL LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 708 | 2026-07-24 |  |  | 2026-08-11 | 2026-08-11 | KPTG-SADV-005264 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-21 | ARCST-TRANSMIT-000346 | NA | Trade Partner | C2 Cooling Tower Grating - Issued for Construction | 154 | 0 | 0 | NA | APPROVED | 2026-07-21 | WF-006446 | NA | 2026-07-29 |  | As instructed by Lola KPTG-IntCorr-016529 |  |  |  | Open | 154 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-21 | SMEPS-TRANSMIT-000245 | NA | Trade Partner | NEL-CNT-SME-2801-BSE-SCH-0005,0006,NEL-CNT-SME-2801-BSE-SDG-0129,0130,0131,0201,0202,0203,0204,0205,0206,0207,0208,0301,0302,0303,0304,0314 | 18 | 0 | 0 | NA | REJECTED | [5 empty] | Same revision already received |  | 2026-07-21 | KPTG-TRANSMIT-001476 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-21 | MAYFLD-TRANSMIT-000471 | NA | Trade Partner | 100222-000613: M3 Stage 2 - LIGHTING CONTROL SYSTEM - As Built Drawings | 3 | 0 | 0 | NA | APPROVED | [5 empty] | FOR DSITRIBUTION ONLY |  | 2026-07-21 | KPTG-TRANSMIT-019839 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-09 | RDSBIM-TRANSMIT-000177 | NA | Trade Partner | NXM3S2 ¦ LEVEL 01 B-1-024 MALE WC-FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-01-09 | NA | 3615 | 2026-01-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-21 | MAYFLD-TRANSMIT-000470 | NA | Trade Partner | 00222-000612: M3 Stage 2 - Baffle Panels "Cancelled" Rev B Drawings - For information | 2 | 0 | 0 | NA | REJECTED | [5 empty] | "cancel" in this transmittal? Does it mean that only this particular revision has been cancelled, or does it indicate that the drawing is no longer in use |  | 2026-07-21 | KPTG-SADV-006760 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-21 | SMEPS-TRANSMIT-000246 | SPARK-CRFI-KPG-000284 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0033 | 1 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 364 | 2026-07-28 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-001661 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-21 | WDes-TRANSMIT-000058 | NA | Consultant | Brick wall sections - | 6 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 606 | 2026-07-23 |  | NA | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-003188 | Closed | 6 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-21 | Altaire-TRANSMIT-000125 | NA | Trade Partner | NEXTDC M3S4 - Dry Fire Shop Drawings (For Construction) | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Revision is incorrect |  | 2026-07-21 | KPTG-DA-007680 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-21 | SMEPS-TRANSMIT-000247 | SPARK-CRFI KPG-000340 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0001,0105,0107 | 3 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 365 | 2026-07-28 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-001479 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-21 | SMEPS-TRANSMIT-000077 | NA | Trade Partner | M2 - Cable Cleat / Anchors | 0 | 2 | 0 | NA | APPROVED | 2026-07-21 | WF-001293 | NA | 2026-07-31 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-006161 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-21 | Arc Plas-TRANSMIT-000007 | NA | Trade Partner | Updated - Acoustic Panel Plan Shop Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 3905 | 2026-07-30 |  | As instructed by Finn J - Terminated (need to supersede with updated drawing) |  | 2026-07-30 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-21 | SMEPS-TRANSMIT-000249 | SPARK-CRFI-KPG-000291 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-1101,1104,1105,1106 | 4 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 366 | 2026-07-28 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-001481 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-14 | KPTG-IntCorr-001708 | NA | Trade Partner | ORISE CX DOCS | 0 | 8 | 0 | NA | APPROVED | 2026-07-20 | WF-001169 | NA | 2026-07-23 |  | 8 docs locked in w/flows - wf -1148 released | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-004187 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-21 | KBGA-TRANSMIT-000007 | NA | Trade Partner | Strompro tech data for approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-21 | NA | 476 | 2026-07-29 |  | KBGA-TRANSMIT-000004 superseded | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-000840 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-09 | RDSBIM-TRANSMIT-000180 | NA | Trade Partner | NXM3S2 ¦ GROUND FLOOR-B-G-097 CLEANERS-FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-01-12 | NA | 3620 | 2026-01-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-21 | KBGA-TRANSMIT-000008 | NA | Trade Partner | UPVC/DWV tech data for approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-21 | NA | 479 | 2026-07-29 |  | KBGA-TRANSMIT-000005 superseded | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-000839 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-21 | KALLIBRE-TRANSMIT-000017 | NA | Trade Partner | TEC - Urinal divider | 0 | 1 | 0 | NA | APPROVED | 2026-07-21 | WF - 001092 | NA | 2026-07-27 |  | NA | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-003212 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-14 | KPTG-IntCorr-001706 | NA | Trade Partner | PARRATECH CX DOCS | 0 | 1 | 0 | NA | APPROVED | 2026-07-20 | WF-001167 | NA | 2026-07-23 |  | 1 pending locked in a workflow - WF-001037 released |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-21 | SMEPS-TRANSMIT-000041 | NA | Trade Partner | Tech Data - Electrical | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Rejected: Revision of a Tech Data needs to be updated: |  | 2026-07-21 | KPTG-SADV-000988 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-21 | INTRFRM-TRANSMIT-000105 | NA | Trade Partner | Geelong Edge - Civil Tech Data (Submission 7) | 0 | 1 | 0 | NA | APPROVED | 2026-07-21 | WF-000351 | NA | 2026-07-30 |  |  | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-001272 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-21 | JAZBC-SUBADVICE-000042 | NA | Trade Partner | GE1-BCA-JAZ-REP-A-0100-R03 Updated BCA Report | 0 | 1 | 0 | NA | REJECTED | [5 empty] | above submission does not comply with the document control standards |  | 2026-07-21 | KPTG-SADV-000985 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-21 | EAEGROUP-TRANSMIT-000116 | NA | Trade Partner | Re: EAE-FAT TEST REPORTS_M3 STAGE 4_BINDER_2026.07.21 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-07-14 | KPTG-TRANSMIT-019859 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-21 | JCBa-TRANSMIT-000275 | NA | Consultant | Building Permit - L00 Breezeway Ramps | 6 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 607 | 2026-07-23 |  | NA | 2026-07-27 | 2026-07-27 | KPTG-SADV-008274 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-21 | EAEGROUP-TRANSMIT-000115 | NA | Trade Partner | Updated Shop Drawing Revision - UMTD-USB (FF ) INTECONN AND (FG) | 1 | 0 | 0 | NA | APPROVED | 2026-07-21 | WF-006450 | NA | 2026-08-03 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-020533 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-21 | PCForm-TRANSMIT-000283 | NA | Trade Partner | level 5 and 6 reissued IFC stamp | 2 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 1002 | 2026-07-27 |  |  | 2026-08-10 | 2026-08-14 | KPTG-TRANSMIT-003441 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-16 | ARCST-TRANSMIT-000182 | NA | Trade Partner | C3 Switchroom Upper Gantry Handrail - Issued for Approval | 39 | 0 | 0 | NA | APPROVED | 2026-01-16 | WF-003838 |  | 2026-02-02 |  |  |  | 2026-02-23 | KPTG-TRANSMIT-013300 | Closed | 39 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-21 | Axiom-TRANSMIT-000012 | NA | Trade Partner | VMU Drawings ME11 - Issued for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 1000 | 2026-07-27 |  |  | 2026-07-23 | 2026-07-24 | KPTG-TRANSMIT-003038 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-21 | Axiom-TRANSMIT-000010 | NA | Trade Partner | VMU Drawings ME11 - Issued for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 1000 | 2026-07-27 |  |  | 2026-07-23 | 2026-07-24 | KPTG-TRANSMIT-003040 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-14 | KPTG-IntCorr-001705 | NA | Trade Partner | PARRATECH CX DOCS | 0 | 11 | 0 | NA | APPROVED | 2026-07-14 | WF-001156 | NA |  |  | 1 doc - no action, 5 pending locked in w/flow - (WF-001147) | 2026-07-16 | 2026-07-23 | KPTG-TRANSMIT-004137 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-14 | KPTG-IntCorr-001705 | NA | Trade Partner | PARRATECH CX DOCS | 0 | 5 | 0 | NA | APPROVED | 2026-07-20 | WF-001168 | NA |  |  | 1 doc - no action, 5 pending locked in w/flow - (WF-001147) released | 2026-07-16 |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-21 | TTW-TRANSMIT-000198 | NA | Consultant | M3 Stage 1 Civil Drawing - HVM Bollards | 1 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 4420 | 2026-07-23 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-21 | Altaire-TRANSMIT-000126 | NA | Trade Partner | NEXTDC M3S4 - Dry Fire Shop Drawings (For Construction) (3) | 3 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 3907 | 2026-07-30 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-21 | SMEPS-TRANSMIT-000248 | NA | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0010,0029,0187,0188,0190 | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Same revision already received and in bim360review |  | 2026-07-21 | KPTG-TRANSMIT-001477 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-21 | PCForm-TRANSMIT-000281 | NA | Trade Partner | Stair Form Building A - transmittal fix | 9 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 1004 | 2026-07-27 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-003356 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-21 | KBGA-TRANSMIT-000009 | NA | Trade Partner | HDPE tech data for approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-21 | NA | 481 | 2026-07-29 |  | KBGA-TRANSMIT-000006 superseded | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-000852 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-21 | DLTS-TRANSMIT-000064 | NA | Trade Partner | S9-Link Bridge Roof-IFA Issue | 8 | 0 | 0 | NA | APPROVED | 2026-07-21 | WF-001294 | NA | 2026-07-30 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-006060 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-16 | Syfon1-TRANSMIT-000007 | NA | Trade Partner | Syfon's full set of shop drawings (with revised revision numbers) of Stage 4, issued for approval | 11 | 0 | 0 | NA | APPROVED | 2026-01-16 |  | 1789 | 2026-01-26 |  |  |  | 2026-02-18 | KPTG-TRANSMIT-013111 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-21 | SES AU-TRANSMIT-000004 | NA | Trade Partner | Security Shop Drawings | 25 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 1478 | 2026-07-28 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-006291 | Closed | 25 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-16 | INTERSIG-TRANSMIT-000010 | NA | Trade Partner | Assemble Coburg - WAYFINDING SIGNAGE - S.101, S.102, S.103, S.201 | 4 | 0 | 0 | NA | APPROVED | 2026-07-16 | WF - 001085 | NA | 2026-07-21 |  | NA | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-003168 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-21 | SKS Tech-TRANSMIT-000198 | NA | Trade Partner | ITP for Earth Grid Injection | 0 | 1 | 0 | NA | APPROVED | 2026-07-21 | WF-001170 | NA | 2026-07-23 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-004189 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-21 | WGAVIC-TRANSMIT-000010-CER | NA | Consultant | Grading and Stormwater Drawings and Certificate - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated on ACC |  | 2026-07-21 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-21 | Aurecon-TRANSMIT-000136 | NA | Consultant | Documents No Longer in Use | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer in use |  | 2026-07-21 | KPTG-TRANSMIT-000635 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-21 | Aurecon-TRANSMIT-000139 | NA | Consultant | Documents No Longer in Use | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer in Use |  | 2026-07-21 | KPTG-TRANSMIT-000639 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-21 | Highbu-TRANSMIT-000059 | NA | Trade Partner | HPS-HY-SMP-048 & HPS-HY-SMP-049 - S/S pipe & fittings for CW & RW water mains for approval | 0 | 2 | 0 | KPTG-IntCorr-001227 | APPROVED | 2026-07-22 | WF-000851 | NA | 2026-07-24 |  | KPTG-IntCorr-001227 - Requested guidance ,but no responance yet | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-002783 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-21 | NXT-TRANSMIT-000447 | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 06 - HDR, AURECON, TTW, 4DW, ARUP, Eukai, LAT, SCG, A&A, dCC. | 895 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Already submitted-736 |  | 2026-07-21 | NA | Closed | 863 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-21 | Auspan-TRANSMIT-000527 | NA | Trade Partner | Precast shop drawings for construction. Level 3 | 113 | 0 | 0 | KPTG-IntCorr-001044 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise- KPTG-IntCorr-001044 85 are OK to proceed - Registered & transmit - KPTG-TRANSMIT-002920 28 are to be revised - KPTG-SADV-003622 |  | 2026-07-22 | KPTG-TRANSMIT-002920 | Closed | 113 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-16 | RDSBIM-TRANSMIT-000192 | NA | Trade Partner | NXM3S4 ¦ GROUND FLOOR-C-G-054 ACC WC (RH) FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-01-16 |  | 1791 |  |  |  |  | 2026-01-20 | KPTG-TRANSMIT-011707 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-21 | Auscool-TRANSMIT-000111 | NA | Trade Partner | BASEMENT SHOP DRAWING UPDATE | 2 | 0 | 0 | KPTG-IntCorr-001228 | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001228 - Requested guidance ,but no responance yet KPTG-IntCorr-001243 - As per direction from Mark, we only update register and distribute to IGS and FJC . | 2026-07-23 | 2026-07-23 | KPTG-IntCorr-001243 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-21 | Auspan-TRANSMIT-000526: | NA | Trade Partner | Precast shop drawings for construction. Level 2 | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Kim to advise KPTG-IntCorr-001042 No Action required. KPTG-IntCorr-001046 |  | 2026-07-21 | KPTG-IntCorr-001046 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-21 | Auspan-TRANSMIT-000527 | NA | Trade Partner | Precast shop drawings for construction. Level 3 | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected - QA issues in revision. DRAFT-01025 |  | 2026-07-21 | DRAFT-01025 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-21 | Auspan-TRANSMIT-000529 | NA | Trade Partner | Precast shop drawings for construction | 8 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC -As advised by KIM, Register and Transmit KPTG-IntCorr-001037. Registered and Transmitted - KPTG-TRANSMIT-002878 |  | 2026-07-21 | KPTG-TRANSMIT-002878 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-21 | Auscool-TRANSMIT-000067 | NA | Trade Partner | : Basement - IFC Drawings | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Zone 2 to 5 are Ok to update register and transmit. Zone 1 is on hold - KPTG-TRANSMIT-002881 |  | 2026-07-21 | KPTG-TRANSMIT-002881 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-21 | Auscool-TRANSMIT-000067 | NA | Trade Partner | : Basement - IFC Drawings | 1 | 0 | 1 | KPTG-TRANSMIT-002881 | APPROVED |  | NA | NA |  |  | Zone 1 is on hold - KPTG-TRANSMIT-002881 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-21 | M.2-TRANSMIT-000066 | NA | Trade Partner | 12 Pole DB Tech Data | 0 | 2 | 0 | KPTG-IntCorr-001048 | APPROVED | 2026-07-22 | WF-000737 | NA | 2026-07-28 |  | Kapitol PC to advise -KPTG-IntCorr-001048 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-21 | Auspan-TRANSMIT-000530 | NA | Trade Partner | Precast panel 2P4057 for construction. | 1 | 0 | 0 | KPTG-IntCorr-001041 | APPROVED |  | NA | NA |  |  | IFC Kim to advise KPTG-IntCorr-001041 IFC update and Transmit KPTG-TRANSMIT-002930 |  | 2026-07-23 | KPTG-TRANSMIT-002930 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-21 | fjc-TRANSMIT-000170 | NA | Consultant | Drawing Updates | 12 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 709 | 2026-07-24 |  | KPTG-SADV-005035 - 12 Drawings received 1 drawing rejected. because NO LONGER IN USE KPTG-IntCorr-001229 - As per direction from Ashlin, we transmit to RDS KPTG-IntCorr-001232 - As per direction from Ashlin,we have unlocked the drawings. | 2026-07-23 | 2026-07-23 | KPTG-SADV-005062 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-21 | Arc Plas-TRANSMIT-000019 | NA | Trade Partner | Revised INS-03/04 - Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-07-21 | WF-001289 | NA | 2026-07-24 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-005888 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-16 | SMEPS-TRANSMIT-000004 | NA | Trade Partner | SME Shop Drawing Review Lighting and Power | 8 | 0 | 0 | NA | APPROVED | 2026-01-16 | WF-000009 | NA | 2026-01-22 |  | Revise and Resubmit documents | 2026-02-03 | 2026-02-03 | KPTG-TRANSMIT-000073 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-21 | Nilsen3-TRANSMIT-000074 | NA | Trade Partner | Nilsen Sample submissions #7 | 0 | 2 | 0 | NA | APPROVED | 2026-07-21 | WF-001267 | NA | 2026-07-24 |  |  | 2026-07-21 | 2026-07-21 | KPTG-TRANSMIT-005833 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-21 | RDSBIM-TRANSMIT-000016 | NA | Trade Partner | GROUND FLOOR RCP KEY PLAN ¦ LAYOUT | 5 | 0 | 0 | NA | APPROVED | 2026-07-21 | NA | 1480 | 2026-07-23 |  |  | 2026-08-17 | 2026-08-17 | KPTG-SADV-007649 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-21 | ELLISAIR-SUBADVICE-000011 | NA | Trade Partner | PBDB - Reduction of insulation thickness - refrigerated pipework | 0 | 1 | 0 | NA | APPROVED | 2026-07-21 | WF-001292 | NA | 2026-07-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-21 | ELLISAIR-TRANSMIT-000132 | NA | Trade Partner | NextDC Stage 9-11 Fire Matrix | 0 | 6 | 0 | NA | APPROVED | 2026-07-21 | WF-001296 | NA | 2026-07-29 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-006667 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-22 | Jangho-TRANSMIT-000261 | NA | Trade Partner | Re: FT01&FT02 PMU Comparison Report | 0 | 1 | 0 | NA | APPROVED | 2026-07-22 | WF-001015 | NA | 2026-07-28 |  | DIFFERENCE IN TITLE AND NO REVISION HISTORY BOX - as per xavier's teams' message - forwarded for TTW approval | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-003087 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-22 | PCForm-TRANSMIT-000284 | NA | Trade Partner | Fwd: Consep Hoist IFC Drawings | 28 | 0 | 0 | NA | REJECTED | [5 empty] | Difference in the document attached |  | 2026-07-22 | DRAFT-014303 | Closed | 28 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-22 | TATE_-TRANSMIT-000035 | NA | Trade Partner | Brush Seal Tech Data | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected: Revision mismatched:KPTG-IntCorr-000709 |  | 2026-07-22 | KPTG-IntCorr-000709 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-22 | RDSBIM-TRANSMIT-000230 | NA | Trade Partner | BATHROOM TYPE BB-01 FINISHES LAYOUT & ELEVATIONS (TYPICAL) | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | NA |  | 2026-07-22 | KPTG-TRANSMIT-003170 | Open | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-22 | SMEPS-TRANSMIT-000250 | SPARK-CRFI-KPG-000235 & SPARK-CRFI-KPG-000284 | Trade Partner | SMEPS-TRANSMIT-000250 | 2 | 0 | 0 | NA | APPROVED | 2026-07-22 |  | 367 | 2026-07-29 |  |  | 2026-07-24 | 2026-07-27 | KPTG-TRANSMIT-001500 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-22 | SIL-TRANSMIT-000029 | NA | Trade Partner | BD2 Busway above rack routing - COLO4-5 Rev C | 0 | 1 | 0 | NA | APPROVED | 2026-07-22 | WF-000406 | NA | 2026-07-24 |  |  | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-001106 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-16 | ARCST-TRANSMIT-000181 | NA | Trade Partner | C3 Switchroom Upper Gantry Grating - Issued for Approval | 73 | 0 | 0 | NA | APPROVED | 2026-01-16 | WF-003840 |  | 2026-02-02 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-017031 | Closed | 72 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-22 | TATE_-TRANSMIT-000036 | NA | Trade Partner | Brush Seal Performance | 0 | 1 | 0 | NA | REJECTED | [5 empty] | KPTG-IntCorr-000710:Rejected: DOCUMENT STATUS NEEDS CORRECTION:KPTG-IntCorr-000710 |  | 2026-07-22 | KPTG-IntCorr-000710 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-22 | Entire M-TRANSMIT-000070 | NA | Trade Partner | FOA-3 OAP's | 0 | 1 | 0 | NA | APPROVED | 2026-07-22 | WF-000353 | NA | 2026-08-04 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001613 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-22 | SMEPS-TRANSMIT-000251 | SPARK-CRFI KPG-000363, SPARK-CRFI-KPG-000504, SPARK-CRFI-KPG-000438 & SPARK-CRFI-KPG-000462 | Trade Partner | NEL-CNT-SME-2801-BSE-SCH-0005,006,NEL-CNT-SME-2801-BSE-SDG-01290,0130,0131,0301,0302,0303,0314 | 10 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 368 | 2026-07-29 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-001531 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-22 | D&E-TRANSMIT-000930 | NA | Trade Partner | Mechanical Dog Box Details - Issued for Approval | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rev history not mentioned |  | 2026-07-22 | KPTG-DA-007697 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-22 | JAZBC-IntCorr-000043 | NA | Trade Partner | GE1-BCA-JAZ-REP-A-0100-R03 Updated BCA Report | 0 | 1 | 0 | NA | APPROVED | [5 empty] | For updating document register only. |  | 2026-07-22 | KPTG-TRANSMIT-001220 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-22 | PARR-TRANSMIT-000216 | NA | Trade Partner | Re: P2680 - NDC M3 Stage 4 - Fuel - COC PROPOSED BUILDING WORK-PUMP ROOM REG126 | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-07-22 | KPTG-DA-007699 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-22 | RDSBIM-TRANSMIT-000232 | NA | Trade Partner | LINDRUM ¦LEVEL 07 PARTITION WALL LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 710 | 2026-07-27 |  |  | 2026-08-11 | 2026-08-11 | KPTG-SADV-005263 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-22 | Entire M-TRANSMIT-000071 | NA | Trade Partner | Mech Elec - Cable & Cable Tray | 0 | 1 | 0 | NA | APPROVED | 2026-07-22 | WF-000354 | NA | 2026-08-04 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-001800 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-22 | RDSBIM-TRANSMIT-000233 | NA | Trade Partner | LINDRUM ¦ LEVEL09 PARTITION WALL LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 711 | 2026-07-27 |  |  | 2026-08-11 | 2026-08-11 | KPTG-SADV-005262 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-22 | SMEPS-TRANSMIT-000252 | SPARK-CRFI KPG-000388 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0602 | 1 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 369 | 2026-07-29 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001538 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-16 | D&E-TRANSMIT-000079 |  | Trade Partner | MWYCCB - GROUND LEVEL DUCTWORK & PENETRATION LAYOUT ZONES - Issued For Construction | 8 | 0 | 0 | NA | APPROVED | 2026-01-16 | WF-000121 | 92 | 2026-01-23 |  | WF terminated- To update latest revision as per Alex advice - KPTG-IntCorr-002480 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-22 | VERTIV-TRANSMIT-000054 | NA | Trade Partner | NEXT DC GE01 _ MATERIAL SUBMISSION _ LV SWITCHBOARD (FOA-4) | 0 | 1 | 0 | NA | REJECTED | 2026-07-22 | WF-000358 | NA | 2026-08-04 |  | Issues with Document Status. | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-001824 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-22 | Nilsen3-TRANSMIT-000236 | NA | Trade Partner | Nilsen Neutral Earthing drawing FOR CONSTRUCTION | 1 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 3910 | 2026-07-31 |  | Terminated as instructed by Duncan Cameron - Terminated the designer to re-issue them |  | 2026-08-21 | KPTG-TRANSMIT-020817 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-22 | RDSBIM-TRANSMIT-000234 | NA | Trade Partner | LINDRUM ¦ LEVEL 08 PARTITION WALL LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 713 | 2026-07-27 |  |  | 2026-08-11 | 2026-08-11 | KPTG-SADV-005261 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-22 | TATE_-TRANSMIT-000037 | NA | Trade Partner | Brush Seal Performance¦ | 0 | 1 | 0 | NA | APPROVED | 2026-07-22 | WF-000407 | NA | 2026-07-31 |  | WORKFLOW RESUBMITTED |  | 2026-08-12 | MICRSFT-WTRAN-000012 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-22 | HDRAus-TRANSMIT-000529 | NA | Consultant | M3 Stage 4 - Document upload - Locked Drawings (26/06 + 03/07) | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Revision not updated |  | 2026-07-22 | KPTG-DA-007711 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-22 | D&E-TRANSMIT-000931 | NA | Trade Partner | NXM3S4 - Roof Level - Chiller Room Sections - Sheet 4 of 5 - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 3912 | 2026-07-31 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-020686 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-22 | RDSBIM-TRANSMIT-000235 | NA | Trade Partner | LINDRUM ¦ LEVEL 10 PARTITION WALL LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 714 | 2026-07-27 |  |  | 2026-08-11 | 2026-08-11 | KPTG-SADV-005260 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-21 | MEL-IntCorr-000017 | NA | Trade Partner | Facade Pressure Report and Tabulated Data | 0 | 3 | 0 | NA | APPROVED | 2026-07-21 | NA | NA | 2026-07-27 |  |  | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-003056, KPTG-TRANSMIT-003061, KPTG-TRANSMIT-003063 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-21 | INGEN3D-TRANSMIT-000211 | NA | Trade Partner | Level 11-13 IFC | 40 | 0 | 0 | KPTG-IntCorr-001037 | APPROVED | [5 empty] | Re-transmitted to change the title - transmitted to all parties |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-21 | PCForm-TRANSMIT-000282 | NA | Trade Partner | Preliminary Layout Package (16.06.26) - acrow | 18 | 0 | 0 | NA | REJECTED | [5 empty] | rejected: preliminary issue - QA Error |  | 2026-07-21 | KPTG-TRANSMIT-003011 | Closed | 18 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-02 | Fredon T-TRANSMIT-000009 | NA | Trade Partner | Surface mount Speaker - Pool Side North Tech Data | 0 | 1 | 0 | NA | APPROVED | 2025-12-02 | WF-000642 |  | 2025-12-05 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-16 | D&E-TRANSMIT-000080 | SPARK-CRFI-KPG-000466 | Trade Partner | MWYCCB - ROOF LEVEL + LEVEL 1 - DUCTWORK LAYOUT ZONES & SECTIONS - Issued For Review | 6 | 0 | 0 | NA | APPROVED | 2026-01-16 | WF-000122 | 93 | 2026-01-23 |  |  |  | 2026-02-03 | KPTG-TRANSMIT-000390 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-21 | INGEN3D-TRANSMIT-000212 | NA | Trade Partner | Level 16 - Document Naming | 30 | 0 | 0 | KPTG-IntCorr-001038 | APPROVED | [5 empty] | Re-transmitted to change the title - transmitted to all parties |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-22 | PCForm-TRANSMIT-000270 | NA | Trade Partner | Level 1 - updated PT Reo | 4 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 1007 | 2026-07-30 |  |  | 2026-07-28 | 2026-07-29 | KPTG-TRANSMIT-003152 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-22 | LNCPPL-TRANSMIT-000020 | NA | Trade Partner | Electrical Services Site Plan - Inground - Shop Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 390 | 2026-07-28 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001303 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-22 | SMEPS-TRANSMIT-000253 | SPARK-CRFI KPG-000388 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0603 | 1 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 370 | 2026-07-29 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001540 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-22 | SMEPS-TRANSMIT-000354 | NA | Trade Partner | SME - IFA Documentation Submission | 2 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 3914 | 2026-07-31 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-22 | KETE-TRANSMIT-000144 | NA | Trade Partner | Glass sample(GL10) form | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-005046 - Tittle, type are incorrect. | 2026-07-22 | 2026-07-22 | KPTG-SADV-005046 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-22 | BTWA-TRANSMIT-000093 | NA | Trade Partner | Stage 2 - REV A - Issue for Information drawing set | 36 | 0 | 0 | KPTG-SADV-005761:Consultant Redds Review stamps are missing, requested incorporate: KPTG-SADV-005761 | APPROVED | 2026-07-22 | NA | 401 | 2026-08-03 |  | Consultant Redds Review stamps are missing, requested incorporate: KPTG-SADV-005761 | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-003227 | Closed | 36 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-22 | Jangho-TRANSMIT-000262 | NA | Trade Partner | Podium Level 1~5 Cast in Channel Shop Drawing | 20 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 1009 | 2026-07-30 |  | Review Voided as Updated drawings received from Jangho Jangho-TRANSMIT-000309 and re initiated under #1085 |  | 2026-08-07 | NA | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-22 | ABB-TRANSMIT-000050 | NA | Trade Partner | Fwd: M3 Stage 4/Ph1 - ABB AU--10025007 - Test Reports (Batch 2.1, 2.2, 2.3 & 3.1) | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Kate: Oh thats fine - nothing required ABB add those documents to the commissioning scripts they're filling it out themselves |  | 2026-07-22 | KPTG-TRANSMIT-019878 | Open | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-22 | ELLISAIR-TRANSMIT-000133 | NA | Trade Partner | L02 Chiller Modules Low Level Duct & Pipe Layout drawing issued for Approval. | 1 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 1482 | 2026-07-29 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-006314 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-01-16 | B Smart-TRANSMIT-000047 | NA | Consultant | B Smart-TRANSMIT-000047: IFC Drawing Packages . | 103 | 0 | 0 | NA | APPROVED | 2026-01-16 | WF-000125 | 213 | 2026-01-20 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-000406 | Closed | 103 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-22 | P & R-TRANSMIT-000101 | NA | Trade Partner | MLC Stage 2 - Mechanical Access Panel Requirements | 2 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 403 | 2026-07-30 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-003184 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-22 | P & R-TRANSMIT-000102 | NA | Trade Partner | Mechanical IFC Export for Steel and Plant Deck Coordination | 0 | 1 | 0 | NA | APPROVED | [5 empty] | ISSUED FOR INFORMATION: UPDATED DOCUMENT REGISTER:KPTG-SADV-005463 |  | 2026-07-22 | KPTG-SADV-005463 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-22 | LNCPPL-TRANSMIT-000021 | NA | Trade Partner | Telecommunication Services Site Plan - Inground - Shop Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 392 | 2026-07-28 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-001354 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-22 | SES AU-TRANSMIT-000086 | NA | Trade Partner | COLO4-CELL1-PROTOTYPE ELEVATIONS & DETAILS-IFA | 1 | 0 | 0 | NA | APPROVED | 2026-07-22 | WF-000408 | NA | 2026-07-28 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-001104 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-22 | KPTG-TRANSMIT-019872 | NA | Trade Partner | Caruso Resubmittal | 0 | 2 | 0 | NA | APPROVED | 2026-07-22 | WF-006454 | NA | 2026-07-24 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-020442 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-22 | OTIS2-TRANSMIT-000002 | NA | Trade Partner | New EOT Lift - Shop Drawings & Design Approval | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status incorrect |  | 2026-07-22 | KPTG-DA-000451 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-22 | ccair-TRANSMIT-000135 | NA | Trade Partner | Roof Ductwork & Pipework Layout - Zone AB | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-07-22 | KPTG-TRANSMIT-003173 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-22 | OTIS2-TRANSMIT-000003 | NA | Trade Partner | New EOT Lift - Shop Drawings & Design Approval | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Superseded with Transmittal OTIS2-TRANSMIT-000006. |  | 2026-07-22 | KPTG-DA-000456 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-22 | OTIS2-TRANSMIT-000004 | NA | Trade Partner | New EOT Lift - Shop Drawings & Design Approval | 1 | 0 | 0 | NA | REJECTED | [5 empty] | superseded by OTIS2-TRANSMIT-000006 |  | 2026-07-22 | KPTG-DA-000457 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-22 | OTIS2-TRANSMIT-000005 | NA | Trade Partner | New EOT Lift - Shop Drawings & Design Approval | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect Revision and Status |  | 2026-07-22 | KPTG-CONTADV-000154 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-01-16 | RDSBIM-TRANSMIT-000019 | NA | Consultant | 671CHP ¦ LEVEL 04 CONCRETE PROFILE KEYPLAN AND SECTION | 3 | 0 | 0 | NA | APPROVED | 2026-01-16 | WF-000245 | NA | 2026-01-16 |  | Review void as advised during a meeting with Kapitol DM & PCs. Review Reinitiated on 27-01-26 27/2/25 as advised by KAPITOL PC ACC review 233 is VOID and initiated ACC review - WF-000245 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-22 | PARR-TRANSMIT-000217 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - BFCP MODBUS REGISTER | 0 | 1 | 0 | NA | APPROVED | 2026-07-22 | WF-006458 | NA | 2026-08-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-22 | Carr-TRANSMIT-000072 | NA | Consultant | Architecture Issue for Coordination (RCP) | 10 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 314 | 2026-07-29 |  | Review Voided - 2 Nos Updated drawings received from Carr. and re Initiated under Review #334 |  | 2026-08-10 | NA | Closed | 10 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-22 | SMEPS-TRANSMIT-000353 | NA | Trade Partner | SME IFC - Documentation | 12 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 3916 | 2026-07-31 |  | WF -Terminated |  | 2026-08-19 | KPTG-TRANSMIT-020725 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-22 | Carr-TRANSMIT-000078 | NA | Consultant | Architectural Facade Drawing Set IFA | 20 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect Drawing status |  | 2026-07-22 | KPTG-DA-000455 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-22 | OTIS2-TRANSMIT-000006 | NA | Trade Partner | New EOT Lift - Shop Drawings & Design Approaval | 3 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 312 | 2026-07-31 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-000272 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-22 | D&E-TRANSMIT-000929 | NA | Trade Partner | Re: NXM3S2 - Mechanical Services - As-Builts - Ground & Level 01 Duct & Pipework Layouts | 16 | 0 | 0 | NA | REJECTED | [5 empty] | Missing Previous Revision History, Issue Status Mismatch, Revision Number Update Required, Issue Status and Revision History |  | 2026-07-22 | KPTG-SADV-006786 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-22 | Nilsen3-TRANSMIT-000078 | NA | Trade Partner | Nilsen Sample submissions #13 | 0 | 1 | 0 | NA | APPROVED | 2026-07-22 | WF-001300 | NA | 2026-08-03 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-006748 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-22 | Civilex-TRANSMIT-000305 | NA | Trade Partner | Stage 2 - sample submission - No Fines Concrete - Hytec | 0 | 1 | 0 | NA | APPROVED | 2026-07-22 | WF-006461 | NA | 2026-07-31 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-020301 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-22 | SMEPS-TRANSMIT-000042 | NA | Trade Partner | Penetration Drawings FOA-2 | 3 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 394 | 2026-07-28 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001342 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-22 | ELLISAIR-TRANSMIT-000134 | NA | Trade Partner | Stage 9 & Stage 11 GA Cooling Tower PCCW Pipework layouts drawings issued for Construction. | 4 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 1484 | 2026-07-29 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-006688 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-16 | Auspan-TRANSMIT-000045 | NA | Trade Partner | Resubmit precast shop drawings for approval | 7 | 0 | 0 | NA | APPROVED | 2026-01-16 | WF-000130 | 253 | 2026-01-22 |  |  |  | 2026-01-30 | KPTG-TRANSMIT-000505 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-22 | SMEPS-TRANSMIT-000005 | NA | Trade Partner | Conduit sample - IFA | 0 | 1 | 0 | NA | APPROVED | 2026-07-22 | NA | 484 | 2026-07-30 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-000862 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-22 | SES AU-TRANSMIT-000087 | NA | Trade Partner | Re- NVR Server Memory Module Change to Expedite Delivery | 0 | 1 | 0 | NA | APPROVED | 2026-07-22 | WF-000409 | NA | 2026-07-30 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-001137 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-22 | SMEPS-TRANSMIT-000355 | NA | Trade Partner | SME - IFC Documentation | 9 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 3918 | 2026-07-27 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-22 | TTW-TRANSMIT-000199 | NA | Consultant | M3 Stage 2 Civil Drawings | 8 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | ONLY FOR UPDATING CAD FILES PDF ARE ALREADY UNDER REVIEW |  | 2026-07-22 | KPTG-TRANSMIT-019883 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-22 | Civilex-TRANSMIT-000307 | NA | Trade Partner | Stage 2 - sample submission - Bitumen / Cationic Rapid Set | 0 | 1 | 0 | NA | APPROVED | 2026-07-22 | WF-006462 | NA | 2026-07-30 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-020319 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-22 | Appselec-TRANSMIT-000139 | NA | Trade Partner | Missing Comms Conduits - COLO5 Gen Yard | 1 | 0 | 0 | NA | APPROVED | 2026-07-22 | WF-000410 | NA | 2026-07-28 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-001147 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-22 | LNCPPL-TRANSMIT-000022 | NA | Trade Partner | Please find attached the most recent versions of these documents | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document number, revision date, title. |  | 2026-07-22 | KPTG-SADV-001008 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-22 | PARR-TRANSMIT-000216 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - COC PROPOSED BUILDING WORK-PUMP ROOM REG126 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-22 | KPTG-TRANSMIT-019880 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-22 | JCBa-TRANSMIT-000276 | NA | Consultant | SRC Building Permit - Laundry Wall Type Updated | 2 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 609 | 2026-07-24 |  | NA | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-003187 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-22 | ARCH-TRANSMIT-000166 | NA | Consultant | MLC - SPR - ISC - Capping beam & CPP Carpark North | 3 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 405 | 2026-07-27 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-003142 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-16 | LVPG-TRANSMIT-000006 | NA | Trade Partner | LVPG-HY-TECH-008 - Styrolag | 0 | 1 | 0 | NA | APPROVED | 2026-01-16 | WF-000131 | NA | 2026-01-22 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-22 | SMEPS-TRANSMIT-000006 | NA | Trade Partner | Conduit accessories - IFC | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Wrong status |  | 2026-07-22 | KPTG-TRANSMIT-000659 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-22 | WAM-TRANSMIT-000831 | NA | Consultant | A40.128 Balconies Services Detail | 1 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 1011 | 2026-07-25 |  |  | 2026-07-28 | 2026-07-29 | KPTG-TRANSMIT-003149 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-22 | LNCPPL-TRANSMIT-000023 | NA | Trade Partner | Fwd: Please find attached the most recent versions of these documents | 1 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 396 | 2026-07-30 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-001243 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-22 | D&E-TRANSMIT-000932 | NA | Trade Partner | NXM3S4 - Ground - Mechanical Duct Layout - Zone 6 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-22 | KPTG-TRANSMIT-019886 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-22 | ADP-TRANSMIT-000126 | NA | Consultant | ADP - Fire Protection Specificaiton | 0 | 1 | 0 | NA | APPROVED | 2026-07-22 | NA | 398 | 2026-07-27 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-001293 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-22 | P & R-TRANSMIT-000103 | NA | Trade Partner | MLC Stage 2 - Mechanical Shop Drawings for Approval | 5 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 407 | 2026-07-30 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-003189 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-22 | Leemark-TRANSMIT-000054 | SPARK-CRFI-KPG-000365 | Trade Partner | MCC - L1 Fire Protection Drawings 121-124 - IFA | 4 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 371 | 2026-07-29 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-001487 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-22 | SMEPS-TRANSMIT-000254 |  | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0611 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status inside the drawing and in Aconex seem different. |  | 2026-07-22 | KPTG-TRANSMIT-001486 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-22 | Baigents-TRANSMIT-000020 | NA | Trade Partner | Block 01 - West Wall - Ground to Lvl 1 Precast Panels Re-Issued for Approval | 18 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 486 | 2026-07-30 |  | NA | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-000826 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-22 | ARCST-TRANSMIT-000350 | NA | Trade Partner | Stage 1 Cross Over IFA Drawings | 25 | 0 | 0 | NA | APPROVED | 2026-07-22 | WF-006463 | NA | 2026-07-31 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-16 | StantecA-TRANSMIT-000293 | NA | Consultant | Updated AV Construction Docs | 6 | 1 | 0 | NA | APPROVED | 2026-01-16 | WF-000132 ¦ WF-000133 | 255 | 2026-01-20 |  |  |  | 2026-01-22 | KPTG-TRANSMIT-000455 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-22 | SKS Tech-TRANSMIT-000204 | NA | Trade Partner | Power Containment layout IFC | 29 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 3921 | 2026-07-31 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-22 | SMEPS-TRANSMIT-000078 | NA | Trade Partner | Stage 9-11 Jemena Easement Plan & Sections | 1 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 1486 | 2026-07-29 |  | Workflow has been terminated as discussed with Project Coordinator and resubmitted with the latest drawing |  | 2026-07-30 | KPTG-IntCorr-001924 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-22 | RDSBIM-TRANSMIT-000015 | NA | Trade Partner | NXM2S9 ¦ LEVEL 2 HOB AND PLINTH LAYOUT ¦ IFA ¦ SUBMISSION | 5 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 1488 | 2026-07-24 |  |  | 2026-08-17 | 2026-08-17 | KPTG-TRANSMIT-006952 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-22 | Leemark-TRANSMIT-000055 | NA | Trade Partner | MCC - L1 Fire Protection Drawings Zone 5 - 7 - IFC | 3 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 372 | 2026-07-29 |  | WF Terminated as per Alex advise |  | 2026-07-30 | KPTG-IntCorr-003846 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-22 | Altaire-TRANSMIT-000023 | NA | Trade Partner | NEXTDC M2S9-11 - Dry Fire Panel Drawings (For Approval) (2) | 1 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 1490 | 2026-07-29 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-006318 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-22 | ARCST-TRANSMIT-000354 | NA | Trade Partner | C1 East Gantry Handrails & Grating - Issued for Construction | 142 | 0 | 0 | NA | REJECTED | [5 empty] | IFA of few documents not received |  | 2026-07-22 | KPTG-DA-007712 | Closed | 142 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-22 | Jangho-TRANSMIT-000263 | NA | Trade Partner | Tower Level 6~12 Cast in Channel Shop Drawing | 12 | 0 | 0 | NA | REJECTED | 2026-07-28 | NA | 1044 | 2026-08-05 |  | Rejected-KPTG-TRANSMIT-003015 | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-003596 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-22 | INTRFRM-TRANSMIT-000106 | NA | Trade Partner | Geelong Edge - Civil Tech Data (Submission 8) | 0 | 1 | 0 | NA | APPROVED | 2026-07-22 | WF-000361 | NA | 2026-07-31 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-001462 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-22 | INTRFRM-TRANSMIT-000107 | NA | Trade Partner | Geelong Edge - Civil Tech Data (Submission 7) | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Same revision already in review under Transmittal #INTRFRM-TRANSMIT-000105 |  | 2026-07-22 | KPTG-TRANSMIT-001247 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-22 | ARCST-TRANSMIT-000352 | NA | Trade Partner | Southern Riser - Issued for Construction | 60 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | The IFA for the documents has not been received |  | 2026-07-22 | KPTG-DA-007714 | Closed | 60 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-14 | JCBa-TRANSMIT-000049 | NA | Consultant | Ground Floor Footings - Zone 1 Update | 1 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-000127 | 249 | 2026-01-16 |  |  |  | 2026-01-16 | KPTG-TRANSMIT-000419 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-22 | ARCH-TRANSMIT-000167 | NA | Consultant | MLC - SPR - ISC - Capping beam & CPP Carpark North | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Duplicate of Transmit:KPTG-SADV-005466 |  | 2026-07-22 | KPTG-SADV-005466 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-23 | ZLH P/L-TRANSMIT-000017 | NA | Trade Partner | Proposed Steel Sheet - ZLH | 0 | 1 | 0 | NA | APPROVED | 2026-07-22 | WF-000362 | NA | 2026-07-31 |  |  |  | 2026-08-03 | KPTG-TRANSMIT-001455 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-23 | ARCST-TRANSMIT-000351 | NA | Trade Partner | Fuel Compound Stairs 1 & 2 Issued for approval | 63 | 0 | 0 | NA | REJECTED | [5 empty] | REVISION DATE MISMATCH |  | 2026-07-23 | KPTG-SADV-006805 | Closed | 63 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-22 | KETE-TRANSMIT-000145 | NA | Trade Partner | Glass sample(GL-10) form updated | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-005052 - TITTLE INCORRECT | 2026-07-22 | 2026-07-22 | KPTG-SADV-005052 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-22 | fjc-TRANSMIT-000171 | NA | Consultant | Drawing Updates | 38 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 715 | 2026-07-27 |  | KPTG-SADV-005058 - 38 drawings were received. One drawing has been rejected because the document title is incorrect and the history box is missing. | 2026-07-24 | 2026-07-24 | KPTG-SADV-005081 | Closed | 37 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-22 | SMEPS-TRANSMIT-000007 | NA | Trade Partner | Electrical Temporary Services Layout | 1 | 0 | 0 | KPTG-IntCorr-000349 | APPROVED |  | NA | NA |  |  | Not for submissionAdvised by Absi |  | 2026-08-21 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-22 | fjc-TRANSMIT-000172 | NA | Consultant | Drawing Updates - Door Schedule Ground | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-005060 - Revision date, tittle incorrect | 2026-07-22 | 2026-07-22 | KPTG-SADV-005060 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-22 | SMEPS-TRANSMIT-000008 | NA | Trade Partner | Stage 6 - IFA samples | 0 | 3 | 0 | NA | APPROVED | 2026-07-22 | NA | 490 | 2026-07-30 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-000860 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-22 | NXT-TRANSMIT-000447-TRF | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 06 - HDR, AURECON, TTW, 4DW, ARUP, Eukai, LAT, SCG, A&A, dCC. | 32 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 493 | 2026-07-31 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-000898 | Closed | 32 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-14 | Jordan-TRANSMIT-000110 | NA | Trade Partner | Hydraulics Updated Samples | 0 | 23 | 0 | NA | REJECTED | [5 empty] | QA ERROR - KPTG-IntCorr-000864 |  | 2026-01-14 | KPTG-IntCorr-000864 | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-22 | 4DW-TRANSMIT-000069 | NA | Consultant | Structural Documentation: Block 2 - Precast walls, Foundations Issued For Construction. | 28 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | "CAD distributed 4DW-TRANSMIT-000069 & 4DW-TRANSMIT-000070 submitted together" |  | 2026-07-22 | KPTG-TRANSMIT-000666 | Closed | 28 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-22 | 4DW-TRANSMIT-000070 | NA | Consultant | Issued for Construction: Precast walls, Foundations, NLB walls - Block 2 | 18 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 492 | 2026-07-30 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-000775 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-22 | POTTSENG-TRANSMIT-000056 | NA | Trade Partner | GMAC HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONE 1,3,4 LAYOUTS | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | OK to proceed IFC KPTG-IntCorr-001059 - Registered and Transmit - KPTG-TRANSMIT-002896 |  | 2026-07-22 | KPTG-TRANSMIT-002896 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-22 | POTTSENG-TRANSMIT-000059 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONE 2 LAYOUT | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | OK to proceed IFC KPTG-IntCorr-001058 Register and Transmit - KPTG-TRANSMIT-002901 |  | 2026-07-22 | KPTG-TRANSMIT-002901 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-22 | RDSBIM-TRANSMIT-000053 | NA | Trade Partner | 671CHP LEVEL 04 CONCRETE PROFILE KEYPLAN AND SECTION | 3 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 696 | 2026-08-05 |  | As advised by Kian Lim , PC Kapitol, a consultant review is initiated on 28/07/26. | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001526 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-22 | B Smart-TRANSMIT-000094 | NA | Trade Partner | CPP L1-L19 revised IFC | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Drawings superseded due to a Title error BSmart-TRANSMIT-000095 |  | 2026-07-22 | NA | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-22 | B Smart-TRANSMIT-000095 | NA | Consultant | CPP L1-L19 revised IFC | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Drawings superseded due to a drawing revision history error. B Smart-TRANSMIT-000096 |  | 2026-07-22 | NA | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-22 | B Smart-TRANSMIT-000096 | NA | Consultant | CPP L1-L19 revised IFC reissue | 7 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 674 | 2026-07-24 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001451 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-22 | Bianco-TRANSMIT-000007 | NA | Trade Partner | CHAPEL STREET SHOP DRAWING FOR APPROVAL | 8 | 0 | 0 | NA | APPROVED | 2026-07-22 | WF-000610 | NA | 2026-07-29 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-001400 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-22 | crossfir-TRANSMIT-000028 | NA | Trade Partner | Wet Fire - Penetrations Level 11 to 20, IFA | 10 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 679 | 2026-07-29 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-001601 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-14 | KETE-TRANSMIT-000028 | NA | Trade Partner | Facade Drawings | 38 | 0 | 0 | NA | APPROVED | 2026-01-14 | NA | 822 | 2026-01-19 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-002875 | Closed | 38 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-22 | RBG-TRANSMIT-000068 | NA | Consultant | : Updated structural drawings - Core Wall Lintel schedule and associated details | 1 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 677 | 2026-07-24 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001448 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-29 | ARCST-GCOR-000034 | NA | Trade Partner | Material Tech Data Sheets | 0 | 4 | 0 | NA | APPROVED | 2026-06-29 | WF-001077 | NA | 2026-07-01 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-23 | Jangho-TRANSMIT-000264 | NA | Trade Partner | Brick Sample Submission（Brick No.1） | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF-001018 | NA | 2026-08-17 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-003475 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-23 | Jangho-TRANSMIT-000265 | NA | Trade Partner | Brick Sample Submission（Brick No.2） | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF-001019 | NA | 2026-08-17 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-003477 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-23 | Jangho-TRANSMIT-000266 | NA | Trade Partner | Brick Sample Submission（Brick No.3） | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF-001020 | NA | 2026-08-17 |  |  | 2026-08-13 | 2026-08-14 | KPTG-TRANSMIT-003415 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-23 | Jangho-TRANSMIT-000267 | NA | Trade Partner | Brick Sample Submission（Brick No.4） | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF-001021 | NA | 2026-08-17 |  |  | 2026-08-13 | 2026-08-14 | KPTG-TRANSMIT-003417 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-23 | Jangho-TRANSMIT-000268 | NA | Trade Partner | Brick Sample Submission（Brick No.5） | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF-001022 | NA | 2026-08-17 |  |  | 2026-08-13 | 2026-08-14 | KPTG-TRANSMIT-003419 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-23 | Jangho-TRANSMIT-000269 | NA | Trade Partner | Brick Sample Submission（Brick No.6） | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF-001023 | NA | 2026-08-17 |  |  | 2026-08-13 | 2026-08-14 | KPTG-TRANSMIT-003421 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-23 | RDSBIM-TRANSMIT-000075 | NA | Trade Partner | LEVEL 03 CONCRETE PROFILE PLAN AND SECTIONS | 4 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 1014 | 2026-07-31 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-003391 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-23 | KBGA-TRANSMIT-000010 | NA | Trade Partner | NXM3S6 - HY - Shop Drawing - Ground Block 1 Drainage Services [IFA] | 1 | 0 | 0 | KPTG-IntCorr-000350 | APPROVED | 2026-07-23 | NA | 477 | 2026-07-31 |  |  | 2026-07-22 | 2026-07-23 | KPTG-TRANSMIT-000693 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-14 | GunAus-TRANSMIT-000008 | NA | Trade Partner | Attack doors details | 18 | 0 | 0 | NA | APPROVED | 2026-01-14 | NA | 824 | 2026-01-16 |  |  | 2026-01-15 | 2026-01-15 | KPTG-TRANSMIT-002479 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-23 | RDSBIM-TRANSMIT-000293 | NA | Trade Partner | NXM3S4 - GROUND FLOOR-C-G-054 ACC WC (RH) FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 3923 | 2026-07-25 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020141 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-22 | Jangho-TRANSMIT-000078 | NA | Trade Partner | Window handle Option 4 CZS619 Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-07-22 | WF-001017 | NA | 2026-07-29 |  | Submitted for Client approval | 2026-08-13 | 2026-08-14 | KPTG-TRANSMIT-003412 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-23 | Auscool-TRANSMIT-000069 | NA | Trade Partner | level 2 - level 7 - precast penetration | 6 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 1547 | 2026-07-30 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-003118 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-23 | Carr-TRANSMIT-000079 | NA | Consultant | Architectural Facade IFA | 20 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 316 | 2026-07-30 |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-000253 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-23 | Auscool-TRANSMIT-000070 | NA | Trade Partner | level 1 - precast penetration | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected -Incomplete drawing DRAFT-010384 |  | 2026-07-23 | DRAFT-010384 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-23 | D&E-TRANSMIT-000930 | NA | Trade Partner | Mechanical Dog Box Details - Issued for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 3925 | 2026-08-01 |  | As instructed by Ellie, KPTG-IntCorr-016620 | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-020742 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-23 | Entire M-TRANSMIT-000088 | NA | Trade Partner | Mechanical Energisation Plan | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF-000411 | NA | 2026-07-29 |  | wf-000411 has been terminated: KPTG-IntCorr-000713 |  | 2026-07-23 | KPTG-IntCorr-000713 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-23 | JCI-TRANSMIT-000036 | NA | Trade Partner | OFCI Cell L3.02 L3 ITC SAT Script | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF - 000554 | NA | 2026-07-29 |  | NA | 2026-07-23 | 2026-07-29 | KPTG-TRANSMIT-001127 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-23 | WilsonPD-TRANSMIT-000123 | NA | Trade Partner | North & South Facade Sections IFC | 1 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 1492 | 2026-07-29 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-006008 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-23 | RDSBIM-TRANSMIT-000076 | NA | Trade Partner | LEVEL 03 CONCRETE PROFILE PLAN | 2 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 1016 | 2026-07-31 |  |  | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-003080 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-02 | BTWA-TRANSMIT-000059 | NA | Trade Partner | BT-FA-SPD-1605 revised . W4 Hob removed and Angle support instead | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Title & revision of drawing is missed, Requested to resubmit the Revision D of this drawing |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-15 | SKS Tech-TRANSMIT-000124 | NA | Trade Partner | Connection cubicle | 0 | 1 | 0 | NA | APPROVED | 2026-01-15 | WF-000700 | NA | 2026-01-21 |  |  | 2026-02-02 | 2026-02-03 | KPTG-TRANSMIT-002655 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-23 | Highbu-TRANSMIT-000157 | NA | Trade Partner | Stage 2 drawings IFC | 5 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 411 | 2026-07-28 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-003182 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-23 | SMEPS-TRANSMIT-000255 | SPARK-CRFI-KPG-000388 | Trade Partner | Re: NEL-CNT-SME-2801-BSE-SDG-0611 | 1 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 373 | 2026-07-23 |  |  | 2026-07-27 | 2026-07-30 | KPTG-TRANSMIT-001536 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-22 | Baigents-TRANSMIT-000229 | NA | Trade Partner | External Lobby Handrail FC-1 | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | FC Docs - KPTG-TRANSMIT-004122 - forwarded to all parties |  | 2026-07-22 | KPTG-TRANSMIT-004122 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-22 | Baigents-TRANSMIT-000230 | NA | Trade Partner | Fire Pump Room Handrail FC-1 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | FC Docs - KPTG-TRANSMIT-004125 - forwarded to all parties |  | 2026-07-22 | KPTG-TRANSMIT-004125 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-23 | Stowe-A-TRANSMIT-000662 | NA | Trade Partner | STOWE - AS BUILTS | 6 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 4423 | 2026-07-28 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020170 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-23 | SMEPS-TRANSMIT-000256 | SPARK-CRFI-KPG-000168 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0161,0162,0163,0164,0165,0166,0167,0168,0169 | 9 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 374 | 2026-07-30 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001511 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-23 | EAEGROUP-TRANSMIT-000117 | NA | Trade Partner | Fwd: EAE M3 Stage4 FAT Reports | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-07-23 | KPTG-TRANSMIT-019899 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-23 | WilsonPD-TRANSMIT-000137 | NA | Trade Partner | Stage 11 Tank Room Layout for approval | 1 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 1494 | 2026-07-30 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-006193 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-23 | Arc Plas-TRANSMIT-000008 | NA | Trade Partner | Askin Volcore Panel - Tech Data Submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect Reference number |  | 2026-07-23 | KPTG-DA-007721 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-15 | VAE-Grp-TRANSMIT-000102 | NA | Trade Partner | Mechanical Services - Mechanical Control Centre MCC-B-L4-05, MCC-B-L4-06 & MCC-B-L4-07 | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  | Register Updated - FC |  | 2026-01-15 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-23 | Arc Plas-TRANSMIT-000009 | NA | Trade Partner | Updated Doc No. - Askin Volcore Panel | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF-006468 | NA | 2026-08-13 |  | As instructed by Finn J., the submission was terminated. A new template was created for this submission by Finn. |  | 2026-07-23 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-23 | Auspan-TRANSMIT-000531 | NA | Trade Partner | Re: Update precast cast in plate layout zone 4, 5 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected- Wrong drawing attached DRAFT-010392 |  | 2026-07-23 | DRAFT-010392 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-23 | RDDCPL-TRANSMIT-000001 | NA | Consultant | Facade Shop drawing | 31 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 409 | 2026-07-29 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-003144 | Closed | 31 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-23 | SMEPS-TRANSMIT-000257 | SPARK-CRFI-KPG-000284 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0026 | 1 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 375 | 2026-07-30 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-23 | WilsonPD-TRANSMIT-000124 | NA | Trade Partner | Stage 9 Level 1 Water & Waste IFC | 2 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 1496 | 2026-07-28 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-006012 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-23 | Facx-TRANSMIT-000020 | NA | Trade Partner | FX - Curtain Wall As-Built update | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Issues with documents number, revision, revision date etc. |  | 2026-07-23 | KPTG-SADV-006814 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-23 | Carr-TRANSMIT-000079 | NA | Consultant | SME-Review - Architectural Facade IFA | 20 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 317 | 2026-07-30 |  |  | 2026-07-31 | 2026-07-31 | KPTG-IntCorr-000268 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-23 | Carr-TRANSMIT-000079 | NA | Consultant | FACADE ENGINEERING REVIEW - Architectural Facade IFA | 20 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 318 | 2026-07-28 |  | Peter from JFS not reviewed the drawings and Renee closed the review- Renee needs advised to forward to JFS, Carr & KPTG | 2026-08-10 | 2026-08-11 | KPTG-TRANSMIT-000288 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-23 | SMEPS-TRANSMIT-000044 | NA | Trade Partner | Tech Data - Electrical Upload | 0 | 4 | 0 | NA | APPROVED | 2026-07-23 | WF-000363 | NA | 2026-08-05 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-001772 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-23 | SES AU-TRANSMIT-000088 | NA | Trade Partner | HAC TYPICAL ELEVATION COLO 4 & 5-IFC | 1 | 0 | 0 | NA | APPROVED | 2026-07-23 | WF-000412 | NA | 2026-07-24 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001109 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-15 | SKS Tech-TRANSMIT-000125 | NA | Trade Partner | GLP DB'S | 0 | 6 | 0 | NA | APPROVED |  | NA | NA |  |  | Register Updated - FC |  | 2026-01-15 | NA | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-23 | SMEPS-TRANSMIT-000258 | SPARK-CRFI-KPG-000291 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-1102,1103 | 2 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 376 | 2026-07-30 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-001502 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-23 | RDSBIM-TRANSMIT-000085 | NA | Trade Partner | 352MAC ¦ LEVEL 01 CONCRETE PROFILE PLANS | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - No review, Updated register and distributed-KPTG-TRANSMIT-002923 |  | 2026-07-23 | KPTG-TRANSMIT-002923 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-23 | HAN IND-TRANSMIT-000004 | NA | Trade Partner | IFA - Cooling Towers, External Soffit and Canopy | 87 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Document Number & Revision are incorrect:DRAFT-003804 |  | 2026-07-23 | DRAFT-003807 | Closed | 87 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-23 | RDSBIM-TRANSMIT-000086 | NA | Trade Partner | 352MAC ¦ LEVEL 02 CONCRETE PROFILE PLANS | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - No review, Updated register and distributed-KPTG-TRANSMIT-002925 |  | 2026-07-23 | KPTG-TRANSMIT-002925 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-23 | Nilsen3-TRANSMIT-000237 | NA | Trade Partner | Nilsen Shop Drawings - IFC | 3 | 0 | 0 | NA | APPROVED |  | NA | 3927 | 2026-08-01 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-020547 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-23 | ZLH P/L-TRANSMIT-000018 | NA | Trade Partner | Proposed PPC 4410 Thermal Break Tape Sample for IN05 - ZLH | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF-000364 | NA | 2026-08-05 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-001861 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-23 | INTRFRM-TRANSMIT-000108 | NA | Trade Partner | Geelong Edge - Hydraulic Tech Data (Submission 6) | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF-000365 | NA | 2026-08-03 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-001839 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-23 | D&E-TRANSMIT-000933 | NA | Trade Partner | Functional Description and System Architecture - Issued AsBuilt | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Issues with revision. |  | 2026-07-23 | KPTG-SADV-006817 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-23 | RDSBIM-TRANSMIT-000019 | NA | Trade Partner | NXGE01 ROOF CONCRETE PROFILE KEY PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 400 | 2026-07-31 |  | Terminated as advised by Chri Doh for submitting the updated documents. | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-001264 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-15 | CEDWA-TRANSMIT-000004 | NA | Consultant | Updated Civil Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-01-15 | NA | 826 | 2026-01-19 |  |  | 2026-01-16 | 2026-01-21 | KPTG-TRANSMIT-002520 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-23 | Auscool-TRANSMIT-000071 | NA | Trade Partner | Re: level 1 - precast penetration | 1 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 1551 | 2026-07-30 |  |  |  | 2026-08-11 | KPTG-TRANSMIT-003176 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-23 | INTERSIG-TRANSMIT-000011 | NA | Trade Partner | Assemble Coburg - STATUTORY SIGNAGE | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF - 001095 | NA | 2026-07-29 |  | NA | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-003221 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-19 | KPTG-IntCorr-001625 | NA | Trade Partner | M2 S9-11 Battery Room Supapanel Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-07-19 | WF-001272 | NA | 2026-07-22 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-005950 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-23 | HVHD-TRANSMIT-000017 | NA | Trade Partner | Updated SMP | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF-001027 | NA | 2026-07-24 |  |  | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-003065 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-23 | IVS-TRANSMIT-000373 | NA | Consultant | Stage 4 - Stair C08 Issued for Certification | 2 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 3929 | 2026-07-28 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-019990 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-23 | MAYFLD-TRANSMIT-000472 | NA | Trade Partner | 100222-000614 - Documentation issued for construction | 2 | 0 | 0 | NA | APPROVED | [5 empty] | FC revision for update and distribution only. |  | 2026-07-23 | KPTG-TRANSMIT-019914 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-23 | ARCST-TRANSMIT-000355 | NA | Trade Partner | Fuel Compound Stairs 1 & 2 Issued for approval | 63 | 0 | 0 | NA | REJECTED | [5 empty] | TITLE MISMATCH BTW PREVIOUS REVISION |  | 2026-07-23 | KPTG-SADV-006819 | Closed | 63 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-23 | SIL-TRANSMIT-000009 | NA | Trade Partner | Formal submission of revised documents | 0 | 2 | 0 | NA | APPROVED | 2026-07-23 | WF-000367 | NA | 2026-08-05 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-001650 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-23 | Auspan-TRANSMIT-000534 | NA | Trade Partner | Re: Precast shop drawings for approval. Zone 1, 2 level 6. | 10 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 1553 | 2026-07-30 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-003160 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-23 | WilsonPD-TRANSMIT-000139 | NA | Trade Partner | Low Profile Fire Collars | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF-001309 | NA | 2026-08-03 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-006489 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-16 | IVS-TRANSMIT-000312 | NA | Consultant | Stage 4 - Cooling Tower & Chiller Room Zone C2 & C3 (Certification Issue) | 8 | 0 | 0 | NA | APPROVED | 2026-01-16 |  | 1795 | 2026-01-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-23 | ARCST-TRANSMIT-000354 | NA | Trade Partner | C1 East Gantry Handrails & Grating - Issued for Construction | 142 | 0 | 0 | NA | APPROVED | 2026-07-23 | WF-006472 | NA | 2026-07-27 |  | AS PER THE KPTG-IntCorr-016691 |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-23 | KPTG-WTRAN-000993 | NA | Trade Partner | Energisation Plan | 0 | 1 | 0 | NA | APPROVED | 2026-07-21 | WF - 000550 | NA | 2026-07-23 |  | NA | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-001122 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-23 | KALLIBRE-TRANSMIT-000018 | NA | Trade Partner | IFC - Mailboxes | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF - 001074 | NA | 2026-07-28 |  | NA | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-003190 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-23 | KALLIBRE-TRANSMIT-000019 | NA | Trade Partner | Mailbox Numbers | 0 | 1 | 0 | NA | APPROVED | 2026-07-27 | WF-001102 | NA | 2026-07-30 |  | NA | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-003201 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-23 | SMEPS-TRANSMIT-000259 | NA | Trade Partner | NEL-CNT-SME-2801-BSE-SCH-0004 | 1 | 0 | 0 | KPTG-IntCorr-003708 | APPROVED | 2026-07-30 | NA | 385 | 2026-08-06 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-23 | ASHSS-TRANSMIT-000001 | NA | Trade Partner | NEXTDC GE1- Access stair Drawings | 21 | 0 | 0 | NA | REJECTED | [5 empty] | Error in title, Document status, revision date, revision history. |  | 2026-07-23 | KPTG-SADV-001012 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-23 | ARCST-TRANSMIT-000352 | NA | Trade Partner | Southern Riser - Issued for Construction | 60 | 0 | 0 | NA | APPROVED | 2026-07-23 | WF-006473 | NA | 2026-07-28 |  | As instructed by Lola KPTG-IntCorr-016689 |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-23 | ELLISAIR-TRANSMIT-000135 | NA | Trade Partner | Intumescent Fire Dampers | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF-001310 | NA | 2026-08-04 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-006663 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-15 | Jordan-TRANSMIT-000112 | NA | Trade Partner | Revised Sample Submissions 45-58, 61-67 | 0 | 21 | 0 | NA | APPROVED | 2026-01-15 | WF-000699 | NA | 2026-01-21 |  |  | 2026-02-03 | 2026-02-03 | KPTG-WTRAN-001477, KPTG-WTRAN-001485~KPTG-WTRAN-001489 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-23 | NXT-TRANSMIT-000447-TTW | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 06 - HDR, AURECON, TTW, 4DW, ARUP, Eukai, LAT, SCG, A&A, dCC. | 38 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 495 | 2026-07-31 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-000897 | Closed | 38 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-23 | Auspan-TRANSMIT-000538 | NA | Trade Partner | Precast shop drawings for construction. Level 5 | 20 | 0 | 20 | KPTG-IntCorr-001086 | APPROVED | [5 empty] | IFC - Waiting for Kim advise -KPTG-IntCorr-001086 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-23 | D&E-TRANSMIT-000935 | NA | Trade Partner | NXM3S2 - Mechanical Services - Ground & L01 Duct & Pipework Layouts - Re-issue As-Builts as per KPTG-CONTADV-009554 | 21 | 0 | 0 | NA | REJECTED | [5 empty] | FOA-2 was rejected during the review. Please obtain approval through the IFA review before submitting for IFC |  | 2026-07-23 | KPTG-SADV-006823 | Closed | 21 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-23 | SMEPS-TRANSMIT-000079 | NA | Trade Partner | Fire Rated H Frame Bracket System | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF-001313 | NA | 2026-08-04 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-006744 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-23 | PROLMC-TRANSMIT-000048 | NA | Trade Partner | Proline Shop Drawings 0013; 0015-0018 submission | 5 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 3934 | 2026-08-01 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-23 | HDRAus-TRANSMIT-000530 | NA | Consultant | As-Built Drawings for Separable Portion 7 | 6 | 0 | 0 | NA | REJECTED | [5 empty] | uring our initial review, we identified an issue with the document status. The documents are marked as As-Built revisions; however, they were submitted in Aconex with the status For Information |  | 2026-07-23 | KPTG-SADV-006830 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-23 | HAN IND-TRANSMIT-000005 | NA | Trade Partner | IFA - Cooling Towers, External Soffit and Canopy | 87 | 0 | 0 | NA | REJECTED | [5 empty] | INCORRECT DOCUMENT NUMBERING: DRAFT-003821 |  | 2026-07-23 | DRAFT-003821 | Closed | 87 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-23 | PROLMC-TRANSMIT-000049 | NA | Trade Partner | Proline Shop Drawing IFA submission | 2 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 3936 | 2026-07-28 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-23 | ARCST-TRANSMIT-000357 | NA | Trade Partner | C1 West Lower Gantry Grating - Issued for Construction | 158 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | The IFA for the documents has not been received |  | 2026-07-23 | KPTG-DA-007737 | Closed | 158 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-07-23 | DI-TRANSMIT-000161 | NA | Trade Partner | As Issued for Final construction Drawings | 37 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 429 | 2026-07-27 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-16 | ADP-TRANSMIT-000153 | NA | Consultant | S4 ¦ ADP MEL4780 - C3-Ground Floor & L1 (IFC Issue) | 29 | 0 | 0 | NA | APPROVED | [7 empty] | 2026-01-19 | KPTG-TRANSMIT-011605 | Closed | 29 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-23 | RDSBIM-TRANSMIT-000236 | NA | Trade Partner | LINDRUM ¦ MEZZANINE LEVEL - BLOCK WALL KEY PLAN AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 716 | 2026-07-28 |  | KPTG-IntCorr-001332,KPTG-IntCorr-001331 - As per direction from Charlie,we void the WF # 716 and distribute every one | 2026-08-19 | 2026-08-19 | KPTG-IntCorr-001331 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-23 | SYNACC-TRANSMIT-000009 | NA | Trade Partner | Transmittal - IFA - Level 10 | 3 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-005069 - The revision number and revision date incorrect. | 2026-07-23 | 2026-07-23 | KPTG-SADV-005069 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-23 | KETE-TRANSMIT-000031 | NA | Trade Partner | Kete - Final IFC Shop Drawings Zone 01 to 05 | 444 | 0 | 0 | KPTG-IntCorr-001071 | APPROVED |  | NA | NA |  |  | Waiting for Kaptol advise - KPTG-IntCorr-001071 433 are ok to register - KPTG-SADV-003839 11 Drawings rejected DRAFT-010782 |  | 2026-07-30 | KPTG-SADV-003839 | Closed | 444 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-23 | Auspan-TRANSMIT-000532 | NA | Trade Partner | Update precast cast in plate level 1 zone 4 | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected by Kapitol PC - KPTG-SADV-003651 |  | 2026-07-23 | KPTG-SADV-003651 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-23 | Auspan-TRANSMIT-000533 | NA | Trade Partner | Re: Level 2 Casting | 3 | 0 | 0 | KPTG-IntCorr-001072 | APPROVED |  | NA | NA |  |  | IFC - Kim to Advise - KPTG-IntCorr-001072 IFC - Register and transmit KPTG-TRANSMIT-002945 |  | 2026-07-24 | KPTG-TRANSMIT-002945 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-23 | Auspan-TRANSMIT-000535 | NA | Trade Partner | Re: Update precast cast in plate layout zone 4, 5 - IFC Transmittal | 2 | 0 | 0 | KPTG-IntCorr-001075 | REJECTED |  | NA | NA |  |  | IFC - Kim to Advise - KPTG-IntCorr-001075 Rejected; Auspan to update the drawing .KPTG-IntCorr-001089 |  | 2026-07-24 | KPTG-IntCorr-001089 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-23 | Auspan-TRANSMIT-000536 | NA | Trade Partner | Precast shop drawings for construction. Levels 2, 3. | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Kim to Advise - KPTG-IntCorr-001076 ok to transmit -KPTG-IntCorr-001087 Update and transmitted - KPTG-TRANSMIT-002933 |  | 2026-07-23 | KPTG-TRANSMIT-002933 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-23 | Auspan-TRANSMIT-000539 | NA | Trade Partner | : Resubmit shop drawing 4P4034 for approval. | 1 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 1556 | 2026-07-30 |  |  | 2026-07-28 | 2026-08-04 | KPTG-TRANSMIT-003086 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-16 | RDSBIM-TRANSMIT-000193 | NA | Trade Partner | NXM3S4 GROUND FLOOR-C-G-023 CLEANERS-FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-01-16 |  | 1793 | 2026-01-20 |  |  |  | 2026-01-20 | KPTG-TRANSMIT-011729 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-23 | Auspan-TRANSMIT-000540 | NA | Trade Partner | : Re: Update precast cast in plate level 1 zone 4 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Kim to Advise KPTG-IntCorr-001080 ¦ OK to proceed - KPTG-IntCorr-001082 Update and transmitted - KPTG-TRANSMIT-002935 |  | 2026-07-23 | KPTG-TRANSMIT-002935 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-23 | SES AU-TRANSMIT-000089 | NA | Trade Partner | SECURITY SERVICES DRAWING LIST | 1 | 0 | 0 | KPTG-IntCorr-000714 | APPROVED | [5 empty] | Kapitol advice awaits: KPTG-IntCorr-000714, As per the direction, just updated document Register:KPTG-SADV-001609 |  | 2026-07-24 | KPTG-SADV-001609 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-23 | SEAPBU-TRANSMIT-000007 | NA | Trade Partner | MSFT MEL11 COLO5 Signed Authorisation To Ship Form | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | As per the direction from Mr. Dean, we have updated the document into document register.KPTG-IntCorr-000715 |  | 2026-07-23 | KPTG-IntCorr-000715 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-23 | LGCE-TRANSMIT-000065 | NA | Trade Partner | : Symbols page | 1 | 0 | 0 | KPTG-IntCorr-001032 | APPROVED |  | NA | NA |  |  | Tayla to advise :KPTG-IntCorr-001032 No action required, as advised by Tayla, |  | 2026-07-24 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-23 | LGCE-TRANSMIT-000066 | NA | Trade Partner | : Basement Baton | 0 | 1 | 0 | KPTG-IntCorr-001033 | APPROVED |  | NA | NA |  |  | Tayla to advise KPTG-IntCorr-001033 No action required KPTG-IntCorr-001035 |  | 2026-07-24 | KPTG-IntCorr-001035 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-23 | LGCE-TRANSMIT-000067 | NA | Trade Partner | : Basement 1 light and power | 1 | 0 | 0 | KPTG-IntCorr-001034 | APPROVED |  | NA | 689 | 2026-07-29 |  | Tayla to advise KPTG-IntCorr-001034 | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001444 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-23 | Ardon-TRANSMIT-000016 | NA | Trade Partner | Door Hardware Schedule Stage 9 - Detail Door Hardware | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF-001304 | NA | 2026-08-03 |  | Workflow has been terminated as advised by kaven and resubmitted with WF-001448 |  | 2026-08-10 | KPTG-IntCorr-002083 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-23 | Ardon-TRANSMIT-000017 | NA | Trade Partner | Door Hardware Schedule Stage 10 - Detail Door Hardware | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF-001312 | NA | 2026-08-03 |  | WF-001312 was terminated as requested by Project Coordinator |  | 2026-08-20 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-23 | DLTS-TRANSMIT-000060 | NA | Trade Partner | S11-Cooling Tower-IFC Issue | 341 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | NA |  |  | IFC drawings, No review required. QA process completed, Updated register and distributed |  | 2026-07-23 | KPTG-TRANSMIT-005916 | Closed | 341 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-23 | Arc Plas-TRANSMIT-000020 | NA | Trade Partner | Updated Tech Data Sheet - INS03 & 04 | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF-001308 | NA | 2026-08-03 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2026-01-16 | Nilsen3-TRANSMIT-000100 | NA | Trade Partner | Nilsen Shop Drawings - As-Builts | 13 | 0 | 0 | NA | APPROVED | [5 empty] | As-Builts, No review required. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-23 | KPTG-IntCorr-001788 | NA | Trade Partner | M2 S9-11 FIE - DC Nexus- Battery Enclosure Lifting Beams | 1 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 1499 | 2026-07-31 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-23 | Fencing sample (Outlook mail) | NA | Trade Partner | Fencing Sample | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF-001311 | NA | 2026-07-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-23 | PTA-TRANSMIT-000031 | NA | Trade Partner | External Precast Elevation & Internal Precast Elev. - Issue for Coordination | 5 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 501 | 2026-07-31 |  | NA | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001023 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-23 | Baigents-TRANSMIT-000021 | NA | Trade Partner | STAGE 06 SPEED PANEL MODEL [FOA-2] | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For Information |  | 2026-07-23 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-23 | PTA-TRANSMIT-000032 | NA | Consultant | Stage 6 and 7 Site Boundary update - Master Site Plan Issue | 1 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 503 | 2026-07-31 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-000894 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-23 | NXT-TRANSMIT-000454 | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 08 - NEXTDC | 49 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Distribution |  | 2026-07-23 | KPTG-TRANSMIT-000687 | Open | 49 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-23 | STRBCK-TRANSMIT-000002 | NA | Trade Partner | Civil material conformance | 0 | 3 | 0 | KPTG-IntCorr-000352 | APPROVED | 2026-07-27 | NA | 508 | 2026-08-04 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-000864 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-23 | Lat-TRANSMIT-000013 | NA | Consultant | M3 Expansion - Landscape Issued For Tender Drawings (IFT-1) | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Wrong status |  | 2026-07-23 | KPTG-TRANSMIT-000689 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-23 | Lat-TRANSMIT-000014 | NA | Consultant | Existing Tree - CAD File | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Distribution |  | 2026-07-23 | KPTG-TRANSMIT-000692 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-23 | NXT-TRANSMIT-000447-RPT | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 06 - HDR, AURECON, TTW, 4DW, ARUP, Eukai, LAT, SCG, A&A, dCC. | 0 | 2 | 0 | NA | APPROVED | 2026-07-23 | NA | 497 | 2026-07-31 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-000896 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2026-01-16 | Nilsen3-TRANSMIT-000101 | NA | Trade Partner | Nilsen Shop Drawings - As-Builts | 11 | 0 | 0 | NA | APPROVED | [5 empty] | As-Builts, No Review required |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-23 | NXT-TRANSMIT-000447-SPE | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 06 - HDR, AURECON, TTW, 4DW, ARUP, Eukai, LAT, SCG, A&A, dCC. | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | NA | 499 | 2026-07-31 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-000895 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-24 | Nilsen3-TRANSMIT-000081 | NA | Trade Partner | Nilsen Shop Drawings - IFC | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, No review required, updated register & distributed |  | 2026-07-24 | KPTG-TRANSMIT-005966 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-24 | RDSBIM-TRANSMIT-000237 | NA | Trade Partner | LINDRUM ¦ LEVEL 12,14,16,18,20,22,24,26 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 717 | 2026-07-29 |  |  | 2026-07-31 | 2026-07-31 | KPTG-SADV-005166 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-24 | RDSBIM-TRANSMIT-000238 | NA | Trade Partner | LINDRUM ¦ LEVEL 11 TO LEVEL 27 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 718 | 2026-07-29 |  | KPTG-IntCorr-001245 - Tittle incorrect. | 2026-07-31 | 2026-07-31 | KPTG-SADV-005165 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-24 | ARCH-TRANSMIT-000168 | NA | Consultant | MLC - SPR - Pile, Boundary wall, CPP, Facade elevation update | 6 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 413 | 2026-07-29 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-003157 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-24 | SMEPS-TRANSMIT-000080 | NA | Trade Partner | STAGE 11-GROUND,LV1,LV2,LV3 LIGHTING LAYOUT {IFC 01} | 4 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 1501 | 2026-07-31 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-006871 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-24 | JCBa-TRANSMIT-000158 | NA | Consultant | Updated Architectural Documentation - GA Plans, Partition Plans & Partition Sections | 82 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 1560 | 2026-07-28 |  | 2 drawings already terminated | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-002968 | Closed | 82 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-24 | RDSBIM-TRANSMIT-000231 | NA | Trade Partner | LEVEL 00 GYM & CO-WORKSPACE FLOOR FINISHES ¦ IFA | 4 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 611 | 2026-07-31 |  | NA | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-003277 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-24 | SIL-TRANSMIT-000038 | NA | Trade Partner | MEL11 COLO4-5 - Tech Subs submission | 0 | 1 | 0 | NA | APPROVED | 2026-07-24 | WF-000413) | NA | 2026-07-30 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-001161 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-02 | D&E-TRANSMIT-000271 | NA | Trade Partner | Drawings - System Arch & Panel DWGS FOC5 | 0 | 1 | 0 | KPTG-IntCorr-002091 | APPROVED |  | NA | NA |  |  | Review not required as confirmed by Kapitol. Distribution Only |  |  | KPTG-TRANSMIT-002134 | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2026-01-16 | Nilsen3-TRANSMIT-000102 | NA | Trade Partner | Nilsen As Builts | 91 | 0 | 0 | NA | APPROVED | [5 empty] | As-Builts, No review required. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-24 | PFP PL-TRANSMIT-000022 | NA | Trade Partner | S11 Level 1 Fire Service Layout IFA | 1 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 1503 | 2026-07-31 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-006326 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-23 | BIMF-TRANSMIT-000015 | NA | Trade Partner | Water Schematics For Approval | 3 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 1022 | 2026-08-04 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-003282 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-24 | SIL-TRANSMIT-000039 | NA | Trade Partner | MEL11 COLO4-5 Siemens ATS Documents submission | 0 | 7 | 0 | Kapitol Advice awaits: KPTG-IntCorr-000716 | APPROVED | [5 empty] | Note: This transmit is duplication of SIL-TRANSMIT-000036. As per the direction From Mr Ayaan Rahman Kapitol Project Team, We do not initiate workflow for these documents. |  | 2026-07-28 | KPTG-IntCorr-000716 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-24 | Auspan-TRANSMIT-000544 | NA | Trade Partner | Level 4 precast shop drawings for construction | 30 | 0 | 0 | KPTG-IntCorr-001094 | APPROVED | [5 empty] | IFC - Waiting for Kim advise -KPTG-IntCorr-001094 21 are OK to proceed IFC KPTG-TRANSMIT-003016; 9 Rejected as advised by Kapitol PC. KPTG-IntCorr-001161 |  | 2026-07-30 | KPTG-TRANSMIT-003016 | Closed | 30 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-24 | Auspan-TRANSMIT-000544 | NA | Trade Partner | Level 4 precast shop drawings for construction | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - Difference in revision code -DRAFT-010463 |  | 2026-07-24 | DRAFT-010463 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-24 | SES AU-TRANSMIT-000090 | NA | Trade Partner | FLOOR PLANS AND CAMERA LAYOUTS - IFC | 6 | 0 | 0 | NA | APPROVED | 2026-07-24 | WF-000414 | NA | 2026-07-27 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-001121 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-24 | Auspan-TRANSMIT-000545 | NA | Trade Partner | Level 5 precast shop drawings for construction | 28 | 0 | 0 | KPTG-IntCorr-001095 | APPROVED | [5 empty] | IFC - Waiting for Kim advise -KPTG-IntCorr-001095 22 ARE OK TO IFC- KPTG-TRANSMIT-003372- Published 6 are Rejected advised by Kapitol PC: KPTG-IntCorr-001400 |  | 2026-08-28 | KPTG-TRANSMIT-003372 | Closed | 28 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-24 | Detail-TRANSMIT-000019 | NA | Trade Partner | DOOR HARDAWRE SCHEDULE | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision |  | 2026-07-24 | KPTG-DA-007743 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-24 | Schindle-TRANSMIT-000023 | NA | Trade Partner | Schindler Interior Drawing Rev 4 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status and revision are missing inside the drawing |  | 2026-07-24 | KPTG-TRANSMIT-001489 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-24 | ZIA-TRANSMIT-000130 | NA | Trade Partner | Re: M3 Stage 4 - IP Device Register | 0 | 1 | 0 | NA | APPROVED | 2026-07-24 | WF-006478 | NA | 2026-08-19 |  | As instructed by damian |  | 2026-08-19 | KPTG-TRANSMIT-020726 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2026-01-16 | ACG-TRANSMIT-000043 | NA | Trade Partner | O&M MANUAL | 0 | 1 | 0 | NA | APPROVED | [5 empty] | As-Built, No review required |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-24 | Eneraque-TRANSMIT-000043 | NA | Trade Partner | ENE - BFCP & GFCP Electrical Drawings | 21 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 1505 | 2026-07-31 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-006444 | Closed | 21 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-24 | Auspan-TRANSMIT-000541 | NA | Trade Partner | Resubmit shop drawings for approval. Zone 3 and 5 level 4 | 1 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 1563 | 2026-07-31 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003080 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-24 | KPTG-IntCorr-000717 | NA | Trade Partner | MEL11-EFP-F-TDS-102-0 Doc Upload | 0 | 1 | 0 | NA | APPROVED | 2026-07-24 | WF-000415 | NA | 2026-07-27 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-24 | Auspan-TRANSMIT-000541 | NA | Trade Partner | Resubmit shop drawings for approval. Zone 3 and 5 level 4 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - Difference in revision code- DRAFT-010470 |  | 2026-07-24 | DRAFT-010470 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-24 | D&E-TRANSMIT-000936 | NA | Trade Partner | NXM3S2 - Mechanical Services - As-Built - L01 Mechanical Duct Layouts | 2 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 4426 | 2026-07-29 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020169 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-24 | Eneraque-TRANSMIT-000044 | NA | Trade Partner | ENE - REV 0 Datasheets | 0 | 12 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected : Difference in status |  | 2026-07-24 | KPTG-SADV-006820 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-23 | KPTG-TRANSMIT-004126 | NA | Trade Partner | Jordan ITP | 0 | 2 | 0 | NA | APPROVED | 2026-07-23 | WF-001171 | NA | 2026-07-28 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-23 | KPTG-TRANSMIT-004127 | NA | Trade Partner | Vertiv FD | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF-001172 | NA | 2026-07-28 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-23 | KPTG-IntCorr-001821 | NA | Trade Partner | SKS Scripts | 0 | 2 | 0 | NA | APPROVED | 2026-07-23 | WF-001173 | NA | 2026-07-28 |  |  | 2026-08-28 | 2026-08-28 | WF-001238 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-23 | PARR-TRANSMIT-000063 | NA | Trade Partner | Fuel Services - Cx TEMPLATES - Update | 0 | 5 | 0 | NA | APPROVED | 2026-07-23 | WF-001174 | NA | 2026-07-28 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2026-01-16 | GSAEng-TRANSMIT-000058 | NA | Trade Partner | Updated CSMS O&M Manual for Stage 5 | 0 | 1 | 0 | NA | APPROVED | [5 empty] | As-Built, No review required. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-23 | KPTG-IntCorr-001834 | NA | Trade Partner | VAE CXL4 | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF-001175 | NA | 2026-07-28 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-22 | ZIA-TRANSMIT-000075 | NA | Trade Partner | Fire Pump Room Handrail FC-1 | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | FC Docs - KPTG-TRANSMIT-004125 - forwarded to all parties |  | 2026-07-22 | KPTG-TRANSMIT-004125 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-24 | SKS Tech-TRANSMIT-000205 | NA | Trade Partner | IFC Lighting Schedule | 0 | 1 | 0 | NA | APPROVED | [5 empty] | For distribution |  | 2026-07-24 | KPTG-TRANSMIT-019942 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-24 | NXES-TRANSMIT-000078 | NA | Trade Partner | Carpark Electrical Layout | 6 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 415 | 2026-08-03 |  |  | 2026-08-17 | 2026-08-17 | KPTG-TRANSMIT-003283 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-24 | SMEPS-TRANSMIT-000045 | NA | Trade Partner | Shop Drawing: Electrcial submission | 5 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 404 | 2026-07-30 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-001659 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-23 | ZIA-TRANSMIT-000075 | NA | Trade Partner | CSMS - IT Cabinets | 10 | 0 | 0 | NA | APPROVED | 2026-07-23 | NA | 1176 | 2026-07-30 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-24 | Eneraque-TRANSMIT-000045 | NA | Trade Partner | ENE - REV 0 Datasheets | 0 | 12 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, No review required, updated register & distributed |  | 2026-07-24 | KPTG-TRANSMIT-005977 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-24 | Auspan-TRANSMIT-000543 | NA | Trade Partner | Level 3 precast shop drawings for construction | 4 | 0 | 0 | KPTG-IntCorr-001097 | APPROVED | [5 empty] | IFC - Waiting for Kim advise-KPTG-IntCorr-001097 Register and Transmit KPTG-TRANSMIT-002960 |  | 2026-07-24 | KPTG-TRANSMIT-002960 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-22 | KPTG-WTRAN-002327 | NA | Trade Partner | COMMISSIONING PLAN / ITP I SERVICES ¦ ELECTRICAL SERVICES - ITP' s | 0 | 14 | 0 | NA | APPROVED | 2026-07-22 | WF-001131 | NA | 2026-07-23 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-004153 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-24 | Tradetec-TRANSMIT-000487 | NA | Trade Partner | IFC - Stage 4 - CP37 | 1 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 3939 | 2026-08-01 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2026-01-16 | ACG-TRANSMIT-000044 | NA | Trade Partner | Updated As-Builts Rev ABS-C | 11 | 0 | 0 | NA | APPROVED | [5 empty] | As-Builts, No Review required |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-22 | KPTG-WTRAN-002328 | NA | Trade Partner | HYDRAULIC Commissioning Manual | 0 | 1 | 0 | NA | APPROVED | 2026-07-22 | WF-001130 | NA | 2026-07-23 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-004155 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-24 | DLTS-TRANSMIT-000062 | NA | Trade Partner | S9-North Eave Gutter-IFC Issue | 32 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. QA process completed, Updated register and distributed |  | 2026-07-24 | KPTG-TRANSMIT-005981 | Closed | 32 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-23 | INGEN3D-TRANSMIT-000213 | NA | Trade Partner | Marking Plans (Precast Column Elevation) - IFC | 13 | 0 | 0 | NA | APPROVED | 2026-07-23 | WF-001028 | NA | 2026-07-31 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-003279 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-23 | INGEN3D-TRANSMIT-000214 | NA | Trade Partner | Marking Plans (Precast Column Elevation) - IFC | 11 | 0 | 0 | NA | APPROVED | 2026-07-23 | WF-001029 | NA | 2026-07-31 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003252 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-23 | HVHD-TRANSMIT-000018 | NA | Trade Partner | NatHERS Certification | 0 | 1 | 0 | NA | APPROVED | 2026-07-23 | WF-001030 | NA | 2026-07-27 |  |  | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-003067 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-23 | INGEN3D-TRANSMIT-000215 | NA | Trade Partner | Level 12-14 - PC0498, PC0504, PC0709 & PC0711 - IFC | 6 | 0 | 0 | NA | APPROVED | 2026-07-23 | WF-001039 | NA | 2026-08-03 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-003327 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-22 | KPTG-WTRAN-002330 | NA | Trade Partner | HYDRAULICS SERVICES - ITP | 0 | 5 | 0 | NA | APPROVED | 2026-07-22 | WF-001128 | NA | 2026-07-23 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-004159 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-22 | KPTG-WTRAN-002331 | NA | Trade Partner | ELECTRICAL SERVICES ITP BY SKS | 0 | 15 | 0 | NA | APPROVED | 2026-07-22 | WF-001127 | NA | 2026-07-23 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-004161 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-22 | KPTG-WTRAN-002332 | NA | Trade Partner | EATON ITP'S | 0 | 6 | 0 | NA | APPROVED | 2026-07-22 | WF-001126 | NA | 2026-07-23 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-004163 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2026-01-16 | Nilsen3-TRANSMIT-000127 | NA | Trade Partner | Nilsen Shop Drawings - Complete As-Built Set | 144 | 0 | 0 | NA | APPROVED | [5 empty] | As-Builts, No review required. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-24 | WilsonPD-TRANSMIT-000140 | NA | Trade Partner | Updated S9 & 11 Level 1 Penetrations | 2 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 1509 | 2026-07-29 |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-006207 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-24 | NXT-TRANSMIT-000447-VCHL-RPT | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 06 - HDR, AURECON, TTW, 4DW, ARUP, Eukai, LAT, SCG, A&A, dCC. | 0 | 1 | 0 | NA | APPROVED | 2026-07-24 | NA | 506 | 2026-08-03 |  |  | 2026-08-18 | 2026-08-19 | KPTG-TRANSMIT-001009 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-24 | DLTS-TRANSMIT-000063 | NA | Trade Partner | S9-L1 H Frames-Revised Columns | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. QA process completed, Updated register and distributed |  | 2026-07-24 | KPTG-TRANSMIT-005986 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-24 | ARCST-TRANSMIT-000358 | NA | Trade Partner | C3 East Lower Gantry Grating - Issued for Construction | 117 | 0 | 0 | NA | APPROVED | 2026-07-24 | WF-006482 | NA | 2026-07-28 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-24 | ARCST-TRANSMIT-000357 | NA | Trade Partner | C1 West Lower Gantry Grating - Issued for Construction | 158 | 0 | 0 | NA | APPROVED | 2026-07-24 | WF-006483 | NA | 2026-07-29 |  | As instructed by Lola KPTG-IntCorr-016735 |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-24 | DLTS-TRANSMIT-000065 | NA | Trade Partner | S11-L1 H Frames-IFC Issue | 25 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. QA process completed, Updated register and distributed |  | 2026-07-24 | KPTG-TRANSMIT-005989 | Closed | 25 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-24 | HAN IND-TRANSMIT-000006 | NA | Trade Partner | IFA - Cooling Towers, External Soffit and Canopy | 87 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Title of drawing does not match:KPTG-TRANSMIT-001277 |  | 2026-07-24 | KPTG-TRANSMIT-001277 | Closed | 87 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-24 | ASV-TRANSMIT-000190 | NA | Trade Partner | Hydraulic Data Sheet | 0 | 1 | 0 | NA | APPROVED | 2026-07-24 | WF-006481 | NA | 2026-08-19 |  |  | 2026-08-17 | 2026-08-17 | KPTG-TRANSMIT-020629 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-24 | D&E-TRANSMIT-000939 | NA | Trade Partner | Fwd: NXM3S4 - Ground - Industrial Water Tank Layout - Zone 8 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-24 | KPTG-TRANSMIT-019950 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-24 | D&E-TRANSMIT-000938 | NA | Trade Partner | NXM3S4 - Ground - Builders Works Layout - Zone 10 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-24 | KPTG-TRANSMIT-019951 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-16 | Auspan-TRANSMIT-000039 | NA | Trade Partner | L shape panels L055 and L056 for construction. | 2 | 0 | 0 | NA | APPROVED | [5 empty] | IFC drawings, no review required. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-24 | ADP-TRANSMIT-000372 | NA | Consultant | Re: ADP MEL4780 - Fire Protection Reg 126 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision number is missing |  | 2026-07-24 | KPTG-DA-007745 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-24 | D&E-TRANSMIT-000940 | NA | Trade Partner | Fwd: NXM3S4 - SECURITY GRILLES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-24 | KPTG-TRANSMIT-019952 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-24 | D&E-TRANSMIT-000941 | NA | Trade Partner | Fwd: NXM3S4 - Ground & Level 1 - Builders Works Layout Zone 8 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED |  | NA |  |  |  | For distribution |  | 2026-07-24 | KPTG-TRANSMIT-019953 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-24 | D&E-TRANSMIT-000942 | NA | Trade Partner | Fwd: NXM3S4 - Ground - Builders Works Layout - Zone 6 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA |  |  |  | For distribution |  | 2026-07-24 | KPTG-TRANSMIT-019954 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D9 | 2026-07-24 | HDRAus-TRANSMIT-000013 | NA | Consultant | Re: Client X Antenna Gantry - Updated Stair Location | 11 | 0 | 0 | NA | APPROVED | [5 empty] | Only for taking confirmation from Isaiah fin and its done |  | 2026-07-24 | KPTG-IntCorr-000113 | Closed | 11 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-24 | DLTS-TRANSMIT-000066 | NA | Trade Partner | S9-Antenna Room-IFC Issue | 92 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. QA process completed, Updated register and distributed |  | 2026-07-24 | KPTG-TRANSMIT-005992 | Closed | 92 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-24 | SMEPS-TRANSMIT-000260 | SPARK-CRFI-KPG-000168 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0141,0142,0143,0144,0145,0146,0147 | 7 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 377 | 2026-07-31 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-24 | ARCST-TRANSMIT-000360 | NA | Trade Partner | Fuel Compound Stairs 1 & 2 Issued for approval | 63 | 0 | 0 | NA | REJECTED | [5 empty] | he drawing title is currently listed as "HANDRAIL", whereas in the previous revision it was "GRATING." Based on the drawing content, "GRATING" is the correct title. |  | 2026-07-24 | KPTG-SADV-006845 | Open | 63 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-24 | WAM-TRANSMIT-000832 | NA | Consultant | WAM ARCH - L1 B CSP Update | 1 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 1024 | 2026-07-28 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-003285 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-24 | BIMF-TRANSMIT-000016 | NA | Trade Partner | Level 4 Hydraulic Setouts, Rev B | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | QA error |  | 2026-07-24 | KPTG-TRANSMIT-003046 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-16 | Auspan-TRANSMIT-000040 | NA | Trade Partner | Precast shop drawings for construction. Columns on ground floor. | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings to be revised DRAFT-002588 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-24 | ASHSS-TRANSMIT-000002 | NA | Trade Partner | NEXTDC GE1- Access stair Drawings | 21 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Drawing status & Revision History are missing:KPTG-TRANSMIT-001278 |  | 2026-07-24 | KPTG-TRANSMIT-001278 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-24 | DLTS-TRANSMIT-000067 | NA | Trade Partner | S6-Awning-IFA Issue | 44 | 0 | 0 | NA | APPROVED | 2026-07-24 | WF-001320 | NA | 2026-08-04 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-006397 | Closed | 44 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-24 | TATE_-TRANSMIT-000008 | NA | Trade Partner | MYWCCB - Tate - IFA - Shop Drawings | 2 | 0 | 0 | NA | REJECTED | [5 empty] | The drawing originator code is incorrect. ⁠Drawing number is incorrect. ⁠Revision block is missing inside the drawing. ⁠Revision date inside the drawing and in Aconex seem different |  | 2026-07-24 | KPTG-TRANSMIT-001492 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-24 | WAM-TRANSMIT-000833 | NA | Consultant | A50.203_Soho Apartment Stairs | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | QA error |  | 2026-07-24 | KPTG-TRANSMIT-003049 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-24 | SMEPS-TRANSMIT-000356 | NA | Trade Partner | SME IFA - Documentation | 12 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | REVISION number incorrect |  | 2026-07-24 | KPTG-DA-007748 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-24 | FNSTR8-TRANSMIT-000001 | NA | Trade Partner | Powdercoat | 0 | 2 | 0 | NA | REJECTED |  | NA | NA |  |  | Wrong document. |  | 2026-07-24 | KPTG-SADV-008245 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-24 | FNSTR8-TRANSMIT-000002 | NA | Trade Partner | Shop Drawing_Assemble BTR | 24 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Wrong Document |  | 2026-07-24 | KPTG-TRANSMIT-003180 | Closed | 24 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-23 | L.E.S.-TRANSMIT-000028 | NA | Trade Partner | Emergency lighting lux plots - AGI Files | 17 | 0 | 0 | KPTG-IntCorr-001031 | APPROVED | 2026-07-23 | NA | 1020 | 2026-07-30 |  | Clarification from John - Requested AGI Files along with PDF - processed on 23/07 | 2026-08-26 | 2026-08-26 | AGI FILES - REGISTER UPDATED | Closed | 17 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-24 | WGAVIC-TRANSMIT-000169 | NA | Consultant | M2 - Civil Main Works - Issued for Construction | 20 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected : Difference in revision date |  | 2026-07-24 | KPTG-DA-003928 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-24 | D&E-TRANSMIT-000937 | NA | Trade Partner | GROUND FLOOR & LEVEL 01 - DATA HALLS SFN UNION & BOLT TORQUE - Issued For Construction | 2 | 0 | 0 | NA | REJECTED | [5 empty] | we have not yet received the corresponding IFA documents. However, the documents have been submitted directly as IFC for review. |  | 2026-07-24 | KPTG-SADV-006846 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-16 | Auspan-TRANSMIT-000041 | NA | Trade Partner | Resubmit shop drawings for approval. Shear wall shop drawings re-split. | 14 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings to be revised DRAFT-002589 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-24 | Auspan-TRANSMIT-000549 | NA | Trade Partner | Resubmit precast panel 3P4024 and 3P4025 | 2 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 1567 | 2026-07-31 |  | Review terminated as advised by Kapito PC. |  | 2026-07-30 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-24 | HAN IND-TRANSMIT-000007 | NA | Trade Partner | Highly Important: IFA - Cooling Towers, External Soffit and Canopy | 86 | 0 | 0 | NA | APPROVED | 2026-07-24 | WF-000370 | NA | 2026-08-07 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-001718 | Closed | 86 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-24 | SMEPS-TRANSMIT-000261 | SPARK-CRFI-KPG-000168 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0148,0149 | 2 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 378 | 2026-07-31 |  |  | 2026-07-27 | 2026-07-30 | KPTG-TRANSMIT-001534 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-24 | ADP-TRANSMIT-000373 | NA | Consultant | ADP MEL4780 - Updated Fire Detection Drawings | 8 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 3948 | 2026-07-28 |  | Terminated as instructed by ellie |  | 2026-08-07 | KPTG-TRANSMIT-020431 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-24 | INSULPAK-TRANSMIT-000032 | NA | Trade Partner | Updated As Built Drawing as per comment | 1 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 430 | 2026-08-06 |  |  | 2026-07-27 | 2026-07-27 | DRAFT-010474 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-24 | HDRAus-TRANSMIT-000531 | NA | Consultant | M3 SW - Document upload - PDF and CAD | 1 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 4428 | 2026-07-31 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-020039 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-24 | SMEPS-TRANSMIT-000046 | NA | Trade Partner | Tech Data: MDB-AA and MDB AB | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Rejected: Attachments of technical data are identical: KPTG-TRANSMIT-001280 |  | 2026-07-24 | KPTG-TRANSMIT-001280 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-24 | ARCH-TRANSMIT-000057 | NA | Consultant | Door schedule | 1 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 407 | 2026-07-29 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-001496 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-24 | ADP-TRANSMIT-000371 | NA | Consultant | ADP MEL4561 - Fire Protection updated drawing and Spec | 1 | 1 | 0 | NA | REJECTED | [5 empty] | incorrect revision date |  | 2026-07-24 | KPTG-DA-007759 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-07-24 | Nilsen3-TRANSMIT-000207 | NA | Trade Partner | Nilsen HV Shop Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-07-24 | WF-006488 | NA | 2026-07-29 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-16 | Auspan-TRANSMIT-000042 | NA | Trade Partner | Deleted ground floor shop drawings | 44 | 0 | 0 | NA | REJECTED | [5 empty] | Deleted ground floor shop drawings |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-24 | Stowe-A-TRANSMIT-000664 | Na | Trade Partner | STOWE - COMMS AS BUILT | 2 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 4300 | 2026-07-31 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020165 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-17 | WSP ANZ-TRANSMIT-000020 | NA | Consultant | Acoustic Report | 0 | 1 | 0 | NA | APPROVED | 2026-07-17 | NA | 308 | 2026-07-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-24 | WilsonPD-TRANSMIT-000217 | NA | Trade Partner | Hydraulic & Civil Services - Updated Layouts | 14 | 0 | 0 | NA | REJECTED | [5 empty] | Multiple drawing statuses |  | 2026-07-24 | KPTG-TRANSMIT-001493 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-24 | Auspan-TRANSMIT-000547 | NA | Trade Partner | Re: RFI: Panel weight 0G368 | 2 | 0 | 0 | KPTG-IntCorr-001101 | APPROVED | [5 empty] | IFC - Waiting for Kim advise-KPTG-IntCorr-001101 Transmit for INFO only - KPTG-IntCorr-00121 |  | 2026-08-10 | KPTG-TRANSMIT-003153 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-24 | Auspan-TRANSMIT-000547 | NA | Trade Partner | Re: RFI: Panel weight 0G368 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected- Revision code difference-DRAFT-010508 |  | 2026-07-24 | DRAFT-010508 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-24 | ARCST-TRANSMIT-000359 | NA | Trade Partner | C2 West Lower Gantry Grating - Issued for Construction | 141 | 0 | 0 | NA | REJECTED | [5 empty] | Mismatch in Revision, revision date |  | 2026-07-24 | KPTG-DA-007760 | Closed | 141 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-24 | SES AU-TRANSMIT-000005 | NA | Trade Partner | Security - Samples | 0 | 6 | 0 | NA | APPROVED | 2026-07-24 | WF-001321 | NA | 2026-07-31 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-006802 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-24 | Civilex-TRANSMIT-000310 | NA | Trade Partner | Stage 2 - Landscape drawings Transmittal SPECIFICATION | 0 | 2 | 0 | NA | APPROVED | 2026-07-24 | WF-006489 | NA | 2026-07-31 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-020314 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-24 | D&E-TRANSMIT-000292 | SPARK-CRFI-KPG-000473 | Trade Partner | MWYCCB - LEVEL 1 - PLINTH LAYOUT ZONE 8 & ZONE 9 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 379 | 2026-07-31 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-001504 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-24 | PROLMC-TRANSMIT-000008 | NA | Trade Partner | TREMFlex Data Sheet Alternative | 0 | 1 | 0 | NA | APPROVED | 2026-07-24 | WF-001322 | NA | 2026-07-29 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-16 | BLUESF-TRANSMIT-000020 | NA | Trade Partner | (GRND LVL) PRECAST GA DRAWINGS RE-IFA | 22 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-02-17 | NA | Closed | 22 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-24 | KALLIBRE-TRANSMIT-000020 | NA | Trade Partner | IFC - Locker Shop Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-07-24 | WF - 01099 | NA | 2026-07-31 |  | NA | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-003208 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-24 | KALLIBRE-TRANSMIT-000021 | NA | Trade Partner | IFC - Toilet Partitions | 6 | 0 | 0 | NA | APPROVED | 2026-07-24 | WF - 001100 | NA | 2026-07-31 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-24 | ARCST-TRANSMIT-000356 | NA | Trade Partner | C2 East Lower Gantry - Issued for Construction | 136 | 0 | 0 | NA | APPROVED | 2026-07-24 | WF-006490 | NA | 2026-07-29 |  | As instructed by Lola KPTG-IntCorr-016734 |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-24 | WilsonPD-TRANSMIT-000216 | NA | Trade Partner | Fwd: IFA Stormwater Pits and Lids | 0 | 5 | 0 | NA | REJECTED | [5 empty] | Same revision already in Aconex |  | 2026-07-24 | KPTG-TRANSMIT-001497 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-24 | Civilex-TRANSMIT-000308 | NA | Trade Partner | Landscape drawings Transmittal - Rev E | 12 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: , document superceded in the transmit:Civilex-TRANSMIT-000309: KPTG-SADV-006860 |  | 2026-07-24 | KPTG-SADV-006860 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-24 | FNSTR8-TRANSMIT-000003 | NA | Trade Partner | Updated: Sample Submission: Powder coat. | 0 | 2 | 0 | NA | APPROVED | 2026-07-24 | WF - 001101 | NA | 2026-07-31 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-24 | KPTG-WTRAN-000843 | NA | Trade Partner | KAP - ARC - GEM - GHD - KAP - Cortek Frame | 0 | 1 | 0 | NA | APPROVED | 2026-07-24 | WF-000352 | na | 2026-07-24 |  |  |  | 2026-07-24 | KPTG-TRANSMIT-001281 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-24 | Civilex-TRANSMIT-000309 | NA | Trade Partner | Stage 2 - Landscape drawings Transmittal - Rev E | 11 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 4433 | 2026-08-04 |  | ONE DOCUMENTS IS ALREADY IN REVIEW. HENCE, WE HAVE INITIATED WORKFLOW FOR THE REST 10 DOCUMENTS |  | 2026-07-30 | KPTG-TRANSMIT-020236 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-24 | ARCST-TRANSMIT-000361 | NA | Trade Partner | Fuel Compound Stairs 1 & 2 Issued for approval | 63 | 0 | 0 | NA | APPROVED | 2026-07-24 | WF-006506 | NA | 2026-08-11 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-24 | RDSBIM-TRANSMIT-000020 | NA | Trade Partner | NXGE01 - ROOF CONCRETE PROFILE KEY PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 402 | 2026-07-30 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-001457 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-02 | DRLL-TRANSMIT-000046 | NA | Trade Partner | Battery Room Modules - EC Fans (UCOP Rooms) Tech Data | 0 | 1 | 0 | NA | APPROVED | 2025-12-02 | WF-000828 | NA | 2025-12-12 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-16 | BLUESF-TRANSMIT-000021 | NA | Trade Partner | M2-STR-BSF-SDRG-1101-(COLUMNS) PRECAST DRAWINGS IFA | 40 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000193 |  | 2026-02-11 |  | Drawings resubmitted as per Kapitol instruction |  | 2026-02-16 | KPTG-TRANSMIT-000838 | Closed | 40 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-24 | HDRAus-TRANSMIT-000532 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 23 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 3957 | 2026-07-29 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-020077 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-24 | CDL-TRANSMIT-000045 | NA | Trade Partner | KPA Stage 2 Documentation | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Document number of all drawing are incorrect: KPTG-SADV-005508 |  | 2026-07-24 | KPTG-SADV-005508 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-24 | HVHD-TRANSMIT-000018 | NA | Trade Partner | NatHERS Certification | 0 | 1 | 0 | NA | APPROVED | 2026-07-24 | WF-001030 | NA | 2026-07-27 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-24 | KPTG-IntCorr-001048 | NA | Trade Partner | District Living: Approved RSA and FLP | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | registered and sent to all parties |  | 2026-07-24 | KPTG-TRANSMIT-003052 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-24 | EAE Busduct shop drawings (Outlook mail) | NA | Trade Partner | EAE Busduct shop drawings Stage 10 | 70 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 1507 | 2026-07-31 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-006147 | Closed | 70 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-24 | Auspan-TRANSMIT-000542: | NA | Trade Partner | Update IFCed shop drawings. Level 2 | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Ok to proceed - KPTG-SADV-003685 IFC - Register and transmit -KPTG-TRANSMIT-002941 |  | 2026-07-24 | KPTG-TRANSMIT-002941 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-24 | Highbu-TRANSMIT-000158 | NA | Trade Partner | ISC in ground fire service | 1 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 417 | 2026-08-04 |  |  | 2026-08-27 | 2026-08-28 | KPTG-TRANSMIT-003355 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-24 | Auspan-TRANSMIT-000548 | NA | Trade Partner | - Precast Shop drawing - 3P4048-1 | 1 | 0 | 0 | KPTG-IntCorr-001102 | APPROVED |  | NA | NA |  |  | IFC Waiting for Kim advise-KPTG-IntCorr-001102 Ok to proceed as IFC : KPTG-TRANSMIT-002971 |  | 2026-07-28 | KPTG-TRANSMIT-002971 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-24 | 4DW-TRANSMIT-000202 | NA | Consultant | Structural Drawing Issue - Piling | 1 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 419 | 2026-07-29 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-003155 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-16 | BLUESF-TRANSMIT-000022 | NA | Trade Partner | M2-STR-BSF-SDRG-1101-(L-SHAPE) PRECAST DRAWINGS IFA | 17 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000195 |  | 2026-02-11 |  | Drawings resubmitted as per Kapitol instruction |  | 2026-02-13 | KPTG-TRANSMIT-000804 | Closed | 17 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-24 | KPTG-IntCorr-001843 | NA | Trade Partner | Technical Data sheets FIE | 0 | 25 | 0 | NA | APPROVED | 2026-07-24 | WF-001319 | NA | 2026-07-29 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-24 | RDSBIM-TRANSMIT-000239 | NA | Trade Partner | LINDRUM ¦ LEVEL 10 UPPER TERRACE CONCRETE PROFILE PLAN | 1 | 0 | 0 | KPTG-IntCorr-001247 | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001247 - requested guidance, but no resonance yet. KPTG-IntCorr-001261 - As per direction from Ashlin, we only update the document register and distribute to everyone. | 2026-07-28 | 2026-07-28 | KPTG-IntCorr-001261 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-24 | SYNACC-TRANSMIT-000001 | NA | Trade Partner | Substation Door - Shop Drawing - For Review and Approval | 1 | 0 | 0 | NA | REJECTED | 2026-07-24 | NA | NA |  |  | Rejected due to incorrect drawing number KPTG-IntCorr-001039 |  | 2026-07-24 | KPTG-IntCorr-001039 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-24 | RDSBIM-TRANSMIT-000089 | NA | Trade Partner | 671CHP LEVEL 01 CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 685 | 2026-07-27 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-001424 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-24 | NXES-TRANSMIT-000063 | NA | Trade Partner | Level 11 Lighting, Power & Comms Layout (Typical 11 to 27) | 2 | 0 | 0 | KPTG-IntCorr-001248 | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-001248 - requested guidance, but no resonance yet. KPTG-IntCorr-001250 - Revision date incorrect. | 2026-07-27 | 2026-07-27 | KPTG-IntCorr-001250 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-24 | POTTSENG-TRANSMIT-000038 | NA | Trade Partner | 671C: HYDRAULIC SERVICES - LEVEL 01 - PENETRATION LAYOU | 1 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 687 | 2026-07-29 |  | ACC review is voided to update the review team as advised by Tayla. | 2026-07-31 | 2026-07-31 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-24 | NXES-TRANSMIT-000064 | NA | Trade Partner | Level 11-27 General & Emergency Lighting Layout | 1 | 0 | 0 | KPTG-IntCorr-001249 | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-001249-requested guidance, but no resonance yet. KPTG-SADV-005090-Revision date and status incorrect. | 2026-07-27 | 2026-07-27 | KPTG-SADV-005090 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-24 | WAM-TRANSMIT-000834 | NA | Consultant | Drawings A14- A75 Series Wall Setout Plans and Wall Type Schedules | 26 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 1026 | 2026-07-27 |  |  | 2026-07-31 | 2026-08-03 | KPTG-TRANSMIT-003218 | Closed | 26 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-24 | WAM-TRANSMIT-000834 | NA | Consultant | Drawings A14- A75 Series Wall Setout Plans and Wall Type Schedules | 1 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 1028 | 2026-07-27 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-003114 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-27 | Auspan-TRANSMIT-000551 | NA | Trade Partner | Re: Resubmit shop drawings for approval. Zone 3 and 5 level 4 | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 1569 | 2026-08-01 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-003329 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-16 | BLUESF-TRANSMIT-000023 | NA | Trade Partner | M2-STR-BSF-SDRG-1101-(POUR 1) PRECAST DRAWINGS IFA | 25 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000196 |  | 2026-02-11 |  | Drawings resubmitted as per Kapitol instruction |  | 2026-02-16 | KPTG-TRANSMIT-000839 | Closed | 25 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-27 | DLTS-TRANSMIT-000069 | NA | Trade Partner | S11-Cooling Tower Grating-IFC Issue | 72 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. QA process completed, Updated register and distributed |  | 2026-07-27 | KPTG-TRANSMIT-006005 | Closed | 72 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-27 | Appselec-TRANSMIT-000140 | NA | Trade Partner | Earth Bracket Tech Data For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-27 | WF-000416 | NA | 2026-07-31 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001132 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-27 | Civilex-TRANSMIT-000311 | NA | Trade Partner | Stage 1 Swale Restoration Landscape Plan Revision E | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with revision, Revision history missing, document status incorrect. Title mismatch. |  | 2026-07-27 | KPTG-SADV-006874 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-27 | EFP-TRANSMIT-000034 | NA | Trade Partner | FIRE SERVICES DRY - PSU UNITS ADDED | 3 | 0 | 0 | NA | APPROVED | 2026-07-27 | WF-000417 | NA | 2026-07-28 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-001116 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-27 | RDSBIM-TRANSMIT-000232 | NA | Trade Partner | LEVEL 00 PARTITION WALL PLAN | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-07-27 | KPTG-TRANSMIT-003182 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-27 | Civilex-TRANSMIT-000312 | NA | Trade Partner | Stage 2 - sample submission - Hytec Mix Design - Rev FOA-G | 0 | 1 | 0 | NA | APPROVED | 2026-07-27 | WF-006496 | NA | 2026-07-31 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-020342 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-27 | KPTG-IntCorr-000718 | NA | Trade Partner | MEL11-EFP-F-TDS-102-0 Doc Upload | 0 | 1 | 0 | NA | APPROVED | 2026-07-27 | WF-000418 | NA | 2026-07-27 |  | workflow resubmitted:KPTG-IntCorr-000719 |  | 2026-07-27 | KPTG-IntCorr-000719 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-27 | SMEPS-TRANSMIT-000047 | NA | Trade Partner | techdata; MDB-AA and MDB AB | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Issue with revision number. |  | 2026-07-27 | KPTG-SADV-001032 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-27 | FNSTR8-TRANSMIT-000004 | NA | Trade Partner | Shop Drawings IFA | 24 | 0 | 0 | NA | APPROVED | 2026-07-27 | WF - 0001103 | NA | 2026-07-31 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-27 | RDSBIM-TRANSMIT-000087 | NA | Trade Partner | GREYSTAR ¦ LEVEL 03 CONCRETE PROFILE PLAN | 6 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 1571 |  |  | Review void as requested by RDS and advised by Kapitol DM. | 2026-08-06 | 2026-08-06 | NA | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-16 | BLUESF-TRANSMIT-000024 | NA | Trade Partner | M2-STR-BSF-SDRG-1101-(POUR 2) PRECAST DRAWINGS IFA | 29 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000197 |  | 2026-02-11 |  | Drawings resubmitted as per kapitol instruction |  | 2026-02-16 | KPTG-TRANSMIT-000822 | Closed | 29 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-27 | RDSBIM-TRANSMIT-000077 | NA | Trade Partner | LEVEL 01 CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 1030 | 2026-08-04 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-003354 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-27 | Nilsen3-TRANSMIT-000082 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 1512 | 2026-08-03 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-006875 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-27 | SMEPS-TRANSMIT-000081 | NA | Trade Partner | ROOF PENETRATION DOG BOX (TX,GEN,BATT) | 3 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 1514 | 2026-08-03 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-006502 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-27 | SKS Tech-TRANSMIT-000207 | NA | Trade Partner | Lighting Control Layout FC | 4 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 3954 | 2026-08-05 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-27 | Auspan-TRANSMIT-000555 | NA | Trade Partner | Resubmit zone 5 level 3 panel 3P5056 for approval | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 1573 | 2026-08-03 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-003061 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-27 | PFP PL-TRANSMIT-000023 | NA | Trade Partner | S11-Level 2 IFA | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected : Incorrect document number |  | 2026-07-27 | KPTG-SADV-006864 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-27 | Auspan-TRANSMIT-000550 | NA | Trade Partner | Re: Level 4 precast shop drawings for construction | 1 | 0 | 0 | KPTG-IntCorr-001106 | APPROVED | [5 empty] | IFC - Waiting for Kim advise- KPTG-IntCorr-001106 OK to proceed IFC KPTG-TRANSMIT-003019 |  | 2026-07-30 | KPTG-TRANSMIT-003019 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-27 | SMEPS-TRANSMIT-000357 | NA | Trade Partner | SME - IFA Sample submissions | 0 | 3 | 0 | NA | APPROVED | 2026-07-27 | WF-006498 | NA | 2026-08-20 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-27 | D&E-TRANSMIT-000943 | NA | Trade Partner | Fwd: ISSUED FOR CONSTRUCTION - GROUND - MECHANICAL DUCT LAYOUT - ZONE 7 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-27 | KPTG-TRANSMIT-019984 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-27 | Auspan-TRANSMIT-000553 | NA | Trade Partner | Precast shop drawings for construction. Level 4 | 25 | 0 | 0 | KPTG-IntCorr-001107 | APPROVED | [5 empty] | IFC - Waiting for Kim advise- KPTG-IntCorr-001107 20 are OK to IFC 5 are rejected by PC- KPTG-SADV-003925 |  | 2026-08-04 | KPTG-TRANSMIT-003070 | Closed | 25 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-16 | BLUESF-TRANSMIT-000025 | NA | Trade Partner | M2-STR-BSF-SDRG-1101-(POUR 3) PRECAST DRAWINGS IFA | 23 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000198 | NA | 2026-02-11 |  | Drawings resubmitted as per Kapitol instruction. | 2026-03-03 | 2026-03-04 | KPTG-TRANSMIT-001179 | Closed | 23 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-27 | SMEPS-TRANSMIT-000048 | NA | Trade Partner | Tech Data - Branch Monitoring | 0 | 1 | 0 | NA | APPROVED | 2026-07-27 | WF-000372 | NA | 2026-08-07 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-001776 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-27 | Civilex-TRANSMIT-000313 | NA | Trade Partner | Stage 1 - Swale Restoration Landscape Plan Revision G / update naming | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with title. |  | 2026-07-27 | KPTG-SADV-006876 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-27 | ADP-TRANSMIT-000376 | NA | Consultant | ADP MEL4780 - M3S4 - Protection Device Report | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-27 | ⁠KPTG-TRANSMIT-019996 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-27 | SKS Tech-TRANSMIT-000206 | NA | Trade Partner | Lighting Layouts FC-01 | 4 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 3959 | 2026-08-01 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-27 | Nilsen3-TRANSMIT-000240 | NA | Trade Partner | Cable Cleat sample | 0 | 1 | 0 | NA | APPROVED | 2026-07-27 | WF-006501 | NA | 2026-08-20 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-27 | Altaire-TRANSMIT-000024 | NA | Trade Partner | NEXTDC M2S10/11 - Shop Drawings (FA-1) | 2 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 1517 | 2026-08-03 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-006322 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-27 | RDSBIM-TRANSMIT-000090 | NA | Trade Partner | 671CHP ¦ BASEMENT 01 BLOCKWORK PLAN AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 691 | 2026-08-04 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-001662 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-27 | KPTG-IntCorr-000719 | NA | Trade Partner | MEL11-EFP-F-TDS-102-0- Doc Upload | 0 | 1 | 0 | NA | APPROVED | 2026-07-27 | WF-000419 | NA | 2026-07-28 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-27 | SMEPS-TRANSMIT-000082 | NA | Trade Partner | 110V DC SYSTEM SCHEMATIC | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 1520 | 2026-08-03 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-006506 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-27 | ADP-TRANSMIT-000375 | NA | Consultant | ADP MEL4561 - Fire Protection updated drawing and Spec | 2 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 3961 | 2026-08-01 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-020963 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-16 | BLUESF-TRANSMIT-000026 | NA | Trade Partner | M2-STR-BSF-SDRG-1101-(POUR 4) PRECAST DRAWINGS IFA | 48 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000199 |  | 2026-02-11 |  | Drawings resubmitted as per Kapitol instruction. | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-001059 | Closed | 48 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-27 | KPTG-IntCorr-000720 | NA | Trade Partner | Integration Plan Upload / WF | 0 | 1 | 0 | NA | APPROVED | 2026-07-27 | WF-000420 | NA | 2026-07-30 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-27 | B Smart-TRANSMIT-000098 | NA | Consultant | GF RCP updated | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 693 | 2026-07-29 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-001643 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-27 | Civilex-TRANSMIT-000304 | NA | Trade Partner | Sample Submission - Southern Retaining Wall No Fines Concrete Backfill | 0 | 1 | 0 | NA | REJECTED | [5 empty] | the attached Document seems document numbering mistake on the Aconex and inside drawing. |  | 2026-07-27 | KPTG-SADV-006879 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-27 | ASHSS-TRANSMIT-000004 | NA | Trade Partner | NEXTDC GE1- Access stair Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | WF-000373 | NA | 2026-08-07 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-001446 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-27 | LNCPPL-TRANSMIT-000024 | NA | Trade Partner | HYDRAULIC SERVICES - SITE PLAN INGROUND SERVICES - Shop Drawing FC-1 | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 410 | 2026-08-07 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-001288 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-27 | INTRFRM-TRANSMIT-000110 | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 2) | 0 | 1 | 0 | NA | APPROVED | 2026-07-27 | WF-000375 | NA | 2026-08-07 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-001530 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-27 | RDSBIM-TRANSMIT-000021 | NA | Trade Partner | NXGE01 GROUND FLOOR PLANT AREA CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 412 | 2026-08-07 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001304 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-27 | WSP ANZ-TRANSMIT-000097 | NA | Consultant | WSP - Data Hall Fitout WIP - (Telecommunications) | 7 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected : Difference in status |  | 2026-07-27 | KPTG-DA-003943 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-27 | Baigents-TRANSMIT-000090 | NA | Trade Partner | SITE STORAGE - CARPORT STEEL - ISSUED FOR CONSTRUCTION | 75 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status inside and in Aconex seem different |  | 2026-07-27 | KPTG-TRANSMIT-001509 | Closed | 75 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-27 | TTW-TRANSMIT-000200 | NA | Consultant | M3 Stage 1 Civil Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 4436 | 2026-07-29 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-16 | BLUESF-TRANSMIT-000027 | NA | Trade Partner | M2-STR-BSF-SDRG-1101-(POUR 5) PRECAST DRAWINGS IFA | 21 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000200 | NA | 2026-02-11 |  | Drawings resubmitted as per Kapitol instruction | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-001482 | Closed | 21 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-27 | Auspan-TRANSMIT-000554 | NA | Trade Partner | Precast shop drawings for construction. Level 3 | 5 | 0 | 0 | KPTG-IntCorr-001111 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise-KPTG-IntCorr-001111 Ok to transmit- KPTG-TRANSMIT-002997 |  | 2026-07-29 | KPTG-TRANSMIT-002997 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-27 | Auspan-TRANSMIT-000554 | NA | Trade Partner | Precast shop drawings for construction. Level 3 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - difference in drawing status-DRAFT-010557 |  | 2026-07-27 | DRAFT-010557 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-27 | ASV-TRANSMIT-000191 | NA | Trade Partner | Hydraulic Sample Submission - Class E Inspection Open Access Cover | 0 | 1 | 0 | NA | APPROVED | 2026-07-27 | WF-006512 | NA | 2026-07-31 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-020087 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-27 | WilsonPD-TRANSMIT-000141 | NA | Trade Partner | Sub Meters and Vinyl Floor Wastes for approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-27 | WF-001333 | NA | 2026-08-05 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-006493 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-27 | Auspan-TRANSMIT-000556 | NA | Trade Partner | Update already IFCed shop drawings | 2 | 0 | 0 | KPTG-IntCorr-001112 | APPROVED | [5 empty] | IFC - Waiting for Kim advise-KPTG-IntCorr-001112 |  | 2026-08-10 | KPTG-TRANSMIT-003155 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-27 | Civilex-TRANSMIT-000314 | NA | Trade Partner | Stage 2 - sample submission - 100mm SN08 (Class 400) Slotted Flexi pipe | 0 | 1 | 0 | NA | APPROVED | 2026-07-27 | WF-006505 | NA | 2026-07-31 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-020244 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-27 | WilsonPD-TRANSMIT-000218 | SPARK-CRFI-KPG-000199, SPARK-CRFI-KPG-000183, SPARK-CRFI-KPG-000182, SPARK-CRFI-KPG-000345 & SPARK-CRFI-KPG-000190 | Trade Partner | Hydraulic & Civil Services - Updated Layouts | 13 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 380 | 2026-08-03 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001515 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-27 | WilsonPD-TRANSMIT-000219 | SPARK-CRFI-KPG-000182 | Trade Partner | Hydraulic Services - Updated Layout | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 381 | 2026-08-03 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001517 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-27 | HDRAus-TRANSMIT-000533 | NA | Consultant | Re: M3 Stage 4 - Document upload (Locked Drawings upload - HDRAus-TRANSMIT-000532) | 2 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 3963 | 2026-07-29 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-020614 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-27 | DLTS-TRANSMIT-000070 | NA | Trade Partner | S11-North & South eave gutters | 9 | 0 | 0 | NA | APPROVED | 2026-07-27 | WF-001335 | NA | 2026-08-05 |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-006240 | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-16 | BLUESF-TRANSMIT-000028 | NA | Trade Partner | M2-STR-BSF-SDRG-1101-(POUR 6) PRECAST DRAWINGS IFA | 8 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000201 | NA | 2026-02-11 |  | Drawings resubmitted as per Kapitol instruction | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-001993 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-27 | ADP-TRANSMIT-000377 | NA | Consultant | MEL4780 - M3S4 - Updated Electrical Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 3965 | 2026-07-29 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-020219 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-27 | WilsonPD-TRANSMIT-000216 | SPARK-CRFI-KPG-000338 | Trade Partner | Fwd: IFA Stormwater Pits and Lids | 0 | 5 | 0 | NA | APPROVED | 2026-07-27 | NA | NA | 2026-08-03 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-001677 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-27 | Civilex-TRANSMIT-000315 | NA | Trade Partner | Stage 1 - Swale Restoration Landscape Plan Revision G | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 4438 | 2026-08-07 |  | Terminated as request by Originator and confirmed by Charlie Johnstone to submit the updated drawings. | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-020223 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-07-27 | WPD-TRANSMIT-000099 | NA | Trade Partner | Re: HANWHA - O&M Manual Powerpack | 0 | 1 | 0 | NA | APPROVED | [5 empty] | Document/revision number is missing |  | 2026-07-27 | DRAFT-010460 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-27 | TTW-TRANSMIT-000201 | NA | Consultant | M3 Stage 2 Civil Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 4440 | 2026-08-07 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-27 | ARCST-TRANSMIT-000349 | NA | Trade Partner | M3S4 - Secure Corridor Bridge - Issued for Approval | 11 | 0 | 0 | NA | APPROVED | 2026-07-27 | WF-006510 | NA | 2026-07-31 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-020389 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-27 | WilsonPD-TRANSMIT-000222 | NA | Trade Partner | Cleaners Sink IFA (SPARK-CRFI-KPG-000132) | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision Incorrect |  | 2026-07-27 | KPTG-TRANSMIT-001510 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-27 | 4DW-TRANSMIT-000204 | NA | Consultant | Structural Documentation - Retaining Walls & Precast Columns | 9 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 423 | 2026-07-30 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-003180 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-16 | VIA Arch-TRANSMIT-000039 | NA | Consultant | Lift Core Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-01-17 |  | 184 |  |  |  |  | 2026-01-19 | KPTG-TRANSMIT-000523 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-27 | RDSBIM-TRANSMIT-000091 | NA | Trade Partner | 671CHP ¦ LEVEL 01 CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 695 | 2026-07-28 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-001436 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-27 | Auspan-TRANSMIT-000557 | NA | Trade Partner | Update IFCed precast shop drawings. level 3 | 3 | 0 | 0 | KPTG-IntCorr-001117 | APPROVED | [5 empty] | IFC - Waiting for Kim advise-KPTG-IntCorr-001117 OK TO IFC |  | 2026-08-04 | KPTG-TRANSMIT-003072 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D9 | 2026-07-27 | HDRAus-TRANSMIT-000013 | NA | Consultant | Client X Antenna Gantry - Updated Stair Location | 11 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 1466 | 2026-07-29 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-000053 | Closed | 11 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-27 | KPTG-TRANSMIT-019988 | NA | Trade Partner | M3S2 - O&M for Review | 0 | 1 | 0 | NA | APPROVED | 2026-07-27 | WF-006511 | NA | 2026-08-05 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-27 | Nilsen3-TRANSMIT-000217 | NA | Trade Partner | Re: Stage 2 ROPS 2C & 2D I/O List | 0 | 1 | 0 | NA | APPROVED | 2026-07-27 | WF-006239 | NA | 2026-07-27 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-020050 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-27 | Rinco-TRANSMIT-000065 | NA | Consultant | L2 to L7 Drawings Update for RFI | 82 | 0 | 0 | KPTG-IntCorr-001118 | APPROVED | 2026-07-28 | NA | 1575 | 2026-07-30 |  | QA Completed-Waiting for Michael advise-KPTG-IntCorr-001118 | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-003350 | Closed | 82 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-27 | Stowe-A-TRANSMIT-000665 | NA | Trade Partner | Re: STOWE - Comms As builts | 0 | 4 | 0 | NA | APPROVED |  | NA | NA |  |  | Stowe-A-SUBADVICE-002055 AS PER REQUEST |  | 2026-07-27 | KPTG-TRANSMIT-020051 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-27 | SMEPS-TRANSMIT-000243 | NA | Trade Partner | Electrical external Earthing | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | WF - 000555 | NA | 2026-07-31 |  | NA | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-001146 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-27 | KPTG-TRANSMIT-020016 | NA | Trade Partner | M3S2 - FIE OMM | 0 | 2 | 0 | NA | APPROVED | 2026-07-27 | WF-006513 | NA | 2026-08-05 |  |  | 2026-08-19 | 2026-08-26 | KPTG-TRANSMIT-021002 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-27 | SMEPS-TRANSMIT-000244 | NA | Trade Partner | SME Electrical Earthing layout IFA 1 | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | WF - 000556 | NA | 2026-08-31 |  | NA | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-001148 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-16 | VIA Arch-TRANSMIT-000040 | NA | Consultant | M2 - Redesign Coordination Issue | 7 | 0 | 0 | NA | APPROVED |  |  | 186 |  |  |  | 2026-01-19 | 2026-01-19 | KPTG-TRANSMIT-000529 | Closed | 7 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-27 | SMEPS-TRANSMIT-000358 | NA | Trade Partner | SME IFA - Documentation | 12 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect status, revision date |  | 2026-07-27 | KPTG-DA-007783 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-27 | TTW-TRANSMIT-000202 | NA | Consultant | M3 Stage 2 Civil Drawings | 0 | 1 | 0 | NA | APPROVED | [5 empty] | attached document with the same revision was previously submitted under transmittal TTW-TRANSMIT-000201 and is currently under review. |  | 2026-07-27 | KPTG-TRANSMIT-020054 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-27 | ARCST-TRANSMIT-000362 | NA | Trade Partner | C1 Cooling Tower Handrails - Issued for Construction | 32 | 0 | 0 | NA | APPROVED | 2026-07-27 | WF-006514 | NA | 2026-07-31 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-27 | fjc-TRANSMIT-000173 | NA | Consultant | Drawing Updates | 12 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 719 | 2026-07-30 |  | KPTG-SADV-005092 -1 drawing has been rejected. The remaining 12 drawings have been processed. | 2026-07-28 | 2026-07-28 | KPTG-SADV-005125 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-27 | fjc-TRANSMIT-000173 | NA | Consultant | Drawing Updates | 0 | 1 | 0 | NA | APPROVED | 2026-07-27 | WF-000863 | NA | 2026-08-03 |  | KPTG-SADV-005092 -5 drawing has been rejected. The remaining 2 drawings have been processed, but different WF | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-002851 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-27 | fjc-TRANSMIT-000173 | NA | Consultant | Drawing Updates | 0 | 1 | 0 | NA | APPROVED | 2026-07-27 | WF-000862 | NA | 2026-08-03 |  | KPTG-SADV-005092 - 5 drawing has been rejected. The remaining 2 drawings have been processed, but different WF | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-002851 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-27 | RDSBIM-TRANSMIT-000241 | NA | Trade Partner | LINDRUM ¦ LEVEL 03 PARTITION WALL LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 722 | 2026-07-30 |  |  | 2026-08-03 | 2026-08-03 | KPTG-SADV-005177 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-27 | RDSBIM-TRANSMIT-000240 | NA | Trade Partner | LINDRUM ¦ MEZZANINE REFLECTED CEILING PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 720 | 2026-07-30 |  |  | 2026-07-31 | 2026-07-31 | KPTG-SADV-005162 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-27 | 42636706-TRANSMIT-000023 | NA | Trade Partner | Re: EMS Communcations SLD | 2 | 0 | 0 | NA | APPROVED | 2026-07-27 | WF-000866 | NA | 2026-07-30 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-27 | KETE-TRANSMIT-000146 | NA | Trade Partner | Kete - Updated Lighting Details - IFC | 5 | 0 | 0 | KPTG-IntCorr-001258 | APPROVED | 2026-07-28 | WF-000871 | NA | 2026-08-03 |  | KPTG-IntCorr-001258 - requested guidance, but no resonance yet. | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-002993 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-02 | Nilsen3-TRANSMIT-000114 | NA | Trade Partner | Nilsen Drawings for Construction | 14 | 0 | 0 | NA | APPROVED | [5 empty] | IFC Review not required on this project as per KG instruction. Updated Bim & Document register |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-27 | NXES-TRANSMIT-000065 | NA | Trade Partner | Level 11 (Typical upto 27) Electrical Layout | 2 | 0 | 0 | KPTG-IntCorr-001259 | APPROVED | 2026-07-28 | NA | 723 | 2026-08-04 |  | KPTG-IntCorr-001259 - requested guidance, but no resonance yet. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-27 | KPTG-IntCorr-001254 | NA | Trade Partner | Level 5/6 Glass Box Sample | 0 | 1 | 0 | NA | APPROVED | 2026-07-27 | WF-000868 | NA | 2026-07-30 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-27 | KPTG-IntCorr-001255 | NA | Trade Partner | Re: GL04 Fritted Glass - Level 10 Soffit | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-001256 - Type is incorrect | 2026-07-27 | 2026-07-27 | KPTG-IntCorr-001256 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-27 | PTA-TRANSMIT-000033 | NA | Consultant | Stair and Lift Core Updates | 4 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 511 | 2026-08-04 |  | NA | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-000968 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-27 | PTA-TRANSMIT-000034 | NA | Consultant | Concrete Profile Plans - Revised Hobs | 3 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 513 | 2026-08-04 |  | NA | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-000972 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-27 | PTA-TRANSMIT-000035 | NA | Consultant | Ground Floor - Revised Mud Room & DCIO Whips | 2 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 515 | 2026-08-04 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-000976 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-27 | VIA Arch-TRANSMIT-000206 | NA | Consultant | Updated Door Schedules IFBP | 9 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-DA-003932 |  | 2026-07-27 | KPTG-DA-003932 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-27 | KPTG-SADV-006839 | NA | Trade Partner | Mayfield USB-XX IFC Drawing Set | 39 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 1521 | 2026-08-03 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-27 | D&E-TRANSMIT-000037 | NA | Trade Partner | ISSUED FOR APPROVAL CHW & CT SCHEMATICS | 12 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong document number |  | 2026-07-27 | KPTG-TRANSMIT-000725 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-27 | WSP ANZ-TRANSMIT-000084 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit (Mechanical Document | 8 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 1523 | 2026-08-03 |  |  | 2026-08-14 | 2026-08-14 | KPTG-DA-004221 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-16 | PARR-TRANSMIT-000028 | NA | Trade Partner | Fuel Services - Generator Fuel Control Panels | 1 | 0 | 0 | Clarification Required - KPTG-IntCorr-000881 | REJECTED | [5 empty] | Rejected by Nick Kumar KPTG-IntCorr-000884 |  | 2026-01-19 | KPTG-TRANSMIT-002857 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-27 | RDSDG-TRANSMIT-000003 | NA | Trade Partner | NXM3S6 - HY - Drainage Shop Drawings - Block 1, Carpark & North Zones | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong Document extension |  | 2026-07-29 | KPTG-TRANSMIT-000723,KPTG-TRANSMIT-000802 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-27 | WSP ANZ-TRANSMIT-000087 | NA | Consultant | SP - Vertical Transportation Services Specification | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 1527 | 2026-08-03 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-007467 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-27 | Aurecon-TRANSMIT-000127 | NA | Consultant | Hydraulic Services - LOD300 Issued for Contract | 54 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 517 | 2026-08-04 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-001049 | Closed | 54 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-27 | WSP ANZ-TRANSMIT-000088 | NA | Consultant | WSP - Mechanical Services Specification | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 1528 | 2026-08-03 |  |  | 2026-08-14 | 2026-08-14 | KPTG-DA-004222 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-27 | SMEPS-TRANSMIT-000011 | NA | Trade Partner | STAGE 6 - TELECOMMUNICATION SERVICES - OVERALL INGROUND SITE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 520 | 2026-08-04 |  | MEPS-TRANSMIT-000010 superseded | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-000861 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-27 | WSP ANZ-TRANSMIT-000089 | NA | Consultant | WSP Electrical Services Documents | 3 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 1529 | 2026-08-03 |  |  | 2026-08-14 | 2026-08-14 | KPTG-DA-004225 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-27 | WSP ANZ-TRANSMIT-000090 | NA | Trade Partner | WSP Updated - Electrical Services Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 1532 | 2026-08-03 |  |  | 2026-08-14 | 2026-08-14 | KPTG-DA-004226 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-27 | WSP ANZ-TRANSMIT-000091 | NA | Consultant | WSP Updated - Hydraulic Services Drawings | 6 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 1533 | 2026-08-03 |  |  | 2026-08-14 | 2026-08-14 | KPTG-DA-004228 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-27 | SMEPS-TRANSMIT-000009 | NA | Trade Partner | STAGE 6 - ELECTRICAL SERVICES - OVERALL INGROUND SITE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 522 | 2026-08-04 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-000893 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-27 | PTA-TRANSMIT-000036 | NA | Consultant | Northe Elevation Bianco Panel Setout | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 518 | 2026-08-04 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-000977 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-16 | VAE-Grp-TRANSMIT-000106 | NA | Trade Partner | MECHANICAL - GROUND LEVEL - DAY 1 DRAWINGS | 3 | 0 | 0 | NA | APPROVED | 2026-01-18 | WF-000711 | 834 | 2026-01-20 |  |  | 2026-01-19 | 2026-01-19 | KPTG-TRANSMIT-002510 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-28 | ARCH-TRANSMIT-000169 | NA | Consultant | MLC - SPR - ISC - Capping Beam update | 4 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 425 | 2026-07-31 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-003186 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-28 | ADP-TRANSMIT-000036 | NA | Consultant | ADP MEL3393 - Updated Reg126 for Hydraulic and Mechanical | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | UPDATED REGISTER AND TRANSMITRRED TO CONCERNED:KPTG-TRANSMIT-003172 |  | 2026-07-28 | KPTG-TRANSMIT-003172 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-28 | DLTS-TRANSMIT-000071 | NA | Trade Partner | S10-HV Room-IFA Issue | 81 | 0 | 0 | NA | APPROVED | 2026-07-28 | WF-001336 | NA | 2026-08-06 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-006468 | Closed | 81 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-28 | FNSTR8-TRANSMIT-000005 | NA | Trade Partner | Sample Submission: Glass | 0 | 1 | 0 | NA | APPROVED | 2026-07-28 | WF - 0001105 | NA | 2026-08-03 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-27 | Jangho-TRANSMIT-000271 | NA | Trade Partner | 4B3A__Podium Level 1~11 Shop Drawing_Rev 02_For Approval | 56 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 1039 | 2026-08-05 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003524 | Closed | 56 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-27 | Jangho-TRANSMIT-000272 | NA | Trade Partner | 4B3B__Podium Level 1~5 Shop Drawing_Rev 02_For Approval | 84 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 1032 | 2026-08-04 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-003491 | Closed | 84 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-27 | Jangho-TRANSMIT-000274 | NA | Trade Partner | 4B3B__Podium Level 1~5 Shop Drawing_Rev 02_For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 1032 | 2026-08-04 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-003491 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-27 | EFWC-TRANSMIT-000003 | NA | Trade Partner | Shop Drawings (Rev. A) - (S2) - Kapitol - V02272 - District Living - 24 Little Docklands Drive, Docklands | 4 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | QA ERROR - DOC NO - REJECTED |  | 2026-07-27 | rejected: KPTG-TRANSMIT-003100 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-27 | TIVINTL-TRANSMIT-000001 | NA | Trade Partner | Off-site Prototype Shop Drawings of District Living Docklands ( DL628) | 14 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | rejected: QA ERROR |  | 2026-07-27 | KPTG-TRANSMIT-003092 | Closed | 14 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-27 | L.E.S.-TRANSMIT-000012 | NA | Trade Partner | Power outlets and Switches | 0 | 5 | 0 | NA | APPROVED | 2026-07-28 | WF-001037 | NA | 2026-08-04 |  |  | 2026-08-25 | 2026-08-25 | WF-001227 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-16 | KETE-TRANSMIT-000030 | NA | Trade Partner | Updated thermal report | 0 | 1 | 0 | NA | APPROVED | 2026-01-16 | WF-000712 | 832 | 2026-01-21 |  |  | 2026-01-22 | 2026-01-22 | KPTG-TRANSMIT-002562 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-27 | BIMF-TRANSMIT-000017 | NA | Trade Partner | Level 4 Hydraulic Setout, Rev D | 2 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 1037 | 2026-08-04 |  |  | 2026-08-18 | 2026-08-19 | KPTG-TRANSMIT-003510 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-27 | BIMF-TRANSMIT-000018 | NA | Trade Partner | LEVEL 01 CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | REJECTED | 2026-07-27 | NA | 1030 | 2026-08-04 |  | rejected: QA ERROR |  | 2026-07-27 | KPTG-TRANSMIT-003105 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-27 | Jangho-TRANSMIT-000276 | NA | Trade Partner | L2, L3 Hydraulic Setout, Preliminary For Approval | 8 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 1039 | 2026-08-05 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003524 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-28 | SMEPS-TRANSMIT-000084 | NA | Trade Partner | Dog Box Fire Seal - Boss Fire Transit Box | 0 | 1 | 0 | NA | APPROVED | 2026-07-28 | WF-001339 | NA | 2026-08-07 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-006740 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-28 | WAM-TRANSMIT-000835 | NA | Consultant | IFC A10 Update | 26 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 1038 | 2026-07-31 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-003178 | Closed | 26 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-28 | VERTIV-TRANSMIT-000055 | NA | Trade Partner | NEXT DC GE01 _ ARCHITECTURAL DRAWINGS (FOA-1 & FOA-3) | 7 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with revision date. |  | 2026-07-28 | KPTG-TRANSMIT-001302 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-28 | Baigents-TRANSMIT-000091 | NA | Trade Partner | Site Storage - Carport Steel - Issued for Construction | 75 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing title inside the drawing and in Aconex seem different |  | 2026-07-28 | KPTG-TRANSMIT-001513 | Closed | 75 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-28 | MCGC-TRANSMIT-000011 | NA | Consultant | Updated Landscape Drawing Set | 56 | 0 | 0 | NA | REJECTED | [5 empty] | Duplication of MCGC-TRANSMIT-000012 |  | 2026-07-28 | KPTG-SADV-005556 | Closed | 56 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-16 | Nick's Email (Mirage Doors) | NA | Trade Partner | ARC - DOORS ¦ RR300P ROL002 3600W x 2400H, RR300P ROL002 1800W x 2400H AND RR300P ROL002 2400W x 2400H | 3 | 0 | 0 | NA | APPROVED | 2026-01-16 | WF-000705 | NA | 2026-01-22 |  |  | 2026-01-19 | 2026-01-23 | KPTG-IntCorr-000929 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-28 | PFP PL-TRANSMIT-000024 | NA | Trade Partner | S11 Level 2 IFA | 1 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 1536 | 2026-08-04 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-006332 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-28 | MCGC-TRANSMIT-000012 | NA | Consultant | Updated Landscape Package | 56 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Revision and revision history of document are irrelevant to previous revision: KPTG-SADV-005555 |  | 2026-07-28 | KPTG-SADV-005555 | Closed | 56 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-28 | WilsonPD-TRANSMIT-000223 | NA | Trade Partner | Re: Cleaners Sink IFA (SPARK-CRFI-KPG-000132) | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document revision is incorrect |  | 2026-07-28 | KPTG-TRANSMIT-001514 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-28 | PFP PL-TRANSMIT-000025 | NA | Trade Partner | S9-10-11 Level 3 IFA | 3 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 1538 | 2026-08-04 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-006372 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-28 | Auspan-TRANSMIT-000105 | NA | Trade Partner | Precast shop drawings for approval. Stage 2. | 42 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Document Number and title has not mentioned in the titlebloc:KPTG-SADV-005558 |  | 2026-07-28 | KPTG-SADV-005558 | Closed | 42 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-28 | INGEN3D-TRANSMIT-000719 | NA | Trade Partner | Re: I3D - M3 Stage 4 - Link Bridge - Precast Panels - IFA | 42 | 0 | 0 | NA | REJECTED | [5 empty] | Revision not updated |  | 2026-07-28 | KPTG-DA-007804 | Closed | 42 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-28 | Auspan-TRANSMIT-000106 | NA | Trade Partner | Precast shop drawings for approval. Stage 2 | 42 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Duplicate ofAuspan-TRANSMIT-000105:KPTG-SADV-005559 |  | 2026-07-28 | KPTG-SADV-005559 | Closed | 42 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-28 | SES AU-TRANSMIT-000091 | NA | Trade Partner | Motion Detector - 90 Degree - Tech Data - IFA | 0 | 1 | 0 | NA | APPROVED | 2026-07-28 | WF-000421 | NA | 2026-08-03 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-001119 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-28 | Auscool-TRANSMIT-000072 | NA | Trade Partner | Level 3&4 - IFA drawings | 10 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 1579 | 2026-08-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-28 | ADP-TRANSMIT-000380 | NA | Consultant | ADP - Updated CSMS Schedules | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Documents submitted in Excel format |  | 2026-07-28 | KPTG-DA-007800 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-16 | Nick's Email (Procore - 287) | NA | Consultant | PWC Approved - Water and Sewer drawings | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Registered and transmitted via Aconex |  | 2026-01-18 | KPTG-TRANSMIT-002492 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-28 | RDSBIM-TRANSMIT-000294 | NA | Trade Partner | NXM3S4 ¦ LEVEL 01 ¦ C-1-044 ACC WC (RH) FLOOR FINISHES LAYOUT AND ELEVATION | 1 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 3970 | 2026-07-31 |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-020276 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-28 | BIMF-TRANSMIT-000019 | NA | Trade Partner | L05 Drainage layouts | 2 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 1042 | 2026-08-05 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-003461 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-28 | Auspan-TRANSMIT-000558 | NA | Trade Partner | Update IFCed precast shpo drawings | 4 | 0 | 0 | KPTG-IntCorr-001137 | APPROVED | [5 empty] | IFC - Waiting for Kim advise-KPTG-IntCorr-001137 OK TO IFC |  | 2026-08-04 | KPTG-TRANSMIT-003074 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-28 | Auspan-TRANSMIT-000558 | NA | Trade Partner | Update IFCed precast shop drawings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - Latest IFA rejected- DRAFT-010622 |  | 2026-07-28 | DRAFT-010622 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-28 | JFS-AU-TRANSMIT-000004 | NA | Consultant | Updated Facade Specification (Rev 02) | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Status Incorrect |  | 2026-07-28 | KPTG-DA-000483 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-28 | ELLISAIR-TRANSMIT-000137 | NA | Trade Partner | Carbon Steel Pipework | 0 | 1 | 0 | NA | APPROVED | 2026-07-21 | WF-001342 | NA | 2026-08-07 |  | Workflow WF-001342 has been terminated as advised by Project Coordinator upon request from Trade Partner who need to resubmit the document as a separate submittal. |  | 2026-07-29 | KPTG-IntCorr-001900 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-28 | Detail-TRANSMIT-000020 | NA | Trade Partner | Re: DOOR HARDAWRE SCHEDULE | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect reference code |  | 2026-07-28 | KPTG-DA-007803 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-28 | ADP-TRANSMIT-000038 | NA | Consultant | ADP MEL3393 - Updated Electrical Reg126 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | updated document Register & transmitted to concerned:KPTG-TRANSMIT-003175 |  | 2026-07-28 | KPTG-TRANSMIT-003175 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-28 | D&E-TRANSMIT-000945 | NA | Trade Partner | Leak Detection Layouts - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-28 | WF-006520 | NA | 2026-08-03 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-020465 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-28 | PFP PL-TRANSMIT-000100 | NA | Trade Partner | Wet Fire Services Schematic IFC | 1 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 3972 | 2026-08-06 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-16 | Endfire-TRANSMIT-000053 | NA | Trade Partner | EndFire IFC Drawings | 12 | 0 | 0 | KPTG-IntCorr-000882 | REJECTED | [5 empty] | QA Error - Resubmitted EndFire Trn 54 |  | 2026-01-17 | KPTG-IntCorr-000882 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-28 | Jangho-TRANSMIT-000278 | NA | Trade Partner | Tower Level 6~12 Cast in Channel Shop Drawing | 3 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 1044 | 2026-08-05 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-003596 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-28 | ADP-TRANSMIT-000379 | NA | Consultant | MEL4780 - Updated Reports | 0 | 2 | 0 | NA | APPROVED | [5 empty] | For Distribution |  | 2026-07-28 | KPTG-TRANSMIT-020062 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-28 | NXES-TRANSMIT-000079 | NA | Trade Partner | Stage 2 Landscape Electrical Layout | 1 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 427 | 2026-08-06 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-28 | SMEPS-TRANSMIT-000361 | NA | Trade Partner | Transmittal: Comms Containment Layouts - Ground Floor, Level 1 & Roof Plant (Issued for Construction) | 9 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Revision number mismatch |  | 2026-07-28 | KPTG-DA-007807 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-28 | EMBIND-TRANSMIT-000001 | NA | Trade Partner | Embelton Gym Isolation System Drawing | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected(KPTG-TRANSMIT-003184) |  | 2026-07-28 | KPTG-TRANSMIT-003184 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-28 | D&E-TRANSMIT-000946 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - GROUND - CHW PIPE LAYOUT - ZONE 6 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-28 | KPTG-TRANSMIT-020068 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-20 | KPTG-WTRAN-000986 | NA | Trade Partner | DOOR HARDWARE SCHEDULE_20260602 | 0 | 1 | 0 | NA | APPROVED | 2026-07-20 | WF - 000548 | NA | 2026-07-27 |  | NA | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001126 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-28 | RDSBIM-TRANSMIT-000022 | NA | Trade Partner | GROUND FLOOR RCP LAYOUT | 3 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 414 | 2026-08-07 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-001817 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-28 | KYFP-TRANSMIT-000011 | NA | Trade Partner | Fire protection Material | 0 | 6 | 0 | NA | APPROVED | 2026-07-28 | WF-001071 | NA | 2026-08-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-28 | KPTG-TRANSMIT-020059 | NA | Client | Stage 2 Protection Study LV SCCS Report - IFCN-7 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution only as advised by Fabian |  | 2026-07-28 | KPTG-TRANSMIT-020069 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-19 | CRSol-TRANSMIT-000074 | NA | Trade Partner | M3S4 ZONE C1 - CRS HAC SHOPDRAWINGS ISSUED FOR APPROVAL REV. A | 10 | 0 | 0 | NA | REJECTED | [5 empty] | The revision date is incorrect |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-28 | ZIA-TRANSMIT-000132 | NA | Trade Partner | M3 S4 SLA & DP SENSOR LOCATION OVERALL DRAWINGS (FC-1) | 4 | 0 | 0 | NA | REJECTED | [5 empty] | IFC received prior to IFA |  | 2026-07-28 | KPTG-DA-007811 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-28 | NXES-TRANSMIT-000023 | NA | Trade Partner | External, L06 to L08 Electrical Layout | 1 | 0 | 0 | NA | APPROVED | 2026-07-28 | WF-000872 | NA | 2026-08-03 |  | KPTG-IntCorr-001283 - As per direction from Mark,we terminate the WF-000872 and creating new WF in BIM. | 2026-08-03 | 2026-08-03 | KPTG-IntCorr-001283 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-28 | D&E-TRANSMIT-000948 | NA | Trade Partner | ISSUED FOR APPROVAL / CONSTRUCTION - BUILDERS WORKS LAYOUTS & ELEVATION VIEWS | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status difference |  | 2026-07-28 | KPTG-DA-007817 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-28 | D&E-TRANSMIT-000950 | NA | Trade Partner | MCC Drawings - Issued for Approval | 7 | 0 | 0 | NA | REJECTED | [5 empty] | Title difference |  | 2026-07-28 | KPTG-DA-007819 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-28 | ARCH-TRANSMIT-000170 | NA | Consultant | MLC - SPR - ISC - RCP update | 2 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 429 | 2026-07-31 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-003219 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-28 | PROLMC-TRANSMIT-000009 | NA | Trade Partner | Proline Shop Drawing 0202 Update | 1 | 0 | 0 | NA | APPROVED | 2026-07-28 | WF-001344 | NA | 2026-07-30 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-007228 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-28 | NXES-TRANSMIT-000080 | NA | Trade Partner | Boom Gate System Drawings | 7 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Document Numbering is incorrect:KPTG-SADV-005562 |  | 2026-07-28 | KPTG-SADV-005562 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-28 | KALLIBRE-TRANSMIT-000015 | NA | Trade Partner | IFC - Door Frames | 61 | 0 | 0 | NA | REJECTED | [5 empty] | Date is missing previous revision missing inside history block Same revision already submitted |  | 2026-07-28 | KPTG-TRANSMIT-001524 | Closed | 61 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-28 | Stowe-A-TRANSMIT-000666 | NA | Trade Partner | Comms As Built | 4 | 0 | 0 | NA | REJECTED | [5 empty] | The document M3-TEL-STO-SDRG-B-0201-0001 has been submitted directly as an As-Built document without prior IFC submission and approval. |  | 2026-07-28 | KPTG-SADV-006931 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-28 | BTWA-TRANSMIT-000095 | NA | Trade Partner | Cleaning up sample register from stage 1 | 0 | 4 | 0 | NA | REJECTED | [5 empty] | Revision & covering sheet of all thees as Built Tech data require updation:KPTG-SADV-005565 |  | 2026-07-28 | KPTG-SADV-005565 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-01-19 | DI-TRANSMIT-000134 | NA | Trade Partner | HFF - IFC updtae (gridlines) | 16 | 0 | 0 | NA | APPROVED | [5 empty] | Teams message from Alex G - no action required with this - I will transmit to project team |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-28 | Baigents-TRANSMIT-000092 | NA | Trade Partner | SITE STORAGE - CARPORT STEEL | 71 | 0 | 0 | NA | REJECTED | [5 empty] | Document title incorrect |  | 2026-07-28 | KPTG-TRANSMIT-001525 | Closed | 71 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-28 | D&E-TRANSMIT-000944 | NA | Trade Partner | ISSUED AS BUILT - GROUND & LEVEL 01 - MECHANICAL PIPE LAYOUTS | 6 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 4442 | 2026-08-07 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020161 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-28 | WilsonPD-TRANSMIT-000224 | NA | Trade Partner | Re: Cleaners Sink IFA (SPARK-CRFI-KPG-000132) | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision incorrect |  | 2026-07-28 | KPTG-TRANSMIT-001519 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-28 | WGAVIC-TRANSMIT-000171 | NA | Consultant | M2 - Blockwork and S11 Retaining Walls - Issued for Construction | 17 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected : Difference in status |  | 2026-07-28 | KPTG-DA-003975 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-28 | ASV-TRANSMIT-000192 | NA | Trade Partner | Hydraulic Data Sheet - External Trench Grates | 0 | 1 | 0 | NA | APPROVED | 2026-07-28 | WF-006527 | NA | 2026-08-03 |  |  | 2026-08-17 | 2026-08-17 | KPTG-TRANSMIT-020642 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-28 | Detail-TRANSMIT-000022 | NA | Trade Partner | DOOR HARDAWRE SCHEDULE | 0 | 1 | 0 | NA | APPROVED | 2026-07-28 | NA | 3975 | 2026-08-03 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-07-28 | Nilsen3-TRANSMIT-000243 | NA | Trade Partner | Re: Stage-3 BTU 3A and 3B Battery sizing calculation data | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect revision |  | 2026-07-28 | KPTG-DA-007821 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-28 | Tradetec-TRANSMIT-000488 | NA | Trade Partner | IFC - Stage 2 - LVP5, LVP6, CP13 | 3 | 0 | 0 | NA | REJECTED | [5 empty] | he attached document M3-TEL-TSA-SDRG-0-0201-6055 seem mismatch in the document numbering in Aconex and inside drawing. |  | 2026-07-28 | KPTG-SADV-006934 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-07-28 | WPD-TRANSMIT-0000100 | NA | Trade Partner | HANWHA - O&M Manual Powerpack | 0 | 1 | 0 | NA | APPROVED | 2026-07-28 | WF-000543 | NA | 2026-07-31 |  | WPD-TRANSMIT-000099 |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-28 | ARCST-TRANSMIT-000363 | NA | Trade Partner | Stage 4 Davit Arms - Issued for Approval | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number, title included in Aconex reference number . |  | 2026-07-28 | KPTG-DA-007824 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-19 | HDRAus-TRANSMIT-000357 | NA | Consultant | Architectural FC issues - 16 Jan 2026 | 16 | 0 | 0 | NA | APPROVED | 2026-01-19 |  | 1815 | 2026-01-23 |  |  |  | 2026-01-20 | KPTG-TRANSMIT-011655 | Closed | 33 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-28 | D&E-TRANSMIT-000949 | NA | Trade Partner | Functional Description - Issued AsBuilt | 0 | 1 | 0 | NA | REJECTED | [5 empty] | attached documents seem missing of revision number in inside document. |  | 2026-07-28 | KPTG-SADV-006936 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-28 | Civilex-TRANSMIT-000317 | NA | Trade Partner | Stage 2 - sample submission - CTCR 5% Mix Design - Resource Co (Heavy duty Pavement) | 0 | 1 | 0 | NA | APPROVED | 2026-07-28 | WF-006528 | NA | 2026-08-07 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-020300 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-28 | ZIA-TRANSMIT-000134 | NA | Trade Partner | Re: M3 S4 SLA & DP SENSOR LOCATION DRAWINGS WITH COMMS TRAY | 11 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 3977 | 2026-08-03 |  | Terminated As instructed by Kazimir |  | 2026-08-17 | KPTG-TRANSMIT-020647 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-28 | KPTG-TRANSMIT-020065 | NA | Trade Partner | Fuji O&M for Review | 0 | 1 | 0 | NA | APPROVED | 2026-07-28 | WF-006531 | NA | 2026-08-06 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-28 | D&E-TRANSMIT-000951 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - SIDESTREAM FILTRATION SCHEMATIC | 1 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 4444 | 2026-08-07 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-020228 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-28 | ASV-TRANSMIT-000193 | NA | Trade Partner | Revised Hydraulic Sample | 0 | 1 | 0 | NA | APPROVED | 2026-07-28 | WF-006532 | NA | 2026-07-31 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-020249 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-28 | RDSBIM-TRANSMIT-000023 | NA | Trade Partner | GROUND FLOOR PARTITION WALL PLAN AND ELEVATIONS | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Mismatch in revision history, kindly change the revision date inside the drawings as 28-07-2026. Kindly rectify and resubmit the same revision again. Kindly submit the whole pack in return in avoid any missing out. |  | 2026-07-28 | KPTG-TRANSMIT-001347 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-28 | ADP-TRANSMIT-000128 | NA | Consultant | ADP MEL4680 - Updated Mechanical Drawings | 28 | 0 | 0 | NA | APPROVED | 2026-07-28 | 416 | NA | 2026-08-07 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-001465 | Closed | 28 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-28 | INGEN3D-TRANSMIT-000720 | NA | Trade Partner | I3D - M3 Stage 4 - Link Bridge - Precast Panels - IFA | 40 | 0 | 0 | NA | APPROVED | 2026-07-28 | WF-006533 | NA | 2026-08-03 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-28 | M.2-TRANSMIT-000068 | NA | Trade Partner | Basement Lux Levels | 2 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 1583 | 2026-08-05 |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-003029 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-02 | TTW-IntCorr-000085 | NA | Consultant | FP1.4 PBDB PERFORMANCE BASED DESIGN BRIEF DRAFT | 0 | 1 | 0 | NA | APPROVED | 2025-12-02 | WF-000050 | NA | 2025-12-04 |  | WF-000050 TERMINATED AS PER KPTG-DA-000360 | 2025-12-04 | 2025-12-03 | KPTG-DA-000360 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-19 | INDS-TRANSMIT-000025 | NA | Trade Partner | Wet Fire - Basement 1 Peno Layout | 1 | 0 | 0 | NA | APPROVED |  | WF-000102 |  |  |  |  | 2026-01-19 | 2026-01-19 | KPTG-TRANSMIT-001580 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-28 | INDS-TRANSMIT-000052 | NA | Trade Partner | : L4 to L7 Zone 4 - Penetration Layout | 4 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to drawing number issues - KPTG-SADV-003756 |  | 2026-07-28 | KPTG-SADV-003756 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-28 | INDS-TRANSMIT-000053: | NA | Trade Partner | L4 to L7 - Zone & Zone 5 | 8 | 0 | 0 | KPTG-IntCorr-001144 | APPROVED |  | NA | 1623 |  |  | Waiting for advise on IFC - KPTG-IntCorr-001144 | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003266 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-28 | INDS-TRANSMIT-000054 | NA | Trade Partner | Dry Fire - Ground & Level 1 | 10 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to drawing number issues - KPTG-SADV-003757 |  | 2026-07-28 | KPTG-SADV-003757 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-28 | RDSBIM-TRANSMIT-000088 | NA | Trade Partner | GREYSTAR GROUND FLOOR STAIR MID LANDING LAYOUT | 1 | 0 | 0 | KPTG-IntCorr-001145 | APPROVED | 2026-07-31 | NA | 1616 | 2026-08-07 |  | QC- Done; waiting for Michael to confirm- KPTG-IntCorr-001145 | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-003315 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-28 | INDS-TRANSMIT-000056: | NA | Trade Partner | Dry Fire - Ground | 5 | 0 | 0 | KPTG-IntCorr-001146 | APPROVED | 2026-07-31 | NA | 1626 |  |  | IFC - Kapitol PC to advise - KPTG-IntCorr-001146 | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003269 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-28 | Auspan-TRANSMIT-000559 | NA | Trade Partner | : Re: ME304 - not up to date | 1 | 0 | 0 | KPTG-IntCorr-001147 | APPROVED |  | NA | NA |  |  | IFC - Kapitol PC to advise - KPTG-IntCorr-001147 OK to proceed IFC-KPTG-TRANSMIT-003021 |  | 2026-07-30 | KPTG-TRANSMIT-003021 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-28 | M.2-TRANSMIT-000039 | NA | Trade Partner | and M.2-TRANSMIT-000029 Electrical Services Penetration layouts | 10 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 1581 | 2026-08-05 |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-003033, KPTG-TRANSMIT-003036 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-28 | INDS-TRANSMIT-000057 | NA | Trade Partner | L2 to L7 Zone 3 - Added Peno | 1 | 0 | 0 | KPTG-IntCorr-001148 | APPROVED | 2026-08-03 | NA | 1636 |  |  | IFC - Kapitol PC to advise - KPTG-IntCorr-001148 Review # 1621 is Void and initiate 1636 - 3/8/26 Review void, to update the drawing |  | 2026-08-10 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-19 | Highbu-TRANSMIT-000037 | NA | Trade Partner | Revised Drainage Layout - IFC | 1 | 0 | 0 | NA | APPROVED | 2026-01-19 |  | 517 | 2026-01-24 |  |  | 2026-02-05 | 2026-02-05 | KPTG-SADV-002906 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-28 | INDS-TRANSMIT-000055 | NA | Trade Partner | : Drawing no longer in use | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Marked as no longer in use; no action required as drawings are not registered . |  | 2026-07-28 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-13 | Auspan-TRANSMIT-000494 | NA | Trade Partner | : Update IFCed shop drawings. Level 3. | 11 | 0 | 0 | KPTG-IntCorr-000936 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise -KPTG-IntCorr-000936 OK TO IFC-KPTG-TRANSMIT-003252 |  | 2026-08-19 | KPTG-TRANSMIT-003252 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-28 | KPTG-IntCorr-001265 | NA | Trade Partner | HERITAGE WORKFLOW | 0 | 5 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-001267 - 1 document duplicate,1 tittle error,1 type is incorrect. | 2026-07-28 | 2026-07-28 | KPTG-IntCorr-001267 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-28 | NXES-TRANSMIT-000066 | NA | Trade Partner | Level 11 Lighting Layout (Typical upto 27) | 1 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 724 | 2026-08-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-28 | EFP-TRANSMIT-000035 | NA | Trade Partner | Commission & Energisation Plans | 0 | 2 | 0 | Kapitol Advice awaits: KPTG-IntCorr-000725 | APPROVED |  | NA | NA |  |  |  |  | 2026-07-29 | KPTG-IntCorr-000725 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-28 | EFP-TRANSMIT-000036 | NA | Trade Partner | Commission & Energisation Plans | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Diplicate of EFP-TRANSMIT-000035 |  | 2026-07-28 | KPTG-IntCorr-000726 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-28 | LGCE-TRANSMIT-000070 | NA | Trade Partner | Level 2 IFC | 2 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 698 | 2026-08-04 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-001702 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-28 | ccair-TRANSMIT-000031 | NA | Trade Partner | Mechanical Services core penetrations Builders works IFC [0] | 2 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 701 | 2026-08-04 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-001704 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-28 | RDSBIM-TRANSMIT-000087 | NA | Trade Partner | 671CHP LEVEL 03 CONCRETE PROFILE KEYPLAN AND SECTION | 3 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 699 | 2026-08-04 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-001507 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-28 | Auspan-TRANSMIT-000117 | NA | Trade Partner | 671CHP LEVEL 03 CONCRETE PROFILE KEYPLAN AND SECTION | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Register drawing and transmit to everyone (Kian) KPTG-TRANSMIT-001449 |  | 2026-07-28 | KPTG-TRANSMIT-001449 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-19 | CRSol-TRANSMIT-000075 | NA | Trade Partner | M3S4 Zone C2 CRS HAC SHOPDRAWINGS ISSUED FOR APPROVAL REV. A | 18 | 0 | 0 | NA | REJECTED | [5 empty] | The revision date is incorrect. - KPTG-TRANSMIT-011550 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-21 | Nilsen3-TRANSMIT-000075 | NA | Trade Partner | Nilsen Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-07-21 | WF-001286 | NA | 2026-07-31 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-006752 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-28 | KPTG-TRANSMIT-000701 | NA | Trade Partner | PCF Concrete Mix Design | 0 | 1 | 0 | NA | APPROVED | 2026-07-28 | NA | 527 | 2026-07-08 |  |  | 2026-07-31 | 2026-08-03 | KPTG-TRANSMIT-000804 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-28 | KPTG-TRANSMIT-000702 | NA | Trade Partner | PPP Concrete Mix Design | 0 | 1 | 0 | NA | APPROVED | 2026-07-28 | NA | 529 | 2026-08-05 |  |  | 2026-07-31 | 2026-08-03 | KPTG-TRANSMIT-000812 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-28 | RDSDG-TRANSMIT-000002 | NA | Trade Partner | NXM3S6 - HY - Drainage Shop Drawings - Block 1, Carpark & North Zones [IFA] | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Naming Conventions |  | 2026-07-28 | KPTG-SADV-000513 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-28 | RDSDG-TRANSMIT-000004 | NA | Trade Partner | Drainage Shop Drawings - Block 1, Carpark & North Zones | 3 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 535 | 2026-08-05 |  | NA | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001024 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-28 | Baigents-TRANSMIT-000022 | NA | Trade Partner | Block 01 - Panel P14 - Additional dimension added - Issued for Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | update register only |  | 2026-07-28 | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-28 | EUKAI-TRANSMIT-000020 | NA | Consultant | Preliminary Signage & Linemarking Drawings | 7 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 533 | 2026-08-05 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-000846 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-28 | KPTG-TRANSMIT-000716 | NA | Consultant | NEXTDC review Arch GAs (GF) and CPPs (GF+L1) | 10 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 531 | 2026-08-05 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-28 | KPTG-TRANSMIT-000717 | NA | Consultant | NEXTDC review Arch Master Site Plan | 1 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 531 | 2026-08-05 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-28 | D&E-TRANSMIT-000041 | NA | Trade Partner | ISSUED FOR APPROVAL - ROOF - CHW & CT SCHEMATICS | 12 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 537 | 2026-08-05 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-19 | NXT-TRANSMIT-001194 / Sienergy-TRANSMIT-000013 | NA | Trade Partner | M3S4 GA Rev03 | 1 | 0 | 0 | NA | APPROVED | 2026-01-19 | WF-003854 |  | 2026-02-04 |  |  |  | 2026-02-02 | NXT-WTRAN-001660 KPTG-TRANSMIT-012305 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-28 | D&E-TRANSMIT-000043 | NA | Trade Partner | ISSUED FOR APPROVAL - Ground & Level 1 - Ductwork Layouts | 6 | 0 | 0 | KPTG-IntCorr-000365 | APPROVED | 2026-07-29 | NA | 543 | 2026-08-04 |  | NA |  |  |  | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-28 | D&E-TRANSMIT-000044 | NA | Trade Partner | ISSUED FOR APPROVAL - CHW SCHEMATICS | 8 | 0 | 0 | KPTG-IntCorr-000367 | APPROVED | 2026-07-29 | NA | 561 | 2026-08-04 |  | NA |  |  |  | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-28 | D&E-TRANSMIT-000045 | NA | Trade Partner | ISSUED FOR APPROVAL - GROUND FLOOR DUCT WORK LAYOUT ZONE 1 & 3 | 2 | 0 | 0 | KPTG-IntCorr-000366 | APPROVED | 2026-07-29 | NA | 547 | 2026-08-04 |  | NA |  |  |  | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-28 | RBG-TRANSMIT-000009 | NA | Trade Partner | Crane Base Drawings IFC | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | update register only |  | 2026-07-28 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-28 | S.T.S-TRANSMIT-000010 | NA | Trade Partner | Safetech Final Shop Drawing Comments | 1 | 0 | 0 | KPTG-IntCorr-000364 | APPROVED | [5 empty] | Revised and submitted |  | 2026-08-07 | KPTG-SADV-000474 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-29 | RDSBIM-TRANSMIT-000233 | NA | Trade Partner | LEVEL 03 PARTITION WALL KEY PLAN | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-07-29 | KPTG-TRANSMIT-003200 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-29 | RDSBIM-TRANSMIT-000024 | NA | Trade Partner | GROUND LEVEL ¦ WET AREA LAYOUT ¦ UAT | 1 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 418 | 2026-08-01 |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-001438 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-29 | RDSBIM-TRANSMIT-000025 | NA | Trade Partner | GROUND LEVEL ¦ WET AREA LAYOUT ¦ CLEANERS | 1 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 420 | 2026-08-03 |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-001439 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-29 | Auspan-TRANSMIT-000560 | NA | Trade Partner | Resubmit precast shop drawings for approval | 2 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 1585 | 2026-08-05 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003081 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-29 | Auspan-TRANSMIT-000107 | NA | Trade Partner | Precast shop drawings for approval. Coen precast columns. Stage 2. | 80 | 0 | 0 | NA | APPROVED | 2026-07-29 | WF-001073 | NA | 2026-08-07 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-003248 | Closed | 80 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-19 | Entire M-TRANSMIT-000011 | NA | Trade Partner | Mechanical Commissioning Plan For Review | 0 | 1 | 0 | NA | APPROVED | 2026-01-19 | WF-003855 |  | 2026-01-30 |  |  |  | 2026-02-13 | KPTG-TRANSMIT-012874 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-29 | Auspan-TRANSMIT-000561 | NA | Trade Partner | Update IFCed precast shop drawings. Levels 2, 3 | 6 | 0 | 0 | KPTG-IntCorr-001152 | APPROVED | [5 empty] | IFC - Waiting for Kim advise-KPTG-IntCorr-001152 4 OK TO IFC 2 Rejected -DRAFT-010943 |  | 2026-08-04 | KPTG-TRANSMIT-003076 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-29 | D&E-TRANSMIT-000954 | NA | Trade Partner | Fwd: Clearance Zones Register - Issued for approval | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-29 | KPTG-TRANSMIT-020106 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-29 | RDSBIM-TRANSMIT-000026 | NA | Trade Partner | GROUND LEVEL ¦ WET AREA LAYOUT ¦ UNISEX WC | 1 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 422 | 2026-08-03 |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-001440 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-29 | INDS-TRANSMIT-000058 | NA | Trade Partner | L4 to L7 - Zone 4 penetration layout | 4 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 1588 | 2026-08-05 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-29 | KALLIBRE-TRANSMIT-000016 | NA | Trade Partner | IFC - Rev B - Door Frames | 38 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing title inside the drawing and in Aconex seem different | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-001526 | Closed | 38 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-29 | KALLIBRE-TRANSMIT-000017 | NA | Trade Partner | IFA - Rev 3 - Door Frames | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing title revision and drawing status are incorrect |  | 2026-07-29 | KPTG-TRANSMIT-001527 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-29 | SPECAUTO-TRANSMIT-000009 | NA | Trade Partner | CSMS Functional Specification - For Review | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Document number error, the document was submitted as a word file, Revision error, Document status must be For Approval instead of For Review, cover sheet not included, document date mismatch. |  | 2026-07-29 | KPTG-TRANSMIT-001350 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-29 | NXES-TRANSMIT-000081 | NA | Trade Partner | Boom Gate Shop Drawing | 7 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 431 | 2026-08-07 |  |  | 2026-08-17 | 2026-08-17 | KPTG-TRANSMIT-003281 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-29 | WAM-TRANSMIT-000836 | NA | Trade Partner | A10 IFC Update Level 4 | 2 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 1051 | 2026-08-03 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-003312 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-29 | D&E-TRANSMIT-000950 | NA | Trade Partner | MCC Drawings - Issued for Approval | 7 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 3981 | 2026-08-07 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-01 | SKS Tech-TRANSMIT-000094 | N/A | Trade Partner | GROUND FLOOR SEISMIC IFA LAYOUTS - TEL | 1 | 0 | 0 | KPTG-IntCorr-000711 | APPROVED | 2025-12-02 | NA | 666 | 2025-12-09 |  |  | 2026-02-12 | 2026-02-12 | KPTG-TRANSMIT-002803 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-29 | RDSBIM-TRANSMIT-000149 | NA | Trade Partner | MLCSPR ¦ ISC L03 - BALUSTRADE SETOUT | 1 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 433 | 2026-08-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-29 | RDSBIM-TRANSMIT-000295 | NA | Trade Partner | NXM3S4 ¦ GROUND FLOOR ¦ WET AREA-C-G-022 ACC WC (LH) | 1 | 0 | 0 | NA | APPROVED | 2026-07-29 | MA | 3983 | 2026-07-31 |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-020272 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-29 | KALLIBRE-TRANSMIT-000018 | NA | Trade Partner | IFA - rev 4 - Door Frames | 21 | 0 | 0 | NA | REJECTED | [5 empty] | previous revision not mentioned in history block |  | 2026-07-29 | KPTG-TRANSMIT-001528 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-28 | INGEN3D-TRANSMIT-000216 | NA | Trade Partner | I3D-389 District Living - Level 21-23 - Precast Columns - IFC (27-07-2026) | 24 | 0 | 0 | NA | APPROVED | 2026-07-28 | WF-001046 | NA | 2026-08-07 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-003317 | Closed | 24 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-28 | INGEN3D-TRANSMIT-000217 | NA | Trade Partner | I3D-389 District Living - Level 21-23 - Precast Columns - No Longer in Use | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No longer in use - forwarded - KPTG-TRANSMIT-003125 |  | 2026-07-28 | KPTG-TRANSMIT-003125 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-28 | INGEN3D-TRANSMIT-000218 | NA | Trade Partner | I3D-389 District Living - Level 21-23 - PC0673-2 & PC0714 - New IFA (27-07-2026) | 2 | 0 | 0 | NA | APPROVED | 2026-07-28 | WF-001047 | NA | 2026-08-07 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-003315 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-28 | INGEN3D-TRANSMIT-000219 | NA | Trade Partner | I3D-389 District Living - Level 9-10 - Precast Wall - IFC (27-07-2026) | 10 | 0 | 0 | NA | APPROVED | 2026-07-28 | WF-001048 | NA | 2026-08-07 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-003374 | Closed | 10 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-29 | ARCST-TRANSMIT-000364 | NA | Trade Partner | Re: Stage 4 Davit Arms - Issued for Approval | 3 | 0 | 0 | NA | APPROVED | 2026-07-29 | WF-006537 | NA | 2026-08-04 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-29 | D&E-TRANSMIT-000952 | NA | Trade Partner | ISSUED FOR APPROVAL / CONSTRUCTION- BUILDERS WORK LAYOUTS & ELEVATIONS | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect drawing status |  | 2026-07-29 | KPTG-DA-007841 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-28 | G&CHyd-TRANSMIT-000009 | NA | Trade Partner | HYD Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-07-28 | WF-001042 | NA | 2026-08-05 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003270 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-16 | NXES-TRANSMIT-000066 | NA | Trade Partner | Common Rack Tech Sheet for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-01-16 | WF-000720 |  | 2026-01-20 |  |  |  | 2026-01-20 | KPTG-TRANSMIT-002140 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-28 | EFWC-TRANSMIT-000004 | NA | Trade Partner | Shop Drawings (Rev. A) (Updated) - (S2) - Kapitol - V02272 - District Living - 24 Little Docklands Drive, Docklands | 4 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 1045 | 2026-08-07 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-28 | L.E.S.-TRANSMIT-000037 | NA | Trade Partner | Lighting Control Data sheet | 0 | 5 | 0 | NA | APPROVED | 2026-07-28 | WF-001050 | NA | 2026-08-05 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-003319 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-28 | L.E.S.-TRANSMIT-000038 | NA | Trade Partner | Ceiling fan and Smoke Alarm Datasheet | 0 | 2 | 0 | NA | APPROVED | 2026-07-28 | WF-001051 | NA | 2026-08-05 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-003283 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-07-29 | JCI-TRANSMIT-000037 | NA | Trade Partner | BAS SAT Test | 0 | 1 | 0 | NA | APPROVED | 2026-07-29 | WF - 000557 | NA | 2026-08-04 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-29 | Stowe-A-TRANSMIT-000670 | NA | Trade Partner | STOWE - COMMS | 3 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 4446 | 2026-08-07 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020157 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-29 | Civilex-TRANSMIT-000318 | NA | Trade Partner | Stage 2 - sample submission - CTCR 5% Mix Design Pronto | 0 | 1 | 0 | NA | APPROVED | 2026-07-29 | WF-006539 | NA | 2026-08-08 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-020420 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-29 | KALLIBRE-TRANSMIT-000019 | SPARK-CRFI-KPG-000623 | Trade Partner | IFC - Rev B resub - Door frames | 38 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 382 | 2026-08-05 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-001607 | Closed | 38 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-29 | D&E-TRANSMIT-000955 | NA | Trade Partner | BMS System Architecture - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | ONLY FOR DISTRIBUTION |  | 2026-07-29 | KPTG-TRANSMIT-020120 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-29 | PFP PL-TRANSMIT-000101 | NA | Trade Partner | Stage 4 Battery Room Most Remote Hydraulic Calc | 0 | 1 | 0 | NA | REJECTED | [5 empty] | the document number, status and revision number mentioned inside the drawings and in Aconex seems different. |  | 2026-07-29 | KPTG-DA-007843 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-29 | Civilex-TRANSMIT-000319 | NA | Trade Partner | Stage 2 - sample submission - 10 mm N L 25_ RAP Asphalt Mix Design | 0 | 1 | 0 | NA | APPROVED | 2026-07-29 | WF-006540 | NA | 2026-08-08 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-020546 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-16 | NXES-TRANSMIT-000067 | NA | Trade Partner | ICT Schematics | 2 | 0 | 0 | NA | APPROVED | [5 empty] | IFC DRAWINGS, Transmitted to trade Partners and consultants |  | 2026-01-16 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-29 | ZIA-TRANSMIT-000135 | NA | Trade Partner | Re: M3 S4 CSMS EQUIPMENT LOCATION OVERALL DRAWINGS (FOA-1) | 4 | 0 | 0 | NA | REJECTED | [5 empty] | DIFFERENCE IN STATUS |  | 2026-07-29 | KPTG-DA-007850 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-29 | RDSBIM-TRANSMIT-000090 | NA | Trade Partner | GREYSTAR ¦ LEVEL 04 CONCRETE PROFILE KEY PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 1593 | 2026-08-05 |  | Review void as requested by RDS and advised by Kapitol DM. | 2026-08-06 | 2026-08-06 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-29 | ARCST-TRANSMIT-000365 | NA | Trade Partner | Stage 1 Cross Over IFA Drawings | 27 | 0 | 0 | NA | APPROVED | 2026-07-29 | WF-006541 | NA | 2026-08-14 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-28 | KPTG-SADV-003855 | NA | Trade Partner | Earthing Injection Testing | 0 | 1 | 0 | NA | APPROVED | 2026-07-28 | WF-001177 | NA | 2026-08-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-29 | INTRFRM-TRANSMIT-000111 | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 3) | 0 | 2 | 0 | NA | APPROVED | 2026-07-29 | WF-000383 | NA | 2026-08-08 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-001534 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-29 | INTRFRM-TRANSMIT-000112 | NA | Trade Partner | Geelong Edge - Civil Tech Data (Submission 10) | 0 | 2 | 0 | NA | APPROVED | 2026-07-29 | WF-000384 | NA | 2026-08-07 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-001470 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-29 | IVS-TRANSMIT-000375 | NA | Consultant | Stage 4 - Secure Corridor Construction Issue (Revised as clouded) | 2 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 3985 | 2026-08-04 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-29 | WilsonPD-TRANSMIT-000225 | NA | Trade Partner | Re: Fixtures Approval | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Document revision is missing |  | 2026-07-29 | KPTG-TRANSMIT-001533 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-29 | WilsonPD-TRANSMIT-000142 | NA | Trade Partner | Hydraulic Services Water Schematic (Sheet 3) | 1 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 1541 | 2026-08-05 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-006647 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-16 | Syfon1-TRANSMIT-000021 | NA | Trade Partner | Sports centre Syfon Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-01-19 |  | 401 | 2026-01-22 |  |  |  | 2026-02-05 | KPTG-SADV-003622 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-29 | WilsonPD-TRANSMIT-000143 | NA | Trade Partner | Hydraulic Services Water Schematics (Sheet1) | 1 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 1541 | 2026-08-05 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-006651 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-29 | WilsonPD-TRANSMIT-000144 | NA | Trade Partner | Hydraulic Services Water Schematics (Sheet2 | 1 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 1541 | 2026-08-05 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-006655 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-29 | PFP PL-TRANSMIT-000026 | NA | Trade Partner | Tech Data - WATERMIST PUMP | 0 | 1 | 0 | NA | APPROVED | 2026-07-29 | WF-001352 | NA | 2026-08-06 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-006521 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-29 | PFP PL-TRANSMIT-000102 | NA | Trade Partner | Roof Plant Level Wet Fire Layouts IFC | 2 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 3987 | 2026-08-07 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-23 | Auspan-TRANSMIT-000537 | NA | Trade Partner | Precast shop drawings for construction. Level 4 | 20 | 0 | 0 | KPTG-IntCorr-001083 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Kim advise-KPTG-IntCorr-001083 11 are OK to proceed IFC KPTG-TRANSMIT-003006 9 Rejected as advised by Kapitol PC. KPTG-IntCorr-001160 -DRAFT-010726 |  | 2026-07-29 | KPTG-TRANSMIT-003006 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-29 | ZIA-TRANSMIT-000138 | NA | Trade Partner | M3S4 CSMS OS LOCATION Roof Zone (FC-1) | 3 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 3989 | 2026-08-04 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-23 | Auspan-TRANSMIT-000537 | NA | Trade Partner | Precast shop drawings for construction. Level 4 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected difference in drawing status-DRAFT-010420 |  | 2026-07-23 | DRAFT-010420 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-03 | PARR-TRANSMIT-000064 | NA | Consultant | SEISMIC DESIGN & SEISMIC BRACE INSTALLATION DETAILS EL SERVICES | 0 | 2 | 0 | KPTG-IntCorr-001935 | APPROVED | [7 empty] | 2026-08-14 | KPTG-IntCorr-002143 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-29 | WilsonPD-TRANSMIT-000226 | SPARK-CRFI-KPG-000511 | Trade Partner | Shop Drawing - Level 1 Zone C & D close out | 2 | 0 | 0 | KPTG-IntCorr-003813 | APPROVED | 2026-07-30 | NA | 383 | 2026-08-06 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001542 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-29 | ARCST-TRANSMIT-000366 | NA | Trade Partner | C1 Cooling Tower HD Bolts - Issued for Construction | 5 | 0 | 0 | NA | REJECTED | [5 empty] | REVISION NOT UPDATED |  | 2026-07-29 | KPTG-DA-007852 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-16 | ARCH-TRANSMIT-000131 | NA | Consultant | MLC - SPR - Updated Drawings | 8 | 0 | 0 | NA | APPROVED | 2026-01-17 |  | 400 | 2026-01-22 |  |  | 2026-01-19 | 2026-01-19 | KPTG-SADV-003402 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-29 | ARCST-TRANSMIT-000367 | NA | Trade Partner | C1 Cooling Tower Grating - Issued for Construction | 167 | 0 | 0 | NA | REJECTED | [5 empty] | IFA revision not received for some docs |  | 2026-07-29 | KPTG-DA-007853 | Closed | 167 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-29 | PFP PL-TRANSMIT-000027 | NA | Trade Partner | Watermist Tank | 0 | 1 | 0 | NA | APPROVED | 2026-07-29 | WF-001353 | NA | 2026-08-06 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-006523 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-29 | Tradetec-TRANSMIT-000489 | NA | Trade Partner | IFA - Stage 4 - CP25 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision |  | 2026-07-29 | KPTG-DA-007851 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-07-29 | DI-TRANSMIT-000162 | NA | Trade Partner | Re: Final construciton issue | 7 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect status |  | 2026-07-29 | DRAFT-010486 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-29 | Tradetec-TRANSMIT-000490 | NA | Trade Partner | IFC - Stage 2 - LVP 5, 6, CP13 | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Title missing in one of the drawings 6055, Revision date mismatch. |  | 2026-07-29 | KPTG-SADV-006976 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-29 | Entire M-TRANSMIT-000075 | NA | Trade Partner | FOA-4 VRF Airconditioning | 0 | 1 | 0 | NA | APPROVED | 2026-07-29 | WF-000386 | NA | 2026-08-07 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001609 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-29 | Eneraque-TRANSMIT-000046 | NA | Trade Partner | Commissioning Management Plan | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-007017 |  | 2026-07-29 | KPTG-SADV-007017 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-29 | SMEPS-TRANSMIT-000051 | NA | Trade Partner | Techdata: Lighting Control F-D | 0 | 1 | 0 | NA | APPROVED | 2026-07-29 | WF-000387 | NA | 2026-08-07 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-001538 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-29 | ZIA-TRANSMIT-000137 | NA | Trade Partner | M3S4 Network Topology (FC-1) | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect document number |  | 2026-07-29 | KPTG-DA-007860 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-29 | Ardon-TRANSMIT-000067 | NA | Trade Partner | Priorty 1, 2, 3 Door Frames IFC | 41 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 3992 | 2026-08-04 |  | review terminated as instructed by esabella |  | 2026-08-03 | KPTG-TRANSMIT-020305 | Closed | 41 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-02 | Nilsen3-TRANSMIT-000115 | NA | Trade Partner | Nilsen Drawing for Approval TYPICAL DRUPS BB-BE SINGLE LINE DIAGRAM | 1 | 0 | 0 | NA | APPROVED | 2025-12-03 |  | 81 | 2025-12-05 |  | Bim Review updated as per KG instruction |  | 2025-12-05 | KPTG-TRANSMIT-000690 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-16 | RDSBIM-TRANSMIT-000098 | NA | Trade Partner | MLCSPR ¦ AQUATIC CENTER LEVEL 02 RCP | 3 | 0 | 0 | NA | APPROVED | 2026-01-17 |  | 399 | 2026-01-19 |  |  | 2026-01-19 | 2026-01-19 | KPTG-SADV-003379 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-29 | RDSBIM-TRANSMIT-000027 | NA | Trade Partner | NXGE01 ¦ GROUND FLOOR PARTITION WALL PLAN AND ELEVATIONS | 5 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 424 | 2026-08-04 |  | Reraised to updated the review status | 2026-08-12 | 2026-08-12 | KPTG-DA-001130 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-29 | D&E-TRANSMIT-000956 | NA | Trade Partner | Functional Description - ABS-01 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | ONLY FOR DISTRIBUTION |  | 2026-07-29 | KPTG-TRANSMIT-020195 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-29 | VIA Arch-TRANSMIT-000211 | NA | Trade Partner | M2 S9 L1 Data Hall Penetration Revisions | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-07-29 | KPTG-TRANSMIT-006143 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-29 | SES AU-TRANSMIT-000092 | NA | Trade Partner | COLO5 CELL 1 TO MECH GALLEY - Break Glass Relocation | 1 | 0 | 0 | NA | APPROVED | 2026-07-29 | WF-000422 | NA | 2026-07-31 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001135 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-29 | Nilsen3-TRANSMIT-000083 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 9 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Need to revise KPTG-SADV-007007 |  | 2026-07-29 | KPTG-SADV-007007 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-29 | EFP-TRANSMIT-000035 | NA | Trade Partner | Commission & Energisation Plans | 0 | 2 | 0 | NA | APPROVED | 2026-07-29 | WF-000423 | NA | 2026-08-05 |  | ONLY ONE DOCUMENT REQUIRES REVIEW | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-001150 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-29 | VIA Arch-TRANSMIT-000209 | NA | Consultant | Updated Stage 9 Wall Setout drawings | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project Team |  | 2026-07-29 | KPTG-TRANSMIT-006107 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-29 | RDSBIM-TRANSMIT-000089 | NA | Trade Partner | GREYSTAR ¦ LEVEL 04 CONCRETE PROFILE PLAN | 5 | 0 | 0 | KPTG-IntCorr-001162 | APPROVED | 2026-07-30 | NA | 1608 | 2026-08-06 |  | Kapitol to advise -KPTG-IntCorr-001162 Review void as requested by RDS and advised by Kapitol DM. | 2026-08-06 | 2026-08-06 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-29 | SYNACC-TRANSMIT-000002: | NA | Trade Partner | Substation Door - Shop Drawing - For Review and Approval | 1 | 0 | 0 | KPTG-IntCorr-001067 | APPROVED | 2026-08-07 | NA | 742 | 2026-08-14 |  | Tayla to advise on the drawing number - KPTG-IntCorr-001067 | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-001684 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-29 | ccair-TRANSMIT-000035 | NA | Trade Partner | Mechanical Services B1 and Ground Ductwork & pipework IFA | 2 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 703 | 2026-08-04 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-001654 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-19 | RDSBIM-TRANSMIT-000194 | NA | Trade Partner | NXM3S4 - GROUND FLOOR-C-G-022 ACC WC (LH) FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-01-19 |  | 1817 | 2026-01-23 |  |  |  | 2026-01-20 | KPTG-TRANSMIT-011738 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-29 | VIA Arch-TRANSMIT-000210 | NA | Consultant | STEEL DRAWINGS AND SWITCHROOMS ELEVATIONS | 7 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-DA-004000 |  | 2026-07-29 | KPTG-DA-004000 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-29 | WGAVIC-TRANSMIT-000170 | NA | Consultant | M2 - Civil - Council Updates - Issued for Construction | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, updated register and distributed |  | 2026-07-29 | KPTG-TRANSMIT-006131 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-29 | WilsonPD-TRANSMIT-000145 | NA | Trade Partner | Hydraulic Services Stage 9 Ground Floor-Plinth Layout | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Drawing for Information only. Just updated register as discussed with Project coordinator. |  | 2026-07-29 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-29 | Eneraque-TRANSMIT-000047 | NA | Trade Partner | CSL (Commissionable System List) Rev C | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Commissioning documents, No action required. Just updated register |  | 2026-07-29 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-29 | MCGC-TRANSMIT-000013 | NA | Consultant | Landscape Drawings Update | 63 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected:Revision and document Numbering of drawings are incorrect: KPTG-TRANSMIT-003191 |  | 2026-07-29 | KPTG-TRANSMIT-003191 | Closed | 63 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-29 | PFP PL-TRANSMIT-000028 | NA | Trade Partner | Tech Data - Micromist Nozzle | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFCs, No review required. Updated register and distributed |  | 2026-07-29 | KPTG-TRANSMIT-006138 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-29 | PFP PL-TRANSMIT-000029 | NA | Trade Partner | Temp tank & tank fill pumpset | 0 | 2 | 0 | NA | APPROVED | 2026-07-29 | WF-001354 | NA | 2026-08-10 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-006527 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-30 | Jangho-TRANSMIT-000282 | NA | Trade Partner | Window Wall PMU Shop Drawing_Rev A_For Construction | 12 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 1055 | 2026-08-10 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-003408 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-30 | D&E-TRANSMIT-000923 | NA | Trade Partner | Fans - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-07-30 | WF-006551 | NA | 2026-08-25 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-021054 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-29 | Teams message by John | NA | Trade Partner | Civil Samples | 0 | 2 | 0 | NA | APPROVED | 2026-07-29 | WF-001056 | NA | 2026-08-06 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003266 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-19 | ARCST-TRANSMIT-000180 | NA | Trade Partner | C3 Switchroom Upper Gantry - Issued for Approval | 125 | 0 | 0 | NA | APPROVED | 2026-01-19 | WF-003858 | NA | 2026-02-02 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-013606 | Closed | 125 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-29 | L.E.S.-TRANSMIT-000036 | NA | Trade Partner | Lighting Control Layout IFA | 27 | 0 | 0 | NA | REJECTED | [5 empty] | INCORRECT DOCUMENT ATTACHED |  | 2026-07-29 | KPTG-TRANSMIT-003163 | Closed | 27 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-29 | TTW-TRANSMIT-000172 | NA | Trade Partner | Lighting Control Layout IFA | 3 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 1047 | 2026-08-03 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-003546 | Closed | 3 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-29 | PCForm-TRANSMIT-000291 | NA | Trade Partner | L1 update | 4 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 1049 | 2026-08-06 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-003389 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-29 | Jangho-TRANSMIT-000281 | NA | Trade Partner | Structural Calculation For Podium Shop Drawing At 1F-5F_Rev 02_For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-29 | WF-001054 | NA | 2026-08-05 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-003278 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-29 | L.E.S.-TRANSMIT-000039 | NA | Trade Partner | Lighting Control Layout IFA | 27 | 0 | 0 | NA | REJECTED | [5 empty] | INCORRECT DOCUMENT ATTACHED AND TITLE BLOCK ERROR |  | 2026-07-29 | KPTG-TRANSMIT-003174 | Closed | 27 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-29 | PCForm-TRANSMIT-000294 | NA | Trade Partner | L1 Loading Plans updated for 6.5 KPa | 1 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 1053 | 2026-08-06 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-003386 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-30 | Jangho-TRANSMIT-000283 | NA | Trade Partner | Podium A & B Level 1~5 Floor Plan Shop Drawing_Rev 04_For Approval | 10 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 1057 | 2026-08-10 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-003365 | Closed | 10 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-29 | KPTG-SADV-000474 | NA | Trade Partner | Safetech Final Shop Drawing Comments | 8 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 545 | 2026-08-04 |  | NA | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-000753 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-30 | Eneraque-TRANSMIT-000048 | NA | Trade Partner | Functional Description Rev0 | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected : Incorrect document number |  | 2026-07-30 | KPTG-SADV-007032 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-29 | Baigents-TRANSMIT-000023 | NA | Trade Partner | Block 01 - West Wall - Revised Lower Ground Panels - Issued for Construction | 10 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 564 | 2026-08-04 |  | NA | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-000774 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-23 | JCBa-TRANSMIT-000204 | NA | Consultant | Coordination Drawing Issue - Various RFIs | 288 | 0 | 0 | NA | APPROVED | 2026-01-16 | WF-000882 | 525 | 2026-01-23 |  |  | 2026-01-27 | 2026-01-27 | KPTG-DA-002334 | Closed | 288 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-29 | KPTG-TRANSMIT-000733 | NA | Trade Partner | Concreter Mix Design for Review | 0 | 1 | 0 | NA | APPROVED | 2026-07-29 | NA | 541 | 2026-08-04 |  | NA | 2026-07-31 | 2026-08-03 | KPTG-TRANSMIT-000811 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-29 | KPTG-IntCorr-001270 | NA | Trade Partner | Workflow | 0 | 1 | 0 | NA | APPROVED | 2026-07-29 | 000874 | NA | 2026-08-04 |  | KPTG-IntCorr-001276 - AS per direction from Mark we terminate the WF. | 2026-07-30 | 2026-07-30 | KPTG-IntCorr-001276 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-30 | KPTG-INTCOM-000377 | NA | Trade Partner | Workflow | 0 | 1 | 0 | NA | APPROVED | 2026-07-30 | WF-000876 | NA | 2026-08-05 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-30 | JCBa-TRANSMIT-000159 | NA | Consultant | Updated Architectural Documentation - GA Plans, Partition Plans, Partition Sections & FSC Plans | 76 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 1598 | 2026-08-01 |  | Terminated as per Michael 's advice- Drawings are updated |  | 2026-07-30 | NA | Closed | 76 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-30 | RDSBIM-TRANSMIT-000017 | NA | Trade Partner | NXM2S9 ¦ GROUND FLOOR ¦ CLEANERS ROOM | 1 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 1544 | 2026-08-06 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-007025 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-29 | WGAVIC-TRANSMIT-000011 | NA | Trade Partner | M3 S6 and S7 Stormwater Management Plan - Issued for Information | 0 | 1 | 0 | NA | APPROVED | 2026-07-29 | NA | 549 | 2026-08-04 |  | NA | 2026-08-18 | 2026-08-19 | KPTG-TRANSMIT-001010 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-29 | D&E-TRANSMIT-000046 | NA | Trade Partner | ISSUED FOR APPROVAL - LEVEL 1 - DUCTWORK LAYOUT - ZONES 10 & 12 (DH12) | 2 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 551 | 2026-08-04 |  | NA |  |  |  | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-29 | D&E-TRANSMIT-000047 | NA | Trade Partner | ISSUED FOR APPROVAL - GROUND FLOOR - DUCTWORK LAYOUT - ZONE 2 & 4 (DH2) | 2 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 553 | 2026-08-04 |  | NA |  |  |  | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-29 | KBGA-TRANSMIT-000013 | NA | Trade Partner | Sika Grout tech data for approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-29 | NA | 557 | 2026-08-04 |  | NA | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-000859 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-29 | KBGA-TRANSMIT-000014 | NA | Trade Partner | Rehau AWASHAFT sewer maintenance shaft for approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-29 | NA | 559 | 2026-08-04 |  | NA | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-000915 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-16 | RDSBIM-TRANSMIT-000146 | NA | Trade Partner | LEVEL 11 TOWER B PARTITION WALL LAYOUT | 2 | 0 | 0 | NA | APPROVED | 2026-01-16 | WF-000879 | 524 | 2026-01-23 |  |  | 2026-02-02 | 2026-02-02 | KPTG-TRANSMIT-002670 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-30 | VERTIV-TRANSMIT-000056 | NA | Trade Partner | ARCHITECTURAL DRAWINGS (FOA-1 & FOA-3) | 6 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 426 | 2026-08-05 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-001521 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-29 | Aurecon-WTRAN-000038 | NA | Trade Partner | (WF-000137) FIE FOR APPROVAL: ABB LV Data Sheet, SLD and Schematics | 3 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 555 | 2026-08-04 |  | NA |  |  |  | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-29 | NXT-TRANSMIT-000456 | NA | Trade Partner | NEXTDC M3 - Staging Plan For IFC Background | 1 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 566 | 2026-08-04 |  | NA | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-001171 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-30 | KETE-TRANSMIT-000148 | NA | Trade Partner | Kete - Updated Cast-in Channels Layout (Rebate Extended at Concrete Columns) | 17 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-005141 - All drawings revision are incorrect. | 2026-07-30 | 2026-07-30 | KPTG-SADV-005141 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-30 | WilsonPD-TRANSMIT-000146 | NA | Trade Partner | Stage 10 tank room layout | 1 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 1546 | 2026-08-06 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-006633 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-30 | PFP PL-TRANSMIT-000028 | NA | Trade Partner | Micromist Nozzle | 0 | 1 | 0 | NA | APPROVED | 2026-07-30 | WF-001357 | NA | 2026-08-11 |  | IFC Sample has been submitted for review on 30/07 as advised by Project Coordinator | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-006531 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-30 | WilsonPD-TRANSMIT-000148 | NA | Trade Partner | Re: LEVEL 1 SLAB PENETRATIONS_STAGE 10 | 1 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 1548 | 2026-08-06 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-006638 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-30 | Auspan-TRANSMIT-000563 | NA | Trade Partner | Precast shop drawings for construction. Level 4 | 2 | 0 | 0 | KPTG-IntCorr-001163 | APPROVED | [5 empty] | IFC - Waiting for Kim advise- KPTG-IntCorr-001163 OK TO IFC |  | 2026-08-04 | KPTG-TRANSMIT-003084 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-30 | SMEPS-TRANSMIT-000262 | SPARK-CRFI KPG-000340 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0101,0102,0103,0104,0106,0108,0109,0110 | 8 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 386 | 2026-08-06 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-001546 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-15 | RDSBIM-TRANSMIT-000145 | NA | Trade Partner | LEVEL 04 RCP KEY PLAN & LAYOUT | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-30 | Arco-TRANSMIT-000009 | NA | Trade Partner | RESUBMISSIONS OF SHOPDRAWINGS - SLIDING GATES | 2 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 387 | 2026-08-06 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-28 | KPTG-WTRAN-002344 (WF-001164) | NA | Trade Partner | UPS L4 ITP | 0 | 1 | 0 | NA | APPROVED | 2026-07-19 | WF-001164 | NA | 2026-07-24 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-004175 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-30 | WSP ANZ-TRANSMIT-000099 | NA | Consultant | WSP Updated - Hydraulic Services Drawings | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-07-30 | KPTG-TRANSMIT-006175 | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-30 | fjc-TRANSMIT-000174 | NA | Trade Partner | Drawing Updates - Wall Types Details Schedule | 4 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 725 | 2026-08-04 |  |  | 2026-08-03 | 2026-08-03 | KPTG-SADV-005175 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-30 | Nilsen3-TRANSMIT-000246 | NA | Trade Partner | Nilsen ELC Shop Drawings - IFC | 1 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 3994 | 2026-08-08 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-020403 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-30 | Arc Plas-TRANSMIT-000011 | NA | Trade Partner | Re: Acoustic Panel Infill - Individual Shop Drawings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incomplete reference numebr |  | 2026-07-30 | KPTG-DA-007872 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-30 | fjc-TRANSMIT-000172 | NA | Consultant | Drawing Updates - Door Schedule Ground | 0 | 1 | 0 | NA | APPROVED | 2026-08-03 | WF-000886 | NA | 2026-08-10 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-002882 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-30 | VIA Arch-TRANSMIT-000212 | NA | Consultant | S11 Level 1 Door Schedule Update | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-07-30 | KPTG-TRANSMIT-006182 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-30 | ZIA-TRANSMIT-000139 | NA | Trade Partner | Re: M3 S4 CSMS EQUIPMENT LOCATION OVERALL DRAWINGS (FOA-1) | 4 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 3994 3996 | 2026-08-05 |  | As instructed by Kazhimir, Terminated Zi-Argus is going to upload a later version of the drawings and resubmit |  | 2026-08-03 | KPTG-TRANSMIT-020284 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-06 | TIVINTL-TRANSMIT-000014 | NA | Trade Partner | SRC-Tivoli- IFC drawings | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-30 | Tradetec-TRANSMIT-000491 | NA | Trade Partner | IFA - Stage 4 - CP25 | 1 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 3998 | 2026-08-08 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-020953 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-30 | Auscool-TRANSMIT-000112 | NA | Trade Partner | Fire Matrix | 0 | 1 | 0 | NA | APPROVED | 2026-07-30 | WF-000879 | NA | 2026-08-04 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-002827 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-30 | Entire M-TRANSMIT-000090 | NA | Trade Partner | COLO4 & 5 External Sensors Elevations | 1 | 0 | 0 | NA | APPROVED | 2026-07-30 | WF-000424 | NA | 2026-08-05 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001149 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-30 | ARCH-TRANSMIT-000171 | NA | Consultant | MLC - SPR - ISC - GA plans | 4 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 437 | 2026-08-04 |  | ACC WORKFLOW 437-TERMINATED: |  | 2026-08-05 | KPTG-SADV-005730 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-30 | VIA Arch-TRANSMIT-000213 | NA | Consultant | S9 L1 Concrete Profile | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-07-30 | KPTG-TRANSMIT-006186 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-30 | ZIA-TRANSMIT-000140 | NA | Trade Partner | Re: M3S4 Network Topology (FC-1) | 4 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED DUE IFC SUBMIITED BEFORE IFA |  | 2026-07-30 | KPTG-DA-007874 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-30 | GunAus-TRANSMIT-000002 | NA | Trade Partner | Drawings for Approval - #02148 - NEXTDC GE1 - SpeedStile FP - New Install | 0 | 2 | 0 | NA | REJECTED | [5 empty] | the attached document GE1-SEC-GUN-TD-A-0100-0001 same revision is already completed the review with reviewed with comments status. Kindly update the revision number to FOA-2 and change the status to issue for Approval. |  | 2026-07-30 | DRAFT-004030 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D9 | 2026-07-30 | HDRAus-TRANSMIT-000013 | NA | Consultant | Client X Antenna Gantry - Updated Stair Location | 7 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 1469 | 2026-08-10 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-000058 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D9 | 2026-07-30 | HDRAus-TRANSMIT-000014 | NA | Consultant | Client X Gantry - Updated Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 1469 | 2026-08-10 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-000059 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-17 | TIVINTL-TRANSMIT-000009 | NA | Trade Partner | SRC-Tivoli-L00-L07 IFC bulk drawings | 604 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 604 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-30 | WAM-TRANSMIT-000838 | NA | Consultant | WAM ARCH - L2 CSP - Jangho Update | 2 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 1059 | 2026-08-03 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-003279 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-30 | Arc Plas-TRANSMIT-000012 | NA | Trade Partner | Acoustic Panel Infill - Individual Shop Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 4000 | 2026-08-08 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-07-30 | Nilsen3-TRANSMIT-000245 Nilsen3-TRANSMIT-000243 | NA | Trade Partner | Stage-3 BTU 3A and 3B Battery sizing calculation data | 0 | 1 | 0 | NA | APPROVED | 2026-07-30 | WF-006557 | NA | 2026-08-04 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-020566 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-30 | SMEPS-TRANSMIT-000085 | NA | Trade Partner | SINGLE/DUAL OUTPUT LV SINGLE LINE DIAGRAMS {IFC} | 18 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 1550 | 2026-08-06 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-30 | ADP-TRANSMIT-000129 | NA | Consultant | ADP MEL4680 - Electrical Protection Report | 0 | 1 | 0 | NA | APPROVED | 2026-07-30 | NA | 430 | 2026-08-04 |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-001431 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-30 | KALLIBRE-TRANSMIT-000020 | NA | Trade Partner | (Resub) IFA-rev 4-Door Frames | 22 | 0 | 0 | NA | REJECTED | [5 empty] | Previous revision is not reflected in history block. |  | 2026-07-30 | KPTG-TRANSMIT-001548 | Closed | 22 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-30 | VIA Arch-TRANSMIT-000214 | NA | Consultant | M2 Door Hardware Schedules | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-07-30 | KPTG-TRANSMIT-006190 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-30 | PMT Sec-TRANSMIT-000045 | NA | Trade Partner | Resubmit Drawings | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing title is incorrect Revision is incorrect |  | 2026-07-30 | KPTG-TRANSMIT-001549 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-30 | D&E-TRANSMIT-000957 | NA | Trade Partner | Re: NXM3S4 - Exterior Builders Works Layouts - Elevations Sheets - Issued For Construction | 3 | 0 | 0 | NA | REJECTED | [5 empty] | The IFA for these drawings has not been received for review. |  | 2026-07-30 | KPTG-DA-007878 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-30 | 4DW-TRANSMIT-000205 | NA | Consultant | Structural Documentation - Loading plan & Landscape area updates | 2 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 439 | 2026-08-04 |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-003204 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-17 | RDSBIM-TRANSMIT-000147 | NA | Trade Partner | LEVEL 14 TOWER A PARTITION WALL LAYOUT (L14 & L15 TYPICAL) | 2 | 0 | 0 | NA | APPROVED | 2026-01-19 | WF-000883 | 526 | 2026-01-23 |  |  | 2026-01-27 | 2026-01-27 | KPTG-TRANSMIT-002638 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-30 | ZIA-TRANSMIT-000141 | NA | Trade Partner | Re: M3S4 Network Topology (FC-1) | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | The Status mismatch in the Aconex register and status history |  | 2026-07-30 | KPTG-DA-007879 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-30 | ADP-TRANSMIT-000384 | NA | Consultant | ADP MEL4780 - M3S4 - Electrical - LAYOUT - SITE IN GROUND | 1 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 4002 | 2026-08-03 |  |  |  | 2026-08-12 | KPTG-TRANSMIT-020514 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-30 | ZIA-TRANSMIT-000142 | NA | Trade Partner | M3S4 Network Topology (FC-1) | 3 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 4004 | 2026-08-08 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-30 | ADP-TRANSMIT-000382 | NA | Consultant | ADP MEL4561 M3S2 Updated Fire Protection Drawings and Spec | 8 | 0 | 0 | NA | REJECTED | [5 empty] | the attached documents seem mismatch in revision numbering in Aconex and inside drawing. |  | 2026-07-30 | KPTG-SADV-006994 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-30 | KPTG-TRANSMIT-003206 | NA | Trade Partner | DDA Compliance Statement – Performance Solutions IFC phase Brief - Revision 5 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | NA |  | 2026-07-30 | KPTG-TRANSMIT-003209 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-30 | ZIA-TRANSMIT-000133 | NA | Trade Partner | ZIA-TRANSMIT-000133 | 0 | 1 | 0 | NA | APPROVED | 2026-07-30 | WF-006560 | NA | 2026-08-04 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-021055 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-30 | Civilex-TRANSMIT-000320 | NA | Trade Partner | Stage 2 - sample submission - Wandin Straight Benches | 0 | 1 | 0 | NA | APPROVED | 2026-07-30 | WF-006599 | NA | 2026-08-21 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-021139 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-30 | KPTG-TRANSMIT-002776 | NA | Trade Partner | Heritage South Glass rev3 | 0 | 1 | 0 | NA | APPROVED | 2026-07-30 | WF-000880 | NA | 2026-08-05 |  | KPTG-IntCorr-001336 - As per direction from Charlie, we have terminated WF-000880 and created a new workflow, WF-000912. | 2026-08-19 | 2026-08-19 | KPTG-IntCorr-001336 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-17 | RDSBIM-TRANSMIT-000148 | NA | Trade Partner | LEVEL10 RCP KEY PLAN AND LAYOUT | 6 | 0 | 0 | NA | APPROVED | 2026-01-19 | WF-000884 | 527 | 2026-01-23 |  |  | 2026-02-02 | 2026-02-02 | KPTG-TRANSMIT-002662 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-30 | SMEPS-TRANSMIT-000086 | NA | Trade Partner | Stage 9 - 11 Jemena Easement Plan & Sections | 2 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 1552 | 2026-08-06 |  | Drawings on this Review # 1552 have been replaced by updated one received on SMEPS-TRANSMIT-000093. |  | 2026-08-06 | KPTG-IntCorr-002016 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-30 | Civilex-TRANSMIT-000322 | NA | Trade Partner | Stage 2 - sample submission - Linemarking | 0 | 1 | 0 | NA | APPROVED | 2026-07-30 | WF-006562 | NA | 2026-08-08 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-020521 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-30 | Auspan-TRANSMIT-000564 | NA | Trade Partner | Resubmit precast shop drawings for approval | 2 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 1606 | 2026-08-06 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-003113 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-30 | Civilex-TRANSMIT-000321 | NA | Trade Partner | Stage 1 - Swale Restoration Landscape Plan | 1 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 4451 | 2026-08-07 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-020682 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-30 | Leemark-TRANSMIT-000056 | SPARK-CRFI-KPG-000317 | Trade Partner | MCC - Wet FIRE Ground Floor shop drawings- IFC | 3 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 388 | 2026-08-06 |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-001556 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-30 | crossfir-TRANSMIT-000005 | NA | Trade Partner | Wet Fire - Ground Floor, IFA | 1 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 428 | 2026-08-13 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-001573 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-30 | SMEPS-TRANSMIT-000052 | NA | Trade Partner | Shop Drawing: Communications | 2 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 432 | 2026-08-05 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-001654 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-30 | TTW-TRANSMIT-000203 | NA | Consultant | M3 Traffic Control Device Plans | 2 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 4006 | 2026-07-03 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-020710 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-30 | Civilex-TRANSMIT-000323 | NA | Trade Partner | Stage 2 - Landscape drawings Transmittal | 10 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 4453 | 2026-08-07 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-11-28 | VIA Arch-TRANSMIT-000023 | NA | Consultant | M2 S9-11 Lift Core & Battery Enclosure | 6 | 0 | 0 | NA | APPROVED | 2025-12-01 | NA | 97 | 2025-12-03 |  |  | 2025-12-04 | 2025-12-04 | KPTG-TRANSMIT-000232 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-03 | WF-003474 | NA | Trade Partner | New Workflow L01 Z11 | 59 | 0 | 0 | NA | APPROVED | 2025-12-03 | WF-003474 | NA | 2025-12-19 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-12 | WSP ANZ-TRANSMIT-000028 | NA | Consultant | WSP - Greater Western Water Sewer Design Drawing | 4 | 0 | 0 | NA | APPROVED | 2026-01-19 |  | 190 | 2026-01-20 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-000618 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-30 | SMEPS-TRANSMIT-000053 | NA | Trade Partner | Shop Drawing: Electrical Submission | 6 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 434 | 2026-08-05 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-001684 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-30 | ADP-TRANSMIT-000386 | NA | Consultant | ADP - MEL4561 M3S2 Updated Site in-ground EL Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 4455 | 2026-08-07 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-020856 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-30 | ADP-TRANSMIT-000387 | NA | Trade Partner | ADP MEL4561 M3S2 Updated Fire Protection Drawings and Spec | 8 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 4457 | 2026-08-07 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-020860 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-30 | ARCST-TRANSMIT-000368 | NA | Trade Partner | C2 West Lower Gantry Grating - Issued for Construction | 141 | 0 | 0 | NA | APPROVED | 2026-07-30 | WF-006567 | NA | 2026-08-05 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-06 | SMEPS-TRANSMIT-000026 | NA | Trade Partner | Techdata: Communications | 0 | 1 | 0 | NA | APPROVED | 2026-07-06 | WF-000286 | NA | 2026-07-17 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-001947 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-30 | KPTG-TRANSMIT-020180 | NA | Trade Partner | M3S2 - LAI OMM | 0 | 1 | 0 | NA | APPROVED | 2026-07-30 | WF-006552 | NA | 2026-08-12 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-30 | Syfon1-TRANSMIT-000014 | NA | Trade Partner | Syfon updated Zone C3 drawings | 3 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 4008 | 2026-08-04 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-30 | WGAVIC-TRANSMIT-000172 | NA | Consultant | M2 - Civil - Civil Stormwater Details Sheet 03 - Issued for Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, updated register and distributed |  | 2026-07-30 | KPTG-TRANSMIT-006172 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-30 | ELLISAIR-TRANSMIT-000140 | NA | Trade Partner | Ground Floor Duct drawings issued for Construction | 2 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 1553 | 2026-08-06 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-006677 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-30 | Highbu-TRANSMIT-000060 | NA | Trade Partner | Water and Drainage Schematics - IFA | 2 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 726 | 2026-08-04 |  |  | 2026-08-28 | 2026-08-28 | KPTG-SADV-005468 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-19 | Tradetec-TRANSMIT-000329 | NA | Trade Partner | IFA - Shop Drawing - Stage 4 | 6 | 1 | 0 | NA | REJECTED | [5 empty] | KPTG-TRANSMIT-011590 - the attached document M3-ELC-TSA-SDRG-0-0401-6026 in this transmit seems different file upload on aconex |  |  |  | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-30 | M.2-TRANSMIT-000069 | NA | Trade Partner | Electrical Services Lighting layouts - L00, L01 & Typical L02-05 | 10 | 0 | 0 | KPTG-IntCorr-001164 | APPROVED | 2026-08-04 | NA | 1643 | 2026-08-11 |  | waiting for advise KPTG-IntCorr-001164. KPTG-TRANSMIT-003288 | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003288 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-30 | M.2-TRANSMIT-000069 | NA | Trade Partner | Electrical Services Lighting layouts - L00, L01 & Typical L02-05 | 5 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | As requested by trade partner, not to process ground floor drawings. M.2-SUBADVICE-000013 |  | 2026-07-30 | M.2-SUBADVICE-000013 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-30 | Eneraque-TRANSMIT-000049 | NA | Trade Partner | Functional Description | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Need to revise KPTG-SADV-007078 |  | 2026-07-30 | KPTG-SADV-007078 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-30 | M.2-TRANSMIT-000070 | NA | Trade Partner | Electrical Services Power & Comms layouts - L00-L07 | 25 | 0 | 0 | KPTG-IntCorr-001166 | APPROVED | 2026-07-31 | NA | 1629 | 2026-08-07 |  | waiting for advise KPTG-IntCorr-001166 | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-003182 | Closed | 25 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-30 | Auspan-TRANSMIT-000562 | NA | Trade Partner | : Precast shop drawings for construction. Level 3. | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | 2 are OK to transmit -KPTG-SADV-003832 Registered & Transmit - KPTG-TRANSMIT-003014 |  | 2026-07-30 | KPTG-TRANSMIT-003014 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-30 | Auspan-TRANSMIT-000562 | NA | Trade Partner | : Precast shop drawings for construction. Level 3. | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected by Kapitol PC- KPTG-SADV-003830 |  | 2026-07-30 | KPTG-SADV-003830 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-30 | Eneraque-TRANSMIT-000050 | NA | Trade Partner | Commissioning Management Plan | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | QA done and Updated register. Commissioning Team will process workflows, |  | 2026-07-30 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-30 | PSGANZ-TRANSMIT-000006 | NA | Trade Partner | Dry Fire Sample Submission | 0 | 12 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect document number - DRAFT-010819 |  | 2026-07-30 | DRAFT-010819 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-30 | Jangho-TRANSMIT-000095 | NA | Trade Partner | 671-VMU NO.1 SHOP IFC Drawings | 25 | 0 | 0 | NA | APPROVED | 2026-07-30 | WF-000635 | NA | 2026-08-06 |  | Initiated as advised by Ruhee. No ACC review |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-30 | KPTG-TRANSMIT-001476 | NA | Trade Partner | : Facade access package | 5 | 0 | 0 | KPTG-IntCorr-001083 | APPROVED | 2026-08-10 | NA | ACC#745 | 2026-08-17 |  | Ben to advise on QA issues - KPTG-IntCorr-001083 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-19 | Altaire-TRANSMIT-000050 | NA | Trade Partner | NEXTDC M3S4 - Dry Fire Ground Shop Drawings (For Approval) (1) | 3 | 0 | 0 | NA | APPROVED | 2026-01-13 |  | 1762 | 2026-01-19 |  |  |  | 2026-01-19 | KPTG-TRANSMIT-011572 | Closed | 3 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-30 | crossfir-TRANSMIT-000029 | NA | Trade Partner | Wet Fire - Penetrations (Drill note) | 5 | 0 | 0 | KPTG-IntCorr-001084 | APPROVED |  | NA | NA |  |  | Tayla to advise: KPTG-IntCorr-001084 No review required, update register. |  | 2026-08-04 | NA | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-30 | ACCCA-TRANSMIT-000013 | NA | Trade Partner | STORMWATER PITS FOR APPROVAL | 34 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 578 | 2026-08-06 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-000930 | Closed | 34 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-30 | Auspan-TRANSMIT-000108 | NA | Trade Partner | Update marking plans and elevations. | 5 | 0 | 0 | NA | REJECTED | [5 empty] | No Action is required, just for seeking confirmation :KPTG-SADV-005657 |  | 2026-07-30 | KPTG-SADV-005657 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-30 | Baigents-TRANSMIT-000025 | NA | Trade Partner | Speed Panel Shop Drawing IFA-A Package | 83 | 0 | 0 | KPTG-IntCorr-000386 | REJECTED | [5 empty] | Different in originator code |  | 2026-08-03 | KPTG-TRANSMIT-000824 | Closed | 83 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-17 | DLTS-TRANSMIT-000057 | NA | Trade Partner | S11 Canopy part 1 IFA Issue | 3 | 0 | 0 | NA | APPROVED | 2026-07-30 | WF-001364 | NA | 2026-08-08 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-006348 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-30 | Baigents-TRANSMIT-000024 | NA | Trade Partner | Speed Panel IFA-A Package | 18 | 0 | 0 | KPTG-IntCorr-000382 | REJECTED | [5 empty] | Different in originator code |  | 2026-08-03 | KPTG-TRANSMIT-000825 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-30 | NXT-PA-000343 | NA | Client | M3 Stage 6 - Schindler Shop Drawings - Goods Lifts | 4 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 576 | 2026-08-07 |  |  | 2026-07-30 | 2026-07-30 | KPTG-TRANSMIT-000769 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-31 | Baigents-TRANSMIT-000027-PTA | NA | Trade Partner | STAGE 06 SPEED PANEL MODEL [FOA-3] | 1 | 0 | 0 |  | APPROVED | 2026-07-31 | NA | 592 | 2026-08-07 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-001123 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-30 | Baigents-TRANSMIT-000026 | NA | Trade Partner | STAGE 06 SPEED PANEL MODEL [FOA-3] | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | 3d-For information |  | 2026-07-30 | 1 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-30 | 4DW-TRANSMIT-000071 | NA | Consultant | Structural Documentation: NLB Feature Precast Issued with Construction updates. | 1 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 568 | 2026-08-07 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-000981 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-01-19 | RDSBIM-TRANSMIT-000020 | NA | Trade Partner | 671CHP LEVEL 11 CONCRETE PROFILE KEYPLAN AND SECTION | 3 | 0 | 0 | NA | APPROVED | 2026-01-19 | NA | NA | 2026-01-22 |  | Review void as advised during a meeting with Kapitol DM & PCs. Review Reinitiated on 27-01-26 27/2/25 as advised by KAPITOL PC, ACC review 234 is VOID and initiated ACC review - WF-000246. Review Void. |  | 2026-02-27 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-30 | 4DW-TRANSMIT-000072 | NA | Consultant | Structural Documentation: Block 2 - Level 1. Issued For Coordination. | 14 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 570 | 2026-08-07 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-000982 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-30 | 4DW-TRANSMIT-000073 | NA | Consultant | Structural Documentation: Link Bridge - Stage 04 to Stage 06 update. | 1 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 574 | 2026-08-07 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-000983 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-30 | 4DW-TRANSMIT-000074 | NA | Consultant | Structural Documentation: NLB Feature Precast Issued with Construction updates. | 1 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 577 | 2026-08-07 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-000984 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-30 | Aurecon-WTRAN-000040 | NA | Consultant | (WF-000066) FOR REVIEW: IT Line Up Switchroom Tech Data 4 | 0 | 8 | 0 | KPTG-IntCorr-000387 | APPROVED | [5 empty] | No Action Required |  | 2026-08-10 | NA | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-30 | Jangho-TRANSMIT-000279 | NA | Trade Partner | FT01,FT02 overall U-value | 0 | 2 | 0 | NA | APPROVED | 2026-07-30 | WF-001058 | NA | 2026-08-06 |  | as instructed by Xavier - expecting a new revision hence terminated to unlock the document | 2026-07-30 | 2026-07-30 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-30 | INGEN3D-TRANSMIT-000222 | NA | Trade Partner | Level 20-22 - PC0666 - Revised IFC (29-07-2026) | 1 | 0 | 0 | KPTG-IntCorr-001091 | APPROVED |  | NA | NA |  |  | FC - DOC REGISTERED - FURTHER AS PER NICK'S ADVICE - KPTG-IntCorr-001091 - confirmed onward submission |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-30 | TIVINTL-TRANSMIT-000002 | NA | Trade Partner | Revised Off-site Prototype Shop Drawings of District Living Docklands ( DL628) | 14 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 1061 | 2026-08-10 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-003251 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-31 | SMEPS-TRANSMIT-000087 | NA | Trade Partner | STAGE 10-LEVEL 1 & 2 LIGHTING LAYOUT {IFC-1} | 2 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 1555 | 2026-08-07 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-006904 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-31 | INTRFRM-TRANSMIT-000113 | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 4) | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | WF-000393 | NA | 2026-08-13 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-01-19 | RDSBIM-TRANSMIT-000021 | NA | Trade Partner | 671CHP BASEMENT 4 CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | KPTG-IntCorr-000300 | APPROVED | 2026-01-22 | WF-000139 | 221 | 2026-01-27 |  | Previous revision is under review, waiting for advise. KPTG-IntCorr-000300 Review Void by Kapitol. |  | 2026-01-27 | NA | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-31 | RDSBIM-TRANSMIT-000091 | NA | Trade Partner | GREYSTAR ¦ LEVEL 01 PARTITION WALL | 6 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 1612 | 2026-08-05 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-31 | SMEPS-TRANSMIT-000088 | NA | Trade Partner | STAGE 10-LEVEL 1 & 2 POWER LAYOUTS {IFC} | 2 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 1557 | 2026-08-07 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-006888 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-31 | D&E-TRANSMIT-000293 | NA | Trade Partner | Filters and Vertigo for Approval | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Transmittal contains multiple statuses Document revision in Aconex and inside the document are different |  | 2026-07-31 | KPTG-TRANSMIT-001550 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-31 | WilsonPD-TRANSMIT-000018 | NA | Trade Partner | Hydraulic Services - Updated Layouts | 3 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 436 | 2026-08-06 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-001722 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-31 | Auspan-TRANSMIT-000569 | NA | Trade Partner | Precast shop drawings for approval. Level 7 zone 3 | 51 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 1614 | 2026-08-07 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-31 | KPTG-IntCorr-000731 | NA | Client | BU Security Plan | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | WF-000425 | NA | 2026-08-05 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-001141 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-31 | Leemark-TRANSMIT-000057 | NA | Trade Partner | MCC - Resubmission - L1 Fire Protection Drawings Zone 5 - 7 - IFC | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Same revision already received |  | 2026-07-31 | KPTG-TRANSMIT-001551 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-31 | D&E-TRANSMIT-000958 | NA | Trade Partner | Fwd: NXM3S4 - Ground - Mech_Elec Layout Zones - Issued For Construction | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-31 | KPTG-TRANSMIT-020258 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-31 | WilsonPD-TRANSMIT-000153 | NA | Trade Partner | Re: Updated Stage 11 Tank Room for approval | 1 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 1561 | 2026-08-07 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-006642 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-30 | Arc Plas-TRANSMIT-000010 | NA | Trade Partner | Acoustic Panel Shop Drawings - Revised | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incomplete reference numebr |  | 2026-07-30 | KPTG-DA-007870 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-19 | JCBa-TRANSMIT-000050 | NA | Consultant | Structural Setout Plans - Levels 07 & 08 IFC | 10 | 0 | 0 | NA | APPROVED | 2026-01-19 | WF-000137 | 263 | 2026-01-22 |  |  |  | 2026-01-22 | KPTG-TRANSMIT-000456 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-31 | D&E-TRANSMIT-000961 | NA | Trade Partner | Fwd: NXM3S4 - Ground - Mechanical Duct Layout - Zone 10 & IW Tank Room - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-31 | KPTG-TRANSMIT-020259 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-31 | TTW-TRANSMIT-000197 | NA | Consultant | M3 Stage 2 Civil Drawings | 7 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 4459 | 2026-08-04 |  | Terminated as requested by Charlie Johnstone for resubmitting the updated documents of some of the document in the set. | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-020612 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-31 | TTW-TRANSMIT-000204 | NA | Consultant | M3 Stage 2 Civil Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 4459 | 2026-08-04 |  | Terminated as advised by Charlie Johnstone for resubmitting updated documents of some of the documents in the set. | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-020613 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-31 | Auspan-TRANSMIT-000567 | NA | Trade Partner | Precast shop drawings for construction. Level 4 | 28 | 0 | 0 | KPTG-IntCorr-001169 | APPROVED | [5 empty] | IFC - Waiting for Kim advise- KPTG-IntCorr-001169 22 OK TO IFC- KPTG-TRANSMIT-003185; 1 Drawing Updated; 5 Rejected as advised by Kapitol PC. KPTG-SADV-004145 |  | 2026-08-12 | KPTG-TRANSMIT-003185 | Closed | 28 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-31 | Auspan-TRANSMIT-000567 | NA | Trade Partner | Precast shop drawings for construction. Level 4 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - Same revision as latest-DRAFT-010837 |  | 2026-07-31 | DRAFT-010837 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-31 | P & R-TRANSMIT-000105 | NA | Trade Partner | Stage 2 Carpark Exhaust Duct - Updated Penetration Set-Outs (Re-Transmittal) | 1 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 441 | 2026-08-11 |  | WORKFLOW IS RESUBMITTED | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-003249 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-31 | ZIA-TRANSMIT-000143 | NA | Trade Partner | M3S4 CSMS OS & ORMB Location (FC-1) | 6 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 4012 | 2026-08-09 |  | WF -Terminated |  | 2026-08-19 | KPTG-TRANSMIT-020733 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-31 | P & R-TRANSMIT-000104 | NA | Trade Partner | Stage 2 Carpark Exhaust Duct - Updated Penetration Set-Outs | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Duplicates- Transmit-P & R-TRANSMIT-000105 Accepted:KPTG-SADV-005664 |  | 2026-07-31 | KPTG-SADV-005664 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-31 | WilsonPD-TRANSMIT-000228 | SPARK-CRFI-KPG-000511 | Trade Partner | Hydraulic Services Layouts | 2 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 389 | 2026-08-07 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-001561 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-31 | Auspan-TRANSMIT-000109 | NA | Trade Partner | Precast shop drawings for approval. Coen Precast Stage 2. | 61 | 0 | 0 | NA | REJECTED | [5 empty] | Trade is requested to categorize and transmit drawings by individual transmit: KPTG-SADV-005665 |  | 2026-07-31 | KPTG-SADV-005665 | Closed | 61 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-19 | Auspan-TRANSMIT-000047 | NA | Trade Partner | Precast shop drawings for construction | 12 | 0 | 0 | NA | APPROVED | 2026-01-19 | WF-000134 | 257 | 2026-01-23 |  |  |  | 2026-01-30 | KPTG-TRANSMIT-000506 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-31 | ARCST-TRANSMIT-000372 | NA | Trade Partner | Re: C3 West Lower Gantry - Issued for Construction | 168 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect title |  | 2026-07-31 | KPTG-DA-007899 | Closed | 168 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-31 | CDL-TRANSMIT-000046 | NA | Trade Partner | Updated KPA Documents | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Document Numbering in Title bloc of drawings does not match with document number: KPTG-TRANSMIT-003202 |  | 2026-07-31 | KPTG-TRANSMIT-003202 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-31 | D&E-TRANSMIT-000959 | NA | Trade Partner | NXM3S4 - Ground - Mech_Elec Layout Zones - Issued For Approval | 5 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 4014 | 2026-08-09 |  |  |  | 2026-08-31 | KPTG-TRANSMIT-021148 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-31 | ARCST-TRANSMIT-000369 | NA | Trade Partner | C2 West Lower Gantry - Issued for Construction | 208 | 0 | 0 | NA | REJECTED | [5 empty] | IFA OF SOME DOCUMENTS NOT RECEIVED |  | 2026-07-31 | KPTG-DA-007916 | Closed | 208 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-31 | CDL-TRANSMIT-000047 | NA | Trade Partner | Updated KPA Documents | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Document Numbering is incorrect:KPTG-SADV-005666 |  | 2026-07-31 | KPTG-SADV-005666 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-06 | ARCST-TRANSMIT-000367 | NA | Trade Partner | C1 Cooling Tower Grating - Issued for Construction | 168 | 0 | 0 | NA | APPROVED | 2026-08-06 | WF-006615 | NA | 2026-08-04 |  | As Instructed by Lola , One Marking plan is added in this Workflow Ref: KPTG-IntCorr-017254 |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-31 | PROLMC-TRANSMIT-000051 | NA | Trade Partner | Proline As-built Shop Drawings Stage 2 | 9 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | current revision available with us is For Approval, they send As- built. |  | 2026-07-31 | KPTG-SADV-007021 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-31 | PARR-TRANSMIT-000218 | NA | Trade Partner | Fwd: P2680 - NDC M3 Stage 4 - Fuel - CLEARANCE ZONE REGISTER - IFC | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-07-31 | KPTG-TRANSMIT-020261 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-31 | WilsonPD-TRANSMIT-000229 | NA | Trade Partner | Cleaners Sink IFA (SPARK-CRFI-KPG-000132) | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision is incorrect |  | 2026-07-31 | KPTG-TRANSMIT-001552 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-31 | ZIA-TRANSMIT-000144 | NA | Trade Partner | M3 Stage 4 - Functional Design Specification | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | WF-006573 | NA | 2026-08-25 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-19 | Auspan-TRANSMIT-000048 | NA | Trade Partner | Basement Precast Column Dowels & Templates | 1 | 0 | 0 | NA | APPROVED | 2026-01-19 | WF-000135 | 259 | 2026-01-23 |  |  |  | 2026-02-02 | KPTG-TRANSMIT-000508 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-31 | SMEPS-TRANSMIT-000054 | NA | Trade Partner | Tech Data - CRAC Isolators | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | WF-000395 | NA | 2026-08-13 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-001780 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-31 | Nilsen3-TRANSMIT-000084 | NA | Trade Partner | Nilsen Sample submissions #14 | 0 | 2 | 0 | NA | APPROVED | 2026-07-31 | WF-001370 | NA | 2026-08-12 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-31 | PMT Sec-TRANSMIT-000046 | NA | Trade Partner | Re: Resubmit Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 390 | 2026-08-07 |  | Terminated as per Peter advise |  | 2026-08-06 | KPTG-IntCorr-003952 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-31 | WGAVIC-TRANSMIT-000174 | NA | Consultant | M2 - Civil - Updated Gabion Details - Issued for Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-07-31 | KPTG-TRANSMIT-006228 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-31 | Civilex-TRANSMIT-000324 | NA | Trade Partner | Stage 2 - sample submission - No Fines Concrete Mix Design - Pronto | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | WF-006574 | NA | 2026-08-06 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-020421 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-31 | SES AU-TRANSMIT-000093 | NA | Trade Partner | SECURITY DOOR HARDWARE ELEVATIONS - IFC | 3 | 0 | 0 | NA | APPROVED | 2026-07-31 | WF-000426 | NA | 2026-08-04 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-001139 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-07-31 | SES AU-TRANSMIT-000093 | NA | Trade Partner | SECURITY DOOR HARDWARE ELEVATIONS - IFC | 1 | 0 | 0 | NA | APPROVED | 2026-07-31 | WF-000427 | NA | 2026-08-04 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-001139 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-31 | PFP PL-TRANSMIT-000103 | NA | Trade Partner | Battery Room Most Remote Calc IFA | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | WF-006575 | NA | 2026-08-28 |  |  | 2026-08-20 | 2026-08-21 | KPTG-TRANSMIT-020811 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-31 | SMEPS-TRANSMIT-000263 | NA | Trade Partner | NEL-CNT-SME-2990-ELC-SAM-0002, 0026, 0028, 0074, 0075, 0076, 0084, 0085 | 0 | 8 | 0 | NA | REJECTED | [5 empty] | Revision is incorrect |  | 2026-07-31 | KPTG-TRANSMIT-001555 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-31 | TATE_-TRANSMIT-000009 | NA | Trade Partner | MYWCCB - Tate - IFA - Shop Drawings | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing originator code is incorrect, drawing revision block is incorrect |  | 2026-07-31 | KPTG-TRANSMIT-001553 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-19 | Auspan-TRANSMIT-000049 | NA | Trade Partner | Basement Precast Column Dowels & Templates | 1 | 0 | 0 | NA | APPROVED | 2026-01-19 | WF-000136 | 261 | 2026-01-23 |  |  |  | 2026-02-03 | Auspan-TRANSMIT-000049 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-31 | DLTS-TRANSMIT-000072 | NA | Trade Partner | S10-Cooling Tower-IFA Issue | 50 | 0 | 0 | NA | APPROVED | 2026-07-31 | WF-001373 | NA | 2026-08-11 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-006472 | Closed | 50 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-31 | ARCST-TRANSMIT-000371 | NA | Trade Partner | C3 Switchroom Upper Gantry - Issued for Construction | 132 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | The IFA has not been received |  | 2026-07-31 | KPTG-TRANSMIT-020262 | Closed | 132 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-31 | Auspan-TRANSMIT-000568 | NA | Trade Partner | Precast shop drawings for approval. Level 4 zone 4 | 7 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 1627 | 2026-08-07 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-003261 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-31 | ARCST-TRANSMIT-000373 | NA | Trade Partner | Stage 1 Cross Over IFA Drawings | 32 | 0 | 0 | NA | REJECTED | [5 empty] | the attached document seems mismatch in title that mentioned in this submitted revision and previous revision. |  | 2026-07-31 | KPTG-SADV-007027 | Closed | 32 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-31 | 4DW-TRANSMIT-000075 | NA | Trade Partner | Structural Documentation: Block 1 - Stair cores & Precast walls issued with Construction updates. | 3 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 585 | 2026-08-07 |  | NA | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-000985 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-30 | Baigents-TRANSMIT-000027 | NA | Trade Partner | Block 01 - Level 01 Precast columns IFA | 46 | 0 | 0 | KPTG-TRANSMIT-000786 | APPROVED | 2026-07-31 | NA | 580 | 2026-08-07 |  | NA | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-000931 | Closed | 46 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | HVHD-TRANSMIT-000019 | NA | Trade Partner | ESD Implementation Matrix Version Update | 0 | 1 | 0 | NA | APPROVED | 2026-08-11 | WF-001131 | NA | 2026-08-13 |  | Rejected - QA error - Aconex date correction is done by DC and forwarded | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-003637 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-30 | Jangho-TRANSMIT-000287 | NA | Trade Partner | Podium&Tower Visual Mock-UP Color Distribution Location Diagram | 1 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 1063 | 2026-08-10 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-31 | ADP-TRANSMIT-000388 | NA | Consultant | ADP MEL4780 M3S4 - Updated Fire Protection Drawings and Reg 126 | 5 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 4020 | 2026-08-05 |  | TERMINATED AS INSTRUCTED BY ELLIE |  | 2026-08-07 | KPTG-TRANSMIT-020429 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-19 | D&E-TRANSMIT-000081 | SPARK-CRFI-KPG-000474 | Trade Partner | MWYCCB - ROOF LEVEL - PENETRATION LAYOUT ZONE 5, 6 & 7 - MECHANICAL SERVICES - Issued For Review | 2 | 0 | 0 | NA | APPROVED | 2026-01-19 | WF-000123 | 94 | 2026-01-19 |  |  |  | 2026-02-04 | KPTG-TRANSMIT-000393 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-31 | ARCST-TRANSMIT-000370 | NA | Trade Partner | C3 Cooling Tower Roof - Issued for Construction | 129 | 0 | 0 | NA | APPROVED | 2026-08-04 | WF-006592 | NA |  |  | As instructed by Lola in KPTG-IntCorr-017196 |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-31 | Mirage D-TRANSMIT-000024 | NA | Trade Partner | Mirage Roller Shutter IFC - M3 STAGE 4 | 10 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 4021 | 2026-08-09 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-31 | Leemark-TRANSMIT-000058 | NA | Trade Partner | Shop Drawings – No Longer in Use – SDG-0110 to SDG-0112 | 3 | 0 | 0 | KPTG-IntCorr-003859 | APPROVED | [5 empty] | No Longer in Use - Register updated |  | 2026-08-03 | KPTG-IntCorr-003874 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-07-31 | ARCH-TRANSMIT-000172 | NA | Trade Partner | MLC - SPR - ISC - Elevations | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Title Bloc of drawings are misplaced:KPTG-SADV-005680 |  | 2026-07-31 | KPTG-SADV-005680 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-31 | INTERSIG-TRANSMIT-000012 | NA | Trade Partner | Assemble Coburg - WAYFINDING SIGNAGE - S.101, S.102, S.103, S.201 | 14 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-003212 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-31 | faulk-TRANSMIT-000001 | NA | Trade Partner | Shop drawings and Tech data | 1 | 1 | 0 | NA | REJECTED | [5 empty] | MIXED DOCUMENTS,MISMATCH IN REVISION NUMBER,.WRONG STATUS TO TECHDATA |  | 2026-07-31 | DRAFT-004084 | Open | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-31 | D&E-TRANSMIT-000960 | NA | Trade Partner | SFN Leak Detection Push Button - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | WF-006579 | NA | 2026-08-05 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-020460 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-31 | SMEPS-TRANSMIT-000056 | NA | Trade Partner | techdata; BTU | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected:As per the kapitol Requirement:KPTG-SADV-001094, document need to be superceded:KPTG-TRANSMIT-001437 |  | 2026-07-31 | KPTG-TRANSMIT-001437 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-31 | HDRAus-TRANSMIT-000534 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 21 | 0 | 0 | NA | REJECTED | [5 empty] | DRAWING STATUS DIFFERENCE |  | 2026-07-31 | KPTG-DA-007917 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-31 | SMEPS-TRANSMIT-000363 | NA | Trade Partner | SME IFA Documentation Submission | 2 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 4023 | 2026-08-06 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-03 | RDSBIM-TRANSMIT-000119 | NA | Trade Partner | LEVEL 09 CONCRETE PROFILE PLAN | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2025-12-03 | KPTG-TRANSMIT-002448 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-19 | Auspan-TRANSMIT-000051 | NA | Trade Partner | Precast shop drawings for construction | 1 | 0 | 0 | NA | APPROVED | 2026-01-19 | WF-000138 | 265 | 2026-01-23 |  |  |  | 2026-02-03 | KPTG-TRANSMIT-000514 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-31 | WGAVIC-TRANSMIT-000175 | NA | Consultant | M2 - Stage 9 Level 1 Updated Loading Dock - Issued for Certification | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-07-31 | KPTG-TRANSMIT-006253 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-07-31 | Archacce-TRANSMIT-000002 | NA | Consultant | Access Advice 01 - IFC Design Review | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | NA | 320 | 2026-08-07 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-31 | SMEPS-TRANSMIT-000057 | NA | Trade Partner | Techdata: DB's submission 1 | 0 | 7 | 0 | NA | APPROVED | 2026-07-31 | WF-000396 | NA | 2026-08-07 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-001796 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-31 | SMEPS-TRANSMIT-000058 | NA | Trade Partner | techdata; BTU | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected: Revision of this Document needs to be " FOA-3"-KPTG-TRANSMIT-001441 |  | 2026-07-31 | KPTG-TRANSMIT-001441 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-07 | JCBa-TRANSMIT-000278 | NA | Consultant | SRC Breezeways Pods and Pavers Overall Plans and GA Plans Updates | 48 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 612 | 2026-08-12 |  | NA | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-003275 | Closed | 48 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-07 | ECBS-IntCorr-000027 | NA | Trade Partner | Re: O&M Manual - DH7&8 Plaster | 0 | 1 | 0 | NA | APPROVED | 2026-07-07 | WF-001025 | NA | 2026-07-15 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-31 | WilsonPD-TRANSMIT-000230 | SPARK-CRFI-KPG-000132 | Trade Partner | Re: Cleaners Sink IFA (SPARK-CRFI-KPG-000132) | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | NA | NA | 2026-07-31 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-10 | SMEPS-TRANSMIT-000364 | NA | Trade Partner | SME IFC Documentation | 3 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 4090 | 2026-08-19 |  | As instructed by Fabian - 3 drawings placed on WF |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-31 | ADP-TRANSMIT-000130 | NA | Consultant | GE1 - Max Demand Calculations Report | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | NA | 438 | 2026-08-05 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-001476 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-19 | D&E-TRANSMIT-000082 | SPARK-CRFI-KPG-000254 | Trade Partner | MWYCCB - GROUND LEVEL - DUCTWORK LAYOUTS ZONE 1, 3 + 2 & ZONE 4 - Issued For Review | 2 | 0 | 0 | NA | APPROVED | 2026-01-19 | WF-000124 | 95 | 2026-01-26 |  | Review terminated |  | 2026-03-24 | KPTG-TRANSMIT-000573 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-31 | Leemark-TRANSMIT-000059 | SPARK-CRFI-KPG-000365 | Trade Partner | Re: MCC - Resubmission - L1 Fire Protection Drawings Zone 5 - 7 - IFC | 3 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 391 | 2026-08-07 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-001558 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-31 | LNCPPL-TRANSMIT-000025 | NA | Trade Partner | TELECOMMUNICATION SERVICES SITE PLAN - SHOP DRAWINGS FC-1 | 2 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 440 | 2026-08-06 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001621 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-31 | CRSol-TRANSMIT-000095 | NA | Trade Partner | M3S2 - SMW Drawings - As-Builts | 48 | 0 | 0 | NA | REJECTED | [5 empty] | THE DRAWING DIRECTLY SUBMITTED FOR AS - BUILT WITHOUT SUBMITTING IFC,,IFC REJECTED DRAWING SUBMITTED FOR AS-BUILT |  | 2026-07-31 | KPTG-SADV-007038 | Closed | 48 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-31 | SMEPS-TRANSMIT-000365 | NA | Trade Partner | SME IFA Documention | 12 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect title |  | 2026-07-31 | KPTG-DA-007920 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-31 | Facx-TRANSMIT-000021 | NA | Trade Partner | Updated IFC | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with revision number, date and revision history. |  | 2026-07-31 | KPTG-SADV-007039 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-07-31 | D&E-TRANSMIT-000962 | NA | Trade Partner | Fire Matrix Excel IFC-9 | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | WF-006584 | NA | 2026-08-07 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-020573 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-31 | Ardon-TRANSMIT-000068 | NA | Trade Partner | Priorty 4, 5, 6 Door Frames IFC | 95 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 4031 | 2026-08-06 |  | review terminated as instructed by esebella |  | 2026-08-03 | KPTG-TRANSMIT-020306 | Closed | 95 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-31 | Baigents-TRANSMIT-000028 | NA | Trade Partner | Ground Level Precast Column Propping Plan | 1 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 587 | 2026-08-07 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001021 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | INGEN3D-TRANSMIT-000223 | NA | Trade Partner | I3D-389 District Living - Level 8-9 - Precast Walls - IFC (30-07-2026) | 8 | 0 | 0 | NA | APPROVED | 2026-07-31 | WF-001069 | NA | 2026-08-05 |  | (2 drawgs re-issued trn 227) | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-003395 | Closed | 8 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-31 | D&E-TRANSMIT-000052 | NA | Trade Partner | Ground Floor Builders Works Layout Zone Sheets - Issued For Approval | 4 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 589 | 2026-08-07 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-19 | HDRAus-TRANSMIT-000360 | NA | Consultant | M3S4 - Corridor Layouts - Architectural Updates/Layouts | 6 | 0 | 0 | NA | APPROVED | 2026-01-19 |  | 1821 | 2026-01-23 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | INGEN3D-TRANSMIT-000224 | NA | Trade Partner | I3D-389 District Living - Level 10-11 - Precast Walls - IFC (30-07-2026) | 10 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | please correct the typo error in the below transmittal |  | 2026-07-31 | KPTG-TRANSMIT-003205 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | INGEN3D-TRANSMIT-000225 | NA | Trade Partner | I3D-389 District Living - Level 11-12 - Precast Walls - IFC (30-07-2026) | 8 | 0 | 0 | NA | APPROVED | 2026-07-31 | WF-001074 | NA | 2026-08-05 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-003393 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | INGEN3D-TRANSMIT-000226 | NA | Trade Partner | I3D-389 District Living - Level 7-8 - Precast Walls - IFC (30-07-2026) | 8 | 0 | 0 | NA | APPROVED | 2026-07-31 | WF-001066 | NA | 2026-08-05 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-003378 | Closed | 8 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | BLTEC-TRANSMIT-000004 | NA | Trade Partner | Re: Precast Pool option | 1 | 0 | 0 | KPTG-IntCorr-001097 | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001097 bradley to confirm |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | G&CHyd-TRANSMIT-000013 | NA | Trade Partner | HYD TEC DATA | 0 | 8 | 0 | NA | REJECTED |  | NA | NA |  |  | The document number in the transmittal matches the document number incorrect |  | 2026-07-31 | KPTG-TRANSMIT-003202 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | INGEN3D-TRANSMIT-000227 | NA | Trade Partner | I3D-389 District Living - Level 8-9 - PW1017 & PW1018 - Revised IFC (31-07-2026) | 2 | 0 | 0 | NA | APPROVED | 2026-07-31 | WF-001069 | NA | 2026-08-05 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-003395 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | INGEN3D-TRANSMIT-000229 | NA | Trade Partner | I3D-389 District Living - Level 11-12 - PW1029 & PW1030 - Revised IFC (31-07-2026) | 10 | 0 | 0 | NA | APPROVED | 2026-07-31 | WF-001080 | NA | 2026-08-05 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-003376 | Closed | 10 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | ccair-TRANSMIT-000006 | NA | Trade Partner | Mechanical Ground Floor to Level 4 Builderworks drawing IFC | 6 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | The revision date is incorrect in all documents and must be updated to match the revision |  | 2026-07-31 | KPTG-TRANSMIT-003204 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-31 | D&E-TRANSMIT-000053 | NA | Trade Partner | Level 1 Builders Work Layout Zones - Issued For Approval | 3 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 591 | 2026-08-07 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | Jangho-TRANSMIT-000287 | NA | Trade Partner | Podium&Tower Visual Mock-UP Color Distribution Location Diagram _Rev:01_For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 1063 | 2026-08-05 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | HDRAus-TRANSMIT-000359 | NA | Consultant | HAC Line Marking - Alignment Across All Stages - Sitewide Detail | 1 | 0 | 0 | NA | APPROVED | 2026-01-19 | NA | 3684 | 2026-01-21 |  |  |  | 2026-01-20 | KPTG-TRANSMIT-011645 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-31 | Aurecon-TRANSMIT-000142 | NA | Consultant | FIE fuel pump room specification and schedules | 0 | 2 | 0 | NA | APPROVED | 2026-07-31 | NA | 583 | 2026-08-07 |  |  | 2026-07-31 | 2026-08-03 | KPTG-TRANSMIT-000803 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | Jangho-TRANSMIT-000292 | NA | Trade Partner | Re: Podium&Tower Visual Mock-UP Color Distribution Location Diagram _Rev:01_For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 1063 | 2026-08-05 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-31 | NXT-TRANSMIT-000448 | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 07 - AURECON | 0 | 10 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated on forma |  | 2026-07-31 | NA | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-31 | ELLISAIR-TRANSMIT-000143 | NA | Trade Partner | Stage 11 Level 1 Duct & Pipework Layouts drawings issued for Approval | 2 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 1569 | 2026-08-07 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-006681 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | Jangho-TRANSMIT-000286 | NA | Trade Partner | Re: Facade Thermal Report Submission Requirements | 0 | 1 | 0 | NA | REJECTED |  | NA | NA | 2026-07-31 |  | Revision number incorrect |  | 2026-07-31 | KPTG-TRANSMIT-003206 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-31 | NXT-TRANSMIT-000454 | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 08 - NEXTDC | 0 | 49 | 0 | KPTG-IntCorr-000397 | APPROVED | [5 empty] | 49 documents updated , 3 zip file is No Action Required |  | 2026-08-24 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | Civilex-TRANSMIT-000115 | NA | Trade Partner | 32MPa Concrete Mix Design | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | WF-001068 | NA | 2026-08-05 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-003632 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-31 | NXT-TRANSMIT-000453 | NA | Client | M3 Stage 6 Customer Docs. | 0 | 121 | 0 | NA | APPROVED |  | NA | NA |  |  | Uploaded |  | 2026-07-31 | NA | Closed | 121 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-31 | NXT-TRANSMIT-000455 | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 09 | 0 | 21 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated on Forma |  | 2026-07-31 | NA | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | Tradetec-TRANSMIT-000331 | NA | Trade Partner | Stage 2 - IFA - LVP18, LVP21 | 2 | 0 | 0 | NA | APPROVED | 2026-01-19 | NA | 3686 | 2026-01-28 |  |  | 2026-02-09 | 2026-02-09 | KPTG-TRANSMIT-012593 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | Axiom-TRANSMIT-000016 | NA | Trade Partner | Building B Setout Plans - Issued for Approval | 11 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 1065 | 2026-08-05 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-003382 | Closed | 11 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-31 | Arc Plas-TRANSMIT-000005 | NA | Trade Partner | Updated Tech Data Submissions | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | WF-001372 | NA | 2026-08-07 |  | Resubmitted as requested by Project Coordinator | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-006416 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-31 | NXT-TRANSMIT-000461 | NA | Client | NXT-PA-000343 - M3 Stage 6 - Schindler Shop Drawings - Goods Lifts - Issued for Approval -#576 | 12 | 0 | 0 | KPTG-IntCorr-000392 | APPROVED |  | NA | NA |  |  | No Action required |  | 2026-08-03 | NA | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | KPTG-IntCorr-001085 (92) | NA | Trade Partner | WAM Signed Samples | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | WF-001070 | NA | 2026-08-06 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | KPTG-IntCorr-001085 (98) | NA | Trade Partner | WAM Signed Samples | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | WF-001071 | NA | 2026-08-05 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | KPTG-IntCorr-001085 (99) | NA | Trade Partner | WAM Signed Samples | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | WF-001072 | NA | 2026-08-05 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | KPTG-IntCorr-001085 (100) | NA | Trade Partner | WAM Signed Samples | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | WF-001075 | NA | 2026-08-05 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-31 | ACCCA-TRANSMIT-000014 | NA | Trade Partner | Electrical Pit Approval | 19 | 0 | 0 | KPTG-IntCorr-000398 | APPROVED | 2026-08-03 | NA | 596 | 2026-08-11 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001020 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-31 | Nilsen3-TRANSMIT-000079 | NA | Trade Partner | Nilsen Drawings Issued for Construction | 8 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 1567 | 2026-08-07 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-007251 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | KPTG-IntCorr-001085 (101) | NA | Trade Partner | WAM Signed Samples | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | WF-001075 | NA | 2026-08-05 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | Tradetec-TRANSMIT-000330 | NA | Trade Partner | Shop Drawing - Stage 2 - CP11 | 1 | 0 | 0 | NA | APPROVED | 2026-01-19 | NA | 3682 | 2026-01-28 |  |  | 2026-02-03 | 2026-02-04 | KPTG-TRANSMIT-012488 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | KPTG-IntCorr-001085 (102) | NA | Trade Partner | WAM Signed Samples | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | WF-001075 | NA | 2026-08-05 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | KPTG-IntCorr-001085 (103) | NA | Trade Partner | WAM Signed Samples | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | WF-001075 | NA | 2026-08-05 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | Axiom-TRANSMIT-000015 | NA | Trade Partner | Design drawings and Building B Setoit Plans | 6 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 1067 | 2026-08-05 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-003383 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | Axiom-TRANSMIT-000015 | NA | Trade Partner | Design drawings and Building B Setoit Plans | 11 | 0 | 0 | NA | REJECTED | [5 empty] | QA ERROR IN DWG NUMBER |  | 2026-07-31 | KPTG-TRANSMIT-003214 | Closed | 11 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | KPTG-IntCorr-001096 | NA | Trade Partner | KPTG SAMPLES ELECTRICAL APPLIANCES | 0 | 15 | 0 | NA | APPROVED | 2026-07-31 | WF-001075 | NA | 2026-08-05 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-31 | Nilsen3-TRANSMIT-000077 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 8 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 1564 | 2026-08-07 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-006908 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-31 | Nilsen3-TRANSMIT-000077 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 3 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 1565 | 2026-08-07 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-07-31 | INGEN3D-TRANSMIT-000228 | NA | Trade Partner | I3D-389 District Living - Level 11-12 - PW1029 & PW1030 - Revised IFC (31-07-2026) | 2 | 0 | 0 | NA | APPROVED | 2026-07-31 | WF-001074 | NA | 2026-08-05 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-003393 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-31 | WilsonPD-TRANSMIT-000149 | NA | Trade Partner | HYDRAULIC SERVICES STAGE 9 LEVEL 2 -SEWER & STORMWATER LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 1559 | 2026-08-06 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-006302 | Open | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-31 | WilsonPD-TRANSMIT-000151 | NA | Trade Partner | Updated Stage 11 Tank Room for approval | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Need to revise KPTG-SADV-007090 |  | 2026-07-31 | KPTG-SADV-007090 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | Tradetec-TRANSMIT-000328 | NA | Trade Partner | Stage 2 - IFC - LVP24 | 1 | 0 | 0 | NA | APPROVED | 2026-01-19 | NA | 3680 | 2026-01-26 |  |  | 2026-01-23 | 2026-01-23 | KPTG-TRANSMIT-011844 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-07-29 | RDSDG-TRANSMIT-000003 | NA | Trade Partner | NXM3S6 - HY - Drainage Shop Drawings - Block 1, Carpark & North Zones | 3 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 525 | 2026-08-06 |  | Coordinator submitted for review |  | 2026-07-31 | KPTG-TRANSMIT-000802 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-31 | VIA Arch-TRANSMIT-000215 | NA | Consultant | BRIDGE LINK ISSUE FOR BUILDING PERMIT | 8 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Need to Revise KPTG-DA-004065 |  | 2026-07-31 | KPTG-DA-004065 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-31 | Auspan-TRANSMIT-000565 | NA | Trade Partner | Re: Panel 3P4027 - Update | 1 | 0 | 0 | KPTG-IntCorr-001168 | APPROVED |  | NA | NA |  |  | IFC - Kapitol to advise - KPTG-IntCorr-001168 OK to IFC |  | 2026-08-04 | KPTG-TRANSMIT-003068 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-31 | Auspan-TRANSMIT-000566 | NA | Trade Partner | Precast shop drawings for construction. Level 3. | 5 | 0 | 0 | KPTG-IntCorr-001170 | APPROVED |  | NA | NA |  |  | IFC - Kapitol to advise - KPTG-IntCorr-001170 2 are OK to IFC: KPTG-TRANSMIT-003089 - The other 3 drawings have been up rev'd - KPTG-IntCorr-001178 |  | 2026-08-04 | KPTG-TRANSMIT-003089 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-31 | Auspan-TRANSMIT-000570 | NA | Trade Partner | Level 4 precast shop drawings for Approval | 2 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 1618 | 2026-08-07 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-003203 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-31 | Metzone-TRANSMIT-000041 | NA | Trade Partner | Ground Steel drawings IFC - rev B | 27 | 0 | 0 | KPTG-IntCorr-001282 | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001282 - requested guidance, but no resonance yet. KPTG-IntCorr-001294-As per direction from Ashlin, we only update the register and distribute everyone. | 2026-08-06 | 2026-08-06 | KPTG-IntCorr-001294 | Closed | 27 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-31 | fjc-TRANSMIT-000175 | NA | Consultant | Architecturals - Ground Design Changes, Wall Types, Tower CPP | 27 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 727 | 2026-08-05 |  |  | 2026-08-03 | 2026-08-03 | KPTG-SADV-005176 | Closed | 27 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-31 | IJF-TRANSMIT-000007 | NA | Trade Partner | Prototype Joinery - Study NBN | 7 | 0 | 0 | KPTG-IntCorr-001087 | APPROVED | 2026-08-03 | WF-000649 | NA | 2026-08-14 |  | IFC - Kapitol PC to advise - KPTG-IntCorr-001087 Initiate Aconex IFC workflow. | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-001545 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-31 | IJF-TRANSMIT-000006 | NA | Trade Partner | Prototype - Bathroom Robe Study Drawings C1 | 16 | 0 | 0 | KPTG-IntCorr-001086 | APPROVED | 2026-08-03 | WF-000648 | NA | 2026-08-14 |  | IFC - Kapitol PC to advise - KPTG-IntCorr-001086 Initiate Aconex workflow- IFC | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-001546 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-31 | RDSBIM-TRANSMIT-000092 | NA | Trade Partner | 671 CHAPEL STREET ¦ LEVEL 20 -BLOCKWORK PLAN AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 710 | 2026-08-07 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-001660 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | Stowe-A-TRANSMIT-000455 | NA | Trade Partner | Stowe - Tech Data Submission - ATS Shop drawing | 0 | 1 | 0 | NA | APPROVED | 2026-01-19 | WF-003881 | NA | 2026-01-29 |  |  |  | 2026-01-29 | KPTG-TRANSMIT-012183 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-31 | KPTG-TRANSMIT-001479 | NA | Trade Partner | : interspan drawing | 97 | 0 | 0 | KPTG-IntCorr-001088 | APPROVED | 2026-08-04 | WF-000652 | NA | 2026-08-11 |  | Waiting for advise from Kian - KPTG-IntCorr-001088 Review Terminated as advised by Kian. |  | 2026-08-05 | NA | Closed | 97 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-31 | ccair-TRANSMIT-000039 | NA | Trade Partner | Mechanical Services L1 duct and pipework layout IFA [A] | 2 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 705 | 2026-08-07 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-001650 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-31 | POTTSENG-TRANSMIT-000041 | NA | Trade Partner | 671C: HYDRAULIC SERVICES - BASEMENT 3-4 - DRAINAGE LAYOUTS | 2 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 708 | 2026-08-07 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-001608 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-31 | LGCE-TRANSMIT-000072: | NA | Trade Partner | Ground floor | 2 | 0 | 0 | KPTG-IntCorr-001093 | APPROVED |  | NA | NA |  |  | IFC - Kapitol PC Tayla to advise -KPTG-IntCorr-001093 As advised by Tayla, No review required as it has been superseded |  | 2026-08-13 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-31 | KPTG-TRANSMIT-001482 | NA | Trade Partner | Level 1- Level 11 hydraulic IFC penetrations | 11 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 706 | 2026-08-07 |  | (As advised by Tayla to put in a WF) | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-001561 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-31 | Auspan-TRANSMIT-000121 BGS | NA | Trade Partner | set out on corbel section detail. Update IFCed shop drawings. | 36 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Kian PC Kapitol - can u please transmit RA Precast- alexander and rocky - Transmitted KPTG-TRANSMIT-001484 |  | 2026-07-31 | KPTG-TRANSMIT-001484 | Closed | 36 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-31 | Jangho-TRANSMIT-000091 | NA | Trade Partner | GRC & GL300 Sample | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | WF-000639 | NA | 2026-08-07 |  | Review void as advised by Xavior, Kapitol PC |  | 2026-08-13 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-31 | POTTSENG-TRANSMIT-000044 | NA | Trade Partner | 671C: HYDRAULIC SERVICES - GROUND TO LEVEL 02 - DRAINAGE LAYOUTS | 3 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 712 | 2026-08-07 |  |  |  | 2026-08-26 | KPTG-TRANSMIT-001693 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-31 | POTTSENG-TRANSMIT-000043 | NA | Trade Partner | 671C: HYDRAULIC SERVICES - GROUND - WATER LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 716 | 2026-07-31 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-001695 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-07-31 | POTTSENG-TRANSMIT-000042 | NA | Trade Partner | : 671C: HYDRAULIC SERVICES - LEVELS 04-10 - DRAINAGE LAYOUTS | 7 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 718 | 2026-08-07 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-001697 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | Stowe-A-TRANSMIT-000454 | NA | Trade Partner | Stowe - Tech Data Submission - Work Station | 0 | 1 | 0 | NA | APPROVED | 2026-01-19 | WF-003880 | NA |  |  |  | 2026-02-17 | 2026-02-17 | KPTG-TRANSMIT-012994 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-07 | TATE_-IntCorr-000047 | NA | Trade Partner | Re: DH78 O&M - Tate | 0 | 1 | 0 | NA | APPROVED | 2026-07-07 | WF-001026 | NA | 2026-08-05 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-07 | ARCST-IntCorr-000103 | NA | Trade Partner | Re: Structural certification - Data Hall 7 & 8 & roof works | 0 | 1 | 0 | NA | APPROVED | 2026-07-07 | WF-001026 | NA | 2026-07-15 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-07 | ExpDG-IntCorr-000005 | NA | Trade Partner | Re: O&M Manual - DH7&8 Painting | 0 | 1 | 0 | NA | APPROVED | 2026-07-07 | WF-001023 | NA | 2026-07-15 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-07 | DRLL-IntCorr-000182 | NA | Trade Partner | Re: DC Nexus - Handover Requirements | 0 | 1 | 0 | NA | APPROVED | 2026-07-07 | WF-001027 | NA | 2026-07-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-07 | NXT-TRANSMIT-000202 | NA | Trade Partner | Fwd: M3 Stg 1 Operating manual for Kiosk | 0 | 1 | 0 | NA | APPROVED | 2026-07-07 | WF-001028 | NA | 2026-07-28 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-07 | MAYFLD-SUBADVICE-000081 | NA | Trade Partner | Re: PC Documentation Request | 0 | 1 | 0 | NA | APPROVED | 2026-07-07 | WF-001029 | NA | 2026-07-28 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-07 | ETNInd-IntCorr-000019 | NA | Trade Partner | Re: PC Documentation Request | 0 | 1 | 0 | NA | APPROVED | 2026-07-07 | WF-001030 | NA | 2026-07-28 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-07 | PenskePS-SUBADVICE-000009 | NA | Trade Partner | Re: PC Documentation Request | 0 | 1 | 0 | NA | APPROVED | 2026-07-07 | WF-001031 | NA | 2026-07-28 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-08 | KPTG-IntCorr-003681 | NA | Trade Partner | Stulz - O&M MANUAL VOLUME:001 | 0 | 1 | 0 | NA | APPROVED | 2026-07-08 | WF-001033 | NA | 2026-07-31 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-13 | KPTG-IntCorr-003683 | NA | Trade Partner | LAI - O&M Manual | 0 | 1 | 0 | NA | APPROVED | 2026-07-08 | WF-001034 | NA | 2026-07-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-16 | KPTG-IntCorr-003699 | NA | Trade Partner | Dry Fire O&M | 0 | 1 | 0 | NA | APPROVED | 2026-07-16 | WF-001035 | NA | 2026-07-22 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-16 | KPTG-IntCorr-003683 | NA | Trade Partner | LAI - O&M Manual | 0 | 1 | 0 | NA | APPROVED | 2026-07-16 | WF-001034 | NA | 2026-07-22 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-16 | KPTG-IntCorr-003667 | NA | Trade Partner | Re: M3 Dh7&8- Practical completion documentation -Baltimore Aircoil | 0 | 1 | 0 | NA | APPROVED | 2026-07-16 | WF-001036 | NA | 2026-07-22 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-16 | KPTG-IntCorr-003648 | NA | Trade Partner | Re: M3S1DH78 - Arjay - Practical Completion Documentation | 0 | 1 | 0 | NA | APPROVED | 2026-07-16 | WF-001037 | NA | 2026-07-22 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-16 | KPTG-IntCorr-003685 | NA | Trade Partner | EAE - O&M Manual External Busduct | 0 | 1 | 0 | NA | APPROVED | 2026-07-16 | WF-001038 | NA | 2026-07-30 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-16 | KPTG-IntCorr-003684 | NA | Trade Partner | EAE - O&M Manual Internal Busduct | 0 | 1 | 0 | NA | APPROVED | 2026-07-16 | WF-001039 | NA | 2026-07-22 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-16 | KPTG-IntCorr-003682 | NA | Trade Partner | SMARDT - O&M Manual | 0 | 1 | 0 | NA | APPROVED | 2026-07-16 | WF-001040 | NA | 2026-07-22 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-24 | ACG-TRANSMIT-000040 | NA | Trade Partner | M3 DH7/8 - Security O&M | 0 | 1 | 0 | NA | APPROVED | 2026-07-24 | WF-001042 | NA | 2026-08-06 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-24 | ACG-SUBADVICE-000062 | NA | Trade Partner | DH7/8 O&M Manual Comment register | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Distribution to NEXTDC |  | 2026-07-24 | KPTG-DA-002100 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-16 | KPTG-IntCorr-003693 | NA | Trade Partner | DFS OMM | 0 | 1 | 0 | NA | APPROVED | 2026-07-16 | WF-001041 | NA | 2026-07-22 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-03 | Auspan-TRANSMIT-000027 |  | Trade Partner | Update precast shop drawings due to steel model updated. First batch. | 9 | 0 | 0 | NA | APPROVED | 2025-12-03 | WF-003475 |  | 2025-12-12 |  | The drawings will be resubmitted for review |  | 2026-07-17 | NA | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | Civilex-TRANSMIT-000174 | NA | Trade Partner | Stage 3 (22KVA switch Room) - Sample Submission - D2 Base Plate HS Grout | 0 | 1 | 0 | NA | APPROVED | 2026-01-20 | WF-003882, WF-004031 |  | 2026-02-10 |  |  |  | 2026-01-29 | KPTG-TRANSMIT-012150 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-16 | KPTG-IntCorr-003685 | NA | Trade Partner | EAE - O&M Manual External Busduct | 0 | 1 | 0 | NA | APPROVED | 2026-07-16 | WF-001038 | NA | 2026-07-22 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-13 | KPTG-IntCorr-003699 | NA | Trade Partner | Dry Fire O&M | 0 | 1 | 0 | NA | APPROVED | 2026-07-13 | WF-001035 | NA | 2026-07-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-13 | KPTG-IntCorr-003693 | NA | Trade Partner | Bulk Fuel System Operation and Maintenance Manual | 0 | 1 | 0 | NA | APPROVED | 2026-07-13 | WF-001041 | NA | 2026-07-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-13 | KPTG-IntCorr-003667 | NA | Trade Partner | Practical completion documentation -Baltimore Aircoil | 0 | 1 | 0 | NA | APPROVED | 2026-07-13 | WF-001036 | NA | 2026-07-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-07-10 | KPTG-IntCorr-003646 | NA | Trade Partner | OP Requirements | 0 | 98 | 0 | NA | APPROVED |  | NA | NA |  |  | Uploaded and distributed to Client |  |  |  | Closed | 98 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | ASV-TRANSMIT-000080 | NA | Trade Partner | Revised PE to Copper Transition | 0 | 1 | 0 | NA | APPROVED | 2026-08-03 | WF-001389 | NA | 2026-08-12 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-03 | Jangho-TRANSMIT-000294 | NA | Trade Partner | Window Wall PMU-Test Proposal of District docklands | 0 | 1 | 0 | NA | APPROVED | 2026-08-03 | WF-001083 | NA | 2026-08-12 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-003276 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-03 | D&E-TRANSMIT-000963 | NA | Trade Partner | NXM3S4 - SECURITY GRILLES / Ground - Builders Works Layout Zone 10 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-03 | KPTG-TRANSMIT-020283 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-03 | Auspan-TRANSMIT-000571 | NA | Trade Partner | Precast shop drawings for approval. Level 4 zone 4 | 5 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 1631 | 2026-08-08 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-003379 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-03 | NXES-TRANSMIT-000023 | NA | Trade Partner | External, L06 to L08 Electrical Layout | 1 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 728 | 2026-08-08 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | Altaire-TRANSMIT-000058 | NA | Trade Partner | NEXTDC M3S4 - Dry Fire L1 Shop Drawings (For Approval) (C3) | 1 | 0 | 0 | NA | APPROVED | 2026-01-20 |  | 1823 | 2026-01-28 |  |  |  | 2026-02-18 | KPTG-TRANSMIT-013077 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-03 | RDSBIM-TRANSMIT-000012 | NA | Trade Partner | 303 COL ¦ BASEMENT 1 CPP ¦ IFA | 3 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 322 | 2026-08-12 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-03 | RDSBIM-TRANSMIT-000013 | NA | Trade Partner | 303COL ¦ BASEMENT 2 TO PODIUM ROOF EOT LIFT CORE WALL CONCRETE PROFILE | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect drawing status |  | 2026-08-03 | KPTG-DA-000501 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-03 | NXES-TRANSMIT-000082 | NA | Trade Partner | Electrical Penetration Layout | 3 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 443 | 2026-08-11 |  | As per the direction from the Ms. Julia, structural review is required for Penetration drawings. dated 24.08.2026 |  | 2026-08-24 | KPTG-TRANSMIT-003320 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-03 | Leemark-TRANSMIT-000060 | SPARK-CRFI-KPG-000365 | Trade Partner | MCC - Fire Detection Layout Drawings – Level 1 Fire Services Zones 1, 3, 4, 6 & 7 - IFC | 5 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 392 & 393 | 2026-08-10 |  | Actual receive date 31/07/2026 | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-001563 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-03 | RDSBIM-TRANSMIT-000079 | NA | Trade Partner | LEVEL 02 CONCRETE PROFILE PLAN | 6 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 1071 | 2026-08-11 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-003384 | Closed | 6 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | ZIA-TRANSMIT-000022 | NA | Trade Partner | M2 Stage 9, 10, 11 Network Topology (FOA-2) | 1 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 1591 | 2026-08-10 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-03 | ETNInd-TRANSMIT-000022 | NA | Trade Partner | MEL11 COLO 5 EPMS Device List | 0 | 1 | 0 | NA | APPROVED | 2026-08-03 | WF-000429 | NA | 2026-08-07 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-001191 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-03 | ETNInd-TRANSMIT-000021 | NA | Trade Partner | MEL11 COLO 4 EPMS Device List | 0 | 1 | 0 | NA | APPROVED | 2026-08-03 | WF-000428 | NA | 2026-08-07 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-001166 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-03 | JCBa-TRANSMIT-000160 | NA | Consultant | Updated Architectural Documentation - GA Plans | 81 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 1635 | 2026-08-05 |  | 1633 Review voided, 1 drawing added from JCBa-TRANSMIT-000159, Initiated review1635 Review terminated as advised by Kapitol DM. "Please unlock the JCB door schedule, ga plans, partition plans and partition detail sections. | 2026-08-11 | 2026-08-11 | NA | Closed | 81 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-03 | Auspan-TRANSMIT-000572 | NA | Trade Partner | Precast shop drawings for construction. Level 3 | 12 | 0 | 0 | KPTG-IntCorr-001175, KPTG-IntCorr-001193 | APPROVED | [5 empty] | IFC - Waiting for Kim advise - KPTG-IntCorr-001175 3 are rejected. -DRAFT-010947 9 are OK to Transmit-KPTG-TRANSMIT-003091 |  | 2026-08-04 | KPTG-TRANSMIT-003091 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-19 | Auspan-TRANSMIT-000044 | NA | Trade Partner | Update already IFCed shop drawings. Columns on ground floor stage 9 | 8 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-SADV-000676 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-03 | Auspan-TRANSMIT-000572 | NA | Trade Partner | Precast shop drawings for construction. Level 3 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - Difference in drawing status -DRAFT-010889 |  | 2026-08-03 | DRAFT-010889 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-08-03 | DI-TRANSMIT-000162<br> | NA | Trade Partner | Re: Final construciton issue | 7 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 431 | 2026-08-06 |  | As instructed by Isaiah, the drawings have been placed for review | 2026-08-04 | 2026-08-04 | DRAFT-010503 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-03 | RDSBIM-TRANSMIT-000078 | NA | Trade Partner | DISTLV ¦ LEVEL 06 CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 1069 | 2026-08-12 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003528 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-03 | PTA-TRANSMIT-000038 | NA | Consultant | Stair 04 09 12 Update - Issue for Coordination | 3 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 594 | 2026-08-11 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-000978 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-03 | KALLIBRE-TRANSMIT-000022 | NA | Trade Partner | IFA - Keyless 1 Lock | 0 | 1 | 0 | NA | APPROVED | 2026-08-03 | WF - 01108 | NA | 2026-08-07 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-03 | SPECAUTO-TRANSMIT-000011 | NA | Trade Partner | CSMS Functional Specification - For Review | 0 | 1 | 0 | NA | APPROVED | 2026-08-03 | WF-000399 | NA | 2026-08-14 |  |  | 2026-08-25 | 2026-08-26 | KPTG-TRANSMIT-002198 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | SES AU-TRANSMIT-000001 | NA | Trade Partner | Security Samples | 0 | 10 | 0 | NA | APPROVED | 2026-08-03 | WF-001391 | NA | 2026-08-04 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-006281 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | Eneraque-TRANSMIT-000052 | NA | Trade Partner | Level Switch Datasheet - Rev0 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-08-03 | KPTG-TRANSMIT-006285 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-03 | SMEPS-TRANSMIT-000059 | NA | Trade Partner | Re: techdata; BTU | 0 | 1 | 0 | NA | APPROVED | 2026-08-03 | WF-000401 | NA | 2026-08-14 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-001784 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-27 | ASHSS-TRANSMIT-000004 | NA | Trade Partner | NEXTDC GE1- Access stair Drawings | 20 | 0 | 0 | NA | APPROVED | 2026-07-27 | WF-000373 | NA | 2026-08-07 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-001972 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-19 | Auspan-TRANSMIT-000045 | NA | Trade Partner | Resubmit shop drawings for approval. Ground floor | 39 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-SADV-000677 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-03 | TATE_-TRANSMIT-000009 | SPARK-CRFI-KPG-000674 | Trade Partner | MYWCCB - Tate - IFA - Shop Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 394 | 2026-08-10 |  | Actual received date - 31/07/2026 | 2026-08-03 | 2026-08-04 | KPTG-TRANSMIT-001565 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | Eneraque-TRANSMIT-000051 | NA | Trade Partner | Line List - Rev0 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-08-03 | Eneraque-TRANSMIT-000051 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-03 | D&E-TRANSMIT-000964 | NA | Trade Partner | NXM3S4 - Ground - Mechanical Duct Layout - Zone 10 & IW Tank Room - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-03 | KPTG-TRANSMIT-020295 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-03 | SMEPS-TRANSMIT-000060 | NA | Trade Partner | Tech Data: DB-SEC-01 | 0 | 1 | 0 | NA | APPROVED | 2026-08-03 | WF-000402 | NA | 2026-08-14 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-001788 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-03 | RDSBIM-TRANSMIT-000014 | NA | Trade Partner | 303COL ¦ BASEMENT 2 TO PODIUM ROOF EOT LIFT CORE WALL CONCRETE PROFILE | 3 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 324 | 2026-08-09 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-000291 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-03 | ETNInd-TRANSMIT-000102 | NA | Trade Partner | UPS Header Box Dimensions on updated UPS GA | 1 | 0 | 0 | NA | REJECTED | [5 empty] | INCORRECT DOCUMENT NUMBER |  | 2026-08-03 | KPTG-DA-007938 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-03 | Jangho-TRANSMIT-000298 | NA | Trade Partner | Tower Level 6~9 FE PIPE & DUCT Shop Drawing | 20 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 1073 | 2026-08-11 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | WilsonPD-TRANSMIT-000155 | NA | Trade Partner | HYDRAULIC SERVICES STAGE 11 GROUND FLOOR -WATER SUPPLY LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 1593 | 2026-08-06 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-006534 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-03 | EFP-TRANSMIT-000037 | NA | Trade Partner | EFP Tech Data response to consultants comments | 0 | 2 | 0 | NA | APPROVED | 2026-08-03 | WF-000430 | NA | 2026-08-04 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-001142 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-03 | KALLIBRE-TRANSMIT-000021 | NA | Trade Partner | IFC - additional frames | 2 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 395 | 2026-08-10 |  |  | 2026-08-04 | 2026-08-05 | KPTG-TRANSMIT-001580 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-19 | Auspan-TRANSMIT-000046 | NA | Trade Partner | M2S9 GF Columns Review ¦ 0GC19 - 0GC34 | 44 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-SADV-000678 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | WilsonPD-TRANSMIT-000156 | NA | Trade Partner | HYDRAULIC SERVICES STAGE 11 GROUND FLOOR-SEWER & STORMWATER LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 1594 | 2026-08-06 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-006621 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-03 | Auspan-TRANSMIT-000573 | NA | Trade Partner | Precast shop drawings for construction. Level 4 | 13 | 0 | 13 | KPTG-IntCorr-001180 | APPROVED | [5 empty] | IFC - Waiting for Kim advise -KPTG-IntCorr-001180 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-03 | Auspan-TRANSMIT-000573 | NA | Trade Partner | Precast shop drawings for construction. Level 4 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - Difference revision code - DRAFT-010913 |  | 2026-08-03 | DRAFT-010913 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-08-03 | WPD-TRANSMIT-000101 | NA | Trade Partner | Re: Hydraulic Services - B08 - Updated As Built | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect Revision |  | 2026-08-03 | DRAFT-010497 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-03 | Auspan-TRANSMIT-000574 | NA | Trade Partner | Precast shop drawings for construction. Level 5 | 5 | 0 | 0 | KPTG-IntCorr-001181 | REJECTED | [5 empty] | IFC - Waiting for Kim advise -KPTG-IntCorr-001181 Rejected by Kapitol PC. KPTG-SADV-004151 |  | 2026-08-11 | KPTG-SADV-004151 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-08-03 | WPD-TRANSMIT-000102 | NA | Trade Partner | Re: Hydraulic Services - B08 - Updated As Built | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect Revision |  | 2026-08-03 | DRAFT-010498 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-22 | INTRFRM-TRANSMIT-000106 | NA | Trade Partner | Geelong Edge - Civil Tech Data (Submission 8) | 0 | 2 | 0 | NA | APPROVED | 2026-07-22 | WF-000361 | NA | 2026-07-31 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-001490 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-03 | KALLIBRE-TRANSMIT-000022 | NA | Trade Partner | (resubmission)-IFA-Rev 4 | 19 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 396 | 2026-08-10 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-03 | Appselec-TRANSMIT-000141 | NA | Trade Partner | MEL11 Loadbank Plan COLO4&5 | 0 | 1 | 0 | NA | APPROVED | 2026-08-03 | WF-000431 | NA | 2026-08-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | Eneraque-TRANSMIT-000053 | NA | Trade Partner | Functional Description Rev0 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Rejected : Difference in revision |  | 2026-08-03 | KPTG-SADV-007176 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-03 | GunAus-TRANSMIT-000003 | NA | Trade Partner | Drawings for Approval - #02148 NEXTDC GE1 - SpeedStile FP - New Install | 0 | 2 | 0 | NA | REJECTED | [5 empty] | the documents are submitted with mixed status, |  | 2026-08-03 | DRAFT-004136 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-03 | BACAU-TRANSMIT-000008 | NA | Trade Partner | Re: BAC Shop drawings | 9 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 448 | 2026-08-10 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-001865 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-03 | Auspan-TRANSMIT-000575 | NA | Trade Partner | Resubmit precast panel 3P5065 for approval. Stair landing updated | 1 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 1638 | 2026-08-10 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-003206 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-03 | D&E-TRANSMIT-000965 | NA | Trade Partner | NXM3S4 - Ground & Level 1 - Mechanical Duct Layout - Zone 7 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-03 | KPTG-TRANSMIT-020307 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-03 | VERTIV-TRANSMIT-000057 | NA | Trade Partner | NEXT DC GE01 _ MATERIAL SUBMISSION _ BUSDUCT SIEMENTS (FOA-1) | 0 | 1 | 0 | NA | REJECTED | [5 empty] | A ZIP file was submitted instead of the required PDF file |  | 2026-08-03 | KPTG-TRANSMIT-001475 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-03 | ARCST-TRANSMIT-000374 | NA | Trade Partner | Re: Stage 1 Cross Over IFA Drawings | 32 | 0 | 0 | NA | REJECTED | [5 empty] | The attached document M3-STR-ARC-SDRG-B-0201-B60500 appears to have a title mismatch compared with the previously submitted document. |  | 2026-08-03 | KPTG-SADV-007076 | Closed | 32 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-03 | Entire M-TRANSMIT-000078 | NA | Trade Partner | Ground Floor Pipework Drawings IFA | 4 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 447 | 2026-08-07 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001625 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-03 | Civilex-TRANSMIT-000325 | NA | Trade Partner | Stage 2 - sample submission - Carpark Concrete Wheel Stops | 0 | 1 | 0 | NA | APPROVED | 2026-08-03 | WF-006588 | NA | 2026-08-14 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-020557 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-03 | Jangho-TRANSMIT-000296 | NA | Trade Partner | FT13 System Concept Drawing_Rev 03_PDF_For Approval | 18 | 0 | 0 | NA | REJECTED | [5 empty] | Revision difference |  | 2026-08-03 | KPTG-TRANSMIT-003227 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-03 | Jangho-TRANSMIT-000299 | NA | Trade Partner | Tower Level 13~23 Cast in Channel Shop Drawing | 12 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 1075 | 2026-08-11 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-003499 | Closed | 12 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-19 | Auspan-TRANSMIT-000048 | NA | Trade Partner | Precast shop drawings for construction | 8 | 0 | 0 | NA | APPROVED | [5 empty] | IFC drawings, No review required |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-03 | B Smart-TRANSMIT-000100 | NA | Consultant | A10 series IFC | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected- Difference in title -DRAFT-011175 |  | 2026-08-03 | DRAFT-011175 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-03 | WAM-TRANSMIT-000839 | NA | Consultant | Material Finishes Schedule Update | 0 | 1 | 0 | NA | APPROVED | 2026-08-03 | WF-001088 | NA | 2026-08-05 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-003634 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-03 | PTA-TRANSMIT-000039 | NA | Consultant | Archi G.A. plans - Issue for Coordination | 17 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 603 | 2026-08-07 |  | NA | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-000979 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-03 | PTA-TRANSMIT-000040 | NA | Consultant | Site plan and Genernal elevation update - Issue for coordination | 10 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 600 | 2026-08-07 |  | NA | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-000980 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-16 | ZLH P/L-TRANSMIT-000004 | NA | Trade Partner | Re: Proposed Material - Design & Sample - ZLH | 0 | 1 | 0 | NA | APPROVED | 2026-06-16 | WF-000213 | NA | 2026-06-25 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-001451 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-03 | Firesafe-TRANSMIT-000016 | NA | Trade Partner | Existing Car Park | 2 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected, QA error |  | 2026-08-03 | KPTG-TRANSMIT-003228 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-03 | Jangho-TRANSMIT-000293 | NA | Trade Partner | AFRC U-Value and SHGC Calculation Report-FT13 V01 | 0 | 1 | 0 | NA | APPROVED | 2026-08-03 | WF-001089 | NA | 2026-08-10 |  | Clarification from Jaanbir | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-003364 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-03 | Auspan-TRANSMIT-000110 | NA | Trade Partner | All columns in one transmittal | 13 | 0 | 0 | NA | APPROVED | 2026-08-03 | WF-001082 | NA | 2026-08-12 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-003264 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-03 | Auspan-TRANSMIT-000110 | NA | Trade Partner | All columns in one transmittal | 3 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 445 | 2026-08-12 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-003232 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | ELLISAIR-TRANSMIT-000117 | NA | Trade Partner | Stage 10 Level 1 Duct and Pipe layouts issued for Approval. | 5 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 1475 | 2026-08-03 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-006336 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-19 | SMEPS-TRANSMIT-000007 | NA | Trade Partner | Electrical & Comms Overall Site Plan (FOA) | 2 | 0 | 0 | NA | APPROVED | 2026-01-19 |  | 193 , 194 | 2026-01-30 |  |  |  | 2026-02-04 | KPTG-TRANSMIT-000705 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | ELLISAIR-TRANSMIT-000115 | NA | Trade Partner | Stage 9 Level 1 Link Bridge Duct & Pipe layout drawing issued for Approval. | 1 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 1476 | 2026-08-03 |  |  | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-006341 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-03 | SMEPS-TRANSMIT-000366 | NA | Trade Partner | SME IFA Documentation | 12 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect status, revision date |  | 2026-08-03 | KPTG-DA-007951 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-03 | Facx-TRANSMIT-000022 | NA | Trade Partner | Re Updated IFC | 8 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 4464 | 2026-08-03 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-03 | BACAU-TRANSMIT-000101 | NA | Trade Partner | Updated As Built docs | 9 | 0 | 0 | NA | REJECTED | [5 empty] | All kinds of QA issues involved. |  | 2026-08-03 | KPTG-SADV-007099 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-03 | Auspan-TRANSMIT-000111 | NA | Trade Partner | Facade panels in one transmittal. | 44 | 0 | 0 | NA | APPROVED | 2026-08-03 | WF-001084 | NA | 2026-08-12 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-03 | Auspan-TRANSMIT-000111 | NA | Trade Partner | Facade panels in one transmittal | 2 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 447 | 2026-08-12 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-003348 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-03 | CDL-TRANSMIT-000048 | NA | Trade Partner | Updated KPA Documentation | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Document Numbering is incorrect, requested to resubmit:KPTG-SADV-005684 |  | 2026-08-03 | KPTG-SADV-005684 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-03 | CLADC-TRANSMIT-000025 | NA | Trade Partner | Resubmission of tech data for Stage 2 | 0 | 25 | 0 | NA | REJECTED | [5 empty] | Rejected:Submission of Reviewed outcome for informationKPTG-SADV-005683: |  | 2026-08-03 | KPTG-SADV-005683: | Closed | 25 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-03 | Aurecon-TRANSMIT-000144 | NA | Consultant | Electrical Services - LOD300 Issued for Contract | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Drawings already submitted |  | 2026-08-03 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-03 | NXT-WTRAN-000122 | NA | Client | FIE FOR APPROVAL: DCNEXUS Switchrooms Structural Drawing | 23 | 0 | 0 | KPTG-IntCorr-000413 | APPROVED | [5 empty] | No Action Required |  | 2026-08-10 | NA | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-19 | BLUESF-TRANSMIT-000029 | NA | Trade Partner | Missing Drawings - Stage 11 - BlueSF | 9 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000202 | NA | 2026-02-11 |  | Drawings resubmitted as per Kapitol instruction | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-001485 | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-03 | KPTG-TRANSMIT-002792 | NA | Trade Partner | Level 10 Soffit Glazing | 3 | 0 | 0 | KPTG-IntCorr-001285 | APPROVED | 2026-08-04 | WF-000887 | NA | 2026-08-06 |  | KPTG-IntCorr-001285 - requested guidance, but no resonance yet. | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-002995 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-03 | KETE-TRANSMIT-000149 | NA | Trade Partner | Kete - Updated Material List | 2 | 0 | 0 | KPTG-IntCorr-001286 | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001286 - requested guidance, but no resonance yet. KPTG-IntCorr-001295-As per direction from Ashlin, we rejected this transmittal because it had already been updated in KETE-TRANSMIT-000150. | 2026-08-06 | 2026-08-06 | KPTG-IntCorr-001295 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-03 | KETE-TRANSMIT-000150 | NA | Trade Partner | Kete - Updates Material List (Insulation) | 2 | 0 | 0 | KPTG-IntCorr-001287 | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001287 - As per advice from Ashlin, we hold this transmittal. KPTG-IntCorr-001296-As per direction from Ashlin, we only update the register and distribute everyone. | 2026-08-06 | 2026-08-06 | KPTG-IntCorr-001296 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-03 | Jangho-TRANSMIT-000295 | NA | Trade Partner | Reaction for Interface of FT01, FT02 & FT05 systems | 0 | 1 | 1 | KPTG-TRANSMIT-003216 | APPROVED |  | NA | NA |  |  | Clarification from Jaanbir |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-03 | RDSBIM-TRANSMIT-000093 | NA | Trade Partner | 671 CHAPEL STREET CPP LEVEL 19 | 3 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 722 | 2026-08-11 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-001664 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-03 | Jangho-TRANSMIT-000096 | NA | Trade Partner | : L3~18 shop drawing Rev02 | 112 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Ben Cox- Update ACC - No Review - KPTG-TRANSMIT-001490 |  | 2026-08-03 | KPTG-TRANSMIT-001490 | Closed | 112 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-03 | Jangho-TRANSMIT-000102 | NA | Trade Partner | Podium 1-2F Shop Drawings Rev01 | 69 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to incorrect revision and Attachment. - DRAFT-011139 |  | 2026-08-03 | DRAFT-011139 | Closed | 69 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | VIA Arch-TRANSMIT-000217 | NA | Consultant | Fuel Room finishes updates | 14 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Building permit drawings, Updated Register and Distributed |  | 2026-08-03 | KPTG-TRANSMIT-006346 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-19 | BLUESF-TRANSMIT-000030 | NA | Trade Partner | (PRECAST COLUMNS) PRECAST DRAWINGS IFA | 1 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000202 |  | 2026-02-11 |  | Drawings resubmitted as per Kapitol instruction | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-001486 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-14 | VIA Arch-TRANSMIT-000196 | NA | Consultant | M2 S9-S11 Architectural Update | 31 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 1571 | 2026-07-20 |  |  | 2026-08-11 | 2026-08-11 | KPTG-DA-004169 | Closed | 31 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-14 | VIA Arch-TRANSMIT-000197 | NA | Consultant | Updated steel details | 1 | 0 | 0 | NA | APPROVED | 2026-07-14 | NA | 1573 | 2026-08-21 |  |  | 2026-08-11 | 2026-08-11 | KPTG-DA-004170 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | ELLISAIR-TRANSMIT-000144 | NA | Trade Partner | SFN equipment | 0 | 7 | 0 | NA | APPROVED | 2026-08-03 | WF-001384 | NA | 2026-08-12 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-007188 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | ELLISAIR-TRANSMIT-000145 | NA | Trade Partner | SFN - Materials | 0 | 5 | 0 | NA | APPROVED | 2026-08-03 | WF-001385 | NA | 2026-08-12 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-007372 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | DLTS-TRANSMIT-000073 | NA | Trade Partner | Cooling Tower-Upper Gantry-IFA Issue (Part-1) | 173 | 0 | 0 | NA | APPROVED | 2026-08-03 | WF-001386 | NA | 2026-08-11 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-006700 | Closed | 173 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | DLTS-TRANSMIT-000073 | NA | Trade Partner | Cooling Tower-Upper Gantry-IFA Issue (Part-2) | 180 | 0 | 0 | NA | APPROVED | 2026-08-03 | WF-001387 | NA | 2026-08-11 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-006700 | Closed | 180 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | CLADC-TRANSMIT-000001 | NA | Trade Partner | Kattsafe Shop Drawings | 3 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Need to revise KPTG-SADV-007149 |  | 2026-08-03 | KPTG-SADV-007149 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | ARCST-GCOR-000063 | NA | Trade Partner | Material Tech Data Sheet | 0 | 1 | 0 | NA | APPROVED | 2026-08-03 | WF-001396 | NA | 2026-08-06 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-006408 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | KPTG-IntCorr-001503 | NA | Trade Partner | M2 S9-11 UPS Dcouments | 14 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 1604 | 2026-08-10 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-04 | SPECAUTO-TRANSMIT-000012 | NA | Trade Partner | HV SCADA ROP IED CSMS Interfacing Hardware | 0 | 4 | 0 | NA | APPROVED | 2026-08-04 | WF-000405 | NA | 2026-08-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-03 | NXT-TRANSMIT-001111 / Sienergy-TRANSMIT-000010 | NA | Trade Partner | Kiosk substation GA drawing S4 | 1 | 0 | 0 | NA | APPROVED | 2025-12-03 | WF-003477 | NA | 2025-12-17 |  |  |  | 2026-01-07 | NXT-WTRAN-001528 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-19 | BLUESF-TRANSMIT-000031 | NA | Trade Partner | (POUR 3) PRECAST DRAWINGS IFA | 4 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000202 |  | 2026-02-11 |  | Drawings resubmitted as per Kapitol instruction | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-001487 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-07-29 | TCL-TRANSMIT-000004 | NA | Consultant | IFC-2 Landscape Issue | 11 | 0 | 0 | NA | APPROVED | 2026-07-29 | NA | 1318 | 2026-08-03 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-004191 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-04 | RDSBIM-TRANSMIT-000150 | NA | Trade Partner | MLCSPR ¦ CARPARK NORTH BLOCKWORK PLAN & ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-08-04 | NA | 449 | 2026-08-10 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003309 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-04 | Auspan-TRANSMIT-000577 | NA | Trade Partner | Precast shop drawings for construction. Levels 4, 5 | 17 | 0 | 0 | KPTG-IntCorr-001187 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise -KPTG-IntCorr-001187 8 are ok to IFC-KPTG-TRANSMIT-003228; 8 Rejected by Kapitol PC. KPTG-SADV-004180; 1 Drawing updated and distributed |  | 2026-08-13 | KPTG-TRANSMIT-003228 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-04 | BACAU-TRANSMIT-000101 | NA | Trade Partner | Updated As Built docs | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated and distributed as advised by Rohit Hendricks. NXT-PA-006169 |  | 2026-08-04 | KPTG-TRANSMIT-020325 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-04 | SMEPS-TRANSMIT-000264 | SPARK-CRFI-KPG-000115, SPARK-CRFI-KPG-000439, SPARK-CRFI-KPG-000157 & SPARK-CRFI-KPG-000187 | Trade Partner | SMEPS-TRANSMIT-000264 | 0 | 8 | 0 | NA | APPROVED | 2026-08-04 | NA | NA | 2026-08-11 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-04 | 4DW-TRANSMIT-000206 | NA | Consultant | Structural Documentation - General updates | 4 | 0 | 0 | NA | APPROVED | 2026-08-04 | NA | 451 |  |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-003228 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-04 | Auspan-TRANSMIT-000576 | NA | Trade Partner | Update IFCed shop drawings. Level 3 | 2 | 0 | 0 | KPTG-IntCorr-001188 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise- KPTG-IntCorr-001188 |  | 2026-08-05 | Auspan-TRANSMIT-000576 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-04 | faulk-TRANSMIT-000002 | NA | Trade Partner | RW02 Eaves gutter TD | 0 | 1 | 0 | NA | APPROVED | 2026-08-04 | WF-000407 | NA | 2026-08-17 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-001667 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-04 | KPTG-IntCorr-000610 | NA | Trade Partner | Heat Protection Plan Submission | 1 | 0 | 0 | NA | APPROVED | 2026-08-04 | WF - 000558 | NA | 2026-08-10 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-04 | KALLIBRE-TRANSMIT-000023 | SPARK-CRFI-KPG-000623 | Trade Partner | IFC rev B - 0013 | 1 | 0 | 0 | NA | APPROVED | 2026-08-04 | NA | 397 | 2026-08-11 |  |  |  | 2026-08-04 | KPTG-TRANSMIT-001577 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-19 | WGAVIC-TRANSMIT-000040 | NA | Consultant | Structural Drawings - Stage 9 Pour Sequence Plans - Issued for Information | 2 | 0 | 0 | NA | APPROVED | [5 empty] | Drawings for Information only |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-04 | WSP ANZ-TRANSMIT-000100 | NA | Consultant | WSP Issued for Building Permit Documents - (Mechanical, CSM, Fire, Hydraulic and Telecomms) | 146 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated Register and distributed |  | 2026-08-04 | KPTG-TRANSMIT-006352 | Closed | 146 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-04 | Jangho-TRANSMIT-000301 | NA | Trade Partner | FT13 System Concept Drawing_Rev 03_PDF_For Approval | 9 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected QA Error |  | 2026-08-04 | KPTG-TRANSMIT-003237 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-04 | Jangho-TRANSMIT-000300 | NA | Trade Partner | FT01(updated),FT02,FT07,FT09/09b therm result | 0 | 2 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected QA Error |  | 2026-08-04 | KPTG-TRANSMIT-003239 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-04 | TTW-TRANSMIT-000212 | NA | Trade Partner | Fwd: M3 Traffic Drawings | 29 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-08-04 | KPTG-TRANSMIT-020326 | Closed | 29 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-05 | SMEPS-TRANSMIT-000201 | NA | Trade Partner | 22KV - Shop drawings IFA | 7 | 0 | 0 | NA | APPROVED | 2026-03-06 | WF-004893 | NA | 2026-03-19 |  | Internal MEMO - waiting for Kina's reply | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-020304 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-17 | Ardon-TRANSMIT-000065 | NA | Trade Partner | Previously Rejected Door Hardware - Re-submission | 0 | 0 | 0 | NA | APPROVED | 2026-07-17 | WF-006421 | NA | [6 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-04 | KALLIBRE-TRANSMIT-000024 | NA | Trade Partner | IFA rev 4 - 0061 | 1 | 0 | 0 | NA | APPROVED | 2026-08-04 | NA | 398 | 2026-08-11 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-04 | Nilsen3-TRANSMIT-000087 | NA | Trade Partner | Nilsen Sample submissions #14 | 0 | 1 | 0 | NA | APPROVED | 2026-08-04 | WF-001400 | NA | 2026-08-14 |  |  | 2026-08-17 | 2026-08-17 | KPTG-TRANSMIT-006948 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-14 | D&E-TRANSMIT-000916<br> | NA | Trade Partner | Pumps - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-07-14 | WF-006373 | NA | 2026-08-04 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-020333 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-04 | Civilex-TRANSMIT-000326 | NA | Trade Partner | Stage 2 - sample submission - 20mm Class 2 CC | 0 | 1 | 0 | NA | APPROVED | 2026-08-04 | WF-006590 | NA | 2026-08-21 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-020703 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-19 | VIA Arch-TRANSMIT-000042 | NA | Consultant | M2 S9-11 Redesign Concept Issue | 30 | 0 | 0 | NA | APPROVED | 2026-01-20 |  | 197 | 2026-01-27 |  |  |  | 2026-01-23 | KPTG-TRANSMIT-000577 | Closed | 30 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-22 | SMEPS-TRANSMIT-000251 | SPARK-CRFI-KPG-000504 | Trade Partner | NEL-CNT-SME-2801-BSE-SCH-0005,006,NEL-CNT-SME-2801-BSE-SDG-01290,0130,0131,0301,0302,0303,0314 | 0 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 368 | 2026-07-29 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-001571 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-04 | Baigents-TRANSMIT-000024 | NA | Trade Partner | Speed Panel IFA-A Package | 18 | 0 | 0 | NA | APPROVED | 2026-08-04 | NA | 605 | 2026-08-12 |  | Clarified BCE-Precast and BAI is Steel Panel |  |  |  | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-04 | SMEPS-TRANSMIT-000061 | NA | Trade Partner | SME-Commissioning Plan | 0 | 1 | 0 | NA | REJECTED | [5 empty] | the attached documents seem document numbering mistake on the Aconex. |  | 2026-08-04 | DRAFT-004166 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-04 | D&E-TRANSMIT-000966 | NA | Trade Partner | NXM3S4 - Ground & Level 1 - Mechanical Duct Layouts - Zone 3 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-04 | KPTG-TRANSMIT-020336 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-04 | D&E-TRANSMIT-000969 | NA | Trade Partner | Chilled & Condensing Water Schematics - Roof & Upper Roof Sheets - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-08-04 | NA | 4467 | 2026-08-14 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-04 | D&E-TRANSMIT-000967 | NA | Trade Partner | NXM3S4 - Level 1 - Mechanical Duct Layout - Zone 9 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | [5 empty] | For distribution |  | 2026-08-04 | KPTG-TRANSMIT-020337 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-04 | EFP-TRANSMIT-000038 | NA | Trade Partner | Entire Seismic Report | 0 | 2 | 0 | NA | APPROVED | 2026-08-04 | WF-000432 | NA | 2026-08-07 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-001153 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-04 | Civilex-TRANSMIT-000327 | NA | Trade Partner | Stage 2 - sample submission - Type F Barrier | 0 | 1 | 0 | NA | REJECTED | [5 empty] | there is a mismatch in the document numbering in Aconex and inside document. |  | 2026-08-04 | KPTG-SADV-007110 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-04 | SMEPS-TRANSMIT-000265 | SPARK-CRFI-KPG-000329 | Trade Partner | UPS-01 (A), UPS-02 (B), UPS-03 (B) | 0 | 1 | 0 | NA | APPROVED | 2026-08-04 | NA | NA | 2026-08-11 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-04 | SMEPS-IntCorr-000395 | NA | Trade Partner | MEL06-UMS BOM | 0 | 1 | 0 | NA | APPROVED | 2026-08-04 | WF - 000559 | NA | 2026-08-10 |  | NA | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-001131 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-20 | Marr Con-TRANSMIT-000002 | NA | Trade Partner | Tower cranes Radius and Elevation | 1 | 0 | 0 | NA | APPROVED | [5 empty] | For Information only |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-04 | Stowe-A-TRANSMIT-000671 | NA | Trade Partner | STOWE - Dwg Submission | 1 | 0 | 0 | NA | REJECTED | [5 empty] | the document same revision is already completed the review with approved status |  | 2026-08-04 | KPTG-SADV-007111 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-04 | PTA-TRANSMIT-000041 | NA | Trade Partner | Mater Site Plan Share for Coordination | 3 | 0 | 0 | NA | APPROVED | 2026-08-04 | NA | 607 | 2026-08-12 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-000987 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-04 | Civilex-TRANSMIT-000328 | NA | Trade Partner | Stage 2 - sample submission - No Fines Concrete - Hytec | 0 | 1 | 0 | NA | REJECTED | [5 empty] | document the same revision of FOA-B is already submitted and completed the review with Rejected status, |  | 2026-08-04 | KPTG-SADV-007113 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-04 | D&E-TRANSMIT-000294 | NA | Trade Partner | Vertigo and Filters Tech Data | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Multiple status documents in a transmittal |  | 2026-08-04 | KPTG-TRANSMIT-001573 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-04 | DLTS-TRANSMIT-000074 | NA | Trade Partner | S11-North & South Eave Gutter-IFC Issue | 63 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, updated register and distributed |  | 2026-08-04 | KPTG-TRANSMIT-006381 | Closed | 63 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-04 | D&E-TRANSMIT-000295 | SPARK-CRFI-KPG-000195 | Trade Partner | CRAC Units - In For Construction | 0 | 1 | 0 | NA | APPROVED | 2026-08-04 | NA | NA | 2026-08-11 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-04 | D&E-TRANSMIT-000968 | NA | Trade Partner | NXM3S4 - Roof Level + Upper Roof Level - Chiller Room & Cooling Tower Sections - Issued For Construction | 9 | 0 | 0 | NA | APPROVED | [5 empty] | FOR DISTRIBUTION |  | 2026-08-04 | KPTG-TRANSMIT-020348 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-04 | D&E-TRANSMIT-000300 | SPARK-CRFI-KPG-000479 | Trade Partner | Filters Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-08-04 | NA | NA | 2026-08-11 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-04 | CDL-TRANSMIT-000049 | NA | Trade Partner | Updated KPA Documentation | 6 | 0 | 0 | NA | APPROVED | 2026-08-04 | NA | 453 | 2026-08-07 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-003233 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D9 | 2026-08-04 | IVS-TRANSMIT-000017 | NA | Trade Partner | STR - Antenna Gantry - Re-Certification Issue | 10 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document number, title block to changed etc. |  | 2026-08-04 | KPTG-DA-000105 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-02 | TATE_-TRANSMIT-000012 | NA | Trade Partner | SCEC Shop Drawings Rev B | 9 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF - 000007 | NA | 2026-01-20 |  | Revise and Resubmit | 2026-01-21 | 2026-01-21 | KPTG-TRANSMIT-000057 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-27 | Eneraque-TRANSMIT-000035 | NA | Trade Partner | Stage 9 - Valve Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-06-27 | WF-001066 | NA | 2026-07-10 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-006388 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-04 | Civilex-TRANSMIT-000329 | NA | Trade Partner | Stage 2 - sample submission - Type F Barrier | 0 | 1 | 0 | NA | APPROVED | 2026-08-04 | WF-006593 | NA | 2026-08-10 |  |  | 2026-08-17 | 2026-08-17 | KPTG-TRANSMIT-020649 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-04 | HDRAus-TRANSMIT-000534 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 17 | 0 | 0 | NA | APPROVED | 2026-08-04 | NA | 4045 | 2026-08-10 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-020594 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-04 | ARCST-TRANSMIT-000370 | NA | Trade Partner | C3 Cooling Tower Roof - Issued for Construction | 129 | 0 | 0 | NA | APPROVED | 2026-08-04 | WF-006592 | NA | 2026-08-12 | [5 empty] | Open | 129 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-04 | D&E-TRANSMIT-000301 | NA | Trade Partner | Vertigo for Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision is incorrect |  | 2026-08-04 | KPTG-TRANSMIT-001574 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-04 | Civilex-TRANSMIT-000330 | NA | Trade Partner | Stage 2 - sample submission - No Fines Concrete - Hytec | 0 | 1 | 0 | NA | APPROVED | 2026-08-04 | WF-006595 | NA | 2026-08-10 |  | Holded due to missing of Arup stamp, however the same was resubmitted by Originator | 2026-08-18 | 2026-08-31 | OveArup-WTRAN-001857 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-04 | D&E-TRANSMIT-000299 | NA | Trade Partner | NEL-CNT-DEA-2801-BSV-SAM-0011 - NOT IN USE | 0 | 1 | 0 | KPTG-IntCorr-003919 | APPROVED | [5 empty] | No Longer in Use |  | 2026-08-04 | KPTG-SADV-006255 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-04 | D&E-TRANSMIT-000298 | NA | Trade Partner | NEL-CNT-DEA-2801-BSV-SAM-0011 - NOT IN USE | 0 | 1 | 0 | KPTG-IntCorr-003920 | APPROVED | [5 empty] | No Longer in use |  | 2026-08-04 | KPTG-SADV-006254 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-04 | faulk-TRANSMIT-000003 | NA | Trade Partner | TD transmittal | 0 | 3 | 0 | NA | APPROVED | 2026-08-04 | WF-000408 | NA | 2026-08-14 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-001663 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | SMEPS-TRANSMIT-000143 | NA | Trade Partner | SME - IFA Sample submissions | 0 | 12 | 0 | NA | REJECTED | [5 empty] | The revision number is not mentioned in the document - KPTG-TRANSMIT-011624 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-04 | D&E-TRANSMIT-000970 | NA | Trade Partner | NXM3S4 - Ground - Mechanical Duct Layout - Zone 8 & IW Tank room - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-04 | KPTG-TRANSMIT-020364 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-04 | Eneraque-TRANSMIT-000055 | NA | Trade Partner | Pipe Datasheet and Pipe Conformance Statement | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected : Difference in Revision date |  | 2026-08-04 | KPTG-SADV-007246 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-04 | HDRAus-TRANSMIT-000537 | NA | Consultant | Concrete plinths roof admin | 1 | 0 | 0 | NA | APPROVED | 2026-08-04 | NA | 4050 | 2026-08-06 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-020399 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-04 | Leemark-TRANSMIT-000061 | SPARK-CRFI-KPG-000365 | Trade Partner | MCC Building – FPT Gas Suppression System Calculations - IFA | 0 | 1 | 0 | KPTG-IntCorr-003923 | APPROVED | 2026-08-05 | NA | NA | 2026-08-12 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-001613 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-04 | VIA Arch-TRANSMIT-000218 | NA | Consultant | Level 02_Concrete Profile updates | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-08-04 | KPTG-TRANSMIT-006405 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-04 | EMBIND-TRANSMIT-000001 | NA | Trade Partner | Embelton Gym Isolation System Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-08-04 | WF - 001110 | NA | 2026-08-10 |  | NA | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-003243 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-04 | Leemark-TRANSMIT-000062 | NA | Trade Partner | MCC - FIRE PROTECTION LAYOUT - GL ZONE 4-7 - IFC | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Same revision received and reviewed |  | 2026-08-04 | KPTG-TRANSMIT-001579 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-04 | Highbu-TRANSMIT-000160 | NA | Trade Partner | IFC Civil drawing | 1 | 0 | 0 | NA | APPROVED | 2026-08-04 | NA | 455 | 2026-08-10 |  | workflow terminated-455#-KPTG-SADV-006166 |  | 2026-08-31 | KPTG-SADV-006166 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-04 | SMEPS-TRANSMIT-000367 | NA | Trade Partner | SME - IFA Documentation | 12 | 0 | 0 | NA | APPROVED | 2026-08-04 | NA | 4052 | 2026-08-10 |  | WF -Terminated |  | 2026-08-19 | KPTG-TRANSMIT-020724 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-04 | OWCCons-TRANSMIT-000019 | NA | Consultant | Updated Civil drawings | 4 | 0 | 0 | NA | APPROVED | 2026-08-04 | NA | 457 | 2026-08-07 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-003235 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-20 | RDSBIM-TRANSMIT-000142 | NA | Trade Partner | LINDRUM ¦ LEVEL 10 UPPER TERRACE CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-01-20 | NA | 518 | 2026-01-27 |  |  |  | 2026-02-27 | KPTG-IntCorr-000759 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-04 | ZIA-TRANSMIT-000145 | NA | Trade Partner | M3S4 CSMS Equipment Location Overall | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Revision is not updated, status difference |  | 2026-08-04 | KPTG-DA-007988 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-04 | Aurecon-WTRAN-000044 | NA | Consultant | (WF-000146) FIE FOR APPROVAL (NEW): Q4 Switchboards Rev.2 | 9 | 0 | 0 | KPTG-IntCorr-000431 | APPROVED | [5 empty] | No Action required |  | 2026-08-10 | NA | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-04 | RBG-TRANSMIT-000010 | NA | Trade Partner | Crane Base Drawings IFC | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Register update |  | 2026-08-04 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-04 | Jangho-TRANSMIT-000302 | NA | Trade Partner | FT13 System Concept Drawing_Rev A_PDF_For Construction | 9 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected QA Error |  | 2026-08-04 | KPTG-TRANSMIT-003238 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-04 | ccair-TRANSMIT-000008 | NA | Trade Partner | Mechanical Nuilderworks drawings IFC | 6 | 0 | 0 | NA | APPROVED | 2026-08-04 | NA | 1077 | 2026-08-11 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-003679 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-04 | Jangho-TRANSMIT-000303 | NA | Trade Partner | FT01(updated),FT02,FT07,FT09/09b therm result | 0 | 2 | 0 | NA | APPROVED | 2026-08-04 | WF-001091 | NA | 2026-08-11 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-003366,KPTG-TRANSMIT-003367 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-04 | DLTS-TRANSMIT-000075 | NA | Trade Partner | S9-HV Room-Re-IFA | 42 | 0 | 0 | NA | APPROVED | 2026-08-04 | WF-001397 | NA | 2026-08-13 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-006784 | Closed | 42 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-04 | CLADC-TRANSMIT-000002 | NA | Trade Partner | Shop Drawings for approval | 6 | 0 | 0 | NA | APPROVED | 2026-08-04 | WF-001399 | NA | 2026-08-11 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-006758 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-04 | ELLISAIR-TRANSMIT-000149 | NA | Trade Partner | STAGE 9 GROUND & LEVEL 01 CCW PIPE RISER FRAME DRAWING ISSUED FOR APPROVAL. | 1 | 0 | 0 | NA | APPROVED | 2026-08-04 | NA | 1611 | 2026-08-11 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-04 | ELLISAIR-TRANSMIT-000147 | NA | Trade Partner | Steel Pipework | 0 | 1 | 0 | NA | APPROVED | 2026-08-04 | WF-001402 | NA | 2026-08-14 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-007192 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-04 | ELLISAIR-TRANSMIT-000148 | NA | Trade Partner | Fire Wrap Insulation | 0 | 1 | 0 | NA | APPROVED | 2026-08-04 | WF-001403 | NA | 2026-08-14 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-007193 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-20 | WSP ANZ-TRANSMIT-000094 | NA | Consultant | Updated WSP Fire Documents | 3 | 0 | 0 | NA | APPROVED | 2026-07-20 | NA | 1612 | 2026-07-25 |  |  | 2026-08-14 | 2026-08-14 | KPTG-DA-004229 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-24 | WSP ANZ-TRANSMIT-000096 | NA | Consultant | WSP - Data Hall Fitout WIP - ELC | 8 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 1613 | 2026-07-29 |  |  | 2026-08-14 | 2026-08-14 | KPTG-DA-004230 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-24 | WSP ANZ-TRANSMIT-000096 | NA | Consultant | WSP - Data Hall Fitout WIP - Fire | 5 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 1614 | 2026-07-29 |  |  | 2026-08-14 | 2026-08-14 | KPTG-DA-004231 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-24 | WSP ANZ-TRANSMIT-000096 | NA | Consultant | WSP - Data Hall Fitout WIP - (Mechanical | 6 | 0 | 0 | NA | APPROVED | 2026-07-24 | NA | 1615 | 2026-07-29 |  |  | 2026-08-14 | 2026-08-14 | KPTG-DA-004232 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-27 | WSP ANZ-TRANSMIT-000098 | NA | Consultant | WSP - Data Hall Fitout WIP - (Telecommunications) | 7 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 1619 | 2026-07-31 |  |  | 2026-08-14 | 2026-08-14 | KPTG-DA-004234 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-30 | WSP ANZ-TRANSMIT-000099 | NA | Consultant | WSP Updated - Hydraulic Services Drawings | 9 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 1621 | 2026-08-05 |  |  | 2026-08-14 | 2026-08-14 | KPTG-DA-004235 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-04 | ARCST-TRANSMIT-000366 | NA | Trade Partner | C1 Cooling Tower HD Bolts - Issued for Construction | 5 | 0 | 0 | NA | APPROVED | 2026-08-04 | WF-006598 | NA | 2026-08-10 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-04 | KPTG-IntCorr-001934 | NA | Trade Partner | O&M Manual - EPOXY FLOORING - CGC-NXD1S2 | 0 | 1 | 0 | NA | APPROVED | 2026-08-04 | WF-001179 | NA | 2026-08-10 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-20 | Aurecon-TRANSMIT-000031 | NA | Trade Partner | HVSB LV Protection Study Memo - REPORT | 0 | 1 | 0 | NA | APPROVED | [9 empty] | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-04 | KPTG-IntCorr-001939 | NA | Trade Partner | O&M Manual - CEILINGS AND PARTITIONS - NEXTDC D1 Stage 2 | 0 | 1 | 0 | NA | APPROVED | 2026-08-04 | WF-001180 | NA | 2026-08-10 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-04 | SKS Tech-TRANSMIT-000199 | NA | Trade Partner | D1S2 - Facilities IT schematicn | 2 | 0 | 0 | NA | REJECTED | [5 empty] | QA ERROR - FC STAMP MISSING |  | 2026-08-04 | KPTG-IntCorr-001944 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-04 | DCN-TRANSMIT-000028 | NA | Trade Partner | M2S9 Link Bridge Structural IFC 03 Shop Drawings | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required, updated register and distributed |  | 2026-08-04 | KPTG-TRANSMIT-006401 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-04 | DLTS-TRANSMIT-000076 | NA | Trade Partner | S10-L1 H Frames-Re-IFA | 35 | 0 | 0 | NA | APPROVED | 2026-08-04 | WF-001404 | NA | 2026-08-13 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-006788 | Closed | 35 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-04 | fjc-TRANSMIT-000176 | NA | Consultant | Architecturals - Drawing Updates | 5 | 0 | 0 | NA | APPROVED | 2026-08-04 | NA | 729 | 2026-08-12 |  |  | 2026-08-04 | 2026-08-04 | KPTG-SADV-005196 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-04 | SMEPS-TRANSMIT-000089 | NA | Trade Partner | GLP's, Antenna, FS & Tenancy DB Sample Drawings {IFA-1} | 0 | 12 | 0 | NA | REJECTED |  | NA | NA |  |  | Need to revise KPTG-SADV-007248 |  | 2026-08-04 | KPTG-SADV-007248 | Closed | 12 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-07-31 | fjc-TRANSMIT-000175 | NA | Consultant | Architecturals - Ground Design Changes, Wall Types, Tower CPP | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | WF-000882 | NA | 2026-08-07 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-002822 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-04 | KETE-TRANSMIT-000032 | NA | Trade Partner | : Kete - Updated Revision Status IFC Drawings | 11 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Register and transmit as advised by Alex McDonald - KPTG-TRANSMIT-003067 |  | 2026-08-04 | KPTG-TRANSMIT-003067 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-04 | PCForm-TRANSMIT-000107 | NA | Trade Partner | Updated Screen Drawings - Reduced Overhang | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Aconex Register updated as advised by Kapitol DM. |  | 2026-08-04 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-04 | IJF-TRANSMIT-000006 | NA | Trade Partner | Re: Joinery - Prototype Drawings | 44 | 0 | 0 | NA | APPROVED | 2026-08-04 | NA | 1653 | 2026-08-13 |  | 1 Drawing terminated and initiated review | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-003209 | Closed | 44 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | CRSol-TRANSMIT-000076 | NA | Trade Partner | M3S4 CRS CEILING SHOPDRAWINGS ISSUED FOR APPROVAL REV. B | 10 | 0 | 0 | NA | REJECTED | [5 empty] | The attachment of the document M3-ARC-CRS-SDRG-C-0401-1301 is incorrect |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-04 | Rinco-TRANSMIT-000066: | NA | Consultant | Structural drawings Issued for Construction | 17 | 0 | 0 | NA | APPROVED | 2026-08-04 | NA | 1656 | 2026-08-07 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-003339 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-04 | Jangho-TRANSMIT-000103 | NA | Trade Partner | Podium 1-2F Shop Drawings Rev01 | 69 | 0 | 0 | NA | APPROVED | 2026-08-04 | WF-000651 | NA | 2026-08-13 |  | Aconex workflow is imitated as advised by kapitol PC, |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-04 | LGCE-TRANSMIT-000075 | NA | Trade Partner | : Level 1 IFC second review | 2 | 0 | 0 | KPTG-IntCorr-001115 | APPROVED | 2026-08-14 | NA | 766 | 2026-08-20 |  | ifc - Tayla to confirm -KPTG-IntCorr-001115 | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-001652 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-04 | IJF-TRANSMIT-000008 | NA | Trade Partner | Prototype Joinery - Kitchen Drawings - IFC | 14 | 0 | 0 | NA | APPROVED | 2026-08-04 | WF-000653 | NA | 2026-08-17 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-001547 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-04 | L.E.S.-TRANSMIT-000040 | NA | Trade Partner | Smoke Detector Technical Data Sheet - Rev 1 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rev. QA Error - Coversheet |  | 2026-08-04 | KPTG-TRANSMIT-003271 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-04 | L.E.S.-TRANSMIT-000041 | NA | Trade Partner | Electrical Shop Drawing Register, Procurement Register | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Doc. Number - QA Error |  | 2026-08-04 | KPTG-TRANSMIT-003272 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-04 | Joinery Samples - teams message Justin Shu | NA | Trade Partner | Joinery Samples - Aconex uploading | 0 | 14 | 0 | NA | APPROVED |  | NA | NA |  |  | RegisterUpdated |  | 2026-08-04 | NA | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-04 | NXT-TRANSMIT-001676 | NA | Client | Fwd: Vertiv Seismic Certifications M3- Stage 4- LVSB | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-08-04 | KPTG-DA-007963 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-05 | INTRFRM-TRANSMIT-000114 | NA | Trade Partner | Hydraulic Tech Data (Submission 7) | 0 | 1 | 0 | NA | APPROVED | 2026-08-05 | WF-000409 | NA | 2026-08-14 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-001835 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-04 | HDRAus-TRANSMIT-000536 | NA | Consultant | Re: M3 Stage 4 - Document upload - Customer Office Re-Issue | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-04 | KPTG-TRANSMIT-020334 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-03 | LANSA-TRANSMIT-000074 | NA | Trade Partner | LEVEL 8 WATER SERVICES LAYOUT | 2 | 0 | 0 | NA | APPROVED | 2025-12-03 | WF-000781 | 490 | 2025-12-09 |  |  | 2025-12-16 | 2025-12-16 | KPTG-SADV-004721 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-05 | TATE_-TRANSMIT-000013 | NA | Trade Partner | Structural Ceiling shop drawings Rev C | 5 | 0 | 0 | NA | APPROVED | 2026-01-13 | WF - 000006 | NA | 2026-01-13 |  | IFC drawing | 2026-01-19 | 2026-01-19 | KPTG-TRANSMIT-000054 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-04 | D&E-TRANSMIT-000971 | NA | Trade Partner | Fwd: NXM3S4 - Level 1 - Mechanical Duct Layout - Zone 10 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-08-04 | KPTG-TRANSMIT-020339 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-05 | Auspan-TRANSMIT-000578 | NA | Trade Partner | Update level 3 precast shop drawings | 2 | 0 | 0 | KPTG-IntCorr-001198 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001198 OK TO IFC - KPTG-TRANSMIT-003187 |  | 2026-08-12 | KPTG-TRANSMIT-003187 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-04 | D&E-TRANSMIT-000972 | NA | Trade Partner | NXM3S4 - Level 1 - Mechanical Duct Layout - Zone 8 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-08-04 | KPTG-TRANSMIT-020340 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-04 | D&E-TRANSMIT-000973 | NA | Trade Partner | NXM3S4 - Roof Level - Chilled Room Sections - Sheet 2 of 5 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-04 | KPTG-TRANSMIT-020346 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-05 | WilsonPD-TRANSMIT-000157 | NA | Trade Partner | HYDRAULIC SERVICES STAGE 10 GROUND FLOOR- SEWER & STORMWATER LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-08-05 | NA | 1624 | 2026-08-11 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-006912 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-05 | RDSBIM-TRANSMIT-000235 | NA | Trade Partner | 511 SRC ¦ L07 RCP ¦ IFC | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-08-05 | KPTG-TRANSMIT-003224 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-05 | WilsonPD-TRANSMIT-000158 | NA | Trade Partner | HYDRAULIC SERVICES STAGE 10 GROUND FLOOR -WATER SUPPLY LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-08-05 | NA | 1626 | 2026-08-11 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-006916 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-05 | ccair-TRANSMIT-000137 | NA | Trade Partner | Mechanical shop drawings for GF - BTR changes | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-08-05 | KPTG-TRANSMIT-003225 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-05 | ELLISAIR-TRANSMIT-000150 | NA | Trade Partner | Stage 10 Ground Floor Duct layout drawings issued for Approval. | 5 | 0 | 0 | NA | APPROVED | 2026-08-05 | NA | 1628 | 2026-08-11 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-006857 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | NXT-TRANSMIT-001197 EAEGROUP-TRANSMIT-000059 | NA | Trade Partner | C1 Zone BUSDUCT FA - FB - FC Shop drawings | 3 | 1 | 0 | NA | APPROVED | 2026-01-20 | WF-003885 |  | 2026-02-02 |  |  |  | 2026-01-20 | NXT-PA-003118 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-05 | Eneraque-TRANSMIT-000056 | NA | Trade Partner | Pipe Datasheet and Pipe Conformance Statement | 0 | 1 | 0 | NA | APPROVED | 2026-08-05 | WF-001409 | NA | 2026-08-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-07-22 | SMEPS-TRANSMIT-000251 | SPARK-CRFI-KPG-000462 | Trade Partner | NEL-CNT-SME-2801-BSE-SCH-0005,006,NEL-CNT-SME-2801-BSE-SDG-01290,0130,0131,0301,0302,0303,0314 | 0 | 0 | 0 | NA | APPROVED | 2026-07-22 | NA | 368 | 2026-07-29 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-001582 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-05 | KPTG-IntCorr-000742 | NA | Client | BU Plan Rev 4 | 0 | 1 | 0 | NA | APPROVED | 2026-08-05 | WF-000433 | NA | 2026-08-10 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-05 | RED Fire-TRANSMIT-000005 | NA | Consultant | Revised FER (Version: FER8) for approval | 0 | 1 | 0 | NA | APPROVED | [5 empty] | Updated document reguster and transmitted to all concerned parties.KPTG-TRANSMIT-003221 |  | 2026-08-05 | KPTG-TRANSMIT-003221 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-05 | WSP ANZ-TRANSMIT-000102 | NA | Consultant | Updated - WSP Mechanical Services Specification | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-08-05 | KPTG-TRANSMIT-006426 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-05 | ACG-TRANSMIT-000113 | NA | Trade Partner | M3 Stage 2 - FOV Register | 0 | 1 | 0 | NA | APPROVED | 2026-08-05 | WF-006600 | NA | 2026-08-12 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-05 | SMEPS-TRANSMIT-000062 | NA | Trade Partner | SME-Commissioning Plan | 0 | 1 | 0 | NA | APPROVED | 2026-08-05 | WF-000410 | NA | 2026-08-18 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-002317 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-05 | ZIA-TRANSMIT-000147 | NA | Trade Partner | M3S4 Ground Floor & Level 1 Strobe light and OS location (FC-1) | 6 | 0 | 0 | NA | APPROVED | 2026-08-05 | NA | 4056 | 2026-08-14 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-05 | HDRAus-TRANSMIT-000538 | NA | Consultant | As-Built Drawings for Separable Portion 9 & 12 - DHB3 + DHB4 | 5 | 0 | 0 | NA | APPROVED | 2026-08-05 | NA | 4471 | 2026-08-07 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-05 | SES AU-TRANSMIT-000012 | NA | Trade Partner | Security Network Drawing Update | 0 | 1 | 0 | NA | APPROVED | 2026-08-05 | WF - 000560 | NA | 2026-08-07 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-19 | MCM Tile-TRANSMIT-000008 | NA | Trade Partner | Re: Lift Tiles | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document number is incorrect |  | 2026-01-19 | KPTG-SADV-000923 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-05 | ELLISAIR-TRANSMIT-000151 | NA | Trade Partner | HAC return air grille | 0 | 1 | 0 | NA | APPROVED | 2026-08-05 | WF-001412 | NA | 2026-08-17 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-007376 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-05 | LANSA-TRANSMIT-000112 | NA | Trade Partner | Level 3 Eastern Pavillion Trench Grates - | 4 | 0 | 0 | NA | APPROVED | [5 empty] | IFC |  | 2026-08-05 | KPTG-TRANSMIT-003225 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-05 | SMEPS-TRANSMIT-000090 | NA | Trade Partner | GLP's, Antenna, FS & Tenancy DB Sample Drawings {IFA-1} | 0 | 12 | 0 | NA | APPROVED | 2026-08-05 | WF-001413 | NA | 2026-08-17 |  |  | 2026-08-17 | 2026-08-17 | KPTG-TRANSMIT-006941, KPTG-TRANSMIT-006953 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-05 | ELLISAIR-TRANSMIT-000152 | NA | Trade Partner | Pipework Painting | 0 | 1 | 0 | NA | APPROVED | 2026-08-05 | WF-001414 | NA | 2026-08-17 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-006571 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-05 | ZIA-TRANSMIT-000146 | NA | Trade Partner | M3S4 CSMS Equipment Location Overall | 4 | 0 | 0 | NA | APPROVED | 2026-08-05 | NA | 4060 | 2026-08-14 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-020823 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-05 | HDRAus-TRANSMIT-000539 | NA | Trade Partner | As-Built Drawings for Separable Portion 10 & 11 - DHB7 + DHB8 - | 5 | 0 | 0 | NA | APPROVED | 2026-08-05 | NA | 4473 | 2026-08-14 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-05 | ccair-TRANSMIT-000009 | NA | Trade Partner | Apartment low profile duct and non-return damper for approval | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Technical Data Submission Cover Sheet missing. |  | 2026-08-05 | KPTG-SADV-004529 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-05 | ARCH-TRANSMIT-000173 | NA | Consultant | MLC - SPR - ISC - GA and CPP updated Facade | 4 | 0 | 0 | NA | APPROVED | 2026-08-05 | NA | 459 | 2026-08-10 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-003230 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-05 | LNCPPL-TRANSMIT-000026 | NA | Trade Partner | Electrical Shop Drawings - Site Inground - FC-1 | 0 | 2 | 0 | NA | REJECTED | [5 empty] | The attached documents are submitted for IFC without approval IFA. the previous IFA is rejected. |  | 2026-08-05 | DRAFT-004232 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-05 | L.E.S.-TRANSMIT-000042 | NA | Trade Partner | Low profile smoke alarm tech data sheet | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-08-05 | KPTG-TRANSMIT-003303 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-14 | TATE_-TRANSMIT-000014 | NA | Trade Partner | COLO 4 CELL 2,4 & TYPICAL DETAILS RESUMISSION | 4 | 0 | 0 | NA | APPROVED | 2026-01-19 | WF - 0000014 | NA | 2026-01-25 |  |  | 2026-01-30 | 2026-01-30 | KPTG-TRANSMIT-000065 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-05 | ARCST-TRANSMIT-000375 | NA | Trade Partner | Stage 1 Cross Over IFA Drawings | 32 | 0 | 0 | NA | APPROVED | 2026-08-05 | WF-006607 | NA | 2026-08-21 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-05 | WAM-TRANSMIT-000840 | NA | Consultant | IFC - A12 CSP Level 2 - Hobs to match balustrade detail updates | 2 | 0 | 0 | NA | APPROVED | 2026-08-05 | NA | 1079 | 2026-08-07 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-003347 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-05 | STRBCK-TRANSMIT-000004 | NA | Trade Partner | Backfilling civil material conformance | 0 | 3 | 0 | NA | APPROVED | 2026-08-05 | NA | 609 | 2026-08-13 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-000851 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-05 | SMEPS-TRANSMIT-000368 | NA | Trade Partner | Revised Jemena Easement Shopdrawing - 05.08.2026 | 2 | 0 | 0 | NA | APPROVED | 2026-08-05 | WF-006608 | NA | 2026-08-13 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-020807 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-05 | D&E-TRANSMIT-000974 | NA | Trade Partner | NXM3S4 - Ground & Level 1 - Mech Elec Layout Zones - Issued For Approval | 11 | 0 | 0 | NA | APPROVED | 2026-08-05 | NA | 4146 | 2026-08-11 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-05 | Baigents-TRANSMIT-000029 | NA | Trade Partner | Level 01 Beam Edge Form Drawings | 3 | 0 | 0 | NA | REJECTED | [5 empty] | wrong naming convention |  | 2026-08-05 | Awaiting approval | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-05 | ADP-TRANSMIT-000131 | NA | Trade Partner | Updated Electrical Drawings | 9 | 0 | 0 | NA | APPROVED | 2026-08-05 | NA | 450 |  |  |  | 2026-08-03 | 2026-08-10 | KPTG-TRANSMIT-001699 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-05 | D&E-TRANSMIT-000302 | SPARK-CRFI-KPG-000569 | Trade Partner | MWYCCB - GROUND LEVEL - RCP LAYOUT ZONE 2 & ZONE 4 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-08-05 | NA | 399 | 2026-08-12 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-001588 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-05 | M.S.-TRANSMIT-000083 | NA | Trade Partner | JH03 - Handle Tech data sheets | 0 | 1 | 0 | NA | APPROVED | 2026-08-05 | WF-001092 | NA | 2026-08-06 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-07-28 | SMEPS-TRANSMIT-000360 | NA | Trade Partner | Transmittal: Electrical Services 22KV Documentation | 1 | 0 | 0 | NA | APPROVED | 2026-07-28 | WF-006517 | NA | 2026-08-04 |  |  | 2026-08-05 | 2026-08-05 | KPTG-TRANSMIT-020382 KPTG-TRANSMIT-020385 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-19 | Danlai-TRANSMIT-000005 | NA | Trade Partner | Technical Data and Sample Sheet | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document number & revision are incorrect. |  | 2026-01-19 | KPTG-SADV-003378 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-05 | Entire M-TRANSMIT-000054 | NA | Trade Partner | Mechanical AS-BUILT drawings | 31 | 0 | 0 | NA | APPROVED | 2026-08-05 | WF - 000561 | NA | 2026-08-11 |  | NA |  |  |  | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-05 | SES AU-TRANSMIT-000095 | NA | Trade Partner | SCEC SECURITY PANEL ELEVATION AND SETOUTS | 1 | 0 | 0 | NA | APPROVED | 2026-08-05 | WF-000434 | NA | 2026-08-11 |  |  |  | 2026-08-13 | KPTG-WTRAN-000859 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-05 | WilsonPD-TRANSMIT-000117 | NA | Trade Partner | Hot Water Return Pumps | 0 | 1 | 0 | NA | APPROVED | 2026-08-05 | WF - 001111 | NA | 2026-08-11 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-05 | faulk-TRANSMIT-000004 | NA | Trade Partner | Re: Shop drawings | 0 | 2 | 0 | NA | REJECTED | [5 empty] | The document number in Aconex appears to be different from the document number shown inside the attached document. The inside document the submitted revision details are missing in the revision history |  | 2026-08-05 | DRAFT-004239 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-05 | SES AU-TRANSMIT-000096 | NA | Trade Partner | NCR - Installation Not As Per Approved Shop Drawing (Flex Aisle Cameras) | 1 | 0 | 0 | NA | APPROVED | 2026-08-05 | WF-000435 | NA | 2026-08-07 |  |  |  | 2026-08-05 | KPTG-TRANSMIT-001145 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-05 | ARCST-TRANSMIT-000376 | NA | Trade Partner | M3S4 - Remaining Infill Mechanical Corridors - Issued for Approval | 20 | 0 | 0 | NA | APPROVED | 2026-08-05 | WF-006609 | NA | 2026-08-11 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-05 | Leemark-TRANSMIT-000063 | SPARK-CRFI-KPG-000365 | Trade Partner | MCC - L1 Fire Protection Drawings 121-124 - IFC | 4 | 0 | 0 | NA | APPROVED | 2026-08-05 | NA | 400 | 2026-08-12 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-001584 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-05 | SES AU-TRANSMIT-000094 | NA | Trade Partner | Re: T1a Setout Elevation Drawing Required | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Document Numver is not in standerd -Requested to resubmit: KPTG-IntCorr-000743 |  | 2026-08-05 | KPTG-IntCorr-000743 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-05 | SMEPS-TRANSMIT-000066 | NA | Trade Partner | Shop Drawings: Communications FC-1 | 3 | 0 | 0 | NA | APPROVED | 2026-08-05 | 452 | NA | 2026-08-11 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-001544 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-05 | INTRFRM-TRANSMIT-000115 | NA | Trade Partner | Geelong Edge - Civil Tech Data (Submission 10) | 0 | 1 | 0 | NA | APPROVED | 2026-07-29 | WF-000413 | NA | 2026-08-12 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-001671 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-19 | Normark-TRANSMIT-000012 (WF-1) | NA | Trade Partner | Tech data for review and approval | 0 | 4 | 0 | NA | APPROVED | 2026-01-19 | WF-000731 |  | 2026-01-21 |  |  |  | 2026-01-21 | KPTG-TRANSMIT-002160 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-05 | KBGA-TRANSMIT-000018 | NA | Trade Partner | Akatherm HDPE tech data for approval | 0 | 1 | 0 | NA | APPROVED | 2026-08-05 | NA | 611 | 2026-08-13 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-000914 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-05 | NXT-TRANSMIT-000465 | NA | Client | M3 Stage 6 - FOKs From Mrs Joh | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | No Action required |  | 2026-08-05 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-05 | Leemark-TRANSMIT-000064 | SPARK-CRFI-KPG-000317 | Trade Partner | Re: MCC - FIRE PROTECTION LAYOUT - GL ZONE 4-7 - IFC | 4 | 0 | 0 | NA | APPROVED | 2026-08-05 | NA | 401 | 2026-08-05 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-001586 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-05 | Diadem-TRANSMIT-000002 | NA | Consultant | Wayfinding DD 03 package | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-08-05 | KPTG-TRANSMIT-003302 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-05 | KBGA-TRANSMIT-000017 | NA | Trade Partner | Tech Data for Approval | 0 | 4 | 0 | NA | APPROVED | 2026-08-05 | NA | 613 | 2026-08-13 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-000913 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-05 | WGAVIC-TRANSMIT-000177 | NA | Consultant | M2 - Stage 10 Level 1 and 2 Slabs - Issued for Construction | 11 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-08-05 | KPTG-TRANSMIT-006437 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-05 | Auspan-TRANSMIT-000579 | NA | Trade Partner | Update IFCed level 4 precast shop drawings | 5 | 0 | 0 | KPTG-IntCorr-001199 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001199 1 OK TO IFC-KPTG-TRANSMIT-003254, 3 Rejected as advised by Kapitol PC-KPTG-SADV-004283, 1 Superseded |  | 2026-08-19 | KPTG-TRANSMIT-003254 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-06 | INTRFRM-TRANSMIT-000116 | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 4) | 0 | 4 | 0 | NA | APPROVED | 2026-08-05 | WF-000414 | NA | 2026-08-14 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001629 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-05 | POTTSENG-TRANSMIT-000045 | NA | Trade Partner | 671C: HYDRAULIC SERVICES - BASEMENT 1 & 2 - DRAINAGE LAYOUTS | 2 | 0 | 0 | NA | APPROVED | 2026-08-05 | NA | 726 | 2026-08-12 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001620 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-05 | POTTSENG-TRANSMIT-000046 | NA | Trade Partner | : 671C: HYDRAULIC SERVICES - BASEMENT 1 - WATER LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-08-05 | NA | 728 | 2026-08-12 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-001635 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-19 | Normark-TRANSMIT-000012(WF-2) | NA | Trade Partner | Tech data for review and approval | 0 | 2 | 0 | NA | APPROVED | 2026-01-19 | WF-000730 |  | 2026-01-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-05 | KPTG-TRANSMIT-001503 | NA | Trade Partner | : Fwd: Precast shop drawings for construction Level 10 to 14. | 25 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | ifc- Register as advised by Kian - Kapitol PC, KPTG-TRANSMIT-001503 |  | 2026-08-05 | KPTG-TRANSMIT-001503 | Closed | 25 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-05 | LGCE-TRANSMIT-000076 | NA | Trade Partner | : Builders works | 1 | 0 | 0 | KPTG-IntCorr-001129 | APPROVED |  | NA | NA |  |  | Tayla to advise -KPTG-IntCorr-001129 Registe update and transmitted: KPTG-TRANSMIT-001511 | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-001511 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-05 | KPTG-TRANSMIT-001479 | NA | Trade Partner | : interspan drawing | 6 | 0 | 0 | NA | APPROVED | 2026-08-05 | WF-000657 | NA | 2026-08-12 |  | As advised by Kian, Initiate Level 1 drawings review with Bates - KG; | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001531 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-05 | KPTG-IntCorr-001118 671- | NA | Trade Partner | Sample submission Forms for Longteng GRC 260415-01 | 0 | 1 | 0 | NA | APPROVED | 2026-08-05 | WF-000658 | NA | 2026-08-12 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-001585 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-05 | crossfir-TRANSMIT-000030 | NA | Trade Partner | Wet & Dry Fire - Basement 01, IFC | 2 | 0 | 0 | KPTG-IntCorr-001128 | APPROVED | 2026-08-06 | NA | 733 | 2026-08-13 |  | Tayla to advise - KPTG-IntCorr-001128 | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-001637 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-31 | VIA Arch-TRANSMIT-000215 | NA | Consultant | BRIDGE LINK ISSUE FOR BUILDING PERMIT | 8 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 1641 | 2026-08-05 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-006563 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-05 | WSP ANZ-TRANSMIT-000101 | NA | Consultant | WSP Issued for Building Permit Documents - (Electrical Services) | 52 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project Team |  | 2026-08-05 | KPTG-TRANSMIT-006409 | Closed | 52 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-05 | VIA Arch-TRANSMIT-000219 | NA | Consultant | Updated Schedules and Drawings | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project Team |  | 2026-08-05 | KPTG-TRANSMIT-006448 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-05 | VIA Arch-TRANSMIT-000220 | NA | Consultant | M2 S9 FM Office & Store Amendments | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to the Project Team |  | 2026-08-05 | KPTG-TRANSMIT-006451 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-05 | Nilsen3-TRANSMIT-000088 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 9 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Need to revise KPTG-SADV-007280 |  | 2026-08-05 | KPTG-SADV-007280 | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-19 | M.S.-TRANSMIT-000036 | NA | Trade Partner | WL10 Wall panelling IFA Re- Issue of IFA drawings | 4 | 0 | 0 | NA | APPROVED | 2026-01-19 | NA | 403 | 2026-01-26 |  |  | 2026-03-11 | 2026-03-12 | KPTG-SADV-003848 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-05 | SMEPS-TRANSMIT-000091 | NA | Trade Partner | Typical Switch room AUX-DB (MA-PF) | 0 | 1 | 0 | NA | APPROVED | 2026-08-05 | WF-001415 | NA | 2026-08-17 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-006567 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-05 | DLTS-TRANSMIT-000077 | NA | Trade Partner | S11-Screen-IFA issue | 35 | 0 | 0 | NA | APPROVED | 2026-08-05 | WF-001584 | NA | 2026-08-14 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-007300 | Closed | 35 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-05 | WSP ANZ-TRANSMIT-000103 | NA | Consultant | Reissue - WSP Issued for Building Permit Documents - (Fire & Hydraulic Services) | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and Distributed to the Project Team |  | 2026-08-05 | KPTG-TRANSMIT-006457 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-05 | INGEN3D-TRANSMIT-000230 | NA | Trade Partner | ZONE A - PRECAST COLUMN ELEVATION | 1 | 0 | 0 | NA | APPROVED | 2026-08-05 | WF-001094 | NA | 2026-08-13 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-003479 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-05 | INGEN3D-TRANSMIT-000231 | NA | Trade Partner | Marking Plans (Precast Column Elevation) - IFC (04-08-2026) | 17 | 0 | 0 | NA | APPROVED | 2026-08-05 | WF-001095 | NA | 2026-08-13 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-05 | Jangho-TRANSMIT-000304 | NA | Trade Partner | FT13 System Concept Drawing_Rev 03_PDF_For Approval | 18 | 0 | 0 | NA | APPROVED | 2026-08-05 | NA | 1081 | 2026-08-13 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-05 | Jangho-TRANSMIT-000306 | NA | Trade Partner | Window handle Option 4 CZS619 Sample Submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | rev.1 under client review |  | 2026-08-05 | KPTG-TRANSMIT-003298 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-06 | JCI-TRANSMIT-000022 | NA | Trade Partner | BAS SAT Alarm Changes | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected: Document numbering is not in standerd, requested to resubmit:KPTG-TRANSMIT-001146 |  | 2026-08-06 | KPTG-TRANSMIT-001146 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-06 | ZLH P/L-TRANSMIT-000019 | NA | Trade Partner | Proposed Steel Sheet - ZLH | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Mismatch in title. |  | 2026-08-06 | KPTG-TRANSMIT-001543 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-05 | fjc-TRANSMIT-000177 | NA | Consultant | Architectural Wall Types Updates coordinated to partition shop drawing reviews | 8 | 0 | 0 | NA | APPROVED | 2026-08-05 | NA | 730 | 2026-08-08 |  | KPTG-SADV-005197 - 1 drawing reject because the tittle and status are incorrect | 2026-08-10 | 2026-08-10 | KPTG-SADV-005243 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-19 | KPTG-IntCorr-004021 -Tuff Turf Sample | NA | Trade Partner | Tuff Turf Sample | 0 | 1 | 0 | NA | APPROVED | 2026-01-19 | WF-000732 |  | 2026-01-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-06 | Nilsen3-TRANSMIT-000249 | NA | Trade Partner | Nilsen Shop Drawings - updated IFC | 1 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 4065 | 2026-08-15 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-020793 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-05 | NXES-TRANSMIT-000067 | NA | Trade Partner | Lighting Protection Layout | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-005202 - Tittle incorrect | 2026-08-05 | 2026-08-05 | KPTG-SADV-005202 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-08-06 | PROLMC-TRANSMIT-000052 | NA | Trade Partner | Re: Stair Nosing 22kv | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-08-06 | KPTG-DA-008002 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-06 | ASV-TRANSMIT-000196 | NA | Trade Partner | Hydraulic Data Sheet - Sound Lagging | 0 | 1 | 0 | NA | APPROVED | 2026-08-06 | WF-006613 | NA | 2026-09-01 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-020478 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-06 | SMEPS-TRANSMIT-000369 | NA | Trade Partner | SME IFA - Documentation | 2 | 0 | 0 | NA | REJECTED | [5 empty] | REVISION NOT UPDATED |  | 2026-08-06 | KPTG-DA-008003 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-06 | SMEPS-TRANSMIT-000370 | NA | Trade Partner | SME IFC Documentation | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Revision date error |  | 2026-08-06 | KPTG-DA-008016 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-06 | RDSBIM-TRANSMIT-000016 | NA | Trade Partner | NXM3S6 ¦ LOWER ROOF ¦ CPP-BLOCK 2 ¦ IFR | 3 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 617 | 2026-08-14 |  |  | 2026-08-18 | 2026-08-19 | KPTG-TRANSMIT-001014 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-06 | SMEPS-TRANSMIT-000067 | NA | Trade Partner | Shop Drawings: Communications FC-1 (submission 2) | 1 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 454 | 2026-08-12 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-001577 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-06 | WilsonPD-TRANSMIT-000159 | NA | Trade Partner | HYDRAULIC SERVICES STAGE 9 GROUND FLOOR- SEWER & STORMWATER LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 1643 | 2026-08-10 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-006543 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-20 | KETE-TRANSMIT-000110 | NA | Trade Partner | Kete - Updated Revision 7014 | 1 | 0 | 0 | NA | APPROVED | 2026-01-22 | WF-000568 |  | 2026-01-27 |  |  | 2026-02-04 | 2026-02-04 | KPTG-TRANSMIT-001726 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-06 | WilsonPD-TRANSMIT-000160 | NA | Trade Partner | HYDRAULIC SERVICES STAGE 9 GROUND FLOOR - WATER SUPPLY LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 1645 | 2026-08-11 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-006625 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-06 | ELLISAIR-TRANSMIT-000153 | NA | Trade Partner | Stage 10 Level 2 Duct & Pipe layout drawings issued for Approval. | 2 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 1647 | 2026-08-13 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-007168 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-06 | SES AU-TRANSMIT-000097 | NA | Trade Partner | HAC TYPICAL ELEVATION COLO 4 & 5-IFA | 1 | 0 | 0 | NA | APPROVED | 2026-08-06 | WF-000436 | NA | 2026-08-11 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-001157 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-06 | Carr-TRANSMIT-000080 | NA | Consultant | Town Planning - Issue for Secondary Consent | 25 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 327 | 2026-08-13 |  | Review Voided as received updated drawings from Carr. |  | 2026-08-07 | NA | Closed | 25 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-06 | RDSBIM-TRANSMIT-000080 | NA | Trade Partner | DISTLV ¦ LEVEL 01 STAGE 4B3 PARTITION WALL | 5 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 1083 | 2026-08-10 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-003444 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-06 | Leemark-TRANSMIT-000065 | SPARK-CRFI-KPG-000365 | Trade Partner | MCC - LEVEL 1 WET FIRE LAYOUT-ZONE 5-7 - IFC | 3 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 402 | 2026-08-13 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-001590 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-06 | EAEGROUP-TRANSMIT-000006 | NA | Trade Partner | IFA Shop Drawings – Main Corridor 2500A Busduct Runs | 3 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Mismatch in title. |  | 2026-08-06 | KPTG-TRANSMIT-001564 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-06 | KPTG-TRANSMIT-001134 | NA | Trade Partner | MEL05C4 Commissioning Plan | 0 | 1 | 0 | NA | APPROVED | 2026-08-06 | WF - 000562 | NA | 2026-08-10 |  | NA | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-001136 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-06 | WilsonPD-TRANSMIT-000162 | NA | Trade Partner | Updated Pressure Booster Pumps IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, updated register and distributed |  | 2026-08-06 | KPTG-TRANSMIT-006476 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-06 | L.E.S.-TRANSMIT-000044 | NA | Trade Partner | 240v Smoke Alarm | 0 | 1 | 0 | NA | APPROVED | 2026-08-06 | WF-001105 | NA | 2026-08-11 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-003600 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-02 | ECBS-TRANSMIT-000033 | NA | Trade Partner | Revised tach data for AM41 for review | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Requested to resubmit |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2025-12-15 | RLA-TRANSMIT-000238 | NA | Consultant | TP SECONDARY CONSENT - REMAINING ITEMS | 18 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Information document sent to consultant KPTG-TRANSMIT-002539 |  |  |  | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-08-06 | PROLMC-TRANSMIT-000054 | NA | Trade Partner | Re: Stair Nosing 22kv | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect project code |  | 2026-08-06 | KPTG-DA-008009 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-06 | VIA Arch-TRANSMIT-000221 | NA | Consultant | M2S9 - Window Elevation Updates | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-08-06 | KPTG-TRANSMIT-006480 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-06 | Entire M-TRANSMIT-000082 | NA | Trade Partner | Roof Mechanical Penetration drawings - Issued for Construction | 4 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Mismatch in date |  | 2026-08-06 | KPTG-TRANSMIT-001566 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-06 | EAEGROUP-TRANSMIT-000118 | NA | Trade Partner | Updated Shop Drawing Revision - Loadbank | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision |  | 2026-08-06 | KPTG-IntCorr-017385 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-31 | ARCST-TRANSMIT-000367 | NA | Trade Partner | C1 Cooling Tower Grating - Issued for Construction | 167 | 0 | 0 | NA | APPROVED | 2026-07-31 | WF-006572 | NA | 2026-08-04 |  | As instructed by Lola - KPTG-IntCorr-017371, WF terminated |  | 2026-08-06 | KPTG-IntCorr-017371 | Closed | 167 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-06 | DLTS-TRANSMIT-000079 | NA | Trade Partner | S9-Link Bridge-IFC issue | 8 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Drawings, Updated register and distributed to Project team |  | 2026-08-06 | KPTG-TRANSMIT-006484 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-06 | L.E.S.-TRANSMIT-000043 | NA | Trade Partner | Load Center Data sheet and Drawing IFA | 2 | 1 | 0 | NA | REJECTED | [5 empty] | Revision not Matching & SPD submitted as combined PDF |  | 2026-08-06 | KPTG-TRANSMIT-003307 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-06 | ELLISAIR-TRANSMIT-000154 | NA | Trade Partner | Revised Stage 10 Level 1 drawing - Pipework issued for Approval. | 2 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 1651 | 2026-08-13 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-006861 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-06 | faulk-TRANSMIT-000005 | NA | Trade Partner | Updated SD | 2 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 456 | 2026-08-14 |  | As per ANDRE advice and considering the site situation, we processed these documents. However, we noticed that the attached documents contain several errors. In particular, we cannot process a shop drawing that has been issued with a sample document naming convention. Due to the urgency of the work, we have superseded the documents with the correct document numbers to avoid any complications in the future. Reraised workflow to updates review outcome |  | 2026-08-12 | KPTG-DA-001130 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-08-06 | PROLMC-TRANSMIT-000055 | NA | Trade Partner | Stair Nosing 22kv | 0 | 1 | 0 | NA | APPROVED | 2026-08-06 | WF-006616 | NA | 2026-08-20 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-020805 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2026-01-12 | ccair-TRANSMIT-000133 | NA | Trade Partner | AIR SCHEMATIC-RA-IFA | 2 | 0 | 0 | NA | APPROVED | 2026-01-16 | N/A | 569 | 2026-01-23 |  |  | 2026-01-27 | 2026-01-27 | KPTG-TRANSMIT-002545 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-06 | EAEGROUP-TRANSMIT-000007 | NA | Trade Partner | IFA Shop Drawings – Mechanical Corridor 1600A Busduct Runs | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Title and Drawing status do not match with title Bloc:KPTG-TRANSMIT-001568 |  | 2026-08-06 | KPTG-TRANSMIT-001568 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-06 | DLTS-TRANSMIT-000078 | NA | Trade Partner | S9-HV Room2-RE-IFA Issue | 109 | 0 | 0 | NA | APPROVED | 2026-08-06 | WF-001422 | NA | 2026-08-17 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-006887 | Closed | 109 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-06 | Eneraque-TRANSMIT-000057 | NA | Trade Partner | Pressure Gauge Product Datasheet - For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-08-06 | WF-001423 | NA | 2026-08-18 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-006603 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-06 | EAEGROUP-TRANSMIT-000008 | NA | Trade Partner | IFA Shop Drawings – Loadbank and Bypass Busduct Runs | 2 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 458 | 2026-08-14 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-001892 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-06 | WAM-TRANSMIT-000841 | NA | Consultant | Bathroom Type Drawings Update | 9 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1093 | 2026-08-10 |  | Drawing status difference - corrected trn 844 | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-003540 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-06 | SMEPS-TRANSMIT-000371 | NA | Trade Partner | SME IFC DOCUMENTATION | 1 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 4067 | 2026-08-15 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-06 | SMEPS-TRANSMIT-000069 | NA | Trade Partner | Fwd: Shop Drawing: Electrical FC-1 (submission 2) | 4 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 458 | 2026-08-21 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-001853 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-06 | KALLIBRE-TRANSMIT-000002 | NA | Trade Partner | FOA-2 - Door Frames | 27 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 463 | 2026-08-12 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-001675 | Closed | 27 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-06 | Baigents-TRANSMIT-000093 | NA | Trade Partner | Site Storage - Screen Support Columns - Revised Paing System - IFC | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing title is incorrect. Drawing status inside the drawing and in Aconex seem different |  | 2026-08-06 | KPTG-TRANSMIT-001592 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-06 | SMEPS-TRANSMIT-000093 | NA | Trade Partner | Stage 9 - 11 Jemena Easement Plan & Sections | 2 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 1552 | 2026-08-13 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-007291 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-20 | KPTG-IntCorr-004034 | NA | Trade Partner | Crafted Stainless Additional Sample/Tech data | 0 | 6 | 0 | NA | APPROVED | 2026-01-20 | WF-000734 |  | 2026-01-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-06 | SES AU-TRANSMIT-000098 | NA | Trade Partner | HAC Prototype Report-Cameras-IFA | 0 | 1 | 0 | NA | APPROVED | 2026-08-06 | WF-000438 | NA | 2026-08-12 |  |  | 2026-08-17 | 2026-08-17 | KPTG-TRANSMIT-001173 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-06 | PMT Sec-TRANSMIT-000047 | SPARK-CRFI-KPG-000631 | Trade Partner | Re: Resubmit Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 403 | 2026-08-13 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-001626 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-06 | ZLH P/L-SUBRFI-000005 | NA | Trade Partner | Verification of Details | 6 | 0 | 0 | NA | APPROVED | 2026-08-06 | WF - 001112 | NA | 2026-08-13 |  | NA | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-003234 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-06 | Entire M-TRANSMIT-000083 | NA | Trade Partner | Mechanical Penetration drawings IFC - Updated | 4 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 466 | 2026-08-14 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-001739 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-06 | Leemark-TRANSMIT-000066 | SPARK-CRFI-KPG-000608 | Trade Partner | MCC – Overall Fire Detection Schematic – IFC | 1 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 404 | 2026-08-13 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-001639 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-06 | 4DW-TRANSMIT-000076 | NA | Consultant | Block 1 - PW104 & PW105 Precast walls issued for Coordination. | 5 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 520 | 2026-08-14 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-000986 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-06 | EAEGROUP-TRANSMIT-000009 | NA | Trade Partner | FA Shop Drawings – Over-Rack Busduct Runs | 4 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 471 | 2026-08-12 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-001830 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-06 | SMEPS-TRANSMIT-000070 | NA | Trade Partner | shop Drawings: Electrical FC-1 (submission 2) | 1 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 472 | 2026-08-12 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-001888 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-06 | VIA Arch-TRANSMIT-000222 | NA | Consultant | M2 S9 - WINDOW DETAILS - SHEET 3 REVISION - IFBP | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-08-06 | KPTG-TRANSMIT-006510 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-16 | KPTG-TRANSMIT-005679 | NA | Trade Partner | VIA Review of Elec Layout Drawings | 18 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 1449 | 2026-08-06 |  |  | 2026-08-06 | 2026-08-06 | KPTG-SADV-007352 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-20 | ECBS-TRANSMIT-000058 | NA | Trade Partner | Resubmssion of the correct data sheet for WL04 | 0 | 1 | 0 | NA | APPROVED | 2026-01-20 | WF-000737 |  | 2026-01-23 |  | As per the Direction from project Coordinator, New updated Sample is required to review. Hence, we void the workflow:WF-000737 |  | 2026-01-20 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-16 | KPTG-TRANSMIT-005679 | NA | Trade Partner | VIA Review of Elec Layout Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-07-16 | NA | 1450 | 2026-08-06 |  |  | 2026-08-06 | 2026-08-06 | KPTG-SADV-007352 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-06 | D&E-TRANSMIT-000978 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - UPPER ROOF & ROOF - CHW PIPE LAYOUT - ZONE 10 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For Distribution |  | 2026-08-06 | KPTG-TRANSMIT-020419 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-06 | ZLH P/L-TRANSMIT-000020 | NA | Trade Partner | Re: Proposed Steel Sheet - ZLH | 0 | 1 | 0 | NA | APPROVED | 2026-08-06 | WF-000417 | NA | 2026-08-17 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-002257 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-06 | LNCPPL-TRANSMIT-000026 | NA | Trade Partner | Electrical Shop Drawings - Site Inground | 2 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 474 | 2026-08-14 |  | AS PER ANDRE INSTRUCTION FOA REJECTED IFC PROCESSED as per requested by chrid doh workflow is terminated |  | 2026-08-07 | KPTG-TRANSMIT-001642 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-06 | SMEPS-TRANSMIT-000068 | NA | Trade Partner | Shop Drawings- Electrical FC-1 (Submission 1) | 20 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 475 | 2026-08-14 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-002292 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-06 | NXT-WTRAN-000125 | NA | Client | Final (WF-000135) FIE FOR APPROVAL: DCNEXUS Switchrooms Tech Data | 0 | 6 | 0 | KPTG-IntCorr-000454 | APPROVED |  | NA | NA |  |  | superseded NXT-WTRAN-000125 with NXT-WTRAN-000126 |  | 2026-08-07 | KPTG-TRANSMIT-000865 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-06 | NXT-TRANSMIT-000469 | NA | Client | FIE Review - Siemens - PSUBs - FIE Elec | 1 | 0 | 0 | KPTG-IntCorr-000457 | APPROVED | 2026-08-10 | WF-000185 | NA | 2026-08-21 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-06 | NXT-TRANSMIT-000470 | NA | Client | FIE Review - Arjay - Switchroom - FIE Electrical | 4 | 0 | 0 | KPTG-IntCorr-000458 | APPROVED | 2026-08-10 | WF-000186 | NA | 2026-08-21 |  |  | 2026-08-27 | 2026-08-28 | KPTG-TRANSMIT-001180 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-06 | NXT-TRANSMIT-000472 | NA | Client | FIE Review - Arjay - Switchroom Fire Detection - FIE Fire | 1 | 0 | 0 | KPTG-IntCorr-000460 | APPROVED | 2026-08-10 | WF-000188 | NA | 2026-08-21 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-06 | Carr-TRANSMIT-000081 | NA | Consultant | Town Planning - Schedule of Changes | 0 | 1 | 0 | NA | APPROVED | 2026-08-06 | NA | 330 | 2026-08-13 |  | Received updated drawings from ,Carr-TRANSMIT-000082 |  | 2026-08-07 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-20 | ECBS-TRANSMIT-000059 | NA | Trade Partner | Revise of Technical Data (TEC-044) | 0 | 1 | 0 | NA | APPROVED | 2026-01-20 | WF-000735 | NA | 2026-01-23 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-002648 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-06 | D&E-TRANSMIT-000975 | NA | Trade Partner | ISSUED FOR CONSTRUCTION HAC PIPEWORK LAYOUTS & TYPICAL SFN LAYOUT | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Document submitted directly as IFC without prior IFA approval. |  | 2026-08-06 | KPTG-DA-008025 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-06 | D&E-TRANSMIT-000976 | NA | Trade Partner | SFN Discharge Register - Issued for Review | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | please resubmit the updated version in PDF format. |  | 2026-08-06 | KPTG-DA-008023 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-06 | D&E-TRANSMIT-000979 | NA | Trade Partner | Mechanical SFN Discharge Register - Issued For Information | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | please resubmit the updated version in PDF format. |  | 2026-08-06 | KPTG-DA-008024 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-29 | D&E-TRANSMIT-000878 | NA | Trade Partner | Mechanical SFN Discharge Register - Issued for Review | 0 | 1 | 0 | NA | APPROVED | 2026-07-02 | WF-006236 | NA | 2026-08-12 |  |  | 2026-08-06 | 2026-08-06 | KPTG-TRANSMIT-020407 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-06 | Schindle-TRANSMIT-000032 | NA | Trade Partner | VT shop drawings - Lifts C1 & C2 - FC5 | 8 | 0 | 0 | NA | APPROVED | 2026-08-06 | WF-006619 | NA | 2026-08-11 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-06 | DLTS-TRANSMIT-000081 | NA | Trade Partner | S10-Eave Gutter Frames-IFA Issue | 27 | 0 | 0 | NA | APPROVED | 2026-08-06 | WF-001426 | NA | 2026-08-17 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-007056 | Closed | 27 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-06 | RDSBIM-TRANSMIT-000092 | NA | Trade Partner | GREYSTAR LEVEL 05 CONCRETE PROFILE PLAN | 6 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 1660 | 2026-08-13 |  | Review Terminated as requested by RDS to update the drawings. |  | 2026-08-18 | NA | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-06 | POTTSENG-TRANSMIT-000061 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - PENETRATION - LEVEL 01 - ZONE 3 LAYOUT | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to incorrect revision. DRAFT-011141 |  | 2026-08-06 | DRAFT-011141 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-06 | Auspan-TRANSMIT-000580 | NA | Trade Partner | Re: Zone 3 RFi 70. Resubmit shop drawings level 5 for approval | 2 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 1662 | 2026-08-13 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-003157 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-06 | Auspan-TRANSMIT-000581 | NA | Trade Partner | 352 - Level 2 Dowel Layout | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC-Update Register and Transmit -KPTG-TRANSMIT-003129 |  | 2026-08-06 | KPTG-TRANSMIT-003129 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-20 | D&E-TRANSMIT-000084 |  | Trade Partner | VOLUME & SMOKE DAMPERS | 0 | 1 | 0 | NA | APPROVED | 2026-01-20 | WF-000125 |  | 2026-01-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-06 | POTTSENG-TRANSMIT-000062 | NA | Trade Partner | : GMAC: HYDRAULIC SERVICES - PENETRATION - LEVEL 02 - ZONE 5 LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 1665 | 2026-08-13 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-003324 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-06 | Auspan-TRANSMIT-000582 | NA | Trade Partner | Update IFCed precast shop drawings. level 3 | 2 | 0 | 0 | KPTG-IntCorr-001205 | APPROVED |  | NA | NA |  |  | IFC - Oliver to advise - KPTG-IntCorr-001205 KPTG-SADV-004081 - OK to IFC |  | 2026-08-10 | KPTG-TRANSMIT-003145 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-06 | Auspan-TRANSMIT-000584 | NA | Trade Partner | : Re: Update IFCed shop drawings. Level 3. | 1 | 0 | 0 | KPTG-IntCorr-001208 | APPROVED |  | NA | NA |  |  | IFC - Oliver to advise - KPTG-IntCorr-001208 OK TO IFC-KPTG-TRANSMIT-003189 |  | 2026-08-12 | KPTG-TRANSMIT-003189 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-06 | RDSBIM-TRANSMIT-000094: | NA | Trade Partner | 671 CHAPEL STREET CORE WALL GROUND TO ROOF | 9 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 735 | 2026-08-13 |  | Review terminated as requested by RDS and as advised by Kian. |  | 2026-08-17 | NA | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-06 | KPTG-TRANSMIT-001511 | NA | Trade Partner | : Fwd: Aloha Penetrations | 1 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 731 | 2026-08-13 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-06 | Jangho-TRANSMIT-000105 | NA | Trade Partner | L1-L2 CALCULATION REPORT Rev01 | 0 | 2 | 0 | NA | APPROVED | 2026-08-06 | WF-000667 | NA | 2026-08-13 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-06 | crossfir-TRANSMIT-000031 | NA | Trade Partner | Wet Fire - Level 02 to 10, IFA | 5 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 738 | 2026-08-13 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-001724 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-06 | GPSElec-TRANSMIT-000020 | NA | Trade Partner | MSB-KX-xx - IFC | 534 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Drawings, Completed QA process, Updated register and ACC folders and distributed to Project Team. |  | 2026-08-06 | KPTG-TRANSMIT-006516 | Closed | 534 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-06 | WilsonPD-TRANSMIT-000141 | NA | Trade Partner | Vinyl Floor Wastes for approval | 0 | 1 | 0 | NA | APPROVED | 2026-08-06 | WF-001424 | NA | 2026-08-11 |  | Resubmitted for VIA review as advised by Project coordinator | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-006705 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-06 | SMEPS-TRANSMIT-000092 | NA | Trade Partner | GF S11 GF containment Drwaing | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Need to revise KPTG-SADV-007323 |  | 2026-08-06 | KPTG-SADV-007323 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-20 | Baigents-TRANSMIT-000063 | SPARK-CRFI-KPG-000222 | Trade Partner | MCC - MCC-P112 - Revised lift vent | 1 | 0 | 0 | NA | APPROVED | 2026-01-20 | WF-000126 | 98 | 2026-01-27 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-000462 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-06 | DLTS-TRANSMIT-000080 | NA | Trade Partner | S9-HV Room 2-IFA Issue | 3 | 0 | 0 | NA | APPROVED | 2026-08-06 | WF-001422 | NA | 2026-08-14 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-006895 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-06 | CDL-TRANSMIT-000050 | NA | Trade Partner | Concrete Mix Design | 0 | 1 | 0 | KPTG-IntCorr-008654 | APPROVED | [5 empty] | Kapitol Advice Awaits: Workflow matrix is yet to finalise it:KPTG-IntCorr-008654 |  | 2026-08-06 |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-08-07 | WPD-TRANSMIT-000103 | NA | Trade Partner | Hydraulic Services - B08 - Updated As Built | 1 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 433 | 2026-08-16 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-07 | INTRFRM-TRANSMIT-000117 | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 5) | 0 | 1 | 0 | NA | APPROVED | 2026-08-07 | WF-000429 | NA | 2026-08-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-06 | NXES-TRANSMIT-000068 | NA | Trade Partner | Level 2-10 General & Emergency Lighting Calculation | 7 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 738 | 2026-08-08 |  |  | 2026-08-28 | 2026-08-28 | KPTG-SADV-005455 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-06 | NXES-TRANSMIT-000069 | NA | Trade Partner | Re: Lighting Protection Layout | 2 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 732 | 2026-08-11 |  |  | 2026-08-28 | 2026-08-28 | KPTG-SADV-005454 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-07 | VERTIV-TRANSMIT-000058 | NA | Trade Partner | NEXT DC GE 01 _ MATERIAL SUBMISSION _ BATTERY DISCONNECT ENCLOSURE (FOA-2) | 0 | 1 | 0 | NA | APPROVED | 2026-08-07 | WF-000430 | NA | 2026-08-20 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-001849 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-07 | Auspan-TRANSMIT-000588 | NA | Trade Partner | Precast shop drawings for construction. Levels 5, 6 | 35 | 0 | 0 | KPTG-IntCorr-001209 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001209 24 Drawing are OK TO IFC -KPTG-TRANSMIT-003151 11 are rejected as advised by Kapitol PC -KPTG-SADV-004075 |  | 2026-08-10 | KPTG-TRANSMIT-003151 | Closed | 35 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-07 | VERTIV-TRANSMIT-000059 | NA | Trade Partner | NEXT DC GE01 _ MATERIAL SUBMISSION _ PTU DB (FOA-1) | 0 | 1 | 0 | NA | APPROVED | 2026-08-07 | WF-000431 | NA | 2026-08-20 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-001874 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | IVS-TRANSMIT-000315 | NA | Consultant | Stage 4 - Drawing 0535 Acoustic Screen Precast Elevations (Construction Issue) | 1 | 0 | 0 | NA | APPROVED | 2026-01-20 |  | 1826 | 2026-01-24 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-012090 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-06 | Jangho-TRANSMIT-000147 - client review | NA | Trade Partner | Facade Sample | 0 | 1 | 0 | NA | APPROVED | 2026-08-06 | WF-001096 | NA | 2026-08-14 |  |  | 2026-08-13 | 2026-08-14 | KPTG-TRANSMIT-003423 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-06 | Jangho-TRANSMIT-000148 - client review | NA | Trade Partner | Facade Sample | 0 | 1 | 0 | NA | APPROVED | 2026-08-06 | WF-001097 | NA | 2026-08-14 |  |  | 2026-08-13 | 2026-08-14 | KPTG-TRANSMIT-003425 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-06 | Jangho-TRANSMIT-000149 - client review | NA | Trade Partner | Facade Sample | 0 | 1 | 0 | NA | APPROVED | 2026-08-06 | WF-001098 | NA | 2026-08-14 |  |  | 2026-08-13 | 2026-08-14 | KPTG-TRANSMIT-003427 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-06 | Jangho-TRANSMIT-000150 - client review | NA | Trade Partner | Facade Sample | 0 | 1 | 0 | NA | APPROVED | 2026-08-06 | WF-001099 | NA | 2026-08-14 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-06 | Jangho-TRANSMIT-000211 - client review | NA | Trade Partner | Facade Sample | 0 | 1 | 0 | NA | APPROVED | 2026-08-06 | WF-001100 | NA | 2026-08-14 |  |  | 2026-08-13 | 2026-08-14 | KPTG-TRANSMIT-003429 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-06 | Jangho-TRANSMIT-000212 - client review | NA | Trade Partner | Facade Sample | 0 | 1 | 0 | NA | APPROVED | 2026-08-06 | WF-001101 | NA | 2026-08-14 |  |  | 2026-08-13 | 2026-08-14 | KPTG-TRANSMIT-003431 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-06 | Jangho-TRANSMIT-000165 - client review | NA | Trade Partner | Facade Sample | 0 | 1 | 0 | NA | APPROVED | 2026-08-06 | WF-001102 | NA | 2026-08-14 |  |  | 2026-08-13 | 2026-08-14 | KPTG-TRANSMIT-003433 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-07 | VERTIV-TRANSMIT-000060 | NA | Trade Partner | NEXT DC GE01 _ MATERIAL SUBMISSION _ BUS DUCUT SIEMENS (FOA-1) | 0 | 1 | 0 | NA | APPROVED | 2026-08-07 | WF-000432 | NA | 2026-08-20 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-001945 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-07 | D&E-TRANSMIT-000980 | NA | Trade Partner | Mechanical SFN Discharge Register - Issued for Information | 0 | 1 | 0 | NA | APPROVED | 2026-08-07 | WF-006621 | NA | 2026-09-09 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-06 | Jangho-TRANSMIT-000209 - client review | NA | Trade Partner | Facade Sample | 0 | 1 | 0 | NA | APPROVED | 2026-08-06 | WF-001103 | NA | 2026-08-14 |  |  | 2026-08-13 | 2026-08-14 | KPTG-TRANSMIT-003435 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | IVS-TRANSMIT-000314 | NA | Consultant | Stage 4 - Chemical Store & Fire Room (Certification Issue) | 3 | 0 | 0 | NA | APPROVED | 2026-01-20 |  | 1828 | 2026-01-24 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-012082 | Closed | 3 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-06 | Jangho-TRANSMIT-000308 | NA | Trade Partner | District Living Docklands-Curtain Wall draft test report | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected QA Error in doc number |  | 2026-08-06 | KPTG-TRANSMIT-003310 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-06 | INGEN3D-TRANSMIT-000234 | NA | Trade Partner | Level 14-16 - IFC - Re-issue with 'Title' change | 30 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | register updated - distributed |  | 2026-08-06 | KPTG-TRANSMIT-003002 | Closed | 30 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-06 | INGEN3D-TRANSMIT-000235 | NA | Trade Partner | Level 22 - Precast Columns & Cast-in Dowels - IFC (05-08-2026) | 21 | 0 | 0 | NA | APPROVED | 2026-08-06 | WF-001108 | NA | 2026-08-13 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003517 | Closed | 21 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-06 | INGEN3D-TRANSMIT-000239 | NA | Trade Partner | Level 22 - PC0703 - Revised IFC | 1 | 0 | 0 | NA | APPROVED | 2026-08-06 | WF-001108 | NA | 2026-08-13 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003517 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-06 | INGEN3D-TRANSMIT-000236 | NA | Trade Partner | Level 22 - CD0159 - New IFA | 1 | 0 | 0 | NA | APPROVED | 2026-08-06 | WF-001111 | NA | 2026-08-18 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003519 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-07 | ADP-TRANSMIT-000389 | NA | Consultant | ADP MEL4780 - Updated FP drawing and Reg 126 | 2 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 4076 | 2026-08-11 |  | Terminated as instructed by ellie |  | 2026-08-07 | KPTG-TRANSMIT-020430 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-07 | ELLISAIR-TRANSMIT-000156 | NA | Trade Partner | Stage 9 Ground floor & Level 1 SFN Pipework drawings issued for Approval. | 2 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 1654 | 2026-08-14 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-007172 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-07 | Nilsen3-TRANSMIT-000250 | NA | Trade Partner | Nilsen Generator Control Cabling sample IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-07 | KPTG-TRANSMIT-020425 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-07 | Auspan-TRANSMIT-000589 | NA | Trade Partner | Precast shop drawings for approval. Level 5 | 5 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 1670 | 2026-08-14 |  | 4 drawings closed and 1 drawing review terminated and superseded | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-003239 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-07 | ccair-TRANSMIT-000139 | NA | Trade Partner | 20260807_Updated L3 & L9 shop drawings IFC | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - only for distribution. |  | 2026-08-07 | KPTG-TRANSMIT-003230 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-20 | vdmcons-TRANSMIT-000016 | NA | Trade Partner | ME25 1144: D11 M3 Stage 3 GIS Building - Shop Drawings & 3D IFC Model - M3 Stage 3 Switchroom - Re-IFF - 2026-01-20 | 33 | 0 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. - KPTG-TRANSMIT-011654 |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-07 | Auspan-TRANSMIT-000585 | NA | Trade Partner | Re: level 2 - level 7 - precast penetration. Update IFCed precast shop drawings | 6 | 0 | 0 | KPTG-IntCorr-001211 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001211 KPTG-SADV-004079 - OK to IFC |  | 2026-08-10 | KPTG-TRANSMIT-003147 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-07 | VERTIV-TRANSMIT-000061 | NA | Trade Partner | NEXT DC GE01 _ MATERIAL SUBMISSION _ VENTILATION CONTROL PANEL (FOA-1) | 0 | 1 | 0 | NA | APPROVED | 2026-08-07 | WF-000433 | NA | 2026-08-20 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-002028 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-07 | PSGANZ-TRANSMIT-000013 | NA | Trade Partner | Commissioning Management Plan - For approval | 0 | 1 | 0 | NA | APPROVED | 2026-08-07 | WF-000434 | NA | 2026-08-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-07 | Auspan-TRANSMIT-000586 | NA | Trade Partner | Precast shop drawings for construction. Level 3 | 3 | 0 | 0 | KPTG-IntCorr-001212 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001212 OK TO IFC- KPTG-TRANSMIT-003231 |  | 2026-08-13 | KPTG-TRANSMIT-003231 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-07 | Civilex-TRANSMIT-000332 | NA | Trade Partner | Stage 2 - sample submission - Aftek Curecon BE Curing | 0 | 1 | 0 | NA | APPROVED | 2026-08-07 | WF-006626 | NA | 2026-08-13 |  | Holded due to missing of Arup stamp, however the same was resubmitted by Originator | 2026-08-18 | 2026-08-31 | OveArup-WTRAN-001858 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-07 | Auspan-TRANSMIT-000587 | NA | Trade Partner | Precast shop drawings for construction. Level 4 | 5 | 0 | 0 | KPTG-IntCorr-001213 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001213 4 OK TO IFC-KPTG-TRANSMIT-003191; 1 Rejected as advised by Kapitol PC. KPTG-SADV-004148 |  | 2026-08-12 | KPTG-TRANSMIT-003191 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-07 | WilsonPD-TRANSMIT-000011 | NA | Trade Partner | (WF-000240) SHOP DRAWING ¦ CONSULTANT REVIEW ¦ HYD ¦ WilsonPD ¦ IFA ¦¦-WilsonPD-TRANSMIT-000008- Re: Hydraulic shop drawing issued for Construction | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Revision of document is incorrect:KPTG-IntCorr-000750 |  | 2026-08-07 | KPTG-IntCorr-000750 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-07 | Eneraque-IntCorr-000007 | NA | Trade Partner | ENE - TYPICAL PIPE SUPPORTS SHEET 3 | 1 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 1656 | 2026-08-14 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-007197 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-07 | JCBa-TRANSMIT-000163 | NA | Consultant | Updated Architectural Documentation - Waterproofing Plans & Facade Assembly | 10 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 1676 | 2026-08-11 |  |  | 2026-08-25 | 2026-08-25 |  | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-07 | ADP-TRANSMIT-000392 | NA | Consultant | ADP MEL4780 - S4 - Electrical Drawig - BACOP & BOB SCHEMATIC | 1 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 4078 | 2026-08-12 |  |  |  | 2026-08-13 | KPTG-TRANSMIT-020537 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-03 | NXT-TRANSMIT-001112 / VERTIV-TRANSMIT-000036 | NA | Trade Partner | NEXTDC M3-ST-4 FWU documents submission | 4 | 0 | 0 | NA | APPROVED | 2025-12-03 | WF-003478 | NA | 2025-12-17 |  |  |  | 2025-12-15 | KPTG-TRANSMIT-010910 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-20 | D&E-TRANSMIT-000303 | NA | Trade Partner | DRAWING - M3-MEC-DEA-DST-A-0100-WALKWAY GA (FOA3) | 0 | 1 | 0 | NA | APPROVED | 2026-01-20 | WF-000880 | NA | 2026-01-27 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-002665 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-07 | STRBCK-TRANSMIT-000005 | NA | Trade Partner | Thermal Sand material conformance | 0 | 2 | 0 | NA | REJECTED | [7 empty] | 2026-08-07 | KPTG-TRANSMIT-000863 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-07 | Auspan-TRANSMIT-000112 | NA | Trade Partner | Precast shop drawings for approval. Coen facade panels. | 61 | 0 | 0 | NA | APPROVED | 2026-08-07 | WF-001093 | NA | 2026-08-17 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-003341 | Closed | 61 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-07 | DLTS-TRANSMIT-000082 | NA | Trade Partner | S10-Cooling Tower Lower-IFC Issue | 50 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Drawings, updated register and distributed |  | 2026-08-07 | KPTG-TRANSMIT-006540 | Closed | 50 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-07 | PMT Sec-TRANSMIT-000049 | NA | Trade Partner | Re: IFC Drawings | 17 | 0 | 0 | KPTG-IntCorr-003967 | APPROVED | [5 empty] | Previous IFA was Revise and Resubmit |  | 2026-08-11 | KPTG-TRANSMIT-001610 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-07 | Entire M-TRANSMIT-000055 | NA | Trade Partner | Mechanical AS-BUILT drawings | 4 | 0 | 0 | NA | APPROVED | 2026-08-07 | WF-000563 | NA | 2026-08-14 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-07 | Jangho-TRANSMIT-000262,309 | NA | Trade Partner | Podium Level 1~5 Cast in Channel Shop Drawing_PDF_Rev A & B_For Construction | 20 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 1085 | 2026-08-17 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-003560 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-07 | SMEPS-TRANSMIT-000072 | NA | Trade Partner | Tech Data - Gripple Hangers | 0 | 1 | 0 | NA | APPROVED | 2026-08-07 | WF-000435 | 0 | 2026-08-14 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001999 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-07 | BIMF-TRANSMIT-000020 | NA | Trade Partner | Level 2 Hydraulic Setout, Re-transmit Rev A | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Incomplete Title Block |  | 2026-08-07 | KPTG-TRANSMIT-003320 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-07 | NXT-TRANSMIT-000476 | NA | Client | Barkers Info | 25 | 2 | 0 | KPTG-IntCorr-000461 | APPROVED | 2026-08-11 | NA | 646 | 2026-08-19 |  | 25 Drawings submitted. 2 Documents on seperate workflow | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-001085 | Closed | 25 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-07 | Entire M-TRANSMIT-000084 | NA | Trade Partner | VRF Airconditioning - FOA-5 | 0 | 1 | 0 | NA | APPROVED | 2026-08-07 | WF-000436 | NA | 2026-08-20 |  |  | 2026-08-17 | 2026-08-17 | KPTG-TRANSMIT-001942 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-01-20 | KEECEPRO-TRANSMIT-000013 | NA | Trade Partner | Inground Shop Drawings - Amended - ELC | 2 | 1 | 0 | NA | APPROVED | 2026-01-20 |  | 272 | 2026-01-26 |  |  |  | 2026-01-22 | DRAFT-008399 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-07 | Entire M-TRANSMIT-000085 | NA | Trade Partner | Return Design Brief - FOA-4 | 0 | 1 | 0 | NA | APPROVED | 2026-08-07 | WF-000437 | NA | 2026-08-20 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-002019 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-07 | ADP-TRANSMIT-000391 | NA | Consultant | ADP MEL4780 - Updated Fire Protection Drawings | 6 | 0 | 0 | NA | APPROVED | 2026-08-07 | na | 4080 | 2026-08-11 |  | terminated as instructed by ellie |  | 2026-08-07 | KPTG-TRANSMIT-020446 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-07 | D&E-TRANSMIT-000981 | NA | Trade Partner | Leak Detection Functional Description - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-08-07 | WF-006628 | NA | 2026-08-12 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-021125 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-07 | PCForm-TRANSMIT-000286 | NA | Trade Partner | Aitkeen Freeman - GranoGrip | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The document number has been already submitted |  | 2026-08-07 | KPTG-TRANSMIT-003231 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-07 | ELLISAIR-TRANSMIT-000157 | NA | Trade Partner | Stage 11 Level 2 Duct Layout and Sections drawings issued for Approval. | 2 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 1658 | 2026-08-14 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-007176 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-07 | L.E.S.-TRANSMIT-000046 | NA | Trade Partner | Electrical Cable Technical Data Submission for Approval | 0 | 6 | 0 | NA | APPROVED | 2026-08-07 | WF-001113 | NA | 2026-08-12 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003530 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-07 | D&E-TRANSMIT-000984 | NA | Trade Partner | Stage 4 - Fire matrix IFC-5 Transmittal 0 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-07 | KPTG-TRANSMIT-020439 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-07 | D&E-TRANSMIT-000983 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - SECURITY GRILLES | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | DISTRIBUTION |  | 2026-08-07 | KPTG-TRANSMIT-020440 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-07 | MAYFLD-TRANSMIT-000473 | NA | Trade Partner | 110693-000233 - CENTER OF MASS DRAWINGS - ISSUED FOR CONSTRUCTION | 12 | 0 | 0 | NA | REJECTED | [5 empty] | The document status appears to be mismatched between Aconex and the drawing. Please review and update the status to ensure both records are consistent.,The revision date shown in the revision history within the document does not match the revision date in Aconex. Please verify and update the dates to ensure consistency. |  | 2026-08-07 | KPTG-SADV-007209 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-07 | Entire M-TRANSMIT-000086 | NA | Trade Partner | BMS Points List - FOA-2 | 0 | 1 | 0 | NA | APPROVED | 2026-08-07 | WF-000438 | NA | 2026-08-14 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-002237 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | TTW-TRANSMIT-000149 | NA | Consultant | Fwd: S4 Facade Structural Reg126 Certification | 0 | 1 | 0 | NA | APPROVED | [5 empty] | KPTG-TRANSMIT-011650 The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | VIA Arch-TRANSMIT-000211 | NA | Consultant | M2 S9 L1 Data Hall Penetration Revisions | 1 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 1602 | 2026-08-07 |  |  | 2026-08-07 | 2026-08-07 | KPTG-DA-004141 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-07 | Entire M-TRANSMIT-000087 | NA | Trade Partner | Pipe Insulation - FOA-1 | 0 | 1 | 0 | NA | APPROVED | 2026-08-07 | WF-000439 | NA | 2026-08-14 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-002253 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-07 | LNCPPL-TRANSMIT-000027 | NA | Trade Partner | TELECOMMUNICATION SERVICES SITE PLAN - IN GROUND - FC-2 | 1 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 477 | 2026-08-14 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-001682 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-07 | WilsonPD-TRANSMIT-000164 | NA | Trade Partner | Stage 9 Level 1 Waste and Water IFA | 2 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 1660 | 2026-08-12 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-006629 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-07 | WilsonPD-TRANSMIT-000163 | NA | Trade Partner | Stage 10 & 11 Level 1 Waste and Water IFA | 3 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 1662 | 2026-08-14 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-006920 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-07 | WilsonPD-TRANSMIT-000165 | NA | Trade Partner | Stage 10 & 11 Level 1 Waste and Water IFA | 1 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 1662 | 2026-08-14 |  |  | 2026-08-14 | 2026-08-14 | 1 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-07 | RDSBIM-TRANSMIT-000095 | NA | Trade Partner | 671 CHP LEVEL 01 CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 740 | 2026-08-07 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-001529 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-07 | VIA Arch-TRANSMIT-000213 | NA | Consultant | S9 L1 Concrete Profile | 1 | 0 | 0 | NA | APPROVED | 2026-08-05 | NA | 1636 | 2026-08-07 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-006557 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-07 | Carr-TRANSMIT-000080,82 | NA | Consultant | Town Planning Issue for Secondary Consent | 26 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 332 | 2026-08-13 |  | Voided- Updated drawings available |  | 2026-08-14 | KPTG-CONTADV-000264 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-07 | SMEPS-TRANSMIT-000073 | NA | Trade Partner | Techdata: copper cabling system (FOA-2) | 0 | 1 | 0 | NA | APPROVED | 2026-08-07 | WF-000441 | NA | 2026-08-14 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002173 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-21 | D&E-TRANSMIT-000343 / D&E-TRANSMIT-000344 | NA | Trade Partner | Fwd: ISSUED FOR APPROVAL - STAGE 4 - Mechanical Services - Ground - Plinth & Equipment Layouts (Zones 1-4) | 4 | 0 | 0 | NA | APPROVED |  |  | 1852 | 2026-01-29 |  | KPTG-TRANSMIT-011659 The register has been updated. If any further action is required, the coordinator will inform. |  | 2026-02-11 | KPTG-TRANSMIT-012722 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-07 | ArcadiaL-TRANSMIT-000003 | NA | Consultant | Landscape Architectural - IFC Updates to Easement | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - Difference in drawing status -DRAFT-011181 |  | 2026-08-07 | DRAFT-011181 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-07 | Auspan-TRANSMIT-000590: | NA | Trade Partner | Update panel 3P4012 | 1 | 0 | 0 | KPTG-IntCorr-001214 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001214 |  | 2026-08-10 | KPTG-TRANSMIT-003170 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-07 | HDRAus-TRANSMIT-000540 | NA | Consultant | M3 Stage 4 - Document upload | 7 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 4083 | 2026-08-11 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-020738 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-07 | ccair-TRANSMIT-000043 | NA | Trade Partner | Mechanical Services L4 ductwork and pipework layout IFA [A] | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected; Wrong attachment-DRAFT-011534 |  | 2026-08-07 | DRAFT-011534 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-07 | D&E-TRANSMIT-000985 | NA | Trade Partner | Fwd: MCC Schedule Rev I | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-07 | KPTG-TRANSMIT-020447 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-07 | ADP-TRANSMIT-000393 | NA | Consultant | Fwd: ADP MEL4780 - Fire Protection Reg 126 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-08-07 | KPTG-TRANSMIT-020449 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-07 | Highbu-TRANSMIT-000061 | NA | Trade Partner | Revised B1 Water Layout | 1 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 734 | 2026-08-14 |  |  | 2026-08-28 | 2026-08-28 | KPTG-DA-002958 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-07 | Ardon-TRANSMIT-000020 | NA | Trade Partner | Switchroom Frames IFC | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, updated register and distributed |  | 2026-08-07 | KPTG-TRANSMIT-006575 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-07 | Ardon-TRANSMIT-000021 | NA | Trade Partner | Ground Floor Frames IFC | 24 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, updated register and distributed |  | 2026-08-07 | KPTG-TRANSMIT-006579 | Closed | 24 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-03 | INDS-TRANSMIT-000049 | NA | Trade Partner | Wet Fire - Level 9 | 1 | 0 | 0 | KPTG-SADV-005173 | APPROVED | 2026-08-07 | NA | 733 | 2026-08-14 |  | KPTG-SADV-005173 - Request to DWFX file. | 2026-08-28 | 2026-08-28 | KPTG-SADV-005465 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | CRSol-TRANSMIT-000077 | NA | Trade Partner | M3S4 CRS CEILING SHOPDRAWINGS ISSUED FOR APPROVAL REV. B | 10 | 0 | 0 | NA | APPROVED | 2026-01-20 |  | 1830 | 2026-01-29 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-014645 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-07 | KPTG-TRANSMIT-002860 | NA | Trade Partner | Door Frame Drawings For Review | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: No Document Number, title, Revision, Drawing status in the title bloc of drawing:KPTG-SADV-005238 |  | 2026-08-07 | KPTG-SADV-005238 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-07 | VIA Arch-TRANSMIT-000223 | NA | Consultant | Updated Elevations | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-08-07 | KPTG-TRANSMIT-006582 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-07 | KPTG-TRANSMIT-002862 | NA | Trade Partner | Door Frame Drawings For Review | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: No Document Number, title, Revision, Drawing status in the title bloc of drawing:KPTG-SADV-005237 |  | 2026-08-07 | KPTG-SADV-005237 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-07 | NXES-TRANSMIT-000070 | NA | Trade Partner | Nexus: Comms, MATV and PayTV - Tech Data Sheets for IFA | 0 | 17 | 0 | NA | APPROVED | 2026-08-07 | WF-000894 | NA | 2026-08-14 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-07 | PCForm-TRANSMIT-000287 | NA | Trade Partner | PCForm-Tec-030 | 0 | 1 | 0 | NA | APPROVED | 2026-08-07 | WF-001116 | NA | 2026-08-13 |  | NA | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-003233 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-07 | IVS-TRANSMIT-000376 | NA | Consultant | Stage 4 - Roof Level - Zone C1 - Part Plan -Admin (Certification Issue) | 1 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 4085 | 2026-08-13 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-021087 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-07 | VERTIV-TRANSMIT-000062 | NA | Trade Partner | NEXT DC GE01_ MATERIAL SUBMISSION _ FIRE RATED GYPSUM BOARD, FIRE RATED DOOR, POWER CABLES (FOA-2) | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  | Superseded by VERTIV-TRANSMIT-000063 as advised by Vertiv. |  | 2026-08-07 | KPTG-TRANSMIT-001643 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-07 | VERTIV-TRANSMIT-000063 | NA | Trade Partner | NEXT DC GE01 _ MATERIAL SUBMISSION _ FIRE RATED GYPSUM BOARD, FIRE RATED DOOR, POWER CABLES (FOA-2) _ 07/08/2026 | 0 | 1 | 0 | NA | APPROVED | 2026-08-07 | WF-000442 | NA | 2026-08-14 |  | ELC SAMPLE FROM VERTIV-TRANSMIT-000063 | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001978 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-07 | RDSBIM-TRANSMIT-000017 | NA | Trade Partner | GROUND FLOOR¦CPP-BLOCK 1 | 3 | 0 | 0 | KPTG-IntCorr-000456 | APPROVED | 2026-08-13 | NA | 662 | 2026-08-21 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-001142 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-07 | VERTIV-TRANSMIT-000063 | NA | Trade Partner | NEXT DC GE01 _ MATERIAL SUBMISSION _ FIRE RATED GYPSUM BOARD, FIRE RATED DOOR, POWER CABLES | 0 | 2 | 0 | NA | APPROVED | 2026-08-07 | WF-000443 | NA | 2026-08-14 |  | ARC FROM VERTIV-TRANSMIT-000063 |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | SKS Tech-TRANSMIT-000004 | NA | Trade Partner | SKS - Technical Data Submissions | 0 | 6 | 0 | NA | REJECTED | [5 empty] | The Aconex reference number is not aligned with the S4 project - KPTG-TRANSMIT-011660 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-07 | Baigents-TRANSMIT-000030 | NA | Trade Partner | Block 01 - East & West Wall Precast Panels Issued For Construction | 23 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 622 | 2026-08-17 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-000884 | Closed | 23 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-07 | STRBCK-TRANSMIT-000006 | NA | Trade Partner | Thermal Sand tech data sheet | 0 | 2 | 0 | NA | APPROVED | 2026-08-07 | NA | 624 | 2026-08-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-07 | SMEPS-TRANSMIT-000012 | NA | Trade Partner | M3S6 - Electrical Temporary Services Layout | 1 | 0 | 0 | KPTG-IntCorr-000469 | APPROVED | 2026-08-19 | NA | 710 | 2026-08-27 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-07 | NXT-WTRAN-000126 | NA | Client | Final (WF-000135) FIE FOR APPROVAL: DCNEXUS Switchrooms Tech Data | 0 | 7 | 0 | KPTG-IntCorr-000468 | APPROVED | 2026-08-10 | WF-000189 | NA | 2026-08-21 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-07 | fjc-TRANSMIT-000178 | NA | Consultant | Architecturals - Ground Floor Design Changes Issue 1 | 22 | 0 | 0 | KPTG-IntCorr-001307 | REJECTED |  | NA | NA |  |  | Kapitol Advice Awaits:KPTG-IntCorr-001307 KPTG-SADV-005248 - TITTLE,DATE ,REVISION ARE INCORRECT | 2026-08-10 | 2026-08-10 | KPTG-SADV-005248 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-07 | Baigents-TRANSMIT-000011 | NA | Trade Partner | Cupboard Lintels - Issued for Approval | 8 | 0 | 0 | NA | APPROVED | 2026-08-20 | WF-006633 |  | 2026-08-20 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-020852 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-07 | NXT-WTRAN-000127 | NA | Client | FIE FOR APPROVAL: ABB LV Data Sheet, SLD and Schematics | 2 | 1 | 0 | KPTG-IntCorr-000466 | APPROVED | 2026-08-10 | WF-000193 | NA | 2026-08-21 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-07 | NXT-WTRAN-000128 | NA | Client | Final (WF-000066) FOR REVIEW: IT Line Up Switchroom Tech Data 4 | 0 | 8 | 0 | KPTG-IntCorr-000467 | APPROVED | [5 empty] | Already submitted |  | 2026-08-10 | NA | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-07 | NXT-WTRAN-000130 | NA | Client | Final (WF-000142) FIE FOR APPROVAL: DCNEXUS Switchrooms Mechanical Drawings Rev.1 | 1 | 0 | 0 | KPTG-IntCorr-000470 | APPROVED | 2026-08-10 | WF-000194 | NA | 2026-08-21 |  |  | 2026-08-17 | 2026-08-19 | KPTG-TRANSMIT-000996 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-07 | D&E-TRANSMIT-000982 | NA | Trade Partner | SFN System Volume & Expansion Calculations - Issued for Construction | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | The document revision number has been already submitted |  | 2026-08-07 | KPTG-DA-008035 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-20 | RDSBIM-TRANSMIT-000012 | NA | Trade Partner | GREYSTAR ¦ GROUND FLOOR MAIN ENTRY RAMP PLAN AND SECTION | 3 | 0 | 0 | NA | APPROVED | 2026-01-20 | WF-000139 | 267 | 2026-01-23 |  |  |  | 2026-02-19 | KPTG-TRANSMIT-000665 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-07 | ADP-TRANSMIT-000394 | NA | Consultant | ADP MEL4780 - Updated Fire Protection Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 4087 | 2026-08-13 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-020980 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-07 | RDSBIM-TRANSMIT-000093 | NA | Trade Partner | 352MAC ¦ LEVEL 02 CONCRETE PROFILE PLAN ZONE 5 | 1 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 1668 | 2026-08-14 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-003293 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-07 | RDSBIM-TRANSMIT-000094 | NA | Trade Partner | GREYSTAR LEVEL 03 CONCRETE PROFILE PLAN ZONE 5 | 1 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 1674 | 2026-08-14 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-07 | RDSBIM-TRANSMIT-000087 | NA | Trade Partner | GREYSTAR LEVEL 03 CONCRETE PROFILE PLAN | 5 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 1674 | 2026-08-14 |  | Review Terminated as requested by RDS to update the drawings. | 2026-08-18 | 2026-08-18 | NA | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-07 | RDSBIM-TRANSMIT-000095 | NA | Trade Partner | : GREYSTAR LEVEL 04 CONCRETE PROFILE PLAN ZONE 5 | 1 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 1692 | 2026-08-14 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-07 | RDSBIM-TRANSMIT-000090 | NA | Trade Partner | GREYSTAR LEVEL 04 CONCRETE PROFILE KEY PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 1692 | 2026-08-14 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-07 | RDSBIM-TRANSMIT-000089 | NA | Trade Partner | GREYSTAR LEVEL 04 CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 1692 | 2026-08-14 |  | Review Terminated as requested by RDS to update the drawings. | 2026-08-18 | 2026-08-18 | NA | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-07 | INGEN3D-TRANSMIT-000238 | NA | Trade Partner | L15-L17 - SHOP DETAIL | 39 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | register updated - sent to all parties via trn # 3321 |  | 2026-08-07 | KPTG-TRANSMIT-003321 | Closed | 39 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-07 | G&CHyd-TRANSMIT-000005 | NA | Trade Partner | HYD Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-08-07 | WF-001110 | NA | 2026-08-10 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-20 | Auspan-TRANSMIT-000052 | NA | Trade Partner | Update precast dowel layout ground floor. Zone 4,5 | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect drawing status and rejected. KPTG-SADV-000621 |  | 2026-01-20 | KPTG-SADV-000621 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-07 | D&E-TRANSMIT-000019 | NA | Trade Partner | L-2 Mechanical Louvers Tech. Data IFA-VML00918 | 0 | 1 | 0 | NA | APPROVED | 2026-08-07 | WF-001117 | NA | 2026-08-14 |  |  | 2026-08-24 | 2026-08-24 | WF-001219 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-07 | INGEN3D-TRANSMIT-000240 | NA | Trade Partner | Level 21-23 - PC0673-2 & PC0714 - IFC (07-08-2026) | 2 | 0 | 0 | NA | APPROVED | 2026-08-07 | WF-001118 | NA | 2026-08-14 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-003481 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-07 | INGEN3D-TRANSMIT-000237 | NA | Trade Partner | PC 562 Update | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | register updated - sent to all parties via trn # 3329 |  | 2026-08-07 | KPTG-TRANSMIT-003329 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-08-07 | Nilsen3-TRANSMIT-000251 | NA | Trade Partner | Nilsen HV Shop Drawings - IFA | 3 | 0 | 0 | NA | APPROVED | 2026-08-07 | WF-006641 | NA | 2026-08-21 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-07 | DLTS-TRANSMIT-000083 | NA | Trade Partner | S11-HV Room-Re-IFA Issue | 21 | 0 | 0 | NA | APPROVED | 2026-08-07 | WF-001438 | NA | 2026-08-18 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-006876 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-07 | DLTS-TRANSMIT-000084 | NA | Trade Partner | S9-Roof Canopy-Re IFA Issue | 38 | 0 | 0 | NA | APPROVED | 2026-08-07 | WF-001439 | NA | 2026-08-18 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-007038 | Closed | 38 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-07 | Arc Plas-TRANSMIT-000005 | NA | Trade Partner | Updated tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-08-07 | WF-001432 | NA | 2026-08-11 |  | Resubmitted as advised by Project Coordinator | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-007033 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-07 | VIA Arch-TRANSMIT-000224 | NA | Consultant | Updated drawings | 14 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to the project team |  | 2026-08-07 | KPTG-TRANSMIT-006587 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-10 | RDSBIM-TRANSMIT-000296 | NA | Trade Partner | NXM3S4 ¦ GROUND FLOOR ¦ WET AREA-C-G-073 UNISEX WC | 1 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 4089 | 2026-08-12 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-020927 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-10 | SMEPS-TRANSMIT-000094 | NA | Trade Partner | Lighting Control Equipment | 0 | 1 | 0 | NA | APPROVED | 2026-08-10 | WF-001446 | NA | 2026-08-20 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-01-20 | StantecA-TRANSMIT-000019 | NA | Consultant | Revised Hydraulic services | 53 | 0 | 0 | KPTG-IntCorr-000302 | APPROVED | 2026-01-21 | WF-000134 | 217 | 2026-01-26 |  | Previous revision is under review. Waiting for advise. KPTG-IntCorr-000302 |  | 2026-02-10 | KPTG-TRANSMIT-000429 | Closed | 53 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-10 | SPECAUTO-TRANSMIT-000013 | NA | Trade Partner | CSMS Commissioning Plan - For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-08-10 | WF-000444 | NA | 2026-08-21 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-002316 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-10 | RDSBIM-TRANSMIT-000297 | NA | Trade Partner | NXM3S4 ¦GROUND FLOOR TO ROOF PRECAST WALL ELEVATION | 23 | 0 | 0 | NA | REJECTED | [5 empty] | Revision not updated |  | 2026-08-10 | KPTG-DA-008044 | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-10 | Auspan-TRANSMIT-000592 | NA | Trade Partner | Precast shop drawings for construction. Level 5 | 47 | 0 | 0 | KPTG-IntCorr-001219 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001219 29 ARE OK TO IFC- KPTG-TRANSMIT-003370- Published 4 Drawings are updated and superseded 14 are Rejected advised by Kapitol PC: KPTG-IntCorr-001401 |  | 2026-08-28 | KPTG-TRANSMIT-003370 | Closed | 47 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-10 | RDSBIM-TRANSMIT-000063 | NA | Trade Partner | MCC ¦ GROUND FLOOR LEVEL RCP KG COMMENTS UPDATION | 5 | 0 | 0 | KPTG-IntCorr-003987 | APPROVED | 2026-08-10 | NA | 406 | 2026-08-17 |  | Terminated as per peter advise |  | 2026-08-27 | KPTG-IntCorr-004197 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-07 | ADP-TRANSMIT-000390 | NA | Consultant | ADP MEL4780 - Fire Protection Reg 126 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-08-07 | KPTG-TRANSMIT-020432 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-10 | VERTIV-TRANSMIT-000064 | NA | Trade Partner | CALCULATION SUBMISSION _ BATTERY SIZING, CABLE SIZING AND ELECTRICAL LOAD MAXIMUM DEMAND (FOA-2 & FOA-3) | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected: Title does not match the title in Aconex |  | 2026-08-10 | KPTG-TRANSMIT-001649 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-10 | D&E-TRANSMIT-000304 | NA | Trade Partner | Mechanical BMS Commissioning Plan | 0 | 1 | 0 | NA | APPROVED | 2026-08-10 | NA | NA | 2026-08-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-10 | LNCPPL-TRANSMIT-000028 | NA | Trade Partner | Electrical Drawings - Site Inground | 2 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 479 | 2026-08-14 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-001857 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-10 | Auspan-TRANSMIT-000595 | NA | Trade Partner | Precast shop drawings for approval. Zone 4, 5 level 7 | 38 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1678 | 2026-08-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-10 | Auspan-TRANSMIT-000595 | NA | Trade Partner | Precast shop drawings for approval. Zone 4, 5 level 7 | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - difference in title and wrong attachment- DRAFT-011217 |  | 2026-08-10 | DRAFT-011217 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-20 | Mirage D-TRANSMIT-000012 | NA | Trade Partner | Steel roller shutters - IFC - Revision 4 | 9 | 0 | 0 | NA | APPROVED | 2026-01-20 | NA | 3689 | 2026-01-23 |  |  | 2026-02-10 | 2026-02-10 | KPTG-TRANSMIT-012639 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-10 | Auspan-TRANSMIT-000593 | NA | Trade Partner | Precast shop drawings for construction. Level 4 | 9 | 0 | 0 | KPTG-IntCorr-001222 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001222 8 OK TO IFC- KPTG-TRANSMIT-003195; 1 Rejected as advised by Kapitol PC. KPTG-SADV-004141 |  | 2026-08-12 | KPTG-TRANSMIT-003195 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-10 | L.E.S.-TRANSMIT-000047 | NA | Trade Partner | Communications Sample Submissions | 0 | 4 | 0 | NA | APPROVED | 2026-08-10 | WF-001120 | NA | 2026-08-13 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-10 | L.E.S.-TRANSMIT-000047 | NA | Trade Partner | Communications Technical Data Submissions | 0 | 3 | 0 | NA | APPROVED | 2026-08-10 | WF-001121 | NA | 2026-08-13 |  |  | 2026-08-20 | 2026-08-20 | WF-001193 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-10 | D&E-TRANSMIT-000305 | NA | Trade Partner | Mechanical Electrical Drawings for Construction | 0 | 4 | 0 | NA | REJECTED | [5 empty] | document number is incorrect |  | 2026-08-10 | KPTG-TRANSMIT-001606 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-10 | Auspan-TRANSMIT-000596 | NA | Trade Partner | Re: GMAC - Level 3 Additional precast penetrations | 3 | 0 | 0 | KPTG-IntCorr-001224 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001224 OK TO IFC- KPTG-TRANSMIT-003197 |  | 2026-08-12 | KPTG-TRANSMIT-003197 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-10 | Auspan-TRANSMIT-000591 | NA | Trade Partner | Precast shop drawings for construction. Level 4 | 1 | 0 | 0 | KPTG-IntCorr-001225 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001225 OK TO IFC- KPTG-TRANSMIT-003193 |  | 2026-08-12 | KPTG-TRANSMIT-003193 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-10 | SMEPS-TRANSMIT-000095 | NA | Trade Partner | STAGE 11-Ground, LV1 & LV2 POWER LAYOUTS {IFC} | 3 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1666 | 2026-08-17 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-10 | Leemark-TRANSMIT-000067 | SPARK-CRFI-KPG-000395 | Trade Partner | Re: MCC - Fire Proection Layout - FDCIE-01 & SHCIE-01- IFA | 2 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 405 | 2026-08-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-10 | Arco-TRANSMIT-000010 | NA | Trade Partner | RESUBMISSION OF SHOPDRAWINGS - SWING GATES (0007 & 0008) | 2 | 0 | 0 | KPTG-SADV-006363 | APPROVED | 2026-08-13 | NA | 409 | 2026-08-20 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-10 | Carr-TRANSMIT-000083 | NA | Consultant | 303 Collins - Updated GA Plans and RCP's | 5 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 336 | 2026-08-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-02 | ARCH-TRANSMIT-000119 | NA | Consultant | MLC - SPR - Drawing update | 11 | 0 | 0 | NA | APPROVED | 2025-12-02 |  | 362 | 2025-12-09 |  |  | 2025-12-09 | 2025-12-09 | KPTG-SADV-003071 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-20 | DS-TRANSMIT-000088 | NA | Trade Partner | HYD SITE - DRAINAGE | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with drawing status in the document register |  | 2026-01-20 | KPTG-DA-004243 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-10 | WilsonPD-TRANSMIT-000167 | NA | Trade Partner | Stage 10 Level 2 Penetrations IFA | 1 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1668 | 2026-08-17 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-006924 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-10 | CDL-TRANSMIT-000050 | NA | Trade Partner | Concrete Mix Design | 0 | 1 | 0 | NA | APPROVED | 2026-08-10 | WF-001094 | NA | 2026-08-12 |  | Covering sheet is not attached, request to resubmit: KPTG-SADV-006006 | 2026-08-20 | 2026-08-25 | KPTG-TRANSMIT-003333 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-10 | Carr-TRANSMIT-000073 | NA | Consultant | Ground Floor and Upper-Level drawings Issued for Approval | 16 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 333 | 2026-08-17 |  | Review Voided as updated drawing received |  | 2026-08-14 | NA | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-10 | POTTSENG-TRANSMIT-000064 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - PENETRATION - LEVEL 01 - ZONE 3 LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1683 | 2026-08-17 |  | Rejected | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-003338 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-10 | Carr-TRANSMIT-000072 | NA | Consultant | Architecture Issue for Coordination | 8 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 334 | 2026-08-17 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-10 | ZIA-TRANSMIT-000150 | NA | Trade Partner | M3 Stage 4 - Device List | 0 | 1 | 0 | NA | REJECTED | [5 empty] | REVISION NOT UPDATED |  | 2026-08-10 | KPTG-DA-008052 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-10 | ARCST-TRANSMIT-000379,378 | NA | Trade Partner | Re: S4 Loading Dock Stair - Issued For Approval | 19 | 0 | 0 | NA | APPROVED | 2026-08-10 | WF-006637 | NA | 2026-08-14 |  |  | 2026-08-17 | 2026-08-17 | KPTG-TRANSMIT-020624 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-10 | WilsonPD-TRANSMIT-000168 | NA | Trade Partner | Stage 11 Level 2 Penetrations IFC | 1 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1670 | 2026-08-13 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-006776 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-07-31 | SMEPS-TRANSMIT-000364 | NA | Trade Partner | SME IFC Documentation | 12 | 0 | 0 | NA | APPROVED | 2026-07-31 | NA | 4027 4029 |  |  | As instructed by Fabian-TERMINATED |  | 2026-08-10 | KPTG-TRANSMIT-020469 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-10 | D&E-TRANSMIT-000986 | NA | Trade Partner | SFN System Volume & Expansion Calculations - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | [5 empty] | For distribution |  | 2026-08-10 | KPTG-TRANSMIT-020470 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-10 | POTTSENG-TRANSMIT-000063 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - PENETRATION - LEVEL 02 - ZONE 1 LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1822 | 2026-08-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-10 | ELLISAIR-TRANSMIT-000158 | NA | Trade Partner | Pipework Painting | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, updated register and distributed |  | 2026-08-10 | KPTG-TRANSMIT-006611 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-10 | RDSBIM-TRANSMIT-000018 | NA | Trade Partner | NXM2S9-11 ¦ STAGE 10 LEVEL 2 HOB & PLINTH LAYOUT | 5 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1688 | 2026-08-17 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-007001 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-10 | RDSBIM-TRANSMIT-000019 | NA | Trade Partner | NXM2S9-11 ¦ STAGE 11 LEVEL 2 HOB & PLINTH LAYOUT | 5 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1689 | 2026-08-17 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-007007 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-10 | D&E-TRANSMIT-000987 | NA | Trade Partner | IW Pumps - Issued for Construction | 0 | 1 | 0 | NA | REJECTED | [5 empty] | need to resubmit KPTG-IntCorr-017510 |  | 2026-08-10 | KPTG-DA-008057 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-10 | SMEPS-TRANSMIT-000245 | NA | Trade Partner | Telecommunication As Built Drawings | 25 | 0 | 0 | NA | APPROVED | 2026-08-10 | WF - 000565 | NA | 2026-08-14 |  | NA |  |  |  | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-10 | POTTSENG-TRANSMIT-000065 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - PENETRATION - LEVELS 03-05 - ZONES 1-5 LAYOUTS | 15 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1687 | 2026-08-17 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-003343 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-10 | D&E-TRANSMIT-000306 | NA | Trade Partner | Mechanical Electrical IFC Drawings | 0 | 4 | 0 | NA | APPROVED | 2026-08-10 | NA | NA | 2026-08-17 |  | Processed as Tech data as advised by chelsea. |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-08-10 | Nilsen3-TRANSMIT-000247 | NA | Trade Partner | M3-HV-NIL-SA-S-0301-0028 - Cable Cleats - Rev 1 - PANDUIT | 0 | 1 | 0 | NA | APPROVED | 2026-08-10 | WF-006640 | NA | 2026-08-20 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-020911 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-10 | DLTS-TRANSMIT-000086 | NA | Trade Partner | S9-Northern Awning-Re-IFA Issue | 31 | 0 | 0 | NA | APPROVED | 2026-08-10 | WF-001454 | NA | 2026-08-19 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-007237 | Closed | 31 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-10 | ccair-TRANSMIT-000010 | NA | Trade Partner | Apartment low profile duct and non-return damper for approval | 0 | 2 | 0 | NA | APPROVED | 2026-08-10 | WF-001122 | NA | 2026-08-13 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-003551 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-10 | SMEPS-TRANSMIT-000246 | NA | Trade Partner | Electrical drawings AB-1 | 20 | 0 | 0 | NA | APPROVED | 2026-08-10 | WF - 000566 | NA | 2026-08-14 |  | NA |  |  |  | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-10 | D&E-TRANSMIT-000307 | NA | Trade Partner | Vertigo for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-08-10 | NA | NA | 2026-08-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-10 | SMEPS-TRANSMIT-000247 | NA | Trade Partner | Electrical Tech data IFA | 0 | 1 | 0 | NA | APPROVED | 2026-08-10 | WF - 000567 | NA | 2026-08-14 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-10 | crossfir-TRANSMIT-000007 | NA | Trade Partner | Wet Fire - Hydraulic Calculation | 0 | 2 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected: Wrong document attaced. |  | 2026-08-10 | KPTG-TRANSMIT-001688 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-10 | Auspan-TRANSMIT-000594 | NA | Trade Partner | Update IFCed precast shop drawings. Levels 3, 4, 5 | 8 | 0 | 0 | KPTG-IntCorr-001232 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001232 OK TO IFC- KPTG-TRANSMIT-003256 |  | 2026-08-19 | KPTG-TRANSMIT-003256 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-10 | KALLIBRE-TRANSMIT-000003 | NA | Trade Partner | FOA-3 Submission | 28 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 483 | 2026-08-21 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-002202 | Closed | 28 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-10 | crossfir-TRANSMIT-000006 | NA | Trade Partner | Wet Fire - Site Plan & Hyd calculations | 2 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 485 | 2026-08-14 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-002029 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-10 | EAEGROUP-TRANSMIT-000006 | NA | Trade Partner | IFA Shop Drawings – Main Corridor 2500A Busduct Runs | 3 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | WF-000452 | 2026-08-21 |  | AS PER STANDING ADVISE FROM KATHERINE REJECTED DOCUMENTS PROCESED |  | 2026-08-17 | KPTG-TRANSMIT-001934 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-10 | D&E-TRANSMIT-000989 | NA | Trade Partner | NXM3S4 - Roof Level - Chiller Room Sections - Sheet 5 of 5 - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 4093 | 2026-08-19 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-021007 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-10 | EAEGROUP-TRANSMIT-000007 | NA | Trade Partner | IFA Shop Drawings – Mechanical Corridor 1600A Busduct Runs | 5 | 0 | 0 | NA | APPROVED | 2026-08-10 | WF-000453 | NA | 2026-08-21 |  | AS PER STANDING ADVISE FROM KATHERINE REJECTED DOCUMENTS PROCESED |  | 2026-08-17 | KPTG-TRANSMIT-001938 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-10 | Baigents-TRANSMIT-000033 | NA | Trade Partner | Block 01 - Upper West Precast Panels - Issued for Approval | 20 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 638 | 2026-08-14 |  | NA | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-001054 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-10 | Baigents-TRANSMIT-000031 | NA | Trade Partner | Block 01 - Upper West Precast Panels - Issued for Approval | 125 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 630 | 2026-08-14 |  | NA | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-000932 | Closed | 125 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-10 | ADP-TRANSMIT-000134 | NA | Trade Partner | Re: ADP MEL4680 - Data Hall Lighting Calculation Summary | 0 | 1 | 0 | NA | REJECTED | [5 empty] | the attached documents seem different stage name on the inside document kindly change the revision 01 to IFI-01 for better identification and easy process |  | 2026-08-10 | KPTG-SADV-001177 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-10 | 4DW-TRANSMIT-000077 | NA | Consultant | Structural Documentation: NLB Feature Precast Wall PW503 Issued with Construction updates. | 1 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 626 | 2026-08-14 |  | NA | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001007 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-10 | Nilsen3-TRANSMIT-000083 | NA | Trade Partner | Nilsen Drawings for Approval | 2 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1674 | 2026-08-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-10 | Nilsen3-TRANSMIT-000088 | NA | Trade Partner | Nilsen drawings for Approval | 6 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1674 | 2026-08-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-10 | Nilsen3-TRANSMIT-000089 | NA | Trade Partner | Nilsen drawings for Approval | 3 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1674 | 2026-08-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-10 | Axiom-TRANSMIT-000018 | NA | Trade Partner | Building B Setout Plans - Issued for Approval. | 11 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1089 | 2026-08-19 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-10 | PSGANZ-TRANSMIT-000014 | NA | Trade Partner | Fire Protection tech data | 0 | 3 | 0 | NA | APPROVED | 2026-08-10 | WF-000454 | NA | 2026-08-21 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-002015 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-19 | WGAVIC-TRANSMIT-000040 | NA | Consultant | Structural Drawings - Stage 9 Pour Sequence Plans - Issued for Information | 2 | 0 | 0 | NA | APPROVED | [5 empty] | Drawings for information only. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-10 | crossfir-TRANSMIT-000008 | NA | Trade Partner | Wet Fire - Hydraulic calculations | 0 | 1 | 0 | NA | APPROVED | 2026-08-10 | WF-000455 | NA | 2026-08-19 |  | remains drawing still under review | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-001900 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-10 | WAM-TRANSMIT-000845 | NA | Consultant | IFC- A40.102 - A40.103 Details Balustrades | 2 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1091 | 2026-08-13 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-003543 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-10 | VERTIV-TRANSMIT-000064 | NA | Trade Partner | NEXT DC GE01 _ CALCULATION SUBMISSION _ CABLE SIZING AND VOLTAGE DROP CALCULATION (FOA-3) | 0 | 1 | 0 | NA | APPROVED | 2026-08-10 | WF-000456 | NA | 2026-08-19 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-001840 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-10 | VERTIV-TRANSMIT-000065 | NA | Trade Partner | NEXT DC GE01 _ CALCULATION SUBMISSION _ CABLE SIZING AND VOLTAGE DROP CALCULATION (FOA-3) | 0 | 1 | 0 | NA | APPROVED | 2026-08-10 | WF-000456 | NA | 2026-08-19 |  |  | 2026-08-17 | 2026-08-17 | KPTG-TRANSMIT-001917 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-10 | Carr-TRANSMIT-000079 | NA | Consultant | SME Review - Facade IFA drawings | 20 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 337 | 2026-08-19 |  | Review Voided as discussed with Renee, Facade IFC Package is under review @366 |  | 2026-08-21 | NA | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-10 | WSP ANZ-TRANSMIT-000020 | NA | Consultant | SME REVIEW - Acoustic Report | 0 | 1 | 0 | NA | APPROVED | 2026-08-10 | NA | 338 | 2026-08-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-10 | GIW-TRANSMIT-000003 | NA | Consultant | J1V3 Report and ESD Markup | 0 | 2 | 0 | NA | APPROVED | 2026-08-10 | NA | 339 | 2026-08-27 |  | Updated documents re initiated for SME review #401 |  | 2026-08-31 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D9 | 2026-08-10 | IVS-TRANSMIT-000018 | NA | Consultant | Drawing Register Update | 10 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1471 | 2026-08-28 |  | Terminated as instructed by Isaiah Finn for submitting the updated documents | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-000070 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-10 | WilsonPD-TRANSMIT-000019 | NA | Trade Partner | Re: HYDRAULIC SERVICES - CLEARANCE ZONES REGISTER | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The attached document seems incorrect status In the submission Mistake in the revision number Incorrect format document submitted |  | 2026-08-10 | KPTG-SADV-001178 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-20 | Marr Con-TRANSMIT-000002 | NA | Trade Partner | Tower cranes Radius and Elevation | 1 | 0 | 0 | NA | APPROVED | [5 empty] | Drawing for Information only |  |  | NA | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-07-03 | VERTIV-TRANSMIT-000042 | NA | Trade Partner | Next DC GE01 _ Technical Data _ Cooling Load Calculation & CFD Analysis Report (FOA-2) | 0 | 1 | 0 | NA | APPROVED | 2026-07-03 | WF-000283 | NA | 2026-07-16 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-001725 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-10 | crossfir-TRANSMIT-000006 | NA | Trade Partner | Wet Fire - Site Plan & Hyd calculations | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Issue with numbering, revision, revision date etc. |  | 2026-08-10 | KPTG-TRANSMIT-001658 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-10 | ZIA-TRANSMIT-000151 | NA | Consultant | SHOP DRAWING | 1 | 0 | 0 | NA | APPROVED | 2026-08-10 | ZIA-TRANSMIT-000151 | NA | 2026-08-21 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-10 | PTA-TRANSMIT-000042 | NA | Consultant | Fire compartment plans for coordination | 2 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 632 | 2026-08-18 |  | NA | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-000998 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-10 | EUKAI-TRANSMIT-000022 | NA | Consultant | Updated Signage and Linemarkinng Plans | 7 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 634 | 2026-08-18 |  |  | 2026-08-18 | 2026-08-19 | KPTG-TRANSMIT-001013 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-10 | RDSDG-TRANSMIT-000005 | NA | Trade Partner | Pressure Shop Drawings - Block 1, Carpark & North Zones [IFA] | 3 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 637 | 2026-08-18 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001019 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-10 | SMEPS-TRANSMIT-000013 | NA | Trade Partner | Stage 6 - Conduit IFA | 0 | 1 | 0 | NA | APPROVED | 2026-08-10 | NA | 628 | 2026-08-18 |  | NA | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-000952 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-10 | Baigents-TRANSMIT-000032 | NA | Trade Partner | Block 1 Level 1 Precast Beams -Updated Edge Form Detail | 2 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 640 | 2026-08-18 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-000909 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-10 | EUKAI-TRANSMIT-000024 | NA | Consultant | Signage & Linemarking Drawing Updates | 8 | 0 | 0 | NA | REJECTED | [5 empty] | same revision submitted again |  | 2026-08-10 | KPTG-TRANSMIT-000881 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-20 | Auspan-TRANSMIT-000049 | NA | Trade Partner | Precast shop drawings for construction. Remaining of L shape panels | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings need to be revised - KPTG-SADV-000699 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-10 | Aurecon-TRANSMIT-000146 | NA | Consultant | NEXTDC M3 | 12 | 0 | 0 | KPTG-IntCorr-000478 | REJECTED | [5 empty] | This documents not for Stage 6 Project. |  | 2026-08-20 | KPTG-TRANSMIT-001036 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-10 | PTA-TRANSMIT-000043 | NA | Consultant | Trench Grate Update - Issue for Coordination | 5 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 642 | 2026-08-18 |  | NA | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-000998 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-10 | NXT-WTRAN-000131 | NA | Client | FIE FOR APPROVAL (NEW): DCNEXUS Finishes Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-08-10 | WF-000195 | NA | 2026-08-18 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-10 | 4DW-TRANSMIT-000207 | NA | Consultant | Structural Documentation - Precast Facade & Steel Framing updates | 4 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 462 | 2026-08-13 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-003246 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-10 | Danlai-TRANSMIT-000016 | NA | Trade Partner | Transmittal of WSI tech data sheet | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected: Document Number of tech data is incorrect:KPTG-SADV-005824 |  | 2026-08-10 | KPTG-SADV-005824 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-10 | Danlai-TRANSMIT-000017 | NA | Trade Partner | Transmittal for WSI tech data sheet | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected: Document Number of tech data is incorrect:KPTG-SADV-005835 |  | 2026-08-10 | KPTG-SADV-005835 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-10 | Ardon-TRANSMIT-000022 | NA | Trade Partner | Ground Level Shop Drawings for Approval | 24 | 0 | 0 | NA | APPROVED | 2026-08-10 | WF-001449 | NA | 2026-08-19 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-006998 | Closed | 24 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-10 | Ardon-TRANSMIT-000023 | NA | Trade Partner | Priority 2 Shop Drawings for Round 2 Approval | 16 | 0 | 0 | NA | APPROVED | 2026-08-10 | WF-001455 | NA | 2026-08-19 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-007000 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-10 | SES AU-TRANSMIT-000007 | NA | Trade Partner | Security Shop Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1676 | 2026-08-17 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-007229 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-10 | KPTG-IntCorr-001221 | NA | Trade Partner | Electrical Services Penetration layouts - Ground - Level 6 | 11 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1679 | 2026-08-17 |  | KPTG-WTRAN-001460 - Trade partner superseded the drawings. | 2026-08-13 | 2026-08-13 | KPTG-WTRAN-001460 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-20 | Auspan-TRANSMIT-000050 | NA | Trade Partner | Update marking plans for ground floor MG03 and MG04 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings need to be revised - KPTG-SADV-000698 |  | 2026-01-21 | KPTG-SADV-000698 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-10 | EUKAI-TRANSMIT-000023 | NA | Consultant | Stage 6 Site Wide Swept Paths | 25 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 644 | 2026-08-18 |  | NA | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-001143 | Closed | 25 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-10 | KPTG-IntCorr-001220 | NA | Trade Partner | : Auscool AC selections | 3 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Returned due to no document number - KPTG-IntCorr-001227 |  | 2026-08-10 | KPTG-IntCorr-001227 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-10 | TTW-TRANSMIT-000022 | NA | Consultant | Facade F3P1 weatherproofing performance solution Update | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required, Updated register and distributed |  | 2026-08-10 | KPTG-TRANSMIT-006607 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-10 | INDS-TRANSMIT-000059: | NA | Trade Partner | L2 to L7 Zone 3 - Typical Floor Penetration Layout | 1 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1693 | 2026-08-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-10 | RDSBIM-TRANSMIT-000243 | NA | Trade Partner | LINDRUM ¦ LEVEL 03 PARTITION WALL LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 736 | 2026-08-13 |  |  | 2026-08-28 | 2026-08-28 | KPTG-SADV-005467 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-10 | Ardon-TRANSMIT-000016 | NA | Trade Partner | Door Hardware Schedule Stage 9 - Detail Door Hardware | 0 | 1 | 0 | NA | APPROVED | 2026-08-10 | WF-001448 | NA | 2026-08-18 |  | Workflow 1448 terminated as requested by Project Coordinator |  | 2026-08-20 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-10 | RDSBIM-TRANSMIT-000242 | NA | Trade Partner | LINDRUM ¦ LEVEL 02 PARTITION WALL LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 735 | 2026-08-13 |  |  | 2026-08-28 | 2026-08-28 | KPTG-SADV-005466 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-10 | RDSBIM-TRANSMIT-000096: | NA | Trade Partner | 671 CHP ¦ GROUND FLOOR BLOCKWORK ELEVATIONS | 2 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 747 | 2026-08-17 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-001665 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-10 | ccair-TRANSMIT-000044 | NA | Trade Partner | : Mechanical Services L4 ductwork and pipework layout IFA [A] | 1 | 0 | 0 | KPTG-IntCorr-001190 | APPROVED | 2026-08-11 | NA | 750 | 2026-08-18 |  | Tayla to Advise - KPTG-IntCorr-001190 | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-001723 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-10 | KPTG-IntCorr-001173 | NA | Trade Partner | - FP1.4 - PBDB Reports [Rev01] | 0 | 1 | 0 | NA | APPROVED | 2026-08-10 | WF-000678 | NA | 2026-08-17 |  | Closed by PC -KPTG-TRANSMIT-001580 | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-001580 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-19 | PCForm-TRANSMIT-000273 | NA | Trade Partner | IFC - TOWER A L14 - L15 & ROOF PT SHOP DRAWINGS | 30 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 30 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-10 | Aloha P-TRANSMIT-000002 | NA | Trade Partner | Pool Issued For Approval Set | 24 | 0 | 0 | KPTG-IntCorr-001185 | REJECTED |  | NA | NA |  |  | Waiting for advice - KPTG-IntCorr-001185 Rejected due to incorrect drawing reference in the drawing KPTG-IntCorr-001185, DRAFT-011696 |  | 2026-08-12 | KPTG-IntCorr-001185 | Closed | 24 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-10 | DLTS-TRANSMIT-000085 | NA | Trade Partner | S6-Awning-IFC Issue | 47 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Need to update KPTG-SADV-007466 |  | 2026-08-10 | KPTG-SADV-007466 | Closed | 47 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-10 | DLTS-TRANSMIT-000087 | NA | Trade Partner | S91011-HV Room Set out | 4 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-007465 |  | 2026-08-10 | KPTG-SADV-007465 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-10 | SMEPS-TRANSMIT-000096 | NA | Trade Partner | Sample Submittals for IFC | 0 | 18 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-007467 |  | 2026-08-10 | KPTG-SADV-007467 | Closed | 18 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-10 | Tradetec-TRANSMIT-000158 | NA | Trade Partner | As Built | 4 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-007464 |  | 2026-08-10 | KPTG-SADV-007464 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-10 | Tradetec-TRANSMIT-000161 | NA | Trade Partner | TSA-INGROUND PROPOSED SEWER RELOCATION - FOR APPROVAL | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Drawing For Information. Updated Register |  | 2026-08-10 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-05 | DLTS-TRANSMIT-000078 | NA | Trade Partner | S9-HV Room2-RE-IFA Issue | 3 | 0 | 0 | NA | APPROVED | 2026-08-05 | WF-001422 | NA | 2026-08-11 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-006662 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-10 | WAM-TRANSMIT-000842 | NA | Consultant | A16 Facade Plans and A71 Facade schedule and elevations - Response to Jangho RFI's | 23 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1088 | 2026-08-13 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-003581 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-10 | WAM-TRANSMIT-000843 | NA | Consultant | A16 Facade Plans and A71 Facade schedule and elevations - IFC stamp amended | 10 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1088 | 2026-08-13 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-003581 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-19 | PCForm-TRANSMIT-000276 | N/A | Trade Partner | Reg 126 - Tower A L14 to Roof | 0 | 1 | 0 | NA | APPROVED |  | NA | N/A |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-10 | WAM-TRANSMIT-000844 | NA | Consultant | A61.201 Update | 1 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1093 | 2026-08-13 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-003540 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-10 | Planning Docs - Teams message | NA | Consultant | Planning Docs | 0 | 9 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-08-10 | KPTG-TRANSMIT-003350 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-10 | VAE-Grp-TRANSMIT-000176 | NA | Trade Partner | IFC - MECHANICAL - SCHED & TECH SUB - PRIMARY CW PUMP CHANGES + MINOR MCC CORRECTIONS | 0 | 2 | 0 | NA | REJECTED | [5 empty] | QA ERROR - REVISION MISTAKE |  | 2026-08-10 | KPTG-IntCorr-002027 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-10 | VAE-Grp-TRANSMIT-000179 | NA | Trade Partner | IFC - MECHANICAL - SCHED & TECH SUB - PRIMARY CW PUMP CHANGES + MINOR MCC CORRECTIONS | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | fc docs - KPTG-TRANSMIT-004241 |  | 2026-08-10 | KPTG-TRANSMIT-004241 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-10 | VAE-Grp-TRANSMIT-000185 | NA | Trade Partner | IFC - MECHANICAL - SCHED & TECH SUB - PRIMARY CW PUMP CHANGES + MINOR MCC CORRECTIONS | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | fc docs - KPTG-TRANSMIT-004246 |  | 2026-08-10 | KPTG-TRANSMIT-004246 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-10 | KPTG-IntCorr-002028 | NA | Trade Partner | D1S2 Fire Matrix Extract - ENDFIRE | 0 | 1 | 0 | NA | APPROVED | 2026-08-10 | WF-001192 | NA | 2026-08-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-11 | Danlai-TRANSMIT-000018 | NA | Trade Partner | Transmittal Crommelin Data sheetTransmittal Crommelin Data sheet | 0 | 1 | 0 | NA | APPROVED | 2026-08-11 | WF-001096 | NA | 2026-08-14 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-003314 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-11 | INTRFRM-TRANSMIT-000118 | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 6) | 0 | 3 | 0 | NA | APPROVED | 2026-08-11 | WF-000457 | NA | 2026-08-20 |  |  | 2026-08-17 | 2026-08-17 | KPTG-TRANSMIT-001929 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-11 | D&E-TRANSMIT-000990 | NA | Trade Partner | Re: Permabond Technical Data - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | As instructed, no further action has been taken on this transmittal. |  | 2026-08-11 | KPTG-IntCorr-017542 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | PFP PL-TRANSMIT-000030 | NA | Trade Partner | S10 L2 IFA | 1 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 1678 | 2026-08-18 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-006865 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-02 | CLADC-TRANSMIT-000009 | NA | Trade Partner | Ordered hardware | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2025-12-02 | KPTG-SADV-002938 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-06 | TIVINTL-TRANSMIT-000013 | NA | Trade Partner | SRC-Tivoli- Updated Tivoli joinery bulk drawings | 404 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 404 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-11 | Auspan-TRANSMIT-000597 | NA | Trade Partner | Re: GMAC - Level 3 Additional precast penetrations | 13 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 1695 | 2026-08-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-11 | Auspan-TRANSMIT-000597 | NA | Trade Partner | Re: GMAC - Level 3 Additional precast penetrations | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected- Difference in document number and status - DRAFT-011290 |  | 2026-08-11 | DRAFT-011290 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | Eneraque-TRANSMIT-000058 | NA | Trade Partner | Rev0 Datasheets Issued for Construction | 0 | 6 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, updated register and distributed |  | 2026-08-11 | KPTG-TRANSMIT-006669 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-11 | D&E-TRANSMIT-000991 | NA | Trade Partner | NXM3S4 - Upper Roof Level - Cooling Tower Sections - Sheet 4 of 4 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | FOR DISTRIBUTION |  | 2026-08-11 | KPTG-TRANSMIT-020497 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-11 | Auspan-TRANSMIT-000598 | NA | Trade Partner | Precast shop drawings for construction. Zone 3 levels 4, 5 | 7 | 0 | 0 | KPTG-IntCorr-001235 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001235 All rejected by Oliver - KPTG-SADV-004285 - |  | 2026-08-18 | KPTG-SADV-004285 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-11 | D&E-TRANSMIT-000993 | NA | Trade Partner | Active Harmonic Filters - Issued for Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | DOCUMENT NUMBER ERROR |  | 2026-08-11 | KPTG-DA-008072 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-10 | SKS Tech-TRANSMIT-000201 | NA | Trade Partner | ELECTRICAL SERVICES-STRING A B C LINE UP SINGLE LINE-DAY 1 | 3 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1321 | 2026-08-14 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-10 | Jordan-TRANSMIT-000132 | NA | Trade Partner | Updated Drawings for UTI Submission | 5 | 0 | 0 | NA | APPROVED | 2026-08-10 | NA | 1324 | 2026-08-14 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-11 | ADP-TRANSMIT-000395 | NA | Consultant | Fwd: ADP - MEL4780 - Updated LV SCCS report | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-11 | KPTG-TRANSMIT-020501 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-11 | RDSBIM-TRANSMIT-000081 | NA | Trade Partner | DISTLV ¦ LEVEL 11 CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 1095 | 2026-08-13 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-003388 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-20 | vdmcons-TRANSMIT-000124 | NA | Consultant | ME25 1004: D107 511-537 Sydney Rd Coburg - Shop Drawings - Core Lid Panels - Re-IFA - 2026-01-20 | 9 | 0 | 0 | NA | APPROVED | 2026-01-20 | WF-000885 | NA | 2026-01-27 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-11 | BIMF-TRANSMIT-000021 | NA | Trade Partner | Sewer Schematic | 1 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 1097 | 2026-08-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-11 | ccair-TRANSMIT-000011 | NA | Trade Partner | Paircoil tech data for approval | 0 | 1 | 0 | NA | APPROVED | 2026-08-11 | WF-001129 | NA | 2026-08-14 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003515 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-06 | FIE Drawings (Outlook mail) | na | Trade Partner | TYPICAL BATTERY ROOM DUCTWORK AND PIPEWORK - SEISMIC DESIGN | 1 | 0 | 0 | NA | APPROVED | 2026-08-06 | NA | 1649 | 2026-08-11 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-006676 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D9 | 2026-08-11 | HDRAus-TRANSMIT-000015 | NA | Consultant | Client X Gantry - Documents For Construction | 14 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 1473 | 2026-08-17 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-000071 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-11 | D&E-TRANSMIT-000994 | NA | Trade Partner | IW Pumps - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-08-11 | WF-006645 | NA | 2026-08-17 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-020620 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | SMEPS-TRANSMIT-000104 | NA | Trade Partner | BTU SYSTEM | 0 | 1 | 0 | NA | APPROVED | 2026-08-11 | WF-001460 | NA | 2026-08-21 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-007391 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-02 | VIA Arch-TRANSMIT-000198 | NA | Consultant | M2 S9-11 Architectural Amendments | 24 | 0 | 0 | NA | APPROVED | 2026-08-02 | NA | 1575 | 2026-08-11 |  |  | 2026-08-11 | 2026-08-11 | KPTG-DA-004171 | Closed | 24 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-11 | D&E-TRANSMIT-000996 | NA | Trade Partner | NXM3S4 - Ground - Mechanical Duct Layout - Zone 1 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | FOR DISTRIBUTION |  | 2026-08-11 | KPTG-TRANSMIT-020505 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-11 | D&E-TRANSMIT-000995 | NA | Trade Partner | NXM3S4 - SECURITY GRILLES / Ground & Level 1 - Builders Works Layout Zones - Issued For Construction | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-08-11 | KPTG-TRANSMIT-020506 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-11 | Ardon-TRANSMIT-000069 | NA | Trade Partner | Previously Rejected Door Hardware | 0 | 2 | 0 | NA | APPROVED | 2026-08-11 | WF-006646 | NA | 2026-08-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-20 | Civilex-TRANSMIT-000019 | N/A | Trade Partner | Sample Submission - Waterproofing Membrane | 0 | 1 | 0 | NA | APPROVED | 2026-01-20 | WF-000106 | NA | 2026-01-22 |  |  | 2026-01-23 | 2026-02-01 | KPTG-TRANSMIT-000348 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D9 | 2026-08-11 | HDRAus-TRANSMIT-000015 | NA | Consultant | Client X Gantry - Documents For Construction | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with document number. |  | 2026-08-11 | KPTG-TRANSMIT-000060 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-11 | JCBa-TRANSMIT-000164 | NA | Consultant | Updated Architectural Documentation - Partition Plans & Partition Detail Sections | 44 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 1697 | 2026-08-13 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-003365 | Closed | 44 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | VIA Arch-TRANSMIT-000199 | NA | Consultant | RCP - S9 Ground Floor - Insulation Update | 1 | 0 | 0 | NA | APPROVED | 2026-08-02 | NA | 1577 | 2026-08-11 |  |  | 2026-08-11 | 2026-08-11 | KPTG-DA-004172 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-11 | NXT-TRANSMIT-001681 | NA | Client | M3 Stage 4 - Admin Block Passenger Lift. | 5 | 0 | 0 | NA | APPROVED | 2026-08-11 | WF-006647 | NA | 2026-09-01 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-02 | VIA Arch-TRANSMIT-000200 | NA | Consultant | Stage 09 Switchroom Coordination Updates | 6 | 0 | 0 | NA | APPROVED | 2026-08-02 | NA | 1578 | 2026-08-11 |  |  | 2026-08-11 | 2026-08-11 | KPTG-DA-004175 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-02 | VIA Arch-TRANSMIT-000202 | NA | Consultant | M2 S9 & S11 - LEVEL 2 CONCRETE PROFILE PLANS | 2 | 0 | 0 | NA | APPROVED | 2026-08-02 | NA | 1580 | 2026-08-11 |  |  | 2026-08-11 | 2026-08-11 | KPTG-DA-004176 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-11 | PROLMC-TRANSMIT-000029 | SPARK-CRFI-KPG-000607 | Trade Partner | 8mm Acoustic Screen Shop Drawings | 8 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 407 | 2026-08-18 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-11 | WGAVIC-TRANSMIT-000013 | NA | Consultant | M3 S6 Civil Drawings - Town Planning Issue | 43 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 648 | 2026-08-13 |  | WGAVIC-TRANSMIT-000012 superseded Void Requested by Tim |  | 2026-08-11 | NA | Closed | 43 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-11 | D&E-TRANSMIT-000992 | NA | Trade Partner | Permabond Technical Data - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | same document received in D&E-TRANSMIT-000990 |  | 2026-08-11 | KPTG-IntCorr-017569 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | VIA Arch-TRANSMIT-000210 | NA | Consultant | STEEL DRAWINGS AND SWITCHROOMS ELEVATIONS | 7 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 1600 | 2026-08-11 |  |  | 2026-08-11 | 2026-08-11 | KPTG-TRANSMIT-006696 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-20 | Civilex-TRANSMIT-000021 | N/A | Trade Partner | Sample Submission - Stormwater Diversion | 0 | 8 | 0 | NA | APPROVED | 2026-01-20 | WF-000105 | NA | 2026-01-22 |  |  | 2026-01-29 | 2026-02-01 | KPTG-TRANSMIT-000342 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-11 | Civilex-TRANSMIT-000333 | NA | Trade Partner | Stage 2 - Sample Submission - Pavement Concrete mix design Hy Tec - Rev H | 0 | 1 | 0 | NA | APPROVED | 2026-08-11 | WF-006648 | NA | 2026-08-21 |  | The document revision submitted in Aconex has already been submitted previously and has completed the review process with a Rejected status. But attached document inside revision number is correct . As we are currently processing the documents while rectifying such issues, kindly double-check the document revision and submission status before making future submissions. This will help avoid unnecessary delays in the review and processing | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-020962 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-11 | HGP-TRANSMIT-000004 | NA | Trade Partner | Typical FT01 Details | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing numbering not as per the project requirement. Discussed with Elisa (Kapitol) |  | 2026-08-11 | KPTG-DA-000543 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-11 | NTRFRM-TRANSMIT-000119 | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 7) | 0 | 1 | 0 | NA | APPROVED | 2026-08-11 | WF-000459 | NA | 2026-08-21 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-02 | VIA Arch-TRANSMIT-000203 | NA | Consultant | Updated drawings | 9 | 0 | 0 | NA | APPROVED | 2026-08-02 | NA | 1582 | 2026-08-11 |  |  | 2026-08-11 | 2026-08-11 | KPTG-DA-004180 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-11 | G&CHyd-TRANSMIT-000016 | NA | Trade Partner | TECH DATA - Bottle Trap | 0 | 1 | 0 | NA | APPROVED | 2026-08-11 | WF-001130 | NA | 2026-08-14 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-003553 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | WGAVIC-TRANSMIT-000160 | NA | Consultant | M2 - Stage 9 and 11 PT Updates and Stage 9 and 10 Block Wall Addition - Issued for Construction | 12 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 1681 | 2026-08-11 |  |  | 2026-08-11 | 2026-08-11 | KPTG-DA-004181 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-11 | Ardon-TRANSMIT-000070 | NA | Trade Partner | Alternative Toilet Roll Holder Submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect revision |  | 2026-08-11 | KPTG-DA-008077 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-11 | Auscool-TRANSMIT-000073 | NA | Trade Partner | Ground Floor - Zone 1 and 3 IFA drawings | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected- Difference in revision code- DRAFT-011333 |  | 2026-08-11 | DRAFT-011333 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-02 | VIA Arch-TRANSMIT-000204 | NA | Consultant | Updated drawings | 13 | 0 | 0 | NA | APPROVED | 2026-08-02 | NA | 1584 | 2026-08-11 |  |  | 2026-08-11 | 2026-08-11 | KPTG-DA-004182 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-11 | D&E-TRANSMIT-000997 | NA | Trade Partner | Permabond Technical Data - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-08-11 | WF-006651 | NA | 2026-09-04 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-20 | OveArup-TRANSMIT-000019 | N/A | Consultant | DISTLV ¦ Arup ¦ 4B3 Documentation - Issued for Construction | 338 | 0 | 0 | NA | APPROVED | 2026-01-21 | WF-000114, WF-000115, WF-000116, | 217, 206, 208, 204 | 2026-01-28 |  | ELC - 125, FIR - 77, HYD - 84, MEC - 52 | 2026-02-02 | 2026-02-02 | KPTG-TRANSMIT-000390, KPTG-TRANSMIT-000393, KPTG-TRANSMIT-000398, KPTG-TRANSMIT-000402 | Closed | 338 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-11 | D&E-TRANSMIT-000998 | NA | Trade Partner | Active Harmonic Filters - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-08-11 | WF-006650 | NA | 2026-08-17 |  |  |  | 2026-08-14 | KPTG-TRANSMIT-020607 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-11 | Ardon-TRANSMIT-000071 | NA | Trade Partner | Alternative Toilet Roll Holder Submission | 0 | 1 | 0 | NA | APPROVED | 2026-08-11 | WF-006652 | NA | 2026-09-03 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-11 | Entire M-TRANSMIT-000088 | NA | Trade Partner | Roof Mechanical Penetration drawing - RE-IFC | 1 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 495 | 2026-08-21 |  | Reinitiated workflow for updating the status 499 | 2026-08-12 | 2026-08-12 | KPTG-DA-001130 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | WilsonPD-TRANSMIT-000169 | NA | Trade Partner | Hydraulic Drawings for Construction | 6 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 1691 | 2026-08-14 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-006780 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D9 | 2026-08-11 | HDRAus-TRANSMIT-000016 | NA | Consultant | Request to Modify the Document Number: Client X Gantry | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with document number, revision date. Uploaded as fresh document instead of superseding previous version. |  | 2026-08-11 | KPTG-IntCorr-000137 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-11 | SPECAUTO-TRANSMIT-000014 | NA | Trade Partner | Modbus RS-485 Cable Approval | 0 | 1 | 0 | NA | APPROVED | 2026-08-11 | WF-000461 | NA | 2026-08-21 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-002052 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-11 | Entire M-TRANSMIT-000089 | NA | Trade Partner | Mechanical Schematics - IFC | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Unable to process the drawings for review since the previous revision was rejected. |  | 2026-08-11 | Drfat | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | VIA Arch-TRANSMIT-000226 | NA | Consultant | M2S9-S11 - 0001-8602 - WINDOW DETAILS - SHEET 2 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-08-11 | KPTG-TRANSMIT-006711 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-11 | WilsonPD-TRANSMIT-000020 | NA | Trade Partner | HYDRAULIC SERVICES - CLEARANCE ZONES REGISTER | 0 | 1 | 0 | NA | REJECTED | [5 empty] | No cover page attached. |  | 2026-08-11 | KPTG-SADV-001190 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D9 | 2026-08-11 | HDRAus-TRANSMIT-000017 | NA | Trade Partner | RE: KPTG-IntCorr-000137 - Request to Modify the Document Number: Client X Gantry | 0 | 1 | 0 | NA | APPROVED | 2026-08-11 | NA | 1475 | 2026-08-14 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-000061 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-18 | Electro-GCOR-000005 | NA | Consultant | Lighting Concept Report | 0 | 1 | 0 | NA | APPROVED |  |  | 202 |  |  |  |  | 2026-01-21 | DRAFT-002770 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-11 | Leemark-TRANSMIT-000068 | SPARK-CRFI-KPG-000317 | Trade Partner | MCC – Ground Level Wet Fire Layout – Zones 8 & 9 – IFA | 2 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 408 | 2026-08-18 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-001643 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | Eneraque-TRANSMIT-000060 | NA | Trade Partner | P&ID's Issued For Construction | 7 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 1695 | 2026-08-18 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-11 | POTTSENG-TRANSMIT-000066 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - PENETRATION - LEVEL 02 - ZONE 4 LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 1699 | 2026-08-18 |  | Rejected | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-003349 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-11 | WilsonPD-TRANSMIT-000021 | NA | Trade Partner | HYDRAULIC SERVICES - CLEARANCE ZONES REGISTER | 0 | 1 | 0 | NA | APPROVED | 2026-08-11 | WF-000462 | NA | 2026-08-18 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | Tradetec-TRANSMIT-000163 | NA | Trade Partner | Re: TSA-INGROUND PROPOSED SEWER RELOCATION - FOR APPROVAL | 1 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 1696 | 2026-08-18 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-007295 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-11 | KPTG-TRANSMIT-020498 | NA | Trade Partner | O&M WF | 0 | 1 | 0 | NA | APPROVED | 2026-08-11 | WF-006653 | NA | 2026-08-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-11 | Carr-TRANSMIT-000084 | NA | Consultant | EOT Lift Core Plans + Sections | 2 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 341 | 2026-08-17 |  | Voided- Updated drawings received from Carr |  | 2026-08-31 | KPTG-CONTADV-000330 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-11 | KPTG-TRANSMIT-020500 | NA | Trade Partner | O&M WF | 0 | 3 | 0 | NA | APPROVED | 2026-08-11 | WF-006654 | NA | 2026-08-20 |  | as per William advise wf is terminated and 2 of the documents in transmittal placed new work | 2026-08-13 | 2026-08-13 | KPTG-IntCorr-017648 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | HGP-TRANSMIT-000012 | NA | Trade Partner | Loading Dock Windows | 5 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 1698 | 2026-08-18 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-006806 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-11 | ARCST-TRANSMIT-000371 | NA | Trade Partner | C3 Switchroom Upper Gantry - Issued for Construction | 132 | 0 | 0 | NA | APPROVED | 2026-08-11 | WF-006655 | NA | 2026-08-17 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-19 | KETE-TRANSMIT-000031 | NA | Trade Partner | Facade | 67 | 0 | 0 | NA | APPROVED | 2026-01-19 | NA | 838 | 2026-01-22 |  |  | 2026-01-29 | 2026-01-30 | KPTG-TRANSMIT-002629 | Closed | 67 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-11 | Lat-TRANSMIT-000015 | NA | Consultant | M3 Expansion - Landscape Issued For Endorsement Drawings (IFE-1) | 57 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect attachment |  |  | KPTG-TRANSMIT-000902 | Closed | 57 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-11 | NXT-WTRAN-000132 | NA | Client | FIE FOR APPROVAL: DCNEXUS Switchrooms OAF | 0 | 1 | 0 | KPTG-IntCorr-000487 | APPROVED |  | NA | NA |  |  | Uploaded on ACC |  | 2026-08-20 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-11 | NXT-TRANSMIT-000479 | NA | Client | FIE Review - LAI - PDU - FIE Electrical Rev 2 | 2 | 0 | 0 | NA | APPROVED | 2026-08-11 | WF-000197 | NA | 2026-08-24 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-001092 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-11 | ABB-TRANSMIT-000016 | NA | Trade Partner | M3 Stage 6 - LV Switchboards - ABB AU-10026006 - CSMS Points List | 0 | 1 | 0 | KPTG-IntCorr-000483 | APPROVED |  | NA | NA |  |  | No Action Required |  | 2026-08-20 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-11 | ABB-TRANSMIT-000017 | NA | Trade Partner | LV Switchboards - ABB AU-10026006 - Single Line Diagram | 1 | 0 | 0 | KPTG-IntCorr-000483 | APPROVED |  | NA | NA |  |  | No Action Required |  | 2026-08-20 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-11 | 4DW-TRANSMIT-000078 | NA | Consultant | Structural Documentation: Block 1 - PW102, PW104 & PW105 Precast walls issued for Certification. | 5 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 650 | 2026-08-19 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001018 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | VIA Arch-TRANSMIT-000227 | NA | Consultant | Stage 2 Watertanks - Concrete Footing | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, Updated register and distributed |  | 2026-08-11 | KPTG-TRANSMIT-006720 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | VIA Arch-TRANSMIT-000228 | NA | Consultant | S9-11 Signage Package | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed |  | 2026-08-11 | KPTG-TRANSMIT-006725 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | VIA Arch-TRANSMIT-000229 | NA | Consultant | Updated drawings and Interior Schedule | 13 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed |  | 2026-08-11 | KPTG-TRANSMIT-006728 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | VIA Arch-TRANSMIT-000225 | NA | Consultant | M2 S9-S11 Fire Separation & S10 Amendments | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed |  | 2026-08-11 | KPTG-TRANSMIT-006590 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-19 | SKS Tech-TRANSMIT-000130 | NA | Trade Partner | Electrical | 0 | 2 | 0 | NA | APPROVED | 2026-01-19 | WF-000718 | NA | 2026-01-26 |  |  | 2026-02-03 | 2026-02-03 | KPTG-WTRAN-001493 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-11 | LVPG-TRANSMIT-000035 | NA | Trade Partner | LVPG - Stormwater Tech Data Submittals | 0 | 2 | 0 | NA | APPROVED | 2026-08-11 | WF-000794 | NA | 2026-08-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-11 | INTSPN-TRANSMIT-000050 | NA | Trade Partner | Updated L2 plans | 5 | 0 | 0 | NA | APPROVED | 2026-08-11 | WF-000682 | NA | 2026-08-18 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-001639 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-11 | KPTG-IntCorr-001194 | NA | Trade Partner | BG&E - FP1.4 Performance Solution Report | 0 | 1 | 0 | NA | APPROVED | 2026-08-11 | WF-000684 | NA | 2026-08-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-11 | Auspan-TRANSMIT-000125 | NA | Trade Partner | Precast shop drawings for construction. Levels 16, 17. | 16 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Register and Transmit KPTG-TRANSMIT-001553 |  | 2026-08-11 | KPTG-TRANSMIT-001553 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | Nilsen3-TRANSMIT-000091 | NA | Trade Partner | Nilsen Seismic Drawings | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Drawings for information. Updated register and distributed. |  | 2026-08-11 | KPTG-TRANSMIT-006729 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | Tradetec-TRANSMIT-000162 | NA | Trade Partner | TSA - INGROUND - PROPOSED SEWER RELOCATION | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Same drawing has been submitted via Tradetec-TRANSMIT-000163 and in review within ACC |  | 2026-08-11 | KPTG-IntCorr-002113 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | GEMBA-D-TRANSMIT-000012 | NA | Consultant | Stage 2 Water tank structural Raft slab | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawing, updated register and distributed |  | 2026-08-11 | KPTG-TRANSMIT-006719 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | SMEPS-TRANSMIT-000102 | NA | Trade Partner | Sample Submittals for IFC | 0 | 18 | 0 | NA | APPROVED |  | NA | NA |  |  | IFCs, Updated register and distributed |  | 2026-08-11 | KPTG-TRANSMIT-006685 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | DLTS-TRANSMIT-000088 | NA | Trade Partner | S9-Glazing Frame Support-Re IFA Issue | 7 | 0 | 0 | NA | APPROVED | 2026-08-11 | WF-001462 | NA | 2026-08-19 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-006899 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | PROLMC-TRANSMIT-000010 | NA | Trade Partner | Proline Dog Box Shop Drawing IFA submission | 3 | 0 | 0 | NA | APPROVED | 2026-08-11 | WF-001468 | NA | 2026-08-14 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-006928 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-19 | Endfire-TRANSMIT-000054 | NA | Trade Partner | EndFire IFC Drawings | 12 | 0 | 0 | NA | APPROVED | 2026-01-19 | NA | 836 | 2026-01-22 |  |  | 2026-01-22 | 2026-01-22 | KPTG-TRANSMIT-002751 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | DLTS-TRANSMIT-000089 | NA | Trade Partner | S6-Awning-IFC Issue | 47 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, Updated register and distributed. |  | 2026-08-11 | KPTG-TRANSMIT-006732 | Closed | 47 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | SMEPS-TRANSMIT-000103 | NA | Trade Partner | Incorrect Docs | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Document marked as No Longer in Use as requested by Trade Partner |  | 2026-08-11 | KPTG-SADV-007487 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-11 | Auspan-TRANSMIT-000114 | NA | Trade Partner | Precast shop drawings for approval. Level 2 - 3 Columns Drawings | 15 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Document Number of Drawing are incorrect, requested to resubmit-KPTG-SADV-005849 |  | 2026-08-11 | KPTG-SADV-005849 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-11 | ARCH-TRANSMIT-000174 | NA | Consultant | MLC - SPR - ISC - Steel and Facade line update | 4 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 466 | 2026-08-14 |  |  | 2026-08-20 | 2026-08-24 | KPTG-TRANSMIT-003324 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-11 | Auspan-TRANSMIT-000113 | NA | Trade Partner | Precast shop drawings for approval. Stage 2 Premium Precast panels. | 18 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Document Number of Drawing are incorrect, requested to resubmit-KPTG-SADV-005840 |  | 2026-08-11 | KPTG-SADV-005840 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-11 | Auspan-TRANSMIT-000115 | NA | Trade Partner | Precast shop drawings for approval. Stage 2 Premium Precast panels. | 2 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 471 | 2026-08-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-11 | Auspan-TRANSMIT-000115 | NA | Trade Partner | Precast shop drawings for approval. Stage 2 Premium Precast panels. | 3 | 0 | 0 | NA | APPROVED | 2026-08-11 | WF-001098 | NA | 2026-08-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-11 | Auspan-TRANSMIT-000113 | NA | Trade Partner | Precast shop drawings for approval. Stage 2 Premium Precast panels. | 13 | 0 | 0 | NA | APPROVED | 2026-08-11 | WF-001098, | NA | 2026-08-21 |  | WORKFLOW IS COMBINED |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-11 | CAP6-TRANSMIT-000008 | NA | Trade Partner | Samples request for Trim to level 3 spectator Seating and stairs | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Rejected: Document Numbering is incorrect:KPTG-SADV-005843 |  | 2026-08-11 | KPTG-SADV-005843 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-11 | SKS Tech-TRANSMIT-000202 | NA | Trade Partner | HV BLOCK DIAGRAM AS BUILT | 1 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 1326 | 2026-08-14 |  |  | 2026-08-13 | 2026-08-14 | KPTG-TRANSMIT-004262 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-19 | SKS Tech-TRANSMIT-000132 | NA | Trade Partner | Electrical | 0 | 3 | 0 | NA | APPROVED | 2026-01-19 | WF-000719 | NA | 2026-01-22 |  |  | 2026-02-03 | 2026-02-03 | KPTG-TRANSMIT-002658 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-11 | SKS Tech-TRANSMIT-000203 | NA | Trade Partner | Packaged Sub Cs L3 ITP Submittal | 0 | 1 | 0 | NA | APPROVED | 2026-08-11 | WF-001195 | NA | 2026-08-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-11 | KPTG-TRANSMIT-004251 | NA | Trade Partner | Bike Parking Layout - IFA | 1 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-08-11 | KPTG-IntCorr-002055 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-12 | ZIA-TRANSMIT-000077 | NA | Trade Partner | CSMS Cable Schedule | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | fc doc forwarded to all parties |  | 2026-08-12 | KPTG-TRANSMIT-004255 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-12 | Schindle-TRANSMIT-000033 | NA | Trade Partner | Lift reveals - C1 & C2 shop drawing | 1 | 0 | 0 | NA | APPROVED | 2026-08-12 | WF-006656 | NA | 2026-09-15 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-12 | INTRFRM-TRANSMIT-000120 | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 8) | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | WF-000463 | NA | 2026-08-21 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-001841 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-11 | fjc-TRANSMIT-000179 | NA | Consultant | Architecturals - Ground Design Updates Issue 1 | 15 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 737 | 2026-08-15 |  |  | 2026-08-14 | 2026-08-14 | KPTG-SADV-005305 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-11 | fjc-TRANSMIT-000179 | NA | Consultant | Architecturals - Ground Design Updates Issue 1 | 5 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 738 | 2026-08-15 |  |  | 2026-08-14 | 2026-08-14 | KPTG-SADV-005305 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-11 | fjc-TRANSMIT-000179 | NA | Consultant | Architecturals - Ground Design Updates Issue 1 | 0 | 3 | 0 | NA | APPROVED | 2026-08-11 | WF-000898 | NA | 2026-08-19 |  | KPTG-SADV-005273 - There are 4 schedules in total. 1 has been rejected, and the remaining 3 have been processed. | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-002899 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-12 | Entire M-TRANSMIT-000089 | NA | Trade Partner | Mechanical Schematics - IFC | 3 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected: wrong document attached |  | 2026-08-12 | KPTG-TRANSMIT-001795 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-11 | CAP6-TRANSMIT-000007 | NA | Trade Partner | Reviewed products- Bollrds | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected, uncorrect document numbering:KPTG-SADV-005850 |  | 2026-08-11 | KPTG-SADV-005850 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-11-27 | KPTG-IntCorr-003252 | NA | Trade Partner | EHS Roof Safety Tech Data submissions | 0 | 2 | 0 | NA | APPROVED | 2025-11-27 | WF-000624 |  | 2025-12-01 |  |  | 2025-12-02 | 2025-12-02 | KPTG-TRANSMIT-001911 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-19 | SKS Tech-TRANSMIT-000127 | NA | Trade Partner | LEVEL 1 & LEVEL 3 SEISMIC IFA LAYOUTS | 2 | 0 | 0 | NA | APPROVED | 2026-01-19 | NA | 840 | 2026-01-22 |  |  | 2026-01-27 | 2026-01-27 | KPTG-TRANSMIT-002596 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-11 | P & R-TRANSMIT-000105 | NA | Trade Partner | Stage 2 Carpark Exhaust Duct - Updated Penetration Set-Outs (Re-Transmittal) | 1 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 464 | 2026-08-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-11 | JCI-TRANSMIT-000023 | NA | Trade Partner | Request to resubmit: BAS SAT Alarm Changes | 0 | 1 | 0 | NA | APPROVED | 2026-08-11 | WF-000442 | NA | 2026-08-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-12 | TATE_-TRANSMIT-000037 | NA | Trade Partner | Brush Seal Performance | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | WF-000444 | NA | 2026-08-13 |  | WORKFLOW RESUBMITTED |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-12 | L.E.S.-TRANSMIT-000048 | NA | Trade Partner | District Living – Electrical Access Control & Security Sample Submittals – For Approval | 0 | 10 | 0 | NA | APPROVED | 2026-08-12 | WF-001134 | NA | 2026-08-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-12 | L.E.S.-TRANSMIT-000048 | NA | Trade Partner | District Living – Electrical Access Control & Security Technical Data Submittals – For Approval | 0 | 8 | 0 | NA | APPROVED | 2026-08-12 | WF-001135 | NA | 2026-08-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-12 | SPECAUTO-TRANSMIT-000015 | NA | Trade Partner | Modbus RS-485 Cable Approval - 3rd Alternative | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | WF-000464 | NA | 2026-08-21 |  | _ | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-002270 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-12 | SES AU-TRANSMIT-000099 | NA | Trade Partner | HAC TYPICAL ELEVATION COLO 4 & 5 - IFA | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Reject: it needs to be IFC-KPTG-TRANSMIT-001159 |  | 2026-08-12 | KPTG-TRANSMIT-001159 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-12 | ADP-TRANSMIT-000138 | NA | Consultant | ADP MEL4680 - Updated Electrical Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-08-12 | NA | 497 | 2026-08-17 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-001831 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-12 | SMEPS-TRANSMIT-000074 | NA | Trade Partner | Tech Data - Electrical Samples for construction | 0 | 27 | 0 | NA | REJECTED | [5 empty] | Issue with status and revision. |  | 2026-08-12 | KPTG-TRANSMIT-001805 | Closed | 27 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-12 | D&E-TRANSMIT-000308 | SPARK-CRFI-KPG-000470 | Trade Partner | Mechanical Functional Description for approval | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | NA | NA | 2026-08-19 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-19 | VAE-Grp-TRANSMIT-000107 | NA | Trade Partner | Mechanical | 2 | 0 | 0 | NA | APPROVED | 2026-01-19 | NA | 842 | 2026-01-21 |  |  | 2026-02-05 | 2026-02-06 | KPTG-TRANSMIT-002715 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-12 | EFP-TRANSMIT-000039 | NA | Trade Partner | FIRE SERVICES SHOP DRAWINGS | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Drawing status are incorret:KPTG-TRANSMIT-001160 |  | 2026-08-12 | KPTG-TRANSMIT-001160 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-12 | ADP-TRANSMIT-000396 | NA | Consultant | ADP MEL4780 - LV SCCS Report | 0 | 1 | 0 | NA | APPROVED | [5 empty] | IFC - All Parties For distribution |  | 2026-08-12 | KPTG-TRANSMIT-020515 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-12 | SES AU-TRANSMIT-000100 | NA | Trade Partner | HAC TYPICAL ELEVATION COLO 4 & 5-IFC | 1 | 0 | 0 | NA | APPROVED | 2026-08-12 | WF-000445 | NA | 2026-08-14 |  |  | 2026-08-17 | 2026-08-17 | KPTG-TRANSMIT-001172 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-12 | SKS Tech-TRANSMIT-000209 | NA | Trade Partner | Fwd: Clearance Zone Register | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-08-12 | KPTG-TRANSMIT-020519 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-12 | ADP-TRANSMIT-000397 | NA | Consultant | MEL4780 - S4 - Electrical - LAYOUT - SITE IN GROUND - ZONE 2 | 1 | 0 | 0 | NA | APPROVED | 2026-08-12 | NA | 4103 | 2026-08-14 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-12 | Auspan-TRANSMIT-000602 | NA | Trade Partner | Re: Precast shop drawings for approval. Zone 4, 5 level 7 | 4 | 0 | 0 | NA | APPROVED | 2026-08-12 | NA | 1708 | 2026-08-19 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-12 | Altaire-TRANSMIT-000027 | NA | Trade Partner | NEXTDC M2S10 - Shop Drawings (FA-1) (Level 1 + Level 2) | 2 | 0 | 0 | NA | APPROVED | 2026-08-12 | NA | 1706 | 2026-08-19 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-12 | D&E-TRANSMIT-000999 | NA | Trade Partner | Fwd: NXM3S4 - SECURITY GRILLES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | [5 empty] | FOR DISTRIBUTION |  | 2026-08-12 | KPTG-TRANSMIT-020520 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-12 | D&E-TRANSMIT-000309 | SPARK-CRFI-KPG-000470 | Trade Partner | Mechanical Points List - IFC | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | NA | NA | 2026-08-19 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-12 | Nilsen3-TRANSMIT-000252 | NA | Trade Partner | Nilsen clearance zone register | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The document revision and status not matching, |  | 2026-08-12 | KPTG-DA-008087 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-19 | VAE-Grp-TRANSMIT-000108 | NA | Trade Partner | Mechanical | 6 | 0 | 0 | NA | APPROVED | 2026-01-19 | NA | 844 | 2026-01-22 |  |  | 2026-02-05 | 2026-02-06 | KPTG-TRANSMIT-002719 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-12 | ELLISAIR-TRANSMIT-000160 | NA | Trade Partner | LEVEL 2 CHILLER MODULES LOW LEVEL - DUCT & PIPE LAYOUT DRAWING ISSUED FOR APPROVAL. | 1 | 0 | 0 | NA | APPROVED | 2026-08-12 | NA | 1708 | 2026-08-19 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-007180 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-12 | DLTS-TRANSMIT-000091 | NA | Trade Partner | S9-Ground Floor Stairs-IFA Issue | 25 | 0 | 0 | NA | APPROVED | 2026-08-12 | WF-001474 | NA | 2026-08-21 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-007232 | Closed | 25 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-12 | D&E-TRANSMIT-000310 | SPARK-CRFI-KPG-000646 | Trade Partner | Mechanical Topology For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | NA | NA | 2026-08-19 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-001663 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-12 | SMEPS-TRANSMIT-000075 | NA | Trade Partner | Tech Data - SME approved/w comments | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | WF-000466 | NA | 2026-08-21 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-001966 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-12 | ARCH-TRANSMIT-000175 | NA | Consultant | MLC - SPR - ISC - Construction Detail updated | 1 | 0 | 0 | NA | APPROVED | 2026-08-12 | NA | 470 | 2026-08-17 |  |  | 2026-08-27 | 2026-08-28 | KPTG-TRANSMIT-003353 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-12 | SPECAUTO-TRANSMIT-000017 | NA | Trade Partner | Modbus RS-485 Cable Approval - 4th Alternative | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | WF-000467 | NA | 2026-08-21 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-002282 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-12 | Auscool-TRANSMIT-000074 | NA | Trade Partner | Re: Ground Floor - Zone 1 and 3 IFA drawings | 2 | 0 | 0 | NA | APPROVED | 2026-08-12 | NA | 1710 | 2026-08-19 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-12 | D&E-TRANSMIT-001000 | NA | Trade Partner | NXM3S4 - Roof - Mech_Elec Layout - Zones - Issued For Approval | 5 | 0 | 0 | NA | APPROVED | 2026-08-12 | NA | 4106 | 2026-08-18 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-021132 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-12 | 4DW-TRANSMIT-000080 | NA | Consultant | Precast wall penetrations & stair cores - Block 1 | 7 | 0 | 0 | NA | REJECTED | [5 empty] | 4DW-TRANSMIT-000079 Superseded |  | 2026-08-12 | KPTG-TRANSMIT-000923 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-12 | NXT-TRANSMIT-000476-OMM | NA | Client | Barkers Info | 0 | 2 | 0 | NA | APPROVED | 2026-08-12 | NA | 652 | 2026-08-20 |  |  | 2026-08-18 | 2026-08-19 | KPTG-TRANSMIT-001011 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | IVS-TRANSMIT-000316 | NA | Consultant | Stage 4 - Cooling Tower & Chiller Room Zone C1 Package (Construction Issue) | 2 | 0 | 0 | NA | APPROVED | 2026-01-20 |  | 1835 | 2026-01-24 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-012060 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-12 | M.S.-TRANSMIT-000084 | NA | Trade Partner | Updtaed IFC shop drawings for J50 Reception counter | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Revision of drawings are not current-KPTG-SADV-005855 |  | 2026-08-12 | KPTG-SADV-005855 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-12 | HGP-TRANSMIT-000005 | NA | Trade Partner | GL01 Glass sample | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Submission not as per the project requirement/ incorrect document number/title |  | 2026-08-12 | KPTG-DA-000548 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-12 | HGP-TRANSMIT-000006 | NA | Trade Partner | Updated Sample | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document number / Title are not matching with attached document |  | 2026-08-12 | KPTG-CONTADV-000246 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-12 | VIA Arch-TRANSMIT-000230 | NA | Consultant | S11 Level 2 Concrete Profile | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-08-12 | KPTG-TRANSMIT-006760 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-12 | Auspan-TRANSMIT-000600 | NA | Trade Partner | Update IFCed precast shop drawings | 18 | 0 | 18 | KPTG-IntCorr-001249 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001249 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-12 | Auspan-TRANSMIT-000600 | NA | Trade Partner | Update IFCed precast shop drawings | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected -Difference in revision-DRAFT-011397 |  | 2026-08-12 | DRAFT-011397 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-12 | L.E.S.-TRANSMIT-000049 | NA | Trade Partner | Existing building generator relocation shop drawings | 5 | 0 | 0 | KPTG-IntCorr-001174 | APPROVED | 2026-08-14 | NA | 1102 | 2026-08-24 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-003607 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-12 | Auspan-TRANSMIT-000599 | NA | Trade Partner | Precast shop drawings for construction | 3 | 0 | 0 | KPTG-IntCorr-001250 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001250 OK TO IFC-KPTG-TRANSMIT-003222 |  | 2026-08-13 | KPTG-TRANSMIT-003222 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-12 | ASV-TRANSMIT-000081 | NA | Trade Partner | Civil Connections for Garden Bed and Electrical Pit Drainage | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | WF-001479 | NA | 2026-08-21 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-12 | faulk-TRANSMIT-000005 | NA | Trade Partner | Updated SD | 2 | 0 | 0 | NA | APPROVED | 2026-08-12 | NA | 498 | 2026-08-14 |  | Review created for updating the review status. | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-001808 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | IVS-TRANSMIT-000317 | NA | Consultant | Stage 4 - Cooling Tower & Chiller Room Zone C2 & C3 (Certification Issue) | 4 | 0 | 0 | NA | APPROVED | 2026-01-20 |  | 1837 | 2026-01-24 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-012056 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-12 | SMEPS-TRANSMIT-000248 | NA | Trade Partner | ROIP drawings As Built | 22 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | NA |  | 2026-08-12 | NA | Closed | 22 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-12 | SMEPS-TRANSMIT-000249 | NA | Trade Partner | Electrical drawings AB-1 | 20 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | NA |  | 2026-08-12 | NA | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-12 | SMEPS-TRANSMIT-000250 | NA | Trade Partner | Communications Drawings AB-1 | 25 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | NA |  | 2026-08-12 | NA | Closed | 25 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-12 | 4DW-TRANSMIT-000081 | NA | Consultant | Block 1 - 3 Foundation & Ground Level | 22 | 0 | 0 | NA | APPROVED | 2026-08-12 | NA | 654 | 2026-08-20 |  | NA | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-001125 | Closed | 22 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-12 | RDSBIM-TRANSMIT-000027 | NA | Trade Partner | NXGE01 ¦ GROUND FLOOR PARTITION WALL PLAN AND ELEVATIONS | 5 | 0 | 0 | NA | APPROVED | 2026-08-12 | NA | 500 | 2026-08-14 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-001809 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-12 | Entire M-TRANSMIT-000088 | NA | Trade Partner | Roof Mechanical Penetration drawing - RE-IFC | 1 | 0 | 0 | NA | APPROVED | 2026-08-12 | NA | 499 | 2026-08-12 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-001818 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-12 | Civilex-TRANSMIT-000334 | NA | Trade Partner | Stage 2 - sample submission - Linemarking | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | WF-006659 | NA | 2026-08-17 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-020565 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-12 | Civilex-TRANSMIT-000335 | NA | Trade Partner | Stage 2 - sample submission - 7mm HBCE - High bitumen content emulsion for superior performance | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | WF-006660 | NA | 2026-08-18 |  | Terminated as requested by Charlie Johnstone for submitting the updated document. | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-020831 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-12 | G&CHyd-TRANSMIT-000017 | NA | Trade Partner | HYD TEC DATA | 0 | 6 | 0 | NA | APPROVED | 2026-08-12 | WF-001141 | NA | 2026-08-17 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-003579 - 3 with client review | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-12 | INTRFRM-TRANSMIT-000121 | NA | Trade Partner | Geelong Edge - Hydraulic Tech Data (Submission 8) | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | WF-000471 | NA | 2026-08-21 |  |  | 2026-08-17 | 2026-08-17 | KPTG-TRANSMIT-001921 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-21 | RDSBIM-TRANSMIT-000144 | NA | Trade Partner | LINDRUM ¦ BASEMENT LEVEL BLOCK WALL LAYOUT AND ELEVATION | 2 | 0 | 0 | NA | APPROVED | 2026-01-21 |  | 519 | 2026-02-18 |  |  | 2026-02-12 | 2026-02-12 | KPTG-SADV-002842 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-12 | G&CHyd-TRANSMIT-000017 | NA | Trade Partner | HYD DATA | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Incorrect document number/ Revision |  | 2026-08-12 | KPTG-TRANSMIT-003373 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-12 | SMEPS-TRANSMIT-000076 | NA | Trade Partner | Tech Data - Resubmissions | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | WF-000468 | NA | 2026-08-21 |  | only one drawing is completed review remains under review | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-001899 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-12 | Auspan-TRANSMIT-000116 | NA | Trade Partner | Precast shop drawings for approval. Level 2 - 3 Columns Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-08-12 | NA | 473 | 2026-08-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-12 | Auspan-TRANSMIT-000116 | NA | Trade Partner | Precast shop drawings for approval. Level 2 - 3 Columns Drawings | 12 | 0 | 0 | NA | APPROVED | 2026-08-12 | WF-001101 | NA | 2026-08-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-12 | SES AU-TRANSMIT-000001 | NA | Trade Partner | Security Samples - Cable | 0 | 5 | 0 | NA | REJECTED | [5 empty] | Issue with Document number, revision number etc. |  | 2026-08-12 | KPTG-TRANSMIT-001807 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-12 | CAP6-TRANSMIT-000009 | NA | Trade Partner | Samples request for Trim to level 3 spectator Seating and stairs | 0 | 2 | 0 | NA | APPROVED | 2026-08-12 | WF-001103 | NA | 2026-08-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-12 | Carr-TRANSMIT-000085 | NA | Consultant | Terracotta Panel Profile | 1 | 0 | 0 | NA | APPROVED | 2026-08-12 | NA | 343 | 2026-08-18 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-12 | RDSBIM-TRANSMIT-000151 | NA | Trade Partner | MLCSPR ¦ STAGE 2 ¦ RETENTION PLAN AND ELEVATION | 5 | 0 | 0 | KPTG-IntCorr-008682 | APPROVED | 2026-08-13 | NA | 483 | 2026-08-19 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-003317 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-12 | ARCST-TRANSMIT-000380 | NA | Trade Partner | Security Cupboards - Issued for Approval | 29 | 0 | 0 | NA | REJECTED | [5 empty] | The documents number mismatch in the Aconex registers and documents number title mentioned inside the pdf file |  | 2026-08-12 | KPTG-DA-008103 | Closed | 29 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-12 | ARCH-TRANSMIT-000177 | NA | Consultant | MLC - SPR - ISC - Carpark North CPP update | 1 | 0 | 0 | NA | APPROVED | 2026-08-12 | NA | 476 | 2026-08-17 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-003287 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | IVS-TRANSMIT-000318 | NA | Consultant | Stage 4 - Eaves Gutter (Certification Issue) | 1 | 0 | 0 | NA | APPROVED | 2026-01-20 |  | 1840 | 2026-01-24 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-012051 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-12 | VIA Arch-TRANSMIT-000231 | NA | Consultant | S9-S11 Signage Package | 14 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed |  | 2026-08-12 | KPTG-TRANSMIT-006768 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-12 | DLTS-TRANSMIT-000093 | NA | Trade Partner | S11-Glazing Frame Support-IFA Issue | 22 | 0 | 0 | NA | APPROVED | 2026-08-12 | WF-001480 | NA | 2026-08-20 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-007433 | Closed | 22 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-12 | CLADC-TRANSMIT-000003 | NA | Trade Partner | Kattsafe chemset fixing detail tech data | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | WF-001475 | NA | 2026-08-21 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-007267 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-12 | M.2-TRANSMIT-000073 | NA | Trade Partner | Revised Lighting Tech Data | 0 | 24 | 0 | NA | APPROVED | 2026-08-12 | WF-000800 | NA | 2026-08-19 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-12 | Auspan-TRANSMIT-000603 | NA | Trade Partner | Re: Precast shop drawings for construction. Level 4. | 1 | 0 | 0 | KPTG-IntCorr-001251 | APPROVED |  | NA | NA |  |  | IFC - waiting for advise - KPTG-IntCorr-001251 OK TO IFC- KPTG-TRANSMIT-003224 |  | 2026-08-13 | KPTG-TRANSMIT-003224 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-12 | Auspan-TRANSMIT-000604 | NA | Trade Partner | Re: GMAC - L4 Additional precast penetrations | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect revision history - DRAFT-011408 |  | 2026-08-12 | DRAFT-011408 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-12 | TGRF-TRANSMIT-000120 | NA | Trade Partner | Level 2 IFC Plans | 36 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Document Numbering & Drawing status are incorrect:KPTG-SADV-005857 |  | 2026-08-12 | KPTG-SADV-005857 | Closed | 36 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-12 | RDSBIM-TRANSMIT-000097 | NA | Trade Partner | 671 CHP LEVEL 01 CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | NA | APPROVED | 2026-08-12 | NA | 755 | 2026-08-19 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-001567 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-12 | crossfir-TRANSMIT-000032 | NA | Trade Partner | Dry Fire - Ground to Level 02, IFA | 3 | 0 | 0 | NA | APPROVED | 2026-08-12 | NA | 757 | 2026-08-19 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-001719 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-12 | LGCE-TRANSMIT-000080 | NA | Trade Partner | : Ground floor IFC | 1 | 0 | 0 | KPTG-IntCorr-001220 | APPROVED | 2026-08-14 | NA | 768 | 2026-08-20 |  | Tayla to advise KPTG-IntCorr-001220 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-19 | CRSol-TRANSMIT-000078 | NA | Trade Partner | CRS HOT AISLE CONTANMENTS SHOPDRAWINGS for M3S4 Zone C1 Issued for Approval Rev. A | 20 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-TRANSMIT-011695 - some of attached documents ,M3-ARC-CRS-SDRG-C-0401-2401,M3-ARC-CRS-SDRG-C-0401-2411,M3-ARC-CRS-SDRG-C-0401-2421,M3-ARC-CRS-SDRG-C-0401-2431,M3-ARC-CRS-SDRG-C-0401-2441,M3-ARC-CRS-SDRG-C-0401-2451,M3-ARC-CRS-SDRG-C-0401-2461 mentioned project code is incorrect |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-12 | crossfir-TRANSMIT-000033 | NA | Trade Partner | : Dry Fire - L03 to L10, IFA | 2 | 0 | 0 | NA | APPROVED | 2026-08-12 | NA | 759 | 2026-08-19 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-001721 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-12 | CDL-TRANSMIT-000051 | NA | Trade Partner | Epoxy for CDL Dowels | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected: Incorrect Document Numbering:KPTG-SADV-005858 |  | 2026-08-12 | KPTG-SADV-005858 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-12 | Blueprin-TRANSMIT-000007 | NA | Trade Partner | Stage 2 Signage finished art as made | 26 | 0 | 0 | KPTG-IntCorr-008683 | REJECTED | [5 empty] | KPTG-IntCorr-008684: Incorrectly transmitted confirmed by Mr. Jarred: |  | 2026-08-13 | KPTG-SADV-005859 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-12 | ARCH-TRANSMIT-000176 | NA | Consultant | MLC - SPR - ISC - Door Schedule update for OH02 | 1 | 0 | 0 | NA | APPROVED | 2026-08-12 | NA | 478 | 2026-08-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-12 | DLTS-TRANSMIT-000090 | NA | Trade Partner | S11-Pump Module Skating Plates-IFA Issue | 1 | 0 | 0 | NA | APPROVED | 2026-08-12 | WF-001476 | NA | 2026-08-21 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-007324 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-12 | DLTS-TRANSMIT-000092 | NA | Trade Partner | S11-Pump Module Skating Plates-IFA Issue | 2 | 0 | 0 | NA | APPROVED | 2026-08-12 | WF-001476 | NA | 2026-08-21 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-007329 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-12 | Ardon-TRANSMIT-000024 | NA | Trade Partner | Remaining Switchroom Frames | 2 | 0 | 0 | NA | APPROVED | 2026-08-12 | WF-001477 | NA | 2026-08-21 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-006999 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-07 | DLTS-TRANSMIT-000083 | NA | Trade Partner | S11-HV Room-Re-IFA Issue | 1 | 0 | 0 | NA | APPROVED | 2026-08-07 | WF-001438 | NA | 2026-08-18 |  |  | 2026-08-12 | 2026-08-12 | KPTG-TRANSMIT-006759 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-12 | ELLISAIR-TRANSMIT-000159 | NA | Trade Partner | Revised Level 01 Duct & Pipe layout drawings issued for Construction | 3 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-007545 |  | 2026-08-12 | KPTG-SADV-007545 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | SKS Tech-TRANSMIT-000005 | NA | Trade Partner | SKS - Technical Data Submissions 2 | 10 | 0 | 0 | NA | APPROVED | 2026-01-20 | WF-003903 |  | 2026-02-11 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-12 | Archacce-TRANSMIT-000010 | NA | Consultant | NEXTDC M2 Stage 9-11 - Design Acceptance Statement 02 (Rev A) - Stage 10 & Stage 11 for Staged BP | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed |  | 2026-08-12 | KPTG-TRANSMIT-006774 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-12 | Eneraque-TRANSMIT-000061 | NA | Trade Partner | Crane Lift Plan & Calculations - BST Installation - RevB | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required. Updated register. |  | 2026-08-12 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-12 | PROLMC-TRANSMIT-000011 | NA | Trade Partner | Proline M2 Tullamarine Roof Package shop drawings IFA submission | 22 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-007546 |  | 2026-08-12 | KPTG-SADV-007546 | Closed | 22 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-12 | Tradetec-TRANSMIT-000164 | NA | Trade Partner | Combined Services | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed |  | 2026-08-12 | KPTG-TRANSMIT-006775 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-11 | KPTG-TRANSMIT-004252 | NA | Trade Partner | EVAC PLANS D2 | 25 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-08-11 | KPTG-IntCorr-002056 | Closed | 25 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-12 | NUBRIK-FA-SMP-001 - Dima - Teams request | NA | Trade Partner | Tan Brick Sample Submission - Avalanche | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | WF-001147 | NA | 2026-09-03 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-12 | NUBRIK-FA-SMP-002 - Dima - Teams request | NA | Trade Partner | Red Brick Sample Submission - Chapel Red | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | WF-001148 | NA | 2026-09-03 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-12 | NUBRIK-FA-SMP-003 - Dima - Teams request | NA | Trade Partner | Red Brick Sample Submission - Lygon Coffee | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | WF-001149 | NA | 2026-09-03 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-12 | NUBRIK-FA-SMP-004 - Dima - Teams request | NA | Trade Partner | Tan Brick Sample Submission - Spencer Tan | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | WF-001150 | NA | 2026-09-03 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-13 | RDSBIM-TRANSMIT-000300 | NA | Trade Partner | NXM3S4 ¦GROUND FLOOR-C-G-054 ACC WC (RH) FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 4108 | 2026-08-15 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-020944 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-19 | Civilex-TRANSMIT-000175 | NA | Trade Partner | Re: Stage 3 - 22KVA Slimdeck Documentation transmittal | 0 | 3 | 0 | NA | REJECTED | [5 empty] | KPTG-TRANSMIT-011697- The document reference number is missing. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-13 | RDSBIM-TRANSMIT-000299 | NA | Trade Partner | NXM3S4 ¦ LEVEL 01 ¦1-C-1-019 ACC WC (LH) FLOOR FINISHES LAYOUT AND ELEVATION | 1 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 4110 | 2026-08-15 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-12 | fjc-TRANSMIT-000180 | NA | Consultant | Architecturals - Ground Door Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | WF-000900 | NA | 2026-08-19 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-002897 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-12 | fjc-TRANSMIT-000181 | NA | Consultant | Architecturals - RFI Updates (mezz / level 01) | 9 | 0 | 0 | NA | APPROVED | 2026-08-12 | NA | 739 | 2026-08-17 |  | KPTG-SADV-005275 - 1 document rejected because the tittle is incorrect. | 2026-08-18 | 2026-08-18 | KPTG-SADV-005324 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-12 | fjc-TRANSMIT-000181 | NA | Consultant | Architecturals - RFI Updates (mezz / level 01) | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | WF-000905 | NA | 2026-08-20 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-002904 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-12 | NXES-TRANSMIT-000071 | NA | Trade Partner | Nexus Cover Sheet & Legend of Drawings | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001318 - As per direction from Mark, we only update the document register and distribute consultant and trade partner only. | 2026-08-12 | 2026-08-12 | KPTG-IntCorr-001318 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-13 | RDSBIM-TRANSMIT-000298 | NA | Trade Partner | NXM3S4 ¦ LEVEL 01 ¦ C-1-054 CLEANERS FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 4113 | 2026-08-15 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-12 | KPTG-IntCorr-001265 | NA | Trade Partner | HERITAGE WORKFLOW | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | WF-000904 | NA | 2026-08-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-12 | KPTG-IntCorr-001265 | NA | Trade Partner | HERITAGE WORKFLOW | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | WF-000903 | NA | 2026-08-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-12 | KPTG-IntCorr-001265 | NA | Trade Partner | HERITAGE WORKFLOW | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | WF-000902 | NA | 2026-08-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-12 | KPTG-IntCorr-001265 | NA | Trade Partner | HERITAGE WORKFLOW | 0 | 1 | 0 | NA | APPROVED | 2026-08-12 | WF-000901 | NA | 2026-08-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-11-28 | B Smart-TRANSMIT-000028 | NA | Consultant | A13 Series Draft IFC (Full Set) & Ground Level GA (Issued for Information) | 50 | 0 | 0 | NA | APPROVED | 2025-12-01 | WF-000069 | 136 | 2025-12-03 |  | Review void as advised during a meeting with Kapitol DM & PCs |  | 2026-01-21 | NA | Closed | 50 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-02 | KPTG-IntCorr-003394 | NA | Trade Partner | Additional RAW Material Tech Data | 0 | 4 | 0 | NA | APPROVED | 2025-12-02 | WF-000643 |  | 2025-12-09 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | Tradetec-TRANSMIT-000333 | NA | Trade Partner | IFA - Shop Drawing - Stage 4 | 6 | 0 | 0 | NA | APPROVED | 2026-01-20 |  | 1842 | 2026-01-29 |  | The workflow has been terminated as per requested by Charlie- reason - pits are incorrect and need to be updated |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-13 | GunAus-TRANSMIT-000004 | NA | Trade Partner | Drawings for review and approval | 0 | 2 | 0 | NA | APPROVED | 2026-08-13 | WF-000472 | NA | 2026-08-24 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-001968 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-13 | BTWA-TRANSMIT-000097 | NA | Trade Partner | MLC Approved Samples | 0 | 6 | 0 | NA | APPROVED | 2026-08-13 | WF-001105 | NA | 2026-08-18 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003311 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-13 | RDSBIM-TRANSMIT-000082 | NA | Trade Partner | -DISTLV - LEVEL12 CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 1101 | 2026-08-16 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-003443 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-13 | KPTG-TRANSMIT-000928 | NA | Trade Partner | Schindler Northern Office Lift | 5 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 656 | 2026-08-20 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-13 | ACCCA-TRANSMIT-000015 | NA | Trade Partner | STORMWATER PITS FOR APPROVAL | 10 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong Attachment |  | 2026-08-13 | KPTG-TRANSMIT-000934 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-13 | CDL-TRANSMIT-000052 | NA | Trade Partner | Epoxy - CDL Dowels | 0 | 1 | 0 | NA | APPROVED | 2026-08-13 | WF-001106 | NA | 2026-08-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-13 | NXT-TRANSMIT-000483 | NA | Client | FIE Review - Q4/DCN - GLP Boards - FIE Elec Rev 2 | 6 | 0 | 0 | NA | APPROVED | 2026-08-13 | WF-000200 | NA | 2026-08-25 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-001096 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-13 | WilsonPD-TRANSMIT-000170 | NA | Trade Partner | S10 & S11 North and South Facade IFA | 2 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 1710 | 2026-08-20 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-007115 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-13 | M.S.-TRANSMIT-000085 | NA | Trade Partner | Updated IFC J50 Shop Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 478 | 2026-08-18 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-003256 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-02 | VIA Arch-TRANSMIT-000205 | NA | Consultant | Updated drawings for Building Permit | 12 | 0 | 0 | NA | APPROVED | 2026-08-02 | NA | 1586 | 2026-08-13 |  |  | 2026-08-13 | 2026-08-13 | KPTG-DA-004213 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-20 | Normark-TRANSMIT-000013 | NA | Trade Partner | TU01 - Turf sample sheet | 0 | 1 | 0 | NA | APPROVED | 2026-01-28 | WF-000762 |  | 2026-01-30 |  | KPTG-IntCorr-004046: REQUESTED TO GET REVIEWERS |  | 2026-02-13 | KPTG-TRANSMIT-002405 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | VIA Arch-TRANSMIT-000208 | NA | Consultant | Blockwork Peno Details / S9 | 6 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 1596 | 2026-08-13 |  |  | 2026-08-13 | 2026-08-13 | KPTG-DA-004214 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-13 | 4DW-TRANSMIT-000079 | NA | Consultant | Block 1 precast stair core issued for re-certification | 1 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 658 | 2026-08-20 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-001124 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-13 | PROLMC-TRANSMIT-000031 | NA | Trade Partner | Proline Facade Package Shop Drawings IFA | 23 | 0 | 0 | NA | REJECTED | [5 empty] | Revision in history block is duplicated Title inside the drawing and in Aconex seem different Revision inside the drawing and in Aconex seem different Drawing date inside the drawing and Aconex seem different. |  | 2026-08-13 | KPTG-TRANSMIT-001615 | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-13 | SES AU-TRANSMIT-000002 | NA | Trade Partner | Security Samples - Cable | 0 | 4 | 0 | NA | APPROVED | 2026-08-13 | WF-000473 | NA | 2026-08-24 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-002068 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-13 | ELLISAIR-TRANSMIT-000162 | NA | Trade Partner | VRF - Stage 9,10 & 11 | 0 | 1 | 0 | NA | APPROVED | 2026-08-13 | WF-001484 | NA | 2026-08-25 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-13 | Stowe-A-TRANSMIT-000672 | NA | Trade Partner | STOWE - Roof Containment As Builts | 2 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 4481 | 2026-08-19 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-13 | ELLISAIR-TRANSMIT-000165 | NA | Trade Partner | Revised Ground Floor Duct & Pipe layout drawing issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 1712 | 2026-08-20 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-007184 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | Auspan-TRANSMIT-000486 | NA | Trade Partner | Precast shop drawings for approval | 2 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 1720 | 2026-08-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | Auspan-TRANSMIT-000518 | NA | Trade Partner | Precast shop drawings for approval | 3 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 1720 | 2026-08-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-13 | SMEPS-TRANSMIT-000266 | NA | Trade Partner | NEL-CNT-KPG-2990-ELC-SAM-0005,0006,007,0008,0038,0040,0041,0056,0057,0058,0059,0060,0061,0062,0063,0020,0021,0022,0025,0027,0032,0033 | 0 | 23 | 0 | NA | REJECTED | [5 empty] | Originator code is incorrect |  | 2026-08-13 | KPTG-TRANSMIT-001616 | Closed | 23 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-20 | NXES-TRANSMIT-000068 | NA | Trade Partner | Security Layout- IFC | 6 | 0 | 0 | NA | APPROVED | [5 empty] | IFC Drawings: Transmitted to Trade Partners & Consultants | 2026-01-20 | 2026-01-20 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-13 | SMEPS-TRANSMIT-000267 | SPARK-CRFI-KPG-000437 | Trade Partner | NEL-CNT-SME-2990-ELC-SAM-0042, 0043, 0044, 0045, 0046, 0047, 0048, 0049, 0050, 0051, 0052, 0064, 0066, 0067, 0070, 0071, 0072 | 0 | 24 | 0 | NA | APPROVED | 2026-08-13 | NA | NA | 2026-08-20 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-13 | Nilsen3-TRANSMIT-000093 | NA | Trade Partner | Nilsen Sample submissions #6 - IFC | 0 | 8 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected : Cover sheet missing |  | 2026-08-13 | KPTG-SADV-007585 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-13 | Civilex-TRANSMIT-000337 | NA | Trade Partner | Stage 2 - sample submission - The Access Ruby Red brick (Tree rings) | 0 | 1 | 0 | NA | APPROVED | 2026-08-13 | WF-006667 | NA | 2026-08-19 |  |  | 2026-08-31 | 2026-08-31 | Civilex-TRANSMIT-000337 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-13 | ADP-TRANSMIT-000399 | NA | Consultant | ADF MEL4780 - S4 - Updated Electrical Schematic | 1 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 4116 | 2026-08-17 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-020746 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-13 | KPTG-TRANSMIT-020500 | NA | Trade Partner | O&M WF | 0 | 2 | 0 | NA | APPROVED | 2026-08-13 | WF-006666 | NA | 2026-08-13 |  |  |  | 2026-08-27 | KPTG-TRANSMIT-021025 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-13 | CAP6-TRANSMIT-000010 | NA | Trade Partner | Reviewed products- Bollrds | 0 | 1 | 0 | NA | APPROVED | 2026-08-13 | WF-001108 | NA | 2026-08-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | IJF-TRANSMIT-000009 | NA | Trade Partner | Joinery - Prototype Drawings - Rev C2 | 38 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 1724 | 2026-08-20 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003279 | Closed | 38 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-13 | Nilsen3-TRANSMIT-000095 | NA | Trade Partner | Nilsen Sample submissions #12 IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, updated register and distributed |  | 2026-08-13 | KPTG-TRANSMIT-006812 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-08-13 | SMEPS-TRANSMIT-000374 | NA | Trade Partner | 22KV - HV Switchroom Telecommunication Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-08-13 | WF-006669 | NA | 2026-08-26 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-020808 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-13 | VIA Arch-TRANSMIT-000233 | NA | Consultant | M2 - S9 Stair 03 - Issued for Construction (FC-1) | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-08-13 | KPTG-TRANSMIT-006815 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-20 | Highbu-TRANSMIT-000110 | NA | Trade Partner | Updated drawing - Site water supply | 1 | 0 | 0 | NA | APPROVED | [5 empty] | IFC Drawing: Transmitted to Trade partners & Consultants |  | 2026-01-20 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-13 | NXT-TRANSMIT-000486 | NA | Client | Kiosk substation GA 3D S6 - Rev05 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For Distribution |  | 2026-08-13 | KPTG-TRANSMIT-000940 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-13 | Civilex-TRANSMIT-000338 | NA | Trade Partner | Stage 2 - sample submission - 10 mm N L 25_ RAP Asphalt Mix Design | 0 | 1 | 0 | NA | APPROVED | 2026-08-13 | WF-006671 | NA | 2026-08-13 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-020924 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-13 | Tradetec-TRANSMIT-000494 | NA | Trade Partner | IFA - CP 28 | 1 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 4119 | 2026-08-22 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-13 | KPTG-TRANSMIT-001154 | NA | Trade Partner | Energisation Plan - IFC | 0 | 1 | 0 | NA | APPROVED | 2026-08-13 | WF - 000568 | NA | 2026-08-12 |  | NA | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-001158 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-13 | SMEPS-TRANSMIT-000251 | NA | Trade Partner | Electrical drawings AB-1 - SMEPS-TRANSMIT-000249 | 1 | 0 | 0 | NA | Choice 1 |  | NA | NA |  |  | AS BIULT |  | 2026-08-13 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-13 | SMEPS-TRANSMIT-000105 | NA | Trade Partner | 110VDC SYSTEM SCHEMATIC | 1 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 1714 | 2026-08-20 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-13 | D&E-TRANSMIT-001012 | NA | Trade Partner | NXM3S4 - SECURITY GRILLES + Level 1 - CHW & SFN Pipe Layouts - Zone 10 - Issued For Construction | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-13 | KPTG-TRANSMIT-020551 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-13 | D&E-TRANSMIT-001014 | NA | Trade Partner | NXM3S4 - Ground - Builders Works Layout - Zone 1 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-13 | KPTG-TRANSMIT-020553 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-13 | WGAVIC-TRANSMIT-000013 | NA | Consultant | M3 S6 Civil Drawings - Town Planning Issue | 43 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 663 | 2026-08-21 |  |  | 2026-08-18 | 2026-08-19 | NA | Closed | 43 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-20 | ECBS-TRANSMIT-000060 | NA | Trade Partner | Tech Data for AM43 - Trafalgar Access Panel | 0 | 1 | 0 | NA | APPROVED | 2026-01-20 | WF-000736 | NA | 2026-01-23 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-002651 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-07-28 | SMEPS-TRANSMIT-000359 | NA | Trade Partner | 22KV - Lightning protection IFA | 0 | 1 | 0 | NA | APPROVED | 2026-07-28 | WF-006515 | NA | 2026-08-04 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-020558 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-13 | WGAVIC-TRANSMIT-000013-SME | NA | Consultant | M3 S6 Civil Drawings - Town Planning Issue | 43 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 664 | 2026-08-21 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-07-28 | Nilsen3-TRANSMIT-000244 | NA | Trade Partner | Re: M3 Stage-3 HVSB additional signage and safety labels | 0 | 1 | 0 | NA | APPROVED | 2026-07-28 | WF-006522 | NA | 2026-08-05 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-020562 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-07-21 | Nilsen3-TRANSMIT-000235 | NA | Trade Partner | Fwd: M3-HV-NIL-SA-S-0301-0067 - Danger Signage | 0 | 1 | 0 | NA | APPROVED | 2026-07-21 | (WF-006495 | NA | 2026-07-29 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-020570 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-13 | SMEPS-TRANSMIT-000014 | NA | Trade Partner | ELECTRICAL SERVICES - OVERALL INGROUND SITE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 669 | 2026-08-21 |  | NA | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-001063 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-13 | HGP-TRANSMIT-000007 | NA | Trade Partner | sample transmittal | 0 | 5 | 0 | NA | APPROVED | 2026-08-13 | NA | 345 | 2026-08-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-13 | Omnii-TRANSMIT-000008 | NA | Trade Partner | Fire Engineering Performance-Based Design Brief (PBDB) Revision F | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect Document number |  | 2026-08-13 | KPTG-CONTADV-000257 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-13 | SMEPS-TRANSMIT-000015 | NA | Trade Partner | TELECOMMUNICATION SERVICES - OVERALL INGROUND SITE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-08-12 | NA | 672 | 2026-08-21 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-13 | Syfon1-TRANSMIT-000026 | NA | Trade Partner | Syfon Drawings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Same Revision has already been registered and reviewed as well.KPTG-SADV-005879 |  | 2026-08-13 | KPTG-SADV-005879 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-13 | RDSBIM-TRANSMIT-000151 | NA | Trade Partner | MLCSPR ¦ STAGE 2 ¦ RETENTION PLAN AND ELEVATION | 5 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 483 | 2026-08-24 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | ADP-TRANSMIT-000156 | NA | Consultant | S4 ¦ ADP MEL4780 - C1 Block FC Issue | 8 | 0 | 0 | NA | REJECTED | [5 empty] | The revision number is incorrect- KPTG-TRANSMIT-011699 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-13 | SMEPS-TRANSMIT-000016 | NA | Trade Partner | ELECTRICAL SERVICES PIT SCHEDULE (FOA-2) | 1 | 0 | 0 | NA | REJECTED | [5 empty] | under review |  | 2026-08-13 | KPTG-TRANSMIT-000943 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-13 | D&E-TRANSMIT-001015 | NA | Trade Partner | NXM3S4 - Ground & Level 1 - Builders Works Layout Zones - Issued For Construction | 12 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-13 | KPTG-TRANSMIT-020577 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-13 | Baigents-TRANSMIT-000034 | NA | Trade Partner | Block 1 Level 1 Precast Beams -Updated Edge Form Detail | 1 | 0 | 0 | NA | APPROVED | 2026-08-12 | NA | 660 | 2026-08-21 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-000944 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-13 | ACCCA-TRANSMIT-000016 | NA | Trade Partner | STORMWATER PITS FOR APPROVAL | 12 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 674 | 2026-08-21 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001017 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-13 | ABB-TRANSMIT-000018 | NA | Client | LV Switchboards - ABB AU-10026006 - Data Sheet, SLD, GA, Label & Schematics and CRS | 4 | 2 | 0 | KPTG-IntCorr-000500 | APPROVED |  | NA | NA |  |  | No Action Required |  | 2026-08-20 | NA | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-13 | NXT-TRANSMIT-000487 | NA | Client | Barkers Fencing Documentation | 52 | 0 | 0 | NA | REJECTED | [5 empty] | File not Acceptable format, Reply to Originator |  | 2026-08-13 | Awaiting approval | Closed | 52 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-13 | KPTG-TRANSMIT-000936 | NA | Consultant | Roof Steel Drawings for SME review | 14 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 675 | 2026-08-21 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-13 | SEAPBU-TRANSMIT-000008 | NA | Trade Partner | MEL11 COLO5 FAT Reports | 0 | 24 | 0 | NA | APPROVED | 2026-08-13 | WF-000448 | NA | 2026-08-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-13 | PTA-TRANSMIT-000044 | NA | Consultant | Revised Concrete Profile Drawings & Slab Waterproofing Details | 11 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 677 | 2026-08-21 |  | NA | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-000999 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-13 | PTA-TRANSMIT-000045 | NA | Consultant | Amenities in Block 2 - Boundary Update | 2 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 679 | 2026-08-21 |  | NA | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001000 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-20 | Nilsen3-TRANSMIT-000004 | NA | Trade Partner | 12.7 22kV 1 core 500mm² HV Cable Sample | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The document number does not align with the S3 project. - KPTG-TRANSMIT-011700 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-13 | KPTG-TRANSMIT-000937-PTA | NA | Consultant | Arch (Peddle Thorpe) and Facade (TTW) Docs for SME review | 26 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 668 | 2026-08-21 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-001128 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-13 | KPTG-TRANSMIT-000937-DS | NA | Consultant | Arch (Peddle Thorpe) and Facade (TTW) Docs for SME review | 0 | 2 | 0 | NA | APPROVED | 2026-08-13 | NA | 666 | 2026-08-21 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-13 | KPTG-TRANSMIT-000937-TTW | NA | Consultant | Arch (Peddle Thorpe) and Facade (TTW) Docs for SME review | 2 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 670 | 2026-08-21 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-001129 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-13 | Omnii-TRANSMIT-000009 | NA | Consultant | Fire Engineering Performance-Based Design Brief (PBDB) Revision F | 0 | 1 | 0 | NA | APPROVED | 2026-08-13 | NA | 347 | 2026-08-21 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-000308 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-13 | Entire M-TRANSMIT-000091 | NA | Trade Partner | BAS Layout drawings | 8 | 0 | 0 | NA | APPROVED | 2026-08-13 | WF-000449 | NA | 2026-08-18 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-001180 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-13 | Entire M-TRANSMIT-000091 | NA | Trade Partner | BAS Layout drawings | 3 | 0 | 0 | NA | APPROVED | 2026-08-13 | WF-000450 | NA | 2026-08-18 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-001180 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-13 | SES AU-TRANSMIT-000095 | NA | Trade Partner | SCEC SECURITY PANEL ELEVATION AND SETOUTS | 1 | 0 | 0 | NA | APPROVED | 2026-08-13 | WF-000447 | NA | 2026-08-19 |  |  | 2026-08-17 | 2026-08-17 | KPTG-TRANSMIT-001170 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-13 | Auspan-TRANSMIT-000117 | NA | Trade Partner | Precast shop drawings for construction. Geelong Precast. | 23 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Incorrect Drawing status: KPTG-SADV-005881 |  | 2026-08-13 | KPTG-SADV-005881 | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | JCBa-TRANSMIT-000165 | NA | Consultant | : Updated Architectural Documentation - GA Plans, Door Schedule & Door Elevations | 48 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 1715 | 2026-08-17 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-003335 | Closed | 48 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | Nilsen3-TRANSMIT-000006 | NA | Trade Partner | Re: 12.7 22kV 1 core 185mm² Sample | 0 | 1 | 0 | NA | REJECTED | [5 empty] | KPTG-TRANSMIT-011702 - The document number does not align with the S3 project. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | LVPG-TRANSMIT-000046 | NA | Trade Partner | LVPG-HY-TECH-069 - 100mm Stainless Allthrough | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to incorrect document number - DRAFT-011451 |  | 2026-08-13 | DRAFT-011451 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | IJF-TRANSMIT-000006 | NA | Trade Partner | Re Joinery - Prototype Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 1713 | 2026-08-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | JCBa-TRANSMIT-000165 | NA | Trade Partner | Door Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-08-13 | NA | 1717 | 2026-08-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | Auspan-TRANSMIT-000605 | NA | Trade Partner | : Re: Architectural Documentation - Return & Precast Return External Elevations | 7 | 0 | 7 | KPTG-IntCorr-001265 | APPROVED |  | NA | NA |  |  | ifc - Witing for confirmation from Oliver -KPTG-IntCorr-001265 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | Auspan-TRANSMIT-000606 | NA | Trade Partner | Re: Removal of Wet Joint - HB | 20 | 0 | 20 | KPTG-IntCorr-001266 | APPROVED |  | NA | NA |  |  | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001266 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | Auspan-TRANSMIT-000606 | NA | Trade Partner | : Re: Removal of Wet Joint - HB | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to incorrect drawing revision history. DRAFT-011461 |  | 2026-08-13 | DRAFT-011461 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | Auspan-TRANSMIT-000607 | NA | Trade Partner | : Re: Removal of Wet Joint - HB | 1 | 0 | 1 | KPTG-IntCorr-001267 | APPROVED |  | NA | NA |  |  | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001267 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | Auspan-TRANSMIT-000608 | NA | Trade Partner | Update IFCed precast shop drawings. Level 3 | 4 | 0 | 0 | KPTG-IntCorr-001268 | APPROVED |  | NA | NA |  |  | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001268 1 OK TO IFC- KPTG-TRANSMIT-003302 3 Rejected as advised by Kapitol PC. KPTG-IntCorr-001349 |  | 2026-08-24 | KPTG-TRANSMIT-003302 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | Auspan-TRANSMIT-000609 | NA | Trade Partner | : Update IFCed shop drawings. Levels 4, 5. Panels are still the same. Just add note for class 2 finish. | 8 | 0 | 0 | KPTG-IntCorr-001269 | APPROVED |  | NA | NA |  |  | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001269 OK TO IFC: KPTG-TRANSMIT-003304 |  | 2026-08-24 | KPTG-TRANSMIT-003304 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | Auspan-TRANSMIT-000610 | NA | Trade Partner | : Re: Update IFCed precast shop drawings. | 9 | 0 | 9 | KPTG-IntCorr-001270 | APPROVED |  | NA | NA |  |  | ifc - Witing for confirmation from Oliver - KPTG-IntCorr-001270 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-20 | Nilsen3-TRANSMIT-000005 | NA | Trade Partner | 12.7 22kV 1 core 300mm² HV Cable Sample | 0 | 1 | 0 | NA | REJECTED | [5 empty] | KPTG-TRANSMIT-011701- Re: 12.7 22kV 1 core 300mm² HV Cable Sample |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | JCBa-TRANSMIT-000165 | NA | Trade Partner | -Door schedule and elevations. ARC - SME REVIEW | 5 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 1718 | 2026-09-03 |  | ARC - SME REVIEW |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | Auspan-TRANSMIT-000611 | NA | Trade Partner | : Re: GMAC - L4 Additional precast penetrations - Drawing QA error | 3 | 0 | 3 | KPTG-IntCorr-001272 | APPROVED |  | NA | NA |  |  | ifc - Witing for confirmation from Oliver KPTG-IntCorr-001272 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | PCForm-TRANSMIT-000108 | NA | Trade Partner | : Level 2 & 3 propping plans | 6 | 0 | 0 | KPTG-IntCorr-001274 | APPROVED |  | NA | NA |  |  | IFC - Michael to advise - KPTG-IntCorr-001274 Update register - KPTG-IntCorr-001281 |  | 2026-08-14 | KPTG-IntCorr-001281 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-13 | CAP6-TRANSMIT-000011 | NA | Trade Partner | Samples request for Trim to level 3 spectator Seating and stairs | 0 | 7 | 0 | NA | REJECTED | [5 empty] | Rejected: Duplication in the submission:KPTG-SADV-005882 |  | 2026-08-13 | KPTG-SADV-005882 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | Auscool-TRANSMIT-000075 | NA | Trade Partner | : MSSB Load Table & Schematics | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Rejected due to lack of document number -DRAFT-011490 |  | 2026-08-13 | DRAFT-011490 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | M.2-TRANSMIT-000074 | NA | Trade Partner | : Electrical Services - Level 00 External lighting layout | 1 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 1730 | 2026-08-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | M.2-TRANSMIT-000075: | NA | Trade Partner | Electrical Services - B1, Ground and Level 6 lighting layouts | 15 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 1735 | 2026-08-20 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-003353 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | M.2-TRANSMIT-000076 | NA | Trade Partner | : Electrical Services - B1, L00, L02-05, L06 & L07 Power & comms layouts | 25 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 1738 | 2026-08-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | M.2-TRANSMIT-000077 | NA | Trade Partner | Electrical Services - B1-Level 6 Cabletray & Penetration layouts | 25 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 1742 | 2026-08-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-13 | M.2-TRANSMIT-000078 | NA | Trade Partner | : Electrical Services - Level 7 Cabletray & Penetration layouts | 5 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 1733 | 2026-08-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-20 | Nilsen3-TRANSMIT-000008 | NA | Trade Partner | 12.7 22kV 1 core 300mm² Sample Submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The revision number is not mentioned in the document - KPTG-TRANSMIT-011704 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-13 | INGEN3D-TRANSMIT-000241 | NA | Trade Partner | Level 9-10 - PW1023 - Revised IFC (31-07-2026) | 1 | 0 | 0 | KPTG-IntCorr-001193 | APPROVED |  | NA | NA |  |  | register updated - Nich to confirm onward submission |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-13 | G&C-HY-TEC-013 | NA | Trade Partner | SNAP FIRE - CAST IN LOW TOP | 0 | 1 | 0 | NA | APPROVED | 2026-08-13 | WF-001142 | NA | 2026-08-18 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-003590 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-14 | INTRFRM-TRANSMIT-000122 | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 9) | 0 | 1 | 0 | NA | APPROVED | 2026-08-14 | WF-000474 | NA | 2026-08-25 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001995 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-14 | Auspan-TRANSMIT-000613 | NA | Trade Partner | Precast shop drawings for construction. Levels 4, 5 | 39 | 0 | 39 | KPTG-IntCorr-001280 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Oliver advise-KPTG-IntCorr-001280 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-14 | Auspan-TRANSMIT-000613 | NA | Trade Partner | Precast shop drawings for construction. Levels 4, 5 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - Difference in revision and status- DRAFT-011506 |  | 2026-08-14 | DRAFT-011506 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-14 | Auspan-TRANSMIT-000118 | NA | Trade Partner | Precast shop drawings for construction. Geelong precast stage 2. | 21 | 0 | 0 | NA | APPROVED | 2026-08-14 | WF-001110 | NA | 2026-08-19 |  | workflow terminated: consultant review is required:KPTG-SADV-005972,KPTG-SADV-005995 |  | 2026-08-19 | KPTG-SADV-005995 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-14 | ADP-TRANSMIT-000400 | NA | Consultant | ADP MEL4780 - S4 - Updated Electrical Schematic | 1 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 4122 | 2026-08-18 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-14 | SIL-TRANSMIT-000040 | NA | Trade Partner | MEL11 COLO4-5 - PDU FAT Report submission | 0 | 2 | 0 | NA | APPROVED | 2026-08-14 | WF-000452 | NA | 2026-08-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-14 | Rinco-TRANSMIT-000068 | NA | Consultant | Structural updated fence drawing | 1 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 1745 | 2026-08-18 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003273 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-14 | WilsonPD-TRANSMIT-000174 | NA | Trade Partner | Updated siphonic drawings stage 9 | 2 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 1716 | 2026-08-19 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-007119 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2025-12-02 | RDSBIM-TRANSMIT-000193 | NA | Trade Partner | LEVEL 01 COMMON AREA (R107) INTERNAL LAYOUT & ELEVATIONS | 4 | 0 | 0 | NA | APPROVED | 2026-01-16 | NA | 1793 | 2026-01-20 |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-20 | Nilsen3-TRANSMIT-000007 | NA | Trade Partner | 12.7 22kV 1 core 500mm² Sample Submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | KPTG-TRANSMIT-011703- The revision number is not mentioned in the document |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-14 | Entire M-TRANSMIT-000092 | NA | Trade Partner | Fire Matrix Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-08-14 | WF-000453 | NA | 2026-08-19 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-001177 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-14 | HGP-TRANSMIT-000013 | NA | Trade Partner | Loading Dock Frames | 5 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 1718 | 2026-08-21 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-13 | ccair-TRANSMIT-000048 | NA | Trade Partner | Mechanical Services L02 Duct and Pipework Layout IFA [A] | 2 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 764 | 2026-08-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-14 | INTRFRM-TRANSMIT-000123 | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 9), ELC | 0 | 1 | 0 | NA | APPROVED | 2026-08-14 | WF-000475 | NA | 2026-08-25 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001982 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-14 | INTRFRM-TRANSMIT-000123 | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 9), TEL | 0 | 1 | 0 | NA | APPROVED | 2026-08-14 | WF-000476 | NA | 2026-08-25 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-002008 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-14 | Nilsen3-TRANSMIT-000093 | NA | Trade Partner | Nilsen Sample submissions #6 - IFC | 0 | 7 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, updated register and distributed |  | 2026-08-14 | KPTG-TRANSMIT-006824 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-13 | ccair-TRANSMIT-000047 | NA | Trade Partner | Mechanical Services L03 Duct and Pipework Layout IFA [A] | 1 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 762 | 2026-08-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-13 | Jangho-TRANSMIT-000091 | NA | Trade Partner | GRC & GL300 Sample (KPTG-TRANSMIT-001571 | 0 | 1 | 0 | NA | APPROVED | 2026-08-13 | WF-000688 | NA | 2026-08-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-14 | Nilsen3-TRANSMIT-000096 | NA | Trade Partner | Nilsen Sample submissions #6 - IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, updated register and distributed |  | 2026-08-14 | KPTG-TRANSMIT-006827 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-14 | Jangho-TRANSMIT-000311 | NA | Trade Partner | Glass Sample Submission（GL-01 Option 4 | 0 | 1 | 0 | NA | APPROVED | 2026-08-14 | WF-001144 | NA | 2026-09-08 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-20 | Aurecon-TRANSMIT-000032 | NA | Trade Partner | Fwd: Specification - Fire Protection | 0 | 1 | 0 | NA | APPROVED | [5 empty] | For information only |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-14 | Jangho-TRANSMIT-000312 | NA | Trade Partner | Skim Coating Sample Submission" | 0 | 1 | 0 | NA | APPROVED | 2026-08-14 | WF-001145 | NA | 2026-09-08 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-14 | WAM-TRANSMIT-000846 | NA | Consultant | IFC - A12 CSP Level 3 & 4 Updates" | 4 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 1104 | 2026-08-18 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-003535 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-14 | ArcadiaL-TRANSMIT-000008 | NA | Trade Partner | Landscape Architectural - Ground Level DWG Export | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | DWG file for record and register update |  | 2026-08-14 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-14 | SMEPS-TRANSMIT-000077 | NA | Trade Partner | Shop Drawings: Electrical IFC | 7 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected: submitted IFA and IFC in same transmittal |  | 2026-08-14 | KPTG-TRANSMIT-001896 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-14 | BTWA-TRANSMIT-000098 | NA | Trade Partner | MLC Stage 2 - internal TD submission | 0 | 6 | 0 | NA | REJECTED | [5 empty] | Rejected: Document status& Revision are incorrect:KPTG-SADV-005895 |  | 2026-08-14 | KPTG-SADV-005895 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-14 | SMEPS-TRANSMIT-000078 | NA | Trade Partner | Shop Drawings; Coms IFC | 1 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 502 | 2026-08-20 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002175 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-14 | L.E.S.-TRANSMIT-000050 | NA | Trade Partner | District Living – LNT-EL-TEC-093 Mortise Locks – For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-08-14 | WF-001151 | NA | 2026-08-18 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-003609 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-14 | IJF-TRANSMIT-000010 | NA | Trade Partner | Prototype Drawings - Bathroom Laundry NBN Robe Study | 23 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - difference in drawing status- DRAFT-012004 |  | 2026-08-14 | DRAFT-012004 | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-14 | D&E-TRANSMIT-001016 | NA | Trade Partner | Pumps - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-08-14 | WF-006676 | NA | 2026-09-09 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-13 | PROLMC-TRANSMIT-000012 | NA | Trade Partner | Proline M2 Tullamarine Roof Package shop drawings IFA submission | 22 | 0 | 0 | NA | APPROVED | 2026-08-13 | WF-001481 | NA | 2026-08-20 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-20 | Civilex-TRANSMIT-000177 | NA | Trade Partner | Stage 3 - 22KVA Slimdeck Documentation transmittal - Rev B | 0 | 3 | 0 | NA | APPROVED | 2026-01-20 | WF-003907 |  | 2026-02-02 |  |  |  | 2026-01-29 | KPTG-TRANSMIT-012149 | Closed | 3 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-14 | Auspan-TRANSMIT-000615 | NA | Trade Partner | Re: Panel Weight Issue - 2P5065 | 2 | 0 | 0 | KPTG-IntCorr-001283 | APPROVED |  | NA | NA |  |  | IFC - Waiting for Oliver advise-KPTG-IntCorr-001283 Rejected by Kapitol PC. KPTG-SADV-004235 |  | 2026-08-14 | KPTG-SADV-004235 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-14 | NXT-TRANSMIT-001684 | NA | Client | Fwd: ABB-PDUs - AU-10025007 - M3-C-Stg/Ph1 - Test Reports - PDU C11 & 12 (Batch 3.2 & 3.3) | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-14 | KPTG-TRANSMIT-020605 | Open | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-14 | ccair-TRANSMIT-000013 | NA | Trade Partner | Substation Fans and Attenuators for Approval | 0 | 2 | 0 | NA | APPROVED | 2026-08-14 | WF-001152 | NA | 2026-08-19 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-003555 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-13 | Archacce-TRANSMIT-000011 | NA | Consultant | NEXTDC M2 Stage 9-11 - Design Acceptance Statement 02 (Rev B) - Stage 10 & Staged 11 for Staged BP | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required Updated and distributed |  | 2026-08-13 | KPTG-TRANSMIT-006832 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-14 | INTRFRM-TRANSMIT-000124 (ELC) | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 11) | 0 | 1 | 0 | NA | APPROVED | 2026-08-14 | WF-000478 | NA | 2026-08-25 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001986 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-14 | INTRFRM-TRANSMIT-000124 (TEL) | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 11) | 0 | 2 | 0 | NA | APPROVED | 2026-08-14 | WF-000479 | NA | 2026-08-25 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-002007 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-14 | Stowe-A-TRANSMIT-000673 | NA | Trade Partner | STOWE - IFC | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected: inside drawing status error |  | 2026-08-14 | KPTG-TRANSMIT-020606 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-14 | VIA Arch-TRANSMIT-000235 | NA | Consultant | M2 S9 Stair 04 - Issued for Construction (FC-1) | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-08-14 | KPTG-TRANSMIT-006834 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-14 | PFP PL-TRANSMIT-000106 | NA | Trade Partner | Fire Plant Room Additional Wall Penetrations | 1 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 4124 | 2026-08-23 |  | As instructed by Ellie S-Terminated Peno drawings are reviewed by structural engineer through RFI process, |  | 2026-08-20 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-14 | LNCPPL-TRANSMIT-000029 | NA | Trade Partner | Fire Shop Drawings - Site Inground - FC-1 | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected: The previous FOA was rejected, but the FC was submitted. |  | 2026-08-14 | DRAFT-004698 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | NXT-TRANSMIT-001202 / EAEGROUP-TRANSMIT-000060 | NA | Trade Partner | Zone C1 IT Busduct – Shop Drawings | 7 | 0 | 0 | NA | APPROVED | 2026-01-20 | WF-003912 |  | 2026-02-03 |  |  |  | 2026-01-27 | NXT-WTRAN-001588 | Closed | 7 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-14 | Entire M-TRANSMIT-000090 | NA | Trade Partner | Valve & Valve Actuators TD - FOA-2 | 0 | 1 | 0 | NA | APPROVED | 2026-08-14 | WF-000480 | NA | 2026-08-25 |  |  | 2026-08-24 | 2026-08-24 | Entire M-TRANSMIT-000090 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-14 | RBG-TRANSMIT-000011 | NA | Consultant | Crane Base Drawings IFC | 0 | 4 | 0 | NA | APPROVED |  | NA | NA |  |  | Update register only |  | 2026-08-14 | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | WGAVIC-TRANSMIT-000164 | NA | Consultant | M2 - Civil - Final Council and Melbourne Water Reissue - Issued for Construction | 8 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 1687 | 2026-08-14 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-006839 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-13 | ELLISAIR-TRANSMIT-000163 | NA | Trade Partner | Ellis Air - Manufacturer Data Report (MDR) document issued for Approval. | 0 | 1 | 0 | KPTG-IntCorr-002152 | APPROVED | 2026-08-18 | WF-001515 | NA | 2026-08-28 |  | KPTG-IntCorr-002152 |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | WGAVIC-TRANSMIT-000170 | NA | Consultant | M2 - Civil - Council Updates - Issued for Construction | 2 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 1687 | 2026-08-14 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-006843 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-14 | POTTSENG-TRANSMIT-000067 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - DRAINAGE - LEVELS 01-04 - ZONES 1-5 LAYOUTS | 10 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 1747 | 2026-08-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-14 | SMEPS-TRANSMIT-000079 | NA | Trade Partner | Re: Tech Data - 110V Control Cable/ Rod Couplers | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Please note that the documents should normally start with revision FOA-1. However, the submitted documents have been directly issued as FOA-2, and we have not yet received the FOA-1 submission. |  | 2026-08-14 | DRAFT-004701 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | WGAVIC-TRANSMIT-000172 | NA | Consultant | M2 - Civil - Civil Stormwater Details Sheet 03 - Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 1687 | 2026-08-14 |  |  | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-006847 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-13 | VIA Arch-TRANSMIT-000232 | NA | Consultant | M2 S9 - Stair 02 - Issued for Construction (FC-1) | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-DA-004237 |  | 2026-08-13 | KPTG-DA-004237 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-13 | ELLISAIR-TRANSMIT-000164 | NA | Trade Partner | MSSB | 0 | 1 | 0 | NA | APPROVED | 2026-08-13 | WF-001492 | NA | 2026-08-21 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | NXT-TRANSMIT-001203 | NA | Trade Partner | P2671 - NDC M3 Stage 4 - Enclosures - CABLE SCHEDULE AND TERMINATIONS (FC-1) | 1 | 0 | 0 | NA | APPROVED | 2026-01-20 | WF-003909 | NA | 2026-02-04 |  |  |  | 2026-03-06 | KPTG-TRANSMIT-011709 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-14 | SMEPS-TRANSMIT-000080 | NA | Trade Partner | Tech Data - MDB AA/AB | 0 | 2 | 0 | NA | REJECTED | 2026-08-14 | NA | NA |  |  | Please note that the documents should normally start with revision FOA-1. However, the submitted documents have been directly issued as FOA-2,FOA-3 and we have not yet received the FOA-1 submission |  | 2026-08-14 | KPTG-TRANSMIT-001898 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-13 | WilsonPD-TRANSMIT-000172 | NA | Trade Partner | Water Schematic Sheet 1 & 2 IFC | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-007618 |  | 2026-08-13 | KPTG-SADV-007618 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-14 | ELLISAIR-TRANSMIT-000166 | NA | Trade Partner | SFN - IMI Balancing valve | 0 | 1 | 0 | NA | APPROVED | 2026-08-14 | WF-001493 | NA | 2026-08-26 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-007377 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-13 | Nilsen3-TRANSMIT-000094 | NA | Trade Partner | Nilsen Sample submissions #12 IFC | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-002156 |  | 2026-08-13 | KPTG-IntCorr-002156 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-14 | WilsonPD-TRANSMIT-000176 | NA | Trade Partner | Vinyl Floor Waste IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, updated register and distributed |  | 2026-08-14 | KPTG-TRANSMIT-006851 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-14 | ADP-TRANSMIT-000039 | NA | Consultant | ADP MEL3393 - Updated mechanical and fire protection documentation | 3 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 485 | 2026-08-19 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-003289 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-14 | Baigents-TRANSMIT-000035 | NA | Trade Partner | Block 01-Upper East & Lower North Precast Panels Issued for Approval | 40 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 681 | 2026-08-24 |  | NA | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-001102 | Closed | 40 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-14 | Entire M-TRANSMIT-000093 | NA | Trade Partner | External Sensors Elevation drawing IFA | 1 | 0 | 0 | NA | APPROVED | 2026-08-14 | WF-000454 | NA | 2026-08-20 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-001186 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-14 | NXT-TRANSMIT-000490 | NA | Client | FIE Review - Arjay - Wet Fire Protection - FIE Fire Rev 2 | 1 | 0 | 0 | NA | APPROVED | 2026-08-14 | WF-000208 | NA | 2026-08-27 |  |  | 2026-08-28 | 2026-08-31 | KPTG-TRANSMIT-001207 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-14 | BSLBBC-TRANSMIT-000001 | NA | Trade Partner | Level 1 Slim Dek | 6 | 0 | 0 | KPTG-IntCorr-000507 | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-28 | KPTG-TRANSMIT-001174 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | NXT-TRANSMIT-001205 / PenskePS-TRANSMIT-000006 | NA | Trade Partner | M3 STAGE 4 Generator General Arrangement Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-01-20 | WF-003910 |  |  |  |  | 2026-02-06 | 2026-01-30 | NXT-WTRAN-001626 KPTG-TRANSMIT-012222 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-14 | ADP-TRANSMIT-000039 | NA | Consultant | ADP MEL3393 - Updated mechanical and fire protection documentation- | 1 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 487 | 2026-08-19 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003302 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-14 | Stowe-A-TRANSMIT-000675 | NA | Trade Partner | Re: GLP 03 and 04 As-Builts | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Submission with Incorrect Status Incorrect Revision Numbering |  | 2026-08-14 | KPTG-SADV-007299 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-14 | NXT-WTRAN-000133 | NA | Client | Final (WF-000123) FIE FOR APPROVAL: DC NEXUS Switchrooms Architectural Rev.2 | 22 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Uploaded on ACC | 2026-08-14 | 2026-08-14 | KPTG-IntCorr-000509 | Closed | 22 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-14 | INTRFRM-TRANSMIT-000125 | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 12) | 0 | 1 | 0 | NA | APPROVED | 2026-08-14 | WF-000481 | NA | 2026-08-21 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-002278 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-14 | NXT-WTRAN-000134 | NA | Client | Final (WF-000124) FIE FOR APPROVAL: DCNEXUS Switchrooms Electrical Drawings Rev.1 | 21 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Uploaded on Acc |  | 2026-08-14 | KPTG-IntCorr-000510 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-14 | " L.E.S.-TRANSMIT-000051" | NA | Trade Partner | Main Switchboard drawing IFA | 11 | 0 | 0 | NA | REJECTED | [5 empty] | Actual drawing revision and Aconex not matching |  | 2026-08-14 | KPTG-TRANSMIT-003414 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-13 | KPTG-TRANSMIT-002883 | NA | Trade Partner | Interior Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 740 | 2026-08-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-14 | SMEPS-TRANSMIT-000081 | NA | Trade Partner | Tech Data - Lighting Control Functional Description/Vertigo fixings | 0 | 2 | 0 | NA | APPROVED | 2026-08-14 | WF-000482 | NA | 2026-08-21 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-002060 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-14 | SMEPS-TRANSMIT-000376 | NA | Trade Partner | SME IFA Documentation - Lighting Control | 41 | 0 | 0 | NA | REJECTED | [5 empty] | Revision and documents uploaded inappropriately. |  | 2026-08-14 | KPTG-DA-008146 | Closed | 41 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-14 | Stowe-A-TRANSMIT-000676 | NA | Trade Partner | GLPs 09, 10, 13, 14, 19, 20 As-Built Schedules | 0 | 6 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected: Submission with Incorrect Status and Incorrect Revision Numbering |  | 2026-08-14 | KPTG-SADV-007300 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-13 | Ardon-TRANSMIT-000019 | NA | Trade Partner | Revised Level 04 & 05 Door Frame Shop Drawings | 36 | 0 | 0 | NA | APPROVED | 2026-01-21 | WF - 000887, 000888 | NA | 2026-01-28 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-14 | ARCH-TRANSMIT-000178 | NA | Consultant | MLC - SPR - ISC - Wall partition plans and Wall Types drawing update | 6 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 489 | 2026-08-19 |  | 489# is void, consultant wants to upload the latest revision:KPTG-SADV-005987 |  | 2026-08-19 | KPTG-SADV-005987 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-14 | KPTG-TRANSMIT-003235 | NA | Trade Partner | Verification of Details | 6 | 0 | 0 | NA | APPROVED | 2026-08-14 | WF - 001112 | NA | 2026-08-21 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-13 | WilsonPD-TRANSMIT-000171 | NA | Trade Partner | S9 L1, L2, L3 & S11 GF Seismic Design IFI | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For Information drawings. No review required as confirmed byPC |  | 2026-08-13 | KPTG-TRANSMIT-006833 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-14 | Civilex-TRANSMIT-000339 | NA | Trade Partner | Stage 2 - sample submission - Stab sand Mix Design (Pronto) | 0 | 1 | 0 | NA | APPROVED | 2026-08-14 | WF-006678 | NA | 2026-08-21 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-13 | VIA Arch-TRANSMIT-000234 | NA | Consultant | Stage 11 Fuel Room wall penetrations | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed |  | 2026-08-13 | KPTG-TRANSMIT-006854 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-14 | PROLMC-TRANSMIT-000032 | NA | Trade Partner | Proline Facade Package Shop Drawings IFA | 23 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 410 | 2026-08-20 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-14 | RDSBIM-TRANSMIT-000244 | NA | Trade Partner | LEVEL 00 CONCRETE PROFILE PLAN & ELEVATIONS - | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-08-14 | KPTG-TRANSMIT-003122 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-14 | ZIA-TRANSMIT-000152 | NA | Trade Partner | M3S4 CSMS Outstation Location Relocation - FF, FG, GB and GC | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision date |  | 2026-08-14 | KPTG-DA-008150 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-14 | NXT-TRANSMIT-000491 | NA | Client | Doc Remove Confidential Status | 20 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | CAD File - For Information |  | 2026-08-14 | Awaiting approval | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-14 | Stowe-A-TRANSMIT-000678 | NA | Trade Partner | Re: Comms As-Bults | 5 | 0 | 0 | NA | REJECTED | [5 empty] | the Reason for Issued Status seems Incorrect in ACONEX,IFC Rejected drawing submitted for as-built ,Revision number seems mismatch |  | 2026-08-14 | KPTG-SADV-007321 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-20 | Nilsen3-TRANSMIT-000011 | NA | Trade Partner | 12.7 22kV 1 core 185mm² Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-01-20 | WF-003917 |  | 2026-02-03 |  |  |  | 2026-01-29 | KPTG-TRANSMIT-012101 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-14 | SRA48-TRANSMIT-000003 | NA | Trade Partner | Raxtar Hoist H1a+b Tower 4B3a IFC Drawings | 15 | 0 | 0 | NA | REJECTED | [5 empty] | Submitted drawing not matching the project requirement |  | 2026-08-14 | KPTG-TRANSMIT-003442 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-14 | PMT Sec-TRANSMIT-000050 | NA | Trade Partner | Revised Datasheets | 0 | 5 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-08-14 | KPTG-TRANSMIT-001625 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-12 | ccair-TRANSMIT-000046 | NA | Trade Partner | Mechanical Services L01 to 11 Builders works | 3 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 770 | 2026-08-21 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-001716 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-12 | ccair-TRANSMIT-000046 | NA | Trade Partner | Mechanical Services L01 to 11 Builders works | 1 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 771 | 2026-08-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-14 | ADP-TRANSMIT-000139 | NA | Trade Partner | ADP MEL4680 - Electrical Drawings - EL Partial | 5 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 504 | 2026-08-21 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-002024 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-14 | SMEPS-TRANSMIT-000082 | NA | Trade Partner | Tech Data - MDB-AA/AB | 0 | 2 | 0 | NA | APPROVED | 2026-08-14 | WF-000484 | NA | 2026-08-21 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-002087 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-14 | WilsonPD-TRANSMIT-000175 | NA | Trade Partner | Siphonic Drainage Stage 10 & 11 IFC | 8 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 1722 | 2026-08-19 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-007123 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-14 | VERTIV-TRANSMIT-000066 | NA | Trade Partner | NEXT DC GE01_ MATERIAL SUBMISSION _ UPS (FOA-3) | 0 | 1 | 0 | NA | APPROVED | 2026-08-14 | WF-000485 | NA | 2026-08-14 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-002122 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-14 | WilsonPD-TRANSMIT-000177 | NA | Trade Partner | Re: Water Schematic Sheet 1 & 2 IFC | 2 | 0 | 0 | NA | APPROVED | 2026-08-07 | NA | 1724 | 2026-08-19 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-007127 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-20 | RDSBIM-TRANSMIT-000149 | NA | Trade Partner | LEVEL 12 TOWER B PARTITION WALL LAYOUT | 2 | 0 | 0 | NA | APPROVED | 2026-01-21 | WF-000889 | 528 | 2026-01-28 |  |  | 2026-02-02 | 2026-02-02 | KPTG-TRANSMIT-002661 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-14 | ZIA-TRANSMIT-000153 | NA | Trade Partner | M3S4 CSMS Outstation Location Relocation - FF, FG, GB and GC | 3 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 4126 | 2026-08-23 |  | As instructed by Kazimir B - Terminated |  | 2026-08-20 | KPTG-TRANSMIT-020768 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-14 | HDRAus-TRANSMIT-000542 | NA | Trade Partner | M3 SW - Document upload | 1 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 4485 | 2026-08-28 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-020925 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-14 | D&E-TRANSMIT-000311 | SPARK-CRFI-KPG-000540 | Trade Partner | BMS Controller - NIAGRA | 0 | 1 | 0 | NA | APPROVED | 2026-08-14 | WF-000633 | NA | 2026-08-20 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-001664 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-14 | Carr-TRANSMIT-000086 | NA | Consultant | Town Planning Issue Including Prourban Updates | 26 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 349 | 2026-08-21 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-14 | Fredon T-TRANSMIT-000028 | NA | Trade Partner | AV Shop drawing Stage 2 - FRE-AV-SPD-015 | 1 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 491 | 2026-08-24 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-003346 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-14 | Carr-TRANSMIT-000087 | NA | Consultant | Roof Updates | 1 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 352 | 2026-08-21 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-14 | RDSDG-TRANSMIT-000007 | NA | Trade Partner | Shop Drawings - Drainage & Pressure - Block 2 | 2 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 683 | 2026-08-24 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001015 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-14 | NXT-TRANSMIT-000493 | NA | Client | FIE Review - Danfoss - HEX - FIE Mech Rev 3 | 1 | 1 | 0 | NA | APPROVED | 2026-08-14 | WF-000210 | NA | 2026-08-27 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-001087 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-14 | M.2-TRANSMIT-000080 | NA | Trade Partner | Apartment DB Shop Drawings | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected- Difference in document number and incomplete titles - DRAFT-011543 |  | 2026-08-14 | DRAFT-011543 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-14 | Fredon T-TRANSMIT-000029 | NA | Trade Partner | AV Shop drawing Stage 2 - FRE-AV-SPD-012 | 1 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 493 | 2026-08-24 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-003347 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-27 | Nilsen3-TRANSMIT-000010 | NA | Trade Partner | 12.7 22kV 1 core 300mm² Sample Submission rev 1 | 0 | 1 | 0 | NA | APPROVED | 2026-01-20 | WF-003918 |  | 2026-02-03 |  |  |  | 2026-01-29 | KPTG-TRANSMIT-012100 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-14 | Auscool-TRANSMIT-000077 | NA | Trade Partner | : updated document number | 0 | 1 | 0 | KPTG-IntCorr-001282 | APPROVED | 2026-08-27 | WF-000843 | NA | 2026-09-03 |  | Kapitol PC to advise -KPTG-IntCorr-001282 KPTG-IntCorr-001391 - send to Stantec for review. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-14 | Auscool-TRANSMIT-000078 | NA | Trade Partner | updated document number mssb schematics | 0 | 1 | 0 | KPTG-IntCorr-001284 | REJECTED |  | NA | NA |  |  | Kapitol PC to advise KPTG-IntCorr-001284 Rejected to update document type to Tecnical data - DRAFT-011762 |  |  | DRAFT-011762 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-14 | JCBa-TRANSMIT-000166 | NA | Trade Partner | : Re: Updated Architectural Documentation - GA Plans, Door Schedule & Door Elevations | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Native file, updated register only. |  | 2026-08-14 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-14 | NXT-TRANSMIT-000494 | NA | Client | FIE Review - Eaton - UPS - FIE Elec Rev 2 | 4 | 22 | 0 | NA | APPROVED | 2026-08-14 | WF-000211 | NA | 2026-08-27 |  |  | 2026-08-27 | 2026-08-28 | KPTG-TRANSMIT-001179 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-14 | KPTG-TRANSMIT-003235 | NA | Trade Partner | : Re: Balustrade & Screen Shop Drawing Details IFA | 7 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 1751 | 2026-08-21 |  | Revise & Resubmit | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-003368 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-14 | Carr-TRANSMIT-000073 | NA | Consultant | Ground Floor and Upper-Level drawings Issued for Approval | 15 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 351 | 2026-08-21 |  | Review Voided - As discussed with Renee, 5Nos. updated drawings received from Carr. |  | 2026-08-25 | NA | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-14 | INTSPN-TRANSMIT-000053 | NA | Trade Partner | Updated L3 Plans | 5 | 0 | 0 | NA | APPROVED | 2026-08-14 | WF-000699 | NA | 2026-08-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-14 | NXT-TRANSMIT-000495 | NA | Client | FIE Review - Vertiv - CRAC/CDU/FWU FD - FIE Mech Rev 3 | 0 | 3 | 0 | NA | APPROVED | 2026-08-14 | WF-000212 | NA | 2026-08-27 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-14 | IJF-TRANSMIT-000011 | NA | Trade Partner | : Prototype Drawings - bathroom robe study laundry NBN | 23 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update and Transmit as advised by Clare Lu -KPTG-IntCorr-001234 Transmitted - KPTG-TRANSMIT-001591 |  | 2026-08-14 | KPTG-TRANSMIT-001591 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-14 | Fredon T-TRANSMIT-000030 | NA | Trade Partner | AV Shop drawing Stage 2 - FRE-AV-SPD-013 | 1 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 495 | 2026-08-25 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-11-13 | KPTG-IntCorr-002914 | NA | Trade Partner | Syfon samples ¦ WF | 0 | 2 | 0 | NA | APPROVED | 2025-11-13 | WF-000579 |  | 2025-11-17 |  |  | 2025-12-02 | 2025-12-02 | KPTG-TRANSMIT-001917 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-20 | VIA Arch-TRANSMIT-000043 | NA | Consultant | M2 Redesign Concept Issue - Sections, Elevations & GA | 27 | 0 | 0 | NA | APPROVED | 2026-01-21 |  | 206 | 2026-01-28 |  |  |  | 2026-01-23 | KPTG-TRANSMIT-000581 | Closed | 27 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-14 | Fredon T-TRANSMIT-000031 | NA | Trade Partner | AV Shop Drawing Stage 2 - FRE-AV-SPD-014 | 1 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 497 | 2026-08-24 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-003345 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-27 | SMEPS-TRANSMIT-000068 | NA | Trade Partner | STAGE 10 - LEVEL 1 & 2 LIGHTING LAYOUTS | 1 | 0 | 0 | NA | APPROVED | 2026-07-27 | NA | 1534 | 2026-08-13 |  |  | 2026-08-13 | 2026-08-13 | KPTG-SADV-007643 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-14 | HDRAus-TRANSMIT-000543 | NA | Trade Partner | M3 Stage 4 - Document upload - PDF and CAD | 13 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 4128 | 2026-08-21 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-021088 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-14 | VERTIV-TRANSMIT-000067 | NA | Trade Partner | NEXT DC GE01 _ MATERIAL SUBMISSION _ FIRE SUPPRESSION & DETECTION SYSTEM GA DRAWINGS (FOA-2) | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with document inside the document. |  | 2026-08-14 | KPTG-TRANSMIT-001901 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-30 | Nilsen3-TRANSMIT-000065 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 17 | 0 | 0 | NA | APPROVED | 2026-07-30 | NA | 1542 | 2026-08-13 |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-006900 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-14 | ARCH-TRANSMIT-000058 | NA | Consultant | S72 Submission (Town Planning) | 16 | 0 | 0 | NA | REJECTED | [5 empty] | Same revisions of the drawings are already transmitted. |  | 2026-08-14 | KPTG-TRANSMIT-001902 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-14 | Stowe-A-TRANSMIT-000677 | NA | Trade Partner | STOWE - CONTAINMENT AS-BUILTS | 13 | 0 | 0 | NA | REJECTED | [5 empty] | some documents same revision resubmitted again |  | 2026-08-14 | Stowe-A-TRANSMIT-000677 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D9 | 2026-08-14 | HDRAus-TRANSMIT-000018 | NA | Consultant | UPDATED FINISHES SCHEDULE | 0 | 1 | 0 | NA | APPROVED | 2026-08-14 | NA | 1477 | 2026-08-19 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-000067 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-14 | ASV-TRANSMIT-000198 | NA | Trade Partner | Resubmit - Class E Inspection Open Access Cover | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Submitted without updating the previous revision of document. |  | 2026-08-14 | KPTG-SADV-007328 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-21 | KARE-TRANSMIT-000078 | NA | Trade Partner | Revised Light and Power Shop Drawings L9-12 | 16 | 0 | 0 | NA | APPROVED | 2026-01-21 | WF-000890 | 529 | 2026-01-28 |  |  | 2026-02-17 | 2026-02-17 | KPTG-TRANSMIT-002708 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-14 | VIA Arch-TRANSMIT-000236 | NA | Consultant | M2 S9 Stair 01 - Issued for Construction (FC-1) | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-08-14 | KPTG-TRANSMIT-006929 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-14 | VIA Arch-TRANSMIT-000237 | NA | Consultant | M2 S9 Stair 02 - Issued for Construction (FC-2) | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-08-14 | KPTG-TRANSMIT-006932 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-13 | VAE-Grp-TRANSMIT-000179 | NA | Trade Partner | IFC - MECHANICAL - SCHED & TECH SUB - PRIMARY CW PUMP CHANGES + MINOR MCC CORRECTIONS | 0 | 1 | 0 | NA | APPROVED | 2026-08-13 | WF-001196 | NA | 2026-08-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-13 | VAE-Grp-TRANSMIT-000185 | NA | Trade Partner | CSMS Cable Schedule | 0 | 2 | 0 | NA | APPROVED | 2026-08-13 | WF-001197 | NA | 2026-08-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-14 | KPTG-TRANSMIT-004251 | NA | Trade Partner | Bike Parking Layout - IFA | 1 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | NA | 2026-08-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-14 | KPTG-TRANSMIT-004252 | NA | Trade Partner | EVAC PLANS D2 | 25 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | NA | 2026-08-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-14 | PARR-TRANSMIT-000065 | NA | Trade Partner | CSMS Cable Schedule | 0 | 5 | 0 | KPTG-IntCorr-002142 | APPROVED | 2026-08-28 | WF-001236 | NA | 2026-09-11 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-14 | Fredon T-TRANSMIT-000032 | NA | Trade Partner | Rejected: Request for IFA,KPTG-SADV-005923 | 1 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-08-14 | ,KPTG-SADV-005923 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-14 | Fredon T-TRANSMIT-000033 | NA | Trade Partner | AV Shop Drawing Stage 2 - FRE-AV-SPD-005 | 1 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 499 | 2026-08-19 |  | Review voided As per the direction from Ms. Julia , trade is required to submit IFA DRAWINGS DATED: 21.08.2026 |  | 2026-08-21 | KPTG-SADV-006027 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-14 | Fredon T-TRANSMIT-000034 | NA | Trade Partner | AV Shop Drawing Stage 2 - FRE-AV-SPD-006 - FRE-AV-SPD-011 | 5 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 501 | 2026-08-19 |  | Trade is required to submit IFA of all these drawings: Hence Terminate ACC workflow-501# dated 21.08.2026 -KPTG-SADV-006026 |  | 2026-08-21 | KPTG-SADV-006026 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | IVS-TRANSMIT-000319 | NA | Consultant | Stage 4 - Office Canopy (Certification Issue) | 1 | 0 | 0 | NA | APPROVED | 2026-01-20 |  | 1854 | 2026-01-24 |  |  |  | 2026-01-29 | KPTG-TRANSMIT-012129 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-14 | Baigents-TRANSMIT-000036 | NA | Trade Partner | Block 1 Level 1 Precast Beams -Updated Edge Form Detail | 1 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 685 | 2026-08-24 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-001101 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-14 | NXES-TRANSMIT-000072 | NA | Trade Partner | Nexus - Emergency Schedule and Remaining Tech Data Sheets - IFA | 2 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 741 | 2026-08-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-14 | NXES-TRANSMIT-000072 | NA | Trade Partner | Nexus - Emergency Schedule and Remaining Tech Data Sheets - IFA | 0 | 9 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-SADV-005304 - type incorrect | 2026-08-14 | 2026-08-14 | KPTG-SADV-005304 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-14 | KPTG-TRANSMIT-002860 | NA | Trade Partner | Door Frame Drawings For Review | 6 | 0 | 0 | NA | APPROVED | 2026-08-10 | WF-000895 | NA | 2026-08-14 |  | WF-000895 -MARK CREATED THE WF | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-002887 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-14 | KPTG-TRANSMIT-002862 | NA | Trade Partner | Door Frame Drawings For Review | 9 | 0 | 0 | NA | APPROVED | 2026-08-10 | WF-000895 | NA | 2026-08-14 |  | WF created Mark. | 2026-08-14 | 2026-08-14 | KPTG-TRANSMIT-002889 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-14 | KPTG-TRANSMIT-002885 | NA | Trade Partner | Door Frame Drawing Review | 15 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001326 - As per direction from Mark, we transmit to FJC. | 2026-08-14 | 2026-08-14 | KPTG-IntCorr-001326 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-14 | ARCH-TRANSMIT-000179 | NA | Consultant | MLC - SPR - ISC - Updated Room Layout Sheets | 12 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 503 | 2026-08-19 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-003321 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-14 | CraftedS-TRANSMIT-000006 | NA | Trade Partner | Request for Crafted Stainless Practical Completion | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated document Register, Just for information |  | 2026-08-14 | KPTG-SADV-005926 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-14 | TGRF-TRANSMIT-000121 | NA | Trade Partner | Re: Level 2 PT - Shop drawings - IFC | 36 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: All Drawings needs to IFA, not IFC-KPTG-SADV-005927 |  | 2026-08-14 | KPTG-SADV-005927 | Closed | 36 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-14 | Auspan-TRANSMIT-000119 | NA | Trade Partner | Precast shop drawings for construction. Geelong Precast. | 23 | 0 | 0 | NA | APPROVED | 2026-08-14 | WF-001122 | NA | 2026-08-19 |  | workflow terminated: consultant review is required:KPTG-SADV-005994 |  | 2026-08-19 | KPTG-SADV-005994 | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | ADP-TRANSMIT-000156 | NA | Consultant | S4 ADP MEL4780 - C1 Block FC Issue | 2 | 0 | 0 | NA | APPROVED | 2026-01-20 |  | 1848 | 2026-01-24 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-012043 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-14 | Syfon1-TRANSMIT-000027 | NA | Trade Partner | Syfon Drawings Level 1 & 2 | 1 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 505 | 2026-08-25 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-14 | PROLMC-TRANSMIT-000013 | NA | Trade Partner | Proline Box Gutter Shop Drawings Rev 3 submission | 2 | 0 | 0 | NA | APPROVED | 2026-08-14 | WF-001489 | NA | 2026-08-18 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-007227 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-14 | Highbu-TRANSMIT-000161 | NA | Trade Partner | IFC Hydraulic drawings | 10 | 0 | 0 | Kapitol Advice awaits: KPTG-IntCorr-008696 | APPROVED |  | NA | NA |  |  | NEW ACC WORKFLOW STARTED |  | 2026-08-18 | KPTG-IntCorr-008696 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-14 | PROLMC-TRANSMIT-000014 | NA | Trade Partner | Aluminium and Tremco ePoxy sample datasheet submissions | 0 | 2 | 0 | NA | APPROVED | 2026-08-14 | WF-001496 | NA | 2026-08-19 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-14 | Ardon-TRANSMIT-000025 | NA | Trade Partner | Balance of Priority 1 Shop Drawings - Round 2 | 31 | 0 | 0 | NA | APPROVED | 2026-08-14 | WF-001490 | NA | 2026-08-21 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-007241 | Closed | 31 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-14 | NUBRIK-FA-SMP-001 | NA | Trade Partner | Tan Brick Sample Submission - Avalanche | 0 | 1 | 0 | NA | APPROVED | 2026-08-14 | WF-001147 | NA | 2026-09-04 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-14 | NUBRIK-FA-SMP-002 | NA | Trade Partner | Red Brick Sample Submission - Chapel Red | 0 | 1 | 0 | NA | APPROVED | 2026-08-14 | WF-001148 | NA | 2026-09-04 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-14 | NUBRIK-FA-SMP-003 | NA | Trade Partner | Red Brick Sample Submission - Lygon Coffee | 0 | 1 | 0 | NA | APPROVED | 2026-08-14 | WF-001149 | NA | 2026-09-04 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-14 | NUBRIK-FA-SMP-004 | NA | Trade Partner | Tan Brick Sample Submission - Spencer Tan | 0 | 1 | 0 | NA | APPROVED | 2026-08-14 | WF-001150 | NA | 2026-09-04 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-14 | L.E.S.-TRANSMIT-000020 | NA | Trade Partner | Internal Lighting Tech Data Sheets for Review | 0 | 22 | 0 | NA | APPROVED | 2026-08-14 | WF-001153 | NA | 2026-08-19 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | ADP-TRANSMIT-000155 | NA | Consultant | S4 ADP MEL4780 - C1 Block FC Issue | 6 | 0 | 0 | NA | APPROVED | 2026-01-20 |  | 1847 / 1849 / 1850 | 2026-01-24 |  |  |  | 2026-01-29 | KPTG-TRANSMIT-012043 KPTG-TRANSMIT-012110 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-14 | L.E.S.-TRANSMIT-000027 | NA | Trade Partner | Exit and Emergency Data sheets | 0 | 9 | 0 | NA | APPROVED | 2026-08-14 | WF-001154 | NA | 2026-08-19 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-24 | Jangho-TRANSMIT-000192 | NA | Trade Partner | Re: Extrusion color Dulux Electro Medium Bronze Kinetic - Flat（PC-02-Powder of Akzo) | 0 | 1 | 0 | NA | APPROVED | 2026-06-24 | WF-000793 | NA | 2026-07-10 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-002644 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-17 | RDSBIM-TRANSMIT-000301 | NA | Trade Partner | NXM3S4 ¦ GROUND FLOOR-C-G-064 UNISEX WC FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 4131 | 2026-08-19 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-020930 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-17 | Auspan-TRANSMIT-000120 | NA | Trade Partner | Precast shop drawings for construction. Stage 2. Coen Precast | 13 | 0 | 0 | NA | APPROVED | 2026-08-17 | WF-001124 | NA | 2026-08-20 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-003343 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-17 | SMEPS-TRANSMIT-000084 | NA | Trade Partner | Tech Data - 110V Control Cable/ Rod Couplers | 0 | 1 | 0 | NA | APPROVED | 2026-08-17 | WF-000486 | NA | 2026-08-26 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-002016 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-17 | SMEPS-TRANSMIT-000085 | NA | Trade Partner | Tech data - Resubmittal of BTU | 0 | 1 | 0 | NA | APPROVED | 2026-08-17 | WF-000487 | NA | 2026-08-26 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-002103 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-17 | VERTIV-TRANSMIT-000067 | NA | Trade Partner | NEXT DC GE01 _ MATERIAL SUBMISSION _ FIRE SUPPRESSION & DETECTION SYSTEM GA DRAWINGS (FOA-2) | 0 | 1 | 0 | NA | APPROVED | 2026-08-17 | WF-000488 | NA | 2026-08-26 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | ELLISAIR-TRANSMIT-000167 | NA | Trade Partner | Intumescent Dampers | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, updated register and distributed |  | 2026-08-17 | KPTG-TRANSMIT-006938 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-17 | Auspan-TRANSMIT-000616 | NA | Trade Partner | Re: Precast shop drawings for construction. Levels 4, 5 | 9 | 0 | 9 | KPTG-IntCorr-001287 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001287 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-17 | Auspan-TRANSMIT-000617 | NA | Trade Partner | Update IFCed precast shop drawing. There is no change to the panels | 7 | 0 | 7 | KPTG-IntCorr-001288 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001288 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-01-21 | RBG-TRANSMIT-000050 | NA | Consultant | Updated structural drawing S06-00059 to capture minor a certification comment | 119 | 0 | 0 | NA | APPROVED | 2026-01-21 | WF-000135 | 219 | 2026-01-26 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-000353 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-17 | Auspan-TRANSMIT-000617 | NA | Trade Partner | Update IFCed precast shop drawing. There is no change to the panels | 1 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-08-17 | DRAFT-011548 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-17 | Entire M-TRANSMIT-000091 | NA | Trade Partner | Ground floor Mechanical Shop drawings IFC - Ground floor Admin | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected- The drawing does not contain a title block; drawing appears to be incomplete. |  | 2026-08-17 | KPTG-TRANSMIT-001909 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-17 | Auspan-TRANSMIT-000618 | NA | Trade Partner | Update IFCed precast shop drawings | 4 | 0 | 4 | KPTG-IntCorr-001289 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001289 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-08-14 | DI-TRANSMIT-000163 | NA | Trade Partner | Re: B18-1 Updated as issued for construction docs | 5 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-08-14 | DRAFT-010533 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-12 | SMEPS-TRANSMIT-000076 | NA | Trade Partner | Tech Data - Resubmissions | 0 | 2 | 0 | NA | APPROVED | 2026-08-12 | WF-000468 | NA | 2026-08-21 |  |  | 2026-08-17 | 2026-08-17 | KPTG-TRANSMIT-001913 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-17 | Auspan-TRANSMIT-000620 | NA | Trade Partner | Update IFCed precast shop drawings | 2 | 0 | 2 | KPTG-IntCorr-001290 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001290 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-17 | Auspan-TRANSMIT-000121 | NA | Trade Partner | Precast shop drawings for approval. Geelong Precast. Stage 2. | 24 | 0 | 0 | NA | APPROVED | 2026-08-17 | WF-001125 | NA | 2026-08-26 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-003330 | Closed | 24 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-10 | VERTIV-TRANSMIT-000064 | NA | Trade Partner | NEXT DC GE01 _ CALCULATION SUBMISSION _ CABLE SIZING AND VOLTAGE DROP CALCULATION (FOA-3) | 0 | 1 | 0 | NA | APPROVED | 2026-08-10 | WF-000456 | NA | 2026-08-19 |  |  | 2026-08-17 | 2026-08-17 | KPTG-TRANSMIT-001917 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-21 | SMEPS-TRANSMIT-000099 | SPARK-CRFI-KPG-000463 | Trade Partner | PLC Shop drawings for Review | 0 | 1 | 0 | NA | APPROVED | 2026-01-21 | WF-000127 |  | 2026-01-28 |  | KPTG-IntCorr-001345 |  | 2026-02-05 | KPTG-TRANSMIT-000405 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-17 | Entire M-TRANSMIT-000092 | NA | Trade Partner | Roof Mechanical Penetration layout IFC | 1 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 506 | 2026-08-21 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001990 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-17 | JFS-AU-TRANSMIT-000005 | NA | Consultant | Updated Facade Specification | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect document status & dates |  | 2026-08-17 | KPTG-CONTADV-000266 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-17 | RDSBIM-TRANSMIT-000015 | NA | Trade Partner | 303COL ¦ BASEMENT 1-DDA EOT LAYOUT & ELEVATIONS | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Superseded by RDSBIM-TRANSMIT-000017 |  | 2026-08-17 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-17 | RDSBIM-TRANSMIT-000016 | NA | Trade Partner | 303COL ¦ GROUND FLOOR CPP ¦ IFR | 3 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 354 | 2026-08-23 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-000310 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-17 | RDSBIM-TRANSMIT-000017 | NA | Trade Partner | 303COL ¦ BASEMENT 1-DDA EOT LAYOUT & ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 361 | 2026-08-27 |  | Email has been sent to Renne & Oliver as advised. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-17 | Entire M-TRANSMIT-000093 | NA | Trade Partner | Ground floor Mechanical Shop drawings IFC - Ground floor Admin- Re-issue | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected: The latest revision of the document available with us is Rev. FOA-1 which is reviewed with status Rejected.they submitted FC revision |  | 2026-08-17 | DRAFT-004728 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | VIA Arch-TRANSMIT-000221 | NA | Consultant | M2S9 - Window Elevation Updates | 1 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1736 | 2026-08-24 |  |  | 2026-08-18 | 2026-08-18 | KPTG-DA-004263 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | VIA Arch-TRANSMIT-000222 | NA | Consultant | M2 S9 - WINDOW DETAILS - SHEET 3 REVISION - IFBP | 2 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1738 | 2026-08-24 |  |  | 2026-08-18 | 2026-08-18 | KPTG-DA-004265 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | VIA Arch-TRANSMIT-000223 | NA | Consultant | Updated Elevations | 5 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1741 | 2026-08-24 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-007341 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-17 | INTERSIG-TRANSMIT-000013 | NA | Trade Partner | Wayfinding IFC documentation | 1 | 0 | 0 | NA | APPROVED | 2026-08-17 | WF - 001127 | NA | 2026-08-21 |  | NA | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-003258 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-21 | SMEPS-TRANSMIT-000100 | SPARK-CRFI-KP-000464 | Trade Partner | Shop drawings - Communication Cabinets Review | 0 | 1 | 0 | NA | APPROVED | 2026-01-21 |  |  | 2026-01-28 |  | KPTG-IntCorr-001347 |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-17 | ADP-TRANSMIT-000401 | NA | Consultant | ADP MEL4780 - LV SCCS Report | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-17 | KPTG-TRANSMIT-020609 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-11 | INTRFRM-TRANSMIT-000119 | NA | Trade Partner | Comms & Elec Tech Data (Submission 7) | 0 | 2 | 0 | NA | APPROVED | 2026-08-17 | WF-000459 | NA | 2026-08-17 |  |  |  | 2026-08-17 | KPTG-TRANSMIT-001925 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-17 | SMEPS-TRANSMIT-000375 | NA | Trade Partner | C1 - telecommunication drawings | 3 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 4133 | 2026-08-26 |  | WF terminated |  | 2026-08-21 | KPTG-TRANSMIT-020822 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-17 | Jangho-TRANSMIT-000314 | NA | Trade Partner | Facade Thermal Report Submission Requirements | 0 | 1 | 0 | NA | APPROVED | 2026-08-17 | WF-001156 | NA | 2026-08-26 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-003623 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | VIA Arch-TRANSMIT-000224 | NA | Consultant | Updated drawings | 14 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1743 | 2026-08-24 |  |  | 2026-08-26 | 2026-08-26 | KPTG-DA-004381 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-17 | Entire M-TRANSMIT-000094 | NA | Trade Partner | Mechanical Security Grille Details | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | The document number is incorrect and there no previous revision and they submitted FC documents. |  | 2026-08-17 | DRAFT-004732 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-17 | SMEPS-TRANSMIT-000268 | NA | Trade Partner | NEL-CNT-KPG-2990-ELC-SAM-0001,0005,0006,0007,0008,0018,0020,0021,0022,0025,00027, 0032, 0033, 0034, 0038, 0039, 0040, 0041,0056,0057,0058,0059,0060,0061,0062,0063 | 0 | 23 | 0 | NA | REJECTED | [5 empty] | Document originator code is incorrect |  | 2026-08-17 | KPTG-TRANSMIT-001628 | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | VIA Arch-TRANSMIT-000225 | NA | Consultant | M2 S9-S11 Fire Separation & S10 Amendments | 5 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1745 | 2026-08-24 |  |  | 2026-08-26 | 2026-08-26 | KPTG-DA-004385 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-17 | Auspan-TRANSMIT-000123 | NA | Trade Partner | Precast shop drawings for approval. Stage 2. Coen Precast | 1 | 0 | 0 | NA | APPROVED | 2026-08-17 | WF-001126 | NA | 2026-08-26 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-003322 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-21 | SMEPS-TRANSMIT-000101 | SPARK-CRFI-KPG-000465 | Trade Partner | Distribution Boards - DB-06(A) DB-07(A) DB-10(A) DB-12(A) DB-14(A) DB-13(B) DB-15(B) | 0 | 1 | 0 | NA | APPROVED | 2026-01-21 | WF-000129 |  | 2026-01-28 |  | KPTG-IntCorr-001350 |  | 2026-02-05 | KPTG-TRANSMIT-000406 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-17 | SMEPS-TRANSMIT-000083 | NA | Trade Partner | Re Shop Drawings Electrical IFC | 2 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 508 | 2026-08-28 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-002135 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | Eneraque-TRANSMIT-000062 | NA | Trade Partner | Flange Data Sheet | 0 | 1 | 0 | NA | APPROVED | 2026-08-17 | WF-001505 | NA | 2026-08-27 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-007449 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-17 | Auspan-TRANSMIT-000122 | NA | Trade Partner | Precast shop drawings for approval. Geelong Precast. Stage 2. | 2 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 507 | 2026-08-26 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-17 | WGAVIC-TRANSMIT-000014 | NA | Consultant | M3 S6 and S7 Stormwater Management Plan - Issued for Information | 0 | 1 | 0 | NA | APPROVED | 2026-08-17 | NA | 687 | 2026-08-21 |  | NA | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-001141 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-17 | D&E-TRANSMIT-001018 | NA | Trade Partner | NXM3S4 - Ground & Level 1 - CHW Pipe Layout / Industrial Water Tank & Builders Works Layouts - Issued For Construction | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | FOR DISTRIBUTION |  | 2026-08-17 | KPTG-TRANSMIT-020646 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-17 | Auspan-TRANSMIT-000621 | NA | Trade Partner | Update IFCed precast shop drawings | 3 | 0 | 3 | KPTG-IntCorr-001291 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001291 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-17 | D&E-TRANSMIT-001017 | NA | Trade Partner | Mechanical O&M Manual Draft - Issued for Review | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect document and status |  | 2026-08-17 | KPTG-DA-008155 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-17 | Stowe-A-TRANSMIT-000679 | NA | Trade Partner | STOWE - CONTAINMENT AS-BUILTS | 4 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | #4489 | 2026-08-28 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-17 | SMEPS-TRANSMIT-000086 | NA | Trade Partner | Data - Containment | 0 | 1 | 0 | NA | APPROVED | 2026-08-17 | WF-000491 | NA | 2026-08-28 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-002241 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-17 | SMEPS-TRANSMIT-000087 | NA | Trade Partner | Data - Crac Isolators | 0 | 1 | 0 | NA | APPROVED | 2026-08-17 | WF-000492 | NA | 2026-08-28 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-002044 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-21 | WilsonPD-TRANSMIT-000143 | SPARK-CRFI-KPG-000387 | Trade Partner | Rain Harvesting Tank for Review REV2 | 0 | 1 | 0 | NA | APPROVED | 2026-01-21 | WF-000135 |  | 2026-01-28 |  | KPTG-IntCorr-001363 | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-000473 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-17 | SMEPS-TRANSMIT-000088 | NA | Trade Partner | data - L2 L1 Lighting | 0 | 2 | 0 | NA | APPROVED | 2026-08-17 | WF-000493 | NA | 2026-08-28 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002179 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | WSP ANZ-TRANSMIT-000100 | NA | Consultant | WSP Issued for Building Permit Documents - (Mechanical, CSM, Fire, Hydraulic and Telecomms) | 20 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1746 | 2026-08-24 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-007084 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-17 | RDSBIM-TRANSMIT-000099 | NA | Trade Partner | 671CHP ¦ LEVEL 04 CONCRETE PROFILE KEYPLAN AND SECTION | 3 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 775 | 2026-08-25 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-001709 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-17 | ZIA-TRANSMIT-000154 | NA | Trade Partner | M3S4 CSMS OS Location Roof Level Zone C1, C2, C3 with OS-FI & OS-FJ New Location | 3 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 4136 | 2026-08-21 |  | As instructed by Kazimir - Terminated |  | 2026-08-18 | KPTG-TRANSMIT-020659 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-17 | Stowe-A-TRANSMIT-000681 | NA | Trade Partner | STOWE - DH 5 CONTAINMENT ASBUILT | 1 | 0 | 0 | NA | REJECTED | [5 empty] | the submitted revision is already received in previous transmittal and completed review status as approved. Kindly update revision number and resubmit the transmittal and the earliest |  | 2026-08-17 | KPTG-SADV-007333 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-17 | ADP-TRANSMIT-000402 | NA | Consultant | ADP MEL4780 - M3 Stage 4 Updated Hydraulic Drawings | 22 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 4138 | 2026-08-19 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-020904 | Closed | 22 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-17 | RDSBIM-TRANSMIT-000100 | NA | Trade Partner | 671CHP ¦ LEVEL 02 CONCRETE PROFILE PLAN AND SECTION | 3 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 777 | 2026-08-24 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-001603 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-17 | INTRFRM-TRANSMIT-000126 | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 13) | 0 | 1 | 0 | NA | APPROVED | 2026-08-17 | WF-000494 | NA | 2026-08-28 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-002228 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-17 | Stowe-A-TRANSMIT-000680 | NA | Trade Partner | Comms As-Bults | 4 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | #4487 | 2026-08-28 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-17 | LGCE-TRANSMIT-000081 | NA | Trade Partner | SLD and Comms Schematic | 2 | 0 | 0 | KPTG-IntCorr-001247 | APPROVED | 2026-08-18 | NA | 783 | 2026-08-26 |  | IFC - Waiting for Tayla advise- KPTG-IntCorr-001247 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-11-24 | WDes-TRANSMIT-000051 | NA | Consultant | Steelwork - Construction Issue | 21 | 0 | 0 | NA | APPROVED | 2025-11-25 | WF-000782 | 479 | 2025-12-03 | 0 |  | 2025-12-03 | 2025-12-03 | KPTG-DA-002200 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-21 | Auspan-TRANSMIT-000053 | NA | Trade Partner | Precast marking plan MB101. | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect drawing status. KPTG-SADV-000647. |  | 2026-01-21 | KPTG-SADV-000647 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | WSP ANZ-TRANSMIT-000100 | NA | Consultant | WSP Issued for Building Permit Documents - (Mechanical, CSM, Fire, Hydraulic and Telecomms) | 50 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1749 | 2026-08-24 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-007102 | Closed | 50 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | WSP ANZ-TRANSMIT-000100 | NA | Consultant | WSP Issued for Building Permit Documents - (Mechanical, CSM, Fire, Hydraulic and Telecomms) | 9 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1750 | 2026-08-24 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-007106 | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-08-17 | VIA Arch-TRANSMIT-000033 | NA | Trade Partner | Fwd: 22kV Amenities Drawing Update | 2 | 0 | 0 | KPTG-TRANSMIT-020641 | APPROVED | 2026-08-18 | WF-006697 | NA | 2026-08-26 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | WSP ANZ-TRANSMIT-000100 | NA | Consultant | WSP Issued for Building Permit Documents - (Mechanical, CSM, Fire, Hydraulic and Telecomms) | 25 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1747 | 2026-08-24 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-007088 | Closed | 25 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-17 | SIL-TRANSMIT-000010 | NA | Trade Partner | submission of drawings Issued for Construction | 0 | 2 | 0 | NA | APPROVED | 2026-08-17 | WF-000495 | NA | 2026-08-17 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-002107 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | WSP ANZ-TRANSMIT-000100 | NA | Consultant | WSP Issued for Building Permit Documents - (Mechanical, CSM, Fire, Hydraulic and Telecomms) | 33 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1748 | 2026-08-24 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-007092 | Closed | 33 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | WSP ANZ-TRANSMIT-000102 | NA | Consultant | Updated - WSP Mechanical Services Specification | 0 | 1 | 0 | NA | APPROVED | 2026-08-17 | NA | 1752 | 2026-08-24 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-007111 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | WSP ANZ-TRANSMIT-000103 | NA | Consultant | Reissue - WSP Issued for Building Permit Documents - (Fire & Hydraulic Services) | 6 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1747 | 2026-08-24 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-007088 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-17 | Axiom-TRANSMIT-000021 | NA | Trade Partner | Building A Level 1 to level 22 Setout Plans - Issued For Approval | 22 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1111 | 2026-08-26 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-003538 | Closed | 22 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | WSP ANZ-TRANSMIT-000103 | NA | Consultant | Reissue - WSP Issued for Building Permit Documents - (Fire & Hydraulic Services) | 3 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1748 | 2026-08-24 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-007092 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-21 | Auspan-TRANSMIT-000054 | NA | Trade Partner | Update precast dowel layout for zone 1, 2. | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect drawing status. KPTG-SADV-000646 |  | 2026-01-21 | KPTG-SADV-000646 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-17 | SIL-TRANSMIT-000011 | NA | Trade Partner | Fwd: Manual and Datasheet - isssued for information | 0 | 2 | 0 | NA | APPROVED | 2026-08-17 | WF-000497 | NA | 2026-08-28 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-17 | ADP-TRANSMIT-000140 | NA | Trade Partner | ADP MEL4680 - Updated Hydraulic Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 510 | 2026-08-28 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-002003 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-17 | NXT-TRANSMIT-001685 | NA | Consultant | M3 Stage 2 Building B Arc Flash Analysis Updated Report | 0 | 1 | 0 | NA | APPROVED | 2026-08-17 | NA | 4491 | 2026-08-20 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-020885 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | WilsonPD-TRANSMIT-000178 | NA | Trade Partner | External Tank Farm Layouts for Approval | 3 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1754 | 2026-08-24 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-007259 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | WilsonPD-TRANSMIT-000179 | NA | Trade Partner | External Tank Farm Layouts IFA pt.2 | 4 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1756 | 2026-08-24 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-007263 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-17 | ZIA-TRANSMIT-000155 | NA | Trade Partner | M3 S4 SLA & DP SENSOR LOCATION DRAWINGS WITH COMMS TRAY UPDATE | 11 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 4140 | 2026-08-21 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-17 | Axiom-TRANSMIT-000020 | NA | Trade Partner | Axiom Design Drawings - Issued For Approval | 15 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1112 | 2026-08-26 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-003613 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-17 | ARCST-TRANSMIT-000382 | NA | Trade Partner | Secure Corridor Bridge - Issued For Construction | 12 | 0 | 0 | NA | APPROVED | 2026-08-17 | WF-006690 | NA | 2026-08-21 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | TTW-TRANSMIT-000023 | NA | Consultant | Facade F3P1 weatherproofing performance solution Update | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For Information. Updated register. |  | 2026-08-17 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | TTW-TRANSMIT-000024 | NA | Consultant | Facade F3P1 weatherproofing performance solution Update- Markup update | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed |  | 2026-08-17 | KPTG-TRANSMIT-006962 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-21 | Auspan-TRANSMIT-000055 | NA | Trade Partner | Precast shop drawings for construction | 2 | 0 | 0 | NA | APPROVED | 2026-01-21 | WF-000140 | 269 | 2026-01-27 |  |  |  | 2026-02-03 | KPTG-TRANSMIT-000515 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | RDSBIM-TRANSMIT-000021 | NA | Trade Partner | GROUND FLOOR RCP LAYOUT | 5 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1757 | 2026-08-22 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | DLTS-TRANSMIT-000094 | NA | Trade Partner | S9-Glazing Frame support-IFA Issue | 7 | 0 | 0 | KPTG-IntCorr-002171 | APPROVED |  | NA | NA |  |  | Updated drawings received on DLTS-TRANSMIT-000099 |  | 2026-08-20 | NA | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | Ardon-TRANSMIT-000027 | NA | Trade Partner | Door Hardware Tech Data | 0 | 26 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-007652 Need to update documents |  | 2026-08-17 | KPTG-SADV-007652 | Closed | 26 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | Ardon-TRANSMIT-000026 | NA | Trade Partner | Re-submission of Ground Level Shop Drawings - Round 2 | 17 | 0 | 0 | NA | APPROVED | 2026-08-17 | WF-001506 | NA | 2026-08-26 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-007445 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | VIA Arch-TRANSMIT-000239 | NA | Consultant | S9-S11 Door Schedules | 9 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed |  | 2026-08-17 | KPTG-TRANSMIT-006935 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-17 | LANSA-TRANSMIT-000116 | NA | Trade Partner | Hydraulic Reticulation Schematics | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  |  | KPTG-TRANSMIT-003239 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-18 | KALLIBRE-TRANSMIT-000023 | NA | Trade Partner | IFC - Drying Racks | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | WF - 001133 | NA | 2026-08-24 |  | NA | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003252 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-17 | RDSBIM-TRANSMIT-000098 | NA | Trade Partner | : 671CHP ¦ LEVEL 04 CONCRETE PROFILE KEYPLAN AND SECTION | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Transmittal Is superseded by RDSBIM-TRANSMIT-000099 |  | 2026-08-17 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-17 | Auspan-TRANSMIT-000619 | NA | Trade Partner | : Precast shop drawings for approval. Level 7 zone 4, 5. | 51 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 1754 | 2026-08-25 |  | IFA - ACC issues, cannot capture title |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-17 | INDS-TRANSMIT-000061 | NA | Trade Partner | : Wet Fire - Level 2 | 5 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 1758 | 2026-08-25 |  | ACC issues cannot capture title. 18/8/2026 0 workflow initiated. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-21 | Auspan-TRANSMIT-000056 | NA | Trade Partner | Resubmit shop drawings for approval | 3 | 0 | 0 | NA | APPROVED | 2026-01-21 | WF-000141 | 271 | 2026-01-27 |  |  |  | 2026-02-03 | KPTG-TRANSMIT-000516 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-17 | INDS-TRANSMIT-000062: | NA | Trade Partner | Wet Fire - Level 3 | 5 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 1762 | 2026-08-26 |  | ACC issues, cannot capture title |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-17 | INDS-TRANSMIT-000060 | NA | Trade Partner | : Wet Fire - Level 2 | 5 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Transmittal superseded - by INDS-TRANSMIT-000061 |  | 2026-08-17 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | PFP PL-TRANSMIT-000032 | NA | Trade Partner | Hydrant System Most Remote Calc | 0 | 1 | 0 | NA | APPROVED | 2026-08-17 | WF-001511 | NA | 2026-08-28 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | SMEPS-TRANSMIT-000106 | NA | Trade Partner | Lighting IFC SA | 0 | 10 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC documents, Updated register and distributed |  | 2026-08-17 | KPTG-TRANSMIT-006945 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-17 | Axiom-TRANSMIT-000022 | NA | Trade Partner | Building B Level 1 to level 19 Setout Plans - Issued For Approval | 19 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1107 | 2026-08-26 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003529 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-17 | RDSBIM-TRANSMIT-000083 | NA | Trade Partner | Axiom Design Drawings - Issued For Approval | 7 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1109 | 2026-08-26 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-17 | ccair-TRANSMIT-000016 | NA | Trade Partner | Heat Load Calculation - IFC | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-08-17 | KPTG-TRANSMIT-003454 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-17 | L.E.S.-TRANSMIT-000052 | NA | Trade Partner | Main Switchboard Drawing IFA | 11 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1114 | 2026-08-26 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-003666 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-17 | Jangho-TRANSMIT-000313 | NA | Trade Partner | Curtain Wall draft test report | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-08-17 | KPTG-TRANSMIT-003451 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-17 | Jangho-TRANSMIT-000315 | NA | Trade Partner | Axiom Design Drawings - Issued For Approval | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-08-17 | KPTG-TRANSMIT-003452 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-21 | Auspan-TRANSMIT-000043 | NA | Trade Partner | Updated DG301 | 1 | 0 | 0 | NA | APPROVED | 2026-01-21 | WF-000142 | 273 | 2026-01-27 |  |  |  | 2026-02-03 | KPTG-TRANSMIT-000517 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-17 | L.E.S.-TRANSMIT-000053 | NA | Trade Partner | Load Center Data sheet and drawing IFA | 6 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-08-17 | KPTG-TRANSMIT-003453 | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-17 | ccair-TRANSMIT-000014 | NA | Trade Partner | AC Unit Schedule for Approval | 0 | 1 | 0 | KPTG-IntCorr-001206 | APPROVED | 2026-08-19 | WF-001173 | NA | 2026-08-27 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-003589 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-17 | ccair-TRANSMIT-000015 | NA | Trade Partner | Mechanical Builderworks Layouts IFA - Levels 5, 6 and 7 to 10 | 3 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1116 | 2026-08-26 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-003681 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | SMEPS-TRANSMIT-000107 | NA | Trade Partner | S11 Level 01 Containment IFA | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-007654 |  | 2026-08-17 | KPTG-SADV-007654 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-18 | SWIFEN-TRANSMIT-000002 | NA | Trade Partner | Water Meter Fence - Next DC | 3 | 0 | 0 | NA | REJECTED | [5 empty] | SUBMITTED AS COMBINED FILE HENCE REJECTED. |  | 2026-08-18 | KPTG-TRANSMIT-004272 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | SES AU-TRANSMIT-000010 | NA | Trade Partner | Security Sample | 0 | 8 | 0 | NA | APPROVED | 2026-08-17 | WF-001512 | NA | 2026-08-28 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | SES AU-TRANSMIT-000009 | NA | Trade Partner | Security Drawing - IFC Issue | 33 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1759 | 2026-08-20 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | VIA Arch-TRANSMIT-000238 | NA | Consultant | Updated drawings and FFE Schedule | 20 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed |  | 2026-08-17 | KPTG-TRANSMIT-006966 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | DLTS-TRANSMIT-000095 | NA | Trade Partner | S11-Canopy Part 1-IFA Issue | 41 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-007644 |  | 2026-08-17 | KPTG-SADV-007644 | Closed | 41 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | DLTS-TRANSMIT-000096 | NA | Trade Partner | S11-Canopy Part1-IFA Issue | 40 | 0 | 0 | NA | APPROVED | 2026-08-17 | WF-001504 | NA | 2026-08-26 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-007330 | Closed | 40 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-21 | POTTSENG-TRANSMIT-000003 | NA | Trade Partner | GMAC HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 INGROUND - ZONE 2,4,5 LAYOUTS | 3 | 0 | 0 | NA | APPROVED | 2026-01-21 | WF-000143 | 275 | 2026-01-27 |  |  |  | 2026-01-27 | KPTG-TRANSMIT-000473 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | DLTS-TRANSMIT-000097 | NA | Trade Partner | S11-Canopy Part 1-Marking Plans-IFA Issue | 3 | 0 | 0 | NA | APPROVED | 2026-08-17 | WF-001504 | NA | 2026-08-26 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-007334 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | Nilsen3-TRANSMIT-000095 | NA | Trade Partner | Nilsen Sample submissions #12 IFC | 0 | 1 | 0 | NA | APPROVED | 2026-08-17 | WF-001502 | NA | 2026-08-26 |  | Submitted for review as advised by Project Coordinator | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-006970 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-17 | PROLMC-TRANSMIT-000015 | NA | Trade Partner | Proline Shop Drawing IFA submission - Dog Box Detail | 1 | 0 | 0 | NA | APPROVED | 2026-08-17 | WF-001519 | NA | 2026-08-19 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-18 | Nilsen3-TRANSMIT-000253 | NA | Trade Partner | Fwd: Nilsen clearance zone register | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distriburion |  | 2026-08-18 | KPTG-TRANSMIT-020653 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-18 | SMEPS-TRANSMIT-000108 | NA | Trade Partner | IFC SA | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, updated register and distributed |  | 2026-08-18 | KPTG-TRANSMIT-006967 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-18 | VERTIV-TRANSMIT-000068 | NA | Trade Partner | NEXT DC GE01_ ARCHITECTURAL DRAWINGS (FOA-2, FOA-3, FOA-4) | 10 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 512 | 2026-08-24 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-18 | Diadem-TRANSMIT-000001 | NA | Consultant | Wayfinding documents | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | WF-001158 | NA | 2026-08-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-18 | Diadem-TRANSMIT-000002 | NA | Consultant | Wayfinding documents | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | WF-001158 | NA | 2026-08-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-17 | Auspan-TRANSMIT-000619 | NA | Trade Partner | Precast shop drawings for approval. Level 7 zone 4, 5 | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - Difference in title -DRAFT-011563 |  | 2026-08-18 | DRAFT-011563 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-18 | INTRFRM-TRANSMIT-000127 | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 13) | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | WF-000498 | NA | 2026-08-27 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-002274 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-21 | Auspan-TRANSMIT-000051 | NA | Trade Partner | Precast shop drawings for construction | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings need to be revised KPTG-SADV-000726 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-18 | JFS-AU-TRANSMIT-000006 | NA | Consultant | Updated Facade Performance Specification | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Closed and superseded by JFS-AU-TRANSMIT-000007 |  | 2026-08-18 | KPTG-CONTADV-000271 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-18 | JFS-AU-TRANSMIT-000007 | NA | Consultant | Facade Specification - REV 03 (Amended) (REDSTICK) | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | NA | 357 | 2026-08-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-18 | JFS-AU-TRANSMIT-000007 | NA | Consultant | Facade Specification - REV 03 (Amended) (SME REVIEW) | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | NA | 358 | 2026-08-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | WGAVIC-TRANSMIT-000162 | NA | Consultant | M2 - S9 & S11 - Lift Lobbies, Stair and Lift Roof - Issued for Construction | 10 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 1682 | 2026-08-18 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-006974 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-18 | RDSBIM-TRANSMIT-000096 | NA | Trade Partner | GREYSTAR L02 PARTITION IFR SUBMISSION | 6 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 1761 | 2026-08-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-18 | Auspan-TRANSMIT-000624 | NA | Trade Partner | Precast shop drawings for construction. Levels 3, 5, 6. | 21 | 0 | 21 | KPTG-IntCorr-001292 | APPROVED | [5 empty] | ⁠IFC - Waiting for Oliver advise-KPTG-IntCorr-001292 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-18 | Auspan-TRANSMIT-000623 | NA | Trade Partner | Precast shop drawings for construction. Levels 3 and 4 zone 4, 5. | 7 | 0 | 7 | KPTG-IntCorr-001297 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001297 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-18 | SES AU-TRANSMIT-000101 | NA | Trade Partner | SCEC SECURITY PANEL ELEVATION AND SETOUTS-IFC | 1 | 0 | 0 | NA | APPROVED | 2026-08-18 | WF-000456 | NA | 2026-08-21 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-001189 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-02 | VIA Arch-TRANSMIT-000207 | NA | Consultant | Building Permit Drawings Update | 18 | 0 | 0 | NA | APPROVED | 2026-08-02 | NA | 1589 | 2026-08-18 |  |  | 2026-08-18 | 2026-08-18 | KPTG-DA-004250 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-18 | Jangho-TRANSMIT-000317 | NA | Trade Partner | Issues Thermal Report FT07 For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | WF-001159 | NA | 2026-08-20 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-21 | Auspan-TRANSMIT-000052 | NA | Trade Partner | Resubmit shop drawings for approval. | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings need to be revised KPTG-SADV-000727 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-18 | Auspan-TRANSMIT-000622 | NA | Trade Partner | Resubmit shop drawings for approval | 2 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 1756 | 2026-08-25 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | VIA Arch-TRANSMIT-000209 | NA | Consultant | Updated Stage 9 Wall Setout drawings | 4 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 1598 | 2026-08-18 |  |  | 2026-08-18 | 2026-08-18 | KPTG-DA-004251 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-18 | Altaire-TRANSMIT-000028 | NA | Trade Partner | NEXTDC M2S9-11 - Shop Drawings (FC-A/B) | 7 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected: Difference in revision and status |  | 2026-08-18 | KPTG-SADV-007669 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-18 | Entire M-TRANSMIT-000093 | NA | Trade Partner | Ground floor Mechanical Shop drawings IFC - Ground floor Admin- Re-issue | 2 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 516 | 2026-08-24 |  | Rejected in QA, as the previous revision which is FOA-1 was rejected in review and submitted FC-1. Processed as advised by Chri Doh. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-17 | Baigents-TRANSMIT-000037 | NA | Trade Partner | Baigents-TRANSMIT-000037 | 36 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 692 | 2026-08-21 |  | NA | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-000993 | Closed | 36 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-18 | WilsonPD-TRANSMIT-000022 | NA | Trade Partner | FXS02 - Kitchen Sink for Approval | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected: The latest revision of the document available with us is Rev. FOA-1 which is reviewed with status Rejected, they submitted FOA-01 |  | 2026-08-18 | KPTG-TRANSMIT-001953 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-17 | Baigents-TRANSMIT-000038 | NA | Trade Partner | Block 01 - Level 01 - Precast Columns updated to new reo configuration IFA | 36 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 691 | 2026-08-21 |  | NA | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-001119 | Closed | 36 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-18 | Highbu-TRANSMIT-000161 | NA | Trade Partner | IFC Hydraulic drawings | 10 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 510 | 2026-08-21 |  | Workflow Terminated-510#KPTG-TRANSMIT-003293 |  | 2026-08-19 | KPTG-TRANSMIT-003293 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-17 | 4DW-TRANSMIT-000082 | NA | Consultant | Structural Documentation: Block 1 - PW102, PW104, PW105 Precast walls & Stair cores issued with Construction updates. | 3 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 694 | 2026-08-21 |  | NA | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-001135 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-21 | Auspan-TRANSMIT-000053 | NA | Trade Partner | Shop drawings 0G439 and 0G440. | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings need to be revised KPTG-SADV-000728 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-17 | 4DW-TRANSMIT-000084 | NA | Consultant | Structural Documentation: Eaves Gutter details update for Coordination. | 1 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 696 | 2026-08-21 |  | NA | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-001137 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-18 | RDSBIM-TRANSMIT-000084 | NA | Trade Partner | DISTLV ¦ LEVEL 03 CONCRETE PROFILE PLAN | 2 | 0 | 0 | KPTG-IntCorr-001211 | APPROVED | 2026-08-18 | NA | 1118 | 2026-08-20 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003526 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-18 | RDSBIM-TRANSMIT-000302 | NA | Trade Partner | NXM3S4 ¦ GROUND FLOOR ¦ WET AREA-C-G-022 ACC WC (LH) | 1 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 4143 | 2026-08-21 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-020991 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-02 | VIA Arch-TRANSMIT-000201 | NA | Consultant | S9-S11 Door Hardware Schedule | 0 | 3 | 0 | NA | APPROVED | 2026-08-02 | NA | 1579 | 2026-08-18 |  |  | 2026-08-18 | 2026-08-18 | KPTG-DA-004253 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-18 | BTWA-TRANSMIT-000099 | NA | Trade Partner | MLC Stage 2 - Glass Submission | 0 | 3 | 0 | NA | APPROVED | 2026-08-18 | WF-001129 | NA | 2026-08-27 |  | As per the direction from the Ms Elisa, KPTG-IntCorr-008710, The wqorkflow has been terminated | 2026-08-18 | 2026-08-18 | 3 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-03 | VIA Arch-TRANSMIT-000212 | NA | Consultant | S11 Level 1 Door Schedule Update | 1 | 0 | 0 | NA | APPROVED | 2026-08-03 | NA | 1603 | 2026-08-18 |  |  | 2026-08-18 | 2026-08-18 | KPTG-DA-004254 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-08-18 | Nilsen3-TRANSMIT-000255 | NA | Trade Partner | Nilsen Shop Drawings - IFC - Stage 3 Ground floor shop drawing updated. | 1 | 0 | 0 | NA | APPROVED | 2026-08-18 | WF-006693 | NA | 2026-08-21 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-05 | VIA Arch-TRANSMIT-000214 | NA | Consultant | M2 Door Hardware Schedules | 0 | 3 | 0 | NA | APPROVED | 2026-08-05 | NA | 1637 | 2026-08-18 |  |  | 2026-08-18 | 2026-08-18 | KPTG-DA-004256 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-18 | Civilex-TRANSMIT-000340 | NA | Trade Partner | Stage 2 - sample submission - Type F Barrier | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | WF-006692 | NA | 2026-08-24 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-021152 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-18 | Civilex-TRANSMIT-000341 | NA | Trade Partner | Stage 2 - sample submission - CTCR Mix Design - Alex Fraser | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | WF-006694 | NA | 2026-08-24 |  | Terminated as advised by Charlie Johnstone for submitting the updated document. | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-020678 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-21 | Auspan-TRANSMIT-000054 | NA | Trade Partner | Precast dowel layout ground floor. Stage 9. | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings need to be revised KPTG-SADV-000725 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-18 | PARR-TRANSMIT-000219 | NA | Trade Partner | Fwd: P2685 - NDC M3 - Stage 4 - Battery Rooms - TEST REPORT CERTIFICATES | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-18 | KPTG-TRANSMIT-020660 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-18 | Altaire-TRANSMIT-000029 | NA | Trade Partner | NEXTDC M2S9-11 - Shop Drawings (FC-A/B) (Revised) | 7 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 1765 | 2026-08-25 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-16 | VIA Arch-TRANSMIT-000216 | NA | Consultant | Updated drawings | 28 | 1 | 0 | NA | APPROVED | 2026-08-16 | NA | 1726 | 2026-08-18 |  |  | 2026-08-18 | 2026-08-18 | KPTG-DA-004257 | Closed | 29 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-28 | Duct & Pipe Layout - VIA review | NA | Trade Partner | Duct & Pipe Layout - VIA review | 10 | 0 | 0 | NA | APPROVED | 2026-07-28 | NA | 1539 | 2026-07-31 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-006984 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-18 | HGP-TRANSMIT-000008 | NA | Trade Partner | Sample Transmittal-Terracotta | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | NA | 360 | 2026-08-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-16 | VIA Arch-TRANSMIT-000217 | NA | Consultant | Fuel Room finishes updates | 14 | 0 | 0 | NA | APPROVED | 2026-08-16 | NA | 1728 | 2026-08-18 |  |  | 2026-08-18 | 2026-08-18 | KPTG-DA-004258 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-16 | VIA Arch-TRANSMIT-000218 | NA | Consultant | Level 02_Concrete Profile updates | 2 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1731 | 2026-08-18 |  |  | 2026-08-18 | 2026-08-18 | KPTG-DA-004259 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-18 | ARCST-TRANSMIT-000383 | NA | Trade Partner | Stair 12 & 13 - Issued for Approval | 19 | 0 | 0 | NA | APPROVED | 2026-08-18 | WF-006695 | NA | 2026-08-22 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-16 | VIA Arch-TRANSMIT-000219 | NA | Consultant | Updated Schedules and Drawings | 6 | 3 | 0 | NA | APPROVED | 2026-08-18 | NA | 1733 | 2026-08-18 |  |  | 2026-08-18 | 2026-08-18 | KPTG-DA-004260 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-16 | VIA Arch-TRANSMIT-000220 | NA | Consultant | M2 S9 FM Office & Store Amendments | 5 | 0 | 0 | NA | APPROVED | 2026-08-17 | NA | 1734 | 2026-08-18 |  |  | 2026-08-18 | 2026-08-18 | KPTG-DA-004261 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-03 | KARE-TRANSMIT-000073 | NA | Trade Partner | Level 5 and 6 Light and Power Layouts | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2025-12-03 | KPTG-TRANSMIT-002455 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-22 | Bianco-TRANSMIT-000042 | Bianco-TRANSMIT-000042 | Trade Partner | Shop Drawing For Approval | 13 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-TRANSMIT-011753-The document reference number is incorrect, and the title is missing |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-18 | D&E-TRANSMIT-001019 | NA | Trade Partner | NXM3S4 - Ground & Level 1 - CHW Pipe Layout Zone 1 + Builders Works - Issued For Construction | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-18 | KPTG-TRANSMIT-020663 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-18 | VERTIV-TRANSMIT-000069 | NA | Trade Partner | NEXT DC GE 01_ELECTRICAL DRAWINGS (FOA-2, FOA-3)_ 17.08.2026 | 14 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 519 | 2026-08-24 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-002091 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-18 | HVHD-TRANSMIT-000020 | NA | Trade Partner | NatHERS Certificates and Stamped Drawings | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | WF-001161 | NA | 2026-08-27 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-003640 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-18 | SC-TRANSMIT-000057 | NA | Trade Partner | MLC - Sports Centre | 16 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Title of drawings does not match with title blocKPTG-SADV-005951: |  | 2026-08-18 | KPTG-SADV-005951 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-18 | D&E-TRANSMIT-001020 | NA | Trade Partner | Mechanical O&M Manual Draft - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | WF-006696 | NA | 2026-08-22 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | WGAVIC-TRANSMIT-000167 | NA | Consultant | M2 - Pumping Module Steel, Loading Diagrams, IH8 - Issued for Construction | 9 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 1694 | 2026-08-18 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-006989 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-18 | Auspan-TRANSMIT-000625 | NA | Trade Partner | Update IFCed precast shop drawings. No change to the panels | 2 | 0 | 0 | KPTG-IntCorr-001301 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001301 OK TO IFC-KPTG-TRANSMIT-003250 |  | 2026-08-19 | KPTG-TRANSMIT-003250 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-18 | ELLISAIR-TRANSMIT-000168 | NA | Trade Partner | Stage 11 Level 2 Builders Works drawings issued for Approval. | 2 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 1767 | 2026-08-25 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-007356 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-18 | VERTIV-TRANSMIT-000071 | NA | Trade Partner | NEXT DC GE 01 _ MECHANICAL DRAWINGS (FOA-2, FOA-3) | 3 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 523 | 2026-08-24 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-002095 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-18 | INDS-TRANSMIT-000063 | NA | Trade Partner | Dry Fire - Level 2 | 5 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 1764 | 2026-08-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-22 | NXT-TRANSMIT-001207 / EAEGROUP-TRANSMIT-000061 | NA | Trade Partner | Zone C1 MECH Busduct – Shop Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-01-22 | WF-003925 |  | 2026-02-04 |  |  |  | 2026-01-28 |  | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-18 | Jangho-TRANSMIT-000318 | NA | Trade Partner | GR26G10-1A-JH-District Living Docklands-Curtain Wall | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | WF-001162 | NA | 2026-08-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-18 | ELLISAIR-TRANSMIT-000169 | NA | Trade Partner | Stage 9 Level 01 Duct & Pipe layout drawing issued for Construction. | 1 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 1769 | 2026-08-25 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-007362 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-18 | KPTG-IntCorr-000762 | NA | Trade Partner | integration Plan R3 | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | WF-000457 | NA | 2026-08-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-18 | NXT-TRANSMIT-000497 | NA | Trade Partner | FIE Review - ABB - LVSB Labelling - FIE Elec Rev 2 | 1 | 0 | 0 | NA | APPROVED | 2026-08-18 | WF-000217 | NA | 2026-08-25 |  |  | 2026-08-28 | 2026-08-31 | KPTG-TRANSMIT-001208 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-08-18 | Auspan-TRANSMIT-000034 | NA | Trade Partner | pdate IFCed shop drawings. Re: 22kV precast retransmit | 2 | 0 | 0 | NA | APPROVED | 2026-08-18 | WF-006698 | NA | 2026-09-11 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-12 | SMEPS-TRANSMIT-000075 | NA | Trade Partner | Tech Data - SME approved/w comments | 0 | 27 | 0 | NA | APPROVED | 2026-08-12 | WF-000466 | NA | 2026-08-21 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-002056 | Closed | 27 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-18 | RBG-TRANSMIT-000069 | NA | Consultant | Structural GAs and Loading Plans | 27 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 785 | 2026-08-20 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-001677 | Closed | 27 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-18 | HAN IND-TRANSMIT-000008 | NA | Trade Partner | IFA - Steel Shop Drawings FOA-2 | 2 | 0 | 0 | NA | APPROVED | 2026-08-18 | WF-000504 | NA | 2026-08-28 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-002038 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-18 | ARCH-TRANSMIT-000059 | NA | Trade Partner | Fwd: S72 Submission (Town Planning) | 16 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | ONLY FOR INFORMATION |  | 2026-08-18 | KPTG-TRANSMIT-001967 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-18 | L.E.S.-TRANSMIT-000054 | NA | Trade Partner | Load Centre Shop Drawing IFA | 6 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 1120 | 2026-08-27 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-003691 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-16 | BVPI-TRANSMIT-000019 | NA | Trade Partner | L4 Mechanical Cx Scripts - Batch 1 | 0 | 6 | 0 | NA | APPROVED | 2026-01-21 | WF-000886 | NA | 2026-01-28 |  |  | 2026-02-05 | 2026-02-05 | KPTG-TRANSMIT-002438 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-18 | L.E.S.-TRANSMIT-000055 | NA | Trade Partner | Load Centre Data Sheet - IFA | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | WF-001165 | NA | 2026-08-27 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-003611 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-18 | Stowe-A-TRANSMIT-000682 STOWE | NA | Trade Partner | - Schematic As Builts | 21 | 0 | 0 | NA | APPROVED | 2026-08-18 | #4493 | NA | 2026-08-28 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-18 | ELLISAIR-TRANSMIT-000170 | NA | Trade Partner | Movement Joint Braided VEES | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | WF-001528 | NA | 2026-08-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-18 | Archacce-TRANSMIT-000022 | NA | Trade Partner | Re: Performance Based Design Briefs: 01-03 and 04 for Stakeholder Sign Off | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Issues with revision, document number, revision date inside the document. |  | 2026-08-18 | KPTG-IntCorr-017792 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-18 | RDSBIM-TRANSMIT-000102 | NA | Trade Partner | 671 CHAPEL STREET ¦ CORE WALL ¦ GROUND TO ROOF | 9 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 787 | 2026-08-25 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-001666 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-18 | VERTIV-TRANSMIT-000072 | NA | Trade Partner | NEXT DC GE 01_STRUCTURAL DRAWINGS (FOA-2) | 13 | 0 | 0 | NA | REJECTED | [5 empty] | There appears to be a mismatch in the revision number mentioned in the document. The revision number shown inside the drawing is from the previously received revision |  | 2026-08-18 | DRAFT-004789 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-18 | VERTIV-TRANSMIT-000070 | NA | Trade Partner | NEXT DC GE 01_FIRE SUPPRESSION DETECTION LAYOUT (FOA-1) | 1 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | #527 | 2026-08-28 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-18 | RDSBIM-TRANSMIT-000097 | NA | Trade Partner | GREYSTAR ¦ LEVEL 03 CONCRETE PROFILE PLAN | 6 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 1768 | 2026-08-25 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-003299 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-18 | 4DW-TRANSMIT-000210 | NA | Consultant | Structural Documentation - General updates | 2 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 512 | 2026-08-21 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003296 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-21 | DRLL-TRANSMIT-000063 | NA | Trade Partner | Battery Room Modules - Air Conditioning Systems Tech data | 0 | 1 | 0 | NA | APPROVED | 2026-01-22 | WF-000887 | NA | 2026-01-29 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-18 | TTW-TRANSMIT-000173 | NA | Consultant | Civil - Pavement Jointing Layout | 5 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 1122 | 2026-08-20 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-003663 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-18 | Jangho-TRANSMIT-000323 | NA | Trade Partner | FT01(updated),FT02,FT07,FT09/09b therm result | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | WF-001167 | NA | 2026-08-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-18 | Jangho-TRANSMIT-000324 | NA | Trade Partner | FT01(updated),FT02,FT07,FT09/09b therm result | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | WF-001168 | NA | 2026-08-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-18 | RDSBIM-TRANSMIT-000098 | NA | Trade Partner | GREYSTAR ¦ LEVEL 04 CONCRETE PROFILE PLAN - ACC | 6 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 1770 | 2026-08-25 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-003312 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-18 | ACCCA-TRANSMIT-000017 | NA | Trade Partner | Electrical Pit Approval | 16 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 698 | 2026-08-25 |  | NA | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-001189 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-18 | Archacce-TRANSMIT-000023 | NA | Trade Partner | Performance Based Design Brief 01-03 (Rev B) and 04 - for stakeholder signoff | 0 | 2 | 0 | NA | APPROVED | 2026-08-18 | WF-006700 | NA | 2026-08-25 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-18 | Entire M-TRANSMIT-000095 | NA | Trade Partner | Roof - Mechanical Pipework drawings - Issued For Approval | 10 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 529 | 2026-08-24 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002145 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-18 | Civilex-TRANSMIT-000342 | NA | Trade Partner | Stage 2 - sample submission -15% Stab Sand Mix Design - Pronto | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | WF-006701 | NA | 2026-08-24 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-020772 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-18 | INTRFRM-TRANSMIT-000128 | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 14) | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | WF-000507 | NA | 2026-08-27 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-002233 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-18 | HDRAus-TRANSMIT-000544 | NA | Consultant | Site Plan - Raingarden layout confirmation with Zinfra | 1 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 4495 | 2026-08-20 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-020690 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-22 | CRSol-TRANSMIT-000080 | NA | Trade Partner | M3S4 ZONE C2 CRS HAC SHOPDRAWINGS ISSUED FOR APPROVAL REV. A | 18 | 0 | 0 | NA | APPROVED | 2026-01-22 |  | 1861 | 2026-02-02 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-014636 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-18 | EAEGROUP-TRANSMIT-000005 | NA | Trade Partner | Approval Request – 160 A and 250 A TOB Shop Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-08-05 | WF-000415 | NA | 2026-08-14 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-001955 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-18 | PenskePS-TRANSMIT-000002 | NA | Trade Partner | GENERATOR DESIGNS AND DRAWINGS - FOR REVIEW AND APPROVAL | 7 | 0 | 0 | NA | APPROVED | 2026-08-05 | WF-000416 | NA | 2026-08-14 |  |  | 2026-08-18 | 2026-08-18 | KPTG-TRANSMIT-001960 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-18 | RDSBIM-TRANSMIT-000099 | NA | Trade Partner | GREYSTAR LEVEL 05 CONCRETE PROFILE PLAN | 6 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 1772 | 2026-08-25 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-18 | Jangho-TRANSMIT-000109 | NA | Trade Partner | Facade Structural Sealant Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | WF-000702 | NA | 2026-08-25 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-18 | B Smart-TRANSMIT-000103 | NA | Trade Partner | : Drawings update | 6 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Drawings superseded by B Smart-TRANSMIT-000104 |  | 2026-08-18 | B Smart-TRANSMIT-000104 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-18 | RDSBIM-TRANSMIT-000101 | NA | Trade Partner | 671CHP LEVEL 03 CONCRETE PROFILE KEYPLAN AND SECTION | 3 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 779 | 2026-08-24 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-001714 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-18 | B Smart-TRANSMIT-000104 | NA | Trade Partner | Drawings update | 6 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 781 | 2026-08-20 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-001681 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-18 | VIA Arch-TRANSMIT-000240 | NA | Consultant | Stage 11_ Level 02 _Concrete Profile update | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed |  | 2026-08-18 | KPTG-TRANSMIT-006979 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-18 | Ardon-TRANSMIT-000028 | NA | Trade Partner | Door Hardware Tech Data | 0 | 26 | 0 | NA | APPROVED | 2026-08-18 | WF-001521 | NA | 2026-08-27 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-007505 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-18 | Ardon-TRANSMIT-000029 | NA | Trade Partner | Ground Level Shop Drawings - Round 2 Approval | 20 | 0 | 0 | NA | APPROVED | 2026-08-18 | WF-001522 | NA | 2026-08-27 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-007506 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-19 | D&E-TRANSMIT-000301 | NA | Trade Partner | L1 ZONE B1 / B2 & D2 DUCT & PIPE LAYOUT SHEETS - Issued For Construction | 3 | 0 | 0 | NA | APPROVED | 2026-01-19 | NA | 1343 | 2026-01-26 |  |  | 2026-01-27 | 2026-01-28 | KPTG-TRANSMIT-002359 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-18 | NCFGroup-RTRFI-000028 | NA | Trade Partner | Retaining Walls - ITP Review and Material Procurement | 0 | 4 | 0 | NA | APPROVED | 2026-08-18 | WF-001526 | NA | 2026-08-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-18 | WDes-TRANSMIT-000060 | NA | Consultant | Civil - Public Domain | 0 | 0 | 6 | KPTG-TRANSMIT-003239 | APPROVED | 2026-08-18 |  |  |  |  | NA |  | 2026-08-21 | KPTG-TRANSMIT-003256 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-18 | Nilsen3-TRANSMIT-000097 | NA | Trade Partner | Nilsen Drawings Issued for Construction | 25 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 1772 | 2026-08-22 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-18 | Nilsen3-TRANSMIT-000098 | NA | Trade Partner | Nilsen Drawings Issued for Construction | 8 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 1773 | 2026-08-25 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-17 | ZIA-TRANSMIT-000079 | NA | Trade Partner | CSMS O & M Manual | 0 | 2 | 0 | KPTG-IntCorr-002178 | APPROVED | [9 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-18 | SKS Tech-TRANSMIT-000204 | NA | Trade Partner | CSMS O & M Manual | 1 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 1328 | 2026-08-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-19 | CLADC-TRANSMIT-000027 | NA | Trade Partner | RFI - latest security/electrical drawings | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Issued for information: Requirement of updated drawings, transmittal forwarded to kapitol's Project Team for action- KPTG-IntCorr-008712 |  | 2026-08-19 | KPTG-IntCorr-008712 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-18 | NXES-TRANSMIT-000073 | NA | Trade Partner | Nexus - Tech Data Sheet | 0 | 2 | 0 | NA | APPROVED | 2026-08-18 | WF-000910 | NA | 2026-08-24 |  |  | 2026-08-28 | 2026-08-28 | KPTG-IntCorr-001368 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-19 | ARCST-TRANSMIT-000384 | NA | Trade Partner | Stage 4 Upper Battery Room Platforms - Issued for Approval | 40 | 0 | 0 | NA | APPROVED | 2026-08-19 | WF-006703 | NA | 2026-08-24 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-18 | NDY-TRANSMIT-000026 | NA | Trade Partner | End Of Trip Mezzanine Lighting Layout | 1 | 0 | 0 | KPTG-IntCorr-001329 | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-001329 - requested guidance, but no resonance yet. KPTG-SADV-005327 - The title and project number are incorrect. | 2026-08-19 | 2026-08-19 | KPTG-SADV-005327 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-22 | CRSol-TRANSMIT-000079 | NA | Trade Partner | M3S4 CRS HAC SHOPDRAWINGS ISSUED FOR APPROVAL REV. A | 20 | 0 | 0 | NA | APPROVED | 2026-01-22 | NA | 1863 | 2026-02-02 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-014956 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-19 | Blueprin-TRANSMIT-000008 | NA | Trade Partner | Stage 2 finished art as made | 26 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Wrong document numbering & revision, requested to resubmit:KPTG-SADV-005970 |  | 2026-08-19 | :KPTG-SADV-005970 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-18 | fjc-TRANSMIT-000181 | NA | Consultant | Architecturals - RFI Updates (mezz / level 01) | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | WF-000911 | NA | 2026-08-25 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-002907 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-19 | ELLISAIR-TRANSMIT-000172 | NA | Trade Partner | Stage 10 Ground Floor Duct & Pipe Layout drawings issued for Construction. | 3 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 1775 | 2026-08-25 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-007366 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-19 | HDRAus-TRANSMIT-000544 | NA | Consultant | Site Plan - Raingarden layout confirmation with Zinfra - WORKFLOW REQUEST | 1 | 0 | 0 | NA | APPROVED | 2026-08-19 | WF-006704 | NA | 2026-08-27 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-19 | Auspan-TRANSMIT-000118 | NA | Trade Partner | Precast shop drawings for construction. Geelong precast stage 2 | 21 | 0 | 0 | NA | APPROVED | 2026-08-19 | WF-001131 | NA | 2026-08-28 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-19 | RDSBIM-TRANSMIT-000085 | NA | Trade Partner | DISTLV ¦ LEVEL 13 - 14 CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 1124 | 2026-08-21 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003527 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-19 | Archacce-TRANSMIT-000003 | NA | Consultant | M3-S6 D4D5 Exempt Areas Markup (DRAFT) | 1 | 0 | 0 | KPTG-IntCorr-000519 | APPROVED | 2026-08-28 | NA | 801 | 2026-09-07 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-19 | ccair-TRANSMIT-000017 | NA | Trade Partner | Mechanical Substation Layout IFA | 1 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 1126 | 2026-08-28 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-003689 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-19 | Lat-TRANSMIT-000023 | NA | Consultant | Marking Superseded Documents as No Longer in Use "No Longer in use Lat-TRANSMIT-000017-26 same document " | 25 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer in use |  | 2026-08-19 | KPTG-TRANSMIT-001003 | Closed | 25 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-19 | Auspan-TRANSMIT-000626 | NA | Trade Partner | Update IFCed precast shop drawings. Level 3 | 5 | 0 | 0 | KPTG-IntCorr-001305 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001305 OK TO IFC KPTG-TRANSMIT-003264 |  | 2026-08-19 | KPTG-TRANSMIT-003264 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-21 | RDSBIM-TRANSMIT-000198 | NA | Trade Partner | NXM3S4 LEVEL-1-C-1-047 FEMALE WC FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-01-21 |  | 1859 | 2026-01-25 |  |  |  | 2026-01-22 | KPTG-TRANSMIT-011783 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-19 | BTWA-TRANSMIT-000100 | NA | Trade Partner | Stage 2 - Facade Glass | 0 | 3 | 0 | NA | APPROVED | 2026-08-19 | WF-001132 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-19 | Auspan-TRANSMIT-000627 | NA | Trade Partner | Update IFCed precast shop drawings. Level 4 | 14 | 0 | 0 | KPTG-IntCorr-001306 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001306 10 OK TO IFC- KPTG-TRANSMIT-003306, 4 Rejected as advised by Kapitol PC. KPTG-IntCorr-001347 |  | 2026-08-24 | KPTG-TRANSMIT-003306 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-19 | ELLISAIR-TRANSMIT-000173 | NA | Trade Partner | Revised Level 01 Duct & Pipe layout drawings issued for Construction (Drawing Titles amended on Aconex) | 2 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 1777 | 2026-08-26 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-19 | WAM-TRANSMIT-000847 | NA | Consultant | A16 Facade Plan 4B3b Level 18-19 | 1 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 1128 | 2026-08-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-19 | D&E-TRANSMIT-001022 | NA | Trade Partner | Fwd: BMS System Architecture - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-19 | KPTG-TRANSMIT-020707 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-19 | D&E-TRANSMIT-001021 | NA | Trade Partner | Re: BMS Functional Description - Issued for Construction | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Ref KPTG-IntCorr-017834 |  | 2026-08-19 | KPTG-IntCorr-017834 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-19 | EAEGROUP-TRANSMIT-000119 | NA | Trade Partner | Updated Shop Drawing Revision - GB | 1 | 0 | 0 | NA | APPROVED | 2026-08-19 | WF-006705 | NA | 2026-09-01 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-19 | Auspan-TRANSMIT-000628 | NA | Trade Partner | Update IFC precast shop drawings. Level 5 | 12 | 0 | 12 | KPTG-IntCorr-001307 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001307 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-19 | Auspan-TRANSMIT-000629 | NA | Trade Partner | Update IFC precast shop drawings. Level 6 | 6 | 0 | 6 | KPTG-IntCorr-001309 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001309 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-19 | SC-TRANSMIT-000058 | NA | Trade Partner | MLC Indoor Sport | 16 | 0 | 0 | NA | APPROVED | 2026-08-19 | WF-001133 | NA | 2026-08-28 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-22 | D&E-TRANSMIT-000346 | NA | Trade Partner | Re: SFN Pipework Material - Issued for Construction | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The revision number is missing from the document - KPTG-TRANSMIT-011765 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-19 | RDSBIM-TRANSMIT-000028 | NA | Trade Partner | NXGE01 ¦GROUND FLOOR RCP LAYOUT | 3 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 532 | 2026-08-25 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-19 | SMEPS-TRANSMIT-000271 | NA | Trade Partner | NEL-CNT-SME-2990-ELC-SAM-0001 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision is incorrect | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001630 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-19 | INDS-TRANSMIT-000064 | NA | Trade Partner | Dry Fire - Level 3 | 5 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 1778 | 2026-08-24 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-19 | SKS Tech-TRANSMIT-000213 | NA | Trade Partner | TYPICAL DETAILS BUSDUCT OPENINGS SECURITY TREATMENT for approval | 1 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 4149 | 2026-08-24 |  | As instructed by Damian, the document should be placed in the Security template |  | 2026-08-24 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-19 | Civilex-TRANSMIT-000343 | NA | Trade Partner | Stage 2 - sample submission - Aftek Curecon BE Curing | 0 | 1 | 0 | NA | APPROVED | 2026-08-19 | WF-006707 | NA | 2026-08-25 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-19 | Civilex-TRANSMIT-000344 | NA | Trade Partner | Stage 2 - sample submission - No Fines Concrete Mix Design - Hytec | 0 | 1 | 0 | NA | APPROVED | 2026-08-19 | WF-006708 | NA | 2026-08-25 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-19 | Civilex-TRANSMIT-000345 | NA | Trade Partner | Stage 2 - sample submission - Line Marking & Omnigrip Reinstatement – Cala Street Crossover | 0 | 1 | 0 | NA | APPROVED | 2026-08-19 | WF-006709 | NA | 2026-08-25 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-22 | Altaire-TRANSMIT-000059 | NA | Trade Partner | S3 22KV Samples | 0 | 12 | 0 | NA | APPROVED | 2026-01-22 | WF-003933 |  | 2026-02-04 |  | The register has been updated. If any further action is required, the coordinator will inform. -KPTG-TRANSMIT-011766 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-19 | D&E-TRANSMIT-001023 | NA | Trade Partner | Fwd: NXM3S4 - Level 1 - Mechanical Duct & Builders Works Layout - Zone 9 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-19 | KPTG-TRANSMIT-020723 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-19 | ZIA-TRANSMIT-000156 | NA | Trade Partner | M3S4 Ground Floor & Level 1 Strobe light and OS location (FC-2) | 6 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 4152 | 2026-08-24 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-020920 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-19 | SRA-PMQ-TRANSMIT-000014 | NA | Trade Partner | Structural Ceiling IFC Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 535 | 2026-08-28 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-002338 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-19 | ACCCA-TRANSMIT-000018 | NA | Trade Partner | TELE PITS FOR APPROVAL | 12 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 700 | 2026-08-27 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-19 | INDS-TRANSMIT-000065 | NA | Trade Partner | Dry Fire - Level 4 | 5 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 1780 | 2026-08-24 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-19 | VERTIV-TRANSMIT-000073 | NA | Trade Partner | NEXT DC GE01_MATERIAL SUBMISSION_SIEMENS BUSDUCT (FOA-2) | 0 | 1 | 0 | NA | APPROVED | 2026-08-19 | WF-000512 | NA | 2026-08-28 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-002034 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-19 | Nilsen3-TRANSMIT-000254 | NA | Trade Partner | Nilsen Sample Typical Busduct Opening Cover | 1 | 0 | 0 | NA | REJECTED | [5 empty] | REVISION INCORRECT |  | 2026-08-19 | KPTG-DA-008186 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-19 | ZIA-TRANSMIT-000157 | NA | Trade Partner | M3S4 CSMS Outstation Location Update - Roof Level | 3 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 4154 | 2026-08-24 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-020873 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-19 | WilsonPD-TRANSMIT-000233 | SPARK-CRFI-KPG-000182 | Trade Partner | Hydraulic Services - Updated Water & Fire Layout - Inground Zone C | 1 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 411 | 2026-08-26 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-001645 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-19 | KPTG-TRANSMIT-020709 | NA | Trade Partner | UPS O&M | 0 | 1 | 0 | NA | APPROVED | 2026-08-19 | WF-006712 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-11-10 | JCBa-TRANSMIT-000191 | NA | Consultant | Building Permit 7 Rev 3 Issue | 6 | 0 | 0 | NA | APPROVED | 2025-11-13 | WF-000783 | 468 | 2025-11-20 |  |  | 2025-12-03 | 2025-12-03 | KPTG-DA-002199 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2026-01-22 | D&E-TRANSMIT-000051 | NA | Trade Partner | NextDC M2 DH11 Updated As-Builts | 5 | 0 | 0 | NA | APPROVED | [5 empty] | As-Builts, No review required. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-19 | Baigents-TRANSMIT-000039 | NA | Trade Partner | Level 01 Block 01 Precast Beams (updated bending data) | 125 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 702 | 2026-08-25 |  | NA | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-001032 | Closed | 125 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-19 | D&E-TRANSMIT-001024 | NA | Trade Partner | NXM3S4 - CHW & CT SCHEMATICS - ROOF C1 TO C3 - Issued For Construction | 6 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 4186 | 2026-08-26 |  | FOR DISTRIBUTION , KPTG-TRANSMIT-020727, (21-08-2026 KPTG-IntCorr-017986 -As requested by Elllie s- IFC WF Start |  | 2026-08-21 | KPTG-TRANSMIT-020837 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-19 | Lat-TRANSMIT-000015-SPE | NA | Consultant | Landscape Issued For Endorsement Drawings-SPE | 0 | 1 | 0 | NA | APPROVED | 2026-08-19 | NA | 706 | 2026-08-27 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-001168 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-19 | Lat-TRANSMIT-000015 | NA | Consultant | Landscape Issued For Endorsement Drawings | 56 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 704 | 2026-08-27 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-001169 | Closed | 56 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-19 | RDSBIM-TRANSMIT-000245 | NA | Trade Partner | LEVEL 03 PARTITION WALL KEY PLAN | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-08-19 | KPTG-TRANSMIT-003245 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-19 | PMT Sec-TRANSMIT-000051 | NA | Trade Partner | Re: Final (WF-000618) MWYCCB ¦¦ DOCUMENT CONTROL REVIEW ¦¦ PMT Sec-TRANSMIT-000047-IFC-Re Resubmit Drawings-#403 | 2 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 412 | 2026-08-26 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-19 | VIA Arch-TRANSMIT-000226 | NA | Consultant | M2S9-S11 - 0001-8602 - WINDOW DETAILS - SHEET 2 | 1 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 1779 | 2026-08-26 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-007348 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-19 | VIA Arch-TRANSMIT-000227 | NA | Consultant | Re: Stage 2 Watertanks - Concrete Footing | 1 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 1781 | 2026-08-26 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-007352 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-17 | ZLH P/L-SUBRFI-000006 | NA | Trade Partner | Verification of Details | 1 | 0 | 0 | NA | APPROVED | 2026-08-17 | WF - 001112 | NA | 2026-08-21 |  | NA | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-003244 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-19 | HGP-TRANSMIT-000009 | NA | Trade Partner | Powdercoat Sample Tranmsittal | 0 | 5 | 0 | NA | APPROVED | 2026-08-19 | NA | 363 | 2026-08-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-20 | SKS Tech-TRANSMIT-000133 | NA | Trade Partner | LEVEL 4 SEISMIC IFA LAYOUTS | 2 | 0 | 0 | NA | APPROVED | 2026-01-20 | WF-000737, 000750 | ACC 846, 878 | 2026-01-23 |  |  | 2026-02-12 | 2026-02-12 | KPTG-TRANSMIT-002808, KPTG-TRANSMIT-002676 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-19 | SMEPS-TRANSMIT-000378 | NA | Trade Partner | C1 Roof - Telecommunication drawing | 1 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 4157 | 2026-08-25 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-020756 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-19 | VIA Arch-TRANSMIT-000228 | NA | Consultant | S9-11 Signage Package | 6 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 1783 | 2026-08-26 |  |  | 2026-08-27 | 2026-08-27 | KPTG-DA-004396 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-07 | Entire M-TRANSMIT-000056 | NA | Trade Partner | TAB Report Sample | 0 | 1 | 0 | NA | APPROVED | 2026-08-07 | WF - 000564 | NA | 2026-08-11 |  | NA | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-001160 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-19 | D&E-TRANSMIT-001025 | NA | Trade Partner | NXM3S4 - Ground - CHW Pipe Layout + Industrial Water Tank Layout Zones - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | [5 empty] | FOR DISTRIBUTION |  | 2026-08-19 | KPTG-TRANSMIT-020734 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-08-19 | SMEPS-TRANSMIT-000380 | NA | Trade Partner | 22KV - Lightning protection sample | 0 | 1 | 0 | NA | APPROVED | 2026-08-19 | WF-006714 | NA | 2026-08-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-19 | Electrical samples Client Review | NA | Trade Partner | Electrical samples | 0 | 1 | 0 | NA | APPROVED | 2026-08-19 | WF-001176 | NA | 2026-08-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-19 | Hydraulic samples Client Review | NA | Trade Partner | Hydraulic Samples | 0 | 4 | 0 | NA | APPROVED | 2026-08-19 | WF-001175 | NA | 2026-08-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-19 | VIA Arch-TRANSMIT-000229 | NA | Consultant | Updated drawings and Interior Schedule | 13 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 1785 | 2026-08-26 |  |  | 2026-08-27 | 2026-08-27 | KPTG-DA-004398 | Closed | 13 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-19 | D&E-TRANSMIT-001026 | NA | Trade Partner | Fwd: NXM3S4 - Roof Level Switchroom - Mechanical Duct Layout - Zone 7 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-19 | KPTG-TRANSMIT-020735 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-19 | VIA Arch-TRANSMIT-000230 | NA | Consultant | S11 Level 2 Concrete Profile | 1 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 1787 | 2026-08-26 |  |  | 2026-08-27 | 2026-08-27 | KPTG-DA-004399 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-20 | Hames-TRANSMIT-000097 | NA | Consultant | Architectural Design Drawings | 64 | 0 | 0 | NA | APPROVED | 2026-01-21 | NA | 852 | 2026-01-23 |  |  | 2026-01-23 | 2026-01-23 | KPTG-TRANSMIT-002583 | Closed | 71 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-19 | VIA Arch-TRANSMIT-000231 | NA | Consultant | S9-S11 Signage Package | 14 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 1789 | 2026-08-26 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-007382 | Closed | 14 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-19 | TTW-TRANSMIT-000214 | NA | Trade Partner | M3 Stage 2 Civil Drawings | 8 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 4498 | 2026-08-19 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-020891 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-19 | VIA Arch-TRANSMIT-000233 | NA | Consultant | M2 - S9 Stair 03 - Issued for Construction (FC-1) | 2 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 1791 | 2026-08-26 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-007386 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-19 | VIA Arch-TRANSMIT-000234 | NA | Consultant | Stage 11 Fuel Room wall penetrations | 1 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 1793 | 2026-08-26 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-007394 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-19 | G&CHyd-TRANSMIT-000018 | NA | Trade Partner | HYD TECH DATA 15 & 40 | 0 | 2 | 0 | NA | APPROVED | 2026-08-19 | WF-001177 | NA | 2026-08-27 |  |  |  | 2026-08-24 | KPTG-TRANSMIT-003557 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-19 | Nilsen3-TRANSMIT-000099 | NA | Trade Partner | Nilsen Drawings Issued for Construction | 2 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 1796 | 2026-08-26 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-19 | Nilsen3-TRANSMIT-000099 | NA | Trade Partner | Nilsen Drawings Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 1797 | 2026-08-26 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-19 | PFP PL-TRANSMIT-000033 | NA | Trade Partner | Watermist pump | 0 | 1 | 0 | NA | APPROVED | 2026-08-19 | WF-001541 | NA | 2026-08-31 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-19 | SMEPS-TRANSMIT-000382 | NA | Trade Partner | SME IFA Documentation - Lighting Control (Amended) | 41 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 4163 | 2026-08-25 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-19 | crossfir-TRANSMIT-000009 | NA | Trade Partner | Wet Fire - Sprinklers Hyd Calcs, Comments Addressed. | 0 | 1 | 0 | NA | APPROVED | 2026-08-19 | WF-000513 | NA | 2026-08-28 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002158 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-20 | Hames-TRANSMIT-000098 | NA | Consultant | Architectural Design Drawings | 7 | 0 | 0 | NA | APPROVED | 2026-01-21 | NA | 852 | 2026-01-23 |  |  | 2026-01-23 | 2026-01-23 | KPTG-TRANSMIT-002583 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-10 | PSGANZ-TRANSMIT-000014 | NA | Trade Partner | Fire Protection tech data | 0 | 1 | 0 | NA | APPROVED | 2026-08-10 | WF-000454 | NA | 2026-08-21 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-002302 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-19 | VERTIV-TRANSMIT-000074 | NA | Trade Partner | NEXT DC GE01_MATERIAL SUBMISSION_LV SWITCHBOARDS GA DRAWINGS (FOA-5) | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | WF-000514 | NA | 2026-08-28 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-002126 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-19 | ADP-TRANSMIT-000142 | NA | Trade Partner | ADP MEL4680 - Partical Electrical Updates | 8 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 537 | 2026-08-24 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002150 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-10 | SMEPS-TRANSMIT-000084 | NA | Trade Partner | Tech Data - 110V Control Cable/ Rod Couplers | 0 | 1 | 0 | NA | APPROVED | 2026-08-10 | WF-000486 | NA | 2026-08-26 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-002048 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-19 | WGAVIC-TRANSMIT-000174 | NA | Consultant | M2 - Civil - Updated Gabion Details - Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 1800 | 2026-08-24 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-007069 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-19 | WGAVIC-TRANSMIT-000177 | NA | Consultant | M2 - Stage 10 Level 1 and 2 Slabs - Issued for Construction | 11 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 1801 | 2026-08-24 |  |  | 2026-08-27 | 2026-08-27 | KPTG-DA-004406 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-19 | PCForm-TRANSMIT-000115 | NA | Trade Partner | : Rigid Scaffold Set IFC | 0 | 8 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol PC, no review required- KPTG-TRANSMIT-003248 |  | 2026-08-19 | KPTG-TRANSMIT-003248 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-19 | RDSBIM-TRANSMIT-000103 | NA | Trade Partner | 671 CHP ¦ BASEMENT 03 BLOCKWORK PLAN AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 790 | 2026-08-26 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-19 | Auspan-TRANSMIT-000129 | NA | Trade Partner | Resubmit precast shop drawings for approval. Columns on levels 4 to 17. | 47 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to incorrect drawing status - KPTG-SADV-003964 |  | 2026-08-19 | KPTG-SADV-003964 | Closed | 47 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-19 | ccair-TRANSMIT-000049 | NA | Trade Partner | : Mechanical Services Latest Builders works drawing | 3 | 0 | 0 | KPTG-IntCorr-001270 | APPROVED | 2026-08-21 | NA | 797 | 2026-08-28 |  | Waiting for advice from KPTG-IntCorr-001270 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-20 | VAE-Grp-TRANSMIT-000109 | NA | Trade Partner | MECHANICAL SERVICES - VSD ENCLOSURES | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Register Updated - FC |  | 2026-06-20 | KPTG-TRANSMIT-003948 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-19 | Auspan-TRANSMIT-000124 | NA | Trade Partner | All precast columns in one transmittal for approval. | 104 | 0 | 0 | NA | APPROVED | 2026-08-19 | WF-001136 | NA | 2026-08-25 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003305 | Closed | 104 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-19 | Highbu-TRANSMIT-000161 | NA | Trade Partner | IFC Hydraulic drawings | 2 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 514 | 2026-08-28 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-19 | Highbu-TRANSMIT-000161 | NA | Trade Partner | IFC Hydraulic drawings | 8 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 515 | 2026-08-28 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-19 | ELLISAIR-TRANSMIT-000171 | NA | Trade Partner | STAGE 9 LEVEL 02 BATTERY ROOM - DUCT & PIPE LAYOUT DRAWING ISSUED FOR CONSTRUCTION. | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-007704 |  | 2026-08-19 | KPTG-SADV-007704 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-19 | SMEPS-TRANSMIT-000109 | NA | Trade Partner | Typical Switch room AUX-DB MA-PF [IFC-1} | 0 | 3 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-007718 |  | 2026-08-19 | KPTG-SADV-007718 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-19 | CRSol-TRANSMIT-000020 | NA | Trade Partner | CRS - HAC - Shop Drawing - Stage 9 - DH21 & DH24 - | 15 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-007721 |  | 2026-08-19 | KPTG-SADV-007721 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-19 | TGRF-TRANSMIT-000121 | NA | Trade Partner | Level 2 PT - Shop drawings - IFC | 36 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 517 | 2026-08-28 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-19 | Ardon-TRANSMIT-000030 | NA | Trade Partner | Batch 3 Shop Drawings | 38 | 0 | 0 | NA | APPROVED | 2026-08-19 | WF-001536 | NA | 2026-08-28 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-19 | SES AU-TRANSMIT-000103 | NA | Trade Partner | SECURITY SERVICES LEVEL 2 SCEC LAYOUT COLO 4 - RETICULATION- Rev C | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected: wrong document Number-KPTG-TRANSMIT-001183 |  | 2026-08-19 | KPTG-TRANSMIT-001183 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-19 | Jangho-TRANSMIT-000325 | NA | Trade Partner | Window Wall PMU Shop Drawing_Rev B_For Construction | 6 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 1130 | 2026-08-27 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-003497 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-20 | PRDoors-TRANSMIT-000001 | NA | Trade Partner | Architectural Door frames | 34 | 0 | 0 | NA | APPROVED | 2026-01-21 | WF-000751 | 860 | 2026-01-27 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-002964 | Closed | 34 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-19 | INGEN3D-TRANSMIT-000242 | NA | Trade Partner | Zone A - Precast Column Elevation - MP0168 - IFC (18-08-2026) | 1 | 0 | 0 | NA | APPROVED | 2026-08-19 | WF-001180 | NA | 2026-08-27 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-003630 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-14 | ELLISAIR-TRANSMIT-000150 | NA | Trade Partner | Stage 10 Ground Floor Duct layout drawings issued for Approval. | 1 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 1719 | 2026-08-17 |  | Resubmitted for WSP stamping | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-007047 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-14 | ELLISAIR-TRANSMIT-000154 | NA | Trade Partner | Revised Stage 10 Level 1 drawing - Pipework issued for Approval. | 1 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 1719 | 2026-08-17 |  | Resubmitted for WSP stamping | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-007051 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | RDSBIM-TRANSMIT-000303 | NA | Trade Partner | NXM3S4 ¦ LEVEL 01 ¦ C-1-044 ACC WC (RH) FLOOR FINISHES LAYOUT AND ELEVATION | 1 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 4165 | 2026-08-20 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-20 | ARCH-TRANSMIT-000180 | NA | Trade Partner | MLC - SPR - ISC - Wall Partition and Wall Types drawing update | 6 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected: Revision is not current, reqiest to retransmit to us-KPTG-SADV-005996 |  | 2026-08-20 | KPTG-SADV-005996 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | Nilsen3-TRANSMIT-000256 | NA | Trade Partner | Nilsen Sample Typical Busduct Opening Cover | 0 | 1 | 0 | NA | APPROVED | 2026-08-20 | WF-006720 | NA | 2026-09-15 |  | A s intructed by damian terminated the document will be in review in security template |  | 2026-08-26 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-19 | SMEPS-TRANSMIT-000017 | NA | Trade Partner | Stage 6 - Conduit spacer sample IFC | 0 | 1 | 0 | KPTG-IntCorr-000532 | APPROVED | 2026-08-20 | NA | 724 | 2026-08-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-19 | SMEPS-TRANSMIT-000018 | NA | Trade Partner | Secondary Primer and Glue sumbittals | 0 | 2 | 0 | NA | APPROVED | 2026-08-19 | NA | 712 | 2026-08-27 |  | Voided requested by muskan |  | 2026-08-21 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-19 | D&E-TRANSMIT-000064 | NA | Trade Partner | Ground Floor Builders Work Layout - Zone 5 & 7 - Issued For Approval | 2 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 708 | 2026-08-27 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-001048 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-19 | Baigents-TRANSMIT-000040 | NA | Trade Partner | Level 01 Block 01 Precast Beams (updated bending data) | 1 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 714 | 2026-08-27 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-001069 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-22 | ASV-TRANSMIT-000004 | NA | Trade Partner | Updated Tech data | 0 | 5 | 0 | NA | APPROVED | 2026-01-22 | WF-000160 |  | 2026-01-30 |  |  |  | 2026-02-05 | KPTG-TRANSMIT-000706 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-19 | Baigents-TRANSMIT-000041 | NA | Trade Partner | Precast panels P20 & P13 Issued for Construction | 3 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 716 | 2026-08-27 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-001047 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-20 | D&E-TRANSMIT-000312 | SPARK-CRFI-KPG-000315 | Trade Partner | MWYCCB - LEVEL 1 - PENETRATION LAYOUT ZONE 5 TO ZONE 7 MECHANICAL SERVICES - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 413 | 2026-08-27 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-001647 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-19 | NDY-TRANSMIT-000025 | NA | Trade Partner | Lighting Foyer Drawings | 5 | 0 | 5 | KPTG-IntCorr-001328 | APPROVED | [5 empty] | KPTG-IntCorr-001328 - requested guidance, but no resonance yet. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-19 | KPTG-TRANSMIT-002905 | NA | Trade Partner | South VIG Glass Option2 | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-001335 - The document number and revision are incorrect. | 2026-08-19 | 2026-08-19 | KPTG-IntCorr-001335 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-19 | KPTG-TRANSMIT-002908 | NA | Trade Partner | INTERNAL LIGHTING SD WORKFLOW | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-001330 - The document does not have a title, the History box has not been filled in, and the document number format is incorrect. | 2026-08-19 | 2026-08-19 | KPTG-IntCorr-001330 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-19 | KPTG-TRANSMIT-002909 | NA | Trade Partner | ICN Functional Description | 0 | 1 | 0 | NA | APPROVED | 2026-08-19 | WF-000913 | NA | 2026-08-25 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-002991 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-19 | KPTG-TRANSMIT-002910 | NA | Trade Partner | South VIG Option 2 | 0 | 1 | 0 | NA | APPROVED | 2026-08-20 | WF-000912 | NA | 2026-08-25 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-19 | KPTG-TRANSMIT-002776 | NA | Trade Partner | Heritage South Glass rev3 | 0 | 1 | 0 | NA | APPROVED | 2026-08-19 | WF-000912 | NA | 2026-08-25 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-20 | Carr-TRANSMIT-000088 | NA | Consultant | Architectural Facade Package IFC | 20 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 365 | 2026-08-26 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-20 | Carr-TRANSMIT-000088 | NA | Consultant | SME- REVIEW - Architectural Facade Package IFC | 20 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 366 | 2026-08-26 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-22 | Auspan-TRANSMIT-000040 | NA | Trade Partner | GF shop drawings issued for construction | 5 | 0 | 0 | NA | REJECTED | 2026-01-22 |  | 520 | 2026-01-29 |  | As per the direction from Ashlin, updated drawing will resubmitted hence, we void this work flow date 02-02-2026 | 2026-02-02 | 2026-02-02 |  | Closed | 5 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | ADP-TRANSMIT-000403 | NA | Consultant | ADP MEL4780 - Updated BACOP Schematics | 1 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 4168 | 2026-08-24 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-20 | Auspan-TRANSMIT-000633 | NA | Trade Partner | Re: Precast shop drawings for approval. Level 7 zone 4, 5 | 4 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 1783 | 2026-08-27 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-20 | Auspan-TRANSMIT-000632 | NA | Trade Partner | Precast shop drawings for construction. Level 5, 6 | 19 | 0 | 19 | KPTG-IntCorr-001328 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001328 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-20 | Auspan-TRANSMIT-000632 | NA | Trade Partner | Precast shop drawings for construction. Level 5, 6 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected- difference in revision and latest IFA was terminated-DRAFT-011728 |  | 2026-08-20 | DRAFT-011728 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-20 | BTWA-TRANSMIT-000101 | NA | Trade Partner | Stage 2 - Facade layout | 20 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected: Document number & Revision of drawings are incorrect, requested to resubmit:KPTG-SADV-005998 |  | 2026-08-20 | KPTG-SADV-005998 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | ZIA-TRANSMIT-000159 | NA | Trade Partner | M3S4 CSMS Outstation & ORMB Location Update - ground level & level 1 C3 | 4 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 4170 | 2026-08-29 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-020868 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-20 | ARCH-TRANSMIT-000061 | NA | Consultant | FC Drawing Update – NEXTDC and Kapitol Redstick Changes | 52 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 539 | 2026-08-25 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002161 | Closed | 52 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | ZIA-TRANSMIT-000160 | NA | Trade Partner | M3S4 CSMS Outstation & ORMB Location Update - level 1 C1 & C2 | 2 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 4172 | 2026-08-29 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-020862 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-20 | SMEPS-TRANSMIT-000091 | NA | Trade Partner | Fire rated cat wire | 0 | 1 | 0 | NA | APPROVED | 2026-08-20 | WF-000518 | NA | 2026-08-31 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-20 | ARCH-TRANSMIT-000181 | NA | Consultant | MLC - ISC - Capping beam drawing update | 2 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 519 | 2026-08-25 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-003326 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-22 | Auscool-TRANSMIT-000065 | NA | Trade Partner | MEZZ DISCHARGE PENETRATION UPDATE | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-01-27 | 2026-01-27 | KPTG-IntCorr-001120 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-20 | Eneraque-TRANSMIT-000064 | NA | Trade Partner | Valves Schedule - Stage 9 for approval | 0 | 1 | 0 | NA | APPROVED | 2026-08-20 | WF-001546 | NA | 2026-09-01 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-20 | Auspan-TRANSMIT-000631 | NA | Trade Partner | Precast shop drawings for construction. Level 4 | 7 | 0 | 7 | KPTG-IntCorr-001329 | APPROVED | [5 empty] | IFC- Waiting for Oliver advise-KPTG-IntCorr-001329 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | ZIA-TRANSMIT-000161 | NA | Trade Partner | M3S4 CSMS Outstation Location Relocation - From SW(FF, FG, GB and GC) to Roof Plant | 3 | 0 | 0 | NA | REJECTED | [5 empty] | STATUS MISTAKE |  | 2026-08-20 | KPTG-DA-008201 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-20 | RDSBIM-TRANSMIT-000086 | NA | Trade Partner | DISTLV ¦ LEVEL 04 STAGE 4B3 PARTITION WALL | 6 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 1135 | 2026-08-24 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-003588 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | D&E-TRANSMIT-001032 | NA | Trade Partner | NXM3S4 - Ground & Level 1 - CHW Pipe Layout Zones - Issued For Construction | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | FOR DISTRIBUTION |  | 2026-08-20 | KPTG-TRANSMIT-020769 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-20 | Auspan-TRANSMIT-000630 | NA | Trade Partner | Update IFCed precast shop drawings. Level 3 | 1 | 0 | 1 | KPTG-IntCorr-001330 | APPROVED | [5 empty] | IFC- Waiting for Oliver advise-KPTG-IntCorr-001330 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-20 | Auspan-TRANSMIT-000630 | NA | Trade Partner | Update IFCed precast shop drawings. Level 3 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected- difference in title - DRAFT-011739 |  | 2026-08-20 | DRAFT-011739 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-20 | CRSol-TRANSMIT-000021 | NA | Trade Partner | Re: CRS - HAC - Shop Drawing - Stage 9 - DH21 & DH24 | 15 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 1806 | 2026-08-27 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | D&E-TRANSMIT-001034 | NA | Trade Partner | NXM3S4 - Exterior Builders Works Layouts - Elevations Sheet 2 - Issued For Construction | 1 | 0 | 0 | NA | REJECTED | [5 empty] | IFA BOTH RECEIVED |  | 2026-08-20 | KPTG-DA-008203 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-22 | D&E-TRANSMIT-000347 | NA | Trade Partner | SFN Pipework Material - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-01-22 | WF-003938 |  | 2026-02-12 |  |  |  | 2026-02-11 | The workflow has been terminated as requested by Zak - KPTG-IntCorr-009181 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-20 | VIA Arch-TRANSMIT-000241 | NA | Consultant | M2 S10 - Stair 05 & 08 Stairs - ISSUED FOR CONSTRUCTION | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, updated register and distributed |  | 2026-08-20 | KPTG-TRANSMIT-007077 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-20 | POTTSENG-TRANSMIT-000068 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - PENETRATION - LEVEL 02 - ZONE 3 LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 1785 | 2026-08-27 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | ZIA-TRANSMIT-000163 | NA | Trade Partner | M3 Stage 4 - IP Device Register | 0 | 4 | 0 | NA | APPROVED | 2026-08-20 | WF-006725 | NA | 2026-09-11 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-021056 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-20 | HDRAus-TRANSMIT-000142 | NA | Consultant | Town Planning Updates - Site Plans and GAs series | 14 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 720 | 2026-08-27 |  | NA | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-001165 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | SMEPS-TRANSMIT-000383 | NA | Trade Partner | SME IFA Documentation - MCCP Schematic | 1 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 4175 | 2026-08-25 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | ACG-TRANSMIT-000114 | NA | Trade Partner | Re: M3 Stage 4 - Security External Drawings | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect status |  | 2026-08-20 | KPTG-DA-008204 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-20 | PTA-TRANSMIT-000046 | NA | Consultant | Block 2 Office Update | 2 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 722 | 2026-08-27 |  | NA | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-001164 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-20 | SMEPS-TRANSMIT-000110 | NA | Trade Partner | Typical Switch Room AUX-DB (MA-PF) | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, updated register and distributed |  | 2026-08-20 | KPTG-TRANSMIT-007096 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | D&E-TRANSMIT-001027 | NA | Trade Partner | Fwd: Air System Points List - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-20 | KPTG-TRANSMIT-020773 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-03 | IVS-TRANSMIT-000288 | NA | Consultant | Stage 4 - Ground Floor Zone C1 Construction Issue (revised as clouded) | 2 | 0 | 0 | NA | APPROVED | 2025-12-05 | NA | 1603 | 2026-01-08 |  |  |  | 2025-12-05 | KPTG-TRANSMIT-010673 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-22 | IVS-TRANSMIT-000321 | NA | Consultant | Stage 4 - Cooling Tower & Chiller Room Zone C1 Package (Construction Issue) | 1 | 0 | 0 | NA | APPROVED | 2026-01-22 |  | 1866 | 2026-01-26 |  |  |  | 2026-01-29 | KPTG-TRANSMIT-012118 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | D&E-TRANSMIT-001028 | NA | Trade Partner | Fwd: IW System Points List - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-20 | KPTG-TRANSMIT-020775 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | D&E-TRANSMIT-001029 | NA | Trade Partner | Fwd: IW System Points List - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-08-20 | WF-006728 | NA | 2026-08-26 |  | For distribution |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | D&E-TRANSMIT-001021 | NA | Trade Partner | Fwd: BMS Functional Description - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-08-20 | WF-006729 | NA | 2026-08-26 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | ZIA-TRANSMIT-000162 | NA | Trade Partner | Re: M3S4 CSMS Outstation Location Relocation - From SW(FF, FG, GB and GC) to Roof Plant | 3 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 4178 | 2026-08-26 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | D&E-TRANSMIT-001030 | NA | Trade Partner | Fwd: SFN Points List - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-20 | KPTG-TRANSMIT-020788 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | D&E-TRANSMIT-001031 | NA | Trade Partner | Fwd: BMS Valve Schedule - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-20 | KPTG-TRANSMIT-020790 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | D&E-TRANSMIT-001033 | NA | Trade Partner | Fwd: MagFlow Meter Schedule - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribtion |  | 2026-08-20 | KPTG-TRANSMIT-020795 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-20 | PCForm-TRANSMIT-000303 | NA | Trade Partner | Updated L4 reo pt drawings | 4 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 1141 | 2026-08-27 |  | IFC Drawings - Update in ACC & Aconex |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-08-20 | VIA Arch-TRANSMIT-000034 | NA | Trade Partner | 22kV Amenites Update | 2 | 0 | 0 | NA | APPROVED | 2026-08-20 | WF-006730 | NA | 2026-09-02 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-020909 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-20 | Civilex-TRANSMIT-000346 | NA | Trade Partner | Stage 2 - sample submission - Line Marking & Omnigrip Reinstatement – Cala Street Crossover (Alternative product) | 0 | 1 | 0 | NA | APPROVED | 2026-08-20 | WF-006731 | NA | 2026-08-26 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-22 | Bianco-TRANSMIT-000046 | NA | Trade Partner | Shop Drawing For Approval | 13 | 0 | 0 | NA | APPROVED | 2026-01-22 | WF-003940 |  | 2026-02-18 |  |  |  | 2026-01-30 | KPTG-TRANSMIT-012236 | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-20 | RBG-TRANSMIT-000012 | NA | Trade Partner | Crane Base Drawings IFC | 8 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | CAD File register updated |  | 2026-08-20 | NA | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-20 | Baigents-TRANSMIT-000042 | NA | Trade Partner | Precast Columns Ligs Set Out | 9 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 720 | 2026-08-27 |  | NA | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-001046 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-20 | Baigents-TRANSMIT-000043 | NA | Trade Partner | Updated Block 01 Level 01 Precast beams | 3 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 726 | 2026-08-27 |  | NA | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-001068 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-20 | SMEPS-TRANSMIT-000089 | NA | Trade Partner | Shop Drawings: IFC | 7 | 0 | 0 | NA | APPROVED | 2026-08-13 | NA | 541 | 2026-08-26 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002171 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-20 | Civilex-TRANSMIT-000347 | NA | Trade Partner | Stage 2 - sample submission - 15% Stab Sand Mix Design - Holcim | 0 | 1 | 0 | NA | APPROVED | 2026-08-20 | WF-006732 | NA | 2026-08-26 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | D&E-TRANSMIT-001035 | NA | Trade Partner | SFN Scripts - Issued for Approval | 0 | 12 | 0 | NA | REJECTED |  |  | NA |  |  | Document number and revision number mismatch |  | 2026-08-20 | KPTG-DA-008205 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-20 | Entire M-IntCorr-000206 | NA | Trade Partner | Condensate Arrangement | 0 | 1 | 0 | NA | APPROVED | 2026-08-20 | WF - 000573 | NA | 2026-08-27 |  | NA | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-001163 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-08-20 | DI-TRANSMIT-000164 | NA | Trade Partner | Re: AS Built updates | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision and status |  | 2026-08-20 | DRAFT-010546 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-01-22 | WPD-TRANSMIT-000058 | NA | Consultant | Hydraulic Shop Drawings for Construction | 8 | 0 | 0 | NA | APPROVED | 2026-01-22 |  | 274 | 2026-01-24 |  |  |  | 2026-01-23 | KAPITOL-TRANSMIT-001008 | Closed | 8 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | SMEPS-TRANSMIT-000384 | NA | Trade Partner | Telecommunication services -DAS | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The document number revision and title mismatch |  | 2026-08-20 | KPTG-DA-008206 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-20 | Nilsen3-TRANSMIT-000100 | NA | Trade Partner | Nilsen Sample submissions #15 | 0 | 1 | 0 | NA | APPROVED | 2026-08-20 | WF-001557 | NA | 2026-09-01 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-20 | 4DW-TRANSMIT-000086 | NA | Consultant | Block 1 - Level 1 suspended slab & Misc Construction issue documentation updates. | 15 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 728 | 2026-08-27 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-001191 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-20 | OveArup-TRANSMIT-000043 | NA | Consultant | Fire and Hydraulic Services IFC documents (Certificates) | 0 | 2 | 0 | NA | APPROVED | 2026-08-20 | WF-001189 | NA | 2026-08-21 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-003580 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-20 | OveArup-TRANSMIT-000043 | NA | Consultant | Fire and Hydraulic Services IFC documents - Fire Specification | 0 | 1 | 0 | NA | APPROVED | 2026-08-20 | WF-001190 | NA | 2026-08-21 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-003580 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-20 | OveArup-TRANSMIT-000043 | NA | Consultant | -Fire and Hydraulic Services IFC documents-Stormwater Flow Rate Calculation Memorandum | 0 | 1 | 0 | NA | APPROVED | 2026-08-20 | WF-001191 | NA | 2026-08-21 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-003580 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-20 | SMEPS-TRANSMIT-000092 | NA | Trade Partner | Cat wire tech data | 0 | 1 | 0 | NA | APPROVED | 2026-08-20 | WF-000520 | NA | 2026-08-27 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-002083 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-20 | OveArup-TRANSMIT-000043 | NA | Consultant | -Fire and Hydraulic Services IFC documents | 3 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 11140 | 2026-08-25 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-003571 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-20 | Entire M-TRANSMIT-000058 | NA | Trade Partner | TAB Report Rev 2 for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-08-20 | WF - 000574 | NA | 2026-08-28 |  | NA | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-001170 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-20 | Arc Plas-TRANSMIT-000001 | NA | Trade Partner | Insulation & Fastener - Tech Data Submissions | 0 | 2 | 0 | NA | APPROVED | 2026-08-20 | WF-000521 | NA | 2026-08-31 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-002070 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-22 | IVS-TRANSMIT-000322 | NA | Consultant | Stage 4 - Cooling Tower & Chiller Room Zone C2 & C3 (Certification Issue) | 2 | 0 | 0 | NA | APPROVED | 2026-01-22 |  | 1868 | 2026-01-26 |  |  |  | 2026-01-29 | KPTG-TRANSMIT-012125 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-20 | CRSol-TRANSMIT-000022 | NA | Trade Partner | CRS - Shop Drawing - Stage 11 - Ceiling | 14 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 1810 | 2026-08-27 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-007426 | Closed | 14 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-20 | CRSol-TRANSMIT-000023 | NA | Trade Partner | Re: CRS - Shop Drawing - Stage 11 - Ceiling | 2 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 1810 | 2026-08-27 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-007426 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-20 | ARCH-TRANSMIT-000182 | NA | Consultant | MLC - SPR ISC - Wall Partition & Types drawing revision update | 6 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 521 | 2026-08-25 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-20 | VIA Arch-TRANSMIT-000242 | NA | Consultant | M2 S11 - Stair 06 & 07 - ISSUED FOR CONSTRUCTION | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, updated register and distributed |  | 2026-08-20 | KPTG-TRANSMIT-007132 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-20 | Auspan-TRANSMIT-000125 | NA | Trade Partner | All column shop drawings in one transmittal. | 123 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected:Same drawings have already been transmitted, earlier-KPTG-IntCorr-008715 |  | 2026-08-20 | KPTG-IntCorr-008715 | Closed | 123 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-20 | RDSBIM-TRANSMIT-000018 | NA | Trade Partner | GROUND FLOOR CONCRETE PROFILE PLAN ¦ BLOCK 2 | 3 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 730 | 2026-08-27 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-20 | Entire M-TRANSMIT-000096 | NA | Trade Partner | FOA-6 VRF Submission | 0 | 1 | 0 | NA | APPROVED | 2026-08-20 | WF-000522 | NA | 2026-08-31 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-002112 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-20 | 4DW-TRANSMIT-000085 | NA | Consultant | Block 2 - Precast walls issued for coordination (Work in Progress). | 4 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 732 | 2026-08-27 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-001190 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-20 | KPTG-TRANSMIT-020771 | NA | Trade Partner | O&M WF | 0 | 1 | 0 | NA | APPROVED | 2026-08-20 | WF-006734 | NA | 2026-08-28 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-20 | Entire M-TRANSMIT-000097 | NA | Trade Partner | MCC Schedules - Issued for Approval | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document and multipage document to be submitted as TD. |  | 2026-08-20 | KPTG-TRANSMIT-002042 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-22 | D&E-TRANSMIT-000085 | SPARK-CRFI-KPG-000470 | Trade Partner | CONTROLS FD & POINTS LIST | 0 | 2 | 0 | NA | APPROVED | 2026-01-22 | WF-000136 |  | 2026-01-29 |  | KPTG-IntCorr-001365 |  | 2026-02-13 | KPTG-TRANSMIT-000437 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-20 | KPTG-TRANSMIT-020802 | NA | Trade Partner | CDU O&M WF | 0 | 1 | 0 | NA | APPROVED | 2026-08-20 | WF-006735 | NA | 2026-09-02 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-20 | faulk-TRANSMIT-000006 | NA | Trade Partner | Updated Eaves gutter SD | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with Document number, revision, date inside the document etc. |  | 2026-08-20 | KPTG-TRANSMIT-002023 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | ACG-TRANSMIT-000115 | NA | Trade Partner | M3 - Stage 4 Security External drawings for review | 2 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 4181 | 2026-08-26 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | D&E-TRANSMIT-001037 | NA | Trade Partner | NXM3S4 - Ground - CHW Pipe Layout - Zone 4 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-20 | KPTG-TRANSMIT-020804 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-20 | WGAVIC-TRANSMIT-000016 | NA | Consultant | Town Planning Updates - Site Plans and GAs series | 14 | 0 | 0 | NA | APPROVED | [5 empty] | Same document HDRAus-TRANSMIT-000142 already submitted |  | 2026-08-20 | NA | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-20 | Ardon-TRANSMIT-000031 | NA | Trade Partner | Door Hardware Schedules | 0 | 1 | 0 | NA | APPROVED | 2026-08-20 | WF-001544 | NA | 2026-08-31 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-20 | Ardon-TRANSMIT-000031 | NA | Trade Partner | Door Hardware Schedule - Stage 11 | 0 | 1 | 0 | NA | APPROVED | 2026-08-20 | WF-001545 | NA | 2026-08-31 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-20 | ELLISAIR-TRANSMIT-000174 | NA | Trade Partner | STAGE 9 LEVEL 02 BATTERY ROOM - DUCT & PIPE LAYOUT DRAWING ISSUED FOR CONSTRUCTION. | 1 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 1803 | 2026-08-29 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-20 | Ardon-TRANSMIT-000032 | NA | Trade Partner | Batch 4 Shop Drawings | 33 | 0 | 0 | NA | APPROVED | 2026-08-20 | WF-001550 | NA | 2026-08-31 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-20 | Ardon-TRANSMIT-000033 | NA | Trade Partner | Stage 10 Door Hardware Schedule | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-007784 |  | 2026-08-20 | KPTG-SADV-007784 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-22 | ccair-TRANSMIT-000084 | NA | Trade Partner | Level 03 Mechanical Penetration Layout Zone 1 - IFC | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-20 | Ardon-TRANSMIT-000034 | NA | Trade Partner | Stage 10 Door Hardware Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-08-20 | WF-001560 | NA | 2026-08-31 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-20 | SMEPS-TRANSMIT-000107 | NA | Trade Partner | S11 Level 01 Containment IFA | 1 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 1808 | 2026-08-28 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-20 | SMEPS-TRANSMIT-000111 | NA | Trade Partner | S11 Earth Bars | 0 | 2 | 0 | NA | APPROVED | 2026-08-20 | WF-001558 | NA | 2026-09-01 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-20 | DLTS-TRANSMIT-000098 | NA | Trade Partner | S10-Cooling Tower-IFC Issue | 381 | 0 | 0 | KPTG-SADV-007798 | APPROVED |  | NA | NA |  |  | Updated register and distributed |  | 2026-08-21 | KPTG-TRANSMIT-007163 | Closed | 381 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-20 | VIA Arch-TRANSMIT-000243 | NA | Consultant | STAGE 11 L2_CONCRETE PROFILE | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-DA-004317 |  | 2026-08-20 | KPTG-DA-004317 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-20 | POTTSENG-TRANSMIT-000069 | NA | Trade Partner | GMAC HYDRAULIC SERVICES - DRAINAGE - GROUND - ZONES 1-5 LAYOUTS | 5 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 1788 | 2026-08-27 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-20 | Auspan-TRANSMIT-000636 | NA | Trade Partner | : Update IFCed shop drawing 3P5065 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC- Waiting for Oliver advise KPTG-IntCorr-001333 proceed IFC - KPTG-IntCorr-001334 IFC Register and Transmit KPTG-TRANSMIT-003291 |  | 2026-08-20 | KPTG-TRANSMIT-003291 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-20 | POTTSENG-TRANSMIT-000070 | NA | Trade Partner | GMAC HYDRAULIC SERVICES - PENETRATION - LEVEL 02 - ZONE 2 LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 1790 | 2026-08-27 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-20 | Auspan-TRANSMIT-000635 | NA | Trade Partner | : Panel 3P5065 | 1 | 0 | 1 | KPTG-IntCorr-001331 | APPROVED |  | NA | NA |  |  | IFC- Waiting for Oliver advise KPTG-IntCorr-001331 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-20 | KPTG-IntCorr-001210 | NA | Consultant | Hot and Cold Plunge Pools FWT drawings | 5 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 1133 | 2026-08-27 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-22 | LANSA-TRANSMIT-000084 | NA | Trade Partner | Levels 12-14 Penetrations IFC | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-20 | INGEN3D-TRANSMIT-000243 | NA | Consultant | -Fire and Hydraulic Services IFC documents | 4 | 0 | 0 | NA | APPROVED | 2026-08-20 | WF-001186 | NA | 2026-08-25 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-003626 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-20 | L.E.S.-TRANSMIT-000056 | NA | Consultant | -Fire and Hydraulic Services IFC documents | 1 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 11137 | 2026-08-25 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-20 | INGEN3D-TRANSMIT-000244 | NA | Consultant | -Fire and Hydraulic Services IFC documents | 4 | 0 | 0 | NA | APPROVED | 2026-08-20 | WF-001188 | NA | 2026-08-25 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-003624 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-20 | RDSBIM-TRANSMIT-000104 | NA | Trade Partner | 671 CHP ¦ BASEMENT 04 BLOCKWORK PLAN AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 792 | 2026-08-27 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-20 | PCForm-TRANSMIT-000304 | NA | Consultant | -Fire and Hydraulic Services IFC documents | 1 | 0 | 0 | NA | REJECTED | [5 empty] | rejected : revision error | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003525 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-20 | RDSBIM-TRANSMIT-000105 | NA | Trade Partner | 671 CHP LEVEL 05 -08 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 795 | 2026-08-27 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-20 | Auspan-TRANSMIT-000130 | NA | Trade Partner | 3PC7E-27. Update shop drawing. | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | ifc - No Review required, Just register. KPTG-TRANSMIT-001627 |  | 2026-08-20 | KPTG-TRANSMIT-001627 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-20 | Auspan-TRANSMIT-000131 | NA | Trade Partner | Re: Resubmit precast shop drawings for approval. Columns on levels 4 to 17. | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | ifc - No Review required, Just register. KPTG-TRANSMIT-001625 |  | 2026-08-20 | KPTG-TRANSMIT-001625 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-20 | Auspan-TRANSMIT-000129 | NA | Trade Partner | Resubmit precast shop drawings for approval. Columns on levels 4 to 17. | 45 | 0 | 0 | NA | APPROVED | 2026-08-20 | WF-000710 | NA | 2026-08-27 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-20 | IJF-TRANSMIT-000012 | NA | Trade Partner | Joinery Prototype - Kitchens | 12 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - As advised by Clare Lu - (KPTG-IntCorr-001291) Register and Transmit. Registered and Transmitted - KPTG-TRANSMIT-001629 |  | 2026-08-20 | KPTG-TRANSMIT-001629 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-21 | TIVINTL-TRANSMIT-000017 | NA | Trade Partner | SRC-Tivoli- L8 joinery IFC drawings | 140 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 140 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-20 | Jangho-TRANSMIT-000091 | NA | Trade Partner | Jangho-TRANSMIT-000091 GL300 GF Glass Sample | 0 | 1 | 0 | NA | APPROVED | 2026-08-20 | WF-000714 | NA | 2026-08-27 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-20 | DCN-TRANSMIT-000038 | NA | Trade Partner | DC Nexus - O&M Manual - Link Bridge | 0 | 1 | 1 | KPTG-IntCorr-002237 | APPROVED |  | NA | NA |  |  | Awaiting advise from Kapitol |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-20 | Eneraque-TRANSMIT-000065 | NA | Trade Partner | Marking this document as no longer in use | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-08-20 | KPTG-TRANSMIT-007080 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-20 | WGAVIC-TRANSMIT-000178 | NA | Consultant | M2 - Civil - Main Works Updates - Issued for Construction | 8 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, Updated register and distributed |  | 2026-08-20 | KPTG-TRANSMIT-007140 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-21 | LNCPPL-TRANSMIT-000029 | NA | Trade Partner | Fire Shop Drawings - Site Inground - FC-1 | 1 | 0 | 0 | NA | REJECTED | 2026-08-21 | NA | 455 | 2026-08-27 |  | FOA-1 was rejected, and originator submitted FC-01. The transmittal was rejected and sent back to Originator for rectification. Processed as advised by Chri Doh. |  | 2026-08-25 | KPTG-TRANSMIT-002140 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-20 | Auscool-TRANSMIT-000115 | NA | Trade Partner | Mezzanine Mech drawings IFC | 2 | 0 | 0 | NA | APPROVED | 2026-08-20 | NA | 742 | 2026-08-27 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-21 | DLTS-TRANSMIT-000099 | NA | Trade Partner | S9-Glazing Frame support-IFC Issue | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, updated register and distributed |  | 2026-08-21 | KPTG-TRANSMIT-007147 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-21 | RDSBIM-TRANSMIT-000152 | NA | Trade Partner | MLCSPR ¦ CARPARK NORTH LEVEL 01 CONCRETE PROFILE | 8 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 523 | 2026-08-26 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-21 | SMEPS-TRANSMIT-000018 | NA | Trade Partner | Secondary Primer and Glue sumbittals | 0 | 2 | 0 | NA | APPROVED | 2026-08-21 | NA | 733 | 2026-08-31 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-20 | SRA48-TRANSMIT-000004 | NA | Trade Partner | Raxtar Twin Hoists Tower A IFC Drawings | 15 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-TRANSMIT-003514 - There is a mismatch between the information in the Aconex register and the drawing/document. | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-003514 | Closed | 15 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-22 | ARCST-TRANSMIT-000184 | NA | Trade Partner | Stage 4 - C3 HD Bolts for Switchhroom & Cooling Tower - Issued for Construction | 9 | 0 | 0 | NA | APPROVED | 2026-01-22 | WF-003943 |  | 2026-02-12 |  |  |  | 2026-02-19 | KPTG-TRANSMIT-013206 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-20 | SKS Tech-TRANSMIT-000206 | NA | Trade Partner | SCADA - Automatic Sequence Test | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | closed out via BASESG-IntCorr-000038 |  | 2026-08-20 | BASESG-IntCorr-000038 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-20 | PARR-TRANSMIT-000066 | NA | Trade Partner | Stage 2 - Fuel Services - CLIENT DRAWINGS - ABS-A | 17 | 0 | 17 | KPTG-IntCorr-002285 | APPROVED | [9 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-20 | L.E.S.-TRANSMIT-000047 | NA | Trade Partner | Communications Technical Data & Sample Submissions | 0 | 3 | 0 | NA | APPROVED | 2026-08-20 | WF-001193 | NA | 2026-08-24 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-20 | INGEN3D-TRANSMIT-000250 | NA | Trade Partner | I3D-389 District Living - Level 6-7 - Precast Walls & Cast in Dowel - IFC (20-08-2026) | 7 | 0 | 0 | NA | APPROVED | 2026-08-20 | WF-001182 | NA | 2026-08-28 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-003591 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-21 | WilsonPD-TRANSMIT-000023 | NA | Trade Partner | FXS02 - Resubmission | 0 | 1 | 0 | NA | APPROVED | 2026-08-21 | WF-000524 | NA | 2026-09-01 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-20 | INGEN3D-TRANSMIT-000245 | NA | Trade Partner | I3D-389 District Living - Level 9-10 - Precast Walls - Revised IFC (19-08-2026) | 5 | 0 | 0 | NA | APPROVED | 2026-08-20 | WF-001195 | NA | 2026-08-31 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-003628 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-20 | INGEN3D-TRANSMIT-000246 | NA | Trade Partner | I3D-389 District Living - Level 10-11 - Precast Walls - Revised IFC (19-08-2026) | 4 | 0 | 0 | NA | APPROVED | 2026-08-20 | WF-001196 | NA | 2026-08-31 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-003685 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-20 | INGEN3D-TRANSMIT-000247 | NA | Trade Partner | I3D-389 District Living - Level 11-12 - Precast Walls - Revised IFC (19-08-2026) | 4 | 0 | 0 | NA | APPROVED | 2026-08-20 | WF-001197 | NA | 2026-08-31 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-003687 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-27 | ZLH P/L-SUBRFI-000001 | NA | Trade Partner | Verification of Details | 7 | 1 | 0 | NA | APPROVED | 2026-07-13 | WF - 001112 | NA | 2026-07-14 |  | NA | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-003253 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-21 | RDSDG-TRANSMIT-000008 | NA | Trade Partner | Drainage Shop Drawings - Block 1, Carpark & North Zones | 3 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 735 | 2026-08-31 |  | NA | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-001127 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-21 | RDSBIM-TRANSMIT-000150 | NA | Trade Partner | LEVEL 11 RCP KEY PLAN AND LAYOUT | 6 | 0 | 0 | NA | APPROVED | 2026-01-22 | WF-000891 | 530 | 2026-01-29 |  |  | 2026-02-02 | 2026-02-02 | KPTG-TRANSMIT-002660 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-21 | 4DW-TRANSMIT-000087 | NA | Consultant | Level 1 Block 1 Floor Design - Revised SlimDek Slab Design Methodology | 8 | 0 | 0 | NA | APPROVED | [5 empty] | Certification Drawings already submitted on redstick |  | 2026-08-21 | NA | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-21 | ABB-TRANSMIT-000019 | NA | Trade Partner | LV Switchboards - ABB AU-10026006 - Shop Drawings CRS | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | No Action Required |  | 2026-08-21 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-21 | Entire M-TRANSMIT-000098 | NA | Trade Partner | MCC Schedules | 0 | 1 | 0 | NA | APPROVED | 2026-08-21 | (WF-000525 | NA | 2026-09-01 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | BIMF-TRANSMIT-000023 | NA | Trade Partner | Mez Hyd Setout Bld B, Rev B | 1 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 1143 | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | BIMF-TRANSMIT-000022 | NA | Trade Partner | Water Schematics, Revised for Approval | 3 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 1145 | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-21 | HDRAus-TRANSMIT-000143 | NA | Consultant | M3 Expansion - Town Planning resubmission - Architectural Package | 6 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 737 | 2026-08-31 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-001225 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-21 | ADP-TRANSMIT-000143 | NA | Trade Partner | ADOP MEL4680 - HV Load Protection Study Report | 0 | 1 | 0 | NA | APPROVED | 2026-08-21 | NA | 546 | 2026-08-26 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-002079 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-21 | NXT-TRANSMIT-000500 | NA | Client | M3S6 Psub Op Manual and Lifting lug calcs | 0 | 2 | 0 | NA | APPROVED | 2026-08-21 | WF-000230 | NA | 2026-09-03 |  | Psub Lifting lug calc-Distributted and O & m put in FIE review |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-21 | KPTG-TRANSMIT-003313 | NA | Trade Partner | In review | 0 | 3 | 0 | NA | APPROVED | 2026-08-21 | WF-001142 | NA | 2026-08-26 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-21 | Auspan-TRANSMIT-000640 | NA | Trade Partner | Update IFCed precast shop drawings | 30 | 0 | 30 | KPTG-IntCorr-001342 | APPROVED | [5 empty] | IFC- Waiting for Oliver advise-KPTG-IntCorr-001342 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-03 | HDRAus-TRANSMIT-000329 | NA | Consultant | M3 Stage 4 - Updated RCP and Concrete profile drawings Ground & L1 | 11 | 0 | 0 | NA | APPROVED | 2025-12-03 | NA | 1605 | 2025-12-05 |  |  |  | 2025-12-05 | KPTG-TRANSMIT-010685 | Closed | 11 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-22 | SMEPS-TRANSMIT-000145 | NA | Trade Partner | SME's outstanding sample submission | 0 | 1 | 0 | NA | APPROVED | 2026-01-24 |  |  | 2026-02-05 |  | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-21 | Auspan-TRANSMIT-000126 | NA | Trade Partner | Premium precast panels | 18 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Same copy of drawings have already been transmitted: KPTG-SADV-006029 |  | 2026-08-21 | KPTG-SADV-006029 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-21 | D&E-TRANSMIT-000934 | NA | Trade Partner | NXM3S4 - CHW & SFN SCHEMATICS / Upper Roof & Roof Level CHW Pipe Layout Zones - Issued For Construction | 10 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 4182 | 2026-08-30 |  | AS INSTRUCTED BY ELLIE SALMON |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-21 | POTTSENG-TRANSMIT-000071 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONE 5 LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 1793 | 2026-08-28 |  | Review void as requested -KPTG-SADV-004555 | 2026-08-28 | 2026-08-28 | KPTG-SADV-004555 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-21 | D&E-TRANSMIT-001012 | NA | Trade Partner | NXM3S4 - SECURITY GRILLES + Level 1 - CHW & SFN Pipe Layouts - Zone 10 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 4183 | 2026-08-30 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-021045 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-21 | VIA Arch-TRANSMIT-000235 | NA | Consultant | M2 S9 Stair 04 - Issued for Construction (FC-1) | 1 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 1812 | 2026-08-28 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-007399 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-21 | SES AU-TRANSMIT-000004 | NA | Trade Partner | Security Samples | 0 | 6 | 0 | NA | APPROVED | 2026-08-21 | WF-000527 | NA | 2026-09-01 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002172 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-21 | VIA Arch-TRANSMIT-000236 | NA | Consultant | M2 S9 Stair 01 - Issued for Construction (FC-1) | 2 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 1814 | 2026-08-28 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-007403 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-21 | Tradetec-TRANSMIT-000497 | NA | Trade Partner | Tech Data - Titan Premix - Thermal Flowable Concrete | 0 | 1 | 0 | NA | APPROVED | 2026-08-21 | WF-006740 | NA | 2026-08-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-21 | VIA Arch-TRANSMIT-000237 | NA | Consultant | M2 S9 Stair 02 - Issued for Construction (FC-2) | 2 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 1816 | 2026-08-28 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-007407 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-21 | BTWA-TRANSMIT-000102 | NA | Trade Partner | Request to modify and resubmit- Stage 2 - Facade layout | 20 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 525 | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-22 | RDSBIM-TRANSMIT-000196 | NA | Trade Partner | LEVEL-1-C-1-044 ACC WC (RH) FLOOR FINISHES LAYOUT AND ELEVATION | 1 | 0 | 0 | NA | APPROVED | 2026-01-20 |  | 1832 | 2026-01-23 |  |  |  | 2026-01-22 | KPTG-TRANSMIT-011792 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-21 | ADP-TRANSMIT-000404 | NA | Consultant | ADP - M3S4 Office Fitout Services Drawings - IFT Issue | 28 | 0 | 0 | NA | REJECTED | [5 empty] | INCORRRECT DRAWING STATUS |  | 2026-08-21 | KPTG-DA-008214 | Closed | 28 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-21 | ADP-TRANSMIT-000406 | NA | Consultant | ADP - M3S4 Office Fitout - Mechanical Services - IFT Issue | 6 | 0 | 0 | NA | REJECTED | [5 empty] | INCORRECT DRAWING STATUS |  | 2026-08-21 | KPTG-DA-008213 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-21 | VIA Arch-TRANSMIT-000238 | NA | Consultant | Updated drawings and FFE Schedule | 19 | 1 | 0 | NA | APPROVED | 2026-08-21 | NA | 1818 | 2026-08-28 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-21 | VIA Arch-TRANSMIT-000239 | NA | Consultant | S9-S11 Door Schedules | 9 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 1820 | 2026-08-28 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-21 | TTW-TRANSMIT-000047 | NA | Consultant | M3 Stage 6 - Civil Technical Specification | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Wrong attachment |  | 2026-08-21 | Awaiting approval | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D9 | 2026-08-21 | Aurecon-TRANSMIT-000001 | NA | Trade Partner | NEXTDC M3 Client X Antenna - Updated Telco/Elec - Issued for Building Permit | 16 | 2 | 0 | NA | REJECTED | [7 empty] | 2026-08-21 | KPTG-SADV-000164 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-21 | VIA Arch-TRANSMIT-000240 | NA | Consultant | Stage 11_ Level 02 _Concrete Profile update | 1 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 1822 | 2026-08-28 |  |  | 2026-08-27 | 2026-08-27 | KPTG-DA-004402 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-21 | D&E-TRANSMIT-001038 | NA | Trade Partner | SFN Scripts - Issued for Approval | 0 | 11 | 0 | NA | APPROVED | 2026-08-21 | WF-006741 | NA | 2026-08-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-14 | ZLH P/L-SUBRFI-000005 - | NA | Trade Partner | Verification of Details JO-804 Shop Drawing | 6 | 0 | 0 | NA | APPROVED | 2026-08-14 | WF - 001126 | NA | 2026-08-20 |  | NA | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-003254 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | INGEN3D-TRANSMIT-000252 | NA | Trade Partner | I3D-389 District Living - Level 13-14 - Precast Walls - IFC (21-08-2026) | 10 | 0 | 0 | NA | APPROVED | 2026-08-21 | WF-001203 | NA | 2026-08-31 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-21 | DS-TRANSMIT-000089 | NA | Trade Partner | HYD SITE - DRAINAGE | 1 | 0 | 0 | NA | APPROVED |  | NA | 3694 | 2026-01-27 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | INGEN3D-TRANSMIT-000253 | NA | Trade Partner | I3D-389 District Living - Level 14-15 - Precast Walls - IFC (21-08-2026) | 10 | 0 | 0 | NA | APPROVED | 2026-08-21 | WF-001204 | NA | 2026-08-31 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | INGEN3D-TRANSMIT-000254 | NA | Trade Partner | I3D-389 District Living - Level 15-16 - Precast Walls - IFC (21-08-2026) | 10 | 0 | 0 | NA | APPROVED | 2026-08-21 | WF-001206 | NA | 2026-08-31 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | INGEN3D-TRANSMIT-000255 | NA | Trade Partner | I3D-389 District Living - Level 16-17 - Precast Walls - IFC (21-08-2026) | 8 | 0 | 0 | NA | APPROVED | 2026-08-21 | WF-001208 | NA | 2026-08-31 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-21 | Auspan-TRANSMIT-000641 | NA | Trade Partner | Re: 2P349 - NLB? Update IFCed precast shop drawings | 4 | 0 | 4 | KPTG-IntCorr-001345 | APPROVED | [5 empty] | IFC- Waiting for Oliver advise-KPTG-IntCorr-001345 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-21 | WilsonPD-TRANSMIT-000180 | NA | Trade Partner | Sub Water Meters tech data IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, updated register and distributed |  | 2026-08-21 | KPTG-TRANSMIT-007158 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | INGEN3D-TRANSMIT-000257 | NA | Trade Partner | I3D-389 District Living - Level 18-19 - Precast Walls - IFC | 9 | 0 | 0 | NA | APPROVED | 2026-08-21 | WF-001209 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | INGEN3D-TRANSMIT-000259 | NA | Trade Partner | I3D-389 District Living - Level 19-20 - Precast Walls - IFC | 8 | 0 | 0 | NA | APPROVED | 2026-08-21 | WF-001211 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-21 | KPTG-IntCorr-008725 | NA | Trade Partner | Danlai-TRANSMIT-000018- Transmittal Crommelin Data sheet | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | DOCUMENT IS NO LONGER IN USE |  | 2026-08-21 | KPTG-TRANSMIT-003316 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-21 | ELLISAIR-TRANSMIT-000175 | NA | Trade Partner | Stage 11 Ground Floor Zone 1 & 3 Duct layout drawings issued for Construction. | 2 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 1824 | 2026-08-28 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | INGEN3D-TRANSMIT-000261 | NA | Trade Partner | I3D-389 District Living - Level 20-21 - Precast Walls - IFC | 7 | 0 | 0 | NA | APPROVED | 2026-08-21 | WF-001212 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-21 | ASV-TRANSMIT-000128 | NA | Trade Partner | FF&E - Update | 0 | 8 | 0 | NA | APPROVED | 2026-01-21 | WF-003900 | NA | 2026-02-05 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-014267 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | INGEN3D-TRANSMIT-000262 | NA | Trade Partner | I3D-389 District Living - Level 21-22 - Precast Walls - IFC | 7 | 0 | 0 | NA | APPROVED | 2026-08-21 | WF-001213 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-21 | SMEPS-TRANSMIT-000112 | NA | Trade Partner | Lighting Control Topology and Schematics | 1 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 1826 | 2026-08-28 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-21 | PMT Sec-TRANSMIT-000053 | NA | Trade Partner | Re: Updated defected drawings | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing title error |  | 2026-08-21 | KPTG-TRANSMIT-001641 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-21 | SMEPS-TRANSMIT-000385 | NA | Trade Partner | STAGE 4 - Electrical Inground Layout | 1 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 4185 | 2026-08-27 |  | As instructed by Chalie J -The drawing will be placed in IFA template |  | 2026-08-24 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-21 | RDSBIM-TRANSMIT-000018 | NA | Trade Partner | 303COL-BASEMENT 1-EOT 1-IFA -SUBMISSION | 2 | 0 | 0 | NA | APPROVED | 2026-08-21 | WF-000177 | 368 | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-21 | POTTSENG-TRANSMIT-000072 | NA | Trade Partner | GAMC: HYDRAULIC SERVICES - WATER - GROUND TO LEVEL 05 - ZONES 1-5 LAYOUTS | 15 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 1797 | 2026-08-28 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-21 | PMT Sec-TRANSMIT-000054 | SPARK-CRFI-KPG-000629 | Trade Partner | IFC Drawings Requested | 11 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 414 | 2026-08-28 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-001651 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-21 | HDRAus-TRANSMIT-000545 | NA | Trade Partner | M3 SW - Document upload - PDF and CAD | 1 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 4501 | 2026-08-28 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-020881 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-21 | SMEPS-TRANSMIT-000386 | NA | Trade Partner | CONTAINMENT LAYOUT AND SECTION | 3 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected: document title erreor |  | 2026-08-21 | KPTG-SADV-007415 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-21 | SMEPS-TRANSMIT-000019 | NA | Trade Partner | TEMPORARY ELECTRICAL SERVICES LAYOUT (FC-1) | 1 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-08-21 | KPTG-TRANSMIT-001066 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-21 | Tradetec-TRANSMIT-000334 | NA | Trade Partner | IFC - Stage 2 - CP07 | 1 | 0 | 0 | NA | APPROVED | 2026-01-21 | NA | 3696 | 2026-01-22 |  |  | 2026-01-28 | 2026-01-28 | KPTG-TRANSMIT-012023 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-21 | M.2-TRANSMIT-000086 | NA | Trade Partner | Electrical Services Basement & Level 00 Cabletray and Penetrations | 10 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 1799 | 2026-08-28 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-21 | D&E-TRANSMIT-000695 | NA | Trade Partner | MCC-IWP-A Electrical Drawing - Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 4188 | 2026-08-30 |  | IN WORKFLOW AS INSTRUCTED BY ELLIE |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-21 | ZIA-TRANSMIT-000164 | NA | Trade Partner | Re: Stage 4 - CSMS Fibre OM4 Cable via In-ground - Sample Tech data submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect revision |  | 2026-08-21 | KPTG-TRANSMIT-020834 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-21 | ADP-TRANSMIT-000407 | NA | Consultant | ADP - M3S4 Office Fitout Services Drawings - IFT Issue | 34 | 0 | 0 | NA | REJECTED | 2026-08-21 |  |  |  |  | INCORRECT TITLE |  | 2026-08-21 | KPTG-DA-008225 | Closed | 34 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-21 | JCBa-TRANSMIT-000280 | NA | Consultant | Balcony Balustrade Details - IFC | 6 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | WF - 613 | 2026-08-26 |  | NA | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-003276 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-21 | KPTG-TRANSMIT-003254 | NA | Trade Partner | laundry mixer and BBQ tech data | 0 | 2 | 0 | NA | APPROVED | 2026-08-21 | WF - 001135 | NA | 2026-08-26 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-21 | SMEPS-TRANSMIT-000093 | NA | Trade Partner | Fiber runner | 1 | 0 | 0 | NA | APPROVED | 2026-08-21 | WF-000528 | NA | 2026-08-28 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-002199 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-21 | IVS-TRANSMIT-000377 | NA | Consultant | STR - Acoustic Screen Re-Certification Issue | 2 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 4191 | 2026-08-25 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-021109 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-21 | HDRAus-TRANSMIT-000547 | NA | Consultant | Re: M3 Stage 1&4 - Document upload - PDF (Office Fitout) | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Stage 1 and Stage 4 have been submitted under the same transmittal. |  | 2026-08-21 | KPTG-DA-008222 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-22 | SMEPS-TRANSMIT-000006 | NA | Trade Partner | SME Shop Drawing Review | 8 | 0 | 0 | NA | APPROVED | 2026-01-22 | WF-000017 | NA | 2026-01-29 |  |  | 2026-02-03 | 2026-02-03 | KPTG-TRANSMIT-000082 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-21 | IJF-TRANSMIT-000011 | NA | Trade Partner | Joinery prototype drawings - Rev C3 | 7 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 1803 | 2026-08-28 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-003346 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-21 | Ardon-TRANSMIT-000035 | NA | Trade Partner | Batch 5 Shop Drawings | 24 | 0 | 0 | NA | APPROVED | 2026-08-21 | WF-001564 | NA | 2026-09-01 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-21 | Ardon-TRANSMIT-000036 | NA | Trade Partner | Batch 6 Shop Drawings | 26 | 0 | 0 | NA | APPROVED | 2026-08-21 | WF-001565 | NA | 2026-09-01 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-24 | SSem-TRANSMIT-000007 | NA | Trade Partner | S.105 Couriers map | 1 | 0 | 0 | NA | APPROVED | 2026-08-24 | WF - 001138 | NA | 2026-08-28 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-21 | ACG-TRANSMIT-000116 | NA | Trade Partner | M3 Stage 2 - Drawings and Commissioning Sheets for Witness Testing | 10 | 0 | 0 | NA | REJECTED | [5 empty] | the Attached documents seem wrong file attachments in this submitted documents |  | 2026-08-21 | KPTG-SADV-007421 | Closed | 10 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-21 | BTWA-TRANSMIT-000103- MLC Stage 2 - Door stop sample | NA | Trade Partner | MLC Stage 2 - Door stop sample | 0 | 1 | 0 | NA | APPROVED | 2026-08-21 | WF-001144 | NA | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-21 | INTERSIG-TRANSMIT-000015 | NA | Trade Partner | 26-004 Assemble Coburg - WAYFINDING SIGNAGE - SHOP DRAWING ISSUE 04 | 1 | 0 | 0 | NA | APPROVED | 2026-08-21 | WF - 001137 | NA | 2026-08-27 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-18 | HAN IND-TRANSMIT-000008 | NA | Trade Partner | IFA - Steel Shop Drawings FOA-2 | 91 | 0 | 0 | NA | APPROVED | 2026-08-18 | WF-000504 | NA | 2026-08-28 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-002075 | Closed | 91 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-21 | Appselec-TRANSMIT-000142 | NA | Trade Partner | MEL11-APPSELEC-BU-TP-001 | 0 | 1 | 0 | KPTG-IntCorr-000767 | APPROVED |  | NA | NA |  |  | As per the direction from the PC:KPTG-SADV-001943, no workflow is required, just update register. |  | 2026-08-24 | KPTG-SADV-001943, | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-21 | D&E-TRANSMIT-000313 | SPARK-CRFI-KPG-000466 | Trade Partner | MWYCCB - LEVEL 1 / ROOF LEVEL SOUTH SECTIONS & DETAILS MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 415 | 2026-08-28 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-001649 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-22 | SMEPS-TRANSMIT-000007 | NA | Trade Partner | SME Shop Drawing Review | 4 | 0 | 0 | NA | APPROVED | 2026-01-22 | WF-000015 | NA | 2026-01-29 |  |  | 2026-02-03 | 2026-02-03 | KPTG-TRANSMIT-000080 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-21 | TATE_-TRANSMIT-000033 | NA | Trade Partner | TATE HACs/ CEILING/ SCEC O&M | 0 | 1 | 0 | NA | APPROVED | 2026-08-21 | WF - 000575 | NA | 2026-08-26 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-21 | SKS Tech-TRANSMIT-000208 | NA | Trade Partner | Stage 2 - Fuel Services - CLIENT DRAWINGS - ABS-A | 0 | 1 | 0 | NA | APPROVED | 2026-08-21 | WF-001224 | NA | 2026-08-28 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-21 | SKS Tech-TRANSMIT-000210 | NA | Trade Partner | Stage 2 - Fuel Services - CLIENT DRAWINGS - ABS-A | 0 | 1 | 0 | NA | APPROVED | 2026-08-21 | WF-001226 | NA | 2026-08-28 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-28 | TATE_-TRANSMIT-000032 | NA | Trade Partner | HACS, SCEC, CEILING TATE AS-BUILT | 23 | 0 | 0 | NA | REJECTED |  | NA | NA | 2026-08-21 |  | QA rejected |  | 2026-08-28 | 23 | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-21 | Civilex-TRANSMIT-000349 | NA | Trade Partner | Stage 2 - sample submission - 7mm HBCE - High bitumen content emulsion for superior performance | 0 | 1 | 0 | NA | APPROVED | 2026-08-21 | WF-006748 | NA | 2026-08-28 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-021017 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-21 | GHD-TRANSMIT-000011 | NA | Trade Partner | GE1 FC-3 Security Services Documentation | 18 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 549 | 2026-08-28 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-21 | SMEPS-TRANSMIT-000094 | NA | Trade Partner | 110v cable | 0 | 1 | 0 | NA | APPROVED | 2026-08-21 | WF-000531 | NA | 2026-08-28 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-002245 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-21 | HDRAus-TRANSMIT-000548 | NA | Consultant | M3 Stage 4 - Document upload - PDF Locked drawing upload (07/08/26) | 4 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 4194 | 2026-08-26 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-021081 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-21 | ARCH-TRANSMIT-000062 | NA | Consultant | IFC Landscape Update | 8 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 551 | 2026-08-26 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002167 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-22 | SMEPS-TRANSMIT-000008 | NA | Trade Partner | Submit IFC Tech Data HV Cable | 0 | 1 | 0 | NA | APPROVED | 2026-01-22 | WF-000018 | NA | 2026-01-29 |  |  | 2026-01-22 | 2026-01-22 |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-21 | ADP-TRANSMIT-000408 | NA | Consultant | SCADA - Site Wide - Update | 1 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 4196 | 2026-08-27 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-021032 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-21 | RDSBIM-TRANSMIT-000244 | NA | Trade Partner | LINDRUM ¦ LEVEL 04 PARTITION WALL LAYOUT | 1 | 0 | 0 | KPTG-IntCorr-001338 | APPROVED | 2026-08-26 | NA | 749 | 2026-08-31 |  | KPTG-IntCorr-001338 - requested guidance, but no resonance yet. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-21 | RDSBIM-TRANSMIT-000245 | NA | Trade Partner | LINDRUM ¦ LEVEL 05 PARTITION WALL LAYOUT | 1 | 0 | 0 | KPTG-IntCorr-001339 | APPROVED | 2026-08-25 | NA | 750 | 2026-08-31 |  | KPTG-IntCorr-001339 - requested guidance, but no resonance yet. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-21 | RDSBIM-TRANSMIT-000246 | NA | Trade Partner | LINDRUM ¦ LEVEL 06 PARTITION WALL LAYOUT | 1 | 0 | 0 | KPTG-IntCorr-001340 | APPROVED | 2026-08-25 | NA | 751 | 2026-08-31 |  | KPTG-IntCorr-001340 - requested guidance, but no resonance yet. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-21 | RDSBIM-TRANSMIT-000247 | NA | Trade Partner | LINDRUM ¦ LEVEL09 PARTITION WALL LAYOUT | 1 | 0 | 0 | KPTG-IntCorr-001341 | APPROVED | 2026-08-26 | NA | 752 |  |  | KPTG-IntCorr-001341 - requested guidance, but no resonance yet. | 2026-09-01 |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-21 | Auspan-TRANSMIT-000637 | NA | Trade Partner | Re: Precast SD Audit. Level 3 Zone 3. | 7 | 0 | 7 | KPTG-IntCorr-001338 | APPROVED |  | NA | NA |  |  | ifc - waiting for Oliver advise - KPTG-IntCorr-001338 - |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-21 | Auspan-TRANSMIT-000638 | NA | Trade Partner | Re: Precast SD Audit. Levels 3, 4 Zone 1, 2. | 13 | 0 | 0 | KPTG-IntCorr-001339 | APPROVED |  | NA | NA |  |  | ifc - waiting for Oliver advise - KPTG-IntCorr-001339 3 OK TO IFC- KPTG-TRANSMIT-003308, 10 No action required, |  | 2026-08-24 | KPTG-TRANSMIT-003308 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-21 | TTW-TRANSMIT-000151 | NA | Consultant | M3 Stage 2 Civil Drawings | 38 | 0 | 0 | NA | APPROVED | 2026-01-21 | NA | 3698 | 2026-01-27 |  |  |  | 2026-01-22 | KPTG-TRANSMIT-011812 | Closed | 38 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-21 | Auspan-TRANSMIT-000639 | NA | Trade Partner | : Re: Precast SD Audit. Level 3 zone 4,5. | 17 | 0 | 17 | KPTG-IntCorr-001340 | APPROVED |  | NA | NA |  |  | ifc - waiting for Oliver advise - KPTG-IntCorr-001340 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-21 | Auscool-TRANSMIT-000079 | NA | Trade Partner | Greystar Kensington MSSB Schematics | 0 | 1 | 1 | KPTG-IntCorr-001337 | APPROVED |  | NA | NA |  |  | Waiting for Kapitol advise - KPTG-IntCorr-001337 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-21 | INTSPN-TRANSMIT-000060 | NA | Trade Partner | Updated L3 Plans | 5 | 0 | 0 | NA | APPROVED | 2026-08-21 | WF-000715 | NA | 2026-08-28 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-07-24 | KPTG-IntCorr-001832 | NA | Trade Partner | M2 S9-11 - Eaton - UPS Drawings, Cable Schedules & Calcs (IFCs) | 4 | 5 | 0 | NA | APPROVED | 2026-07-24 | NA | 1510 | 2026-08-01 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-007068 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-19 | ccair-TRANSMIT-000049 | NA | Trade Partner | : Mechanical Services Latest Builders works drawing | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Waiting for advice from KPTG-IntCorr-001270 |  | 2026-08-21 | KPTG-IntCorr-001270 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-21 | Nilsen3-TRANSMIT-000101 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 13 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-007824 |  | 2026-08-21 | KPTG-SADV-007824 | Closed | 13 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-21 | Tradetec-TRANSMIT-000165 | NA | Trade Partner | As-builts | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No action required. Updated register |  | 2026-08-21 | KPTG-TRANSMIT-007198 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-21 | CLADC-TRANSMIT-000004 | NA | Trade Partner | Updated Kattsafe aluminium walkway shop drawings | 13 | 0 | 0 | NA | APPROVED | 2026-08-21 | WF-001561 | NA | 2026-08-31 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-007319 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | INGEN3D-TRANSMIT-000256 | NA | Trade Partner | Level 16-17 - PW1067 & PW1068 - New IFA (21-08-2026) | 2 | 0 | 0 | NA | APPROVED | 2026-08-21 | WF-001200 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | INGEN3D-TRANSMIT-000258 | NA | Trade Partner | Level 18-19 - PW1052-2 - New IFA (21-08-2026) | 1 | 0 | 0 | NA | APPROVED | 2026-08-21 | WF-001201 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-21 | Stowe-A-TRANSMIT-000456 | NA | Trade Partner | Tech Data Submission - External Lighting Rev B | 0 | 1 | 0 | NA | APPROVED | 2026-01-21 | WF-003916 | NA | 2026-02-02 |  |  | 2026-02-11 | 2026-02-11 | KPTG-TRANSMIT-012695 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | INGEN3D-TRANSMIT-000260 | NA | Trade Partner | Level 19-20 - PW1066 & PW1069 - New IFA (21-08-2026) | 2 | 0 | 0 | NA | APPROVED | 2026-08-21 | WF-001202 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | INGEN3D-TRANSMIT-000249 | NA | Trade Partner | Level 22 - CD0159 - IFC (20-08-2026) | 1 | 0 | 0 | NA | APPROVED | 2026-08-21 | WF-001214 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | INGEN3D-TRANSMIT-000251 | NA | Trade Partner | Level 12-13 - Precast Walls, Cast In & Loose Plate - IFC (20-08-2026) | 15 | 0 | 0 | KPTG-IntCorr-001249 | APPROVED | 2026-08-27 | WF-1246 | NA | 2026-09-04 |  | Clarification Nich: SUBMITTED ALONG WITH TRN-266 - 13+2 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | INGEN3D-TRANSMIT-000263 | NA | Trade Partner | Level 17-18 - Precast Walls - IFC (21-08-2026) | 9 | 0 | 0 | NA | APPROVED | 2026-08-21 | WF-001216 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | INGEN3D-TRANSMIT-000264 | NA | Trade Partner | Level 17-18 - PW1067-1 & PW1068-1 - New IFA (21-08-2026) | 2 | 0 | 0 | NA | APPROVED | 2026-08-21 | WF-001213 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | INGEN3D-TRANSMIT-000265 | NA | Trade Partner | Precast Walls - No Longer In Use | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | NO LONGER IN USE - |  | 2026-08-21 | KPTG-TRANSMIT-003549 | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | Jangho-TRANSMIT-000328 | NA | Trade Partner | I3D-389 District Living - Level 21-22 - Precast Walls - IFC | 0 | 1 | 0 | NA | APPROVED | 2026-08-21 | WF-001215 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | OveArup-TRANSMIT-000044 | NA | Trade Partner | I3D-389 District Living - Level 21-22 - Precast Walls - IFC | 0 | 1 | 0 | NA | APPROVED | 2026-08-21 | WF-001218 | NA | 2026-09-01 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-003594 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | PCForm-TRANSMIT-000305 | NA | Trade Partner | GA plans updated with pour break numbers and L3 slab profile | 17 | 0 | 0 | process tomorrow | APPROVED | 2026-08-24 | NA | 1150 | 2026-08-31 |  | process tomorrow - 5 ALREADY RE-ISSUED, 11 SUBMITTED | 2026-08-28 | 2026-08-28 | VOIDED | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | PCForm-TRANSMIT-000306 | NA | Trade Partner | level 3 updated with CJ | 5 | 0 | 0 | process tomorrow | APPROVED | 2026-08-24 | NA | 1149 | 2026-08-31 |  | process tomorrow |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-03 | IVS-TRANSMIT-000289 | NA | Consultant | Stage 4 - Roof Gantry Zone C1 Plinths & Zone C2/C3 Plinths Certification Issue (formal Issue) | 4 | 0 | 0 | NA | APPROVED | 2025-12-02 | NA | 1607 | 2025-12-05 |  |  |  | 2025-12-05 | KPTG-TRANSMIT-010681 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-21 | RDSBIM-TRANSMIT-000197 | NA | Trade Partner | NXM3S2 - LEVEL 01 B-1-024 MALE WC-FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-01-21 | NA | 3702 | 2026-01-28 |  |  | 2026-02-17 | 2026-02-19 | KPTG-TRANSMIT-013213 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | PCForm-TRANSMIT-000307 | NA | Trade Partner | Level 4 GA moving CJ | 1 | 0 | 0 | process tomorrow | APPROVED | 2026-08-24 | NA | 1150 | 2026-08-31 |  | process tomorrow | 2026-08-28 | 2026-08-28 | VOIDED | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | Jangho-TRANSMIT-000146 | NA | Trade Partner | Extrusion color Duralloy Surfmist-Matt Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-08-21 | WF-001207 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-21 | Jangho-TRANSMIT-000071 | NA | Trade Partner | Alum sheet color Dulux Duralloy Surfmist - Matt Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-08-21 | WF-001210 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-21 | Electro-TRANSMIT-000002 | NA | Consultant | Specialist Lighting IFC Documentation (Layouts, Schedule and Specification) | 12 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Superseded with Electro-TRANSMIT-000005 |  | 2026-08-25 | KPTG-CONTADV-000301 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-24 | EAEGROUP-TRANSMIT-000011 | NA | Trade Partner | Updated Shop Drawings – Main Corridor 2500A Busduct Runs – FOA-2 | 3 | 0 | 0 | NA | APPROVED | 2026-08-24 | WF-000533 | NA | 2026-09-02 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002189 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | WGAVIC-TRANSMIT-000178 | NA | Consultant | M2 - Civil - Main Works Updates - Issued for Construction | 9 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 1828 | 2026-08-29 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-007455 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-24 | Baigents-TRANSMIT-000044 | NA | Trade Partner | Block 01 - South Wall - Ground Floor Precast Panels Re-Issued for Approval | 28 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 740 | 2026-08-28 |  | NA | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-001188 | Closed | 28 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-24 | EAEGROUP-TRANSMIT-000012 | NA | Trade Partner | Updated Shop Drawings – Mechanical Corridor 1600A Busduct Runs – FOA-2 | 5 | 0 | 0 | NA | APPROVED | 2026-08-24 | WF-000534 | NA | 2026-09-02 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002183 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-06 | SMEPS-TRANSMIT-000003 | NA | Trade Partner | SME shop drawing review | 9 | 0 | 0 | NA | APPROVED | 2026-01-22 | WF-000011, WF-000012, WF-000013, WF-000043 | NA | 2026-01-29 |  |  | 2026-02-10 | 2026-02-10 | KPTG-TRANSMIT-000103 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-24 | D&E-TRANSMIT-001039 | NA | Trade Partner | NXM3S4 - ALL DRAWING / SHOP DRAWINGS ISSUED AS OF 21ST AUGUST 2026 - For Information | 3 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 4198 | 2026-09-02 |  | AS INSTRUCTED BY ELLIE 3 DOCS ARE LOCKED |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-24 | D&E-TRANSMIT-000066 | NA | Trade Partner | Level 01 Block 2 (BOH) Facade Penetration Layout (Zones 5 & 7) - Issued For Approval | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong Naming Convention |  | 2026-08-24 | KPTG-TRANSMIT-001075 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-24 | NXES-TRANSMIT-000082 | NA | Trade Partner | Electrical Penetration Layout | 3 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 526 | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-24 | NXT-TRANSMIT-000501 | NA | Client | FIE CSMS Services Template Rev 2-CSMS POINTS LIST | 0 | 1 | 0 | NA | APPROVED | 2026-08-21 | WF-000233 | NA | 2026-08-31 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | VIA Arch-TRANSMIT-000241 | NA | Consultant | M2 S10 - Stair 05 & 08 Stairs - ISSUED FOR CONSTRUCTION | 3 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 1830 | 2026-08-29 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-007412 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-24 | Auspan-TRANSMIT-000642 | NA | Trade Partner | Resubmit precast shop drawings for approval | 7 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 1805 | 2026-08-29 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-24 | D&E-TRANSMIT-000900 | NA | Trade Partner | Re: NXM3S4 - INDUSTRIAL WATER & FOH & BOF AIR SCHEMATICS - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 4199 | 2026-09-02 |  | AS INSRTUCTED BY ELLIE LOCKED |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-24 | EAEGROUP-TRANSMIT-000013 | NA | Trade Partner | Updated Shop Drawing – Loadbank Busduct Run – FOA-2 | 1 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 553 | 2026-08-28 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002154 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | VIA Arch-TRANSMIT-000242 | NA | Consultant | M2 S11 - Stair 06 & 07 - ISSUED FOR CONSTRUCTION | 2 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 1835 | 2026-08-29 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-007459 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-07-27 | ZLH P/L-SUBRFI-000002 | NA | Trade Partner | Verification of Details | 6 | 0 | 0 | NA | APPROVED | 2026-07-27 | WF-001112 | NA | 2026-07-31 |  | NA | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-003259 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-21 | NXT-TRANSMIT-001204 | NA | Client | 31679 - M3 - PDU - AS BUILT | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-01-21 | KPTG-TRANSMIT-011748 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-24 | INTRFRM-TRANSMIT-000129 | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 15) | 0 | 2 | 0 | NA | APPROVED | 2026-08-24 | WF-000536 | NA | 2026-09-02 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-002131 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-24 | STRBCK-TRANSMIT-000007 | NA | Trade Partner | Civil material conformance | 0 | 7 | 0 | NA | APPROVED | 2026-08-24 | NA | 742 | 2026-08-31 |  | Voided |  | 2026-08-25 | NA | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-24 | INDS-TRANSMIT-000066 | NA | Trade Partner | Wet Fire - Ground Zone 1, 2 & 4 | 3 | 0 | 1 | KPTG-IntCorr-001350 | APPROVED | 2026-08-24 | NA | 1809 | 2026-08-31 |  | IFC- Waiting for Julianne and Brent advise-KPTG-IntCorr-001350 1 Drawing is in hold (Latest IFA-revise & resubmit) |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-24 | NXT-TRANSMIT-000502 | NA | Client | Revit file and CAD file for unit support | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | Distribution |  | 2026-08-24 | KPTG-TRANSMIT-001080 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-24 | SES AU-TRANSMIT-000013 | NA | Trade Partner | Security O&M and As Built | 12 | 0 | 0 | NA | APPROVED | 2026-08-24 | WF - 000576 | NA | 2026-08-28 |  | NA |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | VIA Arch-TRANSMIT-000244 | NA | Consultant | Updated drawings | 31 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 1838 | 2026-08-31 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-24 | KPTG-WTRAN-012757 | NA | Trade Partner | (WF-006753) M3 - DOCUMENT CONTROL REVIEW - DUCT LAYOUT DRAWINGS #4200 TERMINATED AS INSTRUCTED BY ELLIE | 20 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 4200 | 2026-09-02 |  | 20 DOCS PUT IFC WORKFLOW AS INSTRUCTED BY ELLIE |  | 2026-08-24 | NA | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-24 | INDS-TRANSMIT-000067 | NA | Trade Partner | Wet Fire - Level 1 | 5 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 1807 | 2026-08-31 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-24 | RDSBIM-TRANSMIT-000019 | NA | Trade Partner | 303COL ¦ BASEMENT 1 ¦ EOT-2 | 2 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 370 | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-24 | D&E-TRANSMIT-001026 | NA | Trade Partner | NXM3S4 - Roof Level Switchroom - Mechanical Duct Layout - Zone 7 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 4201 | 2026-09-02 |  | AS INSTRUCTED BY ELLIE 1 DOC LOCKED |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-21 | Facx-TRANSMIT-000014 | NA | Trade Partner | Updated glass shop drawings | 9 | 0 | 0 | NA | APPROVED | 2026-01-21 | NA | 3703 | 2026-01-27 |  |  | 2026-02-18 | 2026-02-19 | KPTG-TRANSMIT-013193 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-24 | ASHSS-TRANSMIT-000006 | NA | Trade Partner | NEXTDC GE1- Access stair Drawings | 20 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | The document attached in the drawing is different from the document number available in Aconex. Revision date error |  | 2026-08-24 | KPTG-TRANSMIT-002077 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-08-24 | Nilsen3-TRANSMIT-000259 | NA | Trade Partner | M3-HV-NIL-SA-S-0301-0024- Interface Control Cabling+10pair | 0 | 1 | 0 | NA | APPROVED | 2026-08-24 | WF-006755 | NA | 2026-08-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-24 | D&E-TRANSMIT-001041 | NA | Trade Partner | NXM3S4 - Ground & Level 1 - Builders Works Layout Zone 1 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | [5 empty] | FOR DISTRIBUTION |  | 2026-08-24 | KPTG-TRANSMIT-020850 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-24 | TTW-TRANSMIT-000048 | NA | Consultant | M3 Stage 6 - Civil Technical Specification | 0 | 1 | 0 | NA | APPROVED | 2026-08-24 | NA | 744 | 2026-08-31 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-001224 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-21 | HDRAus-TRANSMIT-000546 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 1 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 4192 | 2026-08-27 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-021114 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-24 | Auspan-TRANSMIT-000646 | NA | Trade Partner | Precast shop drawings for construction. Level 6 | 45 | 0 | 45 | KPTG-IntCorr-001351 | APPROVED | [5 empty] | IFC- Waiting for Oliver advise-KPTG-IntCorr-001351 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-24 | EFP-TRANSMIT-000041 | NA | Trade Partner | FIRE SERVICES SHOP DRAWINGS | 9 | 0 | 0 | NA | APPROVED | 2026-08-24 | WF-000463 | NA | 2026-08-27 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-001197 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-18 | ELLISAIR-TRANSMIT-000126 | NA | Trade Partner | STAGE 09 DATA HALL - CONDENSER WATER SCHEMATIC DRAWING ISSUED FOR APPROVAL. | 1 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 1761 | 2026-08-24 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-007217 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-24 | Auspan-TRANSMIT-000643 | NA | Trade Partner | Precast shop drawings for construction. Level 3 | 1 | 0 | 0 | KPTG-IntCorr-001353 | APPROVED | [5 empty] | IFC- Waiting for Oliver advise-KPTG-IntCorr-001353 KPTG-IntCorr-001356- IFC- 1 drawing only, 1 Drawing superseded by Auspan-TRANSMIT-000648 |  | 2026-08-25 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | SMEPS-TRANSMIT-000113 | NA | Trade Partner | LIGHTING CONTROL SCHEMATIC SHEET 2 | 1 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 1840 | 2026-08-31 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-22 | Stowe-A-TRANSMIT-000457 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - POWER CONTAINMENT LAYOUT - 22.01.2026 | 1 | 0 | 0 | NA | REJECTED | 2026-01-19 |  |  |  |  | The document number inside and outside seems different. | 2026-01-21 | 2026-01-21 | KPTG-DA-004287 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-24 | EFP-TRANSMIT-000042 | NA | Trade Partner | Entire Fire Seismic Report - Clarification Required | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected: Document Numbering is incorrect, request to resubmit: KPTG-TRANSMIT-001185 |  | 2026-08-24 | KPTG-TRANSMIT-001185 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-24 | D&E-TRANSMIT-000068 | NA | Trade Partner | Level 01 Block 2 (BOH) Facade Penetration Layout (Zones 5 & 7) - Issued For Approval | 2 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 746 | 2026-08-31 |  | NA | 2026-08-24 | 2026-08-26 | KPTG-TRANSMIT-001157 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-24 | ZIA-TRANSMIT-000165 | NA | Trade Partner | Stage 4 - CSMS Fibre OM4 Cable via In-ground - Sample Tech data submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | REVISION NOT MENTIONED |  | 2026-08-24 | KPTG-DA-008236 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | ELLISAIR-TRANSMIT-000176 | NA | Trade Partner | Revised Stage 9 Levels 01 Duct drawings issued for Construction. | 2 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 1842 | 2026-08-31 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | ELLISAIR-TRANSMIT-000177 | NA | Trade Partner | Revised Stage 9 Ground Floor Builders Works drawing issued for Construction. | 1 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 1844 | 2026-08-31 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-24 | Arc Plas-TRANSMIT-000002 | NA | Trade Partner | Alternative Insulation Fastener - Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-08-24 | WF-000538 | NA | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | WilsonPD-TRANSMIT-000183 | NA | Trade Partner | S11 L1 Waste and Water IFC | 1 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 1846 | 2026-08-27 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-007480 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | WilsonPD-TRANSMIT-000184 | NA | Trade Partner | Re: S11 L1 Waste and Water IFC | 1 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 1846 | 2026-08-27 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-007480 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-24 | SMEPS-TRANSMIT-000387 | NA | Trade Partner | Stage 4 - Telecommunications drawing set | 11 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 4204 | 2026-09-02 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-24 | Fredon T-TRANSMIT-000035 | NA | Trade Partner | AV Shop Drawings Stage 2 | 6 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected: Required IFA:KPTG-SADV-006061 |  | 2026-08-24 | KPTG-SADV-006061 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-22 | Stowe-A-TRANSMIT-000458 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - ROOF PLANT TRAY ZONE B2 - 22.01.2026 | 1 | 0 | 0 | NA | APPROVED | 2026-01-22 | NA | 3706 | 2026-01-27 |  |  | 2026-01-29 | 2026-01-29 | KPTG-TRANSMIT-012157 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-24 | SMEPS-TRANSMIT-000388 | NA | Trade Partner | Re: Telecommunications drawing- Roof C1 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | INCORRECT STATUS |  | 2026-08-24 | KPTG-DA-008234 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-24 | SMEPS-TRANSMIT-000020 | NA | Trade Partner | TEMPORARY ELECTRICAL SERVICES LAYOUT (FC-1) | 1 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 749 | 2026-08-31 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-001126 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-24 | D&E-TRANSMIT-001042 | NA | Trade Partner | C-MCC-CH-XX Electrical Drawing - Issued for Construction | 1 | 0 | 0 | NA | REJECTED | [5 empty] | TITLE NOT UPDATED |  | 2026-08-24 | KPTG-DA-008238 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-24 | Fredon T-TRANSMIT-000036 | NA | Trade Partner | AV Shop Drawing | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Requested to issue IFA of this drawings:KPTG-SADV-006062 |  | 2026-08-24 | KPTG-SADV-006062 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | WilsonPD-TRANSMIT-000185 | NA | Trade Partner | Instantaneous Hot Water Unit IFA | 0 | 1 | 0 | NA | APPROVED | 2026-08-24 | WF-001580 | NA | 2026-09-03 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | WGAVIC-TRANSMIT-000179 | NA | Consultant | M2 - Stage 11 Level 2 Slab Updates - Issued for Construction | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, updated register and distributed |  | 2026-08-24 | KPTG-TRANSMIT-007242 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-24 | D&E-TRANSMIT-001040 | NA | Trade Partner | NXM3S4 - Ground & Level 1 - Mechanical Duct Layout Zones - Issued For Approval | 4 | 0 | 0 | NA | REJECTED | [5 empty] | already submitted these drawings through the IFC workflow |  | 2026-08-24 | KPTG-DA-008237 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-19 | SKS Tech-TRANSMIT-000213 | NA | Trade Partner | TYPICAL DETAILS BUSDUCT OPENINGS SECURITY TREATMENT for approval | 1 | 0 | 0 | NA | APPROVED | 2026-08-19 | NA | 4205 | 2026-09-02 |  | As instructed by Damian, the document placed in the Security template |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-24 | ACG-TRANSMIT-000117 | NA | Consultant | M3 Stage 2 - Updated Drawings | 9 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 4504 | 2026-09-04 |  | Terminated as advised by Henry Robertson for submitting updated drawings. | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-020943 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | SMEPS-TRANSMIT-000114 | NA | Trade Partner | STS | 0 | 1 | 0 | NA | APPROVED | 2026-08-24 | WF-001582 | NA | 2026-09-03 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-01-22 | B Smart-TRANSMIT-000048 | NA | Consultant | Lift 4 and 5 Core Plans and Elevations | 2 | 0 | 0 | NA | APPROVED | 2026-01-22 | WF-000138 | 223 | 2026-01-27 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-000716 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | WSP ANZ-TRANSMIT-000104 | NA | Consultant | WSP Issued for Building Permit Documents - (Mechanical Services drawings) | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-08-24 | KPTG-TRANSMIT-007248 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-24 | ACCCA-TRANSMIT-000019 | NA | Trade Partner | STORM WATER PITS FOR APPROVAL | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong attachment |  | 2026-08-24 | KPTG-TRANSMIT-001086 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-13 | SES AU-TRANSMIT-000002 | NA | Trade Partner | Security Samples - Cable | 0 | 1 | 0 | NA | APPROVED | 2026-08-13 | WF-000473 | NA | 2026-08-24 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-002099 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-24 | INTERSIG-TRANSMIT-000016 | NA | Trade Partner | Quote: Variation 1- Additional & changes to signage/ QU26-004_v1c | 1 | 0 | 0 | NA | APPROVED | 2026-08-24 | WF - 001139 | NA | 2026-08-28 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-31 | KALLIBRE-TRANSMIT-000024 | NA | Trade Partner | Kenton Woven Panel Sample | 0 | 1 | 0 | NA | APPROVED | 2026-08-31 | WF - 001149 | NA | 2026-09-04 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-24 | Auspan-TRANSMIT-000644 | NA | Trade Partner | Precast shop drawings for construction. Level 4 | 7 | 0 | 7 | KPTG-IntCorr-001359 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001359 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-24 | SMEPS-TRANSMIT-000389 | NA | Trade Partner | SME IFA Documentation - For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 4207 | 2026-09-02 |  | Terminated and submitted for review again - ACC 4218 asper Kazimir |  | 2026-08-25 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-24 | ADP-TRANSMIT-000409 | NA | Consultant | ADP - M3S4 Office Fitout Services Drawings - IFT Issue | 34 | 0 | 0 | NA | REJECTED | [5 empty] | TITLE DIFFERENCE |  | 2026-08-24 | KPTG-DA-008250 | Closed | 34 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-24 | Auspan-TRANSMIT-000645 | NA | Trade Partner | Precast shop drawings for construction. Level 5 | 4 | 0 | 4 | KPTG-IntCorr-001360 | APPROVED | [5 empty] | IFC - Waiting for Oliver advise-KPTG-IntCorr-001360 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-24 | KPTG-IntCorr-000649 - | NA | Trade Partner | Heat Protection Plan Submission | 0 | 1 | 0 | NA | APPROVED | 2026-08-24 | WF - 000558 | NA | 2026-08-28 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-22 | NXT-TRANSMIT-001208 | NA | Client | 31679 - STAGE 2 PDU ITP B1 & B3 | 0 | 28 | 0 | NA | APPROVED | 2026-01-22 | NA | NA |  |  |  |  | 2026-01-21 | KPTG-TRANSMIT-011775 | Closed | 28 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-24 | PMT Sec-TRANSMIT-000055 | NA | Trade Partner | Commissioning ITR | 0 | 1 | 0 | NA | REJECTED | [5 empty] | incorrect document number | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-001653 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-24 | D&E-TRANSMIT-001043 | NA | Trade Partner | BMS Damper Schedule and IP List - Issued for Construction | 0 | 1 | 0 | NA | REJECTED | [5 empty] | COVERSHEET NOT MENTIONED |  | 2026-08-24 | KPTG-DA-008245 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-24 | KBGA-TRANSMIT-000019 | NA | Trade Partner | Tech Data for approval | 0 | 2 | 0 | KPTG-IntCorr-000555 | APPROVED | 2026-08-25 | NA | 757 | 2026-09-02 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-24 | Entire M-TRANSMIT-000099 | NA | Trade Partner | FC - VRF Airconditioning | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Non drawings document to be resubmitted as FOA version only as per the process. |  | 2026-08-24 | KPTG-TRANSMIT-002120 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-24 | D&E-TRANSMIT-001044 | NA | Trade Partner | BMS Damper Schedule and IP List - Issued for Construction | 0 | 1 | 0 | NA | REJECTED | [5 empty] | COVERSHEET MISSING |  | 2026-08-24 | KPTG-DA-008248 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-24 | ASHSS-TRANSMIT-000007 | NA | Trade Partner | NEXTDC GE1- Access stair Drawings | 20 | 0 | 0 | NA | APPROVED | 2026-08-24 | WF-000539 | NA | 2026-09-04 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-002206 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-24 | Baigents-TRANSMIT-000094 | SPARK-CRFI-KPG-000167 | Trade Partner | MCC revised brace issued for fabrication | 3 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 416 | 2026-08-31 | [5 empty] | Open | 0 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | VIA Arch-TRANSMIT-000246 | NA | Consultant | Level 02 Services Cabinets | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed |  | 2026-08-24 | KPTG-TRANSMIT-007283 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-24 | SMEPS-TRANSMIT-000095 | NA | Trade Partner | SEC DB | 0 | 1 | 0 | NA | REJECTED | [5 empty] | here is no need to up rev the non-drawings document, such as Technical Data, Sample, Data sheet to FC revision or change the document revision to For Construction. As per the procedure the document status will subsequently get updated to For Construction once the For Approval document is reviewed with Status Approved or Approved with Comments updated as per requested by chri doh ,workflow is not updated from our side. waiting .. for will advise |  | 2026-08-24 | DRAFT-005005 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | WilsonPD-TRANSMIT-000186 | NA | Trade Partner | Updated sub water meter tech data | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, updated register and distributed |  | 2026-08-24 | KPTG-TRANSMIT-007272 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-22 | DS-TRANSMIT-000091 | NA | Trade Partner | HYD SITE - DRAINAGE | 1 | 0 | 0 | NA | APPROVED | 2026-01-22 | NA | 3708 | 2026-01-29 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-24 | PMT Sec-TRANSMIT-000056 | NA | Trade Partner | Updated Data Sheets | 0 | 5 | 0 | NA | APPROVED | 2026-08-24 | NA | NA | 2026-08-24 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-24 | ACG-TRANSMIT-000118 | NA | Trade Partner | M3 Stage 2 - Updated Drawings and Commissioning Sheets for Witness Testing | 9 | 1 | 0 | NA | REJECTED | [5 empty] | please note that the attached documents are already in review now .one of the documents is only not in review. resubmit the document M3-SEC-ACG-REG-B-0201-9030 separately in a new single transmit. |  | 2026-08-24 | KPTG-SADV-007455 | Closed | 10 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | VIA Arch-TRANSMIT-000247 | NA | Consultant | S9 Level 1 Concrete Profile Plan | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawing, updated register and distributed |  | 2026-08-24 | KPTG-TRANSMIT-007275 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-24 | Jangho-TRANSMIT-000329 | NA | Trade Partner | Skim Coating Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-08-24 | WF-001210 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-24 | RDSBIM-TRANSMIT-000088 | NA | Trade Partner | LEVEL 02 STAGE 4B3 PARTITION WALL | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | closed out by RDSBIM-TRANSMIT-000089 |  | 2026-08-24 | RDSBIM-TRANSMIT-000089 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-24 | RDSBIM-TRANSMIT-000087 | NA | Trade Partner | LEVEL 03 CONCRETE PROFILE PLAN AND SECTIONS | 4 | 0 | 0 | KPTG-IntCorr-001261 - UR Issues | APPROVED | 2026-08-25 | NA | 1162 | 2026-08-27 |  | UR ACC Issues |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-24 | D&E-TRANSMIT-000019 | NA | Trade Partner | L-2 Mechanical Louvers Tech. Data IFA-VML00918 | 0 | 1 | 0 | NA | APPROVED | 2026-08-24 | WF-001219 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-24 | KPTG-WTRAN-012786 | NA | Trade Partner | (WF-006762) M3 - S4 DOCUMENT CONTROL REVIEW -DUCT LAYOUT DRAWINGS #4209 | 16 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 4209 | 2026-09-02 |  | PUT IN IFC WORKFLOW AS PER INSTRUCTED BY ELLIE |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-24 | SMEPS-TRANSMIT-000390 | NA | Trade Partner | SME Documentation - For Construction | 3 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 4227 | 2026-08-31 |  | the documents received above transmittal have IFC unresolved issues in ACC (KPTG-IntCorr-018049) |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | DLTS-TRANSMIT-000101 | NA | Trade Partner | S10-Canopy-Re-IFA Issue | 20 | 0 | 0 | NA | APPROVED | 2026-08-24 | WF-001583 | NA | 2026-09-02 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-007434 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-22 | IVS-TRANSMIT-000320 | NA | Consultant | OSD Tank and Fire Tank Hard Stand | 0 | 1 | 0 | NA | APPROVED | 2026-01-22 | WF-003937 | NA | 2026-01-29 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-24 | NXT-TRANSMIT-000506 | NA | Client | Barkers O&M and Installation Manual | 0 | 7 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-24 | KPTG-TRANSMIT-001102 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-24 | Carr-TRANSMIT-000091 | NA | Consultant | Concrete Profile Plans - IFA | 5 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 372 | 2026-08-31 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-24 | SMEPS-TRANSMIT-000385 | NA | Trade Partner | STAGE 4 - Electrical Inground Layout | 1 | 0 | 0 | NA | APPROVED | 2026-08-21 | NA | 4210 | 2026-09-02 |  | As instructed by Chalie J -The drawing placed in IFA template, as instructed by Oliver S, the drawing has been placed in the IFC template again. |  | 2026-08-27 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | VIA Arch-TRANSMIT-000248 | NA | Consultant | Amenities - Issued For Construction | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, updated register and distributed |  | 2026-08-24 | KPTG-TRANSMIT-007278 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-08-24 | Nilsen3-TRANSMIT-000258 | NA | Trade Partner | Re: M3-HV-NIL-SA-S-0301-0070 - Endurance Cable Cleat | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-08-24 | KPTG-DA-008252 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-24 | KPTG-WTRAN-012789 | NA | Trade Partner | (WF-006764) M3 - S4 DOCUMENT CONTROL REVIEW -PIPE AND DUCT LAYOUT DRAWINGS #4211 | 14 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 4211 | 2026-09-02 |  | TEMPORARY IFC WORKFLOW AS INSTRUCTED BY ELLIE |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-24 | WGAVIC-TRANSMIT-000011 | NA | Consultant | Civil - Revised Drawings - Issued for Construction | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Revision date inside the drawings in the revision date of an older version. |  | 2026-08-24 | DRAFT-005010 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-24 | ZIA-TRANSMIT-000166 | NA | Trade Partner | Re: Stage 4 - CSMS Fibre OM4 Cable via In-ground - Sample Tech data submission | 0 | 1 | 0 | NA | APPROVED | 2026-08-24 | WF-006765 | NA | 2026-08-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-24 | HDRAus-TRANSMIT-000550 | NA | Trade Partner | M3 Stage 1 - Document upload - Office Fitout Re-Issue | 2 | 0 | 0 | NA | APPROVED | [5 empty] | FURTHER ACTION SEEKED |  | 2026-08-24 | KPTG-TRANSMIT-020889 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2025-12-03 | WEBBAUST-TRANSMIT-000060 |  | Consultant | WEBB - B10.2 ICT and Power update | 9 | 0 | 0 |  | REJECTED | [5 empty] | Some of the drawing revisions do not match the Aconex revisions. Requested the originator to correct the revision number and resubmit the transmittal |  | 2025-12-03 | KAPITOL-TRANSMIT-000875 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-22 | EAEGROUP-TRANSMIT-000062 | NA | Trade Partner | Stage 2 – Catcher Busduct INTX Interconnection Pieces (Switchrooms EA–EI) | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Multiple issues inside and outside the drawings. |  | 2026-01-22 | KPTG-DA-004312 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-24 | ADP-TRANSMIT-000411 | NA | Consultant | Stage 4 - Arc Flash Report - FC01 | 0 | 1 | 0 | NA | APPROVED | 2026-08-24 | WF-006766 | NA | 2026-08-28 |  |  |  | 2026-08-25 | KPTG-TRANSMIT-020926 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-24 | INTRFRM-TRANSMIT-000129 | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 15) | 0 | 4 | 0 | NA | APPROVED | 2026-08-24 | WF-000536 | NA | 2026-09-01 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-002284 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-19 | TTW-TRANSMIT-000214 | NA | Trade Partner | M3 Stage 2 Civil Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 4507 | 2026-09-04 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-24 | ARCH-TRANSMIT-000183 | NA | Consultant | MLC - SPR - ISC - T-Schedule [C07] | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | transmitted to concerned parties: KPTG-TRANSMIT-003328 |  | 2026-08-24 | KPTG-TRANSMIT-003328 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-24 | SMEPS-TRANSMIT-000096 | NA | Trade Partner | Tech Data: LV Submains | 0 | 1 | 0 | NA | APPROVED | 2026-08-24 | WF-000540 | NA | 2026-09-02 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-002249 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-24 | ADP-TRANSMIT-000410 | NA | Trade Partner | ADP MEL4561 - S2 Inground drawing | 1 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 4509 | 2026-09-04 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-24 | NXES-TRANSMIT-000084 | NA | Trade Partner | MLC STAGE 1 - SOLAR DESIGN AS BUILT DRAWINGS | 7 | 0 | 0 | KPTG-SADV-006071 | REJECTED | [5 empty] | As Built Drawings-Clarification is required:KPTG-SADV-006071. Revision and revision history are incorrect, requested to reissue: KPTG-SADV-006073 |  | 2026-08-25 | KPTG-SADV-006073 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-24 | IVS-TRANSMIT-000378 | NA | Consultant | Stage 4 - Stair C08 Structural Construction Issue | 2 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 4213 | 2026-08-28 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-021103 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-24 | KPTG-IntCorr-001243 | NA | Trade Partner | Fire Tank Technical Data & Shop Drawings | 4 | 1 | 0 | NA | REJECTED | [5 empty] | QA ERROR - |  | 2026-08-24 | KPTG-TRANSMIT-003568 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | Stowe-A-TRANSMIT-000453 | NA | Trade Partner | Stowe - Tech Data Submission - Nylon Cable Ties | 0 | 1 | 0 | NA | APPROVED | 2026-01-19 | WF-003878 | NA | 2026-01-29 |  |  |  | 2026-02-16 | KPTG-TRANSMIT-012907 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-24 | G&CHyd-TRANSMIT-000018 | NA | Trade Partner | HYD TECH DATA 15 & 40 | 0 | 1 | 0 | NA | APPROVED | 2026-08-24 | WF-001220 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-24 | RDSBIM-TRANSMIT-000089 | NA | Trade Partner | LEVEL 02 STAGE 4B3 PARTITION WALL | 5 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 1152 | 2026-09-01 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-003615 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-24 | WAM-TRANSMIT-000848 | NA | Consultant | A12 Concrete Setout Plans - Ground Floor to Level 16 – IFC Updates | 36 | 0 | 0 | KPTG-IntCorr-001262 | APPROVED | 2026-08-25 | NA | 1159 | 2026-08-28 |  | UR ACC Issues |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-24 | HDRAus-TRANSMIT-000549 | NA | Consultant | M3 Stage 1&4 - Document upload - PDF (Office Fitout) | 7 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 4215 | 2026-08-28 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | WilsonPD-TRANSMIT-000181 | NA | Trade Partner | S10 & S11 Water and Drainage Drawings IFC | 4 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 1834 | 2026-08-31 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-007472 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | WilsonPD-TRANSMIT-000182 | NA | Trade Partner | S9 Water & Drainage drawings for IFC | 2 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 1836 | 2026-08-31 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-007476 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | Eneraque-TRANSMIT-000066 | NA | Trade Partner | Supports Datasheets - IFA | 0 | 1 | 0 | NA | APPROVED | 2026-08-24 | WF-001619 | NA | 2026-09-04 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | ELLISAIR-TRANSMIT-000178 | NA | Trade Partner | Stage 10 Level 2 Pumping String Module drawing issued for Approval. | 1 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 1848 | 2026-08-31 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | DLTS-TRANSMIT-000100 | NA | Trade Partner | S10-Cooling Tower HD Bolts-IFC Issue | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, updated register and distributed |  | 2026-08-24 | KPTG-TRANSMIT-007208 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-24 | Auscool-TRANSMIT-000080 | NA | Trade Partner | AC Schedules | 0 | 1 | 0 | NA | APPROVED | 2026-08-24 | WF-000836 | NA | 2026-08-31 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | Stowe-A-TRANSMIT-000452 | NA | Trade Partner | Stowe - Tech Data Submission - Communication Products | 0 | 1 | 0 | NA | APPROVED | 2026-01-19 | WF-003879 | NA | 2026-01-29 |  |  |  | 2026-02-16 | KPTG-TRANSMIT-012908 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-24 | Auscool-TRANSMIT-000081 | NA | Trade Partner | : Ac Selections | 0 | 1 | 0 | NA | APPROVED | 2026-08-24 | WF-000837 | NA | 2026-08-31 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-24 | PSGANZ-TRANSMIT-000007 | NA | Trade Partner | Tech Data | 0 | 11 | 0 | NA | APPROVED | 2026-08-24 | WF-000838 | NA | 2026-08-31 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-24 | ccair-TRANSMIT-000050 | NA | Trade Partner | Carpark CO Sensor for Approval | 0 | 1 | 0 | KPTG-IntCorr-001324 | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001324 - Tayla to advise as advised by Tayla No action required- |  | 2026-08-25 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | DCN-TRANSMIT-000039 | NA | Trade Partner | M2S9 Link Bridge Structural ABS A Shop Drawings | 9 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-007921 |  | 2026-08-24 | KPTG-SADV-007921 | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | DCN-TRANSMIT-000040 | NA | Trade Partner | M2S9 Link Bridge Architectural ABS A Shop Drawings | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-007922 |  | 2026-08-24 | KPTG-SADV-007922 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | VIA Arch-TRANSMIT-000245 | NA | Consultant | M2 S10-S11 Riser Cupboard Details | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-DA-004343 |  | 2026-08-24 | KPTG-DA-004343 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | Eneraque-TRANSMIT-000067 | NA | Trade Partner | Draft Bulk Tank Manufacturing Data Report (MDR) - Tank 1 | 0 | 1 | 0 | KPTG-IntCorr-002278 | APPROVED | 2026-08-26 | WF-001600 | NA | 2026-09-01 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-24 | Tradetec-TRANSMIT-000166 | NA | Trade Partner | As Builts | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and forwarded to project team |  | 2026-08-24 | KPTG-TRANSMIT-007284 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | ARCST-TRANSMIT-000385 | NA | Trade Partner | S4 - Loading Dock Stair - Issued for Construction | 21 | 0 | 0 | NA | REJECTED | [5 empty] | REVISION DATE NOT UPDATE |  | 2026-08-25 | KPTG-DA-008261 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-25 | STRBCK-TRANSMIT-000007 | NA | Trade Partner | Civil material conformance | 0 | 7 | 0 | NA | APPROVED | 2026-08-25 | NA | 750 | 2026-09-02 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | Stowe-A-TRANSMIT-000451 | NA | Trade Partner | Stowe - Tech Data Submission - Light & Power | 0 | 1 | 0 | NA | APPROVED | 2026-01-19 | WF-003875 | NA | 2026-01-29 |  |  | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-013171 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | KPTG-WTRAN-012799 | NA | Trade Partner | (WF-006770) M3 -S4 DOCUMENT CONTROL REVIEW -PIPE LAYOUT DRAWINGS #4216 | 11 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 4216 | 2026-09-03 |  | 11 DRAWINGS HAS BEEN PALCED IN IFC WORKFLOW AS REQUESTED BY ELLIE |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-24 | fjc-TRANSMIT-000183 | NA | Consultant | No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | The drawings are no longer in use | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-002918 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-24 | fjc-TRANSMIT-000182 | NA | Consultant | Drawing Transmittal | 13 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 743 | 2026-08-27 |  |  | 2026-08-25 | 2026-08-25 | KPTG-SADV-005411 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-24 | fjc-TRANSMIT-000182 | NA | Consultant | Drawing Transmittal | 0 | 2 | 0 | NA | APPROVED | 2026-08-24 | WF-000918 | NA | 2026-08-31 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002975 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-24 | KETE-TRANSMIT-000152 | NA | Trade Partner | Kete - Ground Floor Arch Windows | 4 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-005378 - For LD-KETE-FA-PODIUM-6008, LD-KETE-FA-PODIUM-6009, and LD-KETE-FA-PODIUM-6010, the status, revision, and title are incorrect. | 2026-08-24 | 2026-08-24 | KPTG-SADV-005378 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-25 | NXT-TRANSMIT-000506-OM | NA | Client | Barkers O&M and Installation Manual | 0 | 7 | 0 | NA | APPROVED | 2026-08-25 | NA | 752 | 2026-09-02 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-001223 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | Nilsen3-TRANSMIT-000102 | NA | Trade Partner | Nilsen Sample submissions #16 | 0 | 1 | 0 | NA | APPROVED | 2026-08-25 | WF-001585 | NA | 2026-09-04 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-24 | NXES-TRANSMIT-000057 | NA | Trade Partner | MATV & PTV SCHEMATIC | 2 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 744 | 2026-08-29 |  |  | 2026-08-28 | 2026-08-28 | KPTG-SADV-005453 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | SMEPS-TRANSMIT-000389 | NA | Trade Partner | SME IFA Documentation - For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 4218 | 2026-09-02 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-24 | fjc-TRANSMIT-000186 | NA | Consultant | No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | The drawings are no longer in use. | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-002925 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | Stowe-A-TRANSMIT-000450 | NA | Trade Partner | Stowe - Tech Data Submission - Communication Cabling | 0 | 1 | 0 | NA | APPROVED | 2026-01-19 | WF-003874 | NA | 2026-01-29 |  |  |  | 2026-02-16 | KPTG-TRANSMIT-012914 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-24 | fjc-TRANSMIT-000207 | NA | Consultant | Architecturals - Ground Document Issue | 27 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 745 | 2026-08-27 |  |  | 2026-08-25 | 2026-08-25 | KPTG-SADV-005412 | Closed | 27 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-24 | fjc-TRANSMIT-000207 | NA | Consultant | Architecturals - Ground Document Issue | 0 | 4 | 0 | NA | APPROVED | 2026-08-24 | WF-000920 | NA | 2026-08-25 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002972 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-24 | NXES-TRANSMIT-000075 | NA | Trade Partner | Tech Data Sheet for Superframe LED Strip | 0 | 1 | 0 | NA | APPROVED | 2026-08-24 | WF-000922 | NA | 2026-08-31 |  | KPTG-IntCorr-001354 - As per direction from Charlie, we terminate the WF. | 2026-08-26 | 2026-08-26 | KPTG-IntCorr-001354 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-25 | fjc-TRANSMIT-000187 | NA | Consultant | No Longer In Use | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | The drawings are no longer in use | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002921 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-25 | fjc-TRANSMIT-000188 | NA | Consultant | No Longer In Use | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | The drawings are no longer in use. | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002930 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | KPTG-WTRAN-012802 | NA | Trade Partner | (WF-006772) M3 - DOCUMENT CONTROL REVIEW - DUCT AND PIPE LAYOUT DRAWINGS #4219 | 19 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 4219 | 2026-09-03 |  | 19 DRAWINGS PUT IN IFC WORKFLOW AS INSTRUCTED BY ELLIE |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-25 | EUKAI-TRANSMIT-000026 | NA | Consultant | Site 6 Site Wide Swept PAths | 33 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 755 | 2026-09-02 |  | 32 drawings submitted , 1 CAD file | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-001222 | Closed | 32 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | ELLISAIR-TRANSMIT-000182 | NA | Trade Partner | CCW Schematic drawings re-issued for Approval - Rev. Dates on Aconex amended. | 5 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 1850 | 2026-09-01 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-25 | Rinco-TRANSMIT-000069 | NA | Consultant | Structural drawings Issued for Construction | 6 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 1815 | 2026-08-27 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-25 | NXT-TRANSMIT-000508 | NXT-TRANSMIT-000508 | Client | M3 Stage 6 Data Sheet | 0 | 1 | 0 | NA | APPROVED | 2026-08-25 | WF-000240 | NA | 2026-09-04 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | Stowe-A-TRANSMIT-000449 | NA | Trade Partner | Stowe - Tech Data Submission - Cable Tray & Accessories | 0 | 1 | 0 | NA | APPROVED | 2026-01-19 | WF-003873 | NA | 2026-01-29 |  |  | 2026-02-17 | 2026-02-17 | KPTG-TRANSMIT-013003 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-25 | BTWA-TRANSMIT-000097 | NA | Trade Partner | MLC Approved Samples | 0 | 6 | 0 | NA | APPROVED | 2026-08-25 | WF-001146 | NA | 2026-08-31 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | VIA Arch-TRANSMIT-000249 | NA | Consultant | Stage 11 Level 02 Concrete Profile | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawing, updated register and distributed |  | 2026-08-25 | KPTG-TRANSMIT-007304 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-25 | NXT-TRANSMIT-000509 | NA | Client | Switchrooms (Type,2,3 & 4) - Fire Protection IFA 01 Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-08-25 | WF-000241 | NA | 2026-09-03 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-25 | Blueprin-TRANSMIT-000009 | NA | Trade Partner | Stage 2 signs | 26 | 0 | 0 | NA | REJECTED | [5 empty] | Document Number and revision are incorrect: KPTG-SADV-006072 |  | 2026-08-25 | KPTG-SADV-006072 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-25 | INGEN3D-TRANSMIT-000002 | NA | Trade Partner | Model for Coordination with Precast Detailer | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For information Only |  | 2026-08-25 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | Nilsen3-TRANSMIT-000206 | NA | Trade Partner | Nilsen Shop Drawings - IFC | 9 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 4221 | 2026-09-03 |  | 9 DOCS PLACED IN WORKFLOW AS INSTRUCTED BY ANNA |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-24 | ACG-TRANSMIT-000022 | NA | Trade Partner | D1-SEC-ACG-DRG-B-0201-8018 - No longer in use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Forwarded to all parties |  | 2026-08-24 | KPTG-TRANSMIT-004276 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-24 | Baigents-TRANSMIT-000234 | NA | Trade Partner | Load Bank Handrail FC-1 | 1 | 0 | 1 | KPTG-IntCorr-002341 | APPROVED |  | NA | NA |  |  | Luke to clarify further distribution: KPTG-IntCorr-002341 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-24 | CEDWA-TRANSMIT-000013 | NA | Trade Partner | Civil drawing updates - Parking bay, footpath, Garramilla Verge Swale | 5 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 1330 | 2026-08-28 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-25 | fjc-TRANSMIT-000189 | NA | Consultant | No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | The drawings are no longer in use | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002933 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | Stowe-A-TRANSMIT-000448 | NA | Trade Partner | Stowe - Tech Data Submission - Light Fitting R1 | 0 | 1 | 0 | NA | APPROVED | 2026-01-19 | WF-003872 | NA | 2026-01-29 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | RDSBIM-TRANSMIT-000022 | NA | Trade Partner | NXM2S9 ¦ LEVEL 01 RCP LAYOUT ¦ IFR | 5 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 1852 | 2026-08-27 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-25 | fjc-TRANSMIT-000191 | NA | Consultant | No Longer In Use | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-005398 - THEY DONT MENSION NO LONGER IN USE | 2026-08-25 | 2026-08-25 | KPTG-SADV-005398 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-25 | fjc-TRANSMIT-000193 | NA | Consultant | No Longer In Use | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-005399 - THEY DONT MENSION NO LONGER IN USE. | 2026-08-25 | 2026-08-25 | KPTG-SADV-005399 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-25 | fjc-TRANSMIT-000195 | NA | Consultant | No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | THE DRAWING IS NO LONGER IN USE | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002936 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | KPTG-WTRAN-012811 | NA | Trade Partner | WF-006774) M3 - S4 DOCUMENT CONTROL REVIEW - SEISMIC DRAWING #4224 | 3 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 4224 | 2026-09-03 |  | 3 DOCS PLACED IN IFA WORKFLOW AS INSTRUCTED BY ELLIE |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-25 | ZLH P/L-TRANSMIT-000010 | NA | Trade Partner | Verification of Details: 511SRC-ARC-ZLH-DRG-005 | 7 | 0 | 0 | NA | APPROVED | 2026-08-25 | WF - 001141 | NA | 2026-08-31 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | SKS Tech-TRANSMIT-000214 | NA | Trade Partner | Fwd: Comms Containment Earthing As-Builts | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-25 | KPTG-TRANSMIT-020938 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | SKS Tech-TRANSMIT-000215 | NA | Trade Partner | Fwd: Typical Details for Pre Fab hangers Asbuilt | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-25 | KPTG-TRANSMIT-020941 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-25 | NXT-TRANSMIT-000507 | NA | Client | GK Solutions Bollards Details | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For Distribution only |  | 2026-08-25 | KPTG-TRANSMIT-001117 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-25 | Auspan-TRANSMIT-000648 | NA | Trade Partner | Update IFCed precast shop drawings for construction due to penos added | 2 | 0 | 0 | KPTG-IntCorr-001366 | APPROVED | [5 empty] | IFC- Waiting for Oliver advise-KPTG-IntCorr-001366 |  | 2026-08-25 | KPTG-TRANSMIT-003328 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | Stowe-A-TRANSMIT-000447 | NA | Trade Partner | Stowe - Tech Data Submission - Light Fitting R1 | 0 | 1 | 0 | NA | APPROVED | 2026-01-19 | WF-003872 | NA | 2026-01-29 |  |  | 2026-02-17 | 2026-02-17 | KPTG-TRANSMIT-012976 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | D&E-TRANSMIT-001042 | NA | Trade Partner | Fwd: C-MCC-CH-XX Electrical Drawing - Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 4223 | 2026-08-31 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | SMEPS-TRANSMIT-000391 | NA | Trade Partner | Telecommunications drawing- Roof C1 | 1 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 4226 | 2026-08-31 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | SMEPS-TRANSMIT-000115 | NA | Trade Partner | EXTERNAL POLE LIGHTING | 0 | 1 | 0 | NA | APPROVED | 2026-08-25 | WF-001593 | NA | 2026-09-04 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-25 | TATE_-TRANSMIT-000011 | NA | Trade Partner | MYWCCB - Tate - Training & Traffic Control Room Rev C - IFA Shop Drawing | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing number inside and in Aconex seem different. |  | 2026-08-25 | KPTG-TRANSMIT-001656 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | VIA Arch-TRANSMIT-000246 | NA | Consultant | Level 02 Services Cabinets | 10 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 1856 | 2026-09-01 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-25 | OTIS2-TRANSMIT-000009 | NA | Trade Partner | Existing Lifts Upgrade work- shop drawings for approval | 4 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 375 | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-25 | SMEPS-TRANSMIT-000386 | NA | Trade Partner | CONTAINMENT LAYOUT AND SECTION | 2 | 0 | 0 | NA | APPROVED | 2026-08-25 | WF-006778 | NA | 2026-09-01 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-021138 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-25 | SMEPS-TRANSMIT-000392 | NA | Trade Partner | CONTAINMENT LAYOUT AND SECTION | 1 | 0 | 0 | NA | APPROVED | 2026-08-25 | WF-006778 | NA | 2026-09-01 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-021138 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | VIA Arch-TRANSMIT-000247 | NA | Consultant | S9 Level 1 Concrete Profile Plan | 1 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 1858 | 2026-09-01 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-007416 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | ARCST-TRANSMIT-000386 | NA | Trade Partner | QA checked ,Update Register,Aconex in review (M3S4) | 3 | 0 | 0 | NA | APPROVED | 2026-08-25 | WF-006779 | NA | 2026-08-31 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | Stowe-A-TRANSMIT-000446 | NA | Trade Partner | Stowe - Tech Data Submission - Light Fitting EM 1 | 0 | 1 | 0 | NA | APPROVED | 2026-01-19 | WF-003934 | NA | 2026-02-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | VIA Arch-TRANSMIT-000248 | NA | Consultant | Amenities - Issued For Construction | 7 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 1861 | 2026-09-01 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-25 | ACG-TRANSMIT-000118 | NA | Trade Partner | M3 Stage 2 - Updated Drawings and Commissioning Sheets for Witness Testing | 9 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 4514 | 2026-08-27 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | VIA Arch-TRANSMIT-000249 | NA | Consultant | Stage 11 Level 02 Concrete Profile | 1 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 1863 | 2026-09-01 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-007420 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | SMEPS-TRANSMIT-000394 | NA | Trade Partner | SME IFC Documentation | 6 | 0 | 0 | NA | REJECTED | [5 empty] | REVISION INCORRECT |  | 2026-08-25 | KPTG-DA-008270 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | WSP ANZ-TRANSMIT-000104 | NA | Consultant | WSP Issued for Building Permit Documents - (Mechanical Services drawings) | 9 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 1865 | 2026-09-01 |  |  | 2026-08-28 | 2026-08-28 | KPTG-DA-004423 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-25 | fjc-TRANSMIT-000196 | NA | Consultant | No Longer In Use | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001346 - For ARC-FJC-63011, the PDF was already sent earlier. The latest transmittal only has the CAD file, so I have only updated the register. | 2026-08-25 | 2026-08-25 | KPTG-IntCorr-001346 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | TTW-TRANSMIT-000217 | NA | Trade Partner | Fwd: M3 Stage 4 Building C Civil Drawings | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | For Distribution |  | 2026-08-25 | KPTG-TRANSMIT-020947 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | TTW-TRANSMIT-000218 | NA | Trade Partner | Fwd: M3 Stage 4 Building C Civil Drawings | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For Distribution |  | 2026-08-25 | KPTG-TRANSMIT-020951 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-25 | fjc-TRANSMIT-000197 | NA | Consultant | No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | the document are no longer in use | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002940 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | Eneraque-TRANSMIT-000068 | NA | Trade Partner | Fuel Supply Restriction Orifice Datasheet - Rev 0 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech Data, updated register and distributed |  | 2026-08-25 | KPTG-TRANSMIT-007313 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | Stowe-A-TRANSMIT-000445 | NA | Trade Partner | Stowe - Tech Data Submission - Light Fitting D1 | 0 | 1 | 0 | NA | APPROVED | 2026-01-19 | WF-003935 | NA | 2026-02-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-25 | Firesafe-TRANSMIT-000017 | NA | Trade Partner | Pump room Drawing IFA | 1 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 1165 | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-25 | fjc-TRANSMIT-000198 | NA | Consultant | No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Documents are no longer in use | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002944 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-21 | SES AU-TRANSMIT-000004 | NA | Trade Partner | Security Samples | 0 | 35 | 0 | NA | APPROVED | 2026-08-21 | WF-000527 | NA | 2026-09-01 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-25 | INTRFRM-TRANSMIT-000130 | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 16) | 0 | 1 | 0 | NA | APPROVED | 2026-08-25 | WF-000541 | NA | 2026-09-03 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-002334 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-25 | SMEPS-TRANSMIT-000097 | NA | Trade Partner | Static Bypass FC-1 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | TD doesnt needs to submit with FC revision. or IFC status as per the procedure. |  | 2026-08-25 | DRAFT-005062 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-25 | Auspan-TRANSMIT-000647 | NA | Trade Partner | : Re: L4 IFC Drawings | 44 | 0 | 0 | NA | APPROVED | [5 empty] | 22 are OK TO IFC -KPTG-TRANSMIT-003330, 22 are rejected advised by Kapitol PC-KPTG-IntCorr-001367 |  | 2026-08-25 | KPTG-TRANSMIT-003330 | Closed | 44 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-25 | Auspan-TRANSMIT-000647 | NA | Trade Partner | Re: L4 IFC Drawings | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected- Difference in status- KPTG-SADV-004453 - 2 Drawings |  | 2026-08-25 | KPTG-SADV-004453 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | WSP ANZ-TRANSMIT-000105 | NA | Consultant | Updated - WSP Issued for Building Permit Documents - (Mechanical Services drawing) | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register and distributed to Project team |  | 2026-08-25 | KPTG-TRANSMIT-007316 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-25 | SMEPS-TRANSMIT-000099 | NA | Trade Partner | Tech data R1 fitting | 0 | 1 | 0 | NA | REJECTED | [5 empty] | TD doesnt need to submit as IFC as per the procedure. |  | 2026-08-25 | DRAFT-005064 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-25 | faulk-TRANSMIT-000007 | NA | Trade Partner | RW-02-SD | 1 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 558 | 2026-09-01 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-002322 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-01 | Auspan-TRANSMIT-000017 | NA | Trade Partner | Preliminary marking plans and elevations for zone 4, 5 for review of panel breakup | 7 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Transmittal rejected due to incorrect drawing number in the drawing sheets. |  | 2025-12-01 | KPTG-SADV-000352 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2025-12-03 | WPD-TRANSMIT-000051 |  | Trade Partner | Hydraulic Services As Builts | 2 | 0 | 0 | NA | APPROVED | 2025-12-04 |  | 245 | 2025-12-10 |  | The document has been unlocked as requested by - Alex G |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | Stowe-A-TRANSMIT-000444 | NA | Trade Partner | Stowe - Tech Data Submission - MDB-EJ-RF-2 | 0 | 1 | 0 | NA | APPROVED | 2026-01-19 | WF-003867 | NA | 2026-02-02 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-011995 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-25 | Electro-TRANSMIT-000003 | NA | Consultant | Preliminary IFC Revision Drawings for Record | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Superseded with Electro-TRANSMIT-000005 |  | 2026-08-25 | KPTG-CONTADV-000299 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-25 | Electro-TRANSMIT-000004 | NA | Consultant | IFC drawing update (plans) | 11 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Superseded with Electro-TRANSMIT-000005 |  | 2026-08-25 | KPTG-CONTADV-000302 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-25 | Electro-TRANSMIT-000005 | NA | Consultant | Complete Specialist Lighting IFC Set | 14 | 0 | 0 | KPTG-CONTADV-000300 | APPROVED | 2026-08-26 | NA | 379 | 2026-09-02 |  | Cover sheet needs to revise informed to Electrolight KPTG-CONTADV-000300 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | PARR-TRANSMIT-000221 | NA | Trade Partner | Re: P2685 - NDC M3 - Stage 4 - Battery Rooms - PROMATECT100x FIRE TEST RPEORT | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document details are missing |  | 2026-08-25 | KPTG-DA-008272 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-24 | L.E.S.-TRANSMIT-000057 | NA | Trade Partner | Level Mezz Power and Comms, Level 1 Light, Power and Comms IFA | 6 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 1154 | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-24 | L.E.S.-TRANSMIT-000058 | NA | Trade Partner | cable calculation, discrimination study and max demand report IFA | 0 | 3 | 0 | NA | APPROVED | 2026-08-24 | WF-001225 | NA | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-24 | BIMF-TRANSMIT-000024 | NA | Trade Partner | Drainage Plans up to L4, IFA | 10 | 0 | 0 | NA | APPROVED | 2026-08-24 | NA | 1157 | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-24 | L.E.S.-TRANSMIT-000047 | NA | Trade Partner | Communications Technical Data & Sample Submissions | 0 | 7 | 0 | NA | APPROVED | 2026-08-24 | WF-001221 | NA | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-25 | SMEPS-TRANSMIT-000101 | NA | Trade Partner | Shop drawings: Electrical | 2 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 565 | 2026-08-31 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | Stowe-A-TRANSMIT-000443 | NA | Trade Partner | Stowe - Tech Data Submission - MDB-EJ-RF | 0 | 1 | 0 | NA | APPROVED | 2026-01-19 | WF-003866 | NA | 2026-02-02 |  |  | 2026-01-28 | 2026-01-28 | KPTG-TRANSMIT-012013 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-25 | ZLH P/L-TRANSMIT-000009 | NA | Trade Partner | Verification of Details | 5 | 0 | 0 | NA | APPROVED | 2026-08-25 | WF - 001142 | NA | 2026-08-25 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-25 | Civilex-TRANSMIT-000350 | NA | Trade Partner | Stage 2 - sample submission - Thermal Fill Concrete - Holcim | 0 | 1 | 0 | NA | APPROVED | 2026-08-18 | WF-006784 | NA | 2026-08-31 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-25 | SMEPS-TRANSMIT-000098 | NA | Trade Partner | Tech data: Cable Transit | 0 | 1 | 0 | NA | APPROVED | 2026-08-25 | WF-000547 | NA | 2026-09-03 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-002310 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-25 | Aurecon-TRANSMIT-000147-Com | NA | Consultant | LOD300 Issued for Contract Updates | 32 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 759 | [6 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-25 | Aurecon-TRANSMIT-000147-CSM | NA | Consultant | LOD300 Issued for Contract Updates | 8 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 761 | [6 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-25 | Aurecon-TRANSMIT-000147-ELC | NA | Consultant | LOD300 Issued for Contract Updates | 37 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 763 | [6 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-25 | Aurecon-TRANSMIT-000147-FID | NA | Consultant | LOD300 Issued for Contract Updates | 5 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 765 | [6 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-25 | Aurecon-TRANSMIT-000147-FIP | NA | Consultant | LOD300 Issued for Contract Updates | 9 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 767 | [6 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-25 | Aurecon-TRANSMIT-000147-FUL | NA | Consultant | LOD300 Issued for Contract Updates | 23 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 769 | [6 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-25 | Aurecon-TRANSMIT-000147-HYD | NA | Consultant | LOD300 Issued for Contract Updates | 44 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 771 | 2026-09-04 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | Stowe-A-TRANSMIT-000442 | NA | Trade Partner | Stowe - Tech Data Submission - MDB-EL-RF | 0 | 1 | 0 | NA | APPROVED | 2026-01-19 | WF-003865 | NA | 2026-02-02 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-011988 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-25 | NXT-TRANSMIT-000510 | NA | Client | Switchrooms (Type,2,3 & 4) - Structural IFA 02 Drawings | 30 | 0 | 0 | NA | APPROVED | 2026-08-25 | WF-000244 | NA | 2026-09-04 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-25 | EAEGROUP-TRANSMIT-000002 | NA | Trade Partner | BUSDUCT DATA SHEETS | 0 | 1 | 0 | KPTG-IntCorr-000559 | APPROVED |  | NA | NA |  |  | Distribution only |  | 2026-08-27 | KPTG-TRANSMIT-001160 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-25 | EAEGROUP-TRANSMIT-000003 | NA | Trade Partner | EAE BUSDUCTS DATA SHEET FOR M3 STAGE 6 PROJECT | 0 | 1 | 0 | KPTG-IntCorr-000560 | APPROVED |  | NA | NA |  |  | superseded NXT-TRANSMIT-000522- For distribution only |  | 2026-08-26 | KPTG-TRANSMIT-001187 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-25 | NXT-TRANSMIT-000511 | NA | Client | NEXT DC - M3 - Stage 6 - CDU FC Document submission | 3 | 2 | 0 | NA | APPROVED | 2026-08-25 | WF-000243 | NA | 2026-09-04 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-25 | Baigents-TRANSMIT-000045 | NA | Trade Partner | Block 01 - Level 01 - Precast beams IFC | 108 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 773 | 2026-09-01 |  | NA | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-001156 | Closed | 108 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-25 | PenskePS-TRANSMIT-000003 | NA | Trade Partner | Generator Enclosure - Issued for Construction Drawings. | 11 | 2 | 0 | NA | APPROVED | 2026-08-25 | WF-000548 | NA | 2026-09-09 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-26 | INTRFRM-TRANSMIT-000131 | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 17) | 0 | 5 | 0 | NA | APPROVED | 2026-08-25 | WF-000549 | NA | 2026-09-03 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-002318 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-25 | SMEPS-TRANSMIT-000100 | NA | Trade Partner | FC drawings | 4 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 567 | 2026-08-31 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-10 | crossfir-TRANSMIT-000008 | NA | Trade Partner | Wet Fire - Hydraulic calculations | 0 | 1 | 0 | NA | APPROVED | 2026-08-10 | WF-000455 | NA | 2026-08-19 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002194 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | PARR-TRANSMIT-000220 | NA | Trade Partner | P2671 - NDC M3 Stage 4 - Enclosures - EARTHING SCHEMATIC | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | The documents number and title mismatch |  | 2026-08-25 | KPTG-DA-008274 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | Stowe-A-TRANSMIT-000441 | NA | Trade Partner | Stowe - Tech Data Submission - MDB-EL-RF-2 | 0 | 1 | 0 | NA | APPROVED | 2026-01-19 | WF-003863 | NA | 2026-02-02 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-011983 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | ADP-TRANSMIT-000412 | NA | Consultant | ADP - M3S4 Office Fitout Services Drawings - IFT Issue | 1 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 4237 | 2026-08-31 |  |  | 2026-08-28 | 2026-08-28 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | ADP-TRANSMIT-000412 | NA | Consultant | ADP - M3S4 Office Fitout Services Drawings - IFT Issue | 7 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 4238 | 2026-08-31 |  |  | 2026-08-28 | 2026-08-28 | NA | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | ADP-TRANSMIT-000412 | NA | Consultant | ADP - M3S4 Office Fitout Services Drawings - IFT Issue | 5 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 4239 | 2026-08-31 |  |  | 2026-08-28 | 2026-08-28 | NA | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | ADP-TRANSMIT-000412 | NA | Consultant | ADP - M3S4 Office Fitout Services Drawings - IFT Issue | 5 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 4240 | 2026-08-31 |  |  | 2026-08-28 | 2026-08-28 | NA | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | ADP-TRANSMIT-000412 | NA | Consultant | ADP - M3S4 Office Fitout Services Drawings - IFT Issue | 5 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 4241 | 2026-08-31 |  |  | 2026-08-28 | 2026-08-28 | NA | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | ADP-TRANSMIT-000412 | NA | Consultant | ADP - M3S4 Office Fitout Services Drawings - IFT Issue | 6 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 4242 | 2026-08-31 |  |  | 2026-08-28 | 2026-08-28 | NA | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | ADP-TRANSMIT-000412 | NA | Consultant | ADP - M3S4 Office Fitout Services Drawings - IFT Issue | 5 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 4243 | 2026-08-31 |  |  | 2026-08-28 | 2026-08-28 | NA | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-25 | ADP-TRANSMIT-000413 | NA | Consultant | Stage 4 - Arc Flash Report - FC02 | 0 | 1 | 0 | NA | APPROVED | 2026-08-25 | WF-006790 | NA | 2026-09-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-25 | fjc-TRANSMIT-000199 | NA | Consultant | No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | drawings no longer in use | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002947 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | ELLISAIR-TRANSMIT-000179 | NA | Trade Partner | CCW Schematic drawings issued for Approval | 5 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Drawings revised and resubmitted by Trade Partner via ELLISAIR-TRANSMIT-000182 |  | 2026-08-25 | KPTG-IntCorr-002290 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | Tradetec-TRANSMIT-000327 | NA | Trade Partner | Shop Drawings - Stage 2 - LVP18, LVP21, LVP24 | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Different statuses |  | 2026-01-19 | KPTG-DA-004216 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-25 | fjc-TRANSMIT-000200 | NA | Consultant | No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | DRAWINGS ARE NO LONGER IN USE. | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002950 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-25 | fjc-TRANSMIT-000201 | NA | Consultant | No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | DRAWINGS ARE NO LONGER IN USE. | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002953 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | ELLISAIR-TRANSMIT-000180 | NA | Trade Partner | Revised Stage 9 Ground Floor Duct Sections drawing issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 1870 | 2026-09-01 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-24 | Auspan-TRANSMIT-000643 | NA | Trade Partner | Precast shop drawings for construction. Level 3 | 2 | 0 | 2 | KPTG-IntCorr-001353 | APPROVED |  | NA | NA |  |  | IFC- Waiting for Oliver advise-KPTG-IntCorr-001353 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-25 | fjc-TRANSMIT-000202 | NA | Consultant | No Longer In Use | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | DRAWINGS ARE NO LONGER IN USE | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002956 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | ELLISAIR-TRANSMIT-000181 | NA | Trade Partner | Revised Stage 9 Ground floor Duct & Pipe layout issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 1871 | 2026-09-01 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-07-03 | RDSBIM-TRANSMIT-000079 | NA | Trade Partner | GREYSTAR BASEMENT LEVEL PARTITION WAL -1404 | 1 | 0 | 0 | NA | APPROVED | 2026-08-18 | NA | 1766 | 2026-08-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-25 | Auspan-TRANSMIT-000649 | NA | Trade Partner | Re: Zone 1 RFi 91. Update IFCed shop drawings. Penos for overflow added | 4 | 0 | 4 | KPTG-IntCorr-001372 | APPROVED |  | NA | NA |  |  | IFC waiting for Kapitol advise - KPTG-IntCorr-001372 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-25 | Auspan-TRANSMIT-000648 | NA | Trade Partner | : Update IFCed precast shop drawings for construction due to penos added. | 2 | 0 | 2 | KPTG-IntCorr-001366 | APPROVED |  | NA | NA |  |  | IFC- Waiting for Oliver advise-KPTG-IntCorr-001366 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | Altaire-TRANSMIT-000030 | NA | Trade Partner | NEXTDC M2S9-11 - MASDS Calculations (IFA/IFC) | 0 | 2 | 0 | NA | APPROVED | 2026-08-25 | WF-001591 | NA | 2026-09-04 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | D&E-TRANSMIT-000341 | NA | Trade Partner | NXM3S2 - Chilled & Condensing Water Schematic - Roof & Upper Roof Sheets - Issued For Review | 2 | 0 | 0 | NA | APPROVED | 2026-01-19 | NA | 3676 | 2026-01-28 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-013476 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | Altaire-TRANSMIT-000030 | NA | Trade Partner | NEXTDC M2S9-11 - MASDS Calculations - IFA | 0 | 1 | 0 | NA | APPROVED | 2026-08-25 | WF-001592 | NA | 2026-09-04 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-25 | fjc-TRANSMIT-000203 | NA | Consultant | No Longer In Use | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | DRAWINGS ARE NO LONGER IN USE | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002959 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-25 | fjc-TRANSMIT-000204 | NA | Consultant | No Longer In Use | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | DRAWINGS ARE NO LONGER IN USE | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-002962 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-25 | INTSPN-TRANSMIT-000063 | NA | Trade Partner | L4 Updated plans | 5 | 0 | 0 | NA | APPROVED | 2026-08-25 | WF-000723 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-25 | Auspan-TRANSMIT-000135 | NA | Trade Partner | 6P02(E)-WEATHER JOINT CLARIFICATION REQUIRED | 13 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - as advised by Kapitol PC Kian, no action required |  | 2026-08-25 | NA | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-25 | Auspan-TRANSMIT-000134 | NA | Trade Partner | Architectural panels IFC levels 10 to 17. | 56 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - as advised by Kapitol PC Kian, no action required |  | 2026-08-25 | 56 | Closed | 56 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-25 | Auspan-TRANSMIT-000133 | NA | Trade Partner | Re: DIMENSION CLARIFICATION - PANEL 6P03 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - as advised by Kapitol PC Kian, no action required |  | 2026-08-25 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-25 | Auspan-TRANSMIT-000118 | NA | Trade Partner | Resubmit precast lid for approval. | 2 | 0 | 0 | NA | APPROVED | 2026-08-25 | WF-000724 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-25 | fjc-TRANSMIT-000205 | NA | Consultant | No Longer In Use | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-005410 - they are didnot mension inside the document longer in use. | 2026-08-25 | 2026-08-25 | KPTG-SADV-005410 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | Altaire-TRANSMIT-000057 | NA | Trade Partner | HS1 Dry Fire - IFC Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-01-19 | NA | 3678 | 2026-01-28 |  |  | 2026-01-21 | 2026-01-21 | KPTG-TRANSMIT-011743 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-25 | fjc-TRANSMIT-000206 | NA | Consultant | No Longer In Use | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-005409 - THEY DONT MENSION INSIDE THE DOCUMENT NO LONGER IN USE. | 2026-08-25 | 2026-08-25 | KPTG-SADV-005409 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | Tradetec-TRANSMIT-000169 | NA | Trade Partner | PROPOSED SEWER RELOCATION (Rev 2) | 1 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 1866 | 2026-08-28 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | Nilsen3-TRANSMIT-000103 | NA | Trade Partner | Nilsen Sample submissions #10 Updated | 0 | 1 | 0 | NA | APPROVED | 2026-08-25 | WF-001587 | NA | 2026-09-04 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | SMEPS-TRANSMIT-000116 | NA | Trade Partner | First Floor Containment drawings | 1 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 1868 | 2026-08-28 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | WilsonPD-TRANSMIT-000187 | NA | Trade Partner | Updated S9 North & South Facade Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 1854 | 2026-08-28 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-007484 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | DCN-TRANSMIT-000042 | NA | Trade Partner | Updated- M2S9 Link Bridge Architectural ABS A Shop Drawings | 6 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 1873 | 2026-08-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-25 | DCN-TRANSMIT-000041 | NA | Trade Partner | Updated- M2S9 Link Bridge Structural ABS A Shop Drawings | 9 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-008000 |  | 2026-08-25 | KPTG-SADV-008000 | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-25 | G&CHyd-TRANSMIT-000017 | NA | Trade Partner | HYD TEC DATA | 0 | 1 | 0 | NA | APPROVED | 2026-08-25 | WF-001230 | NA | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-25 | G&CHyd-TRANSMIT-000017 | NA | Trade Partner | HYD TEC DATA | 0 | 2 | 0 | NA | APPROVED | 2026-08-25 | WF-001233 | NA | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-25 | TIVINTL-TRANSMIT-000007 | NA | Trade Partner | Rev.C1 Off‑site Prototype Shop Drawings For Construction — District Living Docklands (DL628) | 16 | 0 | 0 | PROCESS TOMORROW | APPROVED |  | NA | NA |  |  | AS PER KPTG-IntCorr-001259 - FORWARDED TO ALL PARTIES - ACC UPDATED |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | D&E-TRANSMIT-000340 | NA | Trade Partner | NXM3S2 - Ground - Builders Works Layout - B1 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-01-19 | NA | 3673 | 2026-01-23 |  |  | 2026-01-20 | 2026-01-20 | KPTG-TRANSMIT-011670 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-25 | G&CHyd-TRANSMIT-000005 - CLIENT SIGN OFF | NA | Trade Partner | HYD Tech Data | 0 | 9 | 0 | NA | APPROVED | 2026-08-25 | WF-001228 | NA | 2026-08-26 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-25 | G&CHyd-TRANSMIT-000016 - ARCHITECT - CLIENT SIGN OFF | NA | Trade Partner | TECH DATA - Bottle Trap | 0 | 1 | 0 | NA | APPROVED | 2026-08-25 | WF-001231 | NA | 2026-08-26 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-25 | L.E.S.-TRANSMIT-000012 - CLIENT SIGN OFF | NA | Trade Partner | Power outlets and Switches | 0 | 5 | 0 | NA | APPROVED | 2026-08-25 | WF-001227 | NA | 2026-09-02 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-003677 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-25 | L.E.S.-TRANSMIT-000005 - CLIENT SIG OFF | NA | Trade Partner | Carpark Level 2 and 3 light fitting data sheets - IFA | 0 | 3 | 0 | NA | APPROVED | 2026-08-25 | WF-001229 | NA | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-25 | WAM-TRANSMIT-000849 | NA | Consultant | A61 - Bathroom Types IFC | 11 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 1163 | 2026-08-26 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-003657 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-25 | RDSBIM-TRANSMIT-000091 | NA | Trade Partner | DISTLV ¦ MEZZANINE FLOOR STAGE 4B3 PARTITION WALL KEY PLAN ¦ LAYOUT | 5 | 0 | 0 | PROCESS TOMORROW | APPROVED | 2026-08-26 | NA | 1169 | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-25 | KPTG-SADV-005013 | NA | Trade Partner | Acoustic Report | 0 | 1 | 0 | PROCESS TOMORROW | APPROVED | 2026-08-26 | WF-001242 | NA | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-25 | RDSBIM-TRANSMIT-000090 | NA | Trade Partner | DISTLV ¦ GROUND FLOOR STAGE 4B3 PARTITION WALL KEY PLAN | 5 | 0 | 0 | PROCESS TOMORROW | APPROVED | 2026-08-26 | NA | 1168 | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-25 | WAM-TRANSMIT-000850 | NA | Trade Partner | A50 Core update - Issue for construction | 13 | 0 | 0 | PROCESS TOMORROW | REJECTED | [5 empty] | rejected : KPTG-TRANSMIT-003599 - QA ERROR IN 1 DWG |  | 2026-08-26 | KPTG-TRANSMIT-003599 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | D&E-TRANSMIT-000339 | NA | Trade Partner | ISSUED FOR APPROVAL - UPPER ROOF - EQUIPMENT LAYOUTS - ZONE 3 & 5 | 2 | 0 | 0 | NA | APPROVED | 2026-01-19 | NA | 3670 | 2026-01-28 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-013480 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-26 | Auspan-TRANSMIT-000650 | NA | Trade Partner | Precast shop drawings for construction. Level 3 | 2 | 0 | 0 | KPTG-IntCorr-001375 | APPROVED | [5 empty] | IFC- Waiting for Oliver advise-KPTG-IntCorr-001375 No Action required. - KPTG-IntCorr-001376 |  | 2026-08-26 | KPTG-IntCorr-001376 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-26 | PMT Sec-TRANSMIT-000057 | NA | Trade Partner | Re: Commissioning ITR | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document number, Title and revision are not include inside the document |  | 2026-08-26 | KPTG-TRANSMIT-001658 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-26 | WGAVIC-TRANSMIT-000012 | NA | Consultant | Civil - Revised Drawings - Issued for Construction | 8 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 569 | 2026-08-29 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-002262 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-26 | ARCST-TRANSMIT-000387 | NA | Trade Partner | S4 - Loading Dock Stair - Issued for Construction | 21 | 0 | 0 | NA | APPROVED | 2026-08-26 | WF-006791 | NA | 2026-09-03 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-25 | Carr-TRANSMIT-000073 | NA | Consultant | Ground Floor and Upper Level drawings Issued for Approval | 10 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 374 | 2026-09-02 |  | This workflow has been voided due to revisions made to some of the associated drawings from Carr. The remaining drawings will be re-initiated separately under a new workflow. |  | 2026-08-27 | NA | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-26 | SMEPS-TRANSMIT-000395 | NA | Trade Partner | SME IFC Documentation | 6 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 4248 | 2026-09-04 |  |  |  | 2026-08-28 | KPTG-TRANSMIT-021073 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-26 | NXT-TRANSMIT-000515 | NA | Client | O&M Manual | 0 | 1 | 0 | NA | APPROVED | 2026-08-26 | WF-000247 | NA | 2026-09-08 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-26 | PTA-TRANSMIT-000047 | NA | Consultant | BBU, Roof plinth and Block 2 External Ele update | 13 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 775 | 2026-09-03 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-26 | Auspan-TRANSMIT-000655 | NA | Trade Partner | Resubmit shop drawings for approval | 6 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 1819 | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-26 | Auspan-TRANSMIT-000655 | NA | Trade Partner | Resubmit shop drawings for approval | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - difference in status - DRAFT-012037 |  | 2026-08-26 | DRAFT-012037 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-22 | ASV-TRANSMIT-000005 | NA | Trade Partner | Siphonic Stormwater - HDPE | 0 | 1 | 0 | NA | APPROVED | 2026-01-22 | WF-000160 |  | 2026-01-29 |  |  |  | 2026-02-05 | KPTG-TRANSMIT-000708 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-26 | NXT-TRANSMIT-000517 | NA | Client | NEXT DC - M3 - Stage 6 - CRAC FC Document submission | 2 | 6 | 0 | NA | APPROVED | 2026-08-26 | WF-000248 | NA | 2026-09-03 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-26 | Civilex-TRANSMIT-000351 | NA | Trade Partner | Stage 2 - sample submission - Thermal Fill Concrete - Titan | 0 | 1 | 0 | NA | APPROVED | 2026-08-26 | WF-006793 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-26 | ZLH P/L-TRANSMIT-000012 | NA | Trade Partner | BTR Joinery Production | 18 | 0 | 0 | NA | APPROVED | 2026-08-26 | WF - 001143 | NA | 2026-09-02 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-26 | Civilex-TRANSMIT-000352 | NA | Trade Partner | Stage 2 - sample submission - Pavement Concrete mix design Hytec | 0 | 1 | 0 | NA | APPROVED | 2026-08-26 | WF-006795 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-26 | Auspan-TRANSMIT-000651 | NA | Trade Partner | Update IFCed precast shop drawings due to penos added. Level 4 | 7 | 0 | 0 | KPTG-IntCorr-001377 | APPROVED | [5 empty] | IFC- Waiting for Oliver advise-KPTG-IntCorr-001377 6 are OK TO IFC KPTG-TRANSMIT-003357 1 rejected advised by Kapitol PC-KPTG-IntCorr-001384 |  | 2026-08-27 | KPTG-TRANSMIT-003357 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-25 | fjc-TRANSMIT-000207 | NA | Consultant | Architecturals - Ground Document Issue | 8 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 746 | 2026-08-28 |  |  | 2026-08-25 | 2026-08-25 | KPTG-SADV-005412 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | WGAVIC-TRANSMIT-000168 | NA | Consultant | M2 - Structural Notes Update - Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 1700 | 2026-08-26 |  |  | 2026-08-26 | 2026-08-26 | KPTG-DA-004377 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-26 | NXT-TRANSMIT-000518 | NA | Client | NEXT DC - M3 - Stage 6 - FWU FC Document submission | 1 | 2 | 0 | NA | APPROVED | 2026-08-26 | WF-000249 | NA | 2026-09-07 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | WGAVIC-TRANSMIT-000171 | NA | Consultant | M2 - Blockwork and S11 Retaining Walls - Issued for Construction | 17 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 1704 | 2026-08-26 |  |  | 2026-08-26 | 2026-08-26 | KPTG-DA-004379 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-25 | fjc-TRANSMIT-000207 | NA | Consultant | Architecturals - Ground Document Issue | 2 | 0 | 0 | NA | APPROVED | 2026-08-25 | NA | 747 | 2026-08-28 |  |  | 2026-08-26 | 2026-08-26 | KPTG-SADV-005415 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-03 | D&E-TRANSMIT-000068 |  | Trade Partner | ISSUED FOR APPROVAL - ROOF LEVEL - DUCTWORK & PENETRATION LAYOUTS ZONES 1-4 MECHANICAL SERVICES | 4 | 0 | 0 | KPTG-IntCorr-001039 | APPROVED | 2025-12-03 | WF-000089 | 55 | 2025-12-10 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-000418 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-22 | ASV-TRANSMIT-000006 | NA | Trade Partner | Stage 9,10,11 Internal Works | 7 | 0 | 0 | NA | REJECTED | [5 empty] | Need to be revised - KPTG-SADV-000724 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-26 | ADP-TRANSMIT-000040 | NA | Consultant | Old fire reg126 marked as no longer in use | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | No longer in use: transmitted to all-KPTG-TRANSMIT-003338 |  | 2026-08-26 | KPTG-TRANSMIT-003338 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-26 | NXT-TRANSMIT-000519 | NA | Client | Submittal package revised | 0 | 1 | 0 | NA | APPROVED | 2026-08-26 | WF-000250 | NA | 2026-09-09 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-26 | Auspan-TRANSMIT-000652 | NA | Trade Partner | Precast shop drawings for construction. Level 5 | 21 | 0 | 21 | KPTG-IntCorr-001378 | APPROVED | [5 empty] | IFC- Waiting for Oliver advise-KPTG-IntCorr-001378 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-26 | Auspan-TRANSMIT-000653 | NA | Trade Partner | Precast shop drawings for construction. Level 6 | 2 | 0 | 2 | KPTG-IntCorr-001379 | APPROVED | [5 empty] | IFC- Waiting for Oliver advise-KPTG-IntCorr-001379 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-26 | SMEPS-TRANSMIT-000396 | NA | Trade Partner | SME IFC Documentation | 12 | 0 | 0 | NA | REJECTED | [5 empty] | INCORRECT DOCUMENT NUMBER |  | 2026-08-26 | KPTG-DA-008290 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-26 | DS-TRANSMIT-000126 | NA | Trade Partner | Inground Site - Drainage | 1 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 4516 | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-26 | NXT-TRANSMIT-000520 | NA | Client | M3 S6 - LVSB Switchboard Shop Drawing IFC Transmittal | 15 | 0 | 0 | NA | APPROVED | 2026-08-26 | WF-000251 | NA | 2026-09-08 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-26 | M.2-TRANSMIT-000088 | NA | Trade Partner | Carprark Ramp Lighting Lux Reports | 1 | 0 | 1 | KPTG-IntCorr-001380 | APPROVED | [5 empty] | IFI- Waiting for Julianne advise-KPTG-IntCorr-001380 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-26 | Entire M-TRANSMIT-000100 | NA | Trade Partner | Roof penetration Drawings IFC | 2 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 571 | 2026-09-01 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-002224 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-26 | NXT-TRANSMIT-000521 | NA | Client | M3 Stage 6 - LV Switchboards - ABB AU-10026006 - ITP | 0 | 1 | 0 | NA | APPROVED | 2026-08-26 | WF-000252 | NA | 2026-09-07 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-22 | Auspan-TRANSMIT-000055 | NA | Trade Partner | IFC Panels - 145 - 146 & 149 - 151 & 442 - 446 | 10 | 0 | 0 | NA | APPROVED | [5 empty] | IFC drawings, No review required. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-26 | PARR-TRANSMIT-000180 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - BF RETIC LAYOUT & SECTIONS | 12 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 4250 | 2026-09-04 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-26 | NXES-TRANSMIT-000085 | NA | Trade Partner | Level 2 & 3 Electrical Shop Drawings | 6 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 532 | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-26 | PROLMC-TRANSMIT-000016 | NA | Trade Partner | Proline Dog Box Hob Flashing detail submission | 1 | 0 | 0 | NA | APPROVED | 2026-08-26 | WF-001604 | NA | 2026-08-28 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-26 | Auspan-TRANSMIT-000654 | NA | Trade Partner | Update IFCed precast shop drawings. Level 4 | 6 | 0 | 6 | KPTG-IntCorr-001381 | APPROVED | [5 empty] | IFC- Waiting for Oliver advise-KPTG-IntCorr-001381 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-26 | NXT-TRANSMIT-000522 | NA | Client | EAE BUSDUCTS DATA SHEET FOR M3 STAGE 6 PROJECT | 0 | 1 | 0 | NA | APPROVED | [5 empty] | EAEGROUP-TRANSMIT-000003-superseded-distribution Only |  | 2026-08-26 | KPTG-TRANSMIT-001140 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-26 | SMEPS-TRANSMIT-000272 | NA | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0022,0121,0122,0123,0124,0125,0126,0127,0128,0129,0130,0131.0161,0162,0163,0164,0165,0166,0167,0168,0169,0301,0302,0303,0304,0314 | 26 | 0 | 0 | NA | REJECTED | [5 empty] | IFC in Aconex and Attached IFA |  | 2026-08-26 | KPTG-TRANSMIT-001657 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-26 | HDRAus-TRANSMIT-000551 | NA | Consultant | S4 - Facade | 1 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 4252 | 2026-09-01 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-021095 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-26 | SMEPS-TRANSMIT-000273 | SPARK-CRFI-KPG-000504, SPARK-CRFI KPG-000388 & SPARK-CRFI KPG-000340 | Trade Partner | NEL-CNT-SME-2801-BSE-SCH-0001,NEL-CNT-SME-2801-BSE-SDG-0108,0109,0110,0612 | 5 | 0 | 0 | NA | APPROVED | 2026-08-26 |  | 417 | 2026-09-02 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-001667 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-26 | Electro-TRANSMIT-000006 | NA | Consultant | Cover Sheet Specialist Lighting IFC Set | 1 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 379 | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-26 | Appselec-TRANSMIT-000143 | NA | Trade Partner | MEL11C45 - Typical Penetration Plate Details - Issued for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-08-26 | WF-000464 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-22 | BLUESF-TRANSMIT-000032 | NA | Trade Partner | M2-STR-BSF-SDRG-1101-LEVEL 1 (POUR 1) PRECAST DRAWINGS IFA | 34 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000205 | NA | 2026-02-11 |  | Drawings resubmitted as per Kapitol instruction | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-001506 | Closed | 34 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-26 | INTRFRM-TRANSMIT-000124 | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 11) | 0 | 3 | 0 | NA | APPROVED | 2026-08-26 | WF-000552 |  | 2026-08-26 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-002210 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-26 | WGAVIC-TRANSMIT-000013 | NA | Trade Partner | Civil - Revised Details - Issued for Construction | 2 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 573 | 2026-08-31 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-002266 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-26 | NXES-TRANSMIT-000086 | NA | Trade Partner | Revision Update on Solar Design As-Built Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 534 | 2026-08-31 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-003359 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-26 | SMEPS-TRANSMIT-000274 | SPARK-CRFI-KPG-000284, SPARK-CRFI-KPG-000462, SPARK-CRFI-KPG-000462 & SPARK-CRFI-KPG-000462 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0027, 0321, 0322 & 0323 | 4 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 418 | 2026-09-02 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-26 | Leemark-TRANSMIT-000069 | NA | Trade Partner | MCC - Fire Installation ITP &ITR - IFA | 0 | 12 | 0 | NA | REJECTED | [5 empty] | Document number, Title and revision are not include inside the document |  | 2026-08-26 | KPTG-TRANSMIT-001659 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-26 | SMEPS-TRANSMIT-000275 | SPARK-CRFI-KPG-000168 & SPARK-CRFI KPG-000388 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0148,0603 | 2 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 419 | 2026-09-02 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-001669 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-26 | SMEPS-TRANSMIT-000276 | NA | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0602,0613 | 2 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 420 | 2026-09-02 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-26 | SMEPS-TRANSMIT-000252- | NA | Trade Partner | Electrical seismic drawing for approval | 1 | 0 | 0 | NA | APPROVED | 2026-08-26 | WF - 000579 | NA | 2026-09-01 |  | NA |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-26 | SMEPS-TRANSMIT-000277 | SPARK-CRFI-KPG-000265 | Trade Partner | NEL-CNT-SME-2801-BSE-SCH-0002 | 1 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 421 | 2026-09-02 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-26 | INTRFRM-TRANSMIT-000132 | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 18) | 0 | 1 | 0 | NA | APPROVED | 2026-08-26 | WF-000554 | NA | 2026-09-04 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-002326 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-22 | BLUESF-TRANSMIT-000033 | NA | Trade Partner | M2-STR-BSF-SDRG-1101-LEVEL 1 (POUR 2) PRECAST DRAWINGS IFA | 31 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000206 |  | 2026-02-11 |  | Drawings resubmitted as per Kapitol instruction | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-001787 | Closed | 31 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-26 | Aurecon-TRANSMIT-000147-MEC | NA | Consultant | LOD300 Issued for Contract Updates | 46 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 780 | 2026-09-03 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-26 | Aurecon-TRANSMIT-000147-TEL | NA | Consultant | LOD300 Issued for Contract Updates | 29 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 779 | 2026-09-03 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-26 | SMEPS-TRANSMIT-000278 | SPARK-CRFI KPG-000302 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0184,0185,0186 | 3 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 426 | 2026-08-26 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-001673 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-26 | ADP-TRANSMIT-000147 | NA | Consultant | ADP MEL4680 - Updated HYD Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 576 | 2026-08-31 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-002215 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-26 | NXES-TRANSMIT-000087 | NA | Trade Partner | ISC CONDUIT MARKUP FOR SCOREBOARD SYSTEM | 1 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 536 | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-08-26 | Nilsen3-TRANSMIT-000260 | NA | Trade Partner | Nilsen ELC Shop Drawings -IFC Updated | 1 | 0 | 0 | NA | APPROVED | 2026-08-26 | WF-006799 | NA | 2026-09-08 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-26 | ADP-TRANSMIT-000148 | NA | Consultant | ADP - Updated Electrical Protection Report FC-02 | 0 | 1 | 0 | NA | APPROVED | 2026-08-26 | NA | 578 | 2026-08-31 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-002215 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-08-26 | Nilsen3-TRANSMIT-000247 | NA | Trade Partner | M3-HV-NIL-SA-S-0301-0028 - Cable Cleats - Rev 1 - PANDUIT | 0 | 1 | 0 | NA | APPROVED | 2026-08-26 | WF-006800 | NA | 2026-09-16 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-26 | SMEPS-TRANSMIT-000279 | SPARK-CRFI-KPG-000168, SPARK-CRFI KPG-000363, SPARK-CRFI-KPG-000462 & SPARK-CRFI-KPG-000504 | Trade Partner | Re: NEL-CNT-SME-2801-BSE-SDG-0022,0121,0122,0123,0124,0126,0127,0129,0130,0131.0161,0162,0163,0164,0165,0166,0167,0168,0169,0301,0302,0303,0304,0314 | 24 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 423 | 2026-09-02 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-001671 | Closed | 24 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-26 | VERTIV-TRANSMIT-000075 | NA | Trade Partner | NEXT DC GE01 _ STRUCTURAL DRAWINGS (FOA-2) | 1 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 580 | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-22 | BLUESF-TRANSMIT-000034 | NA | Trade Partner | M2-STR-BSF-SDRG-1101-LEVEL 1 (POUR 3) PRECAST DRAWINGS IFA | 11 | 0 | 0 |  | APPROVED | 2026-02-04 | WF-000207 |  | 2026-02-11 |  | Drawings resubmitted as per Kapitol instruction | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-001786 | Closed | 11 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-26 | SMEPS-TRANSMIT-000280 | SPARK-CRFI-KPG-000363 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0125, 0128 | 2 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 424 | 2026-09-02 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-26 | Nilsen3-TRANSMIT-000256 | NA | Trade Partner | Nilsen Sample Typical Busduct Opening Cover | 0 | 1 | 0 | NA | APPROVED | 2026-08-26 | WF-006801 | NA | 2026-09-22 |  | A s intructed by damian the document will be in review in security template |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-08-20 | VIA Arch-TRANSMIT-000034 | NA | Trade Partner | 22kV Amenites Update | 2 | 0 | 0 | NA | APPROVED | 2026-08-20 | WF-006730 | NA | 2026-09-02 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-020995 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-26 | Baigents-TRANSMIT-000046 | NA | Trade Partner | Block 01 - Level 01 - Precast Columns updated to new reo configuration-Issued for Construction | 45 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 783 | 2026-09-04 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-001167 | Closed | 45 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-26 | D&E-TRANSMIT-001045 | NA | Trade Partner | BMS Documentation - Issued for Construction | 0 | 2 | 0 | NA | REJECTED |  | NA | NA |  |  | the document number and revision number mismatch |  | 2026-08-26 | KPTG-TRANSMIT-020997 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-26 | Aurecon-TRANSMIT-000147-SCH | NA | Consultant | LOD300 Issued for Contract Updates | 0 | 2 | 0 | KPTG-IntCorr-000572 | APPROVED | 2026-08-27 | NA | 792 | 2026-09-04 |  | Uploaded on ACC | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-001219 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-26 | SMEPS-TRANSMIT-000281 | NA | Trade Partner | NEL-CNT-SME-2990-ELC-SAM-0001 | 0 | 1 | 0 | NA | APPROVED | 2026-08-26 | NA | NA | 2026-09-02 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-26 | RBG-TRANSMIT-000013 | NA | Trade Partner | Crane Base Drawings IFC | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update register only |  | 2026-08-26 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-26 | Stowe-A-TRANSMIT-000683 | NA | Trade Partner | STOWE - AS BUILTS | 5 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Reject: the documents with revision ABS-02 have already been reviewed and approved. |  | 2026-08-26 | KPTG-SADV-007499 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-26 | Baigents-TRANSMIT-000095 | NA | Trade Partner | MCC - Operable Wall - Steel Shop Drawings - Issued for Approval | 19 | 0 | 0 | NA | REJECTED | [5 empty] | The drawing number code for Operable wall is incorrect |  | 2026-08-26 | KPTG-TRANSMIT-001660 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-22 | BLUESF-TRANSMIT-000035 | NA | Trade Partner | M2-STR-BSF-SDRG-1101-LEVEL 1 (POUR 4) PRECAST DRAWINGS IFA | 10 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000208 |  | 2026-02-11 |  | Drawings resubmitted as per Kapitol instruction. | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-001997 | Closed | 10 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-26 | HDRAus-TRANSMIT-000552 | NA | Consultant | SW drawing update | 1 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 4519 | 2026-08-28 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-26 | ADP-TRANSMIT-000149 | NA | Consultant | ADP - MEL4680 - Updated Electrical Drawings | 7 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 583 | 2026-08-31 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-26 | Leemark-TRANSMIT-000070 | SPARK-CRFI-KPG-000613 & SPARK-CRFI-KPG-000365 | Trade Partner | MCC - Site Plan & WET FIRE LAYOUT - LEV 1 ZONE 10 shop drawigs - IFA | 2 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 425 | 2026-09-02 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-26 | EUKAI-TRANSMIT-000028 | NA | Consultant | Paramount Road revised access - swept paths, signs and linemarking | 12 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 786 | 2026-09-03 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-26 | NXT-TRANSMIT-000523 | NA | Client | M3S6 Psub FAT reports - 14 units Batch 1 | 0 | 14 | 0 | NA | APPROVED |  | NA | NA |  |  | distribution |  | 2026-08-26 | KPTG-TRANSMIT-001155 | Closed | 14 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | Baigents-TRANSMIT-000012 | NA | Trade Partner | Re: C08 Stair Steel - Issued for Approval | 18 | 0 | 0 | NA | APPROVED | 2026-08-20 | WF-006726 | NA | 2026-08-25 |  |  | 2026-08-26 | 2026-08-27 | KPTG-TRANSMIT-021012 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-26 | Rinco-TRANSMIT-000070: | NA | Consultant | Structural drawings Issued for Construction | 6 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 1821 | 2026-08-31 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-26 | crossfir-TRANSMIT-000035 | NA | Trade Partner | Wet Fire - Level 11 to 15, IFA | 3 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 799 | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-26 | B Smart-TRANSMIT-000107 | NA | Consultant | Wall type details updated with CSR number | 5 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 801 | 2026-08-31 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-22 | BLUESF-TRANSMIT-000036 | NA | Trade Partner | M2-STR-BSF-SDRG-1101-LEVEL 1 (POUR 6) PRECAST DRAWINGS IFA | 5 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000209 |  | 2026-02-11 |  | Drawings resubmitted as per Kapitol instruction | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-003170 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-26 | PROLMC-TRANSMIT-000017 | NA | Trade Partner | Proline Box Gutter Detail Rev 4 submission | 3 | 0 | 0 | NA | APPROVED | 2026-08-26 | WF-001605 | NA | 2026-08-31 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-007441 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-26 | Diadem-TRANSMIT-000014 | NA | Consultant | Wayfinding Package IFT-2 | 101 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-DA-004394 |  | 2026-08-26 | KPTG-DA-004394 | Closed | 101 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-26 | SMEPS-TRANSMIT-000117 | NA | Trade Partner | Peno Schedule Level 01 | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-008043 |  | 2026-08-26 | KPTG-SADV-008043 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-26 | Carr-TRANSMIT-000092 | NA | Consultant | Interiors - Doors, EOT and Joinery Updates | 15 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 381 | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-26 | SES AU-TRANSMIT-000011 | NA | Trade Partner | Security IFC re-submission post IFA review returns | 4 | 0 | 0 | KPTG-IntCorr-002322 | APPROVED |  | NA | 1759 | 2026-09-01 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-26 | NCFGroup-GCOR-000140 | NA | Trade Partner | Concrete Mix Design | 0 | 1 | 0 | NA | APPROVED | 2026-08-26 | WF-001601 | NA | 2026-09-04 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-26 | Nilsen3-TRANSMIT-000101 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 9 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 1877 | 2026-09-04 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-26 | Nilsen3-TRANSMIT-000101 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 3 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 1878 | 2026-09-04 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-26 | Eneraque-TRANSMIT-000042 | NA | Trade Partner | ENE - Typical Pipe Supports | 2 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 1874 | 2026-08-31 |  | Resubmitted for VIA & WGA review as advised by Project Coordinator |  |  |  | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-26 | Eneraque-TRANSMIT-000067 | NA | Trade Partner | Draft Bulk Tank Manufacturing Data Report (MDR) - Tank 1 | 0 | 1 | 0 | NA | APPROVED | 2026-08-26 | WF-001600 | NA | 2026-09-01 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-22 | BLUESF-TRANSMIT-000037 | NA | Trade Partner | M2-STR-BSF-SDRG-1101-LEVEL 1 (PRECAST COLUMN) PRECAST DRAWINGS IFA | 40 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000203 |  | 2026-02-11 |  | Drawings resubmitted as per Kapitol instruction | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-001577 | Closed | 40 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-26 | Tradetec-TRANSMIT-000170 | NA | Trade Partner | Combined Services | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated register. For information only |  | 2026-08-26 | NA | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-27 | Nilsen3-TRANSMIT-000104 | NA | Trade Partner | Nilsen Sample submissions #17 | 0 | 1 | 0 | NA | APPROVED | 2026-08-27 | WF-001606 | NA | 2026-09-08 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-26 | OTIS2-TRANSMIT-000010 | NA | Trade Partner | New EOT Lift - Revised Shop Drawings & Hall fixture drawing for review and Approaval | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Submitted drawings revisions and status not matching with actual drawings |  | 2026-08-26 | KPTG-CONTADV-000307 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-26 | L.E.S.-TRANSMIT-000060 | NA | Trade Partner | A50 Core update - Issue for construction | 17 | 0 | 0 | PROCESS TOMORROW | APPROVED | [9 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-26 | Firesafe-TRANSMIT-000018 | NA | Trade Partner | A50 Core update - Issue for construction | 0 | 1 | 0 | NA | APPROVED | 2026-08-27 | WF-001243 | NA | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-27 | KPTG-WTRAN-012870 | NA | Trade Partner | (WF-006803) M3 - DOCUMENT CONTROL REVIEW - chiller layout drawings #4256 | 10 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 4256 | 2026-09-05 |  | 10 DOCS PALCED IN WORKFLOW AS INSTRUCTED BYE ELLIE |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-27 | Auspan-TRANSMIT-000657 | NA | Trade Partner | Re: Resubmit shop drawings for approval | 1 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 1824 | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-27 | Auspan-TRANSMIT-000656 | NA | Trade Partner | Precast panel 5P1034 for construction | 1 | 0 | 1 | KPTG-IntCorr-001387 | APPROVED | [5 empty] | IFC- Waiting for Oliver advise-KPTG-IntCorr-001387 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-27 | crossfir-TRANSMIT-000057 1 | NA | Trade Partner | Wet Fire - Ground Floor, Sprs to glazing near to booster added | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-08-27 | KPTG-TRANSMIT-003264 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-27 | ZLH P/L-TRANSMIT-000014 | NA | Trade Partner | Verification of Details JO-804 Shop Drawing | 6 | 0 | 0 | NA | APPROVED | 2026-08-27 | WF - 001144 | NA | 2026-09-02 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-23 | SMEPS-TRANSMIT-000147 | NA | Trade Partner | SME - IFA Sample submissions | 0 | 5 | 0 | NA | REJECTED | [5 empty] | The Aconex revision does not match the document revision.-KPTG-TRANSMIT-011827 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-27 | Auspan-TRANSMIT-000658 | NA | Trade Partner | Re: Corbel - Zone 4 | 2 | 0 | 2 | KPTG-IntCorr-001388 | APPROVED | [5 empty] | IFC- Waiting for Oliver advise-KPTG-IntCorr-001388 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-27 | Leemark-TRANSMIT-000071 | NA | Trade Partner | Re: MCC - Fire Installation ITP &ITR - IFA | 0 | 12 | 12 | NA | APPROVED | 2026-08-27 | NA | AN | 2026-09-03 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-27 | KPTG-WTRAN-012873 | NA | Trade Partner | (WF-006804) M3 - DOCUMENT CONTROL REVIEW -D&E Builders Works drawings #4259 | 35 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 4259 |  |  | 35 DOCS IN WORKFLOW AS INSTRUCTED BY ELLIE TERMINATED AS INSTRUCTED BY ELLIE REASON- terminate ACC 4259 D&E have 2 x drawings that need an Up Rev. Let me know when complete. Once new drawings are transmitted if you can please put all of the drawings back in another IFC WF. |  | 2026-08-27 | NA | Closed | 35 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-27 | PSGANZ-TRANSMIT-000016 | NA | Trade Partner | Fire Detection tech. data submission - ASD PSU | 0 | 1 | 0 | NA | APPROVED | 2026-08-27 | WF-000562 | NA | 2026-09-07 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-08-27 | DI-TRANSMIT-000165 | NA | Trade Partner | Re: Updted as Builts | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision |  |  | DRAFT-010569 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-27 | SES AU-TRANSMIT-000005 | NA | Trade Partner | Security Samples - New Devices | 0 | 5 | 0 | NA | APPROVED | 2026-08-27 | WF-000563 | NA | 2026-09-07 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-26 | NXES-TRANSMIT-000075 | NA | Trade Partner | Tech Data Sheet for Superframe LED Strip | 0 | 1 | 0 | NA | APPROVED | 2026-08-26 | WF-000928 | NA | 2026-08-31 |  | KPTG-IntCorr-001355 - As per direction from Charlie, we terminate the WF | 2026-08-27 | 2026-08-27 | KPTG-IntCorr-001355 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-27 | NXES-TRANSMIT-000075 | NA | Trade Partner | Tech Data Sheet for Superframe LED Strip | 0 | 1 | 0 | NA | APPROVED | 2026-08-27 | WF-000929 | NA | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-26 | KPTG-WTRAN-001702 | NA | Consultant | FJC ARCHITECTURAL DRAWINGS | 25 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 748 | 2026-08-29 |  |  | 2026-08-31 | 2026-08-31 | KPTG-SADV-005481 | Closed | 25 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-27 | SMEPS-TRANSMIT-000118 | NA | Trade Partner | Peno Schedule Level 01 | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected: Incorrect revision |  | 2026-08-27 | KPTG-SADV-008050 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-23 | SMEPS-TRANSMIT-000146 | NA | Trade Partner | Re: SME - IFA Sample submissions | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The Aconex revision does not match the document revision.-KPTG-TRANSMIT-011829 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-27 | Auspan-TRANSMIT-000129 | NA | Trade Partner | IFC panel 1P379 as sample panel. | 1 | 0 | 0 | NA | APPROVED | 2026-08-27 | WF-001151 | NA | 2026-08-31 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-27 | Auspan-TRANSMIT-000129 | NA | Trade Partner | panel 1P379 as sample panel. | 1 | 0 | 0 | NA | APPROVED | 2026-08-27 | WF-001152 | NA | 2026-09-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-27 | RDSBIM-TRANSMIT-000248 | NA | Trade Partner | LINDRUM ¦ LEVEL 08 PARTITION WALL LAYOUT | 1 | 0 | 0 | KPTG-IntCorr-001357 | APPROVED | 2026-08-31 | NA | 754 | 2026-09-03 |  | KPTG-IntCorr-001357-requested guidance, but no resonance yet. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-27 | WilsonPD-TRANSMIT-000188 | NA | Trade Partner | All-In-One Zip Tap | 0 | 1 | 0 | NA | APPROVED | 2026-08-27 | WF-001621 | NA | 2026-09-07 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-27 | RDSBIM-TRANSMIT-000249 | NA | Trade Partner | LINDRUM ¦ LEVEL 07 PARTITION WALL LAYOUT | 1 | 0 | 0 | KPTG-IntCorr-001358 | APPROVED | 2026-08-31 | NA | 755 | 2026-09-03 |  | KPTG-IntCorr-001358-requested guidance, but no resonance yet. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-20 | Baigents-TRANSMIT-000012 | NA | Trade Partner | Re: C08 Stair Steel - Issued for Approval | 43 | 0 | 0 | NA | APPROVED | 2026-08-20 | WF-006726 | NA | 2026-08-25 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-021003 | Closed | 25 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-27 | SYNACC-TRANSMIT-000010 | NA | Trade Partner | Transmittal - Roof Access - Level 28-29 | 6 | 0 | 6 | KPTG-IntCorr-001359 | APPROVED | [5 empty] | KPTG-IntCorr-001359 - requested guidance, but no resonance yet. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-27 | HDRAus-TRANSMIT-000553 | NA | Consultant | Stage 4 - Facade Type | 4 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 4262 | 2026-08-31 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-021096 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-27 | 4DW-TRANSMIT-000088 | NA | Consultant | Roof Plinth. Issued For Coordination. | 9 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 788 | [6 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-27 | KPTG-WTRAN-012876 | NA | Trade Partner | (WF-006807) M3 -S4 DOCUMENT CONTROL REVIEW - MEC-ELEC LAYOUT DRAWINGS#4263 | 4 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 4263 | 2026-09-05 |  | 4 DOCS PLACED IN IFC WORKFLOW AS INSTRUCTED BY ELLIE |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-03 | SMEPS-TRANSMIT-000089 |  | Trade Partner | IFC - Structured Cabling Schematic | 1 | 0 | 0 | KPTG-IntCorr-001036 | APPROVED | 2025-12-03 | WF-000088 | 51 | 2025-12-10 |  |  |  | 2026-04-23 | KPTG-TRANSMIT-000682 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-01 | HDRAus-TRANSMIT-000072 | NA | Consultant | Architectural Documentation - Door Schedule & Statutory Signage | 4 | 1 | 0 | NA | APPROVED | 2025-12-01 | NA | 1271 | 2025-12-08 |  |  | 2026-01-21 | 2026-01-22 | KPTG-TRANSMIT-002323 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-27 | ACG-TRANSMIT-000119 | NA | Consultant | M3 Stage 2 - Updated External Drawings - SITE PLAN - PART 1 | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected: The submitted document does not have any previous revision and has been submitted with As-Built status. |  | 2026-08-27 | KPTG-SADV-007509 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-27 | Auscool-TRANSMIT-000117 | NA | Trade Partner | IFC - MSSB load tables, MSSB Schematics and MSSB Meters | 0 | 1 | 0 | KPTG-IntCorr-001361 | APPROVED | 2026-08-28 | WF-000932 | NA | 2026-09-02 |  | KPTG-IntCorr-001361 - requested guidance, but no resonance yet. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-27 | NXES-TRANSMIT-000076 | NA | Trade Partner | Typical Electrical Switchboards (DB, TOB, MP) | 3 | 0 | 0 | KPTG-IntCorr-001362 | APPROVED | 2026-08-28 | NA | 753 | 2026-09-02 |  | KPTG-IntCorr-001362 - requested guidance, but no resonance yet. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-27 | Entire M-TRANSMIT-000101 | NA | Trade Partner | Ground Floor Mechanical Shop Drawings IFC | 2 | 0 | 0 | NA | APPROVED | 2026-08-27 | 589 | NA |  |  | Rejected: The latest revision of the document available with us is Rev. FOA-1, which was reviewed and marked as Rejected. FC-01 has been submitted. processed as instructed by chri. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-27 | faulk-TRANSMIT-000008 | NA | Trade Partner | Main entry Box gutter Shop drawing | 1 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 585 | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-27 | KETE-TRANSMIT-000153 | NA | Trade Partner | Kete - Glass Box Design and Shop Drawing | 10 | 0 | 0 | KPTG-IntCorr-001363 | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-001363 - requested guidance, but no resonance yet. KPTG-SADV-005446 - tittle and status are incorrect. | 2026-08-28 | 2026-08-28 | KPTG-SADV-005446 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-27 | Auspan-TRANSMIT-000074 | NA | Trade Partner | Precast roof lid layout issued for review | 1 | 0 | 1 | KPTG-IntCorr-001364 | APPROVED | [5 empty] | KPTG-IntCorr-001364 - requested guidance, but no resonance yet. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-27 | faulk-TRANSMIT-000009 | NA | Trade Partner | RW01- Box gutter TD | 0 | 1 | 0 | NA | APPROVED | 2026-08-27 | WF-000565 | NA | 2026-10-07 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-27 | ELLISAIR-TRANSMIT-000184 | NA | Trade Partner | Stage 11 Ground Floor Builders Works drawing issued for Approval | 4 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 1883 | 2026-09-03 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-27 | D&E-TRANSMIT-001046 | NA | Trade Partner | BMS Documentation - Issued for Construction | 0 | 2 | 0 | NA | REJECTED | [5 empty] | DOCUMENT INCORRECT |  | 2026-08-27 | KPTG-DA-008317 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-23 | SMEPS-TRANSMIT-000009 | NA | Trade Partner | SME Shop Drawing Review | 9 | 0 | 0 | NA | APPROVED | 2026-01-23 | WF-000019 | NA | 2026-01-29 |  |  | 2026-02-03 | 2026-02-03 | KPTG-TRANSMIT-000083 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-27 | ADP-TRANSMIT-000150 | NA | Consultant | ADP MEL4680 - Electrical Protection Report FC-02. | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected:The latest revision of the document available with us is Rev. FC-02 which is reviewed with status Approved. resubmit the FC-03. |  | 2026-08-27 | KPTG-DA-001191 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-08-27 | ZLH P/L-TRANSMIT-000011 | NA | Trade Partner | Variation details | 0 | 7 | 0 | NA | APPROVED | 2026-08-27 | wf - 001145 | NA | 2026-09-01 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-27 | D&E-TRANSMIT-001048 | NA | Trade Partner | NXM3S4 - Roof Level & Level 1 - Chiller Room Sections / Plinth & Equipment Layouts & East String Pipe Sections - Issued For Construction | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distributio |  | 2026-08-27 | KPTG-TRANSMIT-021024 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-27 | WilsonPD-TRANSMIT-000191 | NA | Trade Partner | Re: S10 & 11 L3 Sewer & Stormwater Drawings IFA | 2 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 1886 | 2026-09-03 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-08-27 | KPTG-SADV-001629 | NA | Trade Partner | MEL05 C4 - HAC Mockup Checklist Item | 0 | 1 | 0 | NA | APPROVED | 2026-08-27 | WF - 000580 | NA | 2026-09-01 |  | NA |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-27 | Auspan-TRANSMIT-000659 | NA | Trade Partner | Re: Elevation 05 | 3 | 0 | 3 | KPTG-IntCorr-001393 | APPROVED | [5 empty] | IFC- Waiting for Oliver advise-KPTG-IntCorr-001393 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-27 | D&E-TRANSMIT-001050 | NA | Trade Partner | Fwd: Offsite Passivation Documents - Issued for Information | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-27 | KPTG-TRANSMIT-021026 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-27 | SMEPS-TRANSMIT-000393 | NA | Trade Partner | Re: S4 GF HV Room - Earth Bar | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect revision |  | 2026-08-27 | SMEPS-TRANSMIT-000393 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-27 | ADP-TRANSMIT-000151 | NA | Consultant | Max Demand Calculations | 0 | 1 | 0 | NA | APPROVED | 2026-08-27 | NA | 587 | 2026-09-04 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-002306 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-27 | OTIS2-TRANSMIT-000011 | NA | Trade Partner | New EOT Lift - Shop Drawing removal of CWT safety | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Revision and Status incorrect |  | 2026-08-27 | KPTG-CONTADV-000309 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-22 | SMEPS-TRANSMIT-000250 | NA | Trade Partner | EXTERNAL BUSDCUCT RAIN PROTECTION | 1 | 0 | 0 | NA | APPROVED | 2025-12-01 | NA | 1348 | 2026-01-29 |  |  | 2026-02-11 | 2026-02-11 | KPTG-TRANSMIT-002498 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-27 | OTIS2-TRANSMIT-000012 | NA | Trade Partner | New EOT Lift - Shop Drawings of Hall fixture | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | superseded with OTIS2-TRANSMIT-000015 |  | 2026-08-27 | KPTG-CONTADV-000310 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-27 | OTIS2-TRANSMIT-000013 | NA | Trade Partner | Re: New EOT Lift - Shop Drawings hall fixture for approval | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect attachment and revision |  | 2026-08-27 | KPTG-CONTADV-000308 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-27 | Omnii-TRANSMIT-000010 | NA | Consultant | Draft Fire Engineering Report P1 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Superseded with Omnii-TRANSMIT-000011 |  | 2026-08-28 | KPTG-CONTADV-000316 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-27 | OTIS2-TRANSMIT-000014 | NA | Trade Partner | Re: New EOT Lift - Shop Drawings - Revised removed CWT safety | 2 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 389 | 2026-09-07 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-000340 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-27 | Civilex-TRANSMIT-000272 | NA | Trade Partner | Stage 4 - sample submission - Crash Barrier | 0 | 1 | 0 | NA | APPROVED | 2026-08-27 | WF-006809 | NA | 2026-09-15 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-27 | Nilsen3-TRANSMIT-000105 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 1888 | 2026-09-03 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-27 | Stowe-A-TRANSMIT-000684 | NA | Trade Partner | STOWE - DAS AS BUILTS | 4 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | document number is not as per NEXTDC Standards. |  | 2026-08-27 | KPTG-SADV-007518 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-27 | OTIS2-TRANSMIT-000015 | NA | Trade Partner | Re: New EOT Lift - Shop Drawings - Hal lfixture | 1 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 392 | 2026-09-07 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-27 | EUKAI-TRANSMIT-000029 | NA | Consultant | Hostile Vehicle Assessment | 8 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | #790 | 2026-09-04 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-001221 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-22 | RDSBIM-TRANSMIT-000151 | NA | Trade Partner | LEVEL 13 TOWER B PARTITION WALL LAYOUT (L13 & L14 TYPICAL) | 2 | 0 | 0 | NA | APPROVED | 2026-01-23 | WF-000892 | 531 | 2026-01-29 |  |  | 2026-02-02 | 2026-02-02 | KPTG-TRANSMIT-002659 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-27 | Carr-TRANSMIT-000073 | NA | Consultant | Basement Level drawings Issued for Approval | 14 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 382 | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-27 | Carr-TRANSMIT-000073 | NA | Consultant | Ground Floor and Upper Level drawings Issued for Approval | 8 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 383 | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-27 | Carr-TRANSMIT-000073 | NA | Consultant | Interior drawings Issued for Approval | 11 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 384 | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-27 | Carr-TRANSMIT-000076 | NA | Consultant | Wall and Floor Finishes Details | 3 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 385 | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-27 | Carr-TRANSMIT-000074 | NA | Consultant | -Wet Areas Package | 4 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 386 | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-27 | Civilex-TRANSMIT-000353 | NA | Trade Partner | Stage 2 - sample submission - WARM MIX DESIGNS FULTON HOGAN | 0 | 1 | 0 | NA | APPROVED | 2026-08-27 | WF-006810 | NA | 2026-08-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-27 | D&E-TRANSMIT-001053 | NA | Trade Partner | NXM3S4 - Level 1 - Builders Works Layout Zones 7 & 9 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 4267 | 2026-09-03 |  | TO BE IFC WORKFLOW |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-27 | KPTG-WTRAN-012892 | NA | Trade Partner | (WF-006811) M3 - DOCUMENT CONTROL REVIEW - D&E Builders Works drawings #4267 | 35 | 0 | 0 | NA | APPROVED | 2026-08-27 | na | 4267 | 2026-09-05 |  | as instructed by Ellie 35 docs have been placed in workflow |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-27 | HAN IND-TRANSMIT-000009 | NA | Trade Partner | Steel Shop Drawings FOC-1 | 93 | 0 | 0 | NA | REJECTED | [5 empty] | : Some documents are submitted directly to IFC without approval of IFA. GE1-STR-HAN-SDRG-A-0101-EA7 GE1-STR-HAN-SDRG-A-0101-HB011 GE1-STR-HAN-SDRG-A-0101-HB012 2: Mistake on the revision numbering. kindly change the revision number from FOC-1 TO FC-1 for maintaining project standard. 3: CAD File Naming Mistake. kindly make changes the cad file names Like this for you reference example : GE1-STR-HAN-DWG-A-0101-MP100 |  | 2026-08-27 | KPTG-SADV-001347 | Closed | 93 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-27 | MAYFLD-TRANSMIT-000474 | NA | Trade Partner | 100222-000615: M3 DC Stage 2 - EA Room Revised MDR & EB Room Revised IOM - For Review | 0 | 2 | 0 | NA | REJECTED | [5 empty] | One of the submitted documents is already under review |  | 2026-08-27 | KPTG-SADV-007531 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-22 | RDSBIM-TRANSMIT-000152 | NA | Trade Partner | LEVEL 15 TOWER B & ROOF LEVEL TOWER A PARTITION WALL LAYOUT | 2 | 0 | 0 | NA | APPROVED | 2026-01-23 | WF-000893 | 532 | 2026-01-29 |  |  | 2026-02-02 | 2026-02-02 | KPTG-TRANSMIT-002658 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-27 | Eneraque-TRANSMIT-000070 | NA | Trade Partner | Re: Sealant Datasheet | 0 | 1 | 0 | NA | APPROVED | 2026-08-27 | WF-001626 | NA | 2026-09-08 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-27 | SMEPS-TRANSMIT-000102 | NA | Trade Partner | lightning protection FOA-2 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The document details are missing in the inside document |  | 2026-08-27 | KPTG-SADV-001348 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-27 | SMEPS-TRANSMIT-000103 | NA | Trade Partner | Tech data-Straight terms | 0 | 1 | 0 | NA | APPROVED | 2026-08-27 | WF-000569 | NA | 2026-09-03 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-27 | D&E-TRANSMIT-001054 | NA | Trade Partner | Active Harmonic Filters - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-08-27 | WF-006813 | NA | 2026-09-29 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-27 | DLTS-TRANSMIT-000102 | NA | Trade Partner | S9-HV Room 1-IFC Issue | 130 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, updated register and distributed |  | 2026-08-27 | KPTG-TRANSMIT-007430 | Closed | 130 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-27 | Entire M-TRANSMIT-000094 | NA | Trade Partner | External Sensors Elevation drawing IFC | 1 | 0 | 0 | NA | APPROVED | 2026-08-27 | WF-000465 | NA | 2026-09-01 |  |  | 2026-08-31 | 2026-08-31 | Entire M-TRANSMIT-000094 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-27 | SMEPS-TRANSMIT-000385 | NA | Trade Partner | STAGE 4 - Electrical Inground Layout | 1 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 4266 | 2026-09-03 |  | As instructed by Oliver S, the drawing has been placed in the IFC template again. ACC 4266 |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-27 | INGEN3D-TRANSMIT-000721 | NA | Consultant | I3D - M3 Stage 4 - Link Bridge - Precast Panels - IFC | 49 | 0 | 0 | NA | APPROVED | 2026-08-27 | WF-006814 | NA | 2026-09-02 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-27 | P & R-TRANSMIT-000107 | NA | Trade Partner | Mechanical Shop Drawing Re-Issue | 1 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 539 | 2026-09-09 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-27 | P & R-TRANSMIT-000107 | NA | Trade Partner | Mechanical Shop Drawing Re-Issue | 1 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 540 | 2026-09-07 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-22 | Auspan-TRANSMIT-000056 | NA | Trade Partner | Precast shop drawings for construction. South elevation. | 41 | 0 | 0 | NA | APPROVED | [5 empty] | IFC drawings, No review required |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-27 | MCGC-TRANSMIT-000014 | NA | Consultant | Request to fix revision and document numbering of Landscape Drawings Update | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Reject: Document Numbering is incorrect, request to resubmit:KPTG-SADV-006128 |  | 2026-08-27 | KPTG-SADV-006128 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-27 | Auspan-TRANSMIT-000127 | NA | Trade Partner | Update precast columns for construction. Stage 2. | 6 | 0 | 0 | NA | APPROVED | 2026-08-27 | WF-001155 | NA | 2026-09-01 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-003356 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-27 | Auspan-TRANSMIT-000128 | NA | Trade Partner | Precast shop drawings for construction. Stage 2 Geelong Precast columns on level 1. | 26 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Revision table of a drawing is incorrect, requested to resubmit:KPTG-SADV-006129 |  | 2026-08-27 | KPTG-SADV-006129 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-27 | Auspan-TRANSMIT-000130 | NA | Trade Partner | Precast shop drawings for construction. Stage 2 Geelong Precast columns on level 1. | 26 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: It is duplocation of transmit:Auspan-TRANSMIT-000128-KPTG-SADV-006130 |  | 2026-08-27 | KPTG-SADV-006130 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-27 | INDS-TRANSMIT-000068: | NA | Trade Partner | L2 to L7 Zone 2 - Typical Floor Penetration Layout | 1 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 1827 | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-27 | Auspan-TRANSMIT-000660 | NA | Trade Partner | Re: Corbel - Zone 4 | 3 | 0 | 3 | KPTG-IntCorr-001392 | APPROVED |  | NA | NA |  |  | IFC 0 waiting for Oliver advise - KPTG-IntCorr-001392 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-27 | Fredon T-TRANSMIT-000037 | NA | Trade Partner | AV Shop Drawings Stage 2 | 8 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 546 | 2026-10-07 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-27 | KPTG-IntCorr-001394 | NA | Trade Partner | : IJF approved samples - register documents | 14 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-TRANSMIT-003361 - Update register and transmit to Kapitol PC - Faye. |  | 2026-08-27 | KPTG-TRANSMIT-003361 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-27 | ArcadiaL-TRANSMIT-000004 | NA | Trade Partner | : Landscape Architectural -Eastern 2-way Road IFC drawings | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect revison - KPTG-DA-001833 |  | 2026-08-27 | KPTG-DA-001833 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-27 | JCBa-TRANSMIT-000168 | NA | Consultant | : Updated Architectural Documentation - Joinery Details & Joinery Schedules | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect revision - DRAFT-012153 |  | 2026-08-27 | DRAFT-012153 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-23 | RDSBIM-TRANSMIT-000200 | NA | Trade Partner | Re: NXM3S4 ¦ GROUND FLOOR CONCRETE PROFILE PLAN NORTH OFFICE AND SECTION | 2 | 0 | 0 | NA | REJECTED | [5 empty] | these drawings contain too many unresolved items and reverse clouds to go to IFC. - KPTG-IntCorr-008424 (Tim Shallue to RDS |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-27 | crossfir-TRANSMIT-000036 | NA | Trade Partner | Dry Fire - Level 11 to 17, IFA | 3 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 803 | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-27 | KPTG-TRANSMIT-001711 | NA | Trade Partner | : Fwd: Thermal Calculation of FT04 Rev00 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected due to missing document number. KPTG-SADV-004235 |  | 2026-08-27 | KPTG-SADV-004235 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-27 | Nilsen3-TRANSMIT-000106 | NA | Trade Partner | Nilsen Drawings Issued for Approval | 15 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Drawings are already submitted on another review |  | 2026-08-27 | KPTG-SADV-008090 | Closed | 15 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-27 | WilsonPD-TRANSMIT-000189 | NA | Trade Partner | S10 & 11 L3 Sewer & Stormwater Drawings IFA | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-008051 |  | 2026-08-27 | KPTG-SADV-008051 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-27 | WilsonPD-TRANSMIT-000190 | NA | Trade Partner | Seismic Design S9 L2 & 3 IFI | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required, as advised by Project coordinator. For Information only, Updated register |  | 2026-08-27 | NA | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-27 | Eneraque-TRANSMIT-000069 | NA | Trade Partner | Sealant Datasheet | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Tradepartner himself requested to Disregard the transmittal to correct numbering and resubmitted the document on same thread via Eneraque-TRANSMIT-000070 |  | 2026-08-27 | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-27 | CRSol-TRANSMIT-000022 | NA | Trade Partner | CRS - Shop Drawing - Stage 11 - Ceiling | 14 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 1884 | 2026-09-02 |  | Resubmitted for WSP review as requested by Project Coordinator |  |  |  | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-27 | CRSol-TRANSMIT-000023 | NA | Trade Partner | CRS - Shop Drawing - Stage 11 - Ceiling | 2 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 1884 | 2026-09-02 |  | Resubmitted for WSP review as requested by Project Coordinator |  |  |  | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-27 | GunAus-TRANSMIT-000001 | NA | Trade Partner | Gunnebo Shop Drawings for Approval | 29 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-008070 |  | 2026-08-27 | KPTG-SADV-008070 | Closed | 29 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-27 | PFP PL-TRANSMIT-000034 | NA | Trade Partner | Nitrogen generator | 0 | 1 | 0 | NA | APPROVED | 2026-08-27 | WF-001623 | NA | 2026-09-08 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-23 | SMEPS-TRANSMIT-000149 | NA | Trade Partner | SME - IFA Sample submissions | 0 | 9 | 0 | NA | APPROVED | 2026-01-23 | WF-003950 |  | 2026-02-13 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-27 | SMEPS-TRANSMIT-000119 | NA | Trade Partner | Updated Cable Supplier | 0 | 2 | 0 | NA | APPROVED | 2026-08-27 | WF-001625 | NA | 2026-09-08 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-27 | SMEPS-TRANSMIT-000120 | NA | Trade Partner | Updated Submittals | 0 | 7 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-008086 |  | 2026-08-27 | KPTG-SADV-008086 | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-27 | ELLISAIR-TRANSMIT-000186 | NA | Trade Partner | Stage 9 Ground Floor - SFN Pipework - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-08-27 | NA | 1891 | 2026-09-08 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-27 | Teams message - Nicholas | NA | Trade Partner | MATERIAL SUBMITTAL MIX DESIGN | 0 | 2 | 0 | NA | APPROVED | 2026-08-27 | WF-001245 | NA | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-27 | INGEN3D-TRANSMIT-000251, INGEN3D-TRANSMIT-000266 | NA | Trade Partner | Level 12-13 - Precast Walls, Cast In & Loose Plate - IFC (20-08-2026) | 15 | 0 | 0 | NA | APPROVED | 2026-08-27 | WF-001246 | NA | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-27 | L.E.S.-TRANSMIT-000059 | NA | Trade Partner | Apartment Meter Panels IFA | 3 | 0 | 0 | NA | APPROVED | 2026-08-27 | 1172 | NA | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-27 | SME Review - 1170 | NA | Trade Partner | SME Review - 1170 | 11 | 0 | 0 | NA | APPROVED | 2026-08-27 | 1170 | NA | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-27 | WAM-TRANSMIT-000851 | NA | Trade Partner | A65 Common Area update | 56 | 0 | 0 | PROCESS TOMORROW | APPROVED | 2026-08-28 | NA | 1186 | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-27 | WAM-TRANSMIT-000852 | NA | Trade Partner | A50.203_Soho Apartment Stairs | 1 | 0 | 0 | NA | APPROVED | 2026-08-27 | 1176 | NA | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-28 | SMEPS-TRANSMIT-000121 | NA | Trade Partner | Re: Peno Schedule Level 01 | 1 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 1893 | 2026-09-04 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-23 | SKS Tech-TRANSMIT-000006 | NA | Trade Partner | SKS - Submain tech data | 0 | 1 | 0 | NA | APPROVED | 2026-01-23 | WF-003951 |  | 2026-02-13 |  |  |  | 2026-02-13 | KPTG-TRANSMIT-012818 | Open | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-28 | KPTG-WTRAN-012903 | NA | Trade Partner | LEVEL 1 PINTH AND EQUIPMENT LAYOUT | 2 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 4269 | 2026-09-06 |  | As instructed by Ellie Salmon, 2 drawings have been placed in WF review |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-28 | KPTG-WTRAN-012904 | NA | Trade Partner | (WF-006816) M3 - DOCUMENT CONTROL REVIEW - chiller room section and cooling tower sections #4270 | 9 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 4270 | 2026-09-06 |  | 9 DOCS PLACED IN IFC WORKFLOW AS INSTRUCTED BY ELLIE |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-28 | KPTG-WTRAN-012905 | NA | Trade Partner | (WF-006817) M3 - DOCUMENT CONTROL REVIEW - PIPE SECTION DRAWINGS #4271 | 2 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 4271 | 2026-09-06 |  | 2 DOCS PLACED IN IFC WORKFLOW AS INSTRUCTED BY ELLIE |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-28 | Nilsen3-TRANSMIT-000262 | NA | Trade Partner | M4 Stage-4 ROP 4A and 4B GA and Schematic diagrams | 0 | 1 | 0 | NA | REJECTED | [5 empty] | DOCUMENT NUMBER INCORRECT |  | 2026-08-28 | KPTG-DA-008330 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-28 | KETE-TRANSMIT-000154 | NA | Trade Partner | Kete - Pigtail Facade Access Locations and Details for Approval | 5 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-005448 - REVISION INCORRECT | 2026-08-28 | 2026-08-28 | KPTG-SADV-005448 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-28 | RDSBIM-TRANSMIT-000029 | NA | Trade Partner | NXGE01 ¦ GROUND FLOOR PLANT AREA CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 591 | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-28 | RDSBIM-TRANSMIT-000030 | NA | Trade Partner | NXGE01 ¦ GROUND FLOOR GE1-17 CLEANERS FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 593 | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-28 | WilsonPD-TRANSMIT-000193 | NA | Trade Partner | S10&11 L3 Water Supply IFA | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected: Difference in document number |  | 2026-08-28 | KPTG-SADV-008115 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-28 | IJF-TRANSMIT-000013 | NA | Trade Partner | Joinery - Kitchen Drawings - Delivery 2 | 116 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - difference in status and titles- DRAFT-012159 |  | 2026-08-28 | DRAFT-012159 | Closed | 116 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-10 | PSGANZ-TRANSMIT-000014 | NA | Trade Partner | Fire Protection tech data | 0 | 1 | 0 | NA | APPROVED | 2026-08-10 | WF-000454 | NA | 2026-08-21 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-002298 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-23 | ABB-TRANSMIT-000022 NXT-TRANSMIT-001213 | NA | Trade Partner | Fwd: Updated secondary drawings for M3-22-HVSB-A,B,D & R | 1 | 0 | 0 | NA | APPROVED | 2026-01-23 | WF-003953 |  | 2026-02-04 |  | The register has been updated. If any further action is required, the coordinator will inform.- KPTG-TRANSMIT-011833 |  | 2026-02-05 | KPTG-TRANSMIT-012508 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-28 | Omnii-TRANSMIT-000011 | NA | Consultant | Fire Engineering Report Rev A | 0 | 1 | 0 | NA | APPROVED | 2026-08-28 | NA | 394 | 2026-09-04 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-000330 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-28 | WilsonPD-TRANSMIT-000194 | NA | Trade Partner | Re: S10&11 L3 Water Supply IFA | 2 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 1895 | 2026-09-04 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-28 | RDSBIM-TRANSMIT-000031 | NA | Trade Partner | NXGE01 ¦ GROUND FLOOR GE1-03 UNISEX WC FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 595 | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-27 | KPTG-IntCorr-002387 | NA | Trade Partner | SKS CxL4 scripts | 0 | 4 | 0 | NA | APPROVED | 2026-08-28 | WF-001233 | NA | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-27 | KPTG-IntCorr-002387 | NA | Trade Partner | SKS CxL4 scripts | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | already in review (WF-001231) - no action |  | 2026-08-27 | WF-001231 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-27 | KPTG-IntCorr-002369 | NA | Trade Partner | EATON L4 SCRIPTS | 0 | 2 | 0 | NA | APPROVED | 2026-08-28 | WF-001234 | NA | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-11 | WGAVIC-TRANSMIT-000169 | NA | Consultant | M2 - Civil Main Works - Issued for Construction | 20 | 0 | 0 | NA | APPROVED | 2026-08-11 | NA | 1702 | 2026-08-28 |  |  | 2026-08-28 | 2026-08-28 | KPTG-DA-004417 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-28 | ADP-TRANSMIT-000414 | NA | Consultant | ADP MEL4780 - Updated HYD Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 4273 | 2026-09-03 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-28 | NXES-TRANSMIT-000088 | NA | Trade Partner | ISC Roof Electrical Layout | 3 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 549 | 2026-09-08 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-20 | KPTG-TRANSMIT-021064 | NA | Trade Partner | O&M WF | 0 | 1 | 0 | NA | APPROVED | 2026-08-20 | WF-006734 | NA | 2026-08-28 |  |  |  | 2026-08-28 | KPTG-TRANSMIT-021064 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-03 | SMEPS-TRANSMIT-000088 | SPARK-CRFI-KPG-000462 | Trade Partner | IFA - Electrical Sections & Schematics | 5 | 0 | 0 | KPTG-IntCorr-001035 | APPROVED | 2025-12-03 | WF-000087 | 49 | 2025-12-10 |  |  |  | 2026-01-30 | KPTG-TRANSMIT-000379 & KPTG-TRANSMIT-000638 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-28 | D&E-TRANSMIT-001051 | NA | Trade Partner | Fwd: NXM3S4 - No Longer In Use #0401 Series - Issued For Information | 19 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For Distribution |  | 2026-08-28 | KPTG-TRANSMIT-021065 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-28 | D&E-TRANSMIT-001049 | NA | Trade Partner | NXM3S4 - Drawings Marked No Longer In Use | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For Distribution |  | 2026-08-28 | KPTG-TRANSMIT-021062 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-28 | KPTG-TRANSMIT-001170 | NA | Trade Partner | Concrete Mix - Footings, PC Beams Slab for Review | 0 | 1 | 0 | NA | APPROVED | 2026-08-28 | NA | 794 | 2026-09-07 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-28 | NXT-WTRAN-000144 | NA | Client | Final (WF-000140) FIE STRUCT/ARC NEW: Arjay Switchrooms Rev.2- | 10 | 0 | 0 | NA | APPROVED | 2026-08-28 | WF-000140 | NA | 2026-09-11 |  | FIE review completion |  | 2026-08-28 | KPTG-TRANSMIT-001184 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-14 | KPTG-IntCorr-001506 | NA | Trade Partner | M2 S9-11 Generator & Enclosure Documents | 19 | 0 | 0 | NA | APPROVED | 2026-08-14 | NA | 1369 | 2026-08-28 |  |  | 2026-08-28 | 2026-08-28 | KPTG-DA-004419 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-28 | ZIA-TRANSMIT-000167 | NA | Trade Partner | M3S4 Mini-OS datasheet (FOA-2) | 0 | 1 | 0 | NA | APPROVED | 2026-08-28 | WF-006819 | NA | 2026-09-21 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-28 | KETE-TRANSMIT-000156 | NA | Trade Partner | Kete - Ground Floor Arch Windows Shop Drawings | 4 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-005456 - status and Revision are incorrect. | 2026-08-28 | 2026-08-28 | KPTG-SADV-005456 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-28 | Eneraque-TRANSMIT-000071 | NA | Trade Partner | ENE - Transfer Skid Assembly IFC | 1 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 1897 | 2026-09-04 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D9 | 2026-08-28 | IVS-TRANSMIT-000019 | NA | Consultant | Antenna Gantry Construction Issue | 10 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 1479 | 2026-09-05 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-000073 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-28 | IJF-TRANSMIT-000014 | NA | Trade Partner | Joinery Drawings - Kitchens - Delivery 2 | 116 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 1833 | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-23 | Tradetec-TRANSMIT-000335 | NA | Trade Partner | Stage 4 IFC - CP36 | 1 | 0 | 0 | NA | APPROVED | 2026-01-23 |  | 1874 | 2026-01-30 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-012047 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-28 | PFP PL-TRANSMIT-000035 | NA | Trade Partner | Level 2 Hebel Block Layouts | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFI drawings, updated register and distributed |  | 2026-08-28 | KPTG-TRANSMIT-007464 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D9 | 2026-08-28 | HDRAus-TRANSMIT-000019 | NA | Consultant | Structural Set Out Plan | 1 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 1481 | 2026-09-04 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-000072 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-28 | ADP-TRANSMIT-000152 | NA | Consultant | Electrical Protection Report | 0 | 1 | 0 | NA | APPROVED | 2026-08-28 | NA | 587 | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-28 | NXT-TRANSMIT-001693 | NA | Trade Partner | M3 DC Stage 2 - EA Room Revised MDR & EB Room Revised IOM - For Review | 0 | 2 | 0 | NA | APPROVED | 2026-08-28 | WF-006824 | NA | 2026-09-11 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-28 | NXES-TRANSMIT-000089 | NA | Trade Partner | Level 02 & 03 Emergency Lighting Calculation | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Title of drawing are interchanged, requested to retransmit-KPTG-SADV-006151 |  | 2026-08-28 | KPTG-SADV-006151 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-28 | NXT-TRANSMIT-001699 | NA | Client | NEXT DC - M3 - Stage 2 - CRAC, FWU & CDU As-Built Documentation | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Document Numbering Issue in Aconex Missing Document Details in the Drawings Mismatch in Reason for Submission Documents Submitted Directly for Construction Without IFA Approval Incorrect Revision Numbering |  | 2026-08-28 | KPTG-SADV-007550 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-28 | ADP-TRANSMIT-000412 | NA | Consultant | ADP - M3S4 Office Fitout Services Drawings - IFT Issue | 26 | 0 | 0 | NA | APPROVED | 2026-08-28 | WF-006823 | NA | 2026-09-18 |  | PLACED IN BLUE BIM REVIEW AS INSTRUCTED BY JAN | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-021126 | Closed | 26 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-28 | Syfon1-TRANSMIT-000028 | NA | Trade Partner | Syfon Drawings IFA | 3 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 551 | 2026-09-08 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-28 | NXES-TRANSMIT-000073 | NA | Trade Partner | Nexus - Tech Data Sheet | 0 | 2 | 0 | NA | APPROVED | 2026-08-28 | WF-000935 | NA | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-28 | PARR-TRANSMIT-000222 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - PUMP ROOM GA, BFTC RETIC, BFS DB | 7 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 4278 | 2026-09-02 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-23 | TTW-TRANSMIT-000153 | NA | Consultant | M3 Stage 4 Building C Civil Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-01-23 |  | 1876 | 2026-01-27 |  |  |  | 2026-01-27 | KPTG-TRANSMIT-011944 | Closed | 5 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-21 | HDRAus-TRANSMIT-000547 | NA | Consultant | M3 Stage 1&4 - Document upload - PDF (Office Fitout) | 7 | 0 | 0 | NA | APPROVED |  | NA | 4215 | 2026-08-28 |  |  |  | 2026-08-28 | KPTG-TRANSMIT-021079 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-28 | HDRAus-TRANSMIT-000554 | NA | Consultant | Updated Sitewide Drawings | 4 | 1 | 0 | NA | REJECTED | [5 empty] | Document submitted with previous revision Mixed submission of IFA and IFC Revision Mistake |  | 2026-08-28 | KPTG-SADV-007551 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-28 | VIA Arch-TRANSMIT-000251 | NA | Consultant | M2 S11 L1 Concrete Profile Plan | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawing, updated register and distributed |  | 2026-08-28 | KPTG-TRANSMIT-007490 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-28 | SMEPS-TRANSMIT-000104 | NA | Trade Partner | Cable Calculation | 0 | 1 | 0 | NA | APPROVED | 2026-08-28 | WF-000574 | NA | 2026-09-07 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-28 | ADP-TRANSMIT-000415 | NA | Trade Partner | ADP M3 PLANT REPLACEMENT REPORT R5 | 0 | 1 | 0 | NA | APPROVED | 2026-08-29 | WF-006826 | NA | 2026-09-04 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-28 | INTRFRM-TRANSMIT-000136 | NA | Trade Partner | Geelong Edge - Civil Tech Data (Submission 11) | 0 | 8 | 0 | NA | APPROVED | 2026-08-28 | WF-000575 | NA | 2026-09-08 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-28 | ADP-TRANSMIT-000415 | NA | Consultant | ADP M3 PLANT REPLACEMENT REPORT R5 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-08-28 | KPTG-TRANSMIT-021107 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-28 | HDRAus-TRANSMIT-000549 | NA | Consultant | M3 Stage 1&4 - Document upload - PDF (Office Fitout) | 7 | 0 | 0 | NA | APPROVED | 2026-08-28 | WF-006827 | NA | 2026-09-18 |  | As instructed by Jan, the drawings have been placed in Bluebeam review |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-08-28 | Nilsen3-TRANSMIT-000261 | NA | Trade Partner | M3-HV-NIL-SA-S-0301-0071 - Simona Dutchclamp | 0 | 1 | 0 | NA | APPROVED | 2026-08-28 | WF-006828 | NA | 2026-09-03 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-28 | WSP ANZ-TRANSMIT-000106 | NA | Consultant | WSP Issued for Building Permit Documents - (Fire Services Documents) | 3 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFBP drawings, updated register and distributed |  | 2026-08-28 | KPTG-TRANSMIT-007493 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-23 | SMEPS-TRANSMIT-000150 | NA | Trade Partner | S3 I SHOP DRAWING I CONSULTANT REVIEW ¦ ELE IFC - KG, aurecon elec, and NDC - SMEPS-TRANSMIT-000150 Stage 3 - MDB's | 0 | 1 | 0 | NA | APPROVED | 2026-01-23 | WF-003955 |  | 2026-02-05 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-012080 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-28 | NXES-TRANSMIT-000090 | NA | Trade Partner | Level 02 & 03 Emergency Lighting Calculation | 2 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 553 | 2026-09-08 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-28 | Altaire-TRANSMIT-000131 | NA | Trade Partner | M3S2 - Altaire As-Built Submissions | 16 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 4521 | 2026-09-04 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-28 | Altaire-TRANSMIT-000131 | NA | Trade Partner | Altaire As-Built Submissions | 1 | 0 | 0 | NA | REJECTED | [5 empty] | document M3-FID-ALT-SDRG-B-0201-8012 was directly submitted for As-Built status without prior approval as an IFC document. |  | 2026-08-28 | KPTG-SADV-007554 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-28 | HDRAus-TRANSMIT-000555 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 8 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 4281 | 2026-09-03 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-28 | NXT-TRANSMIT-000529 | NA | Client | S6 Barkers Gates - Vehicle Gates | 8 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For Distribution |  | 2026-08-28 | KPTG-TRANSMIT-001194 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-28 | DLTS-TRANSMIT-000104 | NA | Trade Partner | S9 Canopy-IFC Issue | 41 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings updated register and distributed |  | 2026-08-28 | KPTG-TRANSMIT-007499 | Closed | 41 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-28 | DLTS-TRANSMIT-000105 | NA | Trade Partner | S9-Canopy updated documents | 24 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Resubmitted by Trade partner correcting revision date |  | 2026-08-28 | KPTG-IntCorr-002369 | Closed | 24 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-28 | DLTS-TRANSMIT-000106 | NA | Trade Partner | S9-Canopy Updated documents | 24 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Drawings Updated register and distributed |  | 2026-08-28 | KPTG-TRANSMIT-007502 | Closed | 24 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-28 | DLTS-TRANSMIT-000103 | NA | Trade Partner | S11-Cooling Tower-FR4002-IFA Issue | 2 | 0 | 0 | NA | APPROVED | 2026-08-28 | WF-001635 | NA | 2026-09-08 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-28 | Ardon-TRANSMIT-000039 | NA | Trade Partner | Door Hardware Tech Data - Additional Submission | 0 | 1 | 0 | NA | APPROVED | 2026-08-28 | WF-001634 | NA | 2026-09-08 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-23 | RDSBIM-TRANSMIT-000201 | NA | Trade Partner | NXM3S4 LEVEL-1-C-1-055 CLEANERS FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-01-23 |  | 1878 | 2026-01-27 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-012053 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-28 | GunAus-TRANSMIT-000001 | NA | Trade Partner | Gunnebo Shop Drawings for Approval | 30 | 0 | 0 | NA | APPROVED | 2026-08-28 | WF-001630 | NA | 2026-09-04 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-28 | Auspan-TRANSMIT-000662: | NA | Trade Partner | Precast dowel layout for level 3 up. | 12 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to drawing QA issues. - DRAFT-012157 |  | 2026-08-28 | DRAFT-012157 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-28 | inco-TRANSMIT-000071 | NA | Trade Partner | R: Structural drawings Issued for Construction | 11 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 1829 | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-28 | POTTSENG-TRANSMIT-000073 | NA | Trade Partner | : GMAC: HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONES 1-5 LAYOUTS | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected One drawing PDF is missing- KPTG-SADV-004555 |  | 2026-08-28 | KPTG-SADV-004555 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-28 | POTTSENG-TRANSMIT-000074: | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONES 1--5 LAYOUTS | 5 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 1831 | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-28 | IJF-TRANSMIT-000015 | NA | Trade Partner | : JO202 - Prototype Drawomh | 1 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 1839 | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-28 | M.2-TRANSMIT-000089: | NA | Trade Partner | Electrical Services Typical apartment show drawing | 69 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 1837 | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-28 | Endfire-TRANSMIT-000084 | NA | Trade Partner | ENDFIRE DRAFT O&M Submittal | 0 | 1 | 1 | KPTG-IntCorr-002403 | APPROVED | [5 empty] | Hugh to Confirm |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-28 | Endfire-TRANSMIT-000085 | NA | Trade Partner | ENDFIRE ASSET REGISTER | 0 | 1 | 1 | KPTG-IntCorr-002403 | APPROVED | [5 empty] | Hugh to Confirm |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-28 | ACG-TRANSMIT-000025 | NA | Trade Partner | ACG - O&M + Asset Register | 0 | 1 | 1 | KPTG-IntCorr-002403 | APPROVED | [5 empty] | Hugh to Confirm |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-23 | JCBa-TRANSMIT-000051 | NA | Consultant | Overall GA Plans - IFC Issue | 10 | 0 | 0 | NA | APPROVED | 2026-01-23 | WF-000144 | 277 | 2026-01-28 |  |  |  | 2026-01-27 | KPTG-TRANSMIT-000476 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-28 | KPTG-IntCorr-002402 | NA | Trade Partner | EATON L4 SCRIPTS | 0 | 1 | 0 | NA | APPROVED | 2026-08-28 | WF-001238 | NA | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-28 | crossfir-TRANSMIT-000037: | NA | Trade Partner | Wet Fire - Tank and pumproom V2 - FOR REVIEW | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - No Drawing number inside the sheet & incorrect rev. and title - KPTG-SADV-004305 |  | 2026-08-28 | KPTG-SADV-004305 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-28 | Jangho-TRANSMIT-000115 671 | NA | Trade Partner | -GL-300& telescopic braces (SC320-12)&perforated stainless‑steel panel&GRC remedial sample 2026/8/25 | 0 | 3 | 0 | NA | APPROVED | 2026-08-28 | WF-000732 | NA | 2026-09-04 |  | WF-000732 Refer to KPTG-TRANSMIT-001718 from Xavier |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-28 | ccair-TRANSMIT-000053 | NA | Trade Partner | Pool and corridor supply air packaged units for approval | 0 | 2 | 0 | NA | APPROVED | 2026-08-28 | WF-000733 | NA | 2026-09-04 |  | WF-000733 initiated by Kapitol PC- Tayla |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-28 | ccair-TRANSMIT-000054 | NA | Trade Partner | : Low Profile Duct for approval | 0 | 1 | 1 | KPTG-IntCorr-001357 | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001357 - Waiting for Tayla advise |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-08-27 | KPTG-IntCorr-002369 | NA | Trade Partner | EATON L4 SCRIPTS | 0 | 1 | 0 | NA | APPROVED | 2026-08-28 | WF-001234 | NA | 2026-09-04 |  | TERMINATED 1 DUE TO RE-ISSUE OF REVISED DOC - MADE SEPERATED ENTRY FOR BALANCE 2 ITEMS |  | 2026-08-28 | KPTG-IntCorr-002402 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-28 | PCForm-TRANSMIT-000311- LVL 5 | NA | Trade Partner | Fwd: L5 TO L10 UPDATED | 5 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 1182 | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-28 | PCForm-TRANSMIT-000311- LVL 6 | NA | Trade Partner | Fwd: L5 TO L10 UPDATED | 5 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 1184 | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-28 | PCForm-TRANSMIT-000311- LVL 7 | NA | Trade Partner | Fwd: L5 TO L10 UPDATED | 5 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 1190 | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-28 | PCForm-TRANSMIT-000311- LVL 8 - 9 | NA | Trade Partner | Fwd: L5 TO L10 UPDATED | 6 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 1192 | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-23 | POTTSENG-TRANSMIT-000004 | NA | Trade Partner | GMAC HYD - DRAINAGE - BASEMENT 1 INGROUND - ZONE 1 & 3 LAYOUTS | 2 | 0 | 0 | NA | APPROVED | 2026-01-23 | WF-000145 | 280 | 2026-01-29 |  | Review void as requested by Kapitol PC. |  | 2026-01-27 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-28 | PCForm-TRANSMIT-000311- LVL 10 | NA | Trade Partner | Fwd: L5 TO L10 UPDATED | 5 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 1194 | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-28 | WAM-TRANSMIT-000854 | NA | Consultant | A17 series Power and Communications Drawing issued for construction | 26 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 1188 | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-28 | Civilex-TRANSMIT-000116 | NA | Trade Partner | Re: Above Ground OSD Tank Inlets | 1 | 0 | 0 | NA | REJECTED | [5 empty] | QA ERROR - SHOP DRAWING SUBMITTED AS COMBINED SHEETS |  | 2026-08-28 | KPTG-TRANSMIT-003651 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-28 | BIMF-TRANSMIT-000025 | NA | Trade Partner | Level 3 Hydraulic Setout, Rev C | 2 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 1196 | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-28 | WAM-TRANSMIT-000853 | NA | Consultant | A17 series Power and Communications Drawing issued for construction | 26 | 0 | 0 | NA | REJECTED | [5 empty] | RE-ISSUED VIA WAM-TRANSMIT-000854 |  | 2026-08-28 | WAM-TRANSMIT-000854 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-28 | Jangho-TRANSMIT-000331 | NA | Trade Partner | Window Hardware Sample Submission（Kinglong) | 0 | 1 | 0 | NA | APPROVED | 2026-08-28 | WF-001255 | NA | 2026-09-11 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-28 | Jangho-TRANSMIT-000330 | NA | Trade Partner | Window Hardware Sample Submission（CMECH) | 0 | 1 | 0 | NA | APPROVED | 2026-08-28 | WF-001250 | NA | 2026-09-11 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-28 | OveArup-TRANSMIT-000045 | NA | Consultant | Mech Reg 126 | 0 | 1 | 0 | NA | APPROVED | 2026-08-28 | WF-001249 | NA | 2026-09-04 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-003674 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-28 | L.E.S.-TRANSMIT-000062 | NA | Consultant | Level 2-3 Light, Power and Comms drawing IFA | 8 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 1198 | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-28 | L.E.S.-TRANSMIT-000061 | NA | Consultant | Lightning Protection Shop Drawings IFA | 5 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 1178 | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-23 | StantecA-TRANSMIT-000296 | NA | Consultant | Updated Hydraulics - Trench grates | 6 | 0 | 0 | NA | APPROVED | 2026-01-23 | WF-000146 | 282 | 2026-01-27 |  |  |  | 2026-01-27 | KPTG-TRANSMIT-000474 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-28 | Civilex-TRANSMIT-000117 | NA | Consultant | Re: Above Ground OSD Tank Inlets | 5 | 0 | 0 | NA | APPROVED | 2026-08-28 | NA | 1180 | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-08-28 | ccair-TRANSMIT-000020 | NA | Consultant | Heat Load Calculation IFC | 0 | 1 | 0 | NA | APPROVED | 2026-08-28 | WF-001266 | NA | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-28 | Omnii-TRANSMIT-000012 | NA | Consultant | Fire Engineering Report Rev B | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-08-28 | KPTG-TRANSMIT-000331 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-28 | GIW-TRANSMIT-000004 | NA | Consultant | J1V3 Report and ESD Markup | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Incorrect document number |  | 2026-08-28 | KPTG-TRANSMIT-000332 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-31 | VERTIV-TRANSMIT-000076 | NA | Trade Partner | NEXT DC GE01 _ COOLING LOAD CALCULATION (FOA-3) | 0 | 1 | 0 | NA | APPROVED | 2026-08-31 | WF-000576 | NA | 2026-09-09 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-31 | EAEGROUP-TRANSMIT-000014 | NA | Trade Partner | Submission of KX Indoor and CCR Outdoor Busduct Technical Documents | 0 | 4 | 0 | NA | APPROVED | 2026-08-31 | WF-000577 | NA | 2026-09-09 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-31 | fjc-TRANSMIT-000210 | NA | Consultant | No Longer in Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | drawings are no longer in use | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-003029 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-21 | HDRAus-TRANSMIT-000549 | NA | Consultant | M3 Stage 1&4 - Document upload - PDF (Office Fitout) | 7 | 0 | 0 | NA | APPROVED | 2026-08-28 | WF-006827 | NA | 2026-08-31 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-021121 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-31 | fjc-TRANSMIT-000209 | NA | Consultant | No Longer in Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001369 - Its CAD files, The PDF file for document ARC-FJC-56000 was received in transmittal FJC-TRANSMIT-000210 and has already been processed. | 2026-08-31 | 2026-08-31 | KPTG-IntCorr-001369 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-23 | IVS-TRANSMIT-000323 | NA | Consultant | Stage 4 - Cooling Tower & Chiller Room Zone C1 - C3 Package (Construction Issue) | 12 | 0 | 0 | NA | REJECTED | [5 empty] | The document revision number does not match with Aconex revision number. KPTG-TRANSMIT-011887 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-31 | Auspan-TRANSMIT-000670 | NA | Trade Partner | Precast shop drawings for approval. Level 7 | 32 | 0 | 0 | NA | APPROVED | 2026-08-31 | NA | 1841 | 2026-09-05 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-31 | Auspan-TRANSMIT-000670 | NA | Trade Partner | Precast shop drawings for approval. Level 7 | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected- Revision history missing, difference in title and same revision as latest- DRAFT-012209 |  | 2026-08-31 | DRAFT-012209 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-31 | RDSBIM-TRANSMIT-000032 | NA | Trade Partner | NXGE01 ¦ GROUND FLOOR GE1-06 UAT FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-08-31 | NA | 600 | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-31 | fjc-TRANSMIT-000212 | NA | Consultant | No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | drawings are no longer in use. | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-003032 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-31 | fjc-TRANSMIT-000211 | NA | Consultant | No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001371 - Its CAD files, The PDF file for document ARC-FJC-56010 was received in transmittal FJC-TRANSMIT-000212 and has already been processed. | 2026-08-31 | 2026-08-31 | KPTG-IntCorr-001371 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-31 | DLTS-TRANSMIT-000107 | NA | Trade Partner | S10 Eave Gutter Frames-IFC issue | 44 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, updated register and distributed |  | 2026-08-31 | KPTG-TRANSMIT-007512 | Closed | 44 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-31 | Nilsen3-TRANSMIT-000263 | NA | Trade Partner | Stage-4 ROP 4A and 4B GA and Schematics | 0 | 1 | 0 | NA | APPROVED | 2026-08-31 | WF-006831 | NA | 2026-09-22 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-31 | PSGANZ-TRANSMIT-000017 | NA | Trade Partner | Water mist tank F0A-02 | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected: the revision indicated in the document appears to be incorrect, and placed on the wrong side in the document | 2026-08-31 | 2026-08-31 | KPTG-SADV-001363 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-31 | Auspan-TRANSMIT-000671 | NA | Trade Partner | Precast shop drawings for approval. Level 8 | 12 | 0 | 0 | NA | APPROVED | 2026-08-31 | NA | 1843 | 2026-09-07 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-23 | TTW-TRANSMIT-000150 | NA | Consultant | S4 Facade Details IFC | 26 | 0 | 0 | NA | APPROVED | 2026-01-23 |  | 1880 | 2026-01-27 |  |  |  | 2026-02-02 | KPTG-TRANSMIT-012358 | Closed | 26 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-31 | VIA Arch-TRANSMIT-000252 | NA | Consultant | M2 S9 - S11 - ISSUED FOR CONSTRUCTION (FC-1) | 71 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected: Incorrect document number |  | 2026-08-31 | KPTG-DA-004429 | Closed | 71 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-31 | Auspan-TRANSMIT-000671 | NA | Trade Partner | Precast shop drawings for approval. Level 8 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected- difference in title and overlapping issue - DRAFT-012211 |  | 2026-08-31 | DRAFT-012211 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-31 | PTA-TRANSMIT-000048 | NA | Consultant | Precast Panel Elevations - Block 1 &2 | 6 | 0 | 0 | NA | APPROVED | 2026-08-31 | NA | 807 | 2026-09-07 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-31 | 4DW-TRANSMIT-000089 | NA | Consultant | Roof Steelwork. Issued For Coordination. | 17 | 0 | 0 | NA | APPROVED | 2026-08-31 | NA | 803 | 2026-09-08 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-31 | 4DW-TRANSMIT-000090 | NA | Consultant | Block 2 - Precast stair cores issued for re-certification. | 6 | 0 | 0 | NA | APPROVED | 2026-08-31 | NA | 805 | 2026-09-08 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-31 | Auspan-TRANSMIT-000668 | NA | Trade Partner | Resubmit precast shop drawings for approval. Level 4 | 2 | 0 | 0 | NA | APPROVED | 2026-08-31 | NA | 1845 | 2026-09-07 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-31 | Auspan-TRANSMIT-000669 | NA | Trade Partner | Resubmit precast shop drawing for approval. Level 5 panel 5P1061 | 1 | 0 | 0 | NA | APPROVED | 2026-08-31 | NA | 1847 | 2026-09-07 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-31 | Auspan-TRANSMIT-000128 | NA | Trade Partner | Precast shop drawings for construction. Stage 2 Geelong Precast columns on level 1. | 26 | 0 | 0 | NA | APPROVED | 2026-08-31 | WF-001161 | NA | 2026-09-03 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-003364 | Closed | 26 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-31 | Auspan-TRANSMIT-000131 | NA | Trade Partner | Precast shop drawings for construction. Stage 2 Geelong Precast columns on level 1. | 1 | 0 | 0 | NA | APPROVED | 2026-08-31 | WF-001161 | NA | 2026-09-03 |  | WORKFLOW IS COMBINED | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-003364 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-31 | SC-TRANSMIT-000015 | NA | Trade Partner | Update C4 & C5 columns connection and K1 frame. | 8 | 0 | 0 | NA | REJECTED | [5 empty] | IFA OF THE MOST DRAWING S HAVE NOT BEEN ISSUED SO FAR, REQUESTED TO RESUBMIT: KPTG-TRANSMIT-001675 |  | 2026-08-31 | KPTG-TRANSMIT-001675 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-03 | D&E-TRANSMIT-000067 | SPARK-CRFI-KPG-000490 | Trade Partner | ISSUED FOR APPROVAL - LEVEL 1 & ROOF - DUCTWORK & PIPEWORK LAYOUTS ZONES 1 - 4 MECHANICAL SERVICESS | 5 | 0 | 0 | KPTG-IntCorr-001034 | APPROVED | 2025-12-03 | WF-000086 | 53 | 2025-12-10 |  |  |  | 2026-02-17 | KPTG-TRANSMIT-000449 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-23 | SMEPS-TRANSMIT-000102 | SPARK-CRFI-KPG-000370 | Trade Partner | Ev Charging Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-01-23 | WF-000140 |  | 2026-01-30 |  | KPTG-IntCorr-001382 |  | 2026-02-17 | KPTG-TRANSMIT-000447 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-31 | D&E-TRANSMIT-000318 | NA | Trade Partner | Approved samples IFC | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Revision and covering sheet of sample are not current: KPTG-TRANSMIT-001676 |  | 2026-08-31 | KPTG-TRANSMIT-001676 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-26 | PFP PL-TRANSMIT-000021 | NA | Trade Partner | S11 Ground Floor IFA | 1 | 0 | 0 | NA | APPROVED | 2026-08-26 | NA | 1880 | 2026-08-31 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-007515 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-31 | Baigents-TRANSMIT-000048 | NA | Trade Partner | Updated Plans and elevations IFA | 6 | 0 | 0 | NA | APPROVED | 2026-08-31 | NA | 809 | 2026-09-08 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-08-31 | NXT-TRANSMIT-000532 | NA | Client | PDU V3 3D Drawing | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | 3D drawings For distribution |  | 2026-08-31 | 1 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-31 | D&E-TRANSMIT-001055 | NA | Trade Partner | BMS Documentation - Issued for Construction | 0 | 2 | 0 | NA | APPROVED | 2026-08-31 | WF-006832 | NA | 2026-09-26 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-08-31 | Highbu-TRANSMIT-000063 | NA | Trade Partner | Updated sanitary samples from architectural changes - (except TAP 4) | 0 | 17 | 17 | KPTG-IntCorr-001375 | APPROVED | [5 empty] | KPTG-IntCorr-001375 - requested guidance, but no resonance yet. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-31 | RDSBIM-TRANSMIT-000021 | NA | Trade Partner | 303COL ¦ MEZZANINE CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect drawing number |  | 2026-08-31 | KPTG-CONTADV-000324 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-31 | DCN-TRANSMIT-000044 | NA | Trade Partner | Updated Rev history/Rev date & Status Drawing - M2S9 Link Bridge Structural ABS 1 Shop Drawings | 9 | 0 | 0 | NA | APPROVED | 2026-08-31 | NA | 1899 | 2026-09-02 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-31 | D&E-TRANSMIT-001056 | NA | Trade Partner | North Office Split Systems Technical Data - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-08-31 | WF-006833 | NA | 2026-09-04 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-23 | WilsonPD-TRANSMIT-000144 | SPARK-CRFI-KPG-000190 | Trade Partner | Updated Civil drawing IFC | 1 | 0 | 0 | NA | APPROVED | 2026-01-23 | WF-000141 | 263 | 2026-01-30 |  |  | 2026-05-04 | 2026-05-05 | KPTG-TRANSMIT-000820 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-31 | GIW-TRANSMIT-000005 | NA | Consultant | J1V3 Report and ESD Markup | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | No longer in use |  | 2026-08-31 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-31 | GIW-TRANSMIT-000006 | NA | Consultant | J1V3 Report (Rev F) and ESD Markup (v8) | 0 | 2 | 0 | NA | APPROVED | 2026-08-31 | NA | 400 | 2026-10-05 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-31 | RDSBIM-TRANSMIT-000022 | NA | Trade Partner | 303COL ¦ MEZZANINE CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2026-08-31 | NA | 396 | 2026-09-07 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-31 | Eneraque-TRANSMIT-000073 | NA | Trade Partner | ENE - Fuel Storage Tanks General Arrangement - FC2 | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected: Difference in status |  | 2026-08-31 | KPTG-SADV-008177 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-31 | SKS Tech-TRANSMIT-000215 | NA | Trade Partner | Typical Details for Pre Fab hangers Asbuilt | 1 | 0 | 0 | NA | APPROVED | 2026-08-31 | NA | 4291 | 2026-09-02 |  | AS INSTRUCTED BY JAN |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-31 | SKS Tech-TRANSMIT-000214 | NA | Trade Partner | Comms Containment Earthing As-Builts | 4 | 0 | 0 | NA | APPROVED | 2026-08-31 | NA | 4292 | 2026-09-04 |  | As a instructed by jan |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-31 | Stowe-A-TRANSMIT-000685 | NA | Trade Partner | STOWE - AS BUILTS | 3 | 0 | 0 | NA | APPROVED | 2026-08-31 | NA | 4523 | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-31 | Carr-TRANSMIT-000093 | NA | Consultant | New Lift Updated Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-08-31 | NA | 399 | 2026-09-07 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-31 | B Smart-TRANSMIT-000110 | NA | Consultant | Purchaser Variations | 2 | 0 | 0 | NA | APPROVED | 2026-08-31 | NA | 807 | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-31 | TTW-TRANSMIT-000219 | NA | Trade Partner | M3 Stage 2 Civil Drawings | 9 | 0 | 0 | NA | APPROVED | 2026-08-31 | NA | 4525 | 2026-09-04 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-23 | SMEPS-TRANSMIT-000103 | SPARK-CRFI-KPG-000363 | Trade Partner | Lighting Level 1 IFA | 8 | 0 | 0 | NA | APPROVED | 2026-01-23 | WF-000142 | 102 | 2026-01-30 |  | KPTG-IntCorr-001387 |  | 2026-03-16 | KPTG-TRANSMIT-000540 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-31 | Eneraque-TRANSMIT-000074 | NA | Trade Partner | ENE - Fuel Storage Tanks General Arrangement - FC2 | 1 | 0 | 0 | NA | APPROVED | 2026-08-31 | NA | 1901 | 2026-09-07 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-31 | D&E-TRANSMIT-000317 | NA | Trade Partner | Approved Control Niagra master | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Wrong Revision and covering sheet is not replaced with latest revision-KPTG-TRANSMIT-001679 |  | 2026-08-31 | KPTG-TRANSMIT-001679 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-20 | Arc Plas-TRANSMIT-000001 | NA | Trade Partner | Insulation & Fastener - Tech Data Submissions | 0 | 2 | 0 | NA | APPROVED | 2026-08-20 | WF-000521 | NA | 2026-08-31 |  |  | 2026-08-31 | 2026-08-31 | KPTG-TRANSMIT-002330 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-08-31 | B Smart-TRANSMIT-000108 | NA | Consultant | Level 13 and Level 18 Amalgamation | 11 | 0 | 0 | NA | APPROVED | 2026-08-31 | NA | 809 | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-31 | VIA Arch-TRANSMIT-000252 | NA | Consultant | M2 S9 - S11 - ISSUED FOR CONSTRUCTION (FC-1) | 71 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, updated register and distributed |  | 2026-08-31 | KPTG-TRANSMIT-007523 | Closed | 71 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-31 | JCBa-TRANSMIT-000170 | NA | Consultant | Updated Architectural Documentation - Joinery Details & Joinery Schedules | 6 | 0 | 0 | NA | APPROVED | 2026-08-31 | NA | 1849 | 2026-09-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-08-31 | VIA Arch-TRANSMIT-000251 | NA | Consultant | M2 S11 L1 Concrete Profile Plan | 1 | 0 | 0 | NA | APPROVED | 2026-08-31 | NA | 1903 | 2026-09-07 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-08-31 | TATE_-TRANSMIT-000012 | NA | Trade Partner | MYWCCB - Tate - IFC Shop Drawing | 2 | 0 | 0 | NA | REJECTED | [5 empty] | DUPLICATION OF DRAWINGS WITH WRONG DOCUMENT NUMBER-KPTG-TRANSMIT-001680 |  | 2026-08-31 | KPTG-TRANSMIT-001680 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-31 | HDRAus-TRANSMIT-000557 | NA | Consultant | M3 Stage 4 - Document upload - Office Fitout Package | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For information - update register and for distribution |  | 2026-08-31 | (KPTG-TRANSMIT-021145 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-31 | Auspan-TRANSMIT-000665 | NA | Trade Partner | Update IFCed precast shop drawings. Level 5 | 26 | 0 | 26 | KPTG-IntCorr-001407 | APPROVED | [5 empty] | IFC- Waiting for Oliver advise-KPTG-IntCorr-001407 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-23 | SMEPS-TRANSMIT-000104 | SPARK-CRFI-KPG-000291 | Trade Partner | Yard Layout - Ground Level - IFC | 5 | 0 | 0 | NA | APPROVED | 2026-01-23 | WF-000144 | 103/266 | 2026-01-30 |  | KPTG-IntCorr-001389 |  | 2026-05-05 | KPTG-TRANSMIT-000822 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-08-31 | ADP-TRANSMIT-000416 | NA | Trade Partner | Fwd: ADP MEL4780 M3S4 - AS3000 Part 1 Protection Device & Generator Reports | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-08-31 | KPTG-TRANSMIT-021146 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-31 | Civilex-TRANSMIT-000295 | NA | Trade Partner | Updated Drawing Set - Southern Retaining Wall Rev M | 2 | 0 | 0 | NA | APPROVED | 2026-08-31 | WF-006837 | NA | 2026-09-14 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-31 | Auspan-TRANSMIT-000664 | NA | Trade Partner | Update IFCed precast shop drawings. Level 4. | 16 | 0 | 16 | KPTG-IntCorr-001407 | APPROVED | [5 empty] | IFC- Waiting for Oliver advise-KPTG-IntCorr-001408 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-31 | Civilex-TRANSMIT-000354 | NA | Trade Partner | Re: Southern Retaining Wall Deflection Calculations | 0 | 1 | 0 | NA | APPROVED | 2026-08-31 | WF-006837 | NA | 2026-09-14 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-08-31 | Auspan-TRANSMIT-000664 | NA | Trade Partner | Update IFCed precast shop drawings. Level 4 | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - difference in drawing status-DRAFT-012247 |  | 2026-08-31 | DRAFT-012247 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-08-31 | HDRAus-TRANSMIT-000556 | NA | Consultant | Updated IFA retaining Wall Drawings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | the documents were submitted for Approval review. However, in the case of consultant drawing approval, the review is not proceeding as an approval review. Instead, the drawing should be issued with For Information status. |  | 2026-08-31 | KPTG-SADV-007573 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-08-31 | INTRFRM-TRANSMIT-000137 | NA | Trade Partner | Geelong Edge - Civil Tech Data (Submission 12) | 0 | 2 | 0 | NA | APPROVED | 2026-08-31 | WF-000580 | NA | 2026-09-09 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-08-31 | GIW-TRANSMIT-000006 | NA | Consultant | SME -REVIEW - J1V3 Report (Rev F) and ESD Markup (v8) | 0 | 2 | 0 | NA | APPROVED | 2026-08-31 | NA | 401 | 2026-10-05 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-31 | KPTG-TRANSMIT-003366 | NA | Trade Partner | MLC ¦ BC22 Sports Dividing Net - sample submission | 0 | 1 | 0 | NA | APPROVED | 2026-08-31 | WF-001163 | NA | 2026-09-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-08-31 | EFP-TRANSMIT-000043 | NA | Trade Partner | O&M Manual Draft | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected: Document Numbeing is incorrect, requested to resubmit:KPTG-TRANSMIT-001200 |  | 2026-08-31 | KPTG-TRANSMIT-001200 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-23 | D&E-TRANSMIT-000088 |  | Trade Partner | MWYCCB - GROUND LEVEL - PIPEWORK LAYOUT ZONES - Issued For Construction | 5 | 0 | 0 | NA | APPROVED | 2026-01-23 | WF-000145 | 104 | 2026-01-30 |  | KPTG-IntCorr-001390 |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-31 | MCGC-TRANSMIT-000015 | NA | Consultant | Action Requires:- Request to fix revision and document numbering of Landscape Drawings Update | 64 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Revision id drawings do not match with title bloc of drawing-KPTG-SADV-006185 |  | 2026-08-31 | KPTG-SADV-006185 | Closed | 64 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-08-31 | Auspan-TRANSMIT-000132 | NA | Trade Partner | Remaining precast columns on level 1 issued for construction. Stage 2 Geelong Precast. | 10 | 0 | 0 | NA | APPROVED | 2026-08-31 | WF-001162 | NA | 2026-09-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-14 | D&E-TRANSMIT-000297 | NA | Trade Partner | MSSB HOOD DRIP TRAY & PIPE HEADER SPOOL | 1 | 0 | 0 | KPTG-IntCorr-002362 | APPROVED | 2026-02-06 | NA | 1366 | 2026-02-13 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-002637 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-14 | SMEPS-TRANSMIT-000248 | NA | Trade Partner | SME - SHOPDRAWINGS - SEISMIC | 1 | 0 | 0 | KPTG-IntCorr-002384 | REJECTED |  | NA | NA | [6 empty] | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-19 | D&E-TRANSMIT-000299 | NA | Trade Partner | Mechanical services-Cx Scripts-L2 - MCCs - FOA | 0 | 1 | 0 | KPTG-IntCorr-002422 | APPROVED | 2026-01-19 | WF-000879 | NA | 2026-01-26 |  |  | 2026-01-20 | 2026-01-20 | KPTG-TRANSMIT-002300 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-19 | ZIA-TRANSMIT-000069 | NA | Trade Partner | M3S1 DATAHALL A7 ORMB Location | 1 | 0 | 0 | KPTG-IntCorr-002406 | APPROVED | 2026-02-10 | NA | 1376 |  |  | 1376 - Review void-Requested by chri doh(re-issue for IFC review to Kapitol and NEXTDC only) and Resubmitted 1401 |  | 2026-02-24 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-20 | D&E-TRANSMIT-000302 | NA | Trade Partner | SCRIPTS - IFC | 0 | 1 | 0 | KPTG-IntCorr-002417 | APPROVED |  | NA | NA |  |  | IFC-Distribution Only |  | 2026-02-04 | KPTG-TRANSMIT-002413 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-03 | WilsonPD-TRANSMIT-000131 |  | Trade Partner | NEL-CNT-WPD-2990-CDR-DST-0040 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Sent back (KPTG-TRANSMIT-000289) |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-20 | D&E-TRANSMIT-000304 | NA | Trade Partner | SFN - AS LISTED - ITP -FC2 | 0 | 12 | 0 | KPTG-IntCorr-002427 | APPROVED |  | NA | NA |  |  | IFC- Distribution |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-23 | NXES-TRANSMIT-000038 | NA | Trade Partner | Ground Floor Electrical Penetration Layout | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-000653 - As per instruction FROM MARK we have updated this drawing into document register only. | 2026-01-23 | 2026-01-23 | KPTG-IntCorr-000653 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-23 | Stowe-A-TRANSMIT-000459 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - POWER CONTAINMENT LAYOUT - 23.01.2026 | 1 | 0 | 0 | NA | APPROVED | 2026-01-23 | NA | 3710 | 2026-01-28 |  |  | 2026-01-27 | 2026-01-27 | KPTG-TRANSMIT-011916 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-23 | SMEPS-TRANSMIT-000148 | NA | Trade Partner | Stage 2 - Lightning protection samples | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Document type inside and outside the documents seems different |  |  | KPTG-DA-004339 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-23 | Diadem-TRANSMIT-000004 | NA | Trade Partner | Door Schedules M3 S2 Update | 1 | 7 | 0 | NA | REJECTED | [5 empty] | Multiple issues within the documents and the register. |  | 2026-01-23 | KPTG-DA-004337 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-23 | ARCST-TRANSMIT-000185 | NA | Trade Partner | Roof Walkway Steel Marking Plan | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Status inside and outside the document seems different. |  | 2026-01-23 | KPTG-DA-004338 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-23 | SMEPS-TRANSMIT-000010 | NA | Trade Partner | LV Cable Approval | 0 | 1 | 0 | NA | APPROVED | 2026-01-23 | WF-000020 | NA | 2026-01-29 |  |  | 2026-01-23 | 2026-01-23 |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-16 | D&E-TRANSMIT-000336 | NA | Trade Partner | NXM3S2 - Upper Roof - Equipment Layout - Issued For Approval | 2 | 0 | 0 | NA | REJECTED | [5 empty] | The revision date inside and outside the documents seems different. |  | 2026-01-16 | KPTG-DA-004190 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-16 | Tradetec-TRANSMIT-000326 | NA | Trade Partner | Stage 2 - Tech Data - Siegelseal | 0 | 1 | 0 | NA | APPROVED | 2026-01-16 | WF-003843 | NA | 2026-01-29 |  |  | 2026-01-28 | 2026-01-28 | KPTG-TRANSMIT-011965 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-16 | Tradetec-TRANSMIT-000325 | NA | Trade Partner | Stage 2 - Tech Data - Bitac | 0 | 1 | 0 | NA | APPROVED | 2026-01-16 | WF-003842 | NA | 2026-01-29 |  |  |  | 2026-02-03 | KPTG-TRANSMIT-012414 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-03 | LANSA-TRANSMIT-000075 | NA | Trade Partner | Levels 10 -14 Water Services Layout IFA | 6 | 0 | 0 | NA | APPROVED | 2025-12-03 | WF-000785 | 491 | 2025-12-09 |  |  | 2026-01-14 | 2026-01-14 | KPTG-TRANSMIT-002594 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-06 | Tradetec-TRANSMIT-000315 | NA | Trade Partner | Tech Data - Site Wide - Soilworx Type A Capping Material | 0 | 1 | 0 | NA | APPROVED | 2026-01-12 | WF-003729 | NA | 2026-01-29 |  |  | 2026-01-21 | 2026-01-21 | KPTG-TRANSMIT-011708 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-16 | BASESG-TRANSMIT-000001 | NA | Trade Partner | P2649 - KPG NDC M3 - Stage 2 - Fuel - CX L2, L3, L4 and Commissioning Plan | 0 | 20 | 0 | NA | APPROVED | 2026-01-16 | WF-003847 | NA | 2026-01-29 |  |  | 2026-01-16 | 2026-02-03 | KPTG-TRANSMIT-012411 | Closed | 16 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-16 | Stowe-A-TRANSMIT-000440 | NA | Trade Partner | STOWE - TECH DATA SUBMISSION - SEISMIC EQUIPMENT - 16.01.2026 | 0 | 1 | 0 | NA | APPROVED | 2026-01-16 | WF-003832 | NA | 2026-01-28 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-013247 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-15 | KPTG-TRANSMIT-011465 | NA | Trade Partner | New Workflow Waterproofing site wide | 0 | 7 | 0 | NA | APPROVED | 2026-01-15 | WF-003829 | NA | 2026-01-23 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-09 | RDSBIM-TRANSMIT-000182 | NA | Trade Partner | GROUND FLOOR-B-G-090 FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED |  | WF-003733 | 3622 | 2026-01-15 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-21 | D&E-TRANSMIT-000306 | NA | Trade Partner | BMS Points List | 0 | 1 | 0 | KPTG-IntCorr-002440 | APPROVED |  | NA | NA |  |  | IFC-Distribution Only |  | 2026-02-04 | KPTG-TRANSMIT-002426 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-21 | D&E-TRANSMIT-000307 | NA | Trade Partner | Technical Data Submission - BMS Arch & Panel | 0 | 1 | 0 | KPTG-IntCorr-002441 | APPROVED |  | NA | NA |  |  | IFC-distribution Only |  | 2026-02-04 | KPTG-TRANSMIT-002423 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-22 | SMEPS-TRANSMIT-000249 | NA | Trade Partner | SME - 22KV INTERLOCKING SHOPDRAWINGS | 1 | 0 | 0 | KPTG-IntCorr-002454 | APPROVED | 2026-02-06 | NA | 1371 |  |  | 1371-Review void Requested by Chri doh, SME will resubmit. |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-23 | Auspan-TRANSMIT-000041 | NA | Trade Partner | Revised shop drawings issued for approval | 21 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-SADV-002729 - REVISION WRONG | 2026-01-24 | 2026-01-24 | KPTG-SADV-002729 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-23 | NXES-TRANSMIT-000039 | NA | Trade Partner | Re: Ground Floor Electrical Penetration Layout | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-000653 - As per instruction FROM MARKwe have updated this drawing into document register only. | 2026-01-23 | 2026-01-23 | KPTG-IntCorr-000653 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-02 | VIA Arch-TRANSMIT-000024 | NA | Consultant | M2 S9-11 Fuel Room Layout | 3 | 0 | 0 | NA | APPROVED | 2025-12-03 |  | 101 | 2025-12-06 |  |  | 2025-12-05 | 2025-12-08 | KPTG-TRANSMIT-000254 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-23 | Metzone-TRANSMIT-000005 | NA | Consultant | Re: Catch Deck - Column Stubs at Window Locations | 75 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-002730 - REVISION IS NOT CURRENT | 2026-01-24 | 2026-01-24 | KPTG-SADV-002730 | Closed | 75 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-23 | fjc-TRANSMIT-000123 | NA | Consultant | Precast Elevations | 2 | 0 | 0 | NA | APPROVED | 2026-01-23 |  | 522 | 2026-01-28 |  |  | 2026-01-29 | 2026-01-29 | KPTG-SADV-002778 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-23 | RDSBIM-TRANSMIT-000145 | NA | Trade Partner | LINDRUM ¦ BASEMENT LEVEL PARTITION WALL LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-01-29 |  | 526 | 2026-02-03 |  |  | 2026-01-07 | 2026-02-07 | KPTG-SADV-002927 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-21 | Normark-TRANSMIT-000014 | NA | Trade Partner | Square and round Furniture Shop drawing | 2 | 0 | 0 | NA | APPROVED | 2026-01-21 |  | 404 | 2026-01-28 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-002853 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-21 | ECBS-TRANSMIT-000061 | NA | Trade Partner | EMP-ARCH_TEC-041 Rev1 - 8mm Fairview ‘Genesis’ Range 'INFUSE' - WL04 | 0 | 1 | 0 | NA | APPROVED | 2026-01-21 | WF-000740 | NA | 2026-01-26 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-002645 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-21 | ECBS-TRANSMIT-000062 | NA | Trade Partner | EMP-ARCH-TEC-051 Rev1 8mm Fairview ‘Genesis’ Range 'RAW' - CL31 | 0 | 1 | 0 | NA | APPROVED | 2026-01-21 | WF-000741 | NA | 2026-01-26 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-002644 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-21 | SC-TRANSMIT-000035 | NA | Trade Partner | VQ33 - Facade Support Steel IFC | 5 | 0 | 0 | NA | APPROVED | [5 empty] | As per the direction from project coordinators, we have updated the drawings into Document Register only. |  | 2026-01-21 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-21 | SC-TRANSMIT-000036 | NA | Trade Partner | IFC Drawings | 6 | 0 | 0 | NA | APPROVED | [5 empty] | As per the direction, it is updated to document register. |  | 2026-01-21 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-21 | SC-TRANSMIT-000037 | NA | Trade Partner | Facade Support Steel | 2 | 0 | 0 | NA | APPROVED | [5 empty] | IFC DRAWINGS: TRANSMITTED TO TRADE AND CONSULTANTS |  | 2026-01-21 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-21 | BTWA-TRANSMIT-000065 | NA | Trade Partner | External Glazing sample | 0 | 7 | 0 | NA | APPROVED | [5 empty] | Revision of a sample is mismatched. requested to resubmit |  | 2026-01-21 | KPTG-SADV-003458 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-03 | Auspan-TRANSMIT-000014 | NA | Trade Partner | Precast shop drawings for approval. Remaining shop drawings for ground floor. | 308 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong Title Guide-KPTG-IntCorr-000188,Kapitol initiated an Internal Workflow-WF-000053 |  | 2025-12-03 | KPTG-IntCorr-000188 | Closed | 308 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-21 | SC-TRANSMIT-000038 | NA | Trade Partner | VQ27 Secondary Steel to Support Auto Slider Doors | 20 | 0 | 0 | NA | APPROVED | 2026-01-22 | WF-000744 |  | 2026-01-28 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-002221 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-21 | BTWA-TRANSMIT-000066 | NA | Trade Partner | External Glazing Sample | 0 | 7 | 0 | NA | APPROVED | 2026-01-21 | WF-000743 | NA | 2026-01-23 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-003059 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-21 | Danlai-TRANSMIT-000006 | NA | Trade Partner | Technical Data and Sample Sheet | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Please adjust the document title in the transmittal to say “WL02 primer - Eucorete Activator Data Sheet”. Its important that the arch tag is in the title of documents in the doc register, for easy understanding for the site team. BY Project Coordinator |  | 2026-01-21 | KPTG-SADV-003465 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-21 | SC-TRANSMIT-000039 | NA | Trade Partner | VQ27 Secondary Steel to Support Auto Slider Doors | 3 | 0 | 0 | NA | APPROVED | 2026-01-22 | WF-000744 |  | 2026-01-28 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-002221 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-21 | ECBS-TRANSMIT-000063 | NA | Trade Partner | Tech Data for IN01 and IN51 | 0 | 2 | 0 | NA | APPROVED | 2026-01-22 | WF-000745 | NA | 2026-01-26 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-002641 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-21 | CLADC-TRANSMIT-000013 | NA | Trade Partner | Timber door leaf shop drawings | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document Number of Sample is incorrect. Requested to resubmit. |  | 2026-01-21 | KPTG-SADV-003482 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-21 | Fredon T-TRANSMIT-000010 | NA | Trade Partner | AV Tech Data | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The sample are submitted as Zip file. requested to resubmit. |  | 2026-01-21 | KPTG-SADV-003480 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-21 | Fredon T-TRANSMIT-000011 | NA | Trade Partner | Av Tech Data -02 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The samples are submitted as zip file. requested to retransmit. |  | 2026-01-21 | KPTG-SADV-003481 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-18 | RDSBIM-TRANSMIT-000094 | NA | Trade Partner | MLCSPR ¦ OUTDOOR COURT LEVEL 02 CONCRETE PROFILE PLAN SHEET 5 | 1 | 0 | 0 | NA | APPROVED | 2025-12-18 |  | 388 | 2025-12-25 |  |  | 2026-01-21 | 2026-01-21 | KPTG-SADV-003476 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-18 | KPTG-IntCorr-003786 | NA | Trade Partner | Barnett Maxiflex Diving Board | 0 | 1 | 0 | NA | APPROVED | 2026-01-15 | WF-000712 |  | 2026-01-19 |  |  | 2026-01-21 | 2026-01-21 | KPTG-TRANSMIT-002151 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-03 | Tradetec-TRANSMIT-000278 | NA | Trade Partner | IFC - Stage 2 - LVP4 and CP15 | 2 | 0 | 0 | NA | APPROVED | 2025-12-03 | NA | 3402 | 2025-12-10 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-22 | RDSBIM-TRANSMIT-000099 | NA | Trade Partner | MLCSPR ¦ AQUATIC CENTER LEVEL 02 INTERNAL FITOUT PLAN AND ELEVATION | 3 | 0 | 0 | NA | APPROVED | 2026-01-23 |  | 407 | 2026-01-30 |  |  |  | 2026-01-27 | KPTG-SADV-003534 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-22 | Danlai-TRANSMIT-000007 | NA | Trade Partner | Technical Data and Sample Sheet | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Tech data is submitted with wrong revision, requested to resubmit |  | 2026-01-22 | KPTG-SADV-003501 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-22 | ARCH-TRANSMIT-000132 | NA | Consultant | MLC - SPR - Drawing and T-Schedule Update | 3 | 0 | 0 | NA | APPROVED | 2026-01-23 |  | 408 | 2026-01-30 |  |  |  | 2026-01-27 | KPTG-SADV-003533 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-22 | ECBS-TRANSMIT-000064 | NA | Trade Partner | EMP-ARCH-TEC-056 Rev0 - Ecowool Insulation - IN01 | 0 | 1 | 0 | NA | APPROVED | 2026-01-22 | WF-000745 |  | 2026-01-26 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-22 | BTWA-TRANSMIT-000067 | NA | Trade Partner | RE : Internal Glazing sample | 0 | 2 | 0 | NA | APPROVED | 2026-01-26 | WF-000752 | NA | 2026-01-28 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-003057 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-22 | Danlai-TRANSMIT-000008 | NA | Trade Partner | Technical Data and Sample Sheet | 0 | 1 | 0 | NA | APPROVED | 2026-01-23 | WF-000751 | NA | 2026-01-28 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-002639 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-22 | Danlai-TRANSMIT-000009 | NA | Trade Partner | WP09 - Flowcoat-cr-TDS For Construction | 0 | 1 | 0 | NA | APPROVED | [5 empty] | IFC SAMPLE-Transmitted to Trade partners & consultants |  | 2026-01-22 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-22 | Danlai-TRANSMIT-000010 | NA | Trade Partner | WP02 - Eucocrete - NWP - Data - Sheet For Construction | 0 | 1 | 0 | NA | APPROVED | [5 empty] | IFC sample-Transmitted to trade partners & consultants |  | 2026-01-22 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-22 | Danlai-TRANSMIT-000011 | NA | Trade Partner | WP04/PT62 - TDS-Rocfloor-November-2022 For Construction | 0 | 1 | 0 | NA | APPROVED | [5 empty] | IFC SAMPLE, TRANSMITTED TO TRADE & CONSULTANTS |  | 2026-01-22 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-22 | Danlai-TRANSMIT-000012 | NA | Trade Partner | WP01 - TREMboard-Data-Sheet For Construction | 0 | 1 | 0 | NA | APPROVED | [5 empty] | IFC SAMPLE, TRANSMITTED TO TRADE & CONSULTANTS |  | 2026-01-22 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-01 | fjc-TRANSMIT-000115 | NA | Consultant | Drawing Update | 8 | 0 | 0 |  | APPROVED | 2025-12-01 | NA | 470 | 2025-12-05 |  | All are approved | 2025-12-01 | 2025-12-01 | KPTG-SADV-002303 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-03 | PFP PL-TRANSMIT-000052 | NA | Trade Partner | Ground Wall Peno DWG IFA | 1 | 0 | 0 | NA | APPROVED | 2025-12-03 | NA | 3405 | 2025-12-12 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-014664 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-22 | Danlai-TRANSMIT-000013 | NA | Trade Partner | WP01 - TREMproof-250GC-Data-Sheet For Construction | 0 | 1 | 0 | NA | APPROVED | [5 empty] | IFC DRAWING- TRANSMITTED TO TRADE & CONSULTANTS |  | 2026-01-22 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-22 | Danlai-TRANSMIT-000014 | NA | Trade Partner | WP03 - TREMproof-Torch-3000-Data-Sheet For Construction | 0 | 1 | 0 | NA | APPROVED | [5 empty] | IFC SAMPLE- TRANSMITTED TO TRADE & CONSULTANTS |  | 2026-01-22 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-22 | Danlai-TRANSMIT-000015 | NA | Trade Partner | WP03 - TREMproof-Torch-Bitumen-Primer-Data-Sheet For Construction | 0 | 1 | 0 | NA | APPROVED | [5 empty] | IFC SAMPLE-TRANSMITTED TO TRADE & CONSULTANTS |  | 2026-01-22 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-22 | Tensile-TRANSMIT-000002 | NA | Trade Partner | Tensile Shop Drawings | 3 | 0 | 0 | NA | APPROVED | [5 empty] | DOCUMENT NUMBER OF THE DRAWINGS ARE INCORRECT, REQUESTED THEM TO RESUBMIT |  | 2026-01-22 | KPTG-SADV-003504 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-22 | Fredon T-TRANSMIT-000012 | NA | Trade Partner | Re: MCL Variation Scope Change - Additional Equipment | 0 | 1 | 0 | NA | APPROVED | 2026-01-23 | WF-000748 |  | 2026-01-27 |  |  |  | 2026-02-13 | KPTG-TRANSMIT-002429 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-22 | Fredon T-TRANSMIT-000013 | NA | Trade Partner | MCL Variation AV Tech Data | 0 | 28 | 0 | NA | APPROVED | 2026-01-28 | WF-000763 |  | 2026-02-06 |  | DISCIPLINE OF ALLDOCUMENT IS INCORRECT, REQUESTED TO RESUBMIT, DOCUMENTS WERE SUPERCDED BY PROJECT COORINATOR | 2026-02-13 | 2026-02-13 | KPTG-TRANSMIT-002423 | Closed | 28 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-23 | RDSBIM-TRANSMIT-000100 | NA | Trade Partner | MLCSPR ¦ AQUATIC CENTER LEVEL 02 PARTITION WAL | 3 | 0 | 0 | NA | APPROVED | 2026-01-23 |  | 405 | 2026-01-30 |  |  | 2026-03-13 | 2026-03-13 | KPTG-SADV-003865 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-23 | Tensile-TRANSMIT-000003 | NA | Trade Partner | Tensile Shop Drawings | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Document Number of drawing is not placed properly on the drawing, requested them to resubmit. |  | 2026-01-23 | KPTG-SADV-003518 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-23 | Best.-TRANSMIT-000006 | NA | Consultant | Revised Lift Directory Signage | 6 | 0 | 0 | NA | APPROVED | [5 empty] | Previous revision is still in review |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-23 | OWCCons-TRANSMIT-000017 | NA | Consultant | Fwd: Update Civil drawings - C012 | 1 | 0 | 0 | NA | APPROVED | [9 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-03 | Stowe-A-TRANSMIT-000393 | NA | Trade Partner | Stowe - Tech Data Submission - SCADA | 0 | 1 | 0 | NA | APPROVED | 2026-03-16 | WF-004821 | NA | 2026-03-25 |  | IFC TD shared with broader team | 2025-12-03 | 2025-12-03 | KPTG-TRANSMIT-010558 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-27 | HDRAus-TRANSMIT-000364 | NA | Consultant | MEL741 - FC progressive issue | 14 | 0 | 0 | NA | APPROVED | 2026-01-27 |  | 1884 | 2026-01-31 |  |  |  | 2026-01-27 | KPTG-TRANSMIT-011940 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-27 | Altaire-TRANSMIT-000061 | NA | Trade Partner | NEXTDC M3S4 - Dry Fire Roof Shop Drawings (For Approval) (C1,C2,C3) | 3 | 0 | 0 | NA | APPROVED | 2026-01-27 |  | 1886 | 2026-02-04 |  |  |  | 2026-01-30 | KPTG-TRANSMIT-012230 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-22 | TTW-TRANSMIT-000073 | N/A | Consultant | Updated Civil Stormwater IFC Drawings | 8 | 0 | 0 | 1 QA Error drawing resubmitted TTW-77 | APPROVED | 2026-01-28 | WF-000122 | 221 | 2026-01-30 |  | QA Error - KPTG-DA-000605 - resubmitted ttw-77 | 2026-01-30 | 2026-01-30 | KPTG-TRANSMIT-000353 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-22 | TTW-TRANSMIT-000074 | N/A | Consultant | Structural Documentation - Issued for Certification | 35 | 0 | 0 | NA | APPROVED | 2026-01-22 | WF-000111 | 210 | 2026-01-26 |  |  | 2026-01-28 | 2026-01-28 | KPTG-TRANSMIT-000323 | Closed | 35 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-22 | OveArup-TRANSMIT-000020 | N/A | Consultant | EARLY WORKS - SCOPE DELINEATION MATRIX | 1 | 0 | 0 | Sent clarification mail to John - KPTG-IntCorr-000228 | APPROVED | [5 empty] | Already issued document - no further action |  | 2026-01-22 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-22 | WAM-TRANSMIT-000078 | N/A | Consultant | Pages no longer in use | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | drawings made 'No Longer in use" KPTG-DA-000623 |  | 2026-01-23 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-27 | CRSol-TRANSMIT-000081 | NA | Trade Partner | M3S4 - ZONE C3 - CRS HAC SHOPDRAWINGS - ISSUED FOR APPROVAL - REV. A | 18 | 0 | 0 | NA | APPROVED | 2026-01-27 |  | 1888 | 2026-02-05 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-014560 | Open | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-27 | NXT-TRANSMIT-001217 | NA | Trade Partner | S4 FWU IFC Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-01-27 | WF-003968 |  | 2026-02-10 |  |  |  | 2026-01-28 | NXT-WTRAN-001601 | Closed | 3 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-27 | NXT-TRANSMIT-001216 | NA | Trade Partner | PDUs - AU-10025007 M3-C-Stg4/Ph1 - Data Sheet, GA, SLD, Nameplate and Schematics | 7 | 0 | 0 | NA | APPROVED | 2026-01-27 | WF-003969 |  | 2026-02-12 |  |  |  | 2026-02-10 | KPTG-TRANSMIT-012625 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-27 | Altaire-TRANSMIT-000062 | NA | Trade Partner | NEXTDC M3S4 - Dry Fire Ground Shop Drawings (FA-2) (C1,C2,C3) | 3 | 0 | 0 | NA | APPROVED | 2026-01-27 |  | 1891 | 2026-02-04 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-012083 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-03 | Stowe-A-TRANSMIT-000394 | NA | Trade Partner | Stowe - Tech Data Submission - Communication Products | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC TD shared with the broader team |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-27 | NXT-TRANSMIT-001222 | NA | Trade Partner | Fwd: IFC Bulk Tank fixing/ anchor details prior to delivery | 1 | 0 | 0 | NA | APPROVED | 2026-01-27 | WF-003979 |  | 2026-02-17 |  | For information - KPTG-TRANSMIT-011905 |  | 2026-02-09 | KPTG-TRANSMIT-012579 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-27 | NXT-TRANSMIT-001225 | NA | Trade Partner | Fwd: M3 STAGE 4 Generator 3D Models | 2 | 0 | 0 | NA | APPROVED | [5 empty] | For information- KPTG-TRANSMIT-011904 |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-23 | TTW-TRANSMIT-000076 | N/A | Consultant | Civil Update Pit Schedule | 1 | 0 | 0 | NA | REJECTED | [5 empty] | QA Error - KPTG-DA-000614 |  | 2026-01-23 | KPTG-DA-000614 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-23 | WAM-TRANSMIT-000079 | N/A | Consultant | WAM ARCH - 80% DD RCP Update | 29 | 0 | 0 | NA | APPROVED | 2026-01-23 | NA | 212 | 2026-01-28 |  |  | 2026-01-28 | 2026-01-28 | KPTG-TRANSMIT-000333 | Closed | 29 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-27 | NXT-TRANSMIT-001221 | NA | Trade Partner | Fwd: 8 tank CAD model Rev3 | 1 | 0 | 0 | NA | APPROVED | [5 empty] | For information - KPTG-TRANSMIT-011906 |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-23 | OveArup-TRANSMIT-000021 | N/A | Consultant | DISTLV ¦ Arup 80% Issue for Construction - Part 3 - Missing Revision-C02 Electrical drawings | 23 | 0 | 0 | NA | APPROVED | [5 empty] | Old revision issued as per request - update Register |  | 2026-01-23 | NA | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-23 | RDSBIM-TRANSMIT-000013 | N/A | Trade Partner | DISTLV - GROUND FLOOR FOUNDATION LAYOUT PLAN AND SECTION AND COMPLETENESS MEASURE | 7 | 0 | 0 | NA | APPROVED | 2026-01-23 | NA | 216 | 2026-01-28 |  |  | 2026-02-16 | 2026-02-16 | KPTG-TRANSMIT-000445 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-27 | ARCST-TRANSMIT-000188 | NA | Trade Partner | C1 Chiller Base Framing - Issued for Approval | 68 | 0 | 0 | NA | APPROVED | 2026-01-27 | WF-003971 |  | 2026-02-17 |  |  |  | 2026-02-20 | KPTG-TRANSMIT-013234 | Closed | 68 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-27 | NXT-TRANSMIT-001220 | NA | Trade Partner | Bulk Tanks layout & walkway-IFA-3 | 1 | 0 | 0 | NA | APPROVED | 2026-01-27 | WF-003972 |  | 2026-02-02 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-012574 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-03 | Stowe-A-TRANSMIT-000396 | NA | Trade Partner | Stowe - Tech Data Submission - DAS | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | TD IFC shared with broader team |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-27 | TTW-TRANSMIT-000154 | NA | Consultant | Traffic updates - bollard deletion | 2 | 0 | 0 | NA | APPROVED | 2026-01-27 |  | #1894 | 2026-01-29 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-012000 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-20 | LANSA-TRANSMIT-000083 | NA | Trade Partner | Levels 6,7,8, & 10 Drainage Drawings IFC | 8 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-27 | HDRAus-TRANSMIT-000363 | NA | Consultant | Re: M3S4-MEL741 - Switchroom - FC issue | 7 | 0 | 0 | NA | APPROVED | 2026-01-22 |  | 1871 | 2026-01-25 |  |  |  | 2026-01-27 | KPTG-TRANSMIT-011926 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-27 | TTW-TRANSMIT-000155 | NA | Consultant | Traffic updates - bollard deletion (part 2) | 15 | 0 | 0 | NA | APPROVED | 2026-01-27 |  | 1897 | 2026-01-29 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-011978 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-27 | ADP-TRANSMIT-000157 | NA | Consultant | ADP MEL4780 - Updated Mech drawings, | 7 | 0 | 0 | NA | APPROVED | 2026-01-27 |  | 1899 | 2026-01-30 |  |  |  | 2026-01-30 | KPTG-TRANSMIT-012216 | Closed | 7 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-01-19 | KAPITOL-TRANSMIT-000993 | NA | Trade Partner | Re Inground Shop Drawings - Amended - ELC | 2 | 0 | 0 | NA | APPROVED | 2026-01-19 |  | #272 | 2026-01-23 |  |  |  | 2026-01-23 | KAPITOL-TRANSMIT-001011 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-21 | SKS Tech-TRANSMIT-000137 | NA | Trade Partner | 4mm 2C+E fire rated cable | 0 | 1 | 0 | NA | APPROVED | 2026-01-21 | WF-000730 | NA | 2026-01-27 |  |  | 2026-02-03 | 2026-02-03 | KPTG-TRANSMIT-002659 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-21 | SKS Tech-TRANSMIT-000138 | NA | Trade Partner | 70mm 4C+E | 0 | 1 | 0 | NA | APPROVED | 2026-01-21 | WF-000731 | NA | 2026-01-27 |  |  | 2026-02-03 | 2026-02-03 | KPTG-WTRAN-001496 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-21 | VAE-Grp-TRANSMIT-000112 | NA | Trade Partner | Mechanical Services - L4 & L5 MECH ELEC & L1-L3 SCHEDULES | 4 | 3 | 0 | NA | APPROVED | 2026-01-21 | NA | 854 | 2026-01-23 |  | 3 schedules Register Updated - FC 4 drawings in ACC | 2026-02-05 | 2026-02-06 | KPTG-TRANSMIT-002723 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-21 | VAE-Grp-TRANSMIT-000113 | NA | Trade Partner | Mechanical Services - L4 Sheet 2 layout revised (duct change) & L5 BWs tundish location revised | 3 | 0 | 0 | NA | APPROVED | 2026-01-21 | NA | 856 | 2026-01-23 |  |  | 2026-02-05 | 2026-02-06 | KPTG-TRANSMIT-002727 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-03 | PFP PL-TRANSMIT-000053 | NA | Trade Partner | Water Mist Pump Plinth Layout IFC | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Seek advice from Melisa KPTG-IntCorr-007385 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-21 | Hames-TRANSMIT-000100 | NA | Consultant | IFC - Architectural Packages | 21 | 0 | 0 | NA | APPROVED | 2026-01-21 | NA | 858 | 2026-01-23 |  |  | 2026-01-22 | 2026-01-22 | KPTG-TRANSMIT-002578 | Closed | 22 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-27 | D&E-TRANSMIT-000089 |  | Trade Partner | FILTERS | 0 | 1 | 0 | NA | REJECTED | [8 empty] | KPTG-TRANSMIT-000367 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-27 | HDRAus-TRANSMIT-000367 | NA | Consultant | FC - For Buidling Permit Issue | 5 | 0 | 0 | NA | APPROVED | 2026-01-27 |  | 1901 | 2026-01-29 |  |  |  | 2026-02-02 | KPTG-TRANSMIT-012352 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-27 | SMEPS-TRANSMIT-000105 | SPARK-CRFI-KPG-000369 | Trade Partner | Lighting Control System REV5 | 0 | 1 | 0 | NA | APPROVED | 2026-01-27 | WF-000146 | NA | 2026-02-03 |  | KPTG-IntCorr-001441 | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-000478 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-27 | D&E-TRANSMIT-000090 | SPARK-CRFI-KPG-000479 | Trade Partner | FILTERS | 0 | 1 | 0 | NA | APPROVED | 2026-01-27 | WF-000147 |  | 2026-02-03 |  | KPTG-IntCorr-001442 | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-001446 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-22 | SKS Tech-TRANSMIT-000139 | NA | Trade Partner | ELECTRICAL SERVICES-PENETRATIONS LAYOUT-DAY 1-LEVEL 5 | 1 | 0 | 0 | NA | APPROVED | 2026-01-22 | WF-000739 | ACC 862 | 2026-01-27 |  |  | 2026-02-12 | 2026-02-12 | KPTG-TRANSMIT-002812 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-22 | VAE-Grp-TRANSMIT-000114 | NA | Trade Partner | MECHANICAL SERVICES - MECHANICAL CONTROL CENTRE | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected - KPTG-IntCorr-000922 |  | 2026-01-22 | KPTG-IntCorr-000922 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-22 | VAE-Grp-TRANSMIT-000119 | NA | Trade Partner | MECHANICAL SERVICES - MECHANICAL CONTROL CENTRE | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | FC Docs - Register updated |  | 2026-06-03 | VAE-Grp-TRANSMIT-000168 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-22 | Jordan-TRANSMIT-000113 | NA | Trade Partner | Level 05 - Plumbing Setouts | 1 | 0 | 0 | KPTG-IntCorr-000928 | REJECTED | [5 empty] | Rejected - QA ERROR IN REVISION |  | 2026-01-23 | KPTG-IntCorr-000928 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-03 | Stowe-A-TRANSMIT-000395 | NA | Trade Partner | Stowe - Tech Data Submission - Fire Rating Materials | 0 | 1 | 0 | NA | APPROVED | 2025-12-03 | WF-003480 | NA | 2025-12-15 |  |  |  | 2025-12-09 | KPTG-TRANSMIT-010737 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-22 | BG&E Fac-TRANSMIT-000004 | NA | Consultant | NEXTDC DATA CENTRE D2_F3P1 PBDB | 1 | 0 | 0 | NA | APPROVED | 2026-01-22 | WF-000741 | 864 | 2026-01-26 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-003927 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-22 | Hames-TRANSMIT-000102 | NA | Consultant | GLAZING SCHEDULE SHEET 1 | 1 | 0 | 0 | NA | APPROVED | 2026-01-23 | NA | 866 | 2026-01-26 |  |  | 2026-01-23 | 2026-01-23 | KPTG-TRANSMIT-002561 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-12 | NXT-TRANSMIT-001180 | NA | Client | M3ST-2- FWU FD customer comments- ref: NXT-RTRFI-000405 | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Document number for the documents are not as per the project standards. |  | 2026-01-12 | KPTG-DA-004081 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-09 | RDSBIM-TRANSMIT-000183 | NA | Trade Partner | NXM3S2 ¦ LEVEL 01 B-1-014 FEMALE WC-FLOOR FINISHES AND ELEVATIONS | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Date inside the document is incorrect. |  | 2026-01-12 | KPTG-DA-004069 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-27 | RDSBIM-TRANSMIT-000013 | NA | Trade Partner | GREYSTAR ¦ FORMATION LEVEL LAYOUT | 4 | 0 | 0 | NA | APPROVED | 2026-01-27 | WF-000147 | 284 | 2026-01-29 |  |  |  | 2026-01-27 | KPTG-TRANSMIT-000475 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-27 | POTTSENG-TRANSMIT-000005 | NA | Trade Partner | GMAC: HYD - DRAINAGE - BASEMENT 1 INGROUND - ZONE 1 & 3 LAYOUT | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to drawing revision error.- KPTG-SADV-000699 |  | 2026-01-27 | KPTG-SADV-000699 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-10 | RDSBIM-TRANSMIT-000181 | NA | Trade Partner | NXM3S2 ¦ GROUND FLOOR-B-G-032 ACC WC-FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED |  | NA | 3624 | 2026-01-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-27 | POTTSENG-TRANSMIT-000006 | NA | Trade Partner | GMAC: HYD - DRAINAGE - BASEMENT 1 INGROUND - ZONE 2,4,5 LAYOUTS | 3 | 0 | 0 | NA | APPROVED | 2026-01-27 | WF-000148 | 286 | 2026-02-04 |  |  |  | 2026-01-29 | KPTG-TRANSMIT-000492 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-27 | POTTSENG-TRANSMIT-000007 | NA | Trade Partner | GMAC HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 INGROUND - ZONE 1 & 3 LAYOUT | 257 | 0 | 0 | NA | APPROVED | 2026-01-27 | WF-000149 | 288 | 2026-02-04 |  |  |  | 2026-01-29 | KPTG-TRANSMIT-000493 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-12 | Tradetec-TRANSMIT-000317 | NA | Trade Partner | Stage 2 - IFC Drawing - CP14 | 1 | 0 | 0 | NA | APPROVED | 2026-01-12 | NA | 3629 | 2026-01-21 |  |  | 2026-01-14 | 2026-01-14 | KPTG-TRANSMIT-011443 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-03 | Tradetec-TRANSMIT-000279 | NA | Trade Partner | Penstock Valve - Tech Data - Stage 2 | 0 | 1 | 0 | NA | APPROVED | 2025-12-03 | WF-003481 | NA | 2025-12-15 |  |  |  | 2025-12-10 | KPTG-TRANSMIT-010782 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-12 | Ardon-TRANSMIT-000013 | NA | Trade Partner | Door Seal Cover Page | 0 | 1 | 0 | NA | APPROVED | 2026-01-12 | WF-003744 | NA | 2026-01-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-12 | ACG-TRANSMIT-000036 | NA | Trade Partner | M3 - S2 Samples IFC revision | 0 | 36 | 0 | NA | REJECTED | [5 empty] | Revision date seems different inside and outside of the documents. |  | 2026-01-12 | KPTG-DA-004079 | Closed | 36 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-27 | HDRAus-TRANSMIT-000369 | NA | Consultant | FC - For Building Permit Issue | 2 | 0 | 0 | NA | APPROVED | 2026-01-27 |  | #1903 | 2026-01-29 |  |  |  | 2026-02-02 | KPTG-TRANSMIT-012348 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-12 | Ardon-TRANSMIT-000015 | NA | Trade Partner | Lock Bolt Sample | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision number inside and outside the document seems different. |  | 2026-01-12 | KPTG-DA-004080 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-13 | ASV-TRANSMIT-000125 | NA | Trade Partner | Revised Samples - Fixtures | 0 | 8 | 0 | NA | REJECTED | [7 empty] | 2026-01-13 | KPTG-DA-004107 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-13 | ASV-TRANSMIT-000126 | NA | Trade Partner | Hydraulic Sample - TMV | 0 | 1 | 0 | NA | APPROVED |  | WF-003814 | NA | 2026-01-29 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-020998 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-27 | Auscool-TRANSMIT-000067 | NA | Trade Partner | Acoustic Insulation | 0 | 1 | 0 | NA | APPROVED | 2026-01-27 | WF-000571 | NA | 2026-01-29 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-001903 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-27 | Auspan-TRANSMIT-000042 | NA | Trade Partner | Revised shop drawings issued for approval | 21 | 0 | 0 | NA | APPROVED | 2026-01-28 | NA | 524 | 2026-02-04 |  |  | 2026-02-10 | 2026-02-10 | KPTG-SADV-002984 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-27 | fjc-TRANSMIT-000124 | NA | Consultant | Re: Level 1 void – infill slab option | 1 | 0 | 0 | NA | APPROVED | 2026-01-27 | NA | #523 | 2026-01-30 |  |  | 2026-02-03 | 2026-02-03 | KPTG-SADV-002853 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-22 | ARCST-TRANSMIT-000166 | NA | Trade Partner | Stage 2 - Lower Ground Additional Stairs - Issued for Review | 78 | 0 | 0 | NA | APPROVED | 2025-12-22 | WF-003688 | NA | 2026-01-07 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-03 | D&E-TRANSMIT-000286 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - CHILLED WATER & SFN WATER SCHEMATIC - GROUND FLOOR - MECH CORRIDOR & DATA HALL B1-8 | 7 | 0 | 0 | NA | APPROVED | 2025-12-03 | NA | 3409 | 2025-12-10 |  |  | 2026-01-27 | 2026-01-27 | KPTG-TRANSMIT-011909 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-13 | D&E-TRANSMIT-000327 | NA | Trade Partner | Panel Layout Drawings - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-01-13 | WF-003754 | NA | 2026-01-27 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-014173 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-27 | PROLMC-TRANSMIT-000021 | NA | Trade Partner | CD01 Fabrication drawings | 0 | 1 | 0 | NA | APPROVED | 2026-01-27 |  | 410 | 2026-02-03 |  |  |  | 2026-02-10 | KPTG-SADV-003668 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-27 | Normark-TRANSMIT-000015 | NA | Trade Partner | PL07- Mound Tunnel Sample Sheet for approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision of the sample is incorrect. Requested to resubmit. |  | 2026-01-27 | KPTG-SADV-003521 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-27 | M.S.-TRANSMIT-000037 | NA | Trade Partner | IFC Shop drawings for WL01 Wall panelling Level 1 | 4 | 0 | 0 | NA | APPROVED | [5 empty] | KPTG-IntCorr-004225: Kapitol Advice is required on Status of drawing |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-27 | Normark-TRANSMIT-000016 | NA | Trade Partner | Samples information - Soft Landscape- Mound Tunnel | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document Number of sample is incorrect., requested to resubmit. |  | 2026-01-27 | KPTG-SADV-003525 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-27 | KPTG-TRANSMIT-002195 | NA | Client | KPTG-ARCH-TEC-001 FFG10 Classroom Set of Bins Submission | 0 | 1 | 0 | NA | APPROVED | 2026-01-27 | WF-000755 |  | 2026-01-30 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-27 | Normark-TRANSMIT-000017 | NA | Trade Partner | Samples information - Soft Landscape- SP05 WSUD Inorganic Recycled Drainage Agg- Tuscan 20mm | 0 | 1 | 0 | NA | APPROVED | 2026-01-27 | WF-000758 |  | 2026-01-29 |  |  |  | 2026-02-02 | KPTG-TRANSMIT-002273 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-27 | Normark-TRANSMIT-000018 | NA | Trade Partner | Samples information - Soft Landscape- SP05- WSUD soil A2 Filter Sand | 0 | 1 | 0 | NA | APPROVED | 2026-01-27 | WF-000759 |  | 2026-01-29 |  |  |  | 2026-02-02 | KPTG-TRANSMIT-002270 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-27 | Tensile-TRANSMIT-000004 | NA | Trade Partner | Tensile Shop Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-01-27 |  | 412 | 2026-02-03 |  |  |  | 2026-02-05 | KPTG-SADV-003628 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-27 | Normark-TRANSMIT-000019 | NA | Trade Partner | Samples information - Soft Landscape- updated Mound Tunnel transmittal | 0 | 1 | 0 | NA | APPROVED | 2026-01-27 | WF-000757 |  | 2026-01-29 |  |  |  | 2026-02-02 | KPTG-TRANSMIT-002250 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-02 | RDSBIM-TRANSMIT-000120 | NA | Trade Partner | LINDRUM ¦ GROUND AND MEZZANINE LEVEL CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | NA | APPROVED | 2025-12-03 | NA | 475 | 2025-12-06 |  |  | 2025-12-09 | 2025-12-09 | KPTG-SADV-002423 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-27 | Normark-TRANSMIT-000020 | NA | Trade Partner | Samples information - Soft Landscape- SP03 Soil Profile A | 0 | 1 | 0 | NA | APPROVED | 2026-01-27 | WF-000761 |  | 2026-01-29 |  | As per the direction from Mr, Jarred, this workflow was terminated on 28.01.2023, A few changes are required on the tech data |  | 2026-01-28 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-27 | Stowe-A-TRANSMIT-000460 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - HS1 OFFICE SMALL POWER LAYOUT & COMMUNICATION DEVICE - 27.01.2026 | 1 | 0 | 0 | NA | APPROVED | 2026-01-27 | NA | 3715 | 2026-02-03 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-013274 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-27 | Stowe-A-TRANSMIT-000460 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - HS1 OFFICE SMALL POWER LAYOUT & COMMUNICATION DEVICE - 27.01.2026 | 1 | 0 | 0 | NA | APPROVED | 2026-01-27 | NA | 3713 | 2026-02-05 |  |  | 2026-03-11 | 2026-03-12 | KPTG-TRANSMIT-014213 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-27 | DS-TRANSMIT-000092 | NA | Trade Partner | HYD SITE - DRAINAGE | 1 | 0 | 0 | NA | APPROVED | 2026-01-27 | NA | 3717 | 2026-02-03 |  |  | 2026-01-29 | 2026-01-29 | KPTG-TRANSMIT-012153 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-27 | Normark-TRANSMIT-000021 | NA | Trade Partner | Samples information - Soft Landscape- SP04- Soil Profile B | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The Attached document of NMK-LA-TEC-021 is duplicates of NMK-LA-TEC-020 | 2026-01-27 | 2026-01-27 | KPTG-SADV-003540 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-27 | Tradetec-TRANSMIT-000336 | NA | Trade Partner | Tech Data Submission - Soilworx 5mm Minus Dust | 0 | 1 | 0 | NA | APPROVED | 2026-01-27 | WF-003974 | NA | 2026-01-30 |  |  | 2026-02-17 | 2026-02-17 | KPTG-TRANSMIT-013001 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-27 | Tradetec-TRANSMIT-000337 | NA | Trade Partner | Tech Data Submission - Soilworx 7mm Concrete Agg | 0 | 1 | 0 | NA | APPROVED | 2026-01-27 | WF-003977 | NA | 2026-01-30 |  |  | 2026-02-17 | 2026-02-17 | Tradetec-TRANSMIT-000337 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-27 | M.S.-TRANSMIT-000038 | NA | Trade Partner | J53 Circulation joinery IFA shop drawing for approval | 2 | 0 | 0 | NA | REJECTED | 2026-01-27 |  |  |  |  | Revision history of drawing is corrupted, requested to resubmit |  | 2026-01-27 | KPTG-SADV-003531 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-27 | M.S.-TRANSMIT-000039 | NA | Trade Partner | IFC shop drawings J41C, J80, J81, J82, J83 & J84 | 13 | 0 | 0 | NA | REJECTED | [5 empty] | Revision & Revision history of drawing are incorrect, Requested to resubmit. |  | 2026-01-27 | KPTG-SADV-003532 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-27 | WGAVIC-TRANSMIT-000046 | NA | Consultant | Structural Drawings - No Longer in Use - Issued for Information | 11 | 0 | 0 | NA | APPROVED | [5 empty] | No Longer in Use, updated register and distributed for information. |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-11-14 | Highbu-TRANSMIT-000035 | NA | Trade Partner | HPS-HY-SMP-040/41/42- GF & L1 door entry trench grates/ Puddle flange & drop in grate for Basement plant room/GF loading dock trench grates for approval | 0 | 3 | 0 | NA | APPROVED | 2025-11-17 | WF-000476 | NA | 2025-11-20 |  |  | 2025-12-03 | 2025-12-03 | KPTG-TRANSMIT-001430 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-23 | TTW-TRANSMIT-000005 | NA | Consultant | Facade IFC and Reg 126 | 12 | 0 | 0 | NA | APPROVED | 2026-01-27 |  | 210 | 2026-02-03 |  |  |  | 2026-01-29 | KPTG-TRANSMIT-000629 | Closed | 12 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-23 | Auspan-TRANSMIT-000059 | NA | Trade Partner | Update already IFCed precast shop drawings. | 25 | 0 | 0 | NA | APPROVED | [5 empty] | IFC drawings, No Review required |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-26 | Auspan-TRANSMIT-000060 | NA | Trade Partner | Update already IFCed L shape panels. | 4 | 0 | 0 | NA | APPROVED | [5 empty] | IFC drawings, No Review required. |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-26 | Auspan-TRANSMIT-000061 | NA | Trade Partner | Update dowel layout ground floor stage 9. | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Need to revise, KPTG-SADV-000784 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-26 | Auspan-TRANSMIT-000062 | NA | Trade Partner | Update IFCed shop drawings for construction. Ground floor stage 9. | 65 | 0 | 0 | NA | APPROVED | [5 empty] | IFC drawings, No review required. |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-27 | Auspan-TRANSMIT-000064 | NA | Trade Partner | Precast shop drawings for approval. Ground floor stage 9. | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Need to Revise , KPTG-SADV-000785 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-27 | Auspan-TRANSMIT-000065 | NA | Trade Partner | Precast shop drawing 0G629 for construction | 1 | 0 | 0 | NA | APPROVED | [5 empty] | IFC Drawings, No Review required. |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-27 | VIA Arch-TRANSMIT-000049 | NA | Consultant | M2 S9-11 Redesign Fire Separation Plans | 3 | 0 | 0 | NA | APPROVED | 2026-01-27 |  | 220 | 2026-02-03 |  |  |  | 2026-01-30 | KPTG-TRANSMIT-000646 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-28 | NXT-TRANSMIT-001226 EAEGROUP-TRANSMIT-000060 | NA | Trade Partner | Zone C1 IT Busduct – Shop Drawings - IFC | 7 | 0 | 0 | NA | APPROVED | 2026-01-28 | WF-003989 |  | 2026-02-13 |  | The workflow has been terminated. - NXT-PA-003237 terminated M3-ELC-EAE-SDRG-C-0401-0006-FH IT Busduct-IFC from WF3989 - NXT-PA-003255 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-01 | HDRAus-TRANSMIT-000327 | NA | Consultant | Updated Rack Layouts Stage 4 DH C1 and C2 | 1 | 0 | 0 |  | APPROVED | 2025-12-01 | NA | 1588 | 2025-12-03 |  |  |  | 2025-12-05 | HDRAus-TRANSMIT-000327 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-02 | RDSBIM-TRANSMIT-000119 | NA | Trade Partner | LINDRUM ¦ BASEMENT LEVEL CONCRETE PROFILE PLAN AND SECTIONS | 1 | 0 | 0 | NA | APPROVED | 2025-12-02 | NA | 474 | 2025-12-05 |  |  | 2025-12-03 | 2025-12-03 | KPTG-SADV-002335 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-28 | NXT-TRANSMIT-001227 | NA | Trade Partner | EAE Busduct (5000A / 2000A) – Flange Connection Shop Drawing | 3 | 0 | 0 | NA | APPROVED | 2026-01-28 | WF-003990 |  | 2026-02-13 |  |  |  | 2026-02-10 | KPTG-TRANSMIT-012653 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-27 | KARE-TRANSMIT-000079 | NA | Trade Partner | Level 13 and 14 Light and Power Shop Drawings | 8 | 0 | 0 | NA | APPROVED | 2026-01-27 | WF-000894 | 533 | 2026-02-03 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-002734 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-28 | PFP PL-TRANSMIT-000058 | NA | Trade Partner | Tech Data for approval | 0 | 7 | 0 | NA | APPROVED | 2026-01-28 | WF-003994 | NA | 2026-02-18 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-013773 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-28 | SMEPS-TRANSMIT-000152 | NA | Trade Partner | Multicore cable sample | 0 | 1 | 0 | NA | APPROVED | 2026-01-28 | WF-003998 |  | 2026-02-10 |  |  |  | 2026-01-29 | KPTG-TRANSMIT-012152 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-01-28 | B Smart-TRANSMIT-000050 | NA | Consultant | Basement RCP drawings Draft IFC | 4 | 0 | 0 | NA | APPROVED | 2026-01-28 | WF-000149 | 236 | 2026-01-30 |  |  |  | 2026-02-10 | KPTG-TRANSMIT-000430 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-22 | ECBS-TRANSMIT-000010 | NA | Trade Partner | James Hardie HardieBreak Thermal Break Strip (12mm x 43mm) | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Forwarded to all Consultants as adviced by Emma |  |  | KPTG-TRANSMIT-002551 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-22 | VAE-Grp-TRANSMIT-000117 | NA | Trade Partner | MECH - TECH SUBS & SCHEDS - CRACs & COOLING TOWERS | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  | FC Docs - Register updated |  | 2026-06-20 | KPTG-TRANSMIT-003951 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-22 | VAE-Grp-TRANSMIT-000116 | NA | Trade Partner | MECHANICAL - MCS POINTS LIST - MINOR UPDATES | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | FC Docs - Register updated - superseded by VAE-Grp-TRANSMIT-000146 |  | 2026-04-04 | VAE-Grp-TRANSMIT-000146 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-22 | VAE-Grp-TRANSMIT-000115 | NA | Trade Partner | MECH COMMISSIONING PLAN | 0 | 1 | 0 | NA | APPROVED | 2026-01-22 | WF-000735 | NA | 2026-01-28 |  |  | 2026-02-13 | 2026-02-13 | KPTG-WTRAN-001600 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-22 | RDSBIM-TRANSMIT-000051 | NA | Trade Partner | LEVEL05 - WEBFORGE SETOUT PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-01-22 | NA | 868 | 2026-01-26 |  | Drawing replaced with RDSBIM-TRN # 000052 - hence made void review 868 | 2026-01-23 | 2026-01-23 | RDSBIM-TRANSMIT-000052 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-11-26 | Auspan-TRANSMIT-000030 | NA | Trade Partner | Revised GF shop drawings issued for approval | 12 | 0 | 0 | NA | APPROVED | 2025-11-28 | NA | 468 | 2025-12-03 |  |  | 2025-12-03 | 2025-12-03 | KPTG-SADV-002340 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-23 | RDSBIM-TRANSMIT-000052 | NA | Trade Partner | LEVEL05 - WEBFORGE SETOUT PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-01-25 | NA | 870 | 2026-01-28 |  |  | 2026-02-02 | 2026-02-02 | KPTG-TRANSMIT-002648 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-23 | RDSBIM-TRANSMIT-000053 | NA | Trade Partner | LEVEL 01 CONCRETE PROFILE PLAN | 5 | 0 | 0 | NA | APPROVED | 2026-01-25 | NA | 872 | 2026-01-27 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-002866 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-23 | ECBS-TRANSMIT-000011 | NA | Trade Partner | SikaSeal® Roof & Gutter | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | No action required by Emma - Approved by Emma dtd 31/03/2026 | 2026-03-31 | 2026-03-31 | KPTG-DA-001371 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-28 | HDRAus-TRANSMIT-000370 | NA | Consultant | M3 Stage4 Concrete Profile Plan - Upper Roof - C1, C2, C3 - For construction issue | 3 | 0 | 0 | NA | APPROVED | 2026-01-28 |  | 1908 | 2026-01-31 |  |  |  | 2026-02-02 | KPTG-TRANSMIT-012344 | Open | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-23 | ZIA-TRANSMIT-000008 | NA | Trade Partner | CSMS - Network Devices Sample Documents | 0 | 4 | 0 | NA | APPROVED | 2026-01-28 | WF-000755 | NA | 2026-02-03 |  |  | 2026-02-11 | 2026-02-11 | KPTG-WTRAN-001573 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-23 | ZIA-TRANSMIT-000009 | NA | Trade Partner | CSMS - Device Register | 0 | 1 | 0 | NA | APPROVED | 2026-01-28 | WF-000756 | NA | 2026-02-03 |  |  | 2026-02-13 | 2026-02-13 | KPTG-WTRAN-001593 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-23 | ZIA-TRANSMIT-000010 | NA | Trade Partner | CSMS - Outstations drawings | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - KPTG-IntCorr-000935, 936 |  | 2026-01-26 | KPTG-IntCorr-000935, 936 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-28 | SMEPS-TRANSMIT-000012 | NA | Trade Partner | COLO4 Wesco BOM | 0 | 1 | 0 | NA | APPROVED | 2026-01-28 | WF-000024 | NA | 2026-02-04 |  |  | 2026-02-03 | 2026-02-03 | KPTG-TRANSMIT-000087 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-28 | ZIA-TRANSMIT-000040 | NA | Trade Partner | Re: Stage 3 - CSMS Device Register | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number - KPTG-TRANSMIT-012006 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-28 | NXT-TRANSMIT-001231 | NA | Trade Partner | Fwd: M3 Stage 4 Generator Data Sheets | 3 | 0 | 0 | NA | APPROVED | [5 empty] | For information - KPTG-TRANSMIT-012011 |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-03 | ECBS-TRANSMIT-000034 | NA | Trade Partner | Revised tech data for 316 stainless stain access panel | 0 | 1 | 0 | NA | APPROVED | 2025-12-03 | WF-000645 |  | 2025-12-08 |  |  | 2025-12-04 | 2025-12-04 | KPTG-TRANSMIT-001935 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-28 | D&E-TRANSMIT-000350 | NA | Trade Partner | NXM3S4 - Ground - CHW Pipe Layout ZONES - Issued For Review | 4 | 0 | 0 | NA | APPROVED |  |  | 1904 | 2026-02-05 |  |  |  | 2026-02-11 | KPTG-TRANSMIT-012734 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-28 | ZIA-TRANSMIT-000039 | NA | Trade Partner | Re: M3S4 CSMS Ground level SLA sensor Location | 3 | 0 | 0 | NA | REJECTED |  |  |  | 2026-02-05 |  | QA REJECTED DUE TO WRONG TYPE MENTIONED IN THE DRAWING |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-28 | SMEPS-TRANSMIT-000013 | NA | Trade Partner | SME COLO4 AFL BOM | 0 | 2 | 0 | NA | APPROVED | 2026-01-28 | WF-000025 | NA | 2026-02-04 |  |  | 2026-02-02 | 2026-02-02 |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-28 | SMEPS-TRANSMIT-000011 | NA | Trade Partner | Tech Data- Isolation Transformers XFM02 | 0 | 1 | 0 | NA | APPROVED | 2026-01-28 | WF-000021 | NA | 2026-02-04 |  |  | 2026-02-03 | 2026-02-03 | KPTG-TRANSMIT-000084 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-28 | Auscool-TRANSMIT-000068 | NA | Trade Partner | Cold Shell Levels IFC | 8 | 0 | 0 | NA | APPROVED | 2026-01-28 | NA | 525 | 2026-02-04 |  |  | 2026-02-24 | 2026-02-24 | KPTG-SADV-003203 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-28 | IVS-TRANSMIT-000324 | NA | Consultant | STR - Cooling Tower & Chiller Room Platform Zone C1 - Construction Issue (Revised as clouded) | 1 | 0 | 0 | NA | APPROVED | 2026-01-28 |  | 1910 | 2026-01-30 |  |  |  | 2026-02-02 | KPTG-TRANSMIT-012327 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-28 | SMEPS-TRANSMIT-000155 | NA | Trade Partner | STAGE 4 - Inground Site Layout (C07) | 1 | 0 | 0 | NA | APPROVED | 2026-01-28 |  | 1912 | 2026-02-04 |  |  |  | 2026-02-17 | The workflow has been terminated as requested by Charlie | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-28 | ZIA-TRANSMIT-000042 | NA | Trade Partner | CSMS Device List - Stage 3 | 0 | 1 | 0 | NA | APPROVED | 2026-01-28 | WF-004007 | NA | 2026-02-05 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-013588 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-28 | M.S.-TRANSMIT-000040 | NA | Trade Partner | Updated J41C Shop drawing | 1 | 0 | 0 | NA | APPROVED | [5 empty] | IFC DRAWINGS: TRANSMITTED TO TRADE PARTNERS & CONSULTANTS |  | 2026-01-28 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-28 | Normark-TRANSMIT-000022 | NA | Trade Partner | Samples information - Soft Landscape- SP03 soil Profile A- revised | 0 | 1 | 0 | NA | APPROVED | 2026-01-28 | WF-000766 |  | 2026-01-30 |  |  |  | 2026-02-02 | KPTG-TRANSMIT-002262 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-03 | Highbu-TRANSMIT-000105 | NA | Trade Partner | Revised drawing | 1 | 0 | 0 | NA | APPROVED | [5 empty] | IFC DRAWING,Transmitted to consultants and trade partners |  | 2025-12-03 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-28 | M.S.-TRANSMIT-000041 | NA | Trade Partner | Updated IFA shop drawing for J53 | 2 | 0 | 0 | NA | APPROVED | 2026-01-28 |  | 414 | 2026-02-04 |  |  | 2026-03-11 | 2026-03-12 | KPTG-SADV-003847 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-28 | Normark-TRANSMIT-000023 | NA | Trade Partner | Samples information - Soft Landscape- SP04 soil profile B revised title | 0 | 1 | 0 | NA | APPROVED | 2026-01-28 | WF-000765 |  | 2026-01-30 |  |  |  | 2026-02-02 | KPTG-TRANSMIT-002265 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-28 | M.S.-TRANSMIT-000042 | NA | Trade Partner | Updated IFC shop drawings J80, J81, J82, J83 & J84 | 10 | 0 | 0 | NA | APPROVED | [5 empty] | IFC Drawings- Transmitted to Trade Partners & Consultants |  | 2026-01-28 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-28 | Arco-TRANSMIT-000012 | NA | Trade Partner | BIFOLD DOORS - WEST AND EAST CARPARK | 3 | 0 | 0 | NA | APPROVED | 2026-01-28 |  | 415 | 2026-02-02 |  |  |  | 2026-01-30 | KPTG-SADV-003580 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-28 | M.S.-TRANSMIT-000043 | NA | Trade Partner | IFA shop drawing for J80 | 2 | 0 | 0 | NA | APPROVED | 2026-01-28 |  | 416 | 2026-02-04 |  |  | 2026-03-11 | 2026-03-12 | KPTG-SADV-003846 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-28 | M.S.-TRANSMIT-000044 | NA | Trade Partner | Updated IFC shop drawing for WL01 Wall panellin | 4 | 0 | 0 | NA | APPROVED | [5 empty] | IFC Drawings- Transmitted to trade partners & consultants |  | 2026-01-28 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-28 | M.S.-TRANSMIT-000045 | NA | Trade Partner | FSG12 - robe hook sample form | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Sample requires modification. |  | 2026-01-28 | KPTG-IntCorr-004263 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-28 | SRA48-TRANSMIT-000001 | NA | Trade Partner | Hoist re-IFC Drawings | 12 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Document Number of all drawings are incorrect. |  | 2026-01-28 | KPTG-SADV-002761 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-28 | SMEPS-TRANSMIT-000014 | NA | Trade Partner | Tech Data- Light fittings | 0 | 8 | 0 | NA | APPROVED | 2026-01-28 | WF-000026 | NA | 2026-02-04 |  |  | 2026-02-03 | 2026-02-03 | KPTG-TRANSMIT-000085 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-03 | ECBS-TRANSMIT-000035 | NA | Trade Partner | Knauf Wall Type Proposal Report | 0 | 1 | 0 | NA | APPROVED | 2025-12-03 | WF-000648 |  | 2025-12-08 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-28 | INGEN3D-TRANSMIT-000681 | NA | Consultant | I3D-378 Next DC M3 Stage 4 - Acoustic Wall - IFA (28-01-2026) | 36 | 0 | 0 | NA | APPROVED | 2026-01-29 | WF-004014 |  | 2026-02-24 |  | Please note that the approval status seems different status for some documents in Aconex and inside the drawings Workflow processed, as per requested by Oliver - KPTG-IntCorr-008606 |  | 2026-02-05 | KPTG-TRANSMIT-012526 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-23 | SKS Tech-TRANSMIT-000140 | NA | Trade Partner | LEVEL 4 & 5 IFC LAYOUTS | 5 | 0 | 0 | NA | APPROVED | 2026-01-23 | NA | 876 | 2026-01-28 |  |  | 2026-01-29 | 2026-01-29 | KPTG-TRANSMIT-002624 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-23 | SKS Tech-TRANSMIT-000141 | NA | Trade Partner | LEVEL 1 POWER CONTAINMENT IFC UPDATE | 1 | 0 | 0 | NA | APPROVED | 2026-01-23 | NA | 874 | 2026-01-28 |  | made void by Emma | 2026-01-27 | 2026-01-30 | KPTG-IntCorr-000946 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-28 | Auspan-TRANSMIT-000066 | NA | Trade Partner | Update already IFCed precast columns 0GC053 and 0GC054 | 2 | 0 | 0 | NA | APPROVED | [5 empty] | IFC drawings, No review required |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-28 | Auspan-TRANSMIT-000067 | NA | Trade Partner | Update already IFCed precast columns 0GC053 and 0GC054 | 2 | 0 | 0 | NA | APPROVED | [5 empty] | IFC drawings, No review required |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-28 | HGP-TRANSMIT-000035 |  | Trade Partner | Heritage Glass - Sample DB-4 Door Sweep Seal | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Wrong document number and title (KPTG-TRANSMIT-000370) |  | 2026-01-28 | KPTG-TRANSMIT-000370 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-28 | BLUESF-TRANSMIT-000038 | NA | Trade Partner | M2-STR-BSF-SDRG-1101-MP1103 - RE-ISSUE FOR APPROVAL | 1 | 0 | 0 | NA | APPROVED | [5 empty] | No review required, updated register |  | 2026-02-09 | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-28 | HGP-TRANSMIT-000036 |  | Trade Partner | Heritage Glass - Sample DB-4 Door Sweep Seal - Updated | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Wrong document number (KPTG-TRANSMIT-000371) |  | 2026-01-28 | KPTG-TRANSMIT-000371 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-28 | HGP-TRANSMIT-000037 |  | Trade Partner | Heritage Glass - Sample DB-4 Door Sweep Seal - Updated Document Number | 0 | 1 | 0 | NA | APPROVED | 2026-01-28 | WF-000148 |  | 2026-02-04 |  | KPTG-IntCorr-001457 |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-28 | UNI-TRANSMIT-000004 | NA | Trade Partner | M2 S9-11 Tower Cranes - TC1,TC2,TC3 Drawing Updates | 6 | 0 | 0 | NA | APPROVED | [5 empty] | IFCs, No review required |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-03 | KPTG-IntCorr-003418 | NA | Trade Partner | Crafted Stainless Shop Drawings | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Shared Drawings are combined with sub drawing, requested them resubmit |  | 2025-12-03 | KPTG-IntCorr-003419 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-27 | TTW-TRANSMIT-000006 | NA | Consultant | Facade IFC drawing revision update | 5 | 0 | 0 | NA | APPROVED | 2026-01-27 |  | 210 | 2026-02-03 |  |  |  | 2026-01-29 | KPTG-TRANSMIT-000634 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-23 | VIA Arch-TRANSMIT-000044 | N/A | Consultant | M2 S9-11 Pricing Issue Update | 58 | 0 | 0 | NA | APPROVED | 2026-01-28 |  | 213 | 2026-02-03 |  |  | 2026-02-02 | 2026-02-02 | KPTG-TRANSMIT-000676 | Closed | 58 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-24 | VIA Arch-TRANSMIT-000045 | NA | Consultant | VIA Wall type detail update | 3 | 0 | 0 | NA | APPROVED | 2026-01-27 |  | 214 | 2026-02-03 |  |  |  | 2026-01-30 | KPTG-TRANSMIT-000642 | Closed | 3 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-27 | KPTG-IntCorr-000313 | N/A | Consultant | Structural Drawings - Issued for Tender | 99 | 0 | 0 | NA | APPROVED | 2026-01-27 |  | 218 | 2026-02-04 |  |  |  | 2026-01-30 | KPTG-TRANSMIT-000637 | Closed | 99 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-29 | Auspan-TRANSMIT-000068 | NA | Trade Partner | Update precast shop drawings for construction. | 12 | 0 | 0 | NA | APPROVED | [5 empty] | IFCs, No review required. |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-29 | OveArup-TRANSMIT-000156 | NA | Consultant | M3 Stage 3 SCADA Schematic Drawings for HVSB in Stage 2 & Stage 4 | 2 | 0 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-29 | KPTG-TRANSMIT-012031 | NA | Trade Partner | Paint Tech Data Submittal for Workflow | 0 | 11 | 0 | NA | APPROVED | 2026-01-29 | WF-004010 |  | 2026-02-16 |  | The review of one document has been completed. -KPTG-TRANSMIT-012289 - |  | 2026-02-02 | KPTG-TRANSMIT-012289 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-14 | Auspan-TRANSMIT-000039 | NA | Trade Partner | Revised Mezzanine drawings issued for approval | 4 | 0 | 0 | NA | APPROVED | 2026-01-14 |  | 513 | 2026-01-21 |  |  | 2026-01-29 | 2026-01-29 | KPTG-SADV-002774 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-11-25 | PCForm-RTRFI-000002 | NA | Trade Partner | Required Documentation - NXM2S9-11 | 0 | 6 | 0 | NA | APPROVED | 2025-11-27 | WF-000044 |  | 2025-12-05 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-000622 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-29 | SKS Tech-TRANSMIT-000008 | NA | Trade Partner | SKS - Tech Data Seismic Vertigos | 0 | 1 | 0 | NA | APPROVED | 2026-01-29 | WF-004018 |  | 2026-02-19 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-11-20 | M.S.-TRANSMIT-000030 | NA | Trade Partner | IFA Shop drawings for WL01 Wall panels | 4 | 0 | 0 | NA | APPROVED | 2025-11-20 |  | 343 | 2025-11-27 |  |  | 2025-12-03 | 2025-12-03 | KPTG-SADV-002944 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-09-17 | PFP PL-TRANSMIT-000033 | NA | Trade Partner | Roof Level Zone 1D IFC | 1 | 0 | 0 | NA | APPROVED | 2025-09-22 | NA | 1120 | 2025-09-29 |  |  | 2025-10-22 | 2025-10-22 | KPTG-TRANSMIT-001836 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-29 | NXT-TRANSMIT-001233 EAEGROUP-TRANSMIT-000068 | NA | Trade Partner | 1000A TAP OFF BOX-1250A - Depth Change | 0 | 1 | 0 | NA | APPROVED | 2026-01-29 | WF-004019 |  | 2026-02-16 |  |  |  | 2026-02-11 | KPTG-TRANSMIT-012716 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-23 | Baigents-TRANSMIT-000058 | NA | Trade Partner | DH7-8 Door Penetration Steel - Updated Shop Drawings - For Fabrication | 7 | 0 | 0 | KPTG-IntCorr-002474 | REJECTED |  | NA | NA |  |  | REV 1 is already locked |  |  | KPTG-TRANSMIT-002653 | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-29 | NXT-TRANSMIT-001234 ABB-TRANSMIT-000024 | NA | Trade Partner | ABB PDUs - AU-10025007 - M3 Stage 4 / Ph1 - Quality Documents | 4 | 0 | 0 | NA | APPROVED | 2026-01-29 | WF-004020 | NA | 2026-02-16 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-013510 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-23 | SMEPS-TRANSMIT-000252 | NA | Trade Partner | SME- Samples Submission - IFA | 0 | 1 | 0 | NA | APPROVED | 2026-01-24 | WF-000851 | NA | 2026-01-31 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-23 | SMEPS-TRANSMIT-000251 | NA | Trade Partner | SME- Samples Submission - IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | No need to submission |  |  | KPTG-IntCorr-002490 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-22 | D&E-TRANSMIT-000308 | NA | Trade Partner | COMMISSIONING PLAN - FC2 | 0 | 1 | 0 | KPTG-IntCorr-002473 | APPROVED |  | NA | NA |  |  | IFC-Distribution Only | 2026-02-04 | 2026-02-04 | KPTG-TRANSMIT-002410 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-29 | PARR-TRANSMIT-000112 NXT-TRANSMIT-001235 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - BFS SCHEMATIC | 1 | 0 | 0 | NA | APPROVED | 2026-01-29 | WF-004021 |  | 2026-02-12 |  |  |  | 2026-02-05 | KPTG-TRANSMIT-012509 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-23 | D&E-TRANSMIT-000309 | NA | Trade Partner | LEVEL 1 ZONE B PIPE SECTIONS SHEET 2 - Issued For Construction | 1 | 0 | 0 | KPTG-IntCorr-002475 | APPROVED |  | NA | NA |  |  | IFC-Distribution Only |  | 2026-02-10 | KPTG-TRANSMIT-002590 | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-23 | D&E-TRANSMIT-000310 | NA | Trade Partner | SECONDARY FLUID NETWORK SCHEMATIC - Issued For Construction | 1 | 0 | 0 | KPTG-IntCorr-002477 | APPROVED | 2026-01-27 | NA | 1350 | 2026-02-03 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-002645 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-11-28 | KPTG-IntCorr-003302 | NA | Trade Partner | Raw Sample Parapet Cladding and Capping | 0 | 2 | 0 | NA | APPROVED | 2025-12-02 | WF-000634 |  | 2025-12-04 |  |  | 2025-12-03 | 2025-12-03 | KPTG-TRANSMIT-001919 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-23 | ETNInd-TRANSMIT-000070 | NA | Trade Partner | UPS FD issued for Construction | 0 | 1 | 0 | KPTG-IntCorr-002478 | APPROVED |  | NA | NA |  |  | IFC-Distribution Only |  | 2026-02-20 | KPTG-TRANSMIT-002613 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-29 | SKS Tech-TRANSMIT-000009 | NA | Trade Partner | SKS - Seismic Vertigo Hangers - Iccons Thunderbolt | 0 | 1 | 0 | NA | APPROVED | 2026-01-29 | WF-004022 |  | 2026-02-19 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2026-01-29 | RDSBIM-TRANSMIT-000195 | NA | Trade Partner | LOWER GROUND STAIR & RAMP PLAN & SECTIONS | 6 | 0 | 0 | NA | APPROVED | 2026-01-29 | NA | 570 | 2026-02-05 |  |  | 2026-02-04 | 2026-02-04 | KPTG-TRANSMIT-002559 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-29 | RDSBIM-TRANSMIT-000153 | NA | Trade Partner | LEVEL12 RCP LAYOUT TOWER A & B | 4 | 0 | 0 | NA | APPROVED | 2026-01-29 | WF-000895 | 534 | 2026-02-05 |  |  | 2026-02-10 | 2026-02-10 | KPTG-TRANSMIT-002687 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-29 | RDSBIM-TRANSMIT-000154 | NA | Trade Partner | LEVEL13 RCP LAYOUT TOWER B | 2 | 0 | 0 | NA | APPROVED | 2026-01-29 | WF-000896 | 535 | 2026-02-05 |  |  | 2026-02-10 | 2026-02-10 | KPTG-TRANSMIT-002686 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-29 | NXT-TRANSMIT-001236 EAEGROUP-TRANSMIT-000065 | NA | Trade Partner | Zone C1 FA IT Busduct – Shop Drawings - IFC | 1 | 0 | 0 | NA | APPROVED | 2026-01-29 | WF-004025 |  | 2026-02-16 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-29 | SMEPS-TRANSMIT-000015 | NA | Trade Partner | SME Shop Drawing Review | 14 | 0 | 0 | NA | APPROVED | 2026-01-29 | WF-000028 | NA | 2026-02-05 |  |  | 2026-02-08 | 2026-02-08 | KPTG-TRANSMIT-000094 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-29 | TATE_-TRANSMIT-000015 | NA | Trade Partner | SCEC WALL TYPICAL DETAILS REVISION C | 1 | 0 | 0 | NA | APPROVED | 2026-01-29 | WF-000029 | NA | 2026-02-05 |  |  | 2026-02-09 | 2026-02-09 | KPTG-TRANSMIT-000101 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-29 | SMEPS-TRANSMIT-000158 | NA | Trade Partner | 22KV - Multicore cable sample | 0 | 1 | 0 | NA | APPROVED | 2026-01-29 | WF-004027 |  | 2026-02-11 |  |  |  | 2026-01-30 | KPTG-TRANSMIT-012227 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-29 | D&E-TRANSMIT-000357 | NA | Trade Partner | Victaulic Valves & Fittings - Issued for approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The revision number is not mentioned in the document. - KPTG-TRANSMIT-012178 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-11-27 | RDSBIM-TRANSMIT-000084 | NA | Trade Partner | MLCSPR ¦ AQUATIC CENTER LEVEL 01 BLOCKWORK PLAN & ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2025-11-28 |  | 356 | 2025-12-03 |  |  | 2025-12-03 | 2025-12-03 | KPTG-SADV-002950 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-29 | RDSBIM-TRANSMIT-000016 | NA | Trade Partner | GREYSTAR ¦ FORMATION LEVEL LAYOUT ZONE 2,4 & 5 | 4 | 0 | 0 | NA | APPROVED | 2026-01-29 | WF-000151 | 292 | 2026-02-02 |  |  |  | 2026-01-29 | KPTG-TRANSMIT-000489 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-08-18 | ZIA-TRANSMIT-000021 | NA | Trade Partner | CSMS OS Panel Seismic Design-Wall Bracket mounting | 1 | 0 | 0 | NA | APPROVED | 2025-08-27 | NA | 872 | 2025-09-03 |  |  | 2026-01-27 | 2026-02-20 | KPTG-TRANSMIT-002343 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-29 | Auspan-TRANSMIT-000058 | NA | Trade Partner | Update dowel layout for zone 3, 4, 5 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect drawing status - KPTG-SADV-000729 |  | 2026-01-29 | KPTG-SADV-000729 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-29 | Auspan-TRANSMIT-000059 | N/A | Trade Partner | Precast shop drawings for approval. Ground floor | 22 | 0 | 0 | NA | APPROVED | 2026-01-29 | WF-000152 | 294 | 2026-02-04 |  |  |  | 2026-02-11 | KPTG-TRANSMIT-000579 | Closed | 22 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-29 | JCBa-TRANSMIT-000052 | NA | Consultant | Structural Setout Plans - Basement & Pit (Fire Tank Sump & Goods Lift updates | 3 | 0 | 0 | NA | APPROVED | 2026-01-29 | WF-000156 | 296 | 2026-02-02 |  |  |  | 2026-02-03 | KPTG-TRANSMIT-000518 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-09-12 | Altaire-TRANSMIT-000022 | NA | Trade Partner | Dry Fire Schematic - IFC | 2 | 0 | 0 | NA | APPROVED | 2026-01-16 | NA | 1339 | 2026-01-23 |  |  | 2026-01-27 | 2026-01-28 | KPTG-TRANSMIT-002351 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-09-30 | D&E-TRANSMIT-000212 | NA | Trade Partner | L1 MECH ELECTRICAL SENSOR LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-01-16 | NA | 1341 | 2026-01-23 |  |  | 2026-01-27 | 2026-01-28 | KPTG-TRANSMIT-002363 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-01-29 | D&E-TRANSMIT-000092 | SPARK-CRFI-KPG-000313 | Trade Partner | MWYCCB - COMPRESSED AIR SCHEMATIC MECHANICAL SERVICES SHEET 1 OF 1 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-01-29 | WF-000149 | 105/267 | 2026-02-05 |  | KPTG-IntCorr-001471 | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000824 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-09 | SMEPS-TRANSMIT-000116 , SMEPS-SUBADVICE-000279 | NA | Trade Partner | SME - Lux plots issued for approval DH7 and DH8 | 5 | 0 | 0 | NA | APPROVED | 2025-12-09 | NA | 1296 | 2025-12-16 |  |  | 2026-01-21 | 2026-01-28 | KPTG-TRANSMIT-002365 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-11-27 | RDSBIM-TRANSMIT-000085 | NA | Trade Partner | MLCSPR ¦ AQUATIC CENTER LEVEL 01 HOB LAYOUT PLAN | 1 | 0 | 0 | NA | APPROVED | 2025-11-28 |  | 357 | 2025-12-03 |  |  | 2025-12-03 | 2025-12-03 | KPTG-SADV-002949 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-22 | SMEPS-TRANSMIT-000226, 238,240 | NA | Trade Partner | SME Electrical Services - IFC Submission | 5 | 0 | 0 | NA | APPROVED | 2026-01-22 | NA | 1346 | 2026-01-29 |  |  | 2026-01-27 | 2026-01-28 | KPTG-TRANSMIT-002371 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-29 | JAZBC-TRANSMIT-000006 | NA | Consultant | Updated BCA Report | 0 | 1 | 0 | NA | APPROVED | 2026-01-29 |  | 227 | 2026-02-05 |  |  |  | 2026-01-30 | KPTG-TRANSMIT-000650 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-29 | ZIA-TRANSMIT-000044 | NA | Trade Partner | Re M3S4 CSMS Ground level & Level 1 SLA sensor Location (FOA-1) | 6 | 0 | 0 | NA | APPROVED | 2026-01-29 | NA | 1917 | 2026-02-06 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014348 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-29 | Tradetec-TRANSMIT-000339 | NA | Trade Partner | Stage 4 IFA - C36 | 1 | 0 | 0 | NA | APPROVED | 2026-01-29 |  | 1919 | 2026-02-06 |  |  |  | 2026-02-05 | KPTG-TRANSMIT-012527 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-01-29 | KEECEPRO-TRANSMIT-000015 | NA | Trade Partner | Re: IFC Shop Drawings | 4 | 0 | 0 | NA | REJECTED | 2026-01-29 |  |  |  |  | the document KCE-ELE-SPD-B18-4002 shows a different drawing title on Aconex compared to the title inside the drawing. Additionally, a mistake has been identified in the Revision History Description. The correct reason must be added there. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-01-29 | KEECEPRO-TRANSMIT-000016 | NA | Trade Partner | MSB Shop Drawing | 1 | 0 | 0 | NA | APPROVED |  |  | 276 | 2026-02-04 |  |  |  | 2026-02-04 | : KAPITOL-TRANSMIT-001037 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-22 | RDSBIM-TRANSMIT-000199 | NA | Trade Partner | NXM3S4 LEVEL 01-C-G-042 CLEANER FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-01-22 |  | 1872 | 2026-01-26 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-012035 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-29 | SMEPS-TRANSMIT-000016 | NA | Trade Partner | Tech Data - Secure Duct, and Comms Cabling Accesories | 0 | 2 | 0 | NA | APPROVED | 2026-01-29 | WF-000031 | NA | 2026-02-05 |  |  | 2026-02-08 | 2026-02-08 | KPTG-TRANSMIT-000092 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-29 | Entire M-TRANSMIT-000002 | NA | Trade Partner | Mechanical IFA Rev A Sample Submissions | 0 | 1 | 0 | NA | APPROVED | 2026-01-29 | WF-000030 | NA | 2026-02-05 |  | WF - TErminated | 2026-01-29 | 2026-01-29 |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-01 | Auspan-TRANSMIT-000018 | NA | Trade Partner | Auspan-TRANSMIT-000018 Precast shop drawings for approval. Basement | 54 | 0 | 0 | NA | APPROVED | 2025-12-01 | WF-000072 | 140 | 2025-12-05 |  |  |  | 2025-12-08 | KPTG-TRANSMIT-000265 | Closed | 54 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-11-28 | Fredon T-TRANSMIT-000001 | NA | Trade Partner | AV Shop drawings for approval | 1 | 0 | 0 | NA | APPROVED | 2025-11-29 |  | 358 | 2025-12-05 |  |  | 2025-12-03 | 2025-12-02 | KPTG-SADV-002951 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-28 | JCI-TRANSMIT-000003 | NA | Trade Partner | COLO 4 Documents | 0 | 32 | 0 | NA | APPROVED | 2026-02-10 | WF-000093 | NA | 2026-02-16 |  | KPTG-IntCorr-000070, Zip files with 118 docs. WF-000033 Terminated 30/1/26, WF-000090 Terminated 10/2/26, | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-000310 | Closed | 32 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-28 | SIL-TRANSMIT-000020 | NA | Trade Partner | Requested Documents | 100 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | "DRAFT-000332, Sent back to originator, awaiting approval, mix up of doc. status." |  |  |  | Closed | 100 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-29 | SMEPS-TRANSMIT-000017 | NA | Trade Partner | SME Shop Drawing Review EPMS | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | DRAFT-000340, Sent back to originator, awaiting approval, Doc. No. mismatch |  |  |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-29 | SMEPS-TRANSMIT-000018 | N/A | Trade Partner | Tech-Data Motion detectors | 0 | 1 | 0 | NA | REJECTED |  | N/A | NA |  |  | DRAFT-000346, Sent back to Originator, Awating Approval, Title mismatch. |  |  |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-19 | Schindle-SUBRFI-000016 | NA | Trade Partner | 000131 - PL1 Landing Frames. | 2 | 0 | 0 | NA | APPROVED | 2026-01-29 | WF-004034 | NA | 2026-02-11 |  |  | 2026-03-11 | 2026-03-12 | KPTG-TRANSMIT-014179 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-29 | ARCST-TRANSMIT-000190 | NA | Trade Partner | Loading Dock Steel - Issued for Approval | 24 | 0 | 0 | NA | REJECTED | [5 empty] | Multiple issues | 2026-01-29 | 2026-01-29 | KPTG-DA-004457 | Closed | 24 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-28 | KPTG-TRANSMIT-011971 / Schindle-TRANSMIT-000016 | NA | Trade Partner | New Workflow Schindler Lifts | 6 | 0 | 0 | NA | APPROVED | 2026-01-28 | WF-003997 |  | 2026-02-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-28 | KPTG-TRANSMIT-012032 | NA | Trade Partner | Workflow Submittal for Epoxy Flooring | 0 | 1 | 0 | NA | APPROVED | 2026-01-29 | WF-004033 | NA | 2026-02-16 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-29 | D&E-TRANSMIT-000356 | NA | Trade Partner | HS1 Mechanical Rooftop dwg | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Revision number inside and outside is incorrect. | 2026-01-29 | 2026-01-29 | KPTG-DA-004450 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-29 | D&E-TRANSMIT-000355 | NA | Trade Partner | NXM3S2 - Industrial Water Schematic - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-01-29 | NA | 3736 | 2026-02-05 |  | As instructed by Ibrahim Shekari Soleimanloo KPTG-IntCorr-009745 |  | 2026-02-20 |  | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-02 | Fredon T-TRANSMIT-000009 | NA | Trade Partner | Surface mount Speaker - Pool Side North Tech Data | 0 | 1 | 0 | NA | APPROVED | 2025-12-02 | WF-000642 |  | 2025-12-04 |  |  | 2025-12-03 | 2025-12-03 | KPTG-TRANSMIT-001931 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-29 | D&E-TRANSMIT-000354 | NA | Trade Partner | NXM3S2 - Air Schematic - Issued For Review | 1 | 0 | 0 | NA | APPROVED | 2026-01-29 | NA | 3731 | 2026-02-09 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-014619 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-29 | KPTG-TRANSMIT-012116 | NA | Trade Partner | Symal - IFA Crash Barrier Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-01-29 | WF-004026 | NA | 2026-02-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-29 | SMEPS-TRANSMIT-000157 | NA | Trade Partner | Stage 2 - Lightning protection samples | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Document number is not as per project standards. |  | 2026-01-29 | KPTG-DA-004425 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-29 | BASESG-TRANSMIT-000003 | NA | Trade Partner | M3 Stage 2 – Request for Commissioning Plan, FD & ITP | 0 | 3 | 0 | NA | APPROVED | 2026-01-29 | WF-004028 | NA | 2026-02-09 |  |  |  | 2026-02-13 | KPTG-TRANSMIT-012851 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-29 | D&E-TRANSMIT-000353 | NA | Trade Partner | Bermad Valves - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-01-29 | WF-004013 | NA | 2026-02-12 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-28 | KPTG-IntCorr-008582 | NA | Trade Partner | Upload & Transmit Documents | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-01-28 | KPTG-TRANSMIT-012042 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-28 | KPTG-TRANSMIT-012032 | NA | Trade Partner | Workflow Submittal for Epoxy Flooring | 0 | 1 | 0 | NA | APPROVED |  | WF-004033 | NA | 2026-01-16 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-29 | ACG-TRANSMIT-000041 | NA | Trade Partner | Re: M3 - Stage 3 Samples | 0 | 17 | 0 | NA | REJECTED | [5 empty] | The revision number is not mentioned in the document |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-28 | RDSBIM-TRANSMIT-000014 | NA | Trade Partner | GREYSTAR - FORMATION LEVEL LAYOUT | 4 | 0 | 0 | NA | APPROVED | 2026-01-28 | WF-000150 | 290 | 2026-01-30 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-000486 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-11-05 | Normark-TRANSMIT-000001 | NA | Trade Partner | PV02 Bluestone sample sheet - For review and approval | 0 | 1 | 0 | NA | APPROVED | 2025-11-14 | WF-000581 |  | 2025-11-18 |  |  | 2025-12-03 | 2025-12-03 | KPTG-TRANSMIT-001932 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-29 | Normark-TRANSMIT-000024 | NA | Trade Partner | Samples information - Soft Landscape- PV 04 compacted aggregate revised with photo | 0 | 1 | 0 | NA | APPROVED | 2026-01-29 | WF-000770 |  | 2026-02-02 |  |  |  | 2026-02-12 | KPTG-TRANSMIT-002408 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-29 | Normark-TRANSMIT-000025 | NA | Trade Partner | Samples information - Soft Landscape- PV05 Softfall mulch revised version | 0 | 1 | 0 | NA | APPROVED | 2026-01-29 | WF-000771 |  | 2026-02-02 |  |  |  | 2026-02-12 | KPTG-TRANSMIT-002402 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-29 | Normark-TRANSMIT-000026 | NA | Trade Partner | Samples information - Soft Landscape- SP02 top soil revised sample sheet | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision of the document is wrong, requested to resubmit |  | 2026-01-29 | KPTG-SADV-003551 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-29 | Normark-TRANSMIT-000027 | NA | Trade Partner | Samples information - Soft Landscape- SP02 revised sample sheet with corrected revision number | 0 | 1 | 0 | NA | APPROVED | 2026-01-29 | WF-000772 |  | 2026-02-02 |  |  |  | 2026-02-12 | KPTG-TRANSMIT-002399 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-29 | M.S.-TRANSMIT-000046 | NA | Trade Partner | Sample form for WL03 Whiteboards | 0 | 1 | 0 | NA | APPROVED | 2026-01-29 | WF-000777 |  | 2026-02-03 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-002622 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-29 | Normark-TRANSMIT-000028 | NA | Trade Partner | Samples information - Soft Landscape- PL09 Play element Timber Logs | 0 | 1 | 0 | NA | APPROVED | 2026-01-29 | WF-000773 |  | 2026-02-02 |  |  |  | 2026-02-02 | KPTG-TRANSMIT-002255 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-29 | Normark-TRANSMIT-000029 | NA | Trade Partner | Samples information - Soft Landscape- PL10- Timber Steppers | 0 | 1 | 0 | NA | APPROVED | 2026-01-29 | WF-000774 |  | 2026-02-02 |  |  |  | 2026-02-02 | KPTG-TRANSMIT-002258 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-03 | Ardon-TRANSMIT-000011 | NA | Trade Partner | Level 01 - Frame Shop Drawings | 63 | 0 | 0 | NA | APPROVED | 2025-12-03 | NA | 3412 | 2025-12-12 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-29 | Normark-TRANSMIT-000030 | NA | Trade Partner | Sample form - WA03 Recycled bricks and BE01, BE02,BE03,BE04,BE05 & SS03 - spotted Gum | 0 | 1 | 0 | NA | APPROVED | 2026-01-29 | WF-000776 |  | 2026-02-02 |  |  |  | 2026-01-30 | KPTG-TRANSMIT-002232 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-29 | Normark-TRANSMIT-000031 | NA | Trade Partner | Samples information - Soft Landscape- PL02 Basketball Hoop Tower | 0 | 1 | 0 | NA | REJECTED | [5 empty] | No attachment with TECH Data, requested to resubmit |  | 2026-01-29 | KPTG-IntCorr-004314 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-29 | Normark-TRANSMIT-000032 | NA | Trade Partner | Samples information - Soft Landscape- PL02 Basketball Hoop Tower | 0 | 1 | 0 | NA | APPROVED | 2026-01-29 | WF-000779 |  | 2026-02-03 |  |  |  | 2026-02-02 | KPTG-TRANSMIT-002247 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-29 | Normark-TRANSMIT-000033 | NA | Trade Partner | Samples information - Soft Landscape- PL01 Basketball Hoop | 0 | 1 | 0 | NA | APPROVED | 2026-01-29 | WF-000780 |  | 2026-02-03 |  |  |  | 2026-02-02 | KPTG-TRANSMIT-002244 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-29 | ARCH-TRANSMIT-000133 | NA | Consultant | MLC - SPR - Drawing Update | 4 | 0 | 0 | NA | APPROVED | 2026-01-29 |  | 417 | 2026-02-05 |  |  |  | 2026-02-10 | KPTG-SADV-003665 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-29 | M.S.-TRANSMIT-000047 | NA | Trade Partner | IFA shop drawings A1.02, A1.03, A1.04 Wall Paneling for review | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Revision of a drawing found wrong, requested to resubmit |  | 2026-01-29 | KPTG-SADV-003561 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-29 | Highbu-TRANSMIT-000113 | NA | Trade Partner | Updated IFC drawings | 4 | 0 | 0 | NA | APPROVED | [5 empty] | IFC Drawings, Transmitted to trade partners & consultants |  | 2026-01-29 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-29 | Highbu-TRANSMIT-000114 | NA | Trade Partner | Northern carpark water services IFA | 1 | 0 | 0 | NA | APPROVED | 2026-01-29 | WF-000775 | NA | 2026-02-02 |  |  | 2026-03-05 | 2026-03-05 | KPTG-TRANSMIT-002502 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-28 | D&E-TRANSMIT-000311 | NA | Trade Partner | SCRIPTS - IFC | 0 | 2 | 0 | KPTG-IntCorr-002527 | APPROVED |  | NA | NA |  |  | IFC-Distribution Only |  | 2026-02-06 | KPTG-TRANSMIT-002443 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-28 | ZIA-TRANSMIT-000070 | NA | Trade Partner | M3 Stage 1 ITP Resubmission (IFI-2) | 0 | 12 | 0 | NA | APPROVED | 2026-01-29 | WF-000901 | NA | 2026-02-05 |  |  | 2026-02-06 | 2026-02-06 | KPTG-TRANSMIT-002453 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-03 | TTW-TRANSMIT-000043 | NA | Consultant | Structural Documentation | 85 | 0 | 0 | NA | APPROVED | 2025-12-05 | WF-000052 | 124 | 2025-12-05 |  | SUBMITTED WITH REVIEW 113 DTD 3/12/2025 - 10 REVISED DRAWINGS ISSUED BY TTW AGAIN HENCE MADE 113 VOID | 2025-12-10 | 2025-12-10 | KPTG-TRANSMIT-000228 | Closed | 88 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-28 | WilsonPD-TRANSMIT-000019 | NA | Trade Partner | 150mm Water Meter Setup inc RPZD ( IW ) | 0 | 1 | 0 | NA | APPROVED | 2026-01-29 | WF-000896 | NA | 2026-02-05 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-29 | SMEPS-TRANSMIT-000253 | NA | Trade Partner | SME - SEISMIC SHOPDRAWINGS - IFC | 1 | 0 | 0 | KPTG-IntCorr-002533 | APPROVED | 2026-02-10 | WF-000914 | NA | 2026-02-17 |  | Chri Doh submitted 10 documents. SMEPS-TRANSMIT-000256 also added. | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-002629 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-29 | ZIA-TRANSMIT-000071 | NA | Trade Partner | CSMS DATAHALL A7 Leak detection Strobe Light (FOA-1) | 1 | 0 | 0 | NA | APPROVED | 2026-01-29 | NA | 1355 | 2026-02-05 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-002719 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-29 | LANSA-TRANSMIT-000014 | NA | Trade Partner | Water Services Layout - Ground Floor - Zone 1 IFA | 1 | 0 | 0 | NA | APPROVED | 2026-01-29 | NA | 1357 | 2026-02-05 |  |  | 2026-02-16 | 2026-02-16 | KPTG-TRANSMIT-002568 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-29 | Auspan-TRANSMIT-000069 | NA | Trade Partner | Update precast dowel layout for ground floor. | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Need to revise, KPTG-SADV-000847 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-29 | Auspan-TRANSMIT-000070 | NA | Trade Partner | Resubmit precast shop drawings for approval. Ground floor. | 7 | 0 | 0 | NA | APPROVED | 2026-01-29 | WF-000179 |  | 2026-02-04 |  |  |  | 2026-02-03 | KPTG-TRANSMIT-000680 | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-30 | HDRAus-TRANSMIT-000372 | NA | Consultant | M3 Stage4 Finishes Plan Ground level & Level 1 | 6 | 0 | 0 | NA | APPROVED | 2026-01-30 |  | 1921 | 2026-02-03 |  |  |  | 2026-01-30 | KPTG-TRANSMIT-012246 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-28 | KPTG-TRANSMIT-002211 | NA | Client | Audio Visual Technical Data ¦ Procurement (Fredon) | 0 | 27 | 0 | NA | APPROVED | 2026-01-28 | WF-000763 |  | 2026-01-30 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-29 | fjc-TRANSMIT-000125 | NA | Consultant | Architectural Updates - RFIs. | 25 | 0 | 0 | NA | APPROVED | 2026-01-30 | NA | 527 | 2026-02-04 |  |  | 2026-02-02 | 2026-02-02 | KPTG-SADV-002822 | Closed | 25 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-30 | RDSBIM-TRANSMIT-000017 | NA | Trade Partner | GREYSTAR FORMATION LEVEL LAYOUT | 4 | 0 | 0 | NA | APPROVED | 2026-01-30 | WF-000157 ¦ WF-000158 | 298 | 2026-02-03 |  | Review void due to updated drawings issued. |  | 2026-02-10 | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-03 | TTW-TRANSMIT-000044 | NA | Consultant | Structural Documentation - Issued for Construction | 3 | 0 | 0 | NA | APPROVED | 2025-12-03 | WF-000053 | 112 | 2025-12-05 |  |  | 2025-12-09 | 2025-12-10 | KPTG-TRANSMIT-000221 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-30 | Auspan-TRANSMIT-000060 | NA | Trade Partner | Precast shop drawings for approval. Ground floor. | 24 | 0 | 0 | NA | APPROVED | 2026-01-30 | WF-000159 | 300 | 2026-02-05 |  |  |  | 2026-02-11 | KPTG-TRANSMIT-000580 | Closed | 24 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-27 | PPX-TRANSMIT-000014 | NA | Trade Partner | FAT Record M1559 - Next DC Melbourne M3- CH4 - (Rev-01) | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For information only |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-30 | SKS Tech-TRANSMIT-000011 | NA | Trade Partner | SKS - Basket Waterfall Technical Data | 0 | 1 | 0 | NA | APPROVED | 2026-01-30 | WF-004037 |  | 2026-02-20 |  |  |  | 2026-02-13 | KPTG-TRANSMIT-012817 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-30 | INDS-TRANSMIT-000026 | NA | Trade Partner | (WF-000578) INDS-TRANSMIT-000027 - Wet Fire - Level 6 to Level 8 -#529 | 4 | 0 | 0 | NA | APPROVED | 2026-01-30 | NA | 528 | 2026-02-06 |  |  | 2026-02-10 | 2026-02-10 | KPTG-SADV-002972 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-30 | KARE-TRANSMIT-000080 | NA | Trade Partner | Lightning Protection Layouts | 8 | 0 | 0 | NA | APPROVED | 2026-01-30 | WF-000898 | 536 | 2026-02-05 |  | NA | 2026-04-20 | 2026-04-21 | DRAFT-017017 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-27 | JCBa-TRANSMIT-000206 | NA | Trade Partner | Updated POD's Acoustic Details -IFC | 4 | 0 | 0 | NA | APPROVED | 2026-01-30 | WF-000897 | 537 | 2026-02-05 |  |  | 2026-02-04 | 2026-02-04 | KPTG-TRANSMIT-002675 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-30 | INDS-TRANSMIT-000027 | NA | Trade Partner | Wet Fire - Level 6 to Level 8 | 3 | 0 | 0 | NA | APPROVED | 2026-01-30 | NA | 529 | 2026-02-06 |  |  | 2026-02-12 | 2026-02-12 | KPTG-SADV-003019 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-30 | LVPG-TRANSMIT-000008 | NA | Trade Partner | LVPG - Tech Data Submittals | 0 | 9 | 0 | NA | APPROVED | 2026-01-30 | WF-000161 ¦WF-000162 ¦ WF-000163 | NA | 2026-02-06 |  | Partially Closed. 23/2/2026 : Workflow terminated as advised by PC. | 2026-02-23 | 2026-02-05 | KPTG-TRANSMIT-000556 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-01-30 | RDSBIM-TRANSMIT-000024 | NA | Trade Partner | 671CHP ¦ LEVEL 16 - TYPICAL L16-17 - CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2026-01-30 | WF-000247 | NA |  |  | 27/2/25 as advised by KAPITOL PCACC review 238 is VOID and initiated ACC review - WF-000247 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-27 | BASESG-IntCorr-000063 | NA | Trade Partner | D&E SFN ITP Resubmission - Batch 1 | 0 | 7 | 0 | NA | APPROVED | 2026-01-30 | NA | NA |  |  | For information only-1 document pending with NEXTDC review |  | 2026-01-30 | KPTG-TRANSMIT-002381 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-03 | WAM-TRANSMIT-000016 | NA | Consultant | 80% GA Update | 46 | 0 | 0 | NA | APPROVED | 2025-12-03 | NA | 115 | 2025-12-06 |  |  | 2025-12-05 | 2025-12-05 | KPTG-TRANSMIT-000191 | Closed | 46 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-30 | VERTIV-TRANSMIT-000045 NXT-TRANSMIT-001238 | NA | Trade Partner | M3S4 FWU- Vertiv User manual submission | 1 | 0 | 0 | NA | APPROVED | 2026-01-30 | WF-004038 |  | 2026-02-13 |  |  |  | 2026-02-04 | NXT-WTRAN-001669 KPTG-TRANSMIT-012449 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-27 | BASESG-IntCorr-000063 | NA | Trade Partner | D&E SFN ITP Resubmission - Batch 1 | 0 | 12 | 0 | KPTGTRANSMIT-002381 | APPROVED | 2026-01-30 | WF-000902 | NA | 2026-02-06 |  | workflow Terminated instructed by Base Team |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-28 | D&E-TRANSMIT-000293/BASESG-IntCorr-000064 | NA | Trade Partner | M3DH7&8 - Cx Script - Mechanical-BASESG-IntCorr-000064/D&E-TRANSMIT-000293 -Technical Data Submission - SCRIPT SUBMISSIONS FOA1 | 0 | 2 | 0 | NA | APPROVED | 2026-01-30 | WF-000904 | NA | 2026-02-06 |  | workflow Terminated instructed by Base Team |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-30 | NXT-TRANSMIT-001239 | NA | Trade Partner | Zone C1 FH IT Busduct, FF - FG Mech Busduct – Shop Drawings - IFC-1 | 3 | 0 | 0 | NA | APPROVED | 2026-01-30 | WF-004039 |  | 2026-02-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-30 | INDS-TRANSMIT-000029 | na | Trade Partner | Dry Fire - Level 5 to Level 8 | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-02-17 | KPTG-SADV-003096 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-30 | KPTG-TRANSMIT-012207 | NA | Consultant | ADP IFCs - part 1 | 167 | 0 | 0 | NA | APPROVED | 2026-01-30 | WF-004043 WF-004052 |  | 2026-02-23 |  |  |  | 2026-02-11 | KPTG-TRANSMIT-012708 | Closed | 167 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-30 | INDS-TRANSMIT-000028 | NA | Trade Partner | Dry Fire - Level 1 to Level 4 | 4 | 0 | 0 | NA | APPROVED | 2026-01-30 | NA | 530 | 2026-02-06 |  |  |  | 2026-02-12 | KPTG-SADV-003020 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-27 | Auscool-TRANSMIT-000066 | NA | Trade Partner | Fan Tech Data For Approval. | 0 | 1 | 0 | NA | APPROVED | 2026-01-30 | WF-000579 |  | 2026-02-03 |  |  | 2026-02-05 | 2026-02-05 |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-30 | RDSBIM-TRANSMIT-000101 | NA | Trade Partner | MLCSPR ¦ RAW TYPICAL AQUATIC CENTRE ROOF PARAPET DETAILS | 1 | 0 | 0 | NA | APPROVED | 2026-02-02 |  | 420 | 2026-02-07 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-30 | Normark-TRANSMIT-000034 | NA | Trade Partner | SS03 - Shop drawing IFC | 2 | 0 | 0 | NA | REJECTED | [5 empty] | REVISION OF DRAWING IS WRONG, REQUESTED TO RESUBMIT |  | 2026-01-30 | KPTG-SADV-003578 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-03 | WAM-TRANSMIT-000017 | NA | Consultant | 80% DD Facade Update | 80 | 0 | 0 | NA | APPROVED | 2025-12-03 | NA | 118 | 2025-12-06 |  |  | 2025-12-05 | 2025-12-05 | KPTG-TRANSMIT-000201 | Closed | 80 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-30 | M.S.-TRANSMIT-000048 | NA | Trade Partner | IFA shop drawing MS-ARCH-DRW-MS-26A | 1 | 0 | 0 | NA | APPROVED | 2026-01-30 | NA | 418 | 2026-02-06 |  |  | 2026-03-11 | 2026-03-12 | KPTG-SADV-003843 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-30 | Normark-TRANSMIT-000035 | NA | Trade Partner | Amphitheatre shop drawing - Plan View - IFC | 1 | 0 | 0 | NA | APPROVED | [5 empty] | IFC DRAWING: TRANSMITTED TO TRADE PARTNERS & CONSULTANTS |  | 2026-01-30 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-30 | Highbu-TRANSMIT-000116 | NA | Trade Partner | HP-PM-SMP-050 - Stainless steel trough sample | 0 | 1 | 0 | NA | APPROVED | [5 empty] | Waiting for confirmation on reviewers |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-30 | Normark-TRANSMIT-000036 | NA | Trade Partner | SS03 - Amphitheatre seating section view - shop drawing IFC | 1 | 0 | 0 | NA | APPROVED | [5 empty] | IFC DRAWING: TRANSMITTED TRADE PARTNERS & CONSULTANTS |  | 2026-01-30 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-30 | Leegroup-TRANSMIT-000010 | NA | Trade Partner | IFC Shop drawings for M3 Stage 3 Gates & layout of fence | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number - KPTG-TRANSMIT-012228 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-30 | NXT-TRANSMIT-001237 OveArup-TRANSMIT-000156 | NA | Consultant | M3 Stage 3 SCADA Schematic Drawings for HVSB in Stage 2 & Stage 4 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | The drawings have been uploaded incorrectly - KPTG-TRANSMIT-012229 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-14 | Entire M-TRANSMIT-000032 | NA | Trade Partner | Pipework Technical Data for approval | 0 | 1 | 0 | NA | APPROVED | 2026-01-14 | WF-003790 |  | 2026-02-04 |  |  |  | 2026-01-30 | KPTG-TRANSMIT-012235 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-01-30 | B Smart-TRANSMIT-000051 | NA | Consultant | A19Series Podium Joinery IFC | 6 | 0 | 0 | NA | APPROVED | 2026-01-30 | WF-000169 | 240 | 2026-02-03 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-000403 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-01-30 | RBG-TRANSMIT-000051 |  | Consultant | Latest Structural Documentation Issued for Construction - Retention Updates | 4 | 0 | 0 | NA | APPROVED | 2026-01-30 | WF-000170 | 242 | 2026-02-03 |  | Review Void |  | 2026-02-13 | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-30 | JCBa-TRANSMIT-000053 | NA | Consultant | Capping Beam Elevation Sheet 3 - Hydraulic Update | 1 | 0 | 0 | NA | APPROVED | 2026-01-30 | WF-000166 | 302 | 2026-02-03 |  |  |  | 2026-02-03 | KPTG-TRANSMIT-000519 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-30 | LVPG-TRANSMIT-000009 | NA | Trade Partner | LVPG-HY-TECH-003 REV C | 0 | 1 | 0 | NA | APPROVED | 2026-01-30 | WF-000164 | NA | 2026-02-05 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-30 | LVPG-TRANSMIT-000010 | NA | Trade Partner | LVPG-HY-TECH-007 REV B | 0 | 1 | 0 | NA | APPROVED | 2026-01-30 | WF-000165 | NA | 2026-02-05 |  | Review void. |  | 2026-02-04 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-30 | LANSA-TRANSMIT-000086 | NA | Trade Partner | Levels 11 & 12-14 Drainage Drawings IFC | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-30 | SMEPS-TRANSMIT-000023 | NA | Trade Partner | Tech Data - Power Reels | 0 | 1 | 0 | NA | APPROVED | 2026-01-30 | WF-000034 | NA | 2026-02-06 |  |  | 2026-02-03 | 2026-02-03 | KPTG-TRANSMIT-000086 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-30 | SMEPS-TRANSMIT-000028 | NA | Trade Partner | SME Comms Tech Data Rev 2 | 0 | 5 | 0 | NA | APPROVED | 2026-01-30 | WF-000035 | NA | 2026-02-06 |  |  | 2026-02-08 | 2026-02-08 | KPTG-TRANSMIT-000092 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-30 | SMEPS-TRANSMIT-000029 | NA | Trade Partner | SME Shop Drawing Review Electrical | 2 | 0 | 0 | NA | APPROVED | 2026-01-30 | WF-000036 | NA | 2026-02-06 |  |  | 2026-02-08 | 2026-02-08 | KPTG-TRANSMIT-000095 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-30 | RDSBIM-TRANSMIT-000204 | NA | Trade Partner | ¦ LEVEL-1-C-1-046 MALE WC FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-01-30 |  | 1923 | 2026-02-03 |  | KPTG-WTRAN-007320 |  | 2026-02-03 | KPTG-TRANSMIT-012419 | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-30 | SMEPS-TRANSMIT-000159 | NA | Trade Partner | SME - IFA Drawings | 14 | 0 | 0 | NA | APPROVED |  |  | 1928 | 2026-02-03 |  | KPTG-WTRAN-007335 Reference Number KPTG-WTRAN-007335 (WF-004050) M3 - DOCUMENT CONTROL REVIEW - STAGE 4- IFA - GENERAL ELECTRICAL & COMMS - CONSULTANT REVIEW-SHOP DRAWING - SMEPS-TRANSMIT-000159 SME - IFA Drawings - #1928 | 2026-05-27 | 2026-05-27 | KPTG-TRANSMIT-017913 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-30 | IVS-TRANSMIT-000325 | NA | Consultant | Roof Gantry Construction Issue (Revised as clouded) | 3 | 0 | 0 | NA | REJECTED | [5 empty] | the document M3-STR-IVS-DRG-C-0401-4051 seems different revision number on aconex and inside drawing |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-01-30 | KAPITOL-WTRAN-000656 | NA | Trade Partner | Re IFC Shop Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-01-30 |  | 277 | 2026-02-05 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-03 | D&E-TRANSMIT-000275 | NA | Trade Partner | L1 CORRIDOR AC LAYOUT (V-017) | 1 | 0 | 0 | NA | APPROVED | 2025-12-03 | NA | 1280 | 2025-12-12 |  |  | 2025-12-15 | 2025-12-15 | KPTG-TRANSMIT-002178 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-01-30 | WPD-TRANSMIT-000059 | NA | Consultant | Hydraulic Services Layouts For Review | 7 | 0 | 0 | NA | REJECTED | [5 empty] | QA REJECTED DUE TO PREVIOUS REVISION NUMBER USED AGAIN FOR LATEST |  |  | KAPITOL-TRANSMIT-001029 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-29 | D&E-TRANSMIT-000318 | NA | Trade Partner | GROUND FLOOR ZONE C DUCT & PIPE + PIPE SECTIONS SHEETS - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-01-30 | NA | 1359 | 2026-02-06 |  |  | 2026-02-10 | 2026-02-10 | KPTG-TRANSMIT-002468 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-29 | BASESG-IntCorr-000069 | NA | Trade Partner | AHF & PDU Scripts | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  | Only for distribution |  | 2026-01-30 | KPTG-TRANSMIT-002383 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-28 | D&E-TRANSMIT-000312 | NA | Trade Partner | SCRIPTS - IFC | 0 | 2 | 0 | NA | APPROVED | 2026-01-30 | WF-000906 | NA | 2026-02-06 |  |  | 2026-02-11 | 2026-02-11 | KPTG-TRANSMIT-002487 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-29 | D&E-TRANSMIT-000317 | NA | Trade Partner | SCRIPTS - FOA2 | 0 | 14 | 0 | NA | APPROVED | 2026-01-30 | WF-000907 | NA | 2026-02-06 |  | After update with comment register 3 documents will transmit, WF-000907-Terminated requested by Maria.(Please remove item from that workflow) |  |  |  | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-29 | D&E-TRANSMIT-000319 | NA | Trade Partner | SCRIPT - IFC | 0 | 1 | 0 | NA | APPROVED | 2026-01-30 | WF-000908 | NA | 2026-02-06 |  |  | 2026-02-12 | 2026-02-12 | KPTG-TRANSMIT-002530 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-28 | D&E-TRANSMIT-000313 | NA | Trade Partner | SCRIPTS - IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | No need for submission |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-29 | LANSA-TRANSMIT-000013 | NA | Trade Partner | Water Services Layout - Ground Floor - Zone 1 | 1 | 0 | 0 | KPTG-IntCorr-002756 | APPROVED |  | NA | NA |  |  | Superseded by LANSA-TRANSMIT-000014 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-30 | LANSA-TRANSMIT-000015 | NA | Trade Partner | Drainage Layout - Roof Plant - Zone 1D | 1 | 0 | 0 | KPTG-IntCorr-002575 | APPROVED | 2026-02-10 | NA | 1378 | 2026-02-17 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-002696 | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-11-27 | RBG-TRANSMIT-000036 | NA | Consultant | Drawings No longer In Use | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  | 0 | Drawing issued to update register only, no review required. |  | 2025-11-27 | NA | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-01 | Baigents-TRANSMIT-000056 | NA | Trade Partner | DH7-8 Door Penetration Steel - Shop Drawings - Issued for Fabrication | 7 | 0 | 0 | KPTG-IntCorr-002454 | APPROVED | 2025-12-01 | WF-000819 | NA | 2025-12-15 |  | Workflow terminated as advised by Kapitol. Updated drawings will be resubmitted by trade partner |  |  | NA | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-02 | D&E-TRANSMIT-000273 | NA | Trade Partner | Technical Data - M3-MEC-DEA-DST-A-0100-POINTS LIST (FC6) | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated document register. Review not required. |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-28 | D&E-TRANSMIT-000316 | NA | Trade Partner | SCRIPTS - FOA2 | 0 | 12 | 0 | NA | APPROVED | 2026-01-30 | WF-000910 | NA | 2026-02-06 |  | 5 Documents will resubmit-Hold Requested by Maria |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-30 | ZIA-TRANSMIT-000073 | NA | Trade Partner | Sample tech data of Strobe light & Cable for LC rack leak detection | 0 | 2 | 0 | KPTG-IntCorr-002577 | APPROVED | 2026-02-02 | WF-000915 | NA | 2026-02-09 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-002801 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-30 | VIA Arch-TRANSMIT-000051 | N/A | Consultant | M2 S9-11 Pricing Issue Update | 38 | 0 | 0 |  | APPROVED |  |  | NA |  |  | No need to review, updated register. |  | 2026-02-09 | NA | Closed | 38 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-28 | D&E-TRANSMIT-000352 | NA | Trade Partner | Stage 2 Cx Scripts - Issued for review | 0 | 14 | 0 | NA | APPROVED | 2026-01-30 | WF-004042 | NA | 2026-02-10 |  |  | 2026-02-03 | 2026-02-05 | KPTG-TRANSMIT-012513 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-28 | NXT-TRANSMIT-001232 | NA | Client | 110693-000218 - AS BUILT INSPECTION & TEST PLANS | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-01-28 | KPTG-TRANSMIT-012024 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-28 | SMEPS-TRANSMIT-000154 | NA | Trade Partner | STAGE 2 - Inground Site Layout (C09) | 1 | 0 | 0 | NA | APPROVED | 2026-02-05 | NA | 3775 | 2026-02-12 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014848 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-28 | HDRAus-TRANSMIT-000371 | NA | Consultant | M3_S2_Building Permit Related items - HDRAus-TRANSMIT-000333 | 36 | 0 | 0 | NA | REJECTED | [5 empty] | SW drawings, SW schedules and M3S2 documents in same transmittal. |  | 2026-01-28 | KPTG-DA-004416 | Closed | 36 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-28 | DS-TRANSMIT-000093 | NA | Trade Partner | Stage 2 - Site Fire and Water | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Documents having two different disciplines in a single transmittal. |  | 2026-01-28 | KPTG-DA-004414 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-28 | INGEN3D-TRANSMIT-000680 | NA | Trade Partner | I3D-375 Next DC M3 Stage 2 - Fuel Compound - Cast in Dowels - IFC (28-01-2026) | 5 | 0 | 0 | NA | APPROVED | 2026-01-28 | WF-004008 | NA | 2026-02-04 |  |  | 2026-08-21 | 2026-08-21 | KPTG-TRANSMIT-020838 | Closed | 5 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-28 | D&E-TRANSMIT-000351 | NA | Trade Partner | NXM3S2 - Schematics / IFA + IFC Issue | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Documents with two different statuses in a single transmittal. |  | 2026-01-28 | KPTG-DA-004413 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-02 | D&E-TRANSMIT-000270 | NA | Trade Partner | Controls - IP LIST - FOA1 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated document register, review not required as confirmed by Kapitol Commissioning team. |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-28 | D&E-TRANSMIT-000349 | NA | Trade Partner | NXM3S2 - Level 01 Mechanical Duct Layout - ZONE 3 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-01-29 | NA | 3737 | 2026-02-05 |  |  | 2026-02-18 | 2026-02-19 | KPTG-TRANSMIT-013180 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-28 | BASESG-TRANSMIT-000002 | NA | Trade Partner | M3 Stage 2 – Request for Commissioning Plan, FD & ITP | 0 | 1 | 0 | NA | APPROVED | 2026-01-28 | WF-004001 | NA | 2026-02-03 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-013293 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-30 | HDRAus-TRANSMIT-000375 | NA | Consultant | Site Wide - Architectural Documentation - No Longer in Use - PDF Files | 16 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-01-31 | KPTG-TRANSMIT-012261 | Closed | 16 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-28 | NXT-TRANSMIT-001228 | NA | Client | 110693-000217 ITP'S & ITC'S | 0 | 4 | 0 | NA | APPROVED |  | NA | NA |  |  | As Built |  | 2026-01-28 | KPTG-TRANSMIT-011966 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-27 | Altaire-TRANSMIT-000065 | NA | Trade Partner | Dry Fire L2/L3 Script Submission M3 Stage 2 For Approval | 0 | 5 | 0 | NA | APPROVED | 2026-01-27 | WF-003986 | NA | 2026-03-05 |  |  | 2026-02-03 | 2026-02-05 | KPTG-TRANSMIT-012522 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-30 | HDRAus-TRANSMIT-000377 | NA | Consultant | Stage 2 - Architectural Documentation - ACC Comments | 35 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 3988 | 2026-03-20 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-014988 | Closed | 35 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-27 | Altaire-TRANSMIT-000064 | NA | Trade Partner | Dry Fire L2/L3 Script Submission M3 Stage 2 For Approval | 0 | 3 | 0 | NA | APPROVED |  | WF-003985 | NA | 2026-02-05 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-21 | Diadem-TRANSMIT-000003 | NA | Consultant | Stage 2 Signage Update | 65 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-01-30 | KPTG-DA-004483 | Closed | 65 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-21 | Diadem-TRANSMIT-000003 | NA | Consultant | Stage 2 Signage Update | 65 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-01-30 | KPTG-DA-004483 | Closed | 65 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-21 | Diadem-TRANSMIT-000003 | NA | Consultant | Stage 2 Signage Update | 65 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-01-30 | KPTG-DA-004483 | Closed | 65 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-03 | VAE-Grp-TRANSMIT-000078 | NA | Trade Partner | MECHANICAL - TECH SUB & SCHED ¦ L4 & L5 FANS DAY 1 | 0 | 2 | 0 | KPTG-IntCorr-000742 | APPROVED | 2025-12-04 | WF-000602 |  | 2025-12-10 |  |  | 2025-12-12 | 2025-12-12 | KPTG-WTRAN-001223 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-23 | BASESG-IntCorr-000026 | NA | Trade Partner | Commissionable System List Review - M3 Stage 2 | 0 | 1 | 0 | NA | APPROVED | 2026-01-27 | WF-003981 | NA | 2026-01-05 |  |  |  | 2026-02-12 | KPTG-TRANSMIT-013008 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-30 | RDSBIM-TRANSMIT-000205 | NA | Trade Partner | NXM3S2 ¦ GROUND LEVEL REFLECTED CEILING PLAN- KEY PLAN AND LAYOUT | 3 | 0 | 0 | NA | APPROVED | 2026-01-30 | WF-004047 | 3749 | 2026-02-06 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-013766 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-27 | PARR-TRANSMIT-000110 | NA | Trade Partner | P2649 - KPG NDC M3 - Stage 2 - Fuel - CX L2, L3, L4 and Commissioning Plan | 0 | 19 | 0 | NA | REJECTED | [5 empty] | Locked in workflow |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-27 | PARR-TRANSMIT-000109 | NA | Trade Partner | P2649 - KPG NDC M3 - Stage 2 - Fuel - BFS BUILDERS WORKS RISER WALLS L1 -IFC | 1 | 0 | 0 | NA | APPROVED | 2026-01-27 | NA | 3719 | 2026-02-03 |  |  | 2026-02-23 | 2026-02-24 | KPTG-TRANSMIT-013462 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-30 | ASV-TRANSMIT-000130 | NA | Trade Partner | Hydraulic Sample - Emergency Eyewash Station | 0 | 1 | 0 | NA | APPROVED | 2026-01-30 | WF-004048 | NA | 2026-02-17 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-013108 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-27 | Altaire-TRANSMIT-000063 | NA | Trade Partner | Dry Fire L2/L3 Script Submission M3 Stage 2 For Approval | 0 | 8 | 0 | NA | REJECTED | [5 empty] | Documents with different status in the same transmittals |  | 2026-01-27 | KPTG-DA-004369 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-27 | HDRAus-TRANSMIT-000365 | NA | Consultant | Stage 2 - Architectural Documentation - General Updates | 31 | 0 | 0 | NA | REJECTED | [5 empty] | Multiple issues |  | 2026-01-27 | KPTG-DA-004377 | Closed | 31 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-27 | Tradetec-TRANSMIT-000338 | NA | Trade Partner | Tech Data Submission - Soilworx Bedding Sand | 0 | 1 | 0 | NA | APPROVED | 2026-01-27 | WF-003980 | NA | 2026-02-03 |  |  | 2026-02-17 | 2026-02-17 | KPTG-TRANSMIT-013005 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-30 | Stowe-A-TRANSMIT-000466 | NA | Trade Partner | STOWE - CONTAINMENT DRAWINGS - FOR APPROVAL - 30.01.2026 | 4 | 0 | 0 | NA | APPROVED | 2026-01-30 | WF-004046 | 3746 | 2026-02-06 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-03 | Jordan-TRANSMIT-000107 | NA | Trade Partner | Level 04 - Precast Penetrations | 1 | 0 | 0 | NA | APPROVED | 2025-12-03 | NA | 685 | 2025-12-08 |  |  | 2026-01-15 | 2026-01-15 | KPTG-TRANSMIT-002424 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-30 | Stowe-A-TRANSMIT-000465 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - DATA HALL SUBMAIN RETICULATION - 30.01.2026 | 4 | 0 | 0 | NA | APPROVED | 2026-01-30 | WF-004045 | 3744 | 2026-02-06 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-013724 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-30 | Stowe-A-TRANSMIT-000464 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - 30.01.2026 - SCHEMATICS | 22 | 0 | 0 | NA | APPROVED | 2026-01-30 | NA | 3742 | 2026-01-04 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-013610 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-15 | KPTG-TRANSMIT-011465 | NA | Trade Partner | New Workflow Waterproofing site wide | 0 | 7 | 0 | NA | APPROVED | 2026-01-15 | WF-003829 | NA | 2026-01-23 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-30 | HDRAus-TRANSMIT-000373 | NA | Consultant | Drawings no longer in use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-01-31 | KPTG-TRANSMIT-012264 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-15 | Stowe-A-TRANSMIT-000438 | NA | Trade Partner | Stowe - Tech Data Submission - Temp Generator Connection Panel | 0 | 1 | 0 | NA | APPROVED | 2026-01-15 | WF-003820 | NA | 2026-02-03 |  |  | 2026-01-28 | 2026-01-29 | KPTG-TRANSMIT-012106 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-15 | ACG-TRANSMIT-000040 | NA | Trade Partner | M3 - S2 ACG Document Tidy | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | NLIU |  | 2026-01-15 | KPTG-TRANSMIT-011471 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-15 | Stowe-A-TRANSMIT-000437 | NA | Trade Partner | Stowe - Tech Data Submission - X1 External Light Pole Rev D | 0 | 1 | 0 | NA | APPROVED | 2026-01-16 | WF-003839 | NA | 2026-02-05 |  |  | 2026-01-30 | 2026-02-02 | KPTG-TRANSMIT-012323 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-30 | D&E-TRANSMIT-000360 | NA | Trade Partner | Rooftop Mech Drawing IFA | 1 | 0 | 0 | NA | APPROVED | 2026-01-30 | NA | 3739 | 2026-02-04 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-013454 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-15 | RDSBIM-TRANSMIT-000191 | NA | Trade Partner | NXDCM3S2 ¦ LOWER GROUND REFLECTED CEILING PLAN KEY PLAN | 3 | 0 | 0 | NA | APPROVED | 2026-01-15 | NA | 3663 | 2026-01-26 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-15 | KPTG-TRANSMIT-011450 | NA | Trade Partner | M3 S2 - PMJ Sample Submission | 0 | 4 | 0 | NA | APPROVED | 2026-01-15 | WF-003828 | NA | 2026-01-04 |  | Terminated as directed by William Duffield to uploaded updated document. |  | 2026-03-31 | KPTG-IntCorr-011402 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-11-28 | ZIA-TRANSMIT-000063 | NA | Trade Partner | CSMS ITP Level 3 Cx Document - Issued for Construction | 0 | 3 | 0 | NA | APPROVED | 2026-01-21 | WF-000833 | NA | 2026-01-28 |  |  | 2026-01-21 | 2026-01-22 | KPTG-TRANSMIT-002324 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-30 | Civilex-TRANSMIT-000183 | NA | Consultant | Southern Retaining Wall Updated Drawings Rev H | 2 | 0 | 0 | NA | APPROVED | 2026-01-30 | WF-004049 | NA | 2026-02-02 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-013642 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-15 | ACG-TRANSMIT-000039 | NA | Trade Partner | M3 - S2 Samples IFA revision | 0 | 6 | 0 | NA | APPROVED | 2026-01-15 | WF-003821 | NA | 2026-01-27 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-014433 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-13 | Altaire-TRANSMIT-000051 | NA | Trade Partner | Dry Fire Samples For Construction | 0 | 2 | 0 | NA | APPROVED |  | WF-003240 | NA |  |  |  |  | 2026-01-13 | KPTG-TRANSMIT-011392 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-11-18 | CRSol-TRANSMIT-000056 | NA | Trade Partner | Rejected - Technical Data - CRS | 0 | 2 | 0 | NA | APPROVED | 2025-11-18 | WF-003329 | NA | 2026-01-19 |  |  | 2026-01-31 | 2026-01-31 | KPTG-TRANSMIT-012258 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-13 | Stowe-A-TRANSMIT-000424 | NA | Trade Partner | Stowe - Tech Data Submission - Earthing Rebar Clamp | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-01-14 | KPTG-DA-004134 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-13 | ACG-TRANSMIT-000037 | NA | Consultant | M3 - S2 Samples IFC revision | 0 | 36 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-01-13 | KPTG-TRANSMIT-011398 | Closed | 36 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-11-14 | KPTG-TRANSMIT-009883 | NA | Trade Partner | Stage 2 darwinngs | 0 | 2 | 0 | NA | APPROVED | 2025-11-17 | WF-003311 | NA | 2026-01-13 |  |  | 2026-01-31 | 2026-01-31 | KPTG-TRANSMIT-012260 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-10-20 | ECBS-TRANSMIT-000019 | NA | Trade Partner | Technical data sheet revision B | 0 | 6 | 0 | NA | APPROVED | 2026-01-20 | WF-003032 | NA | 2025-11-05 |  |  |  | 2026-01-31 | KPTG-TRANSMIT-012256 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-11-17 | ECBS-TRANSMIT-000021 | NA | Trade Partner | Revise material for Review (Stud and Top Hat) | 0 | 2 | 0 | NA | APPROVED | 2026-01-17 | WF-003325 | NA | 2025-12-02 |  |  | 2026-01-31 | 2026-01-31 | KPTG-TRANSMIT-012254 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-13 | Tradetec-TRANSMIT-000320 | NA | Trade Partner | Stage 2 - IFC Shop Drawings - LVP20, LVP22, LVP23, LVP24 | 4 | 0 | 0 | NA | APPROVED | 2026-01-13 | WF-003761 | 3636 | 2026-01-20 |  |  |  | 2026-01-14 | KPTG-TRANSMIT-011439 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-03 | VAE-Grp-TRANSMIT-000077 | NA | Trade Partner | MECHANICAL - TECH SUB & SCHED GRILLES & DIFFUSERS DAY 1 | 0 | 2 | 0 | KPTG-IntCorr-000743 | APPROVED |  | N/A | N/A |  |  | FC Docs hence Register Updated |  | 2026-02-22 | KPTG-TRANSMIT-002896 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-10-16 | INGEN3D-TRANSMIT-000652 | NA | Trade Partner | I3D-375 Next DC M3 Stage 2 - Fuel Compound - Precast Panels - IFC (16-10-2025) | 41 | 0 | 0 | NA | APPROVED | 2025-10-17 | WF-003014 | NA | 2025-11-03 |  |  | 2026-01-29 | 2026-01-30 | KPTG-TRANSMIT-012250 | Closed | 41 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-13 | Tradetec-TRANSMIT-000319 | NA | Trade Partner | GIS Building South - IFA Drawings | 2 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-01-13 | KPTG-DA-004109 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-13 | Stowe-A-TRANSMIT-000425 | NA | Trade Partner | Stowe - Commissioning Implementation Plan | 0 | 2 | 0 | NA | REJECTED | [7 empty] | 2026-01-13 | KPTG-DA-004108 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-14 | Stowe-A-TRANSMIT-000428 | NA | Trade Partner | STOWE - POWER LAYOUT - LOWER ROOF - B1 - 14.01.2026 | 1 | 0 | 0 | NA | APPROVED | 2026-01-14 | NA | 3646 | 2026-01-29 |  |  | 2026-01-30 | 2026-01-30 | KPTG-TRANSMIT-012195 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-13 | RDSBIM-TRANSMIT-000185 | NA | Trade Partner | NXM3S2 ¦ LEVEL 01 B-1-012 ACC WC-FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED |  | WF-003765 | 3638 | 2026-01-23 |  |  | 2026-02-11 | 2026-02-11 | KPTG-TRANSMIT-013024 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-14 | RDSBIM-TRANSMIT-000186 | NA | Trade Partner | NXM3S2 ¦ LEVEL 01 B-1-043 ACC WC-FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-003767 | 3640 | 2026-01-16 |  |  | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-013859 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-14 | Stowe-A-TRANSMIT-000432 | NA | Trade Partner | STOWE - TECH DATA SUBMISSION - SCADA FIBRE - REV B - 14.01.2026 | 0 | 1 | 0 | NA | APPROVED | 2026-01-14 | WF-003774 | NA | 2026-01-24 |  |  | 2026-01-29 | 2026-01-29 | KPTG-TRANSMIT-012185 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-14 | RDSBIM-TRANSMIT-000187 | NA | Trade Partner | NXM3S2 ¦ LEVEL 01 B-1-089 UNISEX WC-FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-003768 | 3642 | 2026-01-23 |  |  | 2026-02-11 | 2026-02-17 | KPTG-TRANSMIT-013027 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-14 | RDSBIM-TRANSMIT-000188 | NA | Trade Partner | NXM3S2 ¦ LEVEL 01-B-1-048 CLEANERS-FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-003769 | 3644 | 2026-01-23 |  |  | 2026-02-17 | 2026-02-20 | KPTG-TRANSMIT-013262 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-14 | Stowe-A-TRANSMIT-000426 | NA | Trade Partner | Re: Stowe - Tech Data Submission - Earthing Rebar Clamp | 0 | 1 | 0 | NA | REJECTED | [8 empty] | KPTG-DA-004133 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-03 | BASESG-IntCorr-000030 | NA | Trade Partner | Comment Register submission - D&E | 0 | 1 | 0 | NA | APPROVED | 2025-12-03 | WF-000834 | NA | 2025-12-12 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-14 | Stowe-A-TRANSMIT-000431 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - LIGHTING SECTION & DETAILS - 14.01.2026 | 1 | 0 | 0 | NA | APPROVED | 2026-01-14 | NA | 3652 | 2026-01-29 |  |  | 2026-01-28 | 2026-01-29 | KPTG-TRANSMIT-012162 | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-14 | Stowe-A-TRANSMIT-000426 | NA | Trade Partner | Re: Stowe - Tech Data Submission - Earthing Rebar Clamp | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-01-14 | KPTG-DA-004133 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-14 | Stowe-A-TRANSMIT-000427 | NA | Trade Partner | Stowe - Commissioning Implementation Plan REV B | 0 | 1 | 0 | NA | APPROVED | 2026-01-27 | WF-003786 | NA | 2026-01-28 |  |  | 2026-02-12 | 2026-02-12 | KPTG-TRANSMIT-012777 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-14 | Stowe-A-TRANSMIT-000429 | NA | Trade Partner | STOWE - LIGHTING CONTROL SINGLE LINE DIAGRAM - 14.01.2026 | 1 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-003793 | 3648 | 2026-01-19 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-14 | Stowe-A-TRANSMIT-000430 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - POWER LAYOUT - GROUND FLOOR - B1 - 14.01.2026 | 1 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-003799 | 3650 | 2026-01-20 |  |  | 2026-01-20 | 2026-01-20 | KPTG-TRANSMIT-011634 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-14 | ASV-TRANSMIT-000127 | NA | Trade Partner | Revised - Hydraulic Samples - FF&E | 0 | 8 | 0 | NA | REJECTED | [7 empty] | 2026-01-14 | KPTG-DA-004129 | Closed | 8 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-14 | ACG-TRANSMIT-000038 | NA | Trade Partner | M3 - S2 Samples IFA revision | 0 | 6 | 0 | NA | REJECTED | [7 empty] | 2026-01-14 | KPTG-DA-004141 | Closed | 6 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-10-16 | INGEN3D-TRANSMIT-000653 | NA | Trade Partner | INGEN3D-TRANSMIT-000653 | 4 | 0 | 0 | NA | APPROVED | 2025-10-17 | WF-003009 | NA | 2025-11-02 |  |  | 2026-01-28 | 2026-01-28 | KPTG-TRANSMIT-012026 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-14 | Tradetec-TRANSMIT-000323 | NA | Trade Partner | Stage 2 - IFA Drawing - CP17 | 1 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-003802 | 3657 | 2026-01-30 |  |  | 2026-02-03 | 2026-02-04 | KPTG-TRANSMIT-012484 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-14 | RDSBIM-TRANSMIT-000189 | NA | Trade Partner | NXM3S2 ¦ LEVEL 01 B-1-024 MALE WC-FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | REJECTED | [8 empty] | KPTG-DA-004142 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-14 | Stowe-A-TRANSMIT-000433 | NA | Trade Partner | Stowe - Cx Level 2 Script IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-01-14 | KPTG-TRANSMIT-011435 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-11-18 | BASESG-IntCorr-000009 | NA | Trade Partner | M3 Stage 2 – Request for FD, L2/L3 Scripts & ITP | 0 | 1 | 0 | NA | APPROVED | 2025-12-01 | WF-003457 | NA | 2025-12-16 |  |  | 2026-01-28 | 2026-01-28 | KPTG-TRANSMIT-011956 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-14 | Stowe-A-TRANSMIT-000434 | NA | Trade Partner | STOWE - TECH DATA SUBMISSION - EARTHING REBAR CLAMP - REV B | 0 | 1 | 0 | NA | APPROVED | 2026-01-14 | WF-003783 | NA |  |  |  |  | 2026-01-23 | KPTG-TRANSMIT-011830 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-22 | ARCST-TRANSMIT - 000166 | NA | Trade Partner | Stage 2 - Lower Ground Additional Stairs - Issued for Review | 77 | 0 | 0 | NA | APPROVED | 2025-12-22 | WF-003688 | NA | 2026-01-06 |  |  | 2026-01-27 | 2026-01-27 | KPTG-TRANSMIT-011950 | Closed | 77 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-14 | Stowe-A-TRANSMIT-000435 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - DB SCHEMATIC - 14.01.2026 | 1 | 0 | 0 | NA | APPROVED | 2026-01-14 | NA | 3690 | 2026-01-23 |  |  | 2026-02-26 | 2026-02-27 | KPTG-TRANSMIT-013655 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-14 | RDSBIM-TRANSMIT-000190 | NA | Trade Partner | NXM3S2 ¦ LEVEL 01-B-1-016 CLEANERS-FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-01-15 | WF-003807 | 3659 | 2026-01-17 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-013790 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-12 | Ardon-TRANSMIT-000014 | NA | Trade Partner | Door Locks Samples | 0 | 3 | 0 | NA | REJECTED | [8 empty] | KPTG-TRANSMIT-011341 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-15 | Stowe-A-TRANSMIT-000436 | NA | Trade Partner | Stowe - Tech Data Submission - NHF 100A Isolator | 0 | 1 | 0 | NA | APPROVED | 2026-01-29 | WF-003817 | NA |  |  |  | 2026-01-29 | 2026-02-02 | KPTG-TRANSMIT-012330 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-15 | Ardon-TRANSMIT-000016 | NA | Trade Partner | Lock Bolt Sample | 0 | 1 | 0 | NA | APPROVED | 2026-01-16 | WF-003808 | NA | [6 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-10-09 | RDSBIM-TRANSMIT-000139 | NA | Trade Partner | NXM3S1 ¦ LEVEL 1 - HS1 OFFICE RCP LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-002953 | 3011 | 2026-01-20 |  |  | 2026-01-20 | 2026-01-20 | KPTG-TRANSMIT-011662 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-03 | PFP PL-TRANSMIT-000030 | NA | Trade Partner | Fire Protection Layout - Roof Level - Stage 1&2 Extinguisher Layout FOA-1 | 1 | 0 | 0 | NA | APPROVED | 2025-12-03 |  | 82 | 2025-12-10 |  |  |  | 2025-12-10 | KPTG-TRANSMIT-000735 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-11-13 | D&E-TRANSMIT-000263 | NA | Trade Partner | NXM3S2 - GROUND FLOOR & LEVEL 01 - Mech Layouts B1 & B2 Sheets - Issued For Construction | 4 | 0 | 0 | NA | APPROVED | 2025-11-13 | WF-003292 | 3231 | 2025-11-20 |  |  |  | 2026-01-20 | KPTG-TRANSMIT-011674 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-10 | ADP-TRANSMIT-000145 | NA | Consultant | S2 ¦ ADP MEL4561 - Updated Elec Schematic | 1 | 0 | 0 | NA | APPROVED | 2025-12-10 | NA | 3482 | 2026-01-27 |  |  | 2026-01-12 | 2026-01-12 | KPTG-TRANSMIT-011335 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-10-06 | RDSBIM-TRANSMIT-000137 | NA | Trade Partner | NXM3S1 LEVEL 1 - HS1 OFFICE PARTITION WALL KEYPLAN AND ELEVATIONS | 2 | 0 | 0 | NA | APPROVED | 2025-10-14 | WF-002949 | 3009 | 2025-10-21 |  |  | 2025-10-07 | 2026-01-07 | KPTG-TRANSMIT-008438 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-10-30 | D&E-TRANSMIT-000255 | NA | Trade Partner | ISSUED FOR APPROVAL - GROUND - MECHANICAL PIPE LAYYOUTS - ZONES 1-6 | 6 | 0 | 0 | NA | APPROVED | 2025-10-30 | WF-003154 | 3148 | 2026-01-20 |  |  |  | 2026-01-20 | KPTG-TRANSMIT-011678 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-11-28 | D&E-TRANSMIT-000284 | NA | Trade Partner | NXM3S2 - REFRIGERANT SCHEMATIC - Issued For Approval / Review | 1 | 0 | 0 | NA | APPROVED | 2025-11-28 | WF-003432 | 3359 |  |  |  |  | 2026-01-22 | KPTG-TRANSMIT-011786 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-02 | Auspan-TRANSMIT-000071 | NA | Trade Partner | Stage 9 Shop Drawing Priorities | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFCs , No review required. |  | 2026-02-02 |  | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-02 | Auspan-TRANSMIT-000072 | NA | Trade Partner | Update precast shop drawings for construction. | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFCs, No review required. |  | 2026-02-02 |  | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-02 | Auspan-TRANSMIT-000073 | NA | Trade Partner | Precast shop drawings for construction. Stage 9 ground floor. | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Drawings, No review required. |  | 2026-02-02 |  | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-02 | Auspan-TRANSMIT-000074 | NA | Trade Partner | Precast shop drawings for construction. Stage 9 ground floor. | 24 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFCs No review required |  | 2026-02-02 |  | Closed | 24 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-23 | SKS Tech-TRANSMIT-000140 | NA | Trade Partner | LEVEL 4 & 5 IFC LAYOUTS | 1 | 0 | 0 | NA | APPROVED | 2026-01-23 | NA | 880 | 2026-01-28 |  |  | 2026-01-28 | 2026-01-28 | KPTG-TRANSMIT-002600 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-04 | RDSBIM-TRANSMIT-000121 | NA | Trade Partner | LINDRUM ¦ LEVEL 11 TO LEVEL 27 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 476 | 2025-12-09 |  |  | 2025-12-08 | 2025-12-08 | KPTG-SADV-002399 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-27 | PCForm-TRANSMIT-000042 | N/A | Trade Partner | Ground floor drawing pack for review | 4 | 0 | 0 | NA | APPROVED | 2026-01-27 | NA | 219 | 2026-01-30 |  |  | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-000501 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-27 | WAM-TRANSMIT-000080 | N/A | Consultant | FFE Schedule | 1 | 0 | 0 | NA | APPROVED | 2026-01-27 | WF-000118 | NA | 2026-01-30 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-000551 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-27 | SKS Tech-TRANSMIT-000142 | NA | Trade Partner | DB-GLP | 0 | 4 | 0 | NA | APPROVED |  | NA | NA |  |  | FC - Documents - Register updated and forwarded to all parties |  | 2026-02-04 | KPTG-TRANSMIT-002663 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-27 | ZIA-TRANSMIT-000012 | NA | Trade Partner | CSMS - Loading Dock & Ground Level Outstations | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - KPTG-IntCorr-000940 |  | 2026-01-27 | KPTG-IntCorr-000940 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-27 | ZIA-TRANSMIT-000011 | NA | Trade Partner | CSMS - Swith Room Outstations | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - KPTG-IntCorr-000941 |  | 2026-01-27 | KPTG-IntCorr-000941 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-27 | KETE-TRANSMIT-000032 | NA | Trade Partner | submission- steel frame package | 0 | 1 | 0 | NA | APPROVED | 2026-01-27 | WF-000754 | NA | 2026-01-30 |  |  | 2026-01-30 | 2026-01-30 | KPTG-WTRAN-001468 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-28 | TTW-TRANSMIT-000079 | N/A | Consultant | Facade Details - Orange and yellow detail updates | 13 | 0 | 0 | NA | APPROVED | 2026-01-28 | NA | 223 | 2026-01-30 |  |  | 2026-02-04 | 2026-02-04 | KPTG-TRANSMIT-000412 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-28 | OveArup-TRANSMIT-000022 | N/A | Consultant | SERVICES | 10 | 0 | 0 | QA ERROR | REJECTED | [5 empty] | KPTG-DA-000673 |  | 2026-01-28 | KPTG-DA-000673 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-28 | TTW-TRANSMIT-000078 | N/A | Consultant | Civil Stormwater DWG | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | CAD drawings- Register updated |  | 2026-01-28 | NA | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-28 | TTW-TRANSMIT-000077 | N/A | Consultant | Civil Updated Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-01-28 | NA | 221 | 2026-01-30 |  |  | 2026-01-30 | 2026-01-30 | KPTG-TRANSMIT-000353 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-11-28 | RDSBIM-TRANSMIT-000116 | NA | Trade Partner | LEVEL 09 CONCRETE PROFILE PLAN | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2025-12-01 | KPTG-TRANSMIT-002436 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-04 | RDSBIM-TRANSMIT-000120 | NA | Trade Partner | LEVEL 11 CONCRETE PROFILE PLAN | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2025-12-04 | KPTG-TRANSMIT-002462 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-28 | TTW-TRANSMIT-000080 | N/A | Consultant | BP1 Structural Documentation - Issued for Certification | 33 | 0 | 0 | NA | APPROVED | 2026-01-28 | NA | 225 | 2026-01-30 |  | Review Made void and 26 drawings re-issued with Review - 226 | 2026-01-29 | 2026-02-05 | KPTG-TRANSMIT-000434 | Closed | 26 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-28 | PARR-TRANSMIT-000029 | N/A | Trade Partner | FUL | 9 | 0 | 0 | NA | APPROVED | 2026-01-28 | NA | 882 | 2026-02-02 |  |  | 2026-02-17 | 2026-02-17 | KPTG-TRANSMIT-002857 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-28 | Hames-TRANSMIT-000103 | N/A | Consultant | UPDATED ELEVATIONS | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Re-issued with Hames Trn # 104 |  | 2026-01-28 | Hames-TRANSMIT-000104 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-28 | Hames-TRANSMIT-000104 | N/A | Consultant | Capturing certifer comments | 30 | 0 | 0 | NA | APPROVED | 2026-01-28 | NA | 894 | 2026-02-05 |  | 884 - MADE VOID TRN 104 AND 105 SUBMITTED TOGETHER REVIEW 894 2 docs error - REISSUED HAMES-TRN-106 (SO TOT DOC 30) | 2026-02-03 | 2026-02-04 | KPTG-TRANSMIT-002685 | Closed | 30 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-28 | PARR-TRANSMIT-000030 | N/A | Trade Partner | Fuel Services - LOWER GROUND SECTIONS - IFC | 5 | 0 | 0 | NA | APPROVED | 2026-01-28 | NA | 886 | 2026-02-02 |  |  | 2026-02-05 | 2026-02-05 | KPTG-TRANSMIT-002710 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-02 | ARCST-TRANSMIT-000193 | NA | Trade Partner | C1 Cooling Tower Upper Gantry Grating Shop Drawings - Issued for Approval | 72 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-004054 | NA | 2026-02-26 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015140 | Closed | 72 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-02 | RDSBIM-TRANSMIT-000206 | NA | Trade Partner | NXM3S4 ¦ LEVEL 01-C-1-020 CLEANER FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-02-02 | NA | 1932 | 2026-02-06 |  |  |  | 2026-02-03 | KPTG-TRANSMIT-012423 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-29 | TTW-TRANSMIT-000081 | N/A | Consultant | BP3 certification issue | 86 | 0 | 0 | NA | APPROVED | 2026-01-29 | NA | 230 | 2026-02-02 |  |  | 2026-02-10 | 2026-02-10 | KPTG-TRANSMIT-000425 | Closed | 86 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-29 | TTW-TRANSMIT-000082 | N/A | Consultant | BP2 issue for certification | 33 | 0 | 0 | NA | APPROVED | 2026-01-29 | NA | 228 |  |  |  | 2026-02-16 | 2026-02-16 | KPTG-TRANSMIT-000450 | Closed | 33 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-29 | TTW-TRANSMIT-000083 | N/A | Consultant | Issued for Certification BP4 | 13 | 0 | 0 | NA | APPROVED | 2026-01-29 | NA | 232 | 2026-02-02 |  |  | 2026-02-16 | 2026-02-16 | KPTG-TRANSMIT-000455 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-04 | ARCST-TRANSMIT-000143 | NA | Trade Partner | Stage 4 - C1 Switchroom Upper Gantry Grating - Issued for Approval (Rev 2) | 95 | 0 | 0 | NA | APPROVED | 2025-12-04 | WF-003489 | NA | 2025-12-25 |  |  |  | 2025-12-17 | KPTG-TRANSMIT-011043 | Closed | 95 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-29 | TTW-TRANSMIT-000084 | N/A | Consultant | Structural Documentation - Issued for Construction | 21 | 0 | 0 | NA | APPROVED | 2026-01-30 | NA | 235 | 2026-02-03 |  |  | 2026-02-12 | 2026-02-12 | KPTG-TRANSMIT-000435 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-29 | TTW-TRANSMIT-000085 | N/A | Consultant | Structural Documentation - Issued for Construction | 21 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | TTW-84 repeated hence no action - KPTG-IntCorr-000253 |  | 2026-01-29 | NA | Closed | 21 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-29 | TTW-TRANSMIT-000086 | N/A | Consultant | Structural Documentation - Issued for Construction | 2 | 0 | 0 | NA | APPROVED | 2026-01-29 | NA | 235 | 2026-02-03 |  |  | 2026-02-12 | 2026-02-12 | KPTG-TRANSMIT-000435 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-29 | PCForm-TRANSMIT-000046 | N/A | Trade Partner | STR | 12 | 0 | 0 | KPTG-IntCorr-000252 | APPROVED |  | NA | NA |  |  | Drawings issued with differnt Doc. No. ref: KPTG-IntCorr-000801 and KPTG-TRANSMIT-000264 |  | 2026-01-29 | NA | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-29 | TCL-TRANSMIT-000003 | N/A | Consultant | Landscape Issue | 11 | 0 | 0 | NA | APPROVED | 2026-01-29 | NA | 890 | 2026-02-03 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-003005 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-29 | PARR-TRANSMIT-000033 | N/A | Trade Partner | FUL | 2 | 0 | 0 | NA | APPROVED | 2026-01-29 | NA | 892 | 2026-02-05 |  |  | 2026-02-03 | 2026-02-04 | KPTG-TRANSMIT-002680 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-29 | KETE-TRANSMIT-000033 | N/A | Trade Partner | steel frame package | 23 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected : KPTG-TRANSMIT-002619 |  | 2026-01-29 | KPTG-TRANSMIT-002619 | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-29 | RDSBIM-TRANSMIT-000055 | N/A | Trade Partner | LEVEL 05 CONCRETE PROFILE KEYPLAN | 5 | 0 | 0 | NA | APPROVED | 2026-01-29 | NA | 888 | 2026-02-03 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-002908 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-29 | CRSol-TRANSMIT-000055 | N/A | Trade Partner | SEC | 1 | 0 | 0 | Emma to clarify - KPTG-IntCorr-000943 | APPROVED |  | NA | NA |  |  | Emma to clarify - KPTG-IntCorr-000943 Emma clarified - No action document already approved via Trn 51 |  | 2026-01-07 | KPTG-TRANSMIT-002367 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-29 | Jordan-TRANSMIT-000114 | N/A | Trade Partner | GROUND FLOOR - PLUMBING RETICULATION AND PLUMBING DRAINAGE | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected : KPTG-TRANSMIT-002620 RE-ISSUED AS PER HARRY'S EMAIL KPTG-TRANSMIT-002900 |  | 2026-01-29 | KPTG-TRANSMIT-002620 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-04 | RDSBIM-TRANSMIT-000121 | NA | Trade Partner | ¦ LEVEL 00 RCP KEY PLAN & LAYOUT | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2025-12-04 | KPTG-TRANSMIT-002460 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-29 | Hames-TRANSMIT-000105 | N/A | Consultant | ARC | 7 | 0 | 0 | NA | APPROVED | 2026-01-30 | NA | 894 | 2026-02-05 |  | 2 sheets already received with 104 hence 7 only in review closed out along with TRN 104 | 2026-02-03 | 2026-02-04 | KPTG-TRANSMIT-002685 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-02 | RDSBIM-TRANSMIT-000207 | NA | Trade Partner | NXM3S4 ¦ LEVEL-1-C-1-019 ACC WC (LH) FLOOR FINISHES LAYOUT AND ELEVATION | 1 | 0 | 0 | NA | APPROVED | 2026-02-02 | NA | 1934 | 2026-02-06 |  |  |  | 2026-02-03 | KPTG-TRANSMIT-012428 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-02 | NXT-TRANSMIT-001240 PenskePS-TRANSMIT-000011 | NA | Trade Partner | M3 Stage 4 Generator Alternator General Arrangement | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | The register has been updated. If any further action is required, the coordinator will inform. - KPTG-TRANSMIT-012277 |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-11-19 | RDSBIM-TRANSMIT-000019 |  | Trade Partner | MWYCCB ¦ SITE STORAGE BUILDING GF & LEVEL 01 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-01-29 |  | 106 | 2026-02-05 |  |  |  | 2026-02-02 | KPTG-TRANSMIT-000372 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-02 | ARCST-TRANSMIT-000192 | NA | Trade Partner | C1 Cooling Tower Upper Gantry Primary Steel Shop Drawings - Issued for Approval | 131 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-004057 |  | 2026-02-26 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-015943 | Closed | 126 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-02 | ARCST-TRANSMIT-000194 | NA | Trade Partner | C1 Cooling Tower Roof Framing Shop Drawings - Issued for Approval | 135 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-004059 | NA | 2026-02-26 |  | The WF has been terminate as requested by Lola | 2026-02-24 | 2026-02-24 | NA | Closed | 135 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-02 | INGEN3D-TRANSMIT-000683 | NA | Trade Partner | I3D-378 Next DC M3 Stage 4 - Level 1 (Zone 7) - MP0128 - IFC (02-02-2026) | 1 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-004061 |  | 2026-02-09 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-02 | SKS Tech-TRANSMIT-000012 | NA | Trade Partner | SKS - Earth Bar Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-02-02 | WF-004062 |  |  |  |  | 2026-02-23 |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-02 | D&E-TRANSMIT-000364 | NA | Trade Partner | NXM3S4 - Upper Roof - CHW Pipe Layout - Zones - Issued For Review | 4 | 0 | 0 | NA | APPROVED | 2026-02-02 | NA | 1941 | 2026-02-10 |  | The workflow has been terminated at Zak’s request. There is a new set of drawings coming through that will replace these |  | 2026-02-05 | The workflow has been terminated at Zak’s request. | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-02 | ZIA-TRANSMIT-000049 | NA | Trade Partner | M3S4 CSMS Ground level Zone C1 Strobe Lights (FOA-1) | 1 | 0 | 0 | NA | APPROVED | 2026-02-02 | NA | 1945 | 2026-02-10 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-04 | LTEPRCST-TRANSMIT-000140 / Rinco-TRANSMIT-000006 | NA | Trade Partner | Structural Drawings - Precast Lids & Stair + Computation Report - IFA | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no action is required - Demi |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-02 | Auspan-TRANSMIT-000061 | NA | Trade Partner | Precast shop drawings for approval. Ground floor. | 100 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-000167 | 304 | 2026-02-09 |  |  |  | 2026-02-11 | KPTG-TRANSMIT-000583 | Closed | 100 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-02 | RDSBIM-TRANSMIT-000018 | NA | Trade Partner | GREYSTAR FORMATION LEVEL LAYOUT KEYPLAN, LAYOUT AND SECTIONS | 4 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-000168 ¦WF-000169 | 306 | 2026-02-05 |  | Review closed due to updated drawings issued. |  | 2026-02-10 | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-02 | Rinco-TRANSMIT-000026 | NA | Consultant | Precast Detail sheet revision | 1 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-000170 | 308 | 2026-02-05 |  |  |  | 2026-02-12 | KPTG-TRANSMIT-000593 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-02 | RDSBIM-TRANSMIT-000025 | NA | Trade Partner | 671CHP LEVEL 18 CONCRETE PROFILE PLAN & SECTION | 3 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-000248 | NA | 2026-02-05 |  | 27/2/25 as advised by KAPITOL PC, ACC review 244 is VOID and initiated ACC review - WF-000248 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-02 | RDSBIM-TRANSMIT-000026 | NA | Trade Partner | 671CHP BASEMENT 04 BLOCKWORK PLAN AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-02-02 | ¦WF-000172 | 246 | 2026-02-05 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-000400 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-02 | RDSBIM-TRANSMIT-000027 | NA | Trade Partner | 671CHP BASEMENT 03 BLOCKWORK PLAN AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-02-02 | ¦WF-000174 | 248 | 2026-02-05 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-000401 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-02 | RDSBIM-TRANSMIT-000028 | NA | Trade Partner | 671CHP BASEMENT 02 BLOCKWORK PLAN AND ELEVATION | 1 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-000175 | 250 | 2026-02-05 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-000402 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-02 | NXT-TRANSMIT-001245 VERTIV-TRANSMIT-000044 | NA | Trade Partner | NEXTDC M3S4- HYBRID CRAC- revised GA | 1 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-004069 |  | 2026-02-13 |  |  |  | 2026-02-06 | KPTG-TRANSMIT-012549 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-02 | HDRAus-TRANSMIT-000380 | NA | Consultant | M3 Stage4 Concrete Profile Plan - Roof C1 and C3 update - revision date and description | 2 | 0 | 0 | NA | APPROVED | 2026-02-02 | NA | 1947 | 2026-02-06 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-012612 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-02 | IVS-TRANSMIT-000327 | NA | Trade Partner | Stage 4 - Cooling Tower & Chiller Room Platform Construction Issue (Revised as clouded) | 2 | 0 | 0 | NA | APPROVED | 2026-02-02 | NA | 1950 | 2026-02-06 |  |  |  | 2026-02-13 | KPTG-TRANSMIT-012813 | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-04 | Auspan-TRANSMIT-000020 | NA | Trade Partner | Update precast dowel layout for zone 1, 2 | 2 | 0 | 0 | NA | APPROVED | 2025-12-04 | WF-000078 | 150 | 2025-12-10 |  |  |  | 2025-12-09 | KPTG-TRANSMIT-000291 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-02 | D&E-TRANSMIT-000093 | SPARK-CRFI-KPG-000487 | Trade Partner | DIFFUSION | 0 | 1 | 0 | NA | APPROVED | 2026-02-02 | WF-000153 |  | 2026-02-09 |  |  |  |  | KPTG-TRANSMIT-000391 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-02 | SMEPS-TRANSMIT-000107 | SPARK-CRFI-KPG-000489 | Trade Partner | Distribution Boards DB-16(A), DB-02(A), DB-03(A) DB-04(A), DB-05(A), DB-11(B) DB-17(B) | 0 | 1 | 0 | NA | APPROVED | 2026-02-02 | WF-000154 |  | 2026-02-09 |  | Aconex WF terminated as per peter advise - To update latest |  |  |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-02 | INGEN3D-TRANSMIT-000684 | NA | Trade Partner | Re: I3D-378 Next DC M3 Stage 4 - Ground Floor Fuel Tank - CDS4-36 & MP0183 - Revised IFC (02-02-2026) | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | The IFA review of the drawings received via INGEN3D-TRANSMIT-000684 was completed this morning with a status of Rejected. However, we have now received the IFC. Awaiting response from KAP to process - KPTG-TRANSMIT-012333 Aa per Finlay- no need to proceed |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-02 | HDRAus-TRANSMIT-000378 | NA | Consultant | FC - Weekly Updates | 15 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect attribute - KPTG-TRANSMIT-012337 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-30 | ZIA-TRANSMIT-000072 | NA | Trade Partner | M3 Stage 1 Cx Scripts Updated After Review (IFC-2) | 0 | 5 | 0 | NA | APPROVED |  | NA | NA |  |  | Distribution only |  | 2026-02-02 | KPTG-TRANSMIT-002396 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-01 | RDSBIM-TRANSMIT-000155 | NA | Trade Partner | LEVEL 06 PARTITION WALL PLAN | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-28 | D&E-TRANSMIT-000316 | NA | Trade Partner | SCRIPTS - FOA2 | 0 | 6 | 0 | NA | APPROVED | 2026-02-02 | WF-000912 | NA | 2026-02-09 |  |  | 2026-02-11 | 2026-02-11 | KPTG-TRANSMIT-002490 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-02 | SMEPS-TRANSMIT-000254 | NA | Trade Partner | Functional Description IFC | 0 | 1 | 0 | NA | APPROVED | 2026-02-02 | WF-000911 | NA | 2026-02-09 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-04 | Auspan-TRANSMIT-000029 | NA | Trade Partner | Update already IFCed shop drawings due to steel model updated. 22KV building. | 28 | 0 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-02 | DRLL-TRANSMIT-000064 | NA | Trade Partner | Battery Room Modules 1 & 2 Hydraulic Services - As Built Shop Drawings | 8 | 0 | 0 | KPTG-IntCorr-002596 | APPROVED |  | NA | NA |  |  | As built drawings- DRLL-TRANSMIT-000064 superseded and Resubmitted DRLL-TRANSMIT-000065 DRLL-TRANSMIT-000064-Closed out by Originator |  | 2026-02-02 | NA | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-30 | RDSBIM-TRANSMIT-000014 | N/A | Trade Partner | LEVEL 04 CONCRETE PROFILE PLAN | 5 | 0 | 0 | NA | APPROVED | 2026-01-30 | NA | 237 | 2026-02-03 |  |  | 2026-02-18 | 2026-02-19 | KPTG-TRANSMIT-000500 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-30 | WAM-TRANSMIT-000081 | N/A | Consultant | arc | 4 | 0 | 0 | NA | APPROVED | 2026-01-30 | WF-000134 | 239 | 2026-02-03 |  |  | 2026-02-16 | 2026-02-17 | KPTG-TRANSMIT-000461 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-30 | INGEN3D-TRANSMIT-000002 | N/A | Trade Partner | str | 48 | 0 | 0 | NA | APPROVED | 2026-01-30 | WF-000129 | NA | 2026-02-03 |  |  | 2026-02-17 | 2026-02-18 | KPTG-TRANSMIT-000477 | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-30 | OveArup-TRANSMIT-000026 | N/A | Consultant | services | 1 | 0 | 0 | KPTG-IntCorr-000257 | APPROVED | 2026-02-03 | WF-000151 | NA | 2026-02-05 |  | TERMINATED - NEW ISSUED VIA OveArup-TRANSMIT-000034 | 2026-02-04 | 2026-02-04 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-02 | Tradetec-TRANSMIT-000340 | NA | Trade Partner | Stage 2 - Tech Data - Siegelseal (2) | 0 | 1 | 0 | NA | APPROVED | 2026-02-02 | WF-004053 | NA | 2026-02-12 |  |  |  | 2026-02-18 | KPTG-TRANSMIT-013094 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-11-17 | KPTG-IntCorr-006870 | NA | Trade Partner | M3 S2 Acoustic Plant Screens | 0 | 1 | 0 | NA | APPROVED | 2025-11-18 | WF-003333 | NA | 2025-11-26 |  |  | 2026-01-22 | 2026-02-02 | KPTG-TRANSMIT-012273 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-31 | RDSBIM-TRANSMIT-000146 | NA | Trade Partner | LINDRUM ¦ LEVEL 28 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-02-02 | NA | 531 | 2026-02-05 |  | KPTG-SADV-003327 - AS PER DIRECTION FROM ASHLIN,WE TERMINATE THE WORK FLOW | 2026-03-06 | 2026-03-06 | KPTG-SADV-003327 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-11-17 | KPTG-IntCorr-006866 | NA | Trade Partner | M3 S2 BeSpoke Wire Technical Data | 0 | 1 | 0 | NA | APPROVED | 2025-11-18 | WF-003334 | NA | 2025-12-02 |  |  | 2026-01-22 | 2026-02-02 | KPTG-TRANSMIT-012274 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-02 | Auspan-TRANSMIT-000043 | NA | Trade Partner | Mezzanine shop drawings issued for construction | 6 | 0 | 0 | NA | APPROVED | 2026-02-02 | NA | 532 | 2026-02-09 |  |  | 2026-02-02 | 2026-02-02 | KPTG-SADV-002837 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-04 | RDSBIM-TRANSMIT-000087 | NA | Trade Partner | MLCSPR ¦ AQUATIC CENTER LEVEL L01 RCP | 2 | 0 | 0 | NA | APPROVED | 2025-12-04 |  | 364 | 2025-12-11 |  |  | 2025-12-08 | 2025-12-08 | KPTG-SADV-003065 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-01-30 | NXES-TRANSMIT-000040 | NA | Trade Partner | Level 02 to 11 Electrical Penetration Layouts | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per the direction we have all updated these documents into document register. KPTG-IntCorr-000667 |  | 2026-01-30 | KPTG-IntCorr-000667 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-02 | NXT-TRANSMIT-001243 | NA | Client | 100222-000219 - AS BUILT ITP'S ISSUED FOR INFORMATION | 0 | 8 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-02-02 | KPTG-TRANSMIT-012322 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-02 | PCForm-TRANSMIT-000056 | NA | Trade Partner | Fwd: Lubeca Jumpform System IFC package | 26 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per the direction from Ms Ashlin we don't take any action on these drawing. KPTG-SADV-002838 |  | 2026-02-02 | KPTG-SADV-002838 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-02 | Metzone-TRANSMIT-000006 | NA | Trade Partner | Re: Catch Deck - Column Stubs at Window Locations | 75 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-000669 |  | 2026-02-03 | KPTG-TRANSMIT-001698 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-02 | DS-TRANSMIT-000095 | NA | Trade Partner | HYD SITE - DRAINAGE | 1 | 0 | 0 | NA | APPROVED | 2026-02-02 | NA | 3758 | 2026-02-11 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-02 | fjc-TRANSMIT-000126 | na | Consultant | Architecturals - Crane Penos + RFI Updates | 6 | 0 | 0 | NA | APPROVED | 2026-02-02 | NA | 533 | 2026-02-05 |  |  | 2026-02-03 | 2026-02-03 | KPTG-SADV-002852 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-02 | Stowe-A-TRANSMIT-000467 | NA | Trade Partner | Stowe - Tech Data Submission - R1 HS1 | 0 | 1 | 0 | NA | APPROVED | 2026-02-02 | WF-004065 | NA | 2026-02-13 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-02 | Stowe-A-TRANSMIT-000468 | NA | Trade Partner | Stowe - Tech Data Submission - HS1 Floor box | 0 | 1 | 0 | NA | APPROVED | 2026-02-02 | WF-004064 | NA | 2026-02-12 |  |  | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-013140 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-02 | ZIA-TRANSMIT-000048 | NA | Trade Partner | M3S2 CSMS ORMB Location (FOA-3) | 4 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-004060 | NA | 2026-02-16 |  |  |  | 2026-02-16 | KPTG-TRANSMIT-012964 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-30 | ZIA-TRANSMIT-000046 | NA | Trade Partner | L3 and Cx Plan Submission | 0 | 51 | 0 | NA | REJECTED | [5 empty] | The document number contains the title in it. |  | 2026-02-02 | KPTG-DA-004508 | Closed | 51 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-04 | RDSBIM-TRANSMIT-000088 | NA | Trade Partner | MLC ¦ AQUATIC CENTER LEVEL 02 INTERNAL FITOUT PLAN AND ELEVATION | 3 | 0 | 0 | NA | APPROVED | 2025-12-04 |  | 365 | 2025-12-11 |  |  |  | 2026-01-12 | KPTG-SADV-003243 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-27 | RDSBIM-TRANSMIT-000202 | NA | Trade Partner | NXM3S2 ¦ OSD TANK SLAB DETAIL | 1 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-004058 | NA | 2026-02-09 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-30 | HDRAus-TRANSMIT-000376 | NA | Consultant | Site Wide - Architectural Documentation | 9 | 0 | 0 | NA | APPROVED | 2026-02-02 | NA | 3756 | 2026-02-04 |  |  | 2026-02-11 | 2026-02-11 | KPTG-TRANSMIT-012691 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-02 | Stowe-A-TRANSMIT-000469 | NA | Trade Partner | Stowe - Tech Data Submission - Temporary Generator | 0 | 1 | 0 | NA | APPROVED | 2026-02-02 | WF-004072 | NA | 2026-02-12 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-02 | PARR-TRANSMIT-000113 | NA | Trade Partner | P2649 - KPG NDC M3 - Stage 2 - Fuel - Modbus Register - IFC | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-02-02 | KPTG-TRANSMIT-012339 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-02 | ZIA-TRANSMIT-000050 | NA | Trade Partner | L3 and Cx Plan Submission | 0 | 49 | 0 | NA | REJECTED | [5 empty] | Missed some documents and resubmitted in ZIA-TRANSMIT-000053 |  | 2026-02-02 | KPTG-DA-004526 | Closed | 49 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-11-10 | ARCST-TRANSMIT-000128 | NA | Trade Partner | Roof Walkway Steel Updated IFC Shop Drawings Part 2 | 200 | 0 | 0 | NA | APPROVED | 2025-12-16 | WF-003631 | NA | 2026-01-01 |  |  | 2026-01-29 | 2026-02-02 | KPTG-TRANSMIT-012378 | Closed | 200 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-01 | RDSBIM-TRANSMIT-000156 | NA | Trade Partner | LEVEL 09 PARTITION WALL KEY PLAN | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-01 | RDSBIM-TRANSMIT-000157 | NA | Trade Partner | LEVEL 07 PARTITION WALL PLAN | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-11-10 | DS-TRANSMIT-000077 | NA | Trade Partner | GROUND FLOOR - INGROUND - DRAINAGE - C2 AND c3 | 2 | 0 | 0 | NA | APPROVED | 2025-11-10 | NA | 1505 | 2026-02-19 |  |  |  | 2026-02-02 | KPTG-TRANSMIT-012309 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-02 | JCBa-TRANSMIT-000207 | NA | Consultant | Pods' Shaft Liner Wall | 6 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-000902 | 538 | 2026-02-09 |  |  | 2026-03-03 | 2026-03-03 | KPTG-DA-002453 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2025-12-04 | WEBBAUST-TRANSMIT-000061 | NA | Consultant | Webb - B18 HFF 100% DD | 6 | 0 | 0 | NA | APPROVED | 2025-12-04 |  | 247 | 2025-12-07 |  |  |  | 2025-12-05 | KAPITOL-TRANSMIT-000894 | Closed | 6 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-07-28 | INGEN3D-TRANSMIT-000532 | NA | Consultant | I3D-378 Next DC M3 Stage 4 - Ground Floor (Fuel Tanks) - Cast in Dowels - IFA Checked (28-07-2025) | 8 | 0 | 0 | NA | APPROVED |  | NA | 003193 | [5 empty] | KPTG-TRANSMIT-012332 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-31 | CLADC-TRANSMIT-000015 | NA | Trade Partner | Door shop drawings | 23 | 0 | 0 | NA | APPROVED | 2026-02-11 | NA | 436 | 2026-02-18 |  | Revision history and drawing status have not been mentioned anywhere on drawing, requested to resumbit:KPTG-SADV-003595 | 2026-03-10 | 2026-03-10 | KPTG-SADV-003831 | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-31 | RDSBIM-TRANSMIT-000102 | NA | Trade Partner | MLCSPR ¦ AQUATIC CENTER LEVEL L01 RCP | 6 | 0 | 0 | NA | APPROVED | 2026-02-02 |  | 419 | 2026-02-07 |  |  |  | 2026-02-04 | KPTG-SADV-003611 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-02 | Highbu-TRANSMIT-000117 | NA | Trade Partner | Updated drawing | 1 | 0 | 0 | NA | APPROVED | [5 empty] | IFC drawing- Transmitted to trade and consultants |  | 2026-02-02 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-02 | KPTG-TRANSMIT-002243 | NA | Trade Partner | FFW01, FFW02, FFL03 Schiavello Systems Submission | 1 | 0 | 0 | NA | REJECTED | [5 empty] | SUBMITTED DRAWING IS SET OF COMBINED SHOP DRAWING |  | 2026-02-02 | KPTG-IntCorr-004408 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-02 | MCM Tile-TRANSMIT-000009 | NA | Trade Partner | Caulked Expansion Joints | 0 | 1 | 0 | NA | APPROVED | 2026-02-02 | WF:000785 | NA | 2026-02-05 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-002479 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-02 | Normark-TRANSMIT-000037 | NA | Trade Partner | Samples information - Soft Landscape- PL01 Basketball Hoop Wall mounted- revised with photo of hoop | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision of technical data is incorrect |  | 2026-02-02 | KPTG-SADV-003594 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-02 | P & R-TRANSMIT-000079 | NA | Trade Partner | Final (WF-000538) P & R-TRANSMIT-000068-- Fire Cause and Effect Matrix | 0 | 1 | 0 | NA | APPROVED | [5 empty] | IFC document. Transmitted to Trade & consultants |  | 2026-02-02 | KPTG-TRANSMIT-002275, KPTG-TRANSMIT-002276 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-02 | SC-TRANSMIT-000041 | NA | Trade Partner | South Elevation Facade Support IFC | 11 | 0 | 0 | NA | APPROVED | [5 empty] | IFC Drawings -transmitted to trade and consultants |  | 2026-02-02 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-02 | SC-TRANSMIT-000042 | NA | Trade Partner | Secondary Steel Facade Support IFA | 9 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-000784 |  | 2026-02-05 |  |  |  | 2026-02-04 |  | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2025-12-04 | SCP_NR-TRANSMIT-000088 | NA | Consultant | PPT updated mech | 8 | 0 | 0 | NA | APPROVED | 2025-12-04 |  | 246 |  |  |  | 2025-12-07 | 2025-12-05 | 8 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-03 | Tradetec-TRANSMIT-000341 | NA | Trade Partner | IFA - Stage 4 - Pit Shop Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-02-03 | NA | 1958 | 2026-02-11 |  |  |  | 2026-02-05 | KPTG-TRANSMIT-012531 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-03 | D&E-TRANSMIT-000368 | NA | Trade Partner | IW Pumps - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-02-03 | WF-004078 |  | 2026-02-24 |  |  |  | 2026-02-06 | KPTG-TRANSMIT-012548 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-03 | NXT-TRANSMIT-001246 EAEGROUP-TRANSMIT-000071 | NA | Trade Partner | Zone C1 Loadbank, UI UJ Catcher and FF FG Bypass Busduct - Shop Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-02-03 | WF-004080 |  | 2026-02-16 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-02 | vdmcons-TRANSMIT-000126 | NA | Consultant | ME25 1004: D108 511-537 Sydney Rd Coburg - Shop Drawings - Core Lid Panels - IFF - 2026-02-02 | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-03 | NXT-TRANSMIT-001247 Sienergy-TRANSMIT-000014 | NA | Trade Partner | Fwd: Kiosk substation GA drawing S4 | 1 | 0 | 0 | NA | APPROVED |  | NA |  |  |  | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-02 | Ardon-TRANSMIT-000025 | NA | Trade Partner | Shop Drawing Sample - Generic Frames for concrete openings | 1 | 0 | 0 | NA | APPROVED | 2026-02-02 |  | WF - 000900 | 2026-02-04 |  | Awaiting PC reply | 2026-02-03 | 2026-02-03 | KPTG-WTRAN-002014 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-02 | RDSBIM-TRANSMIT-000158 | NA | Trade Partner | LEVEL14 RCP LAYOUT TOWER B | 2 | 0 | 0 | NA | APPROVED | 2026-02-03 | WF-000904 | 539 | 2026-02-10 |  |  | 2026-02-23 | 2026-02-23 |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-02 | WilsonPD-TRANSMIT-000098 | NA | Trade Partner | WPD-HY-TEC-043 | 0 | 1 | 0 | NA | APPROVED | 2026-02-03 | WF-000903 | NA | 2026-02-10 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-30 | SMEPS-TRANSMIT-000019 | NA | Trade Partner | Tech-Data Motion detectors | 0 | 1 | 0 | NA | APPROVED | 2026-02-02 | WF-000040 | NA | 2026-02-09 |  |  | 2026-02-05 | 2026-02-05 | KPTG-TRANSMIT-000090 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-11-29 | RDSBIM-TRANSMIT-000117 | NA | Trade Partner | LEVEL 00 PARTITION WALL PLAN | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2025-12-01 | KPTG-TRANSMIT-002437 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-03 | SKS Tech-TRANSMIT-000098 | NA | Trade Partner | ELECTRICAL SERVICES - LEVEL 4LAYOUTS | 3 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 687 | 2025-12-09 |  |  | 2026-01-15 | 2026-01-15 | KPTG-TRANSMIT-002412 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-03 | SMEPS-TRANSMIT-000161 | NA | Trade Partner | Light switch | 0 | 1 | 0 | NA | APPROVED | 2026-02-03 | WF-004081 |  | 2026-02-16 |  |  |  | 2026-02-04 | KPTG-TRANSMIT-012459 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-02 | SMEPS-TRANSMIT-000030 | NA | Trade Partner | SME Shop Drawing Review EPMS | 1 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-000041 | NA | 2026-02-09 |  |  | 2026-02-05 | 2026-02-05 |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-03 | SMEPS-TRANSMIT-000160 | NA | Trade Partner | 22KV - MSWB sample - REV3 | 0 | 1 | 0 | NA | APPROVED | 2026-02-03 | WF-004082 |  | 2026-02-19 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-019791 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-03 | Nilsen3-TRANSMIT-000016 | NA | Trade Partner | M3-HV-NIL-SA-S-0301-0005 BTU Battery Charger Stage 3 - REV 1 | 0 | 1 | 0 | NA | APPROVED | 2026-02-03 | WF-004083 |  | 2026-02-16 |  |  |  | 2026-02-04 | NXT-WTRAN-001665 KPTG-TRANSMIT-012456 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-03 | Highbu-TRANSMIT-000038 | NA | Trade Partner | HP - Sample012A - DCW panel tank - shop drawing for approval | 1 | 0 | 0 | NA | APPROVED | 2026-02-03 | WF-000586 | NA | 2026-02-06 |  |  |  | 2026-02-18 | KPTG-TRANSMIT-001841 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-03 | RDSBIM-TRANSMIT-000148 | NA | Trade Partner | LINDRUM ¦ GROUND AND MEZZANINE LEVEL CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per the instruction from Ms ashlin, we do not take any action on this drawing |  | 2026-02-04 | KPTG-IntCorr-000673 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-11 | Civilex-TRANSMIT-000152 | NA | Trade Partner | Shotcrete wall strip drain sample submission | 0 | 1 | 0 | NA | APPROVED | 2026-02-03 | WF-004085 | NA | 2026-02-24 |  |  | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-015373 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-03 | Leegroup-TRANSMIT-000011 | NA | Trade Partner | IFC Shop drawings for M3 Stage 3 Gates & layout of fence | 3 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-004101 |  | 2026-02-19 |  | The register has been updated. If any further action is required, the coordinator will inform. -KPTG-TRANSMIT-012405 | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-015028 | Closed | 3 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-03 | HDRAus-TRANSMIT-000381 | NA | Consultant | M3 Stage 4 - Updated drawings - Previously sent through - KPTG-TRANSMIT-012337 | 14 | 0 | 0 | NA | APPROVED | 2026-02-03 | NA | 1983 | 2026-02-07 |  |  |  | 2026-02-10 | KPTG-TRANSMIT-012635 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-03 | Auspan-TRANSMIT-000062 | NA | Trade Partner | Update precast dowel layout for basement and ground floor | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Review required; update register and transmit to all consultants and TPs. |  | 2026-02-03 | KPTG-TRANSMIT-000531 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-04 | TTW-TRANSMIT-000142 | NA | Consultant | M3 Stage 4 Building C Civil Drawings | 29 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 1614 | 2025-12-07 |  | KPTG-IntCorr-007430 -The document revision does not align with the Aconex revision. They have been requested to resubmit the transmittal. Resubmitted via TTW-TRANSMIT-000143 -4/12/2025 |  | 2025-12-08 | KPTG-TRANSMIT-010724 | Closed | 29 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-30 | SKS Tech-TRANSMIT-000143 | N/A | Trade Partner | Security/Roof DB-GLP | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Rejected - KPTG-IntCorr-000947 |  | 2026-01-30 | KPTG-IntCorr-000947 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-30 | ACG-TRANSMIT-000014 | N/A | Trade Partner | SEC | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - KPTG-IntCorr-000948 |  | 2026-01-30 | KPTG-IntCorr-000948 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-01-27 | RDSBIM-TRANSMIT-000022 | NA | Trade Partner | 671CHP ¦ LEVEL 12 - TYPICAL L12-15 - CONCRETE PROFILE KEYPLAN | 3 | 0 | 0 | NA | APPROVED | 2026-01-27 | WF-000242 | NA | 2026-01-30 |  | 27/2/25 as advised by KAPITOL PC, ACC review 225 is VOID and initiated ACC review - WF-000242 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-01-27 | B Smart-TRANSMIT-000049 | NA | Consultant | A00.000 & A11.507 IFC | 2 | 0 | 0 | NA | APPROVED | 2026-01-27 | WF-000141 | 227 | 2026-01-30 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-000404 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-01-27 | RDSBIM-TRANSMIT-000023 | NA | Trade Partner | 671CHP ¦ BASEMENT 4 CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | NA | APPROVED | 2026-01-27 | WF-000142 | 229 | 2026-01-30 |  |  |  | 2026-02-10 | KPTG-TRANSMIT-000431 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-03 | Auspan-TRANSMIT-000063 | NA | Trade Partner | Resubmit precast shop drawings for approval. Basement. | 19 | 0 | 0 | NA | APPROVED | 2026-02-03 | WF-000172 | 310 | 2026-02-10 |  |  |  | 2026-02-12 | KPTG-TRANSMIT-000595 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-01-30 | LANSA-TRANSMIT-000088 | NA | Trade Partner | Water Services Layout IFC | 20 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-30 | KETE-TRANSMIT-000034 | N/A | Trade Partner | Updated podium IFC drawings | 23 | 0 | 0 | NA | APPROVED | 2026-01-30 | NA | 896 | 2026-02-05 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-002933 | Closed | 24 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-30 | Endfire-TRANSMIT-000056 | N/A | Trade Partner | Dry Fire Basement and GF Layout IFC Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-01-30 | NA | 898 | 2026-02-02 |  |  | 2026-02-03 | 2026-02-03 | KPTG-TRANSMIT-002661 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-03 | KEECEPRO-TRANSMIT-000018 | NA | Trade Partner | Re: IFC Shop Drawings | 4 | 0 | 0 | NA | REJECTED | [5 empty] | The status is incorrect. According to Alex Glavic, the documents will be resubmitted |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-04 | ADP-TRANSMIT-000141 | NA | Consultant | ADP MEL4780 - HYD Services Specifications - (Tender Issue) | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | The register has been updated. If any further action is required, the coordinator will inform. KPTG-TRANSMIT-010592 |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-30 | Hames-TRANSMIT-000106 | N/A | Consultant | ARC | 2 | 0 | 0 | NA | APPROVED | 2026-01-30 | NA | 894 | 2026-02-05 |  | SUBMITTED ALONG WITH TRN 104 | 2026-02-03 | 2026-02-04 | KPTG-TRANSMIT-002685 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-30 | SKS Tech-TRANSMIT-000144 | N/A | Trade Partner | Security/Roof DB-GLP | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  | Register Updated |  | 2026-03-02 | KPTG-TRANSMIT-003025 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-01-30 | VAE-Grp-TRANSMIT-000120 | N/A | Trade Partner | MECHANICAL - LOWER GROUND & GROUND LAYOUTS | 3 | 0 | 0 | NA | APPROVED | 2026-01-30 | NA | 900 | 2026-02-06 |  |  | 2026-02-05 | 2026-02-05 | KPTG-TRANSMIT-002706 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-03 | INV-TRANSMIT-000039 | NA | Consultant | Revised Civil Stormwater Drawings (Tundish Connection) | 2 | 0 | 0 | NA | REJECTED | [5 empty] | The document has been uploaded incorrectly. - DRAFT-008523 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-02 | VAE-Grp-TRANSMIT-000121 | N/A | Trade Partner | MECH - MCS FUNCTIONAL DESCRIPTION | 0 | 1 | 0 | NA | APPROVED | [5 empty] | FC Register updated |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-03 | NXT-TRANSMIT-001248 | NA | Trade Partner | ADE Power Acoustic Generator Enclosure GA Submission - Revision 2 | 4 | 0 | 0 | NA | APPROVED | 2026-02-03 | WF-004090 |  | 2026-02-19 |  |  |  | 2026-02-13 | KPTG-TRANSMIT-012800 | Open | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-03 | RDSBIM-TRANSMIT-000208 | NA | Trade Partner | NXM3S4 GROUND FLOOR TO ROOF PRECAST WALL PLAN AND ELEVATION | 15 | 0 | 0 | NA | APPROVED | 2026-02-03 | NA | 1936 | 2026-02-05 |  |  |  | 2026-02-11 | KPTG-TRANSMIT-012726 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-03 | KPTG-TRANSMIT-012413 | NA | Trade Partner | M3 Stage 4 - Fire Eng Docs | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution only |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-02 | Jordan-TRANSMIT-000116 | N/A | Trade Partner | Sample Submission - 68,69,70 | 0 | 3 | 0 | NA | APPROVED | 2026-02-02 | WF-000770 |  | 2026-02-06 |  |  | 2026-02-05 | 2026-02-05 | KPTG-WTRAN-001520 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-02 | VAE-Grp-TRANSMIT-000122 | N/A | Trade Partner | MECHANICAL - L4 & L5 SCHEDULES | 0 | 2 | 0 | NA | APPROVED | [5 empty] | FC Register updated |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-04 | Entire M-TRANSMIT-000007 | NA | Trade Partner | Fan Technical Data Submission Rev 2 | 0 | 1 | 0 | NA | APPROVED | [5 empty] | The revision number is not mentioned in the document.- KPTG-IntCorr-007433 |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-02 | CEDWA-TRANSMIT-000005 | N/A | Consultant | Updated Civil Drawings | 4 | 0 | 0 | Rejected - KPTG-IntCorr-000957 | REJECTED | [5 empty] | Rejected - KPTG-IntCorr-000957 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-02 | ZIA-TRANSMIT-000013 | N/A | Trade Partner | Outstation D1.B-L4-OS-A Drawings | 10 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-000775 | 912 | 2026-02-04 |  |  |  | 2026-02-05 | KPTG-TRANSMIT-002699 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-02 | ZIA-TRANSMIT-000014 | N/A | Trade Partner | Outstation D1.B-L4-OS-B Drawings | 10 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-000776 | 914 | 2026-02-04 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-002754 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-02 | ZIA-TRANSMIT-000015 | N/A | Trade Partner | CSMS - Outstation D1.B-L4-OS-C Drawings | 10 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-000777 | 916 | 2026-02-04 |  |  |  | 2026-02-05 | KPTG-TRANSMIT-002695 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-02 | ZIA-TRANSMIT-000016 | N/A | Trade Partner | CSMS - Outstation D1.B-LD-OS-01 Drawings | 11 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-000778 | 906 | 2026-02-09 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-002762 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-02 | ZIA-TRANSMIT-000017 | N/A | Trade Partner | CSMS - Outstation D1.B-GF-OS-01 Drawings | 10 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-000779 | 908 | 2026-02-09 |  |  | 2026-02-10 | 2026-02-10 | KPTG-TRANSMIT-002775 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-02 | ZIA-TRANSMIT-000018 | N/A | Trade Partner | CSMS - Outstation D1.B-GF-OS-02 Drawings | 10 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-000780 | 910 | 2026-02-09 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-002758 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-02 | RDSBIM-TRANSMIT-000056 | N/A | Trade Partner | GROUND FLOOR RCP PLAN AND LAYOUT | 5 | 0 | 0 | NA | APPROVED | 2026-02-02 | NA | 903 | 2026-02-06 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-002983 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-02 | RDSBIM-TRANSMIT-000057 | N/A | Trade Partner | LEVEL 01 RCP KEY PLAN AND LAYOUT | 5 | 0 | 0 | NA | APPROVED | 2026-02-02 | NA | 904 | 2026-02-06 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-002941 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-03 | D&E-TRANSMIT-000094 | SPARK-CRFI-KPG-000279 | Trade Partner | MWYCCB - MECHANICAL NOTES & LEGENDS - NCC2022 - Issued For Review | 1 | 0 | 0 | NA | APPROVED | 2026-02-03 | WF-000155 | 113 | 2026-02-10 |  |  |  | 2026-02-13 | KPTG-TRANSMIT-000438 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-04 | D&E-TRANSMIT-000277 | NA | Trade Partner | MECHANICAL SERVICES - MSSB HOOD, DRIP TRAY & PIPE HEADER SPOOL DETAILS | 1 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 1285 | 2025-12-12 |  | Workflow terminated as instructed by Kapitol, will resubmit the updated drawing on another review. |  | 2025-12-11 |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-03 | D&E-TRANSMIT-000095 | SPARK-CRFI-KPG-000320 | Trade Partner | ATTENUATOR | 0 | 1 | 0 | NA | APPROVED | 2026-02-03 | WF-000156 |  | 2026-02-10 |  | WF terminated - KPTG-IntCorr-003043 |  | 2026-05-25 | KPTG-IntCorr-003043 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-03 | DRLL-TRANSMIT-000066 | NA | Trade Partner | Battery Room Modules Electrical Drawings IFC 04 | 8 | 0 | 0 | KPTG-IntCorr-002624 | APPROVED | 2026-02-04 | NA | 1362 | 2026-02-11 |  | voided-Requested by Fabian for Template change. Again started the workflow- 1410 | 2026-03-04 |  | NA | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-03 | ccair-TRANSMIT-000086 | NA | Trade Partner | AC Unit Schedule IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-08 | BVPI-TRANSMIT-000018 | NA | Trade Partner | BVPI-CxL4-ELEC-FPT -BATCH1 | 0 | 4 | 0 | NA | APPROVED | 2026-01-16 | WF-000878 | NA | 2026-01-23 |  |  | 2026-02-03 | 2026-02-03 | KPTG-TRANSMIT-002408 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-02 | WAM-TRANSMIT-000082 | N/A | Consultant | A10.112- 4B3b - FLOOR PLANS LEVEL 11 no longer in use | 1 | 0 | 0 | NA | APPROVED | [5 empty] | No longer in use - distributed |  | 2026-02-02 | KPTG-TRANSMIT-000378 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-02 | KPTG-TRANSMIT-000374 | N/A | Consultant | Hollow core review | 6 | 0 | 0 | NA | APPROVED | 2026-02-02 | NA | 241 | 2026-02-06 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-000499 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-03 | ARCST-TRANSMIT-000198 | NA | Trade Partner | Stage 2 Internal Loading Dock Stair - IFA Drawings | 7 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to DWG” from the CAD file's document number. |  |  | KPTG-DA-004566 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-02 | Str. Spec. - BRADLEY Email | N/A | Consultant | Structural specifications | 1 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-000135 | NA | 2026-02-04 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-000557 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-02 | Civil. Spec. - BRADLEY Email | N/A | Consultant | Civil specification | 1 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-000136 | NA | 2026-02-04 |  |  | 2026-03-05 | 2026-03-06 | KPTG-TRANSMIT-000650 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-04 | IVS-TRANSMIT-000290 | NA | Consultant | Stage 4- Roof Zone C2 Delay Pour update (Construction Issue revised as clouded) | 5 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 1610 | 2025-12-08 |  |  |  | 2025-12-05 | KPTG-TRANSMIT-010669 | Closed | 5 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-02 | WAM-TRANSMIT-000706 | N/A | Consultant | Prototype Package Update | 10 | 0 | 0 | Rejected - KPTG-TRANSMIT-000381 - 8 DWGS SUBMITTED | APPROVED | 2026-02-04 | NA | 251 | 2026-02-06 |  | Rejected - KPTG-TRANSMIT-000381- 8 DWGS SUBMITTED | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-000488 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-02 | WAM-TRANSMIT-000707 | N/A | Consultant | Kichen Package | 8 | 0 | 0 | Rejected as per KPTG-DA-000731 | APPROVED | 2026-02-03 | NA | 247 | 2026-02-05 |  | Red Stick Review as instructed by BM | 2026-02-16 | 2026-02-17 | KPTG-TRANSMIT-000466 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-03 | ZIA-TRANSMIT-000051 | NA | Trade Partner | L3 and Cx Plan Submission | 0 | 3 | 0 | NA | APPROVED | 2026-02-03 | WF-004093 | NA | 2026-02-12 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-03 | D&E-TRANSMIT-000370 | NA | Trade Partner | Stage 2 Cx Scripts - Issued for review | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Document numbers seem not to be as per the M3S2 standard. |  |  | KPTG-DA-004564 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-03 | PFP PL-TRANSMIT-000060 | NA | Trade Partner | Commissioning Plan | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The document number should include a unique 4-digit document number at the end. |  |  | KPTG-DA-004562 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-03 | Tradetec-TRANSMIT-000343 | NA | Trade Partner | Stormwater Pit - D5-01 | 1 | 1 | 0 | NA | APPROVED | 2026-02-03 | NA | #3769 | 2026-02-12 |  |  | 2026-02-09 | 2026-02-09 | KPTG-TRANSMIT-012585 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-03 | Altaire-TRANSMIT-000069 | NA | Trade Partner | Updated Dry Fire Drawings and SP3 Equipment List | 8 | 0 | 0 | NA | APPROVED | 2026-02-03 | NA | 3767 | 2026-02-10 |  |  | 2026-03-11 | 2026-03-12 | KPTG-TRANSMIT-014209 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-02 | PCForm-TRANSMIT-000051 | N/A | Trade Partner | Mezzanine to Level 10 - Loading Plan, Profile Plan and Reinforcement Plan | 20 | 0 | 0 | NA | APPROVED | 2026-02-02 | NA | 243 | 2026-02-06 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-000497 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-02 | PCForm-TRANSMIT-000052 | N/A | Trade Partner | Mezzanine bottom, post tensioning plan and shear reinforcement transmittal | 3 | 0 | 0 | NA | APPROVED | 2026-02-02 | NA | 245 | 2026-02-06 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-000493 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-04 | RDSBIM-TRANSMIT-000022 |  | Trade Partner | MWYCCB ¦ GROUND FLOOR CULVERT DETAILS | 1 | 0 | 0 | KPTG-IntCorr-001040 | APPROVED | 2025-12-04 | WF-000090 | 39 | 2025-12-11 |  | Terminated by Brentyn, Reason : To allow RDS to work |  | 2025-12-18 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-02 | Civilex-TRANSMIT-000024 | N/A | Trade Partner | OSD Tank Shop Drawing | 0 | 1 | 0 | NA | APPROVED | 2026-02-02 | WF-000138 | NA | 2026-02-05 |  |  | 2026-02-10 | 2026-02-10 | KPTG-TRANSMIT-000424 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-03 | PFP PL-TRANSMIT-000059 | NA | Trade Partner | Cx L2 and L3 scripts for review. | 0 | 8 | 0 | NA | REJECTED | [5 empty] | 1. The document numbers do not include the title or revision in them. 2. No two documents can have the same document number. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-02 | Civilex-TRANSMIT-000025 | N/A | Trade Partner | Pile Cage Shop Drawing | 10 | 0 | 0 | Clarification needed from Victoria - KPTG-IntCorr-000281 | APPROVED | 2026-02-03 | WF-000140 | NA | 2026-02-05 |  |  | 2026-02-12 | 2026-02-13 | KPTG-TRANSMIT-000439 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-11-19 | Stowe-A-SUBADVICE-000292 | NA | Trade Partner | M3 Stage 2 – Request for Commissioning Plan, FD, L3 Scripts & ITP | 0 | 13 | 0 | NA | APPROVED | 2025-11-25 | WF-003389 | NA | 2026-02-02 |  |  |  | 2026-02-03 | KPTG-TRANSMIT-012412 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-10-09 | Auspan-TRANSMIT-000002 | NA | Trade Partner | Resubmit precast shop drawings for retaining wall for approval due to structural drawings updated. | 84 | 0 | 0 | NA | APPROVED | 2025-10-10 | WF-000002 |  | 2025-10-15 |  |  |  | 2025-10-29 | KPTG-TRANSMIT-000030 | Closed | 84 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-03 | Stowe-A-TRANSMIT-000473 | NA | Consultant | Tech Data Submission - tEMPORARY gENERATOR | 0 | 1 | 0 | NA | APPROVED | 2026-02-03 | WF-004088 | NA | 2026-02-13 |  |  | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-013142 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-03 | Stowe-A-TRANSMIT-000472 | NA | Trade Partner | DRAWING SUBMISSION - LOAD BANK SCHEMATIC - 03.02.2026 | 1 | 0 | 0 | NA | APPROVED | 2026-02-03 | NA | 3765 | 2026-02-16 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-013596 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-03 | SMEPS-TRANSMIT-000162 | NA | Trade Partner | Lightning protection samples | 0 | 2 | 0 | NA | APPROVED | 2026-02-03 | WF-004084 | NA | 2026-02-06 |  |  | 2026-02-05 | 2026-02-09 | KPTG-TRANSMIT-012566 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-03 | D&E-TRANSMIT-000369 | NA | Trade Partner | Sidestream Filtration Schematic - Issued For Review | 1 | 0 | 0 | NA | APPROVED | 2026-02-04 | NA | 3772 | 2026-02-11 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-013444 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-03 | D&E-TRANSMIT-000367 | NA | Trade Partner | CDU Group Control Cable - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-02-03 | WF-004076 | NA | 2026-02-12 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-013107 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-04 | WilsonPD-TRANSMIT-000134 |  | Trade Partner | HYDRAULIC SERVICES - DRAINAGE LAYOUT - GROUND LEVEL ZONE A DRAWING FOR CONSTRUCTION | 1 | 0 | 0 | KPTG-IntCorr-001043 | APPROVED | 2025-12-04 | WF-000091 | 57 | 2025-12-11 |  |  |  | 2026-01-23 | KPTG-TRANSMIT-000364 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-03 | D&E-TRANSMIT-000366 | NA | Trade Partner | BMS System Architecture - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-02-03 | WF-004075 | NA | 2026-02-12 |  |  | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-013137 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-03 | Highbu-TRANSMIT-000118 | NA | Trade Partner | Updated drawings | 2 | 0 | 0 | NA | APPROVED | [5 empty] | IFC DRAWINGS-TRANSMITTED TO TRADE AND CONSULTANTS |  | 2026-02-03 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-03 | Highbu-TRANSMIT-000119 | NA | Trade Partner | IFA in ground fire service | 1 | 0 | 0 | NA | APPROVED | 2026-02-03 | WF-000790 |  | 2026-02-05 |  |  |  | 2026-02-10 | KPTG-TRANSMIT-002354 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-03 | Normark-TRANSMIT-000038 | NA | Trade Partner | Irrigation Design Preliminary Issue for review | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Attachment of this document is a combined set of shop drawing. it is not a sample, REQUESTED TO RESUBMIT |  | 2026-02-03 | KPTG-SADV-003600 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-03 | Normark-TRANSMIT-000039 | NA | Trade Partner | Samples information - Soft Landscape- E01 Steel edge (flush) | 0 | 1 | 0 | NA | APPROVED | 2026-02-03 | WF-000791 |  | 2026-02-05 |  |  |  | 2026-02-10 | KPTG-TRANSMIT-002361 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-03 | Auspan-TRANSMIT-000044 | NA | Trade Partner | Revised shop drawing M01 issued for construction | 2 | 0 | 0 | NA | APPROVED | 2026-02-03 | NA | 535 | 2026-02-06 |  |  |  | 2026-02-04 | KPTG-SADV-002872 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-03 | 4DW-TRANSMIT-000080 | NA | Consultant | Structural Drawing Issue - Walls | 3 | 0 | 0 | NA | APPROVED | 2026-02-03 | NA | 534 | 2026-02-09 |  |  | 2026-02-03 | 2026-02-03 | KPTG-SADV-002857 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-04 | WilsonPD-TRANSMIT-000132 |  | Trade Partner | Stormwater Pit 4301G-01 | 0 | 1 | 0 | KPTG-IntCorr-001041 | APPROVED | [5 empty] | Same revision recieved - WilsonPD-TRANSMIT-000140 |  | 2026-02-13 | KPTG-TRANSMIT-000439 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-13 | AdntCons-IntCorr-000008 | NA | Trade Partner | Dry fire RFI | 2 | 0 | 0 | NA | APPROVED | 2026-01-14 |  | 393 | 2026-01-21 |  |  | 2026-02-03 | 2026-02-03 | KPTG-SADV-003599 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-02 | WSP ANZ-IntCorr-000257 | NA | Consultant | M2 WSP Services Design Markups for Pricing - Hydraulics | 1 | 0 | 0 | NA | APPROVED | 2026-02-03 | NA | 235 | 2026-02-10 |  |  | 2026-02-09 | 2026-02-09 | KPTG-TRANSMIT-000747 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-03 | fjc-TRANSMIT-000128 | NA | Consultant | Architecturals _ Ground Floor + Crane Peno Updates | 13 | 0 | 0 | NA | APPROVED | 2026-02-03 | NA | 536 | 2026-02-06 |  |  |  | 2026-02-04 | KPTG-SADV-002870 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-03 | KPTG-IntCorr-004443 | NA | Trade Partner | PV11 and Surface Primer Sample and Tech Data | 0 | 2 | 0 | NA | APPROVED | 2026-02-03 | WF-000788 |  | 2026-02-06 |  |  |  | 2026-02-03 | KPTG-TRANSMIT-002282 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-02 | WSP ANZ-IntCorr-000257 | NA | Consultant | M2 WSP Services Design Markups for Pricing - Telecom | 1 | 0 | 0 | NA | APPROVED | 2026-02-03 | NA | 241 | 2026-02-10 |  |  | 2026-02-09 | 2026-02-09 | KPTG-TRANSMIT-000747 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-03 | KPTG-IntCorr-004136 | NA | Trade Partner | Tuff Turf Sample Resubmission | 0 | 1 | 0 | NA | APPROVED | 2026-02-03 | WF-000789 | NA | 2026-02-05 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-003052 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-03 | Fredon T-TRANSMIT-000014 | NA | Trade Partner | Re: Fredon Procurement Items ¦ Rejected | 0 | 3 | 0 | NA | REJECTED | [5 empty] | attached documents are technical data, the Document Number of all documents are incorrect and also appear to be duplicates |  | 2026-02-03 | KPTG-SADV-003605 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-02 | WSP ANZ-IntCorr-000257 | NA | Consultant | M2 WSP Services Design Markups for Pricing - Electrical | 1 | 0 | 0 | NA | APPROVED | 2026-02-03 | NA | 238 | 2026-02-10 |  |  | 2026-02-09 | 2026-02-09 | KPTG-TRANSMIT-000747 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-02 | WSP ANZ-IntCorr-000257 | NA | Consultant | M2 WSP Services Design Markups for Pricing - Fire | 1 | 0 | 0 | NA | APPROVED | 2026-02-03 | NA | 234 | 2026-02-10 |  |  | 2026-02-09 | 2026-02-09 | KPTG-TRANSMIT-000747 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-03 | Fredon T-TRANSMIT-000015 | NA | Trade Partner | Re: Fredon Procurement Items ¦ Rejected | 0 | 1 | 0 | NA | REJECTED | [5 empty] | SUBMITTED DOCUMENT IS DUPLICATES OF ANOTHER TEC DATA |  | 2026-02-03 | KPTG-SADV-003601 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-04 | WilsonPD-TRANSMIT-000133 |  | Trade Partner | Hot Water Plant | 0 | 1 | 0 | KPTG-IntCorr-001042 | APPROVED | [7 empty] | 2025-12-18 | KPTG-TRANSMIT-000310 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-02 | WSP ANZ-IntCorr-000257 | NA | Consultant | M2 WSP Services Design Markups for Pricing - Fuel | 1 | 0 | 0 | NA | APPROVED | 2026-02-03 | NA | 237 | 2026-02-10 |  |  | 2026-02-09 | 2026-02-09 | KPTG-TRANSMIT-000747 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-03 | Fredon T-TRANSMIT-000016 | NA | Trade Partner | Fredon Procurement Items ¦ Rejected | 0 | 1 | 0 | NA | REJECTED | [5 empty] | SUBMITTED DOCUMENTS IS DUPLICATES OF ANOTHER TECH DATA |  | 2026-02-03 | KPTG-SADV-003602 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-03 | Fredon T-TRANSMIT-000017 | NA | Trade Partner | Fredon Procurement Items ¦ Rejected | 0 | 1 | 0 | NA | REJECTED | [5 empty] | SUBMITTED DOCUMENT IS DUPLICATES OF ANOTHER |  | 2026-02-03 | KPTG-SADV-003603 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-02 | WSP ANZ-IntCorr-000258 | NA | Consultant | M2 WSP Services Design Markups for Pricing - Mechanical | 1 | 0 | 0 | NA | APPROVED | 2026-02-03 |  | 236 | 2026-02-10 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-000748 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-31 | SCG2014-TRANSMIT-000011 | NA | Consultant | Security - updated Draft for Tender after redesign | 1 | 0 | 0 | KPTG-IntCorr-000342 | APPROVED |  | NA | 455 | 2026-03-21 |  |  | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-001429 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-31 | SCG2014-TRANSMIT-000012 | NA | Consultant | Security - updated Draft for Tender after redesign | 42 | 0 | 0 | KPTG-IntCorr-000342 | APPROVED |  | NA | 456 | 2026-03-21 |  |  | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-001433 | Closed | 42 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-03 | CAP6-TRANSMIT-000004 | NA | Trade Partner | Classic Architectural Onboarding ¦ MLCSPR | 0 | 4 | 0 | NA | REJECTED | [5 empty] | Document number of tech data are incorrect, requested to resubmit |  | 2026-02-03 | KPTG-SADV-003604 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-04 | D&E-TRANSMIT-000331 KPTG-IntCorr-008856 | NA | Trade Partner | NXM3S4 - LEGEND AND GENERAL NOTES - Issued For Review | 1 | 0 | 0 | NA | APPROVED | 2026-02-04 | NA | 1965 | 2026-02-11 |  |  |  | 2026-02-05 | KPTG-TRANSMIT-012495 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-11-25 | Tradetec-TRANSMIT-000270 | NA | Trade Partner | Stage 4 - IFC - LVP39 | 1 | 0 | 0 | NA | APPROVED | 2025-11-25 | NA | 1557 - 1966 | 2026-02-11 |  | As per requested by Charlie - The workflow has been terminated. tsa issuing new drawing |  | 2026-02-03 |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-04 | NXT-TRANSMIT-001251 | NA | Trade Partner | NextDC M3 Stage4 LVSB - CSMS Var Proposal and TS | 2 | 0 | 0 | NA | APPROVED | 2026-02-03 | WF-004095 |  | 2026-02-20 |  |  |  | 2026-02-16 | KPTG-TRANSMIT-012893 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-01 | INGEN3D-TRANSMIT-000671 | NA | Trade Partner | I3D-378 Next DC M3 Stage 4 - Ground Floor (Zone 13) - PWS4-1237-1 & CPS4-439 - IFC (01-12-2025) | 2 | 0 | 0 | KPTG-TRANSMIT-010451 | REJECTED | [5 empty] | KPTG-TRANSMIT-010451 – I3D submitted the IFC without IFA approval. They have been requested to remove the drawings and resubmit the transmittal. |  | 2025-12-01 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-04 | CECPL-TRANSMIT-000009 | NA | Consultant | Collective Engineering MEPF - 100% Design Development Review | 54 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 248 | 2025-12-07 |  | The register has been updated. If any further action is required, the coordinator will inform. |  | 2025-12-08 | KAPITOL-TRANSMIT-000897 | Closed | 54 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-10-10 | INGEN3D-TRANSMIT-000657 | NA | Trade Partner | I3D-378 Next DC M3 Stage 4 - Level 1 (Zone 6) - MP0209 - Revised IFA (17-10-2025) | 1 | 0 | 0 | NA | APPROVED | 2025-10-20 | WF-003033 |  | 2026-02-05 |  |  |  | 2026-02-04 | KPTG-TRANSMIT-012440 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-10-08 | INGEN3D-TRANSMIT-000645 | NA | Trade Partner | I3D-378 Next DC M3 Stage 4 - Ground Floor (Zone 13) - Cast in Dowel - IFC (08-10-2025) | 3 | 0 | 0 | NA | APPROVED | 2025-10-08 | WF-003077 |  | 2026-02-02 |  |  |  | 2026-02-04 | KPTG-TRANSMIT-012444 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-02 | KPTG-TRANSMIT-002243 | NA | Trade Partner | FFW01, FFW02, FFL03 Schiavello Systems Submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Attachment of Document is not sample, it is a set of combined shop drawings, requested to resubmit |  | 2026-02-02 | KPTG-IntCorr-004408 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-04 | NXT-TRANSMIT-001252 EAEGROUP-TRANSMIT-000072 | NA | Trade Partner | Fwd: UMTD-USB (FF) And (FG) Interconnection Busduct - Shop Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-004099 |  | 2026-02-12 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-04 | SKS Tech-TRANSMIT-000015 SKS Tech-TRANSMIT-000016 | NA | Trade Partner | Re: DHC1 LIGHTING LAYOUT FOR REVIEW | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number - KPTG-TRANSMIT-012451 |  | 2026-02-04 | KPTG-TRANSMIT-012451 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-04 | DS-TRANSMIT-000096 | NA | Trade Partner | Stage 03 - Basement, GF and Roof - Combined drainage and Water and Roof - Penetrations | 4 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-004104 - New WF-004200. |  | 2026-02-20 |  | The WF has been terminated and reinitiated via WF-004200. |  | 2026-02-17 | KPTG-TRANSMIT-013023 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-04 | Ardon-TRANSMIT-000018 | NA | Trade Partner | Re: Stage 3 22KV - FFE Tech Data Submission | 0 | 4 | 0 | NA | REJECTED | [5 empty] | The document reference number is not aligned with S3 project. |  | 2026-02-04 | KPTG-TRANSMIT-012458 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-20 | Nilsen3-TRANSMIT-000011 | NA | Trade Partner | Re: 12.7 22kV 1 core 185mm² Sample Submission | 1 | 0 | 0 | NA | APPROVED | 2026-01-29 | WF-004011 |  | 2026-02-03 |  |  |  | 2026-02-04 | KPTG-TRANSMIT-012460 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-04 | SMEPS-TRANSMIT-000165 | NA | Trade Partner | 22KV - Light switch | 0 | 1 | 0 | NA | APPROVED | 2026-02-04 | WF-004102 |  | 2026-02-12 |  |  |  | 2026-02-05 | KPTG-TRANSMIT-012504 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-04 | Nilsen3-TRANSMIT-000017 | NA | Trade Partner | M3-HV-NIL-SA-S-0301-0007 ABB SCADA ROP - Sample | 0 | 1 | 0 | NA | APPROVED | 2026-02-04 | WF-004103 |  | 2026-02-16 |  | Terminated by Reviewers |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-04 | Entire M-TRANSMIT-000008 | NA | Trade Partner | Fan Coil Unit & Condenser Technical Data Submission | 0 | 1 | 0 | NA | APPROVED | 2025-12-04 | WF-003503 |  | 2025-12-12 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-03 | Nilsen3-TRANSMIT-000016 | NA | Trade Partner | M3-HV-NIL-SA-S-0301-0005 BTU Battery Charger Stage 3 - REV 1 | 0 | 1 | 0 | NA | APPROVED | 2026-02-04 | WF-004105 |  | 2026-02-20 |  |  |  | 2026-02-16 | KPTG-TRANSMIT-012904 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-04 | SMEPS-TRANSMIT-000164 | NA | Trade Partner | S3 I SHOP DRAWING I CONSULTANT REVIEW ¦ ELE IFC - KG, aurecon elec, arup elec and NDC | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect status |  | 2026-02-04 | KPTG-TRANSMIT-012464 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-03 | TTW-TRANSMIT-000089 | NA | Consultant | BP2 issue for certification | 33 | 0 | 0 | NA | APPROVED | [5 empty] | No action - Same as Trn # 83 |  | 2026-02-04 | KPTG-IntCorr-000291 | Closed | 33 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-03 | TTW-TRANSMIT-000088 | NA | Consultant | Issued for Certification BP4 | 13 | 0 | 0 | NA | APPROVED | [5 empty] | No action - Same as Trn # 82 |  | 2026-02-04 | KPTG-IntCorr-000290 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-03 | WAM-TRANSMIT-000708 | NA | Consultant | Arch - CSP Updates - L2-4 | 6 | 0 | 0 | NA | APPROVED | 2026-02-03 | NA | 249 | 2026-02-05 |  |  | 2026-02-17 | 2026-02-17 | KPTG-TRANSMIT-000471 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-04 | ARCST-TRANSMIT-000200 | NA | Trade Partner | C3 Cooling Tower Base Framing - Issued for Review | 28 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-004106 | NA | 2026-02-25 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015131 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-04 | Nilsen3-TRANSMIT-000019 | NA | Trade Partner | SCADA Bankbone Fibre Sample | 0 | 1 | 0 | NA | APPROVED | 2026-02-04 | WF-004109 | NA | 2026-02-20 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-013699 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-04 | Nilsen3-TRANSMIT-000014 | NA | Trade Partner | Nilsen Sample Submission | 0 | 25 | 0 | NA | REJECTED | [5 empty] | The revision number is not included in the document. |  | 2026-02-04 | KPTG-TRANSMIT-012467 | Closed | 25 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-04 | Auspan-TRANSMIT-000065 | NA | Trade Partner | Auspan-TRANSMIT-000065 Update precast dowel layout basement. Zone 1, 2 | 1 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000174 | 313 | 2026-02-13 |  |  |  | 2026-02-12 | KPTG-TRANSMIT-000594 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-03 | LANSA-TRANSMIT-000076 | NA | Trade Partner | Level 09 Penetrations IFC | 1 | 0 | 0 | KPTG-IntCorr-001338 | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2025-12-18 | KPTG-TRANSMIT-002550 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-04 | Auscool-TRANSMIT-000006 T | NA | Trade Partner | Typical apartment layouts | 1 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000173 | NA | 2026-02-11 |  | Only Aconex review. No ACC. |  | 2026-02-17 | KPTG-TRANSMIT-000627 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-04 | Ardon-TRANSMIT-000019 | NA | Trade Partner | Stage 3 - FFE Tech Data Submission | 0 | 4 | 0 | NA | APPROVED | 2026-02-04 | WF-004111 |  | 2026-02-17 |  |  |  | 2026-02-10 | The WF has ben terminated as per requested by Sam S | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-04 | KPTG-TRANSMIT-012469 ADP-TRANSMIT-000160 | NA | Consultant | Plant Replacement Report - Site Wide | 0 | 5 | 0 | NA | APPROVED | 2026-02-04 | WF-004114 |  | 2026-02-09 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-012565 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-04 | NXT-TRANSMIT-001253 | NA | Trade Partner | Submiting Technical Data IFC | 0 | 6 | 0 | NA | APPROVED | 2026-02-04 | WF-004119 |  | 2026-02-17 |  |  |  | 2026-02-12 | KPTG-TRANSMIT-012758 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-04 | KEECEPRO-TRANSMIT-000019 | NA | Trade Partner | IFC Shop Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-02-04 | NA | 280 | 2026-02-07 |  |  |  | 2026-02-06 | DRAFT-008618 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-02 | WPD-TRANSMIT-000060 | na | Trade Partner | Hydraulic Layouts | 7 | 0 | 0 | NA | APPROVED | 2026-02-04 | NA | 281 | 2026-02-07 |  |  |  | 2026-02-06 | KAPITOL-TRANSMIT-001052 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-03 | KPTG-TRANSMIT-009535 | NA | Consultant | Re: New Workflow | 11 | 0 | 0 | NA | APPROVED | 2025-11-03 | WF-003191 |  | 2026-01-29 |  |  |  | 2026-02-04 | KPTG-TRANSMIT-012463 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-04 | WPD-TRANSMIT-000061 | NA | Trade Partner | Updated Site Plan | 1 | 0 | 0 | NA | APPROVED | 2026-02-04 | NA | 282 | 2026-02-07 |  |  |  | 2026-02-06 | KAPITOL-TRANSMIT-001053 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-04 | D&E-TRANSMIT-000374 | NA | Trade Partner | Chiller Roof - Builders Works Layouts - Zone 1 & 3 - Issued For Review | 2 | 0 | 0 | NA | APPROVED | 2026-02-04 | NA | 1973 | 2026-02-12 |  | The workflow has been terminated as requested by William Kee |  | 2026-02-05 | WF Terminated -William Keely | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-04 | ARCST-TRANSMIT-000199 | NA | Trade Partner | C2 Cooling Tower Base Framing - Issued for Review | 26 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-004112 | NA | 2026-03-02 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015127 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2025-12-04 | DI-TRANSMIT-000128 | NA | Consultant | FPS - As Built Issue | 10 | 0 | 0 | NA | APPROVED | 2025-12-04 |  | 249 | 2025-12-07 |  |  |  | 2025-12-05 | KAPITOL-TRANSMIT-000893 | Closed | 10 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-04 | LANSA-TRANSMIT-000091 | NA | Trade Partner | Level 07 Drainage IFC | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-04 | LANSA-TRANSMIT-000092 | NA | Trade Partner | Level 6 Drainage IFC | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-04 | LANSA-TRANSMIT-000093 | NA | Trade Partner | Level 6 Penetrations IFC | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-04 | B Smart-TRANSMIT-000052 | NA | Consultant | 260204_Architectural Facade Doors IFC | 6 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000190 | 254 | 2026-02-09 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-000399 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-04 | KPTG-IntCorr-002627 | NA | Trade Partner | DH7&8 Signage Shop Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000917 |  | 2026-02-11 |  | WF-000917 -Terminated requested by Kim Taylor and submitted on ACC |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-04 | RDSBIM-TRANSMIT-000103 | NA | Trade Partner | MLC ¦ AQUATIC CENTER LEVEL 01 INTERNAL SCREED LAYOUT | 10 | 0 | 0 | NA | APPROVED | 2026-02-04 |  | 421 | 2026-02-11 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-04 | PROLMC-TRANSMIT-000022 | NA | Trade Partner | GRC IFC Shop drawings | 30 | 0 | 0 | NA | REJECTED | [5 empty] | Document number of Drawing are mismatched with what were transmitted and registered in Document register |  | 2026-02-04 | KPTG-SADV-003616 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2025-11-21 | RDSBIM-TRANSMIT-000191 | NA | Trade Partner | LOWER GROUND COMMON AREA WELLNESS | 8 | 0 | 0 | NA | APPROVED | 2025-11-24 | NA | 559 | 2025-12-01 |  |  | 2026-02-04 | 2026-02-04 | KPTG-TRANSMIT-002562 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-04 | Arco-TRANSMIT-000013 | NA | Trade Partner | ALUMINIUM ROLLER SHUTTERS - OH4A STORE & OH04 STORE | 5 | 0 | 0 | NA | APPROVED | [5 empty] | IFC Drawings, transmitted to Trade and consultants |  | 2026-02-04 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-04 | M.S.-TRANSMIT-000049 | NA | Trade Partner | FSG12 - Robe Hook for review | 0 | 1 | 0 | NA | APPROVED | 2026-02-04 | WF-000794 | NA | 2026-02-09 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-002495 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-04 | KARE-TRANSMIT-000082 | NA | Trade Partner | Elec Penetrations IFC | 32 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 32 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-04 | Normark-TRANSMIT-000042 | NA | Trade Partner | SS03- Amphitheatre seating, BE04- Square table, BE05- Circular Seat- Powder coat color on end plates and legs | 0 | 1 | 0 | NA | APPROVED | 2026-02-04 | WF-000795 |  | 2026-02-06 |  |  |  | 2026-02-04 | KPTG-TRANSMIT-002305 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-04 | ARCH-TRANSMIT-000136 | NA | Consultant | MLC - SPR - AQC - Wet Area Threshold Detail | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Document number of Drawing is incorrect, requested to resubmit. |  | 2026-02-04 | KPTG-SADV-003613 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-04 | PROLMC-TRANSMIT-000023 | NA | Trade Partner | GRC IFC Shop Drawings (4-2-26) | 30 | 0 | 0 | NA | REJECTED | [5 empty] | Document number of drawings are incorrect, requested to resubmit |  | 2026-02-04 | KPTG-SADV-003617 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-03 | Normark-TRANSMIT-000041 | NA | Trade Partner | Shop Drawing- Irrigation Design- System Layout- for review | 1 | 0 | 0 | NA | APPROVED | 2026-02-04 |  | 422 | 2026-02-11 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-12 | NXT-WTRAN-001633 | NA | Trade Partner | M3 Stage 4 - GF Z03 Panels & Marking Plans Next DC M3 Stage 4 ****Refer to M3-STR-I3D-DRG-C-0401-MP0005 | 4 | 0 | 0 | NA | APPROVED | 2025-12-12 | (WF-003578 |  | 2026-01-13 |  |  |  | 2026-02-02 | KPTG-TRANSMIT-012299 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-11-14 | NXES-TRANSMIT-000065 | NA | Trade Partner | Electrical Shop drawings - Aquatic Centre 1, 2 & Roof Layout | 6 | 0 | 0 | NA | APPROVED | 2025-11-15 |  | 380 | 2025-11-21 |  |  |  | 2026-02-04 | KPTG-SADV-003615 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-02 | NXT-WTRAN-001631 | NA | Trade Partner | Stage 4 - Level 1 Zone 6 Panels & Marking Plans Next DC M3 Stage 4 | 27 | 0 | 0 | NA | APPROVED | 2025-12-02 | WF-003462 |  | 2026-02-02 |  |  |  | 2026-02-02 | KPTG-TRANSMIT-012310 | Closed | 27 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-16 | KPTG-IntCorr-003968 | NA | Trade Partner | Melbourne Stainless Handrails and Balustrades Sample and Techdata | 0 | 9 | 0 | NA | APPROVED | 2026-01-16 | WF-000719 |  | 2026-01-23 |  |  |  | 2026-02-04 | KPTG-TRANSMIT-002292 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-04 | PFP PL-TRANSMIT-000061 | NA | Trade Partner | Commissioning plan, CX L2 & L3 scripts for review | 0 | 9 | 0 | NA | APPROVED | 2026-02-04 | WF-004115 | NA | 2026-02-11 |  |  | 2026-02-06 | 2026-02-06 | KPTG-TRANSMIT-012562 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-04 | B Smart-TRANSMIT-000029 | NA | Consultant | Podium Levels Draft IFC | 31 | 0 | 0 | NA | APPROVED | 2025-12-04 | WF-000074 | 138 | 2025-12-08 |  | Workflow Void as requested by Kapitol |  | 2025-12-08 | NA | Closed | 31 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-04 | D&E-TRANSMIT-000371 | NA | Trade Partner | Stage 2 Cx Scripts - Issued for review | 0 | 4 | 0 | NA | APPROVED | 2026-02-04 | WF-004117 | NA | 2026-02-13 |  |  | 2026-02-12 | 2026-02-12 | KPTG-TRANSMIT-012775 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-04 | Stowe-A-TRANSMIT-000475 | NA | Trade Partner | Stowe - Tech Data Submission - HS1 - CAPTIVE OUTLET | 0 | 1 | 0 | NA | APPROVED | 2026-02-04 | WF-004097 | NA | 2026-02-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-04 | Stowe-A-TRANSMIT-000476 | NA | Trade Partner | STOWE - TECH DATA SUBMISSION - CAT6A CABLING - BLUE JACKET - 04.02.2026 | 0 | 1 | 0 | NA | APPROVED | 2026-02-04 | WF-004098 | NA | 2026-02-17 |  |  | 2026-02-17 | 2026-02-17 | KPTG-TRANSMIT-012995 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-04 | Ardon-TRANSMIT-000020 | NA | Trade Partner | Stage 2 - FFE Tech Data Submission | 0 | 9 | 0 | NA | APPROVED | 2026-02-04 | WF-004116 | NA | 2026-02-12 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-04 | ASV-TRANSMIT-000132 | NA | Trade Partner | Hydraulic Sample - DDA Basin Mixer | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The document number is not as per the project standards. |  | 2026-02-04 | KPTG-DA-004609 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-04 | Diadem-TRANSMIT-000021 | NA | Consultant | Updated Wayfinding Signage drawings | 58 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-004108 | NA | 2026-02-25 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-04 | Diadem-TRANSMIT-000020 | NA | Consultant | Message And Door Schedules | 0 | 21 | 0 | NA | APPROVED | 2026-02-04 | WF-004107 | NA | 2026-02-25 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-04 | Tradetec-TRANSMIT-000344 | NA | Trade Partner | Bitac TD - Stage 2 - Rev 2 | 0 | 1 | 0 | NA | APPROVED | 2026-02-04 | WF-004120 | NA | 2026-02-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-04 | D&E-TRANSMIT-000376 | NA | Trade Partner | ITPs - Issued for Review | 0 | 20 | 0 | NA | APPROVED | 2026-02-04 | WF-004122 | NA | 2026-02-13 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-013101 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-04 | ZIA-TRANSMIT-000052 | NA | Trade Partner | L3 and Cx Plan Submission | 0 | 3 | 0 | NA | APPROVED | 2026-02-04 | WF-004123 | NA | 2026-02-13 |  |  | 2026-02-13 | 2026-02-13 | KPTG-TRANSMIT-012862 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2025-12-04 | WEBBAUST-TRANSMIT-000062 | NA | Consultant | WEBB - B10.2 ICT and Power update | 9 | 0 | 0 | NA | APPROVED | 2025-12-04 |  | 250 | 2025-12-07 |  |  |  | 2025-12-15 |  | Closed | 9 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-04 | Altaire-TRANSMIT-000070 | NA | Trade Partner | Updated Dry Fire Drawings and SP3 Equipment List | 0 | 2 | 0 | NA | APPROVED | 2026-02-04 | WF-004125 | NA | 2026-02-13 |  |  | 2026-02-13 | 2026-02-13 | KPTG-TRANSMIT-012857 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-04 | Tradetec-TRANSMIT-000022 | NA | Trade Partner | Technical Data Submissions - TSA | 0 | 1 | 0 | NA | APPROVED | 2026-02-04 | WF-000210 | NA | 2026-02-11 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-001100 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-04 | ASV-TRANSMIT-000010 | NA | Trade Partner | Hydraulic & Civil Shop Drawings - External | 3 | 0 | 0 | NA | APPROVED | 2026-02-04 | NA | 243 | 2026-02-13 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-000875 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-16 | BLUESF-TRANSMIT-000021 | NA | Trade Partner | M2-STR-BSF-SDRG-1101-(COLUMNS) PRECAST DRAWINGS IFA | 41 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000194 |  | 2026-02-11 |  | Drawings resubmitted as per Kapitol instruction |  | 2026-02-18 | KPTG-TRANSMIT-000884 | Closed | 41 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-04 | D&E-TRANSMIT-000321 | NA | Trade Partner | Functional Description - SIEMENS | 0 | 1 | 0 | KPTG-IntCorr-002655 | APPROVED |  | NA | NA |  |  | IFC-Distribution |  | 2026-02-10 | KPTG-TRANSMIT-002464 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-04 | SMEPS-TRANSMIT-000257 | NA | Trade Partner | SME- Labels Samples Submission - IFC | 0 | 1 | 0 | NA | APPROVED | 2026-02-04 | WF-000919 | NA | 2026-02-11 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-04 | WAM-TRANSMIT-000709 | NA | Consultant | Prototype Package Update | 2 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000154 | NA | 2026-02-06 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-000554 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-04 | TTW-TRANSMIT-000090 | NA | Consultant | Facade Scoping Mark Up - Tag Details | 4 | 0 | 0 | NA | APPROVED | 2026-02-04 | NA | 253 | 2026-02-06 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-000483 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-22 | BLUESF-TRANSMIT-000037 | NA | Trade Partner | M2-STR-BSF-SDRG-1101-LEVEL 1 (PRECAST COLUMN) PRECAST DRAWINGS IFA | 39 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000204 |  | 2026-02-11 |  | Drawings resubmitted as per Kapitol instruction. | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-002468 | Closed | 39 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-04 | Tradetec-TRANSMIT-000281 | NA | Trade Partner | Stage 4 - HVs IFA - HVP 20 , 23, 24, 26 | 5 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 1612 | 2025-12-12 |  | The workflow has been terminated as per requested by Charlie. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-04 | D&E-TRANSMIT-000322 | NA | Trade Partner | SIEMENS FUNCTIONAL TESTING ITP - FC2 | 0 | 5 | 0 | KPTG-IntCorr-002660 | APPROVED | 2026-02-06 | WF-000923 | NA | 2026-02-13 |  | 1-document hold requested by Maria and will resubmit with comment register | 2026-02-13 | 2026-02-13 | KPTG-TRANSMIT-002542 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-23 | ASV-TRANSMIT-000007 | N/A | Trade Partner | Revised Shop Drawings for Review | 7 | 0 | 0 | NA | APPROVED | 2026-01-23 |  | 208 | 2026-01-30 |  |  |  | 2026-02-04 | KPTG-TRANSMIT-000701 | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-05 | ASV-TRANSMIT-000131 | NA | Trade Partner | Re: Hydraulic Sample - Issued for Approval | 0 | 36 | 0 | NA | REJECTED | [5 empty] | The reference number is incorrect. The originator will correct it and resubmit the document - KPTG-TRANSMIT-012492 |  | 2026-02-05 | KPTG-TRANSMIT-012492 | Closed | 36 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-30 | KPTG-TRANSMIT-000641 | N/A | Trade Partner | XL Concrete Sample | 0 | 1 | 0 | NA | APPROVED | 2026-01-30 | WF-000183 |  | 2026-02-05 |  |  |  | 2026-02-05 | KPTG-TRANSMIT-000709 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-05 | TTW-CADV-000013 | N/A | Consultant | F3P1 Weatherproofing performance solution report-Draft | 0 | 1 | 0 | NA | APPROVED | 2026-02-05 | NA | 250 | 2026-02-10 |  |  | 2026-02-09 | 2026-02-09 | KPTG-TRANSMIT-000742 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-02-04 | GEMBA-D-TRANSMIT-000004 | NA | Consultant | Structural Drawings - Precast - For Certification | 19 | 0 | 0 | NA | APPROVED | 2026-02-04 | NA | 1 | 2026-02-09 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-000033 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-03 | ACG-TRANSMIT-000015 | N/A | Trade Partner | GF Data Hall TZ Rack Locking Schematic | 1 | 0 | 0 | NA | APPROVED | 2026-02-03 | NA | 918 | 2026-02-06 |  |  | 2026-02-10 | 2026-02-10 | KPTG-TRANSMIT-002769 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-03 | RDSBIM-TRANSMIT-000058 | N/A | Trade Partner | NXD1S2 ¦ LEVEL05 - WEBFORGE SETOUT PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-02-04 | NA | 923 | 2026-02-07 |  |  |  | 2026-02-06 | KPTG-TRANSMIT-002731 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-03 | SKS Tech-TRANSMIT-000145 | N/A | Trade Partner | HV TIES | 0 | 1 | 0 | NA | APPROVED | 2026-02-05 | WF-000788 | NA | 2026-02-10 |  |  | 2026-02-13 | 2026-02-13 | KPTG-WTRAN-001594 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-03 | Endfire-TRANSMIT-000057 | N/A | Trade Partner | Dry Fire Layout Level 4 & 5 IFA Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-02-04 | NA | 920 | 2026-02-07 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-002975 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-01 | SKS Tech-TRANSMIT-000096 | NA | Trade Partner | BASEMENT AND GROUND FLOOR IFC LAYOUTS - TEL | 7 | 0 | 0 | NA | APPROVED | 2025-12-02 | WF-000591 | 683 | 2025-12-04 |  | 4 elc drawings in review 681 | 2025-12-03 | 2025-12-06 | KPTG-TRANSMIT-002182 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-03 | CEDWA-TRANSMIT-000006 | N/A | Consultant | Updated Civil Drawings | 4 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED : WRONG ATTACHMENT |  | 2026-02-03 | KPTG-TRANSMIT-002667 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-05 | TTW-TRANSMIT-000007 | NA | Consultant | Facade 126 Certification update | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC, No review required |  | 2026-02-05 | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-05 | PCForm-TRANSMIT-000059 | NA | Trade Partner | Jumpform Concrete Envelope & Wall Elevation - Stage 10 - Stair 8 - revised | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFCs No review required. |  | 2026-02-05 | KPTG-TRANSMIT-000712 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-05 | ASV-TRANSMIT-000136 | NA | Trade Partner | Re: Hydraulic Sample - Drinking Fountains | 0 | 2 | 0 | NA | REJECTED | [5 empty] | The document Reference number is incorrect. |  | 2026-02-05 | KPTG-TRANSMIT-012499 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-05 | ASV-TRANSMIT-000134 | NA | Trade Partner | Resubmittal - Hydraulic Samples | 0 | 36 | 0 | NA | APPROVED | 2026-02-05 | WF-004135 | NA | 2026-02-26 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-013431 | Closed | 35 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-04 | D&E-TRANSMIT-000096 |  | Trade Partner | DIFFUSION | 0 | 1 | 0 | NA | APPROVED | 2026-02-04 | WF-000162 |  | 2026-02-11 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-03 | Metzone-TRANSMIT-000007 | NA | Trade Partner | Catch Deck - Column Stubs at Window Locations | 8 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC DRAWINGS- TRANSMITTED TO TRADE, CONSULTANTS AND CLIENT |  | 2026-02-03 | KPTG-TRANSMIT-001712 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-04 | D&E-TRANSMIT-000097 |  | Trade Partner | MWYCCB - GROUND LEVEL + LEVEL 1 - PLINTH LAYOUT ZONES - Issued For Construction | 3 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000163 | 114 | 2026-02-11 |  | Terminated - latest revision received |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-03 | fjc-TRANSMIT-000127 | NA | Consultant | Re: Roller Door | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Schedule- Transmitted to trade, consultants and client |  | 2026-02-03 | KPTG-TRANSMIT-001695 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-04 | D&E-TRANSMIT-000098 | SPARK-CRFI-KPG-000473 | Trade Partner | MWYCCB - LEVEL 1 PLINTH LAYOUT ZONE 8 & 9 - Issued For Review | 1 | 0 | 0 | NA | APPROVED | 2026-02-04 |  | 115 | 2026-02-11 |  |  |  | 2026-03-16 | KPTG-TRANSMIT-000539 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-04 | D&E-TRANSMIT-000099 | SPARK-CRFI-KPG-000497 | Trade Partner | SEISMIC GROUND FLOOR | 5 | 0 | 0 | NA | APPROVED | 2026-02-18 | WF-000207 |  | 2026-02-18 |  | KPTG-TRANSMIT-000398 - 1 document rejected |  | 2026-02-18 | KPTG-TRANSMIT-000451 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-03 | fjc-TRANSMIT-000129 | NA | Consultant | Rakign Column Elevations | 1 | 0 | 0 | NA | APPROVED | 2026-02-04 | NA | 537 | 2026-02-09 |  |  |  | 2026-02-04 | KPTG-SADV-002883 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-04 | NXES-TRANSMIT-000041 | NA | Trade Partner | Electrical Penetration - Ground Floor to Level 01 | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per the direction from the Mr. Mark, we transmitted these drawings to trade, consultant & client |  | 2026-02-04 | KPTG-TRANSMIT-001717 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-05 | ASV-TRANSMIT-000137 | NA | Trade Partner | Drinking Fountain's | 0 | 2 | 0 | NA | REJECTED | [5 empty] | S2 and S4 documents have been submitted together. |  | 2026-02-05 | KPTG-TRANSMIT-012500 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-05 | ACG-TRANSMIT-000042 |  | Trade Partner | M3 - Stage 3 Sample IFA | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The document does not include the revision number. |  | 2026-02-05 | KPTG-TRANSMIT-012501 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-04 | WilsonPD-TRANSMIT-000146 |  | Trade Partner | Store DHWU (HWL-02) for Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Error in title and revision |  | 2026-02-05 | KPTG-TRANSMIT-000400 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-04 | WilsonPD-TRANSMIT-000145 |  | Trade Partner | Rain Reuse System for Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Error in title and revision |  |  | KPTG-TRANSMIT-000399 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-11-24 | D&E-TRANSMIT-000058 | SPARK-CRFI-KPG-000374 | Trade Partner | Mangnetic Flow Meters - Decoupler line | 0 | 1 | 0 | NA | APPROVED | [7 empty] | 2026-02-04 | KPTG-TRANSMIT-000394 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-04 | Auspan-TRANSMIT-000045 | NA | Trade Partner | Revised M05, 1P05 shop drawings issued for approval | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per the direction from Ms.Ashlin, No action is required. Updated register only |  | 2026-02-04 | KPTG-IntCorr-000678 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-11-13 | D&E-TRANSMIT-000050 | SPARK-CRFI-KPG-000367 | Trade Partner | COMPRESSED AIR STATION | 0 | 1 | 0 | NA | APPROVED | [7 empty] | 2026-02-04 | KPTG-TRANSMIT-000396 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-01 | D&E-TRANSMIT-000065 | SPARK-CRFI-KPG-000476 | Trade Partner | MWYCCB - AIR SCHEMATIC MECHANICAL SERVICES SHEET 1 OF 1 - Issued For Review/Approval | 1 | 0 | 0 | KPTG-IntCorr-001009 | APPROVED | 2025-12-01 | WF-000085 |  | 2025-12-05 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-000415 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-05 | ASV-TRANSMIT-000133 | NA | Trade Partner | Re: Hydraulic Samples | 0 | 26 | 0 | NA | REJECTED | [5 empty] | The document revision number does not match the Aconex revision number. |  | 2026-02-05 | KPTG-TRANSMIT-012502 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-11-13 | D&E-TRANSMIT-000049 | SPARK-CRFI-KPG-000366 | Trade Partner | THERMAL WATER STORAGE TANK | 0 | 1 | 0 | NA | APPROVED | [7 empty] | 2026-02-04 | KPTG-TRANSMIT-000397 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-11-07 | D&E-TRANSMIT-000046 | SPARK-CRFI-KPG-000339 | Trade Partner | AIR DIRT SEPARATOR | 0 | 1 | 0 | NA | APPROVED | [7 empty] | 2026-02-04 | KPTG-TRANSMIT-000395 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-05 | ASV-TRANSMIT-000135 | NA | Trade Partner | Re: Hydraulic Samples - Trench Grate Grout & DDA Basin Mixer | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-02-05 | KPTG-TRANSMIT-012505 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-11-25 | D&E-TRANSMIT-000062 | SPARK-CRFI-KPG-000376 | Trade Partner | FIRE MATRIX | 0 | 1 | 0 | NA | APPROVED | [7 empty] | 2026-02-05 | KPTG-TRANSMIT-000403 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-11-14 | SMEPS-TRANSMIT-000066 | SPARK-CRFI-KPG-000393 | Trade Partner | Shop drawings - Containment Roof REV B | 8 | 0 | 0 | NA | APPROVED | 2025-12-09 | WF-000092 | 45 | 2025-12-16 |  |  |  | 2026-02-05 | KPTG-TRANSMIT-000404 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-04 | Hames-TRANSMIT-000107 | NA | Consultant | Updated Architectural set | 5 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000784 | 925 | 2026-02-09 |  |  |  | 2026-02-05 | KPTG-TRANSMIT-002691 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-04 | ZIA-TRANSMIT-000019 | NA | Trade Partner | CSMS - Sensor Location Drawings | 2 | 0 | 0 | NA | REJECTED | [5 empty] | QAError - Revision field |  | 2026-02-04 | KPTG-IntCorr-000969 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-04 | ZIA-TRANSMIT-000020 | NA | Trade Partner | CSMS - Outstation Location Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-02-05 | WF-000791 | 930 | 2026-02-10 |  |  | 2026-02-16 | 2026-02-16 | KPTG-TRANSMIT-002825 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-04 | KETE-TRANSMIT-000035 | NA | Trade Partner | Thermal Report | 0 | 1 | 0 | NA | APPROVED | 2026-02-05 | NA | 931 | 2026-02-10 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-003028 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-04 | Inhabit-TRANSMIT-000012 | NA | Consultant | Updated JV3 Report - Removal of GF corridor insulation | 1 | 0 | 0 | NA | APPROVED | 2026-02-06 | NA | 929 | 2026-02-10 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-002979 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-04 | CEDWA-TRANSMIT-000008 | NA | Consultant | Civil set | 4 | 0 | 0 | NA | APPROVED | 2026-02-05 | WF-000793 | 933 | 2026-02-10 |  |  | 2026-02-12 | 2026-02-12 | KPTG-TRANSMIT-002791 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-05 | Nilsen3-TRANSMIT-000020 | NA | Trade Partner | Re: Samples submitted for approval | 0 | 5 | 0 | NA | REJECTED | [5 empty] | The revision number is missing. |  | 2026-02-05 | KPTG-TRANSMIT-012506 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-14 | NXT-TRANSMIT-001186 ABB-TRANSMIT-000013 | NA | Trade Partner | Fwd: Primary drawings for M3-22-HVSB-B for contruction | 1 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-003776 |  | 2026-02-02 |  |  |  | 2026-02-05 | KPTG-TRANSMIT-012507 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-05 | ACG-TRANSMIT-000043 | NA | Trade Partner | M3 - Stage 3 ACG Shop Drawings IFA-1 | 5 | 0 | 0 | NA | APPROVED | 2026-02-05 | WF-004136 |  | 2026-02-23 |  |  |  | 2026-02-11 | KPTG-TRANSMIT-012701 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-05 | PARR-TRANSMIT-000114 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - TECH DATA | 0 | 23 | 0 | NA | APPROVED | 2026-02-05 | WF-004137 |  | 2026-02-26 |  | A total of 23 drawings have been submitted for review. One drawing has been closed via KPTG-TRANSMIT-012978, and the remaining 21 drawings are under review |  | 2026-02-17 | KPTG-TRANSMIT-012978 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-05 | ASV-TRANSMIT-000139 | NA | Trade Partner | Drinking Fountain - Stage 4 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | The same document has been received via ASV-TRANSMIT-000134 |  | 2026-02-05 | KPTG-TRANSMIT-012512 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-05 | SKS Tech-TRANSMIT-000018 | NA | Trade Partner | SKS - 100A FWU Isolator Technical Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-02-05 | WF-004139 |  | 2026-02-26 |  | Incorrect data and information was submitted. - SKS Tech-IntCorr-000040 |  | 2026-02-05 | KPTG-IntCorr-008987 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-05 | SKS Tech-TRANSMIT-000019 | NA | Trade Partner | SKS - Comms Cabling & Accessories Technical Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-02-05 | WF-004141 |  | 2026-02-26 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-05 | ASV-TRANSMIT-000142 | NA | Trade Partner | Drinking Fountain - Stage 4 | 0 | 1 | 0 | NA | APPROVED | 2026-02-05 | WF-004142 |  | 2026-02-26 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014292 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-04 | ccair-TRANSMIT-000069 | NA | Trade Partner | Level 04 - 06 Mechanical Shop Drawings - IFC | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2025-12-05 | KPTG-TRANSMIT-002475 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-05 | ARCST-TRANSMIT-000158 / KPTG-WTRAN-007495 | NA | Trade Partner | Stage 4 - C1 Switchroom Stage 1 Shop Drawings - Issued for Re-Approval | 17 | 0 | 0 | NA | APPROVED | 2026-02-05 | WF-004145 |  | 2026-02-13 |  | The rejected drawings have been resubmitted for review, as requested by Lola W. |  | 2026-02-17 | KPTG-TRANSMIT-013038 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-05 | ARCST-TRANSMIT-000162 | NA | Trade Partner | C2 Switchroom & Cooling Tower HD Bolts - Issued for Review | 4 | 0 | 0 | NA | APPROVED | 2026-02-05 | WF-004147 |  | 2026-02-13 |  | The rejected drawings have been resubmitted for review, as requested by Lola W. |  | 2026-02-17 | KPTG-TRANSMIT-013055 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-05 | ASV-TRANSMIT-000141 | NA | Trade Partner | Stage 3 - Samples | 0 | 26 | 0 | NA | APPROVED | 2026-02-05 | WF-004128 |  | 2026-02-18 |  | Mr. Sam S initiated the WF |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-05 | Auspan-TRANSMIT-000066 |  | Trade Partner | Auspan-TRANSMIT-000066: Precast marking plan ground floor zone 1, 2 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected by Kapitol PC; No review required. KPTG-SADV-000814 |  | 2026-02-05 | KPTG-SADV-000814 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-05 | ARCST-TRANSMIT-000147 KPTG-WTRAN-007507 | NA | Trade Partner | C1 Cooling Tower HD Bolts | 4 | 0 | 0 | NA | APPROVED | 2026-02-05 | WF-004155 |  | 2026-02-13 |  | The rejected drawings have been resubmitted for review as per requested by Lola |  | 2026-02-19 | KPTG-TRANSMIT-013214 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-05 | RBG-TRANSMIT-000052 | NA | Consultant | Structural Drawings for Lobby Slabs, Secondary Slabs and Stairs - Issued for Construction | 10 | 0 | 0 | NA | APPROVED | 2026-02-05 | NA | 256 | 2026-02-09 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000530 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-05 | ARCST-TRANSMIT-000154 KPTG-WTRAN-007507 | NA | Trade Partner | C1 Cooling Tower HD Bolts | 1 | 0 | 0 | NA | APPROVED | 2026-02-05 | WF-004155 |  | 2026-02-13 |  | The rejected drawings have been resubmitted for review as requested by Lola |  | 2026-02-19 | KPTG-TRANSMIT-013215 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-05 | WilsonPD-TRANSMIT-000147 |  | Trade Partner | Rain Re-use system | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-02-05 | KPTG-TRANSMIT-000408 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-04 | D&E-TRANSMIT-000325 | NA | Trade Partner | Fire matrix - updated EXCEL | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Distribution Only |  | 2026-02-11 | KPTG-TRANSMIT-002489 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-03 | WGAVIC-TRANSMIT-000028 | NA | Consultant | Structural Drawings - Piling - Issued for Construction | 4 | 0 | 0 | NA | APPROVED | 2025-12-04 |  | 103 | 2025-12-08 |  |  | 2025-12-08 | 2025-12-08 | KPTG-TRANSMIT-000281 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-05 | WilsonPD-TRANSMIT-000148 |  | Trade Partner | Store DHWU (HWL-02( | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-02-05 | KPTG-TRANSMIT-000409 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-04 | D&E-TRANSMIT-000326 | NA | Trade Partner | INDUSTRIAL / CHILLED WATER + SIDESTREAM SCHEMATICS - Issued For Construction | 4 | 0 | 0 | NA | APPROVED | 2026-02-04 | NA | 1364 | 2026-02-11 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-002622 | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-05 | D&E-TRANSMIT-000100 |  | Trade Partner | SEISMIC INSTALLATION GUIDE | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Error in title |  | 2026-02-05 | KPTG-TRANSMIT-000407 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-05 | D&E-TRANSMIT-000101 |  | Trade Partner | THERMAL WATER STORAGE TANK | 0 | 1 | 0 | NA | APPROVED | 2026-02-05 | WF-000169 |  | 2026-02-12 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-05 | D&E-TRANSMIT-000102 |  | Trade Partner | THERMAL WATER STORAGE TANK | 0 | 1 | 0 | NA | REJECTED | [5 empty] | same revision of this document is already registered |  |  | KPTG-IntCorr-001572 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-05 | D&E-TRANSMIT-000104 | SPARK-CRFI-KPG-000374 | Trade Partner | MAGNETIC FLOW METER | 0 | 1 | 0 | NA | APPROVED | 2026-02-05 | WF-000170 |  | 2026-02-12 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-04 | D&E-TRANSMIT-000328 | NA | Trade Partner | COMMISSIONING SCRIPTS - L3 IFC | 0 | 7 | 0 |  | APPROVED | 2026-02-04 | WF-000920 | NA | 2026-02-11 |  | requested by Maria 1 comment register added BASESG-IntCorr-000078 | 2026-02-12 | 2026-02-12 | KPTG-TRANSMIT-002526 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-04 | D&E-TRANSMIT-000327 | NA | Trade Partner | COMMISSIONING - STULZ FWU ITP FC2 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC-Distribution |  | 2026-02-04 | KPTG-TRANSMIT-002433 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-05 | WilsonPD-TRANSMIT-000149 |  | Trade Partner | Rainwater Plant (RWTP-01) | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Error in document number |  | 2026-02-05 | KPTG-TRANSMIT-000410 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-04 | D&E-TRANSMIT-000329 | NA | Trade Partner | COMMISSIONING L3 SCRIPTS - IFC | 0 | 8 | 0 | KPTG-IntCorr-002681 | APPROVED |  | NA | NA |  |  | IFC-Distribution only |  | 2026-02-10 | KPTG-TRANSMIT-002469 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-03 | WGAVIC-TRANSMIT-000029 | NA | Consultant | Structural Drawings - Stages 9, 10, 11 Level 1 Slabs, Stage 9 Ground Floor Slab - Issued for Certification | 35 | 0 | 0 | NA | APPROVED | 2025-12-05 |  | 113 | 2025-12-10 |  |  | 2025-12-09 | 2025-12-10 | KPTG-TRANSMIT-000292 | Closed | 34 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-04 | ZIA-TRANSMIT-000074 | NA | Trade Partner | CSMS Commissioning Manual | 0 | 1 | 0 | KPTG-IntCorr-002679 | APPROVED |  | NA | NA |  |  | IFC-Distribution Only |  | 2026-02-06 | KPTG-TRANSMIT-002588 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-04 | Auspan-TRANSMIT-000046 | NA | Trade Partner | Shop drawings issued for construction | 3 | 0 | 0 | NA | APPROVED | 2026-02-05 | NA | 539 | 2026-02-12 |  |  | 2026-02-05 | 2026-02-05 | KPTG-SADV-002907 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-05 | ccair-TRANSMIT-000087 | NA | Trade Partner | Roof Level Penetration Layout - IFC | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-05 | TIVINTL-TRANSMIT-000020 | NA | Trade Partner | SRC-Tivoli- L14-B-L15-A IFC drawings and updated IFC drawings | 112 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 112 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-05 | D&E-TRANSMIT-000377 | NA | Trade Partner | Upper Roof - CHW Pipe Layout ZONES | 4 | 0 | 0 | NA | APPROVED | 2026-02-05 | NA | 1981 | 2026-02-13 |  |  |  | 2026-02-18 | KPTG-TRANSMIT-013081 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-05 | D&E-TRANSMIT-000378 | NA | Trade Partner | Ground - Mech Elec Layout ZONES | 4 | 0 | 0 | NA | APPROVED | 2026-02-05 | NA | 1979 | 2026-02-13 |  |  |  | 2026-02-19 | KPTG-TRANSMIT-013161 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-05 | SKS Tech-TRANSMIT-000017 | NA | Trade Partner | Ground C1 Lighting drawing with corrected title | 1 | 0 | 0 | NA | APPROVED | 2026-02-05 | NA | 1977 | 2026-02-13 |  |  |  | 2026-02-13 | KPTG-TRANSMIT-012847 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2026-02-05 | JP-TRANSMIT-000012 | NA | Consultant | IFC Landscape Issue - Revision H | 24 | 0 | 0 | NA | APPROVED | 2026-02-05 | NA | 572 | 2026-02-12 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-04 | ccair-TRANSMIT-000070 | NA | Trade Partner | Roof Penetration layout - Mechanical Services - IFA | 2 | 0 | 0 | NA | APPROVED | 2025-12-04 | WF - 000788 | 493 | 2025-12-11 |  |  | 2025-12-15 | 2025-12-15 | KPTG-TRANSMIT-002529 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-05 | DI-TRANSMIT-000136 | NA | Consultant | Acoustic Wall layout change | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | UPLOADED IN ACC AND SEEKED FURTHER ANY ACTION NEEDED FOR THIS TRANSMIT BECAUSE OF TEMPKATE IS INACTIVE |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-05 | DI-TRANSMIT-000135 | NA | Consultant | PPT - Update to Acoustic elements | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | UPLOADED IN ACC AND SEEKED FURTHER ANY ACTION NEEDED FOR THIS TRANSMIT BECAUSE OF TEMPKATE IS INACTIVE |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-05 | CECPL-TRANSMIT-000014 | NA | Consultant | Updated Hydraulic Documentation | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | UPLOADED IN ACC AND SEEKED ADVISE FOR ANY ACTION REQUIRED BECAUSE OF REVIEW TEMPLATE IS INACTIVE |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-20 | OveArup-TRANSMIT-000019 | N/A | Consultant | DISTLV ¦ Arup ¦ 4B3 Documentation - Issued for Construction | 0 | 17 | 0 | NA | APPROVED | 2026-02-03 | WF-000141, WF-000142, WF-000145 ~ WF-000150 | NA | 2026-02-05 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-000605,KPTG-TRANSMIT-000609,KPTG-TRANSMIT-000618 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-05 | Normark-TRANSMIT-000043 | NA | Trade Partner | Samples information - Soft Landscape- SP03 soil profile A- reised sample sheet with new soil report | 0 | 1 | 0 | NA | APPROVED | 2026-02-05 | WF-000796 |  | 2026-02-09 |  |  |  | 2026-02-18 | KPTG-TRANSMIT-002446 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-05 | Normark-TRANSMIT-000044 | NA | Trade Partner | PV06 - Pavement Softfall rubber - EPDM Color sample - Sample sheet | 0 | 1 | 0 | NA | APPROVED | 2026-02-05 | WF-000798 |  | 2026-02-09 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-002346 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-05 | KPTG-IntCorr-004582 - | NA | Trade Partner | Shade Sail Services-SAMPLES | 0 | 3 | 0 | NA | APPROVED | 2026-02-10 | WF-000817 |  | 2026-02-18 |  | Review closed: kapitol advice awaits | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-002451 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-05 | P & R-TRANSMIT-000081 | NA | Trade Partner | BMS Functional Description and Wiring Diagram - IFA | 0 | 2 | 0 | NA | APPROVED | 2026-02-05 | WF-000799 | NA | 2026-02-09 |  | wf-000729 terminated | 2026-07-07 | 2026-07-07 | KPTG-SADV-005188 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-05 | CAP6-TRANSMIT-000005 | NA | Trade Partner | Classic Architectural Onboarding ¦ MLCSPR | 0 | 4 | 0 | NA | APPROVED | 2026-02-05 | WF-000800 | NA | 2026-02-10 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-002463, KPTG-TRANSMIT-002722 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-05 | Auspan-TRANSMIT-000047 | NA | Trade Partner | Revised G24, GC06 issued for approval | 4 | 0 | 0 | NA | APPROVED | 2026-02-05 | NA | 538 | 2026-02-12 |  |  | 2026-02-13 | 2026-02-13 | KPTG-SADV-003039 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-03 | WGAVIC-TRANSMIT-000030 | NA | Consultant | Civil Drawings - Main Works Setout - Reissued for Tender | 6 | 0 | 0 | NA | APPROVED | 2025-12-04 |  | 107 | 2025-12-08 |  |  | 2025-12-08 | 2025-12-08 | KPTG-TRANSMIT-000277 | Closed | 6 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-05 | Auspan-TRANSMIT-000075 | NA | Trade Partner | Precast shop drawings for construction. Ground floor stage 9. | 42 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFCs, no review required |  | 2026-02-05 | KPTG-TRANSMIT-000717 | Closed | 42 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-05 | Auspan-TRANSMIT-000076 | NA | Trade Partner | Resubmit columns 0GC080 and 0GC081 for approval | 2 | 0 | 0 |  | APPROVED |  | NA | NA |  |  | No need review of these drawings as they need to be revised as confirmed by Kapitol |  | 2026-02-05 | KPTG-IntCorr-000361 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-05 | Auspan-TRANSMIT-000077 | NA | Trade Partner | Precast shop drawings for construction. Stage 9 ground floor. | 38 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFCs No review required |  | 2026-02-06 | KPTG-TRANSMIT-000720 | Closed | 38 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-05 | Auspan-TRANSMIT-000078 | NA | Trade Partner | Revised Columns for Review - 0GC035 - 0GC043 | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings No review required |  | 2026-02-05 | NA | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-05 | Auspan-TRANSMIT-000079 | NA | Trade Partner | Precast shop drawings for construction. Stage 9 ground floor. | 30 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFCs No review required |  | 2026-02-06 | KPTG-TRANSMIT-000723 | Closed | 30 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-06 | INSULPAK-TRANSMIT-000006 | NA | Trade Partner | NXM3S4 - Upper Roof - CHW Pipe Layout ZONES - Issued For Review | 1 | 0 | 0 | NA | REJECTED | [5 empty] | The reference number is not included on the cover sheet. |  | 2026-02-06 | KAPITOL-TRANSMIT-001042 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-06 | RDSBIM-TRANSMIT-000209 | NA | Trade Partner | Fwd: NXM3S4 ¦ SITE HOIST-1 SETOUT LAYOUT | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | The drawing is for information . The register has been updated. If any further action is required, the coordinator will inform. RDSBIM-TRANSMIT-000210 |  | 2026-02-06 | KPTG-TRANSMIT-012542 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-05 | PFP PL-TRANSMIT-000047 | NA | Trade Partner | Commissioning plan for construction | 0 | 1 | 0 | KPTG-IntCorr-002680 | APPROVED |  | NA | NA |  |  | IFC-Distribution Only |  | 2026-02-09 | KPTG-TRANSMIT-002456 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-10-30 | PARR-TRANSMIT-000046 | NA | Trade Partner | Seismic Design - Fuel - Preliminary | 0 | 1 | 0 | NA | APPROVED | 2026-01-22 | WF-000818 | NA | 2026-01-29 |  |  | 2026-02-05 | 2026-02-05 | KPTG-TRANSMIT-002442 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-06 | Nilsen3-TRANSMIT-000022 | NA | Trade Partner | Nilsen Sample Submission | 0 | 26 | 0 | NA | APPROVED | 2026-02-06 | WF-004157 | NA | 2026-02-27 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014789 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-03 | VIA Arch-TRANSMIT-000025 | NA | Consultant | Stair Core Stair 1 & 2 Issued for Tender | 4 | 0 | 0 | NA | APPROVED | 2025-12-04 |  | 105 | 2025-12-08 |  |  | 2025-12-05 | 2025-12-08 | KPTG-TRANSMIT-000251 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-05 | RDSBIM-TRANSMIT-000149 | NA | Trade Partner | LINDRUM ¦ BASEMENT 1 LEVEL REFLECTED CEILING PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-02-06 | NA | 540 | 2026-02-11 |  |  |  | 2026-02-17 | KPTG-SADV-003097 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-06 | Nilsen3-TRANSMIT-000021 | NA | Trade Partner | Sample submission | 0 | 1 | 0 | NA | APPROVED | 2026-02-06 | WF-004158 |  | 2026-02-19 |  |  |  | 2026-02-20 | KPTG-TRANSMIT-013252 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-04 | ECBS-TRANSMIT-000005 | NA | Trade Partner | Revised form as attached | 0 | 1 | 0 | NA | APPROVED | 2026-02-05 | WF-000073 | NA | 2026-02-12 |  |  | 2026-02-13 | 2026-02-13 |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-05 | SMEPS-TRANSMIT-000054 | NA | Trade Partner | Kounis Secure Duct | 0 | 1 | 0 | NA | APPROVED | 2026-02-05 | WF-000075 | NA | 2026-02-12 |  |  | 2026-02-05 | 2026-03-05 |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-05 | SMEPS-TRANSMIT-000056 | NA | Trade Partner | SME Shop Drawing Review EPMS | 7 | 0 | 0 | NA | APPROVED | 2026-02-05 | WF-000077 | NA | 2026-02-12 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-000174 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-06 | INSULPAK-TRANSMIT-000007 | NA | Trade Partner | Re: Power Pack MSSB Drawings For Review | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-02-06 | KAPITOL-TRANSMIT-001050 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-05 | SMEPS-TRANSMIT-000057 | NA | Trade Partner | Tech Data - Wafer Seals Rev 3 | 0 | 1 | 0 | NA | APPROVED | 2026-02-06 | WF-000078 | NA | 2026-02-09 |  |  | 2026-02-11 | 2026-02-11 | KPTG-TRANSMIT-000125 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-04 | ECBS-TRANSMIT-000003 | NA | Trade Partner | COLO 4 - Tech Data Submission - R0 | 0 | 24 | 0 | NA | APPROVED | 2026-02-04 | WF-000067 | NA | 2026-02-02 |  |  | 2026-02-04 | 2026-02-04 |  | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-03 | SIL-TRANSMIT-000021 | NA | Trade Partner | MEL05 C4 - 32PO-41735-T018 Technical Submittals | 107 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000069 | NA | 2026-02-11 |  | WF - Terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-03 | SES AU-TRANSMIT-000002 | NA | Trade Partner | Security - Samples | 0 | 58 | 0 | NA | APPROVED | 2026-02-04 | WF-000070 | NA | 2026-02-11 |  |  | 2026-02-10 | 2026-02-10 | KPTG-TRANSMIT-000106 | Closed | 52 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-04 | SCG2014-TRANSMIT-000008 | NA | Consultant | Security Services - For Tender | 41 | 5 | 0 | 1 drawing wrong attachment,5 Technical Data | APPROVED | 2025-12-04 |  | 109 | 2025-12-08 |  |  | 2025-12-12 | 2025-12-13 | KPTG-TRANSMIT-000328 | Closed | 40 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-04 | D&E-TRANSMIT-000372 | NA | Trade Partner | M3 HS1 Office CU feet (plinth alternative) | 0 | 1 | 0 | NA | APPROVED | 2026-02-05 | WF-004130 | NA | 2026-02-19 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-013338 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-02 | D&E-TRANSMIT-000361 | NA | Trade Partner | HS1 Acoustic review for Registers | 0 | 1 | 0 | NA | APPROVED | 2026-02-05 | WF-004131 | NA | 2026-02-19 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014784 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-02 | D&E-TRANSMIT-000362 | NA | Trade Partner | Mechanical OA fans acoustic review | 0 | 1 | 0 | NA | APPROVED | 2026-02-05 | WF-004132 | NA | 2026-02-19 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014782 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-02 | D&E-TRANSMIT-000363 | NA | Trade Partner | Mechanical split units HS1 office acoustic review | 0 | 1 | 0 | NA | APPROVED | 2026-02-05 | WF-004133 | NA | 2026-02-19 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014780 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-05 | ASV-TRANSMIT-000138 | NA | Trade Partner | Drinking Fountain - Stage 2 | 0 | 1 | 0 | NA | APPROVED | 2026-02-05 | WF-004140 | NA | 2026-02-18 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-013617 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-05 | ECBS-TRANSMIT-000022 | NA | Trade Partner | Acess Panel Tech Data for Review | 0 | 1 | 0 | NA | APPROVED | 2026-02-05 | WF-004143 | NA | 2026-02-24 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-05 | ASV-TRANSMIT-000140 | NA | Trade Partner | Bunding Approval | 0 | 1 | 0 | NA | APPROVED | 2026-02-05 | WF-004148 | NA | 2026-02-18 |  |  | 2026-02-10 | 2026-02-10 | KPTG-TRANSMIT-012648 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-05 | ASV-TRANSMIT-000135 | NA | Trade Partner | Hydraulic Samples - Trench Grate Grout & DDA Basin Mixer | 0 | 2 | 0 | NA | APPROVED | 2026-02-05 | WF-004149 | NA | 2026-02-18 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-013620 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-06 | JAZBC-TRANSMIT-000010 | NA | Trade Partner | Re: Updated BCA Report for Stage 4 MEL741 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-02-06 | KPTG-TRANSMIT-012547 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-05 | Tradetec-TRANSMIT-000346 | NA | Trade Partner | IFA - Stage 2 - LVP26 | 1 | 0 | 0 | NA | APPROVED | 2026-02-05 | NA | 3777 | 2026-02-16 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-013758 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-03 | WGAVIC-TRANSMIT-000031 | NA | Consultant | Structural Drawings - Stage 9 Pile Caps, Columns and Walls - Issued for Construction | 12 | 0 | 0 | NA | APPROVED | 2025-12-05 |  | 111 | 2025-12-09 |  |  | 2025-12-10 | 2025-12-10 | KPTG-TRANSMIT-000305 | Closed | 12 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-04 | SMEPS-TRANSMIT-000052 | NA | Trade Partner | SME Shop Drawing Review Electrical | 1 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000071 | NA | 2026-02-11 |  |  | 2026-02-11 | 2026-02-11 | KPTG-TRANSMIT-000116 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-04 | SMEPS-TRANSMIT-000053 | NA | Trade Partner | SME Shop Drawing Review Communications | 11 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000072 | NA | 2026-02-11 |  |  | 2026-02-11 | 2026-02-11 | KPTG-TRANSMIT-000119 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-06 | RDSBIM-TRANSMIT-000210 | NA | Trade Partner | Fwd: NXM3S4 ¦ SITE HOIST-2 SETOUT LAYOUT | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For information only |  | 2026-02-06 | KPTG-TRANSMIT-012561 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-06 | CANDR-TRANSMIT-000001 |  | Trade Partner | Timber fin setout - Rev A | 48 | 0 | 0 | NA | REJECTED | [5 empty] | Error in document number& revision history block |  | 2026-02-06 | KPTG-TRANSMIT-000411 | Closed | 48 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-06 | WilsonPD-TRANSMIT-000151 |  | Trade Partner | Approved Stormwater Pump Station | 0 | 1 | 0 | KPTG-IntCorr-001591 | APPROVED | [5 empty] | No action - KPTG-IntCorr-001633 |  | 2026-02-11 | KPTG-IntCorr-001633 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-06 | PROLMC-TRANSMIT-000006 |  | Trade Partner | Proline post and louvre shop drawings 6-2-26 | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Error in document number |  | 2026-02-06 | KPTG-TRANSMIT-000413 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-06 | WilsonPD-TRANSMIT-000153 |  | Trade Partner | 315L Hot Water Unit (HWL-02) | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Error in revision |  |  | KPTG-TRANSMIT-000412 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-06 | PROLMC-TRANSMIT-000007 |  | Trade Partner | Proline roofing drawings 6-2-26 | 15 | 0 | 0 | NA | REJECTED | [5 empty] | Error in document number |  |  | KPTG-TRANSMIT-000414 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-05 | WilsonPD-TRANSMIT-000150 | SPARK-CRFI-KPG-000499 | Trade Partner | RWTP-01 | 0 | 1 | 0 | NA | APPROVED | 2026-02-06 | WF-000171 |  | 2026-02-13 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-000934 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-11-29 | LANSA-TRANSMIT-000073 | NA | Trade Partner | Levels 10-14 Drainage Drawings Issued for Approval | 6 | 0 | 0 | NA | APPROVED | 2025-12-01 | WF-000777 | 489 | 2025-12-05 |  |  | 2026-01-14 | 2026-01-14 | KPTG-SADV-004876 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-04 | HICKORY-TRANSMIT-000052 | NA | Trade Partner | SYNC Pods IFC Drawings | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2025-12-05 | KPTG-TRANSMIT-002471 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-06 | KPTG-IntCorr-001512 | NA | Trade Partner | Tile Samples Workflow - Linkstone | 0 | 4 | 0 | NA | APPROVED | 2026-02-06 | WF-000907 -WF-000910 | NA | 2026-02-13 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-06 | KPTG-IntCorr-001513 | NA | Trade Partner | Prototype Paint Samples Workflow - Kapitol/Dulux | 0 | 5 | 0 | NA | APPROVED | 2026-02-06 | WF-000907 | NA | 2026-02-13 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-06 | KPTG-IntCorr-001514 | NA | Trade Partner | Shower Screen Samples Workflow - RB&A | 0 | 2 | 0 | NA | APPROVED | 2026-02-06 | WF-000911 - WF-000912 | NA | 2026-02-13 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-06 | vdmcons-TRANSMIT-000127 | NA | Trade Partner | ME25 1004: D109 511-537 Sydney Rd Coburg - Shop Drawing - Panel B-L11-P8 - Re-IFF - 2026-02-05 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-06 | IVS-TRANSMIT-000328 | NA | Consultant | Stage 4, Acoustic Wall & Fuel Tank Steel Stairs | 5 | 0 | 0 | NA | APPROVED | 2026-02-05 | NA | 1988 | 2026-02-10 |  |  |  | 2026-02-13 | KPTG-TRANSMIT-012809 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-06 | HDRAus-TRANSMIT-000384 | NA | Consultant | Switch room and Chiller room package of drawings | 13 | 0 | 0 | NA | APPROVED | 2026-02-06 | NA | 1990 | 2026-02-10 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-012586 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-06 | HDRAus-TRANSMIT-000385 | NA | Consultant | general Updated to drawings previously issues | 11 | 0 | 0 | NA | APPROVED | 2026-02-06 | NA | 1992 | 2026-02-10 |  |  |  | 2026-02-13 | KPTG-TRANSMIT-012824 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-06 | RDSBIM-TRANSMIT-000211 | NA | Trade Partner | GROUND FLOOR TO ROOF PRECAST WALL PLAN AND ELEVATION | 8 | 0 | 0 | NA | APPROVED | 2026-02-06 | NA | 1994 | 2026-02-10 |  |  |  | 2026-02-11 | KPTG-TRANSMIT-012730 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-06 | Auspan-TRANSMIT-000080 | NA | Trade Partner | Precast shop drawings for construction. Stage 9 ground floor | 23 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. |  | 2026-02-07 | KPTG-TRANSMIT-000732 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-03 | OveArup-TRANSMIT-000015 | NA | Consultant | Arup 80% Issue for Construction | 99 | 1 | 0 | KPTG-IntCorr-000124 | APPROVED | 2025-12-04 | NA | 120 | 2025-12-09 |  |  | 2025-12-10 | 2025-12-10 | KPTG-TRANSMIT-000236 | Closed | 99 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-06 | Auspan-TRANSMIT-000081 | NA | Trade Partner | Latest precast dowel layout for stage 9 ground floor | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. |  | 2026-02-07 | KPTG-TRANSMIT-000735 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-06 | Auspan-TRANSMIT-000082 | NA | Trade Partner | Update already IFCed shop drawings. Lenton coupler details added. | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required |  | 2026-02-06 | KPTG-TRANSMIT-000738 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-06 | PFP PL-TRANSMIT-000048 | Na | Trade Partner | DH 7&8 Northern Corridor Dwgs | 2 | 0 | 0 | NA | APPROVED | 2026-02-06 | NA | 1369 | 2026-02-13 |  |  | 2026-02-16 | 2026-02-16 | KPTG-TRANSMIT-002556 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-06 | BASESG-IntCorr-000081 | NA | Trade Partner | L4 scripts | 0 | 4 | 0 | NA | APPROVED | 2026-02-06 | WF-000925 | NA | 2026-02-13 |  |  | 2026-02-12 | 2026-02-12 | KPTG-TRANSMIT-002534 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-06 | D&E-TRANSMIT-000330 | NA | Trade Partner | L2 & L3 Scripts - Revise & Resubmit | 0 | 3 | 0 | NA | APPROVED | 2026-02-06 | WF-000926 | NA | 2026-02-13 |  | submitted with 1 comment register | 2026-02-12 | 2026-02-12 | KPTG-TRANSMIT-002538 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-06 | ZIA-TRANSMIT-000076 | NA | Trade Partner | CSMS Test Results - Fibre & Cat6a | 0 | 2 | 0 | KPTG-IntCorr-002705 | APPROVED |  | NA | NA |  |  | As-Built- Distribution Only |  | 2026-02-12 | KPTG-TRANSMIT-002514 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-08-21 | Altaire-TRANSMIT-000016 | NA | Trade Partner | Dry Fire Commissioning Package | 0 | 22 | 0 | NA | APPROVED | 2025-11-28 | WF-000814 | NA | 2025-12-05 |  |  | 2026-02-06 | 2026-02-06 | KPTG-TRANSMIT-002448 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-06 | WGAVIC-TRANSMIT-000052 | NA | Consultant | Structural Drawings - Stage 9 Pour Plan and Stage 11 Ground Floor - Issued for Construction/Information | 12 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFCs No review required. Updated register and ACC. |  | 2026-02-06 | NA | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-06 | VIA Arch-TRANSMIT-000053 | NA | Consultant | M2 S9-11 Architecture 75% DD Issue | 86 | 0 | 0 | NA | APPROVED | 2026-02-09 | NA | 265 | 2026-02-13 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-000933 | Closed | 86 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-04 | ZIA-TRANSMIT-000005 | NA | Trade Partner | CSMS - Switch Room Outstation Shop Drawings | 3 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 689 | 2025-12-08 |  | Closed mail sent to originator only - Some document Number clarification needed from Zi-Argus - Distribution pending | 2025-12-05 | 2025-12-08 | KPTG-TRANSMIT-002204 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-06 | WGAVIC-TRANSMIT-000054 | NA | Consultant | Civil Drawings - Main Works (Exc. Drainage) - Issued for Construction | 32 | 0 | 0 | NA | APPROVED | 2026-02-10 | WF-000227 | NA | 2026-02-17 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-001155 | Closed | 32 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-06 | Highbu-TRANSMIT-000039 | NA | Trade Partner | HPS-HY-SMP-025/27/28 - WC1/WC2/WC3 suites for approval (with WELS certificates) | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Kapitol is required to confirm the Reviewers: KPTG-IntCorr-000686. The item was rejected due to an incorrect revision number. KPTG-SADV-002935 | 2026-02-09 | 2026-02-09 | KPTG-SADV-002935 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-06 | fjc-TRANSMIT-000130 | NA | Consultant | Ground, EOT, West Precast Arch Updates | 10 | 0 | 0 | NA | APPROVED | 2026-02-06 | NA | 541 | 2026-02-11 |  |  | 2026-02-11 | 2026-02-11 | KPTG-SADV-002993 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-06 | NXES-TRANSMIT-000069 | NA | Trade Partner | Updated Security Layout | 2 | 0 | 0 | NA | APPROVED | [5 empty] | IFC DRAWING: TRANSMITTED TO TRADE PARTNERS AND CONSULTANTS |  | 2026-02-06 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-06 | NXES-TRANSMIT-000070 | NA | Trade Partner | Re: Updated Security Layout | 1 | 0 | 0 | NA | APPROVED | [5 empty] | IFC DRAWING: TRANSMITTED TO TRADE & CONSULTANTS |  | 2026-02-06 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-06 | 4DW-TRANSMIT-000154 | NA | Consultant | Structural Documentation Updates | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Stamps are placed on Drawings. Hence, requested to resubmit |  | 2026-02-06 | KPTG-SADV-003630 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-06 | 4DW-TRANSMIT-000156 | NA | Consultant | Re: Structural Documentation Updates | 2 | 0 | 0 | NA | APPROVED | 2026-02-06 |  | 423 | 2026-02-13 |  |  |  | 2026-02-10 | KPTG-SADV-003667 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-06 | ARCH-TRANSMIT-000137 | NA | Consultant | MLC - SPR - AQC - Drawing update | 11 | 0 | 0 | NA | APPROVED | 2026-02-06 |  | 424 | 2026-02-13 |  |  |  | 2026-02-10 | KPTG-SADV-003666 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-06 | NXES-TRANSMIT-000071 | NA | Trade Partner | Electrical Drawings IFC | 7 | 0 | 0 | NA | APPROVED | [5 empty] | IFC DRAWINGS - TRANSMITED TO TRADE & CONSULTANTS |  | 2026-02-06 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-06 | NXES-TRANSMIT-000072 | NA | Trade Partner | AQC - Roof Comms Layout | 1 | 0 | 0 | NA | APPROVED | 2026-02-06 |  | 425 | 2026-02-13 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-003159 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-04 | ADP-TRANSMIT-000033 | NA | Consultant | ADP MEL4834 - Updated FP Drawings | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Register updated and distributed. Review not required. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-06 | ECBS-TRANSMIT-000065 | NA | Trade Partner | Submission of Ripplesound (2) | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Document number of drawings are incorrect, requested to submit. |  | 2026-02-06 | KPTG-SADV-003636 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-06 | ECBS-TRANSMIT-000066 | NA | Trade Partner | Submission of Ripplesound Connection Detail Shop Drawings Rev0 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Revision of Drawing has not mentioned in drawing, requested to resubmit. |  | 2026-02-06 | KPTG-SADV-003637 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-06 | RDSBIM-TRANSMIT-000104 | NA | Trade Partner | MLCSPR ¦ CARPARK SOUTH LEVEL 01 RCP | 1 | 0 | 0 | NA | APPROVED | 2026-02-07 |  | 426 | 2026-02-13 |  |  |  | 2026-02-10 | KPTG-SADV-003669 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-06 | RDSBIM-TRANSMIT-000105 | NA | Trade Partner | MLCSPR ¦ RAW TYPICAL AQUATIC CENTRE ROOF PARAPET DETAILS | 1 | 0 | 0 | NA | APPROVED | 2026-02-07 |  | 427 | 2026-02-13 |  |  |  | 2026-02-10 | KPTG-SADV-003670 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-05 | Hames-TRANSMIT-000108 | NA | Consultant | Arch. Drawings FC | 2 | 0 | 0 | NA | APPROVED | 2026-02-10 | NA | 962 | 2026-02-13 |  |  | 2026-02-13 | 2026-02-13 | KPTG-TRANSMIT-002813 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-05 | ACG-TRANSMIT-000016 | NA | Trade Partner | Electronic Security Drawings IFC | 5 | 0 | 0 | NA | APPROVED | 2026-02-05 | WF-000803 | 940 | 2026-02-09 |  |  |  | 2026-02-06 | KPTG-TRANSMIT-002735 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-05 | Hames-TRANSMIT-000109 | NA | Consultant | Arch. Drawings FC | 40 | 0 | 0 | NA | APPROVED | 2026-02-10 | NA | 962 | 2026-02-13 |  |  | 2026-02-13 | 2026-02-13 | KPTG-TRANSMIT-002813 | Closed | 38 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-05 | ZIA-TRANSMIT-000021 | NA | Trade Partner | CSMS - Sensor Location Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-02-06 | NA | 949 | 2026-02-11 |  |  | 2026-02-16 | 2026-02-16 | KPTG-TRANSMIT-002831 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-05 | Hames-TRANSMIT-000110 | NA | Consultant | Arch. Drawings FC | 2 | 0 | 0 | NA | APPROVED | 2026-02-06 | WF-000804 | 946 | 2026-02-10 |  |  |  | 2026-02-11 | KPTG-TRANSMIT-002782 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-05 | KPTG-TRANSMIT-002750 (Ayyan's Email) | NA | Trade Partner | DOOR SHUTTER - AT B-LG-012A AND AT B-LG-012B | 2 | 0 | 0 | NA | APPROVED | 2026-02-05 | NA | 935 | 2026-02-10 |  |  | 2026-03-06 | 2026-03-09 | KPTG-TRANSMIT-003086 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-06 | Luke Email | NA | Consultant | FIE - GENERATOR DOCUMENTATION SET | 6 | 0 | 0 | NA | APPROVED | [5 empty] | Only Aconex registration |  |  |  | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-06 | RDSBIM-TRANSMIT-000059 | NA | Trade Partner | WEBFORGE SETOUT PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-02-06 | NA | 950 | 2026-02-10 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-002862 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-06 | Harry's Email | NA | Consultant | PWC Approved - Power Services | 26 | 0 | 0 | NA | APPROVED | 2026-02-06 |  |  |  |  | Aconex registration and forwarded to all parties |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-06 | Hames-TRANSMIT-000111 | NA | Consultant | Arch. Drawings FC | 1 | 0 | 0 | NA | APPROVED | 2026-02-10 | NA | 962 | 2026-02-13 |  |  | 2026-02-13 | 2026-02-13 | KPTG-TRANSMIT-002813 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-06 | Endfire-TRANSMIT-000058 | NA | Trade Partner | Dry Fire Layout IFC Drawings - Basement and Levels 1-3 | 4 | 0 | 0 | NA | APPROVED | 2026-02-06 | WF-000798 | 954 | 2026-02-10 |  |  | 2026-02-17 | 2026-02-17 | KPTG-TRANSMIT-002845 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-06 | SKS Tech-TRANSMIT-000147 | NA | Trade Partner | SCADA FUNCTIONAL DESIGN SPECIFICATION, NETWORK TOPOLOGY AND REMOTE OPERATING PANEL | 0 | 3 | 0 | NA | APPROVED | 2026-02-06 | WF-000802 | NA | 2026-06-10 |  |  | 2026-02-13 | 2026-02-13 | KPTG-WTRAN-001603 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-05 | ACG-TRANSMIT-000016 | NA | Trade Partner | Electronic Security Drawings IFA | 1 | 0 | 0 | NA | APPROVED | 2026-02-05 | WF-000803 | 941 | 2026-02-09 |  |  |  | 2026-02-18 | KPTG-TRANSMIT-002852 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-09 | PFP PL-TRANSMIT-000063 | NA | Trade Partner | Ground & Level 1 Zone 1 IFA | 2 | 0 | 0 | NA | APPROVED | 2026-02-09 | NA | 1995 | 2026-02-17 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-09 | RDSBIM-TRANSMIT-R000212 | NA | Trade Partner | NXM3S4 GROUND FLOOR CONCRETE PROFILE PLAN & SECTIONS | 4 | 0 | 0 | NA | APPROVED | 2026-02-09 | NA | 2084 | 2026-02-23 |  |  | 2026-03-02 | 2026-03-02 | KPTG-IntCorr-010128 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-09 | SKS Tech-TRANSMIT-000010 | NA | Trade Partner | SKS - Lug, Glands and Heatshrink technical data | 0 | 1 | 0 | NA | APPROVED | 2026-02-09 | NA | WF-004177 | 2026-03-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-03 | TTW-TRANSMIT-000046 | NA | Consultant | Structural Documentation - Issued for Certification | 10 | 0 | 0 | KPTG-IntCorr-000125 | APPROVED | 2025-12-05 | NA | 124 | 2025-12-05 |  | submitted together with trn # 43 | 2025-12-10 | 2025-12-10 | KPTG-TRANSMIT-000228 | Closed | 88 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-07 | RDSBIM-TRANSMIT-000150 | NA | Trade Partner | LINDRUM ¦ LEVEL 02 TO LEVEL 05 COREWALL CONCRETE PROFILE PLAN ELEVATIONS | 2 | 0 | 0 | NA | APPROVED | 2026-02-09 | NA | 543 | 2026-02-16 |  |  | 2026-02-18 | 2026-02-18 | KPTG-SADV-003116 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-07 | RDSBIM-TRANSMIT-000151 | NA | Trade Partner | LINDRUM ¦ GROUND AND MEZZANINE LEVEL CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | NA | APPROVED | 2026-02-09 | NA | 542 | 2026-02-12 |  |  | 2026-02-12 | 2026-02-12 | KPTG-SADV-003017 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-09 | D&E-TRANSMIT-000382 | NA | Trade Partner | NXM3S4 - Chiller Roof - Builders Works Layout Zones - Issued For Review | 2 | 0 | 0 | NA | APPROVED | 2026-02-09 | NA | 1999 | 2026-02-17 |  |  |  | 2026-02-19 | KPTG-TRANSMIT-013125 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-09 | D&E-TRANSMIT-000383 | NA | Trade Partner | NXM3S4 - Cooling Tower Mesh - Builders Works Layout ZONES - Issued For Review | 2 | 0 | 0 | NA | APPROVED | 2026-02-09 | NA | 2001 | 2026-02-17 |  |  |  | 2026-02-19 | KPTG-TRANSMIT-013133 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-09 | KPTG-WTRAN-007547 | NA | Trade Partner | Klip-Lok Classic 700 | 0 | 1 | 0 | NA | APPROVED | 2026-02-09 | WF-004180 |  | 2026-02-25 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-05 | KPTG-IntCorr-008944 | NA | Trade Partner | Verge HD Safety Barrier Technical Data Sheet | 0 | 1 | 0 | NA | APPROVED | 2026-02-05 | NA | WF-004146 | 2026-02-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-05 | ACG-TRANSMIT-000044 | NA | Trade Partner | M3 - Stage 2 Samples | 0 | 2 | 0 | NA | APPROVED | 2026-02-05 | WF-004154 | NA | 2026-02-12 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-014430 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-11-05 | OveArup-WTRAN-001134 | NA | Trade Partner | CLIENT REVIEW | 9 | 0 | 0 | NA | APPROVED | 2025-11-05 | WF-003205 |  | 2026-02-04 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-012569 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-04 | KPTG-IntCorr-003427 | NA | Trade Partner | Crafted Stainless Shop Drawings | 12 | 0 | 0 | NA | REJECTED | [5 empty] | Document Number of drawings are incorrect, requested them to resubmit |  | 2025-12-04 | KPTG-IntCorr-003434 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-04 | KPTG-IntCorr-008861 | NA | Consultant | URGENT: Upload & Transmit Documents | 0 | 4 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-02-05 | KPTG-TRANSMIT-012519 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-05 | KPTG-IntCorr-008944 | NA | Trade Partner | Verge HD Safety Barrier Technical Data Sheet | 0 | 1 | 0 | NA | APPROVED | 2026-02-05 | WF-004146 | NA | 2026-02-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-04 | Altaire-TRANSMIT-000071 | NA | Trade Partner | Action Required: Outstanding Commissioning Documentation | 0 | 4 | 0 | NA | APPROVED | 2026-02-05 | WF-004153 | NA | 2026-02-16 |  |  | 2026-02-13 | 2026-02-13 | KPTG-TRANSMIT-012859 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-06 | Stowe-A-TRANSMIT-000477 | NA | Trade Partner | Stowe - Tech Data Submission - NHP 100A ISOLATOR | 0 | 1 | 0 | NA | APPROVED | 2026-02-06 | WF-004156 | NA | 2026-02-19 |  |  | 2026-02-24 | 2026-02-25 | KPTG-TRANSMIT-013532 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-06 | ASV-TRANSMIT-000143 | NA | Trade Partner | Fire Treatment Samples | 0 | 3 | 0 | NA | APPROVED | 2026-02-06 | WF-004159 | NA | 2026-02-18 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-013618 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-06 | ARCST-TRANSMIT-000201 | NA | Trade Partner | Stage 2 Southern Internal Stair - IFA Package | 1 | 0 | 0 | NA | APPROVED | 2026-02-06 | WF-004168 | NA | 2026-02-24 |  |  | 2026-04-30 | 2026-05-01 | KPTG-TRANSMIT-016767 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-06 | D&E-TRANSMIT-000381 | NA | Trade Partner | D&E Commissioning Plan - Issued for Review | 0 | 1 | 0 | NA | APPROVED | 2026-02-06 | WF-004163 | NA | 2026-02-17 |  |  | 2026-02-13 | 2026-02-13 | KPTG-TRANSMIT-012853 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-06 | PFP PL-TRANSMIT-000062 | NA | Trade Partner | CX L2 & L3 Nitrogen generator scripts for review | 0 | 2 | 0 | NA | APPROVED | 2026-02-06 | WF-004161 | NA | 2026-02-17 |  |  |  | 2026-02-18 | KPTG-TRANSMIT-013092 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-06 | ZIA-TRANSMIT-000053 | NA | Trade Partner | L3 and Cx Plan Submission | 0 | 4 | 0 | NA | APPROVED | 2026-02-06 | WF-004164 | NA | 2026-02-17 |  |  | 2026-02-13 | 2026-02-13 | KPTG-TRANSMIT-012854 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-06 | ZIA-TRANSMIT-000053 | NA | Trade Partner | L3 and Cx Plan Submission | 0 | 32 | 0 | NA | APPROVED | 2026-02-06 | WF-004165 | NA | 2026-02-17 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-013096 | Closed | 32 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-04 | KPTG-IntCorr-003435 | NA | Trade Partner | Crafted Stainless Shop Drawings | 12 | 0 | 0 | NA | APPROVED | 2025-12-04 |  | 367 | 2025-12-11 |  |  |  | 2026-01-27 | KPTG-SADV-003536 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-06 | ZIA-TRANSMIT-000053 | NA | Trade Partner | L3 and Cx Plan Submission | 0 | 11 | 0 | NA | APPROVED | 2026-02-06 | WF-004166 | NA | 2026-02-17 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-013098 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-06 | HDRAus-TRANSMIT-000383 | NA | Consultant | HAC Line Marking - Alignment Across All Stages - Sitewide Detail | 1 | 0 | 0 | NA | APPROVED | 2026-02-09 | NA | 3781 | 2026-02-11 |  |  | 2026-02-11 | 2026-02-17 | KPTG-TRANSMIT-013050 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-06 | D&E-TRANSMIT-000379 | NA | Trade Partner | ITPs - Issued for Review | 0 | 6 | 0 | NA | APPROVED | 2026-02-06 | WF-004169 | NA | 2026-02-17 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-013099 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-09 | KPTG-WTRAN-007551 | NA | Trade Partner | Slim Deck PARAPET | 0 | 3 | 0 | NA | APPROVED | 2026-02-09 | WF-004181 |  | 2026-02-20 |  | The workflow has been initiated as requested by Max H. |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-09 | NXT-TRANSMIT-001259 | NA | Trade Partner | Fwd: Secondary drawings for HVSB-V - IFC | 1 | 0 | 0 | NA | APPROVED | 2026-02-09 | WF-004182 |  | 2026-02-25 |  |  |  | 2026-02-23 | KPTG-TRANSMIT-013363 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-09 | D&E-TRANSMIT-000385 | NA | Trade Partner | NXM3S4 - Ground & Level 1 - Builders Works Layout Zones + Elevation Views - Issued For Review | 6 | 0 | 0 | NA | APPROVED | 2026-02-09 | NA | 2004 | 2026-02-17 |  |  |  | 2026-02-19 | KPTG-TRANSMIT-013132 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-09 | SMEPS-TRANSMIT-000169 | NA | Trade Partner | Electrical Services 22KV | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect transmittal subject line.. |  | 2026-02-09 | KPTG-TRANSMIT-012582 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-09 | NXT-TRANSMIT-001260 | NA | Trade Partner | Labels for M3-22-HVSB-A,B,D,R,U & V for approval | 1 | 0 | 0 | NA | APPROVED | 2026-02-09 | WF-004185) |  | 2026-02-25 |  |  |  | 2026-02-20 | KPTG-TRANSMIT-013250 | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-09 | Nilsen3-TRANSMIT-000023 | NA | Trade Partner | Samples submitted for approval | 0 | 4 | 0 | NA | APPROVED | 2026-02-09 | WF-004187 | NA | 2026-02-19 |  |  | 2026-02-28 | 2026-03-02 | Nilsen3-TRANSMIT-000023 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-09 | SMEPS-TRANSMIT-000166 | NA | Trade Partner | Re: 22KV - MSWB IFC | 1 | 0 | 0 | NA | REJECTED | [5 empty] | The same revision has been received via SMEPS-TRANSMIT-000160 |  | 2026-02-09 | KPTG-TRANSMIT-012583 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-11-27 | KPTG-IntCorr-003258 | NA | Trade Partner | EHS Roof and Level 2 Updated Plans | 4 | 0 | 0 | NA | APPROVED | 2025-11-27 |  | 355 | 2025-12-04 |  | Kapitol Advice awaits on final approval of BIM Review-355 | 2025-12-04 |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-09 | Altaire-TRANSMIT-000074 | NA | Trade Partner | Fwd: NEXTDC M3S3 - HVSB 22KV Dry Fire Shop Drawings (For Approval) | 4 | 0 | 0 | NA | APPROVED | 2026-02-10 | WF-004195 |  | 2026-02-23 |  | KPTG-TRANSMIT-012584 - The register has been updated. If any further action is required, the coordinator will inform. |  | 2026-02-18 | KPTG-TRANSMIT-013090 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-09 | KAPITOL-TRANSMIT-001057 | NA | Trade Partner | HFF - MSB Shop Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-02-09 | NA | 283 | 2026-02-13 |  |  |  | 2026-02-13 | KAPITOL-TRANSMIT-001083 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-09 | ARCST-TRANSMIT-000204 | NA | Trade Partner | C1 Cooling Tower Upper Gantry Handrails Shop Drawings - Issued for Approval | 33 | 0 | 0 | NA | APPROVED | 2026-02-09 | WF-004188 | NA | 2026-03-05 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-013777 | Closed | 33 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-09 | RDSBIM-TRANSMIT-000213 | NA | Trade Partner | Fwd: NXM3S2 ¦ ROOF HOB AND PLINTH PLAN | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | The register has been updated. If any further action is required, the coordinator will inform. - KPTG-TRANSMIT-012604 RDSBIM-TRANSMIT-000213 & RDSBIM-TRANSMIT-000214 are same. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-07 | WilsonPD-TRANSMIT-000154 |  | Trade Partner | 315L Hot Water Unit (HWL-02) | 0 | 1 | 0 | NA | APPROVED | 2026-02-09 | WF-000172 |  | 2026-02-16 |  |  | 2026-02-09 | 2026-02-09 | KPTG-TRANSMIT-000421 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-09 | RDSBIM-TRANSMIT-000214 | NA | Trade Partner | Fwd: NXM3S3 ¦ ROOF HOB AND PLINTH PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-02-10 | RDSBIM-TRANSMIT-000214 |  | 2026-02-26 |  | As per Max (Teams) - I terminated because it’s only internal document. Not to be reviewed by others yet. My bad |  | 2026-02-11 | The workflow has been terminated by Max H - (teams Comment - it’s only internal document. -) | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-08 | RDSBIM-TRANSMIT-000031 | SPARK-CRFI-KPG-000222 | Trade Partner | MWYCCB ¦ LEVEL 01 CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | [5 empty] | KPTG-TRANSMIT-000417 - Issued to all trades Latest revision received |  | 2026-03-09 | KPTG-TRANSMIT-000417 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-09 | HDRAus-TRANSMIT-000074 | NA | Consultant | HAC Line Marking - Alignment Across All Stages - Sitewide Detail | 1 | 0 | 0 | NA | APPROVED | 2026-02-09 | NA | 1373 | 2026-02-16 |  |  | 2026-03-01 | 2026-03-02 | KPTG-TRANSMIT-002679 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-09 | NXT-TRANSMIT-000357 | NA | Client | NEXTDC M3 Functional Description Issued For Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC-Distribution Only |  | 2026-02-09 | KPTG-TRANSMIT-002455 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-09 | IVS-TRANSMIT-000326 | NA | Trade Partner | Re: Stage 4 - Roof Steel stair pack Certification Issue | 2 | 0 | 0 | NA | APPROVED | 2026-01-30 | NA | 1929 | 2026-02-02 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-012607 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-04 | Arco-TRANSMIT-000006 | NA | Trade Partner | SERIES 2 - ALUMINUM ROLLER SHUTTERS | 5 | 0 | 0 | NA | APPROVED | 2025-12-04 |  | 375 | 2025-12-09 |  |  | 2025-12-17 | 2025-12-17 | KPTG-SADV-003187 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-09 | D&E-TRANSMIT-000331 | NA | Trade Partner | L1 MANTRAP DUCT & PIPE LAYOUT & PENETRATIONS | 2 | 0 | 0 | NA | APPROVED |  | NA | 1375 | 2026-02-16 |  |  | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-002598 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-09 | Auspan-TRANSMIT-000069 | NA | Consultant | Rinco-RTRFI-000157: Re: Zone 3 RFI 19. Update IFCed shop drawings for construction | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required, Update Register and circulate to all. KPTG-TRANSMIT-000563 |  | 2026-02-09 | KPTG-TRANSMIT-000563 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-09 | Auscool-TRANSMIT-000007 | NA | Trade Partner | Heat load package for review | 0 | 1 | 0 | NA | APPROVED | 2026-02-09 | WF-000179 | NA | 2026-02-16 |  |  |  | 2026-02-16 | KPTG-TRANSMIT-000625 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-06 | Rinco-TRANSMIT-000027 | NA | Consultant | Structural drawing Issued for Construction | 41 | 0 | 0 | NA | APPROVED | 2026-02-06 | WF-000178 | 316 | 2026-01-15 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-000568 | Closed | 41 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-09 | SMEPS-TRANSMIT-000167 | NA | Trade Partner | SME - DRAWINGS IFA SUBMISSIONS | 8 | 0 | 0 | NA | APPROVED | 2026-02-09 | NA | 2008 / New WF - 2109 | 2026-02-25 |  | The WF has been terminated as requested by Peter Z |  | 2026-03-16 | KPTG-RFI-006723 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-09 | SMEPS-TRANSMIT-000167 | NA | Trade Partner | SME - DRAWINGS IFA SUBMISSIONS | 2 | 0 | 0 | NA | APPROVED | 2026-02-09 | NA | 2009 - New WF 2110 | 2026-02-25 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014822 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-09 | SMEPS-TRANSMIT-000170 | NA | Trade Partner | SME - DRAWINGS IFA PART SUBMISSIONS | 2 | 0 | 0 | NA | APPROVED | 2026-02-09 | NA | 2011 | 2026-02-17 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014868 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-09 | OveArup-WTRAN-001136 | NA | Consultant | TEMPORARY CLIENT IFC KAP-ARUP-HS-NEXTDC Next DC M3 Stage 4 - Ground Floor Zone 5 Panels & Marking Plans Next DC M3 Stage 4 | 60 | 0 | 0 | NA | APPROVED | 2025-11-06 | 003216 |  | 2026-02-17 |  | ITS HAVE DIFFERENT MOTHER TRANSMITS |  | 2026-02-09 | KPTG-TRANSMIT-012618 | Closed | 60 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-09 | DI-TRANSMIT-000138 | NA | Consultant | PPT - wall junction details update | 2 | 0 | 0 | NA | APPROVED | 2026-02-09 | NA | 284 | 2026-02-11 |  |  |  | 2026-02-10 | KAPITOL-TRANSMIT-001063 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2025-11-28 | RLA-TRANSMIT-000236 | NA | Consultant | ARCHITECTURAL DRAWING UPDATES - FOR CONSTRUCTION | 19 | 0 | 0 | NA | APPROVED | 2025-12-01 | NA | 563 | 2025-12-08 |  |  | 2025-12-03 | 2025-12-03 | KPTG-TRANSMIT-002508 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-04 | PROLMC-TRANSMIT-000016 | NA | Trade Partner | Proline updated set of shop drawings (4/12/25) | 16 | 0 | 0 | NA | APPROVED | 2025-12-04 |  | 368 | 2025-12-11 |  |  | 2025-12-08 | 2025-12-08 | KPTG-SADV-003037 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-09 | SMPS-TRANSMIT-000103 | NA | Consultant | Updated As builts | 6 | 0 | 0 | NA | APPROVED | 2026-02-09 | NA | 286 | 2026-02-11 |  | IN THIS TRANSMIT RECEIVED 4 SCHDULES AND 2 DRAWING AND CLOSEDOUT TWO DRAWINGS . |  | 2026-02-10 | KAPITOL-TRANSMIT-001061 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-09 | DI-TRANSMIT-000137 | NA | Consultant | Updated Plans | 2 | 0 | 0 | NA | APPROVED | 2026-02-08 | NA | 287 | 2026-02-11 |  |  |  | 2026-02-10 | KAPITOL-TRANSMIT-001062 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-09 | INSULPAK-TRANSMIT-000008 | NA | Consultant | Power Pack MSSB Drawings For Review | 1 | 0 | 0 | NA | APPROVED | 2026-02-09 | NA | 303 | 2026-03-04 |  | WF 288 -VOID- Moved to PP template -303 | 2026-03-02 | 2026-03-02 | KAPITOL-TRANSMIT-001139 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-09 | Tradetec-TRANSMIT-000024 | NA | Trade Partner | Technical Data Submissions for Review | 0 | 13 | 0 | NA | REJECTED | [5 empty] | Need to revise the documents, KPTG-SADV-001004 |  | 2026-02-09 | KPTG-SADV-001004 | Closed | 13 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-06 | PCForm-TRANSMIT-000067 | NA | Trade Partner | Boral - Resubmission for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-02-09 | WF-000216 | NA | 2026-02-11 |  |  | 2026-02-09 | 2026-02-09 | KPTG-TRANSMIT-000749 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-11-17 | WilsonPD-TRANSMIT-000120 | SPARK-CRFI-KPG-000337 | Trade Partner | IFA Floor Waste | 0 | 1 | 0 | NA | APPROVED | 2026-02-09 | WF-000173 |  | 2026-02-16 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-000416 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-11-10 | SMEPS-TRANSMIT-000060 | SPARK-CRFI-KPG-000330 | Trade Partner | Generator Tech Data | 0 | 1 | 0 | NA | APPROVED | 2025-11-12 | WF-000069 |  | 2025-11-19 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-000420 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-04 | Ardon-TRANSMIT-000019 | NA | Trade Partner | Stage 3 - FFE Tech Data Submission | 0 | 4 | 0 | NA | APPROVED | 2026-02-10 | WF-004196 |  | 2026-02-26 |  |  | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-013872 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-09 | RDSBIM-TRANSMIT-000159 | NA | Trade Partner | LEVEL 10 PARTITION WALL SUBMISSION | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-11-25 | Schindle-TRANSMIT-000016 | NA | Trade Partner | VT - stage 4 - IFC Rev 2 - Lift C3 | 6 | 0 | 0 | NA | APPROVED | 2025-11-25 | WF-003997 |  | 2026-02-12 |  |  |  | 2026-02-10 | KPTG-TRANSMIT-012621 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-04 | ECBS-TRANSMIT-000036 | NA | Trade Partner | Revised tech data for AM41 - 316 stainless steel access panel | 0 | 1 | 0 | NA | APPROVED | 2025-12-05 | WF-000654 |  | 2025-12-10 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-10 | Altaire-TRANSMIT-000075 | NA | Trade Partner | Fwd: NEXTDC M3S4 - Dry Fire MASDS Calculations (For Approval) (1) | 0 | 1 | 0 | NA | APPROVED |  | NA |  |  |  | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-09 | fjc-TRANSMIT-000131 | NA | Consultant | Re: 4D stamp and review of on hold panels. | 1 | 0 | 0 | NA | APPROVED | 2026-02-10 | NA | 546 | 2026-02-13 |  |  | 2026-02-10 | 2026-02-10 | KPTG-SADV-002957 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-06 | DRLL-TRANSMIT-000067 | NA | Trade Partner | Battery Room FCU Leak Detection System Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-02-10 | WF-000927 | NA | 2026-02-17 |  |  | 2026-02-12 | 2026-02-12 | KPTG-TRANSMIT-002521 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-10 | Auscool-TRANSMIT-000072 | NA | Trade Partner | BMS Functional Description - For Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | the document number is not given. |  | 2026-02-10 | KPTG-IntCorr-000693 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-10 | Entire M-TRANSMIT-000034 | NA | Trade Partner | Mechanical Seismic Design | 1 | 0 | 0 | NA | APPROVED | 2026-02-10 | WF-004199 | NA | 2026-02-23 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-013767 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-28 | DS-TRANSMIT-000094 | NA | Trade Partner | Stage 03 - GF - Penetrations | 1 | 0 | 0 | NA | APPROVED | 2026-02-10 | WF-004200 |  | 2026-02-27 |  |  |  | 2026-02-17 | KPTG-TRANSMIT-013021 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-10 | Nilsen3-TRANSMIT-000024 | NA | Trade Partner | Nilsen Sample Submission #2 | 0 | 3 | 0 | NA | APPROVED | 2026-02-10 | WF-004201 |  | 2026-03-03 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-09 | SKS Tech-TRANSMIT-000148 | NA | Trade Partner | HV Cable Sizing Report | 0 | 1 | 0 | NA | REJECTED | [5 empty] | QA Error - KPTG-IntCorr-000978 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-04 | SC-TRANSMIT-000030 | NA | Trade Partner | IFC DRAWING, Transmitted to Trade partners and Consultants | 26 | 0 | 0 | NA | APPROVED | [9 empty] | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-09 | KETE-TRANSMIT-000036 | NA | Trade Partner | Calculation report for steel frame | 0 | 1 | 0 | NA | APPROVED | 2026-02-09 | NA | 958 | 2026-02-12 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-003009 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-10 | Altaire-TRANSMIT-000076 Altaire-TRANSMIT-000075 | NA | Trade Partner | Re: NEXTDC M3S4 - Dry Fire MASDS Calculations (For Approval) (1) | 0 | 1 | 0 | NA | APPROVED | 2026-02-10 | WF-004203 |  | 2026-03-03 |  |  |  | 2026-02-16 | KPTG-TRANSMIT-012955 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-10 | Tradetec-TRANSMIT-000027 | NA | Trade Partner | Bell Mouths & Mastic Sealant Technical Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-02-10 | WF-000224 | NA | 2026-02-17 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-001108 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-05 | INGEN3D-TRANSMIT-000004 | NA | Trade Partner | Precast Columns - New IFA (04-02-2026) | 10 | 0 | 0 | NA | REJECTED | [5 empty] | QA Error - KPTG-SADV-000608 |  | 2026-02-05 | KPTG-SADV-000608 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-05 | Civilex-TRANSMIT-000026 | NA | Trade Partner | Micropile Casing Spec | 0 | 1 | 0 | Approval from Enzo - KPTG-IntCorr-000298 | APPROVED | [5 empty] | No review needed - KPTG-IntCorr-000310 |  | 2026-02-09 | KPTG-SADV-000634 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-05 | Msg from Jerrad | NA | Client | SYM-ST-TEC-001, KPTG-ST-SMP-001, KPTG-ST-SMP-002 - CONCRETE AND PILING MIX DESIGN | 0 | 3 | 0 | NA | APPROVED | 2026-02-05 | WF-000157 | NA | 2026-02-09 |  | Terminated | 2026-02-25 |  | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-06 | RDSBIM-TRANSMIT-000015 | NA | Trade Partner | LEVEL 01 CONCRETE PROFILE PLAN AND COMPLETENESS MEASURES | 1 | 0 | 0 | NA | REJECTED | [5 empty] | QA Error - KPTG-SADV-000626 |  | 2026-02-09 | KPTG-SADV-000626 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-10 | SMEPS-TRANSMIT-000172 | NA | Trade Partner | M3 Stage 3 - Ground Floor Earthing Welding Design | 0 | 1 | 0 | NA | APPROVED | 2026-02-10 | WF-004205 |  | 2026-02-13 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-10 | SMEPS-TRANSMIT-000171 | NA | Trade Partner | M3 Stage 3 - Precast Wall Bonding Shop Drawings - FOA-2 | 4 | 0 | 0 | NA | APPROVED | 2026-02-10 | WF-004206 | NA | 2026-02-26 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-013567 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-04 | CLADC-TRANSMIT-000010 | NA | Trade Partner | Tech data for approval - sika fire caulk | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document Number and Title of a TEC is incorrect, requested to resubmit |  | 2025-12-04 | KPTG-SADV-002997 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-09 | PCForm-TRANSMIT-000059 | NA | Trade Partner | Raft 3 Concrete Envolope IFC trasmittal | 1 | 0 | 0 | NA | REJECTED | [5 empty] | RE-ISSUED TRN # 60 |  | 2026-02-09 | PCForm-TRANSMIT-000060 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-09 | PCForm-TRANSMIT-000060 | NA | Trade Partner | Raft 3 concrete envelope IFC | 1 | 0 | 0 | NA | REJECTED | [5 empty] | QA Error - KPTG-SADV-000637 |  | 2026-02-09 | KPTG-SADV-000637 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-10 | ASV-TRANSMIT-000012 | NA | Trade Partner | Finalized Hydraulic Crane Shop Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-02-10 | NA | 269 | 2026-02-17 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-000921 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-10 | Tradetec-TRANSMIT-000351 | NA | Trade Partner | IFC - Stage 4 - CP36 | 1 | 0 | 0 | NA | APPROVED | 2026-02-10 | NA | 2015 | 2026-02-17 |  |  |  | 2026-02-11 | KPTG-TRANSMIT-012687 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-09 | Highbu-TRANSMIT-000040 | NA | Trade Partner | Revised GF Drainage [C] | 1 | 0 | 0 | NA | APPROVED | 2026-02-10 | NA | 545 | 2026-02-16 |  |  | 2026-02-10 | 2026-02-10 | KPTG-SADV-002982 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-10 | NXT-TRANSMIT-001267 | NA | Trade Partner | Secondary drawings for M3-22-HVSB-R for construction | 1 | 0 | 0 | NA | APPROVED | 2026-02-10 | WF-004211 | NA | 2026-02-23 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-013965 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-11-17 | WilsonPD-TRANSMIT-000128 | SPARK-CRFI-KPG-000510 & SPARK-CRFI-KPG-000511 | Trade Partner | Hydraulic Services - Level 1 - Zone A, B, C & D - Drainage & Penetration Layouts | 8 | 0 | 0 | NA | APPROVED | [7 empty] | 2026-02-10 | NA | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-27 | BLUESF-TRANSMIT-000039 | N/A | Trade Partner | S11 Precast - Level 1 (Pour 3) - ADDITIONAL DRAWINGS | 4 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000202 |  | 2026-02-10 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-001459 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-10 | KPTG-TRANSMIT-012634 | NA | Trade Partner | New Workflow VT S4 | 7 | 0 | 0 | NA | APPROVED | 2026-02-10 | (WF-004204) |  | 2026-02-20 |  |  |  | 2026-02-20 | The workflow has been terminated and reinitiated. | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-04 | ECBS-TRANSMIT-000037 | NA | Trade Partner | Revise as per Commented | 0 | 8 | 0 | NA | REJECTED | [5 empty] | Document Number of all Tech data are incorrect, requested to resubmit |  | 2025-12-04 | KPTG-SADV-002998 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-10 | Auscool-TRANSMIT-000073 | NA | Trade Partner | BMS Functional Description For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-02-10 | WF-000598 | NA | 2026-02-12 |  |  |  | 2026-02-18 | KPTG-TRANSMIT-001846 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-10 | IVS-TRANSMIT-000329 | NA | Consultant | Eaves Gutter & Office Steelwork Construction Issue | 2 | 0 | 0 | NA | APPROVED | 2026-02-10 | NA | 2017 | 2026-02-12 |  |  |  | 2026-02-16 | KPTG-TRANSMIT-012930 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-10 | LTEPRCST-TRANSMIT-000145 | NA | Trade Partner | NEXRDC STAGE 04 - CORE 01-09 LIDS IFC | 8 | 0 | 0 | NA | APPROVED | 2026-02-10 | WF-004216 |  | 2026-02-17 |  |  |  | 2026-02-19 | KPTG-TRANSMIT-013160 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-10 | DI-TRANSMIT-000140 | NA | Trade Partner | Updated HFF signage schedule | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | signage schedule |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-10 | Auspan-TRANSMIT-000071 | NA | Trade Partner | Precast Column Details | 21 | 0 | 0 | NA | APPROVED | 2026-02-10 | WF-000180 | 319 | 2026-02-18 |  | Void review and circulate to all |  | 2026-02-12 | KPTG-TRANSMIT-000591 | Closed | 21 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-10 | Auspan-TRANSMIT-000073 | NA | Trade Partner | Precast shop drawings for approval. Basement | 16 | 0 | 0 | NA | APPROVED | 2026-02-10 | WF-000181 | 321 | 2026-02-18 |  |  |  | 2026-02-13 | KPTG-TRANSMIT-000608 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-10 | Auspan-TRANSMIT-000074 | NA | Trade Partner | Precast shop drawings for approval. Ground floor zone 4 | 62 | 0 | 0 | NA | APPROVED | 2026-02-10 | WF-000182 | 323 | 2026-02-18 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-000673 | Closed | 62 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-10 | JCBa-TRANSMIT-000054 | NA | Consultant | Updated Architectural Documentation | 20 | 0 | 0 | NA | APPROVED | 2026-02-10 | WF-000184 | 327 | 2026-02-13 |  |  |  | 2026-02-12 | KPTG-TRANSMIT-000604 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-10 | RDSBIM-TRANSMIT-000019 | NA | Trade Partner | GREYSTAR FORMATION LEVEL LAYOUT | 8 | 0 | 0 | NA | APPROVED | 2026-02-10 | WF-000183 | 325 | 2026-02-18 |  | ACC Review Voided as drawings updated. |  | 2026-02-12 | NA | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-04 | Auscool-TRANSMIT-000054 | NA | Trade Partner | Level 9 - 27 Builders Works | 19 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Drawings, instructed to transmit to trade partners, consultant and client |  | 2025-12-04 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-10 | LVPG-TRANSMIT-000012 | N/A | Trade Partner | Tech Data Submittals | 0 | 2 | 0 | NA | APPROVED | 2026-02-10 | WF-000185 ¦ WF-000186 | NA | 2026-02-18 |  |  |  | 2026-02-17 | KPTG-TRANSMIT-000631 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-10 | OveArup-TRANSMIT-000158 | NA | Trade Partner | M3 Stage 3 Jemena Interface Panel Updates incl cable schedule | 11 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-10 | IVS-TRANSMIT-000330 | NA | Consultant | Stage 4 - Chemical Store & Fire Room Certification Issue (revised as clouded) | 2 | 0 | 0 | NA | APPROVED | 2026-02-10 | NA | 2020 | 2026-02-13 |  |  |  | 2026-02-16 | KPTG-TRANSMIT-012960 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-10 | NXT-TRANSMIT-001268 | NA | Consultant | EAE Busduct (5000A / 2000A) – Flange Connection Shop Drawing | 9 | 0 | 0 | NA | APPROVED | 2026-02-10 | WF-004222 |  | 2026-02-23 |  |  |  | 2026-02-11 | KPTG-TRANSMIT-012680 | Closed | 9 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-09 | ACG-TRANSMIT-000045 | NA | Trade Partner | M3 - S2 Samples IFA revision | 0 | 3 | 0 | NA | APPROVED | 2026-02-09 | WF-004186 | NA | 2026-02-16 |  | KPTG-TRANSMIT-014436 2 Doc 3/16/2026 KPTG-TRANSMIT-014487 1 Doc 3/17/2026 | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-014487 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-10 | HDRAus-TRANSMIT-000386 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 6 | 0 | 0 | NA | APPROVED | 2026-02-10 | NA | 2022 | 2026-02-12 |  |  |  | 2026-02-11 | KPTG-TRANSMIT-012718 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-09 | ARCST-TRANSMIT-000203 | NA | Trade Partner | Ground Floor Stairs - IFC Drawings | 66 | 0 | 0 | NA | APPROVED | 2026-02-09 | WF-004191 | NA | 2026-02-16 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-016630 | Closed | 66 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-09 | Tradetec-TRANSMIT-000348 | NA | Trade Partner | Bitac TD - Stage 2 - Rev 3 | 0 | 1 | 0 | NA | APPROVED | 2026-02-09 | WF-004184 | NA | 2026-02-10 |  | Terminated the workflow | 2026-02-10 |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-09 | ARCST-TRANSMIT-000205 | NA | Trade Partner | Stage 2 - Lower Ground Stairs | 45 | 0 | 0 | NA | APPROVED | 2026-02-09 | WF-004193 | NA | 2026-02-16 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-017061 | Closed | 45 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-04 | ACG-TRANSMIT-000039 | NA | Trade Partner | M2 - DH11 - ACG Hand over documentation | 16 | 1 | 0 | NA | REJECTED | [5 empty] | Transmittal rejected for incorrect drawing number (KPTG-SADV-001450) |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-09 | D&E-TRANSMIT-000386 | NA | Trade Partner | Functional Description - Issued for Review | 0 | 1 | 0 | NA | APPROVED | 2026-02-10 | WF-004210 | NA | 2026-02-24 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-013339 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-10 | TTW-TRANSMIT-000156 | NA | Consultant | M3 Stage 2 Civil Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-02-10 | NA | 3785 | 2026-02-12 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-10 | Tradetec-TRANSMIT-000349 | NA | Trade Partner | IFC - D05-01 - Stage 2 | 1 | 0 | 0 | NA | APPROVED | 2026-02-10 | NA | 3789 | 2026-02-12 |  |  | 2026-02-10 | 2026-02-11 | KPTG-TRANSMIT-012710 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-10 | Tradetec-TRANSMIT-000350 | NA | Trade Partner | IFC - Stage 2 - CP14, LVP18, LVP21 | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Multiple issues |  | 2026-02-10 | KPTG-DA-004751 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-10 | Tradetec-TRANSMIT-000352 | NA | Trade Partner | Tech Data - Stage 2 - Bitac - Rev 4 | 0 | 1 | 0 | NA | APPROVED | 2026-02-10 | WF-004215 | NA | 2026-02-13 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-10 | D&E-TRANSMIT-000388 | NA | Trade Partner | Stage 2 Office Technical Data - Issued for Approval | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Document numbers inside and outside are wrong |  | 2026-02-10 | KPTG-DA-004750 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-10 | DI-TRANSMIT-000139 | NA | Consultant | Airlock Update | 6 | 0 | 0 | NA | APPROVED | 2026-02-10 | NA | 289 | 2026-02-12 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-10 | Tradetec-TRANSMIT-000354 | NA | Trade Partner | IFC - Penstocks - Stage 2 and 4 | 4 | 0 | 0 | NA | APPROVED | 2026-02-10 | NA | 3791 | 2026-02-17 |  |  | 2026-02-11 | 2026-02-17 | KPTG-TRANSMIT-013029 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-10 | KAPITOL-TRANSMIT-001060 | NA | Trade Partner | HFF - Window Shop Drawings IFA | 20 | 0 | 0 | NA | APPROVED | 2026-02-10 | NA | 291 | 2026-02-23 |  |  |  | 2026-02-17 | KAPITOL-TRANSMIT-001096 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-10 | WGAVIC-TRANSMIT-000056 | NA | Consultant | Civil Drawings - Main Works (Exc. Drainage) - Issued for Construction | 3 | 0 | 0 | NA | APPROVED | 2026-02-10 | WF-000227 | NA | 2026-02-17 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-001155 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-02 | ECBS-TRANSMIT-000033 | NA | Trade Partner | Revised tach data for AM41 for review | 0 | 1 | 0 | NA | REJECTED | [5 empty] | As per the Kapitol Advice, requested to resubmit |  | 2025-12-02 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-10 | BLUESF-TRANSMIT-000048 | NA | Trade Partner | S11 Precast - Ground level (Revised Columns) - IFA | 9 | 0 | 0 | NA | APPROVED | 2026-02-10 | WF-000226 | NA | 2026-02-17 |  |  | 2026-02-26 | 2026-03-01 | KPTG-TRANSMIT-001092 | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-10 | VIA Arch-TRANSMIT-000054 | NA | Consultant | Update Site plan with Stage 12 perimeter RLs | 1 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-DA-001100 |  | 2026-02-10 | KPTG-DA-001100 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-10 | GPSElec-TRANSMIT-000004 | NA | Trade Partner | NextDC Stage 9-12 switchboard - MSB-XX-1 drawings - IFR | 29 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings to be revised, KPTG-SADV-001055 |  | 2026-02-10 | KPTG-SADV-001055 | Closed | 29 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-10 | GPSElec-TRANSMIT-000005 | NA | Trade Partner | NextDC Stage 9-12 switchboard - MSB-XX-2 drawings - IFR | 51 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings to be revised, KPTG-SADV-001056 |  | 2026-02-10 | KPTG-SADV-001056 | Closed | 51 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-10 | D&E-TRANSMIT-000105 | SPARK-CRFI-KPG-000466 | Trade Partner | MWYCCB - LEVEL 1 - DUCTWORK LAYOUT ZONES + ROOF & SOUTH SECTIONS & DETAILS - Issued For Review | 4 | 0 | 0 | NA | APPROVED | 2026-02-10 | WF-000176 | 116 | 2026-02-17 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000518 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-10 | BASESG-IntCorr-000083 | NA | Trade Partner | Industrial Water System ITP | 0 | 1 | 0 | NA | APPROVED | 2026-02-10 | WF-000934 | NA | 2026-02-17 |  |  | 2026-02-13 | 2026-02-13 | KPTG-TRANSMIT-002554 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-10 | PARR-TRANSMIT-000055 | NA | Trade Partner | P2645 - KPG NDC M3 S1 DH7&8 - Fuel - KELAIR TRANSFER and RECIRCULATION PUMP | 0 | 2 | 0 | KPTG-IntCorr-002761 | APPROVED | 2026-02-18 | WF-000945 | NA | 2026-02-25 |  |  | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-002809 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-10 | D&E-TRANSMIT-000332 | NA | Trade Partner | Mantrap Technical Data - Issued for Review | 0 | 2 | 0 | NA | APPROVED | 2026-02-10 | Wf-000933 | NA | 2026-02-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-10 | D&E-TRANSMIT-000333 | NA | Trade Partner | Fire matrix - updated PDF | 0 | 2 | 0 | KPTG-IntCorr-002758 | APPROVED |  | NA | NA |  |  | IFC-distribution Only |  | 2026-02-11 | KPTG-TRANSMIT-002488 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-10 | HGP-TRANSMIT-000038 | SPARK-CRFI-KPG-000153 | Trade Partner | Transmittal-Curtain wall FT01 Shop Drawings | 91 | 0 | 0 | NA | APPROVED | 2026-02-10 | WF-000177 | 117 | 2026-02-17 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-001313 | Closed | 91 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-10-30 | NXES-TRANSMIT-000034 | NA | Trade Partner | Nexus: Lighting Tech Data Rev 2 | 0 | 41 | 0 | NA | APPROVED | 2025-11-06 | WF-000450 | NA | 2025-11-11 |  |  | 2025-12-04 | 2025-12-05 | KPTG-TRANSMIT-001450 | Closed | 41 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-10 | PROLMC-TRANSMIT-000008 |  | Trade Partner | Proline Louvre Shop drawings (10-2-26) | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Error in document number |  |  | KPTG-TRANSMIT-000425 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-10 | M.S.-TRANSMIT-000050 | NA | Trade Partner | Updated IFC shop drawings for J62, J64 & J63 | 7 | 0 | 0 | NA | REJECTED | [5 empty] | REVISION HISTORY OF TWO DRAWINGS ARE MISMATCHED, REQUESTED TO RESUBMIT |  | 2026-02-10 | KPTG-SADV-003660 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-10 | M.S.-TRANSMIT-000051 | NA | Trade Partner | Updated IFC shop drawing for J61 | 1 | 0 | 0 | NA | APPROVED | [5 empty] | IFC DRAWIN, TRANSMITTED TO TRADE AND CONSULTANTS |  | 2026-02-10 |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-10 | M.S.-TRANSMIT-000052 | NA | Trade Partner | Updated IFC shop drawing for J65 | 1 | 0 | 0 | NA | APPROVED | [5 empty] | IFC DRAWING, TRANSMITTED TO TRADE & CONSULTANTS |  | 2026-02-10 |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-10 | M.S.-TRANSMIT-000053 | NA | Trade Partner | IFC J63 & J64 | 5 | 0 | 0 | NA | APPROVED | [5 empty] | IFC DRAWING TRANSMITTED TO TRADE & CONSULTANTS |  | 2026-02-10 |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-10 | M.S.-TRANSMIT-000054 | NA | Trade Partner | Shop drawing Register | 0 | 1 | 0 | NA | APPROVED | [5 empty] | ISSUED FOR INFORMATION, TRANSMITTED TO TRADE & CONSULTANTS |  | 2026-02-10 |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-10 | M.S.-TRANSMIT-000055 | NA | Trade Partner | JS02 Sample Issued for Information | 0 | 1 | 0 | NA | APPROVED | 2026-02-12 | WF-000824 | NA | 2026-02-17 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-002489 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-10 | KPTG-IntCorr-004784 | NA | Trade Partner | Re: EHS - Roof Stair Shop Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-02-10 |  | 435 | 2026-02-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-10 | RDSBIM-TRANSMIT-000109 | NA | Trade Partner | MLCSPR ¦ OUTDOOR COURT LEVEL 02 CONCRETE PROFILE PLAN SHEET 6 | 1 | 0 | 0 | NA | APPROVED | [5 empty] | KEEP PENDING FOR CONFIRMATION |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-28 | BLUESF-TRANSMIT-000041 | NA | Trade Partner | S11 Precast - Level 1 (GA) - IFA | 13 | 0 | 0 | NA | APPROVED | [5 empty] | Not to be reviewed, updated register. |  | 2026-01-28 | NA | Closed | 13 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2025-12-04 | D&E-TRANSMIT-000024 | NA | Trade Partner | NextDC M3 DHA6 OM Manual draft IFA | 0 | 1 | 0 | NA | APPROVED | 2025-12-04 | WF-000169 |  | 2025-12-10 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-30 | BLUESF-TRANSMIT-000042 | NA | Trade Partner | S11 Precast - Ground Floor (Updated MP's) | 7 | 0 | 0 | NA | APPROVED |  | NA |  |  |  | Not to be reviewed, updated register. |  | 2026-02-03 | NA | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-01-30 | BLUESF-TRANSMIT-000045 | NA | Trade Partner | S11 Precast - Level 1 (Updated MP's) | 7 | 0 | 0 | NA | APPROVED |  | NA |  |  |  | Not to be reviewed, Updated register. |  | 2026-01-30 | NA | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-10 | BLUESF-TRANSMIT-000047 | NA | Trade Partner | S11 Precast - Ground Floor (Revised GA) - Re-IFA | 8 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Not to be reviewed, updated register |  | 2026-02-10 | NA | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-10 | Auspan-TRANSMIT-000083 | NA | Trade Partner | Pack 2 of IFC shop drawings. | 38 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFCs No review required |  | 2026-02-10 | NA | Closed | 38 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-06 | Auspan-TRANSMIT-000084 | N/A | Trade Partner | Resubmit precast shop drawings for approval. Stage 9 ground floor | 11 | 0 | 0 | N/A | APPROVED |  | N/A | N/A |  |  | No review required. |  | 2026-02-09 | NA | Closed | 11 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-07 | Auspan-TRANSMIT-000085 | N/A | Trade Partner | Replacement of Precast Panel 259 with Blockwork - Stage 9 GF | 1 | 0 | 0 | N/A | REJECTED | [5 empty] | KPTG-SADV-001009 |  | 2026-02-09 | KPTG-SADV-001009 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-28 | NXT-TRANSMIT-001227 | NA | Trade Partner | Fwd: EAE Busduct (5000A / 2000A) – Flange Connection Shop Drawing | 2 | 0 | 0 | NA | APPROVED | 2026-01-28 | WF-004003 |  | 2026-02-02 |  |  |  | 2026-02-11 | KPTG-TRANSMIT-012666 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-11 | vdmcons-TRANSMIT-000017 | NA | Trade Partner | D12 Me Stage 3 GIS Building - Shop Drawings & 3D IFC Model - M3 Stage 3 Switchroom - Grating - Modified - Re-IFF - 2026-02-11 | 19 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | The register has been updated. If any further action is required, the coordinator will inform. - KPTG-TRANSMIT-012669 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-01 | Hames-TRANSMIT-000079 | N/A | Consultant | NEXTDC D1 Stage 2 - For Construction - Paritions | 6 | 0 | 0 | N/A | APPROVED | 2025-12-01 | N/A | 659 | 2025-12-03 |  |  | 2025-12-02 | 2025-12-03 | KPTG-TRANSMIT-002140 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-03 | BASESG-IntCorr-000030 | NA | Trade Partner | Comment Register Submission - Fuel | 0 | 2 | 0 | NA | APPROVED | 2025-12-03 | WF-000835 | NA | 2025-12-12 |  |  | 2026-01-14 | 2026-01-14 | KPTG-TRANSMIT-002285 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-11 | Highbu-TRANSMIT-000041 | NA | Trade Partner | Revised GF Drainage [D] | 1 | 0 | 0 | NA | APPROVED | 2026-02-11 | NA | 548 | 2026-02-18 |  |  | 2026-03-26 | 2026-03-26 | KPTG-SADV-003568 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-10 | CANDR-TRANSMIT-000002 |  | Trade Partner | Timber fin setout - Rev A+B | 48 | 0 | 0 | NA | APPROVED | 2026-02-11 | WF-000178 | 119 | 2026-02-18 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-01-16 | Civilex-TRANSMIT-000174 | NA | Trade Partner | Stage 3 (22KVA switch Room) - Sample Submission - D2 Base Plate HS Grout | 0 | 1 | 0 | NA | APPROVED | 2026-02-11 | WF-004225 |  | 2026-02-16 |  | As requested by Max H- The workflow reinitiated. |  | 2026-02-11 | KPTG-TRANSMIT-012703 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-11 | Baigents-TRANSMIT-000064 |  | Trade Partner | MCC - Stair Shop Drawings - IFC | 14 | 0 | 0 | NA | APPROVED | 2026-02-11 | WF-000179 | 118 | 2026-02-18 |  | Bim360 review terminated by Lawden Constructed |  | 2026-08-25 | NA | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-02 | DRLL-TRANSMIT-000065 | NA | Trade Partner | Battery Room Modules 1 & 2 Hydraulic Services - As Built Shop Drawings | 8 | 0 | 0 | KPTG-IntCorr-002596 | APPROVED |  | NA | NA |  |  | As Built Drawings-Review not Required |  | 2026-02-06 | KPTG-TRANSMIT-002505 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-11 | D&E-TRANSMIT-000389 | NA | Trade Partner | Stage 2 Office Technical Data - Issued for Approval | 0 | 2 | 0 | NA | APPROVED | 2026-02-11 | WF-004223 | NA | 2026-02-25 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-013507 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-11 | ECBS-TRANSMIT-000023 | NA | Trade Partner | Resubmission to include AcoustiC | 0 | 1 | 0 | NA | APPROVED | 2026-02-11 | WF-004224 | NA | 2026-03-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-11 | RDSBIM-TRANSMIT-000032 |  | Trade Partner | MWYCCB ¦ LEVEL 01 CONCRETE PROFILE PLAN | 5 | 0 | 0 | NA | REJECTED | [5 empty] | As per Lawden's advise - KPTG-TRANSMIT-000427 |  | 2026-02-11 | KPTG-TRANSMIT-000427 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-09 | D&E-TRANSMIT-000384 | NA | Trade Partner | MCC L2 Cx Script - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-02-11 | KPTG-TRANSMIT-012702 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-11 | ZIA-TRANSMIT-000054 | NA | Trade Partner | Re: Zi-Argus SD & Procurements | 4 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-02-11 | KPTG-TRANSMIT-012704 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-03 | BASESG-IntCorr-000030 | NA | Trade Partner | Comment Register Submission - Fire | 0 | 2 | 0 | NA | APPROVED | 2025-12-03 | WF-000836 | NA | 2025-12-12 |  |  | 2026-01-14 | 2026-01-14 | KPTG-TRANSMIT-002283 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-08-27 | SMEPS-TRANSMIT-000009 |  | Trade Partner | Issued for approval- Shop Drawings CONTAINMENT | 26 | 0 | 0 | NA | APPROVED | 2026-02-11 | WF-000180 | [5 empty] | 2026-02-11 | KPTG-TRANSMIT-000426 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-11 | Bianco-TRANSMIT-000047 | NA | Trade Partner | Ground Level IFA Shop Drawings | 27 | 0 | 0 | NA | APPROVED | 2026-02-11 | WF-004227 |  | 2026-03-10 |  |  |  | 2026-02-23 | KPTG-TRANSMIT-013329 | Closed | 27 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-11 | fjc-TRANSMIT-000132 | NA | Consultant | Re: GF Design Change Update - additional GF entry swing door pit for auto operator - URGENT actions | 1 | 0 | 0 | NA | APPROVED | 2026-02-11 | NA | 549 | 2026-02-16 |  |  | 2026-02-12 | 2026-02-12 | KPTG-SADV-003021 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-11 | D&E-TRANSMIT-000390 | NA | Trade Partner | SFN Pipework Material - 304SS tube - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-02-11 | WF-004228 |  | 2026-03-04 |  |  |  | 2026-02-12 | As per Mr. Zak, it is not required to go into WF. | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-11 | NXT-TRANSMIT-001273 | NA | Trade Partner | Supervault Generic Tank Hold Down Information | 1 | 0 | 0 | NA | APPROVED | 2026-02-11 | WF-004229 |  | 2026-02-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-11 | 4DW-TRANSMIT-000083 | NA | Consultant | Wall Updates | 2 | 0 | 0 | NA | APPROVED | 2026-02-13 | NA | 558 | 2026-02-19 |  |  | 2026-02-16 | 2026-02-16 | KPTG-SADV-003049 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-11 | NXT-TRANSMIT-001272 | NA | Consultant | Revised GA drawing for review + Tech data as IFC submission | 4 | 0 | 0 | NA | APPROVED | 2026-02-11 | WF-004231 |  | 2026-02-24 |  |  |  | 2026-02-12 | KPTG-TRANSMIT-012766 KPTG-TRANSMIT-012897 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-11 | SMEPS-TRANSMIT-000108 | SPARK-CRFI-KPG-000359 | Trade Partner | MDB-01 (A) Shop drawings for approval | 0 | 1 | 0 | NA | APPROVED | 2026-02-11 | WF-000181 | NA | 2026-02-18 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000484 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-11 | SMEPS-TRANSMIT-000109 | SPARK-CRFI-KPG-000359 | Trade Partner | MDB-02 (B) Shop drawings for approval | 0 | 1 | 0 | NA | APPROVED | 2026-02-11 | WF-000182 | NA | 2026-02-18 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000485 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-03 | BASESG-IntCorr-000030 | NA | Trade Partner | Comment Register Submission - SME | 0 | 1 | 0 | NA | APPROVED | 2025-12-03 | WF-000837 | NA | 2025-12-12 |  |  | 2026-01-14 | 2026-01-14 | KPTG-TRANSMIT-002276 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-11 | SMEPS-TRANSMIT-000110 | SPARK-CRFI-KPG-000359 | Trade Partner | DB-01 (G) Shop drawings for approval | 0 | 1 | 0 | NA | APPROVED | 2026-02-11 | WF-000183 | NA | 2026-02-18 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000486 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-11 | SMEPS-TRANSMIT-000111 | SPARK-CRFI-KPG-000359 | Trade Partner | DB-08 (A) shop drawings for approval | 0 | 1 | 0 | NA | APPROVED | 2026-02-11 | WF-000184 | NA | 2026-02-18 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000487 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-11 | DI-TRANSMIT-000141 | NA | Trade Partner | Fwd: HFF Door Hardware Schedule | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-11 | SMEPS-TRANSMIT-000112 | SPARK-CRFI-KPG-000359 | Trade Partner | DB-09 (B) shop drawing for approval | 0 | 1 | 0 | NA | APPROVED | 2026-02-11 | WF-000185 | NA | 2026-02-18 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000488 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-11 | SMEPS-TRANSMIT-000113 | SPARK-CRFI-KPG-000359 | Trade Partner | DB-18 (B) shop drawing for approval | 0 | 1 | 0 | NA | APPROVED | 2026-02-11 | WF-000186 | NA | 2026-02-18 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000489 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-11-03 | INGEN3D-TRANSMIT-000665 | NA | Trade Partner | I3D-378 Next DC M3 Stage 4 - Level 1 (Zone 10 & 12) - Cast in Dowels - IFC (03-11-2025) | 10 | 0 | 0 | NA | APPROVED | 2025-11-03 | 003206 |  | 2026-02-11 |  |  |  | 2026-02-11 | KPTG-TRANSMIT-012717 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-11 | B Smart-TRANSMIT-000053 | NA | Consultant | GF- L02 - A04 Draft IFC | 3 | 0 | 0 | NA | APPROVED | 2026-02-11 | NA | 260 | 2026-02-13 |  | Review void as advised by Kapitol PC. Updated drawings to be issued. |  | 2026-03-12 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-11 | B Smart-TRANSMIT-000054 | NA | Consultant | A08 - IFC | 13 | 0 | 0 | NA | APPROVED | 2026-02-11 | NA | 262 | 2026-02-13 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-000597 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-11 | Tradetec-TRANSMIT-000355 | NA | Trade Partner | Tech Data - Soilworx - Thermal Sand | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document number inside and outside is wrong. |  | 2026-02-11 | KPTG-DA-004793 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-11 | Auspan-TRANSMIT-000076 | NA | Trade Partner | Precast shop drawings for approval. Ground floor. | 73 | 0 | 0 | NA | APPROVED | 2026-02-11 | WF-000187 | 329 | 2026-02-18 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-000674 | Closed | 73 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-03 | BASESG-IntCorr-000030 | NA | Trade Partner | Comment Register Submission - NEXTDC M3-1 UPS L3 | 0 | 1 | 0 | NA | APPROVED | 2025-12-03 | WF-000838 | NA | 2025-12-12 |  |  | 2026-01-14 | 2026-01-14 | KPTG-TRANSMIT-002281 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-11 | StantecA-TRANSMIT-000300 | NA | Consultant | IFC Documents - Fire Protection - Stantec | 45 | 0 | 0 | NA | APPROVED | 2026-02-11 | WF-000188 | 331 | 2026-02-13 |  |  |  | 2026-02-13 | KPTG-TRANSMIT-000617 | Closed | 45 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-11 | POTTSENG-TRANSMIT-000008 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONES 3-5 LAYOUT | 3 | 0 | 0 | NA | APPROVED | 2026-02-11 | NA | 334 | 2026-02-18 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-000581 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-09 | ECBS-TRANSMIT-000069 | NA | Trade Partner | Resubmssion for Ripplesound Two Way Exposed Seismic Ceiling Grid System and Details | 5 | 0 | 0 | NA | APPROVED | 2026-02-09 | NA | 432 | 2026-02-16 |  |  | 2026-03-13 | 2026-03-13 | KPTG-SADV-003862 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-11 | PFP PL-TRANSMIT-000064 | NA | Trade Partner | Cx L2 & L3 scripts for construction | 0 | 8 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-02-11 | KPTG-TRANSMIT-012705 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-11 | LVPG-TRANSMIT-000015 | NA | Trade Partner | LVPG - GIT Tech Data Submittals | 0 | 2 | 0 | NA | APPROVED | 2026-02-11 | WF-000191 | NA | 2026-02-16 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-000697 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-11 | LVPG-TRANSMIT-000016 | NA | Trade Partner | LVPG Tech Data - Fire Tank Drainage Pumpstation | 0 | 1 | 0 | NA | APPROVED | 2026-02-11 | WF-000192 | NA | 2026-02-16 |  |  |  | 2026-02-17 | KPTG-TRANSMIT-000632 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-11 | Fyfe-TRANSMIT-000011 | NA | Consultant | Civil (Building Set) - Issued for Construction | 8 | 0 | 0 | NA | APPROVED | 2026-02-11 | WF-000193 | 336 | 2026-02-13 |  |  |  | 2026-02-18 | KPTG-TRANSMIT-000646 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-11 | HDRAus-TRANSMIT-000387 | NA | Consultant | Site Wide - Architectural Documentation - Finishes Schedules | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Document number in the register is not as per the project standards. |  | 2026-02-11 | KPTG-DA-004794 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-09 | Normark-TRANSMIT-000045 | NA | Trade Partner | Samples information - Soft Landscape- SP05 Revised sample sheet | 0 | 1 | 0 | NA | APPROVED | 2026-02-09 | WF-000807 |  | 2026-02-12 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-002345 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-09 | Syfon1-TRANSMIT-000023 | NA | Trade Partner | Revied Syfon Drawings re-issued | 3 | 0 | 0 | NA | APPROVED | 2026-02-09 |  |  |  |  | IFC DRAWINGS, TRANSMITTED TO TRADE AND CONSULTANTS |  | 2026-02-09 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-05 | ARCST-TRANSMIT-000144 | NA | Trade Partner | Stage 4 C1 Switchroom - Stage 1 Issued for Approval | 77 | 0 | 0 | NA | APPROVED | 2025-12-05 | WF-003513 | NA | 2025-12-26 |  | The workflow has been terminated as reuested by Kap New transmittal - ARCST-TRANSMIT-000158 |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-11 | HDRAus-TRANSMIT-000388 | NA | Consultant | Stage 2 - Architectural Documentation - ACC Comments | 7 | 0 | 0 | NA | APPROVED | 2026-02-11 | NA | 3794 | 2026-02-13 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-013240 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-11 | KPTG-IntCorr-009203 | NA | Consultant | URGENT: Upload & Transmit Documents | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-02-11 | KPTG-TRANSMIT-012706 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-07 | ECBS-TRANSMIT-000067 | NA | Trade Partner | Revise as per Comments | 1 | 0 | 0 | NA | APPROVED | 2026-02-09 |  | 428 | 2026-02-13 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-07 | ECBS-TRANSMIT-000068 | NA | Trade Partner | Submission Tech Data for Arch Beads and PVC L Beads | 0 | 1 | 0 | NA | APPROVED | 2026-02-09 | WF-00080 | NA | 2026-02-12 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-002492 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-07 | RDSBIM-TRANSMIT-000106 | NA | Trade Partner | MLCSPR ¦ AQUATIC CENTER LEVEL 01 HOB LAYOUT PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-02-09 |  | 429 | 2026-02-14 |  |  | 2026-02-24 | 2026-02-24 | KPTG-SADV-003760 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-07 | RDSBIM-TRANSMIT-000107 | NA | Trade Partner | MLC ¦ AQUATIC CENTER LEVEL 01 WALL PANELING PLAN & ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-02-09 | NA | 430 | 2026-02-14 |  |  | 2026-03-13 | 2026-03-13 | KPTG-SADV-003867 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-07 | RDSBIM-TRANSMIT-000108 | NA | Trade Partner | MLCSPR ¦ AQUATIC CENTER LEVEL 01 INTERNAL SCREED LAYOUT | 6 | 0 | 0 | NA | APPROVED | 2026-02-09 | NA | 431 | 2026-02-16 |  |  | 2026-03-11 | 2026-03-11 | KPTG-SADV-003837 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-10 | RDSBIM-TRANSMIT-000016 | NA | Trade Partner | LEVEL 05 CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | REJECTED | [5 empty] | QA Error - KPTG-SADV-000665 |  | 2026-02-11 | KPTG-SADV-000665 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-10 | INGEN3D-TRANSMIT-000005 | NA | Trade Partner | Level 3 - Precast Columns & Cast in Dowels - IFA | 73 | 0 | 0 | NA | REJECTED | 2026-02-12 | WF-000162 | NA | 2026-02-17 |  | QA Error - KPTG-SADV-000652 - SUBMISSION REQUESTED VIA - KPTG-IntCorr-000332 - 65 DRAWINGS ONLY | 2026-03-02 | 2026-03-02 | WF-000196 TO RDS | Closed | 65 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-10 | Civilex-TRANSMIT-000027 | NA | Trade Partner | Crane Pile Design | 0 | 1 | 0 | KPTG-IntCorr-000322 | APPROVED | 2026-02-12 | WF-000163 | NA | 2026-02-17 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-000560 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-05 | RDSBIM-TRANSMIT-000122 | NA | Trade Partner | LEVEL 06 RCP PLAN AND LAYOUT | 10 | 0 | 0 | NA | APPROVED | 2025-12-05 | WF - 000789 | 494 | 2025-12-12 |  |  | 2025-12-15 | 2025-12-15 | KPTG-DA-002260 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-11 | ASV-TRANSMIT-000013 | N/A | Trade Partner | Hydraulic Internal Shop Drawings Rev2 | 6 | 0 | 0 | N/A | APPROVED | 2026-02-11 | N/A | 276 | 2026-02-18 |  |  |  | 2026-02-17 | KPTG-TRANSMIT-000856 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-10 | WAM-TRANSMIT-000710 | NA | Consultant | Prototype Package Update | 10 | 0 | 0 | No action - dwgs are already issued via Trn 706, 709 | REJECTED | [5 empty] | No action - dwgs are already issued via Trn 706, 709 |  | 2026-02-12 | KPTG-IntCorr-000330 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-10 | Resonate-TRANSMIT-000008 | NA | Consultant | Facade acoustic requirements document | 0 | 1 | 0 | NA | APPROVED | 2026-02-10 | WF-000159 | NA | 2026-02-12 |  |  | 2026-02-17 | 2026-02-23 | KPTG-TRANSMIT-000526 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-11 | WGAVIC-TRANSMIT-000057 | N/A | Consultant | Structural Drawings - No Longer in Use - Issued for Information | 7 | 0 | 0 | N/A | APPROVED |  | N/A | N/A |  |  | No Longer in Use |  | 2026-02-11 | N/A | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-11 | PCForm-TRANSMIT-000070 | N/A | Trade Partner | NEXTDC - Stage 9 drawings | 3 | 0 | 0 | KPTG-IntCorr-000408 | APPROVED |  | NA | NA |  |  | Review not required as confirmed by Kapitol |  | 2026-03-03 | NA | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-11 | AXIS-NSW-TRANSMIT-000002 | NA | Trade Partner | NEXT DC STAGE 2 Samples | 0 | 1 | 0 | NA | APPROVED | 2026-02-11 | WF-000229 | NA | 2026-02-18 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-001115 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-11 | Tradetec-TRANSMIT-000030 | N/A | Trade Partner | 1st Batch of Shop Drawings for Electrical and Communications Pits | 14 | 0 | 0 | N/A | REJECTED | [5 empty] | Need to revise, KPTG-SADV-001092 |  | 2026-02-11 | KPTG-SADV-001092 | Closed | 14 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-11 | D&E-TRANSMIT-000334 | NA | Trade Partner | Max Cool FD - Issued for Construction | 0 | 1 | 0 | KPTG-IntCorr-002768 | APPROVED |  | NA | NA |  |  | IFC-Distribution Only |  | 2026-02-12 | KPTG-TRANSMIT-002506 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-11 | D&E-TRANSMIT-000335 | NA | Trade Partner | SFN Monitoring panel L3 Cx Script - Issued for Review | 0 | 1 | 0 | KPTG-IntCorr-002785 | APPROVED | 2026-02-20 | WF-000949 | NA | 2026-02-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-11 | WilsonPD-TRANSMIT-000020- KPTG-TRANSMIT-002472 | NA | Trade Partner | IW Meter Setup IFC and with return comments | 0 | 1 | 0 | NA | APPROVED | 2026-02-11 | WF-000936 | NA | 2026-02-18 |  |  | 2026-02-16 | 2026-02-16 | KPTG-TRANSMIT-002557 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-05 | ccair-TRANSMIT-000071 | NA | Trade Partner | Ductwork Riser Core B - IFA | 2 | 0 | 0 | NA | APPROVED | 2025-12-05 | WF - 000790 | 495 | 2025-12-12 |  |  | 2025-12-15 | 2025-12-15 | KPTG-DA-002259 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-11 | SMEPS-TRANSMIT-000258 | NA | Trade Partner | SME- AS BUILT Submission - Typical Line Up Neutral Earthing Schematic | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As Built-Disribution Only |  | 2026-02-12 | KPTG-TRANSMIT-002500 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-11 | D&E-TRANSMIT-000336 | NA | Trade Partner | IW Tank L2 Cx Script - Issued for Review | 0 | 1 | 0 | NA | APPROVED | 2026-02-11 | Wf-000937 | NA | 2026-02-18 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-002581 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-11 | TTW-TRANSMIT-000091 | NA | Consultant | Structural Documentation - Issued for Certification | 7 | 0 | 0 | NA | APPROVED | 2026-02-11 | NA | 255 | 2026-02-13 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-000478 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-11 | PCForm-TRANSMIT-000064 | NA | Trade Partner | Tec Grout HS | 0 | 1 | 0 | NA | REJECTED | [5 empty] | QA Error - KPTG-SADV-000696 |  | 2026-02-12 | KPTG-SADV-000696 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-11 | PCForm-TRANSMIT-000065 | NA | Trade Partner | Tech data - Sample003 Chemset reo 502 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | QA Error - KPTG-SADV-000696 |  | 2026-02-12 | KPTG-SADV-000696 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-11 | PCForm-TRANSMIT-000067 | NA | Trade Partner | Aitken Freeman Tecgrout Fine | 0 | 1 | 0 | NA | REJECTED | [5 empty] | QA Error - KPTG-SADV-000696 |  | 2026-02-12 | KPTG-SADV-000696 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-11 | Civilex-TRANSMIT-000028 | NA | Trade Partner | Static Pump Design Addendum Package | 0 | 1 | 0 | KPTG-IntCorr-000331 | APPROVED | 2026-02-13 | WF-000164 | NA | 2026-02-16 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-000563 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-10 | Auspan-TRANSMIT-000086 | N/A | Trade Partner | Precast shop drawings for construction. Stage 9 ground floor. | 5 | 0 | 0 | N/A | APPROVED |  | N/A | N/A |  |  | IFC Drawings, No review required. |  | 2026-02-11 | NA | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-10 | Auspan-TRANSMIT-000087 | N/A | Trade Partner | Update panel 0G275. | 1 | 0 | 0 | N/A | APPROVED |  | N/A | N/A |  |  | IFC Drawing, No review required |  | 2026-02-11 | N/A | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-10 | Auspan-TRANSMIT-000088 | N/A | Trade Partner | Precast shop drawings for construction. Stage 9 ground floor. | 29 | 0 | 0 | N/A | APPROVED |  | N/A | N/A |  |  | IFC drawings, No review required |  | 2026-02-11 | N/A | Closed | 29 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-04 | TATE_-TRANSMIT-000030 | NA | Trade Partner | shop drawings for adjustable blanking panel | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Transmittal rejected to correct the drawing numbers (KPTG-SADV-001882) |  | 2025-12-05 | KPTG-SADV-001882 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-11 | WGAVIC-TRANSMIT-000058 | N/A | Consultant | Structural Drawings - Early Works - Issued for Construction | 7 | 0 | 0 | N/A | APPROVED | 2026-02-11 | N/A | 279 | 2026-02-18 |  |  | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-000909 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-12 | SKS Tech-TRANSMIT-000021 | NA | Trade Partner | Ground C1 Small Power | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect title - KPTG-TRANSMIT-012736 |  | 2026-02-12 | KPTG-TRANSMIT-012736 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-12 | RDSBIM-TRANSMIT-000215 | NA | Trade Partner | NXM3S4 ¦ UPPER ROOF PARTITION WALL KEY PLAN AND ELEVATION | 2 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 2036 | 2026-02-16 |  |  |  | 2026-02-23 | KPTG-TRANSMIT-013334 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-12 | ARCST-TRANSMIT-000206 | NA | Trade Partner | Re: C2 Switchroom Upper Gantry Primary Steel - IFC Shop Drawings | 185 | 0 | 0 | NA | APPROVED | [5 empty] | KPTG-TRANSMIT-012737 - INCORRECT ATTACHMENTS |  | 2026-02-12 | KPTG-TRANSMIT-012737 | Closed | 185 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-12 | RDSBIM-TRANSMIT-000152 | NA | Trade Partner | LINDRUM ¦ LEVEL 2 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 550 | 2026-02-19 |  |  | 2026-03-06 | 2026-03-06 | KPTG-SADV-003335 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-12 | RDSBIM-TRANSMIT-000153 | NA | Trade Partner | LINDRUM ¦ LEVEL 03 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 551 | 2026-02-19 |  |  | 2026-03-05 | 2026-03-06 | KPTG-SADV-003336 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-12 | SKS Tech-TRANSMIT-000022 | NA | Trade Partner | Ground Floor Power C1 revised | 1 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 2038 | 2026-02-20 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-12 | ZIA-TRANSMIT-000055 | NA | Trade Partner | Re: Zi-Argus SD & Procurements | 22 | 0 | 0 | NA | APPROVED | 2026-02-12 | WF-004238 |  | 2026-02-27 |  | As requested by Kian, The WF has been terminated. As instructed, this will be resubmitted for review |  |  | NA | Closed | 22 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-12 | RDSBIM-TRANSMIT-000033 |  | Trade Partner | MWYCCB ¦ LEVEL 01 CONCRETE PROFILE PLAN | 5 | 0 | 0 | NA | APPROVED | 2026-02-12 | WF-000187 | 120 | 2026-02-19 |  |  | 2026-02-12 | 2026-02-12 | KPTG-TRANSMIT-000429 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-03 | KETE-TRANSMIT-000015 | NA | Trade Partner | FACADE - SHOP DRAWINGS | 51 | 0 | 0 | NA | APPROVED | 2025-12-05 | NA | 693 | 2025-12-10 |  |  | 2025-12-16 | 2025-12-16 | KPTG-TRANSMIT-002299 | Closed | 51 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-11 | PCForm-TRANSMIT-000057 | NA | Trade Partner | Fwd: Backpropping Requirements | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per the direction Ashlin no action,12-02-2026. only updated to document register. |  | 2026-02-12 | KPTG-IntCorr-000700 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-12 | ARCST-TRANSMIT-000207 | NA | Trade Partner | RE: C2 Switchroom Upper Gantry Primary Steel - IFC Shop Drawings | 185 | 0 | 0 | NA | APPROVED | 2026-02-12 | WF-004239 |  | 2026-02-17 |  |  |  | 2026-02-13 | The workflow has been terminated as per requested by Lola W | Closed | 185 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-11 | NXES-TRANSMIT-000043 | NA | Trade Partner | Level 05-08 Electrical Shopdrawings & Lighting Protection Layout | 9 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 552 | 2026-02-19 |  | close out pending-KPTG-IntCorr-000806 | 2026-03-19 | 2026-03-20 | KPTG-SADV-003517 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-10 | SKS Tech-TRANSMIT-000149 | NA | Trade Partner | for construction submittal | 0 | 1 | 0 | NA | REJECTED | [5 empty] | QA Error - KPTG-IntCorr-000979 |  | 2026-02-10 | KPTG-IntCorr-000979 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-10 | Hames-TRANSMIT-000112 | NA | Consultant | WALL SCHEDULE | 1 | 0 | 0 | NA | APPROVED | 2026-02-10 | NA | 962 | 2026-02-13 |  |  | 2026-02-13 | 2026-02-13 | KPTG-TRANSMIT-002813 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-10 | Endfire-TRANSMIT-000060 | NA | Trade Partner | Dry Fire Layout Ground Level IFC Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-02-10 | NA | 960 |  |  | Made void - NEW REVISED DWGS ISSUED |  | 2026-02-10 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-10 | PARR-TRANSMIT-000034 | NA | Trade Partner | P2666 - KPG NDC D1 Stage 2 - Fuel Services - GFCP | 9 | 0 | 0 | NA | REJECTED | [5 empty] | QA Error - KPTG-IntCorr-000980 |  | 2026-02-10 | KPTG-IntCorr-000980 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-10 | KPTG-DA-001084 | NA | Consultant | Approved FER - NTFRS response FEDRR 036-25-26E 200-9703-04 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Doc Regisered and forwarded to all parties |  | 2026-02-10 | KPTG-TRANSMIT-002779 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-11 | Inhabit-TRANSMIT-000013 | NA | Consultant | Updated NABERS Energy Report IFI-3 | 0 | 1 | 0 | NA | APPROVED | 2026-02-11 | NA | 964 | 2026-02-16 |  |  | 2026-02-12 | 2026-02-12 | KPTG-TRANSMIT-002795 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-11 | Endfire-TRANSMIT-000061 | NA | Trade Partner | Dry Fire Layout Ground Level IFC Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-02-11 | NA | 966 | 2026-02-16 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-002971 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-05 | NXT-TRANSMIT-001120 | NA | Trade Partner | M3 ST-4 XDU - Vertiv documents submissions | 11 | 0 | 0 | NA | APPROVED | 2025-12-05 | WF-003516 | NA | 2025-12-19 |  |  |  | 2025-12-15 | KPTG-TRANSMIT-010916 | Closed | 11 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-11 | VAE-Grp-TRANSMIT-000124 | NA | Trade Partner | FC Docs - MECH - TECH SUBS & SCHEDS - HEAT LOAD & VRF AC SYSTEMS | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  | FC - Docs - Forwarded to all parties |  | 2026-02-11 | KPTG-TRANSMIT-002820 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-11 | Procore TRN 296 | 296 | Consultant | ENVIRONMENTAL ACOUSTICS REPORT | 0 | 1 | 0 | NA | APPROVED | 2026-02-11 | NA | 968 | 2026-02-16 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-003013 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-12 | SKS Tech-TRANSMIT-000150 | NA | Trade Partner | HV Cable Sizing Report | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | FC Docs register updated and forwarded to all parties |  | 2026-02-12 | KPTG-TRANSMIT-002823 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-12 | Hames-TRANSMIT-000114 | NA | Consultant | Performance Solution Thresholds | 0 | 1 | 0 | NA | APPROVED | 2026-02-12 | WF-000820 | NA | 2026-02-17 |  |  | 2026-02-17 | 2026-02-18 | KPTG-TRANSMIT-002851 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-12 | SKS Tech-TRANSMIT-000152 | NA | Trade Partner | ELECTRICAL IFC DOCS | 8 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 971 | 2026-02-17 |  |  | 2026-02-17 | 2026-02-17 | KPTG-TRANSMIT-002841 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-12 | SKS Tech-TRANSMIT-000152 | NA | Trade Partner | TELECOMMUNICATION IFC DOCS | 5 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 972 | 2026-02-17 |  |  | 2026-02-17 | 2026-02-17 | KPTG-TRANSMIT-002837 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-12 | ADP-TRANSMIT-000167 | NA | Consultant | MEL741 - Stage 4 Services IFC Issue (Hydraulic drawings and Reg126) | 17 | 0 | 0 | NA | APPROVED |  | NA | 2042 | 2026-02-16 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-013383 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-11-13 | D&E-TRANSMIT-000051 | SPARK-CRFI-KPG-000349 | Trade Partner | AUTO REFILL & EXPANSION TANKS & DOSING POT | 0 | 1 | 0 | NA | APPROVED | 2026-02-12 | WF-000188 |  | 2026-02-12 |  |  |  | 2026-02-12 | KPTG-TRANSMIT-000430 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-12 | ADP-TRANSMIT-000168 | NA | Consultant | MEL741 - Stage 4 Services IFC Issue (CSMS drawings) | 8 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 2044 | 2026-02-16 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-013424 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-12 | ADP-TRANSMIT-000164 | NA | Consultant | MEL741 - Stage 4 Services IFC Issue (Electrical drawings and Reg126) | 64 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-02-12 | KPTG-TRANSMIT-012743,TRANSMIT-012745 | Closed | 64 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-11-28 | KETE-TRANSMIT-000013 | N/A | Trade Partner | PMU Comparison Report - Rev.2 | 0 | 1 | 0 | N/A | REJECTED | [5 empty] | Rejected due to wrong revision attached |  | 2025-12-01 | KPTG-IntCorr-000705 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-05 | B Smart-TRANSMIT-000030 | NA | Consultant | Architectural Facade Package IFC | 33 | 0 | 0 | NA | APPROVED | 2025-12-05 | WF-000075 | 140 | 2025-12-09 |  | Review void as advised by DM |  | 2025-12-16 | NA | Closed | 33 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-12 | ADP-TRANSMIT-000169 | NA | Consultant | Re: MEL741 - Stage 4 Services IFC Issue (Fuel drawings) | 9 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 2050 | 2026-02-16 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-013420 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-12 | HGP-TRANSMIT-000040 |  | Trade Partner | HGP-TRANSMIT-000040 | 0 | 11 | 0 | NA | APPROVED | 2026-02-12 | WF-000189 |  | 2026-02-19 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-12 | D&E-TRANSMIT-000106 | SPARK-CRFI-KPG-000497 | Trade Partner | SEISMIC INSTALLATION GUIDE | 0 | 1 | 0 | NA | APPROVED | 2026-02-12 | WF-000190 |  | 2026-02-19 |  |  |  | 2026-02-18 | KPTG-TRANSMIT-000452 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-12 | IVS-TRANSMIT-000331 | NA | Trade Partner | Stage 4 - Roof Gantry Construction Issue (Revised as clouded) | 3 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 2052 | 2026-02-16 |  |  |  | 2026-02-23 | KPTG-TRANSMIT-013320 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-12 | SMEPS-TRANSMIT-000173 | NA | Trade Partner | F1 - Light pole sample | 0 | 1 | 0 | NA | APPROVED | 2026-02-12 | WF-004247 | NA | 2026-02-26 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-013667 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-12 | Baigents-TRANSMIT-000066 |  | Trade Partner | MCC Remaining Precast IFC | 19 | 0 | 0 | NA | APPROVED | 2026-02-12 | WF-000191 | 121 | 2026-02-19 |  | Review void - Latest revision received |  | 2026-02-24 |  | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-12 | PROLMC-TRANSMIT-000009 |  | Trade Partner | Proline Louvre shop drawings (12-2-26) | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Error in document number |  | 2026-02-12 | KPTG-TRANSMIT-000431 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-12 | SMEPS-TRANSMIT-000174 | NA | Trade Partner | M3 Stage 3 - Precast Wall Bonding Shop Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-02-12 | WF-004252 | NA | 2026-03-03 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-013590 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-12 | JCBa-TRANSMIT-000055 | NA | Consultant | BASEMENT- GA PLANS AND SSP'S FOR IFC | 12 | 0 | 0 | NA | APPROVED | 2026-02-12 | WF000194 | 338 | 2026-02-17 |  |  |  | 2026-02-16 | KPTG-TRANSMIT-000626 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-12 | Auspan-TRANSMIT-000078: | NA | Trade Partner | Precast shop drawings for approval. Ground floor zone 2 | 27 | 0 | 0 | NA | APPROVED | 2026-02-12 | WF000195 | 340 | 2026-02-19 |  |  |  | 2026-02-19 | KPTG-TRANSMIT-000654 | Closed | 27 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2025-12-05 | Best_-TRANSMIT-000021 | NA | Consultant | Plans and schedule update for FER Signage | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-12 | Auspan-TRANSMIT-000079 | NA | Trade Partner | Precast shop drawings for approval. Level 1 zone 3 | 20 | 0 | 0 | NA | APPROVED | 2026-02-12 | WF000196 | 342 | 2026-02-19 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-000687 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-12 | Auspan-TRANSMIT-000075 | NA | Trade Partner | Precast Column Details. Update IFCed precast shop drawings. | 17 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required. Register and Distribution only |  | 2026-02-12 | KPTG-TRANSMIT-000602 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-12 | RDSBIM-TRANSMIT-000020 | NA | Trade Partner | GREYSTAR FORMATION LEVEL LAYOUT | 8 | 0 | 0 | NA | APPROVED | 2026-02-12 | WF000197 | 345 | 2026-02-17 |  |  |  | 2026-02-13 | KPTG-TRANSMIT-000609 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-04 | POTTSENG-TRANSMIT-000002 | NA | Trade Partner | 671C: HYDRAULIC SERVICES - BASEMENT 4 INGROUND - DRAINAGE LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-000189 | 252 | 2026-02-12 |  |  |  | 2026-02-12 | KPTG-TRANSMIT-000451 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-12 | RDSBIM-TRANSMIT-000216 | NA | Trade Partner | NXM3S4 ¦ GROUND FLOOR CONCRETE PROFILE PLAN NORTH OFFICE AND SECTION | 2 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 2062 | 2026-02-16 |  |  |  | 2026-02-23 | KPTG-TRANSMIT-013319 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-12 | ZIA-TRANSMIT-000056 | NA | Trade Partner | M3S3 Substation CSMS Sample Tech Data Submission | 16 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision number -KPTG-TRANSMIT-012769 |  | 2026-02-12 | KPTG-TRANSMIT-012769 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-12 | VIA Arch-TRANSMIT-000023 | NA | Trade Partner | Fwd: 22kV Switchroom Railing Updates | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-12 | DI-TRANSMIT-000144 | NA | Trade Partner | Re: PPT - Specification | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number - DRAFT-008749 |  | 2026-02-12 | KAPITOL-TRANSMIT-001079 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-12 | ADP-TRANSMIT-000165 | NA | Consultant | Re: MEL741 - Stage 4 Services IFC Issue (Mechanical drawings and Reg126) | 34 | 0 | 0 | NA | REJECTED | [5 empty] | qa rjected Revision FC-02 of drawing M3-MEC-ADP-DRG-C-0400-1002 has already been reviewed and completed. Could you please clarify why this previous revision has been resubmitted under Transmittal ADP-TRANSMIT-000165 |  | 2026-02-12 | KPTG-TRANSMIT-012750 | Closed | 34 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-12 | ADP-TRANSMIT-000166 | NA | Consultant | Re MEL741 - Stage 4 Services IFC Issue (Mechanical drawings and Reg126 | 2 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 2047 | 2026-02-16 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-013819 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-04 | DS-TRANSMIT-000078 | NA | Trade Partner | HYD SITE - WATER AND DRAINAGE | 2 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 3414 | 2025-12-10 |  |  |  | 2025-12-10 | KPTG-TRANSMIT-010812 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-12 | ADP-TRANSMIT-000170 | NA | Consultant | MEL741 - Stage 4 Services IFC Issue (FIP drawings | 9 | 1 | 0 | NA | APPROVED | 2026-02-12 | NA | 2054 | 2026-02-16 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-013398 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-12 | ADP-TRANSMIT-000171 | NA | Consultant | MEL741 - Stage 4 Services IFC Issue (Comms drawings) | 8 | 2 | 0 | NA | APPROVED | 2026-02-12 | NA | 2056 | 2026-02-16 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-013410 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-12 | ADP-TRANSMIT-000172 | NA | Consultant | MEL741 - Stage 4 Services IFC Issue (FID drawings | 12 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 2063 | 2026-02-16 |  | 7 PROCESSED FROM THIS AND 5 FROM ADP 173 | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-013389 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-12 | INGEN3D-TRANSMIT-000685 | NA | Trade Partner | DI | 7 | 0 | 0 | NA | APPROVED | 2026-02-12 | (WF-004253 |  | 2026-02-16 |  |  | 2026-03-05 | 2026-03-05 | KPTG-TRANSMIT-013907 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-12 | ADP-TRANSMIT-000173 | NA | Consultant | Stage 4 Services IFC Issue (FID drawings) | 5 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 2065 | 2026-02-16 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-013397 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-12 | ZIA-TRANSMIT-000077 | NA | Trade Partner | L2 Installation and Static Testing Procedure | 0 | 12 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC-Distribution Only |  | 2026-02-12 | KPTG-TRANSMIT-002522 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-11 | KARE-TRANSMIT-000086 | NA | Trade Partner | Conduit Set Out Plans | 32 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 32 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-11 | KARE-TRANSMIT-000087 | NA | Trade Partner | Revised Camera Sample | 0 | 1 | 0 | NA | APPROVED | 2026-02-11 | WF-000915 | NA | 2026-02-18 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-05 | KARE-TRANSMIT-000083 | NA | Trade Partner | EMS Schematic | 2 | 0 | 0 | NA | APPROVED | 2026-02-11 | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-11 | KPTG-IntCorr-001521 | NA | Trade Partner | Tiling samples for sample review | 0 | 6 | 0 | NA | APPROVED | 2026-02-12 | WF-000921,WF-000922,WF-000923,WF-000924,WF-000925,WF-000926 | NA | 2026-02-19 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-04 | D&E-TRANSMIT-000287 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - LOWER GROUND LEVEL 01 - MECHANICAL DUCT LAYOUTS & SECTIONS | 6 | 0 | 0 | NA | APPROVED |  | NA | 3416 | 2025-12-11 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014362 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-12 | Tradetec-TRANSMIT-000032 | N/A | Trade Partner | Shop Drawings for Electrical Pits | 11 | 0 | 0 | N/A | APPROVED | 2026-02-12 | N/A | 284 | 2026-02-19 |  |  | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-000900 | Closed | 11 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-12 | Tradetec-TRANSMIT-000032 | N/A | Trade Partner | Shop Drawings for Communications Pits | 3 | 0 | 0 | N/A | APPROVED | 2026-02-12 | N/A | 285 | 2026-02-19 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-000866 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-11 | KPTG-SADV-005339 | NA | Trade Partner | Flooring samples for review | 0 | 2 | 0 | NA | APPROVED | 2026-02-12 | WF-000919,WF-000920 | NA | 2026-02-19 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-12 | GPSElec-TRANSMIT-000006 | NA | Trade Partner | NextDC Stage 9-12 switchboard - MSB-JA-01 drawings - IFR | 29 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 287 | 2026-02-19 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-001220 | Closed | 29 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-12 | RDSBIM-TRANSMIT-000160 | NA | Trade Partner | LEVEL 11 TOWER A PARTITION LAYOUT (L11 to L13 TYPICAL) | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-12 | SMEPS-TRANSMIT-000012 | N/A | Trade Partner | STAGE 9-11: Electrical Inground layout | 1 | 0 | 0 | N/A | APPROVED | 2026-02-12 | N/A | 290 | 2026-02-19 |  |  | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-000905 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-12 | RDSBIM-TRANSMIT-000162 | NA | Trade Partner | LEVEL 11 TOWER B PARTITION WALL LAYOUT | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-12 | SMEPS-TRANSMIT-000012 | N/A | Trade Partner | STAGE 9-11: Telecoms Inground layout | 1 | 0 | 0 | NA | APPROVED | 2026-02-12 | N/A | 291 | 2026-02-19 |  |  | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-000905 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-12 | LANSA-TRANSMIT-000094 | NA | Trade Partner | Levels 11 & 12-14 Drainage Drawings with Correct Attachemts | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-11 | Auspan-TRANSMIT-000090 | N/A | Trade Partner | Precast shop drawings for construction. Stage 9 ground floor. | 17 | 0 | 0 | N/A | APPROVED |  | N/A | N/A |  |  | IFC drawings, No review required. |  | 2026-02-12 | NA | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-04 | Tradetec-TRANSMIT-000280 | NA | Trade Partner | IFA - Stage 2 - HVP1 and CP1 | 2 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 3421 |  |  |  | 2025-12-05 | 2025-12-05 | KPTG-TRANSMIT-010689 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-11 | AUSPAN-TRANSMIT-000093 | N/A | Trade Partner | Update IFCed shop drawings. 0G317 and 0GC035 | 2 | 0 | 0 | N/A | APPROVED |  | N/A | N/A |  |  | IFC Drawings No review required. |  | 2026-02-12 | N/A | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-11 | Auspan-TRANSMIT-000094 | N/A | Trade Partner | Precast shop drawings for construction. Stage 9 ground floor. | 1 | 0 | 0 | N/A | APPROVED |  | N/A | N/A |  |  | IFC Drawing No review required |  | 2026-02-12 | N/A | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-11 | Auspan-TRANSMIT-000097 | N/A | Trade Partner | Precast shop drawings for construction. Stage 9 ground floor. | 11 | 0 | 0 | N/A | APPROVED |  | N/A | N/A |  |  | IFC Drawings, No review required |  | 2026-02-12 | N/A | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-12 | WGAVIC-TRANSMIT-000060 | NA | Consultant | Civil Drawings - Early Works - Issued for Construction | 4 | 0 | 0 | N/A | APPROVED |  | N/A | N/A |  |  | IFC drawings No review required |  | 2026-02-12 | NA | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-12 | DI-TRANSMIT-000143 | NA | Trade Partner | PPT - IFC Issue | 9 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 292 | 2026-02-15 |  |  |  | 2026-02-13 | The WF has been terminated as per requested by Isaiah | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-12 | RDSBIM-TRANSMIT-000217 | NA | Trade Partner | NXM3S4 LEVEL 01 CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-02-13 | WF-004262 | 2073 | 2026-02-23 |  |  | 2026-03-02 | 2026-03-02 | KPTG-IntCorr-010133 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-13 | ARCST-TRANSMIT-000208 | NA | Trade Partner | C1 - Switchroom North Wall Beam and Bracing - Issued for Approval | 24 | 0 | 0 | NA | APPROVED | 2026-02-13 | WF-004263 |  | 2026-03-11 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-014085 | Closed | 24 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-11-21 | ACG-TRANSMIT-000028 | NA | Trade Partner | M3 - DH7/8 IFC Drawings | 13 | 0 | 0 | NA | APPROVED | 2025-11-25 | NA | 1251 | 2025-12-02 |  |  | 2026-02-13 | 2026-02-13 | KPTG-TRANSMIT-002545 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-04 | Stowe-A-TRANSMIT-000379 | NA | Trade Partner | Stowe - Drawing Submission - HS1 Office Stage 1 - 26.11.2025 - Electrical | 2 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 3425 | 2025-12-15 |  |  |  | 2025-12-10 | KPTG-TRANSMIT-010807 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-06 | SMEPS-TRANSMIT-000058 | NA | Trade Partner | ELECTRICAL - COLO 4 CELL 1 - 4, PHASE 4 CONTAINMENT LAYOUT | 4 | 0 | 0 | NA | APPROVED | 2026-02-09 | WF-000080 | NA | 2026-02-16 |  |  | 2026-02-15 | 2026-02-15 | KPTG-TRANSMIT-000142 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-06 | SMEPS-TRANSMIT-000059 | NA | Trade Partner | SME Shop Drawing Review Telecommunications | 1 | 0 | 0 | NA | APPROVED | 2026-02-06 | WF-000081 | NA | 2026-02-13 |  |  | 2026-02-12 | 2026-02-12 | KPTG-TRANSMIT-000135 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-30 | Entire M-TRANSMIT-000003 | NA | Trade Partner | Mechanical IFA Rev A Sample Submissions | 0 | 14 | 0 | NA | APPROVED | 2026-02-02 | WF-000037 | NA | 2026-02-09 |  | WF terminated | 2026-02-05 | 2026-02-05 |  | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-06 | Entire M-TRANSMIT-000004 | NA | Trade Partner | Mechanical IFA Rev A Sample Submissions Package 2 | 0 | 6 | 0 | NA | APPROVED | 2026-02-11 | WF-000100 | NA | 2026-02-24 |  | IFC drawing | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-000287 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-06 | SMEPS-TRANSMIT-000061 | NA | Trade Partner | BOM REV1 | 0 | 3 | 0 | NA | APPROVED | 2026-02-09 | WF-000086 | NA | 2026-02-16 |  |  | 2026-02-12 | 2026-06-12 |  | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-06 | SMEPS-TRANSMIT-000060 | NA | Trade Partner | Tech Data- LV cable submission | 0 | 1 | 0 | NA | APPROVED | 2026-02-09 | WF-000088 | NA | 2026-02-16 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-000151 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-13 | RDSBIM-TRANSMIT-000219 | NA | Trade Partner | NXM3S4 ¦ UPPER ROOF CONCRETE PROFILE KEY PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-02-13 | NA | 2076 | 2026-02-26 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-017288 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-13 | ARCST-TRANSMIT-000207 | NA | Trade Partner | C2 Switchroom Upper Gantry Primary Steel - IFC Shop Drawings | 185 | 0 | 0 | NA | APPROVED | 2026-02-13 | WF-004267 |  | 2026-03-11 |  | The existing workflow WF-004239 has been terminated and reinitiated via the IFA template, as requested by Lola W. | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-016279 | Closed | 144 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-04 | Stowe-A-TRANSMIT-000379 | NA | Trade Partner | Stowe - Drawing Submission - HS1 Office Stage 1 - 26.11.2025 - Telecommunication | 1 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 3424 | 2025-12-11 |  |  |  | 2025-12-10 | KPTG-TRANSMIT-010807 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-12 | Auspan-TRANSMIT-000048 | NA | Trade Partner | 1P10 shop drawing issued for construction | 1 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 555 | 2026-02-18 |  |  | 2026-02-12 | 2026-02-13 | KPTG-SADV-003040 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-12 | Auspan-TRANSMIT-000049 | NA | Trade Partner | Revised 1P05, 1P08 shop drawings issued for approval | 3 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 556 | 2026-02-19 |  |  | 2026-02-13 | 2026-02-13 | KPTG-SADV-003041 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-13 | Entire M-TRANSMIT-000035 | NA | Trade Partner | Re: Mechanical Equipment - Issued for Construction | 0 | 10 | 0 | NA | REJECTED | [7 empty] | 2026-02-13 | KPTG-TRANSMIT-012819 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-13 | D&E-TRANSMIT-000107 | SPARK-CRFI-KPG-000525 | Trade Partner | MWYCCB - GROUND LEVEL + LEVEL 1 - RCP LAYOUT ZONES MECHANICAL SERVICES - Issued For Review | 6 | 0 | 0 | NA | APPROVED | 2026-02-13 | WF-000195 | 122 | 2026-02-20 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000514 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-12 | Civilex-TRANSMIT-000029 | NA | Trade Partner | OSD Tank Shop Drawing | 0 | 1 | 0 | KPTG-IntCorr-000344 | APPROVED | 2026-02-13 | WF-000167 | NA | 2026-02-17 |  |  | 2026-02-19 | 2026-02-20 | KPTG-TRANSMIT-000521 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-12 | TTW-TRANSMIT-000092 | NA | Consultant | Updated Civil construction documentation | 26 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 258 | 2026-02-16 |  |  | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-000505 | Closed | 26 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-13 | KETE-TRANSMIT-000112 | NA | Trade Partner | Kete - Facade Cast-in Channels Layouts L01-L09 IFC | 9 | 0 | 0 | NA | APPROVED | 2026-02-16 | NA | 562 | 2026-02-21 |  |  | 2026-03-02 | 2026-03-02 | KPTG-SADV-003265 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-11 | ECBS-TRANSMIT-000071 | NA | Trade Partner | MLC ¦ Drawing Review of Door Wall Ceiling and Glazing | 9 | 0 | 0 | NA | REJECTED | [5 empty] | SUBMITTED DOCUMENTS ARE COMBINED WITH RECH DATA AND DHOP DRAWINGS, REQUESTED TO RESUBMIT |  | 2026-02-12 | KPTG-IntCorr-004869 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-04 | D&E-TRANSMIT-000288 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - LEVEL 01 - MECHANICAL DUCT LAYOUT - ZONE 4 | 1 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 3418 | 2025-12-11 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014369 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-11 | RDSBIM-TRANSMIT-000110 | NA | Trade Partner | MLCSPR ¦ OUTDOOR COURT LEVEL 02 CONCRETE PROFILE PLAN SHEET 6 | 1 | 0 | 0 | NA | APPROVED | 2026-02-11 |  | 440 | 2026-02-17 |  |  |  | 2026-02-12 | KPTG-SADV-003687 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-13 | D&E-TRANSMIT-000393 | NA | Trade Partner | NXM3S4 - LEGEND AND GERNAL NOTES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-02-13 | NA | 2078 | 2026-02-23 |  |  |  | 2026-02-19 | KPTG-TRANSMIT-013220 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-12 | PROLMC-TRANSMIT-000010 |  | Trade Partner | Proline roofing shop drawings 12-12-26 | 15 | 0 | 0 | NA | REJECTED | [5 empty] | Error in document number |  |  | KPTG-TRANSMIT-000434 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-09 | SMEPS-TRANSMIT-000020 | NA | Trade Partner | SME Shop Drawing Review Electrical | 4 | 0 | 0 | NA | APPROVED | 2026-02-02 | WF-000038 | NA | 2026-02-09 |  |  | 2026-02-08 | 2026-02-08 | KPTG-TRANSMIT-000096 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-11 | SC-TRANSMIT-000043 | NA | Trade Partner | VQ41 Void Space Steel IFA | 16 | 0 | 0 | NA | APPROVED | 2026-02-11 | WF-000821 |  | 2026-02-16 |  |  |  | 2026-02-13 | KPTG-TRANSMIT-002417 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-13 | D&E-TRANSMIT-000394 | NA | Trade Partner | Fans - Issued for Review | 0 | 1 | 0 | NA | APPROVED | 2026-02-13 | WF-004270 | NA | 2026-03-06 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015087 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-13 | KPTG-TRANSMIT-012838 | NA | Trade Partner | Zone C1 EAE Busduct Shop drawings - IFC | 14 | 0 | 0 | NA | APPROVED | 2026-02-13 | WF-004271 |  | 2026-02-26 |  | Zone C1 EAE Busduct Shop drawings - IFC |  | 2026-02-13 |  | Open | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-12 | PROLMC-TRANSMIT-000011 |  | Trade Partner | Proline Shop drawings cladding 12-2-26 | 19 | 0 | 0 | NA | REJECTED | [5 empty] | Error in document number |  | 2026-02-13 | KPTG-TRANSMIT-000440 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-10 | SES AU-TRANSMIT-000003 | NA | Trade Partner | SECURITY SHOP DRAWING FOR REVIEW | 12 | 0 | 0 | NA | APPROVED | 2026-02-10 | WF-000095 | NA | 2026-02-17 |  |  | 2026-02-20 | 2026-02-20 |  | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-10 | TATE_-TRANSMIT-000016 | NA | Trade Partner | COLO 4 SCEC WALL REVISION D | 9 | 0 | 0 | NA | APPROVED | 2026-02-12 | WF-000112 | NA | 2026-02-19 |  |  | 2026-02-18 | 2026-02-18 |  | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-04 | D&E-TRANSMIT-000289 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - LOWER GROUND - HIGH LEVEL MECHANICAL PIPE LAYOUT ZONE 3 | 1 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 3427 | 2025-12-11 |  | Void as instructed by Ibrahim Shekari Soleimanloo KPTG-IntCorr-009745 |  | 2026-02-20 |  | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-13 | HGP-TRANSMIT-000041 |  | Trade Partner | Heritage Glass - Updated Sample Submission | 0 | 3 | 0 | NA | APPROVED | 2026-02-13 | WF-000196 |  | 2026-02-20 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-10 | SMEPS-TRANSMIT-000063 | NA | Trade Partner | SME Tech data | 0 | 1 | 0 | NA | APPROVED | 2026-02-11 | WF-000097 | NA | 2026-02-18 |  |  | 2026-02-12 | 2026-02-12 | KPTG-TRANSMIT-000129 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-10 | SMEPS-TRANSMIT-000064 | NA | Trade Partner | Containment Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-02-11 | WF-000098 | NA | 2026-02-18 |  | WF Terminated |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-13 | HGP-TRANSMIT-000042 |  | Trade Partner | Re: Heritage Glass - Updated Sample Submission | 0 | 1 | 0 | KPTG-IntCorr-001695 | APPROVED | 2026-02-16 | WF-000201 |  | 2026-02-23 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-12 | RDSBIM-TRANSMIT-000218 | NA | Consultant | NXM3S4 LEVEL-1-C-1-055 CLEANERS FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 2072 | 2026-02-16 |  |  |  | 2026-02-23 | KPTG-TRANSMIT-013358 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-28 | SIL-TRANSMIT-000020 | NA | Trade Partner | MEL05 C4 - Requested Documents | 0 | 12 | 0 | NA | APPROVED | 2026-02-11 | WF-000102 | NA | 2026-02-18 |  |  | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-000191 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-09 | SEAPBU-TRANSMIT-000002 | NA | Trade Partner | SCHNEIDER OFCI DOCUMENTS - ATS | 0 | 20 | 0 | NA | APPROVED | 2026-02-11 | WF-000103 | NA | 2026-02-18 |  |  | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-000201 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-13 | D&E-TRANSMIT-000337 | NA | Trade Partner | L1 MANTRAP DUCT& PIPE LAYOUT (V-07) | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Already Locked In same drawings and requested for resubmission to originator by Ellie salmon |  |  | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-06 | ETNInd-TRANSMIT-000003 | NA | Trade Partner | COLO4 FAT Reports | 0 | 8 | 0 | NA | APPROVED | 2026-02-09 | WF-000084 | NA | 2026-02-16 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-000168 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-03 | KETE-TRANSMIT-000016 | NA | Trade Partner | structural calculation report | 0 | 1 | 0 | NA | APPROVED | 2025-12-05 | NA | 692 | 2025-12-10 |  |  | 2025-12-16 | 2025-12-18 | KPTG-TRANSMIT-002307 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-13 | D&E-TRANSMIT-000338 | NA | Trade Partner | Mantrap Technical Data | 0 | 2 | 0 | NA | APPROVED | 2026-02-13 | WF-000939 | NA | 2026-02-20 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-002666 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-10 | SMEPS-TRANSMIT-000062 | NA | Trade Partner | Shop Drawing Review Electrical IFA Rev 2 | 4 | 0 | 0 | NA | APPROVED | 2026-02-11 | WF-000099 | NA | 2026-02-18 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-000171 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-11 | SMEPS-TRANSMIT-000065 | NA | Trade Partner | Tech Data Revision 4 Cell Containment | 0 | 1 | 0 | NA | APPROVED | 2026-02-13 | WF-000119 | NA | 2026-02-20 |  |  | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-000188 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-13 | ACG-TRANSMIT-000031 | NA | Trade Partner | Drawings IFC-2 | 6 | 0 | 0 | KPTG-IntCorr-002828 | APPROVED |  | NA | NA |  |  | IFC-Distribution only |  | 2026-02-16 | KPTG-TRANSMIT-002565 | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-13 | Leemark-TRANSMIT-000006 | SPARK-CRFI-KPG-000530 | Trade Partner | Tech Data Submission 2 -LEEMARK | 0 | 6 | 0 | NA | APPROVED | 2026-02-13 | WF-000197 |  | 2026-02-20 |  |  |  | 2026-02-16 | KPTG-TRANSMIT-000443 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-13 | IVS-TRANSMIT-000332 | NA | Trade Partner | STR - Future Link Construction Issue (Revised as clouded) | 5 | 0 | 0 | NA | APPROVED | 2026-02-13 | NA | 2080 | 2026-02-16 |  |  |  | 2026-02-17 | KPTG-TRANSMIT-012972 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-12 | 4DW-TRANSMIT-000084 | NA | Consultant | Ground Level Updates | 5 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 556 | 2026-02-18 |  |  | 2026-02-12 | 2026-02-13 | KPTG-SADV-003016 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-12 | 4DW-TRANSMIT-000085 | NA | Consultant | Ground Level Updates - Part 2 | 1 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 554 | 2026-02-18 |  |  | 2026-02-13 | 2026-02-13 | KPTG-SADV-003015 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-13 | OveArup-TRANSMIT-000159 | NA | Trade Partner | Fwd: M3 - Stage 3 Earthing Schematic and Typical Details Update | 2 | 0 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-13 | PFP PL-TRANSMIT-000066 | NA | Trade Partner | Re: DH C8 Level 1 Most Remote Hydraulic Calc IFA | 0 | 1 | 0 | NA | APPROVED | 2026-02-13 | WF-004277 | NA | 2026-03-09 |  |  | 2026-03-06 | 2026-03-03 | KPTG-TRANSMIT-013789 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-01 | Rinco-TRANSMIT-000021 | NA | Consultant | Structural Drawings - L6-Roof PT & Reinforcement for Review | 84 | 0 | 0 | NA | APPROVED | 2025-12-01 | WF-000073 | 142 | 2025-12-03 |  |  |  | 2025-12-08 | KPTG-TRANSMIT-000274 | Closed | 84 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-04 | D&E-TRANSMIT-000290 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - GROUND - MECHANICAL DUCT LAYOUTS - ZONES 2-6 | 5 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 3436 | 2025-12-11 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014406 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-13 | KPTG-IntCorr-002821 | NA | Consultant | Door Work Order, Frame Shop Drawing, Frame Work Order | 0 | 3 | 0 | NA | APPROVED | 2026-02-13 | WF-000940 |  |  |  | WF-000940 is Terminated Requested by Kim,and Resubmitted through ACC |  | 2026-02-16 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-13 | HDRAus-TRANSMIT-000394 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 14 | 0 | 0 | NA | APPROVED | 2026-02-13 | NA | 2088 | 2026-02-17 |  |  |  | 2026-02-16 | KPTG-TRANSMIT-012922 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-13 | DI-TRANSMIT-000146 | NA | Trade Partner | M3 Stage 4 - Document upload - PDF and CAD | 1 | 0 | 0 | NA | APPROVED | 2026-02-13 | NA | 294 | 2026-02-17 |  |  |  | 2026-02-17 | KAPITOL-TRANSMIT-001097 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-13 | DI-TRANSMIT-000145 | NA | Trade Partner | Re: Updtaed document name | 1 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-02-13 | DRAFT-008780 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-13 | INGEN3D-TRANSMIT-000686 | NA | Trade Partner | I3D-378 Next DC M3 Stage 4 - Ground Floor (Zone 4) - MP0023 & PWS4-677 - Revised IFC (13-02-2026) | 2 | 0 | 0 | NA | APPROVED | 2026-02-13 | 004278 | NA | 2026-02-20 |  |  | 2026-03-06 | 2026-03-06 | INGEN3D-TRANSMIT-000686 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-13 | ADP-TRANSMIT-000165 | NA | Consultant | Re MEL741 - Stage 4 Services IFC Issue (Mechanical drawings and Reg126) | 32 | 2 | 0 | NA | APPROVED | 2026-02-13 | NA | 2087 | 2026-02-17 |  | 30 PROCESSED FROM THIS 1 FROM ADP 166 AND 1 FROM ADP 175 AND 29 DOCUMENTS COMPELETED REVIEW AND 1 IN ACC WF-2238 | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-013422 | Closed | 29 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-13 | ADP-TRANSMIT-000175 | NA | Consultant | Re MEL741 - Stage 4 Services IFC Issue (Mechanical drawings and Reg126 | 1 | 0 | 0 | NA | APPROVED | 2026-02-13 | NA | 2090 | 2026-02-17 |  |  |  | 2026-02-17 | The workflow has been terminated. The updated drawing will be submitted | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-13 | HDRAus-TRANSMIT-000395 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 1 | 0 | 0 | NA | APPROVED | 2026-02-13 | NA | 2092 | 2026-02-17 |  |  |  | 2026-02-16 | KPTG-TRANSMIT-012926 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-13 | VIA Arch-TRANSMIT-000024 | NA | Trade Partner | Re: Retransmitting VIA docs | 49 | 0 | 0 | NA | REJECTED |  |  |  | 2026-02-17 |  | DUE THE REVISION OF THE ONE DOCUMENT IS MENTION DELECTED NEED CLARIFICATION FOR PROCESSING |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-10-11 | RDSBIM-TRANSMIT-000145 | NA | Trade Partner | XM3S4 ¦ LEVEL 01 CONCRETE PROFILE PLAN ZONE C1 doc-1 | 1 | 0 | 0 | NA | APPROVED | 2025-10-11 | NA | 1339 | 2026-02-13 |  |  |  | 2026-02-13 | KPTG-TRANSMIT-012825 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-04 | D&E-TRANSMIT-000291 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - LOWER GROUND - HIGH LEVEL MECHANICAL PIPE LAYOUT - ZONE 5 | 1 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 3429 | 2025-12-11 |  | As instructed by Ibrahim Shekari Soleimanloo KPTG-IntCorr-009745 |  | 2026-02-20 |  | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-10-10 | RDSBIM-TRANSMIT-000144 | NA | Trade Partner | NXM3S4 ¦ ROOF ZONE C1 CONCRETE PROFILE PLAN AND SECTIONS | 4 | 0 | 0 | NA | APPROVED | 2025-10-10 | NA | 1336 | 2026-02-13 |  |  |  | 2026-02-13 | KPTG-TRANSMIT-012832 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-10-10 | RDSBIM-TRANSMIT-000142 | NA | Trade Partner | ROOF ZONE C3 CONCRETE PROFILE PLAN AND SECTIONS | 2 | 0 | 0 | NA | APPROVED | 2025-11-10 | NA | 1305 | 2026-02-13 |  |  |  |  | KPTG-TRANSMIT-012836 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-10-10 | RDSBIM-TRANSMIT-000160 | NA | Trade Partner | RDSBIM-TRANSMIT-000160 | 1 | 0 | 0 | NA | APPROVED | 2025-10-10 | NA | 1475 | 2026-02-13 |  |  |  | 2026-02-13 | KPTG-TRANSMIT-012864 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-11-07 | RDSBIM-TRANSMIT-000162 | NA | Trade Partner | NXM3S4 ¦ ROOF LEVEL CONCRETE PROFILE PLAN NORTH OFFICE | 1 | 0 | 0 | NA | APPROVED | 2025-11-07 | NA | 1493 | 2026-02-13 |  |  |  | 2026-02-13 | KPTG-TRANSMIT-012868 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-13 | KETE-TRANSMIT-000004 | NA | Trade Partner | : Kete - Facade Shop Drawing 1st Submission Zone 01 - L01 to L07 | 99 | 0 | 0 | NA | APPROVED | 2026-02-13 | WF-000200 | 352 | 2026-02-20 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-000759 | Closed | 99 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-13 | Auspan-TRANSMIT-000080 | NA | Trade Partner | : Precast shop drawings for approval. Ground floor. | 17 | 0 | 0 | NA | APPROVED | 2026-02-13 | WF-000199 | 348 | 2026-02-20 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-000689 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-13 | Auspan-TRANSMIT-000081 | NA | Trade Partner | Precast shop drawings for approval. Level 1. | 20 | 0 | 0 | NA | APPROVED | 2026-02-13 | NA | 350 | 2026-02-20 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-000716 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-13 | Auspan-TRANSMIT-000082 | NA | Trade Partner | Precast shop drawings for construction. Basement | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required, update and distribute. |  | 2026-02-13 | KPTG-TRANSMIT-000610 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-13 | IVS-TRANSMIT-000008 | NA | Trade Partner | J1462-STR-MEM-005 - Hoist base design IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Register and Distribute to all trade Partners. |  | 2026-02-13 | KPTG-TRANSMIT-000605 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-13 | Rinco-TRANSMIT-000029 | NA | Consultant | Structural drawings update | 56 | 0 | 0 | NA | APPROVED | 2026-02-13 | WF-000201 | 354 | 2026-02-17 |  |  |  | 2026-02-17 | KPTG-TRANSMIT-000633 | Closed | 56 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-04 | HDRAus-TRANSMIT-000330 | NA | Consultant | SW - Fencing - NLIU | 3 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | NA | 2025-12-04 | 0 | No Longer In Use | 2025-12-04 | 2025-12-04 | KPTG-TRANSMIT-010607 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-13 | JCBa-TRANSMIT-000056 | NA | Consultant | IFC_PRECAST & GA ELEVATIONS | 32 | 0 | 0 | NA | APPROVED | 2026-02-13 | WF-000202 | 356 | 2026-02-17 |  |  |  | 2026-02-17 | KPTG-TRANSMIT-000630 | Closed | 32 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-13 | ARCH-TRANSMIT-000139 | NA | Consultant | MLC - SPR - AQC - WL04 Setout Update | 2 | 0 | 0 | NA | APPROVED | 2026-02-13 | NA | 440 | 2026-02-20 |  |  | 2026-03-05 | 2026-03-05 | KPTG-SADV-003816 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-13 | Highbu-TRANSMIT-000120 | NA | Trade Partner | Resubmission of terminated sample submission | 0 | 1 | 0 | NA | REJECTED | [9 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-13 | Highbu-TRANSMIT-000121 | NA | Trade Partner | Recently terminated sample submission by KP | 0 | 1 | 0 | NA | REJECTED | [9 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-13 | Highbu-TRANSMIT-000122 | NA | Trade Partner | Terminated sample submission resubmitted | 0 | 1 | 0 | NA | REJECTED | [9 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-13 | Highbu-TRANSMIT-000123 | NA | Trade Partner | Terminated sample submission resubmitted | 0 | 1 | 0 | NA | REJECTED | [9 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-13 | Highbu-TRANSMIT-000124 | NA | Trade Partner | Terminated sample submission resubmitted | 0 | 1 | 0 | NA | REJECTED | [9 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-13 | SC-TRANSMIT-000044 | NA | Trade Partner | Additional Door Header IFA | 3 | 0 | 0 | NA | APPROVED | 2026-02-12 | WF-000826 |  | 2026-02-19 |  |  |  | 2026-02-13 | KPTG-TRANSMIT-002420 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-13 | WGAVIC-TRANSMIT-000061 | NA | Consultant | Civil Drawings - No Longer in Use - Issued for Information | 25 | 0 | 0 | N/A | APPROVED |  | N/A | N/A |  |  | Drawings marked as No Longer in Use, Updated register & distributed. Removed from ACC & Build sheets |  | 2026-02-13 | NA | Closed | 25 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-13 | WGAVIC-TRANSMIT-000062 | NA | Consultant | Civil Drawings - No Longer in Use - Issued for Information | 7 | 0 | 0 | N/A | APPROVED |  | N/A | N/A |  |  | Drawings marked as No Longer in Use. Updated register and distributed. Removed from ACC & Build sheets |  | 2026-02-13 | NA | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-04 | D&E-TRANSMIT-000292 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - SECURITY GRILLES | 1 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 3432 | 2025-12-11 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-013589 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-13 | AXIS-NSW-TRANSMIT-000003 | NA | Trade Partner | NEXT DC Samples and Tech data | 0 | 3 | 0 | NA | APPROVED | 2026-02-13 | WF-000239 | NA | 2026-02-20 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-001102 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-13 | AXIS-NSW-TRANSMIT-000003 | NA | Trade Partner | NEXT DC Samples and Tech data | 0 | 4 | 0 | NA | APPROVED | 2026-02-13 | WF-000240 | NA | 2026-02-20 |  |  | 2026-02-27 | 2026-03-02 | KPTG-TRANSMIT-001102 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-13 | GPSElec-TRANSMIT-000007 | NA | Trade Partner | NextDC Stage 9-12 switchboard - MSB-JA-02 drawings - IFR | 50 | 0 | 0 | NA | APPROVED | 2026-02-13 | NA | 299 | 2026-02-24 |  |  | 2026-03-05 | 2026-03-05 | KPTG-TRANSMIT-001216 | Closed | 50 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-12 | JAANBIR'S MESSAGE | NA | Consultant | FT09B - BRICK CURTAIN WALL DETAILS | 8 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 256 | 2026-02-17 |  | New drawings issued by TTW-Transmit-000093 - hence made void |  |  | NA | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-12 | KPTG-IntCorr-000338 | NA | Client | DL - Planning Endorsement | 13 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Register updated, and sent transmittals to all |  | 2026-02-25 | KPTG-TRANSMIT-000568 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-13 | RDSBIM-TRANSMIT-000163 | NA | Trade Partner | LEVEL 15 & ROOF RCP LAYOUT | 2 | 0 | 0 | NA | APPROVED | 2026-02-13 | WF-000930 | 540 | 2026-02-20 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-002735 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-13 | vdmcons-TRANSMIT-000128 | NA | Trade Partner | ME25 1004: D110 511-537 Sydney Rd Coburg - Shop Drawings - Core Lid Panels - Re-IFF - 2026-02-13 | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Aconex Update Register only |  | 2026-02-13 | KPTG-IntCorr-001531 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-13 | vdmcons-TRANSMIT-000129 | NA | Trade Partner | ME25 1004: D111 511-537 Rd Coburg - Shop Drawings - Building A L14 Panel Bottom Grout Tube As-Built - Re-IFF - 2026-02-13 | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-13 | KPTG-TRANSMIT-002696 | NA | Trade Partner | HVN - DDA shower & Handryer | 0 | 2 | 0 | NA | APPROVED | 2026-02-13 | WF-000927 | NA | 2026-02-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-04 | D&E-TRANSMIT-000293 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - LOWER GROUND - HIGH LEVEL MECHANICAL PIPE LAYOUT - ZONE 1 | 1 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 3440 | 2025-12-11 |  |  | 2026-01-23 | 2026-01-23 | KPTG-TRANSMIT-011894 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-13 | ccair-TRANSMIT-000089 | NA | Trade Partner | Level 04 - 06 Mechanical Duct & Pipework Layout | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-13 | ccair-TRANSMIT-000090 | NA | Trade Partner | Level 07 - Mechanical Duct & Pipework Layout - IFC | 12 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-13 | LANSA-TRANSMIT-000095 | NA | Trade Partner | Level 09 Drainage Issued for Approval | 2 | 0 | 0 | NA | APPROVED | 2026-02-13 | WF-000931 | 541 | 2026-02-20 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-002776 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2026-02-12 | RDSBIM-TRANSMIT-000196 | NA | Trade Partner | LOWER GROUND STAIR & RAMP PLAN & SECTIONS | 6 | 0 | 0 | NA | APPROVED | 2026-02-13 | NA | 573 | 2026-02-20 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-002574 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-11 | SMEPS-TRANSMIT-000066 | NA | Trade Partner | Secure Duct Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-02-11 | WF-000105 | NA | 2026-02-18 |  |  | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-000194 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-11 | SMEPS-TRANSMIT-000069 | NA | Trade Partner | B5 fitting | 0 | 1 | 0 | NA | APPROVED | 2026-02-11 | WF-000108 | NA | 2026-02-18 |  |  | 2026-02-16 | 2026-02-16 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-11 | SMEPS-TRANSMIT-000067 | NA | Trade Partner | SME Shop Drawing Electrical IFC | 4 | 0 | 0 | NA | APPROVED | 2026-02-12 | WF-000114 | NA | 2026-02-18 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-000159 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-11 | SMEPS-TRANSMIT-000068 | N/A | Trade Partner | SME Shop Drawing Electrical IFC | 1 | 0 | 0 | NA | APPROVED | 2026-02-12 | WF-000115 | NA | 2026-02-19 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-000156 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-11 | SMEPS-TRANSMIT-000070 | NA | Trade Partner | Tech Data NLP01- PNL01-PNL02 submission | 12 | 0 | 0 | NA | APPROVED | 2026-02-12 | WF-000109 | NA | 2026-02-19 |  |  | 2026-02-12 | 2026-02-12 |  | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-12 | TATE_-TRANSMIT-000018 | NA | Trade Partner | MEL05 HAC TECH DATA | 0 | 8 | 0 | NA | APPROVED | 2026-02-12 | WF-000111 | NA | 2026-02-19 |  |  | 2026-02-12 | 2026-02-12 |  | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-04 | D&E-TRANSMIT-000294 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - LOWER GROUND - LOW LEVEL MECHANICAL PIPE LAYOUT - ZONE 4 & 6 | 2 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 3450 | 2025-12-11 |  |  | 2026-01-23 | 2026-01-23 | KPTG-TRANSMIT-011861 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-12 | SMEPS-TRANSMIT-000071 | NA | Trade Partner | SME Shop Drawing Telecomunications IFC | 11 | 0 | 0 | NA | APPROVED | 2026-02-13 | WF-000125 | NA | 2026-02-20 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-000228 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-13 | SMEPS-TRANSMIT-000072 | NA | Trade Partner | Tech Data Fire Sealing equipment | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-02-13 | KPTG-TRANSMIT-000138 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-12 | SMEPS-TRANSMIT-000073 | NA | Trade Partner | SME Shop Drawing Electrical IFC | 4 | 0 | 0 | NA | APPROVED | 2026-02-13 | WF-000122 | NA | 2026-02-19 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-000153 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-12 | SMEPS-TRANSMIT-000074 | NA | Trade Partner | SME Shop Drawing Telecomunications IFC | 3 | 0 | 0 | NA | APPROVED | 2026-02-13 | WF-000126 | NA | 2026-02-20 |  | IFC drawing | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-000217 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-12 | SMEPS-TRANSMIT-000075 | NA | Trade Partner | BOM-revision | 3 | 0 | 0 | NA | APPROVED | 2026-02-13 | WF-000118 | NA | 2026-02-20 |  |  | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-000213 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-12 | SMEPS-TRANSMIT-000076 | NA | Trade Partner | Tech Data- DBs (NLP,PNL01,PNL02) | 0 | 12 | 0 | NA | APPROVED | 2026-02-13 | WF-000120 | NA | 2026-02-20 |  |  | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-000197 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-13 | Hames-TRANSMIT-000115 | NA | Consultant | GA PLANS WITH UPDATED ACTIVE LEAF INDICATOR | 4 | 0 | 0 | KPTG-IntCorr-000992 | APPROVED | 2026-02-12 | NA | 974 | 2026-02-17 |  | 1 drawing re-issued hames-Trn-000118 | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-002925 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-13 | Hames-TRANSMIT-000116 | NA | Consultant | ARCHITECTURAL MATERIALS AND FINISHES SCHEDULE | 1 | 0 | 0 | NA | APPROVED | 2026-02-15 | NA | 976 | 2026-02-18 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-002966 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-13 | PARR-TRANSMIT-000035 | NA | Trade Partner | Fuel Services - Client documents - IFC | 14 | 0 | 0 | KPTG-IntCorr-001003 | APPROVED | 2026-02-18 | NA | 984 | 2026-02-20 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-002883 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-13 | Endfire-TRANSMIT-000063 | NA | Trade Partner | Water Mist Drawings-FIP | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - KPTG-IntCorr-000994 |  | 2026-02-13 | KPTG-IntCorr-000994 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-04 | D&E-TRANSMIT-000295 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - LEVEL 01 - MECHANICAL DUCT LAYOUT - ZONE 3 | 1 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 3439 | 2025-12-11 |  |  | 2026-01-23 | 2026-01-23 | KPTG-TRANSMIT-011873 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-13 | WAM-TRANSMIT-000711 | NA | Consultant | MATERIAL FINISHES SCHEDULE | 1 | 0 | 0 | NA | APPROVED | 2026-02-13 | WF-000168 | NA | 2026-02-17 |  |  |  | 2026-03-03 | KPTG-TRANSMIT-000623 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-13 | TTW-TRANSMIT-000093 | NA | Consultant | Drawing update FACADE | 19 | 1 | 0 | KPTG-IntCorr-000349 - SPEC submitted for review | APPROVED | 2026-02-13 | WF-000169 | NA | 2026-02-17 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-000541 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-14 | SMEPS-TRANSMIT-000114 | SPARK-CRFI-KPG-000329 | Trade Partner | UPS-01 (A), UPS-02 (B) & UPS-03 (B) tech data for approval | 0 | 1 | 0 | NA | APPROVED | 2026-02-16 | WF-000198 |  | 2026-02-23 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-000553 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-16 | SKS Tech-TRANSMIT-000023 | NA | Trade Partner | Elec and Comms Containment ROOF for review | 1 | 0 | 0 | NA | APPROVED | 2026-02-16 | NA | 2095 | 2026-02-24 |  |  |  | 2026-02-19 | As requested by Oliver S. -VOID MSG - a new drawing will be coming through shortly | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-16 | SKS Tech-TRANSMIT-000023 | NA | Trade Partner | Elec and Comms Containment ROOF for review | 1 | 0 | 0 | NA | APPROVED | 2026-02-16 | NA | 2096 | 2026-02-24 |  |  |  | 2026-02-20 | KPTG-TRANSMIT-013239 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-16 | Nilsen3-TRANSMIT-000025 | NA | Trade Partner | NXM3S4 ¦ Nilsen ELC Shop Drawings - FOA | 13 | 0 | 0 | NA | APPROVED | 2026-02-16 | NA | 2097 | 2026-02-24 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014867 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-12 | SMEPS-TRANSMIT-000077 | NA | Trade Partner | SME Shop Drawing EPMS IFC | 1 | 0 | 0 | NA | APPROVED | 2026-02-13 | WF-000127 | NA | 2026-02-20 |  |  | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-000210 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-12 | SMEPS-TRANSMIT-000078 | NA | Trade Partner | SME Shop Drawing Electrical IFA 2 | 1 | 0 | 0 | NA | APPROVED | 2026-02-13 | WF-000124 | NA | 2026-02-20 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-000162 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-12 | SMEPS-TRANSMIT-000079 | NA | Trade Partner | SMEPS-TRANSMIT-000009 - SME Shop Drawing for Electrical Low Voltage Diagram - Phase 4 | 1 | 0 | 0 | NA | APPROVED | 2026-02-13 | WF-000123 | NA | 2026-02-20 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-000165 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-13 | SMEPS-TRANSMIT-000081 | NA | Trade Partner | SME Shop Drawing Review Electrical | 4 | 0 | 0 | NA | APPROVED | 2026-02-13 | WF-000129 WF-000137 | NA | 2026-02-20 |  |  | 2026-05-06 | 2026-03-06 |  | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-04 | D&E-TRANSMIT-000296 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - LEVEL 01 - EQUIPMENT & PLINTHS LAYOUT - ZONE 1 | 6 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 3449 | 2025-12-11 |  |  | 2026-01-23 | 2026-01-23 | KPTG-TRANSMIT-011870 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-01-30 | JCI-TRANSMIT-000005 | NA | Trade Partner | JCI DOC TRANSMITTAL | 0 | 31 | 0 | NA | APPROVED | 2026-02-13 | WF-000128 | NA | 2026-02-20 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-000314 | Closed | 31 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-16 | SMEPS-TRANSMIT-000180 | NA | Trade Partner | 22KV - Earth bar sample | 0 | 1 | 0 | NA | APPROVED | 2026-02-19 | WF-004293 |  | 2026-02-27 |  |  |  | 2026-02-20 | KPTG-TRANSMIT-013249 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-16 | HEXA-TRANSMIT-000002 | NA | Trade Partner | B08 - Mechanical Services Drawings for Review | 3 | 0 | 0 | NA | APPROVED | 2026-02-16 | NA | 295 | 2026-02-27 |  |  |  |  | The workflow has been terminated and re-initiated using a new template. | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-16 | D&E-TRANSMIT-000109 |  | Trade Partner | AIR CONDITIONERS SPLIT TYPE | 0 | 1 | 0 | NA | REJECTED | [8 empty] | KPTG-TRANSMIT-000442 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-16 | D&E-TRANSMIT-000110 | SPARK-CRFI-KPG-000279 | Trade Partner | MWYCCB - MECHANICAL NOTES & LEGENDS - NCC2022 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-02-16 | WF-000199 | 123 | 2026-02-23 |  |  | 2026-03-16 | 2026-05-04 | KPTG-TRANSMIT-000804 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-16 | ARCST-TRANSMIT-000209 | NA | Trade Partner | Admin East & West Canopy Framing - Shop Drawings - Issued for Approval | 19 | 0 | 0 | NA | APPROVED | 2026-02-16 | WF-004294 |  | 2026-03-12 |  |  | 2026-04-14 | 2026-04-14 | KPTG-TRANSMIT-015884 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-16 | D&E-TRANSMIT-000111 | SPARK-CRFI-KPG-0000533 | Trade Partner | MECHANICAL ACOUSTIC REVIEW | 0 | 1 | 0 | NA | APPROVED | 2026-02-16 | WF-000200 |  | 2026-02-23 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-16 | DI-TRANSMIT-000143 | NA | Trade Partner | PPT - IFC Issue | 6 | 0 | 0 | NA | APPROVED | 2026-02-16 | NA | 296 | 2026-02-18 |  |  |  | 2026-02-16 | KAPITOL-TRANSMIT-001091 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-13 | PCForm-TRANSMIT-000076 | N/A | Trade Partner | Schedules for the rest of the levels for all cores. | 16 | 0 | 0 | N/A | REJECTED | [5 empty] | Need to revise, KPTG-SADV-001175 |  | 2026-02-16 | KPTG-SADV-001175 | Closed | 16 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-16 | HGP-TRANSMIT-000043 |  | Trade Partner | Transmittal-IFC Curtain wall FT01 Performance mock up test report | 0 | 1 | 0 | NA | APPROVED | [5 empty] | KPTG-IntCorr-001717 |  | 2026-02-16 | KPTG-TRANSMIT-000441 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-04 | D&E-TRANSMIT-000297 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - GROUND - EQUIPMENT & PLINTHS LAYOUT - ZONE 2 | 5 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 3445 | 2025-12-04 |  |  | 2026-01-23 | 2026-01-23 | KPTG-TRANSMIT-011890 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-13 | 4DW-TRANSMIT-000086 | NA | Consultant | Level 01 Updates | 7 | 0 | 0 | NA | APPROVED | 2026-02-14 | NA | 559 | 2026-02-18 |  |  | 2026-02-16 | 2026-02-16 | KPTG-SADV-003050 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-04 | INGEN3D-TRANSMIT-000003 | NA | Trade Partner | Level 2 - Cast in Dowels | 15 | 0 | 0 | NA | APPROVED | 2026-02-03 | WF-000139 | NA | 2026-02-06 |  |  | 2026-02-13 | 2026-02-13 | KPTG-TRANSMIT-000444 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-16 | HEXA-TRANSMIT-000002 | NA | Trade Partner | B08 - Mechanical Services Drawings for Review | 3 | 0 | 0 | NA | APPROVED | 2026-02-16 | NA | 297 | 2026-02-27 |  |  |  | 2026-02-20 | DRAFT-008937 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-13 | DI-TRANSMIT-000147 | NA | Consultant | Updated Title blocks | 3 | 0 | 0 | NA | APPROVED | 2026-02-13 | NA | 293 | 2026-02-16 |  |  |  | 2026-02-16 | KAPITOL-TRANSMIT-001092 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-16 | NXT-TRANSMIT-001287 | NA | Trade Partner | NextDC M3 Stage4 LVSB - CSMS Var Proposal and TS | 2 | 0 | 0 | NA | APPROVED | 2026-02-16 | WF-004297 |  | 2026-03-03 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-11-28 | SMEPS-TRANSMIT-000076 |  | Trade Partner | Inground Drawings - IFA Rev.F | 3 | 0 | 0 | NA | APPROVED | 2026-02-16 | WF-000093 | [5 empty] | 2026-02-16 | KPTG-TRANSMIT-000444 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-16 | SMEPS-TRANSMIT-000115 | SPARK-CRFI-KPG-000168 | Trade Partner | IFA: Containment and Legend of Symbols drawings | 7 | 0 | 0 | NA | APPROVED | 2026-02-16 | WF-000202 | 187 | 2026-02-23 |  | Bim360 review changed - Coordinator change |  | 2026-03-24 | KPTG-TRANSMIT-000571 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-06 | D&E-TRANSMIT-000380 | NA | Trade Partner | Re: SFN Valves - Issued for Approval | 0 | 3 | 0 | NA | APPROVED |  | NA | [5 empty] | 2026-02-16 | KPTG-TRANSMIT-012940 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-16 | KEECEPRO-TRANSMIT-000023 | NA | Trade Partner | Re: DB Shop Drawings | 2 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-02-16 | DRAFT-008814 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-16 | Jangho-TRANSMIT-000006 | NA | Trade Partner | 671C- VMU NO.2 & NO.3 Shop drawings REV.0 | 41 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected, Drawings are not registered and properly; All sheets combined into one PDF and transmitted. KPTG-SADV-000795 |  | 2026-02-16 | KPTG-SADV-000795 | Closed | 41 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-04 | D&E-TRANSMIT-000299 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - LOWER GROUND - MECHANICAL DUCT LAYOUT - ZONES 3-5 | 3 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 3435 | 2025-12-11 |  |  | 2026-03-11 | 2026-03-12 | KPTG-TRANSMIT-014224 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-16 | Jangho-TRANSMIT-000007 | NA | Trade Partner | 671 Chapel St Project PMU shop drawings Rev00 | 40 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected, Drawings are not registered and properly; All sheets combined into one PDF and transmitted. KPTG-SADV-000793 |  | 2026-02-16 | KPTG-SADV-000793 | Closed | 40 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-16 | Jangho-TRANSMIT-000008 | NA | Trade Partner | Jangho-TRANSMIT-000008 671 Chapel St Project PMU shop drawings Rev00 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect document number and title. KPTG-SADV-000794 |  | 2026-02-16 | KPTG-SADV-000794 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-16 | Auspan-TRANSMIT-000083 | NA | Trade Partner | Precast shop drawings for construction. Basement. | 42 | 0 | 0 | NA | APPROVED | 2026-02-16 | NA | NA |  |  | No Review required, Register and circulate. |  | 2026-02-16 | KPTG-TRANSMIT-000621 | Closed | 42 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-16 | Auspan-TRANSMIT-000084 | NA | Trade Partner | Precast shop drawings for approval. Ground floor | 31 | 0 | 0 | NA | APPROVED | 2026-02-16 | WF-000203 | 358 | 2026-02-23 |  |  |  | 2026-02-19 | KPTG-TRANSMIT-000667 | Closed | 31 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-16 | Auspan-TRANSMIT-000085 | NA | Trade Partner | : Precast lift shaft panels for approval. | 4 | 0 | 0 | NA | APPROVED | 2026-02-16 | WF-000204 | 361 | 2026-02-23 |  |  |  | 2026-02-17 | KPTG-TRANSMIT-000642 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-16 | RDSBIM-TRANSMIT-000220 | NA | Trade Partner | ROOF PARTITION WALL KEY PLAN AND ELEVATION | 10 | 0 | 0 | NA | APPROVED | 2026-02-16 | NA | 2100 | 2026-02-18 |  |  |  | 2026-02-23 | KPTG-TRANSMIT-013360 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-12 | Tradetec-TRANSMIT-000356 | NA | Trade Partner | IFC - Stage 2 - CP14, LVP18, LVP21 | 3 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 3796 | 2026-02-16 |  |  | 2026-02-12 | 2026-02-17 | KPTG-TRANSMIT-013017 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-16 | ADP-TRANSMIT-000176 | NA | Consultant | Stage 4 Services IFC Issue (Power - roof roof top containment layouts | 6 | 0 | 0 | NA | APPROVED | 2026-02-16 | NA | 2103 | 2026-02-18 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-013413 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-12 | ACG-TRANSMIT-000046 | NA | Trade Partner | M3 - S2 Camera Pole Sample | 0 | 1 | 0 | NA | APPROVED | 2026-02-12 | WF-004236 | NA | 2026-02-19 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-014435 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-16 | HDRAus-TRANSMIT-000397 | NA | Consultant | Stage 4 Updated drawings and Cad | 15 | 0 | 0 | NA | APPROVED | 2026-02-16 | NA | 2107 | 2026-02-18 |  |  |  | 2026-02-17 | KPTG-TRANSMIT-013046 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-11-27 | RBG-TRANSMIT-000035 | NA | Consultant | Latest Structural Documentation - Columns - Issue for certification | 6 | 0 | 0 | KPTG-IntCorr-000233 | APPROVED |  | NA | NA |  | 0 | As advised by Kapitol No review required. |  | 2025-11-27 | NA | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-01 | JCBa-TRANSMIT-000038 | NA | Consultant | CAPPING BEAM ELEVATIONS - SHEET 2 UPDATE | 1 | 0 | 0 | NA | APPROVED | 2025-12-01 | WF-000074 | 144 | 2025-12-03 |  |  |  | 2025-12-08 | KPTG-TRANSMIT-000268 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-04 | Stowe-A-TRANSMIT-000397 | NA | Trade Partner | STOWE - TECH DATA SUBMISSION - SCADA FIBRE - 04.12.2025 | 0 | 1 | 0 | NA | APPROVED | 2025-12-04 | WF-003496 | NA | 2025-12-16 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-12 | HDRAus-TRANSMIT-000390 | NA | Consultant | Site Wide - Architectural Documentation - Finishes Schedules | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-02-12 | KPTG-TRANSMIT-012753 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-15 | TIVINTL-TRANSMIT-000024 | NA | Trade Partner | SRC-Tivoli-Updated joinery drawings | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-12 | PFP PL-TRANSMIT-000065 | NA | Trade Partner | Schematic IFC | 1 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 3798 | 2026-02-19 |  |  | 2026-03-11 | 2026-03-12 | KPTG-TRANSMIT-014214 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-16 | crossfir-TRANSMIT-000046 | NA | Trade Partner | Wet Fire - Level 07, IFC | 2 | 0 | 0 | NA | APPROVED | 2026-02-16 | WF-000932 | 542 | 2026-02-24 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-16 | JCBa-TRANSMIT-000209 | NA | Consultant | POD'S SHAFT LINER | 2 | 0 | 0 | NA | APPROVED | 2026-02-16 | WF-000933 | 543 | 2026-02-23 |  |  | 2026-02-24 | 2026-02-24 | KPTG-DA-002425 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-12 | DS-TRANSMIT-000097 | NA | Trade Partner | HYD SITE - DRAINAGE | 1 | 0 | 0 | NA | APPROVED | 2026-02-12 | NA | 3801 | 2026-02-19 |  |  | 2026-03-11 | 2026-03-12 | KPTG-TRANSMIT-014218 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-12 | NXT-TRANSMIT-001278 | NA | Client | EAE Fire Barrier Penetration CCR and KX | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-02-12 | KPTG-TRANSMIT-012770 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-11 | NXT-TRANSMIT-001272 | NA | Consultant | CRAC- Revised GA drawing for review + Tech data as IFC submission | 4 | 0 | 0 | NA | APPROVED | 2026-02-11 | -004230 |  | 2026-02-16 |  |  |  | 2026-02-16 | KPTG-TRANSMIT-012897 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-28 | D&E-TRANSMIT-000352 | NA | Trade Partner | Stage 2 Cx Scripts - Issued for review | 0 | 16 | 0 | NA | APPROVED | 2026-02-12 | WF-004248 | NA | 2026-02-23 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-013105 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-12 | PROLMC-TRANSMIT-000020 | NA | Trade Partner | Proline updated shop drawings 12-2-26 | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Document M3-ARC-PRO-SDRG-B-0201-3006 does not have a revision number or revision history. |  | 2026-02-12 | KPTG-DA-004831 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-04 | D&E-TRANSMIT-000300 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - ROOF MECHANICAL PIPE LAYOUT - ZONE 1, 3 & 5 | 3 | 0 | 0 | NA | APPROVED | 2025-12-04 | NA | 3442 | 2025-12-11 |  |  | 2026-01-23 | 2026-01-23 | KPTG-TRANSMIT-011882 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-12 | HDRAus-TRANSMIT-000391 | NA | Consultant | M3 SW - Security Treatment of Service Penos | 7 | 0 | 0 | NA | REJECTED | [5 empty] | Stage 2 documents and Sitewide documents in same transmittals |  | 2026-02-12 | KPTG-DA-004835 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-13 | Stowe-A-TRANSMIT-000480 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - HS1 OFFICE SMALL POWER LAYOUT & COMMUNICATION DEVICE - 13.02.2026 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | ELC and TEL documents in same transmittal |  | 2026-02-13 | KPTG-DA-004853 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-10 | D&E-TRANSMIT-000387 | NA | Trade Partner | BMS Functional Test Scripts - Issued for Approval | 0 | 4 | 0 | NA | APPROVED | 2026-02-13 | WF-004261 | NA | 2026-02-24 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-013103 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-28 | INGEN3D-TRANSMIT-000681 | NA | Consultant | Acoustic Wall | 36 | 0 | 0 | NA | APPROVED | 2026-01-29 | 004014 |  |  |  | TOTAL 34 DOCUMENTS AND 2 TD. 4 DOC ALREADY CLOSED AND REMAIN 30 CLOSED IN HERE |  | 2026-02-16 | KPTG-TRANSMIT-012969 | Closed | 30 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-13 | SMEPS-TRANSMIT-000179 | NA | Trade Partner | JEMENA EASEMENT - SECTION/DETAIL | 2 | 0 | 0 | NA | APPROVED | 2026-02-13 | WF-004272 | NA | 2026-02-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-13 | SMEPS-TRANSMIT-000178 | NA | Trade Partner | Stage 2 - Lightning protection IFC | 1 | 0 | 0 | NA | APPROVED | 2026-02-13 | NA | 3804 | 2026-02-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-13 | HDRAus-TRANSMIT-000393 | NA | Consultant | Site Wide - Architectural Documentation - ACC Comments | 14 | 0 | 0 | NA | APPROVED | 2026-02-13 | NA | 3806 | 2026-02-17 |  |  | 2026-02-23 | 2026-02-24 | KPTG-TRANSMIT-013453 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-16 | NCFGroup-TRANSMIT-000023 | NA | Trade Partner | S9-11 ISG Pile Design Drawings | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Need to revise the drawings KPTG-SADV-001187 |  | 2026-02-16 | KPTG-SADV-001187 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-16 | DRLL-TRANSMIT-000068 | NA | Trade Partner | Battery Room modules - Flooding Sensor Detector Tech Data IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC-Distribution only |  | 2026-02-20 | KPTG-TRANSMIT-002617 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-16 | D&E-TRANSMIT-000339 | NA | Trade Partner | MaxCool Main Panel L3 Cx Script - Issued for review | 0 | 1 | 0 | NA | APPROVED | 2026-02-16 | WF-000941 | NA | 2026-02-23 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-002607 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-04 | Hames-TRANSMIT-000082 | NA | Consultant | RCP & GF RLS FC | 30 | 0 | 0 | NA | APPROVED | 2025-12-05 | NA | 695 | 2025-12-09 |  |  | 2025-12-10 | 2025-12-10 | KPTG-TRANSMIT-002237 | Closed | 30 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-16 | DRLL-TRANSMIT-000069 | NA | Trade Partner | Battery Room Modules Mechanical Drawings IFC 04 | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC-Distribution only |  | 2026-02-17 | KPTG-TRANSMIT-002573 | Closed | 10 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-16 | KPTG-IntCorr-002854 | NA | Trade Partner | Movement joint cover plate - Unison Dz H | 0 | 2 | 0 | KPTG-IntCorr-002860 | APPROVED | 2026-02-17 | WF-000943 | NA | 2026-02-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-16 | PCForm-TRANSMIT-000058 | NA | Trade Partner | Level 2 to 10 - Issued for Construction | 49 | 0 | 0 | NA | APPROVED | 2026-02-16 | NA | 565 | 2026-02-23 |  | As per the direction from the Ms. Ashlin, We void this BIM-565#, Trade will submit latest revision |  | 2026-02-27 | KPTG-SADV-003240 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-16 | Auspan-TRANSMIT-000050 | NA | Trade Partner | Shop drawings issued for construction | 17 | 0 | 0 | NA | APPROVED | 2026-02-16 | NA | 561 | 2026-02-19 |  |  |  | 2026-02-19 | KPTG-SADV-003129 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-16 | Auspan-TRANSMIT-000051 | NA | Trade Partner | Revised shop drawings issued for approval | 7 | 0 | 0 | NA | APPROVED | 2026-02-16 | NA | 564 | 2026-02-23 |  |  | 2026-03-02 | 2026-03-03 | KPTG-SADV-003283 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-16 | 4DW-TRANSMIT-000087 | NA | Consultant | Structural Drawing Updates | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Dwfx file has not provided to us , request to submit |  | 2026-02-16 | KPTG-SADV-003061 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-16 | fjc-TRANSMIT-000134 | NA | Consultant | Architecturals - Ground Design Updates | 31 | 0 | 0 | NA | APPROVED | 2026-02-16 | NA | 563 | 2026-02-19 |  |  |  | 2026-02-17 | KPTG-SADV-003094 | Closed | 31 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-16 | KETE-TRANSMIT-000113 | NA | Trade Partner | Kete - Tower Shop Drawing Resubmission IFA 03 | 53 | 0 | 0 | KPTG-IntCorr-000709 | APPROVED | 2026-02-18 | NA | 570 | 2026-02-23 |  | Kapitol advice awaits: KPTG-IntCorr-000709 |  | 2026-03-17 | KPTG-SADV-003457 | Closed | 53 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-16 | 4DW-TRANSMIT-000089 | NA | Consultant | Minor Drawing Update | 1 | 0 | 0 | NA | REJECTED | [5 empty] | DWFX FILE HAS NOT GIVEN, REQUESTED TO SUBMIT |  | 2026-02-16 | KPTG-SADV-003071 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-16 | Highbu-TRANSMIT-000125 | NA | Trade Partner | Stainless steel 316 bib-cock cold water lockable hose tap sample | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document Numbering is incorrect, requested to resubmit |  | 2026-02-16 | KPTG-SADV-003696 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-04 | D&E-TRANSMIT-000298 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - ROOF - BUILDERS WORKS LAYOUT - B2 | 1 | 0 | 0 | NA | APPROVED | 2025-12-05 | NA | 3454 | 2025-12-12 |  |  | 2026-01-23 | 2026-01-23 | KPTG-TRANSMIT-011866 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-16 | Normark-TRANSMIT-000047 | NA | Trade Partner | Shop Drawing- Irrigation revision 2 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Wrongly attached shop drawings, requested to resubmit |  | 2026-02-16 | KPTG-IntCorr-005013 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-16 | Normark-TRANSMIT-000048 | NA | Trade Partner | NMK-LA-SPD-034- Irrigation System Layout- for approval | 1 | 0 | 0 | NA | APPROVED | 2026-02-16 | NA | 443 | 2026-02-23 |  | Revision has not mentioned in the drawing | 2026-03-03 | 2026-03-06 | KPTG-SADV-003824 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-16 | Normark-TRANSMIT-000049 | NA | Trade Partner | NMK-LA-SPD-034- Irrigation System Layout- for approval- revision version | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Duplicates of drawing which transmitted in Normark-TRANSMIT-000049 |  | 2026-02-16 | KPTG-SADV-003711 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-16 | CLADC-TRANSMIT-000018 | NA | Trade Partner | Timber dowel handrail shop drawings | 2 | 0 | 0 | NA | REJECTED | [5 empty] | DOCUMENT NUMBER HAS NOT FULLY MENTIONED IN THE DRAWING, HENCE, REQUESTED TO RESUBMIT |  | 2026-02-16 | KPTG-SADV-003710 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2026-02-16 | D&E-TRANSMIT-000028 | NA | Trade Partner | NextDC M3 DHA6 Updated As-Builts | 1 | 0 | 0 | NA | APPROVED | [5 empty] | AS-Built, No review required |  | 2026-02-16 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-16 | Hames-TRANSMIT-000117 | NA | Consultant | NEXTDC D1 Stage 2 - Services Enclosure | 1 | 0 | 0 | Clarifications from Will required - KPTG-IntCorr-001001 | APPROVED | 2026-02-17 | NA | 980 | 2026-02-20 |  |  | 2026-02-24 | 2026-02-25 | KPTG-TRANSMIT-002945 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-16 | Hames-TRANSMIT-000118 | NA | Consultant | PHASE 1 - GENERAL ARRANGEMENT PLAN -LEVEL 5 PLANT | 1 | 0 | 0 | NA | APPROVED | 2026-02-16 | NA | 978 | 2026-02-19 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-002921 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-16 | ZIA-TRANSMIT-000022 | NA | Trade Partner | CSMS - Samples | 0 | 3 | 0 | KPTG-IntCorr-001002 | APPROVED | 2026-03-06 | WF-000890 | NA | 2026-03-10 |  | Clarifications fromHarry required - - 2 docs processed - 1 revised | 2026-03-20 | 2026-03-20 | KPTG-WTRAN-001828, KPTG-WTRAN-001829 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-17 | IDS-TRANSMIT-000009 | NA | Trade Partner | HFF - Ground Level Zone 1 & 2 | 1 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 298 | 2026-03-02 |  | As per Alex - void review 298 as it the drawing is being superseded |  | 2026-02-25 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-17 | KPTG-WTRAN-007799 | NA | Trade Partner | Slim Deck PARAPET DECKING CUTTING | 0 | 3 | 0 | NA | APPROVED | 2026-02-17 | WF-004305 |  | 2026-02-20 |  |  |  | 2026-02-17 | KPTG-TRANSMIT-013028 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-05 | Stowe-A-TRANSMIT-000398 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - ROOF LIGHTING - 05.12.2025 | 4 | 0 | 0 | NA | APPROVED | 2025-12-05 | NA | 3452 | 2025-12-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-17 | ADP-TRANSMIT-000202 | NA | Consultant | Fwd: Hydraulic drawings NLIU (0401 Series) | 8 | 0 | 0 | NA | APPROVED |  | NA |  |  |  | For information only - |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-16 | WAM-TRANSMIT-000712 | NA | Consultant | WAM ARCH - DD Update - Ground Floor CSP | 2 | 0 | 0 | NA | APPROVED | 2026-02-16 | WF-000173 | 264 | 2026-02-19 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-000517 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-16 | WAM-TRANSMIT-000713 | NA | Consultant | WAM ARCH - DD Update - GA Plans | 47 | 0 | 0 | NA | APPROVED | 2026-02-16 | WF-000172 | 263 | 2026-02-19 |  |  |  | 2026-02-19 | KPTG-TRANSMIT-000516 | Closed | 47 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-16 | WAM-TRANSMIT-000714 | NA | Consultant | Common Areas 80%DD | 23 | 0 | 0 | Rejected - KPTG-TRANSMIT-000449 | REJECTED | [5 empty] | Rejected - KPTG-TRANSMIT-000449 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-16 | PCForm-TRANSMIT-000070 | NA | Trade Partner | Sample submissions | 0 | 4 | 0 | KPTG-IntCorr-000351 | APPROVED | 2026-02-17 | WF-000174 | NA | 2026-02-20 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-000531 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-17 | Tradetec-TRANSMIT-000359 | NA | Trade Partner | IFC - Stage 4 - CP36 | 1 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 2112 | 2026-02-25 |  |  |  | 2026-02-17 | KPTG-IntCorr-009480 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-16 | HVHD-TRANSMIT-000001 | NA | Consultant | Upfront Carbon Report | 0 | 1 | 0 | NA | APPROVED | 2026-02-16 | WF-000170 | NA | 2026-02-17 |  |  |  | 2026-02-17 | KPTG-TRANSMIT-000476 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-16 | WAM-TRANSMIT-000715 | NA | Consultant | WAM ARCH - DD Update - A09 Plans on CAD format | 18 | 0 | 0 | NA | APPROVED | 2026-02-16 |  |  |  |  | CAD Files - Rev. Checked and registered |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-17 | NXT-TRANSMIT-001290 | NA | Trade Partner | ABB PDUs - AU-10025007 M3-C-Stage 4 / Ph1 - Shop drawings | 8 | 0 | 0 | NA | APPROVED | 2026-02-17 | WF-004306 | NA | 2026-03-11 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-013668 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-10-27 | SMEPS-TRANSMIT-000045 |  | Trade Partner | Shop Drawings for Review - Power & Comms Level 1 (A) | 8 | 0 | 0 | NA | APPROVED | 2026-02-17 | WF-000203 |  | 2026-02-17 |  |  |  | 2026-02-17 | KPTG-TRANSMIT-000448 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-05 | Stowe-A-TRANSMIT-000399 | NA | Trade Partner | Stowe - Tech Data Submission - LV Submains | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | TD with IFC status | 2025-12-05 | 2025-12-05 | KPTG-TRANSMIT-010625 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-08 | ARCST-TRANSMIT-000145 | NA | Trade Partner | C1 Switchroom Upper Roof - Issued for Approval | 124 | 0 | 0 | NA | APPROVED | 2026-01-16 | WF-003834 |  | 2026-02-16 |  | 95 DOCUMENTS CLOSED FIRST AND 1 CLOSED SECONDLY |  | 2026-02-16 | KPTG-TRANSMIT-012938,KPTG-TRANSMIT-012968 | Closed | 96 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-01-19 | TATE_-TRANSMIT-000002 | NA | Trade Partner | MEL11 HAC Shop Drawings | 15 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Latest Revision 2 is submitted for approval |  | 2026-01-19 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-01-22 | Appselec-TRANSMIT-000001 | NA | Trade Partner | Tech Data Submissions | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Document Number of Technical Data are found incorrect. requested them to resubmit. |  | 2026-01-23 | KPTG-TRANSMIT-000001 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-01-27 | Appselec-TRANSMIT-000002 | NA | Trade Partner | Tech Data Submissions | 0 | 2 | 0 | NA | REJECTED | [5 empty] | As per the comment from Mr. Will Mason, it is noted that Discipline of Documents are missed from the documents, requested to resubmit |  | 2026-01-27 | KPTG-IntCorr-000005 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-01-27 | Appselec-TRANSMIT-000003 | NA | Trade Partner | Tech Data No Longer In Use | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | NO LONGER IN USE ,JUST FOR INFORMATION. |  | 2026-01-27 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-17 | IVS-TRANSMIT-000334 | NA | Consultant | Stage 4 - Future Link drawings (Revised Construction Issue) | 2 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 2114 | 2026-02-20 |  |  |  | 2026-02-23 | KPTG-TRANSMIT-013324 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-17 | Nilsen3-TRANSMIT-000027 | NA | Trade Partner | M3-HV-NIL-SA-S-0301-0019 Interface Panel | 0 | 1 | 0 | NA | APPROVED | 2026-02-17 | WF-004308 | NA | 2026-03-03 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-014080 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-12 | SMEPS-TRANSMIT-000080 | NA | Trade Partner | SME Shop Drawing Electrical IFA 2 | 1 | 0 | 0 | NA | APPROVED | 2026-02-17 | WF-000138 | NA | 2026-02-20 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-000221 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-01-30 | Appselec-TRANSMIT-000004 | NA | Trade Partner | LV Cable Tech Data Submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | INCORRECT DOCUMENT NUMBERING, REQUESTED TO RESUBMIT |  | 2026-02-03 | KPTG-SADV-000012 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-09 | RDSBIM-TRANSMIT-000010 | NA | Trade Partner | 671CHP LEVEL 01 CONCRETE PROFILE PLAN AND SECTIONS - ACC#230 | 3 | 0 | 0 | NA | APPROVED | 2026-01-27 | NA | 230 | 2026-01-29 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-000405 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-05 | RBG-TRANSMIT-000038 | NA | Consultant | Latest Structural Documentation Issued for Construction - Insitu Core Wall | 6 | 0 | 0 | NA | APPROVED | 2025-12-05 | WF-000076 | 142 | 2025-12-09 |  | Review Void |  | 2025-12-18 | NA | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-13 | RBG-TRANSMIT-000053 | NA | Consultant | Latest Structural Documentation Issued for Construction - Retention Update | 4 | 0 | 0 | NA | APPROVED | 2026-02-13 | NA | 264 | 2026-02-16 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000531 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-01-30 | Appselec-TRANSMIT-000005 | NA | Trade Partner | Tech Data Issued For Approval | 0 | 22 | 0 | NA | REJECTED | [5 empty] | Shop drawings are attached with technical data, requested to retransmit all these tech dara again |  | 2026-02-03 | KPTG-SADV-000011 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-13 | B Smart-TRANSMIT-000055 | NA | Consultant | B Smart-TRANSMIT-000055: 251002_Facade IFC Drawing Updates | 20 | 0 | 0 | NA | APPROVED | 2026-02-13 | NA | 266 | 2026-02-16 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-000556 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-13 | B Smart-TRANSMIT-000057 | NA | Consultant | A13 | 48 | 0 | 0 | NA | APPROVED | 2026-02-13 | NA | 268 | 2026-02-16 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-000762 | Closed | 48 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-02 | Appselec-TRANSMIT-000006 | NA | Trade Partner | Tech Data Submission (MV Cable & Lighting) | 0 | 2 | 0 | NA | REJECTED | [5 empty] | INCORRECT DOCUMENT NUMBERING, REQUESTED TO RESUBMIT |  | 2026-02-03 | KPTG-SADV-000010 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-13 | B Smart-TRANSMIT-000056 | NA | Consultant | A14, A16, A18 IFC | 34 | 0 | 0 | NA | APPROVED | 2026-02-13 | NA | 270 |  |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-000712 | Closed | 34 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-16 | PFP PL-TRANSMIT-000067 | NA | Trade Partner | ITP-08 Pre action & Water Mist | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-02-16 | KPTG-TRANSMIT-012936 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-03 | Appselec-TRANSMIT-000007 | NA | Trade Partner | Appselec Tech Data Submission | 0 | 27 | 0 | NA | REJECTED | [5 empty] | ATTACHEMENT OF THREE TECHNICAL DATA ARE SHOP DRAWING, REQUESTED TO RETRANSMIT |  | 2026-02-05 | KPTG-SADV-000015 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-16 | Stowe-A-TRANSMIT-000481 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - GF & L1 CONTAINMENT - 16.02.2026 | 4 | 0 | 0 | NA | REJECTED | [5 empty] | The reason for the transmittal is wrong. |  | 2026-02-16 | KPTG-DA-004882 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-05 | Stowe-A-TRANSMIT-000400 | NA | Trade Partner | Stowe - Tech Data Submission - MDB CMDB SWITCHGEAR | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | TD IFC issue | 2025-12-05 |  | KPTG-TRANSMIT-010628 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-06 | Appselec-TRANSMIT-000008 | NA | Trade Partner | LV Cable Substitution Request | 0 | 1 | 0 | NA | APPROVED | 2026-02-09 | WF-000008 | NA | 2026-02-12 |  |  | 2026-02-12 | 2026-02-12 | KPTG-TRANSMIT-000033 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-16 | D&E-TRANSMIT-000395 | NA | Trade Partner | MaxCool Main Panel L3 Cx Script - Issued for review | 0 | 1 | 0 | NA | APPROVED | 2026-02-16 | WF-004291 | NA | 2026-02-24 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-013223 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-12 | Appselec-TRANSMIT-000009 | NA | Trade Partner | Electrical Shop Drawings | 3 | 0 | 0 | NA | REJECTED | [5 empty] | title of drawings has not been mentioned completely, requested to resubmit |  | 2026-02-13 | KPTG-IntCorr-000021 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-17 | ADP-TRANSMIT-000246 | NA | Consultant | Re: MEL741 - Stage 4 Updated Mechanical drawing | 1 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 2116 | 2026-02-20 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-013376 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-13 | Appselec-TRANSMIT-000011 | NA | Trade Partner | Tech Data No Longer in Use | 0 | 3 | 0 | NA | APPROVED | [5 empty] | NO LONGER IN USE,JUST FOR INFORMATION |  | 2026-02-13 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-13 | Appselec-TRANSMIT-000013 | NA | Trade Partner | Electrical Shop Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-02-19 | WF-000015 | NA | 2026-02-24 |  |  | 2026-03-03 | 2026-03-04 | KPTG-TRANSMIT-000059 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-01-22 | TATE_-TRANSMIT-000003 | NA | Trade Partner | MEL11 HAC Shop Drawings REV2 | 15 | 0 | 0 | NA | APPROVED | 2026-01-22 | WF-000003 | NA | 2026-01-27 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-000034 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-05 | JCI-TRANSMIT-000001 | NA | Trade Partner | JCI BAS DOCUMENT TRANSMITTAL | 0 | 36 | 0 | NA | APPROVED | 2026-02-09 | WF-000010 | NA | 2026-02-12 |  |  | 2026-03-10 | 2026-03-18 | KPTG-TRANSMIT-000142 | Closed | 37 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-05 | Stowe-A-TRANSMIT-000401 | NA | Trade Partner | Stowe - Tech Data Submission - WHIP LABEL CABLES | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | TD IFC issue |  | 2025-12-05 | KPTG-TRANSMIT-010631 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-16 | D&E-TRANSMIT-000397 | NA | Trade Partner | D&E Cx Plan - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-02-16 | KPTG-TRANSMIT-012935 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-06 | Auspan-TRANSMIT-000067 | NA | Trade Partner | Precast shop drawings for approval. Basement | 26 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected and returned to the Trade partner due to sheet error . KPTG-DA-000677 |  | 2026-02-06 | KPTG-DA-000677 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-06 | Auspan-TRANSMIT-000068 | NA | Trade Partner | Precast shop drawings for approval. Basement. | 56 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected and returned to the Trade partner due to incorrect sheet number . KPTG-DA-000678 |  | 2026-02-06 | KPTG-DA-000678 | Closed | 56 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-28 | D&E-TRANSMIT-000352 | NA | Trade Partner | Stage 2 Cx Scripts - Issued for review | 0 | 1 | 0 | NA | APPROVED | 2026-02-16 | WF-004295 | NA | 2026-02-24 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-013225 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-06 | ETNInd-TRANSMIT-000001 | NA | Trade Partner | MEL11 COLO4&5 EATON Equipment Handling/Preservation/Protection Guidelines/ Recommendations | 0 | 3 | 0 | NA | REJECTED | [5 empty] | DOCUMENT NUMBER OF TECHNICAL DATA ARE INCORRECT, REQUESTED TO RESUBMIT |  | 2026-02-07 | KPTG-SADV-000030 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-09 | Auspan-TRANSMIT-000069 | NA | Trade Partner | Auspan-TRANSMIT-000069: Rinco-RTRFI-000157: Re: Zone 3 RFI 19. Update IFCed shop drawings for construction. | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required, Update Register and circulate to all. KPTG-TRANSMIT-000563 |  | 2026-02-09 | KPTG-TRANSMIT-000563 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-16 | Tradetec-TRANSMIT-000357 | NA | Trade Partner | IFC - Stage 2 - CP7 | 1 | 0 | 0 | NA | APPROVED |  | NA | 3811 | 2026-02-20 |  |  | 2026-02-17 | 2026-02-17 | KPTG-TRANSMIT-013042 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-29 | D&E-TRANSMIT-000358 | NA | Trade Partner | Re: Victaulic Valves & Fittings - Issued for approval | 0 | 1 | 0 | NA | APPROVED | 2026-01-30 | WF-004030 |  | 2026-02-25 |  |  |  | 2026-02-17 | KPTG-TRANSMIT-012992 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-07 | SEAPBU-TRANSMIT-000001 | NA | Trade Partner | ASCO ATS Drawings for MEL11 COLO 4 & 5 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | DOCUMENT NUMBER OF ATTACHED DRAWING ARE MISMATCHED WITH WHAT TRANMITTED IN A TRANSMIT. |  | 2026-02-10 | KPTG-SADV-000039 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-02 | ZIA-TRANSMIT-000047 | NA | Trade Partner | CSMS M3 Stage 2 Interface Data Sheets | 0 | 1 | 0 | NA | APPROVED | 2026-02-16 | WF-004300 | NA | 2026-03-02 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-018935 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-05 | RBG-TRANSMIT-000039 | NA | Consultant | Latest Structural Documentation Issued for Construction - B4 Crane base update | 1 | 0 | 0 | NA | APPROVED | 2025-12-05 | WF-000077 | 144 | 2025-12-10 |  | Review void as advised during a meeting with Kapitol DM & PCs. |  | 2026-01-22 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-01-14 | KETE-TRANSMIT-000002 | NA | Trade Partner | submission – DIP shop drawings | 36 | 0 | 0 | NA | APPROVED | 2026-01-14 | WF-000126 | 247 | 2026-01-21 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-000564 | Closed | 56 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-16 | PFP PL-TRANSMIT-000068 | NA | Trade Partner | Commissioning Plan Rev B | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-02-16 | KPTG-TRANSMIT-012939 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-12 | TATE_-TRANSMIT-000004 | NA | Trade Partner | MEL11 SCEC SHOP DRAWINGS FOR APPROVAL | 43 | 0 | 0 | NA | REJECTED | [5 empty] | DISCIPLINE OF DOCUMENTS ARE NOT ALIGNED TO OUR STANDERD. |  | 2026-02-12 | KPTG-IntCorr-000020 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-16 | D&E-TRANSMIT-000396 | NA | Trade Partner | Mechanical IFC HS1 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | The date inside the revision history is an error. |  | 2026-02-16 | KPTG-DA-004887 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-17 | INGEN3D-TRANSMIT-000688 | NA | Trade Partner | I3D-378 Next DC M3 Stage 4 - Acoustic Wall - R19 - IFA Checked (17-02-2026) | 1 | 0 | 0 | NA | APPROVED | 2026-02-17 | WF-004310 |  | 2026-03-13 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-016423 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-17 | ARCST-TRANSMIT-000210 | NA | Trade Partner | C2 - Chemical Store Base Shop Drawings - Issued for Approval | 2 | 0 | 0 | NA | APPROVED | 2026-02-17 | WF-004312 | NA | 2026-03-13 |  |  | 2026-04-14 | 2026-04-14 | KPTG-TRANSMIT-015881 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-17 | ADP-TRANSMIT-000245 | NA | Consultant | Fwd: MEL741 - Stage 4 Electrical Specification | 0 | 2 | 0 | NA | REJECTED | [5 empty] | SPC files - For info |  | 2026-02-17 | KPTG-DA-004904 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-17 | D&E-TRANSMIT-000114 | SPARK-CRFI-KPG-000367 | Trade Partner | COMPRESSED AIR STATION | 0 | 1 | 0 | NA | APPROVED | 2026-02-17 | WF-000204 |  | 2026-02-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-17 | SKS Tech-TRANSMIT-000024 | NA | Trade Partner | SKS - L1E/L2E Alternative Light Fitting Submission | 0 | 1 | 0 | NA | APPROVED | 2026-02-17 | WF-004313 |  | 2026-03-10 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-17 | WilsonPD-TRANSMIT-000157 | SPARK-CRFI-KPG-000183 | Trade Partner | Hydraulic Layouts - Ground Level Zone B & C | 2 | 0 | 0 | NA | APPROVED | 2026-02-17 | WF-000205 | 125 | 2026-02-24 |  |  |  | 2026-03-25 | KPTG-TRANSMIT-000599 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-01 | Fyfe-TRANSMIT-000005 | NA | Consultant | Civil Building Set - For Approval | 9 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Transmittal rejected due to incorrect drawing attachment in Aconex. (KPTG-DA-000456) |  | 2025-12-01 | KPTG-DA-000456 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-05 | Stowe-A-TRANSMIT-000402 | NA | Trade Partner | Stowe - Tech Data Submission - Class 6 Earth Cabling | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2025-12-05 | KPTG-TRANSMIT-010634 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-17 | SMEPS-TRANSMIT-000259 | NA | Trade Partner | SME- UPREV -Electrical Services -Data Hall A7 Busduct Loading Matrix -TOB | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Previous Rev is in Review- sent back to originator |  | 2026-02-17 | KPTG-TRANSMIT-002586 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-17 | SMEPS-TRANSMIT-000260 | NA | Trade Partner | SME - BUSDUCT PROTECTION - IFC | 1 | 0 | 0 | NA | APPROVED |  | NA | 1387 |  |  | Terminated-requested by originator |  |  | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-17 | KEECEPRO-TRANSMIT-000024 | NA | Trade Partner | Re: DB Shop Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 299 | 2026-02-23 |  | Only the COM file needs to be reviewed |  | 2026-02-17 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-17 | SCP_NR-TRANSMIT-000090 | NA | Consultant | IFC Fire Drawings | 7 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 301 | 2026-02-19 |  |  |  | 2026-02-20 | DRAFT-008938 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-13 | KEECEPRO-TRANSMIT-000022 | NA | Trade Partner | Comms Data Sheets | 0 | 3 | 0 | NA | APPROVED | 2026-02-13 | WF-000374 |  | 2026-02-17 |  |  |  | 2026-02-17 | KAPITOL-TRANSMIT-001098 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-17 | JCBa-TRANSMIT-000210 | NA | Consultant | Bathroom Transition Details | 2 | 0 | 0 | NA | APPROVED | 2026-02-17 | WF-000934 | 544 | 2026-02-24 |  |  | 2026-02-24 | 2026-02-24 | KPTG-DA-002426 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-17 | OveArup-TRANSMIT-000028 | NA | Consultant | DL-ARP-4B3-DR-F22-0000-2 no longer in use | 1 | 0 | 0 | Rejected DRAFT-004197 | REJECTED | [9 empty] | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-17 | crossfir-TRANSMIT-000048 | NA | Trade Partner | Wet Fire- Level 09 , IFA | 2 | 0 | 0 | NA | APPROVED | 2026-02-17 | WF-000935 | 545 | 2026-02-24 |  | The kapittol review was void and change in the new revision |  | 2026-03-03 |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-17 | ccair-TRANSMIT-000091 | NA | Trade Partner | Fan Schedule for Acoustic Approval | 0 | 1 | 0 | NA | APPROVED | 2026-02-17 | WF-000936 | NA | 2026-02-24 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-13 | TTW-TRANSMIT-000093 | NA | Consultant | Drawing update - SPEC | 19 | 1 | 0 | Drawings submitted ACC | APPROVED | 2026-02-16 | NA | 265 | 2026-02-18 |  |  |  | 2026-02-19 | KPTG-TRANSMIT-000510 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-04 | OveArup-TRANSMIT-000016 | NA | Consultant | MECHANICAL SERVICES - 80% Issue for Construction | 51 | 0 | 0 | NA | APPROVED | 2025-12-05 | NA | 122 | 2025-12-10 |  |  | 2025-12-10 | 2025-12-11 | KPTG-TRANSMIT-000237 | Closed | 51 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-29 | KPTG-TRANSMIT-012031 | NA | Trade Partner | Paint Tech Data Submittal for Workflow | 0 | 11 | 0 | NA | APPROVED | 2026-01-29 | WF-004010 |  | 2026-02-16 |  |  |  | 2026-02-17 | KPTG-TRANSMIT-012998 | Closed | 10 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-17 | Stowe-A-TRANSMIT-000482 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - GF & L1 CONTAINMENT - 17.02.2026 | 4 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 3814 | 2026-02-26 |  |  | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-014889 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-17 | IVS-TRANSMIT-000335 | NA | Consultant | Stage 2 - Ground Floor Steel Stairs Certification Issue (revised as clouded) | 1 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 3816 | 2026-02-19 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-013372 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-17 | DS-TRANSMIT-000099 | NA | Trade Partner | Stage 2 - Site Fire and Water | 1 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 3818 | 2026-02-20 |  |  | 2026-02-18 | 2026-02-19 | KPTG-TRANSMIT-013185 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-16 | PARR-TRANSMIT-000118 | NA | Trade Partner | P2649 - KPG NDC M3 - Stage 2 - Fuel - CX L2, L3, and Commissioning Plan - FOA | 0 | 3 | 0 | NA | APPROVED | 2026-02-17 | WF-004315 | NA | 2026-02-26 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-013574 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-17 | WilsonPD-TRANSMIT-000101 | NA | Trade Partner | Balancing valve for approval | 0 | 1 | 0 | NA | APPROVED | 2026-02-17 | WF-000937 | NA | 2026-02-24 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-16 | PARR-TRANSMIT-000119 | NA | Trade Partner | P2649 - KPG NDC M3 - Stage 2 - Fuel - CX L2, L3, L4 - IFC | 0 | 5 | 0 | NA | APPROVED | 2026-02-17 | WF-004316 | NA | 2026-02-26 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-013350 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-17 | ETNInd-TRANSMIT-000085 | NA | Trade Partner | M3 Stage 2 – Commisioning Plan Revise & Resubmit | 0 | 2 | 0 | NA | APPROVED | 2026-02-17 | WF-004317 | NA | 2026-02-26 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-013346 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-02 | ARCST-TRANSMIT-000195 | NA | Trade Partner | Roof Walkway Steel Marking Plan - Updated | 1 | 0 | 0 | NA | APPROVED | 2026-02-17 | WF-004321 | NA | 2026-02-24 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-013972 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-17 | DS-TRANSMIT-000098 | NA | Trade Partner | Stage 2 - Site Fire and Water | 1 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 3821 | 2026-02-20 |  |  | 2026-03-10 | 2026-03-12 | KPTG-TRANSMIT-014205 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-05 | Stowe-A-TRANSMIT-000403 | NA | Trade Partner | Stowe-A-TRANSMIT-000403 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | TD IFC issue |  | 2025-12-05 | KPTG-TRANSMIT-010637 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-17 | KETE-TRANSMIT-000005 | NA | Trade Partner | : Kete - VMU Drawings Submission | 18 | 0 | 0 | NA | APPROVED | 2026-02-17 | WF-000208 | 363 | 2026-02-23 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-000762 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-17 | LVPG-TRANSMIT-000013 | NA | Trade Partner | LVPG-HY-TECH-016 - Poly Sleeve [B] | 0 | 1 | 0 | NA | APPROVED | 2026-02-17 | WF-000205 | NA | 2026-02-23 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-000698 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-17 | LVPG-TRANSMIT-000014 | NA | Trade Partner | - LVPG-HY-TECH-015 - Polilag [B] | 0 | 1 | 0 | NA | APPROVED | 2026-02-17 | WF-000206 | NA | 2026-02-23 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-000700 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-17 | LVPG-TRANSMIT-000017 | NA | Trade Partner | LVPG - Tech Data Submittals Silt Traps | 0 | 2 | 0 | NA | APPROVED | 2026-02-17 | WF-000207 | NA | 2026-02-23 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-000677 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-17 | KETE-TRANSMIT-000006 | NA | Trade Partner | : Kete - Additional Detail Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-02-17 | WF-000209 | 365 | 2026-02-23 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-000756 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-17 | Rinco-TRANSMIT-000030 | NA | Consultant | Structural Elevation drawing update | 11 | 0 | 0 | NA | APPROVED | 2026-02-17 | WF-000211 | 367 | 2026-02-19 |  |  |  | 2026-02-19 | KPTG-TRANSMIT-000651 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-17 | Auscool-TRANSMIT-000008 | NA | Trade Partner | Updated Camel Calculations for review | 0 | 1 | 0 | NA | APPROVED | 2026-02-17 | WF-000210 | NA | 2026-02-23 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-000719 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-17 | Electro-TRANSMIT-000002 | NA | Consultant | Common Areas Specialist Lighting IFC Documentation | 8 | 0 | 0 | NA | APPROVED | 2026-02-17 | 0 | 272 | 2026-02-19 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000525 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-17 | RDSBIM-TRANSMIT-000030 | NA | Trade Partner | 671CHP ¦ BASEMENT 2 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 279 | 2026-02-19 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-000493 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-17 | RDSBIM-TRANSMIT-000031 | NA | Trade Partner | : 671CHP ¦ BASEMENT 3 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 280 | 2026-02-19 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-000494 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-05 | Stowe-A-TRANSMIT-000404 | NA | Trade Partner | Stowe - Tech Data Submission - CUPBOARD B1-L-E | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | TD IFC issue |  | 2025-12-05 | KPTG-TRANSMIT-010640 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-28 | KPTG-TRANSMIT-012032 | NA | Trade Partner | Workflow Submittal for Epoxy Flooring | 0 | 1 | 0 | NA | APPROVED | 2026-01-29 | WF-004033 | NA | 2026-02-04 |  |  | 2026-02-01 | 2026-02-17 | KPTG-TRANSMIT-013011 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-17 | POTTSENG-TRANSMIT-000003 | NA | Trade Partner | : 671C: HYDRAULIC SERVICES - BASEMENT 4 INGROUND - DRAINAGE LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 274 | 2026-02-23 |  |  |  | 2026-02-19 | KPTG-TRANSMIT-000477 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-17 | RBG-TRANSMIT-000054 | NA | Trade Partner | : Structural Drawings for Blockwork – Issued for Certification | 8 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Drawings issued for information. Register updated. |  | 2026-02-17 | NA | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-17 | Tradetec-TRANSMIT-000358 | NA | Trade Partner | Re: IFA - Stage 4 (LVP44, LV45, CP34, CP35) | 4 | 0 | 0 | NA | REJECTED | [5 empty] | due to incorrect file contains |  | 2026-02-17 | KPTG-TRANSMIT-013004 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-17 | Altaire-TRANSMIT-000077 | NA | Trade Partner | NEXTDC M3S4 - Dry Fire MASDS Calculations (For Construction) (A) | 0 | 1 | 0 | NA | REJECTED | [5 empty] | qa rejected due to important fields missing |  | 2026-02-17 | KPTG-TRANSMIT-013009 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-17 | Tradetec-TRANSMIT-000361 | NA | Trade Partner | Re: IFA - Stage 4 - CP20 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | qa rejected due to incorrect document number mentioned in aconex |  | 2026-02-17 | KPTG-TRANSMIT-013022 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-17 | Tradetec-TRANSMIT-000362 | NA | Trade Partner | Re: Stage 4 South - HV Pits | 4 | 0 | 0 | NA | REJECTED | [5 empty] | qa rejected due to seems different document number mentioned in inside drawing |  | 2026-02-17 | KPTG-TRANSMIT-013037 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-17 | PARR-TRANSMIT-000120 | NA | Trade Partner | NDC M3 Stage 4 - Fuel - PUMP ROOM, CONTROL SYSTEM DRAWINGS | 9 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 2125 | 2026-02-25 |  | The WF has been terminated as requested by Peter Z |  | 2026-02-19 | KPTG-IntCorr-009624 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-17 | Tradetec-TRANSMIT-000363 | NA | Trade Partner | IFA - LVP44, LV45, CP34, CP35 | 4 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 2127 | 2026-02-25 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-014450 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-17 | SCP_NR-TRANSMIT-000091 | NA | Trade Partner | Power Pack - IFC Mechanical Issue | 8 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 302 | 2026-02-19 |  |  |  | 2026-02-18 | DRAFT-008876 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-05 | Stowe-A-TRANSMIT-000405 | NA | Trade Partner | Stowe - Tech Data Submission - ALTERNATIVE EARTHING CRIMP CONNECTOR | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | TD IFC issue |  | 2025-12-05 | KPTG-TRANSMIT-010644 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-17 | IVS-TRANSMIT-000333 | NA | Consultant | Stage 4 - Chemical Store & Fire Room Drawings Construction Issue | 2 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 2119 | 2026-02-19 |  |  |  | 2026-02-23 | KPTG-TRANSMIT-013309 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-17 | INGEN3D-TRANSMIT-000687 | NA | Consultant | I3D-378 Next DC M3 Stage 4 - Acoustic Wall - Priority 2 & 3 - IFC | 27 | 0 | 0 | NA | APPROVED | 2026-02-17 | 004325 |  | 2026-02-24 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-17 | SMEPS-TRANSMIT-000181 | NA | Trade Partner | SME - DRAWINGS IFA PART SUBMISSIONS | 2 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 2130 | 2026-02-17 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-016389 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-13 | SMEPS-TRANSMIT-000083 | NA | Trade Partner | SME Shop Drawing Electrical IFA 2 | 1 | 0 | 0 | NA | APPROVED | 2026-02-16 | WF-000130 | NA | 2026-02-23 |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-000179 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-13 | SMEPS-TRANSMIT-000084 | NA | Trade Partner | SMEPS-TRANSMIT-000084 | 8 | 0 | 0 | NA | APPROVED | 2026-02-16 | WF-000131 | NA | 2026-02-23 |  |  | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-000204 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-11 | TATE_-TRANSMIT-000017 | NA | Trade Partner | MEL05 COLO 4 SCEC WALL REVISION D (Speed Panel Updated) | 9 | 0 | 0 | NA | APPROVED | 2026-02-12 | WF-000112 | NA | 2026-02-19 |  |  | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-000198 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-12 | SIL-TRANSMIT-000023 | NA | Trade Partner | MEL05 C4 - 32PO-41735-T019 Technical Submittals | 0 | 1 | 0 | NA | APPROVED | 2026-02-16 | WF-000132 | NA | 2026-02-23 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-000267 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-17 | PPX-TRANSMIT-000015 | NA | Trade Partner | NEXTDC M3 – SMARDT CHILLERS - FD - 2025 - V1 | 0 | 1 | 0 | KPTG-IntCorr-002888 | APPROVED |  | NA | NA |  |  | IFC-Distribution only |  | 2026-02-18 | KPTG-TRANSMIT-002583 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-17 | PCForm-TRANSMIT-000078 | N/A | Trade Partner | Jumpform Concrete Envelopes - Stage 11 - Cores 6,7 & Lift - Issued for approval | 5 | 0 | 0 | NA | APPROVED | 2026-02-17 | WF-000244 | N/A | 2026-02-20 |  |  |  | 2026-02-17 | KPTG-TRANSMIT-000852 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-17 | WGAVIC-TRANSMIT-000064 | NA | Consultant | Structural Drawings - Stage 10 and 11 Ground Floor Pour Plans - Issued for Construction/Information | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required |  | 2026-02-17 | KPTG-TRANSMIT-000849 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-05 | Stowe-A-TRANSMIT-000406 | NA | Trade Partner | Stowe - Tech Data Submission - TYPE L3 FITTING | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | TD IFC issue |  | 2025-12-05 | KPTG-TRANSMIT-010655 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-17 | WSP ANZ-TRANSMIT-000046 | NA | Consultant | WSP - Building Services Documents - Issue for Tender - Fire | 80 | 0 | 0 | NA | APPROVED | 2026-02-20 | N/A | 332 | 2026-02-27 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-001068 | Closed | 80 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-17 | CLAD-TRANSMIT-000019 | NA | Trade Partner | Timber dowel shop drawings | 2 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 445 | 2026-02-24 |  |  |  | 2026-02-19 | KPTG-SADV-003736 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-17 | MCGC-TRANSMIT-000003 | NA | Trade Partner | Landscape Drawing Updates - CO2 Tank and Stairs | 6 | 0 | 0 | NA | REJECTED | [5 empty] | DOCUMENT NUMBERING ARE INCORRECT, REQUESTED TO RESUBMIT |  | 2026-02-17 | KPTG-SADV-003716 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-10 | KPTG-IntCorr-004764 | NA | Trade Partner | Western ramp handrail | 2 | 0 | 0 | NA | APPROVED | 2026-02-10 |  | 434 | 2026-02-16 |  |  | 2026-02-17 | 2026-02-17 | KPTG-SADV-003715 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-17 | RDSBIM-TRANSMIT-000154 | NA | Trade Partner | LINDRUM ¦ LEVEL 04 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 566 | 2026-02-24 |  |  | 2026-03-16 | 2026-03-17 | KPTG-SADV-003444 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-17 | RDSBIM-TRANSMIT-000155 | NA | Trade Partner | LINDRUM ¦ LEVEL 05 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 567 | 2026-02-24 |  |  | 2026-03-16 | 2026-03-17 | KPTG-SADV-003447 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-17 | RDSBIM-TRANSMIT-000156 | NA | Trade Partner | LINDRUM ¦ LEVEL-09 REFLECTED CEILING PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 568 | 2026-02-20 |  |  | 2026-03-19 | 2026-03-19 | KPTG-SADV-003500 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-17 | RDSBIM-TRANSMIT-000157 | NA | Trade Partner | LINDRUM ¦ LEVEL-11 REFLECTED CEILING PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 569 | 2026-02-20 |  |  | 2026-03-20 | 2026-03-24 | KPTG-SADV-003534 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-17 | Auscool-TRANSMIT-000074 | NA | Trade Partner | Outside Air Lourve | 0 | 1 | 0 | NA | APPROVED | 2026-02-17 | WF-000620 | NA | 2026-02-19 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-002021 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-17 | NXES-TRANSMIT-000045 | NA | Trade Partner | Re: GF Design Change Update - additional GF entry swing door pit for auto operator - URGENT actions | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per thge direction from Mr. Mark, we have transmitted this drawing into traders and consultants |  | 2026-02-17 | KPTG-IntCorr-000722 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2025-12-05 | DI-TRANSMIT-000129 | NA | Consultant | HFF - 100% DD Issue | 23 | 0 | 0 | NA | APPROVED | 2025-12-05 |  | 252 | 2025-12-08 |  |  |  | 2025-12-10 | KAPITOL-TRANSMIT-000905 | Closed | 23 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-17 | Metzone-TRANSMIT-000008 | NA | Trade Partner | Catch Deck - Scaffold Clash Update | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | kAPITOL ADVICE AWAITS:KPTG-IntCorr-000721 KPTG-IntCorr-000727 - As per the direction Ashlin, we updated document into document register only. No other action has suggested. |  | 2026-02-18 | KPTG-IntCorr-000727 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-18 | ACG-TRANSMIT-000049 | NA | Trade Partner | Fwd: M3 - Stage 3 ACG Shop Drawings IFC-1 | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | The drawings have been registered. As instructed (Kian), no further action has been taken |  | 2026-02-18 | KPTG-TRANSMIT-013060 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-18 | RDSBIM-TRANSMIT-000034 |  | Trade Partner | MWYCCB ¦ SITE STORAGE BUILDING GF & LEVEL 01 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-02-18 | WF-000208 | 126 | 2026-02-25 |  | As per lawdens advise no further action for this transmittal. | 2026-03-03 | 2026-03-03 |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-18 | Nilsen3-TRANSMIT-000029 | NA | Trade Partner | Re: NXM3S4 ¦ Nilsen ELC Shop Drawings - FOA | 4 | 0 | 0 | NA | APPROVED | 2026-02-18 | NA | 2133 | 2026-02-26 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-014574 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-18 | D&E-TRANSMIT-000115 |  | Trade Partner | FIRE DAMPER | 0 | 1 | 0 | NA | APPROVED | 2026-02-18 | WF-000209 |  | 2026-02-25 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-18 | D&E-TRANSMIT-000116 |  | Trade Partner | SPLIT AC SYSTEMS | 0 | 1 | 0 | NA | REJECTED | [5 empty] | revision 3 missing - KPTG-TRANSMIT-000453 |  | 2026-02-18 | KPTG-TRANSMIT-000453 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-18 | SKS Tech-TRANSMIT-000025 | NA | Trade Partner | Re: Ground Floor and Level 1 Lighting | 2 | 0 | 0 | NA | REJECTED | [5 empty] | IFA and IFC were submitted together |  | 2026-02-18 | KPTG-TRANSMIT-013063 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-18 | D&E-TRANSMIT-000117 | SPARK-CRFI-KPG-000540 | Trade Partner | CONTROL THERMOSTAT | 0 | 1 | 0 | NA | APPROVED | 2026-02-18 | WF-000210 |  | 2026-02-25 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-000523 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-18 | D&E-TRANSMIT-000118 | SPARK-CRFI-KPG-000540 | Trade Partner | CONTROLS MISCELLANEOUS | 0 | 1 | 0 | NA | APPROVED | 2026-02-18 | WF-000211 |  | 2026-02-25 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-000525 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-04 | WDes-TRANSMIT-000053 | NA | Consultant | Civil Construction Set C1 | 56 | 0 | 0 | NA | APPROVED | 2025-12-05 | WF -000791 | 496 | 2025-12-12 |  |  | 2025-12-15 | 2025-12-15 | KPTG-DA-002258 | Closed | 56 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-18 | Altaire-TRANSMIT-000078 | NA | Trade Partner | NEXTDC M3S4 - Dry Fire MASDS Calculations (For Construction) (A) | 0 | 1 | 0 | NA | APPROVED | 2026-02-18 | WF-004327 |  | 2026-03-11 |  |  |  | 2026-02-19 | KPTG-IntCorr-009630 -As requested by Zak | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-18 | D&E-TRANSMIT-000119 |  | Trade Partner | MWYCCB - LEVEL 1 - PENETRATION LAYOUT ZONE 6 & ZONE 7 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-02-18 | WF-000212 | 127 | 2026-02-25 |  | Review void - To update latest revision | 2026-02-26 | 2026-02-26 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-18 | SKS Tech-TRANSMIT-000026 | NA | Trade Partner | Typical Switchboard Sections | 1 | 0 | 0 | NA | APPROVED | 2026-02-18 | NA | 2140 | 2026-02-26 |  | As requested by Peter Z. - Reason: Updated drawing ready for submission. |  | 2026-03-04 | KPTG-IntCorr-010292 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-18 | D&E-TRANSMIT-000120 |  | Trade Partner | CONTROL FIELD CONTROLLERS | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Error in document number KPTG-TRANSMIT-000454 |  | 2026-02-18 | KPTG-TRANSMIT-000454 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-18 | D&E-TRANSMIT-000121 | SPARK-CRFI-KPG-000540 | Trade Partner | CONTROL NIAGRA MASTER | 0 | 1 | 0 | NA | APPROVED | 2026-02-18 | WF-000213 |  | 2026-02-25 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-000524 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-18 | Nilsen3-TRANSMIT-000030 | NA | Trade Partner | SUPA 80 Frame - SAMPLE | 0 | 1 | 0 | NA | APPROVED | 2026-03-03 | WF-004334 | NA | 2026-02-26 |  |  |  | 2026-02-24 | KPTG-TRANSMIT-013452 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-18 | D&E-TRANSMIT-000122 |  | Trade Partner | MWYCCB - LEVEL 1 - PENETRATION LAYOUT ZONE 5 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-02-18 | WF-000214 | 128 | 2026-02-25 |  | Review terminated as per peter advise To update latest revision | 2026-02-27 | 2026-02-27 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-18 | OveArup-TRANSMIT-000151 | NA | Trade Partner | Fwd: Updated M3 Interim Supply to Stage 4 - Concept | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | for your information. It has also been uploaded to ACC. Actioned by Kian |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-18 | D&E-TRANSMIT-000123 | SPARK-CRFI-KPG-000540 | Trade Partner | THERMAL INSULATION | 0 | 1 | 0 | NA | APPROVED | 2026-02-18 | WF-000215 |  | 2026-02-25 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-000526 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-18 | WilsonPD-TRANSMIT-000158 | SPARK-CRFI-KPG-000541 | Trade Partner | Cleaners Tapware | 0 | 1 | 0 | NA | APPROVED | 2026-02-18 | WF-000216 | NA | 2026-02-25 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-000506 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-05 | Tradetec-TRANSMIT-000284 | NA | Trade Partner | IFA Shop Drawings - Stage 4 - LVP48, 49, 60, CP34, CP36 | 5 | 0 | 0 | NA | APPROVED | 2025-12-05 | NA | 1617 | 2025-12-15 |  |  |  | 2025-12-11 | KPTG-TRANSMIT-010825 | Closed | 5 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-18 | Altaire-TRANSMIT-000081 | NA | Trade Partner | M3S4 - Dry Fire Shop Drawings (For Construction) (L1 C3) | 1 | 0 | 0 | NA | APPROVED | 2026-02-18 | NA | 2142 | 2026-02-26 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-013517 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-18 | D&E-TRANSMIT-000124 | SPARK-CRFI-KPG-000349 | Trade Partner | AUTO REFILL & EXPANSION TANKS & DOSING POT | 0 | 1 | 0 | NA | APPROVED | 2026-02-18 | WF-000217 |  | 2026-02-25 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-18 | Entire M-TRANSMIT-000038 | NA | Trade Partner | Fwd: Mechanical Drawings Issued For Construction | 4 | 0 | 0 | NA | APPROVED | 2026-02-18 | WF-004344 | NA | 2026-03-03 |  | The register has been updated. If any further action is required, the coordinator will inform. |  | 2026-02-24 | KPTG-TRANSMIT-013419 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-18 | Altaire-TRANSMIT-000083 | NA | Trade Partner | Re: S3 22kv Dry-Fire Samples IFC | 0 | 11 | 0 | NA | REJECTED | [7 empty] | 2026-02-18 | KPTG-TRANSMIT-013087 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-18 | WilsonPD-TRANSMIT-000159 | SPARK-CRFI-KPG-000199, SPARK-CRFI-KPG-000261, SPARK-CRFI-KPG-000334 & SPARK-CRFI-KPG-000345 | Trade Partner | Hydraulic Layouts - Issued For Construction | 7 | 0 | 0 | NA | APPROVED | 2026-02-18 | WF-000218 | 129 | 2026-02-25 |  |  | 2026-03-16 | 2026-05-01 | KPTG-TRANSMIT-000779 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-18 | Altaire-TRANSMIT-000084 | NA | Trade Partner | S3 22kv Dry-Fire Samples IFC | 0 | 11 | 0 | NA | APPROVED | 2026-02-18 | WF-004340 | NA | 2026-03-03 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014300 | Closed | 11 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-18 | JCBa-TRANSMIT-000057 | NA | Consultant | Fixtures & Fittings - Principal Supplied Items - FF&E Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-02-18 | WF-000213 | NA | 2026-02-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-18 | JCBa-TRANSMIT-000058 | NA | Consultant | Lift Core Setout Drawings - Goods Lift update | 150 | 0 | 0 | NA | APPROVED | 2026-02-18 | WF-000214 | 371 | 2026-02-20 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-000693 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-18 | Jangho-TRANSMIT-000009 | NA | Trade Partner | 671C- VMU NO.2 & NO.3 Shop drawings REV.0 | 41 | 0 | 0 | NA | APPROVED | 2026-02-18 | NA | 285 | 2026-02-27 |  | As advised by Kapitol PC; "ACC review process not followed correctly. Unable to generate BIM issues by consultant" Unable to generate BIM issues by consultant. Further instruction is awaited. | 2026-02-27 | 2026-02-27 |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-05 | RDSBIM-TRANSMIT-000033 | NA | Trade Partner | LEVEL 01 PARTITION WALL PLAN AND ELEVATION | 3 | 0 | 0 | NA | APPROVED | 2025-12-05 | NA | 697 | 2025-12-09 |  |  | 2025-12-18 | 2025-12-18 | KPTG-TRANSMIT-002313 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-18 | Jangho-TRANSMIT-000010 | NA | Trade Partner | 671 Chapel St Project PMU shop drawings Rev00 | 40 | 0 | 0 | NA | APPROVED | 2026-02-18 | NA | 287 | 2026-02-27 |  | As advised by Kapitol PC; "ACC review process not followed correctly. Unable to generate BIM issues by consultant" Further instruction is awaited. | 2026-02-27 | 2026-02-27 |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-18 | RDSBIM-TRANSMIT-000221 | NA | Trade Partner | ROOF CONCRETE PROFILE PLAN AND SECTION | 7 | 0 | 0 | NA | APPROVED | 2026-02-18 | NA | 2146 | 2026-02-26 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-014271 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-18 | Altaire-TRANSMIT-000079 | NA | Trade Partner | Dry Fire Shop Drawings (For Construction) (G,L1,Roof C1-C3) | 8 | 0 | 0 | NA | APPROVED | 2026-02-18 | NA | 2148 | 2026-02-26 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-013515 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-18 | Tradetec-TRANSMIT-000367 | NA | Trade Partner | Re: Stage 4 South HVs - IFA | 3 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-02-18 | KPTG-TRANSMIT-013073 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-18 | Tradetec-TRANSMIT-000368 | NA | Trade Partner | IFC - LVP48, LVP49, LVP60 | 3 | 0 | 0 | NA | APPROVED | 2026-02-18 | NA | 2136 | 2026-02-26 |  |  |  | 2026-02-19 | KPTG-TRANSMIT-013221 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-18 | Tradetec-TRANSMIT-000369 | NA | Trade Partner | Stage 4 South HVs - IFA | 4 | 0 | 0 | NA | APPROVED | 2026-02-18 | NA | 2138 | 2026-02-26 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-014276 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-18 | Altaire-TRANSMIT-000080 | NA | Trade Partner | Dry Fire Shop Drawings (For Approval) (Cover, Legend, Upper Roof C1 & C2) | 4 | 0 | 0 | NA | APPROVED | 2026-02-18 | NA | 2145 | 2026-02-26 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-014093 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-10-27 | INGEN3D-TRANSMIT-000660 | NA | Consultant | I3D-378 Next DC M3 Stage 4 - Core 10 - Precast Panels - IFC | 54 | 0 | 0 | NA | APPROVED | 2025-10-27 | 003120 |  | 2026-02-18 |  |  |  | 2026-02-18 | KPTG-TRANSMIT-013068 | Closed | 54 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-18 | NXT-TRANSMIT-000361 | NA | Client | QUALITY PLAN ITP/ITC'S - AS BUILT | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  | As-Built-Distribution Only |  | 2026-02-18 | KPTG-TRANSMIT-002578 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-18 | SMEPS-TRANSMIT-000261 | NA | Trade Partner | BUSDUCT PROTECTION - IFC | 1 | 0 | 0 | KPTG-IntCorr-002912 | REJECTED |  | NA | NA |  |  | IFC |  | 2026-02-23 | KPTG-SADV-002251 | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-11-28 | TTW-TRANSMIT-000042 | N/A | Consultant | Facade Tender Documentation | 33 | 1 | 0 | KPTG-IntCorr-000110 | APPROVED | 2025-12-01 | WF-000046 | 103 | 2025-12-03 |  |  | 2025-12-05 | 2025-12-09 | KPTG-TRANSMIT-000212 | Closed | 33 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-05 | vdmcons-TRANSMIT-000012 | NA | Trade Partner | D09 M3 Stage 3 GIS Building - Shop Drawings & 3D IFC Model - M3 Stage 3 Switchroom - Re-IFA - 2025-12-05 | 199 | 0 | 0 | vdmcons-TRANSMIT-000012 | APPROVED | 2025-12-08 | WF-003523 / WF-003652 |  | 2025-12-18 |  |  |  | 2026-01-12 | KPTG-TRANSMIT-011330 | Closed | 199 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-18 | NXT-TRANSMIT-000362 | NA | Client | As-Built-documentation - GAs, BOMs and Label schedules | 75 | 16 | 0 | NA | APPROVED |  | NA | NA |  |  | As-Built-Distribution only |  | 2026-02-18 | KPTG-TRANSMIT-002593 | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-18 | TATE_-TRANSMIT-000033 | NA | Trade Partner | Tate Penetration Detail | 0 | 4 | 0 | KPTG-IntCorr-002907 | APPROVED | 2026-02-19 | NA | 1393 | 2026-02-26 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-28 | TATE_-IntCorr-000036 | NA | Trade Partner | DH7&8-HAC-LEVEL 1- DETAILS | 1 | 0 | 0 | NA | APPROVED | 2026-02-18 | NA | 1391 | 2026-02-25 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-18 | Highbu-TRANSMIT-000129 | NA | Trade Partner | Revised civil drawings | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC DRAWINGS TRANSMITTED TO TRADE & CONSULTANTS |  | 2026-02-18 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-18 | Highbu-TRANSMIT-000131 | NA | Trade Partner | Revised drawing | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC DRAWINGS, TRANSMITTED TO TRADE AND CONSULTANTS |  | 2026-02-18 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-18 | MCGC-TRANSMIT-000004 | NA | Consultant | Landscape Drawing Updates - CO2 Tank and Stairs | 6 | 0 | 0 | 0 | REJECTED | [5 empty] | kapitol advice awaits: KPTG-IntCorr-005196 Document Revision are not in chronological order, First revision F was Transmitted in March, 2025, now they issued revision C & D now |  | 2026-02-24 | KPTG-SADV-003764 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-18 | PROLMC-TRANSMIT-000024 | NA | Trade Partner | Proline/AUGRC Shop drawings IFC 18/2 | 29 | 0 | 0 | NA | REJECTED | [5 empty] | Titles of drawing do not match with existing drawings |  | 2026-02-18 | KPTG-SADV-003727 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-17 | KPTG-IntCorr-005111 | NA | Trade Partner | Handrails and Balustrades Meeting Items 12-02-2026 | 2 | 0 | 0 | NA | APPROVED | 2026-02-18 | NA | 446 |  |  |  |  | 2026-02-19 | KPTG-SADV-003735 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-18 | KPTG-IntCorr-005167 | NA | Trade Partner | Stairs X/Y/L Shop drawings and Ramp 4 detail | 5 | 0 | 0 | NA | APPROVED | 2026-02-18 | NA | 447 |  |  |  |  | 2026-02-19 | KPTG-SADV-003737 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-18 | WSP ANZ-TRANSMIT-000047 | NA | Consultant | WSP - Missing Building Services Drawings - Issue for Tender | 22 | 0 | 0 | N/A | APPROVED |  | N/A | N/A |  |  | No Review required, updated register |  | 2026-02-18 | NA | Closed | 22 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2025-12-05 | Nilsen3-TRANSMIT-000089 | NA | Trade Partner | Nilsen Tech Data Submission #5 | 0 | 1 | 0 | NA | APPROVED | [5 empty] | IFC, Review not required, updated register and distributed. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-18 | WSP ANZ-TRANSMIT-000048 | NA | Consultant | WSP - Telecommunications Drawings - Issue for Tender | 52 | 0 | 0 | N/A | APPROVED | 2026-02-20 | NA | 333 | 2026-02-27 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-001072 | Closed | 52 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-21 | KPTG-IntCorr-004052 | NA | Trade Partner | Samples and Reg126 Certificates | 143 | 0 | 0 | NA | APPROVED | 2026-02-10 |  | 433 | 2026-02-18 |  |  | 2026-02-18 | 2026-02-18 | KPTG-SADV-003723 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-18 | WSP ANZ-TRANSMIT-000049 | NA | Consultant | WSP - Building Services Documents - Reissue for Tender | 5 | 0 | 0 | N/A | REJECTED | [5 empty] | Drawings to be revised KPTG-DA-001200 |  | 2026-02-18 | KPTG-DA-001200 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-11 | MSHB-IntCorr-000037 | NA | Trade Partner | Stair ST01E | 2 | 0 | 0 | NA | APPROVED | 2026-02-11 |  | 439 | 2026-02-18 |  |  |  | 2026-02-18 | KPTG-SADV-003729 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-18 | WGAVIC-TRANSMIT-000065 | NA | Consultant | Structural Drawings - Stage 9 Stairs and Connections - Issued for Certification | 5 | 0 | 0 | N/A | REJECTED | [5 empty] | Drawing to be revised KPTG-DA-001194 |  | 2026-02-18 | KPTG-DA-001194 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-18 | WGAVIC-TRANSMIT-000066 | NA | Consultant | Structural Drawings - Stage 11 Piling Plan Update - Issued for Construction/Information | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawing, No review required. Updated register. |  | 2026-02-18 | KPTG-TRANSMIT-000974 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-18 | WGAVIC-TRANSMIT-000067 | NA | Consultant | Structural Drawings - Stage 9 Level 1 Slab - Issued for Certification | 11 | 0 | 0 | N/A | APPROVED |  | NA | NA |  |  | IFI drawings, No review required, updated register |  | 2026-02-18 | KPTG-TRANSMIT-000977 | Closed | 11 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-18 | SYNACC-TRANSMIT-000001 | NA | Trade Partner | 26 Flinders St Substation - Initial Design Drawings - For Engineer Approval | 17 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong Document Number, requested to resubmit |  | 2026-02-18 | KPTG-SADV-003099 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-18 | SYNACC-TRANSMIT-000002 | NA | Trade Partner | 26 Flinders St Substation - Initial Design Drawings - For Engineer Approval | 17 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong Document Number, requested to resubmit |  | 2026-02-18 | KPTG-SADV-003117 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-19 | KPTG-WTRAN-007880 | NA | Trade Partner | Chemset 502 | 1 | 0 | 0 | NA | APPROVED | 2026-02-19 | WF-004348 |  | 2026-03-03 |  | The WF has been initiated as requested by Ned. |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-05 | BTWA-TRANSMIT-000060 | NA | Trade Partner | Update 3 pages history version details Re: MLC ¦ Internal glazing shop drawings review | 3 | 0 | 0 | NA | APPROVED | [5 empty] | IFC Drawings- Transmitted to trade Partners & Consultants |  | 2025-12-05 |  | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-19 | D&E-TRANSMIT-000400 | NA | Trade Partner | Leak Detection - Issued for Review | 0 | 1 | 0 | NA | APPROVED | 2026-02-19 | WF-004349 |  | 2026-03-12 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-013700 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-19 | D&E-TRANSMIT-000401 | NA | Trade Partner | SFN - IMI Balancing Valves - Issued for review | 0 | 1 | 0 | NA | APPROVED | 2026-02-19 | WF-004350 | NA | 2026-03-12 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-013474 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-18 | Auscool-TRANSMIT-000076 | NA | Trade Partner | CO2 Sensor Tech Data For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-02-19 | WF-000623 | NA | 2026-02-25 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-002017 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-18 | TATE_-TRANSMIT-000005 | NA | Trade Partner | MEL11 SCEC SHOP DRAWINGS (UPDATED NAMING COV) FOR APPROVAL | 43 | 0 | 0 | NA | APPROVED | 2026-02-19 | WF-000014 | NA | 2026-02-25 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-000121 | Closed | 43 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-18 | SIL-TRANSMIT-000002 | NA | Trade Partner | MEL11 COLO 4-5 - FAT Reports and L3 Scripts - Transmittal 1 | 0 | 27 | 0 |  | APPROVED | 2026-02-19 | WF-000016 | NA | 2026-02-25 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-000171 | Closed | 27 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-19 | ARCST-TRANSMIT-000211 | NA | Trade Partner | C3 Chiller Base Framing - Checker Plate Issued for Approval | 66 | 0 | 0 | NA | APPROVED | 2026-02-19 | WF-004353 |  | 2026-03-17 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-17 | Tradetec-TRANSMIT-000360 | NA | Trade Partner | IFA - Stage 2 - CP11, CP17 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Different document numbers inside and outside. |  | 2026-02-18 | KPTG-DA-004941 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-19 | RDSBIM-TRANSMIT-000224 | NA | Trade Partner | NXM3S4 ¦ GROUND FLOOR-C-G-056 MALE WC-FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-02-19 | NA | 2157 | 2026-02-23 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014386 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-19 | crossfir-TRANSMIT-000049 | NA | Trade Partner | Wet Fire - Level 08 , IFA | 2 | 0 | 0 | NA | APPROVED | 2026-02-19 | WF-000940 | 546 | 2026-02-26 |  | The kapittol review was void and change in the new revision |  | 2026-03-03 |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-18 | KETE-TRANSMIT-000038 | NA | Trade Partner | Data sheet for hardwares | 0 | 4 | 0 | Currently hold as per Emma's Site Advice KPTG-SADV-002417 | APPROVED | 2026-03-06 | WF-000893 | NA | 2026-03-11 |  | Currently hold as per Emma's Site Advice KPTG-SADV-002417 |  | 2026-02-18 | KPTG-WTRAN-001904 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-05 | BTWA-TRANSMIT-000061 | NA | Trade Partner | MLC ¦ Internal glazing shop drawings review | 2 | 0 | 0 | NA | APPROVED | 2025-12-05 |  | 369 | 2025-12-12 |  |  |  | 2026-01-19 | KPTG-SADV-003415 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-18 | SKS Tech-TRANSMIT-000153 | NA | Consultant | ELECTRICAL SERVICES-STRING A LINE UP SINGLE LINE-DAY 1 | 1 | 0 | 0 | KPTG-IntCorr-001005 | REJECTED | [5 empty] | Rejected |  | 2026-02-18 | KPTG-IntCorr-001005 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-18 | Endfire-TRANSMIT-000064 | NA | Trade Partner | Water Mist IFA Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-02-18 | NA | 986 | 2026-02-24 |  |  | 2026-02-24 | 2026-02-25 | KPTG-TRANSMIT-002949 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-18 | Tradetec-TRANSMIT-000365 | NA | Trade Partner | Stage 2 - IFA - CP17, Cp11 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong document is attached to the document. |  | 2026-02-18 | KPTG-DA-004943 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-18 | D&E-TRANSMIT-000398 | NA | Trade Partner | NXM3S2 - Ground - Mechanical Pipe Layout - Zone 3 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-02-18 | NA | 3823 | 2026-02-25 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-013254 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-18 | PROLMC-TRANSMIT-000022 | NA | Trade Partner | Proline Shop drawings 18/2/26 | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Revision history not provided. |  | 2026-02-18 | KPTG-DA-004959 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-18 | PARR-TRANSMIT-000036 | NA | Trade Partner | Fuel Services - BFS FD | 0 | 1 | 0 | NA | APPROVED | 2026-02-18 | WF-000832 | NA | 2026-02-24 |  |  | 2026-04-02 | 2026-04-02 | KPTG-WTRAN-001889 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-18 | ZIA-TRANSMIT-000023 | NA | Trade Partner | CSM | 0 | 2 | 0 | NA | APPROVED | 2026-02-18 | WF-000831 | NA | [6 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-18 | ZIA-TRANSMIT-000023 | NA | Trade Partner | CSMS - Functional Design Specification | 0 | 3 | 0 | NA | APPROVED | 2026-02-18 | WF-000831 | NA | 2026-02-24 |  |  | 2026-04-02 | 2026-03-20 | KPTG-WTRAN-001827 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-19 | KPTG-WTRAN-007889 | NA | Trade Partner | ROOF ACCESS | 2 | 0 | 0 | NA | APPROVED | 2026-02-19 | WF-004357 |  | 2026-03-04 |  | The drawings have been placed for review as requested by Sam S. | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-013868 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-19 | Ardon-TRANSMIT-000023 | NA | Trade Partner | Stage 3 - Door Hardware Tech Data Submission | 0 | 13 | 0 | NA | APPROVED | 2026-02-19 | WF-004358 | NA | 2026-03-09 |  |  |  |  | KPTG-TRANSMIT-014755 | Open | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-05 | BTWA-TRANSMIT-000062 | NA | Trade Partner | MLC ¦ Level 02 door jamb ¦ IFC shop drawings | 4 | 0 | 0 | NA | APPROVED | 2025-12-05 |  | 370 | 2025-12-12 |  | Of the 4 drawings, 3 are IFC drawings, Only One drawing is put for Review |  | 2026-01-19 | KPTG-SADV-003406 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-18 | ACG-TRANSMIT-000050 | NA | Trade Partner | M3 - Stage 2 Internal ACG Shop Drawings IFC | 9 | 0 | 0 | NA | APPROVED | 2026-02-18 | NA | 3829 | 2026-02-24 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-18 | D&E-TRANSMIT-000399 | NA | Trade Partner | NXM3S2 - Upper Roof - Builders Works Layouts B1 & B2 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-02-18 | NA | 3827 | 2026-02-24 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-013258 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-19 | W TITE-TRANSMIT-000010 | NA | Trade Partner | Tremco TREMflex 25FC | 0 | 1 | 0 | NA | APPROVED | 2026-02-19 | WF-004359 | NA | 2026-03-04 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-014195 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-05 | KPTG-WTRAN-007467 | NA | Trade Partner | Hydraulic Samples | 0 | 25 | 0 | NA | APPROVED | 2026-02-05 | WF-004128 |  | 2026-02-23 |  | The WF has been processed by Sam S . KPTG-WTRAN-007467 |  | 2026-02-19 | KPTG-TRANSMIT-013156 | Closed | 25 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-18 | WAM-TRANSMIT-000716 | NA | Consultant | Kitchen Package | 2 | 0 | 0 | NA | APPROVED | 2026-02-18 | NA | 267 | 2026-02-21 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-000584 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-18 | Schindle-SUBADVICE-000138 | NA | Trade Partner | GL1 and GL2 - Lift Landing Frames | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Submit this document as a transmittal with a project standard document number in the register. |  | 2026-02-18 | KPTG-DA-004951 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-19 | VIA Arch-TRANSMIT-000025 | NA | Trade Partner | Fwd: Finishes Schedule updated - FA02 FA03 removed | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | SCH - The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-18 | NXT-TRANSMIT-001297 | NA | Client | 000221-2-110693 As built documentation - GA's, BOMs and Label Schedules | 65 | 14 | 0 | NA | APPROVED |  | NA | NA |  |  | As-Built |  | 2026-02-18 | KPTG-TRANSMIT-013091 | Closed | 79 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-18 | Tradetec-TRANSMIT-000366 | NA | Trade Partner | IFA - Stage 2 - CP11, CP17 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong attachment is placed. |  | 2026-02-18 | KPTG-DA-004960 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-18 | Stowe-A-TRANSMIT-000483 | NA | Trade Partner | Stowe - Tech Data - IFC | 0 | 2 | 0 | NA | REJECTED | [5 empty] | The document attached inside M3-ELC-STO-SA-B-0201-0086 is M3-ELC-STO-SA-B-0201-0080. |  | 2026-02-18 | KPTG-DA-004966 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-05 | Schindle-TRANSMIT-000009 | NA | Trade Partner | Schindler Lift 1 Transom Panel Drawing - IFA | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Document Number of the Drawing is mismatched |  | 2025-12-05 | KPTG-SADV-003005 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-18 | TTW-TRANSMIT-000094 | NA | Consultant | Structural Documentation | 46 | 0 | 0 | NA | APPROVED | 2026-02-18 | NA | 269 | 2026-02-20 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-000537 | Closed | 46 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-18 | Schindle-TRANSMIT-000017 | NA | Trade Partner | Lift GL1 and GL2 - Extended Landing Frame for approval | 1 | 0 | 0 | KPTG-TRANSMIT-013119 | APPROVED |  | WF-004345 | NA |  |  |  | 2026-03-11 | 2026-03-12 | KPTG-TRANSMIT-014178 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-18 | Altaire-TRANSMIT-000082 | NA | Trade Partner | Outstanding Commissioning Documentation | 0 | 5 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-02-18 | KPTG-TRANSMIT-013110 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-19 | ARCST-TRANSMIT-000212 | NA | Trade Partner | C2 Chiller Base Framing - Checker Plate Issued for Approval | 68 | 0 | 0 | NA | APPROVED | 2026-02-19 | WF-004356 |  | 2026-03-17 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-016400 | Closed | 68 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-19 | RDSBIM-TRANSMIT-000223 | NA | Trade Partner | NXM3S4 GROUND FLOOR-C-G-057 FEMALE WC FLOOR FINISHES LAYOUT AND ELEVATION | 1 | 0 | 0 | NA | APPROVED | 2026-02-19 | NA | 2158 | 2026-02-23 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014379 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-19 | D&E-TRANSMIT-000125 |  | Trade Partner | MWYCCB - AIR SCHEMATIC MECHANICAL SERVICES SHEET 1 OF 1 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-02-19 | WF-000219 | 130 | 2026-02-26 |  |  |  | 2026-03-17 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-18 | ccair-TRANSMIT-000093 | NA | Trade Partner | Level 08 Mechanical Ductwork & Pipework Layout | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Revision number is mismatching KPTG-TRANSMIT-002713 -sent back to originator |  | 2026-02-19 | KPTG-TRANSMIT-002713 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-18 | HVHD-TRANSMIT-000002 | NA | Consultant | Sustainability Management Plan | 1 | 0 | 0 | Rejected - KPTG-DA-000926, But as per HVHD-IntCorr-000011 forwarded for review | APPROVED | 2026-02-24 | WF-000179 | NA | 2026-02-25 |  | Rejected - KPTG-DA-000926, But as per HVHD-IntCorr-000011 forwarded for review | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-000576 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-19 | HEXA-TRANSMIT-000004 | NA | Trade Partner | Furnished Facility (B18) Shop Drawings for approval HEXA-TRANSMIT-000004 and INSULPAK-TRANSMIT-0000010 are same | 9 | 0 | 0 | NA | APPROVED | 2026-02-19 | NA | 307 | 2026-02-25 |  |  | 2026-03-03 | 2026-03-03 | DRAFT-009079 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-19 | PFP PL-TRANSMIT-000049 | NA | Trade Partner | Northern Corridor Dwgs IFC | 2 | 0 | 0 | NA | APPROVED | 2026-02-19 | NA | 1395 | 2026-02-26 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-002633 | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-11-12 | BTWA-TRANSMIT-000054 | NA | Trade Partner | Revised- Hardware -hinged lock/lever/closer/El301 & Rockwool S80 | 0 | 5 | 0 | NA | APPROVED | 2025-11-12 | WF-000573 |  | 2025-11-14 |  |  | 2025-12-05 | 2025-12-05 | KPTG-TRANSMIT-001941 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-19 | D&E-TRANSMIT-000340 | NA | Trade Partner | L1 MANTRAP DUCT& PIPE LAYOUT (V-07) - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-02-19 | NA | 1397 |  |  | Acc review void by Ellie salmon-The contractors IFC document didn't capture all IFA comments, the contractor needs to revise. |  | 2026-02-26 | KPTG-TRANSMIT-002670 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-19 | DI-TRANSMIT-000148 | NA | Consultant | Updated HFF Signage info | 1 | 0 | 0 | NA | APPROVED |  | NA | 306 | 2026-02-23 |  | 1 drawing and 1 SCH |  | 2026-02-20 | DRAFT-008945 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-19 | SMPS-TRANSMIT-000104 | NA | Trade Partner | O&M Manual | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | The register has been updated. If any further action is required, the coordinator will inform. O&M Manual |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-19 | ADP-TRANSMIT-000035 | NA | Consultant | Fire Protection Layout - Level 1 - Zone 1B - Data Hall A7 | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC-Distribution Only |  | 2026-02-20 | KPTG-TRANSMIT-002603 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-19 | PROLMC-TRANSMIT-000012 | SPARK-CRFI-KPG-000545 & SPARK-CRFI-KPG-000544 | Trade Partner | Proline Shop Drawings 19-2-26 | 42 | 0 | 0 | NA | APPROVED | 2026-02-19 | WF-000220 | 131 | 2026-02-26 |  | Review terminated as per Jed's advise |  | 2026-03-12 | NA | Closed | 42 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-19 | PARR-TRANSMIT-000121 | NA | Trade Partner | Re: P2680 - NDC M3 Stage 4 - Fuel - TECH DATA | 2 | 0 | 0 | NA | REJECTED | [5 empty] | There is a discrepancy in the submission. In the document it is listed as mechanical, but in the Aconex transmittal it is listed as fuel. |  | 2026-02-19 | KPTG-TRANSMIT-013172 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-19 | Schindle-TRANSMIT-000018 | NA | Trade Partner | Lift C1, C2 FC4 | 9 | 0 | 0 | NA | APPROVED | 2026-02-19 | WF-004366 | NA | 2026-03-03 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-013781 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-19 | Schindle-TRANSMIT-000019 | NA | Trade Partner | Lift C3- Shop drawings rev FC3 | 6 | 0 | 0 | NA | APPROVED | 2026-02-19 | WF-004366 | NA | 2026-03-03 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-013785 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-19 | KPTG-WTRAN-007907 | NA | Trade Partner | Tech Data | 0 | 7 | 0 | NA | APPROVED | 2026-02-19 | WF-004367 | NA | 2026-03-09 |  | The WF has been generated as requested by Lola. The WF has been terminated as requested by Lola |  |  | NA | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-19 | INDS-TRANSMIT-000002 | NA | Trade Partner | Precast Penetration Layout - Ground | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol PC (Amee) : Update and transmit to Prec cast Trade Partner Auspan. |  | 2026-02-19 | KPTG-TRANSMIT-000649 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-05 | Rinco-TRANSMIT-000022 | NA | Consultant | Structural drawings Issued for Construction | 72 | 0 | 0 | NA | APPROVED | 2025-12-05 | WF-000079 | 152 | 2025-12-10 |  |  |  | 2025-12-11 | KPTG-TRANSMIT-000309 | Closed | 72 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-19 | INDS-TRANSMIT-000003 | NA | Trade Partner | Precast Penetration Layout - Basement and Ground | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol PC (Amee) : Update and transmit to Prec cast Trade Partner Auspan. KPTG-TRANSMIT-000650 |  | 2026-02-19 | KPTG-TRANSMIT-000650 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-19 | Fyfe-TRANSMIT-000012 | NA | Consultant | Civil (Building Set) - Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-02-19 | WF-000215 | 373 | 2026-02-26 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-000675 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-19 | HDRAus-TRANSMIT-000398 |  | Consultant | M3 Stage4 - Updated Roof Level Set out plans, Switchroom, Chiller room detail and Door schedule | 12 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status column is empty inside the documents |  |  | KPTG-TRANSMIT-013147 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-04 | D&E-TRANSMIT-000373 | NA | Trade Partner | NXM3S2 - Ground Floor - Mech Elec Layouts - B1 & B2 + Level 01 - Mech Elec Layout B2 - Issued For Construction | 3 | 0 | 0 | NA | APPROVED | 2026-02-04 | NA | 3774 | 2026-02-19 |  |  | 2026-02-18 | 2026-02-19 | KPTG-TRANSMIT-013181 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-11-10 | CRSol-TRANSMIT-000050 | NA | Trade Partner | CRS CEILING SHOPDRAWINGS for DHB6 IFC | 10 | 0 | 0 | NA | APPROVED | 2026-02-11 | NA | 3204 | 2026-02-21 |  |  | 2026-02-18 |  | KPTG-TRANSMIT-013205 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-19 | SKS Tech-TRANSMIT-000027 | NA | Consultant | PREFABRICATED HANGERS TYPICAL DETAILS | 1 | 0 | 0 | NA | APPROVED | 2026-02-19 | NA | 2161 | 2026-02-27 |  | As requested by Oliver S — VOID. Comment: A mistake was made on the drawing. | 2026-02-24 | 2026-02-24 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-19 | SKS Tech-TRANSMIT-000029 | NA | Trade Partner | Lighting layout level 1 Zone C1 | 1 | 0 | 0 | NA | APPROVED | 2026-02-19 | NA | 2164 | 2026-02-27 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014844 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-19 | RDSBIM-TRANSMIT-000222 | NA | Trade Partner | NXM3S4 ¦ GROUND FLOOR-C-G-052 CLEANER FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-02-19 | NA | 2155 | 2026-02-23 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-013720 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-19 | SKS Tech-TRANSMIT-000028 | NA | Trade Partner | Re: LIGHTNG LAYOUT GROUND ZONE C1 | 1 | 0 | 0 | NA | REJECTED | 2026-02-19 |  |  |  |  | qa rejected due to incorrect revision number mentioned on the drawing |  | 2026-02-19 | KPTG-TRANSMIT-013170 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-05 | B Smart-TRANSMIT-000031 | NA | Consultant | Podium Levels Draft IFC (Part 2) | 5 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-000079 | 146 | 2025-12-11 |  | Internal Correspondence ref. KPTG-IntCorr-000245 . Workflow initiated. Workflow Void. |  | 2025-12-18 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-11-05 | NXT-WTRAN-001766 | NA | Consultant | TEMPORARY CLIENT IFC -KAP-ARUP-NEXTDC | 69 | 0 | 0 | NA | APPROVED | 2025-11-05 | WF-003205 |  | 2026-02-19 |  |  |  | 2026-02-19 | KPTG-TRANSMIT-013197 | Closed | 69 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-19 | HDRAus-TRANSMIT-000399 | NA | Consultant | Resubmission [KPTG-TRANSMIT-013147] M3 Stage4 - Updated Roof Level Set out plans, Switchroom, Chiller room detail and Door schedule | 9 | 3 | 0 | NA | APPROVED | 2026-02-19 | NA | 2178 | 2026-02-23 |  |  |  | 2026-02-20 | KPTG-TRANSMIT-013269 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-19 | SMEPS-TRANSMIT-000183 | NA | Trade Partner | SME - DRAWINGS IFA PART SUBMISSIONS | 14 | 0 | 0 | NA | APPROVED | 2026-02-19 | WF-004368 | 2172 | 2026-02-27 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014872 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-19 | Nilsen3-TRANSMIT-000031 | NA | Trade Partner | Nilsen Sample Submission #3 | 0 | 1 | 0 | NA | APPROVED | 2026-02-19 | WF-004369 | NA | 2026-02-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-19 | SKS Tech-TRANSMIT-000030 | NA | Trade Partner | Ground floor zone C1 lighting | 1 | 0 | 0 | NA | APPROVED | 2026-02-19 | WF-004371 | 2180 | 2026-02-26 |  |  |  | 2026-02-23 | KPTG-TRANSMIT-013354 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-08 | ARCST-TRANSMIT-000145 | NA | Trade Partner | C1 Switchroom Upper Roof - Issued for Approval | 124 | 0 | 0 | NA | APPROVED | 2026-01-16 | WF-003834 |  | 2026-02-19 |  |  |  | 2026-02-19 | KPTG-TRANSMIT-013166 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-19 | Entire M-TRANSMIT-000001 | NA | Trade Partner | Mechanical Technical Data Package Rev A IFA | 0 | 20 | 0 | NA | REJECTED | [5 empty] | DOCUMENT NUMBER OF ALL TECH DATA DO NOT MATCH WITH WHAT MENTIONED IN THE COVERING PAGE. REQUESTED TO RESUBMIT:KPTG-IntCorr-000037 |  | 2026-02-19 | KPTG-IntCorr-000037 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-19 | Auscool-TRANSMIT-000077 | NA | Trade Partner | MECHANICAL EOT Design updated | 1 | 0 | 0 | NA | REJECTED | [5 empty] | As per the direction from Mr mark, drawing need to be updated, instructed us not to take action. |  | 2026-02-19 | KPTG-SADV-003140 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-19 | Auscool-TRANSMIT-000078 | NA | Trade Partner | Mechanical Riser shop drawings | 2 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 584 | 2026-03-06 |  |  | 2026-04-21 | 2026-04-21 | KPTG-SADV-003828 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-19 | Auscool-TRANSMIT-000079 | NA | Trade Partner | Substation Mechanical layout IFC | 1 | 0 | 0 | NA | REJECTED | [5 empty] | As per the direction from Mr. Mark, Substation drawing needs to be revised, requested resubmit |  | 2026-02-19 | KPTG-SADV-003141 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-05 | SMEPS-TRANSMIT-000090 | SPARK-CRFI-KPG-000439 | Trade Partner | Cable tray tech-data submittal | 0 | 1 | 0 | KPTG-IntCorr-001055 | APPROVED | [7 empty] | 2026-04-17 | KPTG-TRANSMIT-000657 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-13 | Hames-WTRAN-000382 | NA | Trade Partner | I3D-378 Next DC M3 Stage 4 - Ground Floor Fuel Tank - Precast P | 23 | 0 | 0 | NA | APPROVED | 2026-01-13 | WF-003756 |  | 2026-01-16 |  |  |  | 2026-02-19 | KPTG-TRANSMIT-013188 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-19 | Metzone-TRANSMIT-000009 | NA | Trade Partner | Re: Catch Deck Cast-Ins for Thru-Bolts | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No workflow recommended. Ms Ashlin instructed me to update the socuments into document register only, |  | 2026-02-19 | KPTG-IntCorr-000731 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-19 | 4DW-TRANSMIT-000090 | NA | Consultant | Mezzanine Level Updates | 6 | 0 | 0 | NA | APPROVED | 2026-02-19 | NA | 572 | 2026-02-24 |  |  | 2026-02-23 | 2026-02-23 | KPTG-SADV-003176 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-19 | KETE-TRANSMIT-000115 | NA | Trade Partner | Kete - Structural Calculation for Tower | 0 | 1 | 0 | NA | APPROVED | 2026-02-19 | WF-000625 | NA | 2026-02-23 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-001928 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-16 | SES AU-TRANSMIT-000004 | NA | Trade Partner | Security IFC | 5 | 0 | 0 | NA | APPROVED | 2026-02-16 | WF-000133 | NA | 2026-02-20 |  |  | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-000207 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-17 | ETNInd-TRANSMIT-000007 | NA | Trade Partner | MEL05-COLO4 UPS Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-02-19 | WF-000150 | NA | 2026-02-26 |  |  | 2026-04-07 | 2026-06-07 | KPTG-TRANSMIT-000674 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-17 | TATE_-TRANSMIT-000020 | NA | Trade Partner | HAC TECH DATA IFC | 0 | 4 | 0 | NA | APPROVED | 2026-02-19 | WF-000151 | NA | 2026-02-26 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-000719 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-17 | SMEPS-TRANSMIT-000089 | NA | Trade Partner | SME Shop Drawing Electrical IFC | 1 | 0 | 0 | NA | APPROVED | 2026-02-18 | WF-000139 | NA | 2026-02-25 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-000271 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-17 | SMEPS-TRANSMIT-000090 | NA | Trade Partner | SME Shop Drawing Electrical IFC | 1 | 0 | 0 | NA | APPROVED | 2026-02-18 | WF-000140 | NA | 2026-02-25 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-000294 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-17 | Entire M-TRANSMIT-000008 | NA | Trade Partner | Mechanical shop drawings IFA | 9 | 0 | 0 | NA | APPROVED | 2026-02-18 | WF-000141 | NA | 2026-02-26 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-000367 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-01 | Auspan-TRANSMIT-000026 |  | Trade Partner | Update IFC precast shop drawings due to penos changed. | 8 | 0 | 0 |  | APPROVED | 2025-12-02 | WF-003454 |  | 2025-12-22 |  | The register has been updated. If any further action is required, the coordinator will inform. | [6 empty] | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-04 | Baigents-TRANSMIT-000056 | SPARK-CRFI-KPG-000237 | Trade Partner | MCC roof steel (Re-issued for Fabrication) | 138 | 0 | 0 | KPTG-IntCorr-001059 | APPROVED | 2025-12-05 | WF-000095 | 100 | 2025-12-12 |  | Latest revision received for 4 Drawings | 2026-05-27 | 2026-05-27 | KPTG-TRANSMIT-000942 | Closed | 134 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-17 | SIL-TRANSMIT-000024 | NA | Trade Partner | MEL05 C4 - 32PO-41735-T020 Technical Submittals | 24 | 0 | 0 | NA | APPROVED | 2026-02-18 | WF-000145 | NA | 2026-02-25 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-000509 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-19 | Highbu-TRANSMIT-000132 | NA | Trade Partner | Revised drawings | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings , transmitted to trade and consultants |  | 2026-02-19 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-17 | SIL-TRANSMIT-000025 | NA | Trade Partner | MEL05 C4 - 32PO-41735-T021 Technical Submittals | 2 | 0 | 0 | NA | APPROVED | 2026-02-18 | WF-000146 | NA | 2026-02-25 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-000660 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-19 | Tensile-TRANSMIT-000005 | NA | Trade Partner | Tensile Shop Drawings - IFC | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC DRAWINGS, TRANSMITTED TO TRADE AND CONSULTANTS |  | 2026-02-19 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-18 | RDSBIM-TRANSMIT-000001 | NA | Trade Partner | LEVEL 02 COLO 04 AREA PARTITION WALL ENLARGED LAYOUT | 3 | 0 | 0 | NA | APPROVED | 2026-02-19 | WF-000148 | NA | 2026-02-25 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000332 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-18 | TATE_-TRANSMIT-000021 | NA | Trade Partner | HAC TECH DATA AND AIR LEAKAGE TEST FOR REVIEW | 0 | 3 | 0 | NA | APPROVED | 2026-02-18 | WF-000161 | NA | 2026-02-25 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-000354 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-19 | MCGC-TRANSMIT-000005 | NA | Consultant | Stair ST01C Drawings | 2 | 0 | 0 | KPTG-IntCorr-005229 | REJECTED | [5 empty] | KAPITOL ADVICE AWAITS:KPTG-IntCorr-005229, updated to Document Register & Transmitted all concerned parties |  | 2026-02-24 | KPTG-SADV-003763 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-19 | TATE_-TRANSMIT-000022 | NA | Trade Partner | Tate Duo Install Manual For Information | 0 | 1 | 0 | NA | APPROVED | [5 empty] | File superseded | 2026-02-02 | 2026-02-02 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-18 | ETNInd-TRANSMIT-000008 | NA | Trade Partner | COLO4 UPS And Battery Cabinets BIM Models | 3 | 0 | 0 | NA | APPROVED | 2026-02-18 | WF-000147 | NA | 2026-02-25 |  |  | 2026-04-07 | 2025-04-07 | KPTG-TRANSMIT-000741 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-19 | MCGC-TRANSMIT-000006 | NA | Consultant | Stair ST01C Drawings | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Duplicates of MCGC-TRANSMIT-000005, same copy | 2026-02-24 | 2026-02-24 | KPTG-SADV-003763 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-05 | D&E-TRANSMIT-000069 |  | Trade Partner | ISSUED FOR APPROVAL - LEVEL 1 - PENETRATION LAYOUT ZONE 8 & ZONE 9 MECHANICAL SERVICES | 1 | 0 | 0 | KPTG-IntCorr-001061 | APPROVED | 2025-12-05 | WF-000096 | 58 | 2025-12-12 |  | WF terminated - To update latest revision as per Alex advice - KPTG-IntCorr-002480 |  | 2026-03-31 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-18 | SES AU-TRANSMIT-000006 | NA | Trade Partner | Security Drawings for Review | 3 | 0 | 0 | NA | APPROVED | 2026-02-19 | WF-000149 | NA | 2026-02-26 |  | Please note that the drawing mentioned below does not contain a stamp. KPTG-TRANSMIT-000331 and next transmittal 7 Supersede by SES AU-TRANSMIT-000007 | 2026-03-02 |  | KPTG-TRANSMIT-000331 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-19 | AXIS-NSW-TRANSMIT-000004 | NA | Trade Partner | Stormwater Services 100mm - 150mm | 0 | 1 | 0 | NA | APPROVED | 2026-02-19 | WF-000246 | NA | 2026-02-26 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-001230 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-19 | Tradetec-TRANSMIT-000042 | NA | Trade Partner | Shop Drawings for HV Pit details | 3 | 0 | 0 | N/A | APPROVED | 2026-02-19 | N/A | 319 | 2026-02-26 |  |  |  | 2026-02-20 | KPTG-TRANSMIT-000937 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-11-05 | ZIA-TRANSMIT-000048 | NA | Trade Partner | CSMS OUTSTATION Shop Drawings Issue for Construction | 10 | 0 | 0 | KPTG-IntCorr-001746 | APPROVED | 2025-11-28 | NA | 1263 | 2025-12-05 |  |  | 2026-02-19 | 2026-02-19 | KPTG-TRANSMIT-002605 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-19 | ASV-TRANSMIT-000015 | NA | Trade Partner | CIVIL STORMWATER SITE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-02-19 | NA | 323 | 2026-02-26 |  |  | 2026-03-05 | 2026-03-05 | KPTG-TRANSMIT-001189 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-19 | SKS Tech-TRANSMIT-000154 | NA | Consultant | TYPICAL DETAILS BUS DUCT SUPPORT ARRANGEMENT | 1 | 0 | 0 | KPTG-IntCorr-001009 | REJECTED | [5 empty] | QA Error |  | 2026-02-19 | KPTG-IntCorr-001009 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-19 | VAE-Grp-TRANSMIT-000126 | NA | Trade Partner | MECHANICAL - CRAC SCHEDULE / TECH SUB, FIRE MATRIX - CRAC POWER SUPPLIES | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Docs - registered and forwarded to all parties |  | 2026-02-19 | KPTG-TRANSMIT-002882 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-19 | GunAus-TRANSMIT-000010 | NA | Trade Partner | Door Drawing for Approval | 1 | 0 | 0 | Reissued Trn GunAus-TRANSMIT-000011 | REJECTED | [5 empty] | QA Error |  | 2026-02-19 | GunAus-TRANSMIT-000011 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-19 | GunAus-TRANSMIT-000011 | NA | Trade Partner | Door Drawing for approval | 1 | 0 | 0 | KPTG-IntCorr-001008 | REJECTED | [5 empty] | QA Error |  | 2026-02-19 | KPTG-IntCorr-001008 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-05 | VIA Arch-TRANSMIT-000027 | NA | Consultant | M2 S9-11 Loading Dock Concrete Profile Plan - Piling Coorindation | 1 | 0 | 0 | NA | APPROVED | 2025-12-05 |  | 116 | 2025-12-10 |  |  | 2025-12-09 | 2025-12-09 | KPTG-TRANSMIT-000297 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-19 | GunAus-TRANSMIT-000012 | NA | Trade Partner | Door Drawing for Approval- ARC | 1 | 0 | 0 | NA | APPROVED | 2026-02-19 | NA | 988 | 2026-02-24 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-002937 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-19 | Hames-TRANSMIT-000119 | NA | Consultant | Services Enclosure-ARC | 2 | 0 | 0 | KPTG-IntCorr-001010 | REJECTED | [5 empty] | QA Error |  | 2026-02-19 | KPTG-IntCorr-001010 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-19 | SKS Tech-TRANSMIT-000155 | NA | Consultant | for APPROVAL submittals-ELC | 0 | 3 | 0 | NA | APPROVED | 2026-02-19 | WF-000834 | NA | 2026-02-23 |  |  | 2026-03-02 | 2026-03-02 | KPTG-WTRAN-001702 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-19 | WAM-TRANSMIT-000717 | NA | Consultant | ARCH - 95% DD Update - Elevations | 10 | 0 | 0 | NA | APPROVED | 2026-02-19 | NA | 272 | 2026-02-23 |  |  | 2026-02-26 | 2026-02-27 | KPTG-TRANSMIT-000580 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-19 | Civilex-TRANSMIT-000030 | NA | Trade Partner | Sheet Pile Design | 0 | 1 | 0 | Jarrod to Confirm - KPTG-IntCorr-000369 | APPROVED | 2026-02-19 | NA | NA |  |  | For info. to TTW only |  | 2026-02-20 | KPTG-TRANSMIT-000522 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-20 | NXT-TRANSMIT-001304 | NA | Trade Partner | Resbumitting IFC Tech docs | 4 | 0 | 0 | NA | APPROVED | 2026-02-20 | WF-004375 |  | 2026-03-05 |  | still 1 doc pending |  | 2026-07-22 | KPTG-TRANSMIT-019866 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-20 | SMEPS-TRANSMIT-000185 | NA | Trade Partner | Fwd: SME - GLP DB SCHEDULES - IFA | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | SCH - No further action is required. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-20 | SMEPS-TRANSMIT-000184 | NA | Trade Partner | SME - IFA Sample submissions | 0 | 5 | 0 | NA | APPROVED |  | NA | NA |  |  | As per Peter Z, No action required. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-20 | Nilsen3-TRANSMIT-000032 | NA | Trade Partner | Surge Arresters Stage 3 HV Switchboards | 0 | 1 | 0 | NA | APPROVED | 2026-02-20 | WF-004377 | NA | 2026-03-02 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-013600 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-20 | Nilsen3-TRANSMIT-000033 | NA | Trade Partner | Interface Control Cabling | 0 | 1 | 0 | NA | APPROVED | 2026-02-20 | WF-004378 | NA | 2026-03-02 |  |  |  | 2026-02-24 | KPTG-TRANSMIT-013451 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-04 | OveArup-TRANSMIT-000016 | NA | Consultant | HYDRAULIC SERVICES - 80% Issue for Construction | 75 | 0 | 0 | NA | APPROVED | 2025-12-05 | NA | 128 | 2025-12-10 |  |  | 2025-12-10 | 2025-12-11 | KPTG-TRANSMIT-000233 | Closed | 75 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-20 | Nilsen3-TRANSMIT-000035 | NA | Trade Partner | Sample submissions | 0 | 2 | 0 | NA | APPROVED | 2026-02-20 | WF-004379 | NA | 2026-03-06 |  |  | 2026-02-28 | 2026-03-02 | KPTG-TRANSMIT-013694 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-20 | IVS-TRANSMIT-000338 | NA | Consultant | Issued For Construction - Cooling Tower & Chiller Room Bracing & Trimmers (Revised as clouded) | 3 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 2184 | 2026-02-24 |  |  |  | 2026-02-23 | KPTG-TRANSMIT-013314 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-20 | SKS Tech-TRANSMIT-000031 | NA | Trade Partner | SKS - LV Submains Submission Rev B | 0 | 1 | 0 | NA | APPROVED | 2026-02-20 | WF-004376 | NA | 2026-02-25 |  | The WF has been terminated as requested by Oliver S | 2026-02-24 | 2026-02-24 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-20 | PCForm-TRANSMIT-000085 | NA | Trade Partner | 80Mpa Mix Design | 0 | 1 | 0 | NA | APPROVED | 2026-02-20 | WF-000250 | NA | 2026-02-27 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-001119 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-20 | KPTG-TRANSMIT-012634 | NA | Trade Partner | New Workflow VT S4 | 7 | 0 | 0 | NA | APPROVED | 2026-02-20 | WF-004383 | NA | 2026-02-27 |  | As requested by Finlay, the drawings have been placed back into the workflow. |  |  | NA | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-20 | PARR-TRANSMIT-000122 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - Client Drawings | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status mentioned inside the drawings is different from the status shown in the document register |  | 2026-02-20 | KPTG-TRANSMIT-013244 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-20 | SMEPS-TRANSMIT-000092 | N/A | Trade Partner | SME Shop Drawing Electrical IFA 2 | 4 | 0 | 0 | NA | APPROVED | 2026-02-20 | WF-000155 | N/A | 2026-02-26 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-000299 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-20 | SMEPS-TRANSMIT-000182 | NA | Trade Partner | 22KV - Lightning protection sample | 0 | 1 | 0 | NA | APPROVED | 2026-02-20 | WF-004386 | NA | 2026-03-02 |  |  |  | 2026-02-24 | KPTG-TRANSMIT-013443 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-20 | RDSBIM-TRANSMIT-000225 | NA | Trade Partner | NXM3S4 - LEVEL-1-C-1-046 MALE WC FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 2186 | 2026-02-24 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-013716 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-04 | OveArup-TRANSMIT-000016 | NA | Consultant | FIRE SERVICES - 80% Issue for Construction | 77 | 0 | 0 | NA | APPROVED | 2025-12-05 | WF-000062 | 131 | 2025-12-10 |  |  | 2025-12-10 | 2025-12-11 | KPTG-TRANSMIT-000240 | Closed | 77 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-20 | Nilsen3-TRANSMIT-000034 | NA | Trade Partner | M3-HV-NIL-SA-S-0301-0025 - BTU Cabling | 0 | 1 | 0 | NA | APPROVED | 2026-02-20 | WF-004390 | NA | 2026-02-25 |  |  |  | 2026-02-24 | KPTG-TRANSMIT-013449 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-20 | Altaire-TRANSMIT-000085 | NA | Trade Partner | NEXTDC M3S3 - Dry Fire 22KV FIP Show Drawings (For Approval) | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-02-20 | KPTG-TRANSMIT-013246 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-20 | Nilsen3-TRANSMIT-000037 | NA | Trade Partner | M3-HV-NIL-SA-S-0301-0027 - Fire Rated Tray (SAMPLE) | 0 | 1 | 0 | NA | APPROVED | 2026-02-20 | WF-004394 | NA | 2026-02-25 |  |  |  | 2026-02-24 | KPTG-TRANSMIT-013446 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-20 | SKS Tech-TRANSMIT-000032 | NA | Trade Partner | Power Containment Roof Zone C1 | 1 | 0 | 0 | NA | APPROVED | 2026-02-20 | WF-004395 | 2192 | 2026-03-02 |  | As requested by Peter Z - VOID |  | 2026-02-26 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-20 | IVS-TRANSMIT-000339 | NA | Consultant | Stage 4 - Secure Corridor Construction Issue (Revised as clouded) | 1 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 2194 | 2026-02-24 |  |  |  | 2026-02-23 | KPTG-TRANSMIT-013305 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-16 | SES AU-TRANSMIT-000005 | NA | Trade Partner | Security IFA for review | 4 | 0 | 0 | NA | APPROVED | 2026-02-16 | WF-000134 | NA | 2026-02-20 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-000224 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-20 | SMEPS-TRANSMIT-000091 | N/A | Trade Partner | Steel Plinths | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Sent back to originator for resubmission as the status of the document was wrongly marked as For Information. |  | 2026-02-20 | KPTG-SADV-000279 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-04 | D&E-TRANSMIT-000376 | NA | Trade Partner | ITPs - Issued for Review | 0 | 4 | 0 | NA | APPROVED | 2026-02-06 | WF-004169 | NA | 2026-02-19 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-013227 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-20 | SMEPS-TRANSMIT-000093 | NA | Trade Partner | SME Shop Drawing Electrical IFA 2 | 7 | 0 | 0 | NA | APPROVED | 2026-02-20 | WF-000156 | N/A | 2026-02-26 |  |  | 2026-04-15 | 2026-04-15 | SMEPS-TRANSMIT-000115 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-20 | B Smart-TRANSMIT-000058 | NA | Consultant | Substation access | 2 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 291 | 2026-02-24 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000522 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-04 | OveArup-TRANSMIT-000016 | NA | Consultant | Services Specification | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | All are updated in the register |  |  |  | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-20 | POTTSENG-TRANSMIT-000004 | NA | Trade Partner | 671C: HYDRAULIC SERVICES - BASEMENT 4 INGROUND - DRAINAGE LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 289 | 2026-02-27 |  | Void by Kapitol PC -Tayla | 2026-03-26 | 2026-03-26 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-20 | B Smart-TRANSMIT-000059 | NA | Consultant | : A03.016 - drawing title updated | 1 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 293 | 2026-02-24 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000511 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-20 | RDSBIM-TRANSMIT-000032 | NA | Trade Partner | RDSBIM-TRANSMIT-000032: 671CHP ¦ BASEMENT 4 CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | NA |  |  | No action required.. As advised by Kevin Choi, RDS will issue updated drawings. DRAFT-003754 |  | 2026-02-20 | KPTG-SADV-000862 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-20 | SMEPS-TRANSMIT-000094 | N/A | Trade Partner | SME Shop Drawing Electrical IFA 2 | 2 | 0 | 0 | NA | APPROVED | 2026-02-20 | WF-000157 | NA | 2026-02-26 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-000281 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-20 | Auspan-TRANSMIT-000087 | NA | Trade Partner | Update already IFCed shop drawings for construction | 11 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required, Register and distribute. - KPTG-TRANSMIT-000671 |  | 2026-02-20 | KPTG-TRANSMIT-000671 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-20 | Auspan-TRANSMIT-000088 | NA | Trade Partner | Resubmit precast shop drawings for approval. Basement 1. | 8 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 378 | 2026-02-27 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-000738 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-20 | RDSBIM-TRANSMIT-000021 | NA | Trade Partner | GREYSTAR BASEMENT FLOOR CONCRETE PROFILE KEY PLAN | 9 | 0 | 0 | NA | APPROVED | 2026-02-20 | WF-000216 | 375 | 2026-02-27 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-000695 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-20 | POTTSENG-TRANSMIT-000009 | NA | Trade Partner | GMAC: HYD - DRAINAGE - BASEMENT 1 INGROUND - ZONE 1-5 LAYOUTS | 5 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 380 | 2026-02-27 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-000720 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-20 | JCBa-TRANSMIT-000059 | NA | Consultant | 23-122_A-1300 - OVERALL BUILDING ELEVATIONS & SECTIONS | 5 | 0 | 0 | NA | APPROVED | 2026-02-20 | WF-000219 | 382 | 2026-02-24 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-000694 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-20 | RDSBIM-TRANSMIT-000022 | NA | Trade Partner | GREYSTAR BASEMENT FLOOR CONCRETE PROFILE KEY PLAN SECTIONS | 11 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 384 | 2026-02-27 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-000732 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-04 | RDSBIM-TRANSMIT-000006 | NA | Trade Partner | LEVEL 10 TO LEVEL 24 (ROOF) LIFT CORE 01 CONCRETE PROFILE PLAN AND SECTIONAL ELEVATION | 5 | 0 | 0 | NA | APPROVED | 2025-12-05 | NA | 133 | 2025-12-09 |  |  | 2026-01-13 | 2026-01-14 | KPTG-TRANSMIT-000277 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-19 | Stowe-A-TRANSMIT-000484 | NA | Trade Partner | Stowe - Tech Data Submission - IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-02-19 | KPTG-TRANSMIT-013139 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-19 | ASV-TRANSMIT-000148 | NA | Trade Partner | Hydraulic Sample - Bunding | 0 | 1 | 0 | NA | APPROVED | 2026-02-19 | WF-004346 | NA | 2026-02-25 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-013267 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-19 | D&E-TRANSMIT-000402 | NA | Trade Partner | NXM3S2 - Ground - Builders Works Layout - B1 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-02-19 | NA | 3836 | 2026-02-24 |  |  | 2026-02-20 | 2026-02-20 | KPTG-TRANSMIT-013278 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-20 | SMEPS-TRANSMIT-000095 | N/A | Trade Partner | LV Cell Containment, Unistrut, Cable Tray and Ladder Supersedence | 0 | 3 | 0 | NA | APPROVED | 2026-02-20 | WF-000158 | N/A | 2026-02-26 |  |  | 2026-04-19 | 2026-04-19 | KPTG-TRANSMIT-000590 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-19 | PFP PL-TRANSMIT-000069 | NA | Trade Partner | L2 & L3 scripts for constructions | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-02-20 | KPTG-TRANSMIT-013245 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-18 | ACG-TRANSMIT-000052 | NA | Consultant | M3 - S1 ACG Shop Drawings | 8 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-02-19 | KPTG-DA-004990 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-19 | W TITE-TRANSMIT-000009 | NA | Trade Partner | M3-WPF-WTW-TD-B-0201-0010 | 0 | 1 | 0 | NA | APPROVED | 2026-02-19 | WF-004363 | NA | 2026-03-10 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-017230 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-19 | Facx-TRANSMIT-000016 | NA | Trade Partner | CLDO7/FT03B1 - IFA | 7 | 0 | 0 | NA | APPROVED | 2026-02-19 | NA | 3838 | 2026-03-02 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-013548 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-20 | Stowe-A-TRANSMIT-000485 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - LOWER ROOF HOUSE CONTAINMENT - 20.02.2026 | 2 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 3841 | 2026-02-25 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-013799 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-20 | Stowe-A-TRANSMIT-000486 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - MAINS CABLE SCHEDULE | 1 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 3843 | 2026-02-25 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-013795 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-05 | D&E-TRANSMIT-000279 | NA | Trade Partner | L1 ZONE B1 & B2 DUCT & PIPE LAYOUTS | 2 | 0 | 0 | NA | APPROVED | 2025-12-08 | NA | 1288 | 2025-12-15 |  |  |  | 2025-12-18 | KPTG-TRANSMIT-002238 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-20 | Stowe-A-TRANSMIT-000487 | NA | Trade Partner | Stowe - Tech Data Submission - ATS Shop drawing | 0 | 1 | 0 | NA | APPROVED | 2026-02-20 | WF-004374 | NA | 2026-03-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-20 | SMEPS-TRANSMIT-000096 | N/A | Trade Partner | SME Shop Drawing EPMS IFC | 7 | 0 | 0 | NA | APPROVED | 2026-02-20 | WF-000159 | N/A | 2026-02-26 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-000288 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-20 | D&E-TRANSMIT-000407 | NA | Trade Partner | ISSUED FOR APPROVAL - Cooling Tower Mesh - Builders Works Layout - Zone 1 & 3 | 2 | 0 | 0 | NA | APPROVED | 2026-02-20 | WF-004398 | 2199 | 2026-03-02 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-013673 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-20 | D&E-TRANSMIT-000403 | NA | Trade Partner | L2 Cx Scripts - Issued for Review | 0 | 15 | 0 | NA | APPROVED | 2026-02-20 | WF-004392 | NA | 2026-03-03 |  | Terminated workflow. These documents have already been reviewed, so they should be issued as IFC rather than submitted for review again. |  | 2026-02-23 | KPTG-DA-005060 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-20 | SMEPS-TRANSMIT-000097 | N/A | Trade Partner | Steel Plinths | 0 | 1 | 0 | N/A | APPROVED | 2026-02-20 | WF-000160 | N/A | 2026-02-26 |  |  | 2026-04-23 | 2026-06-23 | KPTG-TRANSMIT-000788 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-20 | D&E-TRANSMIT-000404 | NA | Trade Partner | L3 Cx Scripts - Issued for Review | 0 | 29 | 0 | NA | APPROVED | 2026-02-20 | WF-004391 | NA | 2026-03-03 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-013576 | Closed | 29 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-20 | Stowe-A-TRANSMIT-000488 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - COMMUNICATIONS - 20.02.2026 | 9 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 3845 | 2026-02-25 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-013768 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-20 | ZIA-TRANSMIT-000057 | NA | Trade Partner | L3 and Cx Plan Submission | 0 | 11 | 0 | NA | APPROVED | 2026-02-20 | WF-004389 | NA | 2026-03-03 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-013578 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-20 | Tradetec-TRANSMIT-000370 | NA | Trade Partner | Stage 2 - IFA CP11, CP17 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Different status in a single transmittal. |  | 2026-02-20 | KPTG-DA-005018 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-20 | Stowe-A-TRANSMIT-000489 | NA | Trade Partner | Stowe - Tech Data Submission - 3PIN 5 PHASE OUTLET | 0 | 1 | 0 | NA | APPROVED | 2026-02-20 | WF-004396 | NA | 2026-03-04 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014283 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-05 | D&E-TRANSMIT-000278 | NA | Trade Partner | DH7&8 Annunciator and Main Panels | 0 | 8 | 0 | NA | APPROVED | 2025-12-05 | WF-000840 | NA |  |  | Workflow terminated as instructed by Kapitol, and distributed to Client / Consultant / Trade partners as PC advised review not required for these documents. |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-20 | HDRAus-TRANSMIT-000400 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 10 | 0 | 0 | NA | APPROVED | 2026-02-23 | NA | 2209 | 2026-03-03 |  | The revision status in the document register seems incorrect. | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-013807 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-20 | RDSBIM-TRANSMIT-000166 | NA | Trade Partner | LEVEL 01 PARTITION WALL PLAN | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-20 | RDSBIM-TRANSMIT-000167 | NA | Trade Partner | LEVEL 02 PARTITION WALL PLAN | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-11 | D&E-TRANSMIT-000335 | NA | Trade Partner | SFN Monitoring panel L3 Cx Script | 0 | 1 | 0 | KPTG-IntCorr-002785 | APPROVED | 2026-02-20 | WF-000949 | NA | 2026-02-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-20 | D&E-TRANSMIT-000341 | NA | Trade Partner | L3 Cx Scripts-IFC | 0 | 16 | 0 | KPTG-IntCorr-002935 | APPROVED |  | NA | NA |  |  | IFC-Distribution Only |  | 2026-02-20 | KPTG-TRANSMIT-002610 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-20 | ASV-TRANSMIT-000016 | NA | Trade Partner | Stage 9 Internal Hydraulic Services | 1 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 345 | 2026-02-27 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-001247 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-20 | Hames-TRANSMIT-000120 | NA | Consultant | Updated Fire Room Per | 4 | 0 | 0 | QA Error - Rejected - KPTG-TRANSMIT-002890 | REJECTED | [5 empty] | QA Error - Rejected - KPTG-TRANSMIT-002890 |  | 2026-02-20 | KPTG-TRANSMIT-002890 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-20 | Jordan-TRANSMIT-000118 | NA | Trade Partner | Level 4 and 5 - Plumbing Reticulation - For Approval | 2 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 994 | 2026-02-24 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-002916 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-20 | WGAVIC-TRANSMIT-000068 | NA | Consultant | Structural Drawings - Stage 10 & 11 Precast and Insitu Walls and Columns - Issued for Construction/Information | 13 | 0 | 0 | KPTG-IntCorr-000442 | APPROVED |  | NA | NA |  |  | No review required, Updated register and uploaded to ACC |  | 2026-02-24 | KPTG-TRANSMIT-000980 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-04 | SKS Tech-TRANSMIT-000101 | NA | Trade Partner | LEVEL 4 IFA CONTAINTMENT LAYOUTS | 1 | 0 | 0 | NA | APPROVED | 2025-12-05 | NA | 699 | 2025-12-10 |  |  | 2026-01-15 | 2026-01-15 | KPTG-TRANSMIT-002416 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-20 | WGAVIC-TRANSMIT-000069 | NA | Consultant | Civil Drawings - Early Works - BCC Comment Closeout - Issued for Construction | 2 | 0 | 0 | KPTG-IntCorr-000443 | APPROVED |  | NA | NA |  |  | No review required. Updated register and uploaded to ACC |  | 2026-02-24 | KPTG-TRANSMIT-000983 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-20 | WSP ANZ-TRANSMIT-000050 | NA | Consultant | WSP - Building Services Documents - Reissue for Tender | 45 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 346 | 2026-02-27 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-001076 | Closed | 45 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-20 | PARR-TRANSMIT-000038 | NA | Trade Partner | FUEL RETICULATION L4 & L5 GA | 1 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 992 | 2026-02-25 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-002987 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-20 | PARR-TRANSMIT-000037 | NA | Trade Partner | Fuel Services - LG SECTIONS PIPE/CABLE PENOS - IFC | 2 | 0 | 0 | NA | APPROVED | 2026-02-20 | WF-000835 | 990 | 2026-02-25 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-002912 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-20 | VAE-Grp-TRANSMIT-000127 | NA | Trade Partner | MECH - DESIGN CERTIFICATE | 0 | 1 | 0 | KPTG-IntCorr-001014 | APPROVED |  | NA | NA |  |  | forwarded to all parties |  | 2026-03-03 | KPTG-TRANSMIT-003044 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-20 | Civilex-TRANSMIT-000031 | NA | Trade Partner | UPT Shop Drawing Approval | 0 | 1 | 0 | QA Error Rejected - KPTG-TRANSMIT-000523 | REJECTED | 2026-02-20 | NA | NA |  |  | QA Error Rejected - KPTG-TRANSMIT-000523 |  | 2026-02-20 | KPTG-TRANSMIT-000523 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-20 | SMEPS-TRANSMIT-000186 | NA | Trade Partner | SME - DRAWINGS IFA PART SUBMISSIONS | 10 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 2196 | 2026-03-02 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-017839 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-20 | SKS Tech-TRANSMIT-000033 | NA | Trade Partner | Zone C2 and C3 Comms and Power Containment for approval | 2 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 2190 & 2189 | 2026-03-02 |  | THIS TRANSMITTAL HAVE 2 DIFFERENT TYPE DISCIPLINE DOCUMENTS ITS NEED TO GO ON DIFFERENT WORKFLOWS |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-05 | PARR-TRANSMIT-000114 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - TECH DATA | 0 | 23 | 0 | NA | APPROVED | 2026-02-05 | 004137 |  | 2026-02-20 |  |  |  | 2026-02-20 | KPTG-TRANSMIT-013233 | Closed | 21 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-01 | IVS-TRANSMIT-000287 | NA | Consultant | Stage 4 - Fuel Tank Precast Elevations Construction Issue (revised as clouded) | 1 | 0 | 0 |  | APPROVED | 2025-12-01 | NA | 1596 | 2025-12-03 |  |  |  | 2025-12-05 | KPTG-TRANSMIT-010677 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-04 | SKS Tech-TRANSMIT-000101 | NA | Trade Partner | LEVEL 4 IFA CONTAINTMENT LAYOUTS | 1 | 0 | 0 | NA | APPROVED | 2025-12-05 | NA | 701 | 2025-12-10 |  |  | 2026-01-15 | 2026-01-15 | KPTG-TRANSMIT-002420 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-20 | WEBBAUST-TRANSMIT-000066 | NA | Consultant | Webb - Power Pack Test IFC update - Re Transmit | 5 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 308 | 2026-02-23 |  |  |  | 2026-02-23 | DRAFT-008955 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-23 | Altaire-TRANSMIT-000086 | NA | Trade Partner | NEXTDC M3S3 - Dry Fire 22KV FIP Show Drawings (For Approval) | 1 | 0 | 0 | NA | APPROVED | 2026-02-23 | WF-004408 |  | 2026-03-03 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-23 | Auspan-TRANSMIT-000033 | NA | Trade Partner | 22kV precast retransmit | 78 | 0 | 0 | NA | APPROVED | 2026-02-23 | WF-004410 |  | 2026-03-19 |  | The WF-004412 has been generated by Max H - 23/28/2026 | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-020484 | Closed | 78 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-20 | Nilsen3-TRANSMIT-000036 | NA | Trade Partner | M3-HV-NIL-SA-S-0301-0026 - Cable Ties (Sample) | 0 | 1 | 0 | NA | APPROVED | 2026-02-23 | WF-004417 | NA | 2026-03-05 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-013595 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2026-02-20 | RDSBIM-TRANSMIT-000197 | NA | Trade Partner | LOWER AND UPPER GROUND COMMON AREA GYM & WELLNESS LAYOUT & ELEVATIONS | 18 | 0 | 0 | NA | APPROVED | 2026-02-23 | NA | 574 | 2026-02-27 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-23 | HGP-TRANSMIT-000044 |  | Trade Partner | Heritage Glass - Self Cleaning coating | 0 | 1 | 0 | NA | APPROVED | 2026-02-23 | WF-000222 |  | 2026-03-02 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2026-02-23 | ccair-TRANSMIT-000136 | NA | Trade Partner | Air Schematic-R0-IFC | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-23 | HGP-TRANSMIT-000045 |  | Trade Partner | Louvre Sample Transmittals | 0 | 3 | 0 | NA | REJECTED | [5 empty] | drawing title inside the drawing and in Aconex seem different |  | 2026-02-23 | KPTG-TRANSMIT-000463 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-23 | WilsonPD-TRANSMIT-000161 | SPARK-CRFI-KPG-000549 | Trade Partner | Water meters | 0 | 1 | 0 | NA | APPROVED | 2026-02-23 | WF-000223 |  | 2026-03-02 |  |  |  | 2026-03-25 | KPTG-TRANSMIT-000593 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-05 | RDSBIM-TRANSMIT-000124 | NA | Trade Partner | LINDRUM ¦ LEVEL 07 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2025-12-05 | NA | 479 | 2025-12-12 |  |  | 2025-12-09 | 2025-12-09 | KPTG-SADV-002417 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-23 | KPTG-WTRAN-008013 | NA | Trade Partner | 22KVA HANDRAIL MARKING PLAN & SECTIONS | 0 | 1 | 0 | NA | APPROVED | 2026-02-23 | WF-004424 |  | 2026-03-06 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-23 | KARE-TRANSMIT-000090 | NA | Trade Partner | House Distribution Boards | 13 | 1 | 0 | NA | APPROVED | 2026-02-23 |  | 547 | 2026-02-27 |  |  | 2026-04-01 | 2026-04-01 | DRAFT-016479 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-23 | NXT-TRANSMIT-001314 | NA | Trade Partner | Fwd: Re-submitting GA & Batt calcs | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-23 | WPD-TRANSMIT-000066 | NA | Trade Partner | Re: HFF - Hydraulic Tech Data Submissions | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | The register has been updated. If any further action is required, the coordinator will inform. |  |  | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-23 | WPD-TRANSMIT-000065 | NA | Trade Partner | Fwd: HFF - Samples | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Please find the attached document for your information. It has also been uploaded to ACC. |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-23 | ARCST-TRANSMIT-000215 | NA | Trade Partner | Chemical Store Roof Framing Shop Drawings | 11 | 0 | 0 | NA | APPROVED | 2026-02-23 | 004406 |  | 2026-03-19 |  |  | 2026-04-14 | 2026-04-14 | KPTG-TRANSMIT-015893 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-23 | HIP-TRANSMIT-000003 | NA | Trade Partner | Building 08 - Additional Steel Variation | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect Reference number |  | 2026-02-23 | DRAFT-008971 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-23 | ARCST-TRANSMIT-000214 | NA | Trade Partner | Fire Room roof Shop Drawings | 18 | 0 | 0 | NA | APPROVED | 2026-02-23 | 004409 |  | 2026-02-23 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-015929 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-23 | SKS Tech-TRANSMIT-000034 | NA | Trade Partner | COMMS CONTAINMENT LAYOUT-ROOF-ZONE C1 | 1 | 0 | 0 | NA | APPROVED | 2026-02-23 | NA | 2203 | 2026-03-02 |  | As requested by Peter Z - VOID |  |  | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-23 | RDSBIM-TRANSMIT-000227 | NA | Trade Partner | NXM3S4 GROUND FLOOR-C-G-023 CLEANERS-FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-02-23 | NA | 2206 | 2026-02-25 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014365 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-05 | RDSBIM-TRANSMIT-000125 | NA | Trade Partner | LINDRUM ¦ LEVEL-11 REFLECTED CEILING PLAN | 1 | 0 | 0 | NA | APPROVED | 2025-12-05 | NA | 480 | 2025-12-10 |  |  | 2025-12-12 | 2025-12-12 | KPTG-SADV-002486 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-23 | SMEPS-TRANSMIT-000187 | NA | Trade Partner | SME - DRAWINGS IFA PART SUBMISSIONS -ELC | 1 | 0 | 0 | NA | APPROVED | 2026-02-23 | NA | 2214 | 2026-03-03 |  | 2 two disciplines in one transmittal and putted in different wf |  | 2026-02-26 | KPTG-IntCorr-010035 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-23 | SMEPS-TRANSMIT-000187 | NA | Trade Partner | SME - DRAWINGS IFA PART SUBMISSIONS - TEL | 1 | 0 | 0 | NA | APPROVED | 2026-02-23 | NA | 2213 | 2026-03-03 |  | 2 two disciplines in one transmittal and putted in different wf . WF terminated as requested by Oliver S - to update the drawings |  | 2026-02-26 | KPTG-IntCorr-010034 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-23 | WPD-TRANSMIT-000063 | NA | Trade Partner | HFF - Hydraulic Tech Data Submissions | 1 | 0 | 0 | NA | APPROVED | 2026-02-23 | NA | 312 | 2026-03-03 |  |  | 2026-03-03 | 2026-03-03 | DRAFT-009081 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-23 | WEBBAUST-WTRAN-000069 | NA | Trade Partner | Fwd: (WF-000392) HFF - Remaining Comms Tech data submissions | 0 | 5 | 0 | NA | APPROVED |  | NA | NA |  |  | The register has been updated. If any further action is required, the coordinator will inform. |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-23 | KEECEPRO-TRANSMIT-000026 | NA | Trade Partner | Re: Data Sheet Submittal | 11 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-02-23 | DRAFT-008973 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-23 | SMEPS-TRANSMIT-000100 | NA | Trade Partner | SME Shop Drawing Electrical IFC A | 1 | 0 | 0 | NA | APPROVED | 2026-02-23 | WF-000169 | NA | 2026-02-27 |  | Revise & Resubmit | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-000309 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-23 | SMEPS-TRANSMIT-000101 | NA | Trade Partner | SME Shop Drawing Electrical IFC A | 1 | 0 | 0 | NA | APPROVED | 2026-02-23 | WF-000170 | NA | 2026-02-27 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-000278 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-23 | ZIA TRANSMIT-000058 | NA | Trade Partner | Fwd: CSMS- Procurement Schedule. | 0 | 16 | 0 | NA | APPROVED |  | NA | NA |  |  | SEEKD ADVISE FOR NEXT PROCESS |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-23 | SMEPS-TRANSMIT-000099 | NA | Trade Partner | SME Shop Drawing Electrical IFC A | 8 | 0 | 0 | NA | APPROVED | 2026-02-23 | WF-000166 | NA | 2026-02-27 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-000300 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-05 | Auspan-TRANSMIT-000032 | NA | Trade Partner | GF shop drawings issued for construction | 3 | 0 | 0 | NA | APPROVED | 2025-12-08 | NA | 483 | 2025-12-11 |  |  | 2025-12-08 | 2025-12-08 | KPTG-SADV-002403 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-23 | SMEPS-TRANSMIT-000102 | NA | Trade Partner | SME Shop Drawing Electrical IFC A | 1 | 0 | 0 | NA | APPROVED | 2026-02-23 | WF-000168 | NA | 2026-02-27 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-000306 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-23 | SMEPS-TRANSMIT-000104 | NA | Trade Partner | SME Shop Drawing Electrical IFC A | 4 | 0 | 0 | NA | APPROVED | 2026-02-23 | WF-000167 | NA | 2026-02-27 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-000303 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-23 | SMEPS-TRANSMIT-000103 | NA | Trade Partner | SME Shop Drawing Electrical IFA 2 | 1 | 0 | 0 | NA | APPROVED | 2026-02-23 | WF-000164 | NA | 2026-02-27 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-000341 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-23 | HDRAus-TRANSMIT-000401 | NA | Consultant | Re: M3 Stage 4 - Document upload - PDF and CAD | 10 | 0 | 0 | NA | APPROVED | 2026-02-23 | WF-004415 | 2209 | 2026-02-25 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-23 | PARR-TRANSMIT-000123 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - Revit Model | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Wrong Document number format |  | 2026-02-23 | KPTG-TRANSMIT-013337 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-20 | RDSBIM-TRANSMIT-000111 | NA | Trade Partner | MLCSPR ¦ CHAPEL CARPARK LANDSCAPE KEY PLAN AND SECTION | 4 | 0 | 0 | NA | APPROVED | 2026-02-23 | NA | 449 | 2026-03-02 |  |  | 2026-02-24 | 2026-02-24 | KPTG-IntCorr-005332 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-23 | Auspan-TRANSMIT-000089 | NA | Trade Partner | Resubmit precast shop drawings for approval. Basement. | 4 | 0 | 0 | NA | APPROVED | 2026-02-23 | WF-000222 | 387 | 2026-03-02 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000778 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-20 | RDSBIM-TRANSMIT-000112 | NA | Trade Partner | MLCSPR ¦ AQUATIC CENTRE WEST LANDSCAPE PLAN | 1 | 0 | 0 | NA | REJECTED | [5 empty] | As per the direction from Tim Shallue, Drawing needs to be updated:KPTG-IntCorr-005298 : |  | 2026-02-23 | KPTG-IntCorr-005298 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-23 | Auspan-TRANSMIT-000090 | NA | Trade Partner | Precast shop drawings for approval. Ground floor. | 12 | 0 | 0 | NA | APPROVED | 2026-02-23 | WF-000223 | 389 | 2026-03-02 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-000794 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-23 | Auspan-TRANSMIT-000091 | NA | Trade Partner | Update already IFCed shop drawings for construction. Basement panels. | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - No Review required; Register update and distribute. KPTG-TRANSMIT-000691 | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-000691 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-05 | Auspan-TRANSMIT-000033 | NA | Trade Partner | Revised GF shop drawings issued for approval | 7 | 0 | 0 | NA | APPROVED | 2025-12-05 | NA | 482 | 2025-12-10 |  |  | 2025-12-12 | 2025-12-12 | KPTG-SADV-002488 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-23 | LVPG-TRANSMIT-000018 | NA | Trade Partner | Tech Data - Unistrut update | 0 | 1 | 0 | NA | APPROVED | 2026-02-23 | WF-000221 | NA | 2026-02-25 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-000699 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-23 | INDS-TRANSMIT-000004: | NA | Trade Partner | Precast Penetration Layout - Basement | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Register and issue to Precast trade partner. | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-000701 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-23 | BTWA-TRANSMIT-000069 | NA | Trade Partner | BT-FA-SMP-019_GT31 Translucent Glazing | 0 | 1 | 0 | NA | APPROVED | 2026-02-23 | WF-000840 | NA | 2026-02-26 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-002467 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-23 | BTWA-TRANSMIT-000070 | NA | Trade Partner | BT-ARCH-SMP-016 & BT-ARCH-SMP-017 | 0 | 2 | 0 | NA | APPROVED | 2026-02-23 | WF-000841 | NA | 2026-02-26 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-002468 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-23 | KPTG-TRANSMIT-002459 | NA | Client | Fwd: MLC ¦ GL05 & GL06 Glass testing report | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | ISSUED FOR INFORMATION, TRANSMITTED TO TRADE & CONSULTANTS |  | 2026-02-23 | KPTG-TRANSMIT-002460,KPTG-TRANSMIT-002461 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-23 | KPTG-IntCorr-005257 | NA | Trade Partner | Ramp 2 Carpark Stairs shop drawings | 2 | 0 | 0 | NA | APPROVED | 2026-02-23 | NA | 448 | 2026-02-28 |  |  | 2026-03-05 | 2026-03-05 | KPTG-SADV-003819 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-23 | RDSBIM-TRANSMIT-000033 | NA | Trade Partner | 671CHP BASEMENT 4 CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | NA | APPROVED | 2026-02-23 | WF-000249 | NA | 2026-02-26 |  | 27/2/25 as advised by KAPITOL PC, ACC review 295 is VOID and initiated ACC review - WF-000249 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-23 | D&E-TRANSMIT-000342 | NA | Trade Partner | BVPI Fire Matrix Comments | 0 | 1 | 0 | KPTG-IntCorr-002960 | APPROVED |  | NA | NA |  |  | This transmittal Superseded with D&E-TRANSMIT-000343 |  | 2026-02-23 | KPTG-SADV-002249 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-23 | ZIA-TRANSMIT-000078 | NA | Trade Partner | CSMS Point List FC-3 | 0 | 1 | 0 | KPTG-IntCorr-002962 | APPROVED |  | NA | NA |  |  | IFC-Distribution Only |  | 2026-02-24 | KPTG-TRANSMIT-002650 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-23 | ADP-TRANSMIT-000036 | NA | Consultant | Northern Corridor Sprinkler Install (Fire Reg 126) | 0 | 1 | 0 | KPTG-IntCorr-0029640 | APPROVED |  | NA | NA |  |  | This does not need to be transmitted to anyone-Requested by Fabian. |  | 2026-02-25 | KPTG-IntCorr-003001 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-05 | Novas-TRANSMIT-000004 | NA | Trade Partner | NOVAS UPDATED DOOR HARDWARE SCHEDULE - R4 | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Shared file is excel sheetm not a pdf file, Hence we request them to resubmit |  | 2025-12-05 | KPTG-SADV-002381 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-23 | TATE_-IntCorr-000042-Mail | NA | Trade Partner | Tate Penetration Detail | 2 | 0 | 0 | NA | APPROVED | 2026-02-23 | NA | 1400 | 2026-03-02 |  | Voided- Requested by Fatima, Drawings are not valid |  | 2026-04-08 | NA | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-23 | Hames-TRANSMIT-000004 | NA | Consultant | A7A8 Consultant Walk - Inspection Report | 0 | 1 | 0 | KPTG-IntCorr-002965 | APPROVED |  | NA | NA |  |  | Only for information-Distributed |  | 2026-02-25 | KPTG-TRANSMIT-002668 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-23 | OveArup-TRANSMIT-000068 | NA | Consultant | M3 S1 A7A8 CSMS Site Walkthrough Inspection Report | 0 | 1 | 0 | KPTG-IntCorr-002966 | APPROVED |  | NA | NA |  |  | Distribution only- In This transmittal and NXT-TRANSMIT-000366 are same documents -Distribution only |  | 2026-02-25 | KPTG-TRANSMIT-002658 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-23 | NXT-TRANSMIT-000364 | NA | Client | 10693-0002235 - INSPECTION & TEST PLAN | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | As Built-Distribution only |  | 2026-02-23 | KPTG-TRANSMIT-002631 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-10-09 | RDSBIM-TRANSMIT-000014 | NA | Trade Partner | NXM3S1D7&8 ¦ LEVEL 1 - HS1 OFFICE RCP LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2025-10-13 | NA | 1112 | 2025-10-20 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-002623 | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-23 | RED Fire-TRANSMIT-000005 | NA | Consultant | Fire and Smoke Compartment Drawings | 18 | 0 | 0 | Clarification requested - KPTG-IntCorr-000383 | REJECTED | [7 empty] | 2026-02-24 | KPTG-DA-000969 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-23 | Head Contract Set | NA | Consultant | HC Docs | 798 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | document updation only |  | 2026-02-23 | NA | Closed | 798 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-22 | RDSBIM-TRANSMIT-000158 | NA | Trade Partner | LINDRUM ¦ GROUND AND MEZZANINE LEVEL CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | NA | APPROVED | 2026-02-23 | NA | 574 | 2026-03-02 |  |  | 2026-02-24 | 2026-02-25 | KPTG-SADV-003207 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-23 | Auspan-TRANSMIT-000052 | NA | Trade Partner | Shop drawings issued for construction | 2 | 0 | 0 | NA | APPROVED | 2026-02-23 | NA | 575 | 2026-03-02 |  |  | 2026-02-23 | 2026-02-23 | KPTG-SADV-003179 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-23 | Auspan-TRANSMIT-000053 | NA | Trade Partner | L4 L5 shop drawings issued for approval | 10 | 0 | 0 | NA | APPROVED | 2026-02-23 | NA | 578 | 2026-03-02 |  |  | 2026-03-03 | 2026-03-03 | KPTG-SADV-003282 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-04 | RDSBIM-TRANSMIT-000122 | NA | Trade Partner | LINDRUM ¦ LEVEL-09 REFLECTED CEILING PLAN | 1 | 0 | 0 | NA | APPROVED | 2025-12-05 | NA | 477 | 2025-12-10 |  |  | 2025-12-12 | 2025-12-12 | KPTG-SADV-002482 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-23 | Auspan-TRANSMIT-000054 | NA | Trade Partner | Updated L4 L5 marking plan drawings issued for approval | 2 | 0 | 0 | NA | APPROVED | 2026-02-23 | NA | 578 | 2026-03-03 |  | COMBINED BIM WORKFLOW=578 | 2026-03-03 | 2026-03-03 | KPTG-SADV-003282 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-23 | 4DW-TRANSMIT-000091 | NA | Trade Partner | Ground Level Updates | 6 | 0 | 0 | NA | APPROVED | 2026-02-23 | NA | 577 | 2026-03-02 |  |  | 2026-02-23 | 2026-02-23 | KPTG-SADV-003178 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-23 | Arc Plas-TRANSMIT-000002 | NA | Trade Partner | Updated Document Number - Tech Data Submission | 0 | 5 | 0 | NA | APPROVED | 2026-02-23 | WF-000017 | NA | 2026-02-26 |  | WORKFLOW RESUBMITTED-WF-000075, EXISTING WORKFLOW-WF-000017 IS SUBMITTED WITH NON STAMPED DOCUMENTS | 2026-03-19 | 2026-03-20 | KPTG-IntCorr-000171 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-23 | ETNInd-TRANSMIT-000003 | NA | Trade Partner | MEL11 COLO4 & 5 FAT Script Updated | 0 | 1 | 0 | NA | APPROVED | 2026-02-23 | WF-000020 | NA | 2026-02-27 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-000129 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-23 | ETNInd-TRANSMIT-000004 | NA | Trade Partner | MEL11 COLO4 & 5 Technical Documents submission for Information | 0 | 13 | 0 | NA | REJECTED | [5 empty] | Status of drawing needs to be updated. |  | 2026-02-23 | KPTG-IntCorr-000050 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-23 | ETNInd-TRANSMIT-000005 | NA | Trade Partner | MEL11-COLO4 UPS Drawings - IFC | 5 | 0 | 0 | NA | APPROVED | 2026-02-23 | WF-000033 | NA | 2026-02-24 |  |  | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-000063 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-24 | KEECEPRO-TRANSMIT-000027 | NA | Trade Partner | Lighting Control | 1 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 313 | 2026-03-02 |  |  | 2026-03-03 | 2026-03-03 | DRAFT-009091 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-23 | KPTG-TRANSMIT-002900 | NA | Trade Partner | GROUND FLOOR - PLUMBING RETICULATION AND PLUMBING DRAINAGE | 2 | 0 | 0 | NA | APPROVED | 2026-02-23 | NA | 996 | 2026-02-26 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-002903 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-23 | PARR-TRANSMIT-000039 | NA | Trade Partner | P2666 - KPG NDC D1 Stage 2 - Fuel Services - LG SECTIONS - IFC | 5 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 1252 | 2026-05-05 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-003636 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-23 | PARR-TRANSMIT-000040 | NA | Trade Partner | P2666 - KPG NDC D1 Stage 2 - Fuel Services - LG SECTIONS - IFA | 1 | 0 | 0 | NA | APPROVED | 2026-02-23 | NA | 999 | 2026-02-26 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-002991 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-04 | RDSBIM-TRANSMIT-000123 | NA | Trade Partner | LINDRUM ¦ LEVEL 06 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2025-12-05 | NA | 478 | 2025-12-12 |  |  | 2025-12-09 | 2025-12-09 | KPTG-SADV-002413 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-23 | SKS Tech-TRANSMIT-000156 | NA | Trade Partner | SKS SCHEMATICS FOR APPROVAL - TEL | 2 | 0 | 0 | NA | APPROVED | 2026-02-23 | NA | 1003 | 2026-02-26 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-003206 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-23 | VAE-Grp-TRANSMIT-000130 | NA | Trade Partner | NXDS1S2 - IFC - MECHANICAL - BUILDERS WORKS - LEVEL 5 - DAY 1 - SHEET 2 | 1 | 0 | 0 | QA Error rejected - KPTG-IntCorr-001020 | APPROVED | 2026-02-25 | NA | 1011 | 2026-02-27 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-003153 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-23 | ZIA-TRANSMIT-000025 | NA | Trade Partner | CSMS - Interface Data Sheets | 0 | 7 | 0 | clarification from Harry - KPTG-IntCorr-001021 | APPROVED | 2026-02-24 | WF-000845 | NA | 2026-03-02 |  |  |  |  | KPTG-WTRAN-001957 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-20 | fjc-TRANSMIT-000135 | NA | Consultant | Architecturals - Design Updates | 43 | 2 | 0 | NA | APPROVED | 2026-02-20 | NA | #573 | 2026-02-25 |  | 1 Drawing rejected because, The document number does not match. KPTG-SADV-003165 | 2026-02-23 | 2026-02-24 | KPTG-SADV-003186 | Closed | 42 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-23 | VIA Arch-TRANSMIT-000055 | NA | Consultant | M2 S9-10 75% DD Issue Redesign | 130 | 0 | 0 | NA | APPROVED | 2026-02-23 | NA | 350 | 2026-03-03 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-001034 | Closed | 130 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-23 | ZIA-TRANSMIT-000058 | NA | Trade Partner | Re: CSMS- Procurement Schedule. | 0 | 16 | 0 | NA | APPROVED | 2026-02-24 | WF-004434 WF-005193 |  | 2026-03-12 |  |  |  |  | KPTG-TRANSMIT-015656 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-20 | Auscool-TRANSMIT-000081 | NA | Trade Partner | SUBSTATION UPDATED | 1 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-IntCorr-000744 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-02-24 | GEMBA-D-TRANSMIT-000005 | NA | Consultant | NEXTDC GE1 ¦ Ground floor - For Certification | 12 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 19 | 2026-02-27 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-000036 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-12 | ADP-TRANSMIT-000174 | NA | Consultant | MEL741 - Stage 4 Services IFC Issue (Electrical drawings and Reg126) | 63 | 0 | 0 | NA | APPROVED | 2026-02-12 | WF-004257 | NA | 2026-02-17 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-013388 | Closed | 63 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-24 | SMEPS-TRANSMIT-000116 | SPARK-CRFI-KPG-000168 | Trade Partner | IFA: Ground Level Containment | 4 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 183 | 2026-03-03 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-000565 & KPTG-TRANSMIT-000582 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-05 | VAE-Grp-TRANSMIT-000084 | NA | Trade Partner | MECHANICAL - TECH SUB & SCHED - SIDESTREAM & PUMPS | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | Register Update Only - Done |  | 2026-02-22 | KPTG-TRANSMIT-002899 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-24 | SKS Tech-TRANSMIT-000035 | NA | Trade Partner | Re: SKS - LV Submains Submission Rev C (M3-ELC-SKS-SA-C-0400-0005) | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect revision number |  | 2026-02-24 | KPTG-TRANSMIT-013409 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-24 | D&E-TRANSMIT-000126 | NA | Trade Partner | MWYCCB - ROOF LEVEL - PENETRATION LAYOUT ZONE 5 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Attached document is different | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-000466 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-24 | NXT-TRANSMIT-001324 | NA | Trade Partner | Zone C2 - GA,GD,GE IT Busduct Shop Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-02-24 | WF-004435 | NA | 2026-03-12 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-013669 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-24 | NXT-TRANSMIT-001323 | NA | Trade Partner | Fwd: SO 611300374- M3S4 XDU pump curves and selection sheet | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For border team distribution. |  | 2026-02-24 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-24 | SKS Tech-TRANSMIT-000036 | NA | Trade Partner | SKS - LV Submains Submission Rev C (M3-ELC-SKS-SA-C-0400-0005) | 0 | 1 | 0 | NA | APPROVED | 2026-02-24 | WF-004437 | NA | 2026-03-17 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-013701 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-24 | D&E-TRANSMIT-000127 | NA | Trade Partner | MWYCCB - ROOF LEVEL - PENETRATION LAYOUT ZONE 5 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 133 | 2026-03-03 |  |  | 2026-03-16 | 2026-04-24 | KPTG-TRANSMIT-000710 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-20 | ACG-TRANSMIT-000054 | NA | Consultant | M3 - S1 ACG Shop Drawings | 7 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 3849 | 2026-02-27 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-20 | D&E-TRANSMIT-000406 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - CHILLED WATER & SFN WATER SCHEMATICS | 7 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 3847 | 2026-02-27 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-013438 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-11-17 | WilsonPD-TRANSMIT-000119 | SPARK-CRFI-KPG-000327 | Trade Partner | IFA Basin Mixer and Dryer | 0 | 1 | 0 | NA | APPROVED | 2026-02-24 | WF-000226 |  | 2026-02-24 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-000467 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-08 | ARCST-TRANSMIT-000146 | NA | Trade Partner | Stage 4 - C1 Switchroom Upper Roof Handraill - Issued for Approval | 28 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-003522 | NA | 2025-12-29 |  |  |  | 2025-12-12 | KPTG-TRANSMIT-010880 | Closed | 28 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-24 | AXIS-NSW-TRANSMIT-000005 | NA | Trade Partner | Updated Samples | 0 | 2 | 0 | NA | APPROVED | 2026-02-24 | WF-000270 | NA | 2026-03-03 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-001307 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-23 | NXT-TRANSMIT-001308 | NA | Client | 110693-000224 - Quality Plan ITP'S/ITC'S | 0 | 12 | 0 | NA | APPROVED |  | NA | NA |  |  | As-Built |  | 2026-02-23 | KPTG-TRANSMIT-013296 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-20 | W TITE-TRANSMIT-000002 | NA | Trade Partner | TDS for Waterproofing Membrane | 0 | 5 | 0 | NA | APPROVED | 2026-02-25 | WF-000950 | NA | 2026-03-03 |  | this wf terminated WF-000945 |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-24 | crossfir-TRANSMIT-000050 | NA | Trade Partner | Dry Fire - Level 09 to Roof, IFA | 10 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 548 | 2026-03-02 |  |  | 2026-04-13 | 2026-04-13 | DRAFT-016766 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-23 | ZIA-TRANSMIT-000059 | NA | Trade Partner | L3 and Cx Plan Submission | 0 | 1 | 0 | NA | APPROVED | 2026-02-23 | WF-004421 | NA | 2026-03-03 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-013581 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-21 | HDRAus-TRANSMIT-000402 | NA | Consultant | HDRAus-TRANSMIT-000402 | 5 | 1 | 0 | NA | REJECTED | [5 empty] | Drawings and technical data in single transmittal. |  | 2026-02-23 | KPTG-DA-005055 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-23 | HDRAus-TRANSMIT-000403 | NA | Consultant | Stage 2 - Architectural Documentation - General Updates | 28 | 0 | 0 | NA | APPROVED | 2026-02-23 | NA | 3853 | 2026-02-25 |  |  | 2026-03-04 | 2026-03-12 | KPTG-TRANSMIT-014187 | Closed | 28 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-23 | KPTG-TRANSMIT-002726 | NA | Trade Partner | Fold Away Shower Seat 960x395mm White Compact Laminate SAN-07 | 0 | 1 | 0 | NA | APPROVED | 2026-02-24 | WF-000947 | NA | 2026-03-02 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-24 | Nilsen3-TRANSMIT-000038 | NA | Trade Partner | Nilsen Sample Submission | 0 | 7 | 0 | NA | APPROVED | 2026-02-24 | WF-004438 | NA | 2026-03-17 |  | As requested by Peter Z, the WF has been terminated | 2026-02-25 |  | NA | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-24 | KPTG-WTRAN-008061 | NA | Trade Partner | HYCHEM SUPAFLOOR | 0 | 3 | 0 | NA | APPROVED | 2026-02-24 | WF-004439 | NA | 2026-03-09 |  | As per requested by Sam S - WF terminated |  |  | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-01 | KARE-TRANSMIT-000072 | NA | Trade Partner | Revised Light fixtures for review | 0 | 2 | 0 |  | APPROVED | 2025-12-01 | WF-000778 | NA | 2025-12-08 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-05 | RDSBIM-TRANSMIT-000123 | NA | Trade Partner | LEVEL 12 CONCRETE PROFILE PLAN | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2025-12-08 | KPTG-TRANSMIT-002488 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-24 | RDSBIM-TRANSMIT-000035 | NA | Trade Partner | MWYCCB ¦ LEVEL 01 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Review needed IFC issued to trades |  | 2026-02-25 | KPTG-TRANSMIT-000471 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-11-05 | Ardon-TRANSMIT-000007 | NA | Trade Partner | Updated Aconex Doc No - Frames Shop Drawings | 65 | 0 | 0 | NA | APPROVED | 2025-11-05 | NA | 3172 | 2025-11-24 |  |  | 2026-02-23 | 2026-02-23 | KPTG-TRANSMIT-013368 | Closed | 66 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-17 | KEECEPRO-TRANSMIT-000024 | NA | Trade Partner | Re: DB Shop Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 314 | 2026-03-02 |  |  | 2026-03-03 | 2026-03-03 | DRAFT-009092 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-24 | LANSA-TRANSMIT-000096 | NA | Trade Partner | Level 3 Water IFC | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  | KPTG-TRANSMIT-002737 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-19 | W TITE-TRANSMIT-000001 | NA | Trade Partner | WTITE-ARCH-TEC-001 Vandex® BB75E-Z | 0 | 1 | 0 | NA | APPROVED | 2026-02-25 | WF-000949 | NA | 2026-03-03 |  | this wf terminated WF-000948 |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-24 | HGP-TRANSMIT-000046 | NA | Trade Partner | Louvre Sample Transmittals | 0 | 3 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-23 | Stowe-A-TRANSMIT-000490 | NA | Trade Partner | Next DC -Stowe Commissioning Implementation Plan | 0 | 1 | 0 | NA | APPROVED | 2026-02-23 | WF-004422 | NA | 2026-03-03 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-014112 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-24 | VIA Arch-TRANSMIT-000057 | NA | Consultant | M2 S9-10 Redesign 75% DD Issue | 8 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 351 | 2026-03-03 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-001038 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-24 | INSULPAK-TRANSMIT-000011 | NA | Trade Partner | HFF MSSB Drawings for review. | 1 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 315 | 2026-03-02 |  |  | 2026-03-03 | 2026-03-03 | DRAFT-009100 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-23 | Stowe-A-TRANSMIT-000491 | NA | Trade Partner | Stowe - Tech Data - IFC | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-02-23 | KPTG-TRANSMIT-013335 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-06 | RDSBIM-TRANSMIT-000124 | NA | Trade Partner | LEVEL 09 CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2025-12-08 | KPTG-TRANSMIT-002489 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-24 | Baigents-TRANSMIT-000069 | SPARK-CRFI-KPG-000222 | Trade Partner | MCC Precast Lid IFC | 1 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 135 | 2026-03-03 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-001441 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-24 | KEECEPRO-TRANSMIT-000028 | NA | Trade Partner | Above Ground Shop Drawings | 6 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 316 | 2026-03-02 |  |  | 2026-03-03 | 2026-03-03 | KAPITOL-TRANSMIT-001151 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-24 | D&E-TRANSMIT-000344 | NA | Trade Partner | Siemens ITPS - Issued for construction | 0 | 4 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC-Distribution Only. Comment register added |  | 2026-02-24 | KPTG-TRANSMIT-002642 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-24 | OveArup-TRANSMIT-000070 | NA | Consultant | 3 S1 A7A8 FIP_FID_HYD Site Walkthrough Inspection Report | 0 | 3 | 0 | KPTG-IntCorr-002982 | APPROVED |  | NA | NA |  |  | This does not need to be transmitted to anyone-Requested by Fabian- This transmittal and NXT-TRANSMIT-000365 are same documents-Only for kapitol Information |  | 2026-02-25 | KPTG-IntCorr-003002 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-23 | Tradetec-TRANSMIT-000371 | NA | Trade Partner | Stage 2 - IFA CP11, CP17 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Attached PDF file has a name error. Not the latest revision. |  | 2026-02-23 | KPTG-DA-005061 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-23 | Stowe-A-TRANSMIT-000496 | NA | Trade Partner | Stowe - Tech Data Submission - Temp Gen Panel | 0 | 1 | 0 | NA | APPROVED | 2026-02-23 | WF-004423 | NA | 2026-03-05 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-013685 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-23 | Stowe-A-TRANSMIT-000495 | NA | Trade Partner | Stowe - Tech Data Submission - Work station | 0 | 1 | 0 | NA | APPROVED | 2026-02-23 | WF-004425 | NA | 2026-03-06 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-014265 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-23 | Stowe-A-TRANSMIT-000499 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - COMMS TRAY - LOWER ROOF B1 - 23.02.2026 | 1 | 0 | 0 | NA | APPROVED | 2026-02-23 | NA | 3855 | 2026-03-02 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-013729 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-05 | ASV-TRANSMIT-000134 | NA | Trade Partner | Resubmittal - Hydraulic Samples | 35 | 0 | 0 | NA | APPROVED | 2026-02-24 | WF-004446 | NA | 2026-03-17 |  | The drawings have been resubmitted for review as requested by Zak | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014854 | Closed | 35 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-24 | Baigents-TRANSMIT-000068 | NA | Trade Partner | MCC Lift Precast - IFC | 9 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 136 | 2026-03-03 |  | Bim360 review terminated by Lawden Constructed |  | 2026-08-25 | NA | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-08 | ARCST-TRANSMIT-000145 | NA | Trade Partner | C1 Switchroom Upper Roof - Issued for Approval | 124 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-003735 | NA | 2026-02-16 |  | The drawings have been resubmitted for review as requested by Max. the following steps have been skipped - IVS-HDR-KAP. As requested by Lola Winstanley, the workflow (WF-003735) has been terminated. The workflow has been restarted as requested by Lola.16/1/2026 |  | 2025-12-18 | KPTG-TRANSMIT-011085, | Closed | 124 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-18 | KPTG-IntCorr-009561 | NA | Trade Partner | Arcus Wire - Technical Data Sheet | 0 | 3 | 0 | NA | APPROVED | 2026-02-23 | WF-004420 | NA | 2026-03-10 |  | KPTG-TRANSMIT-014318 3/10/2026 1 Doc Rejected KPTG-TRANSMIT-014488 3/17/2026 2 Docs | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-014488 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-24 | Normark-TRANSMIT-000050 | NA | Trade Partner | PL03- Goal Post Tech data sheet for approval | 0 | 1 | 0 | NA | APPROVED | 2026-02-24 | WF-000843 | NA | 2026-03-03 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-003050 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-05 | SMEPS-TRANSMIT-000055 | NA | Trade Partner | Updated Tech Data - Unistrut | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Supersede by revision 3 |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-03 | SMEPS-TRANSMIT-000031 -SMEPS-TRANSMIT-000051 | NA | Trade Partner | Tech Data - MV Crimp Lugs | 0 | 21 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings | 2026-02-11 | 2026-02-11 | KPTG-TRANSMIT-000113 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-13 | SMEPS-TRANSMIT-000082- | NA | Trade Partner | SME Shop Drawing Electrical IFA 2 | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-02-16 | KPTG-SADV-000221 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-23 | SKS Tech-TRANSMIT-000156 | NA | Trade Partner | SKS SCHEMATICS FOR APPROVAL - ELC | 6 | 0 | 0 | NA | APPROVED | 2026-02-23 | NA | 1001 | 2026-02-26 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-003271 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-24 | SMEPS-TRANSMIT-000105 | NA | Trade Partner | SME Shop Drawing Electrical IFC A | 1 | 0 | 0 | NA | APPROVED | 2026-02-24 | WF-000171 | NA | 2026-02-24 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-000284 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-24 | Entire M-TRANSMIT-000011 | NA | Trade Partner | Mechanical penetration shop drawings IFA | 4 | 0 | 0 | NA | APPROVED | 2026-02-24 | WF-000172 | NA | 2026-03-02 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-000360 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-24 | SMEPS-TRANSMIT-000107 | NA | Trade Partner | SME Shop Drawing Electrical IFA 2 | 3 | 0 | 0 | NA | APPROVED | 2026-02-24 | WF - 000174 | NA | 2026-03-03 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-000342 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-24 | RDSBIM-TRANSMIT-000060 | NA | Trade Partner | NXD1S2 ¦ LEVEL 05 CONCRETE PROFILE KEYPLAN | 5 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 1005 | 2026-02-27 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-003000 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-06 | RDSBIM-TRANSMIT-000125 | NA | Trade Partner | LEVEL 01 PARTITION WALL PLAN | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2025-12-12 | KPTG-TRANSMIT-002486 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-24 | SKS Tech-TRANSMIT-000157 | NA | Trade Partner | STRING B & STRING C SCHEMATICS IFC | 2 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 1009 | 2026-02-27 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-002960 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-24 | SKS Tech-TRANSMIT-000158 | NA | Trade Partner | SINGLE LINE DRAWINGS IFC ¦ RE-TRANSMIT | 1 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 1008 | 2026-02-27 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-002956 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-24 | ADP-TRANSMIT-000252 | NA | Consultant | MEL741 - Stage 4 Services IFC Issue Electrical drawings, current docs | 5 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 2231 | 2026-02-26 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-013827 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-24 | RDSBIM-TRANSMIT-000023 | NA | Trade Partner | GREYSTAR - BASEMENT FLOOR CONCRETE PROFILE KEY PLAN | 2 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 391 | 2026-02-27 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-000797 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-24 | Auspan-TRANSMIT-000093 | NA | Trade Partner | Precast shop drawings for approval. Ground floor | 1 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 393 | 2026-03-02 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000775 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-24 | Auspan-TRANSMIT-000094 | NA | Trade Partner | Precast shop drawings for approval. Ground floor. | 3 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 395 | 2026-03-02 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000779 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-24 | Fyfe-TRANSMIT-000013 | NA | Consultant | Basement Tank Shop Drawings | 7 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 397 | 2026-03-02 |  |  | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-000941 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-24 | JCBa-TRANSMIT-000060 | NA | Consultant | IFC A-4400 - CAR & BICYCLE RAMPS | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect Aconex status. |  | 2026-02-24 | KPTG-DA-000766 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-24 | JCBa-TRANSMIT-000061 | NA | Consultant | STRUCTURAL SETOUT PLANS GROUND FLOOR: ZONES 2 & 5 | 2 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 399 | 2026-02-27 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-000747 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-11 | StantecA-TRANSMIT-000300 | NA | Consultant | IFC Documents - Fire Protection | 0 | 1 | 0 | NA | APPROVED | 2026-02-11 | WF-000189 | NA | 2026-02-16 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-000705 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-05 | ccair-TRANSMIT-000072 | NA | Trade Partner | Level 03 & 09 - Mechanical Ductwork & Pipework Layout - IFC | 24 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2025-12-12 | KPTG-TRANSMIT-002485 | Closed | 24 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-24 | RBG-TRANSMIT-000055 | NA | Consultant | Structural Drawings for Podium Steelwork - Issued for Certification | 10 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 297 | 2026-02-27 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000519 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-24 | B Smart-TRANSMIT-000060 | NA | Consultant | CPP B1 and L2-L20 IFC | 9 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 299 | 2026-02-27 |  |  | 2026-03-02 | 2026-03-02 | DRAFT-004050 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-03 | D&E-TRANSMIT-000317 | NA | Trade Partner | SCRIPTS - FOA2 | 0 | 14 | 0 | NA | APPROVED | 2026-02-03 | WF-000916 | NA | 2026-02-10 |  | After upadate with comment register | 2026-02-11 | 2026-02-11 | KPTG-TRANSMIT-002476 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-24 | Tradetec-TRANSMIT-000372 | NA | Trade Partner | Stage 4 - IFA - CP20, CP37, LVP39 | 3 | 0 | 0 | NA | REJECTED | 2026-02-24 | [6 empty] | 2026-02-24 | KPTG-TRANSMIT-013473 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-24 | PFP PL-TRANSMIT-000070 | NA | Trade Partner | Ground and Level 1 Zone 2 IFA | 2 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 2219 | 2026-03-04 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-014933 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-24 | ZIA-TRANSMIT-000069 | NA | Trade Partner | M3S1 DATAHALL A7 ORMB Location | 1 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 1401 | 2026-03-03 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-002772 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-06-23 | INGEN3D-TRANSMIT-000434 | NA | Consultant | I3D-378 Next DC M3 Stage 4 - Level 1 (Zone 1) - NLB Panels - IFC | 15 | 0 | 0 | NA | APPROVED | 2025-10-31 | WF-003169 | NA | 2025-11-04 |  | That worklow contains only one document | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-013488 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-10 | KPTG-IntCorr-002627 | NA | Trade Partner | DH7&8 Signage Shop Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-02-10 | NA | 1379 | 2026-02-17 |  | Terminated -Requested by Kim-(Terminate existing workflow as we received comments and actioned) New drawing recieved KPTG-IntCorr-003006-From Kim |  | 2026-02-27 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-24 | RDSBIM-TRANSMIT-000228 | NA | Trade Partner | NXM3S3 ¦ ROOF HOB AND PLINTH PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 3859 | 2026-02-26 |  | The workflow has been terminated as requested by Max , Document resubmitted via new transmittal - KPTG-TRANSMIT-013839 |  |  | NA | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-08 | ARCST-TRANSMIT-000147 | NA | Trade Partner | Stage 4 - C1 Cooling Tower HD Bolts - Issued for Construction | 4 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-003528 | NA | 2025-12-29 |  |  |  | 2026-01-07 | KPTG-TRANSMIT-011281 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-24 | D&E-TRANSMIT-000408 | NA | Trade Partner | Chiller Roof - Builders Works Layout Zones | 5 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 2216 | 2026-03-04 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-013677 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-24 | KPTG-IntCorr-005328 | NA | Trade Partner | 8th Wonder Signage Shop Drawings | 67 | 0 | 0 | KPTG-SADV-003766 | APPROVED | 2026-02-25 | NA | 451 | 2026-03-04 |  |  | 2026-03-13 | 2026-03-13 | KPTG-SADV-003869 | Closed | 67 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-24 | WGAVIC-TRANSMIT-000070 | NA | Consultant | M2 - Stage 9, 10 and 11 Stair Core and Connections Certification Issue | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Issued for Information only. No review required. Updated ACC |  | 2026-02-24 | KPTG-TRANSMIT-000986 | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-24 | BTWA-TRANSMIT-000071 | NA | Trade Partner | Fixing Method- Screw / Anchor Bolt | 0 | 1 | 0 | NA | APPROVED | 2026-02-24 | WF-000844 | NA | 2026-02-27 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-002636 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-24 | SKS Tech-TRANSMIT-000037 | NA | Trade Partner | TYPICAL DETAILS PRE FAB HANGERS | 1 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 2220 | 2026-03-04 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014840 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-24 | ADP-TRANSMIT-000250 | NA | Consultant | Stage 4 Services IFC Issue (Electrical drawings, current docs) | 3 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 2222 | 2026-02-26 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-013815 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-24 | IVS-TRANSMIT-000341 | NA | Consultant | Re: Issued For Construction - Upper Walk way Steelwork Elevations & Details | 5 | 0 | 0 | KPTG-TRANSMIT-013450 | APPROVED |  | NA | NA |  |  | SEEKED ADVISE DUE TO INCORRECT REVISION NUMBER |  |  |  | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-24 | RDSBIM-TRANSMIT-000229 | NA | Trade Partner | GROUND FLOOR-C-G-064 UNISEX WC FLOOR FINISHES LAYOUT AND ELEVATIONS - #2225 | 1 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 2225 | 2026-02-26 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014374 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-24 | RDSBIM-TRANSMIT-000230 | NA | Trade Partner | LEVEL 01-C-1-020 CLEANER FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 2227 | 2026-02-26 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-014452 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-24 | ADP-TRANSMIT-000251 | NA | Consultant | Re MEL741 - Stage 4 Services IFC Issue Electrical drawings, current docs | 9 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 2229 | 2026-02-26 |  | 6 DOCUMENTS ARE COMPELETED REVIEW | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-013823 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-08 | Tradetec-TRANSMIT-000281 | NA | Trade Partner | Stage 4 - HVs IFA - HVP 20, 22, 23, 24, 25, 26 | 7 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-TRANSMIT-010703 The reference number is not aligned with the S4 project |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-24 | ADP-TRANSMIT-000253 | NA | Consultant | Stage 4 Services IFC Issue (Electrical drawings) | 8 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 2233 | 2026-02-27 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-013831 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-24 | Auscool-TRANSMIT-000082 | NA | Trade Partner | Control Valve Schedule & Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-02-25 | WF-000634 | NA | 2026-03-03 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-002009 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-24 | WGAVIC-TRANSMIT-000071 | NA | Consultant | M2 - Stage 10 Level 1 Slab Certification Issue | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Issued for Information, No review required. Updated ACC. |  | 2026-02-24 | KPTG-TRANSMIT-000989 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-24 | Entire M-TRANSMIT-000003 | NA | Trade Partner | Mechanical Technical Data Package Rev A IFA | 0 | 18 | 0 | NA | APPROVED | 2026-02-24 | WF-000044 | NA | 2026-03-02 |  |  | 2026-03-12 | 2026-03-20 | KPTG-TRANSMIT-000087 &KPTG-TRANSMIT-000090,KPTG-TRANSMIT-000168 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-24 | Entire M-TRANSMIT-000003 | NA | Trade Partner | Mechanical Technical Data Package Rev A IFA | 0 | 1 | 0 | NA | APPROVED | 2026-06-09 | WF-000306 | NA | 2026-06-12 |  | SUBSTITUTION REQUEST FORM NEEDS SEPARATE WORKFLOW | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-000915 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-24 | EFP-TRANSMIT-000007 | NA | Trade Partner | Fire Technical Data Sheets | 0 | 14 | 0 | NA | APPROVED | 2026-02-24 | WF-000023 | NA | 2026-03-02 |  |  | 2026-03-05 | 2026-03-05 | KPTG-TRANSMIT-000072 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-24 | Appselec-TRANSMIT-000014 | NA | Trade Partner | LV Cable Rev 1 (APAR) Substitution | 0 | 3 | 0 | NA | APPROVED | 2026-02-24 | WF-000025 | NA | 2026-03-04 |  |  | 2026-03-05 | 2026-03-05 | KPTG-TRANSMIT-000071 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-24 | KPTG-WTRAN-007907 | NA | Consultant | S4 ¦ CONSULTANT REVIEW - KAP- HDR-HAMES-NDC | 0 | 7 | 0 | NA | APPROVED | 2026-02-24 | WF-004367 | NA | 2026-03-04 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-24 | VIA Arch-TRANSMIT-000059 | NA | Consultant | M2S9-10 75% DD Issue Redesign | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required, Updated register and ACC |  | 2026-02-24 | KPTG-TRANSMIT-000992 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-05 | ccair-TRANSMIT-000073 | NA | Trade Partner | Level 07 - 14 Mechanical Ductwork & Pipework Shop Drawings - IFA | 36 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF - 000792 | 498 | 2025-12-15 |  |  | 2026-01-15 | 2026-01-15 | KPTG-SADV-004907 | Closed | 36 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-24 | KEECEPRO-TRANSMIT-000024 | NA | Trade Partner | DB Shop Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 300 | 2026-03-12 |  | As per Alex - void 300 as its been marked as revise and resubmit |  | 2026-02-25 | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-25 | Nilsen3-TRANSMIT-000039 | NA | Trade Partner | Sample submission | 0 | 1 | 0 | NA | APPROVED | 2026-02-25 | WF-004458 | NA | 2026-03-09 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-013601 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-17 | KPTG-IntCorr-002821 | NA | Consultant | Door Work Order, Frame Shop Drawing, Frame Work Order | 0 | 3 | 0 | NA | APPROVED | 2026-02-17 | NA | 1385 | 2026-02-24 |  | Instead of WF-000940 |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-25 | Nilsen3-TRANSMIT-000040 | NA | Trade Partner | Fixings HV Containment and Boards (SAMPLE) | 0 | 1 | 0 | NA | APPROVED | 2026-02-25 | WF-004459 | NA | 2026-03-13 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-014424 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | KPTG-WTRAN-008112 | NA | Trade Partner | Paint - Timeless Grey | 0 | 2 | 0 | NA | APPROVED | 2026-02-25 | WF-004460 | NA | 2026-03-13 |  | The drawing has been submitted for review as requested by Ned | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-013987 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-25 | HEXA-TRANSMIT-000005 | NA | Trade Partner | B08 Mechanical Services Drawings IFC | 8 | 0 | 0 | NA | APPROVED | 2026-02-25 | NA | 317 | 2026-02-28 |  |  | 2026-02-27 | 2026-02-27 | DRAFT-009037 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | Archacce-TRANSMIT-000016 | NA | Trade Partner | Fwd: NEXTDC M3 Stages 1, 2 & 4 - Exemption Report NCC D4D5.pdf | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For Information only |  | 2026-02-25 | KPTG-TRANSMIT-013506 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | NXT-TRANSMIT-001327 | NA | Trade Partner | Zone C2 – IFA Shop Drawings Submission | 13 | 0 | 0 | NA | APPROVED | 2026-02-25 | WF-004461 | NA | 2026-03-13 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-013650 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-25 | Tradetec-TRANSMIT-000045 | NA | Trade Partner | Hauff-Technik Knockout Sleeve Technical Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-02-25 | WF-000274 | NA | 2026-03-05 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-001328 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | NXT-TRANSMIT-001328 | NA | Trade Partner | Re: Vertiv LVSB Shop Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-02-25 | WF-004466 | NA | 2026-03-13 |  | The drawings No. M3-04-EL-VER-SWB-003 and M3-04-EL-VER-SWB-004 are updated versions; however, the revision has not been changed.-KPTG-TRANSMIT-013508 reply from NDC - NXT-PA-003647 |  |  | KPTG-TRANSMIT-013656 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-06 | RDSBIM-TRANSMIT-000126 | NA | Trade Partner | LINDRUM ¦ LEVEL 08 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2025-12-08 | NA | 484 | 2025-12-11 |  |  | 2025-12-17 | 2025-12-17 | KPTG-SADV-002524 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-25 | KPTG-WTRAN-008116 | NA | Trade Partner | Metal Roof Safety Mesh | 0 | 1 | 0 | NA | APPROVED | 2026-02-25 | WF-004462 | NA | 2026-03-13 |  |  | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-013870 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-25 | Archacce-TRANSMIT-000002 | NA | Consultant | S9-11 Exempt Areas Markup (DRAFT) | 1 | 0 | 0 | NA | APPROVED | 2026-02-25 | NA | 357 | 2026-03-02 |  |  | 2026-02-27 | 2026-03-02 | KPTG-TRANSMIT-001107 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | KPTG-TRANSMIT-013503 | NA | Trade Partner | Sample Workflow | 0 | 14 | 0 | NA | APPROVED | 2026-02-25 | WF-004463 | NA | 2026-03-18 |  | The WF has been generated as requested by Peter Z | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015121 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-24 | VAE-Grp-TRANSMIT-000132 | NA | Trade Partner | MECHANICAL - NORTHERN & SOUTHERN RISERS | 4 | 0 | 0 | QA Error rejected - KPTG-IntCorr-001026 | APPROVED | 2026-02-25 | NA | 1015 | 2026-02-27 |  |  | 2026-03-18 | 2026-03-23 | KPTG-TRANSMIT-003218 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-24 | VAE-Grp-TRANSMIT-000131 | NA | Trade Partner | MECHANICAL - HVAC LAYOUT - LEVEL 5 - DAY 1 - SHEET 2 | 1 | 0 | 0 | QA Error rejected - KPTG-IntCorr-001027 | APPROVED | 2026-02-25 | NA | 1013 | 2026-02-27 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-003149 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | PARR-TRANSMIT-000124 | NA | Trade Partner | Re: P2680 - NDC M3 Stage 4 - Fuel - PUMP ROOM, CONTROL SYSTEM DRAWINGS | 6 | 0 | 0 | NA | REJECTED | [5 empty] | The original transmittal (PARR-TRANSMIT-000120) contained a total of 9 drawings, but the new one (PARR-TRANSMIT-000124) |  | 2026-02-25 | KPTG-TRANSMIT-013511 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | NXT-TRANSMIT-001330 | NA | Trade Partner | NextDC M3 Stage 4 LVSB - Updated MSB Schematic | 1 | 0 | 0 | NA | APPROVED | 2026-02-25 | WF-004464 | NA | 2026-03-13 |  |  |  | 2026-02-27 | KPTG-TRANSMIT-013663 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-24 | RDSBIM-TRANSMIT-000017 | NA | Trade Partner | GROUND FLOOR FOUNDATION LAYOUT PLAN AND SECTION AND COMPLETENESS MEASURE | 7 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 274 | 2026-02-27 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-000808 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-24 | KPTG-IntCorr-000390 | NA | Trade Partner | PCF Raft Envelope IFC - Final Review | 18 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 276 | 2026-02-27 |  |  |  | 2026-03-04 | KPTG-TRANSMIT-000633 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-24 | Civilex-TRANSMIT-000032 | NA | Trade Partner | Epoxy Bars Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-02-24 | WF-000180 | NA | 2026-02-26 |  | NO DISTRIBUTION AS PER KPTG-IntCorr-000414 | 2026-03-02 | 2026-03-02 | KPTG-IntCorr-000414 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-08 | Auspan-TRANSMIT-000032 | NA | Trade Partner | Cast in plate SP300 each face detail. | 1 | 0 | 0 | NA | REJECTED | [5 empty] | The reference number does not correspond with the S4 project |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-24 | KPTG-IntCorr-000367 | NA | Trade Partner | COM Drainage Approval | 0 | 1 | 0 | NA | APPROVED | [5 empty] | Internal Transmital only - KPTG-TRANSMIT-000549 |  |  | KPTG-TRANSMIT-000549 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-09-30 | SMEPS-TRANSMIT-000022 | SPARK-CRFI-KPG-000235 | Trade Partner | Shop Drawings - General (Legend, Plans) | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-02-25 | KPTG-TRANSMIT-000476 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-25 | IDS-TRANSMIT-000010 | NA | Trade Partner | Re: Dry Fire - HFF GROUND ZONE 1 & 2 | 1 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-02-25 | DRAFT-009004 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-24 | Stowe-A-TRANSMIT-000501 | NA | Trade Partner | Stowe - Tech Data Submission - ATS Shop drawing | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The revision number inside and outside is wrong. |  | 2026-02-24 | KPTG-DA-005087 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-24 | NXT-TRANSMIT-001325 | NA | Client | 110693-000228 - QUALITY PLAN ITP'S/ITC'S | 0 | 13 | 0 | NA | APPROVED |  | NA | NA |  |  | As Built |  | 2026-02-24 | KPTG-TRANSMIT-013436 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-24 | Tradetec-TRANSMIT-000373 | NA | Trade Partner | Tech Data - Sitewide - Resourceco Recycled Crushed Concrete | 0 | 1 | 0 | NA | APPROVED | 2026-02-24 | WF-004440 | NA | 2026-03-03 |  |  | 2026-03-16 | 2026-03-16 | PTG-TRANSMIT-014449 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-24 | HDRAus-TRANSMIT-000405 | NA | Consultant | M3SW | 0 | 2 | 0 | NA | REJECTED | [5 empty] | “Comment Register” submitted as a transmittal. With the wrong numbering format. |  | 2026-02-24 | KPTG-DA-005091 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-24 | ETNInd-TRANSMIT-000091 | NA | Trade Partner | M3 Stage 2 – Commisioning Plan Revise & Resubmit | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Document number inside and outside are wrong. Comment register shared as a transmittal. |  | 2026-02-24 | KPTG-DA-005092 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-24 | Stowe-A-TRANSMIT-000502 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - LIGHTING CONTROL - 24.02.2026 | 4 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 3858 | 2026-03-03 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014399 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-24 | NXT-TRANSMIT-001326 | NA | Client | M3 Sitewide Earthing Study Report | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-02-24 | KPTG-TRANSMIT-013437 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-01 | RDSBIM-TRANSMIT-000005 | N/A | Trade Partner | GROUND FLOOR TO LEVEL 09 LIFT CORE 1 CONCRETE PROFILE PLAN AND SECTIONAL ELEVATION | 3 | 0 | 0 | NA | APPROVED | 2025-12-01 | NA | 105 | 2025-12-03 |  |  | 2025-12-10 | 2025-12-10 | KPTG-TRANSMIT-000224 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2025-12-08 | SCP_NR-TRANSMIT-000089 | NA | Consultant | PPT AIR SCHEMATIC UPDATED | 1 | 0 | 0 | NA | APPROVED | 2025-12-09 |  | 253 | 2025-12-12 |  | The register has been updated. If any further action is required, the coordinator will inform. |  | 2025-12-19 |  | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-11-10 | ARCST-TRANSMIT-000128 | NA | Trade Partner | Roof Walkway Steel Updated IFC Shop Drawings Part-1 | 200 | 0 | 0 | NA | APPROVED | 2026-02-18 | WF-004343 | NA | 2025-12-03 |  |  | 2026-02-23 | 2026-02-24 | KPTG-TRANSMIT-013483 | Closed | 200 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-10-17 | RDSBIM-TRANSMIT-000157 | NA | Trade Partner | NXM3S2 ¦ LEVEL 01-B-1-093 CLEANERS-FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2025-10-20 | NA | 3073 | 2025-11-05 |  |  | 2026-02-23 | 2026-02-24 | KPTG-TRANSMIT-013469 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-25 | D&E-TRANSMIT-000128 | NA | Trade Partner | MWYCCB - LEVEL 1 - PENETRATION LAYOUT ZONE 2 & ZONE 4 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-02-25 | NA | 137 | 2026-03-04 |  |  |  | 2026-04-17 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | ARCST-TRANSMIT-000216 | NA | Trade Partner | C2 Cooling Tower - Roof & Secondary Steel - Issued for Approval | 151 | 0 | 0 | NA | APPROVED | 2026-02-25 | WF-004471 | NA | 2026-03-23 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-016028 | Closed | 99 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-18 | ccair-TRANSMIT-000093 | NA | Trade Partner | Level 08 Mechanical Ductwork & Pipework Layout | 12 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-02-25 | 2026-02-25 | DRAFT-015246 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | NXT-TRANSMIT-001331 | NA | Trade Partner | Zone C2 – Completion of IFA Shop Drawings Submission | 3 | 0 | 0 | NA | APPROVED | 2026-02-25 | WF-004475 | NA | 2026-03-13 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-013643 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-25 | JCBa-TRANSMIT-000212 | NA | Consultant | SSP BTR | 8 | 0 | 0 | NA | APPROVED | 2026-02-25 | WF-000951 | 549 | 2026-03-04 |  |  | 2026-03-19 | 2026-03-19 | DRAFT-016077 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-23 | D&E-TRANSMIT-000343 | NA | Trade Partner | BVPI Fire Matrix Comments | 0 | 1 | 0 | KPTG-IntCorr-002996 | APPROVED |  | NA | NA |  |  | IFC Distribution Only |  | 2026-02-25 | KPTG-TRANSMIT-002655 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-25 | RDSBIM-TRANSMIT-000025 | NA | Trade Partner | GREYSTAR GROUND FLOOR CONCRETE PROFILE KEY PLAN AND SECTION | 6 | 0 | 0 | NA | APPROVED | 2026-02-25 | NA | 401 | 2026-03-02 |  | Status - Revise & Resubmit; | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-000793 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-04 | Auspan-TRANSMIT-000030 | N/A | Trade Partner | Remaining panels for 22KV building | 28 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-003529 |  | 2025-12-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-25 | RDSBIM-TRANSMIT-000026 | NA | Trade Partner | GREYSTAR BASEMENT FLOOR CONCRETE PROFILE KEY PLAN | 8 | 0 | 0 | NA | APPROVED | 2026-02-25 | NA | 407 | 2026-03-02 |  |  | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-000804 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-25 | Auspan-TRANSMIT-000095 | NA | Trade Partner | Precast shop drawings for construction. Ground floor and basement | 47 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol PC, Register and distribute. |  | 2026-02-25 | KPTG-TRANSMIT-000729 | Closed | 47 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-25 | Auspan-TRANSMIT-000096 | NA | Trade Partner | : Precast shop drawings for construction. Basement. | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol PC, Register and distribute. - |  | 2026-02-25 | KPTG-TRANSMIT-000731 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-25 | Altaire-TRANSMIT-000087 | NA | Trade Partner | NEXTDC M3S3 22KV - Combined Fire Matrix (For Approval) (1) | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | The register has been updated. If any further action is required, the coordinator will inform. |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-25 | Auspan-TRANSMIT-000097 | NA | Trade Partner | Resubmit precast shop drawings for approval. Ground floor | 32 | 0 | 0 | NA | APPROVED | 2026-02-25 | NA | 409 | 2026-03-04 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-000884 | Closed | 32 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-25 | LVPG-TRANSMIT-000019 | NA | Trade Partner | LVPG-HY-TECH-038 - SILT TRAP - 150mm DWV with 100mm outlet | 0 | 1 | 0 | NA | APPROVED | 2026-02-25 | WF-000231 | NA | 2026-03-02 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-000746 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-25 | Altaire-TRANSMIT-000088 | NA | Trade Partner | NEXTDC M3S3 22KV - Dry Fire Shop Drawings (For Construction) | 4 | 0 | 0 | NA | APPROVED | 2026-02-26 | WF-004489 | NA | 2026-03-11 |  | The register has been updated. If any further action is required, the coordinator will inform. #ACTION TAKEN | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-014326 KPTG-TRANSMIT-014515 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-25 | WGAVIC-TRANSMIT-000072 | NA | Consultant | M2 - Stage 9 Ground Floor Shear Stud Update Construction Issue | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, Updated register and ACC and distributed. |  | 2026-02-25 | KPTG-TRANSMIT-001002 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-25 | JCBa-TRANSMIT-000062 | NA | Consultant | IFC A-4400 - CAR & BICYCLE RAMPS | 4 | 0 | 0 | NA | APPROVED | 2026-02-25 | NA | 403 | 2026-02-27 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-000788 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-25 | Auspan-TRANSMIT-000098 | NA | Trade Partner | Update precast dowel layout basement. Zone 4,5 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol PC, Register and distribute. - |  | 2026-02-25 | KPTG-TRANSMIT-000744 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-08 | Tradetec-TRANSMIT-000288 | N/A | Trade Partner | Stage 4 - HVs IFA - HVP 20 22 23 24 25 26 | 6 | 0 | 0 | NA | APPROVED | 2025-12-08 | NA | 1619 | 2025-12-16 |  |  |  | 2026-01-18 | KPTG-TRANSMIT-011111 | Closed | 6 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-25 | IDS-TRANSMIT-000011 | NA | Trade Partner | Dry Fire - HFF GROUND ZONE 1 & 2 | 1 | 0 | 0 | NA | APPROVED | 2026-02-25 | NA | 327 | 2026-03-10 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-28 | Civilex-TRANSMIT-000022 | NA | Trade Partner | Micro Pile Material Procurement | 0 | 2 | 0 | NA | APPROVED | 2026-01-30 | WF-000127 | NA | 2026-02-03 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-000544 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-25 | JCBa-TRANSMIT-000063 | NA | Consultant | STRUCTURAL SETOUT PLANS GROUND FLOOR: ZONES 1, 3 & 4 | 4 | 0 | 0 | NA | APPROVED | 2026-02-25 | NA | 412 | 2026-02-27 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000772 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-25 | KPTG-TRANSMIT-013500 | NA | Trade Partner | Stage 2 Landscape Design | 6 | 1 | 0 | NA | REJECTED | [5 empty] | 1. Drawings and technical documents in the same transmittals. 2. Document number not as per the project standards inside the drawing and in the document register. |  | 2026-02-25 | KPTG-DA-005114 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | KPTG-TRANSMIT-013531 | NA | Consultant | DC Action New Workflow | 12 | 0 | 0 | NA | APPROVED | 2026-02-25 | WF-004484 | NA | 2026-03-04 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-25 | Tradetec-TRANSMIT-000376 | NA | Trade Partner | Atlan Drawing - 72552.C.00.10.01 | 1 | 0 | 0 | NA | APPROVED | 2026-02-25 | NA | 3863 | 2026-03-06 |  | Terminated as advised by Charlie Johnstone as the drawing is no more required. | 2026-07-20 | 2026-07-20 | Tradetec-TRANSMIT-000376 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | IVS-TRANSMIT-000342 | NA | Consultant | Issued For Construction - Precast Wall, Acoustic Wall, Steel Stairs & Details (Revised as Clouded) | 8 | 0 | 0 | NA | APPROVED | 2026-02-25 | NA | 2251 | 2026-02-27 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014811 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-25 | Tradetec-TRANSMIT-000378 | NA | Trade Partner | Stage 2 - IFA CP11, CP17 | 2 | 0 | 0 | NA | APPROVED | 2026-02-25 | NA | 3868 | 2026-03-06 |  |  | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-014520 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-11-03 | INGEN3D-TRANSMIT-000664 | NA | Consultant | Ground Floor (Zone 8) | 6 | 0 | 0 | NA | APPROVED | 2025-11-03 | WF-003190 | NA | 2025-11-25 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-013509 , KPTG-TRANSMIT-013513 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-05 | HDRAus-TRANSMIT-000331 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 44 | 0 | 0 | NA | APPROVED | 2025-12-08 | NA | 1623 | 2025-12-10 |  |  |  | 2025-12-11 | KPTG-TRANSMIT-010843 | Closed | 36 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-25 | Tradetec-TRANSMIT-000375 | NA | Trade Partner | Shop Drawing - Streelight Footing | 1 | 0 | 0 | NA | APPROVED | 2026-02-25 | WF-004794 | NA | 2026-03-06 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-015601 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | D&E-TRANSMIT-000410 | NA | Trade Partner | Ground & Level 1 - Plinth & Equipment Layout Zones | 11 | 0 | 0 | NA | APPROVED | 2026-02-25 | NA | 2241 | 2026-03-05 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-014698 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | RDSBIM-TRANSMIT-000231 | NA | Trade Partner | LEVEL 1 PARTITION WALL KEYPLAN AND ELEVATION | 3 | 0 | 0 | NA | APPROVED | 2026-02-25 | NA | 2243 | 2026-02-27 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-018319 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-25 | KPTG-IntCorr-009936 | NA | Trade Partner | 3M - Technical Data / Arctic Frost Film - Technical Data / Nano Cloaking - Technical Data | 0 | 3 | 0 | NA | REJECTED | [5 empty] | The document number is missing -B- inside. |  | 2026-02-25 | KPTG-IntCorr-009943 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | SKS Tech-TRANSMIT-000038 | NA | Trade Partner | Lighting Layouts and Small power DRAWING | 6 | 0 | 0 | NA | APPROVED | 2026-02-25 | NA | 2247 | 2026-03-05 |  |  |  | 2026-03-12 | KPTG-IntCorr-010606 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-20 | D&E-TRANSMIT-000403 | NA | Trade Partner | L2 Cx Scripts - Issued for Review | 0 | 1 | 0 | NA | APPROVED | 2026-02-25 | WF-004468 | NA | 2026-03-06 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-014114 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | ADP-TRANSMIT-000254 | NA | Consultant | Re: MEL741 - Stage 4 Services IFC Issue (Electrical drawings) | 3 | 0 | 0 | NA | REJECTED | [5 empty] | We have already taken action on the previous transmittal of these same documents (ADP-TRANSMIT-000250). |  | 2026-02-25 | KPTG-IntCorr-009955 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-07-09 | SMEPS-TRANSMIT-000048 | NA | Trade Partner | Power and Comms Containment Layout - Inground - Zone C2 | 1 | 0 | 0 | NA | APPROVED | 2025-10-30 | NA | 1457 | 2026-02-25 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-013522 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | ADP-TRANSMIT-000255 | NA | Consultant | Stage 4 Services IFC Issue (Electrical drawings) | 9 | 0 | 0 | NA | REJECTED | [5 empty] | already taken action on the previous transmittal of these same documents (ADP-TRANSMIT-000251) |  | 2026-02-25 | KPTG-IntCorr-009956 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | ADP-TRANSMIT-000256 | NA | Consultant | Stage 4 Services IFC Issue (Electrical drawing | 5 | 0 | 0 | NA | REJECTED | [5 empty] | already taken action on the previous transmittal of these same documents (ADP-TRANSMIT-000252) |  | 2026-02-25 | KPTG-IntCorr-009958 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-08 | IVS-TRANSMIT-000291 | NA | Consultant | Stage 4 - Roof Plinths C2 C3,Roof Gantry Switch room Zone C1 Construction Issue | 38 | 0 | 0 | NA | APPROVED |  | NA | 1622 | 2025-12-10 |  |  |  | 2025-12-10 | KPTG-TRANSMIT-010797 | Closed | 19 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | Tradetec-TRANSMIT-000377 | NA | Trade Partner | Stage 4 - IFA - CP20, CP37, LVP39 | 3 | 0 | 0 | NA | REJECTED | [5 empty] | The document number mentioned inside the drawing differs from the document number in the register |  | 2026-02-25 | KPTG-TRANSMIT-013520 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | ADP-TRANSMIT-000257 | NA | Consultant | Stage 4 Services IFC Issue (Electrical drawings) | 8 | 0 | 0 | NA | REJECTED | [5 empty] | already taken action on the previous transmittal of these same documents (ADP-TRANSMIT-000253) |  | 2026-02-25 | KPTG-IntCorr-009959 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-25 | ZIA-TRANSMIT-000061 | NA | Trade Partner | L3 and Cx Plan Submission | 0 | 38 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-02-25 | KPTG-TRANSMIT-013518 | Closed | 38 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-25 | KPTG-IntCorr-009944 | NA | Trade Partner | 3M - Technical Data / Arctic Frost Film - Technical Data / Nano Cloaking - Technical Data | 0 | 3 | 0 | NA | APPROVED | 2026-02-25 | WF-004474 | NA | 2026-03-12 |  | 1 Revise and Resubmit 3/27/2026 KPTG-TRANSMIT-015068 | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015068 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-10-30 | SMEPS-TRANSMIT-000101 | NA | Trade Partner | STAGE 4 - POWER & COMMS CONTAINMENT LAYOUT - INGROUND - ZONE C3 (C05) | 1 | 0 | 0 | NA | APPROVED | 2025-10-30 | NA | 1458 | 2026-02-25 |  |  |  | 2026-02-25 | KPTG-TRANSMIT-013519 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | D&E-TRANSMIT-000414 | NA | Trade Partner | MCC Schedules - Initial Issue Rev[C] | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-02-25 | KPTG-TRANSMIT-013516 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | KPTG-TRANSMIT-013530 | NA | Consultant | Admin East & West Canopy Framing - Shop Drawings - Issued for Approval | 19 | 0 | 0 | KPTG-TRANSMIT-013536 | APPROVED |  | NA | NA |  |  | ATTACHED DOCUMENTS THIS TRANSMIT ARE ALREADY UNDER REVIEW LOCK ADVISE SEEKED FOR FURTHER ACTION |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | D&E-TRANSMIT-000413 | NA | Trade Partner | NXM3S4 - Ground - Builders Works Layout ZONES - Issued For Construction | 4 | 0 | 0 | NA | APPROVED | 2026-02-25 | NA | 2248 | 2026-03-05 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-015431 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-25 | D&E-TRANSMIT-000415 | NA | Trade Partner | Fire Matrix - Fire integration | 0 | 1 | 0 | NA | REJECTED | [5 empty] | IFC-3 revision has already finished its review.. |  | 2026-02-25 | KPTG-DA-005116 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-25 | EFP-TRANSMIT-000008 | NA | Trade Partner | FIRE DRY SHOP DRAWINGS IFA | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Title of drawings has not fully mentioned in the TRANSMIT, Requested them retransmit-KPTG-IntCorr-000057 |  | 2026-02-25 | KPTG-IntCorr-000057 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-08 | SMEPS-TRANSMIT-000119 | NA | Trade Partner | 22KV - Sample register and submittals | 6 | 0 | 0 | NA | APPROVED | 2025-12-10 | WF-003552 |  | 2025-12-26 |  | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-25 | Appselec-TRANSMIT-000015 | NA | Trade Partner | Communications Trunking Technical Data Substitution Request | 0 | 1 | 0 | NA | APPROVED | 2026-02-25 | WF-000026 | NA | 2026-03-04 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-000118 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-25 | SIL-TRANSMIT-000007 | NA | Trade Partner | Re-transmitting with FOR CONSTRUCTION Stamp | 0 | 13 | 0 | NA | REJECTED | [7 empty] | 2026-02-25 | KPTG-IntCorr-000056 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-24 | SIL-TRANSMIT-000005 | NA | Trade Partner | Re-Transmitting L1 and L2 Scripts | 0 | 10 | 0 | NA | APPROVED | 2026-02-25 | WF-000027 | NA | 2026-03-03 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-000132 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-25 | KPTG-IntCorr-000052 | NA | Client | Transmittal letter: #1 - Technical Memo: TM-04-E UPM Connection Sequence Update | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per the Direction from Mr.Will , i have supersede the drawings and transmitted to clients and trade partners |  | 2026-02-25 | KPTG-TRANSMIT-000048,KPTG-TRANSMIT-000049 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-25 | D&E-TRANSMIT-000345 | NA | Trade Partner | CHILLED WATER SCHEMATIC PART 1 - Issued For Construction | 1 | 0 | 0 | KPTG-IntCorr-003005 | APPROVED | 2026-03-03 | NA | 1405 | 2026-03-06 |  |  | 2020-03-04 | 2026-03-05 | KPTG-TRANSMIT-002706 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-25 | NXT-TRANSMIT-000367 | NA | Client | M3 - PPR Annexure L - Reg 233 | 0 | 1 | 0 | KPTG-IntCorr-003011 | APPROVED |  | NA | NA |  |  | Distribution only |  | 2026-02-26 | KPTG-TRANSMIT-002673 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-24 | RDSBIM-TRANSMIT-000113 | NA | Trade Partner | MLCSPR ¦ AQUATIC CENTER LEVEL 01 HOB LAYOUT PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-02-25 | NA | 450 | 2026-03-04 |  |  | 2026-03-13 | 2026-03-13 | KPTG-SADV-003868 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-25 | KPTG-IntCorr-005414 | NA | Trade Partner | Pv03 Junior school Courts | 0 | 2 | 0 | NA | APPROVED | 2026-02-25 | WF-000847 | NA | 2026-02-27 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-003017 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-08 | HDRAus-TRANSMIT-000332 | NA | Consultant | M3 Stage 4 - Updated Concrete profile drawings - C1 - Ground and level 01 | 2 | 0 | 0 | NA | APPROVED | 2025-12-08 | NA | 1625 | 2025-12-10 |  | The workflow has been terminated - Latest revision received |  |  |  | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-25 | KPTG-IntCorr-005419 | NA | Trade Partner | Final (WF-000800) CAP6-TRANSMIT-000005- Classic Architectural Onboarding ¦ MLCSPR | 0 | 1 | 0 | NA | APPROVED | 2026-02-25 | WF-000848 | NA | 2026-02-27 |  | CLA-ARCH-TEC-003 IS RESUBMITTED FOR CONSULTANT REVIEW | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-002721 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-25 | MCGC-TRANSMIT-000007 | NA | Consultant | IFC - Landscape Drawings | 57 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 454 | 2026-03-09 |  | Revision & Revision History of current drawings are not match with Revision of previous Drawings: As per the latest communication with Mr. Tim Shallue, (It is okay to process):KPTG-IntCorr-005543 | 2026-05-14 | 2026-05-14 | KPTG-SADV-004331 | Closed | 57 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-24 | Auspan-TRANSMIT-000055 | NA | Trade Partner | Revised GC07 issued for approval | 1 | 0 | 0 | NA | APPROVED | 2026-02-25 | NA | 579 | 2026-03-04 |  |  | 2026-02-27 | 2026-02-27 | KPTG-SADV-003241 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-25 | WGAVIC-TRANSMIT-000073 | NA | Consultant | M2 Stages 10 and 11 - Ground Floor Shear Stud Update - Certification Issue | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Issued for Information only, Updated register and ACC |  | 2026-02-25 | KPTG-TRANSMIT-001007 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | KPTG-WTRAN-008144 | NA | Consultant | TECH DATA - CONSULTANT REVIEW -FIT-OUT & WATERPROOFING - | 0 | 6 | 0 | NA | APPROVED | 2026-02-25 | WF-004485 | NA | 2026-03-13 |  | THE DOCUMENTS REOPEN THE REVIEW AS PER REQUEST BY LOLA WF-004482 - KPTG-WTRAN-008153 -------- Terminated as requested by Lola - No TRN available |  | 2026-02-26 | NA | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-25 | Tradetec-TRANSMIT-000047 | NA | Trade Partner | 3rd Batch of Shop Drawings | 20 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-SADV-001395 |  | 2026-02-25 | KPTG-SADV-001395 | Closed | 20 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-25 | SMEPS-TRANSMIT-000117 | SPARK-CRFI-KPG-000388 | Trade Partner | IFA - Electrical L01 Penetration Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 182 |  |  |  |  | 2026-03-23 | KPTG-TRANSMIT-000566 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-26 | Nilsen3-TRANSMIT-000042 | NA | Trade Partner | M3-HV-NIL-SA-S-0301-0020 - Rev 2 SUPA 80 Frame | 0 | 1 | 0 | NA | APPROVED | 2026-02-26 | WF-004486 | NA | 2026-03-03 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-013957 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-26 | Nilsen3-TRANSMIT-000041 | NA | Trade Partner | Sample submissions | 0 | 1 | 0 | NA | APPROVED | 2026-02-26 | WF-004487 | NA | 2026-03-16 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-014616 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-08 | IVS-TRANSMIT-000295 | NA | Consultant | Stage 4 - Office Precast Construction Issue (Revised as clouded) | 2 | 0 | 0 | NA | APPROVED | 2025-12-08 | NA | 1627 | 2025-12-10 |  |  |  | 2025-12-09 | KPTG-TRANSMIT-010754 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-26 | Altaire-TRANSMIT-000089 | NA | Trade Partner | NEXTDC M3S3 22KV - Combined Fire Matrix (For Approval) (1) | 0 | 1 | 0 | NA | APPROVED | 2026-02-26 | WF-004488 | NA | 2026-03-11 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-014570 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-26 | KPTG-WTRAN-008160 | NA | Trade Partner | Stage 4 - C2 Gantry Roof`& Secondary Steel | 2 | 0 | 0 | NA | APPROVED | 2026-02-26 | WF-004490 | NA | 2026-03-04 |  | The workflow has been generated as requested by Lola. |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-20 | SKS Tech-TRANSMIT-000033 | NA | Trade Partner | Zone C2 and C3 Comms and Power Containment for approval | 2 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 2189 | 2026-03-02 |  | THIS TRANSMITTAL HAVE 2 DIFFERENT TYPE DISCIPLINE DOCUMENTS ITS NEED TO GO ON DIFFERENT WORKFLOWS - As requested by Peter Z - VOID |  |  | NA | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-26 | KPTG-INTCOM-000205 | NA | Trade Partner | Documents to upload for review | 0 | 3 | 0 | NA | APPROVED | 2026-02-26 | WF-000637 | NA | 2026-03-09 |  |  | 2026-04-14 | 2026-04-14 | KPTG-TRANSMIT-002210 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-26 | RDSBIM-TRANSMIT-000159 | NA | Trade Partner | LINDRUM ¦ LEVEL 02 TO LEVEL 05 COREWALL CONCRETE PROFILE PLAN ELEVATIONS | 2 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 580 | 2026-03-05 |  |  | 2026-03-16 | 2026-03-17 | KPTG-SADV-003446 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-26 | RDSBIM-TRANSMIT-000160 | NA | Trade Partner | LINDRUM ¦ LEVEL 06 TO LEVEL 10 COREWALL CONCRETE PROFILE PLAN ELEVATION | 2 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 581 | 2026-03-05 |  |  | 2026-03-24 | 2026-03-24 | KPTG-SADV-003538 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-26 | Nilsen3-TRANSMIT-000044 | NA | Trade Partner | SCADA Remote operating panel - ABB - Stage 4 - SAMPLE | 1 | 0 | 0 | NA | APPROVED | 2026-02-26 | WF-004492 | NA | 2026-03-03 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-014077 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-26 | Auscool-TRANSMIT-000084 | NA | Trade Partner | LEVEL 5 LOUVRE PENETRATION UPDATED | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per the direction from the Mr. Mark, These IFC Drawings are transmitted to all parties |  | 2026-02-26 | KPTG-TRANSMIT-001897 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-24 | Auscool-TRANSMIT-000083 | NA | Trade Partner | Level 1 - 8 IFC | 8 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per the direction from the Mr. Mark, These IFC Drawings are transmitted to all parties |  | 2026-02-26 | KPTG-TRANSMIT-001900 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-08 | RDSBIM-TRANSMIT-000012 | NA | Trade Partner | 671CHP ¦ BASEMENT 4 CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | KPTG-IntCorr-000248 | APPROVED | 2025-12-17 | WF-000078 | 185 | 2025-12-19 |  | Waiting for TN direction from Kapitol, Internal memo ref. KPTG-IntCorr-000248. done, WF initiated. Review void as advised during a meeting with Kapitol DM & PCs |  | 2026-01-21 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-26 | KPTG-WTRAN-008164 | NA | Trade Partner | HYCHEM SUPAFLOOR | 0 | 3 | 0 | NA | APPROVED | 2026-02-26 | WF-004493 | NA | 2026-03-18 |  | The WF has been generated as requested by Sam S |  |  | KPTG-TRANSMIT-014185 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-26 | IDS-TRANSMIT-000012 | NA | Trade Partner | Wet Fire - HFF - GROUND LEVEL ZONE 1 & 2 | 1 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 320 | 2026-03-11 |  |  | 2026-03-03 | 2026-03-03 | DRAFT-009104 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-26 | KPTG-TRANSMIT-013544 | NA | Trade Partner | Fwd: F3P1 Performance Based Design Brief | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-02-26 | KPTG-TRANSMIT-013552 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-26 | D&E-TRANSMIT-000417 | NA | Trade Partner | Re: Fan static calculations | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-02-26 | KPTG-TRANSMIT-013553 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-26 | SKS Tech-TRANSMIT-000040 | NA | Trade Partner | Re: Updated Roof Containment C1, C2 and C3 | 5 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-02-26 | KPTG-TRANSMIT-013554 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-25 | PCForm-TRANSMIT-000081 | NA | Trade Partner | Precast caulking sample submission - Pascoe FireJoint PU | 0 | 1 | 0 | KPTG-IntCorr-000398 | APPROVED | 2026-02-27 | WF-000190 | NA | 2026-03-02 |  | Send for Red fire and WAM Review - WF-000202 | 2026-03-03 | 2026-03-03 | WF-000202 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-25 | WAM-TRANSMIT-000718 | NA | Consultant | WAM ARCH - 80% DD - Metalwork | 7 | 0 | 0 | NA | APPROVED | 2026-02-25 | NA | 278 | 2026-02-27 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-000662 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-25 | KPTG-IntCorr-000389 | NA | Trade Partner | RAFT 1,2,3 WALL ELEVATIONS | 14 | 0 | 0 | NA | APPROVED | 2026-02-25 | NA | 280 | 2026-02-27 |  |  | 2026-03-19 | 2026-03-20 | KPTG-TRANSMIT-000852 | Closed | 14 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-25 | SMEPS-TRANSMIT-000108 | NA | Trade Partner | SME Shop Drawing Telecommunications IFA 1 | 10 | 0 | 0 | NA | APPROVED | 2026-02-25 | WF - 000175 | NA | 2026-03-03 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-000375 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-25 | Leemark-TRANSMIT-000007 | SPARK-CRFI-KPG-000317 | Trade Partner | Transmittal of Ground Floor Wet Fire Shop Draiwngs | 3 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 139 |  |  |  | 2026-03-16 | 2026-05-01 | KPTG-TRANSMIT-000777 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-08 | SMEPS-TRANSMIT-000226 | NA | Trade Partner | SME - IFA drawings | 1 | 0 | 0 | NA | APPROVED | 2025-12-08 | NA | 1290 | 2025-12-16 |  |  | 2026-01-20 | 2026-01-20 | KPTG-TRANSMIT-002310 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-25 | SMEPS-TRANSMIT-000109 | NA | Trade Partner | SME Shop Drawing Telecommunications IFA 1 | 6 | 0 | 0 | NA | APPROVED | 2026-02-25 | WF - 000176 | NA | 2026-03-03 |  |  | 2026-03-05 | 2026-03-06 | KPTG-TRANSMIT-000396 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-25 | SMEPS-TRANSMIT-000110 | NA | Trade Partner | SME Shop Drawing Telecommunications IFA 1 | 1 | 0 | 0 | NA | APPROVED | 2026-02-25 | WF - 000177 | NA | 2026-03-03 |  |  | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-000381 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-25 | SMEPS-TRANSMIT-000111 | NA | Trade Partner | SME Shop Drawing Electrical IFA 3 | 4 | 0 | 0 | NA | APPROVED | 2026-02-26 | WF - 000178 | NA | 2026-03-03 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000335 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-26 | KPTG-WTRAN-008165 | NA | Trade Partner | 200mm Half Round Gutter | 0 | 1 | 0 | NA | APPROVED | 2026-02-26 | WF-004494 | NA | 2026-03-16 |  |  | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-013869 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-26 | SMEPS-TRANSMIT-000118 | SPARK-CRFI-KPG-000463 | Trade Partner | Technical Data - PLC - Rev B for approval | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-10 | KPTG-TRANSMIT-000513 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-26 | KPTG-WTRAN-008166 | NA | Trade Partner | M3-HV-NIL-SA-S-0301-0007 ABB SCADA ROP - Sample | 0 | 1 | 0 | NA | APPROVED | 2026-02-26 | WF-004495 | NA | 2026-03-03 |  | The WF has been generated as requested by Sam S - Nilsen3-TRANSMIT-000017 | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-014193 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-01-27 | WAM-TRANSMIT-000080 | N/A | Consultant | Material and Finishes Schedule | 1 | 0 | 0 | NA | APPROVED | 2026-01-27 | WF-000119 | NA | 2026-01-30 |  | TERMINATED - NEW SCHEDULE RCVD VIA WAM-TRANSMIT-000711 | 2026-02-15 | 2026-02-15 | WAM-TRANSMIT-000711 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-26 | SMEPS-TRANSMIT-000119 | NA | Trade Partner | Generator and Tank - Rev B Technical data for approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Drawing title inside the drawing and in Aconex seem different |  | 2026-02-26 | KPTG-TRANSMIT-000479 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-25 | Hames-TRANSMIT-000121 | NA | Consultant | Level 4 Architectural IFC drawings and Wall Schedule Sheet 5 | 6 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 1020 | 2026-03-01 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-003017 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-25 | RDSBIM-TRANSMIT-000061 | NA | Trade Partner | ROOF CONCRETE PROFILE PLAN | 2 | 0 | 0 | NA | APPROVED | 2026-02-25 | NA | 1017 | 2026-02-27 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-002996 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-11-29 | RDSBIM-TRANSMIT-000086 | NA | Trade Partner | MLC ¦ AQUATIC CENTER LEVEL 01 INTERNAL SCREED LAYOUT | 3 | 0 | 0 |  | APPROVED | 2025-12-01 |  | 361 | 2025-12-06 | [8 empty] | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-08 | RBG-TRANSMIT-000040 | NA | Consultant | Latest Structural Documentation - Issue for Construction - Column Package | 9 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-000080 | 148 | 2025-12-11 |  | Review Void. updated version issued by consultant. |  | 2025-12-09 |  | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-25 | SKS Tech-TRANSMIT-000159 | NA | Trade Partner | LEVEL 04 SEISMIC IFC | 1 | 0 | 0 | QA Error Rejected - KPTG-IntCorr-001031 | REJECTED | [5 empty] | QA Error Rejected |  | 2026-02-25 | KPTG-IntCorr-001031 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-26 | Nilsen3-TRANSMIT-000046 | NA | Trade Partner | Earth Cable 240mm2 (SAMPLE) | 0 | 1 | 0 | NA | APPROVED | 2026-02-26 | WF-004497 | NA | 2026-03-03 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-015662 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-26 | Nilsen3-TRANSMIT-000045 | NA | Trade Partner | Fire Rated Tray REV1 (SAMPLE) | 0 | 1 | 0 | NA | APPROVED | 2026-02-26 | WF-004498 | NA | 2026-03-03 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-013961 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-26 | ACG-TRANSMIT-000055 | NA | Trade Partner | M3 - Stage 3 Samples IFC | 0 | 16 | 0 | NA | REJECTED | [6 empty] | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-013560 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-26 | ACG-TRANSMIT-000056 | NA | Trade Partner | Re: M3 - Stage 3 Samples IFA | 0 | 1 | 0 | NA | REJECTED | [6 empty] | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-013561 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-02-26 | GEMBA-D-TRANSMIT-000008 | NA | Consultant | NEXTDC GE1 ¦ Precast - For Construction | 16 | 0 | 0 | NA | APPROVED | 2026-02-24 | NA | 24 | 2026-03-03 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000051 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-26 | AXIS-NSW-TRANSMIT-000006 | NA | Trade Partner | Samples for Review | 0 | 3 | 0 | NA | APPROVED | 2026-02-26 | WF-000279 | NA | 2026-03-10 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-001707 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-26 | HIP-TRANSMIT-000005 | NA | Trade Partner | Building - 08 - Additional Steel for Powerpack - Issued for Approval | 11 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 321 | 2026-03-11 |  | As requested by Isaiah the WF has been processed- KAPITOL-INTCOR-001093 |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-26 | ASV-TRANSMIT-000018 | NA | Trade Partner | PE to Steel Roll Groove Adaptor | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Need to update the document, KPTG-SADV-001401 |  | 2026-02-26 | KPTG-SADV-001401 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-26 | ASV-TRANSMIT-000019 | NA | Trade Partner | PE to Steel Roll Groove Adaptor | 0 | 1 | 0 | NA | APPROVED | 2026-02-26 | WF-000280 | NA | 2026-03-06 |  |  | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-001175 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-08 | B Smart-TRANSMIT-000032 | NA | Consultant | Tower Apartment Levels: IFC Draft Revision – A13s Update | 42 | 0 | 0 | KPTG-IntCorr-000250 | APPROVED |  | NA | NA |  |  | Updated drawings received; waiting for advise Internal correspondence ref. KPTG-IntCorr-000250. As advised by DM, for information, no review required. Register update only. |  | 2025-12-09 |  | Closed | 42 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-26 | SMEPS-TRANSMIT-000120 | SPARK-CRFI-KPG-000330 | Trade Partner | NEL-CNT-SME-2990-ELC-SAM-0017B - Diesel Generator + Control Panel | 0 | 1 | 0 | NA | APPROVED | 2026-02-26 | WF-000236 | NA | 2026-03-02 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-000562 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-26 | Highbu-TRANSMIT-000042 | NA | Trade Partner | Drainage Drawings for Approval | 5 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 582 | 2026-03-05 |  | close out pending-KPTG-IntCorr-000807 | 2026-03-19 | 2026-03-20 | KPTG-SADV-003518 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-26 | KPTG-WTRAN-008181 | NA | Trade Partner | SAMPLE AND TECH DATA - CONSULTANT REVIEW -KAP-HDR-ARUP-HAMES-NDC | 0 | 7 | 0 | NA | APPROVED | 2026-02-26 | NA | NA | 2026-03-09 |  | The Wf has been generated as requested Lola |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-26 | ACG-TRANSMIT-000058 | NA | Trade Partner | M3 - Stage 3 Samples IFA | 0 | 1 | 0 | NA | APPROVED | 2026-02-26 | WF-004507 | NA | 2026-03-16 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-014073 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-26 | ACG-TRANSMIT-000059 | NA | Trade Partner | M3 - Stage 3 Samples IFC | 0 | 16 | 0 | NA | APPROVED | 2026-02-26 | WF-004508 | NA | 2026-03-16 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-014074 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-26 | D&E-TRANSMIT-000130 | SPARK-CRFI-KPG-000315 | Trade Partner | MWYCCB - LEVEL 1 PENETRATION LAYOUT ZONE 6 & ZONE 7 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 140 | 2026-03-05 |  |  | 2026-03-16 | 2026-04-24 | KPTG-TRANSMIT-000714 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-26 | Leemark-TRANSMIT-000008 | SPARK-CRFI-KPG-000530 | Trade Partner | NEL-CNT-LFP-2801-MFS-DST-0045 - 100mm DUAL HEAD BOOSTER | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-02 | KPTG-TRANSMIT-000611 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-26 | PARR-TRANSMIT-000127 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - bulk fuel system reticulation drawings | 27 | 0 | 0 | NA | REJECTED | [5 empty] | Document attached drawings M3-FUL-PAR-SDRG-C-0401-3151 is showing M3-FUL-PAR-SDRG-C-0401-6151 in Aconex. |  | 2026-02-26 | KPTG-DA-005155 | Closed | 27 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-26 | Auscool-TRANSMIT-000009 | NA | Trade Partner | Ground to Level 8 Auscool Design Drawings for review | 45 | 0 | 0 | NA | APPROVED | 2026-02-26 | WF-000237 | NA | 2026-03-04 |  |  |  | 2026-03-16 | KPTG-TRANSMIT-000933 | Closed | 44 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-26 | Auspan-TRANSMIT-000099 | NA | Trade Partner | Precast Column Details | 24 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update Register and distribute. |  | 2026-02-26 | KPTG-TRANSMIT-000754 | Closed | 24 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-08 | RBG-TRANSMIT-000041 | NA | Consultant | Latest Structural Documentation Issued for Construction - Basement Precast IFC | 7 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-000081 | 150 | 2025-12-11 |  | Review terminated due to updated drawings received. |  | 2026-01-15 | NA | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-26 | Leemark-TRANSMIT-000009 | NA | Trade Partner | Transmittal of Ground Floor Wet Fire Shop Draiwngs | 10 | 0 | 0 | NA | REJECTED | [5 empty] | Documents with Different Statuses in a Single Transmittal Revision History Not Updated |  | 2026-02-26 | KPTG-TRANSMIT-000481 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-26 | RDSBIM-TRANSMIT-000034 | NA | Trade Partner | 671CHP RAMP CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | 542 | 2026-06-12 |  | Review 301 Void; and ACC#542 created on 5/06/2026 | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-001656 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-26 | SKS Tech-TRANSMIT-000042 | NA | Trade Partner | C1, C2 and C3 Roof Containment | 3 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 2295 | 2026-04-10 |  | There are 6 drawings in this transmittal, out of which 3 electrical drawings are included in this workflow. |  | 2026-03-20 | KPTG-TRANSMIT-014765 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-26 | RDSBIM-TRANSMIT-000232 | NA | Trade Partner | RCP ROOF KEYPLAN AND LAYOUT | 4 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 2268 | 2026-03-02 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-014163 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-26 | HDRAus-TRANSMIT-000409 | NA | Consultant | Architectural FC Issue | 5 | 0 | 0 | NA | REJECTED | [5 empty] | The status inside the drawing is differ from the document register |  | 2026-02-26 | KPTG-TRANSMIT-013603 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-26 | SMEPS-TRANSMIT-000190 | NA | Trade Partner | SME - External Structure IFA | 11 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 2264 | 2026-03-06 |  |  | 2026-03-02 | 2026-03-02 | KPTG-IntCorr-010151 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-26 | PARR-TRANSMIT-000121 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - TECH DATA | 0 | 2 | 0 | NA | APPROVED | 2026-02-26 | WF-004505 | NA | 2026-03-03 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-014103 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-26 | SKS Tech-TRANSMIT-000041 | NA | Trade Partner | Containment Roof Zone C1, C2 and C3 -ELC | 3 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 2256 | 2026-03-06 |  | As requested by Oliver S- VOID - KPTG-IntCorr-010109 Latest SKS Tech-TRANSMIT-000042 received | 2026-03-02 | 2026-03-02 | KPTG-IntCorr-010109 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-25 | HDRAus-TRANSMIT-000408 | NA | Consultant | SW drawing issued following unlocked | 5 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 3870 | 2026-03-02 |  |  | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-014142 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-26 | SKS Tech-TRANSMIT-000041 | NA | Trade Partner | Containment Roof Zone C1, C2 and C3 - TEL | 2 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 2258 | 2026-03-06 |  | As requested by Oliver S- VOID - KPTG-IntCorr-010109 Latest SKS Tech-TRANSMIT-000042 received | 2026-03-02 | 2026-03-02 | KPTG-IntCorr-010109 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-08 | B Smart-TRANSMIT-000034 | NA | Consultant | Core IFC | 13 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-000082 | 152 | 2025-12-11 |  | Review void as updated drawing received. |  | 2026-01-16 | NA | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-26 | D&E-TRANSMIT-000418 | NA | Trade Partner | NXM3S4 - Level 1 - Builders Works Layout ZONES - Issued For Approval | 7 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 2254 | 2026-03-06 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-014691 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-16 | PARR-TRANSMIT-000119 | NA | Trade Partner | P2649 - KPG NDC M3 - Stage 2 - Fuel - CX L2, L3, L4 - IFC | 0 | 14 | 0 | NA | APPROVED | 2026-02-18 | WF-004333 | NA | 2026-02-26 |  |  | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-013584 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-26 | ASV-TRANSMIT-000150 | NA | Trade Partner | Hydraulic Samples - Fire Wrap & Chiller Module FW Grate | 0 | 2 | 0 | NA | APPROVED | 2026-02-26 | WF-004501 | NA | 2026-03-13 |  |  | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-015410 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-26 | NXT-TRANSMIT-001334 | NA | Client | 110693-000229 Inspection & test plans | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | As Built |  | 2026-02-26 | KPTG-TRANSMIT-013583 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-26 | NXT-TRANSMIT-001335 | NA | Client | 100222 - M3 DATA CENTER STAGE 2 - FIRE SYSTEM VISUAL ALARM DEVICE (VAD) - SAMPLE | 0 | 1 | 0 | NA | APPROVED | 2026-02-26 | WF-004511 | NA | 2026-03-13 |  |  | 2026-03-05 | 2026-03-05 | KPTG-TRANSMIT-013909 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-26 | ZIA-TRANSMIT-000063 | NA | Trade Partner | L3 and Cx Plan Submission | 0 | 12 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-02-26 | KPTG-TRANSMIT-013604 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-26 | PARR-TRANSMIT-000125 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - PUMP ROOM, CONTROL SYSTEM DRAWINGS-FUEL | 9 | 0 | 0 | NA | APPROVED | 2026-02-26 | WF-004936 | NA | 2026-03-04 |  | ACC WORKFLOWS ARE TERMINATED AND PLACED WORKFLOW IN ACONEX - Aconex WF has been terminated as requested by Oliver-Peter-Jay J - And reinitiated via ACC |  | 2026-03-23 | NA | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-26 | SC-TRANSMIT-000045 | NA | Trade Partner | IFC Drawings | 47 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC DRAWINGS , TRANSMITTED TO TRADE & CONSULTANTS |  | 2026-02-26 | KPTG-TRANSMIT-002472 | Closed | 47 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-26 | NXT-TRANSMIT-000370 | NA | Client | M3 Stage 1 Arc Fault Study | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | NXT-TRANSMIT-000370 & 371 are same documents -Distribution Only |  | 2026-02-26 | KPTG-TRANSMIT-002672 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-08 | SMEPS-TRANSMIT-000091 | SPARK-CRFI-KPG-000437 | Trade Partner | SME-MCC-Custom Luminaires | 0 | 7 | 0 | KPTG-IntCorr-001086 | APPROVED | [7 empty] | 2026-01-21 | KPTG-TRANSMIT-000350 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-26 | NXT-TRANSMIT-000372 | NA | Client | M3 Stage 1 A7A8) Protection Study LV SCCS Report IFCN-8 | 0 | 1 | 0 | KPTG-IntCorr-003038 | APPROVED |  | NA | NA |  |  | Distribution |  | 2026-02-27 | KPTG-TRANSMIT-002676 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-26 | BTWA-TRANSMIT-000072 | NA | Trade Partner | BT-ARCH-SMP-016 | 0 | 1 | 0 | NA | APPROVED | 2026-02-26 | WF-000849 | NA | 2026-03-04 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-002633 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-26 | 4DW-TRANSMIT-000092 | NA | Consultant | Level 06 Steel Updates | 4 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 583 | 2026-03-05 |  | Same revision is submitted & dwfx file of one of the document is found missing, requested them to retransmit. | 2026-02-27 | 2026-02-27 | KPTG-SADV-003235, KPTG-SADV-003249 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-26 | KPTG-IntCorr-000063 | NA | Client | Transmittal letter: #2 - Telecom WESCO PML Update (R04) | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | DOCUMENTS ARE UPLOADED INTO DOCUMENT REGISTER, AND TRANSMITTED TO TRADE & CLIENT |  | 2026-02-26 | KPTG-TRANSMIT-000050 &KPTG-TRANSMIT-000051 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-26 | Tradetec-TRANSMIT-000048 | NA | Trade Partner | 3rd Batch of Shop Drawings (Priority 1 pits) - ELC | 2 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 364 | 2026-03-06 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-001235 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-26 | Tradetec-TRANSMIT-000048 | NA | Trade Partner | 3rd Batch of Shop Drawings (Priority 1 pits) - Telecom | 3 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 365 | 2026-03-06 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-001235 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-26 | Tradetec-TRANSMIT-000048 | NA | Trade Partner | 3rd Batch of Shop Drawings - Electrical | 10 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 366 | 2026-03-06 |  |  | 2026-03-05 | 2026-03-05 | KPTG-TRANSMIT-001199 | Closed | 10 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-26 | Tradetec-TRANSMIT-000048 | NA | Trade Partner | 3rd Batch of Shop Drawings - Telecom | 5 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 367 | 2026-03-06 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-001235 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-26 | PCForm-TRANSMIT-000109 | NA | Trade Partner | Cladding Elevations - Stage 9 Stair 1 & Lift, Stair 2, Stair 3, Stair 4, & Stage 10 Stair 5 & Stair 8 | 20 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. |  | 2026-02-26 | KPTG-TRANSMIT-001033 | Closed | 20 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-08 | ADP-TRANSMIT-000143 | NA | Consultant | MEL4780 Site-in-ground update for POE-1 location | 1 | 0 | 0 | NA | APPROVED | 2025-12-08 | NA | 1629 | 2025-12-10 |  |  |  | 2025-12-18 | DRAFT-037851 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-26 | Tradetec-TRANSMIT-000050 | NA | Trade Partner | Transmittal of LVP21 and TELP9 Shop Drawings ELC (Priority pits) | 1 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 371 | 2026-03-06 |  |  | 2026-03-05 | 2026-03-05 | KPTG-TRANSMIT-001203 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-26 | Tradetec-TRANSMIT-000050 | NA | Trade Partner | Transmittal of LVP21 and TELP9 Shop Drawings - Telecom (Priority pits) | 1 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 372 | 2026-03-06 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-001239 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-26 | D&E-TRANSMIT-000416 | NA | Trade Partner | DX & VRF Air Conditioning | 0 | 2 | 0 | NA | APPROVED | 2026-02-26 | WF-004496 | NA | 2026-03-19 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014876 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-26 | SMEPS-TRANSMIT-000188 | NA | Trade Partner | SME - IFA SAMPLE RE-SUBMISSION | 0 | 10 | 0 | NA | APPROVED | 2026-02-26 | WF-004499 | NA | 2026-03-19 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-26 | ADP-TRANSMIT-000259 | NA | Consultant | MEL741 - S4 - Updated names on Register (Electrical) | 30 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due to incorrect revision number |  | 2026-02-26 | KPTG-TRANSMIT-013564 | Closed | 30 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-26 | SMEPS-TRANSMIT-000189 | NA | Trade Partner | SME - DRAWINGS IFA PART SUBMISSIONS-ELC | 2 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 2260 | 2026-03-06 |  | TOTAL 4 DOC IN THIS TRANSMIT 2 FROM -ELC & 2 FROM TEL |  | 2026-03-16 | KPTG-RFI-006721 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-26 | SMEPS-TRANSMIT-000189 | NA | Trade Partner | SME - DRAWINGS IFA PART SUBMISSIONS | 2 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 2263 | 2026-03-06 |  | TOTAL 4DOC IN THIS TRANSMIT 2 FROM -ELC & 2 FROM TEL | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-015334 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-26 | Bianco-TRANSMIT-000048 | NA | Trade Partner | L1 -IFA Drawings | 27 | 0 | 0 | NA | APPROVED | 2026-02-26 | WF-004512 | NA | 2026-03-23 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-015319 | Closed | 27 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-31 | PFP PL-TRANSMIT-000081 | NA | Trade Partner | Ground Floor Zone C3 IFA | 1 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 2692 | 2026-04-08 |  | REJECTED DUE TO INVALID DOCUMENT NAMING |  | 2026-02-26 | KPTG-TRANSMIT-01360 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-26 | ASV-TRANSMIT-000150 | NA | Trade Partner | Hydraulic Samples - Fire Wrap & Chiller Module FW Grate | 0 | 2 | 0 | NA | APPROVED | 2026-02-26 | WF-004501 | NA | 2026-03-13 |  |  | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-015410 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-08 | Auscool-TRANSMIT-000055 | NA | Trade Partner | Level 9 - 27 Builders works updated | 19 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | All are drawings for construction, Transmitted to all parties. |  | 2025-12-08 |  | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-27 | KPTG-WTRAN-008205 | NA | Trade Partner | 9mm Fibre Cement Sheet | 0 | 1 | 0 | NA | APPROVED | 2026-02-27 | WF-004517 | NA | 2026-03-20 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-014005 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-27 | Nilsen3-TRANSMIT-000048 | NA | Trade Partner | Sample submission | 0 | 1 | 0 | NA | APPROVED | 2026-02-27 | WF-004518 | NA | 2026-03-04 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-013963 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-27 | SMEPS-TRANSMIT-000191 | NA | Trade Partner | SME - DRAWINGS IFA PART SUBMISSIONS | 0 | 1 | 0 | NA | APPROVED | 2026-02-27 | NA | 2274 | 2026-03-09 |  |  |  | 2026-03-16 | RDSBIM-TRANSMIT-000242 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-27 | PCForm-TRANSMIT-000067 | NA | Trade Partner | Fwd: Updated Drawings - Level 2 to 10 | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-SADV-003243 - As per the instruction from Ashlin, we have updated the register. |  | 2026-02-27 | KPTG-SADV-003243 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-27 | Leemark-TRANSMIT-000010 | SPARK-CRFI-KPG-000317 | Trade Partner | Transmittal of Ground Floor Wet Fire Shop Draiwngs - For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 141 | 2026-03-06 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-000532 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-26 | Hames-TRANSMIT-000122 | NA | Consultant | Door Hardware Schedule | 0 | 1 | 0 | QA ERROR - REJECTED - KPTG-TRANSMIT-002970 | REJECTED | [7 empty] | 2026-02-26 | KPTG-TRANSMIT-002970 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-26 | PARR-TRANSMIT-000041 | NA | Trade Partner | Fuel Services - LG SECTIONS - IFC | 1 | 0 | 0 | QA ERROR - REJECTED - KPTG-IntCorr-001038 | REJECTED | [7 empty] | 2026-02-26 | KPTG-IntCorr-001038 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-26 | ACG-TRANSMIT-000017 | NA | Trade Partner | Camera Field of View Register | 0 | 1 | 0 | NA | REJECTED | [5 empty] | QA ERROR - REJECTED KPTG-IntCorr-001040 |  | 2026-02-26 | KPTG-IntCorr-001040 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-27 | Leemark-TRANSMIT-000011 | SPARK-CRFI-KPG-000317 | Trade Partner | Transmittal of Ground Floor Wet Fire Shop Draiwngs - For Approval | 3 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 142 | 2026-03-06 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-000533 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-26 | Civilex-TRANSMIT-000033 | NA | Trade Partner | UPT Shop Drawing Approval | 0 | 1 | 0 | NA | APPROVED | 2026-02-26 | WF-000185 | NA | 2026-03-02 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000589 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-08 | Metzone-TRANSMIT-000003 | NA | Trade Partner | Re: Catch-Deck & Catch-Fan - Marking Plans IFA | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per direction from Ms. Ashlin no action instructed on this drawing. |  | 2025-12-08 | KPTG-SADV-002398 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-26 | RDSBIM-TRANSMIT-000019 | NA | Trade Partner | LEVEL 01 CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 281 | 2026-03-03 |  |  | 2026-03-04 | 2026-03-05 | KPTG-TRANSMIT-000642 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-26 | RDSBIM-TRANSMIT-000020 | NA | Trade Partner | LEVEL 05 CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 283 | 2026-03-03 |  |  | 2026-03-04 | 2026-03-05 | KPTG-TRANSMIT-000643 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-27 | Syfon1-TRANSMIT-000008 | NA | Trade Partner | Syfon Roof plans and elevations | 5 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 2277 | 2026-03-05 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-014089 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-27 | Leemark-TRANSMIT-000012 | SPARK-CRFI-KPG-000317 | Trade Partner | Transmittal of Ground Floor Wet Fire Shop Draiwngs - For Construction | 6 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 143 | 2026-03-06 |  |  | 2026-03-16 | 2026-05-01 | KPTG-TRANSMIT-000783 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-27 | ZIA-TRANSMIT-000055 | NA | Trade Partner | Re: Zi-Argus SD & Procurements | 22 | 0 | 0 | NA | APPROVED | 2026-02-27 | WF-004526 | NA | 2026-03-03 |  | As requested by Kian - The WF has been restarted | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-015595 | Closed | 21 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-02-27 | WEBBAUST-TRANSMIT-000067 | NA | Trade Partner | Webb specification Power Pack Test | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The Aconex reference number is not included in the document. (SPC document) |  | 2026-02-27 | DRAFT-009047 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-27 | WilsonPD-TRANSMIT-000162 | NA | Trade Partner | Hydraulic Services - Level 1 - Zone A, B,C & D - Penetration Layouts | 4 | 0 | 0 | KPTG-IntCorr-001900 | APPROVED | [5 empty] | No Action |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-27 | RDSBIM-TRANSMIT-000168 | NA | Trade Partner | LEVEL 05 RCP KEY PLAN & LAYOUT | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-002749 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-26 | KARE-TRANSMIT-000091 | NA | Trade Partner | Revised Solar Tech Data | 0 | 2 | 0 | NA | APPROVED | 2026-02-27 | WF-000953 | NA | 2026-03-05 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-02-27 | Schindle-TRANSMIT-000006 | NA | Trade Partner | Updated Lift Layout & Lift Signalisation Drawings - Lift Services | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Documents with Different Statuses in a Single Transmittal |  | 2026-02-27 | KPTG-TRANSMIT-000483 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-08 | Auspan-TRANSMIT-000022 | NA | Trade Partner | Precast shop drawings for approval. Basement panels in zone 3. | 23 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect drawing numbers. mail ref. KPTG-SADV-000409 |  | 2025-12-08 | KPTG-SADV-000409 | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-26 | crossfir-TRANSMIT-000051 | NA | Trade Partner | Wet Fire - Ground to Level 09, IFC | 20 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. | 2026-02-26 | 2026-02-26 | KPTG-TRANSMIT-002750 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-02-27 | Mirage D-TRANSMIT-000001 | NA | Trade Partner | C.00.24.A - CAR PARK TILT DOOR LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 550 | 2026-03-05 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-27 | KPTG-IntCorr-003006 | NA | Trade Partner | DH7&8 Signage Shop Drawings | 1 | 0 | 0 | KPTG-IntCorr-003012 | APPROVED | 2026-02-27 | NA | 1403 | 2026-03-05 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-20 | SIL-TRANSMIT-000026 | NA | Trade Partner | 32PO-41735-T022 Technical Submittals | 0 | 2 | 0 | NA | APPROVED | 2026-02-23 | WF-000165 | NA | 2026-02-27 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000328 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-27 | RDSBIM-TRANSMIT-000161 | NA | Trade Partner | LINDRUM ¦ GROUND AND MEZZANINE LEVEL CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | NA |  |  | As per the direction from Ashlin, this has to be issued to everyone. |  | 2026-02-27 | KPTG-TRANSMIT-001910 | Closed | 3 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-27 | 4DW-TRANSMIT-000093 | NA | Consultant | Level 06 revision correction | 1 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-SADV-003239-This is pending because we have not yet received the DWFX file. |  | 2026-03-03 | KPTG-SADV-003274 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-27 | Entire M-TRANSMIT-000039 | NA | Trade Partner | Mechanical Shop Drawings | 6 | 0 | 0 | NA | APPROVED | 2026-02-27 | WF-004531 | NA | 2026-03-17 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-015030 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-27 | RDSBIM-TRANSMIT-000114 | NA | Trade Partner | MLCSPR ¦ AQUATIC CENTRE WEST LANDSCAPE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 452 | 2026-03-06 |  | As per the requirement of RDS, we have voided BIM 452# | 2026-03-05 | 2026-03-05 | KPTG-IntCorr-005730 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-27 | Highbu-TRANSMIT-000133 | NA | Trade Partner | HP-PM-SMP-052 - ACO Brickslot grate with Klassik drain channel sample submission | 0 | 1 | 0 | NA | APPROVED | 2026-02-27 | WF-000851 | NA | 2026-03-10 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-002529 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-27 | ECBS-TRANSMIT-000073 | NA | Trade Partner | pool Bulkhead Top Sealant - Tech data for Review | 0 | 1 | 0 | NA | APPROVED | 2026-02-27 | WF-000852 | NA | 2026-03-04 |  |  | 2026-03-05 | 2026-03-05 | KPTG-TRANSMIT-002500 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-08 | Auspan-TRANSMIT-000023 | NA | Trade Partner | Update precast dowel layouts for zone 3, 4 5 | 3 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-000080 | 154 | 2025-12-16 |  |  |  | 2026-01-12 | KPTG-TRANSMIT-000369 | Closed | 3 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-27 | VIA Arch-TRANSMIT-000026 | NA | Trade Partner | 22kV Railing, Concrete Profile Drawing Updates | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Awaiting a response from Sam S. - KPTG-TRANSMIT-013693 response from Sam S - Max is confirming with KC and will let me know |  | 2026-03-04 | KPTG-TRANSMIT-013841 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-27 | INDS-TRANSMIT-000005 | NA | Trade Partner | Ground - Floor Penetration Layout | 5 | 0 | 0 | KPTG-IntCorr-000352 | APPROVED |  | NA | NA |  |  | Waiting for Kapitol Advise - KPTG-IntCorr-000352. 1/3/26 As advised by Kapitol DM, register and forward to RDS. KPTG-TRANSMIT-000782 |  | 2026-03-01 | KPTG-TRANSMIT-000782 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-27 | Rinco-TRANSMIT-000031 | NA | Consultant | Structural drawings Issued for Construction | 33 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 415 | 2026-03-04 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-001005 | Closed | 33 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-02-27 | JCBa-TRANSMIT-000064 | NA | Consultant | IFC - A-3100 – PRECAST ELEVATIONS | 8 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 417 | 2026-03-04 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-000893 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-27 | RDSBIM-TRANSMIT-000035 | NA | Trade Partner | 671CHP BASEMENT 1 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 310 | 2026-03-09 |  | 3/3/26 : Review #303 Void and reinitiated. ACC#310 | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-000627 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-09 | RDSBIM-TRANSMIT-000029 | NA | Trade Partner | 671CHP ¦ BASEMENT 01 BLOCKWORK PLAN AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-02-09 | NA | 258 | 2026-02-17 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000512 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-27 | PCForm-TRANSMIT-000065 | NA | Trade Partner | Level 2 - 10 Interspan IFC Drawings | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per direction from Mr.Ashlin, we do not take any action on these drawing |  | 2026-02-27 | KPTG-IntCorr-000758 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-27 | Auspan-TRANSMIT-000056 | NA | Trade Partner | GC07 shop drawing issued for construction | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC DRAWINGS, UPDATED DOCUMENT REGISTER AND TRANSMITTED TO TRADE & CONSULTANTS AND CLIENT |  | 2026-02-27 | KPTG-TRANSMIT-001923 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-27 | Appselec-TRANSMIT-000016 | NA | Trade Partner | COLO4 and COLO5 - Single Line Diagrams - IFA | 12 | 0 | 0 | KPTG-TRANSMIT-000112 | APPROVED | 2026-02-18 | WF-000071 | NA | 2026-03-24 |  | WF-000028 IS RESUBMITTED AS WD-000071 | 2026-03-24 | 2026-03-20 | KPTG-TRANSMIT-000156 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-02-27 | SIL-TRANSMIT-000008 | NA | Trade Partner | Re-transmitting with FOR CONSTRUCTION Stamp with Revision Change | 0 | 13 | 0 | NA | APPROVED | 2026-02-27 | WF-000029 | NA | 2026-03-04 |  |  | 2026-03-05 | 2026-03-05 | KPTG-TRANSMIT-000075 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-01 | Highbu-TRANSMIT-000100 | NA | Trade Partner | IFC drawings | 8 | 0 | 0 |  | APPROVED |  | 0 | 0 |  |  | IFC Drawings | [6 empty] | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-08 | Auspan-TRANSMIT-000024 | NA | Trade Partner | Update cad files of precast marking elevation zone 4, 5 | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due incorrect drawing transmission. PDF not registered on Aconex. Mail Ref. KPTG-SADV-000407 |  | 2025-12-08 | KPTG-SADV-000407 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-27 | ARCST-TRANSMIT-000235 | NA | Trade Partner | NXM3S4 - LEVEL 01 RCP LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 2287 | 2026-03-03 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-014635 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-27 | HDRAus-TRANSMIT-000412 | NA | Consultant | M3 Stage 4 Updated drawings and Cad - weekly issue | 25 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 2285 | 2026-03-03 |  |  | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-013878 | Closed | 25 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-27 | ZIA-TRANSMIT-000066 | NA | Trade Partner | Re-M3S4 CSMS Roof and Roof Plant SLA Sensor Location (FOA-1) | 3 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 2281 | 2026-03-09 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015133 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-27 | ACG-TRANSMIT-000061 | NA | Trade Partner | M3 - Stage 4 ACG Samples | 0 | 44 | 0 | NA | REJECTED | [5 empty] | Document numbers mentioned inside the sample differ from those in the document register |  | 2026-02-27 | KPTG-TRANSMIT-013662 | Closed | 44 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-27 | IVS-TRANSMIT-000344 |  | Consultant | Updated structural Chemical Store & Fire room | 2 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 2686 | 2026-04-13 |  | The status mentioned inside the drawing differs from the status indicated in the document register. |  | 2026-02-13 | KPTG-TRANSMIT-015824 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-27 | Tradetec-TRANSMIT-000381 | NA | Trade Partner | Stage 4 - IFC - LVP48 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Reason mentioned in the register is different from drawing |  | 2026-02-27 | KPTG-TRANSMIT-013648 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-27 | ZIA-TRANSMIT-000065 | NA | Trade Partner | Re-M3S4 CSMS Roof and Roof Plant SLA Sensor Location (FOA-1) | 5 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 2279 | 2026-03-09 |  | Only two documents are included in this workflow. The remaining three documents have been resubmitted through a different transmittal. | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015132 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-26 | SMEPS-TRANSMIT-000112 | NA | Trade Partner | SME Shop Drawing Electrical IFC A | 4 | 0 | 0 | NA | APPROVED | 2026-02-26 | WF-000179 | NA | 2026-03-04 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-000338 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-27 | KPTG-TRANSMIT-013632 | NA | Trade Partner | S4 - C1 Cooling Tower Roof Framing | 135 | 0 | 0 | NA | APPROVED | 2026-02-27 | WF-004525 | NA | 2026-03-04 |  | The WF has been terminated as requested by Lola. |  | 2026-03-10 | KPTG-IntCorr-010478 | Closed | 135 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-27 | NXT-TRANSMIT-000373 | NA | Client | Potential Incident RFI | 0 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Correspondence only-Action Not required |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-08 | JCBa-TRANSMIT-000040 | NA | Consultant | Capping Beam Elevations - IFC - Hyd and Cvivil updates | 3 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-000081 | 156 | 2025-12-10 |  |  |  | 2025-12-08 | KPTG-TRANSMIT-000286 | Closed | 3 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-27 | NXT-TRANSMIT-000374 | NA | Client | Potential Incident RFI | 0 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Correspondence only-Action not required |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-27 | NXT-TRANSMIT-000375 | NA | Client | Whatsapp clarification - HSE team | 0 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Correspondence only-Action Not required |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-02-27 | ACG-TRANSMIT-000032 | NA | Trade Partner | M3 - DH7/8 O&M Manual Rev1 | 0 | 1 | 0 | KPTG-IntCorr-003044 | APPROVED | 2026-03-03 | WF-000953 | NA | 2026-03-17 |  | Terminated Requested by andrew, will reissue on another template |  | 2026-03-05 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-27 | Tradetec-TRANSMIT-000055 | NA | Trade Partner | Electrical Pit Shop Drawings - ELC | 4 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 379 | 2026-03-06 |  |  | 2026-03-05 | 2026-03-05 | KPTG-TRANSMIT-001207 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-27 | Tradetec-TRANSMIT-000055 | NA | Trade Partner | Comms Pit Shop Drawings - Telecom | 2 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 380 | 2026-03-06 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-001243 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-27 | Auspan-TRANSMIT-000110 | NA | Trade Partner | Precast shop drawings for construction. Level 1. | 15 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Drawings, No review required. Updated register and ACC folders. |  | 2026-02-27 | KPTG-TRANSMIT-001082 | Closed | 15 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-27 | Auspan-TRANSMIT-000111 | NA | Trade Partner | Precast shop drawings for construction. Stage 9 level 1. | 36 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required, Updated register and ACC folders. |  | 2026-02-27 | KPTG-TRANSMIT-001085 | Closed | 36 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-27 | Auspan-TRANSMIT-000112 | NA | Trade Partner | Precast shop drawings for construction. Stage 9 ground floor. | 25 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required, Updated register and ACC folders. |  | 2026-02-27 | KPTG-TRANSMIT-001088 | Closed | 25 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-27 | Auspan-TRANSMIT-000113 | NA | Trade Partner | Update already IFCed shop drawings. Level 1 | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC shop drawings, No review required. Updated register and ACC folders |  | 2026-02-27 | KPTG-TRANSMIT-001091 | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-11 | AXIS-NSW-TRANSMIT-000002 | NA | Trade Partner | NEXT DC STAGE 2 Samples | 0 | 4 | 0 | NA | APPROVED | 2026-02-11 | WF-000229 | NA | 2026-02-18 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-001064 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-08 | DG-TRANSMIT-000052 | NA | Trade Partner | Re: DELTA - HYTEC GWP and Mix Design - For Review | 0 | 1 | 0 | NA | APPROVED | 2025-12-08 | WF-000082 | NA | 2025-12-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-17 | WSP ANZ-TRANSMIT-000046 | NA | Consultant | WSP - Building Services Documents - Issue for Tender - Electrical | 84 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 330 | 2026-02-27 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-001068 | Closed | 84 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-17 | WSP ANZ-TRANSMIT-000046 | NA | Consultant | WSP - Building Services Documents - Issue for Tender - CSMS | 25 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 328 | 2026-02-27 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-001068 | Closed | 25 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-17 | WSP ANZ-TRANSMIT-000046 | NA | Consultant | WSP - Building Services Documents - Issue for Tender - Hydraulic | 63 | 0 | 0 | NA | APPROVED | 2026-02-20 | NA | 343 | 2026-02-27 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-001068 | Closed | 63 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-17 | WSP ANZ-TRANSMIT-000046 | NA | Consultant | WSP - Building Services Documents - Issue for Tender - Vertical Transport | 7 | 0 | 0 | NA | APPROVED | 2026-02-17 | NA | 335 | 2026-02-27 |  |  | 2026-02-27 | 2026-02-27 | KPTG-TRANSMIT-001068 | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-27 | TTW-TRANSMIT-000097 | NA | Consultant | Updated Civil Stormwater IFC | 10 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 290 | 2026-03-04 |  | 2 DWGS REJECTED - QA ERROR - KPTG-TRANSMIT-000590 - DWG REISSUED TRN#98 | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-000590 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-27 | Civilex-TRANSMIT-000034 | NA | Trade Partner | GRP Panel Tank | 0 | 1 | 0 | NA | APPROVED | 2026-02-27 | WF-000189 | NA | 2026-03-02 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-000732 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-27 | RDSBIM-TRANSMIT-000021 | NA | Trade Partner | LEVEL 06 CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 286 | 2026-03-03 |  |  | 2026-03-03 | 2026-03-04 | KPTG-TRANSMIT-000645 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-27 | WAM-TRANSMIT-000719 | NA | Consultant | Joinery Prototype Update - DRAWINGS | 2 | 0 | 0 | NA | APPROVED | 2026-02-28 | NA | 288 | 2026-03-04 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-000595 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-02-27 | WAM-TRANSMIT-000719 | NA | Consultant | Joinery Prototype Update - SPEC | 0 | 1 | 0 | NA | APPROVED | 2026-02-28 | WF-000193 | NA | 2026-03-03 |  |  |  | 2026-03-04 | KPTG-TRANSMIT-000638 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-27 | Hames-TRANSMIT-000123 | NA | Consultant | Door Hardware Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-02-27 | NA | 1022 | 2026-03-04 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-003032 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-08 | KPA M&C-TRANSMIT-000008 | NA | Consultant | Updated Shotcrete wall | 2 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-000083 | 158 | 2025-12-11 |  |  |  | 2025-12-11 | KPTG-TRANSMIT-000310 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-27 | Hames-TRANSMIT-000125 | NA | Consultant | Architectural IFC drawings | 14 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 1025 | 2026-03-04 |  | made VOID as per Will Mason - HS will issue new set | 2026-03-02 | 2026-03-06 | Hames-TRANSMIT-000132 | Closed | 14 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-27 | VAE-Grp-TRANSMIT-000133 | NA | Trade Partner | MECH - TECH SUBS & SCHEDS - GRILLES & DIFFUSERS - ADD CIRCULAR | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | FC DOCS REGISTER UPDATED AND FORWARDED TO ALL PARTIES |  | 2026-03-01 | KPTG-TRANSMIT-003023 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-27 | Hames-TRANSMIT-000126 | NA | Consultant | Lower Ground Flashing Detail and Door Signage | 3 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 1031 | 2026-03-04 |  | SUPERSEDED BY HAMES-TRANSMIT-132 | 2026-03-02 | 2026-03-06 | Hames-TRANSMIT-000132 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-27 | Endfire-TRANSMIT-000066 | NA | Trade Partner | WATER MIST LAYOUT | 3 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 1027 | 2026-03-04 |  |  | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-003059 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-27 | Endfire-TRANSMIT-000067 | NA | Trade Partner | WETFIRE SCHEMATIC AND DETAIL IFA's | 3 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 1029 | 2026-03-04 |  |  | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-003055 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-27 | RDSBIM-TRANSMIT-000062 | NA | Trade Partner | LEVEL 02 PARTITION WALL PLAN AND ELEVATION | 3 | 0 | 0 | NA | APPROVED | 2026-03-01 | NA | 1033 | 2026-03-04 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-003082 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-02-27 | ECBS-TRANSMIT-000013 | NA | Trade Partner | Thermoseal Firespec, IROCK PLUS Non-Combustible White Faced Insulation | 0 | 2 | 0 | QA CHECKED - TO BE CONFIRMED BY EMMA - KPTG-IntCorr-001042 | APPROVED | 2026-03-11 | WF-000900 | NA | 2026-03-18 |  |  | 2026-03-23 | 2026-04-08 | KPTG-TRANSMIT-003360 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-27 | SMEPS-TRANSMIT-000192 | NA | Trade Partner | Re: SME - M3S4 - BTU Shop Drawings | 4 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due to incorrect drawing number in inside drawing |  | 2026-02-27 | KPTG-TRANSMIT-013640 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-27 | ZIA-TRANSMIT-000064 | NA | Trade Partner | Re: M3S4 CSMS Roof and Roof Plant SLA Sensor Location (FOA-1) | 5 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due to incorrect drawing number on the inside drawing |  | 2026-02-27 | KPTG-TRANSMIT-013641 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-27 | Tradetec-TRANSMIT-000380 | NA | Trade Partner | Re: Stage 4 - IFA - LVP35, LVP39, LVP46, LVP47, CP20, CP30, CP40, CP37, CP21 | 9 | 0 | 0 | NA | REJECTED | [5 empty] | qa reject do to incorecct document numbering |  | 2026-02-27 | KPTG-TRANSMIT-013654 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-08 | Auspan-TRANSMIT-000025 | NA | Trade Partner | Re: Update precast marking elevation zone 4, 5 | 6 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-000084 | 160 | 2025-12-18 |  |  |  | 2025-12-16 | KPTG-TRANSMIT-000343 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-27 | RDSBIM-TRANSMIT-000233 | NA | Trade Partner | LEVEL 01-C-G-042 CLEANER FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 2283 | 2026-03-02 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-014715 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-02 | D&E-TRANSMIT-000131 | SPARK-CRFI-KPG-000563 | Trade Partner | CONTROL FIELD CONTROLLERS | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-24 | KPTG-TRANSMIT-000572 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-02 | D&E-TRANSMIT-000132 | SPARK-CRFI-KPG-000386 | Trade Partner | MSSB INTERNAL COMPONENTS | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000762 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-02 | Schindle-TRANSMIT-000007 | NA | Trade Partner | NEL MCC - Lift Interior Drawings - For Review | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Revision block is missing |  | 2026-03-02 | KPTG-TRANSMIT-000490 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-02 | Schindle-TRANSMIT-000008 | NA | Trade Partner | Drawings - For Construction - Lift Layout, Landing Button & COP | 3 | 0 | 0 | NA | REJECTED | [5 empty] | The drawing number inside the drawing and in Aconex seem different |  | 2026-03-02 | KPTG-TRANSMIT-000491 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-02 | Schindle-TRANSMIT-000009 | NA | Trade Partner | Drawings - For Approval - Lift Hall Indicator | 1 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-03-02 | KPTG-TRANSMIT-000492 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-02-23 | Civilex-TRANSMIT-000193 | NA | Trade Partner | Stage 3 - 22KVA Switch Room Building HANDRAIL MARKING PLAN & SECTIONS | 0 | 1 | 0 | NA | APPROVED | 2026-02-23 | WF-004424 | NA | 2026-02-27 |  |  | 2026-02-28 | 2026-03-02 | KPTG-TRANSMIT-013697 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-26 | SMEPS-TRANSMIT-000114 | NA | Trade Partner | SME Shop Drawing Electrical IFC A | 1 | 0 | 0 | NA | APPROVED | 2026-02-26 | WF-000182 | NA | 2026-03-03 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-000343 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-27 | SMEPS-TRANSMIT-000113 | NA | Trade Partner | SME Shop Drawing Electrical IFC A Cell 1 Neutral Earth Schematic | 1 | 0 | 0 | NA | APPROVED | 2026-02-26 | WF-000182 | NA | 2026-03-03 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-000346 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-08 | JCBa-TRANSMIT-000041 | NA | Consultant | A-31_Updated Precast Elevations IFC | 16 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-000085 | 162 | 2025-12-11 |  |  |  | 2025-12-11 | KPTG-TRANSMIT-000311 | Closed | 16 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-27 | SMEPS-TRANSMIT-000119 | NA | Trade Partner | Final (WF-000122) SHOP DRAWING ¦ CONSULTANT REVIEW ¦ EL ¦ SME ¦ IFA ¦ SMEPS-TRANSMIT-000073 - SME Shop Drawing Electrical | 3 | 0 | 0 | NA | APPROVED | 2026-02-27 | WF-000187 | NA | 2026-03-03 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-000357 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-27 | SMEPS-TRANSMIT-000120 | NA | Trade Partner | Telecoms drawings issued for review | 3 | 0 | 0 | NA | APPROVED | 2026-03-02 | WF-000188 | NA | 2026-03-06 |  |  | 2026-03-05 | 2026-03-05 | KPTG-TRANSMIT-000389 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-27 | SMEPS-TRANSMIT-000121 | NA | Trade Partner | Electrical drawings issued for review | 3 | 0 | 0 | NA | APPROVED | 2026-03-02 | WF-000190 | NA | 2026-03-06 |  |  | 2026-03-05 | 2026-03-05 | KPTG-TRANSMIT-000385 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-27 | RDSBIM-TRANSMIT-000002 | NA | Trade Partner | LEVEL 2 COLO 4 CEILING LAYOUT | 3 | 0 | 0 | NA | APPROVED | 2026-03-02 | WF-000189 | NA | 2026-03-06 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-000403 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-26 | SMEPS-TRANSMIT-000118 | NA | Trade Partner | BOM R 4 | 0 | 1 | 0 | NA | APPROVED | 2026-02-26 | WF-000183 | NA | 2026-03-06 |  |  | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-000384 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-26 | Altaire-TRANSMIT-000003 | NA | Trade Partner | Dry Fire Shop Drawings (For Approval) (1) | 3 | 0 | 0 | NA | APPROVED | 2026-02-27 | WF-000186 | NA | 2026-03-05 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000428 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-26 | SMEPS-TRANSMIT-000115 | NA | Trade Partner | SME Shop Drawing Electrical IFA 2 | 8 | 0 | 0 | NA | APPROVED | 2026-02-26 | WF-000180 | NA | 2026-03-04 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-000363 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-26 | SMEPS-TRANSMIT-000117 | NA | Trade Partner | SME Shop Drawing Telecommunications IFA 1 | 11 | 0 | 0 | NA | APPROVED | 2026-02-26 | WF-000184 | NA | 2026-03-04 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-000868 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-02 | AXIS-NSW-TRANSMIT-000007 | NA | Trade Partner | Contaminated Sprinkler Drain sample | 0 | 1 | 0 | NA | APPROVED | 2026-03-02 | WF-000291 | NA | 2026-03-09 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-001306 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-07 | Auspan-TRANSMIT-000016 | NA | Trade Partner | Precast shop drawings for approval. L shape panels. | 56 | 0 | 0 | KPTG-DA-000604 | REJECTED | [5 empty] | Wrong title guide-KPTG-DA-000604-Kapitol initiated an Internal Workflow-WF-000068 |  | 2025-12-07 |  | Closed | 56 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-02 | SMEPS-TRANSMIT-000193 | NA | Trade Partner | SME - IFA SAMPLE RE-SUBMISSION | 0 | 4 | 0 | NA | REJECTED | [5 empty] | Wrong attachment |  | 2026-03-02 | KPTG-TRANSMIT-013706 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-02 | ZIA-TRANSMIT-000067 | NA | Trade Partner | Zi-Argus SD & Procurements | 1 | 0 | 0 | NA | REJECTED | [5 empty] | The Aconex subject line is incorrect - |  | 2026-03-02 | KPTG-TRANSMIT-013712 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-02 | Nilsen3-TRANSMIT-000052 | NA | Trade Partner | Sample for approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-02 | WF-004554 | NA | 2026-03-05 |  |  | 2026-03-10 | 2026-03-11 | KPTG-TRANSMIT-014123 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-02 | KPTG-WTRAN-008343 | NA | Trade Partner | Earth Cable | 0 | 1 | 0 | NA | APPROVED | 2026-03-02 | WF-004552 | NA | 2026-03-05 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-02 | D&E-TRANSMIT-000432 | NA | Trade Partner | IW Pumps - Rev B - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-02 | WF-004555 | NA | 2026-03-23 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014858 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-02 | D&E-TRANSMIT-000433 | NA | Trade Partner | Expansion Tanks & Auto Refill Units - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-02 | WF-004559 | NA | 2026-03-23 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014829 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-02 | D&E-TRANSMIT-000434 | NA | Trade Partner | VSDs - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-03-02 | WF-004560 | NA | 2026-03-23 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014828 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-02 | SMEPS-TRANSMIT-000194 | NA | Trade Partner | SME - M3S4 - MDB Typical Shop Drawing | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing Number mismatch between Aconex and drawing sheet |  |  | KPTG-TRANSMIT-013714 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-05 | VIA Arch-TRANSMIT-000028 | NA | Consultant | M2 S9-11 Pricing Issue Update | 14 | 0 | 0 | 1 Drawing on redstick | APPROVED | 2025-12-08 |  | 118 | 2025-12-16 |  |  | 2025-12-12 | 2025-12-13 | KPTG-TRANSMIT-000331 | Closed | 13 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-02 | Tradetec-TRANSMIT-000383 | NA | Trade Partner | Stage 4 - IFA - LVP35, LVP39, LVP46, LVP47, CP20, CP30, CP40, CP37, CP21 | 9 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 2305 | 2026-03-10 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-014253 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-02 | Altaire-TRANSMIT-000091 | NA | Trade Partner | Re: NEXTDC M3S4 - Dry Fire Fire Panel Shop Drawings (For Approval) (1) | 1 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due to incorrect revision number |  | 2026-03-02 | KPTG-TRANSMIT-013715 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-02 | RDSI-TRANSMIT-000033 | NA | Trade Partner | HANWHA ¦ FURNISHED FACILITY (B18) PARTITION WALL LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 326 | 2026-03-06 |  |  | 2026-03-03 | 2026-03-03 | KAPITOL-INTCOR-001100 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-02 | D&E-TRANSMIT-000430 | NA | Trade Partner | Re: Refrigerant Charge Calculations - Issued for Review | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The document number is not included in the document. |  | 2026-03-02 | KPTG-TRANSMIT-013713 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-02 | D&E-TRANSMIT-000428 | NA | Trade Partner | Chiller Roof - Builders Works Layout ZONES | 5 | 0 | 0 | NA | APPROVED | 2026-03-02 | 2310 | NA | 2026-03-10 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-014744 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-10-06 | INGEN3D-TRANSMIT-000641 | NA | Consultant | Re: I3D-378 Next DC M3 Stage 4 - Ground Floor (Zone 6) | 5 | 0 | 0 | NA | APPROVED | 2026-01-06 | WF-001263 | 0 | 2026-02-18 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-013730 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-02 | PARR-TRANSMIT-000126 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel | 0 | 21 | 0 | NA | APPROVED | 2026-03-02 | WF-004565 | NA | 2026-03-23 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-015171 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-02 | Altaire-TRANSMIT-000092 | NA | Trade Partner | NEXTDC M3S4 - Dry Fire Fire Panel Shop Drawings (For Approval) (1) | 1 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 2315 | 2026-04-10 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-014740 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-02 | ACG-TRANSMIT-000057 | NA | Consultant | M3 - Stage 4 Internal Drawings IFA Revision | 14 | 0 | 0 | NA | REJECTED | [5 empty] | Two documents have already been submitted under same revision. Also, the document number mentioned inside the drawing differs from the document register |  | 2026-03-02 | KPTG-TRANSMIT-013731 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-02 | D&E-TRANSMIT-000429 | NA | Trade Partner | NXM3S4 - Cooling Tower Mesh - Builders Works Layouts - ZONES - Issued For Approval | 4 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 2312 | 2026-04-10 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-014749 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-05 | GEMBA-D-TRANSMIT-000008 | NA | Consultant | Stage 10 and 11 piling update - FC2 issue | 2 | 0 | 0 | KPTG-DA-000603 | APPROVED | [7 empty] | 2026-01-14 | KPTG-TRANSMIT-000489 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-02 | D&E-TRANSMIT-000426 | NA | Trade Partner | NXM3S4 - Ground - Plinth & Equipment Layout - Zone 8 & 10 - Issued For Approval | 2 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 2308 | 2026-04-10 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-014724 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-02 | RDSBIM-TRANSMIT-000237 | NA | Trade Partner | NXM3S4 - GROUND FLOOR CONCRETE PROFILE PLAN & SECTIONS | 4 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 2306 | 2026-03-13 |  | As requested by Oliver T - void The drawings do not reflect current architect documentation and need to be revised |  | 2026-03-31 | KPTG-TRANSMIT-015276 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-02 | RDSBIM-TRANSMIT-000236 | NA | Trade Partner | NXM3S4 - LEVEL 01 CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 2300 | 2026-03-13 |  | As requested by Oliver T - void The drawings do not reflect current architect documentation and need to be revised |  | 2026-03-31 | KPTG-TRANSMIT-015277 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-02 | SMEPS-TRANSMIT-000195 | NA | Trade Partner | SME - M3S4 - CMDB Typical Shop Drawing | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Document number is not mentioned inside the drawing |  | 2026-03-02 | KPTG-TRANSMIT-013707 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-02 | SKS Tech-TRANSMIT-000042 | NA | Trade Partner | C1, C2 and C3 Roof Containment | 3 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 2297 | 2026-04-10 |  | There are 6 drawings in this transmittal, out of which 3 telecommunication drawings are included in this workflow. | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016538 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-02 | Tradetec-TRANSMIT-000382 | NA | Trade Partner | Stage 4 - IFC - LVP48 | 1 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 2292 | 2026-03-09 |  |  | 2026-03-05 | 2026-03-05 | KPTG-TRANSMIT-013923 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-02 | ARCST-TRANSMIT-000220 | NA | Trade Partner | C2 Cooling Tower Upper Roof - Issued for Approval | 106 | 0 | 0 | NA | APPROVED | 2026-03-02 | WF-004545 | NA | 2026-03-26 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016186 | Closed | 106 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-27 | D&E-TRANSMIT-000419 | NA | Trade Partner | BMS Graphic Samples - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-02-27 | WF-004524 | NA | 2026-03-13 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-014920 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-02 | RDSBIM-TRANSMIT-000235 | NA | Trade Partner | RCP GROUND FLOOR | 1 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 2289 | 2026-03-04 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-015195 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-27 | D&E-TRANSMIT-000420 | NA | Trade Partner | Stage 2 Office Technical Data - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-02-27 | WF-004527 | NA | 2026-03-13 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-08 | Auspan-TRANSMIT-000018 | NA | Trade Partner | Precast shop drawings for approval. L shape panels. | 2 | 0 | 0 | KPTG-DA-000604 | REJECTED | 2025-12-08 |  |  |  |  | Wrong title guide-KPTG-DA-000604-Kapitol initiated an Internal Workflow-WF-000068 |  | 2025-12-08 | KPTG-DA-000604 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-27 | Facx-TRANSMIT-000017 | NA | Trade Partner | Punch Window Details - IFC | 1 | 0 | 0 | NA | APPROVED | 2026-02-27 | NA | 3874 | 2026-03-06 |  | Terminated as advised by Dean Antony Via KPTG-DA-007682 |  | 2026-07-21 | KPTG-TRANSMIT-019855 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-27 | NXT-TRANSMIT-001346 | NA | Trade Partner | 100222-000578: M3 Data Center Stage 2: EA Room Revised MDR - For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-02-27 | WF-004536 | NA | 2026-03-10 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-015937 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-02 | Jangho-TRANSMIT-000011 | NA | Trade Partner | 671-DIP drawings for FT02& FT20 window wall system REV1 | 28 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 305 | 2026-03-10 |  | Review voided; drawings to be superseded by Jangho |  | 2026-04-28 | NA | Closed | 28 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-02 | Jangho-TRANSMIT-000012 | NA | Trade Partner | Re: 671-DIP drawings for FT02& FT20 window wall system REV1 | 0 | 4 | 0 | NA | APPROVED | 2026-03-02 | WF-000253 | NA | 2026-03-09 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-02 | RDSBIM-TRANSMIT-000036 | NA | Trade Partner | 671CHP ¦ BASEMENT 4A TO BASEMENT 1 CORE WALL PLAN AND ELEVATIONS | 3 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 307 | 2026-03-05 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-000542 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-02 | B Smart-TRANSMIT-000061 | NA | Consultant | A30 - Door series IFC | 13 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 309 | 2026-03-05 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-000720 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-28 | Altaire-TRANSMIT-000090 | NA | Trade Partner | Dry Fire O&M, Certificate & Commissioning document Sample | 0 | 6 | 0 | NA | APPROVED | 2026-03-02 | WF-004567 | NA | 2026-03-17 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-015196 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-02 | RDSBIM-TRANSMIT-000028 | NA | Trade Partner | GREYSTAR ¦ GROUND FLOOR MAIN ENTRY RAMP PLAN AND SECTION | 3 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 419 | 2026-03-09 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-000864 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-01 | HDRAus-TRANSMIT-000414 | NA | Consultant | Site Wide - Architectural Documentation Update | 4 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 3881 | 2026-03-04 |  |  | 2026-03-04 | 2026-03-11 | KPTG-TRANSMIT-014138 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-02 | INDS-TRANSMIT-000006 | NA | Trade Partner | Ground - Floor Penetration Layouts | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapiol DM, register and Transmit to RDS. |  | 2026-03-02 | KPTG-TRANSMIT-000784 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-01 | Fredon T-TRANSMIT-000003 | NA | Trade Partner | AV Display Bracket - Tech Data | 0 | 1 | 0 |  | REJECTED |  | 0 | 0 |  |  | Requested to resubmit | [6 empty] | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-08 | ccair-TRANSMIT-000074 | NA | Trade Partner | Level 15 & Roof - Mechanical Ductwork & Pipework Layout - IFA | 3 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-000798 | 502 | 2025-12-15 |  |  | 2026-01-12 | 2026-01-12 | KPTG-SADV-004824 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-02 | Rinco-TRANSMIT-000032 | NA | Consultant | Ground floor reinforcement drawings Issued for Construction | 12 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 421 | 2026-03-04 |  |  | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-000801 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-02 | INDS-TRANSMIT-000007 | NA | Trade Partner | Level 1 Precast Penetration Layou | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapiol DM, register and Transmit to Auspan . |  | 2026-03-02 | KPTG-TRANSMIT-000785 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-02 | HDRAus-TRANSMIT-000415 | NA | Consultant | Stage 2 - Architectural Documentation - General Updates | 34 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 3887 | 2026-03-04 |  |  | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-013861 | Closed | 35 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-02 | INDS-TRANSMIT-000008 | NA | Trade Partner | Level 1 Precast Penetration Layout | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapiol DM, register and Transmit to Auspan |  | 2026-03-02 | KPTG-TRANSMIT-000786 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-02 | D&E-TRANSMIT-000422 | NA | Trade Partner | NXM3S2 - Lower Ground & Level 01 - Mechanical Duct Layouts - Zone 6 & Zone 3 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 3877 | 2026-03-09 |  |  | 2026-03-10 | 2026-03-12 | KPTG-TRANSMIT-014196 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-02 | INDS-TRANSMIT-000009: | NA | Trade Partner | Level 1 Floor Penetration Layout | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapiol DM, register and Transmit to RDS . |  | 2026-03-02 | KPTG-TRANSMIT-000787 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-02 | D&E-TRANSMIT-000423 | NA | Trade Partner | L2 Cx Scripts - IFC | 0 | 14 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-03-02 | KPTG-TRANSMIT-013733 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-02 | ETNInd-TRANSMIT-000093 | NA | Trade Partner | M3 Stage 2 – Commisioning Plan Revise & Resubmit | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-03-02 | KPTG-TRANSMIT-013732 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-02 | KPTG-TRANSMIT-013688 | NA | Trade Partner | Joinery Shop Drawings - Kitchenette + Breakout Bench | 9 | 0 | 0 | NA | REJECTED | [5 empty] | The document attached to M3-ARC-CTA-SDRG-B-0201-0012 also has M3-ARC-CTA-SDRG-B-0201-0010 & M3-ARC-CTA-SDRG-B-0201-0011 in it. |  | 2026-03-02 | KPTG-IntCorr-010180 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-02 | Tradetec-TRANSMIT-000058 | NA | Trade Partner | Revised TSA Technical Data | 0 | 2 | 0 | NA | APPROVED | 2026-03-02 | WF-000292 | NA | 2026-03-10 |  |  | 2026-03-05 | 2026-03-05 | KPTG-TRANSMIT-001181 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-08 | Tradetec-TRANSMIT-000285 | NA | Trade Partner | IFA Shop Drawings - Central West - CP7, HVP8, HVP10 | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with drawing status in the register |  | 2025-12-08 | KPTG-DA-003788 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-11-26 | Baigents-TRANSMIT-000055 | NA | Trade Partner | Site Storage NEL-MCC (Issued for Approval) | 67 | 0 | 0 | NA | APPROVED | 2025-11-26 |  | 66 | 2025-12-03 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-000493 | Closed | 66 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-02 | D&E-TRANSMIT-000133 | SPARK-CRFI-KPG-000490 | Trade Partner | MWYCCB - LEVEL 1 DUCTWORK LAYOUT ZONE 2 & ZONE 4 MECHANICAL SERVICES - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 146 | 2026-03-09 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-000567 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-02 | D&E-TRANSMIT-000134 | NA | Trade Partner | MWYCCB - LEVEL 1 - PENETRATION LAYOUT ZONE 1 & ZONE 3 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 145 | 2026-03-09 |  | Review terminated as per Peter's advise - KPTG-IntCorr-001976 | 2026-03-04 | 2026-03-04 |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-02 | SIL-TRANSMIT-000009 | NA | Trade Partner | Re-Submitting Schematics Drawings | 0 | 8 | 0 | KPTG-IntCorr-000073 | REJECTED | [5 empty] | KAPITOL ADVICE AWAITS: SUBMITTED DOCUMENTS ARE COMBINED MULTI FILE HAVING DIFFERENT SERIAL SOCUMENT NUMBER, KAPITOL NEEDS TO CONFIRM IT:KPTG-IntCorr-000073 |  | 2026-03-04 | KPTG-IntCorr-000081 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-02 | Appselec-TRANSMIT-000017 | NA | Trade Partner | Tech Data IFA | 0 | 23 | 0 | NA | APPROVED | 2026-03-02 | WF-000032 | NA | 2026-03-05 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-000126,KPTG-TRANSMIT-000206 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-02 | EFP-TRANSMIT-000009 | NA | Trade Partner | Procurement Tracker | 0 | 1 | 0 | KPTG-IntCorr-000072 | APPROVED | [5 empty] | IT LOOKS LIKE TRACKER REGISTER, I HAD ALREADY ASKED MR. JACOB TO CONFIRM IF ANY WORKFLOW IS REQUIRED FOR THIS ? KAPITOL ADVICE AWAITS:KPTG-IntCorr-000072 No workflow is required:KPTG-SADV-000088 |  | 2026-03-04 | KPTG-SADV-000088 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-02 | ETNInd-TRANSMIT-000006 | NA | Trade Partner | COLO4 & COLO5 UPS L2/L3 Script for Review | 0 | 5 | 0 | NA | APPROVED | 2026-03-02 | WF-000031 | NA | 2026-05-03 |  | Final workflow:KPTG-WTRAN-000103 is hold off, No review stamp has placed in the document, hence, requested them to place review stamp and retransmit to us:KPTG-IntCorr-000169 |  | 2026-04-01 | KPTG-TRANSMIT-000262 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-02 | M.S.-TRANSMIT-000056 | NA | Trade Partner | Level 2 Wall Panelling - IFC Shop Drawings | 7 | 0 | 0 |  | REJECTED | [5 empty] | Clarification is required on Status of drawing and revision : Kapitol Advice Awaits KPTG-SADV-003791 |  | 2026-03-02 | KPTG-SADV-003791 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-02 | KPTG-IntCorr-005571 | NA | Trade Partner | Spectator Seating Balustrade | 1 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 453 | 2026-03-09 |  |  | 2026-03-05 | 2026-03-05 | KPTG-SADV-003820 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-02 | KPTG-IntCorr-005572 | NA | Trade Partner | Samples | 0 | 3 | 0 | NA | APPROVED | 2026-03-02 | WF-000854 | NA | 2026-03-10 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-002669 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-08 | LANSA-TRANSMIT-000077 | NA | Trade Partner | LEVEL 9 WATER SERVICES LAYOUT IFA | 2 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-000793 | 497 | 2025-12-15 |  |  | 2025-12-16 | 2025-12-16 | KPTG-SADV-004720 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-01 | ECBS-TRANSMIT-000074 | NA | Trade Partner | Tech data - 13mm Rigid Air Barrier (EF227) for review | 0 | 1 | 0 | NA | APPROVED | 2026-03-02 | WF-000855 | NA | 2026-03-05 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-002630 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-02 | Auspan-TRANSMIT-000115 | NA | Trade Partner | Update already IFCed shop drawings for construction. | 34 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Drawings, No review required. Updated register and ACC |  | 2026-03-02 | NA | Closed | 34 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-02 | BLUESF-TRANSMIT-000063 | NA | Trade Partner | M2 STAGE-11_REVISED_IFC_DRAWING - POUR 1 (11PW-3,55,56,58,59) | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. |  | 2026-03-02 | KPTG-TRANSMIT-001122 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-02 | VIA Arch-TRANSMIT-000060 | NA | Consultant | M2 S9-11 Redesign 75% DD Issue | 25 | 0 | 0 | KPTG-IntCorr-000468 | APPROVED | 2026-03-03 | NA | 384 | 2026-03-05 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-001262 | Closed | 26 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-02 | BLUESF-TRANSMIT-000064 | NA | Trade Partner | S11 Precast - Ground level (Partial - Pour 4) - IFC | 26 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. |  | 2026-03-02 | KPTG-TRANSMIT-001128 | Closed | 26 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-02-23 | Tradetec-TRANSMIT-000022 | NA | Trade Partner | Technical Data Submissions - TSA | 0 | 2 | 0 | NA | APPROVED | 2026-02-23 | WF-000265 | NA | 2026-03-02 |  | Resubmitted for Civil / Str consultant review as per Kapitol instruction | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-001138 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2026-03-02 | Altaire-TRANSMIT-000020 | NA | Trade Partner | Dry Fire O&M, Certificate & Commissioning document Sample | 0 | 5 | 0 | KPTG-IntCorr-000244 | APPROVED |  | NA | NA |  |  | No review required as confirmed by Kapitol |  | 2026-03-03 | KPTG-IntCorr-000245 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-02 | TTW-TRANSMIT-000098 | NA | Consultant | Updated Civil Stormwater Transmittal | 2 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 290 | 2026-03-04 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-000590 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-02 | Civilex-TRANSMIT-000035 | NA | Trade Partner | Curing Compound Sample | 0 | 1 | 0 | NA | APPROVED | 2026-03-02 | WF-000194 | NA | 2026-03-04 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000710 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-08 | D&E-TRANSMIT-000304 | NA | Trade Partner | M3 HS1 Filters IFA | 0 | 1 | 0 | NA | APPROVED |  | WF-003524 | NA |  |  |  |  | 2025-12-08 | WF-003524 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-02 | WAM-TRANSMIT-000720 | NA | Consultant | WAM ARCH - 95% DD - CSP L2 | 2 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 292 | 2026-03-04 |  |  |  | 2026-03-03 | KPTG-TRANSMIT-000613 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-02 | INGEN3D-TRANSMIT-000005 | NA | Trade Partner | District Living - Level 3 - Precast Columns & Cast in Dowels - IFA | 65 | 0 | 0 | NA | APPROVED | 2026-03-02 | WF-000196 | NA | 2026-03-04 |  |  |  | 2026-03-17 | KPTG-TRANSMIT-000790 | Closed | 47 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-02 | D&E-TRANSMIT-000001 | NA | Trade Partner | VML00918 District Living Docklands Woolworths Early Works ¦ Outside Air Fan & Sound Attenuators Tech. Data - FOR APPROVAL | 1 | 0 | 0 | NA | REJECTED | [5 empty] | QA Error |  | 2026-03-02 | DRAFT-004932 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-02 | INGEN3D-TRANSMIT-000008 | NA | Trade Partner | Level 2 & 3 - Cast in Dowels - Revised IFA (02-03-2026) | 17 | 0 | 0 | KPTG-IntCorr-000411 | APPROVED | 2026-03-03 | WF-000200 (9 DWGS), WF-000201 (8 DWGS) | NA | 2026-03-11 |  | Awating Approval From Kapitol (NIch) | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-000795, KPTG-TRANSMIT-000799 | Closed | 15 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-02 | PCForm-TRANSMIT-000085 | NA | Trade Partner | Jumpform Concrete Envelope & Wall Elevation - Raft 2 - Wall thickness change review | 10 | 0 | 0 | NA | REJECTED | [5 empty] | QA ERROR |  | 2026-03-02 | KPTG-SADV-001000 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-02 | INGEN3D-TRANSMIT-000009 | NA | Trade Partner | Level 2 & 3 - Cast in Dowels - Deleted Drawings | 16 | 0 | 0 | NA | REJECTED | [5 empty] | QA ERROR |  | 2026-03-02 | KPTG-SADV-000997 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-02 | PCForm-TRANSMIT-000086 | NA | Trade Partner | Level 2 carpark grout tube asbuilt | 1 | 0 | 0 | KPTG-IntCorr-000412 | APPROVED | [5 empty] | Awating Approval From Kapitol (NIch) - froward to TTW and I3D |  | 2026-03-03 | KPTG-TRANSMIT-000604 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-02 | Altaire-TRANSMIT-000028 | NA | Trade Partner | Dry Fire O&M, Certificate & Commissioning document Sample | 0 | 6 | 0 | KPTG-IntCorr-003074 | APPROVED |  | NA | NA |  |  | No Action Required |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-02 | OveArup-TRANSMIT-000072 | NA | Consultant | M3 S1 A7A8 Electrical Defect Site Walkthrough Inspection Report | 0 | 1 | 0 | KPTG-IntCorr-003080 | APPROVED |  | NA | NA |  |  | NXT-TRANSMIT-000376 & OveArup-TRANSMIT-000072 are same documents-No Action Required |  |  |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-08 | D&E-TRANSMIT-000303 | NA | Trade Partner | M3 HS1 Office fit out Mechanical Drawings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document number and revision |  | 2025-12-08 | KPTG-DA-003774 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-11-19 | TATE_-TRANSMIT-000023 | NA | Trade Partner | SCEC drawings | 3 | 0 | 0 | NA | APPROVED | 2025-11-19 | NA | 1234 | 2026-03-09 |  |  | 2026-03-01 | 2026-03-02 | KPTG-TRANSMIT-002688 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-11-14 | TATE_-TRANSMIT-000020 | NA | Trade Partner | DH7&8 SCEC penetration drawings | 2 | 0 | 0 | NA | APPROVED | 2025-11-17 | NA | 1226 | 2025-11-21 |  |  | 2026-03-01 | 2026-03-02 | KPTG-TRANSMIT-002685 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-02 | Auscool-TRANSMIT-000085 | NA | Trade Partner | MMSB Load Table & MSSB Schematics For Approval | 0 | 1 | 0 | KPTG-IntCorr-000766 | APPROVED | 2026-03-03 | WF-000641 | NA | 2026-03-05 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-002013 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-11-20 | ARJAY-TRANSMIT-000010 | NA | Trade Partner | Arjay - Shop Drawing - update | 23 | 0 | 0 | KPTG-IntCorr-001937 | APPROVED | 2025-11-21 | NA | 1243 | 2025-11-27 |  | Voided by Fabian- Requested for updated drawing submission |  | 2026-03-02 | KPTG-TRANSMIT-002690 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-02 | SKS Tech-TRANSMIT-000160 | NA | Trade Partner | SEISMIC LAYOUTS IFC - ELC | 4 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 1262 | 2026-05-11 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-003715 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-03 | SKS Tech-TRANSMIT-000048 | NA | Trade Partner | Re: Cover sheet, Drawing index, Legend and General Notes | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect status |  | 2026-03-03 | KPTG-TRANSMIT-013744 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-03 | WilsonPD-TRANSMIT-000163 | SPARK-CRFI-KPG-000183 | Trade Partner | Updated Ground Floor Zone A Drainage Layout | 1 | 0 | 0 | NA | APPROVED | 2026-03-03 | NA | 147 | 2026-03-10 |  |  | 2026-03-16 | 2026-04-24 | KPTG-TRANSMIT-000718 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-03 | SKS Tech-TRANSMIT-000049 | NA | Trade Partner | Re: Roof Small Power C1, C2 and C3 | 3 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-03-03 | KPTG-TRANSMIT-013745 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-17 | NXT-TRANSMIT-001290 | NA | Trade Partner | ABB PDUs - AU-10025007 M3-C-Stage 4 / Ph1 - Shop drawings | 8 | 0 | 0 | NA | APPROVED | 2026-02-17 | WF-004306 | NA | 2026-03-11 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-013747 | Closed | 6 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-03 | WGAVIC-TRANSMIT-000006 | NA | Consultant | Re: Drawing updates for site cut | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Document number error inside |  | 2026-03-03 | KPTG-DA-000271 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-08 | LANSA-TRANSMIT-000078 | NA | Trade Partner | Level 15 & Roof Water Services IFA | 4 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-000794 | 499 | 2025-12-15 |  |  | 2026-01-14 | 2026-01-14 | KPTG-SADV-004879 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-03 | WGAVIC-TRANSMIT-000007 | NA | Consultant | Re: Drawing updates for site cut | 3 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 31 | 2026-03-06 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-000063 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-26 | SES AU-TRANSMIT-000007 | NA | Trade Partner | Security IFC drawings | 5 | 0 | 0 | NA | APPROVED | 2026-02-27 | WF-000185 | NA | 2026-03-05 |  |  | 2026-03-02 | 2026-03-02 | KPTG-TRANSMIT-000364 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-02 | SMEPS-TRANSMIT-000122 | NA | Trade Partner | SME Shop Drawing Electrical IFC A | 2 | 0 | 0 | NA | APPROVED | 2026-03-03 | WF-000195 | NA | 2026-03-09 |  |  | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-000378 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-02 | SMEPS-TRANSMIT-000123 | NA | Trade Partner | SME Shop Drawing Communications IFA 1 | 6 | 0 | 0 | NA | APPROVED | 2026-03-03 | WF-000196 | NA | 2026-03-06 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-000413 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-02 | Stowe-A-TRANSMIT-000506 | NA | Trade Partner | Stowe - Tech Data - IFC | 0 | 1 | 0 | NA | APPROVED | [5 empty] | IFC |  | 2026-03-02 | KPTG-TRANSMIT-013705 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-02 | D&E-TRANSMIT-000427 | NA | Trade Partner | NXM3S2 - Ground / Level 01 & Upper Roof - Mechanical Pipe + Equipment Layout Zones - Issued For Construction | 5 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 3885 | 2026-03-09 |  |  | 2026-03-11 | 2026-03-12 | KPTG-TRANSMIT-014197 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-02 | ASV-TRANSMIT-000152 | NA | Trade Partner | Axis sample - Drinking Fountain re-submit | 0 | 1 | 0 | NA | APPROVED | 2026-03-02 | WF-004553 | NA | 2026-03-18 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014312 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-02 | AXIS-NSW-TRANSMIT-000004 | NA | Trade Partner | Sewer Services - HDPE | 0 | 1 | 0 | NA | APPROVED | 2026-03-03 | WF-000295 | NA | 2026-03-11 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-001302 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-02 | Stowe-A-TRANSMIT-000507 | NA | Trade Partner | Stowe - Tech Data Submission - R1 | 0 | 1 | 0 | NA | APPROVED | 2026-03-02 | WF-004546 | NA | 2026-03-11 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-014263 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-02 | NXT-TRANSMIT-001352 | NA | Client | 000230-110693 - Schematics - As Built - transmittal 2 | 91 | 0 | 0 | NA | APPROVED | [5 empty] | As-Built |  | 2026-03-02 | KPTG-TRANSMIT-013734 | Closed | 91 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-08 | LANSA-TRANSMIT-000079 | NA | Trade Partner | LEVEL 09 SANITARY & STORMWATER DRAINAGE LAYOUT | 2 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-000795 | 500 | 2025-12-15 |  |  | 2026-01-14 | 2026-01-14 | KPTG-SADV-004878 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-02 | D&E-TRANSMIT-000431 | NA | Trade Partner | Outstanding FD, Scripts, ITP | 0 | 10 | 0 | NA | REJECTED | [5 empty] | IFA and IFC in the same transmittals. |  | 2026-03-02 | KPTG-DA-005217 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-03 | WilsonPD-TRANSMIT-000164 | SPARK-CRFI-KPG-000199 | Trade Partner | Updated Water Schematic - Hydraulic Services | 2 | 0 | 0 | NA | APPROVED | 2026-03-03 | NA | 148 | 2026-03-10 |  |  | 2026-03-16 | 2026-05-01 | KPTG-TRANSMIT-000781 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-02 | HDRAus-TRANSMIT-000416 | NA | Consultant | M3 S2 - Shop Drawing Review - Door Frames & Door Hardware | 0 | 1 | 0 | NA | APPROVED | 2026-03-02 | NA | 3883 | 2026-03-04 |  |  | 2026-03-10 | 2026-03-11 | KPTG-TRANSMIT-014146 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-02 | ACG-TRANSMIT-000062 | NA | Trade Partner | M3 - Stage 2 Internal ACG Shop Drawings IFC | 9 | 0 | 0 | NA | APPROVED | 2026-03-02 | NA | 3879 | 2026-03-09 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-014462 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-03 | RDSBIM-TRANSMIT-000036 | SPARK-CRFI-KPG-000362 | Trade Partner | MWYCCB ¦ SITE STORAGE BUILDING GF & LEVEL 01 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-03-03 | NA | 149 | 2026-03-10 |  |  | 2026-03-03 | 2026-04-24 | KPTG-TRANSMIT-000722 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-03 | WilsonPD-TRANSMIT-000165 | SPARK-CRFI-KPG-000511 | Trade Partner | Updated Hydraulic Drawing - Level 1 Zone A Penetration Layout | 1 | 0 | 0 | NA | APPROVED | 2026-03-03 | NA | 150 | 2026-03-10 |  |  | 2026-03-16 | 2026-04-24 | KPTG-TRANSMIT-000702 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-03 | SKS Tech-TRANSMIT-000047 | NA | Trade Partner | Basket Radius Piece | 0 | 1 | 0 | NA | APPROVED | 2026-03-03 | WF-004572 | NA | 2026-03-24 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014793 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-03 | WGAVIC-TRANSMIT-000075 | NA | Consultant | M2 Stage 9 Level 1 Slab Construction Issue | 13 | 0 | 0 | KPTG-IntCorr-000472 | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. |  | 2026-03-05 | NA | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-03 | Nilsen3-TRANSMIT-000053 | NA | Trade Partner | NXM3S4 - Nilsen ELC Shop Drawings - FOA #1 | 6 | 0 | 0 | NA | APPROVED | 2026-03-03 | NA | 2317 | 2026-03-11 |  |  | 2026-03-03 | 2026-03-31 | KPTG-TRANSMIT-015321 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-03 | KPTG-TRANSMIT-013739 | NA | Trade Partner | SME Sample Submission | 0 | 14 | 0 | NA | APPROVED | 2026-03-03 | WF-004577 | NA | 2026-03-24 |  |  | 2026-03-25 | 2026-03-26 | KPTG-TRANSMIT-014951, KPTG-TRANSMIT-015089 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-08 | LANSA-TRANSMIT-000080 | NA | Trade Partner | Level 15 & Roof Drainage IFA | 4 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-000797 | 501 | 2025-12-15 |  |  | 2026-02-25 | 2026-02-25 | KPTG-SADV-005660 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-03 | WGAVIC-TRANSMIT-000076 | NA | Consultant | M2 Stage 9 Columns and Walls Construction Issue | 7 | 0 | 0 | KPTG-IntCorr-000473 | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. |  | 2026-03-05 | NA | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-03 | SMEPS-TRANSMIT-000197 | NA | Trade Partner | SME - M3S4 - CMDB & MDB Typical Shop Drawing | 2 | 0 | 0 | NA | APPROVED | 2026-03-03 | 2319 | NA | 2026-03-11 |  |  |  | 2026-03-12 | KPTG-IntCorr-010645 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-03 | PFP PL-TRANSMIT-000072 | NA | Trade Partner | Ground and Level 1 IFC | 2 | 0 | 0 | NA | APPROVED | 2026-03-03 | NA | 2321 | 2026-03-11 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-014459 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-03 | INV-TRANSMIT-000044 | NA | Consultant | STR - Powerpack Construction Issue | 6 | 0 | 0 | NA | APPROVED | 2026-03-03 | NA | 328 | 2026-03-05 |  |  | 2026-03-10 | 2026-03-10 | DRAFT-009218 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-03 | RDSI-TRANSMIT-000034 | NA | Trade Partner | HANWHA FURNISHED FACILITY (B18) PARTITION WALL LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-03-03 | NA | 330 | 2026-03-09 |  |  | 2026-03-10 | 2026-03-10 | KAPITOL-TRANSMIT-001190 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-03 | TTW-TRANSMIT-000161 | NA | Consultant | Fwd: M3 Stage 3 Civil Drawings | 13 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | The register has been updated. If any further action is required, the coordinator will inform.- KPTG-TRANSMIT-013772 As per kian No action required |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-03 | ACG-TRANSMIT-000063 | NA | Consultant | M3 - Stage 4 Internal Drawings IFA Revision | 14 | 0 | 0 | NA | REJECTED | [5 empty] | Waiting for a response from Kiona -Kiona wants to check with KAP team,doc-14 rejected due to incorrect revision in Aconex and inside drawing |  | 2026-03-04 | KPTG-TRANSMIT-013860 | Closed | 14 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-03 | Leemark-TRANSMIT-000014 | NA | Trade Partner | Transmittal of L1 Slab Penetration Drawings - For Approval | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Date in drawing is different |  | 2026-03-03 | KPTG-TRANSMIT-000499 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-03 | TIVINTL-TRANSMIT-000026 | NA | Trade Partner | SRC-Tivoli- Updated joinery drawings | 230 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2026-03-03 | KPTG-TRANSMIT-002771 | Closed | 230 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-03 | JCBa-TRANSMIT-000065 | NA | Consultant | Updated Architectural Documentation - Value Management Amendments | 77 | 1 | 0 | NA | APPROVED | 2026-03-03 | WF-000243 | 423 | 2026-03-06 |  | Tech data 23-122_A-SCH-101 MATERIALS & FINISHES SCHEDULE_INTERIORS. - close-out via KPTG-TRANSMIT-001114. | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-000861 | Closed | 77 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-08 | LANSA-TRANSMIT-000081 | NA | Trade Partner | Level 15 & Roof Penetrations IFA | 4 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-000799 | 503 | 2025-12-15 |  |  | 2026-01-21 | 2026-01-21 | KPTG-SADV-004981 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-03 | PCForm-TRANSMIT-000034 | NA | Trade Partner | IVPT24174 - Basement Sleeving Plan | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing number is not inline with the DesPro-1. TP to update and re-transmit. |  | 2026-03-03 | KPTG-SADV-001166 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-03 | LGCE-TRANSMIT-000004 | NA | Trade Partner | Basement 4 Light and power | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing number is not inline with the DesPro-1. TP to update and re-transmit - DRAFT-004101. |  | 2026-03-03 | DRAFT-004101 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-03 | JCBa-TRANSMIT-000232 | NA | Consultant | Updated Elevations - For Construction | 24 | 0 | 0 | NA | APPROVED | 2026-03-03 | WF-000956 | 551 | 2026-03-09 |  | NA | 2026-05-05 | 2026-05-05 | DRAFT-017498 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-03 | RDSBIM-TRANSMIT-000169 | NA | Trade Partner | LEVEL 15 TOWER B CONCRETE PROFILE PLAN | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2026-03-03 | KPTG-TRANSMIT-002772 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-03 | RDSBIM-TRANSMIT-000029 | NA | Trade Partner | GREYSTAR GROUND FLOOR CONCRETE PROFILE KEY PLAN | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect drawing status. KPTG-SADV-001181 |  | 2026-03-03 | KPTG-SADV-001181 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-03 | crossfir-TRANSMIT-000052 | NA | Trade Partner | Wet Fire - RCP Ground, Level 01 & 02 | 6 | 0 | 0 | NA | APPROVED | 2026-03-03 | WF-000957 | 552 | 2026-03-09 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-03 | Tradetec-TRANSMIT-000384 | NA | Trade Partner | IFC - Stage 2 - LVP226 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | The revision number inside and outside is wrong and also send the wrong revision. |  | 2026-03-03 | KPTG-DA-005227 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-03 | Tradetec-TRANSMIT-000385 | NA | Trade Partner | Tech Data - Culvert Tape | 0 | 1 | 0 | NA | APPROVED | 2026-03-04 | WF-004590 | NA | 2026-03-19 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014284 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-03 | NXT-TRANSMIT-001354 | NA | Client | 100222-000579: M3 DC Stage 2 - EA Room Sprinkler System Layout - As Built | 1 | 0 | 0 | KPTG-DA-005234 | APPROVED | [5 empty] | Seek advice from the originator |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-03 | Tradetec-TRANSMIT-000386 | NA | Trade Partner | IFC - Stage 2 - LVP26 | 1 | 0 | 0 | NA | APPROVED | 2026-03-03 | NA | 3891 | 2026-03-10 |  |  | 2026-03-04 | 2026-03-12 | KPTG-TRANSMIT-014201 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-08 | LANSA-TRANSMIT-000082 | NA | Trade Partner | Level 6 Drainage Reissued due to Incorrect Document on Previous Issue | 2 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-000800 | 504 | 2025-12-15 |  |  | 2026-01-13 | 2026-01-13 | KPTG-SADV-004833 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-03 | INGEN3D-TRANSMIT-000661 | NA | Consultant | I3D-378 Next DC M3 Stage 4 - Core 10 - PWS4-1896-1 & PWS4-1897-1 - IFA Checked (27-10-2025) | 2 | 0 | 0 | NA | APPROVED | 2025-11-06 | WF-003219 | NA | 2026-03-03 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-013791 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-03 | INGEN3D-TRANSMIT-000690 | NA | Trade Partner | I3D-378 Next DC M3 Stage 4 - Ground Floor - R20 | 1 | 0 | 0 | NA | APPROVED | 2026-03-03 | WF-4584 | NA | 2026-03-30 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-016422 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-03 | SKS Tech-TRANSMIT-000046 | NA | Trade Partner | Zone C1 Containment | 14 | 0 | 0 | KPTG-TRANSMIT-013743 | APPROVED |  | NA | NA |  |  | ONLY NEED TO INFORM TEAM-KPTG-TRANSMIT-013842 |  | 2026-03-04 | KPTG-TRANSMIT-013842 | Closed | 14 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-03 | ADP-TRANSMIT-000037 | NA | Consultant | MEL4834 - ADP Updated Mech drawings and Reg 126 | 2 | 1 | 0 | KPTG-IntCorr-003099 | APPROVED |  | NA | NA |  |  | ADP-TRANSMIT-000037 & ADP-TRANSMIT-000038 are same documents-distributed |  | 2026-03-13 | KPTG-TRANSMIT-002754 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-02 | ECBS-TRANSMIT-000075 | NA | Trade Partner | AM41 - Comfab Access Panel tech data for review | 0 | 0 | 0 | NA | REJECTED | [5 empty] | As per the direction from the Ms.Alexia, Documents requires modification : KPTG-SADV-003797 |  | 2026-03-03 | KPTG-SADV-003797 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-03 | CLADC-TRANSMIT-000020 | NA | Trade Partner | Timber handrail shop drawings | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings are transmitted to trade and Consultants |  | 2026-03-03 | KPTG-TRANSMIT-002498 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-03 | fjc-TRANSMIT-000136 | NA | Consultant | Architectural Updates: Door Schedules / Amenities for DDA Review/ Cold Shell | 38 | 4 | 0 | NA | APPROVED | 2026-03-04 | NA | 588 | 2026-03-09 |  |  | 2026-03-10 | 2026-03-11 | KPTG-SADV-003364, KPTG-TRANSMIT-002000 | Closed | 42 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-03 | 4DW-TRANSMIT-000094 | NA | Consultant | Entry Steelwork Updates | 5 | 0 | 0 | NA | APPROVED | 2026-03-03 | NA | 585 | 2026-03-09 |  |  | 2026-03-03 | 2026-03-03 | KPTG-TRANSMIT-001936 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-11-27 | Stowe-A-TRANSMIT-000381 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - OVERALL EARTHING SCHEMATIC - 27.11.2025 | 1 | 0 | 0 | NA | APPROVED | 2025-11-27 | NA | 3338 | 2025-12-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-01 | Fredon T-TRANSMIT-000004 | NA | Trade Partner | Surface Mount Speaker - Pool Side | 0 | 1 | 0 |  | REJECTED | [5 empty] | Requested to Resubmit | [6 empty] | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-08 | WilsonPD-TRANSMIT-000097 | NA | Trade Partner | WPD-HY-TEC-042 Cold Water Booster | 0 | 1 | 0 | NA | APPROVED | 2025-12-08 | WF-000796 | NA | 2025-12-15 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-03 | PSGANZ-TRANSMIT-000008 | NA | Trade Partner | PREM-FR-SMP-014 Fire Curtain | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected: Submitted document is combined set of drawings:KPTG-SADV-003290 |  | 2026-03-03 | KPTG-SADV-003290 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-03 | ZIA-TRANSMIT-000062 | NA | Trade Partner | Re: Stage4 - CSMS Sample Tech data submission for approval | 0 | 10 | 0 | NA | REJECTED | [7 empty] | 2026-03-03 | KPTG-TRANSMIT-013751 | Closed | 10 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-03 | SMEPS-TRANSMIT-000196 | NA | Trade Partner | SME - IFA SAMPLE RE-SUBMISSION | 0 | 4 | 0 | NA | APPROVED | 2026-03-03 | WF-004573 | NA | 2026-03-24 |  | THIS WORKFLOW TERMINATED AS PER REQUESTED FROM PETER DUE TO SAME REVISION CAME WITH DIFFERENT TRANSIMITTAL |  | 2026-03-03 | KPTG-TRANSMIT-013739 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-03 | KPTG-TRANSMIT-013737 | NA | Consultant | SKS Sample Submission | 0 | 4 | 0 | NA | APPROVED | 2026-03-03 | WF-004574 | NA | 2026-03-23 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-015187 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-03 | KPTG-TRANSMIT-013738 | NA | Consultant | Nilsen Sample Submissions | 0 | 26 | 0 | NA | APPROVED | 2026-03-03 | WF-004577 | NA | 2026-03-24 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-03 | LTEPRCST-TRANSMIT-000147 | NA | Trade Partner | Re: NEXTDC STAGE 4: CORE 02 IFC | 23 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due to one document have incorrect revision number mentioned on the inside drawing |  | 2026-03-03 | KPTG-TRANSMIT-013763 | Closed | 23 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-03 | KPTG-TRANSMIT-013764 | NA | Consultant | DC ACTION NEW WF Fwd: NEXTDC STAGE 04 - CORE 08 ISSUED FOR CONSTRUCTION | 25 | 0 | 0 | NA | APPROVED | 2026-03-03 | WF-004588 | NA | 2026-03-10 |  |  | 2026-03-20 | 2026-03-24 | KPTG-TRANSMIT-014898 | Closed | 25 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-03 | Auspan-TRANSMIT-000118 | NA | Trade Partner | Update already IFCed shop drawings for construction. | 35 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. |  | 2026-03-03 | NA | Closed | 35 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-04 | KEECEPRO-TRANSMIT-000029 | NA | Trade Partner | DB Shop Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 331 | 2026-03-09 |  |  | 2026-03-16 | 2026-03-16 | DRAFT-009329 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-04 | Auspan-TRANSMIT-000057 | NA | Trade Partner | L3 column shop drawings issued for construction | 4 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 586 | 2026-03-09 |  |  | 2026-03-04 | 2026-03-04 | KPTG-SADV-003298 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-08 | crossfir-TRANSMIT-000042 | NA | Trade Partner | Dry Fire - Ground to Level 07, IFC | 14 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF - 000801 | 505 | 2025-12-15 |  | NA | 2026-04-20 | 2026-04-21 | DRAFT-017010 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-04 | HIP-TRANSMIT-000006 | NA | Trade Partner | Building - 08 - Variation - 003 - RGV Rails - Issue for Construction | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-03-04 | KAPITOL-TRANSMIT-001156 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-04 | KPTG-WTRAN-008423 | NA | Trade Partner | LINE DULUX | 0 | 2 | 0 | NA | APPROVED | 2026-03-04 | WF-004591 | NA | 2026-03-17 |  | Note: The workflow has been generated as requested by Sam S | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-013874 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-04 | KPTG-WTRAN-008426 | NA | Trade Partner | The workflow has been generated as requested by Lola | 0 | 2 | 0 | NA | APPROVED | 2026-03-04 | WF-004592 | NA | 2026-03-25 |  | Note: The workflow has been generated as requested by Lola |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-04 | DRLL-TRANSMIT-000066 | NA | Trade Partner | Battery Room Modules Electrical Drawings IFC 04 | 8 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 1410 | 2026-03-10 |  | Voided -Requested by Fabian for template changing and resubmitted 1413 |  | 2026-03-05 |  | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-04 | LANSA-TRANSMIT-000016 | NA | Trade Partner | Hydraulic Shop Drawings-IFA | 3 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 1407 | 2026-03-10 |  | Total drawings-6, submitted through 2 workflows | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-002744 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-04 | LANSA-TRANSMIT-000016 | NA | Trade Partner | Hydraulic Shop Drawings-IFC | 3 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 1409 | 2026-03-10 |  | Total drawings-6, submitted through 2 workflows | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-002775 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-03 | WOCEP-TRANSMIT-000001 |  | Trade Partner | SAMPLE DOC | 0 | 16 | 0 | NA | APPROVED |  | NA |  |  |  | terminated as per Jed advise |  | 2026-03-11 | NA | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-04 | DI-TRANSMIT-000150 | NA | Consultant | Hanwha Powerpack Test Specification | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The document reference number has not been included in the document |  | 2026-03-04 | DRAFT-009124 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-04 | D&E-TRANSMIT-000135 | SPARK-CRFI-KPG-000236 | Trade Partner | Split AC Systems | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-04 | Leemark-TRANSMIT-000015 | SPARK-CRFI-KPG-000612 | Trade Partner | Re: Transmittal of L1 Slab Penetration Drawings - For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 151 | 2026-03-11 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-000735 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-11-28 | JCBa-TRANSMIT-000198 | NA | Consultant | Water Proofing Details & Door/Window Updated Setout - IFC | 13 | 0 | 0 | NA | APPROVED | 2025-11-28 | WF-000776 | 488 | 2025-12-05 |  |  | 2025-12-08 | 2025-12-08 | KPTG-DA-002216 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-04 | NXT-TRANSMIT-001359 EAEGROUP-TRANSMIT-000082 | NA | Trade Partner | Block C2 IFC Shop Drawings Submission – Zone C2 | 18 | 0 | 0 | NA | APPROVED | 2026-03-04 | WF-004594 | NA | 2026-03-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-04 | NXT-TRANSMIT-001358 EAEGROUP-TRANSMIT-000083 | NA | Trade Partner | Block C3 – IFA Shop Drawings Submission (HB IT & HA Busduct) | 2 | 0 | 0 | NA | APPROVED | 2026-03-04 | WF-004596 | NA | 2026-03-20 |  |  | 2026-03-05 | 2026-03-05 | KPTG-TRANSMIT-013915 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-04 | NXT-TRANSMIT-001362 EAEGROUP-TRANSMIT-000084 | NA | Trade Partner | Block C2 Load Bank IFC Shop Drawings Submission | 1 | 0 | 0 | NA | APPROVED | 2026-03-04 | WF-004598 | NA | 2026-03-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-04 | D&E-TRANSMIT-000136 | SPARK-CRFI-KPG-000571 | Trade Partner | CABLE TRAY SYSTEMS | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-18 | KPTG-TRANSMIT-000551 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-03 | KPTG-TRANSMIT-000370 | NA | Trade Partner | Siemens L3 Scripts | 0 | 26 | 0 | NA | APPROVED | 2026-03-03 | WF-000197 | NA | 2026-03-09 |  |  | 2026-03-05 | 2026-03-06 | KPTG-TRANSMIT-000412 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-03 | KPTG-TRANSMIT-000371 | NA | Trade Partner | AHU L3 Scripts | 0 | 3 | 0 | NA | APPROVED | 2026-03-03 | WF-000198 | NA | 2026-03-09 |  |  | 2026-03-05 | 2026-03-05 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-03 | PCForm-TRANSMIT-000115 | NA | Trade Partner | Jumpform Concrete Envelopes & Wall Elevations - Stage 11 | 9 | 0 | 0 | NA | APPROVED | 2026-03-03 | WF-000282 | NA | 2026-03-06 |  | Transmittal was not Addressed to DC or not included in Cc, Workflow initiated by Kapitol Project coordinator. Actual receipt date and WF transmit date is 26/02. Workflow Transmittal WGAVIC-WTRAN-000030 received on 03/03 and Transmittal closeout completed by DC on 04/03 | 2026-03-03 | 2026-03-04 | KPTG-TRANSMIT-001171 | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-03 | KPTG-TRANSMIT-000372 | NA | Trade Partner | BAS L3 Scripts | 0 | 9 | 0 | NA | APPROVED | 2026-03-03 | WF-000199 | NA | 2026-03-09 |  |  | 2026-03-03 | 2026-03-03 |  | Closed | 9 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-04 | Ardon-TRANSMIT-000024 | NA | Trade Partner | Threshold Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-03-04 | WF-004599 | NA | 2026-03-20 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015070 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-03 | KPTG-TRANSMIT-000373 | NA | Trade Partner | L3 ATS Script | 0 | 1 | 0 | NA | APPROVED | 2026-03-03 | WF-000200 | NA | 2026-03-09 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-000407 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-04 | JCBa-TRANSMIT-000199 | NA | Consultant | Updated Window Schedule - IFC | 2 | 0 | 0 | NA | APPROVED | 2025-12-04 | WF-000786 | 492 | 2025-12-10 |  |  | 2025-12-08 | 2025-12-08 | KPTG-DA-002217 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-04 | HIP-TRANSMIT-000007 | NA | Trade Partner | Fwd: Building 08 - Mechanical Support Model (Rev D) Review | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC MODEL - |  | 2026-03-04 | DRAFT-009129 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-04 | TTW-TRANSMIT-000162 | NA | Consultant | M3 Stage 3 Civil Drawings | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-TRANSMIT-013845 As instructed, no further action has been taken |  |  |  | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-04 | SKS Tech-TRANSMIT-000051 | NA | Trade Partner | Roof Small power | 3 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 2330 | 2026-03-12 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-015848 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-04 | INGEN3D-TRANSMIT-000691 | NA | Consultant | I3D-378 Next DC M3 Stage 4 - Core 10 - PWS4-1896-1 & PWS4-1897-1 - IFC | 2 | 0 | 0 | NA | APPROVED | 2026-03-04 | WF-004595 | NA | 2026-03-11 |  | TERMINATED AS AS PER REQUESTED BY FINLAY FOR UPDATING NEW REVISION |  | 2026-04-27 | NA | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-04 | SMEPS-TRANSMIT-000198 | NA | Trade Partner | SME - IFA SAMPLE SUBMISSION | 0 | 3 | 0 | NA | APPROVED | 2026-03-04 | WF-004597 | NA | 2026-03-25 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015064 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-02 | ETNInd-TRANSMIT-000011 | NA | Trade Partner | COLO4 UPS L2/L3 Scripts for Review | 0 | 4 | 0 | NA | APPROVED | 2026-03-03 | WF-000206 | NA | 2026-03-09 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-000408 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-03 | KALLIBRE-TRANSMIT-000001 | NA | Trade Partner | MEL05 22x Door Frame Shop Drawings For Review | 1 | 0 | 0 | NA | APPROVED | 2026-03-03 | WF-000202 | NA | 2026-03-09 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000418 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-03 | SES AU-TRANSMIT-000008 | NA | Trade Partner | Security IFC | 3 | 0 | 0 | NA | APPROVED | 2026-03-04 | WF-000208 | NA | 2026-03-10 |  | NA | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000421 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-03 | ETNInd-TRANSMIT-000012 | NA | Trade Partner | MEL05 COLO4 EPMS Data Sheets | 0 | 8 | 0 | NA | APPROVED | 2026-03-04 | WF-000209 | NA | 2026-03-10 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-000415 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-04 | " HIP-TRANSMIT-000009" | NA | Trade Partner | Building - 08 - RGV Rail - Reissued for Information | 3 | 0 | 0 | NA | REJECTED | [5 empty] | IFC and IFA drawings were submitted via the same transmittal |  | 2026-03-04 | KAPITOL-TRANSMIT-001162 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-08 | Omnii-TRANSMIT-000003 | NA | Consultant | Updated Fire Engineering Report | 0 | 1 | 0 | NA | APPROVED | 2025-12-08 | WF-000612 | 707 | 2025-12-11 |  |  | 2025-12-08 | 2025-12-08 | KPTG-TRANSMIT-002196 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-04 | D&E-TRANSMIT-000137 | SPARK-CRFI-KPG-000315 | Trade Partner | MWYCCB - LEVEL 1 PENETRATION LAYOUT ZONE 5 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 125 | 2026-03-11 |  |  | 2026-04-16 | 2026-04-24 | KPTG-TRANSMIT-000689 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-04 | HIP-TRANSMIT-000008 | NA | Trade Partner | Fwd: Block C2 Load Bank IFC Shop Drawings Submission | 13 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 332 | 2026-03-17 |  |  |  | 2026-03-10 | KAPITOL-INTCOR-001116 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-04 | ACG-TRANSMIT-000064 | NA | Trade Partner | M3 - Stage 4 ACG Samples | 0 | 44 | 0 | NA | APPROVED | 2026-03-04 | WF-004603 | NA | 2026-03-31 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-016475 | Closed | 44 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-04 | Leemark-TRANSMIT-000017 | SPARK-CRFI-KPG-000409 | Trade Partner | Re: Transmital of Sprinkler Hydraulic Calculations Reports | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-25 | KPTG-TRANSMIT-000598 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-08-19 | INGEN3D-TRANSMIT-000579 | NA | Consultant | I3D-378 Next DC M3 Stage 4 - C2 Level 1 (Zone 8) - PWS4-1560-1 - IFC (19-08-2025) | 1 | 0 | 0 | NA | APPROVED | 2026-02-27 | WF-004529 | NA | 2026-03-03 |  |  | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-007300 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-04 | ccair-TRANSMIT-000096 | NA | Trade Partner | Level 01 Mechanical Ductwork & Pipework Layout - Zone F Fan Room Updates | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2026-03-04 | KPTG-TRANSMIT-002780 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-11-13 | INGEN3D-TRANSMIT-000668 | NA | Consultant | Re: I3D-378 Next DC M3 Stage 4 - Level 1 (Zone 12) - CAS4-419 - IFA Checked (13-11-2025) | 1 | 0 | 0 | NA | APPROVED | 2025-11-13 | WF-003301 | NA | 2026-03-04 |  |  | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-013847 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-04 | ccair-TRANSMIT-000097 | NA | Trade Partner | Level 10 Ductwork & Pipework - IFC | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2026-03-04 | KPTG-TRANSMIT-002779 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-04 | KALLIBRE-TRANSMIT-000001 | NA | Trade Partner | HANWHA Building 18 - Door Frame Shop Drawings For Review | 1 | 0 | 0 | NA | REJECTED | [5 empty] | The Aconex reference number is not aligned with the Hanwha project. |  | 2026-03-04 | DRAFT-009143 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-04 | SMEPS-TRANSMIT-000121 | NA | Trade Partner | Seismic Restraint | 0 | 1 | 0 | KPTG-IntCorr-001988 | REJECTED | [7 empty] | 2026-03-13 | KPTG-IntCorr-001988 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-08 | D&E-TRANSMIT-000266 | NA | Trade Partner | Technical Data Submission - Flushing Procedure - (FOA3) | 0 | 1 | 0 | NA | APPROVED | 2025-12-08 | WF-000842 | NA | 2025-12-15 |  |  | 2025-12-12 | 2025-12-15 | KPTG-TRANSMIT-002182 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-04 | SMEPS-TRANSMIT-000122 | SPARK-CRFI-KPG-000181 | Trade Partner | Light poles (LP1,LP2,LP3,LP4,LP5,LP6 &LP7) | 0 | 7 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-000563 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-04 | KPTG-TRANSMIT-013839 | NA | Trade Partner | Roof Hob & Plinth Drawings for Workflow 22kV | 1 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 3894 | 2026-03-16 |  | Workflow terminated This drawing is submitted through a new transmittal - RDSBIM-TRANSMIT-000238 |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-04 | DI-TRANSMIT-000151 | NA | Consultant | Fwd: Updated PPT schedule | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For information only |  |  | DRAFT-009145 | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-02 | JCBa-TRANSMIT-000213 | NA | Consultant | Drawings Removal | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated to No Longer In Use |  | 2026-03-03 | KPTG-TRANSMIT-002759 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-02 | JCBa-TRANSMIT-000214 | NA | Consultant | Drawings no longer in use | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated to No Longer In Use |  | 2026-03-03 | KPTG-TRANSMIT-002760 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-04 | RDSBIM-TRANSMIT-000238 | NA | Trade Partner | NXM3S3 - ROOF HOB AND PLINTH PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 3905 | 2026-03-16 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-02 | JCBa-TRANSMIT-000215 | NA | Consultant | Drawings no longer in use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated to No Longer In Use |  | 2026-03-03 | KPTG-TRANSMIT-002761 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-02 | JCBa-TRANSMIT-000218 | NA | Consultant | Drawings no longer in use | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated to No Longer In Use |  | 2026-03-03 | KPTG-TRANSMIT-002762 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-02 | JCBa-TRANSMIT-000220 | NA | Consultant | Drawings no longer in use | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated to No Longer In Use |  | 2026-03-03 | KPTG-TRANSMIT-002769 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-02 | JCBa-TRANSMIT-000221 | NA | Consultant | Drawings no longer in use | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated to No Longer In Use |  | 2026-03-03 | KPTG-TRANSMIT-002763 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-05 | VAE-Grp-TRANSMIT-000081 | NA | Trade Partner | MECHANICAL SERVICES- SHOP DWG - LEVEL 2 AND LEVEL 3 | 12 | 0 | 0 | NA | APPROVED | 2025-12-08 | NA | 709 | 2025-12-10 |  |  | 2025-12-09 | 2025-12-09 | KPTG-TRANSMIT-002224 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-02 | JCBa-TRANSMIT-000222 | NA | Consultant | Drawings no longer in use | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated to No Longer In Use |  | 2026-03-03 | KPTG-TRANSMIT-002764 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-02 | JCBa-TRANSMIT-000224 | NA | Consultant | Drawings no longer in use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated to No Longer In Use |  | 2026-03-03 | KPTG-TRANSMIT-002765 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-02 | JCBa-TRANSMIT-000227 | NA | Consultant | Drawings no longer in use | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated to No Longer In Use |  | 2026-03-03 | KPTG-TRANSMIT-002766 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-02 | JCBa-TRANSMIT-000229 | NA | Consultant | Drawings no longer in use | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated to No Longer In Use |  | 2026-03-03 | KPTG-TRANSMIT-002768 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-02 | JCBa-TRANSMIT-000230 | NA | Consultant | Drawings no longer in use | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated to No Longer In Use |  | 2026-03-03 | KPTG-TRANSMIT-002767 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-04 | JCBa-TRANSMIT-000233 | NA | Consultant | no longer in use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated to No Longer In Use |  | 2026-03-04 |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-04 | SMEPS-TRANSMIT-000199 | NA | Trade Partner | 22KV - Shop drawings | 14 | 0 | 0 | NA | REJECTED | [5 empty] | IFA and IFC documents are combined in one transmittal for submission |  | 2026-03-04 | KPTG-TRANSMIT-013873 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-04 | JCBa-TRANSMIT-000234 | NA | Consultant | no longer in use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated to No Longer In Use |  | 2026-03-04 |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-04 | JCBa-TRANSMIT-000235 | NA | Consultant | no longer in use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated to No Longer In Use |  | 2026-03-04 |  | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-04 | JCBa-TRANSMIT-000237 | NA | Consultant | no longer in use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated to No Longer In Use |  | 2026-03-04 |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-05 | KETE-TRANSMIT-000017 | NA | Trade Partner | Updated Thermal Report | 0 | 1 | 0 | NA | APPROVED | 2025-12-08 | NA | 713 | 2025-12-11 |  |  | 2025-12-17 | 2025-12-17 | KPTG-TRANSMIT-002306 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-04 | JCBa-TRANSMIT-000238 | NA | Consultant | no longer in use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated to No Longer In Use |  | 2026-03-04 |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-04 | SMEPS-TRANSMIT-000200 | NA | Trade Partner | 22KV - Earthing shop drawings | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFA and IFC documents are combined in one transmittal for submission |  | 2026-03-04 | KPTG-TRANSMIT-013876 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-04 | INGEN3D-TRANSMIT-000692 | NA | Consultant | I3D-378 Next DC M3 Stage 4 - Level 1 (Zone 12) - CAS4-419 - IFC (04-03-2026) | 1 | 0 | 0 | NA | APPROVED | 2026-03-04 | WF-004613 | NA | 2026-03-24 |  | TERMINATED AS PER REQUESTED BY FINLAY |  | 2026-04-27 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-04 | NXT-TRANSMIT-001365 | NA | Consultant | Fwd: ABB PDUs - AU-10025007 M3-C-Stage 4 / Ph1 - Quality Documents | 4 | 0 | 0 | NA | APPROVED | 2026-03-04 | WF-004601 | NA | 2026-03-20 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-015712 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-04 | NXT-TRANSMIT-001366 | NA | Consultant | Block C3 – IFA Shop Drawings Submission (HD,HE,HF,HG Busduct) | 5 | 0 | 0 | NA | APPROVED | 2026-03-04 | WF-004602 | NA | 2026-03-20 |  |  | 2026-03-05 | 2026-03-05 | KPTG-TRANSMIT-013899 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-08-06 | INGEN3D-TRANSMIT-000550 | NA | Consultant | Re: I3D-378 Next DC M3 Stage 4 - Level 1 (Zone 3) - Precast Panels - Revised IFC (06-08-2025) | 15 | 0 | 0 | NA | APPROVED | 2025-08-06 | WF-003223 | NA | 2026-03-04 |  |  | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-013864 | Closed | 15 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-04 | HDRAus-TRANSMIT-000418 | NA | Consultant | Nib Walls & Penos Workshop Actions | 2 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 2337 | 2026-03-06 |  |  | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-014524 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-04 | SKS Tech-TRANSMIT-000050 | NA | Trade Partner | Containment Drawings for Zone C1 | 9 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 2339 | 2026-03-12 |  | TOTAL 14 DRAWING FROM THIS TRANSMIT 5TEL DOCUMENT PLACED WORKFLOW | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-016686 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-04 | SKS Tech-TRANSMIT-000050 | NA | Trade Partner | Containment Drawings for Zone C1 | 5 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 2342 | 2026-03-12 |  | TOTAL 14 DRAWING FROM THIS TRANSMIT 9 ELC DOCUMENT PLACED WORKFLOW | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-016855 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-04 | D&E-TRANSMIT-000436 | NA | Trade Partner | NXM3S4 - Ground & Level 1 - CHW Pipe Layout - Zones - Issued For Approval | 5 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 2344 | 2026-03-12 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014816 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-05 | SKS Tech-TRANSMIT-000102 | NA | Trade Partner | ELECTRICAL SERVICES-LIGHTING LAYOUT-REFLECTED CEILING PLAN - DAY 1-GROUND LEVEL | 1 | 0 | 0 | NA | APPROVED | 2025-12-08 | NA | 705 | 2025-12-10 |  |  | 2025-12-09 | 2025-12-09 | KPTG-TRANSMIT-002220 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-04 | Entire M-TRANSMIT-000013 | NA | Trade Partner | Mechanical shop drawings re-issued for approval | 9 | 0 | 0 | NA | APPROVED | 2026-03-04 | WF-000213 | NA | 2026-03-10 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000425 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-04 | SMEPS-TRANSMIT-000125 | NA | Trade Partner | Comms Basket tech data for approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-04 | WF-000211 | NA | 2026-03-10 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-000581 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-03 | SMEPS-TRANSMIT-000124 | NA | Trade Partner | SME Shop Drawing communication IFA 1 | 1 | 0 | 0 | NA | APPROVED | 2026-03-03 | WF-000203 | NA | 2026-03-09 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-000484 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-02 | Altaire-TRANSMIT-000005 | NA | Trade Partner | Dry Fire Technical Data (For Construction / Information) (1) | 0 | 24 | 0 | NA | APPROVED | 2026-03-04 | WF-000210 | NA | 2026-03-10 |  | NA | 2026-03-13 | 2026-03-16 | KPTG-TRANSMIT-000475 | Closed | 24 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-04 | DRLL-TRANSMIT-000070 | NA | Trade Partner | Marshalling Box Drawings - NO LONGER IN USE | 69 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer in Use Drawings |  | 2026-03-04 | KPTG-TRANSMIT-002701 | Closed | 69 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-04 | HDRAus-TRANSMIT-000075 | NA | Consultant | MISSING HARDWARE SCHEDULE | 0 | 1 | 0 | KPTG-IntCorr-003112 | APPROVED |  | NA | NA |  |  | Kapitol Information only |  |  | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-04 | HDRAus-TRANSMIT-000076 | NA | Consultant | Thermal insulation requirements to DH corridor walls & screening areas | 1 | 0 | 0 | KPTG-IntCorr-003114 | APPROVED |  | NA | NA |  |  | No Action Required |  | 2026-03-20 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-11-28 | ZIA-TRANSMIT-000063 | NA | Trade Partner | CSMS ITP Level 3 Cx Document - Issued for Construction | 0 | 31 | 0 | NA | APPROVED | 2025-12-08 | WF-000843 | NA | 2025-12-15 |  |  | 2026-01-14 | 2026-01-15 | KPTG-TRANSMIT-002279 | Closed | 31 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-04 | D&E-TRANSMIT-000346 | NA | Trade Partner | L1 MANTRAP DUCT & PIPE LAYOUT + PENETRATIONS - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 1412 | 2026-03-10 |  | Voided-Requested by Ellie Salmon. There is still a couple of updates in this drawings. D & E Update and will resubmit. |  | 2026-03-06 | KPTG-TRANSMIT-002715 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-04 | WilsonPD-TRANSMIT-000021 | NA | Trade Partner | Emergency Eyewash and Monitor IFA | 0 | 1 | 0 | NA | APPROVED | 2026-03-05 | WF-000955 | NA | 2026-03-17 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-002737 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-03 | KETE-TRANSMIT-000039 | NA | Trade Partner | Submission – Steel frame connection -IFC | 35 | 0 | 0 | NA | APPROVED | 2026-03-03 | NA | 1048 | 2026-03-09 |  |  | 2026-06-19 | 2026-06-22 | KPTG-TRANSMIT-003955 | Closed | 35 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-04 | Highbu-TRANSMIT-000134 | NA | Trade Partner | Resubmission of terminated sample submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Duplicate Document, Same Document is already in Review: KPTG-SADV-003805 |  | 2026-03-04 | KPTG-SADV-003805 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-04 | Highbu-TRANSMIT-000135 | NA | Trade Partner | Resubmission of terminated sample submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | DUPLICATE DOCUMENT: SAME REVISION IS ALREADY IN REVIEW: KPTG-SADV-003806 |  | 2026-03-04 | KPTG-SADV-003806 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-04 | Highbu-TRANSMIT-000136 | NA | Trade Partner | Resubmission of terminated sample submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | DUPLICATE DOCUMENTS: SAME DOCUMENT IS STILL IN REVIEW: KPTG-SADV-003807 |  | 2026-03-04 | KPTG-SADV-003807 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-04 | Highbu-TRANSMIT-000137 | NA | Trade Partner | Resubmission of terminated submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | DUPLICATE DOCUMENTS: SAME DOCUMENT IS STILL IN REVIEW-KPTG-SADV-003808 |  | 2026-03-04 | KPTG-SADV-003808 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-04 | Auscool-TRANSMIT-000011 | NA | Trade Partner | Ground Slab - Mech Penetrations | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect Aconex document number. TP to fix and transmit again. |  | 2026-03-04 | KPTG-SADV-001204 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-04 | M.2-TRANSMIT-000009 | NA | Trade Partner | Electrical Services Basement Lighting layouts | 5 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 426 | 2026-03-11 |  |  | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-001050 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-04 | PCForm-TRANSMIT-000036 | NA | Trade Partner | Stair shop drawings | 36 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect drawing reference. |  | 2026-03-04 | KPTG-SADV-001201 | Closed | 36 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-01 | Highbu-TRANSMIT-000101 | NA | Trade Partner | Re-transmitted drawing | 1 | 0 | 0 |  | APPROVED | [5 empty] | IFC DRAWING | [6 empty] | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-08 | BASESG-IntCorr-000031 | NA | Trade Partner | L2 CRAC Script & Comment Register | 0 | 1 | 0 | NA | APPROVED | 2025-12-08 | WF-000844 | NA | 2025-12-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-04 | Highbu-TRANSMIT-000138 | NA | Trade Partner | Resubmission of terminated sample submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | DUPLICATE DOCUMENTS, SAME DOCUMENT IS STILL IN REVIEW: KPTG-SADV-003809 |  | 2026-03-04 | KPTG-SADV-003809 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-04 | Auspan-TRANSMIT-000100 | NA | Trade Partner | Precast Column Details - IFC | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update register and distribute. KPTG-TRANSMIT-000816 |  | 2026-03-04 | KPTG-TRANSMIT-000816 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-04 | Auspan-TRANSMIT-000101 | NA | Trade Partner | Update precast dowel layout for zone 3. - IFC | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update register and distribute. KPTG-TRANSMIT-000818 |  | 2026-03-04 | KPTG-TRANSMIT-000818 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-04 | Auspan-TRANSMIT-000102 | NA | Trade Partner | Precast Shop Drawings - Mech Review. Zone RFi 29 - IFC | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update register and distribute. KPTG-TRANSMIT-000820 |  | 2026-03-04 | KPTG-TRANSMIT-000820 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-04 | Auspan-TRANSMIT-000103 | NA | Trade Partner | Precast shop drawings for construction. - IFC | 15 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update register and distribute. KPTG-TRANSMIT-000822 |  | 2026-03-04 | KPTG-TRANSMIT-000822 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-03 | Duracube-TRANSMIT-000004 | NA | Trade Partner | REV C Shop Drawings | 21 | 0 | 0 |  | REJECTED | [5 empty] | Transmitted Document do not match with superseded documents in the Document Register |  | 2026-03-04 | KPTG-IntCorr-005678 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-04 | Auspan-TRANSMIT-000104 | NA | Trade Partner | Precast shop drawings for construction - IFC | 50 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update register and distribute. KPTG-TRANSMIT-000824 |  | 2026-03-04 | KPTG-TRANSMIT-000824 | Closed | 50 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-04 | Auspan-TRANSMIT-000105 | NA | Trade Partner | Update precast dowel layout for zone 1, 2, 3, 4, 5. | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update register and distribute. KPTG-TRANSMIT-000826 |  | 2026-03-04 | KPTG-TRANSMIT-000826 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-04 | Auspan-TRANSMIT-000106 | NA | Trade Partner | Resubmit precast shop drawings for approval. | 42 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 428 | 2026-03-11 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-000897 | Closed | 42 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-04 | Auspan-TRANSMIT-000107 | NA | Trade Partner | Update precast dowel layout for zone 1, 2, 3, 4, 5. - IFC | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update register and distribute. KPTG-TRANSMIT-000828 |  | 2026-03-04 | KPTG-TRANSMIT-000828 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-08 | Schindle-TRANSMIT-000010 | NA | Trade Partner | Schindler Lift 1 Transom Panel Drawing - IFA | 1 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-000659 |  | 2025-12-11 |  |  | 2025-12-08 | 2025-12-08 | KPTG-TRANSMIT-001958 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-04 | Auspan-TRANSMIT-000108 | NA | Trade Partner | - Update already IFCed shop drawings. Zone 4, 5. | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update register and distribute. KPTG-TRANSMIT-000830 |  | 2026-03-04 | KPTG-TRANSMIT-000830 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-04 | Auspan-TRANSMIT-000109 | NA | Trade Partner | Resubmit precast shop drawings for approval. Ground floor. | 6 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 430 | 2026-03-11 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-000904 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-04 | Auspan-TRANSMIT-000110 | NA | Trade Partner | Precast shop drawings for construction. Basement. | 29 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update register and distribute. KPTG-TRANSMIT-000832 |  | 2026-03-04 | KPTG-TRANSMIT-000832 | Closed | 29 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-04 | Auspan-TRANSMIT-000111 | NA | Trade Partner | Precast shop drawings for construction. Basement. | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update register and distribute. KPTG-TRANSMIT-000834 |  | 2026-03-04 | KPTG-TRANSMIT-000834 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-04 | Auspan-TRANSMIT-000112 | NA | Trade Partner | Precast shop drawings for construction. Ground floor. | 19 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update register and distribute. KPTG-TRANSMIT-000836 |  | 2026-03-04 | KPTG-TRANSMIT-000836 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-04 | Auspan-TRANSMIT-000113 | NA | Trade Partner | Resubmit precast shop drawings for approval. Ground floor | 8 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 432 | 2026-03-11 |  |  |  | 2026-03-10 | KPTG-TRANSMIT-000879 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-04 | Auspan-TRANSMIT-000114 | NA | Trade Partner | Resubmit precast shop drawings for approval. Ground floor. | 51 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 434 | 2026-03-11 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-000952 | Closed | 51 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-04 | Auspan-TRANSMIT-000115 | NA | Trade Partner | Precast shop drawings for approval. Level 1. | 35 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 436 | 2026-03-11 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-000961 | Closed | 35 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-04 | Auspan-TRANSMIT-000116 | NA | Trade Partner | Precast shop drawings for construction. Ground floor. | 18 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update register and distribute. KPTG-TRANSMIT-000838 |  | 2026-03-04 | KPTG-TRANSMIT-000838 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-03 | Ardon-IntCorr-000001 (LG)-(PRCDOORS) | NA | Trade Partner | PMDF Shop Drawings GF, L1, L2 & L3 | 18 | 0 | 0 | NA | APPROVED | 2026-03-03 | NA | 1036 | 2026-03-09 |  |  |  | 2026-03-18 | KPTG-TRANSMIT-003129 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-08 | ECBS-TRANSMIT-000038 | NA | Trade Partner | Technical Data Submission for Review | 0 | 8 | 0 | NA | APPROVED | 2025-12-08 | WF-000660 |  | 2025-12-11 |  |  |  | 2026-01-15 | KPTG-TRANSMIT-002085 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-04 | Auspan-TRANSMIT-000117 | NA | Trade Partner | Update already IFCed shop drawings. Basement. | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update register and distribute. KPTG-TRANSMIT-000840 |  | 2026-03-04 | KPTG-TRANSMIT-000840 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-03 | Ardon-IntCorr-000001 (G)-(PRCDOORS) | NA | Trade Partner | PMDF Shop Drawings GF, L1, L2 & L3 | 40 | 0 | 0 | NA | APPROVED | 2026-03-03 | NA | 1047 | 2026-03-09 |  | close out process on 10-04-2026 due to VPN issue | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-003374 | Closed | 40 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-03 | Ardon-IntCorr-000001 (L1)-(PRCDOORS) | NA | Trade Partner | PMDF Shop Drawings GF, L1, L2 & L3 | 9 | 0 | 0 | NA | APPROVED | 2026-03-03 | NA | 1054 | 2026-03-09 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-003459 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-03 | Ardon-IntCorr-000001 (L2)-(PRCDOORS) | NA | Trade Partner | PMDF Shop Drawings GF, L1, L2 & L3 | 9 | 0 | 0 | NA | APPROVED | 2026-03-03 | NA | 1038 | 2026-03-09 |  |  | 2026-04-14 | 2026-04-21 | KPTG-TRANSMIT-003467 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-03 | Ardon-IntCorr-000001 (L3)-(PRCDOORS) | NA | Trade Partner | PMDF Shop Drawings GF, L1, L2 & L3 | 9 | 0 | 0 | NA | APPROVED | 2026-03-03 | NA | 1040 | 2026-03-09 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-003463 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-03 | PARR-TRANSMIT-000042 | NA | Trade Partner | Fuel Services - FUEL RETICULATION L4 & L5 GA - IFC | 1 | 0 | 0 | NA | APPROVED | 2026-03-03 | NA | 1042 | 2026-03-04 |  |  |  | 2026-03-04 | KPTG-TRANSMIT-003051 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-03 | Hames-TRANSMIT-000127 | NA | Consultant | Latest door hardware schedule-IFC | 0 | 1 | 0 | NA | APPROVED | 2026-03-03 | NA | 1052 | 2026-03-05 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-003078 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-03 | Hames-TRANSMIT-000128 | NA | Consultant | Certifier Updated Drawings & Threshold Report | 15 | 0 | 0 | Rejected: KPTG-IntCorr-001049 | REJECTED | [5 empty] | Rejected, QA ERROR |  | 2026-03-03 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-03 | ACG-TRANSMIT-000018 | NA | Trade Partner | Electronic Security ITP | 0 | 1 | 0 | KPTG-IntCorr-001050 | APPROVED |  | NA | NA |  |  | Clarification from Harry |  | 2026-06-24 | KPTG-IntCorr-001549 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-04 | RBG-TRANSMIT-000056 | NA | Consultant | Structural Drawings for the Tower Steelwork - Issued for Certification | 7 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 312 | 2026-03-06 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-000724 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-08 | M.S.-TRANSMIT-000034 | NA | Trade Partner | IFA shop drawings for J53, J80, J81, J82, J83, J84 & J41C | 15 | 0 | 0 | NA | APPROVED | 2025-12-08 |  | 372 | 2025-12-15 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-04 | RDSBIM-TRANSMIT-000037 | NA | Consultant | 671CHP ¦ LEVEL 01 CONCRETE PROFILE PLAN AND SECTION | 3 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 316 | 2026-03-06 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-000728 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-04 | Jangho-TRANSMIT-000013 | NA | Trade Partner | Chapel St Project VMU NO.1 SHOP DRAWINGS Rev.00 | 20 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 314 | 2026-03-11 |  | Review voided; drawings to be superseded by Jangho |  | 2026-04-28 | NA | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-04 | fjc-TRANSMIT-000137 | NA | Consultant | Architecturals - EOT + Concrete Profiles | 9 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 587 | 2026-03-11 |  |  | 2026-03-06 | 2026-03-06 | KPTG-SADV-003333 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-04 | Auscool-TRANSMIT-000086 | NA | Trade Partner | Basement Plinth layout | 1 | 0 | 0 | NA | APPROVED | [5 empty] | IFC DRAWING: TRANSMITTED TO TRADE AND CONSULTANTS & CLIENTS |  | 2026-03-04 | KPTG-TRANSMIT-001945 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-04 | Highbu-TRANSMIT-000043 | NA | Trade Partner | HPS-HY-SMP-044 - Rehau for DCW, DHW & RW & HPS-HY-SMP-045 - TAP6 - Mezz EOT vanity basin taps (2 x options) for approval | 0 | 2 | 0 |  | APPROVED | 2026-03-05 | WF-000649 | NA | 2026-03-12 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-001990 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-04 | AFAC-TRANSMIT-000003 | NA | Consultant | Lindrum Facade Access Report & Dwgs | 10 | 0 | 0 | KPTG-IntCorr-000777 | APPROVED |  | NA | NA |  |  | Requested to kapitol to confirm if any action is required on these drawings: KPTG-IntCorr-000777 TRANSMITTD TO 3 PARTIES. | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-002039 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-04 | PSGANZ-TRANSMIT-000008 | NA | Trade Partner | PREM-FR-SMP-014 Fire Curtain | 0 | 1 | 0 | NA | APPROVED | 2026-03-04 | WF-000646 | NA | 2026-03-11 |  | As per the direction from the Mr. Mark, Workflow is created | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-002048 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-05 | INGEN3D-TRANSMIT-000694 | NA | Consultant | I3D-378 Next DC M3 Stage 4 - Acoustic Wall - IFA Checked (04-03-2026) | 6 | 0 | 0 | NA | APPROVED | 2026-03-05 | WF-004634 | NA | 2026-03-31 |  | rejected due to the IFA and IFC documents were submitted in the same transmittal,AS PER ADVISE FROM OLIVER ITS 4 IFC DOCUMENTS PLACED IN WORK FLOW | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-014720 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-04 | Entire M-TRANSMIT-000004 | NA | Trade Partner | Mechanical shop drawings issued for approval | 16 | 0 | 0 |  | REJECTED | [5 empty] | Wrong Document Numbering and Drawing status is not mentioned in the drawing, requested to Resubmi: KPTG-IntCorr-000085 |  | 2026-03-05 | KPTG-IntCorr-000085 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-04 | Auspan-TRANSMIT-000119 | NA | Trade Partner | Update IFC shop drawings for construction | 26 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. Updated document register and ACC. |  | 2026-03-04 | NA | Closed | 26 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-08 | PROLMC-TRANSMIT-000017 | NA | Trade Partner | GRC Shop Drawings (8/12/25) | 29 | 0 | 0 | NA | REJECTED | [5 empty] | DRAWING ARE SUBMITTED WITH WRONG DOCUMENT NUMBER |  | 2025-12-08 | KPTG-SADV-003043 | Closed | 29 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-04 | EFP-TRANSMIT-000010 | NA | Trade Partner | FIRE SERVICES SHOP DRAWINGS IFA | 8 | 0 | 0 |  | APPROVED | 2026-03-05 | WF-000035 | NA | 2026-03-11 |  | QA checking is in progress. | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-000109 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-04 | Appselec-TRANSMIT-000018 | NA | Trade Partner | Communications Tech Data For Approval | 0 | 3 | 0 | NA | APPROVED | 2026-03-13 | WF-000051 | NA | 2026-03-16 |  |  | 2026-03-19 | 2026-03-25 | KPTG-TRANSMIT-000174,KPTG-TRANSMIT-000181,KPTG-TRANSMIT-000196 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-04 | Auspan-TRANSMIT-000114 | NA | Trade Partner | Precast shop drawings for approval. Stage 9 level 1. | 14 | 0 | 0 | NA | APPROVED | 2026-03-04 | WF-000286 | NA | 2026-03-09 |  | Originally the Transmittal received on 26/02 and workflow initiated by Kapitol PC on 27/02. Workflow Transmittal GEMBA-D-WTRAN-000104 received on 04/03/26 and Transmittal Close out completed by DC on 04/03/26 | 2026-03-04 | 2026-03-04 | KPTG-TRANSMIT-001159 | Closed | 14 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-05 | NXT-TRANSMIT-001368 | NA | Trade Partner | Bulk tank access platform layout & details | 1 | 0 | 0 | NA | APPROVED | 2026-03-05 | WF-004623 | NA | 2026-03-18 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018336 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-04 | TATE_-TRANSMIT-000024 | NA | Trade Partner | MEL05 COLO 4 SCEC WALL IFC | 9 | 0 | 0 | NA | APPROVED | 2026-03-04 | WF - 000214 | NA | 2026-03-09 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-000400 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-02-26 | Altaire-TRANSMIT-000004 | NA | Trade Partner | MEL05C4 - Dry Fire Shop Drawings (For Information) (1) | 2 | 0 | 0 | NA | APPROVED | 2026-03-03 | WF - 000207 | NA | 2026-03-10 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000431 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-05 | KALLIBRE-TRANSMIT-000002 | NA | Trade Partner | Re: HANWHA Building 18 - Door Frame Shop Drawings For Review | 1 | 0 | 0 | NA | REJECTED | [5 empty] | The Document reference number is not aligned with the Hanwha project. |  | 2026-03-05 | KALLIBRE-TRANSMIT-000001 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-05 | RDSBIM-TRANSMIT-000003 | NA | Trade Partner | ¦ LEVEL 02 COLO 04 AREA PARTITION WALL ENLARGED LAYOUT | 3 | 0 | 0 | NA | APPROVED | 2026-03-05 | WF-000215 | NA | 2026-03-11 |  | NA | 2026-03-10 | 2026-03-18 | KPTG-TRANSMIT-000510 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-04 | ASV-TRANSMIT-000153 | NA | Trade Partner | Hydraulic Samples for Review | 0 | 8 | 0 | NA | APPROVED | 2026-03-05 | WF-004625 | NA | 2026-03-23 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014330 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-04 | IGS--TRANSMIT-000031 | NA | Consultant | Revised Building Services Layouts | 20 | 0 | 0 | NA | REJECTED | 2026-04-27 | NA | 635 | 2026-04-30 |  | The Dwfx file is not shared to us, requested to retransmit all these drawings along with dwfx. KPTG-SADV-003304 The revision number is C2, but in the revision history box it is shown as C1 (22101-F106)-KPTG-SADV-003390 |  | 2026-03-04 | KPTG-SADV-003304 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-08 | ECBS-TRANSMIT-000039 | NA | Trade Partner | RippleSound shop drawings for review | 3 | 0 | 0 | NA | REJECTED | [5 empty] | DRAWINGS ARE COMBINED WITH SUB DRAWINGS |  | 2025-12-08 | KPTG-SADV-003064 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-04 | HGP-TRANSMIT-000047 | NA | Trade Partner | Transmittal-LOUVRES Shop Drawing For APPROVAL | 14 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 153 | 2026-03-05 |  | Terminated as per Moj advise | 2026-03-12 | 2026-03-11 | NA | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-05 | KAPITOL-TRANSMIT-001169 | NA | Trade Partner | HFF - Louvre Shop Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 334 | 2026-03-11 |  |  | 2026-03-12 | 2026-03-12 | DRAFT-009287 | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-05 | D&E-TRANSMIT-000440 | NA | Trade Partner | BMS Schedules - Issued for Approval | 2 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-03-05 | KPTG-TRANSMIT-013888 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-05 | IDS-TRANSMIT-000013 | NA | Trade Partner | Wet Fire - HFF GROUND LEVEL ZONE 1 & 2 | 1 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 335 | 2026-03-18 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-05 | IDS-TRANSMIT-000014 | NA | Trade Partner | Dry Fire - HFF GROUND ZONE 1 & 2 | 1 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 336 | 2026-03-18 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-11-11 | WilsonPD-TRANSMIT-000116 | SPARK-CRFI-KPG-000343 | Trade Partner | IFA Fixture (Care Backrest F.TAC-04) | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-05 | KPTG-TRANSMIT-000503 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-05 | D&E-TRANSMIT-000141 | SPARK-CRFI-KPG-000569 | Trade Partner | MWYCCB - GROUND LEVEL - RCP LAYOUT ZONES MECHANICAL SERVICES - Issued For Approval | 3 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 154 | 2026-03-12 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-000561 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-05 | KALLIBRE-TRANSMIT-000003 | NA | Trade Partner | Re: HANWHA Building 18 - Door Frame Shop Drawings For Review | 1 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 337 * new WF 345 | 2026-03-11 |  | The WF 337 has been closed but Isaiah asked to put it in a WEB review again . |  | 2026-03-11 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-05 | IDS-TRANSMIT-000015 | NA | Trade Partner | Wet Fire - Buidling B18 - HFF GROUND LEVEL ZONE 1 & 2 | 1 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 342 | 2026-03-18 |  |  | 2026-03-10 | 2026-03-10 | DRAFT-009222 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-08 | ZIA-TRANSMIT-000066 | NA | Trade Partner | CSMS Drawings Submission, Network diagram, Roof & Roof Plant Sensor Location | 3 | 0 | 0 | NA | APPROVED | 2025-12-08 | NA | 1294 | 2025-12-17 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-002731 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-03 | TTW-TRANSMIT-000099 | NA | Consultant | Structural Documentation - Issued for Certification | 15 | 0 | 0 | NA | APPROVED | 2026-03-03 | NA | 294 | 2026-03-05 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-000727 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-03 | PCForm-TRANSMIT-000081 | NA | Trade Partner | Precast caulking sample submission - Pascoe FireJoint PU | 0 | 1 | 0 | NA | APPROVED | 2026-03-03 | WF-000202 | NA | 2026-03-06 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000686 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-05 | LANSA-TRANSMIT-000097 | NA | Trade Partner | Updated Water Drawings IFC | 14 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2026-03-05 | KPTG-TRANSMIT-002791 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-03 | Civilex-TRANSMIT-000036 | NA | Trade Partner | Waterproofing for Raft 4 and 5 | 0 | 1 | 0 | NA | APPROVED | 2026-03-03 | WF-000203 | NA | 2026-03-05 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-000756 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-03 | Civilex-TRANSMIT-000038 | NA | Trade Partner | Alimak Design Addendum | 0 | 1 | 0 | NA | APPROVED | 2026-03-03 | WF-000204 | NA | 2026-03-05 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-000736 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-05 | HIP-TRANSMIT-000010 | NA | Trade Partner | Re: Building - 08 - Variation - RGV Rails - Issue For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 241 | 2026-03-08 |  | The drawings are locked in the WF generated by Kapitol. We are unable to update the register and are waiting for a response from Kapitol – KAPITOL-INTCOR-001110 - Reply -KAPITOL-INTCOR-001113 |  | 2026-03-06 | DRAFT-009192 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-03 | RED Fire-TRANSMIT-000006 | NA | Consultant | Fire Compartmentation Drawings | 18 | 0 | 0 | NA | APPROVED | 2026-03-03 | NA | 298 | 2026-03-08 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-000966 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-03 | TTW-TRANSMIT-000101 | NA | Consultant | Facade Specification_Rev T5 | 0 | 1 | 0 | rejected -KPTG-TRANSMIT-000622 | APPROVED | [7 empty] | 2026-03-17 | KPTG-TRANSMIT-000786 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-03 | PCForm-TRANSMIT-000089 | NA | Trade Partner | Omniform coventional column formwork design | 1 | 0 | 0 | Clarification send to Nich - KPTG-IntCorr-000427 | APPROVED | [5 empty] | Register updated as instructed by Nich |  | 2026-03-04 | KPTG-IntCorr-000429 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-05 | HIP-TRANSMIT-000011 | NA | Trade Partner | Re: Building - 08 - Variation - Marking Plan - Issued For Review | 1 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 340 | 2026-03-18 |  | The drawings are locked in the WF generated by Kapitol. We are unable to update the register and are waiting for a response from Kapitol – KAPITOL-INTCOR-001111 |  | 2026-03-06 | DRAFT-009191 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-09 | ADP-TRANSMIT-000144 | NA | Consultant | MEL741 - Stage 4 Services IFT Issue | 1 | 0 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. -KPTG-TRANSMIT-010728 |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-05 | D&E-TRANSMIT-000442 | NA | Trade Partner | Fwd: BMS Schedules - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-06 | WF-004653 | NA | 2026-03-27 |  | SCH - for info - KPTG-TRANSMIT-013891 | 2026-03-23 | 2026-03-16 | KPTG-TRANSMIT-014833 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-04 | Civilex-TRANSMIT-000039 | NA | Trade Partner | Sample Resubmission - SMP-005 | 0 | 1 | 0 | NA | APPROVED | 2026-03-04 | WF-000208 | NA | 2026-03-07 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000718 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-05 | DI-TRANSMIT-000152 | NA | Trade Partner | PPT - Updated Demolition Plan | 1 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 339 | 2026-03-09 |  |  | 2026-03-10 | 2026-03-10 | KAPITOL-TRANSMIT-001191 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-05 | NXT-TRANSMIT-001371 | NA | Trade Partner | Block C3 – IFA Shop Drawings Submission (FI&FJ Catcher,Loadbank,HH,HI,HJ Busduct) | 6 | 0 | 0 | NA | APPROVED | 2026-03-05 | WF-004631 | NA | 2026-03-23 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-013995 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-04 | INGEN3D-TRANSMIT-000010 | NA | Trade Partner | Ground Floor (Level 1) - Precast Columns - IFA | 101 | 0 | 0 | NA | APPROVED | 2026-03-04 | WF-000206 | NA | 2026-03-07 |  | final transmit sent on 19/03/2026 - 10 dwgs hold by Victoria - KPTG-IntCorr-000510 | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-000930 | Closed | 101 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-04 | D&E-TRANSMIT-000004 | NA | Trade Partner | Outside Air Fan & Sound Attenuators Tech. Data | 0 | 1 | 0 | NA | APPROVED | 2026-03-04 | WF-000162 | NA |  |  |  | 2026-03-05 | 2026-03-05 | KPTG-TRANSMIT-000654 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-04 | WAM-TRANSMIT-000721 | NA | Consultant | WAM ARCH - 95% DD Update - Facade Plans | 30 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 300 | 2026-03-09 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000680 | Closed | 30 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-05 | D&E-TRANSMIT-000443 | NA | Trade Partner | Fwd: BMS Schedules - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-06 | WF-004654 | NA | 2026-03-27 |  | SCH - for info - KPTG-TRANSMIT-013894 |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-05 | KPTG-Intcorr-000477 | NA | Consultant | Electrical Specification - ELC | 0 | 1 | 0 | NA | APPROVED | 2026-03-05 | NA | 400 | 2026-03-11 |  | In KPTG-Intcorr-000477 have 7 documents submitted by discipline | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-001615 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-05 | KPTG-Intcorr-000477 | NA | Consultant | TELECOMMUNICATION SPECIFICATION-TEL | 0 | 1 | 0 | NA | APPROVED | 2026-03-05 | NA | 401 | 2026-03-11 |  |  | 2026-03-22 | 2026-03-24 | KPTG-TRANSMIT-001611 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-09 | JCBa-TRANSMIT-000042 | NA | Consultant | GA cad files for all overall | 10 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-000086 | 164 | 2025-12-12 |  |  |  | 2025-12-10 | KPTG-TRANSMIT-000298 | Closed | 10 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-05 | KPTG-Intcorr-000477 | NA | Consultant | MECHANICAL SPECIFICATION-MEC | 0 | 1 | 0 | NA | APPROVED | 2026-03-05 | NA | 402 | 2026-03-11 |  |  | 2026-03-24 | 2026-03-25 | KPTG-TRANSMIT-001660 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-05 | Baigents-TRANSMIT-000070 | SPARK-CRFI-KPG-000360 | Trade Partner | Site Storage - Car Port - Issued For Approval | 67 | 0 | 0 | DRAFT-006099 | APPROVED | 2026-03-05 | NA | 155 | 2026-03-12 |  | 2 drawings Updated | 2026-07-24 | 2026-07-24 | KPTG-TRANSMIT-001490 | Closed | 64 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-05 | KPTG-Intcorr-000477 | NA | Consultant | HYDRAULIC SPECIFICATION-HYD | 0 | 1 | 0 | NA | APPROVED | 2026-03-05 | NA | 403 | 2026-03-11 |  |  | 2026-03-24 | 2026-03-25 | KPTG-TRANSMIT-001677 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-05 | KPTG-Intcorr-000477 | NA | Consultant | FUEL SYSTEM SPECIFICATION-FUL | 0 | 1 | 0 | NA | APPROVED | 2026-03-05 | NA | 404 | 2026-03-11 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-001561 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-05 | KPTG-Intcorr-000477 | NA | Consultant | FIRE SERVICE SPECIFICATION-FIP | 0 | 1 | 0 | NA | APPROVED | 2026-03-05 | NA | 405 | 2026-03-11 |  |  | 2026-03-19 | 2026-03-20 | KPTG-TRANSMIT-001590 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-04 | D&E-TRANSMIT-000139 | NA | Trade Partner | Mechanical Switchboard Drawings | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision number |  | 2026-03-06 | KPTG-TRANSMIT-000504 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-05 | KPTG-Intcorr-000477 | NA | Consultant | VERTICAL TRANSPORTATION-VRT | 0 | 1 | 0 | NA | APPROVED | 2026-03-05 | NA | 406 | 2026-03-11 |  |  | 2026-03-22 | 2026-03-23 | KPTG-TRANSMIT-001595 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-04 | SKS Tech-TRANSMIT-000161 | NA | Trade Partner | LEVEL 4 & 5 COMMS IFC UPDATE | 2 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 1074 | 2026-03-06 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-003198 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-04 | ZIA-TRANSMIT-000027 | NA | Trade Partner | CSMS Outstation D1.B-LD-OS-01 - For Construction | 11 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 1060 | 2026-03-09 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-003555 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-04 | ZIA-TRANSMIT-000028 | NA | Trade Partner | CSMS Outstation D1.B-GF-OS-01 - Drawings For Construction | 10 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 1062 | 2026-03-10 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-003545 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-09 | Rinco-TRANSMIT-000024 | NA | Consultant | Structural Drawings - L1 PT & Reinforcement for Review | 28 | 0 | 0 | NA | APPROVED | 2025-12-09 | WF-000087 | 166 | 2025-12-12 |  |  |  | 2025-12-12 | KPTG-TRANSMIT-000327 | Closed | 28 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-04 | ZIA-TRANSMIT-000029 | NA | Trade Partner | CSMS Outstation D1.B-GF-OS-02 - Drawings For Construction | 11 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 1064 | 2026-03-10 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-003544 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-04 | ZIA-TRANSMIT-000030 | NA | Trade Partner | CSMS Outstation D1.B-L4-OS-A- Drawings For Construction | 10 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 1066 | 2026-03-10 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-003543 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-04 | D&E-TRANSMIT-000005 | NA | Trade Partner | Outside Air Fan & Sound Attenuators Tech. Data | 0 | 1 | 0 | rejected -KPTG-SADV-001055 | REJECTED | [5 empty] | rejected, Qa error without cover sheet |  | 2026-03-05 | KPTG-SADV-001055 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-04 | ZIA-TRANSMIT-000031 | NA | Trade Partner | CSMS Outstation D1.B-L4-OS-B- Drawings For Construction | 10 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 1068 | 2026-03-10 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-003539 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-04 | ZIA-TRANSMIT-000032 | NA | Trade Partner | CSMS Outstation D1.B-L4-OS-C- Drawings For Construction | 10 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 1070 | 2026-03-10 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-003538 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-04 | SKS Tech-TRANSMIT-000162 | NA | Trade Partner | GROUND FLOOR SEISMIC LAYOUTS | 2 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 1076,1078 | 2026-03-06 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-003188 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-05 | SMEPS-TRANSMIT-000123 | NA | Trade Partner | Fwd: Seismic Restraint | 0 | 1 | 0 | KPTG-IntCorr-002005 | REJECTED | [5 empty] | Already received in SMEPS-TRANSMIT-000121 - KPTG-IntCorr-002043 |  | 2026-03-10 | KPTG-IntCorr-002005 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-04 | RDSBIM-TRANSMIT-000063 | NA | Trade Partner | LEVEL 02 RCP KEY PLAN AND LAYOUT | 5 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 1084 | 2026-03-10 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-003318 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-04 | SKS Tech-TRANSMIT-000165 | NA | Trade Partner | LEVEL 5 PENETRATIONS IFC LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 1082 | 2026-03-06 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-003180 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-01 | Fredon T-TRANSMIT-000005 | NA | Trade Partner | Surface Mount Speaker - Pool Side - Tech Data | 0 | 1 | 0 |  | REJECTED | [5 empty] | Requested to resubmit | [6 empty] | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2025-12-09 | TATE_-TRANSMIT-000019 | NA | Trade Partner | updated HAC shop drawings | 4 | 0 | 0 | NA | APPROVED | 2025-12-09 |  | 1300 | 2025-12-15 |  |  |  | 2025-12-19 | KPTG-TRANSMIT-000663 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-05 | D&E-TRANSMIT-000445 | NA | Trade Partner | Re: MCC Schedules IFA Rev E | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-03-05 | KPTG-TRANSMIT-013900 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-04 | SKS Tech-TRANSMIT-000164 | NA | Trade Partner | EARTHING SCHEMATIC IFC | 1 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 1080 | 2026-03-06 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-003184 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-04 | Hames-TRANSMIT-000129 | NA | Consultant | Performance Solution Thresholds | 0 | 1 | 0 | NA | APPROVED | 2026-03-04 | WF-000870 | NA | 2026-03-06 |  |  |  | 2026-03-05 | rejected by terminating | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-05 | SMEPS-TRANSMIT-000124 | NA | Trade Partner | Fwd: Light poles (LP1,LP2,LP3,LP4,LP5,LP6 &LP7) | 0 | 7 | 0 | KPTG-IntCorr-002006 | APPROVED |  | NA | NA |  |  | Already received SMEPS-TRANSMIT-000122 - No Action - KPTG-IntCorr-002170 |  | 2026-03-13 |  | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-03 | PARR-TRANSMIT-000043 | NA | Trade Partner | Fuel Services - FUEL RETICULATION L4 & L5 GA - IFC | 1 | 0 | 0 | NA | APPROVED | 2026-03-03 | NA | 1044 | 2026-03-04 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-003210 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-03 | Jordan-TRANSMIT-000120 | NA | Trade Partner | Level 4 - Plumbing Drainage - For Construction | 1 | 0 | 0 | Rejected : KPTG-IntCorr-001052 | REJECTED | [5 empty] | Rejected : Qa error |  |  | KPTG-IntCorr-001052 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-05 | KPTG-WTRAN-008505 | NA | Trade Partner | Basement Access Ladder Plan | 0 | 3 | 0 | NA | APPROVED | 2026-03-05 | WF-004638 | NA | 2026-04-13 |  | The WF has been generated as requested by Sam S | 2026-03-12 | 2026-03-12 | KPTG-IntCorr-010631 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-05 | Entire M-TRANSMIT-000042 | NA | Trade Partner | Security Grilles Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-03-05 | WF-004626 | NA | 2026-03-26 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-015280 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-05 | D&E-TRANSMIT-000142 | SPARK-CRFI-KPG-000315 | Trade Partner | MWYCCB - LEVEL 1 - PENETRATION LAYOUT ZONE 1 & ZONE 3 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 156 | 2026-03-12 |  |  | 2026-03-16 | 2026-04-24 | KPTG-TRANSMIT-000712 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-05 | Entire M-TRANSMIT-000041 | NA | Trade Partner | Mechanical Switchboard Drawings Issued for Construction | 2 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-03-05 | KPTG-TRANSMIT-013906 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-08 | VIA Arch-TRANSMIT-000029 | NA | Consultant | IFT - STAGE 0901 - Wall Setout - BOH Wall Type Change | 1 | 0 | 0 | NA | APPROVED | 2025-12-09 |  | 120 | 2025-12-12 |  |  | 2025-12-12 | 2025-12-13 | KPTG-TRANSMIT-000334 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-05 | WilsonPD-TRANSMIT-000166 | SPARK-CRFI-KPG-000568 | Trade Partner | Basin Mixer (F.TAP-03) | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-18 | KPTG-TRANSMIT-000552 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-03 | ACG-TRANSMIT-000019 | NA | Trade Partner | Electronic Security Camera field of view register | 0 | 1 | 0 | KPTG-IntCorr-001051 | APPROVED |  | NA | NA |  |  | Clarification from Harry - forwarded to NEXTDC for information |  | 2026-06-24 | KPTG-TRANSMIT-003980 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-05 | ACG-TRANSMIT-000065 | NA | Trade Partner | M3 - Stage 4 Internal Drawings IFA Revision | 14 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 2359 | 2026-03-11 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-017165 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-05 | Nilsen3-TRANSMIT-000054 | NA | Trade Partner | NXM3S3 ¦ Nilsen ELC Shop Drawings - FOA #1 | 9 | 0 | 0 | NA | APPROVED | 2026-03-05 | WF-004639 | NA | 2026-03-18 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-05 | SMEPS-TRANSMIT-000201 | NA | Trade Partner | 22KV - Shop drawings IFA | 7 | 0 | 0 | NA | APPROVED | 2026-03-06 | WF-004662 | NA | 2026-03-19 |  | Internal MEMO - waiting for Kina's reply | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-014754 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-05 | SMEPS-TRANSMIT-000202 | NA | Trade Partner | 22KV - Shop drawings IFC | 16 | 0 | 0 | NA | APPROVED | 2026-03-06 | WF-004663 | NA | 2026-03-11 |  | Internal MEMO - waiting for Kina's reply |  |  | KPTG-TRANSMIT-014750 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-05 | RDSBIM-TRANSMIT-000030 | NA | Trade Partner | GREYSTAR GROUND FLOOR CONCRETE PROFILE KEY PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 454 | 2026-03-11 |  | Revised & Resubmit - No Published required, | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-000925 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-05 | RDSBIM-TRANSMIT-000031 | NA | Trade Partner | GREYSTAR GROUND FLOOR CONCRETE PROFILE PLAN AND SECTION | 7 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 467 | 2026-03-13 |  | #456 is void and new consultant review 467 initiated on 6/6/26. | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-000922 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-05 | Auspan-TRANSMIT-000118 | NA | Trade Partner | Precast shop drawings for approval. Ground floor | 14 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 451 | 2026-03-12 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-000956 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-05 | Auspan-TRANSMIT-000119 | NA | Trade Partner | Precast shop drawings for construction. Ground floor. | 32 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Update register and distribute. KPTG-TRANSMIT-000843 |  | 2026-03-05 | KPTG-TRANSMIT-000843 | Closed | 32 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-09 | PPX-TRANSMIT-000013 | NA | Trade Partner | NEXTDC M3 – SMARDT CHILLERS - FD - 2025 | 0 | 1 | 0 | NA | APPROVED | 2025-12-09 | WF-000847 | NA | 2025-12-16 |  |  | 2026-01-21 | 2026-01-21 | KPTG-TRANSMIT-002313 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-05 | Auscool-TRANSMIT-000012 | NA | Trade Partner | Ground Slab - Mech Penetrations | 10 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 458 | 2026-03-12 |  | Review Void as new revision of drawings ready to issue for review. As advised by DM, review is void. KPTG-DA-000865 | 2026-03-12 | 2026-03-12 | KPTG-DA-000865 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-05 | M.2-TRANSMIT-000008 | NA | Trade Partner | Electrical Services Ground floor penetration layouts | 5 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 461 | 2026-03-12 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-001138 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-05 | POTTSENG-TRANSMIT-000010: | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONES 3-5 LAYOUTS | 3 | 3 | 0 | NA | APPROVED | 2026-03-05 | NA | 463 | 2026-03-11 |  | Rejected; not to publish. | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-000951 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-05 | NXT-TRANSMIT-001373 | NA | Client | Re-submitting UPS Sys Wiring Diagram | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | These documents are for distribution. The distribution list has been requested via the transmittal KPTG-TRANSMIT-013901 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-05 | D&E-TRANSMIT-000439 | NA | Trade Partner | NXM3S4 - Level 1 - Builders Works Layout Zones 8 & 9 & 10 - Issued For Approval | 3 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 2354 | 2026-03-13 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-015216 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-05 | ECBS-TRANSMIT-000026 | NA | Trade Partner | M3 S3 22KV - Tech data for approval | 0 | 4 | 0 | NA | APPROVED | 2026-03-05 | WF-004643 | NA | 2026-03-18 |  |  | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-014516 | Open | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-05 | D&E-TRANSMIT-000438 | NA | Trade Partner | NXM3S4 - Ground - Builders Works Layout - Zone 10 - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 2350 | 2026-03-13 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014797 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-05 | KPTG-TRANSMIT-013885 | NA | Consultant | S4 - Proline Shop Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 2348 | 2026-03-16 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-015004 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-05 | ADP-TRANSMIT-000263 | NA | Consultant | Re - MEL741 - Stage 4 Combined Services IFC Issue | 19 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 2346 | 2026-03-09 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-013942 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-05 | Endfire-TRANSMIT-000069 | NA | Trade Partner | WATER MIST IFC DRAWINGS | 3 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 1092 | 2026-03-11 |  |  |  | 2026-03-11 | KPTG-TRANSMIT-003110 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-09 | TATE_-TRANSMIT-000031 | NA | Trade Partner | Slidable Adjustable Panel drawings | 2 | 0 | 0 | NA | APPROVED | 2025-12-09 | NA | 1301 | 2025-12-17 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-05 | SKS Tech-TRANSMIT-000166 | NA | Trade Partner | LEVEL 4 PENETRATIONS IFC UPDATE | 1 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 1096 | 2026-03-11 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-003161 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-05 | RDSBIM-TRANSMIT-000171 | NA | Trade Partner | ROOF CPP ¦ IFC ¦ SUBMISSION | 4 | 0 | 0 | NA | APPROVED |  | NA | MA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2026-03-05 | KPTG-TRANSMIT-002793 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-05 | RDSBIM-TRANSMIT-000240 | NA | Trade Partner | Re: NXM3S3 ¦ ROOF HOB AND PLINTH PLAN | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect revision |  | 2026-03-05 | KPTG-TRANSMIT-013927 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-05 | Highbu-TRANSMIT-000139 | NA | Trade Partner | HP-PM-TEC-051 - Stainless steel pool cold water hose tap sample submission | 0 | 1 | 0 | NA | APPROVED | 2026-03-05 | WF-000862 | NA | 2026-03-10 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-002516 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-05 | RDSBIM-TRANSMIT-000115 | NA | Trade Partner | MLCSPR ¦ AQUATIC CENTRE WEST - LANDSCAPE | 1 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 456 | 2026-03-12 |  |  | 2026-03-17 | 2026-03-17 | KPTG-SADV-003890 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-03 | KPTG-IntCorr-001583 | NA | Trade Partner | Various samples | 0 | 4 | 0 | NA | APPROVED | 2026-03-04 | WF 000958 ,WF 000959, WF 000960 WF 000961 | NA | 2026-03-09 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-05 | ARCH-TRANSMIT-000140 | NA | Trade Partner | MLC - SPR - Drawing update | 12 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 455 | 2026-03-12 |  |  | 2026-03-13 | 2026-03-13 | KPTG-SADV-003863 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-05 | ECBS-TRANSMIT-000076 | NA | Trade Partner | 2nd submission for pool Bulkhead Top Sealant - Tech data for Review | 0 | 1 | 0 | NA | APPROVED | 2026-03-05 | WF-000864 | NA | 2026-03-11 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-002522 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-05 | Auspan-TRANSMIT-000058 | NA | Trade Partner | Shop drawings issued for construction | 15 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 589 | 2026-03-12 |  |  | 2026-03-06 | 2026-03-06 | KPTG-SADV-003334 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-09 | Nilsen3-TRANSMIT-000117 | NA | Trade Partner | Nilsen Material Tech Data & Procurement Tracking | 0 | 7 | 0 | NA | APPROVED |  | NA |  |  |  | IFCs, No review required. Distributed to the project team. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-05 | NDY-TRANSMIT-000020 | NA | Trade Partner | Lighting Foyer Drawings For Information | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Action is required, transmitted to Trade partners:KPTG-TRANSMIT-001950 |  | 2026-03-05 | KPTG-TRANSMIT-001950 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-05 | MLAW-TRANSMIT-000001 | NA | Trade Partner | THERMACORD - SLIDING DOORS - TYPICAL DETAILS | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per the direction from the Ms Elisa te, No Review is required, just forwarded to FjC consultants |  | 2026-03-05 | KPTG-TRANSMIT-001952 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-05 | PARR-TRANSMIT-000130 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - bulk fuel system reticulation drawings | 27 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 2362 | 2026-03-11 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-014602 | Closed | 27 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-04 | Appselec-TRANSMIT-000019 | NA | Trade Partner | Telecommunications Drawings No Longer In Use | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  | Documents are No longer in use, just Transmitted to Client and Trade partners for information. |  | 2026-03-05 | KPTG-TRANSMIT-000068 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-04 | Appselec-TRANSMIT-000020 | NA | Trade Partner | Telecommunications Drawings No Longer In Use | 0 | 3 | 0 | NA | REJECTED | [5 empty] | No action is required, it is duplicate transmit of Appselec-TRANSMIT-000019 |  | 2026-03-05 | KPTG-TRANSMIT-000068 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-04 | Appselec-TRANSMIT-000021 | NA | Trade Partner | Telecommunications Drawings No Longer In Use | 0 | 3 | 0 | NA | REJECTED | [5 empty] | No action is required, it is duplicate transmit of Appselec-TRANSMIT-000019 |  | 2026-03-05 | KPTG-TRANSMIT-000068 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-05 | Entire M-TRANSMIT-000005 | NA | Trade Partner | Mechanical shop drawings issued for approval | 16 | 0 | 0 | NA | APPROVED | 2026-03-05 | WF-000036 | NA | 2026-03-11 |  |  |  | 2026-03-13 | KPTG-TRANSMIT-000103, | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-05 | HDRAus-TRANSMIT-000077 | NA | Consultant | HDR Site Inspection 23/02/26 - Actions | 2 | 0 | 0 | KPTG-IntCorr-003123 | APPROVED |  | NA | NA |  |  | No Action Required |  |  | NA | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-05 | HDRAus-TRANSMIT-000078 | NA | Consultant | M3S1 DH7/8 - Thermal insulation requirements to DH corridor walls & screening areas | 1 | 0 | 0 | KPTG-IntCorr-003139 | APPROVED |  | NA | NA |  |  | No Action Required |  |  | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-05 | VERTIV-TRANSMIT-000026 | NA | Trade Partner | M3-ST-1-CRAC revised FD submission as per FD discussion meeting | 0 | 1 | 0 | KPTG-IntCorr-003140 | APPROVED |  | NA | NA |  |  | No Action required |  | 2026-03-20 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-09 | Nilsen3-TRANSMIT-000118 | NA | Trade Partner | Nilsen Material Tech Data & Procurement Tracking | 0 | 4 | 0 | NA | APPROVED |  | NA |  |  |  | IFCs, No Review required, Distributed to the Project Team. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-11-10 | ZIA-TRANSMIT-000051 | NA | Trade Partner | CSMS Drawing Re-issue for Approve | 6 | 0 | 0 | NA | APPROVED | 2025-11-12 | NA | 1210 | 2025-11-18 |  |  | 2026-03-05 | 2026-03-05 | KPTG-TRANSMIT-002708 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-03 | SES AU-TRANSMIT-000001 | NA | Trade Partner | Security Tech Data | 0 | 8 | 0 | NA | REJECTED | [5 empty] | Wrong document Numbering, Revision and title do not match with what is in the covering page, Hence, requested to resubmit: KPTG-IntCorr-000088 |  | 2026-03-05 | KPTG-IntCorr-000088 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-03 | SES AU-TRANSMIT-000002 | NA | Trade Partner | ACS HARDWARE- TECH DATA | 0 | 12 | 0 | NA | REJECTED | [5 empty] | Wrong Document numbering, Revision and title do not match with what mentioned in the covering page, hence, requested them to resubmit:KPTG-IntCorr-000089 |  | 2026-03-05 | KPTG-IntCorr-000089 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-03 | JCI-TRANSMIT-000005 | NA | Trade Partner | MEL11 - Authorization to Ship (COLO 4) | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document number is found wrong, requested to resubmit:KPTG-IntCorr-000082 |  | 2026-03-05 | KPTG-IntCorr-000082 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-03 | JCI-TRANSMIT-000006 | NA | Trade Partner | MEL11 FAT Documents | 0 | 1 | 0 | NA | REJECTED | [5 empty] | SUBMITTED DOCUMENT IS A ZIP FILE, REQUESTED TO ISSUE DOCUMENTS SEPARATELY-KPTG-IntCorr-000083 |  | 2026-03-05 | KPTG-IntCorr-000083 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-03 | JCI-TRANSMIT-000007 | NA | Trade Partner | MEL11 Documents | 0 | 18 | 0 | 18 | APPROVED | [5 empty] | QA checking is in progrss |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-05 | Aurecon-TRANSMIT-000012 | NA | Consultant | Dangerous Goods Report - Final | 0 | 1 | 0 | NA | APPROVED | 2026-03-05 | NA | 407 | 2026-03-10 |  |  | 2026-03-16 | 2026-03-17 | KPTG-TRANSMIT-001401 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-05 | INGEN3D-TRANSMIT-000694 | NA | Consultant | I3D-378 Next DC M3 Stage 4 - Acoustic Wall - IFA Checked (04-03-2026 | 6 | 0 | 0 | NA | APPROVED | 2026-03-05 | WF-004635 | NA | 2026-03-12 |  | AS PER ADVISE FROM OLIVER IFC DRAWING PLACED IN WF | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-018538 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-05 | United-TRANSMIT-000003 | NA | Trade Partner | Stage 9 and 11 Lift 1 to 4 Shop Drawings | 22 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. |  | 2026-03-05 | KPTG-TRANSMIT-001215 | Closed | 22 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-05 | INGEN3D-TRANSMIT-000693 | NA | Consultant | I3D-378 Next DC M3 Stage 4 - Acoustic Wall - Revised IFC | 30 | 0 | 0 | NA | APPROVED | 2026-03-05 | WF-004642 | NA | 2026-03-12 |  | 28 DOC PLACED WF FROM HERE AND 2 DOC FROM ADP-693 | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015113 | Closed | 28 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-08 | RDSBIM-TRANSMIT-000023 |  | Trade Partner | MWYCCB ¦ GROUND FLOOR RCP PLAN AND LAYOUT | 5 | 0 | 0 | KPTG-IntCorr-001090 | APPROVED | 2025-12-09 | WF-000097 |  | 2025-12-15 |  | Bim360 review terminated by Moj |  | 2026-06-29 | KPTG-TRANSMIT-001354 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-05 | SMEPS-TRANSMIT-000204 | NA | Trade Partner | SME - Eastern External Structure IFA | 30 | 1 | 0 | NA | APPROVED | 2026-03-10 | WF-004705 | NA | 2026-04-03 |  | The WF has been terminated by Lola |  | 2026-04-01 | NA | Closed | 30 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-05 | WSP ANZ-TRANSMIT-000046 | NA | Consultant | WSP - Building Services Documents - Issue for Tender - CSMS | 25 | 0 | 0 | NA | APPROVED | 2026-03-05 | WF-000301 | NA | 2026-03-12 |  | Bluebeam review submission as instructed by Kapitol (Original Transmittal receipt date is 17/02) | 2026-03-13 | 2026-03-17 | KPTG-TRANSMIT-001403 | Closed | 25 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-05 | WSP ANZ-TRANSMIT-000046 | NA | Consultant | WSP - Building Services Documents - Issue for Tender - ELC | 84 | 1 | 0 | NA | APPROVED | 2026-03-05 | WF-000302 | NA | 2026-03-12 |  | Bluebeam Review submission as instructed by Kapitol (Original Transmittal receipt date is 17/02) | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-001618 | Closed | 85 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-05 | WSP ANZ-TRANSMIT-000046 | NA | Consultant | WSP - Building Services Documents - Issue for Tender - FIP | 80 | 1 | 0 | NA | APPROVED | 2026-03-05 | WF-000303 | NA | 2026-03-12 |  | Bluebeam review submission as instructed by Kapitol. (Original Transmittal receipt date is 17/02) | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-001403 | Closed | 81 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-05 | WSP ANZ-TRANSMIT-000046 | NA | Consultant | WSP - Building Services Documents - Issue for Tender - Fuel | 22 | 1 | 0 | NA | APPROVED | 2026-03-05 | WF-000304 | NA | 2026-03-12 |  | Bluebeam review submission as instructed by Kapitol (Original Transmittal receipt date is 17/02) | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-001403 | Closed | 23 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-05 | WSP ANZ-TRANSMIT-000046 | NA | Consultant | WSP - Building Services Documents - Issue for Tender - Hydraulic | 63 | 1 | 0 | NA | APPROVED | 2026-03-05 | WF-000305 | NA | 2026-03-12 |  | Bluebeam review submission as instructed by Kapitol (Original Transmittal receipt date is 17/02) | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-001403 | Closed | 64 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-05 | WSP ANZ-TRANSMIT-000046 | NA | Consultant | WSP - Building Services Documents - Issue for Tender - VRT | 6 | 1 | 0 | NA | APPROVED | 2026-03-05 | WF-000308 | NA | 2026-03-12 |  | Bluebeam review submission as instructed by Kapitol. (Original Transmittal receipt date is 17/02) | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-001595 | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-05 | WSP ANZ-TRANSMIT-000048 | NA | Consultant | WSP - Building Services Documents - Reissue for Tender - Telecom | 52 | 1 | 0 | NA | APPROVED | 2026-03-05 | WF-000307 | NA | 2026-03-12 |  | Bluebeam review submission as instructed by Kapitol. (Original Transmittal receipt date is 17/02) | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-001652 | Closed | 53 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-05 | WSP ANZ-TRANSMIT-000050 | NA | Consultant | WSP - Building Services Documents - Reissue for Tender - MEC | 45 | 1 | 0 | NA | APPROVED | 2026-03-05 | WF-000306 | NA | 2026-03-12 |  | Bluebeam review submission as instructed by Kapitol. (Original Transmittal receipt date is 19/02) | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-001660 | Closed | 46 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-06 | RDSBIM-TRANSMIT-000162 | NA | Trade Partner | LINDRUM ¦ MEZZANINE LEVEL CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | #590 | 2026-03-13 |  |  | 2026-03-11 | 2026-03-11 | KPTG-SADV-003377 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-09 | B Smart-TRANSMIT-000035 | NA | Consultant | B2-B4 concrete profile IFC. | 3 | 0 | 0 | NA | APPROVED | 2025-12-09 | WF-000085 | 154 | 2025-12-12 |  |  |  | 2026-01-27 | KPTG-TRANSMIT-000334 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-05 | KETE-TRANSMIT-000117 | NA | Trade Partner | PMU report | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | As per the instruction, the register will be updated and then forwarded to the trade partner and consultants. |  | 2026-03-06 | KPTG-TRANSMIT-001954 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-06 | NXT-TRANSMIT-001361 | NA | Trade Partner | Fwd: M3 Stage 3 Jemena Interface Panel Updates incl cable schedule | 9 | 0 | 0 | NA | APPROVED | 2026-03-06 | WF-004685 | NA | 2026-03-24 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015129 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-06 | D&E-TRANSMIT-000143 | SPARK-CRFI-KPG-000570 | Trade Partner | MSBD-01 to 04 Drawings | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Error in document number |  | 2026-03-25 | KPTG-TRANSMIT-000507 & KPTG-TRANSMIT-000591 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-05 | D&E-TRANSMIT-000437 | NA | Trade Partner | Ground Builders Works Layout Zones + Level 1 CHW Pipe Layout Zones - Issued For Approval | 8 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 2364 | 2026-03-13 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-015254 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-06 | PARR-TRANSMIT-000131 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - PREFAB BATTERY ENCLOSURE INTERFACE REGISTER | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-03-06 | KPTG-TRANSMIT-013935 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-05 | Civilex-TRANSMIT-000040 | NA | Trade Partner | Concrete Mix Design | 0 | 1 | 0 | KPTG-IntCorr-000441 | APPROVED | 2026-03-11 | WF-000229 | NA | 2026-03-12 |  | clarification from Jarrod | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-000737 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-06 | D&E-TRANSMIT-000144 | SPARK-CRFI-KPG-000348 | Trade Partner | FANS & COWLS | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-23 | KPTG-TRANSMIT-000568 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-05 | INGEN3D-TRANSMIT-000011 | NA | Trade Partner | Level 2 & 3 - Cast in Dowels | 16 | 0 | 0 | No longer is use docs | APPROVED | [5 empty] | No longer is use docs - |  |  |  | Closed | 16 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-05 | INGEN3D-TRANSMIT-000015 | NA | Trade Partner | Level 2 & 3 - Cast in Dowels | 1 | 0 | 0 | No longer is use docs | APPROVED | [5 empty] | No longer is use docs - REGISTER UPDATED |  | 2026-03-12 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-05 | Civilex-TRANSMIT-000041 | NA | Trade Partner | Coupler Box System for approval | 0 | 1 | 0 | clarification from Jarrod - KPTG-IntCorr-000442 | APPROVED | 2026-03-11 | WF*000230 | NA | 2026-03-13 |  | clarification from Jarrod | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-000837 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-06 | D&E-TRANSMIT-000145 | NA | Trade Partner | MSDB-02 Mechanical Switchboard | 1 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-03-06 | KPTG-TRANSMIT-000508 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-05 | WAM-TRANSMIT-000724 | NA | Consultant | Facade Elevations and Window Schedules | 17 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 306 | 2026-03-08 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000684 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-05 | D&E-TRANSMIT-000007 | NA | Trade Partner | Woolworths Mechanical Design D&E Engineering Mark-Up | 0 | 1 | 0 | KPTG-IntCorr-000444 | APPROVED | [5 empty] | KPTG-IntCorr-000444 - CLOSED OUT AS PER TEAMS COMMUNICATION DTD 03/16/2026 |  | 2026-03-16 | KPTG-IntCorr-000900 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-05 | WAM-TRANSMIT-000725 | NA | Consultant | Development Summary and Apartment Matrix | 2 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 308 | 2026-03-08 |  | Rejected | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000722 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-05 | ADP-TRANSMIT-000265 | NA | Consultant | Stage 4 Updated Comms Drawings (IFC Issue) | 19 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 2367 | 2026-03-09 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-013937 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-05 | D&E-TRANSMIT-000006 | NA | Trade Partner | Building 4B3-Early Works ¦ EWP Technical Manual - IFA | 0 | 1 | 0 | KPTG-IntCorr-000432 - Clarification | APPROVED | [5 empty] | KPTG-IntCorr-000432 - Clarification - CLOSED BY JOHN |  | 2026-03-23 | KPTG-SADV-001329 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-05 | D&E-TRANSMIT-000444 | NA | Trade Partner | Re: Cooling Tower Waffle Pad - Acoustic Report - Issued for approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | REJECTED DUE TO MISSING OF DOCUMENT NUMBER, REVISION ETC |  | 2026-03-05 | KPTG-TRANSMIT-013928 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-05 | WAM-TRANSMIT-000722 | NA | Consultant | CSP Ground & Mezzanine Update | 4 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 302 | 2026-03-08 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000677 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-06 | D&E-TRANSMIT-000146 | SPARK-CRFI-KPG-000572 | Trade Partner | MWYCCB - GROUND LEVEL + LEVEL 1 MECH. ELEC. LAYOUT ZONES - Issued For Approval | 6 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 157 | 2026-03-13 |  |  | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-000577 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-09 | JCBa-TRANSMIT-000200 | NA | Consultant | Updated POD's Acoustic Details -IFC | 4 | 0 | 0 | NA | APPROVED | 2025-12-09 | WF - 803 | 506 | 2025-12-16 |  |  | 2026-01-27 | 2026-01-27 | KPTG-DA-002374 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-05 | WAM-TRANSMIT-000723 | NA | Consultant | WAM ARCH - Issue for BP5 | 2 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 304 | 2026-03-08 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000683 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-05 | Traf Grp-TRANSMIT-000001 | NA | Consultant | Waste Management Plan for Secondary Consent | 0 | 1 | 0 | NA | APPROVED | 2026-03-05 | WF-000215 | NA | 2026-03-09 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000691 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-05 | Traf Grp-TRANSMIT-000002 | NA | Consultant | Sustainable Transport Plan for Secondary Consent | 0 | 1 | 0 | NA | APPROVED | 2026-03-05 | WF-000216 | NA | 2026-03-09 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000697 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-05 | Traf Grp-TRANSMIT-000003 | NA | Consultant | Loading Management Plan for Secondary Consent | 0 | 1 | 0 | NA | APPROVED | 2026-03-05 | WF-000217 | NA | 2026-03-09 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000698 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-05 | Traf Grp-TRANSMIT-000004 | NA | Consultant | Traffic Letter for Secondary Consent | 0 | 1 | 0 | NA | APPROVED | 2026-03-05 | WF-000218 | NA | 2026-03-09 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000702 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-06 | RDSBIM-TRANSMIT-000116 | NA | Trade Partner | MLCSPR ¦ JUNIOR SCHOOL LANDSCAPE PLAN | 5 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 457 | 2026-03-13 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-05 | Traf Grp-TRANSMIT-000005 | NA | Consultant | Road Safety Audit for Secondary Consent | 0 | 1 | 0 | NA | APPROVED | 2026-03-05 | WF-000219 | NA | 2026-03-09 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000706 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-05 | Resonate-TRANSMIT-000009 | NA | Consultant | Secondary Consent - Acoustic Report | 0 | 1 | 0 | NA | APPROVED | 2026-03-05 | WF-000220 | NA | 2026-03-09 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-000921 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-05 | VAE-Grp-TRANSMIT-000135 | NA | Trade Partner | MECHANICAL - L4&5 LAYOUTS & SCHEDULES | 2 | 2 | 0 | NA | APPROVED | 2026-03-05 | NA | 1094 | 2026-03-09 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-003165 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-06 | D&E-TRANSMIT-000448 | NA | Trade Partner | Re: MCC/MxC Drawings - Issued for Approval | 8 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-03-06 | KPTG-RFI-006567 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-01 | Civilex-TRANSMIT-000007 | N/A | Trade Partner | District Docklands Foundation Pile Design Package | 0 | 1 | 0 | NA | APPROVED | 2025-12-01 | WF-000045 | NA | 2025-12-03 |  |  | 2025-12-04 | 2025-12-04 | KPTG-TRANSMIT-000176 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-09 | SMEPS-SUBADVICE-000279 | NA | Trade Partner | SME - Lux plots issued for approval DH7 and DH8 | 5 | 0 | 0 | NA | APPROVED | 2025-12-09 | NA | 1296 | 2025-12-18 |  |  | 2026-01-21 | 2026-01-27 | KPTG-TRANSMIT-002365 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-06 | D&E-TRANSMIT-000449 | NA | Trade Partner | Re: MCC/MxC Drawings - Issued for Approval | 2 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-03-06 | KPTG-RFI-006568 | Open | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-06 | SMEPS-TRANSMIT-000125 | SPARK-CRFI-KPG-000573 | Trade Partner | General Power Outlets | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-02 | KPTG-TRANSMIT-000613 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-06 | vdmcons-TRANSMIT-000130 | NA | Trade Partner | ME25 1004: D112 511-537 Sydney Rd Coburg - Shop Drawing - A-L01-P38 REV 1- Re-IFF - 2026-03-06 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Aconex Update Register Only |  | 2026-03-06 | KPTG-IntCorr-001598 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-05 | Hames-TRANSMIT-000131 | NA | Consultant | PREFORMANCE SOLUTION THRESOLDS & HOBS | 0 | 1 | 0 | QA Error - rejected - KPTG-IntCorr-001055 | REJECTED | [5 empty] | QA Error - rejected |  | 2026-03-05 | KPTG-IntCorr-001055 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-05 | Inhabit-TRANSMIT-000014 | NA | Consultant | Updated NABERS Energy Report IFI-4 | 0 | 1 | 0 | NA | APPROVED | 2026-03-05 | NA | 1090 | 2026-03-06 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-003073 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-05 | Jordan-TRANSMIT-000121 | NA | Trade Partner | Level 5 - Plumbing Drainage - For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 1086 | 2026-03-07 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-003176 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-05 | Jordan-TRANSMIT-000122 | NA | Trade Partner | Level 4 - Plumbing Drainage - For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 1088 | 2026-03-07 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-003169 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-05 | Ardon-IntCorr-000002 | NA | Trade Partner | PMDF Shop Drawing L4 | 13 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 1056 | 2026-03-09 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-003471 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-05 | Ardon-IntCorr-000003 | NA | Trade Partner | PMDF Shop Drawings L5 | 7 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 1058 | 2026-03-09 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-003475 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-05 | ZIA-TRANSMIT-000033 | NA | Trade Partner | CSMS - Outstation & Sensor Location Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 1072 | 2026-03-09 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-003597 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-09 | RBG-TRANSMIT-000042 | NA | Consultant | Latest Structural Documentation Issued for Construction - Column Schedule Updates | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required As advised by Kapitol PC "this is an update for Certification that is being reviewed independently ". |  | 2025-12-09 |  | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-05 | VAE-Grp-TRANSMIT-000135 | NA | Trade Partner | MECHANICAL - L4&5 LAYOUTS & SCHEDULES | 2 | 2 | 0 | NA | APPROVED | 2026-03-05 | NA | 1094 | 2026-03-12 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-003165 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-06 | Metzone-TRANSMIT-000010 | NA | Trade Partner | Catch Deck - Scaffold Clash Update | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per the direction from Ms. Ashlin, we have updated these documents into our document register only:KPTG-SADV-003330 |  | 2026-03-06 | KPTG-SADV-003330 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-03 | Nilsen3-TRANSMIT-000055 | NA | Trade Partner | NXM3S3 ¦ Nilsen ELC Shop Drawings - FOA #1 | 7 | 0 | 0 | NA | APPROVED | 2026-03-06 | WF-004659 | NA | 2026-03-19 | [5 empty] | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-06 | D&E-TRANSMIT-000147 | NA | Trade Partner | MWYCCB - ROOF LEVEL - PENETRATION LAYOUT ZONES incl CAD Files - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 158 | 2026-03-13 |  | Terminated as per Alex advise |  | 2026-04-17 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-06 | D&E-TRANSMIT-000148 | NA | Trade Partner | MSDB-02 Mechanical Switchboard | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Error in document number |  | 2026-03-06 | KPTG-TRANSMIT-000509 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-05 | TATE_-TRANSMIT-000025 | NA | Trade Partner | COLO 4 HAC IFC | 6 | 0 | 0 | NA | APPROVED | 2026-03-05 | WF-000216 | NA | 2026-03-09 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-000392 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-06 | ADP-TRANSMIT-000034 - ELC | NA | Consultant | ADP MEL4680 - GE1 - IFC Drawings (EL & COMMS) | 1 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 35 | 2026-03-11 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-000068 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-06 | ADP-TRANSMIT-000034 - TEL | NA | Consultant | ADP MEL4680 - GE1 - IFC Drawings (EL & COMMS) | 1 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 36 | 2026-03-11 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-000068 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-06 | Auspan-TRANSMIT-000121 | NA | Trade Partner | Precast shop drawings for construction | 35 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - IFC - Update register and distribute -KPTG-TRANSMIT-000853 |  | 2026-03-06 | KPTG-TRANSMIT-000853 | Closed | 35 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-06 | Auspan-TRANSMIT-000122 | NA | Trade Partner | Re: Precast shop drawings for construction. | 65 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Update register and distribute -KPTG-TRANSMIT-000855 |  | 2026-03-06 | KPTG-TRANSMIT-000855 | Closed | 65 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-11-27 | MALA-TRANSMIT-000027 | NA | Consultant | LANDSCAPE DRAWING IFC (C1) - BTR SCHEME (DWFX) | 38 | 0 | 0 | NA | APPROVED | 2025-12-09 | WF-000802 | 486 | 2025-12-12 |  |  | 2025-12-09 | 2025-12-09 | KPTG-DA-002222 | Closed | 38 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-06 | INDS-TRANSMIT-000010 | NA | Trade Partner | L2 to L7 - Typical Floor Penetration Layout | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapiol DM, register and Transmit to RDS -KPTG-TRANSMIT-000858 |  | 2026-03-06 | KPTG-TRANSMIT-000858 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-06 | Auspan-TRANSMIT-000120 | NA | Trade Partner | For Construction | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Update register and distribute - KPTG-TRANSMIT-000857 |  | 2026-03-06 | KPTG-TRANSMIT-000857 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-06 | POTTSENG-TRANSMIT-000011 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - PENETRATION - GROUND - ZONE 1,2,3,4 & 5 LAYOUTS | 5 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 469 | 2026-03-11 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-001099 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-06 | JCBa-TRANSMIT-000067 | NA | Consultant | :Architectural Documentation | 0 | 1 | 0 | NA | APPROVED | 2026-03-06 | WF-000257 | NA | 2026-03-11 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-001301 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-06 | INDS-TRANSMIT-000011 | NA | Trade Partner | L2 to L7 - Precast Penetration Layout | 22 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapiol DM, register and Transmit to AUSPAN: |  | 2026-03-06 | KPTG-TRANSMIT-000867 | Closed | 22 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-06 | SMEPS-TRANSMIT-000127 | NA | Trade Partner | SME Shop Drawing Electrical IFC A | 3 | 0 | 0 | NA | APPROVED | 2026-03-06 | WF-000219 | NA | 2026-03-10 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-000404 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-06 | LGCE-TRANSMIT-000006 | NA | Trade Partner | Basement 1- 4 | 4 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 316 | 2026-03-11 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-000686 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-06 | POTTSENG-TRANSMIT-000005 | NA | Trade Partner | 671C - HYD Levels B4 - B1 & Penetrations | 4 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 321 | 2026-03-11 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-000698 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-06 | POTTSENG-TRANSMIT-000005 | NA | Trade Partner | 671C - HYD Levels B4 - B1 Water, B4-B2 Drainage Layouts | 7 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 322 | 2026-03-12 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-000744 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-06 | ARCH-TRANSMIT-000030 | NA | Consultant | 2026.03.06_CPP and Precast IFI | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Issued For information only. To be updated in Aconex and ACC. No review required. (Outlook mail: RE: [External] FW: KPTG-DA-000287: DESIGN PROGRAM - KEY DATES ACNXREF<1uIuH6hZXcMNq8sdkUdulB>) |  | 2026-03-06 | KPTG-IntCorr-000100 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-08 | RDSBIM-TRANSMIT-000126 | NA | Trade Partner | LEVEL 01 RCP KEY PLAN & LAYOUT | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2025-12-09 | KPTG-TRANSMIT-002504 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-11 | Partners-TRANSMIT-000012 | NA | Trade Partner | Quickstair and Handrails - Revised from Comments | 20 | 0 | 0 | NA | APPROVED | 2025-12-11 | WF-003280 | NA | 2025-11-14 |  | NA | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-013988 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-04 | ADP-TRANSMIT-000261 | NA | Consultant | ADP MEL4561 - HV Room Design Changes Impacted Drawings Update - Elec | 7 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 3901 | 2026-03-06 |  |  | 2026-03-04 | 2026-03-11 | KPTG-TRANSMIT-014154 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-04 | ADP-TRANSMIT-000261 | NA | Consultant | ADP MEL4561 - HV Room Design Changes Impacted Drawings Update - FID | 1 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 3903 | 2026-03-06 |  |  | 2026-03-04 | 2026-03-11 | KPTG-TRANSMIT-014154 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-06 | ADP-TRANSMIT-000268 | NA | Consultant | MEL741 - Stage 4 Services IFC Issue (FID) | 3 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 2390 | 2026-03-10 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-014159 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-04 | ADP-TRANSMIT-000261 | NA | Consultant | ADP MEL4561 - HV Room Design Changes Impacted Drawings Update - Mec | 1 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 3907 | 2026-03-06 |  |  | 2026-03-04 | 2026-03-11 | KPTG-TRANSMIT-014154 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-04 | ADP-TRANSMIT-000261 | NA | Consultant | ADP MEL4561 - HV Room Design Changes Impacted Drawings Update - Tel | 1 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 3909 | 2026-03-06 |  |  | 2026-03-04 | 2026-03-11 | KPTG-TRANSMIT-014154 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-06 | Tensile-TRANSMIT-000006 | NA | Trade Partner | Tensile Shop Drawings | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Drawings, transmitted to Trade & Consultants |  | 2026-03-06 | KPTG-TRANSMIT-002525 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-06 | Nilsen3-TRANSMIT-000055 | NA | Trade Partner | NXM3S3 ¦ Nilsen ELC Shop Drawings - FOA #1 | 7 | 0 | 0 | NA | APPROVED | 2026-03-06 | WF-004659 | NA | 2026-03-19 |  |  | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-015657 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-06 | Entire M-TRANSMIT-000040 | NA | Trade Partner | BMS Drawings Issued For Construction | 1 | 2 | 0 | NA | APPROVED | 2026-03-06 | WF-004649 | NA | 2026-03-19 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-015430 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-09 | RDSBIM-TRANSMIT-000128 | NA | Trade Partner | LEVEL 13 TOWER B CONCRETE PROFILE PLAN | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2025-12-09 | KPTG-TRANSMIT-002505 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-06 | KPTG-IntCorr-005804 | NA | Trade Partner | Schiavello Systems | 3 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 458 | 2026-03-13 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-06 | PCForm-TRANSMIT-000068 | NA | Trade Partner | Fwd: Ground to Level 1 PT Drawings (S&I Portion) | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per the direction from Ms. Ashlin, PC, we have updated these drawings into our document Register.KPTG-SADV-003332 |  | 2026-03-06 | KPTG-SADV-003332 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-04 | KPTG-TRANSMIT-013836 | NA | Trade Partner | Issue to NEXTDC - Joinery Shop Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 3896 | 2026-03-11 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-016377 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-05 | INDS-TRANSMIT-000031 | NA | Trade Partner | Dry fIRE - Basement to Mezzanine | 3 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 594 | 2026-03-17 |  | The Dwfx file is not shared with us , requested to resubmit:KPTG-SADV-003329 | 2026-03-17 | 2026-03-19 | KPTG-SADV-003499 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-02 | KPTG-TRANSMIT-013688 | NA | Trade Partner | Joinery Shop Drawings - Kitchenette + Breakout Bench | 9 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 3898 | 2026-03-10 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-019185 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-11-25 | LTEPRCST-TRANSMIT-000138 | NA | Trade Partner | NEXTDC STAGE 4 - CORE 5 DOWEL SET-OUT | 1 | 0 | 0 | NA | APPROVED | 2025-11-12 | WF-003287 | NA | 2026-03-06 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-014034 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-06 | NXT-WTRAN-001875 | NA | Consultant | SAMPLE AND TECH DATA - CONSULTANT REVIEW -FIT-OUT & WATERPROOFING - Resiflex FC Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-03-06 | WF-004260 | NA | 2026-03-06 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-014030 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-06 | LTEPRCST-TRANSMIT-000120 | NA | Trade Partner | NEXTDC STAGE 04- CORE 09 DOWEL SET-OUT (REV.2) | 1 | 0 | 0 | NA | APPROVED | 2025-10-14 | WF-003080 | NA | 2026-02-27 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-014026 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-10-09 | LTEPRCST-TRANSMIT-000118 | NA | Trade Partner | NEXTDC STAGE 04- CORE 03 AND CORE 04 (REV.2) DOWEL SET-OUT | 2 | 0 | 0 | NA | APPROVED | 2025-10-22 | WF-003079 | NA | 2026-02-27 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-014006 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-10-23 | LTEPRCST-TRANSMIT-000134 | NA | Trade Partner | NEXTDC STAGE 04 - UPDATED CORE 09 CUBE 01 STAIR LANDING CONNECTION | 2 | 0 | 0 | NA | APPROVED | 2025-10-23 | WF-003090 | NA | 2026-02-27 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-013986 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-10-21 | LTEPRCST-TRANSMIT-000131 | NA | Trade Partner | NEXTDC S4 - CORE 04 CUBE 04 & 06 UPDATED | 2 | 0 | 0 | NA | APPROVED | 2026-03-21 | WF-003039 | NA | 2026-02-27 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-013976 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-06 | NXT-WTRAN-001869 | NA | Consultant | S4 ¦ SHOP DRAWING ¦ CONSULTANT REVIEW ¦ IFC STR ¦ PRE-CAST | 19 | 0 | 0 | NA | APPROVED | 2025-11-05 | WF-003204 | NA | 2025-12-26 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-013968 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-06 | KPTG-TRANSMIT-013941 | NA | Consultant | Roof Design Documentation Update - architecture | 31 | 0 | 0 | NA | APPROVED | 2026-03-06 | WF-004661 | NA | 2026-03-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-10-10 | LTEPRCST-TRANSMIT-000128 | NA | Trade Partner | NEXTDC STAGE 04 - CORE 01 ISSUED FOR CONSTRUCTION | 21 | 0 | 0 | NA | APPROVED | 2026-03-20 | WF-003026 | NA | 2026-02-26 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-013958 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-10-17 | LTEPRCST-TRANSMIT-000126 | NA | Trade Partner | NEXTDC STAGE 04- EL06 IF | 1 | 0 | 0 | NA | APPROVED | 2025-10-20 | WF-003026 | NA | 2026-02-26 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-013951 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-06 | SMEPS-TRANSMIT-000205 | NA | Trade Partner | SME - DRAWINGS IFA PART SUBMISSIONS | 11 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 2369 | 2026-03-16 |  |  | 2026-05-19 | 2026-05-19 | SMEPS-TRANSMIT-000205 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-06 | HDRAus-TRANSMIT-000425 | NA | Consultant | M3 Stage 4 Updated drawings and Cad - weekly issue | 27 | 2 | 0 | NA | APPROVED | 2026-03-06 | NA | 2396 | 2026-03-11 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014860 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-06 | OveArup-TRANSMIT-000073 | NA | Client | M3 S1 A7A8 Mechanical Site Walkthrough Inspection Report | 0 | 1 | 0 | KPTG-IntCorr-003155 | APPROVED |  | NA | NA |  |  | No Action Required |  |  |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-06 | ADP-TRANSMIT-000039 | NA | Consultant | MEL4834 - Updated Mech Reg 126 | 0 | 1 | 0 | KPTG-IntCorr-003156 | APPROVED |  | NA | NA |  |  | Distribution Only |  | 2026-03-16 | KPTG-TRANSMIT-002757 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-10-29 | ZIA-TRANSMIT-000044/ZIA-IntCorr-000108 | NA | Trade Partner | CSMS ORMB Typical Drawing | 1 | 0 | 0 | NA | APPROVED | 2025-11-28 | NA | 1265 | 2025-12-04 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-002735 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-06 | VIA Arch-TRANSMIT-000063 | NA | Consultant | M2 Stage 11 - 75% DD Documentation | 16 | 0 | 0 | KPTG-IntCorr-000486 | APPROVED | 2026-03-13 | NA | 432 | 2026-03-18 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-001383 | Closed | 16 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-06 | VIA Arch-TRANSMIT-000064 | NA | Consultant | Stairs and Lift Cores - Building Permit Issue Documentation | 14 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings need to be revised KPTG-DA-001471 |  | 2026-03-06 | NA | Closed | 14 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-06 | WGAVIC-TRANSMIT-000077 | NA | Consultant | M2 - Stage 9 - Level 2 Slab - Issued for Certification | 5 | 0 | 0 | KPTG-IntCorr-000487 | APPROVED |  | NA | NA |  |  | No review required. Updated register and ACC and distributed |  | 2026-03-13 | KPTG-TRANSMIT-001341 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-06 | WGAVIC-TRANSMIT-000078 | NA | Consultant | M2 - Stage 10 - Level 2 Slab - Issued for Certification | 5 | 0 | 0 | KPTG-IntCorr-000488 | APPROVED |  | NA | NA |  |  | No review required, Updated register and distributed |  | 2026-03-13 | KPTG-TRANSMIT-001342 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-06 | AXIS-NSW-TRANSMIT-000009 | NA | Trade Partner | Updated Trench Grate Sample | 0 | 1 | 0 | NA | APPROVED | 2026-03-06 | WF-000312 | NA | 2026-03-16 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-002208 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-06 | Tradetec-TRANSMIT-000060 | NA | Trade Partner | Revised TSA Technical Data | 0 | 2 | 0 | NA | APPROVED | 2026-03-06 | WF-000311 | NA | 2026-03-18 |  |  | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-001641 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-06 | AXIS-NSW-TRANSMIT-000008 | NA | Trade Partner | Updated Complete Pit Package Sample | 0 | 1 | 0 | NA | APPROVED | 2026-03-06 | WF-000310 | NA | 2026-03-18 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-001311 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-06 | HDRAus-TRANSMIT-000422 | NA | Consultant | Corridor Layouts - Architectural Updates/Layouts | 4 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 2372 - New WF 2573 | 2026-03-10 |  | 3 drawings have been terminated as requested by Oliver T | 2026-03-20 | 2026-03-20 | HDRAus-TRANSMIT-000422 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-09 | Auscool-TRANSMIT-000056 | NA | Trade Partner | Level 9 - 27 Builders works | 19 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | These drawings were supersede with previous one. |  | 2025-12-09 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-06 | ADP-TRANSMIT-000266 | NA | Consultant | Re: MEL741 - Stage 4 FID Drawings - IFC Updates | 11 | 0 | 0 | NA | REJECTED | [5 empty] | QA Rejected due to incorrect revision number and incorrect reason that mentioned on drawing |  | 2026-03-06 | KPTG-TRANSMIT-013950 | Closed | 11 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-06 | RDSBIM-TRANSMIT-000241 | NA | Trade Partner | GROUND FLOOR PARTITION WALL KEY PLAN AND ELEVATIONS | 2 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 2578 | 2026-03-19 |  | Old WF 2433 | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-018307 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-06 | RDSBIM-TRANSMIT-000242 | NA | Trade Partner | NXM3S4 ¦ GROUND FLOOR & LEVEL 01 SPEED PANEL LAYOUT AND ELEVATION | 2 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 2430 | 2026-03-19 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-014445 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-06 | SKS Tech-TRANSMIT-000053 | NA | Trade Partner | LIGHTNG LAYOUT - GROUND - ZONE C1 | 1 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 2382 | 2026-03-16 |  |  |  | 2026-03-12 | KPTG-IntCorr-010605 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-06 | D&E-TRANSMIT-000450 | NA | Trade Partner | Level 1 - CHW Pipe Layout - Zone 5 6 & 7 - Issued For Approval | 3 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 2395 | 2026-03-16 |  |  | 2026-03-25 | 2026-03-26 | KPTG-TRANSMIT-015036 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-06 | PFP PL-TRANSMIT-000073 | NA | Trade Partner | Roof Level Zone C1 IFA | 2 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 2398 | 2026-03-16 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-014929 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-06 | ADP-TRANSMIT-000267 | NA | Consultant | MEL741 - Stage 4 Updated Mech Drawings (IFC Issue) | 22 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 2400 | 2026-03-10 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-014134 | Closed | 22 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-06 | D&E-TRANSMIT-000451 | NA | Trade Partner | Ground - Hangers Layout - Zone 7 & 9 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 2403 | 2026-03-16 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-06 | WAM-TRANSMIT-000726 | NA | Consultant | Common Areas VM Scope Report | 0 | 1 | 0 | NA | APPROVED | 2026-03-06 | WF-000221 | NA | 2026-03-10 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000714 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-06 | TTW-TRANSMIT-000103 | NA | Consultant | BP1 Structural Construction Issue | 32 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 314 | 2026-03-11 |  |  | 2026-03-13 | 2026-03-14 | KPTG-TRANSMIT-000746 | Closed | 32 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-09 | OveArup-TRANSMIT-000135 | NA | Trade Partner | M3 Stage 3 Earthing Drawings IFCN update | 2 | 0 | 0 | NA | REJECTED | [5 empty] | The document revision number does not match the Aconex revision. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-06 | TTW-TRANSMIT-000105 | NA | Consultant | BP4 - Structural Certification Issue | 37 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 319 | 2026-03-12 |  | QA ERROR - 1 DOC - HENCE REJECTED (KPTG-TRANSMIT-000660) - Victoria requested to release 36docs KPTG-IntCorr-000450 |  | 2026-03-17 | TTW-TRANSMIT-000105 | Closed | 37 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-06 | PCForm-TRANSMIT-000093 | NA | Trade Partner | Raft 1 - Pour Sequence for review | 3 | 0 | 0 | KPTG-IntCorr-000449 | APPROVED | 2026-03-11 | NA | 323 | 2026-03-17 |  | Clarification required from Nich | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-000891 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-06 | PCForm-TRANSMIT-000092 | NA | Trade Partner | Jumpform Concrete Envelopes & Wall Elevations - Updated Drawings IFC | 6 | 0 | 0 |  | APPROVED |  | NA | NA |  |  | KPTG-TRANSMIT-000723 - CLOSED OUT REFERANCE |  | 2026-03-12 | KPTG-TRANSMIT-000723 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-06 | Hollow-TRANSMIT-000005 | NA | Trade Partner | L1- Shop drawings | 18 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 312 | 2026-03-12 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-000760 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-06 | WAM-TRANSMIT-000727 | NA | Consultant | Common Areas 80%DD - Clubhouse | 4 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 310 | 2026-03-10 |  | 1 drawing approved | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-000893 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-06 | WAM-TRANSMIT-000728 | NA | Consultant | Line of Heights | 1 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 450 | 2026-04-23 |  | QA ERROR approved and submitted for review as per WAM-CADV-000420 | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-001293 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-06 | Rinco-TRANSMIT-000001 | NA | Trade Partner | Ground Floor IFC | 10 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 316 | 2026-03-13 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-000866 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-06 | D&E-TRANSMIT-000008 | NA | Trade Partner | Fire Pump Room Exhaust Fan | 0 | 1 | 0 | KPTG-IntCorr-000448 | APPROVED | 2026-03-10 | WF-000225 | NA | 2026-03-13 |  |  |  | 2026-03-16 | KPTG-TRANSMIT-000764 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-03 | SSem-TRANSMIT-000004 | NA | Trade Partner | Assemble SRC_Signage & Wayfinding_Operational Signage DD | 0 | 2 | 0 | NA | APPROVED | 2026-03-06 | WF-000962 | NA | 2026-03-12 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-06 | Entire M-TRANSMIT-000014 | NA | Trade Partner | Mechanical shop drawings IFC | 26 | 0 | 0 | NA | APPROVED | 2026-03-06 | WF-000225 | NA | 2026-03-11 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000434 | Closed | 26 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-09 | Kone-VIC-TRANSMIT-000016 | NA | Trade Partner | Updated Layouts for EOT Lift 5 issued FOR CONSTRUCTION | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per the direction documents are updated into document register only and transmitted to all parties. |  | 2025-12-09 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-05 | SMEPS-TRANSMIT-000126 | NA | Trade Partner | SME Shop Drawing Electrical IFA 4 | 4 | 0 | 0 | NA | APPROVED | 2026-03-05 | WF-000217 | NA | 2026-03-09 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-000445 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-05 | TATE_-TRANSMIT-000026 | NA | Trade Partner | COLO 4 Ceiling Engineering Report | 0 | 4 | 0 | NA | APPROVED | 2026-03-05 | WF-000218 | NA | 2026-03-11 |  | NA | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-000465 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-05 | TATE_-TRANSMIT-000027 | NA | Trade Partner | TATE HAC Leakage Tests and Door Closer IFC | 0 | 3 | 0 | NA | APPROVED | 2026-03-06 | WF-000221 | NA | 2026-03-10 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-000443 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-10 | KAPITOL-TRANSMIT-001185 | NA | Trade Partner | Fwd: Furnished Facility (B18) updated IFC Drawings. | 10 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 343 | 2026-03-12 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-10 | Nilsen3-TRANSMIT-000056 | NA | Trade Partner | M3-HV-NIL-SA-S-0301-0023 - Surge Arresters Stage 3 HV Switchboards REV1 | 0 | 1 | 0 | NA | APPROVED | 2026-03-10 | WF-004680 | NA | 2026-03-23 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-014251 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-10 | ACG-TRANSMIT-000066 | NA | Trade Partner | M3 - Stage 3 Camera FOV | 0 | 1 | 0 | NA | APPROVED | 2026-03-10 | WF-004681 | NA | 2026-03-23 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-014124 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-06 | RDSBIM-TRANSMIT-000243 | NA | Trade Partner | NXM3S3 ¦ ROOF HOB AND PLINTH PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 3932 | 2026-03-20 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-10 | Tradetec-TRANSMIT-000061 | NA | Trade Partner | Revised HV Pit Shop Drawings | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Mismatch in revision number in drawing no. 8026. Send back to originator for resubmission. |  | 2026-03-10 | KPTG-SADV-001601 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-06 | Hames-TRANSMIT-000133 | NA | Consultant | Updated Finishes Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-03-06 | NA | 1100 | 2026-03-12 |  | SUPERSEDED BY Hames-TRANSMIT-000139 | 2026-03-12 | 2026-03-17 | Hames-TRANSMIT-000139 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-01 | Fredon T-TRANSMIT-000006 | NA | Trade Partner | Display Bracket - Tech Data | 0 | 1 | 0 |  | REJECTED | [5 empty] | Requested to Resubmit | [6 empty] | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-09 | Lub-doka-TRANSMIT-000017 | NA | Trade Partner | PLATFORM LOADING DETAILS | 1 | 0 | 0 | KPTG-IntCorr-000602 | APPROVED |  | NA | NA |  |  |  |  | 2025-12-09 | KPTG-IntCorr-001116 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-06 | Hames-TRANSMIT-000132 | NA | Consultant | Issue of Certifier Updates | 23 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 1102 | 2026-03-12 |  |  |  | 2026-03-11 | KPTG-TRANSMIT-003106 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-06 | VAE-Grp-TRANSMIT-000136 | NA | Trade Partner | MECHANICAL - L4 SHEET 1 MECH, MECH ELEC & BW REVISED | 3 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 1098 | 2026-03-13 |  |  |  | 2026-03-24 | KPTG-TRANSMIT-003251 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-06 | Hames-TRANSMIT-000134 | NA | Consultant | PREFORMANCE SOLUTION THRESOLDS & HOBS | 0 | 1 | 0 | NA | APPROVED | 2026-03-06 | WF-000897 | NA | 2026-03-12 |  |  | 2026-03-11 | 2026-03-12 | KPTG-TRANSMIT-003114 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-06 | Civilex-TRANSMIT-000200 | NA | Trade Partner | Re: Sample Submission - Stage 3 - 22KVA Switch Room - Class A Super Strength Grout | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-03-06 | KPTG-RTRFI-002995 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-06 | Civilex-TRANSMIT-000201 | NA | Trade Partner | Stage 3 - 22KVA Slimdeck Documentation transmittal - Rev 2 | 0 | 2 | 0 | NA | REJECTED | [5 empty] | The document number is not included in the document. |  | 2026-03-06 | KPTG-RTRFI-002997 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-06 | ZIA-TRANSMIT-000038 | NA | Trade Partner | Comments Register | 0 | 1 | 0 | KPTG-IntCorr-001057 | APPROVED |  | NA | NA |  |  | clarification requested to Harry - closed out referance KPTG-IntCorr-001550 |  | 2026-03-20 | KPTG-IntCorr-001550 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-06 | Endfire-TRANSMIT-000070 | NA | Trade Partner | SAMPLE SUBMISSION - Globe Valve | 0 | 1 | 0 | KPTG-IntCorr-001058 | APPROVED | 2026-03-11 | WF-000904 | NA | 2026-03-17 |  | clarification requested to Harry | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-003226 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-06 | SIL-TRANSMIT-000027 | NA | Trade Partner | MEL05 C4 - 32PO-41735-T023 Technical Submittals | 0 | 5 | 0 | NA | APPROVED | 2026-03-10 | WF - 000230 | NA | 2026-03-17 |  | NA | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-000533 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-10 | Civilex-TRANSMIT-000204 | NA | Trade Partner | Sample Submission - Stage 3 - 22KVA Switch Room - Class A Super Strength Grout - Updated Naming | 0 | 1 | 0 | NA | APPROVED | 2026-03-10 | WF-004682 | NA | 2026-03-26 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-014567 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-06 | JCI-TRANSMIT-000015 | NA | Trade Partner | CC Panel FATs | 0 | 1 | 0 | NA | APPROVED | 2026-03-10 | WF - 000229 | NA | 2026-03-17 |  |  | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-000487 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-08 | WGAVIC-TRANSMIT-000034 | NA | Consultant | Civil Drawings - Early Works Drawings - Reissued for Construction | 12 | 0 | 0 | NA | APPROVED | 2025-12-09 | WF-000076 |  | 2025-12-19 |  |  |  | 2026-01-19 | KPTG-TRANSMIT-000475, KPTG-TRANSMIT-000519 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-10 | Civilex-TRANSMIT-000203 | NA | Trade Partner | Stage 3 - 22KVA Roof Slimdeck Documentation transmittal - Rev 2 | 2 | 0 | 0 | NA | APPROVED | 2026-03-10 | WF-004688 | NA | 2026-03-26 |  |  | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-015374 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-20 | RDSBIM-TRANSMIT-000195 | NA | Trade Partner | NXM3S4 ¦ LEVEL-1-C-1-054 CLEANERS FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 2419 | 2026-03-14 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-014756 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-10 | Tradetec-TRANSMIT-000062 | NA | Trade Partner | Re-Transmittal of Revised HV Pit Shop Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 411 | 2026-03-17 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-001550 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-07 | RDSBIM-TRANSMIT-000163 | NA | Trade Partner | LINDRUM ¦ BASEMENT LEVEL BLOCK WALL LAYOUT AND ELEVATION | 2 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 593 | 2026-03-13 |  | close out pending-KPTG-IntCorr-000805 | 2026-03-19 | 2026-03-20 | KPTG-SADV-003515 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-10 | TATE_-TRANSMIT-000028 | NA | Trade Partner | MEL05 TATE Structural Ceiling IFC drawings | 5 | 0 | 0 | NA | APPROVED | 2026-03-10 | WF - 000232 | NA | 2026-03-09 |  |  | 2026-03-10 | 2026-03-10 | TATE_-TRANSMIT-000028 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-09 | KPTG-TRANSMIT-003093 | 300 | Consultant | Generator Enclosure GA, Calculations and Reports | 11 | 5 | 0 | KPTG-IntCorr-001063 | APPROVED |  | NA | NA |  |  | Clarification from Harry - forwarded to all parties |  | 2026-03-25 | KPTG-TRANSMIT-003263 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-09 | KPTG-TRANSMIT-003094 | 301 | Consultant | Siemens - Psub Kiosk Documents Revised | 1 | 0 | 0 | KPTG-IntCorr-001062 | APPROVED |  | NA | NA |  |  | Clarification from Harry - forwarded to all parties |  | 2026-03-25 | KPTG-TRANSMIT-003260 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-09 | SKS Tech-TRANSMIT-000167 | NA | Trade Partner | ELECTRICAL SERVICES - FOR CONSTRUCTION DATA SHEET SUBMITTALS | 0 | 21 | 0 | NA | APPROVED |  | NA | NA |  |  | 21 FC docs - register updated and sent to all parties - KPTG-TRANSMIT-003096 1Doc Revision Mismatch Rejected - KPTG-IntCorr-001061 |  | 2026-03-10 | KPTG-TRANSMIT-003096 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-10 | D&E-TRANSMIT-000149 | NA | Trade Partner | MSDB-02 MECHANICAL SWITCHBOARD | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Error in document number |  | 2026-03-10 | KPTG-TRANSMIT-000515 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-09 | WSP ANZ-TRANSMIT-000022 | NA | Consultant | WSP - PDF Drawings - Issued for Permit Interim-COM | 3 | 0 | 0 | NA | APPROVED | 2025-12-09 |  | 122 | 2025-12-12 |  |  | 2025-12-10 | 2025-12-11 | KPTG-TRANSMIT-000309 | Closed | 3 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-10 | KPTG-WTRAN-008584 | NA | Trade Partner | Vapour Permeable Membrane - Wall | 0 | 1 | 0 | NA | APPROVED | 2026-03-10 | WF-004691 | NA | 2026-03-12 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-014064 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-10 | KPTG-IntCorr-010478 | NA | Consultant | C1 Cooling Tower Roof Framing Shop Drawings | 135 | 0 | 0 | NA | APPROVED | 2026-03-10 | WF-004692 | NA | 2026-03-16 |  |  |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-06 | Appselec-TRANSMIT-000022 | NA | Trade Partner | LV Cable Tech Data REV 2 | 0 | 1 | 0 | NA | APPROVED | 2026-03-10 | WF-000041 | NA | 2026-03-17 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-000125 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-05 | SIL-TRANSMIT-000010 | NA | Trade Partner | MEL11 COL)5-5 - ATS Documents for Approval | 0 | 13 | 0 | NA | REJECTED | [5 empty] | Documents are submitted wrong attachments, requested to resubmit. KPTG-IntCorr-000092 |  | 2026-03-06 | KPTG-IntCorr-000092 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-09 | RDSBIM-TRANSMIT-000172 | Na | Trade Partner | L03 ¦ PW ¦ IFC ¦ SUBMISSION | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2026-03-10 | KPTG-TRANSMIT-002798 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-09 | RDSBIM-TRANSMIT-000173 | NA | Trade Partner | L04 ¦ PW ¦ IFC ¦ SUBMISSION | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2026-03-10 | KPTG-TRANSMIT-002797 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-10 | D&E-TRANSMIT-000150 | NA | Trade Partner | MWYCCB - GROUND LEVEL - PLINTH LAYOUT ZONES - Issued For Manufacture | 2 | 1 | 0 | NA | REJECTED | [5 empty] | Drawing status is different |  | 2026-03-10 | KPTG-TRANSMIT-000516 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-10 | SKS Tech-TRANSMIT-000056 | NA | Trade Partner | TYPICAL SWITCHROOM SECTIONS | 1 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 2426 | 2026-03-18 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-015852 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-06 | SMEPS-TRANSMIT-000206 | NA | Trade Partner | Re: SME - M3S4 - BTU Shop Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-03-06 | 2384 | NA | 2026-03-16 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-04 | ADP-TRANSMIT-000262 | NA | Consultant | ADP MEL4561 - S2 -Update Hyd and FIP Drawings - HYD | 1 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 3913 | 2026-03-13 |  |  | 2026-03-10 | 2026-03-12 | KPTG-TRANSMIT-014180 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-09 | WSP ANZ-TRANSMIT-000022 | NA | Consultant | WSP - PDF Drawings - Issued for Permit Interim-ELC | 105 | 0 | 0 | NA | APPROVED | 2025-12-09 |  | 124 | 2025-12-12 |  |  | 2025-12-18 | 2025-12-22 | KPTG-TRANSMIT-000404 | Closed | 105 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-04 | ADP-TRANSMIT-000262 | NA | Consultant | ADP MEL4561 - S2 -Update Hyd and FIP Drawings - FIP | 1 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 3911 | 2026-03-13 |  |  | 2026-03-10 | 2026-03-12 | KPTG-TRANSMIT-014180 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-04 | RDSBIM-TRANSMIT-000239 | NA | Trade Partner | NXM3S2 ¦ LEVEL 01-B-1-048 CLEANERS-FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 3904 | 2026-03-11 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-04 | HDRAus-TRANSMIT-000419 | NA | Client | Concrete Lid Angle | 1 | 0 | 0 | NA | REJECTED | [5 empty] | The status inside and outside the document are wrong. |  | 2026-03-04 | KPTG-DA-005267 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-10 | ADP-TRANSMIT-000270 | NA | Consultant | MEL741 - Stage 4 Updated Hyd Drawings | 7 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 2424 | 2026-03-12 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-014624 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-03 | BASESG-IntCorr-000058 | NA | Trade Partner | Siemens IW L3 Cx Script | 0 | 1 | 0 | NA | APPROVED | 2026-03-04 | WF-004622 | NA | 2026-03-13 |  | D&E-TRANSMIT-000431 | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016197 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-05 | NXT-TRANSMIT-001367 | NA | Client | UPS Seismic | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | Transmitted to all as instructed, KPTG-IntCorr-010330 |  | 2026-03-05 | KPTG-TRANSMIT-013886 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-09 | LANSA-TRANSMIT-000098 | NA | Trade Partner | Levels 1 - 8 Drainage Drawings with BTR Cghanges | 16 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2026-03-10 | KPTG-TRANSMIT-002796 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-10 | Baigents-TRANSMIT-000071 | SPARK-CRFI-KPG-000061 | Trade Partner | Remaining Site Storage Precast Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 159 | 2026-03-17 |  | Bim360 review terminated by Lawden Constructed |  | 2026-08-25 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-09 | LANSA-TRANSMIT-000099 | NA | Trade Partner | Levels 1-8 Penetration Drawings with BTR Changes | 16 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2026-03-10 | KPTG-TRANSMIT-002795 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-10 | VIA Arch-TRANSMIT-000065 | NA | Consultant | Stairs and Lift Cores - Building Permit Issue Documentation | 14 | 0 | 0 | NA | REJECTED | [5 empty] | Status to be changed to Building Permit.KPTG-DA-001492 (Drawings resubmitted via VIA Arch-TRANSMIT-000072) |  | 2026-03-10 | KPTG-DA-001492 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-09 | A.S.H.-TRANSMIT-000059 |  | Trade Partner | ASH IFC drawings | 6 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-TRANSMIT-000297 |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-10 | D&E-TRANSMIT-000152 | SPARK-CRFI-KPG-000473 | Trade Partner | MWYCCB - LEVEL 1 PLINTH LAYOUT ZONE 6 & ZONE 7 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 160 | 2026-03-17 |  |  | 2026-04-16 | 2026-04-24 | KPTG-TRANSMIT-000691 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-10 | DS-TRANSMIT-000100 | NA | Trade Partner | HYD Shop Drawings - Issued for construction | 5 | 0 | 0 | NA | APPROVED | 2026-03-10 | WF-004702 | NA | 2026-03-26 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-014186 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-10 | Auspan-TRANSMIT-000059 | NA | Trade Partner | L3 L4 L5 shop drawings issued for approval | 11 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | #595 | 2026-03-17 |  |  | 2026-03-24 | 2026-03-25 | KPTG-SADV-003548 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-10 | HIP-TRANSMIT-000012 | NA | Trade Partner | Building - 08 - Additional Steel (Powerpack - Re - issued for Approval) | 8 | 0 | 0 | NA | APPROVED | 2026-03-10 | WF-000425 | NA | 2026-03-19 |  |  | 2026-03-20 | 2026-03-20 | HIP-TRANSMIT-000014 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-10 | GEMBA-D-TRANSMIT-000009 | NA | Consultant | NEXTDC GE1 ¦ Ground Floor - For Construction issue | 14 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 39 | 2026-03-13 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-000091 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-03 | KALLIBRE-TRANSMIT-000001 | NA | Trade Partner | MEL05 22x Door Frame Shop Drawings For Review | 1 | 0 | 0 | NA | APPROVED | 2026-03-10 | WF - 000234 | NA | 2026-03-17 |  | Additional review to security consultant as advised by Akshay (PC) | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-000501 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-03 | SEAPBU-TRANSMIT-000003 | NA | Trade Partner | Schneider FAT reports - ATS | 0 | 1 | 0 | NA | APPROVED | 2026-03-10 | WF - 000233 | NA | 2026-03-17 |  | NA | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-000449 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-10 | NXES-TRANSMIT-000048 | NA | Trade Partner | Re: Nexus - IFA Switchboard Drawings with Updated Cover Page | 13 | 0 | 0 | NA | APPROVED | 2026-03-11 | WF-000660 | NA | 2026-03-17 |  | 1drawings pennding. KPTG-IntCorr-000835- Copy of | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-002127, KPTG-TRANSMIT-002135 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-10 | NXES-TRANSMIT-000047 | NA | Trade Partner | Nexus - IFA Switchboard Drawings with Cover Page | 13 | 0 | 0 | NA | REJECTED | [5 empty] | Multiple drawings are included in a single document, so it has been rejected. |  | 2026-03-10 | KPTG-SADV-003356 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-10 | PFP PL-TRANSMIT-000001 | NA | Trade Partner | Level 2 Colo 4 Low level layout issued for approval | 1 | 0 | 0 | NA | APPROVED | 2026-03-10 | WF - 000235 | NA | 2026-03-17 |  | NA | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-000493 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-09 | A.S.H.-TRANSMIT-000064 |  | Trade Partner | ASH IFC drawings | 34 | 0 | 0 | NA | APPROVED | 2025-12-09 | WF-000098 | 60 | 2025-12-14 | 5 |  |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-10 | ARCST-TRANSMIT-000221 | NA | Trade Partner | Re: C3 Cooling Tower Upper Roof - Issued for Approval | 164 | 0 | 0 | NA | REJECTED | [5 empty] | Incomplete Title |  | 2026-03-10 | KPTG-IntCorr-010507 | Closed | 164 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-10 | NXT-TRANSMIT-001390 | NA | Trade Partner | : 5000A KXA End Feeder Box IFC Shop Drawings for Review | 1 | 0 | 0 | NA | APPROVED | 2026-03-10 | WF-004709 | NA | 2026-03-23 |  |  | 2026-07-13 | 2026-07-13 | ⁠KPTG-TRANSMIT-019597 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-10 | Tradetec-TRANSMIT-000063 | NA | Trade Partner | Technical Data Submissions | 0 | 2 | 0 | NA | APPROVED | 2026-03-10 | WF-000318 | NA | 2026-03-20 |  |  | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-001645 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-10 | fjc-TRANSMIT-000140 | NA | Consultant | Architectural Updates - RFIs, Facade Assembly Schedules, Wall Review Markup. | 5 | 0 | 0 | NA | APPROVED | 2026-03-10 | WF-000659 | #596 | 2026-03-13 |  |  | 2026-03-11 | 2026-03-11 | KPTG-SADV-003365 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-10 | NXT-TRANSMIT-001391 | NA | Trade Partner | Block C3 IFC Shop Drawings Submission – Zone C3 | 13 | 0 | 0 | NA | APPROVED | 2026-03-10 | WF-004710 | NA | 2026-03-23 |  | AS PER REQUESTED BY SEAN WORKFLOW IS TERMINATED FOR UPDATE NEW REVISION |  | 2026-05-20 | NA | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-10 | RDSBIM-TRANSMIT-000038 | NA | Trade Partner | 671CHP ¦ GROUND FLOOR CONCRETE PROFILE PLAN AND SECTION | 6 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 324 | 2026-03-17 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-000732 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-10 | LGCE-TRANSMIT-000008 | NA | Trade Partner | Basement 4 light and power | 2 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 326 | 2026-03-17 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-000742 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-10 | ccair-TRANSMIT-000005 | NA | Trade Partner | : Mechanical Builders works Drawings - Core & B4 - B1 - IFA | 6 | 0 | 0 | KPTG-IntCorr-000364 | APPROVED | 2026-03-11 | NA | 332 | 2026-03-17 |  | New TP drawings; Waiting for Kapitol advise; KPTG-IntCorr-000364. | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-000748 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-10 | Jangho-TRANSMIT-000014 | NA | Trade Partner | 671 Chapel St Project CONCEPT DRAWINGS@FT-01.REV02 | 34 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 328 | 2026-03-17 |  | Review voided; drawings to be superseded by Jangho |  | 2026-04-28 | NA | Closed | 34 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-09 | A.S.H.-TRANSMIT-000066 |  | Trade Partner | ASH IFC drawings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-TRANSMIT-000299 |  | 2026-01-12 | KPTG-TRANSMIT-000299 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-10 | KPTG-TRANSMIT-000579 | NA | Client | Client review of Facade DIP drawing | 61 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 329 | 2026-03-17 |  | Kapitol forwarded for Client review. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-10 | Auspan-TRANSMIT-000123 | NA | Trade Partner | Update precast dowel layout ground floor. Zone 4,5 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - No review required - Register and distribute, KPTG-TRANSMIT-000871 |  | 2026-03-10 | KPTG-TRANSMIT-000871 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-10 | Auspan-TRANSMIT-000124 | NA | Trade Partner | Precast shop drawings for construction. Ground floor. | 74 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - No review required - Register and distribute, KPTG-TRANSMIT-000873 |  | 2026-03-10 | KPTG-TRANSMIT-000873 | Closed | 74 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-10 | Auspan-TRANSMIT-000125 | NA | Trade Partner | Resubmit precast shop drawings for approval. Ground floor and level 1. | 33 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 473 | 2026-03-17 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-000985 | Closed | 33 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-10 | Auspan-TRANSMIT-000126 | NA | Trade Partner | 0G4014 for approval. | 1 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 475 | 2026-03-17 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-000971 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-10 | Auspan-TRANSMIT-000127 | NA | Trade Partner | Precast shop drawings for approval. Level 1 | 21 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to improper drawing PDF - KPTG-SADV-001264 |  | 2026-03-10 | KPTG-SADV-001264 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-10 | Auspan-TRANSMIT-000128 | NA | Trade Partner | Resubmit shop drawings for approval. Ground floor zone 4, 5. | 5 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | NA |  |  | As advised by Kapitol PC, No Action required, Trade partner is advised to submit IFC. KPTG-SADV-001246 |  | 2026-03-10 | KPTG-SADV-001246 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-10 | VAuspan-TRANSMIT-000129 | NA | Trade Partner | : Update already IFCed shop drawings. Ground floor. | 32 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - No review required - Register and distribute; KPTG-TRANSMIT-000877 |  | 2026-03-10 | KPTG-TRANSMIT-000877 | Closed | 32 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-10 | Auspan-TRANSMIT-000130: | NA | Trade Partner | Cast in plate detail SP4F | 0 | 1 | 0 | NA | APPROVED | 2026-03-10 | WF-000260 | NA | 2026-03-12 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-000918 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-10 | POTTSENG-TRANSMIT-000012 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 INGROUND - ZONE 3 & 5 LAYOUTS | 2 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 478 | 2026-03-10 |  |  | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-000948 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-09 | WilsonPD-TRANSMIT-000135 | SPARK-CRFI-KPG-000436 | Trade Partner | Hydraulic Services - Level 1 - Zone A & B - Water Layouts | 2 | 0 | 0 | NA | APPROVED | 2025-12-09 | WF-000099 | 61 | 2025-12-14 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-000469 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-16 | Auspan-TRANSMIT-000127 | NA | Trade Partner | Re: Precast shop drawings for construction. Stage 9 ground floor. | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. |  | 2026-03-16 | NA | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-10 | PFP PL-TRANSMIT-000071 | NA | Trade Partner | Roof Level Switch Room Zone C1 Penetration Layout IFA | 1 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 2422 | 2026-03-18 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-014937 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-10 | INGEN3D-TRANSMIT-000696 | NA | Consultant | I3D-378 Next DC M3 Stage 4 - Acoustic Wall - Revised IFC (04-03-2026) | 5 | 0 | 0 | NA | APPROVED | 2026-03-10 | WF-004712 | NA | 2026-03-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-10 | SMEPS-TRANSMIT-000127 | SPARK-CRFI-KPG-000583 | Trade Partner | Fire rated cabling - NEL-CNT-SME-2990-ELC-SAM-0018 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-11 | KPTG-TRANSMIT-000527 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-04 | PROLMC-TRANSMIT-000025 | NA | Trade Partner | Proline updated shop drawings 4-3-26 | 8 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 3915 | 2026-03-16 |  | Terminating as requested by William Duffield, KPTG-IntCorr-010636 | 2026-03-19 | 2026-03-19 | KPTG-IntCorr-011003 | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-05 | HDRAus-TRANSMIT-000421 | NA | Consultant | KPTG-DA-005267: Re: Concrete Lid Angle | 1 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 3917 | 2026-03-09 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-015343 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-10 | SMEPS-TRANSMIT-000128 | SPARK-CRFI-KPG-000583 | Trade Partner | Multicore cabling - NEL-CNT-SME-2990-ELC-SAM-0020 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-11 | KPTG-TRANSMIT-000529 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-26 | Civilex-TRANSMIT-000195 | NA | Trade Partner | Stage 2 Landscape Design Transmittal | 0 | 7 | 0 | NA | REJECTED | [5 empty] | 1. The drawing numbers and revision numbers are not given inside the drawings. 2. Not specified which project is this (Stage 2, Stage 3 or Sitewide) |  | 2026-03-05 | KPTG-DA-005285 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-05 | Tradetec-TRANSMIT-000387 | NA | Trade Partner | Tech Data - Sikagrout HES | 0 | 1 | 0 | NA | APPROVED | 2026-03-05 | WF-004630 | NA | 2026-03-18 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-014175 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-05 | ACG-TRANSMIT-000012 | NA | Trade Partner | Electronic security IFC | 6 | 0 | 0 | KPTG-IntCorr-000760 | APPROVED | 2025-12-08 | NA | 748 | 2025-12-10 |  | 1 IFA doc submitted along with ACG transmit - 00013 | 2026-01-07 | 2026-01-07 | KPTG-TRANSMIT-002359 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-05 | Civilex-TRANSMIT-000199 | NA | Trade Partner | Stage 2 - Landscape drawing transmittal | 0 | 7 | 0 | NA | REJECTED | [5 empty] | 1. The given document number seems to be Technical Data but on opening it seems to be a drawing. Technical data should have a cover page, but it seems that these document does not have a cover page and is named as technical data. 2. While opening the document, the document number seems to be incorrect. |  | 2026-03-05 | KPTG-DA-005297 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-10 | SMEPS-TRANSMIT-000129 | SPARK-CRFI-KPG-000583 | Trade Partner | Submains cabling - NEL-CNT-SME-2990-ELC-SAM-0021 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-11 | KPTG-TRANSMIT-000528 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-10 | SMEPS-TRANSMIT-000130 | SPARK-CRFI-KPG-000583 | Trade Partner | Coms Warnign Tape - NEL-CNT-SME-2990-ELC-SAM-0073 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-001554 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-10 | D&E-TRANSMIT-000452 | NA | Trade Partner | NXM3S4 - Roof Level Switchroom - Mechanical Duct Layout Zones - Issued For Approval | 4 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 2409 | 2026-03-17 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014801 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-10 | D&E-TRANSMIT-000453 | NA | Trade Partner | Roof Level Switchroom - Mechanical Duct Layout - Zone 1 | 1 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 2408 | 2026-03-17 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014803 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-10 | KPTG-TRANSMIT-014060 | NA | Consultant | DC ACTION: Nilsen Alternative Sample Submission | 0 | 4 | 0 | NA | APPROVED | 2026-03-10 | WF-004700 | NA | 2026-03-31 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-015491 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-10 | ADP-TRANSMIT-000259 | NA | Consultant | S4 - Updated names on Register (Electrical) | 30 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected Issues on Drawing statues & Drawing title |  | 2026-03-10 | KPTG-TRANSMIT-014072 | Closed | 30 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-10 | ZIA-TRANSMIT-000072 | NA | Trade Partner | M3S4 CSMS Network Topology (FOA-1) | 3 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 2443 | 2026-03-18 |  |  |  | 2026-04-21 | KPTG-TRANSMIT-016273 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-10 | SMEPS-TRANSMIT-000131 | SPARK-CRFI-KPG-000583 | Trade Partner | Power warning tape - NEL-CNT-SME-2990-ELC-SAM-0074 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-001452 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-10 | ZIA-TRANSMIT-000071 | NA | Trade Partner | Re: Stage4 - CSMS Sample Tech data submission for approval | 25 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due to incorrect revision number incorrect reason etc |  | 2026-03-10 | KPTG-TRANSMIT-014083 | Closed | 25 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-08 | Omnii-TRANSMIT-000003 | NA | Consultant | Fire Engineering Report | 1 | 0 | 0 | NA | APPROVED | 2025-12-09 | WF-000612 | 707 | 2025-12-11 |  |  | 2025-12-08 | 2025-12-08 | KPTG-TRANSMIT-002196 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-10 | KPTG-TRANSMIT-014059 | NA | Consultant | S4 - Proline Penetration Flashing Detail | 1 | 0 | 0 | NA | APPROVED | 2026-03-10 | 0 | 2447 | 2026-03-19 |  | The WF has been terminated as requested by Renee |  | 2026-05-21 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-10 | SKS Tech-TRANSMIT-000055 | NA | Trade Partner | Level 1 Zone C1 Containment - ELE | 8 | 0 | 0 | NA | APPROVED | 2026-03-10 | 0 | 2441 | 2026-03-17 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-016625 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-10 | SKS Tech-TRANSMIT-000055 | NA | Trade Partner | Level 1 Zone C1 Containment - TEL | 4 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 2439 | 2026-03-17 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016519 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-10 | SMEPS-TRANSMIT-000132 | SPARK-CRFI-KPG-000583 | Trade Partner | Conduit Glue - NEL-CNT-SME-2990-ELC-SAM-0075 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-001456 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-10 | SKS Tech-TRANSMIT-000045 | NA | Trade Partner | Re: M3-ELC-SKS-SA-C-0400-0005 LV Submains (IFC) | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-03-10 | KPTG-TRANSMIT-014069 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-10 | SMEPS-TRANSMIT-000133 | SPARK-CRFI-KPG-000583 | Trade Partner | Conduit Primer - NEL-CNT-SME-2990-ELC-SAM-0076 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-001449 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-10 | SMEPS-TRANSMIT-000095 | NA | Trade Partner | Final (WF-000212) TECH DATA ¦ CONSULTANT REVIEW ¦ EL ¦ SME ¦ IFA ¦ | 0 | 1 | 0 | NA | APPROVED | 2026-03-10 | WF-000212 | NA | 2026-03-13 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000440, KPTG-TRANSMIT-000441, KPTG-TRANSMIT-000442 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-05 | Tradetec-TRANSMIT-000388 | NA | Trade Partner | Camera Pole Foundation GA933 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing number inside and outside is wrong. |  |  | KPTG-DA-005294 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-05 | NXT-TRANSMIT-001374 | NA | Client | 100222: M3 STAGE 2 - Single Door Non-Firebolt Configuration - Sample | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document seems to have both the document number as well as the revision number also.. |  | 2026-03-05 | KPTG-DA-005296 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-05 | NXT-TRANSMIT-001378 | NA | Client | EOL test documentation for S3E units 25J0154-174 (excluding unit 167 retained at Somersby) | 0 | 20 | 0 | NA | APPROVED | [7 empty] | 2026-03-05 | KPTG-TRANSMIT-013913 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-01 | M.S.-TRANSMIT-000033 | NA | Trade Partner | WL01 - WL02 Updated Sample sheets | 0 | 2 | 0 |  | APPROVED | 2025-12-01 | WF-000636 |  | 2025-12-04 | [8 empty] | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-08 | RDSBIM-TRANSMIT-000034 | NA | Trade Partner | LEVEL 04 CONCRETE PROFILE PLAN | 5 | 0 | 0 | NA | APPROVED | 2025-12-08 | WF-000619 | 711 | 2025-12-10 |  |  | 2026-01-29 | 2026-01-29 | KPTG-TRANSMIT-002614 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-11-14 | CRSol-TRANSMIT-000053 | NA | Trade Partner | CRS Ceiling Shop Drawings for DH8 | 8 | 0 | 0 | NA | APPROVED | 2025-11-14 | NA | 3240 | 2025-11-28 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-014042 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-06 | Tradetec-TRANSMIT-000389 | NA | Trade Partner | Shop Drawing - Camera Pole Footing | 1 | 0 | 0 | NA | APPROVED | 2026-03-06 | WF-004795 | NA | 2026-03-17 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-015596 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-06 | M3-MEC-DEA-DS-B-0201-0047 | NA | Trade Partner | Stage 2 Office Fans - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-06 | WF-004658 | NA | 2026-03-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-06 | SMEPS-TRANSMIT-000207 | NA | Trade Partner | STAGE 2 - Jemena Easement updated drawings | 2 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 3925 | 2026-03-17 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-014760 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-06 | HDRAus-TRANSMIT-000423 | NA | Consultant | Stage 2 - Architectural Documentation Update | 15 | 2 | 0 | NA | APPROVED | 2026-03-06 | NA | 3927 | 2026-03-10 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-014230 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-06 | HDRAus-TRANSMIT-000424 | NA | Consultant | SW - Architectural Documentation - General Updates | 8 | 0 | 0 | NA | APPROVED | 2026-03-06 | NA | 3930 | 2026-03-10 |  |  | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-014237 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-10 | D&E-TRANSMIT-000455 | NA | Trade Partner | HS1 Securtiy Grilles | 0 | 1 | 0 | NA | APPROVED | 2026-03-10 | WF-004686 | NA | 2026-03-24 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-014726 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-10 | Stowe-A-TRANSMIT-000508 | NA | Trade Partner | Stowe - Tech Data Submission - 95mm2 4C+25mm earth X-HF-110 | 0 | 1 | 0 | NA | APPROVED | 2026-03-10 | WF-00469 | NA | 2026-03-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-10 | D&E-TRANSMIT-000456 | NA | Trade Partner | HS1 BMS documents | 0 | 2 | 0 | NA | REJECTED | [5 empty] | The document number seems different inside and outside document. |  | 2026-03-10 | KPTG-TRANSMIT-014063 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-10 | ZIA-TRANSMIT-000070 | NA | Trade Partner | M3S4 CSMS Network Topology (FOA-1) | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong Naming Conventions |  | 2026-03-10 | KPTG-TRANSMIT-014070 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-08 | RDSBIM-TRANSMIT-000035 | NA | Trade Partner | LOWER GROUND PARTITION WALL PLAN AND ELEVATIONS | 7 | 0 | 0 | NA | APPROVED | 2025-12-09 | WF-000620 | 717 | 2025-12-12 |  |  | 2025-12-18 | 2025-12-18 | KPTG-TRANSMIT-002309 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-10 | D&E-TRANSMIT-000347 | NA | Trade Partner | SFN - Removal of Threads Proposal | 0 | 11 | 0 | NA | APPROVED | 2026-03-10 | WF-000956 | NA | 2026-03-20 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-10 | KPTG-SADV-002332 | NA | Trade Partner | HAC Barcode Shop Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 1415 | 2026-03-16 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-002751 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-06 | RDSBIM-TRANSMIT-000117 | NA | Trade Partner | MLCSPR ¦ CHAPEL CARPARK LANDSCAPE KEY PLAN AND SECTION | 4 | 0 | 0 |  | APPROVED | 2026-03-11 | NA | 460 | 2026-03-18 |  | We need to confirm the reviewers. Kapitol Advice awaits:KPTG-IntCorr-005849 |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-10 | 4DW-TRANSMIT-000159 | NA | Consultant | Misc. Updates | 6 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 459 | 2026-03-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-06 | SIL-TRANSMIT-000011 | NA | Trade Partner | Missed Technical Submittal and BIM Models | 0 | 3 | 0 | NA | APPROVED | 2026-03-12 | WF-000049 | NA | 2026-03-17 |  | Attached document is a zip file, requested to resubmit:KPTG-IntCorr-000099 | 2026-03-12 |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-05 | D&E-TRANSMIT-000441 | NA | Trade Partner | Re: NXM3S4 - Ground & Level 1 - Builders Works Layout - Elevation Views - Issued For Approval | 2 | 0 | 0 | NA | APPROVED | 2026-03-19 | NA | 2581 | 2026-03-27 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-016795 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-05 | DRLL-TRANSMIT-000066 | NA | Trade Partner | Battery Room Modules Electrical Drawings IFC 04 | 8 | 0 | 0 | NA | APPROVED | 2026-03-05 | NA | 1413 | 2026-03-11 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-002765 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-06 | fjc-TRANSMIT-000139 | NA | Consultant | hitecturals - L5/L6 Terrace + BP5 Elevations | 14 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 592 | 2026-03-16 |  |  | 2026-03-10 | 2026-03-11 | KPTG-SADV-003363 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-11 | HIP-TRANSMIT-000008 | NA | Trade Partner | Fwd: Block C2 Load Bank IFC Shop Drawings Submission | 13 | 0 | 0 | NA | APPROVED | 2026-03-11 | WF-000426 | 13 | 2026-03-20 |  |  |  | 2026-03-17 | DRAFT-009339 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-11 | SMEPS-TRANSMIT-000128 | NA | Trade Partner | SME Shop Drawing Telecomunications IFC | 2 | 0 | 0 | NA | APPROVED | 2026-03-11 | WF - 000236 | NA | 2026-03-18 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-000452 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-08 | Hames-TRANSMIT-000085, 86 | NA | Trade Partner | Latest Updates Re wall types and wall details | 10 | 0 | 0 | KPTG-DA-000931, KPTG-IntCorr-000766 | APPROVED | 2025-12-09 | WF-000621 | 727 | 2025-12-09 |  |  | 2025-12-11 | 2025-12-11 | KPTG-TRANSMIT-002251 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-11 | HIP-TRANSMIT-000013 | NA | Trade Partner | Powerpack - Building - 08 - Mechanical Support Steel - Issued for Review | 4 | 0 | 0 | NA | APPROVED | 2026-03-11 | WF-000427 | NA | 2026-03-23 |  |  | 2026-03-16 | 2026-03-16 | DRAFT-009323 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-11 | INSULPAK-TRANSMIT-000012 | NA | Trade Partner | Re: HFF MSSB Revised Drawings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-03-11 | KAPITOL-INTCOR-001124 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-11 | SKS Tech-TRANSMIT-000057 | NA | Trade Partner | Re: Zones C1 & C2 Overall Lighting Compliance Conformance Report | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-03-11 | KPTG-RFI-006627 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-11 | LANSA-TRANSMIT-000100 | NA | Trade Partner | Roof Penetration IFC | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2026-03-11 | DRAFT-015750 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-11 | ARCST-TRANSMIT-000226 | NA | Trade Partner | C2 Cooling Tower Upper Gantry Grating - Issued for Approval | 137 | 0 | 0 | NA | APPROVED | 2026-03-11 | WF-004715 | NA | 2026-04-04 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-015542 | Closed | 137 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-10 | Civilex-TRANSMIT-000042 | NA | Trade Partner | UPT Shop Drawing Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | QA Error - Revision error inside doc |  | 2026-03-10 | KPTG-TRANSMIT-000690 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-10 | Civilex-TRANSMIT-000043 | NA | Trade Partner | Hydraulic Tech Data | 0 | 2 | 0 | KPTG-IntCorr-000456 | APPROVED | 2026-03-16 | WF-000243 | NA | 2026-03-19 |  | Clarification from Jarrod - Submitted 16/03/2026 | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-000871 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-10 | INGEN3D-TRANSMIT-000016 | NA | Trade Partner | Ground Floor (Level 1) - Cast in Dowels | 28 | 0 | 0 | NA | APPROVED | 2026-03-11 | WF-000226 | NA | 2026-03-16 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-000839 | Closed | 28 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-10 | TTW-TRANSMIT-000106 | NA | Consultant | Facade details - FT-04 FT-09a | 8 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 321 | 2026-03-13 |  | 3 drawings only approved | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-000892 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-11 | INSULPAK-TRANSMIT-000013 | NA | Trade Partner | HFF MSSB Revised Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 346 | 2026-03-24 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-11-19 | RDSBIM-TRANSMIT-000110 | NA | Trade Partner | LEVEL 15 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2025-12-09 | WF-000804 | 474 | 2025-12-09 |  |  | 2025-12-09 | 2025-12-09 | KPTG-SADV-004583 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-11 | ARCH-TRANSMIT-000032 | NA | Consultant | Precast elevation sheet 3 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Issued For information only. To be updated in Aconex and ACC. No review required. (Outlook mail: RE: [External] FW: KPTG-DA-000287: DESIGN PROGRAM - KEY DATES ACNXREF<1uIuH6hZXcMNq8sdkUdulB>) |  | 2026-03-11 | KPTG-IntCorr-000103 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-11 | SMEPS-TRANSMIT-000131 | NA | Trade Partner | SME Shop Drawing Telecomunications IFC | 1 | 0 | 0 | NA | APPROVED | 2026-03-11 | WF-000240 | NA | 2026-03-17 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-000461 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-11 | D&E-TRANSMIT-000156 | SPRK-CRFI-KPG-000540 | Trade Partner | CONTROL SPECIALIST SENSORS | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-24 | KPTG-TRANSMIT-000579 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-11 | SMEPS-TRANSMIT-000130 | NA | Trade Partner | SME Shop Drawing Telecomunications IFC | 1 | 0 | 0 | NA | APPROVED | 2026-03-11 | WF-000239 | NA | 2026-03-17 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-000458 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-11 | SMEPS-TRANSMIT-000129 | NA | Trade Partner | SME Shop Drawing Telecomunications IFC | 2 | 0 | 0 | NA | APPROVED | 2026-03-11 | WF-000238 | NA | 2026-03-17 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-000455 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-11 | D&E-TRANSMIT-000157 | SPRK-CRFI-KPG-000540 | Trade Partner | CONTROL PIPE SENSORS | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-24 | KPTG-TRANSMIT-000580 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-11 | Entire M-TRANSMIT-000044 | NA | Trade Partner | Commissioning Management Plan Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-03-11 | WF-004726 | NA | 2026-03-24 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-015541 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-11 | ARCST-TRANSMIT-000224 | NA | Trade Partner | C3 Cooling Tower Upper Gantry - Issued for Review | 102 | 0 | 0 | NA | APPROVED | 2026-03-11 | WF-004717 | 0 | 2026-04-06 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016134 | Closed | 79 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-10 | SKS Tech-TRANSMIT-000168 | NA | Trade Partner | For Construction submittals | 1 | 0 | 0 | NA | APPROVED | [5 empty] | FC Docs - Sent to all parties (Rejected document of trn # 167 - re-issued) |  | 2026-03-10 | KPTG-TRANSMIT-003100 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-11-25 | WilsonPD-TRANSMIT-000070 | NA | Trade Partner | Tech Data - Multiple | 0 | 5 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-11 | KPTG-TRANSMIT-000522 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-11-12 | RDSBIM-TRANSMIT-000107 | NA | Trade Partner | LEVEL 14 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2025-12-09 | WF-000730 | 466 | 2025-12-09 |  |  | 2025-12-12 | 2025-12-09 | KPTG-DA-002230 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-10 | PCForm-TRANSMIT-000145 | NA | Trade Partner | PT Grout for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-10 | WF-000321 | NA |  |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-001363 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-11 | D&E-TRANSMIT-000158 | SPARK-CRFI-KPG-000525 | Trade Partner | MWYCCB - GROUND LEVEL - RCP LAYOUT ZONES - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 161 | 2026-03-18 |  |  | 2026-04-15 | 2026-04-24 | KPTG-TRANSMIT-000693 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-11 | KALLIBRE-TRANSMIT-000006 | NA | Trade Partner | HANWHA Building 18 - Door Frame Shop Drawings IFC | 1 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 347 | 2026-03-13 |  |  |  | 2026-03-11 | KAPITOL-INTCOR-001129 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-11 | D&E-TRANSMIT-000159 | SPARK-CRFI-KPG-000376 | Trade Partner | FIRE MATRIX | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-23 | KPTG-TRANSMIT-000569 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-10 | D&E-TRANSMIT-000151 | SPARK-CRFI-KPG-000570 | Trade Partner | MSBD-2 MECHANICAL SWITCHBOARD | 1 | 0 | 0 | KPTG-IntCorr-002131 | APPROVED |  | NA | NA |  |  |  |  | 2026-03-25 | KPTG-TRANSMIT-000592 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-11 | WilsonPD-TRANSMIT-000168 | SPARK-CRFI-KPG-000510 | Trade Partner | Updated Hydraulic Layouts - Level 1 - Drainage Layouts | 4 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 162 | 2026-03-18 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-000677 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-11 | WOCEP-TRANSMIT-000003 | NA | Trade Partner | CSR PLASTERBOARD | 0 | 7 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-11 | RDSBIM-TRANSMIT-000064 | NA | Trade Partner | LEVEL 04 PARTITION WALL KEYPLAN AND ELEVATION | 3 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 1104 | 2026-03-17 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-003303 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-11 | RDSBIM-TRANSMIT-000065 | NA | Trade Partner | LEVEL 05 PARTITION WALL KEYPLAN AND ELEVATIONS | 2 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 1106 | 2026-03-17 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-003299 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-11 | RDSBIM-TRANSMIT-000066 | NA | Trade Partner | RDSBIM-TRANSMIT-000066 | 5 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 1108 | 2026-03-13 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-003295 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-11-27 | RDSBIM-TRANSMIT-000114 | NA | Trade Partner | ROOF CONCRETE PROFILE KEY PLAN | 2 | 0 | 0 | NA | APPROVED | 2025-12-09 | WF-000805 | 484 | 2025-12-09 |  |  | 2025-12-09 | 2025-12-09 | KPTG-DA-002232 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-11 | RDSBIM-TRANSMIT-000067 | NA | Trade Partner | LEVEL 04 RCP KEY PLAN AND LAYOU | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Attached wrong drawings |  | 2026-03-11 | KPTG-IntCorr-001067 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-11 | PARR-TRANSMIT-000045 | NA | Trade Partner | Fuel Services - L4 SECTIONS PENOS | 1 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 1110 | 2026-03-17 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-003275 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-11 | JCBa-TRANSMIT-000068 | NA | Consultant | First floor Structural Setout Plans - Zones 1-5 IFC | 5 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 481 | 2026-03-13 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-001014 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-11 | Auspan-TRANSMIT-000131 | NA | Trade Partner | Precast shop drawings for approval. Level 1 and 2. | 72 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 487 | 2026-03-18 |  |  | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-001056 | Closed | 72 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-11 | Auspan-TRANSMIT-000132: | NA | Trade Partner | Precast shop drawings for construction. Ground floor. | 33 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - No review required - Register and distribute, KPTG-TRANSMIT-000883 |  | 2026-03-11 | KPTG-TRANSMIT-000883 | Closed | 33 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-11 | JCBa-TRANSMIT-000069 | NA | Consultant | First floor Structural Setout Plans - Overall Plan IFC | 1 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 483 | 2026-03-13 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-000974 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-11 | Auspan-TRANSMIT-000133 | NA | Trade Partner | Precast shop drawings for approval. Level 1 | 21 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 485 | 2026-03-18 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-000999 | Closed | 21 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-11 | M.2-TRANSMIT-000010 | NA | Trade Partner | Electrical Services - Level 1 to 6 Penetration layouts | 15 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 489 | 2026-03-17 |  |  | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-001053 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-11 | PCForm-TRANSMIT-000039 | NA | Trade Partner | Fwd: Basement zone 1&2 propping plan | 1 | 0 | 0 | KPTG-IntCorr-000368 | APPROVED | 2026-03-12 | NA | 496 | 2026-03-18 |  | Waiting for Kapitol Advise - KPTG-IntCorr-000368 No distribution required as advised by Kapitol PC - KPTG-IntCorr-000369 | 2026-03-13 | 2026-03-13 | KPTG-IntCorr-000369 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-11 | WGAVIC-TRANSMIT-000079 | NA | Consultant | M2 - Stages 9-11 - Suspended Slab Detail Construction Issue | 1 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 416 | 2026-03-16 |  |  | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-001365 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-11-20 | RDSBIM-TRANSMIT-000111 | NA | Trade Partner | LEVEL 07 PARTITION WALL PLAN | 5 | 0 | 0 | NA | APPROVED | 2025-12-09 | WF-000806 | 477 | 2025-12-09 |  |  | 2025-12-09 | 2025-12-09 | KPTG-DA-002231 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-11 | ARCST-TRANSMIT-000223 | NA | Trade Partner | C3 Cooling Tower Upper Gantry Grating - Issued for Approval | 127 | 0 | 0 | NA | APPROVED | 2026-03-11 | WF-004716 | NA | 2026-03-24 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-016598 | Closed | 127 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-11 | LTEPRCST-TRANSMIT-000150 | NA | Trade Partner | NEXTDC STAGE 4: C02C12 (REV.2) | 1 | 0 | 0 | NA | APPROVED | 2026-03-11 | WF-004719 | NA | 2026-03-18 |  | The WF has been terminated by Finlay |  |  | NA | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-11 | Bianco-TRANSMIT-000049 | NA | Trade Partner | Connection to Canopy - FOR APPROVAL | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Both IFA and IFC documents are included in this transmittal |  | 2026-03-11 | KPTG-TRANSMIT-014122 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-10-29 | LTEPRCST-TRANSMIT-000137 | NA | Trade Partner | NEXTDC STAGE 04 - CORE 01 ISSUED FOR CONSTRUCTION | 4 | 0 | 0 | NA | APPROVED | 2025-10-29 | WF-003135 | NA | 2026-03-10 |  |  | 2026-03-11 | 2026-03-11 | KPTG-TRANSMIT-014129 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-11 | RDSBIM-TRANSMIT-000244 | NA | Trade Partner | NXM3S3 - GROUND FLOOR GENERAL ARRANGEMENT PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 3937 | 2026-03-21 |  | As requested by Kian -VOID (drawing is wrong) | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-014177 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-11 | WGAVIC-TRANSMIT-000080 | NA | Consultant | M2 Civil Main Works - Stormwater Update Construction Issue | 1 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 417 | 2026-03-16 |  |  | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-001437 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-11 | D&E-TRANSMIT-000457 | NA | Trade Partner | Pressure Relief Dampers - Issued for Approval | 0 | 4 | 0 | NA | APPROVED | 2026-03-11 | WF-004722 | 0 | 2026-04-01 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-014998 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-11 | ADP-TRANSMIT-000271 | NA | Consultant | Re: MEL741 - Stage 4 Ammended EL on Register | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Reason for rejection: different status |  | 2026-03-11 | KPTG-TRANSMIT-014120 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-11 | D&E-TRANSMIT-000460 | NA | Trade Partner | Re: MCC Schedules IFA Rev E | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to mismatch in the document number. |  | 2026-03-11 | KPTG-TRANSMIT-014119 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-11 | ccair-TRANSMIT-000101 | NA | Trade Partner | Level 11 Penetration Layout IFC | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2026-03-11 | DRAFT-015760 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-11-28 | RDSBIM-TRANSMIT-000115 | NA | Trade Partner | LEVEL 09 PARTITION WALL KEY PLAN | 3 | 0 | 0 | NA | APPROVED | 2025-12-09 | WF-000807 | 487 | 2025-12-09 |  |  | 2025-12-09 | 2025-12-09 | KPTG-DA-002229 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-11 | D&E-TRANSMIT-000458 | NA | Trade Partner | IW tanks - Issued for approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-11 | WF-004723 | NA | 2026-04-01 |  |  | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-014490 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-11 | D&E-TRANSMIT-000459 | NA | Trade Partner | Fwd: Heat Exchangers - Issued for Construction | 0 | 1 | 0 | KPTG-TRANSMIT-014121 | APPROVED | 2026-03-12 | WF-004740 | NA | 2026-03-26 |  | Advise seekED FOR FURTHER ACTION | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-015000 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-11 | PARR-TRANSMIT-000132 | NA | Trade Partner | NDC M3 Stage 4 - Fuel - BFS SCHEMATIC | 1 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 2622 | 2026-04-03 |  | ACC 2457 has been cancelled | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-016449 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-11 | SMEPS-TRANSMIT-000209 | NA | Trade Partner | SME - M3S4 - MDB-GLP Typical Shop Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 2458 | 2026-03-19 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-11 | ARCST-TRANSMIT-000221 | NA | Trade Partner | Re: RE: C3 Cooling Tower Upper Roof - Issued for Approval | 164 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED DUE TO WRONG TITLE |  | 2026-03-11 | KPTG-TRANSMIT-014128 | Closed | 164 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-11 | D&E-TRANSMIT-000448 | NA | Trade Partner | MCC/MxC Drawings - Issued for Approval | 8 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 2462 | 2026-03-19 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-015556 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-11 | D&E-TRANSMIT-000449 | NA | Trade Partner | Re: MCC/MxC Drawings - Issued for Approval | 2 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 2464 | 2026-03-19 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-015530 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-11 | M.S.-TRANSMIT-000057 | NA | Trade Partner | Level 2 wall panelling Shop drawings for IFC. | 5 | 0 | 0 |  | APPROVED | [5 empty] | Clarification required on IFC status. Kapitol Advice awaits: KPTG-SADV-003836, IFC drawings is updated to Document Register and transmitted to Trade & consultants |  | 2026-03-12 | KPTG-TRANSMIT-002543 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-11 | Auspan-TRANSMIT-000060 | NA | Trade Partner | L6-L9 column shop drawings issued for approval | 20 | 0 | 0 | NA | REJECTED | [5 empty] | Title of the documents are incorrect, requested to resubmit:KPTG-SADV-003371 |  | 2026-03-11 | KPTG-SADV-003371 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-11 | SMEPS-TRANSMIT-000132 | NA | Trade Partner | SME Shop Drawing Electrical | 4 | 0 | 0 | NA | APPROVED | 2026-03-11 | WF - 000242 | NA | 2026-03-18 |  | NA | 2026-03-13 | 2026-03-16 | KPTG-TRANSMIT-000478 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2025-12-08 | KPTG-TRANSMIT-002516 | NA | Consultant | All Remaining Signage IFC Shop Drawings | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-11 | Entire M-TRANSMIT-000015 | NA | Trade Partner | Battery Room Fan Electrical Schematics - IFA | 4 | 0 | 0 | NA | REJECTED |  |  | NA |  |  | Document no and Inside the PDF file is mismatch. Transmittal Rejected. |  | 2026-03-11 | KPTG-SADV-000521 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-11 | Hames-TRANSMIT-000005 | NA | Consultant | DHA7&A8 Defects Inspection - Inspection Report | 0 | 1 | 0 | KPTG-IntCorr-003195 | APPROVED |  | NA | NA |  |  | No Action Required |  |  | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-11 | NXT-TRANSMIT-000380 | NA | Client | M3 Updated Annexure FF to Match Stage 2 & 4 aconex | 0 | 1 | 0 | NA | APPROVED | [5 empty] | NXT-TRANSMIT-000379 superseded with NXT-TRANSMIT-000380-kapitol information Only-Action not required. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-11 | D&E-TRANSMIT-000348 | NA | Trade Partner | MaxCool FD - Issued for Construction | 0 | 1 | 0 |  | APPROVED |  | NA | NA |  |  | Distribution only |  | 2026-03-12 | KPTG-TRANSMIT-002747 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-11 | ASV-TRANSMIT-000023 | NA | Trade Partner | Civil Stormwater Site Plan FOA-3 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-SADV-001671, Send back to originator as there is difference in status. |  | 2026-03-12 | KPTG-SADV-001671 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-12 | Altaire-TRANSMIT-000006 | NA | Trade Partner | FIRE DETECTION SERVICES - SITE MASTER PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-03-12 | WF - 000243 | NA | 2026-03-19 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-000530 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-12 | fjc-TRANSMIT-000141 | NA | Consultant | Architecturals - RFIs / Design Updates | 7 | 1 | 0 | NA | APPROVED | 2026-03-12 | NA | #598 | 2026-03-17 |  |  | 2026-03-13 | 2026-03-16 | KPTG-SADV-003424 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-12 | RDSBIM-TRANSMIT-000245 | NA | Trade Partner | NXM3S3 ¦ GROUND FLOOR GENERAL ARRANGEMENT PLAN | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As instructed,by Kian no further action has been taken on this transmittal. - KPTG-IntCorr-010607 |  | 2026-03-12 | KPTG-IntCorr-010607 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-11 | RDSBIM-TRANSMIT-000038 | SPARK-CRFI-KPG-000178 | Trade Partner | MWYCCB ¦ LEVEL 01 CONCRETE PROFILE PLAN | 5 | 0 | 0 | NA | APPROVED |  | NA | 163 | 2026-03-19 |  |  | 2026-03-19 | 2026-05-08 | KPTG-TRANSMIT-000847 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2025-12-08 | KPTG-TRANSMIT-002517 | NA | Consultant | Updated - O4 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-12 | RDSBIM-TRANSMIT-000001 | NA | Trade Partner | NXGE01 ¦ GROUND FLOOR CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 42 | 2026-03-16 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-000088 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-11 | RDSBIM-TRANSMIT-000039 | NA | Trade Partner | MWYCCB ¦ GROUND FLOOR INTERNAL FITOUT PLAN - FEMALE WC | 2 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 164 | 2026-03-19 |  | Bim 360 review terminated by Moj |  | 2026-06-29 | KPTG-TRANSMIT-001357 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-12 | NXES-TRANSMIT-000049 | NA | Trade Partner | Nexus - L2 to L11 Penetration Layouts IFA Rev1 | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per the direction from Mark, we don't take any action these drawings. KPTG-SADV-003386 |  | 2026-03-12 | KPTG-SADV-003386 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-12 | KALLIBRE-TRANSMIT-000007 | NA | Trade Partner | Re: HANWHA Building 18 - Door Frame Shop Drawings IFC | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision No. |  | 2026-03-12 | KALLIBRE-TRANSMIT-000007 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-11 | Civilex-TRANSMIT-000044 | NA | Trade Partner | UPT Shop Drawing Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-11 | WF-000231 | NA | 2026-03-13 |  | TERMINATED TO SUBMIT AS A SD - NEEDS ACC REVIEW | 2026-03-12 | 2026-03-13 | KPTG-SADV-001187 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-11 | Hollow-TRANSMIT-000006 | NA | Trade Partner | L1- Shop drawings, Issued for approval_2 | 30 | 0 | 0 | NA | REJECTED | [5 empty] | QA Error - 2 dwgs with wrong drawing number |  | 2026-03-12 | KPTG-TRANSMIT-000725 | Closed | 30 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-11 | WAM-TRANSMIT-000729 | NA | Consultant | 80% DD issue - A19 Thermal Envelope Plans | 18 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 325 | 2026-03-13 |  |  | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-000908 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-11 | INGEN3D-TRANSMIT-000017 | NA | Trade Partner | Level 1-3 - Precast Columns & Cast in Dowels - IFA | 94 | 0 | 0 | NA | APPROVED | 2026-03-12 | WF-000234 | NA | 2026-03-16 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-000938 | Closed | 93 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-12 | KALLIBRE-TRANSMIT-000008 | NA | Trade Partner | Re: HANWHA Building 18 - Door Frame Shop Drawings Revision 3 IFC | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Revision No. is missing |  | 2026-03-12 | KAPITOL-INTCOR-001132 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-11 | BG&E Fac-TRANSMIT-000005 | NA | Consultant | FACADE F3P1 Performance Solution Report | 0 | 1 | 0 | NA | APPROVED | 2026-03-11 | WF-000905 | NA | 2026-03-16 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-003506 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-01 | ECBS-TRANSMIT-000032 | NA | Trade Partner | Revise of CL12 & CL12A - Armstrong HERADESIGN Acoustic Ceiling Tile System | 0 | 1 | 0 |  | APPROVED | 2025-12-01 | WF-000635 |  | 2025-12-03 | [8 empty] | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-09 | DS-TRANSMIT-000007 | NA | Trade Partner | HYDRAULIC DOCUMENTATIONS - AS BUILT | 7 | 0 | 0 | NA | APPROVED |  |  | NA |  |  | As-built drawings, Review not required. Updated and distributed to the Project Team. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-12 | ASV-TRANSMIT-000024 | NA | Trade Partner | Revised Civil Stormwater for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 419 | 2026-03-19 |  |  | 2026-03-20 | 2026-03-23 | KPTG-TRANSMIT-001606 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-12 | ZIA-TRANSMIT-000073 | NA | Trade Partner | M3S3 CSMS MDB AUX box Drawings (FOA-1) | 8 | 0 | 0 | NA | APPROVED | 2026-03-12 | WF-004743 | NA | 2026-03-30 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-12 | crossfir-TRANSMIT-000053 | NA | Trade Partner | Wet Fire - Level 10,11 &12 , IFA | 6 | 0 | 0 | NA | APPROVED | 2026-03-12 | WF-000963 | 553 | 2026-03-18 |  | NA | 2026-04-20 | 2026-04-21 | KPTG-SADV-006650 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-12 | ccair-TRANSMIT-000102 | NA | Trade Partner | Level 12 - 14 Penetration Drawings - IFC | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2026-03-12 | DRAFT-015802 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-06 | Civilex-TRANSMIT-000202 | NA | Trade Partner | Stage 2 - Landscape drawing transmittal | 7 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with the document number. |  | 2026-03-11 | KPTG-DA-005366 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-12 | Baigents-TRANSMIT-000072 | NA | Trade Partner | Site Storage Remaining Steel - IFA | 48 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing title inside the drawing and in Aconex seem different - KPTG-TRANSMIT-000531 |  | 2026-03-12 | KPTG-TRANSMIT-000531 | Closed | 48 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-11 | SMEPS-TRANSMIT-000134 | SPARK-CRFI-KPG-000583 | Trade Partner | Cat6A Cable | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-07 | KPTG-TRANSMIT-000617 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-12 | Bianco-TRANSMIT-000050 | NA | Trade Partner | Connection to Canopy - FOR APPROVAL | 6 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-03-12 | KPTG-IntCorr-010635 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-12 | ASV-TRANSMIT-000025 | NA | Trade Partner | Stage 9 Internal Hydraulic Services FOA-5 | 1 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 421 | 2026-03-19 |  |  | 2026-03-20 | 2026-03-23 | KPTG-TRANSMIT-001607 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-12 | DS-TRANSMIT-000101 | NA | Trade Partner | Hydraulic Shop Drawings - GF and L1 - Issued for Construction | 12 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 2471 | 2026-03-18 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-09 | TATE_-TRANSMIT-000034 | NA | Trade Partner | M2 DH11 HACS | 1 | 0 | 0 | NA | APPROVED |  |  | NA |  |  | IFC, Review not required, updated and distributed to the Project Team. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-12 | KALLIBRE-TRANSMIT-000009 | NA | Trade Partner | HANWHA Building 18 - Door Frame Shop Drawings Revision 3 IFC | 1 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 348 | 2026-03-14 |  |  | 2026-03-13 | 2026-03-14 | DRAFT-009302 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-12 | Leemark-TRANSMIT-000018 | SPARK-CRFI-KPG-000365 | Trade Partner | Transmittal of Ground Floor Dry Fire Shop Draiwngs - For Construction | 9 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 165 | 2026-03-19 |  |  | 2026-03-24 | 2026-05-01 | KPTG-TRANSMIT-000788 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-12 | Entire M-TRANSMIT-000016 | NA | Trade Partner | Mechanical shop drawings issue | 15 | 0 | 0 | NA | APPROVED | 2026-03-12 | WF - 000245 | NA | 2026-03-16 |  | IFC Drawings | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-000471 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-12 | Entire M-TRANSMIT-000016 | NA | Trade Partner | Mechanical shop drawings issue -IFA | 6 | 0 | 0 | NA | APPROVED | 2026-03-12 | WF - 000244 | NA | 2026-03-18 |  | IFA Drawings for consultant approval. | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-000494 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-12 | ASV-TRANSMIT-000026 | NA | Trade Partner | Stage 11 Internal Hydraulic Services FC-1 | 1 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 423 | 2026-03-16 |  |  | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-001441 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-12 | Leemark-TRANSMIT-000019 | SPARK-CRFI-KPG-000317 | Trade Partner | Transmittal of Dry Fire Shop Draiwngs - For Approval | 2 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 166 | 2026-03-19 |  |  |  | 2026-04-07 | KPTG-TRANSMIT-000618 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-12 | D&E-TRANSMIT-000162 | SPARK-CRFI-KPG-000586 | Trade Partner | PIPING VALVES | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-08 | KPTG-TRANSMIT-000621 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-12 | ccair-TRANSMIT-000103 | NA | Trade Partner | Level 15 Penetration Layout - IFC | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2026-03-12 | DRAFT-015810 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-12 | ZIA-TRANSMIT-000074 | NA | Trade Partner | Stage4 - CSMS Sample Tech data submission for approval | 0 | 27 | 0 | NA | APPROVED | 2026-03-12 | 4751 | NA | 2026-04-08 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-015941 | Closed | 27 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-12 | Baigents-TRANSMIT-000073 | NA | Trade Partner | REMAINING SITE STORAGE STEEL - IFA | 48 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected as per Jed's advice to add latest updated drawings. |  | 2026-03-12 | KPTG-TRANSMIT-000536 | Closed | 48 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-09 | SC-TRANSMIT-000031 | NA | Trade Partner | VQ27 Secondary Steel IFC | 10 | 0 | 0 | KPTG-SADV-003075 | APPROVED | [5 empty] | 1) Clarification on drawing status: Trader has submitted first revision of Drawing as IFC 2) As per the direction from the Project Coordinator Ms alexia, ot is instructed to transmit drawing as IFC |  | 2025-12-10 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-12 | ASV-TRANSMIT-000027 | NA | Trade Partner | Stage 10 Internal Hydraulic Services | 1 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 425 | 2026-03-18 |  |  | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-001442 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-10 | NXT-TRANSMIT-001387 | NA | Client | M3 - CFD External Report | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Shared with the broader team |  | 2026-03-12 | KPTG-TRANSMIT-014273 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-12 | ccair-TRANSMIT-000104 | NA | Trade Partner | Roof Penetration Layout - IFC | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2026-03-12 | DRAFT-015814 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-11 | Stowe-A-TRANSMIT-000510 | NA | Trade Partner | Stowe - Tech Data Submission - Busduct Rain Hood - Type 1 | 0 | 1 | 0 | NA | APPROVED | 2026-03-11 | WF-004730 | NA | 2026-03-24 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-016372 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-11 | Stowe-A-TRANSMIT-000511 | NA | Trade Partner | Stowe - Tech Data Submission - Busduct Rain Hood Type 2 | 0 | 1 | 0 | NA | APPROVED | 2026-03-11 | WF-004732 | NA | 2026-03-24 |  | Due to VPN issues close out processed on 10/04/2026 | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-015681 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-11 | Stowe-A-TRANSMIT-000512 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - LINEUP SCHEMATICS - 11.03.2026 | 18 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 3935 | 2026-03-17 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014401 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-11 | Stowe-A-TRANSMIT-000513 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - LOAD BANK & OVERALL SCHEMATIC - 11.03.2026 | 2 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 3936 | 2026-03-17 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014405 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-11 | NXT-TRANSMIT-001392 | NA | Client | Data Hall B4 | 0 | 13 | 0 | NA | APPROVED |  | NA | NA |  |  | As-Built |  | 2026-03-11 | KPTG-TRANSMIT-014131 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-11 | D&E-TRANSMIT-000461 | NA | Trade Partner | NXM3S2 - Refrigeration Schematic + Lower Ground / Ground / Level 01 & Upper Roof - Issued For Construction | 16 | 0 | 0 | NA | APPROVED | 2026-03-11 | NA | 3940 | 2026-03-17 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014375 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-09 | MCM Tile-TRANSMIT-000006 | NA | Trade Partner | Expansion Joints MLC | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document has no Document Number ,Title and Revision |  | 2025-12-09 | KPTG-SADV-003082 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-11 | Stowe-A-TRANSMIT-000514 | NA | Trade Partner | Stowe - Tech Data - IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-03-11 | KPTG-TRANSMIT-014126 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-11 | ASV-TRANSMIT-000154 | NA | Trade Partner | Hydraulic Samples for Approval | 0 | 4 | 0 | NA | APPROVED | 2026-03-11 | WF-004734 | NA | 2026-03-23 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-015301 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-12 | WGAVIC-TRANSMIT-000081 | NA | Consultant | M2 - Stage 11 - Ground Floor Slab Construction Issue | 3 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 428 | 2026-03-17 |  |  | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-001443 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-12 | ASV-TRANSMIT-000023 | NA | Trade Partner | Civil Stormwater Site Plan FOA-3 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-SADV-001671, Difference in status of documents. to be resubmitted. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-12 | RDSBIM-TRANSMIT-000068 | NA | Trade Partner | LEVEL 04 RCP KEY PLAN AND LAYOUT | 5 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 1117 | 2026-03-17 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-003352 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-12 | KETE-TRANSMIT-000041 | NA | Trade Partner | Submission – roof louvre drawings | 5 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 1113 | 2026-03-17 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-003348 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-12 | SCG2014-TRANSMIT-000001 | NA | Consultant | Updated IFCN drawings for security | 37 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 1122 | 2026-03-16 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-003356 | Closed | 37 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-12 | VAE-Grp-TRANSMIT-000137 | NA | Trade Partner | NXD1S2 - IFC - MECHANICAL - DETAILS - SHEET 5 | 1 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 1124 | 2026-03-16 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-003157 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-12 | Omnii-TRANSMIT-000004 | NA | Consultant | Fire Engineering Report Revision A | 0 | 1 | 0 | NA | APPROVED | 2026-03-12 | NA | 1119 | 2026-03-16 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-003118 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-12 | TTW-TRANSMIT-000060 | NA | Consultant | Updated Precast Details | 1 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 1115 | 2026-03-16 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-003122 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-09 | M.S.-TRANSMIT-000035 | NA | Trade Partner | FSG12 - Radii SS 316 Robe Hook | 0 | 1 | 0 | NA | APPROVED | 2025-12-09 | WF-000662 |  | 2025-12-12 |  |  |  | 2026-01-14 | KPTG-TRANSMIT-002074 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-12 | NXT-TRANSMIT-001393 | NA | Client | PDU-ENB4-04 - test sheet | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | As Built |  | 2026-03-12 | KPTG-TRANSMIT-014262 | Open | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-11 | HDRAus-TRANSMIT-000426 | NA | Consultant | Stage 2 - Office Wall Panel Drawing Discrepancies | 2 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 3946 | 2026-03-16 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-014470 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-12 | D&E-TRANSMIT-000467 | NA | Trade Partner | ISSUED FOR APPROVAL - LEVEL 1 - SFN PIPE LAYOUTS | 8 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 2478 | 2026-03-20 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016525 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-12 | SMEPS-TRANSMIT-000210 |  | Trade Partner | SME - DRAWINGS IFA PART SUBMISSIONS | 2 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 2473 | 2026-03-20 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-016992 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-12 | D&E-TRANSMIT-000463 | NA | Trade Partner | NXM3S4 - Ground - SFN Pipe Layout Zones - Issued For Approval | 7 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 2469 | 2026-03-20 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016534 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-12 | KPTG-IntCorr-010643 | NA | Trade Partner | Stage 2 - Landscape Transmittal - Updated Naming | 6 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 3943 | 2026-03-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-12 | ADP-TRANSMIT-000272 | NA | Consultant | MEL4780 - ADP Updated EL drawing | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Just NEED TO inform for Trade Partners as per request from william |  | 2026-03-12 | KPTG-TRANSMIT-014257 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-12 | ADP-TRANSMIT-000273 | NA | Consultant | MEL4780 - ADP Updated EL drawings | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Just need to inform all Trade Partners as per request from william |  | 2026-03-12 | KPTG-TRANSMIT-014254 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-12 | Nilsen3-TRANSMIT-000058 | NA | Trade Partner | NXM3S4 ¦ Nilsen ELC Shop Drawings - FOA #1 | 3 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 2477 | 2026-03-20 |  | FOR ELC-DOC | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-015820 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-12 | Nilsen3-TRANSMIT-000058 | NA | Trade Partner | Nilsen ELC Shop Drawings-TEL | 1 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 2485 | 2026-03-20 |  | FOR TEL DOC | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-015836 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-09 | ARCH-TRANSMIT-000123 | NA | Consultant | MLC - SPR - AQC - Level 2 - WC walls update | 4 | 0 | 0 | NA | APPROVED | 2025-12-09 |  | 373 | 2025-12-16 |  |  |  | 2025-12-11 | KPTG-SADV-003122 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-12 | Civilex-TRANSMIT-000206 | NA | Trade Partner | Stage 2 - Landscape Planter box shop drawing | 1 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 3947 | 2026-03-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-12 | D&E-TRANSMIT-000464 | NA | Trade Partner | NXM3S2 - Ground & Level 01 - Mech Elec Layout B1 & B2 - Issued For Construction | 3 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 3951 | 2026-03-19 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014380 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-12 | ADP-TRANSMIT-000274 | NA | Consultant | ADP MEL4561 - HV Room Design Changes Impacted Drawing Update (HYD) | 1 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 3949 | 2026-03-16 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014412 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-12 | DS-TRANSMIT-000102 | NA | Trade Partner | HYD SITE - DRAINAGE | 1 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 3953 | 2026-03-15 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-014461 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-12 | D&E-TRANSMIT-000465 | NA | Trade Partner | NXM3S2 - Level 01 - Mechanical Duct Layout - Zone 3 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 3955 | 2026-03-19 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014387 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-12 | D&E-TRANSMIT-000468 | NA | Trade Partner | NXM3S2 - Lower Ground - Mechanical Duct Layout - Zone 3 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 3958 | 2026-03-19 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014389 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-12 | D&E-TRANSMIT-000469 | NA | Trade Partner | NXM3S2 - Lower Ground - Mechanical Duct Layout - Zone 4 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 3959 | 2026-03-19 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014393 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-12 | D&E-TRANSMIT-000466 | NA | Trade Partner | NXM3S2 - Lower Ground - Mechanical Duct Layout - Zone 6 - Issued For Construction | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Same revision |  | 2026-03-12 | KPTG-TRANSMIT-014280 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-12 | D&E-TRANSMIT-000163 | NA | Trade Partner | THERMAL INSULATION | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-12 | Auscool-TRANSMIT-000014 | NA | Trade Partner | Slab Penetrations – Whole Building | 50 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 498 | 2026-03-19 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-001273 | Closed | 50 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-09 | ARCH-TRANSMIT-000124 | NA | Consultant | MLC - SPR - Drawing update ARCH-CADV-000646 | 5 | 0 | 0 | NA | APPROVED | 2025-12-09 |  | 374 | 2025-12-16 |  |  | 2025-12-11 | 2025-12-11 | KPTG-SADV-003123 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-12 | Auspan-TRANSMIT-000067 | NA | Trade Partner | Precast shop drawings for approval. Basement. | 24 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 494 | 2026-03-19 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-001002 | Closed | 24 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-12 | Auspan-TRANSMIT-000134 | NA | Trade Partner | Update precast dowel layout zone 1, 2 ground floor | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Returned to Trade Partner for clarification by Kapitol PC - KPTG-SADV-001304 |  | 2026-03-12 | KPTG-SADV-001304 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-12 | Auspan-TRANSMIT-000135 | NA | Trade Partner | Precast shop drawings for construction. Ground floor. | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - No review required - Register and distribute- KPTG-TRANSMIT-000909 |  | 2026-03-12 | KPTG-TRANSMIT-000909 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-12 | Auspan-TRANSMIT-000136 | NA | Trade Partner | Precast shop drawings for approval. Level 1. | 22 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 501 | 2026-03-19 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-001078 | Closed | 22 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-12 | Rinco-TRANSMIT-000033 | NA | Trade Partner | Structural - Ground Floor Loading Plan | 1 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 503 | 2026-03-16 |  |  | 2026-03-20 | 2026-03-20 | Rinco-TRANSMIT-000033 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-12 | JCBa-TRANSMIT-000070 | NA | Consultant | A-31, A-32 – PRECAST & GA ELEVATIONS IFC | 21 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 505 | 2026-03-16 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-001101 | Closed | 21 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-12 | Rinco-TRANSMIT-000034 | NA | Consultant | Structural drawings Issued for Construction | 10 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 508 | 2026-03-16 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-001011 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-12 | PCForm-TRANSMIT-000040 | NA | Trade Partner | Stair shop drawings | 36 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 512 | 2026-03-19 |  | WF closed; Issues are not assigned to the originator. Waiting for Kapitol to finalise. | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-001564 | Closed | 36 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-12 | RDSBIM-TRANSMIT-000039 | NA | Trade Partner | 671CHP ¦ BASEMENT 4A TO BASEMENT 1 CORE WALL PLAN AND ELEVATIONS | 3 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 356 | 2026-03-23 |  | 336 superseded; New review has been issued for Consultant review - ACC#356 as advised by Kapitol PC. Review voided as drawings updated. | 2026-04-05 | 2026-04-05 |  | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-12 | Jangho-TRANSMIT-000019 | NA | Trade Partner | 671 Chapel St Project PMU shop drawings （UNFINISHED）Rev01 | 40 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 333 | 2026-03-19 |  | Review voided; drawings to be superseded by Jangho |  | 2026-04-28 | NA | Closed | 40 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-11-28 | ARCH-TRANSMIT-000116 | NA | Consultant | MLC - SPR - Drawing Update | 7 | 0 | 0 | NA | APPROVED | 2025-11-29 |  | 360 | 2025-12-04 | 5 |  | 2025-12-09 | 2025-12-09 | KPTG-SADV-003070 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-12 | B Smart-TRANSMIT-000063: | NA | Consultant | Re: A03, A18 IFC | 1 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 337 | 2026-03-16 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-000736 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-12 | B Smart-TRANSMIT-000062 | NA | Consultant | A03, A18 IFC | 17 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 339 | 2026-03-16 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-000963 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-12 | Stowe-A-TRANSMIT-000516 | NA | Trade Partner | Stowe Commissioning Implementation Plan - Issued For Construction | 0 | 1 | 0 | NA | APPROVED | 2026-03-12 | NA | NA |  |  | IFC |  | 2026-03-12 | KPTG-TRANSMIT-014268 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-12 | TATE_-TRANSMIT-000034 | NA | Trade Partner | complete set of drawings | 10 | 0 | 0 | Fatima to confirm | APPROVED | 2026-03-16 | NA | 1424 | 2026-03-19 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-12 | Altaire-TRANSMIT-000094 | NA | Trade Partner | Dry Fire O&M, Certificate & Commissioning document Sample | 6 | 0 | 0 | NA | REJECTED | [5 empty] | The drawing number is missing for the documents. |  | 2026-03-12 | KPTG-DA-005418 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-12 | NXT-TRANSMIT-000381 | NA | Client | 000230-110693 Schematics - As Built | 98 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Distribution only |  | 2026-03-12 | KPTG-TRANSMIT-002746 | Closed | 98 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-12 | NXT-TRANSMIT-000382 | NA | Client | End of line test documentation (ITP_QA docs) for 25J0144-153 | 0 | 10 | 0 | KPTG-IntCorr-003203 | APPROVED |  | NA | NA |  |  | No Action Required |  | 2026-03-13 | NA | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-12 | Altaire-TRANSMIT-000029 | NA | Trade Partner | M3DH78 - Altaire - Practical completion documents | 17 | 1 | 0 | KPTG-IntCorr-003204 | APPROVED | 2026-03-23 | NA | 1437 | 2026-03-27 |  | 1 Document pending | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-002839 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-12 | HDRAus-TRANSMIT-000079 | NA | Consultant | Update of Door Schedule in line with Stage 2 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Information only |  | 2026-03-12 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-02 | KPTG-TRANSMIT-013681 | NA | Trade Partner | Issue to NEXTDC - Joinery Shop Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-03-03 | NA | 3892 | 2026-03-09 |  |  | 2026-03-06 | 2026-03-12 | KPTG-TRANSMIT-014255 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-11-28 | Fredon T-TRANSMIT-000002 | NA | Trade Partner | Audio Visual Drawings for Approval | 5 | 0 | 0 | NA | APPROVED | 2025-11-28 |  | 359 | 2025-12-05 | 4 |  | 2025-12-09 | 2025-12-09 | KPTG-SADV-003077 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-12 | D&E-TRANSMIT-000462 | NA | Trade Partner | ISSUED FOR APPROVAL - ROOF LEVEL - CHILLER ROOM SECTIONS & LAYOUT | 2 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 2467 | 2026-03-19 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-015247 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-12 | Stanmor-TRANSMIT-000001 | NA | Trade Partner | Sample submissions - fixing material - waterproofing, adhesive, grout, silicon | 0 | 6 | 0 | NA | REJECTED | [5 empty] | Title & discipline of documents are incorrect, requested them to resubmit: KPTG-SADV-003851 |  | 2026-03-12 | KPTG-SADV-003851 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-12 | Stanmor-TRANSMIT-000002 | NA | Trade Partner | Sample submission - engineered screed | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Title and discipline of document are incorrect, requested to resubmit: KPTG-SADV-003852 |  | 2026-03-12 | KPTG-SADV-003852 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-12 | KPTG-IntCorr-005893 | NA | Trade Partner | Samples | 0 | 1 | 0 | NA | APPROVED | 2026-03-12 | WF-000872 | NA | 2026-03-20 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-002654 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-12 | KPTG-IntCorr-005915 | NA | Trade Partner | Re: Samples | 0 | 4 | 0 | NA | APPROVED | 2026-03-12 | WF-000871 | NA | 2026-03-20 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-002661 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-10-14 | DS-TRANSMIT-000070 | NA | Trade Partner | Updated GF and L01 Drainage | 2 | 0 | 0 | NA | APPROVED | 2025-10-14 | NA | 3013 | 2025-10-24 |  |  | 2026-03-11 | 2026-03-12 | KPTG-TRANSMIT-014228 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-12 | Appselec-TRANSMIT-000023 | NA | Trade Partner | Patch cords - Technical Data | 0 | 1 | 0 | NA | APPROVED | 2026-03-12 | WF-000048 | NA | 2026-03-18 |  |  |  | 2026-03-20 | KPTG-TRANSMIT-000178 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-12 | Appselec-TRANSMIT-000024 | NA | Trade Partner | Tech Data No Longer In Use | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | No longer in use data, transmitted to trade & client |  | 2026-03-12 | KPTG-TRANSMIT-000085 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-10-14 | DS-TRANSMIT-000071 | NA | Trade Partner | Updated GF and L01 Penetrations | 2 | 0 | 0 | NA | APPROVED | 2025-10-14 | NA | 3015 | 2025-10-28 |  |  | 2026-03-10 | 2026-03-12 | KPTG-TRANSMIT-014219 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-12 | KPTG-IntCorr-000120 | NA | Client | Building Permit for upload | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | UPLOADED INTO DOCUMENT REGISTER AND TRANSMITTED TO CLIENT & TRADE PARTNERS | 2026-03-12 | 2026-03-12 | KPTG-TRANSMIT-000086 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-09 | VAE-Grp-TRANSMIT-000085 | NA | Trade Partner | MECHANICAL - SAMPLE - REFRIGERATION PIPE BRACKETS | 0 | 1 | 0 | NA | APPROVED | [5 empty] | Register Update Only - Done | 2025-12-09 |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-12 | SMEPS-TRANSMIT-000134 | NA | Trade Partner | ROIP Drawings | 21 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings mismatch in the document register and inside PDF fie. |  | 2026-03-12 | KPTG-TRANSMIT-000466 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-12 | SMEPS-TRANSMIT-000133 | NA | Trade Partner | BOM final | 0 | 3 | 0 | NA | APPROVED | 2026-03-12 | WF - 000246 | NA |  |  |  | 2026-03-19 | 2026-04-03 |  | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-12 | TTPM-TRANSMIT-000004 | NA | Client | Mel05-C4 ¦ OFCI Equipment Preservation Guidelines | 0 | 6 | 0 | NA | APPROVED |  | NA | NA |  |  | Project management schedule distribution for all trades and client. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-10 | SMEPS-TRANSMIT-000126 | SPARK-CRFI-KPG-000576 | Trade Partner | Seismic Restraint | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-10 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-13 | KPTG-WTRAN-008782 | NA | Trade Partner | PYROPANEL DOOR | 0 | 1 | 0 | NA | APPROVED | 2026-03-13 | WF-004768 | NA | 2026-03-31 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-015428 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-12 | INDS-TRANSMIT-000032 | NA | Trade Partner | Fire Penetrations, Level 1 to 27 | 27 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | ISSUE TO FJC AND 3 PARTIES. | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-002005 | Closed | 27 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-12 | RDSBIM-TRANSMIT-000040 | NA | Trade Partner | MWYCCB ¦ GROUND FLOOR INTERNAL FITOUT PLAN - MALE WC | 2 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 167 | 2026-03-20 |  | Bim360 review terminated bu Moj |  | 2026-06-29 | KPTG-TRANSMIT-001358 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-13 | D&E-TRANSMIT-000164 | SPARK-CRFI-KPG-000540 | Trade Partner | D&E-TRANSMIT-000164 CONTROL THERMOSTAT | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-24 | KPTG-TRANSMIT-000588 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-13 | D&E-TRANSMIT-000165 | NA | Trade Partner | CONTROL NIAGRA MASTER | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | 2026-03-20 |  | Terminated as per Peter advise |  | 2026-08-11 | KPTG-SADV-006375 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-12 | TTW-TRANSMIT-000105 | NA | Consultant | BP4 - Structural Certification Issue | 1 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 327 | 2026-03-16 |  | In response to KPTG-TRANSMIT-000660 - TTW give clarification via TTW-tran-107 hence processed the document |  | 2026-03-17 | KPTG-TRANSMIT-000771 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-01 | Arco-TRANSMIT-000005 | NA | Trade Partner | SERIES 2 - ALUMINUM ROLLER SHUTTERS | 5 | 0 | 0 |  | REJECTED | [5 empty] | Drawings do not revision history Details, requested them to resubmit | [6 empty] | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-09 | RDSBIM-TRANSMIT-000036 | NA | Trade Partner | LEVEL 02 PARTITION WALL PLAN AND ELEVATION | 3 | 0 | 0 | NA | APPROVED | 2025-12-09 | WF-000624 | 729 | 2025-12-11 |  |  | 2025-12-18 | 2025-12-18 | KPTG-TRANSMIT-002322 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-12 | WAM-TRANSMIT-000730 | NA | Consultant | WAM ARCH - 95% DD - Facade Details | 54 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 329 | 2026-03-16 |  | BY MISTAKE PROCESSED 52 DRAWINGS - HENCE MADE ADDITIONAL REVIEW 373 | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-000941 | Closed | 52 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-12 | Civilex-TRANSMIT-000045 | NA | Trade Partner | Micropile Design addendum | 0 | 1 | 0 | NA | APPROVED | 2026-03-12 | WF-000236 | NA | 2026-03-16 |  |  |  | 2026-03-17 | KPTG-TRANSMIT-000778 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-12 | Civilex-TRANSMIT-000046 | NA | Trade Partner | Alimak Pile Design Package | 0 | 1 | 0 | NA | REJECTED | [5 empty] | QA Error - Revision field wrong |  | 2026-03-12 | KPTG-TRANSMIT-000731 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-12 | Civilex-TRANSMIT-000047 | NA | Trade Partner | Stremaform - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-12 | WF-000237 | NA | 2026-03-17 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-001121 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-12 | Civilex-TRANSMIT-000048 | NA | Trade Partner | Grease Interceptor Trap | 0 | 1 | 0 | KPTG-IntCorr-000463 | APPROVED | 2026-03-16 | WF-000242 | NA | 2026-03-19 |  | Clarification required from John - Submitted on 16/03/2026 | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-000853 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-12 | D&E-TRANSMIT-000009 | NA | Trade Partner | Woolworths Early Works Shop Drawings - IFA | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Not a proper shop dwg submission |  | 2026-03-12 | KPTG-TRANSMIT-000741 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-13 | ASV-TRANSMIT-000149 | NA | Trade Partner | Hydraulic Sample - Dual Check Valve | 0 | 1 | 0 | NA | APPROVED | 2026-03-13 | WF-004426 | NA | 2026-03-18 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014293 | Open | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-13 | SMEPS-TRANSMIT-000135 | NA | Trade Partner | Roip Heat Map & Bill of Material | 2 | 0 | 0 | NA | APPROVED | 2026-03-13 | WF - 000247 | NA | 2026-03-20 |  | NA | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-000545 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-13 | SMEPS-TRANSMIT-000136 | NA | Trade Partner | Power and Lighting Lay outs | 8 | 0 | 0 | NA | APPROVED | 2026-03-13 | WF - 000248 | NA | 2026-03-20 |  | NA | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-000513 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-13 | D&E-TRANSMIT-000166 | SPARK-CRFI-KPG-000540 | Trade Partner | CONTROLS MISCELLANEOUS | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-09 | Endfire-TRANSMIT-000048 | NA | Trade Partner | Dry Fire Layout - Ground Level | 1 | 0 | 0 | NA | APPROVED | 2025-12-09 | WF-000623 | 731 | 2025-12-12 |  |  | 2026-01-07 | 2026-01-07 | KPTG-TRANSMIT-002355 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-13 | D&E-TRANSMIT-000473 | NA | Trade Partner | ISSUED FOR APPROVAL - ROOF LEVEL - CHW PIPE LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 2493 | 2026-03-23 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-015239 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-12 | Hames-TRANSMIT-000127 | NA | Consultant | Latest door hardware schedule | 0 | 1 | 0 | NA | APPROVED | 2026-03-12 | NA | 1111 | 2026-03-17 |  | PUT IN RE-REVIEW BY SCG CONSULTANT AS RQSTD BY EMMA | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-003327 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-18 | WGAVIC-TRANSMIT-000082 | NA | Consultant | M2 - Stage 10 Slab on Ground and Stage 9 Forklift Update - Construction Issue | 14 | 0 | 0 | KPTG-IntCorr-000529 | APPROVED | 2026-03-18 | NA | 465 | 2026-03-20 |  | Actual receipt date is 13/03 | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-001534 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-13 | VIA Arch-TRANSMIT-000061 | NA | Consultant | M2 S9 GF Concrete Profile Update | 1 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 434 | 2026-03-16 |  | Actual receipt date 03/03 | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-001376 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-13 | WilsonPD-TRANSMIT-000170 | SPARK-CRFI-KPG-000618 | Trade Partner | Hydraulic Services - Roof Level - Zone A & B Drainage & Water Layout | 2 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 168 | 2026-03-20 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-000731 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-13 | D&E-TRANSMIT-000167 | SPARK-CRFI-KPG-000587 | Trade Partner | VARIABLE SPEED DRIVES | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | 2026-03-20 |  |  |  | 2026-04-14 | KPTG-TRANSMIT-000641 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-13 | SMEPS-TRANSMIT-000135 | SPARK-CRFI-KPG-000592 | Trade Partner | Patch Panels and Cable Managers | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-07 | KPTG-TRANSMIT-000614 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-13 | SMEPS-TRANSMIT-000136 | SPARK-CRFI-KPG-000592 | Trade Partner | Fobots | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-07 | KPTG-TRANSMIT-000615 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-13 | SMEPS-TRANSMIT-000137 | SPARK-CRFI-KPG-000592 | Trade Partner | RJ45 Outlet | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-07 | KPTG-TRANSMIT-000616 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-13 | SMEPS-TRANSMIT-000138 | SPARK-CRFI-KPG-000419 | Trade Partner | PV System (SPARK-CRFI-KPG-000419) | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-25 | KPTG-TRANSMIT-000597 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-09 | RDSBIM-TRANSMIT-000127 | NA | Trade Partner | LEVEL 14 CONCRETE PROFILE PLAN | 6 | 0 | 0 |  | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-13 | Schindle-TRANSMIT-000010 | SPARK-CRFI-KPG-000505 | Trade Partner | NEL MCC - Lift Interior Drawings - For Review | 1 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 169 | 2026-03-20 |  | Terminated as per Peter advise | 2026-07-23 | 2026-07-23 | KPTG-IntCorr-003716 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-13 | SMEPS-TRANSMIT-000014 | NA | Trade Partner | STAGE 9-11 Electrical Inground Site Layout | 1 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 438 | 2026-03-20 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-001505 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-13 | SMEPS-TRANSMIT-000015 | NA | Trade Partner | STAGE 9-11 Telecoms Inground Site Layout | 1 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 437 | 2026-03-20 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-001495 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-13 | Leemark-TRANSMIT-000020 | SPARK-CRFI-KPG-000365 | Trade Partner | Transmittal of Level 1 Dry Fire Shop Draiwngs - For Approval | 5 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 170 | 2026-03-20 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-000605 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-13 | Leemark-TRANSMIT-000021 | SPARK-CRFI-KPG-000365 | Trade Partner | Transmittal of Level 1 Dry Fire Shop Draiwngs - For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 171 | 2026-03-20 |  |  | 2026-03-30 | 2026-04-24 | KPTG-TRANSMIT-000694 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-13 | D&E-TRANSMIT-000169 | SPARK-CRFI-KPG-000497 | Trade Partner | SESIMIC GROUND DRAWINGS | 10 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 172 | 2026-03-20 |  |  |  | 2026-04-20 | KPTG-TRANSMIT-000666 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-13 | WOCEP-TRANSMIT-000004 | NA | Trade Partner | ITP | 0 | 1 | 0 | KPTG-IntCorr-002192 | APPROVED | [5 empty] | No Action |  | 2026-03-14 | KPTG-IntCorr-002196 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-13 | D&E-TRANSMIT-000477 |  | Trade Partner | Upper Roof Level - CHW & CCW Pipe Layout | 2 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 2507 | 2026-03-23 |  |  | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-015411 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-13 | D&E-TRANSMIT-000476 | NA | Trade Partner | ISSUED FOR APPROVAL - GROUND - CHW PIPE LAYOUT | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect document number |  | 2026-03-13 | KPTG-TRANSMIT-014316 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-13 | Hames-WTRAN-000442 | NA | Trade Partner | CONSULTANT IFC REVIEW -ARUP STR-HAMES - Stage 4 - C2 Gantry Roof`& Secondary Steel | 2 | 0 | 0 | NA | APPROVED | 2026-01-26 | WF-004490 | NA | 2026-03-13 |  |  | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014308 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-10 | PFP PL-TRANSMIT-000054 | NA | Trade Partner | Ground and Level Zone C1 Shop DWGs IFA | 2 | 0 | 0 | NA | APPROVED | 2025-12-09 | NA | 1631 | 2025-12-11 |  |  |  | 2026-01-06 | KPTG-TRANSMIT-011216 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-13 | Tradetec-TRANSMIT-000390 | NA | Trade Partner | Tech Data - Culvert Tape | 0 | 1 | 0 | NA | APPROVED | 2026-03-13 | WF-004777 | NA | 2026-03-17 |  |  | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-014525 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-13 | ASV-TRANSMIT-000155 | NA | Trade Partner | Hydraulic Sample Submission - Thermal Lagging | 0 | 1 | 0 | NA | APPROVED | 2026-03-13 | WF-004783 | NA | 2026-03-25 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-015282 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-13 | D&E-TRANSMIT-000472 | NA | Trade Partner | C-MCC-CH-05-01 - IFA | 1 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 2498 | 2026-03-23 |  |  | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-015392 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-13 | D&E-TRANSMIT-000471 | NA | Trade Partner | ISSUED FOR APPROVAL - LEVEL 1 - SFN PIPE LAYOUT | 2 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 2491 | 2026-03-23 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016515 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-13 | ADP-TRANSMIT-000275 | NA | Consultant | MEL741 - Stage 4 Updated CSMS Drawings (IFC Issue) | 14 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 2489 | 2026-03-17 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-014426 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-13 | SKS Tech-TRANSMIT-000058 | NA | Trade Partner | LIGHTING - LAYOUT GROUND FLOOR - ZONE C2 | 1 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 2487 | 2026-03-23 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016543 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-13 | Stowe-A-TRANSMIT-000517 | NA | Trade Partner | Stowe - Tech Data Submission - 3PHASE 5 PIN OUTLET | 0 | 1 | 0 | NA | APPROVED | 2026-03-13 | WF-004784 | NA | 2026-03-26 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-014976 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-13 | D&E-TRANSMIT-000470 | NA | Trade Partner | HS1 OFFICE FD IFA | 0 | 1 | 0 | NA | APPROVED | 2026-03-13 | WF-004782 | NA | 2026-03-27 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016107 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-10 | NXT-WTRAN-001930 | NA | Trade Partner | Duroseal 25C | 0 | 1 | 0 | NA | APPROVED | 2026-03-10 | WF-004694 | NA | 2026-03-12 |  | Internally superseded and put in the WF by Henry Robertson | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-014322 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-13 | HDRAus-TRANSMIT-000430 | NA | Consultant | M3 SW - Security Treatment of Service Penos | 1 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 3961 | 2026-03-17 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-014473 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-10 | Entire M-TRANSMIT-000009 | NA | Trade Partner | Mechanical Fixing and Supports Technical Data for Approval | 0 | 1 | 0 | NA | APPROVED | 2025-12-15 | WF-003616 |  |  |  | The register has been updated. If any further action is required, the coordinator will inform. | 2025-12-24 | 2025-12-18 | NXT-WTRAN-001292 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-13 | HDRAus-TRANSMIT-000431 | NA | Consultant | M3_S2_M3_S2_Basement Roller Shutter Goods Lift 1 Plans | 4 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 3964 | 2026-03-17 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-014764 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-13 | ARCH-TRANSMIT-000033 | NA | Consultant | Precast set out & Concrete Profile Ground | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Issued For information only. To be updated in Aconex and ACC. No review required. (Outlook mail: RE: [External] FW: KPTG-DA-000287: DESIGN PROGRAM - KEY DATES ACNXREF<1uIuH6hZXcMNq8sdkUdulB>) | 2026-03-13 | 2026-03-13 | KPTG-TRANSMIT-000096 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-13 | HDRAus-TRANSMIT-000428 | NA | Consultant | SW - External Finishes Schedule - General Updates | 0 | 1 | 0 | NA | APPROVED | 2026-03-13 | NA | 3966 | 2026-03-17 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-014471 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-13 | Auspan-TRANSMIT-000138 | NA | Trade Partner | Precast shop drawings for construction. Ground floor. | 23 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - No review required - Register and distribute- KPTG-TRANSMIT-000917 |  | 2026-03-13 | KPTG-TRANSMIT-000917 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-13 | Fyfe-TRANSMIT-000015 | NA | Consultant | Civil IFC - Building Set | 3 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 514 | 2026-03-17 |  | As advised by Kapitol CDM, review is void to update a drawing and reinitiate once updated drawings issued. | 2026-03-23 | 2026-03-23 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-13 | JCBa-TRANSMIT-000071 | NA | Consultant | Thermal Performance Plans - IFC | 7 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 516 | 2026-03-17 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-001017 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-13 | crossfir-TRANSMIT-000001 | NA | Trade Partner | Wet Fire Services - Schematic, IFA | 1 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 343 | 2026-03-19 |  | ACC Review Voided by Kapitol DM | 2026-04-20 | 2026-04-20 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-13 | LGCE-TRANSMIT-000009 | NA | Trade Partner | Electrical Penetrations for the rest of the project | 3 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 345 | 2026-03-19 |  |  | 2026-04-17 | 2026-04-17 | LGCE-TRANSMIT-000009 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-13 | D&E-TRANSMIT-000168 | SPARK-CRFI-KPG-000588 | Trade Partner | SEISMIC INSTALLATION GUIDE | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-14 | KPTG-TRANSMIT-000640 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-13 | WOCEP-TRANSMIT-000005 | NA | Trade Partner | ARMSTRONG TILE SAMPLE | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-10 | Entire M-TRANSMIT-000010 | NA | Trade Partner | Mechanical Springs and Mounts Technical Data for Approval | 0 | 1 | 0 | NA | APPROVED | 2025-12-15 | WF-003621 / WF-003785 |  | 2025-12-27 |  | The register has been updated. If any further action is required, the coordinator will inform. |  | 2026-01-15 | KPTG-TRANSMIT-011457 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-13 | Tradetec-TRANSMIT-000066 | NA | Trade Partner | HV and Comms Trench Geotextile Technical Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-03-13 | WF-000341 | NA | 2026-03-24 |  | Same document has been resubmitted via Tradetec-TRANSMIT-000069 |  | 2026-03-16 | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-13 | PCForm-TRANSMIT-000155 | NA | Trade Partner | Galdeck Metall Tray for Stage 11 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Need to revise, KPTG-SADV-001728 |  | 2026-03-13 | KPTG-SADV-001728 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-13 | BLUESF-TRANSMIT-000075 | NA | Trade Partner | M2 Stage-11_Revised_GF - (11PW-7,CC42a & CC42b) | 11 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required |  | 2026-03-13 | NA | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-13 | TATE_-IntCorr-000045 | NA | Trade Partner | DH7 & 8-SCEC PAN AND RC BEAM INTERFACE TREATMENT | 7 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 1421 | 2026-03-19 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-13 | NXT-TRANSMIT-000383 | NA | Client | M3 Stage 1 - Notification of First Aid Injury - 25.02.26 | 0 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Correspondence |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-13 | LANSA-TRANSMIT-000017 | NA | Trade Partner | Hydraulic Shop Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 1418 | 2026-03-19 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-002769 | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-13 | KPTG-IntCorr-003216 | NA | Trade Partner | SME Telecommunications | 5 | 0 | 0 | KPTG-IntCorr-003218 | APPROVED |  | NA | NA |  |  |  |  | 2026-03-16 | KPTG-TRANSMIT-002759 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-13 | ADP-TRANSMIT-000040 | NA | Consultant | ADP Reg 126 update for building permit amendment | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | No Action Required |  |  | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-11-24 | KARE-TRANSMIT-000070 | NA | Trade Partner | EMS for approval | 1 | 0 | 0 | NA | APPROVED | 2025-12-09 | WF-000808 | 480 | 2025-12-09 |  |  | 2025-12-09 | 2025-12-09 | KPTG-TRANSMIT-002509 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-13 | RDSBIM-TRANSMIT-000118 | NA | Trade Partner | MLCSPR ¦ AQUATIC CENTER LEVEL 01 INTERNAL SCREED LAYOUT | 5 | 0 | 0 |  | APPROVED |  | NA | NA |  |  | IFC transmitted to trade & Consultants: KPTG-TRANSMIT-002568 |  | 2026-03-16 | KPTG-TRANSMIT-002568 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-13 | ARCH-TRANSMIT-000141 | NA | Consultant | MLC - SPR - Drawing update | 4 | 0 | 0 | NA | APPROVED | 2026-03-14 | NA | 462 | 2026-03-20 |  |  | 2026-03-17 | 2026-03-17 | KPTG-SADV-003891 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-13 | Highbu-TRANSMIT-000140 | NA | Trade Partner | Updated drawings | 4 | 0 | 0 |  | REJECTED | [5 empty] | Dwfx file is not shared, requested to resubmit.KPTG-SADV-003871 |  | 2026-03-14 | KPTG-SADV-003871 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-16 | KPTG-IntCorr-005014 |  | Trade Partner | Re: Shade Sail Services | 1 | 0 | 0 | NA | APPROVED | 2026-02-16 | NA | 442 | 2026-02-23 |  |  | 2026-03-13 | 2026-03-13 | KPTG-SADV-003870 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-03 | TATE_-TRANSMIT-000026 | NA | Trade Partner | MEL05 COLO 4 Ceiling Engineering Report | 0 | 3 | 0 | NA | APPROVED | 2026-03-14 | WF - 000249 | NA | 2026-03-20 |  | Reissue - Approval for Structural consultant. | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-000609 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-12 | Auspan-TRANSMIT-000061 | NA | Trade Partner | L6-L9 column shop drawings issued for approval | 20 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 597 | 2026-03-19 |  |  | 2026-03-24 | 2026-03-25 | KPTG-SADV-003550 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-12 | IGS--TRANSMIT-000033 | NA | Consultant | Re: Urgent Requirement of Dwfx file:: Revised Building Services Layouts | 20 | 0 | 0 | NA | REJECTED | [5 empty] | Dwfx file of a drawing was found wrong, requested to resubmit: KPTG-SADV-003390 |  | 2026-03-12 | KPTG-SADV-003390 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-13 | DI-TRANSMIT-000153 | NA | Trade Partner | RGV Rail Setout | 1 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 349 | 2026-03-17 |  |  | 2026-03-18 | 2026-03-18 | DRAFT-009360 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-13 | HIP-TRANSMIT-000014 | NA | Trade Partner | Building - 08 - Powerpack - Additional Internal Steel - Reissued for Approval | 5 | 0 | 0 | NA | APPROVED | 2026-03-14 | WF-000434 | NA | 2026-03-25 |  |  | 2026-03-20 | 2026-03-20 | KAPITOL-TRANSMIT-001229 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-13 | RDSI-TRANSMIT-000035 | NA | Trade Partner | HANWHA FURNISHED FACILITY (B18) PARTITION WALL LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-03-14 | NA | 351 | 2026-03-17 |  |  | 2026-03-18 | 2026-03-18 | DRAFT-009361 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-10 | vdmcons-TRANSMIT-000120 | NA | Consultant | Shop Drawings - Remain Facade Panels - IFF - 2025-12-09 | 25 | 0 | 0 | NA | APPROVED |  | NA |  |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  | KPTG-TRANSMIT-002524 | Closed | 25 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-13 | W TITE-TRANSMIT-000011 | NA | Trade Partner | M3-WPF-WTW-TD-S-0301-0006 and M3-WPF-WTW-TD-S-0301-0007 | 0 | 1 | 0 | NA | APPROVED | 2026-03-13 | WF-004781 | NA | 2026-03-26 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015071 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-13 | D&E-TRANSMIT-000474 | NA | Trade Partner | ISSUED FOR APPROVAL - LEVEL 1 CHW PIPE LAYOUT | 2 | 0 | 0 | NA | APPROVED | 2026-03-13 | NO | 2497 | 2026-03-23 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-015238 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-13 | ADP-TRANSMIT-000276 | NA | Consultant | Re: MEL741 - Stage 4 Updated EL Drawings (IFC Issue | 39 | 0 | 0 | NA | REJECTED | [5 empty] | due to incorrect reason |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-13 | D&E-TRANSMIT-000475 | NA | Trade Partner | ISSUED FOR APPROVAL - DH C2 CHW & SFN SCHEMATIC | 1 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 2501 | 2026-03-23 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-015597 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-13 | D&E-TRANSMIT-000478 | NA | Trade Partner | Upper Roof Level - Cooling Tower Sections | 2 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 2505 | 2026-03-23 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-015248 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-13 | SMEPS-TRANSMIT-000211 | NA | Trade Partner | Re: SME - M3S4 - MDB/CMDB Typical Shop Drawings | 3 | 0 | 0 | NA | REJECTED | [9 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-13 | HDRAus-TRANSMIT-000432 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 11 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 2509 | 2026-03-16 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014850 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-13 | IVS-TRANSMIT-000350 | NA | Consultant | Issued For Construction - (Revised as Clouded) Core 6 Goods lift Steelwork & Roof Plinth plans | 5 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 2513 | 2026-03-17 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015078 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-13 | Civilex-TRANSMIT-000049 | NA | Trade Partner | Re: Final (WF-000189) Civilex-TRANSMIT-000034 - GRP Panel Tank | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected : QA Document numbering error |  | 2026-03-13 | KPTG-TRANSMIT-000751 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-13 | PCForm-TRANSMIT-000098 | NA | Trade Partner | Stair Shop Drawing Approval | 39 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected : QA Document numbering error |  | 2026-03-13 | KPTG-TRANSMIT-000745 | Closed | 39 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-10 | vdmcons-TRANSMIT-000121 | NA | Consultant | Shop Drawings - Remain Facade Panels (Steel Beams) - IFF - 2025-12-09 | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  | KPTG-TRANSMIT-002526 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-13 | PCForm-TRANSMIT-000099 | NA | Trade Partner | strategic drawings | 34 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected : QA Document numbering error |  | 2026-03-13 | DRAFT-005656 | Closed | 34 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-13 | PCForm-TRANSMIT-000100 | NA | Trade Partner | Raft 1 - Pour Sequence for review | 1 | 0 | 0 | KPTG-IntCorr-000471 | APPROVED |  | NA | NA |  |  | QA Checked - clarification from Victoria - SUPERSEDED BY PCForm-TRANSMIT-000169 |  | 2026-04-22 | PCForm-TRANSMIT-000169 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-13 | INGEN3D-TRANSMIT-000018 | NA | Trade Partner | Level 2-4 - Precast Columns | 23 | 0 | 0 | NA | APPROVED | 2026-03-14 | WF-000239 | NA | 2026-03-20 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-000954 | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-13 | D&E-TRANSMIT-000010 | NA | Trade Partner | Woolworths Early Works Shop Drawings - IFA | 1 | 0 | 0 | NA | APPROVED | 2026-03-15 | NA | 331 | 2026-03-20 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-000861 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-13 | Endfire-TRANSMIT-000071 | NA | Trade Partner | SCHMATIC AND DETAIL IFC's | 3 | 0 | 0 | NA | APPROVED | 2026-03-13 | NA | 1126 | 2026-03-17 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-003222 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-14 | RDSBIM-TRANSMIT-000164 | NA | Trade Partner | LINDRUM ¦ LEVEL 2 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | #599 | 2026-03-21 |  |  | 2026-03-24 | 2026-03-25 | KPTG-SADV-003549 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-15 | RDSBIM-TRANSMIT-000166 | NA | Trade Partner | LINDRUM ¦ LEVEL 03 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | #600 | 2026-03-21 |  |  | 2026-03-24 | 2026-03-24 | KPTG-SADV-003544 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-16 | ARCST-TRANSMIT-000227 | NA | Trade Partner | Re: C1 East Lower Gantry - Issued for Approval | 154 | 0 | 0 | NA | REJECTED | [5 empty] | Incomplete title |  | 2026-03-16 | KPTG-RFI-006719 | Closed | 154 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-15 | RDSBIM-TRANSMIT-000165 | NA | Trade Partner | LINDRUM ¦ LEVEL 01 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | #601 | 2026-03-21 |  |  | 2026-03-24 | 2026-03-24 | KPTG-SADV-003537 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-16 | ARCST-TRANSMIT-000228 | NA | Trade Partner | C2 East Lower Gantry - Issued for Approval | 157 | 0 | 0 | NA | REJECTED | [5 empty] | Incomplete title |  | 2026-03-16 | KPTG-IntCorr-010757 | Closed | 157 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2025-12-10 | KPTG-SADV-000847 | NA | Trade Partner | Signage IFC | 1 | 0 | 0 | NA | APPROVED |  | NA |  |  |  | IFC, No review required. Updated register and distributed to the Project Team. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-16 | NXT-TRANSMIT-001401 | NA | Trade Partner | Fwd: SO 611300382 - NextDC M3 Stage 4 LVSB - MSB+USB Schematic IFC | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For information |  |  | KPTG-TRANSMIT-014416 | Open | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-16 | NXT-TRANSMIT-001402 | NA | Trade Partner | NXT-TRANSMIT-001402 Reference Number VERTIV-TRANSMIT-000057 Fwd: SO 611300382 - NextDC M3 Stage 4 LVSB - EMS Configuration | 2 | 0 | 0 | NA | APPROVED | 2026-03-16 | WF-004796 | NA | 2026-04-01 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-014549 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-16 | NXT-TRANSMIT-001403 | NA | Trade Partner | NextDC M3 Stage 4 LVSB - MSB-FA Schematic | 2 | 0 | 0 | NA | APPROVED | 2026-03-16 | WF-004797 | NA | 2026-03-20 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-16 | NXT-TRANSMIT-001404 | NA | Trade Partner | Vertiv UMTD IFC Submission | 2 | 0 | 0 | NA | APPROVED | 2026-03-16 | WF-004798 | NA | 2026-03-27 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-014439 | Open | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-16 | NXT-TRANSMIT-001405 | NA | Trade Partner | Fwd: SO 611300382 - NextDC M3 Stage 4 LVSB - Vertiv LVSB Cable Connection details | 0 | 5 | 0 | NA | APPROVED | 2026-03-16 | WF-004802 | NA | 2026-03-27 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-014444 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-16 | Baigents-TRANSMIT-000074 | NA | Trade Partner | Remaining Site Storage Steel - IFA | 50 | 0 | 0 | NA | REJECTED | [5 empty] | Different titles in Aconex & Inside the drawing |  | 2026-03-16 | KPTG-TRANSMIT-000538 | Closed | 50 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-01-27 | SMEPS-TRANSMIT-000137 / 154-ACC-869 | NA | Trade Partner | Telecommunications - ICT Schematic (Customer),Level 1 - Data Hall A8 & Ground Floor | 3 | 0 | 0 | NA | APPROVED | 2026-01-27 | NA | 1352 | 2026-02-02 |  | For Stamp | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-002830 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-16 | Auspan-TRANSMIT-000125 | NA | Trade Partner | IFC precast shop drawings. Stage 9 | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings No Review required. (Actual receipt date 06/03) |  | 2026-03-16 | KPTG-TRANSMIT-001359 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-13 | RDSBIM-TRANSMIT-000041 | NA | Trade Partner | MWYCCB ¦ GROUND FLOOR INTERNAL FITOUT PLAN - UAT WC | 1 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 173 | 2026-03-23 |  | Bim360 review terminated by Moj |  | 2026-06-29 | KPTG-TRANSMIT-001359 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-10 | PCForm-TRANSMIT-000144 | NA | Trade Partner | Final (WF-000316) Stair 7,8, Lift 3/4 Keyboxes for Review | 5 | 0 | 0 | NA | APPROVED | 2026-03-10 | WF-000316 | NA | 2026-03-16 |  |  | 2026-03-13 | 2026-03-16 | KPTG-TRANSMIT-001357 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-01 | Highbu-TRANSMIT-000102 | NA | Trade Partner | Stainless steel external drinking trough | 0 | 1 | 0 |  | APPROVED | 2025-12-01 | WF-000637 |  | 2025-12-03 |  |  |  | 2026-02-10 | KPTG-TRANSMIT-002351 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2025-12-10 | KPTG-SADV-000850 | NA | Trade Partner | Rack Signage - IFA | 1 | 0 | 0 | NA | APPROVED | 2025-12-10 | WF-000173 |  | 2025-12-17 |  | Workflow terminated as requested by Kapitol, resubmitted on another workflow |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-13 | RDSBIM-TRANSMIT-000175 | NA | Trade Partner | LEVEL 06 PARTITION WALL PLAN - IFC | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol IFC Drawings only for distribution. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-16 | SMEPS-TRANSMIT-000137 | NA | Trade Partner | SME Shop Drawing Telecommunications IFA 1 | 5 | 0 | 0 | NA | APPROVED | 2026-03-16 | WF - 000250 | NA | 2026-03-20 |  | NA | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-000527 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-16 | SMEPS-TRANSMIT-000138 | NA | Trade Partner | SME Shop Drawing Telecomunications IFA 2 | 3 | 0 | 0 | NA | APPROVED | 2026-03-16 | WF -000251 | NA | 2026-03-20 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-000582 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-16 | SMEPS-TRANSMIT-000139 | SPARK-CRFI-KPG-000583 | Trade Partner | Optic Fibre Cable | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-000885 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-16 | D&E-TRANSMIT-000171 | NA | Trade Partner | MWYCCB - ROOF LEVEL - DUCTWORK LAYOUT ZONES - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 174 | 2026-03-23 |  | Terminated as per alex advise |  | 2026-04-17 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-17 | A.S.H.-TRANSMIT-000076 | NA | Trade Partner | A.S.H.-TRANSMIT-000076 - Updated MP for Southern plantroom columns | 1 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 175 | 2026-03-23 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-001383 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-16 | Tradetec-TRANSMIT-000067 | NA | Trade Partner | 20mm Gravel Technical Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-03-16 | WF-000346 | NA | 2026-03-23 |  |  | 2026-07-05 | 2026-07-05 | KPTG-TRANSMIT-005222 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-16 | KEECEPRO-TRANSMIT-000031 | NA | Trade Partner | Re: DB Shop Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 352 | 2026-03-20 |  |  | 2026-03-24 | 2026-03-24 | DRAFT-009464 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-16 | Baigents-TRANSMIT-000075 | SPARK-CRFI-KPG-000135 | Trade Partner | Remaining Site Storage Steel - IFA | 50 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 176 | 2026-03-23 |  | Terminated as per jed advise |  | 2026-05-26 | KPTG-IntCorr-003071 | Closed | 50 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-16 | Nilsen3-TRANSMIT-000062 | NA | Trade Partner | M3-Stage 3 Rops 3A & 3B | 0 | 1 | 0 | NA | APPROVED | 2026-03-16 | WF-004812 | NA | 2026-03-16 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-10 | JCBa-TRANSMIT-000201 | NA | Consultant | Level 03 East Pavillion - Design for Review | 6 | 0 | 0 | NA | APPROVED | 2025-12-10 | WF- 000810 | 508 | 2025-12-17 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-16 | Ardon-TRANSMIT-000026 | NA | Trade Partner | Revised Door Hardware - For Approval | 0 | 2 | 0 | NA | APPROVED | 2026-03-16 | WF-004813 | NA | 2026-04-01 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-015427 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-16 | SMEPS-TRANSMIT-000140 | NA | Trade Partner | Shop Drawing Telecomunications IFA 1 | 1 | 0 | 0 | NA | APPROVED | 2026-03-16 | WF - 000253 | NA | 2026-03-20 |  | NA | 2026-03-25 | 2026-03-26 | KPTG-TRANSMIT-000591 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-16 | IVS-TRANSMIT-000351 | NA | Consultant | Drawing Revision Update (M3-STR-IVS-DRG-C-0401-4112) | 1 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 2528 | 2026-03-18 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015082 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-16 | IVS-TRANSMIT-000323 | NA | Consultant | Stage 4 - Cooling Tower & Chiller Room Zone C1 - C3 Package (Construction Issue) | 8 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 2534 | 2026-03-18 |  | 8 docs out of 12 partially done as on the urgency | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-014559 | Open | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-16 | KALLIBRE-TRANSMIT-000001 | NA | Trade Partner | MWYCCB - Pressed Metal Door Frame Shop Drawings For Review | 1 | 0 | 0 | NA | REJECTED | [5 empty] | The document does not comply with the project standard |  | 2026-03-16 | KPTG-TRANSMIT-000542 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-16 | SMEPS-TRANSMIT-000142 | SPARK-CRFI-KPG-000359 | Trade Partner | MDB-01 (A) Rev C Tech data for approval | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | 2026-03-26 |  | NA | 2026-03-26 | 2026-03-24 | KPTG-TRANSMIT-000574 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-16 | SMEPS-TRANSMIT-000143 | SPARK-CRFI-KPG-000359 | Trade Partner | MDB-02 (B) Rev C Tech data approval | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-24 | KPTG-TRANSMIT-000576 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-16 | Altaire-TRANSMIT-000007 | NA | Trade Partner | Dry Fire Shop Drawings (For Information / For Construction) (1) | 5 | 0 | 0 | NA | APPROVED | 2026-03-16 | WF - 000255 | NA | 2026-03-20 |  | NA | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-000497 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-16 | LVPG-TRANSMIT-000021 | NA | Trade Partner | Updated 3000L GIT tech data | 0 | 1 | 0 | NA | APPROVED | 2026-03-16 | WF-000277 | NA | 2026-03-23 |  |  | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-001042 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-16 | LVPG-TRANSMIT-000022 | NA | Trade Partner | LVPG-HY-TECH-041 - Pits | 0 | 1 | 0 | NA | APPROVED | 2026-03-16 | WF-000278 | NA | 2026-03-23 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-001201 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-10 | JCBa-TRANSMIT-000201 | NA | Consultant | A-SCH-200_FF&E SCHEDULE_REV9. | 0 | 1 | 0 | NA | APPROVED | 2025-12-10 | WF - 000809 | NA | 2025-12-17 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-16 | Auspan-TRANSMIT-000140 | NA | Trade Partner | Update precast dowel layout zone 1, 2 ground floor | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - No review required - Register and distribute : KPTG-TRANSMIT-000932 |  | 2026-03-16 | KPTG-TRANSMIT-000932 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-16 | Auspan-TRANSMIT-000141 | NA | Trade Partner | Update precast shopd drawings for construction. | 52 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - No review required - Register and distribute KPTG-TRANSMIT-000930 |  | 2026-03-16 | KPTG-TRANSMIT-000930 | Closed | 52 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-16 | M.2-TRANSMIT-000011 | NA | Trade Partner | Tech Data - Basement fittings | 0 | 6 | 0 | NA | APPROVED | 2026-03-16 | WF-000279 | NA | 2026-03-23 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-001100 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-16 | Rinco-TRANSMIT-000035 | NA | Consultant | Structural drawings Issued for Construction | 8 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 520 | 2026-03-18 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-001104 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-16 | Auspan-TRANSMIT-000142 | NA | Trade Partner | Zone 1 & 2 IFC Shop Drawings | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - No review required - Register and distribute KPTG-TRANSMIT-000935 |  | 2026-03-16 | KPTG-TRANSMIT-000935 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-16 | D&E-TRANSMIT-000484 | NA | Trade Partner | ISSUED FOR APPROVAL - MECHANICAL DUCT LAYOUT | 4 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 2536 | 2026-03-24 |  |  | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-015415 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-16 | TTW-TRANSMIT-000164 | NA | Consultant | M3 Stage 3 Civil Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 2532 | 2026-03-18 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015098 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-18 | WGAVIC-TRANSMIT-000084 | NA | Consultant | M2 - Stage 9, 10 and 11 Staircase and Connection Updates - Certification Issue | 8 | 0 | 0 | KPTG-IntCorr-000544 | APPROVED | 2026-03-18 | NA | 466 | 2026-03-23 |  | Actual receipt date is 16/03 | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-001531 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-18 | WGAVIC-TRANSMIT-000085 | NA | Consultant | M2 - Stage 11 Level 1 Slab & Details - Construction Issue | 7 | 0 | 0 | KPTG-IntCorr-000545 | APPROVED | 2026-03-18 | NA | 471 | 2026-03-23 |  | Actual receipt date is 16/03 | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-001537 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-16 | PARR-TRANSMIT-000133 | NA | Consultant | NDC M3 Stage 4 - Enclosures - CLIENT DRAWINGS | 3 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 2523 | 2026-03-16 |  | TERMINATED as requested in NXT-TRANSMIT-001408, the document will be submitted for a new review | 2026-03-16 | 2026-03-16 | NXT-TRANSMIT-001408 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2025-12-10 | TATE_-TRANSMIT-000020 | NA | Trade Partner | Updated Tech Data | 0 | 1 | 0 | NA | REJECTED |  | NA |  |  |  | Rejected. Trade partner to upload correct attachment. (KPTG-SADV-000853) |  | 2025-12-10 | KPTG-SADV-000853 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-16 | NXT-TRANSMIT-001408 | NA | Client | Fwd: P2671 - NDC M3 Stage 4 - Enclosures - CLIENT DRAWINGS - FC-2 | 3 | 0 | 0 | NA | APPROVED | 2026-03-16 | WF-004811 | NA | 2026-03-27 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018355 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-16 | PARR-TRANSMIT-000134 | NA | Consultant | P2671 - NDC M3 Stage 4 - Enclosures - ENCLOSURE TIE-DOWN & WIDE FIXING BRACKET(IFI-2 | 1 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 2526 | 2026-03-16 |  | TERMINATED as requested in NXT-TRANSMIT-001407, the document will be submitted for a new review | 2026-03-16 | 2026-03-16 | NXT-TRANSMIT-001407 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-16 | NXT-TRANSMIT-001407 | NA | Client | P2671 - NDC M3 Stage 4 - Enclosures - ENCLOSURE TIE-DOWN & WIDE FIXING BRACKET(IFI-2) | 1 | 0 | 0 | NA | APPROVED | 2026-03-16 | WF-004810 | NA | 2026-03-30 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018363 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-16 | D&E-TRANSMIT-000481 | NA | Trade Partner | Switchroom Fire Dampers - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-16 | WF-004806 | NA | 2026-04-06 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015086 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-16 | SMEPS-TRANSMIT-000213 | NA | Trade Partner | SME - DRAWINGS IFA PART SUBMISSIONS | 3 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 2519 | 2026-03-24 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016529 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-16 | D&E-TRANSMIT-000480 | NA | Trade Partner | NXM3S2 - Ground - Mechanical Duct Layout - Zones 9 & 10 - Issued For Approval | 2 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 2517 | 2026-03-24 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-015259 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-16 | SMEPS-TRANSMIT-000212 | NA | Trade Partner | SME - DRAWINGS IFA PART SUBMISSIONS | 8 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 2515 | 2026-03-24 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-016660 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-16 | D&E-TRANSMIT-000479 | NA | Trade Partner | NXM3S2 - Lower Ground - High Level Mechanical Pipe Layout - Zone 6 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 3968 | 2026-03-16 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-014469 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-01-16 | KPTG-IntCorr-008113 | NA | Trade Partner | Atlas Alfacade FT01B1 - Technical Data Sheet | 0 | 1 | 0 | NA | APPROVED | 2026-02-23 | WF-004418 | NA | 2026-03-17 |  |  | 2026-03-16 | 2026-03-16 | KPTG-TRANSMIT-014432 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-16 | Stowe-A-TRANSMIT-000518 | NA | Trade Partner | Stowe - Tech Data Submission - Penetration Protection Shop Drawing | 0 | 1 | 0 | NA | APPROVED | 2026-03-16 | WF-004809 | NA | 2026-03-27 |  |  |  | 2026-03-26 | KPTG-TRANSMIT-015035 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-10 | TATE_-TRANSMIT-000032 | NA | Trade Partner | Updated tech data - Iccons strike anchor | 0 | 1 | 0 | NA | APPROVED | 2025-12-10 | WF-000849 | NA | 2025-12-19 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-002664 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-16 | Tradetec-TRANSMIT-000391 | NA | Trade Partner | Pipemakers Multilayer Conduit - Tech Data | 0 | 3 | 0 | NA | APPROVED | 2026-03-16 | WF-004817 | NA | 2026-03-26 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-015461 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-16 | D&E-TRANSMIT-000482 | NA | Trade Partner | NXM3S2 - Industrial Water / Sidestream Filtration Schematics + Level 01 - Mechanical Duct Layout Zone 3 - Issued For Construction | 3 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 3970 | 2026-03-23 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-014553 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-16 | D&E-TRANSMIT-000483 | NA | Trade Partner | ITPs - Issued for Construction | 0 | 7 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-03-16 | KPTG-TRANSMIT-014460 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-16 | D&E-TRANSMIT-000447 | NA | Trade Partner | IFC Requested | 0 | 33 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-03-16 | KPTG-TRANSMIT-014457 | Closed | 33 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-16 | HDRAus-TRANSMIT-000433 | NA | Consultant | M3 Stage 4 - Document upload - Door hardware schedule and general updates | 3 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 2540 | 2026-03-18 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-014625 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-16 | SMEPS-TRANSMIT-000214 | NA | Trade Partner | SME - M3S4 - IFC Drawings | 6 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 2538 | 2026-03-19 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016532 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-06 | ABB-SUBADVICE-000040 | NA | Trade Partner | M3 Stage 2 – Request for Commissioning Plan, FD, L3 Scripts & ITP | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | WF terminated, seek information for new WF. |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-16 | PFP PL-TRANSMIT-000050 | NA | Trade Partner | As-Built Drawings | 9 | 0 | 0 | KPTG-IntCorr-003238 | APPROVED | 2026-03-20 | NA | 1433 | 2026-03-26 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-002835 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-16 | Stanmor-TRANSMIT-000003 | NA | Trade Partner | Revised Sample Submissions | 0 | 5 | 0 | NA | REJECTED | [5 empty] | Document number & Title should not be same, request to resubmit:KPTG-SADV-003885 |  | 2026-03-16 | KPTG-SADV-003885 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-09 | A.S.H.-TRANSMIT-000056 |  | Trade Partner | ASH IFC drawings | 6 | 0 | 0 | NA | REJECTED | [8 empty] | KPTG-TRANSMIT-000298 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-16 | P & R-TRANSMIT-000085 | NA | Trade Partner | MECHANICAL - SCHEDULES PAGE UPDATED | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC document, transmitted to Trade & Consultants |  | 2026-03-16 | KPTG-TRANSMIT-002566 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-16 | 4DW-TRANSMIT-000160 | NA | Consultant | Landscaping Update | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC DRAWING, TRANSMITTED TO TRADE & CONSULTANTS |  | 2026-03-16 | KPTG-TRANSMIT-002564 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-16 | ARCH-TRANSMIT-000142 | NA | Consultant | MLC - SPR - AQC - Drawing update | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings are corrupted, requested to resubmit:KPTG-SADV-003886 |  | 2026-03-16 | KPTG-SADV-003886 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-16 | Best.-TRANSMIT-000007 | NA | Consultant | Signage drawing and message schedule updates based on MLC feedback | 8 | 1 | 0 | NA | APPROVED | [5 empty] | Updated to document Register and transmitted to Trade and consultants:KPTG-TRANSMIT-002588 |  | 2026-03-19 | KPTG-TRANSMIT-002588 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-13 | Entire M-TRANSMIT-000007 | NA | Trade Partner | COLO 5 - Mechanical shop drawings issued for approval | 14 | 0 | 0 | NA | APPROVED | 2026-03-16 | WF-000057 | NA | 2026-03-20 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-000214 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-13 | SES AU-TRANSMIT-000003 | NA | Trade Partner | Re: ACS HARDWARE- TECH DATA | 0 | 20 | 0 | NA | APPROVED | 2026-03-13 | WF-000052 | NA | 2026-03-19 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-000445 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-15 | JCI-TRANSMIT-000011 | NA | Trade Partner | MEL11 COLO 4 - FAT Documents | 0 | 7 | 0 | NA | APPROVED | 2026-03-16 | WF-000059 | NA | 2026-03-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-15 | JCI-TRANSMIT-000012 | NA | Trade Partner | MEL11 Documents - Shop Drawings & Tech Data | 18 | 0 | 0 | NA | APPROVED | 2026-03-18 | WF-000069 | NA | 2026-03-19 |  |  | 2026-03-27 | 2026-03-30 | KPTG-TRANSMIT-000229 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-16 | Appselec-TRANSMIT-000027 | NA | Trade Partner | Wesco & AFL Bill Of Materials | 0 | 2 | 0 | NA | APPROVED | 2026-03-16 | WF-000058 | NA | 2026-03-20 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-000239 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-16 | Entire M-TRANSMIT-000008 | NA | Trade Partner | Intumescent Damper & Drain Pipe Insulation IFA | 0 | 2 | 0 | NA | APPROVED | 2026-03-16 | : WF-000060 | NA | 2026-03-20 |  |  | 2026-03-27 | 2026-03-30 | KPTG-TRANSMIT-000238 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-16 | Auspan-TRANSMIT-000131 | NA | Trade Partner | Precast shop drawings for construction | 19 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. |  | 2026-03-16 | NA | Closed | 19 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-16 | SCG2014-TRANSMIT-000011 | NA | Consultant | Security - updated Draft for Tender after redesign | 1 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 455 | 2026-03-20 |  | Submitted on Redstick review as advised by Kapitol (Stuart Knox) Actual receipt date is 31/01/26 | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-001429 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-16 | SCG2014-TRANSMIT-000012 | NA | Consultant | Security - updated Draft for Tender after redesign | 42 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 456 | 2026-03-20 |  | Submitted on Redstick review as advised by Design Manager (Stuart Knox), Actual receipt date is 31/01/2026 | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-001433 | Closed | 42 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-16 | Tradetec-TRANSMIT-000068 | NA | Trade Partner | Revised HV and Comms Trench Geotextile Technical Data Submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Need to be revised, KPTG-SADV-001755 |  | 2026-03-16 | KPTG-SADV-001755 | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-16 | Tradetec-TRANSMIT-000069 | NA | Trade Partner | HV and Comms Trench Geotextile Technical Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-03-16 | WF-000399 | NA | 2026-03-24 |  | WF-000349 terminated and resubmitted for Civil review on 26/03 as advised by Project Coordinator (Daniel Patton) | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-004913 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-16 | LGCE-TRANSMIT-000010 | NA | Trade Partner | Basement 3 and 2 light and power | 4 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 352 | 2026-03-20 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-000743 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-16 | RDSBIM-TRANSMIT-000040 | NA | Trade Partner | 671CHP BASEMENT 3 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 348 | 2026-03-19 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-000632 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-16 | RDSBIM-TRANSMIT-000041 | NA | Trade Partner | 671CHP ¦ BASEMENT 2 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 350 | 2026-03-19 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-000636 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | KPTG-WTRAN-008900 | NA | Trade Partner | Dock Layout | 6 | 0 | 0 | NA | APPROVED | 2026-03-17 | WF-004825 | NA | 2026-03-24 |  | The wf has been generated as requested by Finlay -KPTG-IntCorr-010825 | 2026-03-23 | 2026-03-24 | KPTG-TRANSMIT-014902 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | KPTG-WTRAN-008898 | NA | Trade Partner | C3 - Door Details | 2 | 0 | 0 | NA | APPROVED | 2026-03-17 | WF-004824 | NA | 2026-03-24 |  | The wf has been generated as requested by FinlayT |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2025-12-09 | Symal-TRANSMIT-000042 | NA | Trade Partner | Sample Submission - Wheel Stops | 0 | 1 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | LTEPRCST-TRANSMIT-000147 | NA | Trade Partner | NEXTDC STAGE 4: CORE 02 IFC | 23 | 0 | 0 | NA | APPROVED | 2026-03-17 | WF-004826 | NA | 2026-03-24 |  | The wf has been generated as requested by Finlay - KPTG-IntCorr-010516 | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-014947 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | NXT-TRANSMIT-001414 | NA | Trade Partner | NextDC M3 Stage 4 LVSB - MSB_USB type 2 updated drawings and CRS for Review | 1 | 0 | 0 | NA | APPROVED | 2026-03-17 | WF-004828 | NA | 2026-03-30 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-17 | ASV-TRANSMIT-000156 | NA | Trade Partner | Hydraulic Samples - FF&E | 0 | 2 | 0 | NA | APPROVED | 2026-03-17 | WF-004831 | NA | 2026-04-02 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-015031 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-16 | SMEPS-TRANSMIT-000139 | 16/03/2026 | Trade Partner | Shop Drawing Electrical IFC A | 1 | 0 | 0 | NA | APPROVED | 2026-03-16 | WF - 000252 | NA | 2026-03-20 |  |  | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-000490 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-17 | D&E-TRANSMIT-000172 | NA | Trade Partner | MWYCCB - LEVEL 1 PIPEWORK LAYOUT ZONES - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 177 | 2026-03-24 |  |  | 2026-04-17 | 2026-04-24 | KPTG-TRANSMIT-000716 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | TTW-TRANSMIT-000165 | NA | Trade Partner | Fwd: M3 Stage 3 Civil Drawings | 0 | 5 | 0 | NA | APPROVED |  | NA | NA |  |  | CAD fiels |  | 2026-03-17 | KPTG-TRANSMIT-014494 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-17 | Civilex-TRANSMIT-000212 | NA | Trade Partner | Fwd: Switchroom Handrail IFC | 16 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-03-17 | KPTG-IntCorr-010857 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-17 | PROLMC-TRANSMIT-000013 | NA | Trade Partner | Proline updated shop drawings 17/3/26 | 21 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-03-17 | KPTG-TRANSMIT-000545 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-17 | SMEPS-TRANSMIT-000144 | SPARK-CRFI-KPG-000574 | Trade Partner | D4 - Luminaire | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-09 | A.S.H.-TRANSMIT-000061 |  | Trade Partner | ASH IFC drawings | 34 | 0 | 0 | NA | APPROVED | [5 empty] | Same revision (A.S.H.-TRANSMIT-000064) |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-17 | HIP-TRANSMIT-000016 | NA | Trade Partner | VAR003 - Powerpack Mechanical Support Steel - Issued for Construction | 13 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 353 | 2026-03-19 |  |  | 2026-03-19 | 2026-03-19 | DRAFT-009411 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-17 | SMEPS-TRANSMIT-000145 | SPARK-CRFI-KPG-000574 | Trade Partner | D5 - Luminaire | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-17 | HEXA-TRANSMIT-000007 | NA | Trade Partner | ISSUED FOR APPROVAL - CHW & SFN SCHEMATIC | 8 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 354 | 2026-03-19 |  | The WF has been terminated and resubmitted (via new tem) as requested by Isaiah |  | 2026-03-19 | NA | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-17 | SMEPS-TRANSMIT-000146 | NA | Trade Partner | D6 - Luminaire | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | As per peter advise No Ineight review - Submitting latest revision |  | 2026-03-25 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-17 | KEECEPRO-TRANSMIT-000034 | NA | Trade Partner | Fwd: Lighting and Power Shop Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 355 | 2026-03-19 |  |  | 2026-03-18 | 2026-03-18 | DRAFT-009379 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-17 | PROLMC-TRANSMIT-000014 | SPARK-CRFI-KPG-000545 | Trade Partner | Proline updated drawings 17-3-26 (New version) | 21 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 178 |  |  |  |  | 2026-07-20 | KPTG-TRANSMIT-001471 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-17 | Baigents-TRANSMIT-000076 | NA | Trade Partner | MCC Monorail - Issued For Approval | 33 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-03-17 | KPTG-TRANSMIT-000548 | Closed | 33 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | KPTG-WTRAN-008928 | NA | Trade Partner | Fibreflex Acoustic Blanket | 0 | 1 | 0 | NA | APPROVED | 2026-03-17 | WF-004847 | NA | 2026-04-13 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016495 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | KPTG-WTRAN-008925 | NA | Trade Partner | C1 East Lower Gantry Bracket | 9 | 0 | 0 | NA | APPROVED | 2026-03-17 | WF-004844 | NA | 2026-04-16 |  | The WF has been generate WF- As requested by Lola,CLOSEOUTED FROM Mail Number Hames-WTRAN-000538 2 DOC TERMINATED ALREADY | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-016012 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-10-24 | SMEPS-TRANSMIT-000044 | SPARK-CRFI-KPG-000310 | Trade Partner | Shop Drawing for Review - General Notes REV A | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-17 | KPTG-TRANSMIT-000546 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2025-12-10 | WPD-TRANSMIT-000052 | NA | Trade Partner | HFF - Samples | 0 | 19 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-17 | PMT Sec-TRANSMIT-000001 | NA | Trade Partner | PMT Tech Data - MCC | 0 | 37 | 0 | NA | REJECTED | [7 empty] | 2026-03-17 | KPTG-TRANSMIT-000547 | Closed | 37 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | ARCST-TRANSMIT-000232 | NA | Trade Partner | C1 East Lower Gantry - MP8001 Issued for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-03-16 | WF-004841 | NA | 2026-04-10 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | ARCST-TRANSMIT-000230 | NA | Trade Partner | C3 Cooling Tower Roof & Secondary Framing - Re-Issued for Approval | 164 | 0 | 0 | NA | APPROVED | 2026-03-16 | WF-004835 | NA | 2026-03-10 |  | 163 docs still under review |  | 2026-05-01 | KPTG-TRANSMIT-016773 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | Tradetec-TRANSMIT-000392 | NA | Trade Partner | Tech Data Submission - Spillceptor Sealant | 0 | 2 | 0 | NA | APPROVED | 2026-03-16 | WF-004859 | NA | 2026-04-07 |  | Old WF-004830 | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-014770 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | PFP PL-TRANSMIT-000075 | NA | Trade Partner | Roof Level Zone C2 IFA | 1 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 2547 | 2026-03-25 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-014941 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-17 | KETE-TRANSMIT-000009 | NA | Trade Partner | Kete - Communal & Retail Ground Floor - SD 1st Submission | 35 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 523 | 2026-03-23 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-001608 | Closed | 35 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-17 | Auspan-TRANSMIT-000143 | NA | Trade Partner | Precast shop drawings for construction. Ground floor. | 22 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | NA |  |  | IFC - No review required - Register and distribute : KPTG-TRANSMIT-000947 |  | 2026-03-17 | KPTG-TRANSMIT-000947 | Closed | 22 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-17 | RDSBIM-TRANSMIT-000032 | NA | Trade Partner | GREYSTAR BASEMENT FLOOR CONCRETE PROFILE KEY PLAN | 2 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 526 | 2026-03-23 |  | Review void as advised by Kapitol DM. updated drawings to be issued. | 2026-03-18 | 2026-03-18 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-17 | JCBa-TRANSMIT-000072 | NA | Consultant | Basement GA Plan IFC: DDA Parking | 3 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 528 | 2026-03-19 |  |  | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-001039 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | Mirage D-TRANSMIT-000014 | NA | Trade Partner | Roller Shutters Data Sheets | 0 | 2 | 0 | NA | APPROVED | 2026-03-16 | WF-004853 | NA | 2026-04-02 |  | The WF has been Terminated as requested by Isabella (msg- i will raise a new internal correspondance) |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-01 | Highbu-TRANSMIT-000103 | NA | Trade Partner | SS ACC free standing drinking fountain with bottle filler | 0 | 1 | 0 |  | APPROVED | 2025-12-01 | WF-000638 |  | 2025-12-03 | [8 empty] | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-09 | A.S.H.-TRANSMIT-000065 |  | Trade Partner | ASH IFC drawings | 1 | 0 | 0 | NA | APPROVED | [5 empty] | Same revision (A.S.H.-TRANSMIT-000066) |  |  | KPTG-TRANSMIT-000300 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-17 | Jangho-TRANSMIT-000023 | NA | Trade Partner | 671 Chapel St Project VMU02/03 shop drawings Rev01 | 56 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 354 | 2026-03-23 |  | Client Review |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-17 | EAEGROUP-TRANSMIT-000091 | NA | Trade Partner | Shop Drawings Submission for Approval – RFI KPTG-RFI-006473 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with the document number and revision |  | 2026-03-17 | KPTG-DA-005506 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-17 | D&E-TRANSMIT-000489 | NA | Trade Partner | NXM3S2 - Lower Roof - Typical Chiller Module Layout - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 3976 | 2026-03-24 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-014675 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-17 | D&E-TRANSMIT-000488 | NA | Trade Partner | Office Mechanical Duct Layout - Issued for Approval | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with the revision |  | 2026-03-17 | KPTG-TRANSMIT-014508 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-17 | D&E-TRANSMIT-000490 | NA | Trade Partner | Office Mechanical Duct Layout - Issued for Approval | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with the document number |  | 2026-03-17 | KPTG-TRANSMIT-014529 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-17 | Tradetec-TRANSMIT-000393 | NA | Trade Partner | Concrete Mix Design TD - Stage 2 - Streetlight Footing | 0 | 1 | 0 | NA | APPROVED | 2026-03-17 | WF-004838 | NA | 2026-03-24 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-17 | Stowe-A-TRANSMIT-000519 | NA | Trade Partner | Stowe - Tech Data Submission - PE Enclosures | 0 | 1 | 0 | NA | APPROVED | 2026-03-17 | WF-004846 | NA | 2026-03-30 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-014959 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-17 | Schindle-TRANSMIT-000021 | NA | Trade Partner | PL1 - Landing Frames for approval | 2 | 0 | 0 | NA | APPROVED | 2026-03-17 | WF-004849 | NA | 2026-03-30 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016205 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-17 | ACG-TRANSMIT-000068 | NA | Trade Partner | M3 - Stage 2 Samples - IFC Revision | 0 | 9 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-03-17 | KPTG-TRANSMIT-014511 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-17 | ACG-TRANSMIT-000069 | NA | Trade Partner | M3 - Stage 2 Samples - IFA Revision | 0 | 2 | 0 | NA | APPROVED | 2026-03-17 | WF-004842 | NA | 2026-03-24 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-015803 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-10 | MCM Tile-TRANSMIT-000007 | NA | Trade Partner | MLC Expansion Joints | 0 | 1 | 0 | NA | APPROVED | 2025-12-10 | WF-000665 |  | 2025-12-15 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-17 | PARR-TRANSMIT-000056 | NA | Trade Partner | P2645 - KPG NDC M3 S1 DH7&8 - Fuel - AS-BUILT | 18 | 1 | 0 | KPTG-IntCorr-003252 | APPROVED | 2026-03-20 | NA | 1435 | 2026-03-26 |  | 1 Tech data submitted through Aconex workflow-WF-000971 | 2026-04-07 | 2026-04-08 | KPTG-TRANSMIT-002841 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-17 | HDRAus-TRANSMIT-000082 | NA | Consultant | Customer Security Change Requests - Direction to Proceed | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | HDRAus-TRANSMIT-000081 superseded with HDRAus-TRANSMIT-000082 -Distribution Only |  | 2026-03-17 | KPTG-TRANSMIT-002776 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | D&E-TRANSMIT-000486 | NA | Trade Partner | BMS Technical data | 0 | 1 | 0 | NA | APPROVED | 2026-03-17 | NA | NA | 2026-04-07 |  | WF TERMINATED AS PER WILL REQUEST |  | 2026-03-23 | KPTG-IntCorr-011091 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | D&E-TRANSMIT-000485 | NA | Trade Partner | NXM3S2 - Ground - Mechanical Duct Layout - Zone 5 & 7 - Issued For Approval | 2 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 2546 | 2026-03-25 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-015603 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | D&E-TRANSMIT-000487 | NA | Trade Partner | Re: ISSUED FOR APPROVAL - CHW & SFN SCHEMATIC | 3 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED - Difference in Drawiing number |  | 2026-03-17 | KPTG-TRANSMIT-014503 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-16 | ADP-TRANSMIT-000282 | NA | Consultant | Re: MEL4780 - ADP upated EL drawing | 1 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 2525 | 2026-03-18 |  |  | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-014497 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | Mirage D-TRANSMIT-000013 | NA | Trade Partner | Re: Technical Data - Roller Shutters | 0 | 2 | 0 | NA | REJECTED | [7 empty] | 2026-03-17 | KPTG-TRANSMIT-014505 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | Altaire-TRANSMIT-000097 | NA | Trade Partner | Re: NEXTDC M3S4 - Dry Fire Shop Drawings (For Construction) (B) | 13 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to difference in status |  | 2026-03-17 | KPTG-TRANSMIT-014506 | Closed | 13 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | ARCST-TRANSMIT-000231 | NA | Trade Partner | C1 East Lower Gantry - Issued for Approval | 159 | 0 | 0 | NA | REJECTED | [5 empty] | CANCELLED AND PROCESSED THE SAME DOCUMENT FROM KPTG-TRANSMIT-014498 |  | 2026-03-17 | KPTG-TRANSMIT-014498 | Closed | 159 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-10 | RDSBIM-TRANSMIT-000129 | NA | Trade Partner | LEVEL 02 PARTITION WALL PLAN | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | KPTG-TRANSMIT-014498 | NA | Consultant | WF Request - C1 East Lower Gantry | 151 | 0 | 0 | NA | APPROVED | 2026-03-10 | WF-004851 & WF-005527 | NA | 2026-04-07 |  | 145 DOCS STILL UNDER REVIEW |  | 2026-05-05 | KPTG-TRANSMIT-016951 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | PARR-TRANSMIT-000136 | NA | Trade Partner | Re: P2685 - NDC M3 - Stage 4 - Battery Rooms - Client Drawings | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - Difference in Revision Number |  | 2026-03-17 | KPTG-TRANSMIT-014530 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | PARR-TRANSMIT-000135 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - TDP | 0 | 28 | 0 | NA | REJECTED | [5 empty] | REJECTED DUE TO INCORRECT DISCIPLINE |  | 2026-03-17 | KPTG-TRANSMIT-014531 | Closed | 28 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | ECBS-TRANSMIT-000027 | NA | Trade Partner | Stage 4 - Material Tech data sheet for approval | 0 | 17 | 0 | NA | APPROVED | 2026-03-17 | WF-004855 | NA | 2026-04-07 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-016565 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-17 | Best.-TRANSMIT-000008 | NA | Consultant | Finalised Message Schedule | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC DOCUMENTS, TRANSMITTED TO TRADE & CONSULTANTS |  | 2026-03-17 | KPTG-TRANSMIT-002579 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-17 | RDSBIM-TRANSMIT-000120 | NA | Trade Partner | MLCSPR ¦ OUTDOOR COURT LEVEL 02 CONCRETE PROFILE PLAN SHEET 8 | 1 | 0 | 0 |  | APPROVED | 2026-03-26 | NA | 474 | 2026-04-02 |  | Kapitol advice sought on Workflow creation in ACC:KPTG-IntCorr-006088 | 2026-05-14 | 2026-05-14 | KPTG-SADV-004332 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-17 | TGRF-TRANSMIT-000100 | NA | Trade Partner | Stage 2 - PT General arrangement drawings for review | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Title of document Number do not match with what is inside the Drawing, requested to resubmit:KPTG-SADV-003898 |  | 2026-03-17 | KPTG-SADV-003898 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-17 | Normark-TRANSMIT-000052 | NA | Trade Partner | Shop drawing for timber inlay in Curved and straight seating | 5 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 463 | 2026-03-20 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-003077 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-17 | PROLMC-TRANSMIT-000025 | NA | Trade Partner | Re: MLC ¦ AM15 tech data submission | 0 | 9 | 0 | NA | REJECTED | [5 empty] | DOCUMENT NUMBER OF A TECHNICAL DATA IS INCORRECT, REQUESTED TO RESUBMIT:KPTG-SADV-003897 |  | 2026-03-17 | KPTG-SADV-003897 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-17 | VIA Arch-TRANSMIT-000072 | NA | Consultant | M2 S9-11 building Permit Status Update issue for Information | 71 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 464 | 2026-03-20 |  |  | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-001650 | Closed | 71 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-10 | SMEPS-TRANSMIT-000120 | NA | Trade Partner | M3 Stage 3 - 22KV Precast Panel Shop Drawings | 4 | 0 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-17 | VIA Arch-TRANSMIT-000073 | NA | Consultant | Building Permit - Cover Sheet | 1 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 464 | 2026-03-20 |  |  | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-001650 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-13 | RDSBIM-TRANSMIT-000119 | NA | Trade Partner | MLCSPR ¦ OUTDOOR COURT LEVEL 02 CONCRETE PROFILE PLAN SHEET 7 | 1 | 0 | 0 | KPTG-IntCorr-006090 | APPROVED | [5 empty] | KPTG-IntCorr-006090: KAPITOL ADVICE AWAITS |  | 2026-03-13 |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-13 | VIA Arch-TRANSMIT-000066 | NA | Consultant | M2 S9-11 Building Permit - GF Progress Issue | 54 | 0 | 0 | NA | REJECTED | [5 empty] | Need to revise KPTG-DA-001592 (Drawings resubmitted via VIA Arch-TRANSMIT-000072 |  | 2026-03-13 | KPTG-DA-001592 | Closed | 54 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-17 | Tradetec-TRANSMIT-000073 | NA | Trade Partner | Transmittal of LVP23 and LVP24 Shop Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 462 | 2026-03-23 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-001758 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-17 | Tradetec-TRANSMIT-000074 | NA | Trade Partner | Recycled Conduits Alternative Technical Data | 0 | 1 | 0 | NA | APPROVED | 2026-03-17 | WF-000357 | NA | 2026-03-27 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-001744 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-17 | ASV-TRANSMIT-000028 | NA | Trade Partner | HDPE Swivel/Expansion joints Joints | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Need to revise the document KPTG-SADV-001802 |  | 2026-03-17 | KPTG-SADV-001802 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-17 | ASV-TRANSMIT-000029 | NA | Trade Partner | HDPE Swivel/Expansion Joints | 0 | 1 | 0 | NA | APPROVED | 2026-03-17 | WF-000354 | NA | 2026-03-27 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-001785 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-17 | ASV-TRANSMIT-000030 | NA | Trade Partner | Revised Complete Pit Package | 0 | 1 | 0 | NA | APPROVED | 2026-03-17 | WF-000356 | NA | 2026-03-27 |  |  | 2026-04-15 | 2026-04-16 | KPTG-TRANSMIT-002182 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-17 | RDSBIM-TRANSMIT-000167 | NA | Trade Partner | LINDRUM ¦ MEZZANINE LEVEL CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | #602 | 2026-03-25 |  | WORKFLOW TERMINATED | 2026-03-24 | 2026-03-24 | KPTG-IntCorr-000817 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-16 | Hames-TRANSMIT-000136 | NA | Consultant | Latest Revision-ARC | 55 | 0 | 0 | 1 DWG REVISED BY HS (TRN#138) | APPROVED | 2026-03-17 | NA | 1128 | 2026-03-19 |  | 1 DWG REVISED BY HS QA error | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-003141 | Closed | 54 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-10 | OveArup-TRANSMIT-000137 | NA | Consultant | 3 Stage 3 Earthing Drawings IFCN update with dwg files | 2 | 0 | 0 | NA | REJECTED | [5 empty] | The document revision number does not match the Aconex revision. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-16 | CRSol-TRANSMIT-000058 | NA | Trade Partner | HAC Drawings Issued for Construction | 12 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 1134 | 2026-03-19 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | KPTG-WTRAN-008926 | NA | Consultant | FACAD WORKFLOW | 0 | 1 | 0 | NA | APPROVED | 2026-03-18 | WF-004845 | NA | 2026-04-13 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016494 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-16 | KETE-TRANSMIT-000118 | NA | Trade Partner | Submission – sample updat | 0 | 4 | 0 | NA | REJECTED | [5 empty] | KPTG-SADV-003469-Its not current revision. |  |  |  | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-18 | RDSBIM-TRANSMIT-000002 | NA | Trade Partner | NXGE01 ¦ GROUND FLOOR CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 45 | 2026-03-23 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-000106 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-16 | Civilex-TRANSMIT-000050 | NA | Trade Partner | District Docklands Alimak Design Addendum Package | 0 | 1 | 0 | KPTG-TRANSMIT-000755 | REJECTED | [5 empty] | Rejected |  | 2026-03-16 | KPTG-TRANSMIT-000755 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-16 | Hollow-TRANSMIT-000007 | NA | Trade Partner | Shop drawings, Issued for approval_2 | 2 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 333 | 2026-03-23 |  | review voided by Victoria | 2026-03-26 |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-17 | Appselec-TRANSMIT-000028 | NA | Trade Partner | COLO 4 & 5 - Earthing Layout and Earthing Schematics - Issued for Approval | 16 | 0 | 0 | NA | APPROVED | 2026-03-17 | WF-000063 | NA | 2026-03-24 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-000161 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-17 | Entire M-TRANSMIT-000011 | NA | Trade Partner | Mechanical Fire Matrix - COLO 4&5 | 0 | 1 | 0 | NA | APPROVED | 2026-03-17 | WF-000064 | NA | 2026-03-24 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-000235 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-16 | Civilex-TRANSMIT-000036 | NA | Trade Partner | Waterproofing for Raft 4 and 5 | 0 | 1 | 0 | NA | APPROVED | 2026-03-17 | WF-000241 | NA | 2026-03-19 |  | For proactive Water proofing Sign off | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-000812 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-16 | PCForm-TRANSMIT-000101 | NA | Trade Partner | XL mix designs | 0 | 1 | 0 | NA | APPROVED | 2026-03-17 | WF-000245 | NA | 2026-03-19 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-000842 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-05 | WAM-TRANSMIT-000018 | NA | Consultant | WAM ARCH - 80% DD Facade Update | 17 | 0 | 0 | NA | APPROVED | 2025-12-08 | NA | 135 | 2025-12-10 |  |  | 2025-12-09 | 2025-12-10 | KPTG-TRANSMIT-000218 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-16 | PCForm-TRANSMIT-000102 | NA | Trade Partner | XL concrete mix design 80mpa | 0 | 1 | 0 | NA | APPROVED | 2026-03-17 | WF-000246 | NA | 2026-03-19 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-000841 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-16 | PCForm-TRANSMIT-000104 | NA | Trade Partner | Sample submission Actech ferrules | 0 | 1 | 0 | NA | APPROVED | 2026-03-17 | WF-000247 | NA | 2026-03-19 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-000840 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-17 | Entire M-TRANSMIT-000010 | NA | Trade Partner | Mechanical IFC Rev 1 - Grilles, Louvres, Armaflex, Pipe Cable Tray & Fire Dampers | 0 | 5 | 0 | NA | APPROVED | 2026-03-17 | WF-000068 | NA | 2026-03-23 |  |  | 2026-03-27 | 2026-03-30 | KPTG-TRANSMIT-000226 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-16 | PCForm-TRANSMIT-000105 | NA | Trade Partner | Stair Shop Drawings Transmittal | 32 | 7 | 0 | NA | APPROVED | 2026-03-17 | NA | 335 | 2026-03-19 |  | 7 DOCS REJECTED : | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-001408 | Closed | 32 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-17 | Entire M-TRANSMIT-000009 | NA | Trade Partner | Mechnical IFA Rev B - Splits, Refidge & Copper pipe, Pipe fittings | 0 | 3 | 0 | NA | APPROVED | 2026-03-17 | WF-000065 | NA | 2026-03-24 |  | Aurecon-WTRAN-000115, Document has no review stamp, hence, requested them to submited revieweed document with review stamp.-KPTG-IntCorr-000202 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-16 | INDS-TRANSMIT-000033 | NA | Trade Partner | Wet Fire - Mezzanine | 1 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-IntCorr-000794 |  | 2026-03-16 | KPTG-IntCorr-000794 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-16 | TTW-TRANSMIT-000109 | NA | Consultant | TTW Detail updates | 9 | 0 | 0 | KPTG-TRANSMIT-000768 | APPROVED | 2026-03-17 | NA | 340 | 2026-03-20 |  | 1 Rejected drawing sent via Trn# 114 | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-000947 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-17 | SES AU-TRANSMIT-000004 | NA | Trade Partner | Security Tech Data | 0 | 20 | 0 | NA | APPROVED | 2026-03-17 | WF-000066 | NA | 2026-03-24 |  |  | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-000267 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-11 | SIL-TRANSMIT-000013 | NA | Trade Partner | Re-Transmitting the documents | 0 | 13 | 0 | NA | APPROVED | 2026-03-16 | WF-000061 | NA | 2026-03-19 |  |  | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-000139 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-11 | SIL-TRANSMIT-000012 | NA | Trade Partner | Documents Issued for Construction | 3 | 0 | 0 | NA | APPROVED | 2026-03-17 | WF-000062 | NA | 2026-03-20 |  |  | 2026-03-27 | 2026-03-30 | KPTG-TRANSMIT-000223 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-10 | SMEPS-TRANSMIT-000120 | NA | Trade Partner | M3 Stage 3 - 22KV Precast Panel Shop Drawings | 4 | 0 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-18 | D&E-TRANSMIT-000173 | NA | Trade Partner | CONTROLS FD & POINTS LIST | 0 | 2 | 0 | NA | REJECTED | [7 empty] | 2026-03-18 | KPTG-TRANSMIT-000554 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-18 | Baigents-TRANSMIT-000077 | SPARK-CRFI-KPG-000172 | Trade Partner | MCC Monorail Issued for Approval | 33 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 179 | 2026-03-25 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-000862 | Closed | 33 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-18 | ADP-TRANSMIT-000033 | NA | Consultant | MEL4680 - BP1 docs and Reg126 | 2 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 47 | 2026-03-21 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-000105 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-10-06 | SMEPS-TRANSMIT-000029 | SPARK-CRFI-KPG-000106 | Trade Partner | IFA - Shop Drawings Ingrounds 2no. | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-18 | KPTG-TRANSMIT-000550 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-18 | Civilex-TRANSMIT-000212 | NA | Trade Partner | Switchroom Handrail IFC | 16 | 0 | 0 | NA | APPROVED | 2026-03-18 | WF-004866 | NA | 2026-03-31 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-015029 | Closed | 16 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-18 | NXT-TRANSMIT-001425 | NA | Trade Partner | P2671 - NDC M3 Stage 4 - Enclosures - SCHEMATIC & CABLE SCHEDULE AND TERMINATIONS | 2 | 0 | 0 | NA | APPROVED | 2026-03-18 | WF-004868 | NA | 2026-03-31 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-18 | NXT-TRANSMIT-001426 | NA | Trade Partner | Fwd: Block C1 IFC Shop Drawings Submission – Zone C1 | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | The documents have been sent to KP team. The team will inform if any further action is required. |  | 2026-03-18 | KPTG-TRANSMIT-014548 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-18 | PMT Sec-TRANSMIT-000002 | NA | Trade Partner | PMT Tech Data - Security | 0 | 37 | 0 | NA | REJECTED | [7 empty] | 2026-03-19 | KPTG-TRANSMIT-000557 | Closed | 37 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-18 | Altaire-TRANSMIT-000098 | NA | Trade Partner | NEXTDC M3S4 - Dry Fire Shop Drawings (For Construction) (B Updated) | 13 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 2556 | 2026-03-24 |  |  | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-015388 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-18 | fjc-TRANSMIT-000142 | NA | Consultant | Architecturals - RFIs + BP6 Items | 59 | 6 | 0 | NA | APPROVED | 2026-03-18 | WF-000669 | 603 | 2026-03-23 |  |  | 2026-03-20 | 2026-03-20 | KPTG-SADV-003519, KPTG-TRANSMIT-002140 | Closed | 63 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-10 | Auscool-TRANSMIT-000058 | NA | Trade Partner | Fan & Attenuator Tech Data Issued For Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | REVISION OF THE DOCUMENT IS INCORRECT. |  | 2025-12-10 | KPTG-SADV-002437 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-18 | PFP PL-TRANSMIT-000076 | NA | Trade Partner | Roof Floor Webforge Peno DWG IFA | 3 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 2566 | 2026-03-24 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-015990 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-18 | PARR-TRANSMIT-000138 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - Client Drawings | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Duplication of NXT-TRANSMIT-001423 | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-014708 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-18 | Nilsen3-TRANSMIT-000066 | NA | Trade Partner | Interface panel - Shop drawings - REV 1 | 0 | 1 | 0 | NA | APPROVED | 2026-03-18 | WF-004879 | NA | 2026-03-30 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-18 | Highbu-TRANSMIT-000044 | NA | Trade Partner | Mezzanine Water and Drainage - IFA | 2 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | #604 | 2026-03-25 |  |  | 2026-03-26 | 2026-03-26 | KPTG-SADV-003566 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-18 | Nilsen3-TRANSMIT-000068 | NA | Trade Partner | Re: Copper tape sample submission | 0 | 1 | 0 | NA | APPROVED | 2026-03-18 | WF-004873 | NA | 2026-04-08 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-18 | Nilsen3-TRANSMIT-000067 | NA | Trade Partner | Re: Stage 4 ROPS A & B Sample | 0 | 1 | 0 | NA | APPROVED | 2026-03-18 | WF-004874 | NA | 2026-04-08 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-18 | Nilsen3-TRANSMIT-000065 | NA | Trade Partner | Re: Stage 4 ROPS A & B Sample | 0 | 1 | 0 | NA | APPROVED | 2026-03-18 | WF-004874 | NA | 2026-04-10 |  | Incorrect document number format | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-015641 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-18 | Nilsen3-TRANSMIT-000064 | NA | Trade Partner | Re: Copper tape sample submission | 0 | 1 | 0 | NA | APPROVED | 2026-03-18 | WF-004873 | NA | 2026-04-10 |  | Incorrect document number format | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-015646 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-18 | KPTG-SADV-002332 | NA | Trade Partner | HAC Barcode Shop Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 1426 | 2026-03-24 |  | Reissue for review-requested by Kim |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-18 | KPTG-IntCorr-003265 | NA | Trade Partner | Services Penetrations - Physical Security Treatment | 1 | 0 | 0 | KPTG-IntCorr-003272 | APPROVED | 2026-03-20 | NA | 1431 | 2026-03-26 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-05 | WAM-TRANSMIT-000019 | NA | Consultant | Prototype Package | 8 | 2 | 0 | NA | APPROVED | 2025-12-08 | NA | 137 | 2025-12-11 |  |  | 2025-12-15 | 2025-12-15 | KPTG-TRANSMIT-000249 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-18 | Stulz -TRANSMIT-000036 | NA | Trade Partner | Stulz Initial draft O&M | 0 | 1 | 0 | Declan to confirm | APPROVED |  | NA | NA |  |  | No action Required |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-18 | D&E-TRANSMIT-000349 | NA | Trade Partner | D&E O&M Manual - Issued for Review | 0 | 1 | 0 | KPTG-IntCorr-003289 | APPROVED |  | NA | NA |  |  | No Action Required |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-18 | Stowe-A-TRANSMIT-000520 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - SCHEMATICS - 18.03.2026 | 3 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 3986 | 2026-03-25 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-014984 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-18 | D&E-TRANSMIT-000493 | NA | Trade Partner | NXM3S2 - Lower Ground - Mechanical Duct Layout Zone 3 & Zone 4 - Issued For Construction | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Revision number already existing and completed review. |  | 2026-03-18 | KPTG-TRANSMIT-014597 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-17 | Hames-TRANSMIT-000137 | NA | Consultant | PREFORMANCE SOLUTION THRESOLDS & HOBS | 0 | 1 | 0 | NA | REJECTED | [5 empty] | REJECTED |  | 2026-03-17 | KPTG-TRANSMIT-003128 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-18 | NXT-TRANSMIT-001420 | NA | Client | 100222-000580: M3 DATA CENTER STAGE 2 EB, EC & ED Rooms - MDR's - For Approval | 0 | 3 | 0 | NA | APPROVED | 2026-03-18 | WF-004887 | NA | 2026-03-23 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-17 | Hames-TRANSMIT-000138 | NA | Consultant | Hames-TRANSMIT-000136 Update | 2 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 1128 | 2026-03-18 |  | 1 DWG REVISED BY HS (TRN#140) - 1 DWG SUBMITTED ALONG WITH TRN#136 |  | 2026-03-18 | KPTG-TRANSMIT-003145 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-17 | Hames-TRANSMIT-000139 | NA | Consultant | Stage 2 - FFE Schedule Issue | 0 | 1 | 0 | REPLACED BY TRN#141 | REJECTED | [5 empty] | REPLACED BY TRN#141 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-18 | Tradetec-TRANSMIT-000395 | NA | Trade Partner | Tech Data - Culvert Tape | 0 | 1 | 0 | NA | APPROVED | 2026-03-18 | WF-004860 | NA | 2026-03-25 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-014578 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-17 | Hames-TRANSMIT-000140 | NA | Consultant | Hames-TRANSMIT-000138 Re-upload | 2 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 1136 | 2026-03-18 |  | 1 DWG ALREADY PROCESSED BY (TRN#138) | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-003133 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2025-12-10 | TATE_-TRANSMIT-000021 | NA | Trade Partner | Tech Data - Iccons Strike Anchor | 0 | 1 | 0 | NA | APPROVED | 2025-12-10 | WF-000174 |  | 2025-12-17 |  |  |  | 2025-12-12 | KPTG-TRANSMIT-000629 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-17 | Hames-TRANSMIT-000141 | NA | Consultant | Updated Schedule. | 0 | 1 | 0 | NA | APPROVED | 2026-03-17 | NA | 1133 | 2026-03-18 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-003137 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-18 | D&E-TRANSMIT-000495 | NA | Trade Partner | NXM3S2 - Lower Ground / Ground / Level 01 Mechanical Duct + Pipe Layout Zones incl Sections - Issued For Construction | 17 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 3989 | 2026-03-31 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-014681 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-17 | RDSBIM-TRANSMIT-000069 | NA | Trade Partner | GROUND FLOOR B-G-009-03 SHOWER 01 FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 1138 | 2026-03-19 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-003291 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-18 | ZIA-TRANSMIT-000075 | NA | Trade Partner | M3S2 Fire Trip Valve Panel Drawing (FOA-1) | 1 | 0 | 0 | NA | APPROVED | 2026-03-20 | WF-004915 | NA | 2026-04-06 |  |  | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-015383 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-18 | Civilex-TRANSMIT-000214 | NA | Trade Partner | Sample Submission - Pavement Concrete mix design (Pronto - Hy Tec) - Updated naming Rev B | 0 | 2 | 0 | NA | REJECTED | [5 empty] | The status is not mentioned inside the document. |  | 2026-03-18 | KPTG-TRANSMIT-014599 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-18 | SKS Tech-TRANSMIT-000170 | NA | Trade Partner | STRING A, B & C SCHEMATIC IFC UPDATES | 3 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 1147 | 2026-03-20 |  |  |  | 2026-03-24 | KPTG-TRANSMIT-003232 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-18 | Diadem-TRANSMIT-000023 | NA | Consultant | Updated Signage D | 67 | 0 | 0 | NA | REJECTED | [5 empty] | Mistakes on naming and revision number in Aconex and inside document |  | 2026-03-18 | KPTG-TRANSMIT-014603 | Closed | 67 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-01 | IVS-TRANSMIT-000285 | NA | Consultant | Stage 4 - Roof Zone C2 Construction Issue (revised as clouded) | 5 | 0 | 0 | NA | APPROVED | 2025-12-01 | NA | 1582 | 2025-12-03 |  | The Workflow has been terminated as per requested by KAP |  |  | NA | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-01 | Fredon T-TRANSMIT-000007 | NA | Trade Partner | AV Display Bracket | 0 | 1 | 0 |  | APPROVED | 2025-12-01 | WF-000641 |  | 2025-12-03 |  |  | 2026-01-13 | 2026-01-13 | KPTG-TRANSMIT-002064 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-10 | NXT-TRANSMIT-001124 / PARR-TRANSMIT-000104 | NA | Trade Partner | P2671 - NDC M3 Stage 4 - Enclosures - Client documents - IFC | 6 | 0 | 0 | NA | APPROVED | 2025-12-10 | WF-003554 | NA | 2025-12-24 |  |  |  | 2026-01-22 | KPTG-TRANSMIT-011801 | Closed | 6 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-18 | D&E-TRANSMIT-000497 | NA | Trade Partner | Office Mechanical Duct Layout - Issued for Aproval | 1 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 3993 | 2026-03-27 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-015435 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-18 | D&E-TRANSMIT-000498 | NA | Trade Partner | NXM3S2 - Lower Ground - High Level Mechanical Pipe + Mechanical Duct Layout Zones - Issued For Construction | 4 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 3992 | 2026-03-25 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-014688 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-27 | HDRAus-TRANSMIT-000411 | NA | Consultant | M3 Stage 1 - HS1 Office Desks in YZ Offices | 6 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 3980 | 2026-03-20 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-015053 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-18 | Civilex-TRANSMIT-000210 | NA | Trade Partner | Stage 1 Swale Restoration Plan Approval | 2 | 0 | 0 | NA | REJECTED | [5 empty] | 1. The document number is not mentioned inside the drawings. 2. Revision number is also not mentioned inside the drawings. 3. The document number should be M3-LAD-MSA-SDRG-A-0110-0001 instead of M3-LAD-MSA-SDRG-B-0101-0001 |  | 2026-03-18 | KPTG-DA-005552 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-18 | HDRAus-TRANSMIT-000368 | NA | Consultant | Site Wide - Architectural Documentation | 1 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 3983 | 2026-03-20 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-014980 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-18 | ARCST-TRANSMIT-000233 | NA | Trade Partner | HV Steel Drawings issued for Approval | 51 | 0 | 0 | NA | REJECTED | [5 empty] | The document numbers seems different in Aconex and inside documents |  | 2026-03-18 | KPTG-TRANSMIT-014609 | Closed | 51 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-09-01 | Schindle-TRANSMIT-000009 | NA | Trade Partner | VT - GL1 FC2 shop drawings | 6 | 0 | 0 | NA | APPROVED | 2025-09-01 | NA | 2383 | 2025-09-10 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-014608 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-09-03 | Schindle-TRANSMIT-000010 | NA | Trade Partner | VT shop drawings - GL2 - REV FC2 | 6 | 0 | 0 | NA | APPROVED | 2025-09-03 | NA | 2436 | 2025-09-19 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-014592 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-17 | WAM-TRANSMIT-000731 | NA | Consultant | DD Update | 73 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 337 | 2026-03-20 |  | 1-DRAWING REJECTED - 72 DWGS IN REVIEW | 2026-03-27 | 2026-03-27 | ACC 374 | Closed | 67 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-10 | NXT-TRANSMIT-001125 | NA | Trade Partner | P2671 - NDC M3 Stage 4 - Enclosures - TECH DATA - IFC | 1 | 0 | 0 | NA | APPROVED | 2025-12-10 | WF-003556 | NA | 2025-12-24 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-012568 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-17 | WAM-TRANSMIT-000731 | NA | Consultant | DD Update | 0 | 1 | 0 | NA | APPROVED | 2026-03-17 | WF-000255 | NA | 2026-03-20 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-000983 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-17 | WAM-TRANSMIT-000732 | NA | Consultant | DD Update CAD | 46 | 0 | 0 | NA | APPROVED | [5 empty] | CAD FILES REGISTER UPDATED - Cross checked for any revision descrepancy |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-17 | Civilex-TRANSMIT-000053 | NA | Trade Partner | District Docklands Alimak Design Addendum Package | 0 | 1 | 0 | NA | APPROVED | 2026-03-17 | WF-000249 | NA | 2026-03-20 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-000845 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-17 | TTW-TRANSMIT-000110 | NA | Consultant | BP1 Update | 1 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 342 | 2026-03-20 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-000890 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-17 | TTW-TRANSMIT-000111 | NA | Consultant | BP8 - Issued for certification | 10 | 1 | 0 | NA | APPROVED | 2026-03-17 | NA | 344 | 2026-03-20 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-000857 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-17 | TTW-TRANSMIT-000113 | NA | Consultant | BP4 Issue Update | 12 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 346 | 2026-03-20 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-000889 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-17 | TTW-TRANSMIT-000114 | NA | Consultant | Updated detail 05403 | 1 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 340 | 2026-03-20 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-000949 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-17 | Rinco-TRANSMIT-000002 | NA | Consultant | Level 2 (Level 3 - Existing car park) | 6 | 0 | 0 | KPTG-IntCorr-000486 | REJECTED | [5 empty] | Rejected by Victoria |  | 2026-03-17 | KPTG-IntCorr-000486 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-17 | SEAPBU-TRANSMIT-000003 | NA | Trade Partner | ASCO Submittals | 3 | 0 | 0 |  | APPROVED | 2026-03-22 | WF-000082 | NA | 2026-03-23 |  | Kapitol advice awaits on Covering sheet of ship drawing:KPTG-IntCorr-000155 | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-000401 | Open | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-17 | SEAPBU-TRANSMIT-000004 | NA | Trade Partner | ASCO Test SCripts | 1 | 0 | 0 | NA | APPROVED | 2026-03-19 | WF-000078 | NA | 2026-03-24 |  | Excel document needs to be Pdf in format:KPTG-IntCorr-000153 | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-000278 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-10 | Auscool-TRANSMIT-000059 | NA | Trade Partner | Fan Tech Data For Approval | 0 | 1 | 0 | NA | APPROVED | 2025-12-10 | WF-000523 |  | 2025-12-12 |  |  | 2026-01-30 | 2026-01-30 | KPTG-TRANSMIT-001657 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-18 | RDSBIM-TRANSMIT-000033 | NA | Trade Partner | GREYSTAR BASEMENT FLOOR CONCRETE PROFILE KEY PLAN | 7 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 538 | 2026-03-26 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-001163 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-18 | Auspan-TRANSMIT-000145 | NA | Trade Partner | Precast shop drawings for approval. Zone 2 level 2 | 39 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 540 | 2026-03-25 |  |  | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-001047 | Closed | 39 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-18 | Auspan-TRANSMIT-000146 | NA | Trade Partner | Precast marking plan level 2 zone 1, 2 | 1 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 542 | 2026-03-25 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-18 | Appselec-TRANSMIT-000029 | NA | Trade Partner | COLO 4 & 5 - Containment and Busway Layout - Issued for Approval | 15 | 0 | 0 | NA | APPROVED | 2026-03-18 | WF-000072 | NA | 2026-03-25 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-000146 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-18 | Auspan-TRANSMIT-000147 | NA | Trade Partner | Precast shop drawings for construction. 1B044A | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - No review required - Register and distribute - KPTG-TRANSMIT-000968 |  | 2026-03-18 | KPTG-TRANSMIT-000968 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-18 | Auspan-TRANSMIT-000148 | NA | Trade Partner | Precast shop drawings for construction | 37 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC No review required - Register and distribute - KPTG-TRANSMIT-000970 |  | 2026-03-18 | KPTG-TRANSMIT-000970 | Closed | 37 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-18 | Auscool-TRANSMIT-000016 | NA | Trade Partner | Mechanical Design Layout Air Schematic | 0 | 1 | 0 | NA | APPROVED | 2026-03-18 | WF-000285 | NA | 2026-03-24 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-001036 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-18 | INDS-TRANSMIT-000006 | NA | Trade Partner | Ground - Floor Penetration Layouts | 5 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 530 | 2026-03-25 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-001064 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-18 | Entire M-TRANSMIT-000012 | NA | Trade Partner | COLO 4/5 - Mechanical shop drawings issued for approval | 12 | 0 | 0 | NA | APPROVED | 2026-03-18 | WF-000070 | NA | 2026-03-23 |  |  | 2026-04-13 | 2026-04-14 | KPTG-TRANSMIT-000357 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-18 | INDS-TRANSMIT-000009 | NA | Trade Partner | Level 1 Floor Penetration Layout | 5 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 532 | 2026-03-25 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-001061 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-10 | IVS-TRANSMIT-000296 | NA | Consultant | Stage 4 - Switchroom Plans Zone C2 (Certification Issue) - Formal Issue | 26 | 0 | 0 | NA | APPROVED | 2025-12-10 | 1633 | NA | 2025-12-12 |  |  |  | 2025-12-16 | KPTG-TRANSMIT-010968 | Closed | 26 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-18 | INDS-TRANSMIT-000010 L2 to L7 | NA | Trade Partner | Typical Floor Penetration Layout | 5 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 534 | 2026-03-25 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-001071 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-18 | INDS-TRANSMIT-000011 | NA | Trade Partner | L2 to L7 - Penetration Layout | 22 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 536 | 2026-03-25 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-001068 | Closed | 22 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-18 | Auspan-TRANSMIT-000149 | NA | Trade Partner | Re: Precast marking plan level 2 zone 1, 2 | 1 | 0 | 0 | KPTG-IntCorr-000393 | APPROVED |  | NA | NA |  |  | Waiting for Kapitol advise KPTG-IntCorr-000393 IFC no review required; register and distribute - KPTG-TRANSMIT-000989 |  | 2026-03-20 | KPTG-TRANSMIT-000989 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-18 | RDSBIM-TRANSMIT-000034 | na | Trade Partner | GREYSTAR BASEMENT FLOOR CONCRETE PROFILE KEY PLAN | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Transmittal returned due to incorrect drawing revision. - DRAFT-004830 |  | 2026-03-18 | DRAFT-004830 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-18 | Stanmor-TRANSMIT-000004 | NA | Trade Partner | Revised sample submissions as per KPTG-SADV-003885 | 0 | 7 | 0 | NA | APPROVED | 2026-03-18 | WF-000882 | NA | 2026-03-23 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-002627 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-18 | crossfir-TRANSMIT-000002 | NA | Trade Partner | Wet Fire- Penetrations, Basement 04 to Ground | 5 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 358 | 2026-03-23 |  | Revised & Resubmit - | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-000671 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-18 | Stanmor-TRANSMIT-000005 | NA | Trade Partner | Transmittal of Mapei Spec | 0 | 1 | 0 | NA | APPROVED | 2026-03-18 | WF-000881 | NA | 2026-03-23 |  |  | 2026-04-14 | 2026-04-14 | KPTG-TRANSMIT-002747 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-18 | RDSBIM-TRANSMIT-000042 | NA | Trade Partner | 671CHP LEVEL 20 CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 36 | 2026-03-23 |  | Review Void as requested by Kevin Choi, Kapitol. | 2026-06-05 | 2026-06-05 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-18 | PROLMC-TRANSMIT-000026 | NA | Trade Partner | MLC ¦ AM15 tech data submission | 0 | 10 | 0 | NA | APPROVED | 2026-03-18 | WF-000880 | NA | 2026-03-23 |  |  | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-002719 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-18 | ARCH-TRANSMIT-000143 | NA | Consultant | MLC - SPR - West Ramp (Chapel Carpark entrance) update | 10 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 455 | 2026-03-25 |  |  | 2026-03-31 | 2026-04-01 | KPTG-SADV-004007 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-10 | IVS-TRANSMIT-000297 | NA | Consultant | Stage 4 - Document Register Update | 9 | 0 | 0 | NA | APPROVED | 2025-12-10 | NA | 1635 | 2025-12-12 |  |  |  | 2025-12-15 | KPTG-TRANSMIT-010954 | Closed | 9 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-18 | WGAVIC-TRANSMIT-000087 | NA | Consultant | M2 - Stage 11 Level 2 Slab - Certification Issue | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required, Drawings For certification. |  | 2026-03-18 | KPTG-TRANSMIT-001470 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-18 | WGAVIC-TRANSMIT-000088 | NA | Consultant | M2 - Stage 9 Level 1 Slab - Construction Issue | 8 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 472 | 2026-03-23 |  |  | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-001665 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-19 | IDS-TRANSMIT-000016 | NA | Trade Partner | POWER PACK PRODUCTION FACILITY - WET & DRY FIRE | 1 | 0 | 0 | NA | APPROVED | 2026-03-19 | NA | 357 | 2026-04-01 |  |  | 2026-03-23 | 2026-03-23 | KAPITOL-TRANSMIT-001232 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-19 | Nilsen3-TRANSMIT-000070 | NA | Trade Partner | M3-HV-NIL-SA-S-0301-0038 Hauff Technik Glands | 0 | 1 | 0 | NA | APPROVED | 2026-03-19 | WF-004895 | NA | 2026-03-27 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-014969 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-16 | RED Fire-TRANSMIT-000004 | NA | Trade Partner | JV22-00260 ¦ 4B3 ¦ PBDB2 for review | 0 | 1 | 0 | NA | APPROVED | 2026-02-27 | WF-000186 | NA | 2026-03-02 |  | SUBMITTED AS PER BRALEY'S MAIL | 2026-03-17 | 2026-03-17 | KPTG-TRANSMIT-000782 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-18 | SMEPS-TRANSMIT-000147 | NA | Trade Partner | DB-01 (G) REV C Tech Data for approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Error in document number and title |  | 2026-03-19 | KPTG-TRANSMIT-000558 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-19 | HEXA-TRANSMIT-000007 | NA | Trade Partner | ISSUED FOR APPROVAL - CHW & SFN SCHEMATIC | 8 | 0 | 0 | NA | APPROVED | 2026-03-17 | NA | 358 | 2026-04-01 |  |  | 2026-03-23 | 2026-03-23 | DRAFT-009441 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-19 | KPTG-WTRAN-009015 | NA | Trade Partner | 250mm Half Round Gutter | 0 | 2 | 0 | NA | APPROVED | 2026-03-19 | WF-004897 | NA | 2026-04-06 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-015032 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-18 | D&E-TRANSMIT-000492 | NA | Trade Partner | NXM3S2 - Ground - Mechanical Duct Layout | 2 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 2559 | 2026-03-26 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-015703 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-18 | D&E-TRANSMIT-000496 | NA | Trade Partner | ISSUED FOR APPROVAL - CHW & SFN SCHEMATIC | 2 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 2561 | 2026-03-26 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016511 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2025-12-10 | INV-TRANSMIT-000037 | NA | Consultant | Revised Civil Drawings | 2 | 0 | 0 | NA | APPROVED | 2025-12-10 |  | 254 | 2025-12-13 |  |  |  | 2025-12-15 | KAPITOL-TRANSMIT-000922 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-18 | SMEPS-TRANSMIT-000217 | NA | Trade Partner | SME - M3S4 - MDB/CMDB Typical Shop Drawings - Re-Submission | 3 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 2564 | 2026-03-26 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-016460 | Open | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-18 | PFP PL-TRANSMIT-000077 | NA | Trade Partner | Roof Zone C3 IFA- | 1 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 2570 | 2026-03-26 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-016021 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-18 | SMEPS-TRANSMIT-000148 | SPARK-CRFI-KPG-000359 | Trade Partner | DB-08 (A) REV C Tech data for approval | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-25 | KPTG-TRANSMIT-000595 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-18 | SMEPS-TRANSMIT-000216 | NA | Trade Partner | SME - IFA SAMPLE SUBMISSION | 0 | 1 | 0 | NA | APPROVED | 2026-03-18 | WF-004882 | NA | 2026-03-31 |  |  | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-015624 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-18 | SMEPS-TRANSMIT-000215 | NA | Trade Partner | IFA SAMPLE SUBMISSION | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | NO NEED TO PROCESSS DOCUMENT FROM THIS TRANSMITTAL ITS LATEST CAMED IN SMEPS-TRANSMIT-000216 |  | 2026-03-18 | SMEPS-TRANSMIT-000216 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-18 | HDRAus-TRANSMIT-000435 | NA | Consultant | General Arrangement Plans - Data Hall Layouts | 6 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 2572 | 2026-03-20 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-014735 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-18 | SMEPS-TRANSMIT-000149 | NA | Trade Partner | DB-09 (B) REV C Tech data for approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | wrong document |  | 2026-03-19 | KPTG-TRANSMIT-000559 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-18 | SMEPS-TRANSMIT-000150 | SPARK-CRFI-KPG-000359 | Trade Partner | DB-18 (B) REV C tech data for approval | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-25 | KPTG-TRANSMIT-000594 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-18 | SMEPS-TRANSMIT-000151 | SPARK-CRFI-KPG-000465 | Trade Partner | Distribution Boards (non cusotm) | 0 | 1 | 0 | KPTG-IntCorr-002270 | APPROVED |  | NA | NA |  |  |  |  | 2026-04-08 | KPTG-TRANSMIT-000620 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-19 | D&E-TRANSMIT-000499 | NA | Trade Partner | NXM3S2 - Lower Ground - Mechanical Duct Layout - Zone 4 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-03-19 | NA | 3995 | 2026-03-24 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-014667 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-10 | A.S.H.-TRANSMIT-000069 |  | Trade Partner | Drawings no longer in use | 10 | 0 | 0 | NA | APPROVED | [5 empty] | No Longer In Use drawings KPTG-IntCorr-001447 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-19 | DRLL-TRANSMIT-000071 | NA | Trade Partner | Battery Room Modules Mechanical Drawings IFC 05 Transmittal | 8 | 1 | 0 | NA | APPROVED | 2026-03-19 | NA | 1429 | 2026-03-25 |  |  | 2026-03-20 | 2026-03-21 | KPTG-TRANSMIT-002788 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-19 | SMEPS-TRANSMIT-000152 | SPARK-CRFI-KPG-000340 | Trade Partner | Revision B Lighting Ground Level | 10 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 191 | 2026-04-01 |  |  |  | 2026-04-17 | KPTG-TRANSMIT-000656 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-19 | D&E-TRANSMIT-000174 | SPARK-CRFI-KPG-000606 | Trade Partner | CONTROL VALVES | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-14 | KPTG-TRANSMIT-000636 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-19 | Stowe-A-TRANSMIT-000522 | NA | Trade Partner | Stowe - Tech Data Submission - HV Switch room Earth Bar Test Links | 0 | 1 | 0 | NA | APPROVED | 2026-03-19 | WF-004900 | NA | 2026-04-01 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-016364 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-19 | Civilex-TRANSMIT-000215 | NA | Trade Partner | Stage 1 Swale Restoration Revised Plan Approval | 2 | 0 | 0 | NA | APPROVED | 2026-03-19 | NA | 3997 | 2026-03-26 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-19 | Diadem-TRANSMIT-000024 | NA | Trade Partner | Updated Transmittal-Diadem TRANSMIT 000023 | 66 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong attachments and Stage 4 document. |  | 2026-03-19 | KPTG-DA-005575 | Closed | 66 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-19 | Auspan-TRANSMIT-000062 | NA | Trade Partner | Revised 1C01, 1C02 issued for construction | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-SADV-003497-As per direction from Ashlin, we have updated document register and transmitted trade & consultants. | 2026-03-19 | 2026-03-19 | KPTG-SADV-003497 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-19 | NXT-TRANSMIT-001435 | NA | Trade Partner | Fwd: 3D Drawings for UPS and Battery Cabinet | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | FOR INFO |  | 2026-03-19 | KPTG-TRANSMIT-014656 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-19 | D&E-TRANSMIT-000175 | SPARK-CRFI-KPG-000470 | Trade Partner | CONTROLS POINTS LIST | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-13 | KPTG-TRANSMIT-000631 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-19 | D&E-TRANSMIT-000350 | NA | Trade Partner | Pipe Thread Rectification Sketch Rev 2 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | No Action Required |  | 2026-03-23 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-10 | A.S.H.-TRANSMIT-000072 |  | Trade Partner | Drawings no longer in use | 10 | 0 | 0 | KPTG-IntCorr-001107 | APPROVED | [5 empty] | No Longer In Use |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-19 | D&E-TRANSMIT-000176 | SPARK-CRFI-KPG-000571 | Trade Partner | CABLE TRAY SYSTEM | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-19 | NXT-TRANSMIT-000388 | NA | Client | Critical Risk Compliance | 0 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Correspondence |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-19 | D&E-TRANSMIT-000351 | NA | Trade Partner | SFN - Removal of Threads Proposal - Updated | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | No Action Required |  | 2026-03-23 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-19 | OveArup-TRANSMIT-000075 | NA | Client | M3 - Stage 1 A7A8 Arup Site Inspection Report | 0 | 4 | 0 | NA | APPROVED |  | NA | NA |  |  | No Action Required-Register updated |  | 2026-04-02 | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-19 | Stowe-A-TRANSMIT-000523 | NA | Trade Partner | Stowe - Tech Data Submission - Metered Rack PDU | 0 | 1 | 0 | NA | APPROVED | 2026-03-19 | WF-004907 | NA | 2026-03-31 |  | Due to VPN issues close out processed on 10/04/2026 | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-015647 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-19 | ZIA-TRANSMIT-000079 | NA | Trade Partner | CSMS- Cable Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-03-19 | WF-000966 | NA | 2026-04-01 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-11-24 | PFP PL-TRANSMIT-000051 | NA | Trade Partner | Level 1 Wall Peno Layout IFA | 1 | 0 | 0 | NA | APPROVED | 2025-11-24 | NA | 3308 | 2025-12-03 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-014658 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-19 | HGP-TRANSMIT-000049 | NA | Trade Partner | Transmittal-IFC Facade calculation and reg126 certificate | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-18 | KPTG-TRANSMIT-000794 | NA | Trade Partner | Precast Concrete Mix Design | 0 | 1 | 0 | NA | APPROVED | 2026-03-18 | WF-000256 | NA | 2026-03-20 |  |  | 2026-03-18 | 2026-03-23 | KPTG-TRANSMIT-000882 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-18 | Civilex-TRANSMIT-000054 | NA | Trade Partner | Micropile Design Package Rev 3 | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-03-18 | KPTG-TRANSMIT-000838 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-10 | A.S.H.-TRANSMIT-000073 |  | Trade Partner | IFC Drawings | 38 | 0 | 0 | KPTG-IntCorr-001110 | APPROVED | [9 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-18 | WAM-TRANSMIT-000733 | NA | Consultant | Common Areas 80%DD | 19 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 348 | 2026-03-20 |  |  |  | 2026-03-31 | KPTG-TRANSMIT-000985 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-18 | WAM-TRANSMIT-000734 | NA | Consultant | DD Update | 3 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 350 | 2026-03-20 |  | 1 DWG REJECTED - RE-ISSUED VIA TRN#736 | 2026-03-27 | 2026-03-27 | ACC 374 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-18 | Hames-TRANSMIT-000143 | NA | Consultant | Performance Solution Thresholds | 0 | 1 | 0 | NA | APPROVED | 2026-03-18 | WF-000932 | NA | 2026-03-20 |  | TERMINATED BY WILL MASON | 2026-03-18 |  | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-18 | Hames-TRANSMIT-000144 | NA | Consultant | Performance Solution Thresholds | 0 | 1 | 0 | NA | APPROVED | 2026-03-18 | WF-000933 | NA | 2026-03-20 |  |  | 2026-03-19 | 2026-03-24 | KPTG-TRANSMIT-003228 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-18 | RDSBIM-TRANSMIT-000072 | NA | Trade Partner | GROUND FLOOR B-G-009-02 SHOWER 02 FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 1145 | 2026-03-20 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-003691 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-18 | RDSBIM-TRANSMIT-000071 | NA | Trade Partner | LEVEL 03 RCP KEY PLAN AND LAYOUT | 5 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 1143 | 2026-03-24 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-003617 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-18 | RDSBIM-TRANSMIT-000070 | NA | Trade Partner | LEVEL 01 PARTITION WALL PLAN AND ELEVATION | 3 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 1141 | 2026-03-20 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-003381 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-18 | VAE-Grp-TRANSMIT-000139 | NA | Trade Partner | MECHANICAL - TECH SUB & SCHED - HUMIDIFIERS - DRAIN TEMPERING KITS | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | FC Docs - Sent to all parties |  | 2026-03-18 | KPTG-TRANSMIT-003174 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-10 | A.S.H.-TRANSMIT-000074 |  | Trade Partner | Drawings no longer in use | 5 | 0 | 0 | KPTG-IntCorr-001109 | APPROVED | [9 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-18 | SKS Tech-TRANSMIT-000169 | NA | Trade Partner | LEVEL 4 & 5 Lighting IFC update | 2 | 0 | 0 | NA | APPROVED | 2026-03-18 | NA | 1149 | 2026-03-20 |  | Lara terminated 1 drawing - sks re-issued via trn # 171 |  | 2026-03-19 | review made void - new revision submitted | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-18 | Omnii-TRANSMIT-000005 | NA | Trade Partner | Updated Fire Engineering Report | 0 | 1 | 0 | NA | REJECTED | [5 empty] | submitted document contains previous revision hence QA error |  | 2026-03-18 | KPTG-IntCorr-001083 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-19 | Auspan-TRANSMIT-000150 | NA | Trade Partner | Precast shop drawings for construction. Ground floor | 41 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - No review required - Register and distribute KPTG-TRANSMIT-000979 |  | 2026-03-19 | KPTG-TRANSMIT-000979 | Closed | 41 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-19 | Auspan-TRANSMIT-000151 | NA | Trade Partner | Update precast dowel layout zone 1, 2 ground floor | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC No review required - Register and distribute KPTG-TRANSMIT-000982 |  | 2026-03-19 | KPTG-TRANSMIT-000982 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-19 | Auspan-TRANSMIT-000152 | NA | Trade Partner | Resubmit precast shop drawings for approval. Ground floor | 15 | 0 | 0 | NA | APPROVED | 2026-03-19 | NA | 549 | 2026-03-26 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-001082 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-19 | RDSBIM-TRANSMIT-000035: | NA | Trade Partner | GREYSTAR BASEMENT FLOOR CONCRETE PROFILE KEY PLAN | 3 | 0 | 0 | NA | APPROVED | 2026-03-19 | NA | 551 | 2026-03-25 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-000984 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-19 | D&E-TRANSMIT-000500 | NA | Trade Partner | NXM3S2 - SECURITY GRILLES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-03-19 | NA | 4000 | 2026-03-26 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-19 | WGAVIC-TRANSMIT-000089 | NA | Consultant | M2 - Stage 10 Level 1 Slab - Construction Issue | 7 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 486 | 2026-03-25 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-001500 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-19 | AXIS-NSW-TRANSMIT-000010 | NA | Trade Partner | Potable & Fire Services PE | 0 | 1 | 0 | NA | APPROVED | 2026-03-19 | WF-000368 | NA | 2026-03-27 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-002213 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-03 | VAE-Grp-TRANSMIT-000134 | NA | Trade Partner | IFC - MECHANICAL - LG & GL REVISED DRAWINGS | 8 | 0 | 0 | NA | APPROVED | 2026-03-03 | NA | 1050 | 2026-03-09 |  |  |  | 2026-03-19 | KPTG-TRANSMIT-003202 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-01 | Fredon T-TRANSMIT-000008 | NA | Trade Partner | Surface Mount Speakers - Pool Side | 0 | 1 | 0 |  | REJECTED | [5 empty] | Requested to Resubmit | [6 empty] | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-10 | A.S.H.-TRANSMIT-000075 |  | Trade Partner | Drawings no longer in use | 5 | 0 | 0 | KPTG-IntCorr-001109 | APPROVED | [9 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-03 | VAE-Grp-TRANSMIT-000134 | NA | Trade Partner | IFC - MECHANICAL - LG & GL REVISED DRAWINGS-SCHEDULES | 0 | 3 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-15 | Auspan-TRANSMIT-000135 | NA | Trade Partner | Precast shop drawings for construction. Stage 9. | 24 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. Updated register and ACC folders (Actual receipt date 15/03) |  | 2026-03-19 | NA | Closed | 24 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-16 | Auspan-TRANSMIT-000137 | NA | Trade Partner | Update IFCed shop drawings for construction. Beam cut out increased to 1240mm. | 11 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, Updated register and distributed |  | 2026-03-19 | NA | Closed | 11 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-17 | Auspan-TRANSMIT-000141 | NA | Trade Partner | Precast shop drawings for construction. Stage 9 ground floor. | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. Updated register and distributed (Actual receipt date 17/03) |  | 2026-03-19 | KPTG-TRANSMIT-001521 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-17 | Auspan-TRANSMIT-000144 | NA | Trade Partner | Precast shop drawings for construction. Ground floor. | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. Updated register and ACC folders |  | 2026-03-19 | NA | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-18 | Auspan-TRANSMIT-000147 | NA | Trade Partner | Precast shop drawings for construction. Stage 9 | 13 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. Updated register and ACC folders |  | 2026-03-19 | NA | Closed | 13 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-19 | PCForm-TRANSMIT-000177 | NA | Trade Partner | Chemset 502 Plus | 0 | 1 | 0 | KPTG-IntCorr-000563 | APPROVED |  | NA | NA |  |  | PC got approval from Consultant through mail. KPTG-SADV-001864 |  | 2026-03-19 | KPTG-SADV-001864 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-20 | Auspan-TRANSMIT-000001 | NA | Trade Partner | Re: Precast Shop Drawing Sequence | 1 | 0 | 0 | NA | REJECTED | [5 empty] | No Document number, title, revision etc available. |  | 2026-03-20 | KPTG-SADV-000045 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-19 | SKS Tech-TRANSMIT-000171 | NA | Trade Partner | LEVEL 5 LIGHTING UPDATE | 1 | 0 | 0 | NA | APPROVED | 2026-03-19 | NA | 1155 | 2026-03-23 |  | submitted with sks trn # 169 |  | 2026-03-24 | KPTG-TRANSMIT-003238 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-10 | SMEPS-TRANSMIT-000092 | SPARK-CRFI-KPG-000438 | Trade Partner | IFA: Luminaire Schedule Sheets | 0 | 2 | 0 | KPTG-IntCorr-001103 | APPROVED | [7 empty] | 2026-01-30 | KPTG-TRANSMIT-000375 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-19 | Hames-TRANSMIT-000145 | NA | Consultant | Floor Junction Note Update | 1 | 0 | 0 | NA | APPROVED | 2026-03-19 | NA | 1153 | 2026-03-23 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-003287 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-20 | KETE-TRANSMIT-000120 | NA | Trade Partner | Kete - Tower IFA - Added Details | 7 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 606 | 2026-03-25 |  |  | 2026-04-07 | 2026-04-07 | KPTG-SADV-003658 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-19 | WilsonPD-TRANSMIT-000103 | NA | Trade Partner | Fire Sound | 0 | 1 | 0 | NA | APPROVED | 2026-03-20 | WF-000968 | NA | 2026-03-24 |  | File supersede and WF terminated. |  |  |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-20 | RDSBIM-TRANSMIT-000168 | NA | Trade Partner | LINDRUM ¦ GROUND LEVEL - BLOCK WALL ELEVATION PLAN AND ELEVATION | 2 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | #607 | 2026-03-27 |  | KPTG-IntCorr-000922-As per the latest communication from the Mr. Charlie Dowling, Latest revisions need to be submitted. | 2026-04-28 | 2026-04-28 | KPTG-IntCorr-000922 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-20 | D&E-TRANSMIT-000501 | NA | Trade Partner | SFN Sanitary Ball & Butterfly Valves - Issued for Approval | 0 | 2 | 0 | NA | APPROVED | 2026-03-20 | WF-004921 | NA | 2026-04-10 |  |  | 2026-04-10 | 2026-04-10 | D&E-TRANSMIT-000501 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-20 | Auspan-TRANSMIT-000002 | NA | Trade Partner | Precast shop drawings for approval. Colulmns. | 19 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected as there is not Document number, title, status. |  | 2026-03-20 | KPTG-SADV-000047 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-20 | SKS Tech-TRANSMIT-000062 | NA | Trade Partner | SKS - Fire Rating Material M3-ELC-SKS-SA-C-0400-0030 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Wrong attachment |  | 2026-03-20 | KPTG-TRANSMIT-014712 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-18 | NXT-TRANSMIT-001422 | NA | Consultant | NDC M3 - Stage 4 - Battery Rooms | 0 | 29 | 0 | NA | APPROVED | 2026-03-19 | 004862 | NA | 2026-03-26 |  | 23 DOC COMPELETED REVIEW REMAINS UNDER REVIEW |  | 2026-03-19 | KPTG-TRANSMIT-014721 | Open | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-10 | NXT-TRANSMIT-001128NXT-TRANSMIT-001128 | NA | Trade Partner | Primary drawings for M3-22-HVSB-A - For Construction | 1 | 0 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform.-KPTG-TRANSMIT-010815 |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-19 | RDSBIM-TRANSMIT-000248 | NA | Trade Partner | NXM3S4 GROUND FLOOR & LEVEL 01 SPEED PANEL LAYOUT AND ELEVATION | 2 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 2576 | 2026-03-23 |  |  | 2026-03-25 | 2026-03-26 | KPTG-TRANSMIT-015012 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-19 | ARCST-TRANSMIT-000234 | NA | Trade Partner | C1 Roof Stairs - Issued for Approval | 43 | 0 | 0 | NA | REJECTED | [5 empty] | status shown as rejected for the document |  | 2026-03-19 | KPTG-TRANSMIT-014618 | Closed | 43 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-19 | Syfon1-TRANSMIT-000009 | NA | Trade Partner | Syfon's Ground Level Zone C1 drawing, | 1 | 0 | 0 | NA | APPROVED | 2026-03-19 | NA | 2577 | 2026-03-26 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-014952 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-20 | PARR-TRANSMIT-000140 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - DFS COM PLAN & CX SCRIPTS | 0 | 18 | 0 | NA | APPROVED | 2026-03-20 | WF-004922 | NA | 2026-04-10 |  | 18 Docs , 17- excel documents are updated to register | 2026-03-23 | 2026-03-23 | PARR-TRANSMIT-000140 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-20 | D&E-TRANSMIT-000504 | NA | Trade Partner | Refrigerant Charge Calculations - Issued for Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect revision |  | 2026-03-20 | KPTG-TRANSMIT-014713 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-20 | HDRAus-TRANSMIT-000437 | NA | Consultant | Demo - Nib walls corridor | 3 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 2596 | 2026-03-24 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015094 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-19 | ARCST-TRANSMIT-000235 | NA | Trade Partner | C1 Roof Stairs - Issued for Approval | 42 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: difference in title |  | 2026-03-19 | KPTG-TRANSMIT-014674 | Closed | 42 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-05 | NXT-TRANSMIT-001369 | NA | Consultant | Re: M3 Stage 1-4 Updated Acoustic Report - For Review | 0 | 1 | 0 | NA | APPROVED | 2026-03-05 | NA | 2530 | 2026-03-19 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-014699 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-04 | SMEPS-TRANSMIT-000121 | SPARK-CRFI-KPG-000576 | Trade Partner | Seismic Restraint | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-20 | KPTG-TRANSMIT-000564 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-20 | D&E-TRANSMIT-000177 | SPARK-CRFI-KPG-000473 | Trade Partner | MWYCCB - GROUND LEVEL - PLINTH LAYOUT ZONE 1 & ZONE 3 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 180 | 2026-03-24 |  |  | 2026-04-17 | 2026-04-24 | KPTG-TRANSMIT-000697 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-10 | Syfon1-TRANSMIT-000002 |  | Trade Partner | Syfon Drawings1 | 4 | 0 | 0 | KPTG-TRANSMIT-000302 | REJECTED | [9 empty] | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-19 | Civilex-TRANSMIT-000058 | NA | Trade Partner | UPT Shop Drawing Approval | 1 | 0 | 0 | NA | APPROVED | 2026-03-19 | NA | 354 | 2026-03-26 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-001053 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-19 | Civilex-TRANSMIT-000057 | NA | Trade Partner | GRP Panel Tank | 2 | 0 | 0 | NA | APPROVED | 2026-03-19 | NA | 352 | 2026-03-26 |  |  | 2026-05-12 | 2026-05-12 | KPTG-TRANSMIT-001698 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-19 | WAM-TRANSMIT-000736 | NA | Consultant | 4B3a - WALL SET-OUT LEVEL 13-21 | 1 | 0 | 0 | NA | APPROVED | 2026-03-19 | NA | 356 | 2026-03-23 |  |  | 2026-03-27 | 2026-03-27 | ACC 374 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-19 | PCForm-TRANSMIT-000108 | NA | Trade Partner | Ground floor to Level 1 Precast Propping Design | 0 | 1 | 0 | NA | REJECTED | [5 empty] | REJECTED : QA ERROR DWG NO |  | 2026-03-19 | KPTG-TRANSMIT-000843 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-19 | SKS Tech-TRANSMIT-000169 | NA | Trade Partner | LEVEL 4 Lighting IFC update | 1 | 0 | 0 | NA | APPROVED | 2026-03-19 | NA | 1155 | 2026-03-23 |  | submitted with sks trn # 171 |  | 2026-03-24 | KPTG-TRANSMIT-003238 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-20 | Nilsen3-TRANSMIT-000071 | NA | Trade Partner | Re: NXM3S3 ¦ Nilsen ELC Shop Drawings - FOA Drawings | 16 | 0 | 0 | NA | APPROVED | 2026-03-23 | WF-004937 | NA | 2026-04-04 |  |  | 2026-04-20 | 2026-04-21 | KPTG-TRANSMIT-016235 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-19 | SKS Tech-TRANSMIT-000172 | NA | Trade Partner | White Rhino Load Bank Connection Panel | 0 | 1 | 0 | KPTG-IntCorr-001086 | APPROVED | 2026-03-23 | WF-000948 | NA | 2026-03-30 |  | harry to confirm | 2026-04-02 | 2026-04-02 | KPTG-WTRAN-001890 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-19 | VAE-Grp-TRANSMIT-000140 | NA | Trade Partner | MECH - L4&5 DWGS + CERTIFICATE - Water Mist Pump Room & Certifier Updates | 2 | 2 | 0 | NA | APPROVED | 2026-03-19 | NA | 1153 | 2026-03-23 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-003214 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-17 | Entire M-TRANSMIT-000019 | NA | Trade Partner | Mechanical Fire Matrix - COLO4 | 0 | 1 | 0 | NA | APPROVED | 2026-03-18 | WF-000265 | NA | 2026-03-23 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-000554 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-20 | SMEPS-TRANSMIT-000154 | NA | Trade Partner | SME Shop Drawing Telecomunications IFC A | 4 | 0 | 0 | NA | APPROVED | 2026-03-20 | WF-000284 | NA | 2026-03-24 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-000551 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-10 | NXT-TRANSMIT-001129 | NA | Trade Partner | Primary drawings for M3-22-HVSB-R for contruction | 1 | 0 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform.KPTG-TRANSMIT-010816 |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-20 | ccair-TRANSMIT-000111 | NA | Trade Partner | MSSB Schematics for approval | 0 | 6 | 0 | NA | APPROVED | 2026-03-20 | WF-000969 | NA | 2026-03-24 |  | File supersede and WF terminated. |  |  |  | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-20 | RDSBIM-TRANSMIT-000073 | NA | Trade Partner | GROUND FLOOR-B-G-035 CLEANERS FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 1157 | 2026-03-24 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-003687 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-20 | RDSBIM-TRANSMIT-000074 | NA | Trade Partner | GROUND FLOOR-B-G-038 FEMALE TOILET FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 1159 | 2026-03-24 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-003683 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-20 | RDSBIM-TRANSMIT-000075 | NA | Trade Partner | GROUND FLOOR-B-G-036 ACC TOILET-FLOOR FINISHES LAYOUT & ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 1161 | 2026-03-24 |  |  | 2026-05-12 | 2026-05-18 | KPTG-TRANSMIT-003724 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-20 | HDRAus-TRANSMIT-000440 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 8 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 2600 | 2026-03-24 |  |  | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-014905 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-20 | WGAVIC-TRANSMIT-000090 | NA | Consultant | M2 - Stages 9, 10 and 11 Wall Updates - Construction Issue | 11 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 489 | 2026-03-25 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-001827 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-20 | KPTG-IntCorr-000571 | NA | Consultant | Updated Acoustic report for Stage 9-11 | 0 | 1 | 0 | NA | APPROVED | 2026-03-20 | NA | 484 | 2026-03-25 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-001772 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-20 | AXIS-NSW-TRANSMIT-000011 | NA | Trade Partner | PVC Pipe & Fittings | 0 | 1 | 0 | NA | APPROVED | 2026-03-20 | WF-000373 | NA | 2026-03-27 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-003687 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-20 | ASV-TRANSMIT-000031 | NA | Trade Partner | Stage 11 Internal Hydraulic Services | 1 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-03-20 | KPTG-SADV-001963 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-20 | ASV-TRANSMIT-000032 | NA | Trade Partner | Stage 11 Internal Hydraulic Services | 1 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 491 | 2026-03-26 |  |  | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-001866 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-10 | NXT-TRANSMIT-001130 | NA | Trade Partner | Primary drawings for M3-22-HVSB-V for construction | 1 | 0 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform.KPTG-TRANSMIT-010818 |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-04 | PCForm-TRANSMIT-000137 | NA | Trade Partner | Jumpform Concrete Envelopes & Wall Elevations - Updated Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-03-05 | WF-000297 | NA | 2026-03-13 |  |  | 2026-03-19 | 2026-03-20 | KPTG-TRANSMIT-001544 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-19 | RDSBIM-TRANSMIT-000249 | NA | Trade Partner | XM3S4 LEVEL 01 CONCRETE PROFILE PLAN NORTH OFFICE | 1 | 0 | 0 | NA | APPROVED | 2026-03-19 | NA | 2585 | 2026-03-23 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015114 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-19 | SMEPS-TRANSMIT-000218 | NA | Trade Partner | SME - Western Side External Structure Drawings | 11 | 0 | 0 | NA | APPROVED | 2026-03-19 | WF-004913 | NA | 2026-03-30 |  | The WF has been terminated by Lola |  | 2026-04-01 | NA | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-20 | KETE-TRANSMIT-000010 | NA | Trade Partner | : Kete - VMU IFC Drawings | 18 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 553 | 2026-03-25 |  | As advised by Kapitol PC - "Review to be voided as no review required." |  | 2026-04-15 | NA | Closed | 18 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-20 | JCBa-TRANSMIT-000073 | NA | Trade Partner | STRUCTURAL SETOUT PLANS GROUND FLOOR: ZONES 2 & 5 | 2 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 555 | 2026-03-25 |  | Terminated as advised by Kapitol DM "to update the drawings". ACC#555 ¦WF-000299 | 2026-03-24 | 2026-03-24 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-20 | RDSBIM-TRANSMIT-000036 | NA | Trade Partner | GREYSTAR GROUND FLOOR MAIN ENTRY RAMP PLAN AND SECTION | 3 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 557 | 2026-03-25 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-001132 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-20 | RDSBIM-TRANSMIT-000037 | NA | Trade Partner | GREYSTAR GROUND FLOOR EAST LANEWAY LANDSCAPE LAYOUT AND SECTIONS | 1 | 0 | 0 | KPTG-IntCorr-000400 | APPROVED | 2026-03-23 | NA | 568 | 2026-03-25 |  | Waiting for advice on document discipline. | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-001619 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-20 | Auspan-TRANSMIT-000154 | NA | Trade Partner | Precast shop drawings for approval. Ground floor | 7 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 559 | 2026-03-25 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-001155 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-20 | Auspan-TRANSMIT-000155 | NA | Trade Partner | : Precast shop drawings for approval. Level 1. | 9 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 561 | 2026-03-25 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-001152 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-20 | Auspan-TRANSMIT-000156 | NA | Trade Partner | Precast shop drawings for approval. Level 2. | 24 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 563 | 2026-03-25 |  |  | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-001172 | Closed | 24 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-10 | StantecA-TRANSMIT-000282 | NA | Consultant | Updated Issued for Tender / Sub-Contractor Engagement - Hydraulics and Fire | 92 | 0 | 0 | NA | APPROVED | 2025-12-10 | WF-000088 | 172 | 2025-12-15 |  | Review Void |  | 2025-12-11 | NA | Closed | 92 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-20 | Auspan-TRANSMIT-000157: | NA | Trade Partner | Precast shop drawings for construction. | 40 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | NA |  |  | IFC No review required - Register and distribute - KPTG-TRANSMIT-000998 |  | 2026-03-20 | KPTG-TRANSMIT-000998 | Closed | 40 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-20 | LVPG-TRANSMIT-000023 | NA | Trade Partner | LVPG-HY-TECH-042 - Multiflex Universal Coupling | 0 | 1 | 0 | NA | APPROVED | 2026-03-20 | WF-000296 | NA | 2026-03-25 |  |  | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-001177 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-20 | LVPG-TRANSMIT-000024 | NA | Trade Partner | LVPG-HY-TECH-043 - StormFLO stormwater and drainage pipe | 0 | 1 | 0 | NA | APPROVED | 2026-03-20 | WF-000297 | NA | 2026-03-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-20 | DS-TRANSMIT-000104 | NA | Trade Partner | Roof - Water and Roof Plant - Drainage and Water | 9 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 2589 | 2026-03-30 |  |  | 2026-04-02 | 2026-04-02 | kPTG-TRANSMIT-015451 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-20 | D&E-TRANSMIT-000502 | NA | Trade Partner | MCC Drawings - Issued for Approval | 3 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 2594 | 2026-03-30 |  |  | 2026-04-01 | 2026-04-01 | D&E-TRANSMIT-000502 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-20 | SMEPS-TRANSMIT-000220 | NA | Trade Partner | SME - DRAWINGS IFA PART SUBMISSIONS | 3 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 2598 | 2026-03-30 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-016584 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-20 | D&E-TRANSMIT-000505 | NA | Trade Partner | Fire matrix - IFA-1 | 0 | 1 | 0 | NA | APPROVED | 2026-03-20 | WF-004933 | NO | 2026-03-20 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016123 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-20 | D&E-TRANSMIT-000506 | NA | Trade Partner | M3S4 - MDB-GLP Typical Shop Drawings | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | ONLY FOR INFORM OTHERS |  | 2026-03-20 | KPTG-TRANSMIT-014767 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-20 | RDSBIM-TRANSMIT-000001 | NA | Trade Partner | MEL11C45 ¦ PARTITION WALL LAYOUT L01 AND L02 COLO4 COLO5A, COLO5B | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Document number of Document is incorrect, requested to resubmit: KPTG-IntCorr-000167 |  | 2026-03-20 | KPTG-IntCorr-000167 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-20 | Appselec-TRANSMIT-000032 | NA | Trade Partner | LV Earth Cable Changed To Nexans & submitted with tech data 028. | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | this Technical Data is no longer in USE |  | 2026-03-20 | KPTG-TRANSMIT-000164 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-10 | StantecA-TRANSMIT-000282 | NA | Consultant | Updated Issued for Tender / Sub-Contractor Engagement - Hydraulics and Fire | 45 | 1 | 0 | NA | APPROVED | 2025-12-10 | WF-000089 | 177 | 2025-12-15 |  | Review Void. |  | 2025-12-12 | NA | Closed | 46 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-20 | Appselec-TRANSMIT-000033 | NA | Trade Partner | No Longer In Use | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | No longer in Use, Transmitted to trade & consultants: KPTG-TRANSMIT-000166 |  | 2026-03-20 | KPTG-TRANSMIT-000166 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-13 | Appselec-TRANSMIT-000026 | NA | Trade Partner | COLO 4 & 5 - Lighting and Power Layout - Issued for Approval | 20 | 0 | 0 | NA | APPROVED | 2026-03-14 | WF-000054 | NA | 2026-03-18 |  | Attachement of review outcome is incorrect, requested to review again: KPTG-IntCorr-000168 | 2026-03-19 | 2026-03-20 | KPTG-IntCorr-000168 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-20 | Appselec-TRANSMIT-000026 | NA | Trade Partner | COLO 4 & 5 - Lighting and Power Layout - Issued for Approval | 20 | 0 | 0 | NA | APPROVED | 2026-03-20 | WF-000081 | NA | 2026-03-25 |  | WORKFLOW IS RESUBMITTED | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-000193 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-19 | Appselec-TRANSMIT-000030 | NA | Trade Partner | LV Cable Technical Data For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-19 | WF-000073 | NA | 2026-03-25 |  |  | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-000182 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-18 | SIL-TRANSMIT-000014 | NA | Trade Partner | Re-Submission of the Schematics Drawings | 0 | 5 | 0 | NA | APPROVED | 2026-03-19 | WF-000076 | NA | 2026-03-24 |  |  | 2026-03-27 | 2026-03-30 | KPTG-TRANSMIT-000240 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-18 | SIL-TRANSMIT-000015 | NA | Trade Partner | Re-Submitting the ATS Documents | 0 | 13 | 0 | NA | APPROVED | [5 empty] | REVISION OF DOCUMENTS IS INCORRECT, REQUESTED TO RESUBMIT: KPTG-IntCorr-000160 |  | 2026-03-19 | KPTG-IntCorr-000160 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-18 | SEAPBU-TRANSMIT-000005 | NA | Trade Partner | ASCO ATS , L2 , L3 Scripts PDF Version | 0 | 2 | 0 | NA | APPROVED | 2026-03-19 | WF-000077 | NA | 2026-03-24 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-000275 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-19 | SIL-TRANSMIT-000016 | NA | Trade Partner | Re-Transmitting the documents | 18 | 0 | 0 | NA | REJECTED | [5 empty] | COVERING SHEET IS ATTACHED WITH ALL SHOP DRAWING , REQUESTED TO REMOVE |  | 2026-03-20 | KPTG-IntCorr-000161 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-19 | SIL-TRANSMIT-000017 | NA | Trade Partner | Documents Submitted FOR CONSTRUCTION | 1 | 3 | 0 | NA | REJECTED | [5 empty] | COVERING PAGE IS ATTACHEED WIRH A SHOP DRAWING, REQUESTED TO RESUBMIT:KPTG-IntCorr-000162 |  | 2026-03-20 | KPTG-IntCorr-000162 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-19 | SIL-TRANSMIT-000018 | NA | Trade Partner | Submitting the L2 Scripts | 0 | 5 | 0 | NA | REJECTED | [5 empty] | Requested to submit pdf format of all these documents:KPTG-IntCorr-000163 |  | 2026-03-20 | KPTG-IntCorr-000163 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-10 | Auspan-TRANSMIT-000026 | NA | Trade Partner | Precast shop drawings for construction. | 30 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required; Update Aconex register and ACC; Circulate to all consultants and TPs. |  | 2025-12-10 | KPTG-TRANSMIT-000296 | Closed | 30 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-13 | EFP-TRANSMIT-000011 | NA | Trade Partner | WET FIRE DRAWINGS ISSUED IFA | 8 | 0 | 0 | NA | APPROVED | 2026-03-16 | WF-000053 | NA | 2026-03-19 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-000175 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-20 | Arc Plas-TRANSMIT-000002 | NA | Trade Partner | Updated Document Number - Tech Data Submission | 0 | 5 | 0 | NA | APPROVED | 2026-03-19 | WF-000075 | NA | 2026-03-24 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-000291 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-19 | RDSBIM-TRANSMIT-000121 | NA | Trade Partner | MLCSPR ¦ CHAPEL CARPARK LANDSCAPE KEY PLAN AND SECTION | 4 | 0 | 0 | NA | APPROVED | 2026-03-19 | NA | 466 | 2026-03-26 |  |  | 2026-03-25 | 2026-03-25 | KPTG-SADV-003969 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-19 | Highbu-TRANSMIT-000141 | NA | Trade Partner | Minor drawing update | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Drawing, transmitted to trade & consultants |  | 2026-03-19 | KPTG-TRANSMIT-002590 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-18 | TGRF-TRANSMIT-000102 | na | Trade Partner | Stage 2 - PT General arrangement drawings for review | 9 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 471 | 2026-04-01 |  | Kapitol Advice Awaits:KPTG-IntCorr-006179 | 2026-04-10 | 2026-04-10 | KPTG-SADV-004040 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-20 | NXT-TRANSMIT-000389 | NA | Client | HRW - ZONE 7 STEEL LOWERING & TEMP LOADBANK INSTALL | 0 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Action Not required-Correspondance. |  | 2026-03-20 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-23 | IDS-TRANSMIT-000017 | NA | Trade Partner | Dry Fire - HFF GROUND ZONE 1 & 2 | 1 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | 362 | 2026-03-25 |  |  | 2026-03-24 | 2026-03-24 | KAPITOL-TRANSMIT-001235 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-20 | Jordan-TRANSMIT-000123 | NA | Trade Partner | Sample 68 & 70 Resubmission | 0 | 2 | 0 | NA | APPROVED | 2026-03-23 | WF-000947 | NA | 2026-03-30 |  |  | 2026-03-24 | 2026-03-24 | KPTG-WTRAN-001850 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-23 | PARR-TRANSMIT-000125 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - PUMP ROOM, CONTROL SYSTEM DRAWINGS-FUEL | 3 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 2603 | 2026-03-31 |  | The WF has been generated as requested by Oliver-Peter-Jay J | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-014887 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-23 | PARR-TRANSMIT-000125 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - PUMP ROOM, CONTROL SYSTEM DRAWINGS-FUEL | 6 | 0 | 0 | NA | APPROVED | 2026-02-26 | NA | 2604 | 2026-03-31 |  | The WF has been generated as requested by Oliver-Peter-Jay J | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-014887 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-10 | JCBa-TRANSMIT-000043 | NA | Consultant | GA OVERALL PLANS: Update to stair doors | 8 | 0 | 0 | KPTG-IntCorr-000183 | APPROVED |  | NA | NA |  |  | Waiting for Kapitol advise - KPTG-IntCorr-000183. No review required; update register and transmit to all consultant and trade partners. |  | 2025-12-11 | KPTG-TRANSMIT-000304 | Closed | 8 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-20 | PCForm-TRANSMIT-000109 | NA | Trade Partner | PCF Precast Grouting Procedure | 0 | 2 | 0 | KPTG-IntCorr-000511 | APPROVED |  | NA | NA |  |  | Nich / Victoria to confirm - 1 Rejected for Resubmitted via pc form Trn # 120 |  | 2026-03-26 | KPTG-TRANSMIT-000931 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-20 | PCForm-TRANSMIT-000110 | NA | Trade Partner | Precast Propping Design & Plan | 2 | 0 | 0 | NA | REJECTED | [5 empty] | QA ERROR - DRAWING NO. AND REV. INSIDE DOC - MISMATCH |  | 2026-03-20 | KPTG-TRANSMIT-000870 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-23 | D&E-TRANSMIT-000178 | SPARK-CRFI-KPG-000569 | Trade Partner | MWYCCB - GROUND LEVEL - RCP LAYOUT ZONES - Issued For Construction | 3 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | 181 | 2026-03-30 |  |  | 2026-04-17 | 2026-05-04 | KPTG-TRANSMIT-000799 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-20 | SMEPS-TRANSMIT-000219 | NA | Trade Partner | M3S4 - MDB-GLP Typical Shop Drawings | 0 | 1 | 0 | NA | APPROVED | 2026-03-20 | NA | 2602 | 2026-03-26 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-20 | Tradetec-TRANSMIT-000397 | NA | Trade Partner | Re: Stage 4 - Pit Shop Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 2592 | 2026-03-30 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-015441 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-23 | DS-TRANSMIT-000105 | NA | Trade Partner | Roof and Plant Roof Webforge Penetrations (HYD) | 6 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | 2606 | 2026-03-31 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-015716 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-20 | KEECEPRO-TRANSMIT-000037 | NA | Trade Partner | Reticulation Layout Shop Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 359 | 2026-03-30 |  |  | 2026-04-22 | 2026-04-22 | DRAFT-009786 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-23 | Auspan-TRANSMIT-000003 | NA | Trade Partner | Marking plans, elevations and dowel layout | 1 | 0 | 0 | NA | APPROVED | 2026-03-23 | WF-000014 | NA | 2026-04-01 |  | Terminated as requested by Chri Doh, resubmission received. |  | 2026-03-26 | KPTG-IntCorr-000138 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-01 | Lub-doka-TRANSMIT-000016 | NA | Trade Partner | Revised Precast Layout - Wallforms | 3 | 0 | 0 |  | APPROVED |  | NA | NA |  |  | As per the Direction, No action has taken:KPTG-IntCorr-000577, Only updated to document register |  | 2025-12-01 | KPTG-IntCorr-000577 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-10 | RBG-TRANSMIT-000043 | NA | Consultant | Revised Structural Drawings for the Hydrostatic Slab Details - Revised IFC to include wall / column starters | 7 | 0 | 0 | KPTG-IntCorr-000260 | APPROVED | 2025-12-11 | WF-000091 | 169 | 2025-12-16 |  | Waiting for Kapitol advise; KPTG-IntCorr-000260 |  | 2026-01-27 | KPTG-TRANSMIT-000335 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-20 | KEECEPRO-TRANSMIT-000036 | NA | Trade Partner | Re Lighting and Power Shop Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 360 | 2026-03-30 |  | Reference TRN KEECEPRO-TRANSMIT-000033 | 2026-03-24 | 2026-03-24 | DRAFT-009465 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-23 | Auspan-TRANSMIT-000004 | NA | Trade Partner | Auspan-TRANSMIT-000004-Precast shop drawings for approval | 41 | 0 | 0 | NA | APPROVED | 2026-03-26 | WF-000018 | NA | 2026-04-06 |  | Terminating and resubmitted as originator is missed out to be added in copy. 1 Document attachment in close out is wrong. |  | 2026-04-10 | KPTG-TRANSMIT-000138, KPTG-TRANSMIT-000140 | Closed | 41 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-06 | Schindle-TRANSMIT-000020 | NA | Trade Partner | Lift C3 - Shop drawings rev FC4 | 6 | 0 | 0 | NA | APPROVED | 2026-03-17 | WF-004773 | NA | 2026-03-23 |  | NXT-WTRAN-001976 - 2 Docs | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-014785 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-20 | HIP-TRANSMIT-000018 | NA | Trade Partner | Powerpack - Louvres Steel - Reissued for Approval | 12 | 0 | 0 | NA | REJECTED | [5 empty] | REVISION MISTAKES ON DRAWINGS |  | 2026-03-20 | KAPITOL-TRANSMIT-001228 | Closed | 12 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-19 | PROLMC-TRANSMIT-000029 | NA | Trade Partner | Proline updated shop drawings 19-3-26 | 9 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 4002 | 2026-03-31 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-019227 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-20 | NXT-TRANSMIT-001442 | NA | Client | 100222-000581 - ROOM EE MDR Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-20 | WF-004926 | NA | 2026-03-24 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-20 | Stowe-A-TRANSMIT-000525 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - COMMS DEVICE LAYOUTS - 20.03.2026 | 8 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 4004 | 2026-03-27 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-015041 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-20 | Stowe-A-TRANSMIT-000526 | NA | Trade Partner | Stowe - Tech Data Submission - 12RU RACK | 0 | 1 | 0 | NA | APPROVED | 2026-03-20 | WF-004928 | NA | 2026-04-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-20 | ASV-TRANSMIT-000157 | NA | Trade Partner | Site Wide - Drinking Fountain - Submittal | 0 | 1 | 0 | NA | APPROVED | 2026-03-20 | WF-004931 | NA | 2026-04-07 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-23 | Leemark-TRANSMIT-000022 | SPARK-CRFI-KPG-000613 | Trade Partner | Transmittal of Fire Shop Drawings - For Approval | 6 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | 184 | 2026-03-30 |  |  |  | 2026-04-16 | KPTG-TRANSMIT-000652 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-05 | TTW-TRANSMIT-000047 | NA | Consultant | Facade Tender Documentation | 1 | 0 | 0 | NA | APPROVED | 2025-12-08 | NA | 139 | 2025-12-10 |  |  | 2025-12-09 | 2025-12-10 | KPTG-TRANSMIT-000215 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-23 | D&E-TRANSMIT-000179 | SPARK-CRFI-KPG-000301 | Trade Partner | FAN STATIC PRESSURE CALCULATIONS | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-08 | KPTG-TRANSMIT-000623 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-23 | D&E-TRANSMIT-000180 | SPARK-CRFI-KPG-000491 | Trade Partner | MWYCCB - LEVEL 1 - PIPEWORK LAYOUT ZONE 8 & ZONE 9 MECHANICAL SERVICES - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | 185 | 2026-03-30 |  |  |  | 2026-04-08 | KPTG-TRANSMIT-000619 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-20 | PenskePS-TRANSMIT-000001 | NA | Trade Partner | MEL05-COLO4-L1 Scripts | 0 | 1 | 0 | NA | APPROVED | 2026-03-20 | WF - 000281 | NA | 2026-03-27 |  | NA | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-000567 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-20 | PenskePS-TRANSMIT-000002 | NA | Trade Partner | MEL05-COLO4-L2 Scripts | 0 | 1 | 0 | NA | APPROVED | 2026-03-20 | WF - 000282 | NA | 2026-03-27 |  | NA | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-000571 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-12 | MICRSFT-RFP-000002 | NA | Trade Partner | RFP 20 DRB10 | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-17 | SMEPS-TRANSMIT-000141 | NA | Trade Partner | SME Shop Drawing Telecomunications IFC | 8 | 0 | 0 | NA | APPROVED | 2026-03-17 | WF-000257 | NA | 2026-03-23 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-000504 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-19 | SMEPS-TRANSMIT-000142 | NA | Trade Partner | SME Shop Drawing Telecomunications IFA 2 | 1 | 0 | 0 | NA | APPROVED | 2026-03-17 | WF-000258 | NA | 2026-03-24 |  | NA | 2026-03-25 | 2026-03-26 | KPTG-TRANSMIT-000594 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-17 | SMEPS-TRANSMIT-000143 | NA | Trade Partner | SME Shop Drawing Telecomunications IFA 2 | 1 | 0 | 0 | NA | APPROVED | 2026-03-17 | WF-000259 | NA | 2026-03-23 |  |  | 2026-03-25 | 2026-03-26 | KPTG-TRANSMIT-000597 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-17 | SMEPS-TRANSMIT-000144 | NA | Trade Partner | SME Shop Drawing Telecomunications IFA 2 | 3 | 0 | 0 | NA | APPROVED | 2026-03-17 | WF-000260 | NA | 2026-03-21 |  | NA | 2026-03-25 | 2026-03-26 | KPTG-TRANSMIT-000606 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-17 | SMEPS-TRANSMIT-000145 | NA | Trade Partner | SME Shop Drawing Electrical IFC A | 4 | 0 | 0 | NA | APPROVED | 2026-03-17 | WF-000261 | NA | 2026-03-23 |  |  | 2026-03-18 | 2026-03-18 | KPTG-TRANSMIT-000507 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-10 | MALA-TRANSMIT-000028 | NA | Consultant | LANDSCAPE DRAWING IFC (C1) - TITLE REVISED | 38 | 0 | 0 | NA | APPROVED | 2025-12-10 | WF-000812 | 509 | 2025-12-16 |  |  | 2025-12-16 | 2025-12-16 | KPTG-DA-002274 | Closed | 38 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-17 | ETNInd-TRANSMIT-000013 | NA | Trade Partner | MEL05 COLO4 DC and Control Cable Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-03-18 | WF-000263 | NA | 2026-03-23 |  | NA | 2026-03-26 | 2026-03-27 | KPTG-TRANSMIT-000612 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-23 | D&E-TRANSMIT-000181 | NA | Trade Partner | MWYCCB - LEVEL 1 - PLINTH LAYOUT ZONE 8 & ZONE 9 MECHANICAL SERVICES - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | 186 | 2026-03-30 |  |  |  | 2026-03-24 | KPTG-TRANSMIT-000575 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-17 | Entire M-TRANSMIT-000018 | NA | Trade Partner | Issued for Construction | 6 | 0 | 0 | NA | APPROVED | 2026-03-18 | WF-000264 | NA | 2026-03-24 |  | NA | 2026-03-19 | 2026-03-20 | KPTG-TRANSMIT-000536 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-20 | Entire M-TRANSMIT-000019 | NA | Trade Partner | Mechanical Fire Matrix - COLO4 | 0 | 1 | 0 | NA | APPROVED | 2026-03-18 | WF-000265 | NA | 2026-03-23 |  | NA | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-000554 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-23 | HIP-TRANSMIT-000019 | NA | Trade Partner | Powerpack - Louvre Support Steel & Internal Steel - Reissued for Approval | 12 | 0 | 0 | NA | APPROVED | 2026-03-23 | WF-000447 | NA | 2026-04-01 |  |  | 2026-03-27 | 2026-03-27 | KAPITOL-TRANSMIT-001251 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-17 | KALLIBRE-TRANSMIT-000002 | NA | Trade Partner | MEL05 Door Frames Shop Drawings IFC | 1 | 0 | 0 | NA | APPROVED | 2026-03-18 | WF-000266 | NA | 2026-03-24 |  |  | 2026-03-19 | 2026-03-19 | KPTG-TRANSMIT-000517 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-20 | SMEPS-TRANSMIT-000155 | NA | Trade Partner | SME Shop Drawing Telecomunications IFA 2 | 1 | 0 | 0 | NA | APPROVED | 2026-03-20 | WF - 000285 | NA | 2026-03-27 |  | NA | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-000677 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-17 | ETNInd-TRANSMIT-000015 | NA | Trade Partner | MEL05 ONSITE DELIVERY CHECKLIST -UPS | 0 | 1 | 0 | NA | APPROVED |  | WF - 000277 | NA | 2026-03-27 |  | NA | 2026-03-19 | 2026-03-20 | KPTG-TRANSMIT-000563 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-19 | ETNInd-TRANSMIT-000016 | NA | Trade Partner | MEL05-COLO4 Asset Register UPS | 0 | 1 | 0 | NA | APPROVED | 2026-03-19 | WF - 000275 | NA | 2026-03-25 |  | NA | 2026-03-19 | 2026-03-20 | KPTG-TRANSMIT-000557 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-17 | ETNInd-TRANSMIT-000017 | NA | Trade Partner | MEL05 COLO4 - Project Master Document Register_GC 17.03.26 | 0 | 1 | 0 | NA | APPROVED | 2026-03-19 | WF - 000276 | NA | 2026-03-25 |  | NA | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-000560 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-10 | ccair-TRANSMIT-000076 | NA | Trade Partner | Ductwork Riser Elevation Core A - IFC | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-19 | SMEPS-TRANSMIT-000153 | NA | Trade Partner | SME Shop Drawing Electrical IFC A | 8 | 0 | 0 | NA | APPROVED | 2026-03-19 | WF - 000279 | NA | 2026-03-23 |  | NA | 2026-03-19 | 2026-03-20 | KPTG-TRANSMIT-000548 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-18 | Entire M-TRANSMIT-000020 | NA | Trade Partner | Drain Pipe Insulation IFA Rev A | 0 | 1 | 0 | NA | APPROVED | 2026-03-19 | WF - 000274 | NA | 2026-03-25 |  | NA | 2026-03-23 | 2026-03-23 | KPTG-TRANSMIT-000577 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-18 | SMEPS-TRANSMIT-000150 | NA | Trade Partner | SME Shop Drawing Telecomunications IFA 2 | 2 | 0 | 0 | NA | APPROVED | 2026-03-18 | WF-000267 | NA | 2026-03-24 |  |  | 2026-03-27 | 2026-04-27 | KPTG-TRANSMIT-000672 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-18 | SMEPS-TRANSMIT-000146 | NA | Trade Partner | SME Shop Drawing Telecomunications IFA 2 | 1 | 0 | 0 | NA | APPROVED | 2026-03-18 | WF-000273 | NA | 2026-03-24 |  | NA | 2026-03-26 | 2026-03-27 | KPTG-TRANSMIT-000625 | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-23 | KPTG-SADV-000687 | NA | Trade Partner | Re: BOM Rev 5 | 0 | 3 | 0 | NA | APPROVED | 2026-03-23 | WF - 000288 | NA |  |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-000637 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-18 | SMEPS-TRANSMIT-000147 | NA | Trade Partner | SME Shop Drawing Telecomunications IFA 2 | 1 | 0 | 0 | NA | APPROVED | 2026-03-18 | WF-000268 | NA | 2026-03-24 |  | NA | 2026-03-26 | 2026-03-27 | KPTG-TRANSMIT-000619 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-19 | SMEPS-TRANSMIT-000148 | NA | Trade Partner | SME Shop Drawing Telecommunications IFA 2 | 3 | 0 | 0 | NA | APPROVED | 2026-03-18 | WF-000269 | NA | 2026-03-24 |  | NA | 2026-03-26 | 2026-03-27 | KPTG-TRANSMIT-000606 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-18 | SMEPS-TRANSMIT-000149 | NA | Trade Partner | SME Shop Drawing Telecommunications IFA 2 | 1 | 0 | 0 | NA | APPROVED | 2026-03-18 | 000270 | NA | 2026-03-24 |  | NA | 2026-03-26 | 2026-03-27 | KPTG-TRANSMIT-000615 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-18 | SMEPS-TRANSMIT-000151 | NA | Trade Partner | SME Shop Drawing Electrical IFC B | 4 | 0 | 0 | NA | APPROVED | 2026-03-20 | WF-000286 | NA | 2026-03-26 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-000539 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-10 | ccair-TRANSMIT-000077 | NA | Trade Partner | Level 10 Mechanical Ductwork & Pipework Layout - IFA | 6 | 0 | 0 | NA | APPROVED | 2025-12-10 | WF-000813 | 511 | 2025-12-15 |  |  | 2026-02-02 | 2026-02-02 | KPTG-TRANSMIT-002663 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-18 | SMEPS-TRANSMIT-000152 | NA | Trade Partner | SME Shop Drawing Electrical IFC A | 4 | 0 | 0 | NA | APPROVED | 2026-03-18 | WF-000272 | NA | 2026-03-24 |  |  | 2026-03-20 | 2026-03-20 | KPTG-TRANSMIT-000542 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-23 | Bianco-TRANSMIT-000053 | NA | Trade Partner | Precast IFC Updates | 31 | 0 | 0 | NA | APPROVED | 2026-03-23 | WF-004952 | NA | 2026-03-30 |  | WORKFLOW TERMINATED AS PER REQUESTED BY OLIVER BECAUSE NEED TO CHANGE DOCUMENTS |  | 2026-03-24 | KPTG-TRANSMIT-014839 | Closed | 32 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-23 | SKS Tech-TRANSMIT-000063 | NA | Trade Partner | SKS - Fire Rating Material Submission | 0 | 1 | 0 | NA | APPROVED | 2026-03-23 | WF-004954 | NA | 2026-04-13 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-018662 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-20 | Stowe-A-TRANSMIT-000527 | NA | Trade Partner | Stowe - Tech Data Submission - Control Cabling | 0 | 1 | 0 | NA | APPROVED | 2026-03-20 | WF-004930 | NA | 2026-04-02 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-015569 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-20 | HDRAus-TRANSMIT-000438 | NA | Consultant | Sitewide Fence Updates | 6 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 4006 | 2026-03-24 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-015568 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-23 | HDRAus-TRANSMIT-000434 | NA | Consultant | M3S4 - Corridor Layouts - Nib walls | 4 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | 2609 | 2026-03-27 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015102 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-18 | Civilex-TRANSMIT-000214 | NA | Trade Partner | Sample Submission - Pavement Concrete mix design (Pronto - Hy Tec) - Updated naming Rev B | 0 | 2 | 0 | NA | APPROVED | 2026-03-23 | WF-004939 | NA | 2026-03-30 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-015424 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-23 | HDRAus-TRANSMIT-000439 | NA | Consultant | M3 SW - Document upload - PDF and CAD | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with the status inside and outside |  | 2026-03-23 | KPTG-DA-005627 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-23 | Civilex-TRANSMIT-000216 | NA | Trade Partner | Stage 2 - Landscape Planter box shop drawing - Updated PDF file content | 1 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | 4012 | 2026-03-27 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-015057 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-08 | RDSBIM-TRANSMIT-000007 | NA | Trade Partner | LEVEL 03 CONCRETE PROFILE PLAN AND SECTIONS | 5 | 0 | 0 | NA | APPROVED | 2025-12-08 | NA | 141 | 2025-12-11 |  |  | 2026-01-13 | 2026-01-14 | KPTG-TRANSMIT-000278 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-23 | ASV-TRANSMIT-000158 | NA | Trade Partner | Hydraulic Sample - Valves | 0 | 2 | 0 | NA | REJECTED | [5 empty] | The mentioned Revision number seems different in Aconex & inside drawing. |  | 2026-03-23 | KPTG-TRANSMIT-014819 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-23 | Stowe-A-TRANSMIT-000528 | NA | Trade Partner | Stowe - Tech Data Submission - B1-H (high output) | 0 | 1 | 0 | NA | APPROVED | 2026-03-23 | WF-004946 | NA | 2026-04-03 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-016368 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-23 | D&E-TRANSMIT-000507 | NA | Trade Partner | Stage 2 office Splits - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-23 | WF-004945 | NA | 2026-04-06 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-23 | NXT-TRANSMIT-001446 | NA | Client | 100222-000582: M3 Stage 2: Rooms EB - ER: Sprinkler System Layout - As Built Drawings | 16 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-23 | KPTG-TRANSMIT-014837 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-23 | Tradetec-TRANSMIT-000398 | NA | Trade Partner | Tech Data: Heidelberg Materials - 20mm Class 3 | 0 | 1 | 0 | NA | APPROVED | 2026-03-23 | WF-00494 | NA | 2026-03-30 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-23 | Tradetec-TRANSMIT-000400 | NA | Trade Partner | Tech Data - Baffle Spacers | 0 | 1 | 0 | NA | APPROVED | 2026-03-23 | WF-004948 | NA | 2026-03-27 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-015506 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-23 | D&E-TRANSMIT-000508 | NA | Trade Partner | D&E O&M Manual DRAFT - Issued for review | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Different status in the document register. |  | 2026-03-23 | KPTG-DA-005629 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-23 | KPTG-TRANSMIT-014778 | NA | Trade Partner | AXIS O&M Manual S2 Review | 0 | 1 | 0 | NA | APPROVED | 2026-03-23 | WF-005000 | NA | 2026-04-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-13 | PFP PL-TRANSMIT-000074 | NA | Trade Partner | Stage 2 O&M manual | 0 | 1 | 0 | NA | APPROVED | 2026-03-23 | WF-004950 | NA | 2026-03-25 |  |  | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-015400 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-23 | NXT-TRANSMIT-000390 | NA | Client | DEEP Version 2 to align with GMP | 0 | 1 | 0 | KPTG-IntCorr-003318 | APPROVED |  | NA | NA |  |  | Distribution only |  | 2026-03-24 | KPTG-TRANSMIT-002791 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-10 | PCForm-TRANSMIT-000267 | NA | Trade Partner | Concrete - Alternative Supplier 40mpa PT mix | 0 | 1 | 0 | NA | APPROVED | 2025-12-10 | WF-000811 | NA | 2025-12-15 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-23 | INGEN3D-TRANSMIT-000697 | NA | Consultant | I3D-378 Next DC M3 Stage 4 - Fuel Tanks IFC Drawings | 73 | 0 | 0 | NA | APPROVED | 2026-03-23 | 004955 | NA | 2026-03-30 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-016580 | Closed | 73 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-23 | RDSBIM-TRANSMIT-000250 | NA | Trade Partner | NXM3S4 ROOF LEVEL CONCRETE PROFILE PLAN NORTH OFFICE | 1 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | 2613 | 2026-03-31 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-017246 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-23 | JCBa-TRANSMIT-000074: | NA | Consultant | STRUCTURAL SETOUT PLANS GROUND FLOOR: ZONES 1,3 & 4 | 3 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | 566 | 2026-03-25 |  | Terminated as advised by Kapitol DM "to update the drawings". ACC#566 ¦ WF-000304 | 2026-03-24 | 2026-03-24 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-23 | M.2-TRANSMIT-000012: | NA | Trade Partner | External Lighting - Level 00 Ground - For Review | 1 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | 570 | 2026-03-27 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-001075 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-23 | Auspan-TRANSMIT-000158 | NA | Trade Partner | Re: Precast shop drawings for approval. Ground floor. | 2 | 0 | 0 | KPTG-IntCorr-000405 | APPROVED |  | NA | 642 | 2026-04-08 |  | Drawing Locked, waiting for Advice - As advised by PC , Wait till the review completed. - KPTG-IntCorr-000405 1/4/26 Review initiated. | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-001329 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-23 | Auspan-TRANSMIT-000159 | NA | Trade Partner | Re: Grout Tube clash - 0G1044 & 0G1046 | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect revision. KPTG-SADV-001470 |  | 2026-03-23 | KPTG-SADV-001470 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-23 | Auspan-TRANSMIT-000161 | NA | Trade Partner | Precast shop drawings for approval. Level 1. | 36 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | 572 | 2026-03-30 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-001198 | Closed | 36 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-23 | Auspan-TRANSMIT-000162 | NA | Trade Partner | Update IFCed shop drawings for construction. Ground floor. | 13 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC No review required - Register and distribute KPTG-TRANSMIT-001031 |  | 2026-03-23 | KPTG-TRANSMIT-001031 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-23 | Auspan-TRANSMIT-000163 | NA | Trade Partner | Re: Grout Tube clash - 0G1044 & 0G1046 | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC No review required - Register and distribute KPTG-TRANSMIT-001032 |  | 2026-03-23 | KPTG-TRANSMIT-001032 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-23 | Rinco-TRANSMIT-000036 | NA | Consultant | : Structural - Reinforcement drawings Issued for Construction | 144 | 0 | 0 | KPTG-IntCorr-000404 | APPROVED | 2026-03-24 | NA | 578 | 2026-03-26 |  | waiting for Transmittal advise; KPTG-IntCorr-000404 | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-001256 | Open | 144 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-08 | PCForm-TRANSMIT-000024 | NA | Trade Partner | Level 2 - Post Tensioning Plans - Zone 1 & Zone 2 | 8 | 0 | 0 | NA | APPROVED | 2025-12-09 | NA | 143 | 2025-12-12 |  |  | 2026-01-27 | 2026-01-27 | KPTG-TRANSMIT-000326 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-23 | Auspan-TRANSMIT-000164 | NA | Trade Partner | Precast panel 1B5016 for construction. | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC No review required - Register and distribute KPTG-TRANSMIT-001035 |  | 2026-03-23 | KPTG-TRANSMIT-001035 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-23 | POTTSENG-TRANSMIT-000007 | NA | Trade Partner | 671C: HYDRAULIC SERVICES CORE WALL PENETRATION LAYOUTS | 2 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | 362 | 2026-03-30 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-000805 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-23 | KPTG-TRANSMIT-000614 | NA | Trade Partner | - Consultant Review PMU Drawings | 40 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | 363 | 2026-03-30 |  | Review voided ; drawings to be superseded by Jangho |  | 2026-04-28 | NA | Closed | 40 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-23 | KPTG-TRANSMIT-000615 | NA | Trade Partner | Consultant Facade Drawings Reviews | 75 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | 364 | 2026-03-30 |  | Review void; Updated drawings received. |  | 2026-04-27 | NA | Closed | 75 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-12 | SMEPS-TRANSMIT-000134 | NA | Trade Partner | ROIP Drawings | 10 | 0 | 0 | NA | APPROVED | 2026-03-19 | WF-000278 | NA | 2026-03-25 |  | NA | 2026-03-30 | 2026-04-07 | KPTG-TRANSMIT-000699 | Closed | 20 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-23 | SIL-TRANSMIT-000023 | NA | Trade Partner | Re: Submitting the L2 Scripts - PDF for Scripts | 0 | 6 | 0 | NA | REJECTED | [5 empty] | Revision of Documents are not current, requested to resubmit: KPTG-IntCorr-000177 |  | 2026-03-23 | KPTG-IntCorr-000177 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-23 | WGAVIC-TRANSMIT-000091 | NA | Consultant | M2 - Stages 9 and 10 Steelwork - Certification Issue | 21 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | 511 | 2026-03-26 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-002039 | Closed | 21 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-23 | SIL-TRANSMIT-000022 | NA | Trade Partner | : Re-Transmitting the documents by Removing Cover Sheet | 18 | 0 | 0 | NA | APPROVED | 2026-03-23 | WF-000085 | NA | 2026-03-27 |  |  | 2026-03-28 | 2026-03-31 | KPTG-TRANSMIT-000258 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-23 | SIL-TRANSMIT-000021 | NA | Trade Partner | Re: Documents Submitted FOR CONSTRUCTION | 1 | 0 | 0 | NA | APPROVED | 2026-03-23 | WF-000084 | NA | 2026-03-27 |  |  | 2026-03-28 | 2026-03-31 | KPTG-TRANSMIT-000255 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-23 | SIL-TRANSMIT-000020 | NA | Trade Partner | Re: Re-Transmitting the documents by Removing Cover Sheet | 18 | 0 | 0 | NA | REJECTED | [5 empty] | Covering sheet is not received, updated documents are transmittted via SIL-TRANSMIT-000022, WE HAVE IGNORED THIS TRANSMIT: |  | 2026-03-23 | KPTG-IntCorr-000176 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-09 | PCForm-TRANSMIT-000027 | NA | Trade Partner | Wall Elevations for review | 13 | 0 | 0 | NA | APPROVED | 2025-12-09 | WF-000069 | NA | 2025-12-15 |  |  | 2026-01-20 | 2026-01-30 | KPTG-TRANSMIT-000340 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-23 | SIL-TRANSMIT-000019 | NA | Trade Partner | Re: Re-Submitting the ATS Documents with B revision | 0 | 13 | 0 | NA | APPROVED | 2026-03-23 | WF-000084 | NA | 2026-03-27 |  |  | 2026-03-28 | 2026-03-31 | KPTG-TRANSMIT-000252 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-23 | Appselec-TRANSMIT-000035 | NA | Trade Partner | LV Cable Tech Data IFC | 0 | 1 | 0 | KPTG-IntCorr-000175 | APPROVED |  | NA | NA |  |  |  |  | 2026-03-25 |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-23 | Appselec-TRANSMIT-000034 | NA | Trade Partner | Technical Data For Construction | 0 | 16 | 0 | KPTG-IntCorr-000174 | APPROVED | [5 empty] | Kapitol Advice Awaits: KPTG-IntCorr-000174, IFC documents have been transmitted to all parties |  | 2026-03-25 | KPTG-TRANSMIT-000188 | Closed | 10 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-23 | WGAVIC-TRANSMIT-000092 | NA | Consultant | M2 - Stages 9 and 10 Steelwork Supplementary Drawings - Construction Issue | 4 | 0 | 0 | KPTG-IntCorr-000595 | APPROVED | 2026-03-30 | NA | 582 | 2026-04-03 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-001585 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-23 | VIA Arch-TRANSMIT-000074 | NA | Consultant | Stair Documentation | 12 | 0 | 0 | KPTG-IntCorr-000596 | APPROVED | 2026-03-26 | NA | 558 | 2026-03-31 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-001604 | Closed | 12 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-23 | VIA Arch-TRANSMIT-000075 | NA | Consultant | Issue for Building Permit - Site Details, FOH, Amenities Level 1 | 24 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | 513 | 2026-03-26 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-001878 | Closed | 24 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-20 | RDSBIM-TRANSMIT-000169 | NA | Trade Partner | LINDRUM ¦ LEVEL 11 TO LEVEL 27 & ROOF COREWALL CONCRETE PROFILE | 5 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | 610 | 2026-03-28 |  | BIM workflow is terminated. As per the Direction from Ms. Ashlin. | 2026-04-07 | 2026-04-07 | KPTG-IntCorr-000850 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-23 | WAM-TRANSMIT-000737 | NA | Consultant | 95% DD Demo update | 5 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | 360 | 2026-03-26 |  | 3 - drawings submitted - 2 dwgs rejected | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-000979 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-23 | WAM-TRANSMIT-000738 | NA | Consultant | WAM ARCH - 95% DD - CSP & Ground | 49 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | 358 | 2026-03-26 |  | CAD ISSUED VIA 739 | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-001130 | Closed | 49 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-23 | WAM-TRANSMIT-000739 | NA | Consultant | WAM ARCH - 95% DD - CSP & Ground_ CAD | 49 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | CAD Dwgs - Register updated - TO BE FORWARDED WITH CORRESPONDING PDF DRAWINGS |  | 2026-04-16 | KPTG-TRANSMIT-001184 | Closed | 49 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-09 | KPTG-TRANSMIT-000207 | NA | Trade Partner | Strategic Core SD review | 12 | 0 | 0 | NA | APPROVED | 2025-12-09 | WF-000064 | NA | 2025-12-12 |  |  | 2026-01-12 | 2026-01-19 | KPTG-TRANSMIT-000292 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-23 | PCForm-TRANSMIT-000112 | NA | Trade Partner | Raft 2 - Cladding Elevation Drawings | 3 | 0 | 0 | KPTG-IntCorr-000521 | APPROVED |  | NA | NA |  |  | Nich to confirm - QA Verified - Nick to clarify - Actioned as per KPTG-IntCorr-000529 |  | 2026-03-26 | KPTG-TRANSMIT-000932 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-23 | PCForm-TRANSMIT-000111 | NA | Trade Partner | Fwd: Raft 1 - Jumpform Drawings Package - Issued for Construction | 23 | 0 | 0 | KPTG-IntCorr-000522 | APPROVED | 2026-03-26 | NA | 370 | 2026-03-31 |  | Nich to confirm | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-001049 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-23 | RDSBIM-TRANSMIT-000004 | NA | Trade Partner | MEL05C4 ¦ LEVEL 02 COLO 04 SCREED LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA |  | 2026-03-31 |  | File supersesed | 2026-03-07 | 2026-03-07 | NA | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-10 | SMEPS-TRANSMIT-000173 | NA | Trade Partner | F1 - Light pole sample | 0 | 1 | 0 | NA | APPROVED | 2026-03-10 | WF-004690 | NA | 2026-03-20 |  |  | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-014880 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-24 | SMEPS-TRANSMIT-000221 | NA | Trade Partner | SME - IFA Sample submissions - Nylon Tie Alternative | 0 | 1 | 0 | NA | APPROVED | 2026-03-24 | WF-004960 | NA | 2026-04-14 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-015191 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-24 | fjc-TRANSMIT-000144 | NA | Consultant | Re: LIN I COREWALL¦ CPP I Stair Landing & Tread detail query | 3 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 612 | 2026-03-27 |  |  | 2026-03-25 | 2026-03-25 | KPTG-SADV-003553 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-02-13 | Novas-TRANSMIT-000005 | NA | Trade Partner | Re: Door Schedule Updates | 0 | 1 | 0 | NA | APPROVED | 2026-02-13 | WF-000615 | NA | 2026-02-19 |  |  | 2026-03-23 | 2026-03-24 | KPTG-TRANSMIT-002091 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-17 | PARR-TRANSMIT-000056 | NA | Trade Partner | P2645 - KPG NDC M3 S1 DH7&8 - Fuel - AS-BUILT | 0 | 1 | 0 | NA | APPROVED | 2026-03-24 | WF-000971 | NA | 2026-04-06 |  | Terminated requested by chri doh |  | 2026-03-30 | KPTG-TRANSMIT-002794 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-11-28 | Auspan-TRANSMIT-000010 | NA | Trade Partner | Resubmit precast shop drawings for approval. Retaining walls. | 102 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Wrong title guide-KPTG-IntCorr-000174. KPTG-DA-000590 |  | 2025-12-02 | KPTG-DA-000590 | Closed | 102 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-10 | SKS Tech-TRANSMIT-000104 | NA | Trade Partner | EARTHING & LIGHTING SCHEMATIC FOR APPROVAL | 2 | 0 | 0 | KPTG-IntCorr-000777 | APPROVED |  | NA | NA |  |  |  |  | 2026-01-23 | KPTG-TRANSMIT-002587 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-23 | RDSBIM-TRANSMIT-000042 | NA | Trade Partner | MWYCCB ¦ LEVEL 01 INTERNAL FITOUT PLAN - FEMALE WC | 2 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 188 | 2026-03-31 |  | Bim 360 review terminated by Moj |  | 2026-06-29 | KPTG-TRANSMIT-001360 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-24 | D&E-TRANSMIT-000183 | SPARK-CRFI-KPG-000348 | Trade Partner | FANS & COWLS | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-24 | crossfir-TRANSMIT-000054 | NA | Trade Partner | Wet Fire - Level 10, 11 & 12 , IFC | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol IFC drawings Distribution only. | 2026-03-24 |  | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-23 | SKS Tech-TRANSMIT-000173 | NA | Trade Partner | FS DB SCHEMATIC IFC | 1 | 0 | 0 | KPTG-IntCorr-001092 | APPROVED |  | NA | NA |  |  | clarification from harry- fc DOCS REGISTER UPDATED AND FORWARDED |  | 2026-04-01 | KPTG-TRANSMIT-003332 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-23 | Endfire-TRANSMIT-000074 | NA | Trade Partner | ENDFIRE IFC DRAWINGS | 11 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | 1163 | 2026-03-25 |  |  | 2026-03-28 | 2026-03-30 | KPTG-TRANSMIT-003311 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-23 | VAE-Grp-TRANSMIT-000141 | NA | Trade Partner | NXD1S2 - IFC - MECH - DWGS, TS, SCH, REP - MCCs, OAPs, AS621439 DESIGN VERIFICATION REPORT | 0 | 17 | 0 | NA | APPROVED |  | NA | NA |  |  | FC Docs register updated, 1 doc - rejected KPTG-IntCorr-001090 and reissued - trn # 142) |  | 2026-04-26 | KPTG-TRANSMIT-003549 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-23 | VAE-Grp-TRANSMIT-000142 | NA | Trade Partner | NXD1S2 - IFC - MECH - MCC DRAWING MCC-B-LG-A-02 (REV CORRECTION) | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | REJECTED DOC REISSUED( trn-0014), registers updated - FC Docs |  | 2026-04-26 | KPTG-TRANSMIT-003549 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-23 | VAE-Grp-TRANSMIT-000143 | NA | Trade Partner | NXD1S2 - IFA - MECHANICAL SERVICES - COMMISSIONING PLAN | 0 | 1 | 0 | NA | APPROVED | 2026-03-23 | WF-000950 | NA | 2026-03-30 |  |  | 2026-04-30 | 2026-04-30 | KPTG-WTRAN-002047 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-24 | ASV-TRANSMIT-000163 | NA | Trade Partner | Revised Samples - Small Bore - Gate Valve & RPZD | 0 | 2 | 0 | NA | APPROVED | 2026-03-24 | WF-004970 | NA | 2026-04-06 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-015318 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-24 | Civilex-TRANSMIT-000217 | NA | Trade Partner | Stage 1 Swale Restoration Revised Plan Approval Revised Plan - Bollard Included | 2 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 4016 | 2026-03-31 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-016281 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-10 | GunAus-TRANSMIT-000005 | NA | Trade Partner | Updated Drawings - Attack Doors | 17 | 0 | 0 | Rejected - KPTG-IntCorr-000778 | REJECTED | 2025-12-11 | NA | 733 | 2025-12-18 |  | Reviews made void - Revised drawings issued via Gun-Aus-Trn#0007 dtd 16/12/2025 | 2025-12-16 | 2025-12-16 | GunAus-TRANSMIT-000007 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-24 | ASV-TRANSMIT-000159 | NA | Trade Partner | Hydraulic Sample - Valves | 0 | 2 | 0 | NA | REJECTED | [5 empty] | The titles inside and outside are wrong. |  | 2026-03-24 | KPTG-DA-005639 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-24 | ASV-TRANSMIT-000161 | NA | Trade Partner | Revised Sample Submission - Trench Grate Grout | 0 | 1 | 0 | NA | APPROVED | 2026-03-24 | WF-004962 | NA | 2026-04-03 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-015462 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-24 | ASV-TRANSMIT-000162 | NA | Trade Partner | Hydraulic Sample - Hot Water Clips | 0 | 1 | 0 | NA | APPROVED | 2026-03-24 | WF-004963 | NA | 2026-04-03 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-015481 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-24 | D&E-TRANSMIT-000512 | NA | Trade Partner | Office BMS Points List - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-24 | WF-004974 | NA | 2026-04-07 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-015944 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-24 | SMEPS-TRANSMIT-000153 | SPARK-CRFI-KPG-000284 | Trade Partner | Revision B MSB Single Line, Gen and DB Schematics & Overall | 6 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 189 | 2026-03-31 |  |  |  | 2026-04-14 | KPTG-TRANSMIT-000639 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-24 | INGEN3D-TRANSMIT-000698 | NA | Consultant | Re: I3D-378 Next DC M3 Stage 4 - Ground Floor Fuel Tank - New IFA (29-01-2026) | 2 | 0 | 0 | NA | APPROVED | 2026-03-24 | WF-004966 | NA | 2026-04-17 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-018718 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-24 | D&E-TRANSMIT-000511 | NA | Trade Partner | BMS Technical Data - Issued for Approval | 0 | 10 | 0 | NA | APPROVED | 2026-03-24 | WF-004965 | NA | 2026-04-14 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016490 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-24 | D&E-TRANSMIT-000510 | NA | Trade Partner | Refrigerant Charge Calculations - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-24 | WF-004964 | NA | 2026-04-14 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-015965 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-11-21 | SMEPS-TRANSMIT-000074 | NA | Trade Partner | Shop drawings - Earthing Schematic Rev B For review | 1 | 0 | 0 | NA | APPROVED | 2025-11-21 | NA | #43 | 2025-11-28 |  |  | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-000581 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-24 | SMEPS-TRANSMIT-000154 | SPARK-CRFI-KPG-000388 | Trade Partner | Rev B Penetration drawings | 3 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 190 | 2026-03-31 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-000771 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-10 | Auscool-TRANSMIT-000057 | NA | Trade Partner | Mech Tower Tundishes | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Not for DC's Action. Internal Communication for information |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-24 | SC-TRANSMIT-000002 | NA | Trade Partner | Secondary Steel IFA Drawings | 10 | 0 | 0 | NA | REJECTED | [5 empty] | Error in document number |  | 2026-03-24 | KPTG-TRANSMIT-000585 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-24 | PMT Sec-TRANSMIT-000003 | SPARK-CRFI-KPG-000617 | Trade Partner | PMT Tech Data | 0 | 37 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-05-04 | KPTG-TRANSMIT-000812 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-24 | KALLIBRE-TRANSMIT-000002 | NA | Trade Partner | 61x Door Frames For Review & Approval | 61 | 0 | 0 | NA | REJECTED | [5 empty] | Missing - Revision block, Revision history, Revision date, Drawing title & Drawing status |  | 2026-03-24 | KPTG-TRANSMIT-000589 | Closed | 61 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-24 | Auspan-TRANSMIT-000006 | NA | Trade Partner | Resend column drawings without marking plans in separated transmittal as request. | 16 | 0 | 0 | NA | REJECTED | [5 empty] | The document was marked as NLIU initially and later Project Team agreed to proceed the drawings as it is. As It was makred initially system was not allowing to update the register. So, the NLIU copy was transmitted to Originator, updated their register and the whole set of drawings was resubmitted in Auspan-TRANSMIT-000007. |  | 2026-03-24 | KPTG-TRANSMIT-000113 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-24 | Auspan-TRANSMIT-000007 | NA | Trade Partner | Resend column drawings without marking plans in separated transmittal as request | 16 | 0 | 0 | NA | APPROVED | 2026-03-24 | WF-000017 | NA | 2026-04-02 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-000134 | Closed | 16 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-24 | RDSBIM-TRANSMIT-000076 | NA | Trade Partner | GROUND FLOOR-B-G-037 MALE TOILET-FLOOR FINISHES LAYOUT & ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 1165 | 2026-03-26 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-003665 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-24 | RDSBIM-TRANSMIT-000077 | NA | Trade Partner | GROUND FLOOR-B-G-011-02 SECURE ACCESSIBLE TOILET LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 1167 | 2026-03-26 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-003652 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-24 | Stowe-A-TRANSMIT-000529 | NA | Trade Partner | STOWE - AS BUILTS - LOWER GROUND - 24.03.2026 - ELC | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with drawing status. |  | 2026-04-01 | KPTG-SADV-004608 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-24 | ACG-TRANSMIT-000070 | NA | Trade Partner | M3 - Stage 2 ATG Sample | 0 | 1 | 0 | NA | APPROVED | 2026-03-24 | WF-004976 | NA | 2026-03-31 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-016722 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-24 | IVS-TRANSMIT-000352 | NA | Consultant | Stage 2 - Southern Retaining Wall Construction Issue (Revised as clouded) | 2 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 4018 | 2026-03-26 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-015049 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-10 | ADP-TRANSMIT-000034 | NA | Consultant | ADP MEL4834 - Updated EL Schematic | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC, Updated register and distributed to Project Team. |  | 2025-12-11 | KPTG-TRANSMIT-002169 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-24 | GHD-TRANSMIT-000003 | NA | Consultant | For Coordination Security Services Drawings | 15 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Issued For information only. To be updated in Aconex and ACC. No review required. (Outlook mail: RE: [External] FW: KPTG-DA-000287: DESIGN PROGRAM - KEY DATES ACNXREF<1uIuH6hZXcMNq8sdkUdulB>) |  | 2026-03-24 | KPTG-TRANSMIT-000114 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-24 | D&E-TRANSMIT-000513 | NA | Trade Partner | Semrad Leak Detection ITP - IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-03-24 | KPTG-TRANSMIT-014897 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-24 | SKS Tech-TRANSMIT-000064 | NA | Trade Partner | LV Submains IFC rev | 0 | 1 | 0 | NA | APPROVED | 2026-03-24 | WF-004975 | NA | 2026-04-14 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-24 | HDRAus-TRANSMIT-000441 | NA | Consultant | Fwd: M3 Stage 4 - Document upload - Door hardware schedule | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC DOCUMENT ONLY FOR INFORM OTHERS |  | 2026-03-24 | KPTG-TRANSMIT-014911 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-24 | KPTG-TRANSMIT-014839, | NA | Trade Partner | Fwd: Precast IFC Updates | 32 | 0 | 0 | NA | APPROVED | 2026-03-24 | WF-004980 | NA | 2026-03-27 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-24 | INDS-TRANSMIT-000012 | NA | Trade Partner | L1 Balcony Sprinkler Layout - Typical | 5 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 579 | 2026-03-31 |  |  | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-001181 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-24 | Auspan-TRANSMIT-000165 | NA | Trade Partner | Shop Drawings to be transmitted | 2 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 581 | 2026-03-31 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-001214 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-24 | Auspan-TRANSMIT-000166 | NA | Trade Partner | Precast shop drawings for approval | 25 | 0 | 0 | NA | APPROVED |  | NA | 583 | 2026-03-30 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-001217 | Closed | 25 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-24 | Auspan-TRANSMIT-000167 | NA | Trade Partner | Precast shop drawings for construction | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC No review required - Register and distribute KPTG-TRANSMIT-001046 |  | 2026-03-24 | KPTG-TRANSMIT-001046 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-24 | M.2-TRANSMIT-000013 | NA | Trade Partner | GPO & Switch Tech Data | 0 | 2 | 0 | NA | APPROVED | 2026-03-24 | WF-000312 | NA | 2026-03-31 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-001451 | Open | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-10 | HDRAus-TRANSMIT-000073 | NA | Consultant | M3S1DH7&8 - RDS Issue for Construction | 1 | 0 | 0 | NA | APPROVED | 2025-12-10 | NA | 1307 | 2025-12-15 |  |  | 2026-03-05 | 2026-03-05 | KPTG-TRANSMIT-002712 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-24 | M.2-TRANSMIT-000014 | NA | Trade Partner | Floor box Tech Data | 0 | 2 | 0 | NA | APPROVED | 2026-03-24 | WF-000313 | NA | 2026-03-31 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-001450 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-24 | JCBa-TRANSMIT-000075 | NA | Consultant | :STRUCTURAL SETOUT PLANS GROUND FLOOR: ALL ZONES | 5 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 586 | 2026-03-26 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-001118 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-24 | Electro-TRANSMIT-000004 | NA | Consultant | Specialist Lighting DD Set | 13 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 497 | 2026-03-26 |  |  | 2026-03-24 | 2026-03-24 | KPTG-TRANSMIT-001656 | Closed | 13 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-24 | B Smart-TRANSMIT-000066: | NA | Consultant | Partition Plans IFC | 24 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 366 | 2026-03-30 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-000770 | Closed | 24 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-23 | KPTG-TRANSMIT-002832 | NA | Trade Partner | BKR-01 bike rack two tier | 0 | 1 | 0 | NA | APPROVED | 2026-03-23 | WF - 000971 | NA |  |  | File supersede and WF terminated. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-24 | ccair-TRANSMIT-000112 | NA | Trade Partner | AC Units IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC only for distribution. |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-24 | KPTG-TRANSMIT-002604 | NA | Client | FFS20 Dial Table | 0 | 1 | 0 | NA | APPROVED | 2026-03-24 | WF-000894) | NA | 2026-03-30 |  | NA | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-002769 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-24 | RDSBIM-TRANSMIT-000004 | NA | Trade Partner | MEL05C4 ¦ LEVEL 02 COLO 04 SCREED LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-03-24 | WF - 000289 | NA | 2026-03-27 |  | File superseded | 2026-04-24 | 2026-04-24 | NA | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-24 | Entire M-TRANSMIT-000021 | NA | Trade Partner | Mechanical Commissioning Management Plan Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-24 | WF - 000291 | NA | 2026-03-27 |  | NA | 2026-03-30 | 2026-03-31 | KPTG-TRANSMIT-000676 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-10 | RDSBIM-TRANSMIT-000130 | NA | Trade Partner | LEVEL 09 CONCRETE PROFILE PLAN | 10 | 0 | 0 | NA | APPROVED |  |  | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties |  |  |  | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-24 | Entire M-TRANSMIT-000022 | NA | Trade Partner | Drain Pipe Insulation IFA Rev B | 0 | 0 | 0 | NA | APPROVED | 2026-03-24 | WF - 000290 | NA | 2026-03-27 |  | NA | 2026-03-25 | 2026-03-26 | KPTG-TRANSMIT-000603 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-23 | 4DW-TRANSMIT-000162 | NA | Consultant | Structural Documentation - General Updates | 25 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | NA |  |  |  | 2026-03-24 | 2026-03-24 | KPTG-SADV-003952 | Closed | 25 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-24 | SMEPS-TRANSMIT-000157 | NA | Trade Partner | SME Shop Drawing ROIP IFC A | 2 | 0 | 0 | NA | APPROVED | 2026-03-24 | WF - 000292 | NA | 2026-03-27 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-000585 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-24 | SMEPS-TRANSMIT-000158 | NA | Trade Partner | - SME Shop Drawing ROIP IFC A | 1 | 0 | 0 | NA | APPROVED | 2026-03-24 | WF - 000293 | NA | 2026-03-26 |  | NA | 2026-03-25 | 2026-03-26 | KPTG-TRANSMIT-000588 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-23 | AdntCons-TRANSMIT-000011 | NA | Trade Partner | Latest wetfire docs for construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC DRAWING, TRANSMITTED TO TRADE & CONSULTANTS |  | 2026-03-24 | KPTG-TRANSMIT-002609 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-24 | PenskePS-TRANSMIT-000004 | NA | Trade Partner | MEL05-COLO4-GPC Drawings | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC only for ACONEX Update. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-24 | PenskePS-TRANSMIT-000005 | NA | Trade Partner | MEL05-COLO4- LV Board SLD & GA | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC onlu for Aconex update. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-24 | PenskePS-TRANSMIT-000006 | NA | Trade Partner | MEL05-COLO4-LV Switchboard Schematic | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-23 | 4DW-TRANSMIT-000163 | NA | Consultant | Structural Documentation - Precast walls package | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | WORKFLOW IS COMBINED WITH 4DW-TRANSMIT-000164 |  | 2026-03-24 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-23 | 4DW-TRANSMIT-000164 | NA | Consultant | Stage 2 Load-bearing PC wall drawings IFC | 6 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 469 | 2026-03-31 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-11 | INGEN3D-TRANSMIT-000672 | NA | Trade Partner | I3D-378 Next DC M3 Stage 4 - Ground Floor Fuel Tank - Precast Panels - IFA Resubmission (11-12-2025) | 25 | 0 | 0 | NA | APPROVED | 2025-12-11 | WF-003562 | NA | 2026-01-06 |  |  |  | 2026-02-17 | KPTG-TRANSMIT-013013 | Closed | 24 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-23 | 4DW-TRANSMIT-000165 | NA | Consultant | Stage 2 demo, retention, piling and foundation IFC structural drawings | 25 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | WORKDLOW IS ALREADY CREATED, IT IS DUPLICATES OF 4DW-TRANSMIT-000162 |  | 2026-03-24 | 4DW-CDMEMO-000650 | Closed | 25 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-24 | KPTG-TRANSMIT-002601 | NA | Trade Partner | FFL03 - Tambor Unit | 5 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 468 | 2026-03-27 |  |  | 2026-03-30 | 2026-03-30 | KPTG-SADV-004022 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-20 | Stanmor-TRANSMIT-000006 | NA | Trade Partner | As per KPTG-IntCorr-006172 | 0 | 1 | 0 | NA | APPROVED | 2026-03-23 | WF-000886 | NA | 2026-03-27 |  |  | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-002716 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-20 | Stanmor-TRANSMIT-000007 | NA | Trade Partner | As per KPTG-IntCorr-006177 | 0 | 1 | 0 | NA | APPROVED | 2026-03-23 | WF-000887 | NA | 2026-03-27 |  |  | 2026-04-14 | 2026-04-14 | KPTG-TRANSMIT-002744 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-20 | 4DW-TRANSMIT-000161 | NA | Consultant | Structural Drawing Updat | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Transmitted to Trade & consultants |  | 2026-03-23 | KPTG-TRANSMIT-002592 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-20 | Stanmor-TRANSMIT-000008 | NA | Trade Partner | As perKPTG-IntCorr-006174 | 0 | 1 | 0 | NA | APPROVED | 2026-03-23 | WF-000888 | NA | 2026-03-27 |  |  | 2026-04-14 | 2026-04-14 | KPTG-TRANSMIT-002733 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-20 | CNGC-TRANSMIT-000002 | NA | Trade Partner | TDS Transmital | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Covering Sheets are not attached with Technical submission , requested to resubmit:KPTG-IntCorr-006213 |  | 2026-03-23 | KPTG-IntCorr-006213 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-20 | ECBS-TRANSMIT-000077 | NA | Trade Partner | Revised tech data for L2 AM41 for review | 0 | 1 | 0 | NA | APPROVED | 2026-03-23 | WF-000890 | NA | 2026-03-27 |  |  | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-002713 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-21 | CNGC-TRANSMIT-000003 | NA | Trade Partner | Re: TDS Transmital | 0 | 3 | 0 | NA | APPROVED | 2026-03-23 | WF-000889 | NA | 2026-03-27 |  |  | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-002724 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-23 | RDSBIM-TRANSMIT-000170 | NA | Trade Partner | LINDRUM ¦ BASEMENT LEVEL BLOCK WALL LAYOUT AND ELEVATION | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | TRANSMITTED TO TRADE & CONSULTANTS |  | 2026-03-24 | KPTG-TRANSMIT-002088 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-11 | JCBa-TRANSMIT-000202 | NA | Consultant | L9 BTR GA - IFC | 2 | 0 | 0 | NA | APPROVED | 2025-12-11 | WF-000816 | 512 | 2025-12-15 |  |  | 2025-12-16 | 2025-12-16 | KPTG-DA-002269 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-24 | RDSBIM-TRANSMIT-000171 | NA | Trade Partner | LINDRUM ¦ LEVEL 02 TO LEVEL 05 COREWALL CONCRETE PROFILE PLAN ELEVATIONS | 2 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 611 | 2026-03-31 |  | workflow 611 terminated. | 2026-03-25 | 2026-03-25 | KPTG-IntCorr-000821 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-24 | Appselec-TRANSMIT-000036 | NA | Trade Partner | MEL11-APPSELEC-T-TDS-13-0- PATCH CORDS Rev 1 | 0 | 1 | 0 | NA | APPROVED | 2026-03-24 | WF-000087 | NA | 2026-03-27 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-000438 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-24 | Entire M-TRANSMIT-000013 | NA | Trade Partner | Mechanical Commissioning Management Plan Issued for Approval | 0 | 1 | 0 |  | APPROVED | 2026-03-29 | WF-000102 | NA | 2026-04-02 |  | Kapitol Advice awaits:KPTG-IntCorr-000193 | 2026-04-14 | 2026-04-14 | KPTG-TRANSMIT-000360 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-24 | PenskePS-TRANSMIT-000001 | NA | Trade Partner | MEL05 COLO4 - FAT Reports and Authorisation to Ship | 0 | 10 | 0 | NA | REJECTED | [5 empty] | All documents are related to MEL 05 project: Rejected KPTG-IntCorr-000183 |  | 2026-03-24 | KPTG-IntCorr-000183 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-24 | Entire M-TRANSMIT-000014 | NA | Trade Partner | Drain Pipe Insulation Technical Data IFA Rev B | 0 | 1 | 0 | NA | APPROVED | 2026-03-24 | WF-000088 | NA | 2026-03-30 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-000211 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-24 | Entire M-TRANSMIT-000015 | NA | Trade Partner | VCD Technical Data IFA Rev B | 0 | 1 | 0 | NA | APPROVED | 2026-03-24 | WF-000089 | NA | 2026-03-30 |  |  |  | 2026-04-01 | KPTG-TRANSMIT-000266 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-24 | WSP ANZ-TRANSMIT-000055 | NA | Consultant | WSP 70% Design Development issue for Building Permit - CSMS | 25 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 519 | 2026-03-27 |  | Actual Receipt Date 20/03 | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-001897 | Closed | 25 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-24 | WSP ANZ-TRANSMIT-000055 | NA | Consultant | WSP 70% Design Development issue for Building Permit - ELC | 69 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 521 | 2026-03-27 |  | Actual Receipt date 20/3 | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-001897 | Closed | 69 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-24 | WSP ANZ-TRANSMIT-000055 | NA | Consultant | WSP 70% Design Development issue for Building Permit - Fire | 92 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 522 | 2026-03-27 |  | Actual receipt date 20/3 | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-001897 | Closed | 92 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-24 | WSP ANZ-TRANSMIT-000055 | NA | Consultant | WSP 70% Design Development issue for Building Permit - Fuel | 23 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 524 | 2026-03-27 |  | Actual receipt Date 20/3 | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-001897 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2025-12-11 | Nilsen3-TRANSMIT-000090 | NA | Trade Partner | Nilsen As-Builts | 24 | 0 | 0 | NA | APPROVED |  |  | NA |  |  | As-builts, No review required. Updated register and distributed to the Project Team. |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-24 | PenskePS-TRANSMIT-000016 | NA | Trade Partner | MEL05 COLO4 - FAT Report and Authorisation to Ship | 0 | 10 | 0 | NA | APPROVED | 2026-03-25 | WF - 000294 | NA |  |  | NA | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-000724 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-20 | PenskePS-TRANSMIT-000006 | NA | Trade Partner | MEL05-COLO4-LV Switchboard Schematic | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC, Update Aconex register only. |  |  |  | Closed | 0 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-20 | PenskePS-TRANSMIT-000007 | NA | Trade Partner | GPC Generator Control Panel GA. | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC, Update Aconex register only. |  |  |  | Closed | 0 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-20 | PenskePS-TRANSMIT-000008 | NA | Trade Partner | GPC Generator Control Panel Schematics | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC, Update Aconex register only. |  |  |  | Closed | 0 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-20 | PenskePS-TRANSMIT-000009 | NA | Trade Partner | Generator Control Panel SLD | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC, Aconex register only. |  |  |  | Closed | 0 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-20 | PenskePS-TRANSMIT-000010 | NA | Trade Partner | MEL05 COLO4 - Fuel Treatment System | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Closed | 0 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-20 | PenskePS-TRANSMIT-000011 | NA | Trade Partner | MEL05-COLO4 - EPMS Schematic | 0 | 1 | 0 | NA | APPROVED |  | Na | NA |  |  | IFC, Aconex register only. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-20 | PenskePS-TRANSMIT-000012 | NA | Trade Partner | MEL05-COLO4- Enclosure Fire System Layouts | 0 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC, Update Aconex register only. |  |  |  | Closed | 0 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-25 | INDS-TRANSMIT-000034 | NA | Trade Partner | Wet Fire - Mezzanine | 1 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 613 | 2026-04-01 |  |  | 2026-04-02 | 2026-04-02 | KPTG-SADV-003642 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-20 | PenskePS-TRANSMIT-000013 | NA | Trade Partner | MEL05-COLO4 - Label Schedule | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC, Update Aconex register only. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2025-12-11 | Nilsen3-TRANSMIT-000091 | NA | Trade Partner | Nilsen Shop Drawings - IFC | 1 | 0 | 0 | NA | APPROVED |  |  | NA |  |  | IFC, No review required. Updated register and distributed to the Project Team. |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-20 | PenskePS-TRANSMIT-000014 | NA | Trade Partner | MEL05 COLO 4 Functional Description | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC, Update Aconex register only. |  |  |  | Closed | 0 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-20 | PenskePS-TRANSMIT-000015 | NA | Trade Partner | MEL05-COLO4- LIGHTNING PROTECTION SYSTEM | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Update Aconex register only. |  |  |  | Closed | 0 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-24 | PenskePS-TRANSMIT-000017 | NA | Trade Partner | MEL05 COLO4 GPC 3D | 0 | 1 | 0 | NA | APPROVED | 2026-03-25 | WF - 000295 | NA | 2026-03-27 |  | NA | 2026-03-25 | 2026-03-26 | KPTG-TRANSMIT-000600 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-24 | ZIA-TRANSMIT-000041 | NA | Trade Partner | CSMS - Samples (022 & 023) | 0 | 2 | 0 | NA | APPROVED | 2026-03-24 | WF-000955 | NA | 2026-03-27 |  |  | 2026-04-09 | 2026-04-09 | KPTG-WTRAN-001901 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-24 | WAM-TRANSMIT-000740 | NA | Consultant | 95% DD Demo - Revision number amended | 2 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 364 | 2026-03-26 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-000974 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-24 | HVHD-TRANSMIT-000003 | NA | Trade Partner | ESD Implementation Matrix | 0 | 1 | 0 | NA | APPROVED | 2026-03-24 | WF-000264 | NA | 2026-03-27 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-000939 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-24 | RDSBIM-TRANSMIT-000022 | NA | Trade Partner | DISTLV - LEVEL 02 CONCRETE PROFILE PLAN AND SECTIONS | 6 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 362 | 2026-03-27 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-001104 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-24 | PWC-TRANSMIT-000001 | NA | Trade Partner | Waterproofing Document | 0 | 1 | 0 | NA | REJECTED | [5 empty] | rejected : KPTG-TRANSMIT-000918 |  |  | KPTG-TRANSMIT-000918 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-24 | PCForm-TRANSMIT-000114 | NA | Trade Partner | Raft 2 - Pour Sequence for review | 3 | 0 | 0 | KPTG-IntCorr-000526 | APPROVED | 2026-03-29 | NA | 376 | 2026-04-01 |  | IFA -1 DRAWING | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-001057 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-25 | crossfir-TRANSMIT-000055 | NA | Trade Partner | Wet Fire - Level 13, 14 ,15 & Roof, IFA | 4 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | WF - 555 | 2026-04-01 |  | Na | 2026-04-07 | 2026-04-07 | KPTG-WTRAN-002245 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-01 | PCForm-TRANSMIT-000050 | NA | Trade Partner | Fwd: Level 11 to Roof - Issued for Approval | 10 | 0 | 0 |  | APPROVED | 2025-12-01 | NA | 471# | 2026-01-16 |  |  | 2026-02-02 | 2026-02-02 | KPTG-SADV-002844 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-11 | Civilex-TRANSMIT-000152 | N/A | Trade Partner | Shotcrete wall strip drain sample submission | 0 | 1 | 0 | NA | APPROVED | 2025-12-11 | WF-003566 / WF-004012 |  | 2025-12-25 |  |  |  | 2026-01-29 | KPTG-TRANSMIT-012099 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-25 | INSULPAK-TRANSMIT-000015 | NA | Trade Partner | Re: PP DDC Documents- FD & Equipment for review | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Ref No. is missing |  | 2026-03-25 | KAPITOL-INTCOR-001161 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-17 | NXES-TRANSMIT-000050 | NA | Trade Partner | Nexus - Mezzanine Level - IFA Layouts | 2 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 614 | 2026-04-01 |  |  | 2026-04-23 | 2026-04-23 | KPTG-SADV-003857 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-25 | INSULPAK-TRANSMIT-000016 | NA | Trade Partner | PP DDC Documents- FD & Equipment For Review | 0 | 1 | 0 | NA | APPROVED | 2026-03-25 | WF-000449 | NA | 2026-04-07 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-25 | Tradetec-TRANSMIT-000401 | NA | Trade Partner | Tech Data - Spillceptor Sealant | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Incorrect Ref No. |  | 2026-03-25 | KPTG-RFI-006920 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-18 | NXT-TRANSMIT-001451 | NA | Trade Partner | NDC M3 Stage 4 - Fuel - BFS ATS & BFS DB | 2 | 0 | 0 | NA | APPROVED | 2026-03-25 | WF-004983 | NA | 2026-04-08 |  | Trade Partner Ref: PARR-TRANSMIT-000142 |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-25 | PARR-TRANSMIT-000143 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - BFS SCHEMATIC - IFC | 1 | 0 | 0 | NA | REJECTED | [5 empty] | IFA is still under review - NXT-PA-004079 |  | 2026-03-25 | NXT-PA-004079 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-25 | D&E-TRANSMIT-000515 | NA | Trade Partner | Insulation & Cladding | 0 | 1 | 0 | NA | APPROVED | 2026-03-25 | WF-004989 | NA | 2026-04-15 |  |  | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-015634 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-25 | GHD-TRANSMIT-000004 | NA | Consultant | For Coordination Security Schematic Diagram Drawings | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Issued For information only. To be updated in Aconex and ACC. No review required. (Outlook mail: RE: [External] FW: KPTG-DA-000287: DESIGN PROGRAM - KEY DATES ACNXREF<1uIuH6hZXcMNq8sdkUdulB>) |  | 2026-03-25 | KPTG-TRANSMIT-000116 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-25 | D&E-TRANSMIT-000185 | SPARK-CRFI-KPG-000540 | Trade Partner | CONTROL PIPE SENSORS | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-25 | D&E-TRANSMIT-000186 | SPARK-CRFI-KPG-000563 | Trade Partner | CONTROL FIELD CONTROLLERS | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-11 | SMEPS-TRANSMIT-000121 | NA | Trade Partner | M3 Stage 3 - 22KV Precast Panel Shop Drawings | 4 | 0 | 0 | NA | APPROVED | 2025-12-11 | WF-003567 |  | 2025-12-29 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-25 | Nilsen3-TRANSMIT-000057 | NA | Trade Partner | M3-HV-NIL-SA-S-0301-0034 - Roxtec 150mm Conduit Seal | 0 | 1 | 0 | NA | APPROVED | 2026-03-11 | WF-004731 | NA | 2026-03-25 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-014946 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-25 | SC-TRANSMIT-000003 | CRFI No. 167 | Trade Partner | Secondary Steel IFA Drawings | 10 | 0 | 0 | KPTG-IntCorr-002389 | APPROVED | 2026-03-31 | NA | 206 |  |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-001379 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-25 | SMEPS-TRANSMIT-000160 | NA | Trade Partner | Coms ITP | 0 | 2 | 0 | NA | APPROVED | 2026-03-25 | WF-000299 | NA | 2026-03-30 |  | NA | 2026-03-30 | 2026-03-31 | KPTG-TRANSMIT-000675 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-25 | SMEPS-TRANSMIT-000155 | SPARK-CRFI-KPG-000574 | Trade Partner | S1 - Luminaire | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-25 | SMEPS-TRANSMIT-000156 | SPARK-CRFI-KPG-000574 | Trade Partner | SMEPS-TRANSMIT-000156 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-25 | WPD-TRANSMIT-000075 | NA | Trade Partner | B18 - Ground Floor Zone 2 Drainage Layout - AS BUILT | 1 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 364 | 2026-03-31 |  |  | 2026-05-21 | 2026-05-21 | DRAFT-010015 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-25 | SMEPS-TRANSMIT-000157 | SPARK-CRFI-KPG-000181 | Trade Partner | Light poles (LP1,LP2,LP3,LP4,LP5,LP6 &LP7) | 0 | 7 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-05-06 | KPTG-TRANSMIT-000828 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-25 | LANSA-TRANSMIT-000101 | NA | Trade Partner | HYD Site Plan | 2 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 556 | 2026-03-31 |  | NA | 2026-04-20 | 2026-04-21 | DRAFT-017024 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-25 | RDSBIM-TRANSMIT-000078 | NA | Trade Partner | GROUND FLOOR-B-G-009-01 ACC TOILET WITH SHOWER-FLOOR FINISHES LAYOUT & ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 1169 | 2026-03-27 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-003648 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-08 | PROLMC-TRANSMIT-000013 | NA | Trade Partner | Sealant Tech Data | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with the document number | 2025-12-08 | 2025-12-08 | KPTG-DA-003786 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-25 | PARR-TRANSMIT-000046 | NA | Trade Partner | Fuel Services - L4 CABLE A GA | 1 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 1171 | 2026-03-27 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-003282 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-25 | SMEPS-TRANSMIT-000160 | SPARK-CRFI-KPG-000388 | Trade Partner | Up Revision Level 1 Penetrations | 4 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 192 | 2026-04-01 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-000660 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-25 | PARR-TRANSMIT-000047 | NA | Trade Partner | Fuel Services - L4 CABLE B GA | 1 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 1173 | 2026-03-27 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-003323 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-25 | SKS Tech-TRANSMIT-000174 | NA | Trade Partner | for APPROVAL submittal | 0 | 1 | 0 | KPTG-IntCorr-001099 | APPROVED | 2026-04-10 | WF-000977 | NA | 2026-04-17 |  | Clarification from harry | 2026-04-24 | 2026-04-24 | KPTG-WTRAN-002005 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-25 | WilsonPD-TRANSMIT-000172 | SPARK-CRFI-KPG-000620 | Trade Partner | Drainage Isolation Valves | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-02 | KPTG-TRANSMIT-000612 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-25 | SMEPS-TRANSMIT-000161 | SPARK-CRFI-KPG-000574 | Trade Partner | D6 - Luminaire | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-25 | ARCH-TRANSMIT-000034 | NA | Consultant | 2026/03/25_Site Plan | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Issued For information only. To be updated in Aconex and ACC. No review required. (Outlook mail: RE: [External] FW: KPTG-DA-000287: DESIGN PROGRAM - KEY DATES ACNXREF<1uIuH6hZXcMNq8sdkUdulB>) |  | 2026-03-25 | KPTG-TRANSMIT-000117 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-26 | ARCH-TRANSMIT-000035 | NA | Consultant | 2026/03/25_Site Plan | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Issued For information only. To be updated in Aconex and ACC. No review required. (Outlook mail: RE: [External] FW: KPTG-DA-000287: DESIGN PROGRAM - KEY DATES ACNXREF<1uIuH6hZXcMNq8sdkUdulB>) |  | 2026-03-26 | KPTG-TRANSMIT-000119 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-25 | KALLIBRE-TRANSMIT-000003 | SPARK-CRFI-KPG-000623 | Trade Partner | Door Frame Shop Drawings Issued For Approval | 61 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 194 |  |  | Review terminated as per dylan's advise |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-25 | HDRAus-TRANSMIT-000442 | NA | Consultant | Updates to HV Room, Acoustic Screen & Link Bridge | 3 | 0 | 0 | NA | APPROVED | 2026-03-25 | WF-005002 | 2624 | 2026-03-27 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-015263 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-08 | PROLMC-TRANSMIT-000014 | NA | Trade Partner | Proline Shop Drawings (IFA Drawings) 8/12/25 | 7 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with the documenrt number | 2025-12-08 | 2025-12-08 | KPTG-DA-003785 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-25 | Tradetec-TRANSMIT-000402 | NA | Trade Partner | Tech Data - Spillceptor Sealant | 0 | 2 | 0 | NA | APPROVED | 2026-03-25 | WF-004991 | NA | 2026-04-02 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-014963 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-25 | D&E-TRANSMIT-000516 | NA | Trade Partner | SFN - IMI Balancing Valves Rev C - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-25 | WF-004986 | NA | 2026-04-15 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-016276 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-25 | D&E-TRANSMIT-000517 | NA | Trade Partner | Copper & Stainless Pipework - Issued for Approval | 0 | 2 | 0 | NA | APPROVED | 2026-03-25 | WF-004985 | NA | 2026-02-15 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-015977 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-25 | D&E-TRANSMIT-000518 | NA | Trade Partner | Carbon Steel Pipework - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-25 | WF-004984 | NA | 2026-02-15 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-015911 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-25 | SMEPS-TRANSMIT-000158 | SPARK-CRFI-KPG-000359 | Trade Partner | DB-01 (G) REV C Tech data / shop drawing for approval | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Delayed due to VPN issue |  | 2026-04-10 | KPTG-TRANSMIT-000627 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-25 | SMEPS-TRANSMIT-000159 | SPARK-CRFI-KPG-000359 | Trade Partner | DB-09 (B) REV C Tech data / shopdrawing for approval | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Delayed due to VPN issue |  | 2026-04-10 | KPTG-TRANSMIT-000628 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-25 | NXT-TRANSMIT-001449 | NA | Client | 100222-000583: M3 STAGE 2: EF, EG, EH, EI, EK, EM & EN Rooms - MDR's For Approval | 0 | 7 | 0 | NA | APPROVED | 2026-03-25 | WF-004992 | NA | 2026-03-30 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-25 | Civilex-TRANSMIT-000218 | NA | Trade Partner | Stage 2 - Landscape Transmittal - Rev C | 6 | 1 | 0 | NA | REJECTED | [5 empty] | Both specification and Shop Drawings are submitted in the same transmittal. Specification is named as Shop Drawing. |  | 2026-03-25 | KPTG-DA-005681 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-25 | RDSBIM-TRANSMIT-000038 | NA | Trade Partner | GREYSTAR GROUND FLOOR CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 590 | 2026-03-30 |  | Review voided as requested by RDS. RDSBIM-SUBADVICE-000031 -KPTG-SADV-001577 | 2026-03-26 | 2026-03-26 | KPTG-SADV-001577 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-08 | ARCST-TRANSMIT-000150 | NA | Trade Partner | Office Screens HD Bolts - IFC | 3 | 0 | 0 | NA | APPROVED |  | WF-003539 | NA | 2025-12-15 |  |  |  | 2026-01-05 | KPTG-TRANSMIT-011184 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-25 | KETE-TRANSMIT-000012: | NA | Trade Partner | Kete - Zone 02 Shop Drawing 1st Submission | 57 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 588 | 2026-03-31 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-001435 | Closed | 57 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-25 | POTTSENG-TRANSMIT-000015 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONE 5 LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 592 | 2026-03-31 |  |  | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-001178 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-25 | D&E-TRANSMIT-000523 | NA | Trade Partner | ITPs & Scripts - IFC | 0 | 7 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-03-25 | KPTG-TRANSMIT-014967 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-25 | Auspan-TRANSMIT-000168 | NA | Trade Partner | Re: WJ removal between 1B5015 and 1B5012 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC No review required - Register and distribute KPTG-TRANSMIT-001089 |  | 2026-03-25 | KPTG-TRANSMIT-001089 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-25 | INDS-TRANSMIT-000013 | NA | Trade Partner | Wet Fire - Schematic | 1 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 595 | 2026-04-01 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-001205 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-25 | POTTSENG-TRANSMIT-000016 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - WATER - BASEMENT 1 - ZONES 1-5 LAYOUTS | 5 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 597 | 2026-03-31 |  | Review void - KPTG-SADV-001569 | 2026-03-26 | 2026-03-26 | KPTG-SADV-001569 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-25 | Auspan-TRANSMIT-000169 | NA | Trade Partner | Re: Zone 3 RFi 35. Resubmit shop drawings for approval | 1 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 599 | 2026-04-01 |  | Rejected | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-001220 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-25 | KPTG-TRANSMIT-014924 | NA | Trade Partner | SP3 Ardon O&M Manual | 0 | 1 | 0 | NA | APPROVED | 2026-03-25 | WF-004993 | NA | 2026-03-27 |  | Terminated as directed by William Duffiled. Via KPTG-IntCorr-015361 | 2026-06-29 | 2026-06-29 | KPTG-IntCorr-015363 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-25 | KPTG-TRANSMIT-014925 | NA | Trade Partner | SP3 CGC - O&M Manual | 0 | 1 | 0 | NA | APPROVED | 2026-03-25 | WF-004994 | NA | 2026-03-27 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018403 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-25 | KPTG-TRANSMIT-014926 | NA | Trade Partner | SP3 ACG O&M Manual | 0 | 1 | 0 | NA | APPROVED | 2026-03-25 | WF-004996 | NA | 2026-03-27 |  |  | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-015377 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-08 | HDRAus-TRANSMIT-000333 | NA | Client | M3_S2_Building Permit Related items | 36 | 0 | 0 | NA | REJECTED | [5 empty] | Different status in a single transmittal | 2025-12-08 | 2025-12-08 | KPTG-DA-003784 | Closed | 36 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-25 | RDSBIM-TRANSMIT-000044 | NA | Trade Partner | 671CHP BASEMENT 4A TO BASEMENT 1 CORE WALL PLAN AND ELEVATIONS | 3 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 370 | 2026-03-31 |  | Review void as RDS requested to update the drawings. | 2026-04-10 | 2026-04-10 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-25 | KPTG-TRANSMIT-014928 | NA | Trade Partner | SP3 Vinage O&M Manual | 0 | 1 | 0 | NA | APPROVED | 2026-03-25 | WF-004997 | NA | 2026-03-27 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-25 | RBG-TRANSMIT-000058 | NA | Consultant | Latest Structural Drawings to Capture Core Wall Updates | 3 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 368 | 2026-03-31 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-000766 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-25 | RDSBIM-TRANSMIT-000045 | NA | Trade Partner | 671CHP BASEMENT 4A TO BASEMENT 1 CORE WALL ELEVATIONS | 2 | 0 | 0 | KPTG-IntCorr-000399 | APPROVED | 2026-03-25 | NA | NA |  |  | Drawings superseded on 13/04/26 |  | 2026-04-13 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-25 | crossfir-TRANSMIT-000004 | NA | Trade Partner | Wet Fire - Hydraulic Calculations | 0 | 4 | 0 | NA | APPROVED | 2026-03-25 | WF-000305 | NA | 2026-03-31 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-25 | KPTG-TRANSMIT-014972 | NA | Trade Partner | SP3 Empire O&M Manual | 0 | 1 | 0 | NA | APPROVED | 2026-03-25 | WF-004999 | NA | 2026-03-30 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-25 | ccair-TRANSMIT-000006 | NA | Trade Partner | B4 - B2 - Mechanical Ductwork & Pipework Layout - IFA | 3 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 372 | 2026-03-31 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-000761 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-25 | D&E-TRANSMIT-000508 | NA | Trade Partner | D&E O&M Manual DRAFT - Issued for review | 0 | 1 | 0 | NA | APPROVED | 2026-03-25 | WF-005001 | NA | 2026-03-30 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-015317 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-23 | ASV-TRANSMIT-000164 | NA | Trade Partner | D&E O&M Manual DRAFT - Issued for review | 0 | 2 | 0 | NA | APPROVED | 2026-03-25 | WF-004982 | NA | 2026-04-06 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-015468 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-25 | RDSBIM-TRANSMIT-000176 | NA | Trade Partner | LEVEL 03 PARTITION WALL PLAN | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per Kapitol advise IFC only for Distribution. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-02 | SMEPS-TRANSMIT-000087 | SPARK-CRFI-KPG-000201 | Trade Partner | Zone works Rev B. | 0 | 1 | 0 | NA | REJECTED | [8 empty] | KPTG-TRANSMIT-000363 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-25 | TATE_-IntCorr-000010 | NA | Trade Partner | MEL05 COLO 4 Ceiling Engineering Report | 0 | 1 | 0 | NA | APPROVED | 2026-03-25 | WF - 000300 | NA | 2026-04-01 |  | NA | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-000685 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-25 | KPTG-IntCorr-003359 | NA | Trade Partner | GENERATOR SIGNAGE SHOP DRAWINGS | 1 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 1439 | 2026-03-31 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-25 | DRLL-TRANSMIT-000072 | NA | Trade Partner | Battery Room Modules 1 & 2 Architectural Drawings IFC 02 | 11 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 1441 | 2026-03-31 |  |  | 2026-04-10 | 2026-04-13 | KPTG-TRANSMIT-002868 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-25 | DRLL-TRANSMIT-000073 | NA | Trade Partner | Battery Room Modules 1 & 2 Structural Drawings ASB A | 6 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 1443 | 2026-03-31 |  |  | 2026-04-29 | 2026-04-30 | KPTG-TRANSMIT-002889 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-25 | DRLL-TRANSMIT-000074 | NA | Trade Partner | Battery Room Modules 1 & 2 Electrical Drawings ASB A | 8 | 0 | 0 | NA | APPROVED | 2026-03-26 | NA | 1445 | 2026-04-01 |  | Due to VPN issue one day delay for closed out | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-002856 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-25 | DRLL-TRANSMIT-000075 | NA | Trade Partner | Battery Room Modules 1 & 2 Mechanical Drawings ASB A | 10 | 0 | 0 | NA | APPROVED | 2026-03-26 | NA | 1448 | 2026-04-01 |  | Due to VPN issue one day delay for closed out | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-002852 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-25 | DRLL-TRANSMIT-000076 | NA | Trade Partner | Battery Room Modules 1 & 2 Seismic Drawings ASB A | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-03-26 | KPTG-IntCorr-003375 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-25 | DRLL-TRANSMIT-000077 | NA | Trade Partner | Battery Room Modules 1 & 2 Switchboard Power and Lighting Shop Drawings ASB A | 2 | 0 | 0 | NA | APPROVED | 2026-03-26 | NA | 1450 | 2026-04-01 |  | Due to VPN issue one day delay for closed out | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-002848 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-25 | PARR-TRANSMIT-000144 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - TDP - IFC | 0 | 19 | 0 | NA | REJECTED | [5 empty] | only for information boader team |  | 2026-03-25 | KPTG-TRANSMIT-014962 | Closed | 19 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-25 | D&E-TRANSMIT-000519 | NA | Trade Partner | ISSUED FOR APPROVAL - LEVEL 1 - MECHANICAL DUCT LAYOUT - ZONE 1 & 2 | 2 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 2618 | 2026-04-04 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-015721 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-08 | Stowe-A-TRANSMIT-000410 | NA | Trade Partner | Stowe - Tech Data Submission - GLP DB (4 off) | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | TD with IFC status | 2025-12-08 | 2025-12-08 | KPTG-TRANSMIT-010711 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-24 | RDSBIM-TRANSMIT-000122 | NA | Trade Partner | MLCSPR ¦ AQUATIC CENTER LEVEL 01 INTERNAL SCREED LAYOUT | 2 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 470 | 2026-04-01 |  |  | 2026-03-30 | 2026-03-30 | KPTG-SADV-003996 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-25 | D&E-TRANSMIT-000522 | NA | Trade Partner | Leak Detection - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-25 | WF-004990 | NA | 2026-04-15 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-015623 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-25 | D&E-TRANSMIT-000524 | NA | Trade Partner | MCC Schedules IFA Rev F | 0 | 1 | 0 | NA | APPROVED | 2026-03-25 | WF-004998 | NA | 2026-04-16 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-016010 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-25 | ARCST-TRANSMIT-000236 | NA | Trade Partner | C2 East Lower Gantry - Issued for Approval | 201 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-03-25 |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-25 | Appselec-TRANSMIT-000037 | NA | Trade Partner | Distribution Board Shop Drawings For Approval | 3 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-03-25 | KPTG-IntCorr-000187 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-25 | Appselec-TRANSMIT-000038 | NA | Trade Partner | Control Cabling Technical Data | 0 | 1 | 0 | NA | APPROVED | 2026-03-25 | WF-000091 | NA | 2026-03-31 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-000460 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-25 | Appselec-TRANSMIT-000039 | NA | Trade Partner | Distribution Board Shop Drawings No Longer In Use | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | documents are not longer in use |  | 2026-03-25 | KPTG-TRANSMIT-000204 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-25 | Appselec-TRANSMIT-000040 | NA | Trade Partner | DB Shop Drawings For Approval | 3 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-03-25 | KPTG-SADV-000201 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-08 | D&E-TRANSMIT-000306 | NA | Trade Partner | M3 HS1 Office fit out Mechanical Drawings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with revision and document number | 2025-12-08 | 2025-12-08 | KPTG-DA-003783 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-25 | Entire M-TRANSMIT-000017 | NA | Trade Partner | Mechanical shop drawings IFC | 12 | 0 | 0 | NA | APPROVED | 2026-03-25 | WF-000092 | NA | 2026-03-30 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-000281 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | ASV-TRANSMIT-000033 | NA | Trade Partner | Stage 9 internal Hydraulic Services | 1 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 528 | 2026-03-31 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-001959 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | ASV-TRANSMIT-000034 | NA | Trade Partner | Stage 10 Internal Hydraulic Services | 1 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 530 | 2026-03-31 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-002035 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-19 | Appselec-TRANSMIT-000031 | NA | Trade Partner | COLO 4 & 5 - Electrical Drawings - Issued for Approval | 23 | 0 | 0 | NA | APPROVED | 2026-03-20 | WF-000080 | NA | 2026-03-25 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-000201 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | ASV-TRANSMIT-000035 | NA | Trade Partner | Stage 9-10 External Drainage, Water & Fire services | 1 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 531 | 2026-03-31 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-001800 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | ASV-TRANSMIT-000036 | NA | Trade Partner | Stage 11 External Drainage, Water & Fire Services | 1 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 533 | 2026-03-31 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-001918 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | ASV-TRANSMIT-000037 | NA | Trade Partner | Civil Stormwater Site Plan | 1 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 534 | 2026-03-31 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-001841 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | ASV-TRANSMIT-000038 | NA | Trade Partner | Updated Sewer TD - HDPE | 0 | 1 | 0 | NA | APPROVED | 2026-03-25 | WF-000389 | NA | 2026-04-03 |  | Workflow terminated as requested by Project coordinator |  | 2026-03-26 | KPTG-IntCorr-000605 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | ASV-TRANSMIT-000039 | NA | Trade Partner | Trench grate TD with Commentary for Flow rate | 0 | 1 | 0 | NA | APPROVED | 2026-03-25 | WF-000395 | NA | 2026-04-03 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-002208 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | Tradetec-TRANSMIT-000081 | NA | Trade Partner | Revised HVP4 Pit Shop Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 546 | 2026-03-31 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-001762 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-08 | Stowe-A-TRANSMIT-000409 | NA | Trade Partner | Stowe - Tech Data Submission - External Light Poles | 0 | 1 | 0 | NA | APPROVED | 2025-12-08 | WF-003535 | NA | 2025-12-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | VIA Arch-TRANSMIT-000076 | NA | Consultant | Stage 9 Concrete Profile Plans - Ground & Level 1 | 2 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 555 | 2026-03-30 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-001792 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | VIA Arch-TRANSMIT-000077 | NA | Consultant | M2 S9 Ground & Level 1 Structural Steel Set-out Plans | 2 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 556 | 2026-03-30 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-002049 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | WSP ANZ-TRANSMIT-000055 | NA | Consultant | WSP 70% Design Development issue for Building Permit - Hydraulic | 65 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 544 | 2026-03-30 |  | Actual receipt date 20/3 | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-001897 | Closed | 65 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | WSP ANZ-TRANSMIT-000055 | NA | Consultant | WSP 70% Design Development issue for Building Permit - Mechanical | 46 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 552 | 2026-03-30 |  | Actual receipt date 20/3 | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-001897 | Closed | 46 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | WSP ANZ-TRANSMIT-000055 | NA | Consultant | WSP 70% Design Development issue for Building Permit - Vertical Transport | 9 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 550 | 2026-03-30 |  | Actual receipt date 20/3 | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-001897 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-25 | KPTG-IntCorr-001094 | NA | Consultant | Specialist Lighting - GF Redesign | 16 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | SL Drawings- register updated and forwarded to all parties |  | 2026-03-25 | NA | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-25 | WSP ANZ-TRANSMIT-000004 | NA | Consultant | WSP Drawings-Audio Visual | 5 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 14 | 2026-04-01 |  | Voided as advised by Renee |  | 2026-04-02 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-26 | INSULPAK-TRANSMIT-000017 | NA | Trade Partner | Re: HFF MSSB Drawings Issued For Construction | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Ref No. is missing |  |  | DRAFT-009514 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-25 | WSP ANZ-TRANSMIT-000004 | NA | Consultant | WSP Drawings-Electrical Drawings | 26 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 15 | 2026-04-01 |  | Voided as advised by Renee |  | 2026-04-02 | NA | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-26 | WPD-TRANSMIT-000076 | NA | Trade Partner | Updated Ground Floor Zone 1 Proposed Pressure Layout | 1 | 0 | 0 | NA | APPROVED | 2026-03-26 | NA | 366 | 2026-03-30 |  |  | 2026-03-30 | 2026-03-30 | KAPITOL-TRANSMIT-001268 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-01 | ADP-TRANSMIT-000139 | NA | Consultant | MEL741 - Stage 4 Services IFT Issue | 227 | 0 | 0 |  | APPROVED |  | NA | NA |  |  | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-08 | D&E-TRANSMIT-000305 | NA | Trade Partner | NXDC M3 S2 - ISSUED FOR CONSTRUCTION - Mechanical Services - Ground Builders Works | 2 | 0 | 0 | NA | APPROVED | 2025-12-08 | NA | 3459 | 2025-12-15 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-25 | WSP ANZ-TRANSMIT-000004 | NA | Consultant | WSP Drawings Fire Protection Drawings | 11 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 16 | 2026-04-01 |  | Voided as advised by Renee |  | 2026-04-02 | NA | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-26 | KPTG-WTRAN-009294 |  | Trade Partner | DOOR HOOD SD | 0 | 1 | 0 | NA | APPROVED | 2026-03-26 | WF-005005 | NA |  |  | The WF has been generated as requested by Sam S. |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-25 | WSP ANZ-TRANSMIT-000004 | NA | Consultant | WSP Drawings- Hydraulic Services drawings | 19 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 17 | 2026-04-01 |  | Voided as advised by Renee |  | 2026-04-02 | NA | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-25 | WSP ANZ-TRANSMIT-000004 | NA | Consultant | WSP Mechanical Drawings | 16 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 18 | 2026-04-01 |  | Voided as advised by Renee |  | 2026-04-02 | NA | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-24 | NA | NA | Consultant | Specialist Lighting Drawings | 10 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 10 | 2026-03-31 |  | Voided as advised by Renee |  | 2026-04-02 | NA | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-24 | NA | NA | Consultant | Structural Drawings | 18 | 0 | 0 | NA | APPROVED | 2026-03-24 | NA | 11 | 2026-03-31 |  | Voided-as advised by Renee on Team meeting 01-04-2026 |  | 2026-04-01 | NA | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-26 | Auspan-TRANSMIT-000008 | NA | Trade Partner | Update dowel layout. | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue in Title Block, no status inside the drawing. |  | 2026-03-26 | KPTG-SADV-000060 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-24 | NA | NA | Consultant | LUMINAIRE SCHEDULE | 0 | 1 | 0 | NA | APPROVED | 2026-03-24 | WF-000005 | NA | 2026-03-31 |  | Voided as advised by Renee |  | 2026-04-02 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-24 | NA | NA | Consultant | LIGHTING SPECIFICATION | 0 | 1 | 0 | NA | APPROVED | 2026-03-24 | WF-000006 | NA | 2026-03-31 |  | Voided as advised by Renee |  | 2026-04-02 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-24 | NA | NA | Consultant | LIGHTING CONTROL FUNCTIONALITY BRIEF | 0 | 1 | 0 | NA | APPROVED | 2026-03-24 | WF-000007 | NA | 2026-03-31 |  | Voided as advised by Renee |  | 2026-04-02 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-24 | NA | NA | Consultant | Geotechnical Document | 0 | 1 | 0 | NA | APPROVED | 2026-03-25 | WF-000008 | NA | 2026-03-31 |  | Terminated - As advised by Renee, the latest document received under ENF-CADV-000008 is to be reviewed |  | 2026-04-16 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-25 | WSP ANZ-TRANSMIT-000004 | NA | Consultant | WSP-MECHANICAL SPECIFICATION | 0 | 1 | 0 | NA | APPROVED | 2026-03-26 | WF-000018 | NA | 2026-04-02 |  | Distribution not required as this is internal review only as advised by Renee | 2026-03-30 | 2026-04-01 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-25 | WSP ANZ-TRANSMIT-000004 | NA | Consultant | WSP-HYDRAULIC SPECIFICATION | 0 | 1 | 0 | NA | APPROVED | 2026-03-26 | WF-000017 | NA | 2026-04-02 |  | Distribution not required as this is internal review only as advised by Renee | 2026-03-30 | 2026-04-01 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-25 | WSP ANZ-TRANSMIT-000004 | NA | Consultant | WSP-ELECTRICAL SPECIFICATION | 0 | 1 | 0 | NA | APPROVED | 2026-03-26 | WF-000016 | NA | 2026-04-02 |  | Voided as advised by Renee |  | 2026-04-02 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-20 | DS-TRANSMIT-000103 | NA | Trade Partner | Roof Drainage and Penetrations - Issued for Construction | 6 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 2587 | 2026-03-25 |  |  | 2026-03-26 | 2026-03-25 | KPTG-TRANSMIT-014963 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-25 | WSP ANZ-TRANSMIT-000004 | NA | Consultant | WSP-AUDIO VISUAL SPECIFICATION | 0 | 1 | 0 | NA | APPROVED | 2026-03-26 | WF-000015 | NA | 2026-04-02 |  | Distribution not required as this is internal review only as advised by Renee | 2026-03-30 | 2026-04-01 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-26 | HDRAus-TRANSMIT-000441 | NA | Consultant | Fwd: M3 Stage 4 - Document upload - Door hardware schedule | 0 | 1 | 0 | NA | APPROVED | 2026-03-26 | NA | 2626 | 2026-03-30 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-015233 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-26 | SMEPS-TRANSMIT-000016 | NA | Trade Partner | Earth Pit Technical Data | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Need to revise KPTG-SADV-002114 |  | 2026-03-26 | KPTG-SADV-002114 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | Auspan-TRANSMIT-000148 | NA | Trade Partner | Shop Drawing of Equal Angle | 1 | 0 | 0 | NA | APPROVED | 2026-03-25 | WF-000370 | NA | 2026-03-28 |  |  | 2026-03-25 | 2026-03-25 | KPTG-TRANSMIT-001722 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | Auspan-TRANSMIT-000149 | NA | Trade Partner | Shop Drawings - Stage 9 GF and L1 | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. |  | 2026-03-25 | NA | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-08 | Tradetec-TRANSMIT-000287 | NA | Trade Partner | Stage 2 - South East - Shop Drawings IFA - CP11, CP13, LVP06 | 3 | 0 | 0 | NA | APPROVED | 2025-12-09 | NA | 3470 | 2025-12-15 |  |  |  | 2025-12-15 | KPTG-TRANSMIT-010929 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | Auspan-TRANSMIT-000150 | NA | Trade Partner | Remaining Shop Drawings - Stage 9 GF and L1 | 31 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings No review required |  | 2026-03-25 | NA | Closed | 31 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | Auspan-TRANSMIT-000151 | NA | Trade Partner | Precast IFC shop drawings. Stage 9. 1PC008 and 1PC009. | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings No review required |  | 2026-03-25 | KPTG-TRANSMIT-001727 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-25 | SMEPS-TRANSMIT-000159 | NA | Trade Partner | SME AHU Isolators | 0 | 1 | 0 | NA | APPROVED | 2026-03-25 | WF - 000298 | NA | 2026-03-30 |  | WF Terminated |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | Auspan-TRANSMIT-000153 | NA | Trade Partner | Precast shop drawings for construction. Stage 9. | 15 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings No review required |  | 2026-03-25 | NA | Closed | 15 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | Auspan-TRANSMIT-000154 | NA | Trade Partner | Precast shop drawings for approval. Stage 9. | 22 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Not reviewed, updated register and ACC |  | 2026-03-25 | NA | Closed | 22 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-26 | HEXA-TRANSMIT-000007 | NA | Trade Partner | ISSUED FOR APPROVAL - CHW & SFN SCHEMATIC | 8 | 0 | 0 | NA | APPROVED | 2026-03-26 | NA | 367 | 2026-04-01 |  |  | 2026-03-30 | 2026-03-30 | DRAFT-009566 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | Auspan-TRANSMIT-000156 | NA | Trade Partner | Precast shop drawings for construction. | 19 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings no review required |  | 2026-03-25 | NA | Closed | 19 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-26 | SMEPS-TRANSMIT-000162 | NA | Trade Partner | Re: Shop Drawings - General (Legend, Plans) | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Error in Document status |  |  | KPTG-TRANSMIT-000601 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | Auspan-TRANSMIT-000157 | NA | Trade Partner | Resubmit precast shop drawings for approval. | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required, updated register and ACC |  | 2026-03-25 | NA | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-08 | Stowe-A-TRANSMIT-000411 | NA | Trade Partner | Stowe - Tech Data Submission - GLP DBs (11 off) | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2025-12-08 | 2025-12-08 | KPTG-TRANSMIT-010715 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-26 | SMPS-TRANSMIT-000105 | NA | Trade Partner | Hanwha: Power Pack B08 - Electrical Shop Drawings - IFA-A | 5 | 0 | 0 | NA | APPROVED | 2026-03-26 | NA | 369 | 2026-04-01 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | Auspan-TRANSMIT-000159 | NA | Trade Partner | Precast shop drawings for construction. Stage 9 ground floor. | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required |  | 2026-03-25 | NA | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-26 | Auscool-TRANSMIT-000089 | NA | Trade Partner | PLANT MECHANICAL BUILDERS WORKS | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-SADV-003574-As per the direction Mark we don't take any action these drawings, only update register. |  | 2026-03-26 | KPTG-SADV-003574 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | Auspan-TRANSMIT-000160 | NA | Trade Partner | Update precast dowel layouts. Stage 9. | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required |  | 2026-03-25 | KPTG-TRANSMIT-001739 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-25 | Auspan-TRANSMIT-000161 | NA | Trade Partner | Precast shop drawings for construction. Stage 9 ground floor. | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required |  | 2026-03-25 | NA | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-26 | SMEPS-TRANSMIT-000163 | NA | Trade Partner | Updated Legend of Symbols Drawings | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Error in drawing status |  | 2026-03-26 | KPTG-TRANSMIT-000602 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-26 | SMEPS-TRANSMIT-000165 | SPARK-CRFI-KPG-000235 | Trade Partner | Re: Shop Drawings - General (Legend, Plans) | 3 | 0 | 0 | NA | APPROVED | 2026-03-26 |  | 195 | 2026-04-02 |  |  | 2026-04-01 | 2026-04-24 | KPTG-TRANSMIT-000699 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-25 | Schindle-TRANSMIT-000011 | NA | Trade Partner | Schindler - Landing Fixture and COP drawings IFC | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Error in revision |  |  | KPTG-TRANSMIT-000600 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-26 | INSULPAK-TRANSMIT-000018 | NA | Trade Partner | HFF MSSB details Added | 1 | 0 | 0 | NA | APPROVED | 2026-03-26 | NA | 370 | 2026-03-29 |  |  | 2026-03-30 | 2026-03-30 | DRAFT-009559 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-11 | HDRAus-TRANSMIT-000340 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 9 | 0 | 0 | NA | APPROVED | 2025-12-11 | NA | 1638 | 2025-12-15 |  |  |  | 2025-12-16 | KPTG-TRANSMIT-010970 | Closed | 9 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-26 | Entire M-TRANSMIT-000024 | NA | Trade Partner | Rubber Isolation Mounts Technical Data Rev A IFA | 0 | 1 | 0 | NA | APPROVED | 2026-03-26 | WF - 000302 | NA | 2026-03-31 |  | NA | 2026-03-30 | 2026-03-31 | KPTG-TRANSMIT-000659 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-26 | Entire M-TRANSMIT-000025 | NA | Trade Partner | Drain Pipe Insulation IFC | 0 | 1 | 0 | NA | APPROVED | 2026-03-26 | WF - 000305 | NA | 2026-03-31 |  | NA | 2026-03-26 | 2026-03-27 | KPTG-TRANSMIT-000628 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-26 | Entire M-TRANSMIT-000026 | NA | Trade Partner | Hangers Fixings Rev 1 IFC | 0 | 1 | 0 | NA | APPROVED | 2026-03-26 | WF - 000304 | NA | 2026-03-31 |  | NA | 2026-03-26 | 2026-03-29 | KPTG-TRANSMIT-000638 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-26 | SMEPS-TRANSMIT-000164 |  | Trade Partner | Updated Distribution Board Schematics | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Error in revision |  | 2026-03-26 | KPTG-TRANSMIT-000603 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-26 | SKS Tech-TRANSMIT-000175 | NA | Trade Partner | for APPROVAL submittals | 0 | 1 | 0 | KPTG-IntCorr-001100 | APPROVED | 2026-03-26 | WF-000959 | NA | 2026-04-02 |  | Clarification from harry | 2026-04-14 | 2026-04-14 | KPTG-WTRAN-001936 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-26 | VAE-Grp-TRANSMIT-000144 | NA | Trade Partner | MECH - TECH SUBS & SCHEDS - VRF & MCC SCHEDULE | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  | Register updated |  | 2026-03-26 | KPTG-TRANSMIT-003280 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-26 | JCBa-TRANSMIT-000077 | NA | Consultant | STRUCTURAL SETOUT PLANS FIRST FLOOR: ALL ZONES | 5 | 0 | 0 | NA | APPROVED | 2026-03-26 | NA | 603 | 2026-04-02 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-001135 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-26 | JCBa-TRANSMIT-000076 | NA | Consultant | Transmittal – Updated Drawings A-4121 (Stair 2 + Goods Lift | 2 | 0 | 0 | NA | APPROVED | 2026-03-26 | NA | 601 | 2026-04-02 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-001270 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-26 | Auspan-TRANSMIT-000170 | NA | Trade Partner | Precast shop drawings for approval. Level 1 zone 4, 5. | 76 | 0 | 0 | NA | APPROVED | 2026-03-26 | NA | 607 | 2026-04-02 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-001239 | Closed | 76 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-09 | Tradetec-TRANSMIT-000289 | NA | Trade Partner | CP16 IFC | 1 | 0 | 0 | NA | APPROVED | 2025-12-09 | NA | 3462 | 2025-12-11 |  |  | 2025-12-09 |  | KPTG-TRANSMIT-010808 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-26 | INDS-TRANSMIT-000014 | NA | Trade Partner | L1 to L7 Floor Penetration Layout | 6 | 0 | 0 | NA | APPROVED | 2026-03-26 | NA | 605 | 2026-03-26 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-001221 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-26 | Auspan-TRANSMIT-000172 | NA | Trade Partner | :Re: Nucon - Bricksnap - Irregular Brick Coursing on Shop Drawings Query | 4 | 0 | 0 | KPTG-IntCorr-000419 | APPROVED |  | NA | NA |  |  | Waiting for Kapitol Advise - KPTG-IntCorr-000419 IFC No review required - Register and distribute- KPTG-TRANSMIT-001123 |  | 2026-03-30 | KPTG-TRANSMIT-001123 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-26 | Auspan-TRANSMIT-000173 | NA | Trade Partner | Precast marking plan basement 1. Zone 4,5 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC No review required - Register and distribute KPTG-TRANSMIT-001113 |  | 2026-03-26 | KPTG-TRANSMIT-001113 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-26 | Auspan-TRANSMIT-000171 | NA | Trade Partner | : Precast shop drawings for construction | 18 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC No review required - Register and distribute KPTG-TRANSMIT-001111 |  | 2026-03-26 | KPTG-TRANSMIT-001111 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-26 | B Smart-TRANSMIT-000067 | NA | Consultant | : Schedules IFC | 0 | 4 | 0 | NA | APPROVED | 2026-03-26 | WF-000307 | NA | 2026-04-01 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-000781 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-26 | PFP PL-TRANSMIT-000079 | NA | Trade Partner | Stage 2 As-Installed Drawings | 9 | 0 | 0 | NA | REJECTED | [5 empty] | M3-FIP-PFP-SDRG-B-0201-321, it appears to be blank. |  | 2026-03-26 | KPTG-DA-005710 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-26 | Civilex-TRANSMIT-000219 | NA | Trade Partner | Stage 2 - Landscape Transmittal - Rev C- Updated Naming | 0 | 1 | 0 | NA | APPROVED | 2026-03-26 | WF-005024 | NA | 2026-04-02 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-019783 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-26 | D&E-TRANSMIT-000525 | NA | Trade Partner | MaxCool FD - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-26 | WF-005007 | NA | 2026-04-09 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-015955 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-26 | Tradetec-TRANSMIT-000403 | NA | Trade Partner | IFC Drawings - CP11, CP17 | 2 | 0 | 0 | NA | APPROVED | 2026-03-26 | NA | 4022 | 2026-03-30 |  |  | 2026-03-26 | 2026-03-26 | KPTG-TRANSMIT-015045 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-26 | Stowe-A-TRANSMIT-000530 | NA | Trade Partner | Stowe - Tech Data Submission - Earthing Rebar Clamp | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-26 | KPTG-TRANSMIT-014997 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-09 | D&E-TRANSMIT-000307 | NA | Trade Partner | HS1 Office mechanical IFA drawing URGENT | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Sent back to originator |  | 2025-12-09 | KPTG-DA-003798 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-26 | ADP-TRANSMIT-000286 | NA | Consultant | ADP MEL4561 - HV Room Update (Hyd Drawing) | 1 | 0 | 0 | NA | APPROVED | 2026-03-26 | NA | 4024 | 2026-03-30 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-015159 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-26 | NXT-TRANSMIT-001454 | NA | Client | 100222-000584 - MDR'S & IOM'S ISSUED FOR APPROVAL | 0 | 15 | 0 | NA | APPROVED | 2026-03-26 | WF-005020 | NA | 2026-03-30 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-26 | Civilex-TRANSMIT-000220 | NA | Trade Partner | Stage 2 - Landscape Transmittal - Rev C - Drawing no.7-8-9 | 0 | 3 | 0 | NA | REJECTED | [5 empty] | For the specifications seems drawing inside the document and it is not mentioned the document number and revision number inside the document. |  | 2026-03-26 | KPTG-DA-005709 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-26 | Diadem-TRANSMIT-000025 | NA | Trade Partner | Wayfinding Signage IFT-03 | 64 | 0 | 0 | NA | REJECTED | [5 empty] | Document Number M3-WAY-DDM-DRG-B-0201-1010 has been repeated twice. The document attached to M3-WAY-DDM-DRG-B-0201-1088 is incorrect. The revisions for some docs are different inside the document and in the register. The Document Number of M3-WAY-DDM-DRG-B-0201-1046 is incorrect in the register. Some of the drawings do not fit inside the box. |  | 2026-03-26 | KPTG-DA-005711 | Closed | 64 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-26 | NXT-TRANSMIT-001455 | NA | Client | 100222-000585: EK, EL, EM & EN Rooms - IOM for Approval | 0 | 4 | 0 | NA | APPROVED | 2026-03-26 | WF-005021 | NA | 2026-03-30 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-26 | NXT-TRANSMIT-001456 | NA | Client | 100222-000586: EO & EP Rooms - IOM's for Approval | 0 | 2 | 0 | NA | APPROVED | 2026-03-26 | WF-005022 | NA | 2026-03-30 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-26 | LANSA-TRANSMIT-000018 | NA | Trade Partner | Hyd As Builts | 8 | 0 | 0 | NA | REJECTED | [5 empty] | As built rev not correct format |  | 2026-03-26 | KPTG-TRANSMIT-002793 | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-26 | Schindle-TRANSMIT-000022 | NA | Trade Partner | Lift GL1 - Asbuilts | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with title, status and document number |  | 2026-03-26 | KPTG-DA-005712 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-26 | Schindle-TRANSMIT-000023 | NA | Trade Partner | GL2 - Asbuilts | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document number revision and status |  | 2026-03-26 | KPTG-DA-005713 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-26 | D&E-TRANSMIT-000352 | NA | Trade Partner | Mechanical Shop drawings As installed | 32 | 0 | 0 | NA | REJECTED | [5 empty] | REV not correct |  | 2026-03-26 | KPTG-TRANSMIT-002792 | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-09 | HDRAus-TRANSMIT-000335 | NA | Consultant | M3_S2_S4 - SPANDREL WALL DETAILS | 2 | 0 | 0 | NA | APPROVED |  | NA | 3464 |  |  | updated drawings received on HDRAus-TRANSMIT-000336. So void the ACC review |  |  | NA | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-26 | ZIA-TRANSMIT-000080 | NA | Trade Partner | M3S1DH78 - Zi-Argus - Practical Completion Documentation | 18 | 0 | 0 | NA | APPROVED | 2026-03-26 | NA | 1452 | 2026-04-01 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-25 | Nilsen3-TRANSMIT-000076 | NA | Trade Partner | Nilsen IFC Sample Submission | 0 | 23 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Samples, distributed to client, consultant, trade partner |  | 2026-03-25 | KPTG-TRANSMIT-015021 | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-25 | RDSBIM-TRANSMIT-000251 | NA | Trade Partner | NXM3S4 GROUND FLOOR & LEVEL 01 SPEED PANEL LAYOUT ZONE C3 | 1 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 2628 | 2026-03-30 |  |  | 2026-03-25 | 2026-03-26 | KPTG-TRANSMIT-015016 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-25 | Nilsen3-TRANSMIT-000076 | NA | Trade Partner | Nilsen IFC Sample Submission | 0 | 2 | 0 | NA | REJECTED | [5 empty] | send back to originator due to partial submission |  | 2026-03-25 | KPTG-TRANSMIT-015010 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-26 | Nilsen3-TRANSMIT-000077 | NA | Trade Partner | LV Earth Cable Sample | 0 | 1 | 0 | NA | APPROVED | 2026-03-25 | WF-005012 | NA | 2026-04-16 |  | The WF has been terminated as requested by Damian |  | 2026-03-26 | KPTG-SADV-004472 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-26 | Nilsen3-TRANSMIT-000076 | NA | Trade Partner | Nilsen IFC Sample Submission | 0 | 23 | 0 | NA | REJECTED | [5 empty] | Incorrect document number |  | 2026-03-26 | KPTG-TRANSMIT-014999 | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-26 | Schindle-TRANSMIT-000012 | NA | Trade Partner | IFA - Schindler HPI/LOP Drawings | 2 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-03-27 | KPTG-SADV-003803 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-26 | WSP ANZ-TRANSMIT-000055 | NA | Consultant | WSP 70% Design Development issue for Building Permit - Telecom | 49 | 0 | 0 | NA | APPROVED | 2026-03-26 | NA | 565 | 2026-03-31 |  | Actual receipt date 20/3 | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-001897 | Closed | 49 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-25 | RDSBIM-TRANSMIT-000123 | NA | Trade Partner | MLC ¦ AQUATIC CENTER LEVEL 01 INTERNAL FITOUT ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-03-26 | NA | 472 | 2026-04-02 |  |  | 2026-03-31 | 2026-03-31 | KPTG-SADV-003998 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-25 | RDSBIM-TRANSMIT-000124 | NA | Trade Partner | MLCSPR ¦ CHAPEL CARPARK LANDSCAPE KEY PLAN AND SECTION | 4 | 0 | 0 | NA | APPROVED | 2026-03-26 | NA | 473 | 2026-04-02 |  |  | 2026-03-31 | 2026-03-31 | KPTG-SADV-003999 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-11 | HDRAus-TRANSMIT-000341 | NA | Consultant | M3 Stage 4 - Chiller room drawings, details, for information | 10 | 0 | 0 | NA | REJECTED | [5 empty] | For information only-HDRAus-TRANSMIT-000341 n the attached document M3-ARC-HDR-DRG-C-0400-4953 Does not seems same drawing number and revision in inside of the drawing |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-26 | KPTG-TRANSMIT-002625 | NA | Client | FFS01 Student chair | 0 | 1 | 0 | NA | APPROVED | 2026-03-26 | WF-000899 | NA | 2026-04-01 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-002768 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-26 | KPTG-IntCorr-006366 | NA | Client | FFT01 SPD | 1 | 0 | 0 | NA | APPROVED | 2026-03-26 | NA | 475 | 2026-03-31 |  |  | 2026-03-30 | 2026-03-30 | KPTG-SADV-004023 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-26 | Auscool-TRANSMIT-000089 | NA | Trade Partner | PLANT MECHANICAL BUILDERS WORKS | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per the direction, we have updated to document register and transmitted to all parties. |  | 2026-03-26 | KPTG-SADV-003574 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-25 | RDSBIM-TRANSMIT-000172 | NA | Trade Partner | LINDRUM ¦ LEVEL 01 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | REJECTED | [5 empty] | submitted drawing is not current, requested to resubmit:KPTG-IntCorr-000829 |  | 2026-03-26 | KPTG-IntCorr-000829 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-26 | RDSBIM-TRANSMIT-000173 | NA | Trade Partner | LINDRUM ¦ CPP ¦ L-01 ¦ IFC | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC DRAWING, TRANSMITTED TO ALL PARTIES. |  | 2026-03-26 | KPTG-SADV-003575 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-26 | RDSBIM-TRANSMIT-000177 | NA | Trade Partner | LEVEL 00 PARTITION WALL PLAN | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - As advised by Kapitol IFC only for distribution. |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-26 | RDSBIM-TRANSMIT-000174 | NA | Trade Partner | LINDRUM ¦ LEVEL 01 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | REJECTED | [5 empty] | This transmittal is a same copy of RDSBIM-TRANSMIT-000173 |  | 2026-03-26 | KPTG-IntCorr-000832 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-26 | RDSBIM-TRANSMIT-000003 | NA | Trade Partner | MEL11C45 ¦ LEVEL 01 COLO 5A AREA RCP LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-03-26 | WF-000121 | NA | 2026-04-01 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-000308 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-26 | SIL-TRANSMIT-000032 | NA | Trade Partner | MEL11-SIL-L1.FAT.COLO5.LBT01.ENCL - Submission | 0 | 1 | 0 | NA | APPROVED | 2026-03-26 | WF - 000308 | NA | 2026-03-31 |  | NA | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-000635 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-26 | Appselec-TRANSMIT-000041 | NA | Trade Partner | COLO 4 & 5 - Comms Drawings Issued for Approval (Grid, MOR to IDFs, EMPS/BAS) | 14 | 0 | 0 | NA | APPROVED | 2026-03-26 | WF-000095 | NA | 2026-04-01 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-000461 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-11 | D&E-TRANSMIT-000287 | NA | Trade Partner | MSSB HOOD, DRIP TRAY & PIPE HEADER SPOOL DETAILS | 1 | 0 | 0 | NA | APPROVED | 2025-12-11 | NA | 1311 | 2025-12-19 |  |  | 2026-01-05 | 2026-01-05 | KPTG-TRANSMIT-002255 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-26 | TATE_-TRANSMIT-000006 | NA | Trade Partner | TATE - TECH DATA Submissions | 0 | 3 | 0 | NA | REJECTED | [5 empty] | DOCUMENT NUMBER OF TECH DATA ARE INCORRECT, REQUESTED TO RESUBMIT:KPTG-IntCorr-000203 |  | 2026-03-26 | KPTG-IntCorr-000203 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-26 | Appselec-TRANSMIT-000042 | NA | Trade Partner | Communications Basket Tech Data For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-26 | WF-000094 | NA | 2026-04-01 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-000331 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-26 | SMEPS-TRANSMIT-000017 | NA | Trade Partner | STAGE 9-11 Electrical/Telecoms Zone drawings (IFC) | 12 | 0 | 0 | NA | REJECTED | [5 empty] | Need to revise KPTG-SADV-002148 |  | 2026-03-26 | KPTG-SADV-002148 | Closed | 12 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-26 | SIL-TRANSMIT-000026 | NA | Trade Partner | L1 FAT Script-MEL11-COLO5-LBT01 Outdoor Enclosure | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | THIS IS FOR INFORMATION. JUST TRANSMITTED TO TRADE PARTNERS:KPTG-TRANSMIT-000217 |  | 2026-03-26 | KPTG-TRANSMIT-000217 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-26 | ASV-TRANSMIT-000040 | NA | Trade Partner | Alternative HDPE Pipework | 0 | 1 | 0 | NA | APPROVED | 2026-03-26 | WF-000398 | NA | 2026-04-06 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-002172 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-26 | VIA Arch-TRANSMIT-000078 | NA | Consultant | S9 Stair 01 & S10 Stair 08 | 3 | 0 | 0 | KPTG-IntCorr-000608 | APPROVED | 2026-03-27 | NA | 569 | 2026-04-01 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-001796 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-26 | Tradetec-TRANSMIT-000083 | NA | Trade Partner | Epoxy and Grouting Material Technical Data Submission | 0 | 2 | 0 | KPTG-IntCorr-000607 | APPROVED |  | WF-000404 | NA | 2026-04-03 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-004918 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-26 | Auspan-TRANSMIT-000162 | NA | Trade Partner | Precast shop drawings for construction. Stage 9 ground floor. | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings No review required |  | 2026-03-26 | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-26 | Auspan-TRANSMIT-000163 | NA | Trade Partner | Precast shop drawings for construction. | 27 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required. Updated register and ACC |  | 2026-03-26 | NA | Closed | 27 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-11-28 | Auspan-TRANSMIT-000012 | NA | Trade Partner | Precast shop drawings for retaining wall for construction. | 51 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Wrong title Guide-KPTG-IntCorr-000174. Kapitol initiated an Internal Workflow-WF-000048 |  | 2025-12-01 | KPTG-IntCorr-000174 | Closed | 51 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-09 | HDRAus-TRANSMIT-000336 | NA | Consultant | M3_S2_S4 - SPANDREL WALL DETAILS - ADDED DIMENSIONS | 2 | 0 | 0 | NA | APPROVED | 2025-12-09 | NA | 3466 | 2025-12-11 |  |  |  |  | KPTG-TRANSMIT-010888 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-26 | Auspan-TRANSMIT-000165 | NA | Trade Partner | Update corner bracket for construction. | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings NO review required |  | 2026-03-26 | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-26 | Auspan-TRANSMIT-000166 | NA | Trade Partner | Precast shop drawings for approval. Stage 9 level 1. | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings, No review required |  | 2026-03-26 | NA | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-26 | D&E-TRANSMIT-000526 | NA | Trade Partner | BMS Valve Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-03-26 | WF-005010 | NA | 2026-04-16 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016484 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-26 | PARR-TRANSMIT-000145 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - TDP - IFA | 0 | 7 | 0 | NA | APPROVED | 2026-03-26 | WF-005016 | NA | 2026-04-10 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-015339 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-26 | D&E-TRANSMIT-000527 | NA | Trade Partner | ISSUED FOR APPROVAL - Roof Level - CHW Pipe Layouts & Sections - Zone 3, 5, 7 & 9 | 5 | 0 | 0 | NA | APPROVED | 2026-03-26 | NA | 2630 | 2026-04-10 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-016797 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-26 | D&E-TRANSMIT-000528 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - LEVEL 1 HANGERS | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - Difference in revision number |  | 2026-03-26 | KPTG-TRANSMIT-015020 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-26 | ARCST-TRANSMIT-000238 | NA | Trade Partner | C2 Upper Cooling Tower Handrails - Issued for Approval | 32 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected- Difference in status |  | 2026-03-26 | KPTG-TRANSMIT-015034 | Closed | 32 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-26 | ARCST-TRANSMIT-000237 | NA | Trade Partner | C2 East Lower Gantry - Issued for Approval | 201 | 0 | 0 | NA | APPROVED | 2026-03-26 | WF-005018,WF-005019 | NA | 2026-04-15 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-016707,KPTG-TRANSMIT-016716, KPTG-TRANSMIT-016723 | Closed | 201 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | Mirage D-TRANSMIT-000014 | NA | Trade Partner | Roller Shutters Data Sheets | 0 | 2 | 0 | NA | APPROVED | 2026-03-27 | WF-005028 | NA | 2026-04-06 |  | The WF has been generated as requested by Isabella | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-015186 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-10 | Syfon1-TRANSMIT-000004 | SPARK-CRFI-KPG-000467 | Trade Partner | Syfon Shop Drawings for review | 4 | 0 | 0 | NA | APPROVED | 2025-12-11 | WF-000100 | 62 | 2025-12-18 |  |  |  | 2026-03-18 | KPTG-TRANSMIT-000555 | Open | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-26 | Nilsen3-TRANSMIT-000079 | NA | Trade Partner | Fwd: Nilsen IFC Sample Submission | 0 | 23 | 0 | NA | APPROVED |  | NA | NA |  |  | ONLY FOR INFORM BORDER TEAM |  | 2026-03-26 | KPTG-TRANSMIT-015025 | Closed | 23 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-26 | Nilsen3-TRANSMIT-000078 | NA | Trade Partner | Re: Nilsen IFC Sample Submission | 0 | 2 | 0 | NA | REJECTED | [5 empty] | DUE TO NOT FILLED DOCUMENTS |  | 2026-03-26 | KPTG-TRANSMIT-015010 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-27 | SMEPS-TRANSMIT-000166 | NA | Trade Partner | Re: Updated Legend of Symbols Drawings | 2 | 0 | 0 | NA | APPROVED | [5 empty] | No Review as per peter - KPTG-IntCorr-002418 |  | 2026-03-27 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-27 | ASV-TRANSMIT-000042 | NA | Trade Partner | Hydraulic X Crane Footing Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 567 | 2026-04-01 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-002084 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-27 | ECBS-TRANSMIT-000006 | NA | Trade Partner | Armstrong Engineering Report for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-27 | WF - 000310 | Na | 2026-04-03 |  | NA | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-000723 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-27 | ELLISAIR-TRANSMIT-000001 | NA | Trade Partner | OAP Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-03-27 | WF-000403 | NA | 2026-04-01 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-002107 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-26 | Hollow-TRANSMIT-000008 | NA | Trade Partner | Raft 2 - Pour Sequence for review | 5 | 0 | 0 | NA | REJECTED | [5 empty] | rejected: QA Error revision: KPTG-TRANSMIT-000933 |  | 2026-03-26 | KPTG-TRANSMIT-000933 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-26 | INGEN3D-TRANSMIT-000021 | NA | Trade Partner | I3D-389 District Living - Level 3 - Cast in Dowels & Precast Columns - IFC (25-03-2026) | 68 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | FC - issues Updated the register |  | 2026-03-26 | NA | Closed | 68 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-26 | INGEN3D-TRANSMIT-000022 | NA | Trade Partner | I3D-389 District Living - Level 3 - Cast in Dowel & Precast Columns - No longer in use | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No longer in use : Updated the registers and forwarded to all parties |  | 2026-03-26 | KPTG-TRANSMIT-000935 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-26 | PCForm-TRANSMIT-000116 | NA | Trade Partner | Level 2 IFC | 6 | 0 | 0 | KPTG-IntCorr-000535 | APPROVED | 2026-03-29 | NA | 380 | 2026-04-03 |  | Clarification from Victoria, - New Revision issued via Rinco-TRANSMIT-000004 - hence review voided | 2026-03-30 | 2026-03-30 | Rinco-TRANSMIT-000004 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-09 | Stowe-A-TRANSMIT-000412 | NA | Trade Partner | Stowe - Tech Data Submission - Basket Radius Piece | 0 | 1 | 0 | NA | APPROVED |  | WF-003543 | NA | 2025-12-19 |  |  |  | 2025-12-17 | KPTG-TRANSMIT-011038 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-26 | PWC-TRANSMIT-000002 | NA | Consultant | Waterproofing Document Update | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected : KPTG-TRANSMIT-000926 |  | 2026-03-26 | KPTG-TRANSMIT-000926 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-26 | Civilex-TRANSMIT-000059 | NA | Trade Partner | Micro Pile Material - Protek Bar System | 0 | 1 | 0 | NA | APPROVED | 2026-03-26 | WF-000272 | NA | 2026-03-30 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-001006 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-26 | TTW-TRANSMIT-000122 | NA | Consultant | DWGs outstanding from 06/03/25 - BP1 drawings | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | CAD Drawings - Updated the registers |  | 2026-03-26 | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-26 | ArcadiaL-TRANSMIT-000001 | NA | Consultant | Landscape Architectural Updates - 4B3 | 12 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected : KPTG-TRANSMIT-000937 |  | 2026-03-26 | KPTG-TRANSMIT-000937 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-26 | TTW-TRANSMIT-000123 | NA | Consultant | BP1 - Construction Update | 6 | 0 | 0 | NA | APPROVED | 2026-03-26 | NA | 372 | 2026-03-31 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-000996 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-26 | Schindle-TRANSMIT-000013 | SPARK-CRFI-KPG-000446 | Trade Partner | HBU Updated IFA drawing | 1 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 197 | 2026-04-03 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-000665 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-27 | KPTG-IntCorr-000613 | NA | Trade Partner | VM submission | 0 | 1 | 0 | NA | APPROVED | 2026-03-27 | WF-000405 | NA | 2026-03-31 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-001822 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-27 | SMEPS-TRANSMIT-000167 | SPARK-CRFI-KPG-000284 | Trade Partner | Re: Updated Distribution Board Schematics | 6 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 198 | 2026-04-03 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-000729 & KPTG-TRANSMIT-000767 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-27 | WilsonPD-TRANSMIT-000173 | SPARK-CRFI-KPG-000511 | Trade Partner | Updated hydraulic Layout - Level 1 Zone B - Penetration Layout | 1 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 199 | 2026-04-03 |  |  | 2026-03-30 | 2026-04-24 | KPTG-TRANSMIT-000704 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-27 | KPTG-IntCorr-003379 | NA | Trade Partner | D&E O&M Manual | 0 | 1 | 0 | NA | APPROVED | 2026-03-27 | WF-000982 | NA | 2026-04-03 |  |  | 2026-04-15 | 2026-04-16 | Awaiting approval | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-09 | Tradetec-TRANSMIT-000292 | NA | Trade Partner | IFA Shop Drawings - Central West - CP7, HVP8, HVP10 | 3 | 0 | 0 | NA | APPROVED | 2025-12-09 | NA | 3469 | 2025-12-15 |  |  |  | 2025-12-15 | KPTG-TRANSMIT-010925 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-27 | PARR-IntCorr-000043 | NA | Trade Partner | P2645 - KPG NDC M3 S1 DH7&8 - Fuel - AS-BUILT | 0 | 1 | 0 | KPTG-IntCorr-003390 | APPROVED | 2026-03-24 | WF-000971 | NA | 2026-04-02 |  | Terminated requested by Chri doh |  | 2026-03-30 | KPTG-TRANSMIT-002794 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-27 | KPTG-IntCorr-003380 | NA | Trade Partner | M3DH78 - Precision fire - practical completion documentation | 0 | 1 | 0 | NA | APPROVED | 2026-03-30 | WF-000984 | NA |  |  |  | 2026-04-16 | 2026-04-16 | Awaiting approval | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-27 | KPTG-IntCorr-003381 | NA | Trade Partner | Dry Fire O&M, | 0 | 1 | 0 | NA | APPROVED | 2026-03-27 | WF-000981 | NA | 2026-04-03 |  | Terminated requested by Andrew BroadStock-ADP attached wrongly |  | 2026-04-02 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-27 | KPTG-IntCorr-003383 | NA | Trade Partner | SME O&M manual | 0 | 1 | 0 | NA | APPROVED | 2026-03-30 | WF-000985 | NA |  |  | Terminated; Requested by andrew and resubmitted through WF-000999. |  | 2026-04-20 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-27 | KPTG-IntCorr-003384 | NA | Trade Partner | M3S1DH78 - Wilson Plumbing and Drainage - Practical Completion Documentation | 0 | 1 | 0 | NA | APPROVED | 2026-03-27 | WF-000983 | NA | 2026-04-03 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-27 | D&E-TRANSMIT-000188 | SPARK-CRFI-KPG-000572 | Trade Partner | ISSUED FOR CONSTRUCTION - GROUND & LEVEL 1- MECH. ELEC. LAYOUTS - MECHANICAL SERVICES | 4 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 200 | 2026-04-03 |  |  | 2026-04-17 | 2026-04-24 | KPTG-TRANSMIT-000708 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-27 | SMEPS-TRANSMIT-000169 | SPARK-CRFI-KPG-000302 | Trade Partner | IFC Power and Comms Layouts | 4 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 201 | 2026-04-03 |  |  | 2026-04-17 | 2026-04-24 | KPTG-TRANSMIT-000720 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | IVS-TRANSMIT-000347 | NA | Consultant | Re: Issued for Certification (Revised as Clouded) - Acoustic Screens | 2 | 0 | 0 | NA | APPROVED | 2026-03-16 | NA | 2483 | 2026-03-27 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015074 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-27 | SMEPS-TRANSMIT-000161 | NA | Trade Partner | SME AHU Samples for review | 0 | 1 | 0 | NA | APPROVED | 2026-03-27 | WF - 000312 | NA | 2026-04-02 |  | NA | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-000700 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-27 | SMEPS-TRANSMIT-000166 | NA | Trade Partner | SME Cable Ties for review | 0 | 1 | 0 | NA | APPROVED | 2026-03-27 | WF - 000311 | NA | 2026-04-02 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-000689 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-09 | Tradetec-TRANSMIT-000291 | NA | Trade Partner | Stage 2 - South East - Shop Drawings IFA - CP11, CP13, LVP06 | 3 | 0 | 0 | NA | APPROVED | 2025-12-09 | NA | 3470 | 2025-12-15 |  |  |  | 2025-12-15 | KPTG-TRANSMIT-010929 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | Nilsen3-TRANSMIT-000080 | NA | Trade Partner | Re: LV Earth Cable Sample | 0 | 1 | 0 | NA | APPROVED | 2026-03-27 | NA | WF-005030 | 2026-04-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-27 | SMEPS-TRANSMIT-000170 | SPARK-CRFI-KPG-000302 | Trade Partner | Power and Comms Layouts Up Rev | 6 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 202 | 2026-04-03 |  | Delayed due to VPN issue |  | 2026-04-10 | KPTG-TRANSMIT-000630 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-27 | SMEPS-TRANSMIT-000162 | NA | Trade Partner | SME Shop Drawing Telecomunications IFC A | 3 | 0 | 0 | NA | APPROVED | 2026-03-27 | WF - 000313 | NA | 2026-04-01 |  | NA | 2026-03-30 | 2026-03-31 | KPTG-TRANSMIT-000647 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-27 | SMEPS-TRANSMIT-000163 | NA | Trade Partner | SME Shop Drawing Telecomunications IFC | 1 | 0 | 0 | NA | APPROVED | 2026-03-27 | WF - 000314 | NA | 2026-03-31 |  | NA | 2026-03-30 | 2026-03-31 | KPTG-TRANSMIT-000650 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-27 | D&E-TRANSMIT-000189 | SPARK-CRFI-KPG-000473 | Trade Partner | ISSUED FOR CONSTRUCTION - PLINTH LAYOUT ZONE 8 & 9 MECHANICAL SERVICES | 1 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 203 | 2026-04-03 |  |  | 2026-04-17 | 2026-04-24 | KPTG-TRANSMIT-000706 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-27 | SMEPS-TRANSMIT-000165 | NA | Trade Partner | SME Shop Drawing Telecomunications IFC | 1 | 0 | 0 | NA | APPROVED | 2026-03-27 | WF - 000316 | NA | 2026-03-31 |  | NA | 2026-03-30 | 2026-03-31 | KPTG-TRANSMIT-000656 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-27 | D&E-TRANSMIT-000529 | NA | Trade Partner | ISSUED FOR APPROVAL - ROOF LEVEL - CHILLER ROOMS, MECHANICAL DUCT LAYOUT - ZONE 1, 3 & 5 | 1 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 4027 | 2026-04-07 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-27 | SMEPS-TRANSMIT-000164 | NA | Trade Partner | SME Shop Drawing Telecomunications IFC | 1 | 0 | 0 | NA | APPROVED | 2026-03-27 | WF - 000315 | NA | 2026-03-31 |  | NA | 2026-03-30 | 2026-03-31 | KPTG-TRANSMIT-000653 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-27 | NXT-TRANSMIT-001457 | NA | Client | 100222-000587: EA, EQ & ER Rooms - IOM's for Approval | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Document number inside and outside are different. |  | 2026-03-27 | KPTG-DA-005735 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | D&E-TRANSMIT-000537 | NA | Trade Partner | Water Meters - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-27 | WF-005048 | NA | 2026-04-17 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-016005 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-09 | TTW-TRANSMIT-000144 | NA | Consultant | M3 Stage 2 Civil Drawings | 4 | 0 | 0 | NA | REJECTED | [5 empty] | The drawing numbers inside and outside the documents are wrong |  |  | KPTG-DA-003816 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | D&E-TRANSMIT-000536 | NA | Trade Partner | BMS System Architecture & Points Lists - Issued for Approval | 0 | 5 | 0 | NA | APPROVED | 2026-03-27 | WF-005047 | NA | 2026-04-17 |  | 1ds compeleted review and blnce 4 remains | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016488 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | D&E-TRANSMIT-000535 | NA | Trade Partner | ISSUED FOR APPROVAL - GROUND CHW PIPE LAYOUT ZONE 8 & 10 | 2 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 2650 | 2026-04-06 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-016821 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-23 | SMEPS-TRANSMIT-000156 | NA | Trade Partner | BOM Rev 5 | 0 | 3 | 0 | NA | APPROVED | 2026-03-23 | WF - 000288 | NA | 2026-03-27 |  | NA | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-000637, KPTG-TRANSMIT-000644 ,KPTG-TRANSMIT-000687 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-27 | ZIA-TRANSMIT-000042 | NA | Consultant | CSMS - Network Architecture | 0 | 1 | 0 | NA | APPROVED | 2026-03-27 | WF-000960 | NA | 2026-03-30 |  |  | 2026-04-20 | 2026-04-20 | KPTG-WTRAN-001965 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-27 | PMT Sec-TRANSMIT-000004 | NA | Trade Partner | PMT Shop Drawings | 25 | 0 | 0 | NA | REJECTED | [5 empty] | Error in revision |  | 2026-03-27 | KPTG-TRANSMIT-000604 | Closed | 25 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-27 | Auspan-TRANSMIT-000174 | NA | Trade Partner | Update IFC shop drawings. | 15 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC No review required - Register and distribute KPTG-TRANSMIT-001116 |  | 2026-03-27 | KPTG-TRANSMIT-001116 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-27 | Auspan-TRANSMIT-000175 | NA | Trade Partner | Resubmit precast shop drawings for approval. Level 1. | 12 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 612 | 2026-04-02 |  |  | 2026-04-14 | 2026-04-14 | KPTG-TRANSMIT-001302 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-27 | M.2-TRANSMIT-000015 | NA | Trade Partner | Apartment DB Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-03-27 | WF-000326 | NA | 2026-04-01 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-001340 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-27 | JCBa-TRANSMIT-000078 | NA | Consultant | STRUCTURAL SETOUT PLANS SECOND FLOOR: ALL ZONES | 5 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 614 | 2026-03-31 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-001194 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | IVS-TRANSMIT-000354 | NA | Consultant | Issued for Certification - HV-Room | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Different drawing status in Aconex and inside drawing |  | 2026-03-27 | KPTG-TRANSMIT-015130 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-09 | Tradetec-TRANSMIT-000294 | NA | Trade Partner | IFA - Stage 2 - CP14 | 1 | 0 | 0 | NA | APPROVED | 2025-12-09 | NA | 3472 | 2025-12-15 |  |  | 2025-12-11 | 2025-12-11 | KPTG-TRANSMIT-010835 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | PARR-TRANSMIT-000149 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - HVAC TDP - IFA | 0 | 2 | 0 | NA | APPROVED | 2026-03-27 | WF-005058 | NA | 2026-04-10 |  |  | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-015640 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-27 | crossfir-TRANSMIT-000005 | NA | Trade Partner | Wet Fire - Penetrations Basement 04 to ground | 5 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 374 | 2026-04-02 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-000697 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-27 | RDSBIM-TRANSMIT-000046 | NA | Trade Partner | 671CHP BASEMENT 3 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 376 | 2026-04-02 |  | Review Voided by Kapitol PC - Tayla | 2026-04-17 | 2026-04-17 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-27 | RDSBIM-TRANSMIT-000047 | NA | Trade Partner | 671CHP - BASEMENT 2 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 378 | 2026-04-02 |  | Review is void. | 2026-03-31 | 2026-03-31 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-27 | Altaire-TRANSMIT-000102 | NA | Trade Partner | Altaire-TRANSMIT-000102 | 3 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 4050 | 2026-04-06 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-015526 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-27 | ASV-TRANSMIT-000165 | ASV-TRANSMIT-000165 | Trade Partner | Revised - Drinking Fountain | 0 | 1 | 0 | NA | APPROVED | 2026-03-27 | WF-005036 | NA | 2026-04-08 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-015502 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-27 | D&E-TRANSMIT-000532 | NA | Trade Partner | MCC-RF-01 (Admin Office) Electrical Drawing - Issued for Approval | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Document doesn't have a document number inside the drawings. |  | 2026-03-27 | KPTG-DA-005738 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-27 | D&E-TRANSMIT-000534 | NA | Trade Partner | Admin Office Splits - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-27 | WF-005041 | NA | 2026-04-10 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-017413 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-27 | HDRAus-TRANSMIT-000444 | NA | Consultant | M3 SW uploaded Architectural Drawing Document - FWU flashing detail. | 1 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 4030 | 2026-03-31 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-015172 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2025-11-25 | RDSBIM-TRANSMIT-000192 | NA | Trade Partner | LOWER AND UPPER GROUND COMMON AREA GYM & WELLNESS | 10 | 0 | 0 | NA | APPROVED | 2025-11-25 | NA | 561 | 2025-12-11 |  |  | 2025-12-11 | 2025-12-11 | KPTG-TRANSMIT-002520 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-27 | ASV-TRANSMIT-000043 | NA | Trade Partner | Civil Stormwater Pipework | 0 | 1 | 0 | NA | APPROVED | 2026-03-27 | WF-000406 | NA | 2026-04-01 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-001955 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-27 | ASV-TRANSMIT-000044 | NA | Trade Partner | Geotextile Filter Wrap for Gravel Pit's | 0 | 1 | 0 | NA | APPROVED | 2026-03-27 | WF-000407 | NA | 2026-04-08 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-002203 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-27 | ASV-TRANSMIT-000045 | NA | Trade Partner | Reflux Valve for Elec pit drainage to gravel pits | 0 | 1 | 0 | NA | APPROVED | 2026-03-27 | WF-000408 | NA | 2026-04-07 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-002450 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-27 | WGAVIC-TRANSMIT-000094 | NA | Consultant | M2 - Stage 9 Level 2 Slab - Issued for Construction | 6 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 572 | 2026-04-01 |  |  | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-001874 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-27 | WGAVIC-TRANSMIT-000095 | NA | Consultant | M2 - Stage 11 Level 1 Slab - Issued for Construction | 4 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 573 | 2026-04-01 |  |  | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-001878 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-23 | WAM-TRANSMIT-000737 | NA | Consultant | 95% DD Demo update | 0 | 0 | 0 | NA | REJECTED | [5 empty] | 2 rejected REVISION ERROR- resubmission trn 740 |  | 2026-03-23 | KPTG-TRANSMIT-000881 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-27 | TATE_-TRANSMIT-000009 | NA | Trade Partner | Tate - MECH WALL 3-3 - TYPICAL LAYOUT | 2 | 0 | 0 | NA | APPROVED | 2026-03-27 | WF-000098 | NA | 2026-04-08 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-000383 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-27 | TATE_-TRANSMIT-000008 | NA | Trade Partner | Tate - New Shop Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-03-27 | WF-000099 | NA | 2026-04-08 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-000379 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-27 | TATE_-TRANSMIT-000007 | NA | Trade Partner | Tate - Tech Data | 0 | 3 | 0 | NA | APPROVED | 2026-03-27 | WF-000096 | NA | 2026-04-02 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-000302,KPTG-TRANSMIT-000313 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-27 | SIL-TRANSMIT-000027 | NA | Trade Partner | Test Scripts | 0 | 7 | 0 | KPTG-IntCorr-000210, | REJECTED | [5 empty] | KAPITOL ADVICE AWAITS: KPTG-IntCorr-000210, SUBMITTED DOCUMENTS ARE FOR INFORMATION |  | 2026-04-01 | KPTG-SADV-000245 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2025-11-17 | RDSBIM-TRANSMIT-000190 | NA | Trade Partner | BATHROOM TYPE BT01.2A-(UG05) FINISHES LAYOUT | 2 | 0 | 0 | NA | APPROVED | 2025-12-01 | NA | 562 | 2025-12-05 |  |  | 2025-12-11 | 2025-12-11 | KPTG-TRANSMIT-002521 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-27 | RDSBIM-TRANSMIT-000004 | NA | Trade Partner | MEL11C45 ¦ LEVEL 02 COLO 4 AND 5B AREA RCP LAYOUT | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Document Number of Drawings are incorrect, requested to resubmit:KPTG-IntCorr-000204 |  | 2026-03-27 | KPTG-IntCorr-000204 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-27 | RDSBIM-TRANSMIT-000005 | NA | Trade Partner | MEL11C45 ¦ LEVEL 02 COLO 4 AND 5B AREA RCP LAYOUT | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Document Number of Drawingsare incorrect, requested to resubmit: KPTG-IntCorr-000209 |  | 2026-03-27 | KPTG-IntCorr-000209 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-27 | RDSBIM-TRANSMIT-000006 | NA | Trade Partner | MEL11C45 ¦ LEVEL 02 COLO 4 AND 5B AREA RCP LAYOUT | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Document number of Drawings are incorrect, requested to resubmit: KPTG-IntCorr-000211 |  | 2026-03-27 | KPTG-IntCorr-000211 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-27 | EFP-TRANSMIT-000013 | NA | Trade Partner | FIRE SERVICES SHOP DRAWINGS UPDATED IFC | 16 | 0 | 0 | NA | REJECTED | [5 empty] | Revision history of drawings were found wrong: KPTG-IntCorr-000205 |  | 2026-03-27 | KPTG-IntCorr-000205 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-27 | Appselec-TRANSMIT-000043 | NA | Trade Partner | COLO 4 - Layout, Schematics and Rack Elevations - Issued for Approval | 9 | 0 | 0 | NA | APPROVED | 2026-03-27 | WF-000097 | NA | 2026-04-02 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-000467 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-13 | EFP-TRANSMIT-000012 | NA | Trade Partner | TECH DATA - SPRINKLER & HYDRANT PIPE | 0 | 1 | 0 | NA | APPROVED | 2026-03-14 | WF-000055 | NA | 2026-03-18 |  |  | 2026-03-27 | 2026-03-30 | KPTG-TRANSMIT-000218 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-24 | PCForm-TRANSMIT-000114 | NA | Trade Partner | Raft 2 - Pour Sequence for review | 0 | 0 | 0 | KPTG-IntCorr-000526 | APPROVED | 2026-03-29 | NA | 377 | 2026-04-01 |  | IFC - 2 DRAWINGS | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-001435 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-25 | TTW-TRANSMIT-000120 | NA | Consultant | BP8 - Issued for Construction | 16 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 366 | 2026-03-26 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-001000 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-25 | WAM-TRANSMIT-000741 | NA | Consultant | Kitchen Island Bench | 3 | 0 | 0 | NA | APPROVED | 2026-03-25 | NA | 368 | 2026-03-26 |  |  |  | 2026-03-31 | KPTG-TRANSMIT-000986 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-27 | RDSBIM-TRANSMIT-000125 | NA | Trade Partner | MLC ¦ AQUATIC CENTER LEVEL 01 CONCRETE PROFILE PLAN AND SECTIONS | 2 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 476 | 2026-04-03 |  |  | 2026-05-14 | 2026-05-14 | KPTG-SADV-004333 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-09 | CRSol-TRANSMIT-000062 | NA | Trade Partner | NXM3 - Updated drawings, Containment DHB5 | 11 | 0 | 0 | NA | REJECTED | [5 empty] | The status inside and outside the documents are different |  |  | KPTG-DA-003818 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-27 | M.S.-TRANSMIT-000058 | NA | Trade Partner | J53 - IFC Shop drawing | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status of drawing is incorrect, requested to resubmit: KPTG-SADV-003987 |  | 2026-03-27 | KPTG-SADV-003987 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-27 | M.S.-TRANSMIT-000059 | NA | Trade Partner | J53 Updated IFA shop drawing | 2 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 477 | 2026-04-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-27 | ECBS-TRANSMIT-000079 | NA | Trade Partner | Revised Tech data for approval - AM40 | 0 | 1 | 0 | NA | APPROVED | 2026-03-27 | WF-000905 | NA | 2026-04-02 |  |  | 2026-04-14 | 2026-04-14 | KPTG-TRANSMIT-002736 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-27 | KPTG-IntCorr-006405 | NA | Client | FFG10 | 0 | 1 | 0 | NA | APPROVED | 2026-03-27 | WF-000903 | NA | 2026-04-03 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-27 | 42636706-TRANSMIT-000014 | NA | Trade Partner | COMS-CO-SPC-002-2 - ISP Functional Description | 0 | 1 | 0 | NA | APPROVED | 2026-03-27 | WF-000685 | NA | 2026-04-02 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-002206 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | RDSBIM-TRANSMIT-000252 | NA | Trade Partner | NXM3S4 GROUND FLOOR LEVEL 01 SPEED PANEL LAYOUT ZONE C3 | 1 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 2633 | 2026-03-31 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-015329 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-27 | WAM-TRANSMIT-000731 | NA | Consultant | DD Update | 67 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 374 | 2026-04-03 |  | ADDITIONAL SME REVIEW | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-001031 | Closed | 67 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-27 | WAM-TRANSMIT-000734 | NA | Consultant | DD Update | 2 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 374 | 2026-04-03 |  | ADDITIONAL SME REVIEW | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-001032 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-27 | WAM-TRANSMIT-000736 | NA | Consultant | DD Update | 1 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 374 | 2026-04-03 |  | ADDITIONAL SME REVIEW | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-001033 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-27 | PWC-TRANSMIT-000003 | NA | Consultant | Waterproofing Spec | 0 | 1 | 0 | NA | APPROVED | 2026-03-30 | WF-000279 | NA | 2026-04-01 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-001031 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-11-14 | RDSBIM-TRANSMIT-000102 | NA | Trade Partner | LINDRUM ¦ BASEMENT 1 LEVEL REFLECTED CEILING PLAN | 1 | 0 | 0 |  | APPROVED | 2025-11-18 | NA | 446# | 2025-11-24 | 6 | Revise & Resubmit | 2025-12-01 | 2025-12-01 | KPTG-SADV-002304 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-09 | KPTG-TRANSMIT-010742 | NA | Trade Partner | VicRoad concrete mix design for fuel compound | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [5 empty] | KPTG-TRANSMIT-010759 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-27 | TTW-TRANSMIT-000124 | NA | Consultant | CAD - LATEST | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Register updated sent to all parties |  | 2026-03-27 | KPTG-TRANSMIT-000960 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-27 | TTW-TRANSMIT-000125 | NA | Consultant | CAD - LATEST | 11 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Register updated sent to all parties |  | 2026-03-27 | KPTG-TRANSMIT-000957 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-27 | TTW-TRANSMIT-000126 | NA | Consultant | TTW CIVIL STORMWATER DWG | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Register updated sent - Requested latest issue |  | 2026-03-27 | KPTG-TRANSMIT-000963 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-30 | KAPITOL-TRANSMIT-001250 | NA | Trade Partner | HFF - Joinery Shop Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 375 | 2026-04-03 |  |  |  | 2026-03-31 | DRAFT-009583 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-30 | D&E-TRANSMIT-000538 | NA | Trade Partner | NXM3S2 - LOWER GROUND & GROUND - MECHANICAL DUCT & PIPE LAYOUTS - As Installed | 26 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong drawings status and Revision number. |  | 2026-03-30 | KPTG-SADV-004530 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-30 | RDSBIM-TRANSMIT-000007 | NA | Trade Partner | MEL11C45 ¦ LEVEL 02 COLO 4 AND 5B AREA RCP LAYOUT | 2 | 0 | 0 | NA | APPROVED | 2026-03-30 | WF-000103 | NA | 2026-04-03 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-000326 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-30 | Arc Plas-TRANSMIT-000003 | NA | Trade Partner | MEL11 COLO 4&5 Armstrong ceiling seismic design | 0 | 1 | 0 | NA | APPROVED | 2026-03-30 | WF-000104 | NA | 2026-04-03 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-000288 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-30 | D&E-TRANSMIT-000191 | SPARK-CRFI-KPG-000376 | Trade Partner | FIRE MATRIX | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-08 | KPTG-TRANSMIT-000622 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-11 | NXT-WTRAN-002005 | NA | Consultant | 50mPa Mix Design | 1 | 0 | 0 | NA | APPROVED | 2026-02-11 | WF-004233 | NA | 2026-03-27 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015073 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | NXT-TRANSMIT-001458 | NA | Consultant | Fwd: 400A Mechanical TOB Shop Drawing, Approval & Quantity Confirmation | 1 | 0 | 0 | NA | APPROVED | 2026-03-27 | WF-005033 | NA | 2026-04-01 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-019591 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-10 | ASV-TRANSMIT-000122 | NA | Trade Partner | Hydraulic Samples - Fixtrues | 0 | 8 | 0 | NA | REJECTED | [5 empty] | Revision 01 of document M3-HYD-AXS-TD-SW-0000-0047 shared in this transmittal has already completed its review |  |  | KPTG-DA-003835 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | PARR-TRANSMIT-000147 | NA | Trade Partner | Fwd: P2680 - NDC M3 Stage 4 - Fuel - TDP | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | ONLY FOR INFORM ALL |  | 2026-03-27 | KPTG-TRANSMIT-015088 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-30 | KALLIBRE-TRANSMIT-000011 | NA | Trade Partner | B08 Door Frames Shop Drawings - Issued For Approval | 2 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 376 | 2026-04-03 |  |  | 2026-03-31 | 2026-03-31 | KAPITOL-TRANSMIT-001274 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | KPTG-TRANSMIT-013739 | NA | Consultant | SME Sample Submission | 2 | 0 | 0 | NA | APPROVED | 2026-03-27 | WF-005039 | NA | 2026-04-04 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015089 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | KPTG-TRANSMIT-015107 | NA | Consultant | SME Tech Data Re-Transmittal | 2 | 0 | 0 | NA | APPROVED | 2026-03-27 | WF-005039 | NA | 2026-04-11 |  | wo samples into a workflow on Aconex with just Hames Sharley and Next DC because they were the last two steps and the previous workflow they were in was accidentally reject |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | SMEPS-TRANSMIT-000223 | NA | Trade Partner | SME - DRAWINGS IFA PART SUBMISSIONS | 8 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 2655 | 2026-04-16 |  | DRAWINGS IFA PART SUBMISSIONS - ELEC | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-016743 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | SMEPS-TRANSMIT-000223 | NA | Trade Partner | SME - DRAWINGS IFA PART SUBMISSIONS | 2 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 2656 | 2026-04-16 |  | SMEPS-TRANSMIT-000223 - TEL | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-016596 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | SMEPS-TRANSMIT-000224 | NA | Trade Partner | SME - IFC drawings | 4 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 2658 | 2026-04-03 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-017233 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | ARCST-TRANSMIT-000239 | NA | Trade Partner | Shop Drawings - Southern Risers | 21 | 0 | 0 | NA | APPROVED | 2026-03-27 | WF-005034 | NA | 2026-04-22 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018419 | Open | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | HDRAus-TRANSMIT-000443 | HDRAus-TRANSMIT-000443 | Consultant | Eaves Gutter & Outrigger RE; KPTG-RFI-006947 | 1 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 2636 | 2026-03-31 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-015203 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | SKS Tech-TRANSMIT-000068 | NA | Trade Partner | Ears Bars - Swithcrooms | 0 | 1 | 0 | NA | APPROVED | 2026-03-27 | 005037 | NA | 2026-04-04 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-016618 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-11 | JCBa-TRANSMIT-000203 | NA | Consultant | L2 and L10 Ceiling Changes | 4 | 0 | 0 | NA | APPROVED | 2025-12-11 | WF-000815 | 513 | 2025-12-17 |  |  | 2025-12-16 | 2025-12-16 | KPTG-DA-002270 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | D&E-TRANSMIT-000533 | NA | Trade Partner | ISSUED FOR APPROVAL - TYPICAL HAC PIPEWORK LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 2640 | 2026-04-06 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-016801 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | PARR-TRANSMIT-000146 | NA | Trade Partner | NDC M3 Stage 4 - Fuel - PUMP ROOM A B & BFS ATS DB- | 10 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 2646 | 2026-04-06 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-016321 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | Nilsen3-TRANSMIT-000081 | NA | Trade Partner | NXM3S4 Nilsen ELC Shop Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 2649 | 2026-04-06 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-016825 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | Nilsen3-TRANSMIT-000081 | NA | Trade Partner | NXM3S4 Nilsen ELC Shop Drawings | 9 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 2647 | 2026-04-06 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-016838 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-19 | Auscool-TRANSMIT-000088 | NA | Trade Partner | Basement - Mezzanine Mech Shop Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-03-19 | NA | 605 | 2026-03-25 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-002132 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | HDRAus-TRANSMIT-000445 | NA | Consultant | Re: M3 Stage4 Re-uploaded Architectural Drawing Document (unlocked) | 10 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected - Different revision number |  | 2026-03-27 | KPTG-TRANSMIT-015142 | Closed | 10 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | IVS-TRANSMIT-000353 | NA | Consultant | Re: Issued For Construction - Web forge Details, Acoustic Screen | 12 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Difference in status and revision |  | 2026-03-27 | KPTG-TRANSMIT-015145 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | HDRAus-TRANSMIT-000446 | NA | Consultant | Re-M3 Stage4 Re-uploaded Architectural Drawing Document (unlocked) | 6 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 2660 | 2026-03-23 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | HDRAus-TRANSMIT-000447 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 14 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 2664 | 2026-03-31 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-015347 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-30 | SMEPS-TRANSMIT-000167 | NA | Trade Partner | SME Shop Drawing Telecommunications IFA | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Transmittal rejected due to same REV submitted by SEMPE. |  | 2026-03-30 | KPTG-TRANSMIT-000641 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-10 | ASV-TRANSMIT-000121 | NA | Trade Partner | Hydraulic Samples - Fire Sealant, Grate Seal & Flashcrete Mortar | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Documents with two different status can't be included in one transmittal |  |  | KPTG-DA-003850 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-30 | SMEPS-TRANSMIT-000168 | NA | Trade Partner | AFL Material BOM 27.03.26 | 0 | 1 | 0 | NA | APPROVED | 2026-03-30 | WF - 000317 | NA | 2026-04-03 |  | NA | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-000678 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-27 | KALLIBRE-TRANSMIT-000010 | NA | Trade Partner | Re: PowerPack Building 08 - Door Frame Shop Drawings For Review | 1 | 0 | 0 | NA | REJECTED | [8 empty] | DRAFT-009544 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-27 | WPD-TRANSMIT-000078 | NA | Consultant | Fwd Updated Hydraulic Layout - B08 - Ground Floor | 1 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 373 | 2026-04-04 |  |  | 2026-04-08 | 2026-04-08 | DRAFT-009640 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-30 | KEECEPRO-TRANSMIT-000039 | NA | Trade Partner | Hanwha DB-01 & DB-COM IFC Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 377 | 2026-04-02 |  |  | 2026-03-30 | 2026-03-30 | KEECEPRO-TRANSMIT-000039 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-30 | SMEPS-TRANSMIT-000169 | NA | Trade Partner | SME Shop Drawing Telecomunications IFC | 1 | 0 | 0 | NA | APPROVED | 2026-03-30 | WF - 000318 | NA | 2026-04-03 |  | NA | 2026-03-30 | 2026-03-31 | KPTG-TRANSMIT-000660 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-30 | SMEPS-TRANSMIT-000170 | NA | Trade Partner | SME Shop Drawing Telecomunications IFC | 1 | 0 | 0 | NA | APPROVED | 2026-03-30 | WF - 000319 | NA | 2026-04-03 |  | NA | 2026-03-30 | 2026-03-31 | KPTG-TRANSMIT-000663 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-30 | SMEPS-TRANSMIT-000171 | Na | Trade Partner | SME Shop Drawing Telecomunications IFC | 1 | 0 | 0 | NA | APPROVED | 2026-03-30 | WF- 000323 | NA | 2026-03-30 |  | NA | 2026-03-30 | 2026-03-31 | KPTG-TRANSMIT-000669 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-30 | SMEPS-TRANSMIT-000172 | NA | Trade Partner | SME Shop Drawing Telecomunications IFC | 3 | 0 | 0 | NA | APPROVED | 2026-03-30 | WF - 000320 | NA | 2026-04-03 |  | NA | 2026-03-30 | 2026-03-31 | KPTG-TRANSMIT-0000667 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-30 | SMEPS-TRANSMIT-000173 | NA | Trade Partner | SME Shop Drawing Telecomunications IFC | 1 | 0 | 0 | NA | APPROVED | 2026-03-30 | WF - 000324 | NA | 2026-04-03 |  | NA | 2026-03-30 | 2026-03-31 | KPTG-TRANSMIT-000672 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-10 | TTW-TRANSMIT-000145 | NA | Consultant | TTW-TRANSMIT-000145 | 3 | 0 | 0 | NA | REJECTED | [5 empty] | The drawing M3-CIV-TTW-DRG-B-0201-6402 is printed incorrectly |  |  | KPTG-DA-003836 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-30 | SMEPS-TRANSMIT-000174 | NA | Trade Partner | SME Shop Drawing Telecomunications IFA 3 | 1 | 0 | 0 | NA | APPROVED | 2026-03-30 | WF - 000325 | NA | 2026-04-03 |  | NA | 2026-04-07 | 2026-04-08 | KPTG-TRANSMIT-000701 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-30 | PMT Sec-TRANSMIT-000005 | SPARK-CRFI-KPG-000631 & SPARK-CRFI-KPG-000629 | Trade Partner | PMT Shop Drawings Rev A | 25 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 204 | 2026-04-06 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-000670 | Closed | 25 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-30 | RDSBIM-TRANSMIT-000253 | NA | Trade Partner | NXM3S4 ¦ GROUND FLOOR-C-G-064 UNISEX WC FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 2671 | 2026-04-02 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-015754 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-30 | SMEPS-TRANSMIT-000175 - | NA | Trade Partner | SME Shop Drawing Telecomunications IFA 3 | 1 | 0 | 0 | NA | APPROVED | 2026-03-30 | WF - 000326 | NA | 2026-04-03 |  | NA | 2026-04-07 | 2026-04-08 | KPTG-TRANSMIT-000702 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-30 | VIA Arch-TRANSMIT-000028 | NA | Trade Partner | Fwd: Updated Arch Detailing 22KV | 4 | 0 | 0 | NA | APPROVED | 2026-03-30 | WF-005094 | NA | 2026-04-09 |  | As per Max no action required - WF has been terminated as requested by Max H | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-015593 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | Mirage D-TRANSMIT-000014 | NA | Trade Partner | Roller Shutters Data Sheets | 0 | 0 | 0 | NA | APPROVED | 2026-03-27 | WF-005028 | NA | 2026-04-06 |  | The WF has been generated as requested by Isabella |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-30 | Schindle-TRANSMIT-000014 | NA | Trade Partner | Schindler Main COP Lift Drawing - IFC | 1 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 205 | 2026-04-06 |  | Terminated as per Peter |  | 2026-04-20 | KPTG-IntCorr-002722 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-03-30 | Auspan-TRANSMIT-000009 | NA | Trade Partner | Auspan-TRANSMIT-000009 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Title block issue, Revision number issue | 2026-03-30 | 2026-03-30 | DRAFT-000912 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-30 | D&E-TRANSMIT-000540 | NA | Trade Partner | Bermad Valves - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-30 | WF-005072 | NA | 2026-04-20 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-016001 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-30 | Tradetec-TRANSMIT-000404 | NA | Trade Partner | IFC - Altan Tank Drawings | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Revision numbers not updated and drawing number not mentioned in the drawing. | 2026-03-30 | 2026-03-30 | KPTG-DA-005768 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-10 | TTW-TRANSMIT-000146 | NA | Consultant | M3 Stage 2 Civil Drawings | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Partial submission |  |  | KPTG-DA-003841 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-30 | SKS Tech-TRANSMIT-000070 | NA | Trade Partner | Zones C1 & C2 Overall Lighting Compliance | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-03-30 | KPTG-RFI-007044 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-30 | D&E-TRANSMIT-000539 | NA | Trade Partner | MCC-RF-01 (Admin Office) Electrical Drawing - Issued for Approval | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Issues in document number in multiple sheets. |  | 2026-03-30 | KPTG-DA-005766 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-30 | Stowe-A-TRANSMIT-000532 | NA | Trade Partner | Stowe - Tech Data Submission - Security Peno Proposal | 0 | 1 | 0 | NA | APPROVED | 2026-03-30 | WF-005074 | NA | 2026-04-10 |  | Workflow terminated for updating document |  | 2026-03-30 |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-30 | NXT-TRANSMIT-001457 | NA | Client | 100222-000587: EA, EQ & ER Rooms - IOM's for Approval | 0 | 2 | 0 | NA | APPROVED | 2026-03-30 | WF-005076 | NA | 2026-04-02 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-30 | PROLMC-TRANSMIT-000017 | NA | Trade Partner | Proline roofing drawings 30/3/26 | 20 | 0 | 0 | NA | REJECTED | [5 empty] | Error in revision |  | 2026-03-30 | KPTG-TRANSMIT-000606 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-30 | D&E-TRANSMIT-000544 | NA | Trade Partner | Admin Office Security Grilles - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-30 | WF-005064 | NA | 2026-04-13 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-016600 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-25 | KPTG-TRANSMIT-014974 | NA | Trade Partner | AXIS O&M Manual S2 Review | 0 | 1 | 0 | NA | APPROVED | 2026-03-25 | WF-005000 | NA | 2026-03-30 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-015212 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-30 | Stowe-A-TRANSMIT-000533 | NA | Trade Partner | Stowe - Tech Data Submission - Security Peno Proposal and Screw Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-03-30 | WF-005077 | NA | 2026-04-10 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-30 | KETE-TRANSMIT-000124 | NA | Trade Partner | Kete - Updated Cast-in Channel Layout Drawings L06-L09 | 4 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-003597-The revision number is not current. Kindly resubmit Revision B. |  | 2026-03-30 | KPTG-SADV-003597 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-30 | D&E-TRANSMIT-000543 | NA | Trade Partner | MCC Schedules IFC Rev 8 - Harmonic information updated | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Change in Document Number, Revision and document type |  | 2026-03-30 | KPTG-DA-005775 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-10 | CRSol-TRANSMIT-000063 | NA | Trade Partner | NXM3 - Updated drawings, Containment DHB5 - 2 | 11 | 0 | 0 | NA | APPROVED | 2025-12-10 | NA | 3478 | 2025-12-16 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-13 | ADP-TRANSMIT-000278 | NA | Consultant | MEL741 - Stage 4 Updated EL Drawings (IFC Issue) | 9 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 2667 | 2026-04-01 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-015307 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-30 | ADP-TRANSMIT-000288 | NA | Consultant | MEL741 - Stage 4 FID Drawings - IFC Updates | 8 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 2672 | 2026-04-01 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-015295 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-30 | ADP-TRANSMIT-000276 | NA | Consultant | MEL741 - Stage 4 Updated EL Drawings (IFC Issue) | 38 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 2677 | 2026-04-01 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-015286 | Closed | 38 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-30 | Nilsen3-TRANSMIT-000082 | NA | Trade Partner | Nilsen Shop Drawings - IFC samples | 0 | 3 | 0 | NA | APPROVED | 2026-03-30 | WF-005071 | NA | 2026-04-20 |  | The WF has been terminated as requested by Damian |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-30 | D&E-TRANSMIT-000541 | NA | Trade Partner | Expansion Tank & Auto Refill Unit - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-03-30 | WF-005075 | NA | 2026-04-20 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-015969 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-30 | ADP-TRANSMIT-000289 | NA | Consultant | Re: MEL741 - Stage 4 Updated EL Drawings (IFC Issue) | 49 | 0 | 0 | NA | REJECTED | [5 empty] | 38 DOCUMENTS PROCESSED FROM PREVIOUS TRANSMIT ADP-TRANSMIT-000276 AND NEW 9 NEED TO RESUBMIT UNDER NEW TRANSMIT |  | 2026-03-30 | KPTG-TRANSMIT-015211 | Closed | 49 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-10 | ARCST-TRANSMIT-000225 | NA | Trade Partner | Re: C3 Cooling Tower Upper Gantry Handrails - Issued for Approval | 38 | 0 | 0 | NA | APPROVED | 2026-03-10 | WF-004718 | NA | 2026-03-30 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-015217 | Closed | 38 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-30 | IVS-TRANSMIT-000355 | NA | Consultant | Re Updated structural Chemical Store & Fire room | 2 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 2686 | 2026-04-04 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-30 | RDSBIM-TRANSMIT-000254 | NA | Trade Partner | NXM3S4 ROOF CONCRETE PROFILE PLAN AND SECTION | 8 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 2679 | 2026-03-07 |  | The WF has been terminated as requested by Max H Drawings need to be updated |  | 2026-04-23 | KPTG-TRANSMIT-016405 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-30 | SMEPS-TRANSMIT-000226 | NA | Trade Partner | Re: SME - GLP DB SCHEDULES - IFA | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected- no cover page |  | 2026-03-30 | KPTG-TRANSMIT-015194 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-10 | Stowe-A-TRANSMIT-000413 | NA | Trade Partner | Stowe - GLP DB Schedules | 0 | 20 | 0 | NA | APPROVED | 2025-12-10 | WF-003555 | NA | 2025-12-22 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-30 | D&E-TRANSMIT-000545 | NA | Trade Partner | ISSUED FOR APPROVAL - Roof Level - Chiller Room Layout & Sections | 2 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 2684 | 2026-04-07 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-30 | ADP-TRANSMIT-000290 | NA | Consultant | Re: ADP MEL4780 - Updated Electrical Reg126 | 0 | 1 | 0 | KPTG-IntCorr-011377 | APPROVED |  | NA | NA |  |  | ADVISE SEEKED FOR IFC REGISTER |  | 2026-03-31 | KPTG-TRANSMIT-015309 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-30 | Tradetec-TRANSMIT-000405 | NA | Trade Partner | Re: IFC - Stage 4 South | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected- Difference in document number and revision format. |  | 2026-03-30 | KPTG-TRANSMIT-015237 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-30 | RDSBIM-TRANSMIT-000256 | NA | Trade Partner | NXM3S4 - GROUND FLOOR-C-G-054 ACC WC (RH) FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 2681 | 2026-04-01 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016162 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-30 | RDSBIM-TRANSMIT-000255 | NA | Trade Partner | NXM3S4 - GROUND FLOOR-C-G-022 ACC WC (LH) FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 2676 | 2026-04-01 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016154 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-30 | ARCST-TRANSMIT-000242 | NA | Trade Partner | Lift Lobby Steel - Issued for Approval | 71 | 0 | 0 | NA | APPROVED | 2026-03-27 | WF-005065 | NA | 2026-04-24 |  | 26 docs are still under review | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-017018 , KPTG-TRANSMIT-018540 | Closed | 63 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-30 | ARCST-TRANSMIT-000240 | NA | Trade Partner | Generator PMJ Support - Issued for Approval | 4 | 0 | 0 | NA | APPROVED | 2026-03-27 | WF-005066 | NA | 2026-04-24 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-017056 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-30 | Tradetec-TRANSMIT-000086 | NA | Trade Partner | Technical Data Submissions for Jemena Works - Baffle Spacers | 0 | 1 | 0 | NA | APPROVED | 2026-03-30 | WF-000426 | NA | 2026-04-03 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-002341 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-30 | Tradetec-TRANSMIT-000086 | NA | Trade Partner | Technical Data Submissions for Jemena Works - Thermal Flowable Concrete | 0 | 1 | 0 | NA | APPROVED | 2026-03-30 | WF-000427 | NA | 2026-04-03 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-001580 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-30 | ELLISAIR-TRANSMIT-000003 | NA | Trade Partner | Technical Data Submission - Pipework, Dampers, Flexible duct, Refrigeration pipework & fittings, Sealants | 0 | 5 | 0 | NA | APPROVED | 2026-03-30 | WF-000431 | NA | 2026-04-03 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-002093 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-04 | RDSBIM-TRANSMIT-000004 | NA | Trade Partner | GREYSTAR ¦ BASEMENT CAPPING BEAM PLAN ELEVATION AND SECTION | 6 | 0 | 0 | NA | APPROVED | 2025-12-11 | WF-000091 | 182 | 2025-12-17 |  |  |  | 2025-12-12 | KPTG-TRANSMIT-000327 | Closed | 6 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-30 | ARCST-TRANSMIT-000241 | NA | Trade Partner | C1 West Roof Walkway - Issued for Approval | 200 | 0 | 0 | NA | APPROVED | 2026-03-30 | WF-0005081 | NA | 2026-04-21 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-017221 | Closed | 200 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-30 | ARCST-TRANSMIT-000241 | NA | Trade Partner | C1 West Roof Walkway - Issued for Approval | 30 | 0 | 0 | NA | APPROVED | 2026-03-30 | WF-0005083 | NA | 2026-03-03 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-017052 | Closed | 30 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-30 | POTTSENG-TRANSMIT-000017 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONE 3 & 4 LAYOUT | 2 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 620 | 2026-04-06 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-001224 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-30 | KETE-TRANSMIT-000013 | NA | Trade Partner | : Kete - Zone 03 and 05 Shop Drawing IFA 1st Submission | 199 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 626 | 2026-04-06 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-001631 | Closed | 199 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-30 | RDSBIM-TRANSMIT-000040 | NA | Trade Partner | GREYSTAR GROUND FLOOR CONCRETE PROFILE KEY PLAN | 9 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 618 | 2026-04-06 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-001368 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-30 | M.2-TRANSMIT-000016: | NA | Trade Partner | Electrical Services External lighting layout | 1 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 622 | 2026-04-06 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-001232 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-30 | M.2-TRANSMIT-000017 | NA | Trade Partner | : Electrical Services Basement Power layouts | 5 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 624 | 2026-04-06 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-001229 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-30 | SMEPS-TRANSMIT-000020 | NA | Trade Partner | STAGE 9-11 Electrical Zoned drawings - Stage 10 & 11 (Priority Items) | 3 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 576 | 2026-04-06 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-001849 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-30 | JCBa-TRANSMIT-000079 | NA | Consultant | : STRUCTURAL SETOUT PLANS : OVERALL PLANS FOR GROUND, 1ST & 2ND | 3 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 628 | 2026-04-06 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-001192 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-30 | LVPG-TRANSMIT-000025 | NA | Trade Partner | LVPG - Tech Data Submittals - Rock & Swivel joints | 0 | 3 | 0 | NA | APPROVED | 2026-03-30 | WF-000332 | NA | 2026-04-06 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-001197 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-11 | Auspan-TRANSMIT-000029 | NA | Trade Partner | Auspan-TRANSMIT-000029: Precast shop drawings for construction | 15 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required updated register and ACC, issue to all Consultants and TPs. |  | 2025-12-11 | KPTG-TRANSMIT-000306 | Closed | 15 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-30 | SMEPS-TRANSMIT-000020 | NA | Trade Partner | STAGE 9-11 Electrical Zoned drawings - Stage 09 & 11 | 3 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 577 | 2026-04-06 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-001963 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-30 | SMEPS-TRANSMIT-000020 | NA | Trade Partner | STAGE 9-11 Telecoms Zoned drawings | 6 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 578 | 2026-04-06 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-002034 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-30 | Tradetec-TRANSMIT-000087 | NA | Trade Partner | HV Pit Shop Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 580 | 2026-04-06 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-001969 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-30 | LGCE-TRANSMIT-000011 | na | Trade Partner | Basement 1 light and power drawings | 2 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 382 | 2026-04-02 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000908 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-30 | KPTG-IntCorr-006308 | NA | Trade Partner | We Are Best Signage Drawings-479# | 97 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 479 | 2026-04-06 |  |  | 2026-04-08 | 2026-04-08 | KPTG-DA-001446 | Closed | 97 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-08-21 | ECBS-TRANSMIT-000009 | NA | Trade Partner | WF-000382 | 0 | 4 | 0 | NA | APPROVED | 2025-08-21 | WF-000382 | NA | 2025-08-25 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-002665 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-18 | fjc-TRANSMIT-000142 | NA | Consultant | Architecturals - RFIs + BP6 Items | 0 | 6 | 0 | NA | APPROVED | 2026-03-18 | WF-000669 | NA | 2026-03-25 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-002139 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-30 | NXES-TRANSMIT-000048 | NA | Trade Partner | Nexus - IFA Switchboard Drawings with Updated Cover Page | 0 | 1 | 0 | NA | APPROVED | 2026-03-11 | WF-000660 | NA | 2026-03-16 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-002134 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-30 | Entire M-IntCorr-000033 | NA | Trade Partner | Re: VCD Technical Data IFA Rev B | 0 | 6 | 0 | NA | APPROVED | 2026-03-30 | WF-000105 | NA | 2026-04-02 |  |  | 2026-04-14 | 2026-04-14 | KPTG-TRANSMIT-000367 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-30 | Entire M-TRANSMIT-000009 | NA | Trade Partner | Mechnical IFA Rev B - Splits, Refidge & Copper pipe, Pipe fittings | 0 | 2 | 0 | NA | APPROVED | 2026-03-18 | WF-000065 | NA | 2026-03-23 |  |  | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-000232 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-01 | WAM-TRANSMIT-000015 | N/A | Consultant | WAM ARCH - 95% DD CSP's and Core | 64 | 0 | 0 | NA | APPROVED | 2025-12-01 | WF-000048 | 108 | 2025-12-03 |  | Due to holiday - Close-out mail approved and sent on jan 12th | 2025-12-19 | 2026-01-12 | KPTG-TRANSMIT-000269 | Closed | 64 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-10 | TTW-TRANSMIT-000147 | NA | Consultant | M3 Stage 2 Civil Drawings | 3 | 0 | 0 | NA | APPROVED | 2025-12-10 | NA | 3480 | 2025-12-15 |  |  | 2025-12-11 | 2025-12-11 | KPTG-TRANSMIT-010831 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-27 | ACG-TRANSMIT-000033 | NA | Trade Partner | C1 West Roof Walkway - Issued for Approval | 8 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Superseded by ACG-TRANSMIT-000034 |  |  | NA | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-30 | LANSA-TRANSMIT-000019 | NA | Trade Partner | Hyd As Builts | 3 | 0 | 0 | KPTG-IntCorr-003413 | APPROVED | 2026-03-31 | NA | 1456 | 2026-04-03 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-002828 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-30 | KPTG-IntCorr-003385 | NA | Trade Partner | Wilson Plumbing and Drainage - Practical Completion Documentation | 0 | 1 | 0 | NA | APPROVED | 2026-03-30 | WF-000986 | NA | 2026-04-06 |  |  | 2026-04-15 | 2026-04-16 | Awaiting approval | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-31 | KEECEPRO-TRANSMIT-000040 | NA | Trade Partner | Re: Lighting Control IFC Drawings | 1 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-03-31 | KEECEPRO-TRANSMIT-000040 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-30 | NXT-TRANSMIT-000391 | NA | Client | HRA 4WLA Report - W.C 23/03/26 | 0 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Action Required-correspondance |  |  |  | Closed | 0 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-30 | ACG-TRANSMIT-000034 | NA | Trade Partner | M3 - Stage 1 DH7/8 As Builts | 8 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 1454 | 2026-04-03 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-002820 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-30 | D&E-TRANSMIT-000353 | NA | Trade Partner | AS BUILT MECHANICAL SHOP DRAWINGS | 32 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 1458 | 2026-04-06 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-002815 | Closed | 32 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-31 | Stowe-A-TRANSMIT-000534 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - HOUSE CONTAINMENT - GL & L1 - 31.03.2026 | 4 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 4067 | 2026-04-10 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-015868 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-31 | Stowe-A-TRANSMIT-000535 | NA | Trade Partner | STOWE - AS-BUILT - GROUND FLOOR COMMS CONTAINMENT - ZONE B1 - 31.03.2026 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with Revision number. To be resubmitted. |  | 2026-03-31 | KPTG-SADV-004550 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-31 | SMPS-TRANSMIT-000106 | NA | Trade Partner | Hanwha: Power Pack B08 - Electrical Shop Drawings - IFC (Rev .01) | 5 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 379 | 2026-04-03 |  |  | 2026-04-08 | 2026-04-08 | DRAFT-009641 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-11 | Auspan-TRANSMIT-000030 | NA | Trade Partner | Auspan-TRANSMIT-000030: Precast shop drawings for approval. Zone 1, 2. | 8 | 0 | 0 | NA | APPROVED | 2025-12-11 | WF-000092 | 185 | 2025-12-18 |  |  |  | 2025-12-16 | KPTG-TRANSMIT-000352 | Closed | 8 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-30 | WAM-TRANSMIT-000742 | NA | Consultant | WAM ARCH - DD - Facade and Insulation Plans | 119 | 0 | 0 | NA | APPROVED | 2026-03-30 | NA | 384 | 2026-04-03 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-001193 | Closed | 119 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-30 | HVHD-TRANSMIT-000005 | NA | Consultant | SMP for Endorsement | 0 | 1 | 0 | NA | REJECTED | [5 empty] | wrong file attached |  | 2026-03-30 | KPTG-TRANSMIT-000965 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-30 | HVHD-TRANSMIT-000004 | NA | Consultant | ESD Implementation Matrix | 0 | 1 | 0 | NA | APPROVED | 2026-03-30 | WF-000280 | NA | 2026-03-31 |  |  | 2026-03-31 | 2026-03-31 | KPTG-TRANSMIT-001007 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-30 | ArcadiaL-TRANSMIT-000002 | NA | Consultant | Landscape Architectural Updates - Responses to Comments | 4 | 0 | 0 | NA | REJECTED | [5 empty] | File name error |  | 2026-03-30 | KPTG-TRANSMIT-000978 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-30 | Resonate-TRANSMIT-000011 | NA | Consultant | Updated acoustic report | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Revision Error |  | 2026-03-30 | KPTG-TRANSMIT-000956 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-31 | Auspan-TRANSMIT-000063 | NA | Trade Partner | Shop drawings issued for construction | 12 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-SADV-003609-As per the direction from Ashlin, we have only update register and upload Bim. |  | 2026-03-31 | KPTG-SADV-003609 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-31 | Stowe-A-TRANSMIT-000536 | NA | Trade Partner | Stowe - Drawing Submission - HS1 Office Stage 1 - 31.03.2026 | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Issues in drawings status, Revisions, and mismatch in revision progression. |  | 2026-03-31 | KPTG-SADV-004552 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-31 | RDSBIM-TRANSMIT-000005 | NA | Trade Partner | LEVEL 02 COLO 04 AREA PARTITION WALL ENLARGED LAYOUT | 3 | 0 | 0 | NA | APPROVED | 2026-03-31 | WF - 000329 | NA | 2026-04-03 |  | WF Terminated |  |  | NA | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-24 | RDSBIM-TRANSMIT-000178 | NA | Trade Partner | LEVEL 04 PARTITION WALL KEY PLAN | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per KAPITOL advise, IFC Drawings only for distribution. |  | 2026-03-24 | KPTG-TRANSMIT-002849 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-31 | Stowe-A-TRANSMIT-000537 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - LIGHTING CONTROL - 31.03.2026 | 7 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 4068 | 2026-04-10 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-015576 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-10 | Tradetec-TRANSMIT-000297 | NA | Trade Partner | Tech Data Submission - Flap Valves | 0 | 1 | 0 | NA | APPROVED | 2025-12-10 | WF-003558 | NA | 2025-12-18 |  |  |  | 2025-12-17 | KPTG-TRANSMIT-011042 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-30 | PCForm-TRANSMIT-000120 | NA | Trade Partner | Precast grout methodology for stacked panels | 0 | 1 | 0 | NA | APPROVED | 2026-03-30 | WF-000282 | NA | 2026-04-03 |  | submitted - 1 doc PCForm-TRANSMIT-000109 also included | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-001029 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-31 | Appselec-TRANSMIT-000044 | NA | Trade Partner | Documents No Longer In Use | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Documents No Longer In Use, Just transmitted to all parties |  | 2026-03-31 | KPTG-TRANSMIT-000249 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-12 | WAM-TRANSMIT-000730 | NA | Consultant | WAM ARCH - 95% DD - Facade Details | 0 | 0 | 0 | NA | APPROVED | 2026-03-27 | NA | 373 | 2026-03-31 |  | MISSED 2 DWGS FROM REVIEW 329 | 2026-03-30 | 2026-03-30 | KPTG-TRANSMIT-000970 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-31 | PFP PL-TRANSMIT-000002 | NA | Trade Partner | Level 2 Colo 4 Low Level Layout Re-IFA | 1 | 0 | 0 | NA | APPROVED | 2026-03-31 | WF - 000330 | NA | 2026-04-07 |  | NA | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-000715 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-31 | Appselec-TRANSMIT-000045 | NA | Trade Partner | Technical Data For Construction | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Revision of documents do not match with the Document Register:KPTG-IntCorr-000216 |  | 2026-03-31 | KPTG-IntCorr-000216 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-30 | KPTG-IntCorr-001108 | NA | Client | Permit Docs | 1 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Register updated |  | 2026-03-30 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-30 | KPTG-RTRFI-000098 | NA | Trade Partner | Tech Data of Access Doors | 0 | 50 | 0 | NA | APPROVED |  | NA | NA |  |  | Register updated |  | 2026-03-30 | NA | Closed | 50 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-31 | Appselec-TRANSMIT-000046 | NA | Trade Partner | Communications Trunking Substitution Request Kounis | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Submitted Technical data is with precious review comment and review stamp, requested to resubmit:KPTG-IntCorr-000217 |  | 2026-03-31 | KPTG-IntCorr-000217 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-31 | SMEPS-TRANSMIT-000172 | NA | Trade Partner | Ground Floor Containment Layout Zone 8 & Overall | 2 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 207 | 2026-04-07 |  |  | 2026-04-17 | 2026-04-27 | KPTG-TRANSMIT-000747 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-31 | NXT-TRANSMIT-001464 | NA | Trade Partner | Vertiv Sample Factory MSB Script | 1 | 0 | 0 | KPTG-IntCorr-011430 | APPROVED |  | NA | NA |  |  | Waiting for response from KG team - KPTG-IntCorr-011430 | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018346 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-11 | JCBa-TRANSMIT-000044 | NA | Consultant | Capping Beam Elevations - Sheet 1 Update | 1 | 0 | 0 | KPTG-IntCorr-000188 | APPROVED | 2025-12-12 | WF-000097 | 193 | 2025-12-17 |  | KPTG-IntCorr-000188. Workflow initiated. |  | 2026-01-14 | KPTG-TRANSMIT-000395 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-31 | KPTG-TRANSMIT-015274 | NA | Trade Partner | KPTG-TRANSMIT-015274 | 0 | 4 | 0 | NA | APPROVED | 2026-03-31 | WF-005088 | NA | 2026-04-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-31 | SMEPS-TRANSMIT-000173 | SPARK-CRFI-KPG-000168 | Trade Partner | IFA Ground Floor Containment | 7 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 208 | 2026-04-07 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-000629 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-31 | Civilex-TRANSMIT-000221 | NA | Trade Partner | Fwd: Switchroom Handrail (revised kickplate height) IFC | 4 | 0 | 0 | NA | APPROVED | 2026-03-31 | WF-005089 | NA | 2026-04-08 |  | KPTG-TRANSMIT-015517 |  | 2026-07-10 | KPTG-TRANSMIT-019565 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-31 | Appselec-TRANSMIT-000048 | NA | Trade Partner | Communications Trunking For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-03-31 | WF-000106 | NA | 2026-04-07 |  |  | 2026-04-12 | 2026-04-13 | KPTG-TRANSMIT-000334 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-31 | vdmcons-TRANSMIT-000018 | NA | Trade Partner | ME25 1144:D13 M3 Stage 3 GIS Building - M3 Stage 3 Switchro0m - Additional Support - IFF - 2026-03-31 | 3 | 0 | 0 | NA | APPROVED | 2026-03-31 | WF-005092 | NA | 2026-04-13 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-015429 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-31 | Baigents-TRANSMIT-000080 | NA | Trade Partner | MCC-P67 ISSUED FOR CONSTRUCTION | 1 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 209 | 2026-04-07 |  | Review void - Latest revision received |  | 2026-04-02 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-31 | Auspan-TRANSMIT-000064 | NA | Trade Partner | Revised shop drawings issued for approval | 3 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 615 | 2026-04-03 |  | KPTG-IntCorr-000880 - The review of Bim workflow is closed #613 closed while I am checking the drawings it's noticed that the review comment given by consultant was revise and resubmit. but you commented as Approved with comments.Could you please conform that what the final comment is. | 2026-04-17 | 2026-04-17 | KPTG-SADV-003791 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-31 | Auspan-TRANSMIT-000064 | NA | Trade Partner | Revised shop drawings issued for approval | 9 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 616 | 2026-04-03 |  |  | 2026-03-31 | 2026-04-01 | KPTG-SADV-003621 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-31 | NXT-TRANSMIT-001465 | NA | Trade Partner | LVSB 3D Models- SO 611300382- M3 ST-4 | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-31 | KPTG-TRANSMIT-015302 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-10 | Tradetec-TRANSMIT-000298 | NA | Trade Partner | Penstock Valves - Shop Drawings | 3 | 0 | 0 | NA | REJECTED | [5 empty] | The attached documents under each document number looks incorrect for the submission |  | 2025-12-10 | KPTG-DA-003849 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-31 | NXT-TRANSMIT-001466 | NA | Trade Partner | LVSB 3D Models- SO 611300382- M3 ST-4 | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-03-31 | KPTG-TRANSMIT-015306 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-03-31 | IDS-TRANSMIT-000019 | NA | Trade Partner | POWER PACK PRODUCTION FACILITY - WET & DRY FIRE | 1 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 381 | 2026-04-03 |  |  | 2026-04-08 | 2026-04-08 | DRAFT-009642 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-31 | Tradetec-TRANSMIT-000406 | NA | Trade Partner | IFC - Altan Tank Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 4037 | 2026-04-13 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-015795 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-31 | D&E-TRANSMIT-000547 | NA | Trade Partner | NXM3S2 - Lower Ground + Ground - Mechanical Duct Layout Zones - Issued AS BUILT / HANDOVER | 12 | 0 | 0 | NA | REJECTED | [5 empty] | Issues with Revision of a document number. Workflow terminated. |  | 2026-04-01 | KPTG-SADV-004601 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-31 | SC-TRANSMIT-000004 | NA | Trade Partner | IFC drawings for Secondary steel (Partly issued) | 11 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing title inside the drawing and in Aconex seem different |  | 2026-03-31 | KPTG-TRANSMIT-000607 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-03-31 | PROLMC-TRANSMIT-000018 | NA | Trade Partner | Proline roofing shop drawings updated 31/1/26 | 20 | 0 | 0 | NA | REJECTED | [5 empty] | Error in drawing title |  | 2026-03-31 | KPTG-TRANSMIT-000608 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-31 | DS-TRANSMIT-000106 | NA | Trade Partner | HYD As Built Drawings | 10 | 0 | 0 | NA | REJECTED | [5 empty] | Issue in Revision Number, Status and Revision history |  | 2026-03-31 | KPTG-SADV-004582 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-31 | PenskePS-TRANSMIT-000003 | NA | Trade Partner | MEL11 COLO4 & 5 - FAT & SAT Scripts | 0 | 4 | 0 | NA | REJECTED | [5 empty] | Document Number and revision of document are incorrect, requested to resubmit.KPTG-IntCorr-000223 |  | 2026-03-31 | KPTG-IntCorr-000223 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-31 | Civilex-TRANSMIT-000222 | NA | Trade Partner | Stage 2 - Landscape Transmittal - Rev C - Drawing 7-8-9 | 3 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 4039 | 2026-04-07 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-015749 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-31 | RDSBIM-TRANSMIT-000039 | NA | Trade Partner | GREYSTAR GROUND IFC FOR SUBMISSION ZONE 1 & 2 | 2 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 630 | 2026-04-07 |  | Review void as advised by Kapitol DM. RDS to update the drawing, | 2026-04-01 | 2026-04-01 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-11 | INGEN3D-TRANSMIT-000673 | NA | Trade Partner | M3 Stage 4 - Ground Floor Fuel Tank - Precast Panels - Batch 2 - IFA Resubmission (11-12-2025) | 42 | 0 | 0 | NA | APPROVED | 2025-12-11 | WF-003570 | NA | 2026-01-06 |  |  |  | 2026-02-17 | KPTG-TRANSMIT-013030 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-31 | Auspan-TRANSMIT-000176 | NA | Trade Partner | : Resubmit precast shop drawings for approval. Ground floor | 20 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 632 | 2026-04-07 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-001320 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-31 | Auspan-TRANSMIT-000177 | NA | Trade Partner | : Precast shop drawings for approval. Level 1 | 22 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 634 | 2026-04-07 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-001344 | Closed | 22 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-31 | Auspan-TRANSMIT-000178 | NA | Trade Partner | Precast shop drawings for approval. Levels 2, 3 | 90 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing PDF not printed properly. |  | 2026-03-31 | KPTG-SADV-001668 | Closed | 90 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-31 | Auspan-TRANSMIT-000179: | NA | Trade Partner | Update IFCed precast shop drawings | 21 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC No review required - Register and distribute KPTG-TRANSMIT-001148 |  | 2026-03-31 | KPTG-TRANSMIT-001148 | Closed | 21 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-31 | KPTG-TRANSMIT-001125: | NA | Trade Partner | Fwd: GF to Level 5 PT and Shear Connector plans for approval | 45 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings number is not inline with DesPro. |  | 2026-03-31 | KPTG-SADV-001663 | Closed | 45 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-31 | Rinco-TRANSMIT-000037 | NA | Consultant | : Structural drawings Issued for Construction | 2 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 637 | 2026-04-07 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-001257 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-31 | JCBa-TRANSMIT-000080 | NA | Consultant | : A-4406 - RETAIL ENTRY STAIR 7, 8_IFC | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect drawing status : KPTG-SADV-001670 |  | 2026-03-31 | KPTG-SADV-001670 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-31 | Auspan-TRANSMIT-000181 | NA | Trade Partner | : Resubmit precast shop drawings for approval. Level 1. | 20 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 640 | 2026-04-07 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-001347 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-31 | Auspan-TRANSMIT-000182 | NA | Trade Partner | Update IFCed shop drawings. Fixing return bricks. | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC No review required - Register and distribute |  | 2026-03-31 | KPTG-TRANSMIT-001162 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-03-31 | Auspan-TRANSMIT-000180: | NA | Trade Partner | Re: 1B5015 | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC No review required - Register and distribute |  | 2026-03-31 | KPTG-TRANSMIT-001159 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-11 | D&E-TRANSMIT-000283 | NA | Trade Partner | Shop Drawing - Electrical - IFC | 4 | 0 | 0 | NA | APPROVED | 2025-12-15 | NA | 1319 | 2025-12-23 |  | Review 1313 terminated and resubmitted on 1319 as advised by Kapitol. | 2025-12-16 | 2025-12-17 | KPTG-TRANSMIT-002206 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-31 | Civilex-TRANSMIT-000223 | NA | Trade Partner | Stage 2 - Landscape works and planting specification - Rev D | 0 | 1 | 0 | NA | APPROVED | 2026-03-31 | WF-005102 | NA | 2026-04-16 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-015580 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-03-31 | LGCE-TRANSMIT-000015 | NA | Trade Partner | Basement 4,3,2 IFC Builders works | 3 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 384 | 2026-04-07 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-000710 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-31 | Stowe-A-TRANSMIT-000538 | NA | Trade Partner | STOWE - TECH DATA SUBMISSION - ALTERNATIVE 12RU RACK - VO-078 | 0 | 1 | 0 | NA | APPROVED | 2026-03-31 | WF-005100 | NA | 2026-04-13 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-31 | VIA Arch-TRANSMIT-000079 | NA | Consultant | M2 S9-11 Building Permit Issue | 54 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 584 | 2026-04-07 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-001883 | Closed | 54 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-31 | VIA Arch-TRANSMIT-000080 | NA | Consultant | M2 S9 - S11 - STEEL DETAILS SHEET 01 | 1 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 586 | 2026-04-07 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-002064 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-31 | VIA Arch-TRANSMIT-000081 | NA | Consultant | M2 S9 GROUND - STEEL STAIRS CALLOUT PLANS - IFBP-1 | 1 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 588 | 2026-04-07 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-002068 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-31 | Tradetec-TRANSMIT-000088 | NA | Trade Partner | Technical Data Submissions for Jemena Works | 0 | 1 | 0 | NA | APPROVED | 2026-03-31 | WF-000435 | NA | 2026-04-08 |  |  | 2026-04-15 | 2026-04-16 | KPTG-TRANSMIT-002186 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-31 | ELLISAIR-TRANSMIT-000004 | NA | Trade Partner | Technical Data Submission - Fans | 0 | 1 | 0 | NA | APPROVED | 2026-03-31 | WF-000437 | NA | 2026-04-09 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-002105 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-31 | IVS-TRANSMIT-000356 | NA | Consultant | Stage 2 - Southern Retaining Wall Construction Issue (Revised as clouded) | 1 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 4041 | 2026-04-03 |  | One drawings supersed in transmittal #IVS-TRANSMIT-000367 | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-019014 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-11 | Baigents-TRANSMIT-000057 |  | Trade Partner | MCC Precast Lift Core Revisions - IFA | 10 | 0 | 0 | KPTG-IntCorr-001124 | APPROVED | [7 empty] | 2026-02-09 | KPTG-TRANSMIT-000419 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-31 | D&E-TRANSMIT-000539 | NA | Trade Partner | MCC-RF-01 (Admin Office) Electrical Drawing - Issued for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 4045 | 2026-04-09 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-017843 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-31 | SMEPS-TRANSMIT-000229 | NA | Trade Partner | Stage 4 - Pit Schedule (P04) - #2 | 0 | 1 | 0 | NA | APPROVED | 2026-03-31 | NA | 2699 | 2026-04-16 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-016343 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-31 | PFP PL-TRANSMIT-000082 | NA | Trade Partner | Level 1 Zone 3 IFA | 1 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 2694 | 2026-04-08 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-016086 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-31 | PFP PL-TRANSMIT-000080 | NA | Trade Partner | Fire Service Schematic IFA | 1 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 2690 | 2026-04-08 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-016254 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-31 | SKS Tech-TRANSMIT-000073 | NA | Trade Partner | M3-ELC-SKS-SA-C-0400-0027 Waterfall IFC submission | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech data distributed to tradepartners & consultant |  | 2026-03-31 | KPTG-TRANSMIT-015279 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-31 | SKS Tech-TRANSMIT-000071 | NA | Trade Partner | Fwd: M3-ELC-SKS-SA-C-0400-0013 Earth Bar IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech data distributed to tradepartners & consultant |  | 2026-03-31 | KPTG-TRANSMIT-015278 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-27 | Carr-TRANSMIT-000013 | NA | Consultant | 80% DD Architectural Drawing Issue | 89 | 0 | 0 | NA | REJECTED | [5 empty] | Carr-TRANSMIT-000013 Superseded with Carr-TRANSMIT-000017 |  |  | NA | Closed | 89 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-27 | Carr-TRANSMIT-000019 | NA | Consultant | 80% DD Architectural Drawing Issue | 18 | 0 | 0 | NA | REJECTED | [5 empty] | Carr-TRANSMIT-000019 Superseded with Carr-TRANSMIT-000022 |  |  | NA | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-27 | Carr-TRANSMIT-000020 | NA | Consultant | 80% DD Architectural Drawing Issue | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Carr-TRANSMIT-000020 Superseded with Carr-TRANSMIT-000023 |  |  | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-11 | WilsonPD-TRANSMIT-000136 |  | Trade Partner | Procurement Register - 4 | 0 | 1 | 0 | KPTG-IntCorr-001125 | APPROVED | [9 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-27 | Carr-TRANSMIT-000022 | NA | Consultant | 80% DD Architectural Drawing Issue | 18 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Aconex & ACC update only as advised by Renee ( Kapitol) |  | 2026-03-27 | NA | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-27 | Carr-TRANSMIT-000023 | NA | Consultant | 80% DD Architectural Drawing Issue | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Aconex & ACC update only as advised by Renee (Kapitol) |  | 2026-03-27 | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-27 | Carr-TRANSMIT-000024 | NA | Consultant | 80% DD Architectural Drawing Issue | 10 | 0 | 0 | NA | REJECTED | [5 empty] | Carr-TRANSMIT-000024 Superseded with Carr-TRANSMIT-000026 |  |  | NA | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-27 | Carr-TRANSMIT-000026 | NA | Consultant | 80% DD Architectural Drawing Issue | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Aconex & ACC Update only as advised by Renee ( Kapitol) |  | 2026-03-27 | NA | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-15 | Carr-TRANSMIT-000036 | NA | Consultant | Additional Architectural Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 134 | 2026-05-20 |  | Actual Received date 27-03-2026 | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000151 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-31 | KPTG-IntCorr-006521 | NA | Trade Partner | Junior Landscape Shop Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 480 | 2026-04-03 |  |  | 2026-04-16 | 2026-04-16 | KPTG-SADV-004091 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-03-31 | Arco-TRANSMIT-000014 | NA | Trade Partner | ALUMINIUM ROLLER SHUTTER OH06 | 1 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 481 | 2026-04-03 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-002859 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-31 | LANSA-TRANSMIT-000102 | NA | Trade Partner | LEVEL 09 SANITARY & STORMWATER DRAINAGE LAYOUT | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol IFC for distribution only. |  | 2026-03-31 | KPTG-TRANSMIT-002860 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-03-19 | KALLIBRE-TRANSMIT-000003 | NA | Trade Partner | Door by Door Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-03-19 | WF - 000280 | NA | 2026-03-26 |  | NA | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000813 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-11 | Baigents-TRANSMIT-000058 |  | Trade Partner | Site Storage Precast - IFC | 15 | 0 | 0 | KPTG-IntCorr-001126 | APPROVED | [5 empty] | KPTG-TRANSMIT-000369 |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-01 | Auspan-TRANSMIT-000010 | NA | Trade Partner | Precast shop drawings for approval. | 4 | 0 | 0 | NA | APPROVED | 2026-04-01 | WF-000019 | NA | 2026-04-10 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-000135 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-31 | D&E-TRANSMIT-000354 | NA | Trade Partner | Fire Matrix - IFC-8 Transmittal | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | Distribution only |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-31 | HDRAus-TRANSMIT-000083 | NA | Consultant | Stage 1 Phase 10 - As Built Package | 62 | 2 | 0 | KPTG-IntCorr-003423 | APPROVED | 2026-04-01 | 1460 | NA | 2026-04-06 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-31 | NXT-TRANSMIT-000392 | NA | Client | Incident closures | 0 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Action Required-Correspondence |  | 2026-03-31 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-31 | HDRAus-TRANSMIT-000084 | NA | Consultant | Stage 1 Phase 10 - As Built Package | 63 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Cad file of HDRAus-TRANSMIT-000083 |  | 2026-03-31 |  | Closed | 63 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-01 | D&E-TRANSMIT-000063 | NA | Trade Partner | HANWHA - LEVEL 0 DUCT AND EQUIPMENT LAYOUTS + SECTIONS & DETAILS SHEETS - AS BUILT | 4 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 383 changed to 406 | 2026-04-13 |  | As per requested by As requested by Andrew Broadstock - VOID (DE-ME-SPD-B16-002) | 2026-07-23 | 2026-07-23 | DRAFT-010429 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-31 | HDRAus-TRANSMIT-000085 | NA | Consultant | Stage 1 Phase 10 - As Built Package | 15 | 3 | 0 | KPTG-IntCorr-003424 | APPROVED | 2026-04-01 | 1462 | NA | 2026-04-06 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-002813 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-01 | DS-TRANSMIT-000107 | NA | Trade Partner | HYD As Built Drawings | 10 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with Drawings status inside the drawing. |  | 2026-04-01 | KPTG-SADV-004586 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-01 | Stowe-A-TRANSMIT-000539 | NA | Trade Partner | STOWE - TECH DATA SUBMISSION - ALTERNATIVE 12RU RACK PDU RAIL | 0 | 1 | 0 | NA | APPROVED | 2026-04-01 | WF-005105 | NA | 2026-04-13 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-31 | VAE-Grp-TRANSMIT-000145 | NA | Trade Partner | IFC - MECHANICAL - DETAILS - SHEET 5 | 1 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 1175 | 2026-04-03 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-003498 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-01 | PARR-TRANSMIT-000020 | N/A | Trade Partner | Fuel Services - BULK FUEL SCHEMATIC | 1 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED - QA ERROR |  | 2025-12-02 | KPTG-IntCorr-000710 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-11 | Baigents-TRANSMIT-000059 |  | Trade Partner | Dowel Plans Issued For Construction | 2 | 0 | 0 | KPTG-IntCorr-001127 | APPROVED | 2025-12-11 | WF-000101 | 53 | 2025-12-18 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-31 | OveArup-TRANSMIT-000029 | NA | Consultant | VT Specification | 0 | 1 | 0 | KPTG-TRANSMIT-000987 | REJECTED | [5 empty] | Rejected : Doc. No Error |  | 2026-03-31 | KPTG-TRANSMIT-000987 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-31 | Resonate-TRANSMIT-000012 | NA | Consultant | Secondary Consent Acoustic Report | 0 | 1 | 0 | NA | APPROVED | 2026-03-31 | WF-000283 | NA | 2026-04-04 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-002231 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-31 | Traf Grp-TRANSMIT-000008 | NA | Consultant | Secondary Consent Loading Management Plan | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected : Doc. No Error |  | 2026-03-31 | KPTG-TRANSMIT-000995 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-31 | Traf Grp-TRANSMIT-000009 | NA | Consultant | Sustainable Transport Plan for Secondary Consent Application | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected : Doc. No Error |  | 2026-03-31 | KPTG-TRANSMIT-0009994 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-31 | Traf Grp-TRANSMIT-000010 | NA | Consultant | Traffic Engineering Review for Secondary Consent Application | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected : Doc. No Error |  | 2026-03-31 | KPTG-TRANSMIT-000992 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-31 | Traf Grp-TRANSMIT-000011 | NA | Consultant | Road Safety Audit for Secondary Consent Application | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected : Doc. No Error |  | 2026-03-31 | KPTG-TRANSMIT-000993 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-31 | HVHD-TRANSMIT-000006 | NA | Consultant | Sustainability Management Plan | 0 | 1 | 0 | NA | APPROVED | 2026-03-31 | WF-000284 | NA | 2026-04-04 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-001030 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-31 | Civilex-TRANSMIT-000060 | NA | Trade Partner | Material Procurement Missing | 0 | 1 | 0 | KPTG-IntCorr-000547 | APPROVED | 2026-04-10 | WF-000302 | NA | 2026-04-14 |  | Clarification from ENZO | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-001470 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-31 | PCForm-TRANSMIT-000123 | NA | Trade Partner | Level 3 Precast Propping Design & Plan | 1 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected : Document attachment wrong |  | 2026-03-31 | DRAFT-006706 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-31 | PCForm-TRANSMIT-000124 | NA | Trade Partner | Tec Grout HS Ultra | 0 | 1 | 0 | NA | APPROVED | 2026-03-31 | WF-000285 | NA | 2026-04-04 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-001025 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-10 | Auspan-TRANSMIT-000019 | NA | Trade Partner | Precast shop drawing for approval. Ground floor panel 0G436. | 1 | 0 | 0 | NA | REJECTED | 2025-12-10 |  |  |  |  | Wrong title guide-KPTG-TRANSMIT-000313 Kapitol initiated an Internal Workflow-WF-000077 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-01 | A.S.H.-TRANSMIT-000077 | NA | Trade Partner | CD2 Angled column connection drawing update | 1 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 210 | 2026-04-08 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-001381 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-04-01 | Nilsen3-TRANSMIT-000084 | NA | Trade Partner | Sample submission | 0 | 1 | 0 | NA | APPROVED | 2026-04-01 | WF-005110 | NA | 2026-04-10 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-016094 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-01 | DS-TRANSMIT-000108 | NA | Trade Partner | HYD As Built Drawings | 10 | 0 | 0 | NA | REJECTED | [5 empty] | Issues with Revision, Workflow terminated and sent back to Originator for resubmission. |  | 2026-04-01 | KPTG-SADV-004593 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-01 | NXT-TRANSMIT-001467 | NA | Trade Partner | NextDC M3 Stage 4 LVSB - MSB_USB type 2 updated drawings and CRS for Review | 1 | 0 | 0 | NA | APPROVED | 2026-04-01 | WF-005111 | NA | 2026-04-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-01 | PARR-TRANSMIT-000152 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - Schematics and Control panel - IFA | 3 | 0 | 0 | NA | APPROVED | 2026-04-01 | WF-005112 | NA | 2026-04-17 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-015561 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-31 | CRSol-TRANSMIT-000083 | NA | Trade Partner | M3S4 CRS SMW Drawings - Issued for Construction - Zones C1 | 10 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 2706 | 2026-04-12 |  | The WF 2701 has been terminated and reissued via new template as requested by Isabella | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-018984 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-01 | WilsonPD-TRANSMIT-000174 | SPARK-CRFI-KPG-000436 | Trade Partner | Hydraulic Services - Level 1 Zone C Water Layout | 1 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 211 | 2026-04-08 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-000679 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-01 | NXT-TRANSMIT-001469 | NA | Trade Partner | Fwd: P2685 - NDC M3 - Stage 4 - Battery Rooms - Wall-mounted Drive - IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-01 | KPTG-TRANSMIT-015364 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-01 | D&E-TRANSMIT-000549 | NA | Trade Partner | NXM3S2 - Lower Ground - High & Low Level Mechanical Pipe Layout Zones - Issued As BUILT | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with a version of document. |  | 2026-04-01 | KPTG-SADV-004592 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-01 | PARR-TRANSMIT-000151 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - Mitsubishi HVAC TDP - IFA | 0 | 2 | 0 | NA | APPROVED | 2026-04-01 | WF-005114 | NA | 2026-04-06 |  | NXT-TRANSMIT-001470 | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-015499 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-10 | Altaire-TRANSMIT-000045 | NA | Trade Partner | Dry Fire L2/L3 Script Submission M3 Stage 2 For Approval | 0 | 8 | 0 | NA | APPROVED | 2025-11-17 | NA | WF-003328 | 2026-01-20 |  |  | 2026-01-19 | 2026-01-20 | KPTG-TRANSMIT-011630 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-31 | Nilsen3-TRANSMIT-000083 | NA | Trade Partner | Re NXM3S4 Nilsen ELC Shop Drawings | 7 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 2697 | 2026-04-04 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-018762 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-31 | CRSol-TRANSMIT-000083 | NA | Trade Partner | M3S4 CRS SMW Drawings - Issued for Construction | 10 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 2701 | 2026-04-04 | [5 empty] | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-26 | PARR-TRANSMIT-000145 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - TDP - IFA | 0 | 7 | 0 | NA | APPROVED | 2026-03-26 | WF-005016 | NA | 2026-04-10 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-01 | SMEPS-TRANSMIT-000176 | NA | Trade Partner | Shop Drawing Telecomunications IFA 3 | 1 | 0 | 0 | NA | APPROVED | 2026-04-01 | WF-000332 | NA | 2026-04-06 |  | NA | 2026-04-07 | 2026-04-08 | KPTG-TRANSMIT-000705 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-01 | SKS Tech-TRANSMIT-000074 | NA | Trade Partner | Re: SKS - IFC tech data submissions | 0 | 10 | 0 | NA | REJECTED | [7 empty] | 2026-04-01 | KPTG-RFI-007112 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-01 | D&E-TRANSMIT-000192 | SPARK-CRFI-KPG-000466 | Trade Partner | MWYCCB - LEVEL 1 - DUCTWORK LAYOUT ZONE 6 & 7 + ROOF LEVEL SOUTH SECTIONS - Issued For Approval | 2 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 212 | 2026-04-08 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-000753 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-31 | OveArup-TRANSMIT-000030 | NA | Consultant | Vertical Transportation Performance Specification | 0 | 1 | 0 | KPTG-TRANSMIT-001004 | REJECTED | [5 empty] | Rejected : Doc. No Error |  | 2026-03-31 | KPTG-TRANSMIT-001004 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-31 | OveArup-TRANSMIT-000031 | NA | Consultant | Vertical Transportation Performance Specification | 0 | 1 | 0 | KPTG-TRANSMIT-001005 | REJECTED | [5 empty] | Rejected : Doc. No Error |  | 2026-03-31 | KPTG-TRANSMIT-001005 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-01 | SMEPS-TRANSMIT-000177 | NA | Trade Partner | SME Shop Drawing Telecomunications IFA | 1 | 0 | 0 | NA | APPROVED | 2026-04-01 | WF-000333 | NA | 2026-04-07 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-000709 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-01 | SMEPS-TRANSMIT-000178 | NA | Trade Partner | Shop Drawing Telecommunications IFA | 1 | 0 | 0 | NA | APPROVED | 2026-04-01 | WF-000334 | NA | 2026-04-07 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-000712 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-10 | Tradetec-TRANSMIT-000296 | NA | Trade Partner | Penstock Valve Shop Drawings - PS1100, PS150, PS300 | 3 | 0 | 0 | NA | REJECTED | [5 empty] | The attached documents under each document number looks incorrect for the submission |  | 2025-12-10 | KPTG-DA-003848 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-01 | Leemark-TRANSMIT-000023 | SPARK-CRFI-KPG-000638 | Trade Partner | Transmittal of Fire Shop Drawings - For Approval | 4 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 213 | 2026-04-08 |  |  |  | 2026-04-16 | KPTG-TRANSMIT-000648 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-01 | PARR-TRANSMIT-000048 | NA | Trade Partner | Fuel Services - L4 CABLE B GA | 2 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 1177 | 2026-04-03 |  | TERMINATED | 2026-04-23 | 2026-04-23 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-01 | D&E-TRANSMIT-000550 | NA | Trade Partner | NXM3S2 - Ground - Mechanical Pipe Layout Zones 1 to 5 - Issued AS BUILT | 5 | 0 | 0 | NA | REJECTED | [5 empty] | The revised FC version of an As-Built drawing was not received. |  | 2026-04-01 | KPTG-DA-005806 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-01 | Stowe-A-TRANSMIT-000542 | NA | Trade Partner | Stowe - Tech Data Submission - External Lighting | 0 | 1 | 0 | NA | APPROVED | 2026-04-01 | WF-005121 | NA | 2026-04-14 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-016650 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-01 | KPTG-INTCOM-000257 | NA | Consultant | Door Drawings | 13 | 0 | 0 | NA | APPROVED | 2026-04-01 | WF-000689 | NA | 2026-04-06 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-002179 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-31 | Rinco-TRANSMIT-000004 | NA | Trade Partner | DLD - Reupload docs on Aconex | 87 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 389, 390 | 2026-04-09 |  | closed out on 10-04-2026 due to VPN issue | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-001089, KPTG-TRANSMIT-001090 | Closed | 87 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-31 | Civilex-TRANSMIT-000061 | NA | Trade Partner | Grout Spec for PT Truncation | 0 | 1 | 0 | KPTG-IntCorr-000550 | APPROVED | 2026-03-31 | WF-000287 | NA | 2026-04-03 |  | CLARIFICATION FROM MICHAEL | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-001068 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-01 | Stowe-A-TRANSMIT-000543 | NA | Trade Partner | STOWE - HV OPERATING & MAINTENANCE PROCEDURES - IFA-1 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issued with document number inside the document. |  | 2026-04-01 | KPTG-DA-005805 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-23 | KETE-TRANSMIT-000123 | NA | Trade Partner | Submission –sample register | 0 | 4 | 0 | NA | APPROVED | 2026-03-23 | WF-000678 | NA | 2026-03-26 |  | Only required for 2 review. | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-002153 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-01 | D&E-TRANSMIT-000193 | SPARK-CRFI-KPG-000466 | Trade Partner | MWYCCB - ROOF LEVEL - DUCTWORK & PENETRATION LAYOUTS ZONE 6 & ZONE 7 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 214 | 2026-04-08 |  |  | 2026-04-17 | 2026-04-27 | KPTG-TRANSMIT-000738 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-08 | Facx-TRANSMIT-000008 | NA | Trade Partner | Expanded Mesh Detail - Rev - 1 | 7 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document number and revision | 2025-12-10 | 2025-12-10 | KPTG-DA-003847 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-01 | ARCST-TRANSMIT-000243 | NA | Trade Partner | HV Steel Drawings issued for Construction | 57 | 0 | 0 | NA | REJECTED | [5 empty] | IFA drawings are still under review and IFA version of 14 drawings in not yet received. |  | 2026-04-01 | KPTG-SADV-004607 | Closed | 57 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-01 | NXT-WTRAN-002039 | NA | Trade Partner | Stage 2 Office Fans | 0 | 1 | 0 | NA | APPROVED | 2026-04-01 | WF-004852 | NA | 2026-04-01 |  |  |  | 2026-04-01 | KPTG-TRANSMIT-015405 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-01 | Hames-TRANSMIT-000147 | NA | Consultant | Latest revision | 16 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 1179 | 2026-04-03 |  | close out process on 10-04-2026 due to VPN issue | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-003370 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-01 | KPTG-TRANSMIT-015404 | NA | Trade Partner | SP3 ACG O&M Manual | 0 | 1 | 0 | NA | APPROVED | 2026-04-01 | WF-005124 | NA | 2026-04-09 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016483 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-01 | KPTG-TRANSMIT-015406 | NA | Trade Partner | Altaire O&M SP3 - NDC Workflow | 0 | 1 | 0 | NA | APPROVED | 2026-04-01 | WF-005125 | NA | 2026-04-09 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-015689 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-01 | KPTG-TRANSMIT-015407 | NA | Trade Partner | S2 - O&M Manual - Niu Edge Review | 0 | 1 | 0 | NA | APPROVED | 2026-04-01 | WF-005853 | NA | 2026-06-04 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018493 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-01 | KPTG-TRANSMIT-015408 | NA | Trade Partner | S2 SP3 - O&M Manual - Axis NDC Review | 0 | 1 | 0 | NA | APPROVED | 2026-04-01 | WF-005127 | NA | 2026-04-09 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-015699 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-24 | Stowe-A-TRANSMIT-000529 | NA | Trade Partner | STOWE - AS BUILTS - LOWER GROUND - 24.03.2026 - TEL | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with drawing status. |  | 2026-04-01 | KPTG-SADV-004608 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-01 | D&E-TRANSMIT-000551 | NA | Trade Partner | Re - ISSUED FOR APPROVAL - CHW & CT SCHEMATIC | 4 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 2714 | 2026-04-09 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-016813 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-01 | D&E-TRANSMIT-000548 | NA | Trade Partner | IW Pumps - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-01 | (WF-005118 | NA | 2026-04-24 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-016051 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-09 | KPTG-IntCorr-007562 | NA | Consultant | URGENT: Upload & Transmit Documents | 0 | 4 | 0 | NA | APPROVED |  | NA | NA |  |  | Shared with the client |  | 2025-12-10 | KPTG-TRANSMIT-010786 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-01 | RDSBIM-TRANSMIT-000259 | NA | Trade Partner | NXM3S4 - GROUND FLOOR-C-G-052 CLEANER FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 2712 | 2026-04-03 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-015791 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-01 | RDSBIM-TRANSMIT-000258 | NA | Trade Partner | NXM3S4 - LEVEL-1-C-1-019 ACC WC (LH) FLOOR FINISHES LAYOUT AND ELEVATION | 1 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 2710 | 2026-04-03 |  |  |  | 2026-04-13 | KPTG-TRANSMIT-015774 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-01 | RDSBIM-TRANSMIT-000257 | NA | Trade Partner | NXM3S4 - GROUND FLOOR-C-G-023 CLEANERS-FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 2708 | 2026-04-03 |  |  |  | 2026-04-13 | KPTG-TRANSMIT-015760 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-01 | JCBa-TRANSMIT-000081 | NA | Trade Partner | : STRUCTURAL SETOUT PLANS : OVERALL & ZONE PLANS FOR L3 & L4 | 12 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 647 | 2026-04-02 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-001189 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-01 | RDSBIM-TRANSMIT-000041 | NA | Trade Partner | GREYSTAR LEVEL 01 CONCRETE PROFILE PLAN AND SECTION | 7 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 649 | 2026-04-07 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-01 | Auspan-TRANSMIT-000183 | NA | Trade Partner | : Re: Precast shop drawings for approval. Levels 2, 3. | 90 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 651 | 2026-04-08 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-001536 | Closed | 90 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-01 | M.2-TRANSMIT-000018 | NA | Trade Partner | : Electrical Services Ground floor Zone 1 penetration updates | 1 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 645 | 2026-04-08 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-001233 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-01 | Auspan-TRANSMIT-000184 | NA | Trade Partner | Precast shop drawings for construction. Ground floor and level 1 | 35 | 0 | 0 | KPTG-IntCorr-000427 | REJECTED | [5 empty] | ifc - Prev. Rev. is in review for 2 drawings; one dewing previous rev. is Rejected, Waiting for Kapitol Advise. KPTG-IntCorr-000427 Rejected, Trade Partner to exclude under review drawings and rejected drawings from IFC package . |  | 2026-04-02 | KPTG-SADV-001707 | Closed | 35 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-01 | Auspan-TRANSMIT-000185 | NA | Trade Partner | Precast shop drawings for approval. Ground floor and level 1. | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect drawing - DRAFT-00536. |  | 2026-04-01 | DRAFT-00536. | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-31 | SCG2014-TRANSMIT-000003 | NA | Consultant | SCEC ZONE STATEMENT OF COMPLIANCE - DHA7 DHA8 | 0 | 1 | 0 | NA | APPROVED | [5 empty] | Update register only |  | 2026-04-07 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-04-01 | VERTIV-TRANSMIT-000027 | NA | Trade Partner | NEXTDC M3 ST-1&2 CDU FD (revised as per BVPI comments) | 0 | 1 | 0 | KPTG-IntCorr-003434 | APPROVED |  | NA | NA |  |  | Distribution only |  | 2026-04-02 | KPTG-TRANSMIT-002805 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-01 | LVPG-TRANSMIT-000026 | NA | Trade Partner | LVPG - Car Park Ramp Trench Grates | 0 | 1 | 0 | NA | APPROVED | 2026-04-01 | WF-000347 | NA | 2026-04-06 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-001236 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-01 | LVPG-TRANSMIT-000027 | NA | Trade Partner | LVPG-HY-TECH-040 - Trench Grates | 0 | 1 | 0 | NA | APPROVED | 2026-04-01 | WF-000349 | NA | 2026-04-07 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-01 | Rinco-TRANSMIT-000038: | NA | Consultant | Structural - Loading plans | 2 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 653 | 2026-04-02 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-001413 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-01 | JCBa-TRANSMIT-000082 | NA | Consultant | STRUCTURAL SETOUT PLANS : 5th FLOOR - ALL ZONES | 5 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 655 | 2026-04-02 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-001292 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-01 | RDSBIM-TRANSMIT-000042 | NA | Trade Partner | GREYSTAR GROUND FLOOR CONCRETE PROFILE KEY PLAN | 3 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 657 | 2026-04-07 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-001267 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-01 | RDSBIM-TRANSMIT-000048 | NA | Trade Partner | 671CHP BASEMENT 2 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 386 | 2026-04-06 |  | Review voided as requested by RDS to update drawings,. Drawings superseded by RDS. | 2026-04-22 | 2026-04-22 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-01 | RDSBIM-TRANSMIT-000049 | NA | Trade Partner | 671CHP GROUND LEVEL TO ROOF CORE WALL LAYOUT AND ELEVATION | 9 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 388 | 2026-04-06 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-000798 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-01 | crossfir-TRANSMIT-000006: | NA | Trade Partner | Wet Fire - Basement 04, 03 & 02 , IFA | 3 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 390 | 2026-04-07 |  | ACC Review Voided by Kapitol DM. | 2026-04-20 | 2026-04-20 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-01 | KPTG-SADV-006339 | NA | Trade Partner | Workflow Request - Tivoli Samples | 0 | 1 | 0 | NA | APPROVED | 2026-04-01 | WF-000981 | NA | 2026-04-07 |  | NA | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-003108 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-09 | WSP ANZ-TRANSMIT-000022 | NA | Consultant | WSP - PDF Drawings - Issued for Permit Interim-FUL | 20 | 0 | 0 | NA | APPROVED | 2025-12-10 |  | 126 | 2025-12-15 |  |  | 2025-12-17 | 2025-12-18 | KPTG-TRANSMIT-000395 | Closed | 20 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-01 | KPTG-SADV-006340 | NA | Trade Partner | Tiling Workflows | 0 | 3 | 0 | NA | APPROVED | 2026-04-01 | WF-000986 | NA | 2026-04-07 |  | File supersede and WF terminated. |  |  |  | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-01 | LANSA-TRANSMIT-000103 | NA | Trade Partner | Levels 09 & 11 Draiange IFC with Coordination Changes | 4 | 0 | 0 | NA | REJECTED | [5 empty] | revision number is mismatch |  | 2026-04-01 | KPTG-IntCorr-001626 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-01 | ARCH-TRANSMIT-000144 | NA | Consultant | MLC - SPR - AQC - Drawing Update | 8 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 482 | 2026-04-08 |  |  | 2026-04-02 | 2026-04-02 | KPTG-SADV-004016 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-31 | MLAW-TRANSMIT-000002 | NA | Trade Partner | THERMACORD SLIDING DOORS - SHOP DRAWINGS | 7 | 0 | 0 | NA | REJECTED | [5 empty] | Document Numberings are incorrect, requested to resubmit:KPTG-SADV-003611 |  | 2026-03-31 | KPTG-SADV-003611 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-05 | Entire M-TRANSMIT-000005 | NA | Trade Partner | Mechanical shop drawings issued for approval | 4 | 0 | 0 | NA | APPROVED | 2026-03-12 | WF-000047 | NA | 2026-03-17 |  |  | 2026-04-01 | 2026-04-01 | KPTG-TRANSMIT-000270 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-01 | ASV-TRANSMIT-000046 | NA | Trade Partner | Sub Soil Drainage | 0 | 1 | 0 | NA | APPROVED | 2026-04-01 | WF-000442 | NA | 2026-04-10 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-002484 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-01 | ASV-TRANSMIT-000047 | NA | Trade Partner | Flow Meter and Pit Comments actioned | 0 | 1 | 0 | NA | APPROVED | 2026-04-01 | WF-000443 | NA | 2026-04-10 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-002347 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-01 | VIA Arch-TRANSMIT-000083 | NA | Consultant | M2 S9 GF Concrete Profile Rev amendment | 1 | 0 | 0 | NA | APPROVED | 2026-04-01 | NA | 589 | 2026-04-08 |  |  | 2026-04-14 | 2026-04-14 | KPTG-TRANSMIT-002126 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-04-02 | Nilsen3-TRANSMIT-000088 | NA | Trade Partner | SUPA 80 Frame | 0 | 1 | 0 | NA | APPROVED | 2026-04-02 | WF-005129 | NA | 2026-04-07 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-02 | Highbu-TRANSMIT-000045 | NA | Trade Partner | Mezz and Level 1 Penetration Layout - FOR INFO | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-SADV-003630-As per Mark’s direction, The register will be updated and shared with the architect and the three parties. |  | 2026-04-02 | KPTG-SADV-003630 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-09 | WSP ANZ-TRANSMIT-000022 | NA | Consultant | WSP - PDF Drawings - Issued for Permit Interim-VRT | 6 | 0 | 0 | NA | APPROVED | 2025-12-11 |  | 130 | 2025-12-15 |  |  | 2025-12-17 | 2025-12-18 | KPTG-TRANSMIT-000389 | Closed | 6 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-02 | Appselec-TRANSMIT-000049 | NA | Trade Partner | DB Shop Drawings For Approval | 3 | 0 | 0 | NA | APPROVED | 2026-04-02 | WF-000109 | NA | 2026-04-07 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-000330 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-02 | D&E-TRANSMIT-000552 | NA | Trade Partner | NXM3S2 - Level 01 - Mechanical Duct Layout - Zone 4 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-02 | NA | 4057 | 2026-04-15 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-015567 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-01 | KETE-TRANSMIT-000125 | NA | Trade Partner | Kete - Update Cast-in Channels Layout L06-L09 | 4 | 0 | 0 | NA | APPROVED | 2026-04-02 | NA | 618 | 2026-04-09 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-002598 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-02 | Tradetec-TRANSMIT-000409 | NA | Trade Partner | Tech Data - Site Wide - Mayfield Thermal Sand | 0 | 1 | 0 | NA | APPROVED | 2026-04-02 | WF-005133 | NA | 2026-04-09 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-016354 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-01 | PCForm-TRANSMIT-000126 | NA | Trade Partner | Reid coupler board sample submission for review | 0 | 1 | 0 | NA | APPROVED | 2026-04-01 | WF-000288 | NA |  |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-001096 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-01 | WAM-TRANSMIT-000743 | NA | Consultant | Ground Level GA Plan & Door Schedule - Fire door Update | 2 | 0 | 0 | KPTG-IntCorr-000554 | APPROVED | [5 empty] | clarification from Bradley- closed out on 10-04-2026 due to VPN issue | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-001091 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-02 | DS-TRANSMIT-000109 | NA | Trade Partner | HYD As Built Drawings | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Issues with revision of a drawing. |  | 2026-04-02 | KPTG-SADV-004617 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-02 | KEECEPRO-TRANSMIT-000042 | NA | Trade Partner | Lighting Control IFC Drawings | 1 | 0 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-02 | KEECEPRO-TRANSMIT-000042 | NA | Trade Partner | Lighting Control IFC Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-04-02 | WF-000470 | NA | 2026-04-07 | [5 empty] | Open | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-02 | WEBBAUST-TRANSMIT-000068 | NA | Trade Partner | B18 HFF - Security drawing update | 3 | 0 | 0 | NA | APPROVED | 2026-04-02 | WF-000471 | NA | 2026-04-07 |  |  | 2026-04-14 | 2026-04-14 | DRAFT-009709 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-09 | WSP ANZ-TRANSMIT-000022 | NA | Consultant | WSP - PDF Drawings - Issued for Permit Interim-TLE | 43 | 0 | 0 | NA | APPROVED | 2025-12-11 |  | 132 | 2025-12-15 |  |  | 2025-12-21 | 2025-12-19 | KPTG-TRANSMIT-000401 | Closed | 43 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-02 | WPD-TRANSMIT-000079 | NA | Trade Partner | Hydraulic shop drawing re-issued for construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-02 | DRAFT-009604 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-03-19 | JCBa-TRANSMIT-000239 | NA | Consultant | GAs For Construction | 30 | 0 | 0 | NA | APPROVED | 2026-04-02 | WF-000987 | 554 | 2026-04-05 |  |  | 2026-04-02 | 2026-04-02 | DRAFT-016532 | Closed | 30 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-02 | KPTG-TRANSMIT-015273 | NA | Trade Partner | Fwd: Final (WF-003571) S2 I TECH DATA I CONSULTANT REVIEW I ARC ¦ PROLMC-TRANSMIT-000016 - Proline sealant tech data | 0 | 1 | 0 | NA | APPROVED | 2026-04-02 | WF-005136 | NA | 2026-04-09 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-02 | D&E-TRANSMIT-000554 | NA | Trade Partner | NXM3S4 - INDUSTRIAL WATER SCHEMATIC - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-04-02 | NA | 2720 | 2026-04-10 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-016812 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-02 | SMEPS-TRANSMIT-000174 | SPARK-CRFI-KPG-000310 | Trade Partner | General Notes IFC | 1 | 0 | 0 | NA | APPROVED | 2026-04-02 | NA | 215 | 2026-04-09 |  |  | 2026-04-17 | 2026-04-30 | KPTG-TRANSMIT-000765 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-01 | Tradetec-TRANSMIT-000408 | NA | Trade Partner | Re: Stage 4 - IFA - LV: 36, 37, 50, 51, 52, 53, 54, 55 | 8 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due to incorrect revision number and drawing number |  | 2026-04-01 | KPTG-DA-005803 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-01 | KPTG-TRANSMIT-015378 | NA | Consultant | NXM3S4 - Drawings to be resubmitted for review | 0 | 2 | 0 | NA | APPROVED | 2026-04-01 | WF-005123 | NA | 2026-04-17 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018507 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-01 | Bianco-TRANSMIT-000058 | NA | Trade Partner | Re: Connection to Canopy - FOR APPROVAL | 6 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due ti incorrect reason mention in aconex |  | 2026-04-01 | KPTG-DA-005807 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-02 | TATE_-TRANSMIT-000013 | NA | Trade Partner | Tate - Tech Data - Batch 2 | 0 | 2 | 0 | NA | APPROVED | 2026-04-02 | WF-000110 | NA | 2026-04-07 |  | MEL11-TATE-A-TDS-005-0 IS SUBMITTED ALONG WITH TATE-TRANSMIT-000014-WF-000110 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-02 | TATE_-TRANSMIT-000014 | NA | Trade Partner | Security Fixings tech data sheet. | 0 | 1 | 0 | NA | APPROVED | 2026-04-02 | WF-000110 | NA | 2026-04-07 |  | MEL11-TATE-A-TDS-004-0 IS SUBMITTED ALONG WITH TATE -TRANSMIT-000013 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-01 | Entire M-TRANSMIT-000006 |  | Trade Partner | Fan Coil Unit & Condenser Technical Data | 0 | 1 | 0 |  | APPROVED | 2025-12-01 | WF-003446 |  | 2025-12-11 |  | The register has been updated. If any further action is required, the coordinator will inform. | 2025-12-15 | 2025-12-15 | KPTG-TRANSMIT-010902 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-01 | Jordan-TRANSMIT-000106 | N/A | Trade Partner | Level 04 - Plumbing Setouts - For Approval | 1 | 0 | 0 | NA | APPROVED | 2025-12-01 | N/A | 661 | 2025-12-04 |  |  | 2025-12-09 | 2025-12-09 | KPTG-TRANSMIT-002230 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-09 | WSP ANZ-TRANSMIT-000022 | NA | Consultant | WSP - PDF Drawings - Issued for Permit Interim-HYD | 70 | 0 | 0 | NA | APPROVED | 2025-12-11 |  | 128 | 2025-12-15 |  |  | 2025-12-18 | 2025-12-19 | KPTG-TRANSMIT-000398 | Closed | 70 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-02 | RDSBIM-TRANSMIT-000261 | NA | Trade Partner | LEVEL 01-C-1-020 CLEANER FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-04-02 | NA | 2722 | 2026-04-08 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-017515 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-02 | D&E-TRANSMIT-000556 | NA | Trade Partner | ISSUED FOR APPROVAL - LEVEL 1 MECH_ELEC ZONES 1 TO 10 | 10 | 0 | 0 | NA | APPROVED | 2026-04-02 | NA | 2724 | 2026-04-09 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016524 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-02 | SMEPS-TRANSMIT-000179 | NA | Trade Partner | SME Shop Drawing Electrical IFC C | 4 | 0 | 0 | NA | APPROVED | 2026-04-02 | WF-000335 | NA | 2026-04-07 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-000693 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-02 | Altaire-TRANSMIT-000008 | NA | Trade Partner | MEL05C4 - Dry Fire Shop Drawings (For Construction) (2) | 1 | 0 | 0 | NA | APPROVED | 2026-04-02 | WF-000336 | NA | 2026-04-07 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-000696 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-02 | D&E-TRANSMIT-000553 | NA | Trade Partner | IW Filtration & Pressure system FAT Checklists - IFC | 0 | 2 | 0 | NA | APPROVED | 2026-04-02 | WF-005142 | NA | 2026-04-13 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-017726 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-02 | D&E-TRANSMIT-000559 | NA | Trade Partner | Pumps Rev B - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-02 | WF-005147 | NA | 2026-04-28 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-016435 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-02 | SMEPS-TRANSMIT-000230 | NA | Trade Partner | JEMENA EASEMENT | 2 | 0 | 0 | NA | APPROVED | 2026-04-02 | WF-005148 | NA | 2026-04-09 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-015936 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-02 | D&E-TRANSMIT-000560 | NA | Trade Partner | IW Tanks - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-02 | WF-005150 | NA | 2026-04-28 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-016345 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-02 | OveArup-WTRAN-001385 | NA | Trade Partner | SP3 STOWE O&M MANUAL | 0 | 1 | 0 | NA | APPROVED | 2026-03-27 | WF-005026 | NA | 2026-04-03 |  |  | 2026-04-02 | 2026-04-02 | KPTG-TRANSMIT-015467 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-02 | D&E-TRANSMIT-000194 | SPARK-CRFI-KPG-000640 | Trade Partner | FLANGE PIPE CONECTIONS | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-000879 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-11 | SC-TRANSMIT-000032 | NA | Trade Partner | Secondary Steel IFC | 9 | 0 | 0 | NA | APPROVED | [5 empty] | IFC Drawings, Transmitted to Trade Partners and Consultants |  | 2025-12-11 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-02 | ADP-TRANSMIT-000291 | NA | Consultant | MEL741 - Stage 4 Sitewide Schematics | 3 | 0 | 0 | NA | APPROVED | 2026-04-02 | NA | 2729 | 2026-04-07 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-015840 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-02 | Coen-TRANSMIT-000002 | NA | Trade Partner | Thread bar alternative to REID | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with document number |  | 2026-04-02 | DRAFT-000991 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-02 | PARR-TRANSMIT-000155 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - DFS COMMISSIONING PLAN - IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-02 | KPTG-TRANSMIT-015471 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-02 | TATE_-TRANSMIT-000011 | NA | Trade Partner | TATE - SHOP DRAWINGS - HACS - IFC | 15 | 0 | 0 | NA | APPROVED | 2026-04-02 | WF-000111 | NA | 2026-04-06 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-000294 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-02 | PARR-TRANSMIT-000156 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - Damper Actuator | 0 | 1 | 0 | NA | APPROVED | 2026-04-02 | WF-005153 | NA | 2026-04-07 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-015844 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-02 | TATE_-TRANSMIT-000012 | NA | Trade Partner | Re: Tate - SCEC Pan Penetration Details | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Document number and Drawing status are incorrect, requested to resubmit:KPTG-IntCorr-000229 |  | 2026-04-02 | KPTG-IntCorr-000229 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-02 | 4DW-TRANSMIT-000166 | NA | Consultant | Structural Drawing Update S002_101 | 1 | 0 | 0 | NA | APPROVED | 2026-04-02 | NA | 483 | 2026-04-09 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-04-02 | KPTG-IntCorr-003381 | NA | Trade Partner | Dry Fire O&M, | 0 | 1 | 0 | NA | APPROVED | 2026-04-02 | WF-000992 | NA | 2026-04-09 |  | Terminated requested by Andrew ,and reissued-WF-000995 |  | 2026-04-10 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-02 | D&E-TRANSMIT-000555 | NA | Trade Partner | NXM3S2 - Level 01 - Mechanical Pipe Sections - Data Hall B6 - Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-02 | NA | 4056 | 2026-04-09 |  | Due to VPN issues close out processed on 10/04/2026 | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-015658 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-02 | Bianco-TRANSMIT-000059 | NA | Trade Partner | Updated Precast IFC | 45 | 0 | 0 | NA | APPROVED | 2026-04-02 | WF-005144 | NA | 2026-04-13 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-11 | Highbu-TRANSMIT-000107 | NA | Trade Partner | Revised drawing | 1 | 0 | 0 | NA | APPROVED | [5 empty] | IFC Drawing-Transmitted to Trade partners and consultants |  | 2025-12-11 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-02 | D&E-TRANSMIT-000561 | NA | Trade Partner | Admin Office Mechanical Layout - Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-02 | NA | 4059 | 2026-04-09 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-02 | IVS-TRANSMIT-000357 | NA | Consultant | Stage 2 - Southern Retaining Wall Construction Issue (Revised as clouded) | 1 | 0 | 0 | NA | APPROVED | 2026-04-02 | NA | 4061 | 2026-04-06 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-015707 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-02 | SES AU-TRANSMIT-000005 | NA | Trade Partner | Security Tech Data- IFC | 0 | 18 | 0 | NA | REJECTED | [5 empty] | Rejected, Revision of document are incorrect and also noted submitted documenta's are reviewed document with stamp, requested ro resubmit:KPTG-IntCorr-000230 |  | 2026-04-02 | KPTG-IntCorr-000230 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-02 | KPTG-TRANSMIT-015466 | NA | Trade Partner | Structural Steel O&M Manual - Review | 0 | 1 | 0 | NA | APPROVED | 2026-04-02 | WF-005158 | NA | 2026-04-22 |  | Terminated and submitted in new template. | 2026-06-30 | 2026-06-30 | KPTG-IntCorr-015396 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-02 | KPTG-TRANSMIT-015456 | NA | Trade Partner | Waterproofing O&M Manual - Review | 0 | 1 | 0 | NA | APPROVED | 2026-04-02 | WF-005852 | NA | 2026-06-04 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018511 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-02 | Auspan-TRANSMIT-000186 | NA | Trade Partner | Update already IFCed shop drawings for construction | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC -as advised, no review required; Register and distribute. |  | 2026-04-02 | KPTG-TRANSMIT-001203 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-02 | Auspan-TRANSMIT-000187 | NA | Trade Partner | : Re: Panel 0G2057 Size | 1 | 0 | 0 | NA | APPROVED | 2026-04-02 | NA | 660 | 2026-04-08 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-001323 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-02 | PCForm-TRANSMIT-000048: | NA | Trade Partner | Basement zone 1&2 propping plan | 1 | 0 | 0 | KPTG-IntCorr-000431 | APPROVED |  | NA | NA |  |  | No Review, Update register only. KPTG-IntCorr-000435 |  | 2026-04-08 | KPTG-IntCorr-000435 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-02 | INDS-TRANSMIT-000015: | NA | Trade Partner | Hydraulic Calculations & Noded Drawings | 0 | 3 | 0 | NA | APPROVED | 2026-04-02 | WF-000357 | NA | 2026-04-09 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-001276 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-02 | Auspan-TRANSMIT-000188 | NA | Trade Partner | Re: Precast shop drawings for approval. Ground floor and level 1. | 6 | 0 | 0 | NA | APPROVED | 2026-04-02 | NA | 662 | 2026-04-08 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-001326 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-11 | ECBS-TRANSMIT-000040 | NA | Trade Partner | IN81 Material Data Sheet for review | 0 | 1 | 0 | NA | APPROVED | 2025-12-11 | WF-000667 |  | 2025-12-15 |  | As per the direction from the Project coordinator, workflow havs been terminated on 11.12.2025 |  | 2025-12-11 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-02 | POTTSENG-TRANSMIT-000018 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONE 5 LAYOUT | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Project coordinator returned to Trade Partner for clarification and update - |  | 2026-04-02 | DRAFT-005407 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-02 | ARCH-TRANSMIT-000038 | NA | Consultant | Concrete Profile Plan - External Plant | 1 | 0 | 0 | NA | APPROVED | [5 empty] | Issued For information only. To be updated in Aconex and ACC. No review required. (Outlook mail: RE: [External] FW: KPTG-DA-000287: DESIGN PROGRAM - KEY DATES ACNXREF<1uIuH6hZXcMNq8sdkUdulB>) |  | 2026-04-02 | KPTG-TRANSMIT-000126 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-02 | DS-TRANSMIT-000110 | NA | Trade Partner | HYD As Built Drawings | 8 | 0 | 0 | NA | APPROVED | 2026-04-02 | NA | 4063 | 2026-04-07 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-018811 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-02 | HDRAus-TRANSMIT-000448 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD (re-upload) | 4 | 1 | 0 | NA | APPROVED | 2026-04-02 | NA | 2734 | 2026-04-06 |  | “3 documents’ latest revision received in HDRAus-TRANSMIT-000449 transmittal; only 2 are in this review.” | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-015651 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-02 | PARR-TRANSMIT-000154 | NA | Trade Partner | Re: P2680 - NDC M3 Stage 4 - Fuel - BF DRAWINGS - IFC | 27 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision |  | 2026-04-02 | KPTG-TRANSMIT-015485 | Closed | 27 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-02 | PARR-TRANSMIT-000153 | NA | Trade Partner | Re: P2680 - NDC M3 Stage 4 - Fuel - TDP - IFC | 0 | 21 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech data |  | 2026-04-07 | KPTG-TRANSMIT-015490 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-02 | Tradetec-TRANSMIT-000413 | NA | Trade Partner | FC - Stage 4 South - HVP 36, 38, 39, 40 - CP27 | 5 | 0 | 0 | NA | APPROVED | 2026-04-02 | NA | 2731 | 2026-04-09 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-015666 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-02 | Tradetec-TRANSMIT-000412 | NA | Trade Partner | Stage 4 - IFA - LVP47 | 1 | 0 | 0 | NA | APPROVED | 2026-04-02 | NA | 2726 | 2026-04-10 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-016682 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-02 | SKS Tech-TRANSMIT-000075 | NA | Trade Partner | Re: SKS - IFC submissions | 0 | 12 | 0 | NA | REJECTED | [5 empty] | Incorrect revision |  | 2026-04-02 | KPTG-TRANSMIT-015460 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-02 | D&E-TRANSMIT-000558 | NA | Trade Partner | SSF System - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-02 | WF-005143 | NA | 2026-04-28 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-016329 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-11 | ECBS-TRANSMIT-000041 | NA | Trade Partner | Revise as per commented | 0 | 2 | 0 | NA | REJECTED | [5 empty] | updated tech data was received in ECBS-TRANSMIT-000041 |  | 2025-12-11 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-02 | Tradetec-TRANSMIT-000410 | NA | Trade Partner | Re: Stage 4 - IFA- LV: 36, 37, 50, 51, 52, 53, 54, 55 | 8 | 0 | 0 | NA | REJECTED | [5 empty] | INCORRECT REVISION |  | 2026-04-02 | KPTG-TRANSMIT-015439 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-04-02 | HDRAus-TRANSMIT-000086 | NA | Consultant | Stage 1 Phase 10 - No longer in use | 162 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer in use |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-02 | RDSBIM-TRANSMIT-000260 | NA | Trade Partner | NXM3S4 LEVEL 01-C-G-042 CLEANER FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-04-02 | NA | 2617 | 2026-04-07 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-015799 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-02 | ARCST-TRANSMIT-000245 | NA | Trade Partner | C3 East Roof Walkway - Issued for Approva | 179 | 0 | 0 | NA | REJECTED | [5 empty] | incompleteness in document numbers |  | 2026-04-02 | KPTG-TRANSMIT-015486 | Closed | 179 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-02 | HDRAus-TRANSMIT-000449 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 18 | 0 | 0 | NA | APPROVED | 2026-04-02 | NA | 2735 | 2026-04-06 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-015677 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-02 | Entire M-TRANSMIT-000018 | NA | Trade Partner | Mechanical IFC Transmittals | 0 | 11 | 0 | NA | APPROVED | 2026-04-02 | WF-000112 | NA | 2026-04-07 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-000354 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-02 | Entire M-TRANSMIT-000019 | NA | Trade Partner | Mechanical IFA Rev B Submission & Comments - Intumescent FDs & Pipe Fittings | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Rejected: Revision of Tech data needs to be changed. Requested to resubmit:KPTG-IntCorr-000231 |  | 2026-04-02 | KPTG-IntCorr-000231 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-02 | Entire M-TRANSMIT-000020 | NA | Trade Partner | Mechanical shop drawings IFC | 28 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing Status of two drawing are incorrect, requested to resubmit:KPTG-IntCorr-000232 |  | 2026-04-02 | KPTG-IntCorr-000232 | Closed | 28 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-02 | RDSBIM-TRANSMIT-000180 | NA | Trade Partner | LEVEL 01 PARTITION WALL LAYOUT | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2026-04-02 | DRAFT-016544 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-02 | ccair-TRANSMIT-000108 | NA | Trade Partner | Roof Mechanical Ductwork & Pipework Layout - IFC | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2026-04-02 | DRAFT-016546 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-11 | ECBS-TRANSMIT-000042 | NA | Trade Partner | Resubmission as per comments | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Revision of the Document is incorrect and requested to resubmit: KPTG-SADV-003117 |  | 2025-12-11 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-07 | Entire M-TRANSMIT-000021 | NA | Trade Partner | Mechanical shop drawings IFA | 8 | 0 | 0 |  | APPROVED | 2026-04-07 | WF-000114 | NA | 2026-04-10 |  |  | 2026-04-13 | 2026-04-14 | KPTG-TRANSMIT-000361 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-02 | ETNInd-TRANSMIT-000008 | NA | Trade Partner | Withdrawal of the Document. | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer in use document, just transmitted to trade & client |  | 2026-04-02 | KPTG-TRANSMIT-000284 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-02 | ETNInd-TRANSMIT-000009 | NA | Trade Partner | Withdrawal of the Document. | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | The Document is no longer in use. Just transmitted to trade and client-KPTG-TRANSMIT-000286 |  | 2026-04-02 | KPTG-TRANSMIT-000286 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-02 | WGAVIC-TRANSMIT-000096 | NA | Consultant | M2 - Stages 9, 10 and 11 Stair and Lift Roofs - Issued for Certification | 3 | 0 | 0 | NA | APPROVED | 2026-04-02 | NA | 593 | 2026-04-09 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-002227 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-02 | WGAVIC-TRANSMIT-000097 | NA | Consultant | M2 - Detail Updates - Issued for Construction | 2 | 0 | 0 | NA | APPROVED | 2026-04-02 | NA | 591 | 2026-04-09 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-002231 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-02 | GPSElec-TRANSMIT-000012 | NA | Trade Partner | NextDC Stage 9-12 switchboard - SWB testing Methodology | 0 | 1 | 0 | NA | APPROVED | 2026-04-02 | WF-000449 | NA | 2026-04-16 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-004481 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-02 | ELLISAIR-TRANSMIT-000005 | NA | Trade Partner | Heat Exchangers | 0 | 1 | 0 | NA | APPROVED | 2026-04-02 | WF-000448 | NA | 2026-04-16 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-002101 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-02 | ELLISAIR-TRANSMIT-000006 | NA | Trade Partner | Technical data submission - Pumps | 0 | 1 | 0 | NA | APPROVED | 2026-04-02 | WF-000450 | NA | 2026-04-16 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-002097 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-02 | ETNInd-TRANSMIT-000010 | NA | Trade Partner | MEL11 COLO4&5 DC And Signal Cable Schedules | 0 | 2 | 0 | NA | APPROVED | 2026-04-03 | WF-000113 | NA | 2026-04-08 |  |  | 2026-04-14 | 2026-04-14 | KPTG-TRANSMIT-000372 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-07 | PenskePS-TRANSMIT-000006 | NA | Trade Partner | Request to modify the document number and Revision MEL11 COLO4 & 5 - FAT & SAT Scripts | 0 | 4 | 0 |  | APPROVED | 2026-04-07 | WF-000118 | NA | 2026-04-10 |  |  |  | 2026-04-08 | KPTG-IntCorr-000241 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-11 | ECBS-TRANSMIT-000043 | NA | Trade Partner | Technical Data Submission | 0 | 5 | 0 | NA | APPROVED | 2025-12-11 | WF-000671 |  | 2025-12-17 |  |  |  | 2026-01-19 | KPTG-TRANSMIT-002115 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-07 | PenskePS-TRANSMIT-000004 | NA | Trade Partner | MEL11 COLO4 & 5 - tech data & drawings | 0 | 16 | 0 |  | APPROVED | 2026-04-07 | WF-000116 | NA | 2026-04-10 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-000299 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-02 | PenskePS-TRANSMIT-000005 | NA | Trade Partner | MEL11 COLO4 & 5 - tech data & drawings | 4 | 0 | 0 | KPTG-IntCorr-000236 | REJECTED | [5 empty] | kapitol Advice awaits:KPTG-IntCorr-000236: Rejected:KPTG-IntCorr-000236 |  | 2026-04-03 | KPTG-IntCorr-000236 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-01 | PROLMC-TRANSMIT-000027 | NA | Trade Partner | Proline Drawings IFC | 24 | 0 | 0 | NA | REJECTED | [5 empty] | The title and attachement of drawings are incorrect, requested to resubmit.KPTG-IntCorr-006640 |  | 2026-04-03 | KPTG-IntCorr-006640 | Closed | 24 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-02 | Jordan-TRANSMIT-000124 | NA | Trade Partner | JP Shop Drawing - For Construction | 7 | 0 | 0 | NA | APPROVED | 2026-04-04 | NA | 1181 | 2026-04-07 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-003502 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-02 | VAE-Grp-TRANSMIT-000146 | NA | Trade Partner | MECHANICAL - SCHEDULE - MCS POINTS LIST - MINOR UPDATES | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | FC DOCS-Send to all parties |  | 2026-04-04 | KPTG-TRANSMIT-003340 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-02 | ZIA-TRANSMIT-000043 | NA | Trade Partner | CSMS - FDS For Approval | 0 | 2 | 0 | NA | APPROVED | 2026-04-04 | WF-000971 | NA | 2026-04-07 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-02 | TTW-TRANSMIT-000128 | NA | Consultant | Civil - Updated Stormwater Drawings and Model | 6 | 0 | 0 | NA | APPROVED | 2026-04-02 | NA | 394 | 2026-04-06 |  | closed out on 10-04-2026 due to VPN issue | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-001081 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-02 | WAM-TRANSMIT-000744 | NA | Consultant | District Living: Kitchen Island Bench | 3 | 0 | 0 | NA | REJECTED | [5 empty] | QA ERROR - REV. NOT UPDATED |  | 2026-04-02 | KPTG-TRANSMIT-001024 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-02 | OveArup-TRANSMIT-000034 | NA | Consultant | Vertical Transportation Performance Specification | 0 | 1 | 0 | NA | APPROVED | 2026-04-02 | WF-000292 | NA | 2026-04-06 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001859 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-02 | HVHD-TRANSMIT-000008 | NA | Consultant | Updated SMP | 0 | 1 | 0 | NA | REJECTED | [5 empty] | QA ERROR - REV. NOT UPDATED |  | 2026-04-02 | KPTG-TRANSMIT-001032 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-11 | ECBS-TRANSMIT-000044 | NA | Trade Partner | Revise as per comments | 0 | 2 | 0 | NA | APPROVED | 2025-12-11 | WF-000672 |  | 2025-12-17 |  |  |  | 2026-01-16 | NA | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-02 | HVHD-TRANSMIT-000007 | NA | Consultant | Updated ESD Implementation Matrix | 0 | 1 | 0 | NA | APPROVED | 2026-04-02 | WF-000294 | NA | 2026-04-06 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-001061 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-06 | Stowe-A-TRANSMIT-000531 | NA | Trade Partner | List of Equipment Procured and Installed by Stowe for SP3 Handover | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with the document number |  | 2026-04-06 | KPTG-DA-005836 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-06 | D&E-TRANSMIT-000531 | NA | Trade Partner | Fire Matrix - Fire integration | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with the document number |  | 2026-04-06 | KPTG-DA-005837 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-06 | ACG-TRANSMIT-000071 | NA | Trade Partner | M3 - Stage 2 As Builts Basement / Ground | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Documents attached wrongly. |  | 2026-04-06 | KPTG-DA-005838 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-06 | ACG-TRANSMIT-000072 | NA | Trade Partner | M3 - Site Wide Drawings - As-Builts | 10 | 0 | 0 | NA | REJECTED | [5 empty] | IFC status not shown in revision history,2 doc latest IFC status are rejected |  | 2026-04-06 | KPTG-DA-005842 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-06 | Tradetec-TRANSMIT-000407 | NA | Trade Partner | Weekly as-builts - Stage 2 and 4 | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Difference in document number, Revision format is incorrect and Latest IFC drawings is not there. |  | 2026-04-06 | KPTG-DA-005841 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-06 | RDSBIM-TRANSMIT-000264 | NA | Trade Partner | NXM3S4 ¦ LEVEL-1-C-1-055 CLEANERS FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-04-06 | NA | 2737 | 2026-04-08 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016171 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-06 | RDSBIM-TRANSMIT-000263 | NA | Trade Partner | NXM3S4 ¦ LEVEL 01 RCP LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-04-06 | NA | 2739 | 2026-04-08 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-016073 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-06 | RDSBIM-TRANSMIT-000262 | NA | Trade Partner | NXM3S4 ¦ GROUND FLOOR-C-G-056 MALE WC-FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-04-06 | NA | 2741 | 2026-04-08 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016182 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-06 | ZIA-TRANSMIT-000069 | NA | Trade Partner | L3 and Cx Plan Submission | 0 | 1 | 0 | NA | APPROVED | 2026-04-06 | WF-005168 | NA | 2026-04-15 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-11 | ECBS-TRANSMIT-000045 | NA | Trade Partner | Revised tech data for review - AM41 Stainless Steel Access Panel | 0 | 1 | 0 | NA | APPROVED | 2025-12-11 | WF-000668 |  | 2025-12-16 |  |  | 2025-12-17 | 2025-12-17 | KPTG-TRANSMIT-002022 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-06 | PARR-TRANSMIT-000148 | NA | Trade Partner | P2649 - KPG NDC M3 - Stage 2 - Fuel - DFS OMM | 0 | 1 | 0 | NA | APPROVED | 2026-04-02 | WF-005164 | NA | 2026-04-10 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-015961 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-02 | SMEPS-TRANSMIT-000175 | SPARK-CRFI-KPG-000504 | Trade Partner | Sub Mains schedule IFA | 1 | 0 | 0 | NA | APPROVED | 2026-04-02 | NA | 216 | 2026-04-09 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-07 | RDSBIM-TRANSMIT-000175 | NA | Trade Partner | LINDRUM ¦ LEVEL 2 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-04-07 | NA | 620 | 2026-04-14 |  |  | 2026-04-14 | 2026-04-14 | KPTG-SADV-003755 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-07 | RDSBIM-TRANSMIT-000176 | NA | Trade Partner | LINDRUM ¦ LEVEL 03 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-04-07 | NA | 621 | 2026-04-14 |  |  | 2026-04-14 | 2026-04-14 | KPTG-SADV-003756 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-07 | RDSBIM-TRANSMIT-000177 | NA | Trade Partner | LINDRUM ¦ LEVEL 04 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-04-07 | NA | 622 | 2026-04-14 |  | WORKFLOW TERMINATED | 2026-04-14 | 2026-04-14 | KPTG-IntCorr-000874 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-07 | ACG-TRANSMIT-000073 | NA | Trade Partner | M3 - Stage 2 As Builts Basement / Ground | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect attachments. |  | 2026-04-07 | KPTG-DA-005850 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-07 | D&E-TRANSMIT-000562 | NA | Trade Partner | Fire Matrix - Fire integration | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Document for record, WF not required |  | 2026-04-07 | KPTG-TRANSMIT-015495 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-07 | RDSBIM-TRANSMIT-000178 | NA | Trade Partner | LINDRUM ¦ BASEMENT 1 LEVEL REFLECTED CEILING PLAN | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-SADV-003651 - As per the instruction from Mark, we have only updated the Aconex register and made an update in BIM. |  | 2026-04-07 | KPTG-SADV-003651 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-04-07 | WSP ANZ-TRANSMIT-000005 | NA | Consultant | WSP - Demolition Construction Issue Drawings Electrical | 12 | 1 | 0 | NA | APPROVED | 2026-04-07 | NA | 25 | 2026-04-14 |  | Voided as advised by Renee 09-04-2026 |  | 2026-04-09 | NA | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-04-07 | WSP ANZ-TRANSMIT-000005 | NA | Consultant | WSP - Demolition Construction Issue Drawings Fire Protection | 6 | 0 | 0 | NA | APPROVED | 2026-04-07 | NA | 26 | 2026-04-14 |  | Voided as advised by Renee 09-04-2026 |  | 2026-04-09 | NA | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-11 | ECBS-TRANSMIT-000046 | NA | Trade Partner | Revised tech data for IN81 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Updated document has been transmitted via ECBS-TRANSMIT-000047 |  | 2025-12-11 | KPTG-TRANSMIT-001999 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-04-07 | WSP ANZ-TRANSMIT-000005 | NA | Consultant | WSP - Demolition Construction Issue Drawings Hydraulic | 5 | 1 | 0 | NA | APPROVED | 2026-04-07 | NA | 27 | 2026-04-14 |  | Requested by WSP Sam Parekh (WSP ANZ-IntCorr-000009) |  | 2026-04-07 | NA | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-04-07 | WSP ANZ-TRANSMIT-000005 | NA | Consultant | WSP - Demolition Construction Issue Drawings Mechanical | 7 | 1 | 0 | NA | APPROVED | 2026-04-07 | NA | 28 | 2026-04-14 |  | Requested by WSP Sam Parekh (WSP ANZ-IntCorr-000009) |  | 2026-04-07 | NA | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-07 | 4DW-TRANSMIT-000168 | NA | Consultant | Structural Drawing Update | 1 | 0 | 0 | NA | APPROVED | 2026-04-07 | NA | 210 | 2026-04-14 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-002786 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-07 | Baigents-TRANSMIT-000082 | SPARK-CRFI-KPG-000222 | Trade Partner | Panel MCC-P67 Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-07 | NA | 217 | 2026-04-14 |  |  |  | 2026-05-12 | KPTG-TRANSMIT-000858 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-07 | ACG-TRANSMIT-000074 | NA | Consultant | M3 - Site Wide Drawings - IFC | 2 | 0 | 0 | NA | APPROVED | 2026-04-07 | NA | 4066 | 2026-04-14 |  | Due to VPN issues close out processed on 10/04/2026 | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-015673 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-24 | RDSBIM-TRANSMIT-000002 | NA | Trade Partner | MEL11C45 ¦ PARTITION WALL LAYOUT L01 AND L02 COLO4 COLO5A, COLO5B | 3 | 0 | 0 | NA | APPROVED | 2026-03-24 | WF-000090 | NA | 2026-03-30 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-000297 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-07 | Auspan-TRANSMIT-000011 | NA | Trade Partner | Re: Update dowel layout | 1 | 0 | 0 | NA | APPROVED | 2026-04-08 | WF-000021 | NA | 2026-04-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-02 | RDSBIM-TRANSMIT-000006 | NA | Trade Partner | MEL05C4 ¦ LEVEL 02 COLO 04 SCREED LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-04-07 | WF - 000339 | NA | 2026-04-14 |  | NA | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-000729 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-07 | KPTG-CONTADV-007335 | NA | Trade Partner | Re: Final (WF-005026) S2 I TECH DATA ¦ KPTG ¦ ADP ¦ ARUP ¦ SP3 STOWE O&M MANUAL | 0 | 1 | 0 | NA | APPROVED | 2026-04-07 | WF-005179 | NA | 2026-04-13 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016200 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-07 | ADP-TRANSMIT-000297 | NA | Consultant | Re: ADP MEL4561 - Stage 2 Updated drawings (EL & Comms) | 5 | 0 | 0 | NA | APPROVED | 2026-04-07 | NA | 4073 | 2026-04-09 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-015581 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-01 | VAE-Grp-TRANSMIT-000073 | N/A | Trade Partner | MECHANICAL SERVICES- HEAT EXCHANGERS | 0 | 2 | 0 | NA | APPROVED |  | N/A | N/A |  |  | REGISTER UPDATION ONLY - DONE |  | 2026-02-22 | KPTG-TRANSMIT-002893 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-07 | ARCST-TRANSMIT-000250 | NA | Trade Partner | Re: C3 East Roof Walkway - Issued for Approval | 179 | 0 | 0 | NA | APPROVED | 2026-04-07 | WF-005187 | NA | 2026-05-01 |  | 88 DRAWING ARE STILL UNDER REVIEW | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-017264 | Closed | 91 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-07 | ARCST-TRANSMIT-000249 | NA | Trade Partner | Stage 4 - C2 Upper Gantry Handrails | 36 | 0 | 0 | NA | APPROVED | 2026-04-07 | WF-005176 | NA | 2026-04-14 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-017038 | Closed | 36 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-07 | PenskePS-TRANSMIT-000004 | NA | Trade Partner | MEL11 COLO4 & 5 - tech data & drawings | 8 | 0 | 0 | NA | APPROVED | 2026-04-07 | WF-000117 | NA | 2026-04-10 |  |  |  | 2026-04-08 | KPTG-TRANSMIT-000305 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-07 | Tradetec-TRANSMIT-000414 | NA | Trade Partner | Re: IFC - Stage 4 Pits | 5 | 0 | 0 | NA | APPROVED | 2026-04-08 | NA | 2749 | 2026-04-10 |  |  |  | 2026-04-10 | KPTG-TRANSMIT-015728 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-07 | ARCST-TRANSMIT-000247 | NA | Trade Partner | Re: (WF-004155) S4 ¦ SHOP DRAWING ¦ CONSULTANT REVIEW ¦ IFA ¦ ARUP-HAMES - ARCST-TRANSMIT-000147 - ARCST-TRANSMIT-000154 | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect document number |  | 2026-04-07 | KPTG-TRANSMIT-015524 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-07 | PARR-TRANSMIT-000158 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - BF PUMP ROOM RETIC | 1 | 0 | 0 | NA | APPROVED | 2026-04-07 | NA | 2745 | 2026-04-15 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-016807 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-07 | RDSBIM-TRANSMIT-000247 | NA | Trade Partner | NXM3S4 ¦ ROOF PARTITION WALL KEY PLAN AND ELEVATION | 13 | 0 | 0 | NA | APPROVED | 2026-04-18 | NA | 2568 | 2026-04-07 |  |  | 2026-04-07 | 2026-04-07 | KPTG-TRANSMIT-015511 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-07 | ARCST-TRANSMIT-000246 | NA | Trade Partner | Re: Final (WF-003696) S4 ¦ SHOP DRAWING ¦ CONSULTANT REVIEW ¦ IFA ¦ ROOF STEEL WORKFLOW | 133 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong revision and attachments |  | 2026-04-07 | KPTG-TRANSMIT-015539 | Closed | 133 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-07 | ARCST-TRANSMIT-000248 | NA | Trade Partner | Final (WF-003699) S4 ¦ SHOP DRAWING ¦ CONSULTANT REVIEW ¦ IFA ¦ ROOF STEEL WORKFLOW | 119 | 0 | 0 | NA | APPROVED | 2026-04-07 | WF-005188 | NA | 2026-04-14 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-017216 | Closed | 119 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-07 | Tradetec-TRANSMIT-000095 | NA | Trade Partner | Haul Road Technical Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-04-07 | WF-000453 | NA | 2026-04-17 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-002374 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-11 | ECBS-TRANSMIT-000047 | NA | Trade Partner | Revised tech data - IN81 (HardieWrap) | 0 | 1 | 0 | NA | APPROVED | 2025-12-11 | WF-000669 |  | 2025-12-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-07 | Tradetec-TRANSMIT-000096 | NA | Trade Partner | Pit Earthing | 0 | 1 | 0 | NA | APPROVED | 2026-04-07 | WF-000456 | NA | 2026-04-17 |  | Workflow terminated as requested by PC, Revised document has been submitted by Trade partner |  | 2026-04-10 | KPTG-IntCorr-000672 | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-07 | DCN-TRANSMIT-000001 | NA | Trade Partner | M2S9 Link Bridge Structural Issued For Information Shop Drawings | 8 | 0 | 0 | NA | APPROVED | 2026-04-07 | NA | 597 | 2026-04-13 |  | For Information drawings No review required |  | 2026-04-07 | NA | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-07 | WGAVIC-TRANSMIT-000098 | NA | Consultant | M2 - Early Works RW12 Retaining Walls - Issued for Certification | 3 | 0 | 0 | NA | APPROVED | 2026-04-07 | NA | 598 | 2026-04-13 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-002235 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-07 | SCG2014-TRANSMIT-000021 | NA | Consultant | M2S9 Issue for Tender (IFT-3) | 38 | 5 | 0 | NA | APPROVED | 2026-04-07 | NA | 601 | 2026-04-13 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-002255 | Closed | 43 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-07 | RDSBIM-TRANSMIT-000265 | NA | Trade Partner | NXM3S4 LEVEL-1-C-1-044 ACC WC (RH) FLOOR FINISHES LAYOUT AND ELEVATION | 1 | 0 | 0 | NA | APPROVED | 2026-04-07 | NA | 2743 | 2026-04-10 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-07 | PARR-TRANSMIT-000157 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - DP Transmitter -IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | ONLY FOR INFORM BOADER TEAM |  | 2026-04-07 | KPTG-TRANSMIT-015500 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-07 | Tradetec-TRANSMIT-000415 | NA | Trade Partner | Re IFC - Stage 4 Pits | 5 | 0 | 0 | NA | APPROVED | 2026-04-07 | NA | 2749 | 2026-04-15 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-07 | ADP-TRANSMIT-000296 | NA | Consultant | Re: MEL4780 - S4 - Electrical - LAYOUT - SITE IN GROUND - ZONE 2 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | doc-1 rejected due to incorrect document number |  | 2026-04-07 | KPTG-DA-005869 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-07 | ADP-TRANSMIT-000294 | NA | Consultant | Re: MEL741 - Updated Electrical Drawings | 2 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due to mentioned wrongly |  | 2026-04-07 | KPTG-DA-005870 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-07 | Auspan-TRANSMIT-000191 | NA | Trade Partner | Resubmit panel 1P2028 for approval. | 1 | 0 | 0 | NA | APPROVED | 2026-04-07 | NA | 672 | 2026-04-14 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-001394 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-11 | KPTG-IntCorr-003566 | NA | Trade Partner | sprinkler tech data REV 2- kaycee Tech | 0 | 1 | 0 | NA | APPROVED | 2025-12-11 | WF-000666 |  | 2025-12-16 |  |  | 2025-12-11 | 2025-12-11 | KPTG-TRANSMIT-001987 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-07 | JCBa-TRANSMIT-000083 | NA | Consultant | IFC: A-2100 Ground–L04, A-2200 Ground | 30 | 0 | 0 | NA | APPROVED | 2026-04-07 | NA | 664 | 2026-04-09 |  | Review void as requested by DM. Consultant is requested to update drawing. | 2026-04-16 | 2026-04-16 | NA | Closed | 29 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-07 | RDSBIM-TRANSMIT-000043 | NA | Trade Partner | GREYSTAR LEVEL 01 CONCRETE PROFILE PLAN AND SECTION | 7 | 0 | 0 | NA | APPROVED | 2026-04-07 | NA | 674 | 2026-04-14 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-001460 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-07 | Auspan-TRANSMIT-000189 | NA | Trade Partner | Resubmit precast shop drawings for approval. Ground floor and level 1 | 21 | 0 | 0 | DRAFT-005438 | REJECTED | [5 empty] | Rejected due to wrong attachment, Incorrect drawings status, DRAFT-005438 |  | 2026-04-07 | NA | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-07 | Auspan-TRANSMIT-000190 | NA | Trade Partner | Precast shop drawings for approval. Level 2. | 61 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to wrong attachment, Incorrect drawings status, DRAFT-005450 |  | 2026-04-07 | DRAFT-005450 | Closed | 61 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-07 | KETE-TRANSMIT-000014 | NA | Trade Partner | Kete - Zone 04 Shop Drawing 1st IFA Submission | 59 | 0 | 0 | NA | APPROVED | 2026-04-07 | NA | 666 | 2026-04-14 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-001628 | Closed | 59 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-07 | Rinco-TRANSMIT-000039 | NA | Consultant | Structural drawings Issued for Construction | 7 | 0 | 0 | NA | APPROVED | 2026-04-07 | NA | 668 | 2026-04-14 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-001258 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-07 | JCBa-TRANSMIT-000084 | NA | Trade Partner | STRUCTURAL SETOUT PLANS OVERALL PLANS FOR GROUND TO 4th FLOOR | 5 | 0 | 0 | NA | APPROVED | 2026-04-07 | NA | 670 | 2026-04-09 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-001360 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-07 | PSGANZ-TRANSMIT-000004 | NA | Trade Partner | PSG WET Fire Tech Data Sample Submission & Procurement register | 0 | 8 | 0 | NA | APPROVED | 2026-04-07 | WF-000365 | NA | 2026-04-14 |  |  | 2026-04-14 | 2026-04-14 | KPTG-TRANSMIT-001299 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-07 | PSGANZ-TRANSMIT-000004 | NA | Trade Partner | PSG WET Fire Tech Data Sample Submission & Procurement register | 0 | 7 | 0 | NA | APPROVED | 2026-04-07 | WF-000366 | NA | 2026-04-14 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-07 | RDSBIM-TRANSMIT-000007 | NA | Trade Partner | MEL05C4 ¦ PARTITION WALL ¦ L02 COLO 4 | 3 | 0 | 0 | NA | APPROVED | 2026-04-07 | WF - 000340 | NA | 2026-04-14 |  | WF Terminated |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-07 | RDSBIM-TRANSMIT-000050 | NA | Trade Partner | 671CHP- BASEMENT 1 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2026-04-07 | NA | 392 | 2026-04-14 |  | Review void as advised by Project Coordinator. | 2026-04-13 | 2026-04-13 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-08 | SMEPS-TRANSMIT-000231 | NA | Trade Partner | SME - GLP Shop Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-04-08 | NA | 2757 | 2026-04-15 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-016988 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-07 | RDSBIM-TRANSMIT-000008 | NA | Trade Partner | MEL05C4 ¦ LEVEL 2 COLO 4 CEILING LAYOUT | 3 | 0 | 0 | NA | APPROVED | 2026-04-07 | WF - 000341 | NA | 2026-04-14 |  | WF Terminated |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-08 | SKS Tech-TRANSMIT-000076 | NA | Trade Partner | SKS - Lighting IFC submissions | 0 | 2 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-04-08 | KPTG-RFI-007171 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-06 | RDSBIM-TRANSMIT-000183 | NA | Trade Partner | LEVEL 07 PARTITION WALL LAYOUT | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC distribution only. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-07 | RDSBIM-TRANSMIT-000184 | NA | Trade Partner | LEVEL 09 PARTITION WALL LAYOUT | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Distribution only. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-08 | TTW-TRANSMIT-000166 | NA | Consultant | TTW Civil and Traffic Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-04-08 | NA | 2759 | 2026-04-13 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-015694 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-07 | PSGANZ-TRANSMIT-000004 | NA | Trade Partner | PSG WET Fire Tech Data Sample Submission & Procurement register | 0 | 7 | 0 | NA | APPROVED | 2026-04-07 | WF-000366 | NA | 2026-04-14 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-001694 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-08 | D&E-TRANSMIT-000195 | SPARK-CRFI-KPG-000643 | Trade Partner | COMPRESSED AIR PIPE & JOINTS | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-20 | KPTG-TRANSMIT-000668 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-10 | VIA Arch-TRANSMIT-000031 | NA | Consultant | CHILLER MODULE UPDATES | 4 | 0 | 0 | NA | APPROVED | 2025-12-11 |  | 134 | 2025-12-16 |  |  | 2025-12-12 | 2025-12-15 | KPTG-TRANSMIT-000338 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-08 | Civilex-TRANSMIT-000224 | NA | Trade Partner | Stage 2 - Landscape Transmittal - Rev C - Drawing No.1-2-3-4-5-6 | 6 | 0 | 0 | NA | APPROVED | 2026-04-08 | NA | 4076 | 2026-04-15 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-016068 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-08 | NXT-TRANSMIT-001477 | NA | Trade Partner | Stage 4 - Battery Rooms - BATTERY ROOM FUNCTIONAL DESCRIPTION | 0 | 1 | 0 | NA | APPROVED | 2026-04-08 | WF-005194 | NA | 2026-04-24 |  | Originator TRN Ref. PARR-TRANSMIT-000159 |  | 2026-06-25 | KPTG-TRANSMIT-019049 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-08 | KETE-TRANSMIT-000038 | NA | Trade Partner | Shop drawing WINDOW SCHEDULE - KETE-TRANSMIT-000038 | 78 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings only for distribution. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-08 | Entire M-TRANSMIT-000027 | NA | Trade Partner | Commissioning Management Plan Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-04-08 | WF -000342 | NA | 2026-04-14 |  | NA | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-000725 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-08 | ADP-TRANSMIT-000298 | NA | Consultant | MEL4780 - S4 - Electrical - LAYOUT - SITE IN GROUND - ZONE 2 | 1 | 0 | 0 | NA | APPROVED | 2026-04-08 | NA | 2761 | 2026-04-12 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-017161 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-08 | Stowe-A-TRANSMIT-000545 | NA | Trade Partner | Stowe - Tech Data Submission - Comms Rack & PDU | 0 | 1 | 0 | NA | APPROVED | 2026-04-08 | WF-005198 | NA | 2026-04-21 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-017488 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-07 | CRSol-TRANSMIT-000084 | NA | Trade Partner | CRS CLN Drawings - Issued for Construction - Zones C1, C2 & C3. | 35 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-04-08 | KPTG-TRANSMIT-015564 | Closed | 35 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-08 | Stowe-A-TRANSMIT-000546 | NA | Trade Partner | Tech Data Not In Use | 0 | 3 | 0 | NA | APPROVED | [5 empty] | No Longer in use. Updated register. |  | 2026-04-08 | KPTG-TRANSMIT-015570 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-08 | D&E-TRANSMIT-000197 | SPARK-CRFI-KPG-000586 | Trade Partner | PIPING VALVES | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-08 | Stowe-A-TRANSMIT-000547 | NA | Trade Partner | Stowe - Tech Data Submission - Control Cabling | 0 | 1 | 0 | NA | APPROVED | 2026-04-08 | WF-005200 | NA | 2026-04-21 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-016833 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-11 | VIA Arch-TRANSMIT-000030 | NA | Consultant | SWITCH ROOM TYP DRAWINGS | 4 | 0 | 0 | NA | APPROVED | 2025-12-11 |  | 136 | 2025-12-16 |  |  | 2025-12-12 | 2025-12-15 | KPTG-TRANSMIT-000341 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-08 | D&E-TRANSMIT-000198 | SPARK-CRFI-KPG-000315 | Trade Partner | MWYCCB - LEVEL 1 - PENETRATION LAYOUT ZONE 8 & ZONE 9 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-08 | NA | 218 | 2026-04-15 |  |  | 2026-04-17 | 2026-04-27 | KPTG-TRANSMIT-000740 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-08 | ACG-TRANSMIT-000075 | NA | Consultant | M3 - Stage 2 Basement / Ground As-Built | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Mismatch in document number attached |  | 2026-04-08 | KPTG-DA-005885 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-08 | D&E-TRANSMIT-000199 | NA | Trade Partner | MWYCCB - GROUND LEVEL - DUCTWORK LAYOUT ZONE 8 & ZONE 9 MECHANICAL SERVICES - Issued for Manufacture | 1 | 0 | 0 | NA | APPROVED | 2026-04-08 | NA | 219 | 2026-04-15 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-08 | Stowe-A-TRANSMIT-000548 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - ROOF LIGHTING - FOR CONSTRUCTION - 08.04.2026 | 4 | 0 | 0 | NA | APPROVED | 2026-04-08 | NA | 4078 | 2026-04-21 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-016641 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-08 | M.S.-TRANSMIT-000001 | NA | Trade Partner | Batch 1 & 2 Shop Drawings | 19 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-04-08 | KPTG-TRANSMIT-000624 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-08 | KPTG-WTRAN-002246 | NA | Trade Partner | Sampe of Roller Door Finish | 0 | 1 | 0 | NA | APPROVED | 2026-04-08 | WF - 000989 | NA | 2026-04-10 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-08 | KPTG-CONTADV-007352 | NA | Trade Partner | Re: Stage 2 O&M manual | 0 | 1 | 0 | NA | APPROVED | 2026-04-08 | WF-005209 | NA | 2026-04-16 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016119 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-08 | Auspan-TRANSMIT-000192 | NA | Trade Partner | Resubmit shop drawings for approval. Ground floor 0G359 and 0G360 | 2 | 0 | 0 | NA | APPROVED | 2026-04-08 | NA | 677 | 2026-04-14 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-001397 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-08 | Auspan-TRANSMIT-000193 | NA | Trade Partner | Precast shop drawings for construction. Ground floor and level 1. | 44 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect revision and drawings status |  | 2026-04-08 | KPTG-SADV-001764 | Closed | 44 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-08 | INDS-TRANSMIT-000016: | na | Trade Partner | FIRE PUMP PLINTH SET OUT | 1 | 0 | 0 | KPTG-IntCorr-000437 | APPROVED |  | NA | NA |  |  | As informed by Project coordinator Amee, no review required. Register and distribute - |  | 2026-04-16 | KPTG-TRANSMIT-001249 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-12 | B Smart-TRANSMIT-000036 | NA | Consultant | A05 Series & A13 Series _ Apartment Levels | 50 | 0 | 0 | NA | APPROVED | 2025-12-11 | WF-000090 | 167 | 2025-12-16 |  | Updated drawings received and review terminated. |  | 2026-01-16 | NA | Closed | 50 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-08 | Auspan-TRANSMIT-000194 | NA | Trade Partner | Re: Resubmit precast shop drawings for approval. Ground floor and level 1 | 1 | 0 | 0 | KPTG-IntCorr-000436. | APPROVED | 2026-04-10 |  | 684 | 2026-04-17 |  | Waiting for Kapitol Advise: KPTG-IntCorr-000436. incomplete transmittal resubmission. | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-001400 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-08 | POTTSENG-TRANSMIT-000019 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONE 5 LAYOUT | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol PC, Update Register and transmit to all (IFC) KPTG-TRANSMIT-001238 |  | 2026-04-08 | KPTG-TRANSMIT-001238 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-08 | RDSBIM-TRANSMIT-000044 | NA | Trade Partner | GREYSTAR ¦ LEVEL 02 CONCRETE PROFILE PLAN | 6 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | ON HOLD as requested by RDS; RDS to update the drawings. Drawings superseded by RDS - RDSBIM-TRANSMIT-000045 |  | 2026-04-09 | RDSBIM-TRANSMIT-000045 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-08 | HGP-TRANSMIT-000051 | NA | Trade Partner | Transmittal-MCC Shop Drawing Louvre IFA Rev02 | 15 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-04-08 | KPTG-TRANSMIT-000625 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-08 | IVS-TRANSMIT-000358 | NA | Consultant | Stage 4 - Secure Corridor Construction Issue (Revised as clouded) | 2 | 0 | 0 | NA | APPROVED | 2026-04-08 | NA | 2775 | 2026-04-10 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-015831 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-08 | ECBS-TRANSMIT-000028 | NA | Trade Partner | Re: Stage 4 - shop drawings for the steel columns | 92 | 0 | 0 | NA | REJECTED | [5 empty] | Revision not mentioned inside the drawing |  | 2026-04-08 | KPTG-TRANSMIT-015591 | Closed | 92 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-08 | SKS Tech-TRANSMIT-000079 | NA | Trade Partner | SKS - Technical Data Submissions | 0 | 12 | 0 | NA | APPROVED | [5 empty] | IFC Tech data- distributed to trade partners and consultant |  | 2026-04-08 | KPTG-TRANSMIT-015594 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-08 | WilsonPD-TRANSMIT-000011 | NA | Trade Partner | Water Storage Tank Tech Data Submission | 0 | 4 | 0 | NA | APPROVED | 2026-04-08 | WF-000461 | NA | 2026-04-17 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-002425 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-08 | VIA Arch-TRANSMIT-000085 | NA | Consultant | M2 S9-11 Interior Package | 133 | 0 | 0 | NA | APPROVED | 2026-04-08 | NA | 604 | 2026-04-13 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-002056 | Closed | 133 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-08 | VIA Arch-TRANSMIT-000086 | NA | Consultant | Building Permit Issue drawings | 59 | 0 | 0 | NA | APPROVED | 2026-04-08 | NA | 664 | 2026-04-13 |  |  | 2026-04-14 | 2026-04-14 | KPTG-TRANSMIT-001941 | Closed | 59 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-11 | StantecA-TRANSMIT-000015 | NA | Consultant | Services IFC Issue - Fire | 40 | 0 | 0 | NA | APPROVED | 2025-12-11 | WF-000086 | 159 | 2025-12-16 |  |  |  | 2026-01-22 | KPTG-TRANSMIT-000304 | Closed | 40 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-08 | SMEPS-TRANSMIT-000180 | NA | Trade Partner | SME TELECOM SHOP DRAWINGS | 12 | 0 | 0 | NA | APPROVED |  |  | NA |  |  | File superseded |  | 2026-04-10 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-09 | Civilex-TRANSMIT-000225 | NA | Trade Partner | Sample Submission - Pavement Concrete mix design Pronto - Rev C | 0 | 1 | 0 | NA | APPROVED | 2026-04-10 | WF-005229 | NA | 2026-04-16 |  | Due to VPN issues processed on 10/04/2026 | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-016921 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-09 | Stowe-A-TRANSMIT-000549 | NA | Trade Partner | STOWE - TECH DATA SUBMISSION - SEISMIC - 09.04.2026 | 0 | 1 | 0 | NA | APPROVED | 2026-04-10 | WF-005217 | NA | 2026-04-23 |  | Due to VPN issues processed on 10/04/2026 | 2026-06-12 | 2026-06-12 | KPTG-TRANSMIT-018583 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-09 | D&E-TRANSMIT-000570 | NA | Trade Partner | NXM3S2 - Roof - Builders Works Layout - B2 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 4082 | 2026-04-17 |  | Due to VPN issues processed on 10/04/2026 | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016130 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-09 | SMEPS-TRANSMIT-000177 | SPARK-CRFI-KPG-000583 | Trade Partner | Re: Cat6A Cable (SPARK-CRFI-KPG-000583) | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-16 | KPTG-TRANSMIT-000650 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-09 | TTW-TRANSMIT-000168 | NA | Trade Partner | TTW Civil and Traffic Drawings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with drawing number inside the drawing. |  | 2026-04-10 | KPTG-TRANSMIT-015618 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-09 | SKS Tech-TRANSMIT-000081 | NA | Trade Partner | Equipment Layouts for Approval | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per Damian-No action required |  | 2026-04-10 | KPTG-IntCorr-011685 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-09 | SKS Tech-TRANSMIT-000082 | NA | Trade Partner | Re: Equipment Layout GF zone C2 for approval | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per Damian-No action required |  | 2026-04-10 | KPTG-IntCorr-011687 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-09 | D&E-TRANSMIT-000201 | SPARK-CRFI-KPG-000329 | Trade Partner | FAN STATIC PRESSURE CCALCULATIONS | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-09 | D&E-TRANSMIT-000572 | NA | Trade Partner | NXM3S2 - Level 01 - Mechanical Duct Layout - Zone 6 - Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 4084 | 2026-04-17 |  | Due to VPN issues processed on 10/04/2026 | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016209 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-11 | StantecA-TRANSMIT-000015 | NA | Consultant | Services IFC Issue - HYD | 45 | 1 | 0 | NA | APPROVED | 2025-12-11 | WF-000087 | 161 | 2025-12-16 |  |  |  | 2026-01-21 | KPTG-TRANSMIT-000290 | Closed | 45 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-08 | CRSol-TRANSMIT-000085 | NA | Trade Partner | M3S4 CRS SMW Drawings - Issued for Construction - Zones C2 & C3 | 20 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 2803 | 2026-04-16 |  | as per requested by isabella workflow has terminated to update new revision |  | 2026-04-27 | na | Closed | 21 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-10 | Nilsen3-TRANSMIT-000091 | NA | Trade Partner | Re: Sample submitted for approval | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect Reference number | 2026-04-09 | 2026-04-10 | KPTG-RFI-007226 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-09 | D&E-TRANSMIT-000203 | SPARK-CRFI-KPG-000646 | Trade Partner | CONTROL TOPOLOGY | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-05-27 | 2026-05-27 | KPTG-TRANSMIT-000944 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-09 | D&E-TRANSMIT-000204 | SPARK-CRFI-KPG-000572 | Trade Partner | MWYCCB - LEVEL 1 - MECH. ELEC. LAYOUT ZONE 6 & ZONE 7 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 220 | 2026-04-17 |  |  | 2026-04-17 | 2026-04-23 | KPTG-TRANSMIT-000685 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-09 | WPD-TRANSMIT-000080 | NA | Trade Partner | Hydraulic shop drawing re-issued for Review | 1 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 397 | 2026-04-19 |  | Old WF - 391 Due to VPN issues, the transmittal was processed on 10/04/2026. | 2026-04-23 | 2026-04-23 | DRAFT-009808 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-04-10 | KPTG-IntCorr-003381 | NA | Trade Partner | Dry Fire O&M, | 0 | 1 | 0 | NA | APPROVED | 2026-04-10 | WF-000996 | NA | 2026-04-15 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-09 | D&E-TRANSMIT-000205 | NA | Trade Partner | MWYCCB - LEVEL 1 - RCP LAYOUT ZONES - Issued For Construction | 3 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 221 | 2026-04-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-09 | WPD-TRANSMIT-000081 | NA | Trade Partner | Hydraulic shop drawings issued As Built | 2 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 393 | 2026-04-19 |  |  | 2026-05-21 | 2026-05-21 | DRAFT-010017 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-10 | Kone-VIC-TRANSMIT-000013 | NA | Trade Partner | Lift EID - Lifts 1 to 4 on Ground Level | 0 | 1 | 0 | NA | APPROVED | 2025-11-24 | WF-000485 | NA | 2025-11-28 |  | KPTG-IntCorr-000862- AS PER THE DIRECTION MARK WE TERMINATE THE WORKFLOW. |  | 2026-04-10 | KPTG-IntCorr-000862 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-11 | StantecA-TRANSMIT-000015 | NA | Consultant | Services IFC Issue -MEC | 57 | 1 | 0 | NA | APPROVED | 2025-12-12 | WF-000093 | 171 | 2025-12-17 |  |  |  | 2025-12-18 | KPTG-TRANSMIT-000248 | Closed | 57 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-07 | HVHD-TRANSMIT-000009 | NA | Consultant | Sustainability Management Plan | 0 | 1 | 0 | KPTG-TRANSMIT-001070 | REJECTED | [5 empty] | QA error |  | 2026-04-07 | KPTG-TRANSMIT-001070 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-10 | Metzone-TRANSMIT-000015 | NA | Trade Partner | Steel Shop Drawings for B1, L5 & L6 _ IFA | 26 | 0 | 0 | NA | APPROVED | 2026-04-22 | WF-000709 | NA | 2026-04-24 |  | KPTG-IntCorr-000861 - AS PER THE DIRECTION ASHLIN WE SUPERSCEDE THE DOCUMENTS. KPTG-IntCorr-001067-The review status shown inside and outside the document appears to be different. | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-002548 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-07 | HVHD-TRANSMIT-000010 | NA | Consultant | Sustainability Management Plan | 0 | 1 | 0 | KPTG-TRANSMIT-001070 | REJECTED | [5 empty] | QA error |  | 2026-04-07 | KPTG-TRANSMIT-001070 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-09 | Coen-TRANSMIT-000003 | NA | Trade Partner | Re: COEN - Material Schedule | 0 | 6 | 0 | NA | APPROVED | 2026-04-10 | WF-000023 | NA | 2026-04-20 |  | Due to VPN issues processed on 10/04/2026 | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000333 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-09 | D&E-TRANSMIT-000206 | SPARK-CRFI-KPG-000254 | Trade Partner | MWYCCB - GROUND LEVEL - DUCTWORK LAYOUT ZONES - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 222 | 2026-04-17 |  |  | 2026-04-17 | 2026-04-27 | KPTG-TRANSMIT-000742 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-09 | WPD-TRANSMIT-000082 | NA | Trade Partner | Hydraulic shop drawings issued for Construction | 5 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 395 | 2026-04-14 |  | Due to VPN issues, the transmittal was processed on 10/04/2026. | 2026-04-14 | 2026-04-14 | DRAFT-009710 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-07 | SKS Tech-TRANSMIT-000177 | NA | Trade Partner | Naming Convention for HV Protection | 0 | 0 | 0 | KPTG-IntCorr-001129 | APPROVED | 2026-04-07 | WF-000974 | NA | 2026-04-16 |  |  |  | 2026-04-28 | KPTG-SADV-003073 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-07 | Endfire-TRANSMIT-000075 | NA | Trade Partner | Dry Fire Layout - Level 4 IFC | 1 | 0 | 0 | NA | APPROVED | 2026-04-07 | NA | 1183 | 2026-04-10 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-003534 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-10 | SKS Tech-TRANSMIT-000086 | NA | Trade Partner | Fwd: SKS - Lighting Compliance Reports | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | For info |  | 2026-04-10 | KPTG-TRANSMIT-015636 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-08 | Auspan-TRANSMIT-000194 | NA | Trade Partner | Resubmit precast shop drawings for approval. Ground floor and level 1 | 19 | 0 | 0 | KPTG-IntCorr-000436 | APPROVED | 2026-04-10 | NA | 686 | 2026-04-17 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-001350 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-01 | SKS Tech-TRANSMIT-000094 | N/A | Trade Partner | GROUND FLOOR SEISMIC IFA LAYOUTS - ELC | 1 | 0 | 0 | KPTG-IntCorr-000711 | APPROVED | 2025-12-02 | N/A | 667 | 2025-12-09 |  |  | 2026-01-16 | 2026-01-16 | KPTG-TRANSMIT-002495 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-11 | StantecA-TRANSMIT-000016 | NA | Consultant | Services IFC Issue- ELE | 57 | 1 | 0 | NA | APPROVED | 2025-12-11 | WF-000089 | 165 | 2025-12-16 |  |  |  | 2026-01-22 | KPTG-TRANSMIT-000303 | Closed | 57 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-04-08 | PARR-TRANSMIT-000057 | NA | Trade Partner | KPG NDC M3 S1 DH7&8 - Fuel - KELAIR TRANSFER PUMP & KELAIR RECIRCULATION PUMP DATA SHEET | 0 | 2 | 0 | KPTG-IntCorr-003459 | APPROVED |  | NA | NA |  |  | Distribution only |  | 2026-04-13 | KPTG-TRANSMIT-002870 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-09 | INTRFRM-TRANSMIT-000006 | NA | Trade Partner | Geelong Edge - Hydraulic Tech Data | 0 | 6 | 0 | NA | REJECTED | [5 empty] | Due to VPN issues processed on 10/04/2026 Issue with Document number, Revision. |  | 2026-04-10 | KPTG-SADV-000114 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-09 | D&E-TRANSMIT-000207 | SPARK-CRFI-KPG-000254 | Trade Partner | MWYCCB - GROUND LEVEL - DUCTWORK LAYOUT ZONES - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 223 | 2026-04-17 |  |  | 2026-04-17 | 2026-04-27 | KPTG-TRANSMIT-000744 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-09 | INTRFRM-TRANSMIT-000007 | NA | Trade Partner | Geelong Edge - Structural Concrete Tech Data | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Due to VPN issues processed on 10/04/2026 Issued with Document number and revision. |  | 2026-04-10 | KPTG-SADV-000113 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-08 | RDSBIM-TRANSMIT-000266 | NA | Trade Partner | NXM3S4 ¦ LEVEL-1-C-1-046 MALE WC FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 2796 | [6 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-10 | GEMBA-D-TRANSMIT-000012 | NA | Consultant | NEXTDCGE01 ¦ External plant area - Issued for Certification | 7 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 64 | 2026-04-15 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-000154 | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-10 | ADP-TRANSMIT-000300 | NA | Consultant | ADP MEL4780 - S4 - Electrical CABLE SCHEDULE(FC-02) | 0 | 1 | 0 | NA | APPROVED | 2026-04-10 | NA | 2799 | 2026-04-14 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-017129 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-09 | D&E-TRANSMIT-000209 | SPARK-CRFI-KPG-000466 | Trade Partner | MWYCCB - LEVEL 1 - DUCTWORK LAYOUT ZONE 5 MECHANICAL SERVICES - Issued for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 224 | 2026-04-17 |  |  |  | 2026-05-06 | KPTG-TRANSMIT-000832 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-10 | Coen-TRANSMIT-000004 | NA | Trade Partner | Precast Sample for Approval. | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision mismatch inside document. |  | 2026-04-10 | KPTG-SADV-000112 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-09 | ACG-TRANSMIT-000076 | NA | Trade Partner | M3 - Stage 2 Basement / Ground As-Built | 3 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 4086 | 2026-04-15 |  | Due to VPN issues processed on 10/04/2026 | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-015864 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-11 | StantecA-TRANSMIT-000016 | NA | Consultant | Services IFC Issue- MEC | 3 | 0 | 0 | NA | APPROVED | 2025-12-12 | WF-000093 | 171 | 2025-12-17 |  | 03 MEC - Previous rev. is in review. KPTG-IntCorr-000262 |  | 2026-01-22 | KPTG-TRANSMIT-000303 | Closed | 57 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-09 | D&E-TRANSMIT-000573 | NA | Trade Partner | NXM3S2 - Level 01 - Mechanical Duct Layout - Zone 5 - Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-10 | na | 4088 | 2026-04-17 |  | Due to VPN issues processed on 10/04/2026 | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016206 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-04-10 | Nilsen3-TRANSMIT-000092 | NA | Trade Partner | Inline Joint Termination (SAMPLE) | 0 | 1 | 0 | NA | APPROVED | 2026-04-10 | WF-005242 | NA | 2026-04-15 |  |  | 2026-04-20 | 2026-04-21 | KPTG-TRANSMIT-016238 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-10 | TTW-TRANSMIT-000170 | NA | Consultant | TTW Civil and Traffic Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 4090 | 2026-04-14 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-015739 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-09 | SMEPS-TRANSMIT-000178 | SPARK-CRFI-KPG-000330 | Trade Partner | Diesel Generator | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-27 | KPTG-TRANSMIT-000746 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-08 | SKS Tech-TRANSMIT-000178 | NA | Trade Partner | Temp gen connection cubicle update | 0 | 1 | 0 | NA | APPROVED | 2026-04-10 | WF-000980 | NA | 2026-04-13 |  |  |  | 2026-04-28 | KPTG-TRANSMIT-003509 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-08 | PARR-TRANSMIT-000049 | NA | Trade Partner | Fuel Services - LG SECTIONS 2 | 1 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 1185 | 2026-04-14 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-003415 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-08 | VAE-Grp-TRANSMIT-000147 | NA | Trade Partner | MECH - SHOP DRAWINGS - LEVEL 5 SHEET 2 | 2 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 1187 | 2026-04-14 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-003494 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-08 | Hames-TRANSMIT-000148 | NA | Consultant | LVL 4 WALL CLADING SETOUT | 2 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 1189 | 2026-04-14 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-003452 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-08 | ZIA-TRANSMIT-000044 | NA | Trade Partner | IP Address Register | 0 | 1 | 0 | NA | APPROVED | 2026-04-09 | WF-000976 | NA | 2026-04-15 |  |  | 2026-04-30 | 2026-04-30 | KPTG-WTRAN-002045 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-10 | SMEPS-TRANSMIT-000179 | SPARK-CRFI-KPG-000330 | Trade Partner | UPS-01 (A), UPS-02 (B), UPS-03 (B) | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000759 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-11 | B Smart-TRANSMIT-000037 | NA | Consultant | Amended Apartment Levels A05s – IFC Revisions | 6 | 0 | 0 | KPTG-IntCorr-000261 | APPROVED | 2025-12-16 | WF-000100 | 177 | 2025-12-19 |  | Previous revision is under review. Waiting for advice. KPTG-IntCorr-000261 |  | 2026-01-22 | KPTG-TRANSMIT-000305 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-05 | SMEPS-TRANSMIT-000201 | NA | Trade Partner | 22KV - Shop drawings IFA | 7 | 0 | 0 | NA | APPROVED | 2026-03-06 | WF-004662 | NA | 2026-03-19 |  | Internal MEMO - waiting for Kina's reply | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-015664<br> | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-09 | ACG-TRANSMIT-000077 | NA | Trade Partner | M3 - Stage 2 FOV | 0 | 1 | 0 | NA | REJECTED | [5 empty] | 1. Due to VPN issues processed on 10/04/2026 2. Document number missing in document. revision number to be changed. |  | 2026-04-10 | KPTG-DA-005925 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-03-05 | SMEPS-TRANSMIT-000201 | NA | Trade Partner | 22KV - Shop drawings IFA | 7 | 0 | 0 | NA | APPROVED | 2026-03-06 | WF-004893 | NA | 2026-03-19 |  | Internal MEMO - waiting for Kina's reply | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-015665 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-04-10 | NXT-TRANSMIT-001482 | NA | Trade Partner | Fwd: As Built drawings for M3-22-HVSB-U Revision B | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For boarder team distribution |  | 2026-04-10 | NXT-TRANSMIT-001482 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-10 | D&E-TRANSMIT-000210 | NA | Trade Partner | MWYCCB - SCHEMATICS - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 225 | 2026-04-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-10 | SMPS-TRANSMIT-000109 | NA | Trade Partner | Re: SKS - IFC submissions | 0 | 9 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-04-10 | DRAFT-009677 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-10 | D&E-TRANSMIT-000208 | NA | Trade Partner | No Longer in use | 1 | 0 | 0 | KPTG-IntCorr-002600 | APPROVED | [5 empty] | No action as per Alex advise - KPTG-IntCorr-002681 |  | 2026-04-17 | KPTG-IntCorr-002681 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-11-06 | Ardon-TRANSMIT-000008 | NA | Trade Partner | Door by Door Schedule | 0 | 1 | 0 | NA | APPROVED | 2025-11-06 | WF-003220 | NA | 2025-11-13 |  | Due to VPN issues close out processed on 10/04/2026 | 2026-04-09 | 2026-04-10 | KPTG-TRANSMIT-015683 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-04-09 | KPTG-IntCorr-003446 | NA | Trade Partner | GENE SIGNAGE FOR APPROVAL | 1 | 0 | 0 | KPTG-IntCorr-003466 | APPROVED |  | NA | NA |  |  | Information on;ly |  | 2026-05-04 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-10 | Civilex-TRANSMIT-000226 | NA | Trade Partner | Sample Submission - Pavement Concrete mix design Hytec- Rev C | 0 | 1 | 0 | NA | APPROVED | 2026-04-10 | WF-005245 | NA | 2026-04-16 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016203 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-12 | Tradetec-TRANSMIT-000301 | NA | Trade Partner | M3-S4-South Pits | 4 | 0 | 0 | NA | REJECTED | [5 empty] | The Aconex revision number does not match the document revision number. KPTG-TRANSMIT-010853 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-04-09 | ACG-TRANSMIT-000037 | NA | Trade Partner | DH7/8 ACG Document Tidy | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Distribution- No Longer in use |  |  | KPTG-TRANSMIT-002861 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-10 | D&E-TRANSMIT-000574 | NA | Trade Partner | NXM3S2 - Upper Roof Equipment Layout + Level 01 - Mechanical Pipe Layout Zones - Issued For Construction | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong revision attached in one drawing. (3635) |  | 2026-04-10 | KPTG-SADV-004756 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-10 | Tradetec-TRANSMIT-000418 | NA | Trade Partner | Tech Data - Sitewide - Multilayer Conduit | 0 | 3 | 0 | NA | APPROVED | 2026-04-10 | WF-005247 | NA | 2026-04-16 |  | Terminated as advised by Charlie Johnstone, for submitting updated document. |  | 2026-04-20 | KPTG-IntCorr-012061 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-10 | Civilex-TRANSMIT-000227 | NA | Trade Partner | Sample Submission - Landscape works and materials | 0 | 4 | 0 | NA | APPROVED | 2026-04-10 | WF-005248 | NA | 2026-04-21 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-10 | Stowe-A-TRANSMIT-000551 | NA | Trade Partner | STOWE - AS BUILT - SP3 GROUND FLOOR ZONE B1 - POWER LAYOUT - 10.04.2026 | 1 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 4096 | 2026-04-15 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-015856 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-09 | ECBS-TRANSMIT-000029 | NA | Trade Partner | Stage 4 - Revised shop drawings for the steel columns | 92 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Titles are not mentioned in drawing sheet and Aconex |  | 2026-04-10 | KPTG-TRANSMIT-015711 | Closed | 92 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-10 | WOCEP-TRANSMIT-000007 | NA | Trade Partner | IROCK PLUS I.CIP-01 TECH DATA | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-10 | HDRAus-TRANSMIT-000452 | NA | Consultant | M3 SW Uploaded Architectural Document - Int. Finishes Schedule and FF&E Schedule. | 0 | 2 | 0 | NA | APPROVED | 2026-04-10 | NA | 4098 | 2026-04-14 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-015744 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-10 | HDRAus-TRANSMIT-000454 | NA | Consultant | Stage 1 GMP - As Built Package | 20 | 2 | 0 | NA | REJECTED | [5 empty] | 1. The status in the register should be As-Built. 2. The revision format should be ABS-01 inside the title block, in the history box, and in the document register. 3. For the door schedules Excel file, document number format is incorrect. |  | 2026-04-10 | KPTG-DA-005933 | Closed | 22 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-12 | ARCST-TRANSMIT-000151 | NA | Trade Partner | North C1 Switchroom Secondary Steel - Issued for Approval | 35 | 0 | 0 | NA | REJECTED | [5 empty] | The document reference numbering does not align with the S4 project. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-04-10 | ACG-TRANSMIT-000038 | NA | Trade Partner | DH7/8 As-Builts | 8 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 1464 | 2026-04-16 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-002867 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-04-10 | D&E-TRANSMIT-000355 | NA | Trade Partner | SFN ITPs - Issued for Construction | 0 | 8 | 0 | KPTG-IntCorr-003467 | APPROVED |  | NA | NA |  |  | Distribution |  | 2026-04-14 | KPTG-TRANSMIT-002878 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-10 | D&E-TRANSMIT-000212 | SPARK-CRFI-KPG-000258 | Trade Partner | MWYCCB - GROUND LEVEL - PENETRATION LAYOUT ZONE 2 & ZONE 4 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 226 | 2026-04-17 |  |  | 2026-04-15 | 2026-04-23 | KPTG-TRANSMIT-000687 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-09 | RDSBIM-TRANSMIT-000185 | NA | Trade Partner | LEVEL 10 PARTITION WALL SUBMISSION | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-10 | KPTG-TRANSMIT-002876 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-09 | ccair-TRANSMIT-000113 | NA | Trade Partner | Level 15 - Mechanical Ductwork & Pipework IFC Updates | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2026-04-10 | KPTG-TRANSMIT-002877 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-09 | KPTG-TRANSMIT-002867 | NA | Trade Partner | Shenseki Bathtub 1510mm | 0 | 1 | 0 | NA | APPROVED | 2026-04-10 | WF-000991 | NA | 2026-04-14 | [5 empty] | Open | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-09 | JCBa-TRANSMIT-000240 | NA | Consultant | BTR Updated Drawings - For Construction | 18 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 557 | 2026-04-14 |  | NA | 2026-04-27 | 2026-04-27 | DRAFT-017203 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-09 | ccair-TRANSMIT-000114 | NA | Trade Partner | Level 15 Buildersworks Drawing Updates - IFC | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2026-04-10 | KPTG-TRANSMIT-002878 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-09 | KALLIBRE-TRANSMIT-000005 | NA | Trade Partner | IFC Door by Door Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-04-10 | WF-000345 | NA | 2026-04-14 |  | File superseded |  | 2026-04-10 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-12 | Tradetec-TRANSMIT-000302 | NA | Trade Partner | M3-S4-South Pits - IFA Shop Drawings CONSULTANT REVIEW-SHOP DRAWING | 4 | 0 | 0 | NA | APPROVED | 2025-12-12 | NA | 1643 | 2025-12-22 |  |  |  | 2026-01-20 | KPTG-TRANSMIT-011652 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-09 | Entire M-TRANSMIT-000028 | NA | Trade Partner | Issued for Construction | 5 | 0 | 0 | NA | APPROVED | 2026-04-10 | WF-000346 | NA | 2026-04-14 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-000726 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-09 | JCBa-TRANSMIT-000085 | NA | Consultant | GA Plans: First Floor Overall & Zone Plans; Ground Floor Overall Plan | 7 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 679 | 2026-04-14 |  | on 9/4/2026 due to VPN Connection issue, Aconex service is not available. | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-001295 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-09 | RDSBIM-TRANSMIT-000045 | NA | Trade Partner | GREYSTAR LEVEL 02 CONCRETE PROFILE PLAN | 6 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 681 | 2026-04-17 |  | on 9/4/2026 due to VPN Connection issue, Aconex service is not available. | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-001561 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-10 | Auspan-TRANSMIT-000196 | NA | Trade Partner | : Precast shop drawings for approval. Ground floor | 2 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 689 | 2026-04-17 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-001403 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-09 | Auspan-TRANSMIT-000197 | NA | Trade Partner | Precast shop drawings for approval. Level 3 zone 1, 2 | 62 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 691 | 2026-04-17 |  | on 9/4/2026 due to VPN Connection issue, Aconex service is not available. | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-001447 | Closed | 62 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-09 | Auspan-TRANSMIT-000198 | NA | Trade Partner | : Update already IFCed precast shop drawings. Ground floor | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - As advise by Kapitol PC, no review required; Register and distribute - on 9/4/2026 due to VPN Connection issue, Aconex service is not available. |  | 2026-04-10 | KPTG-TRANSMIT-001248 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-09 | Auspan-TRANSMIT-000199 | NA | Trade Partner | : Re: Precast shop drawings for approval. Ground floor | 2 | 0 | 0 | KPTG-IntCorr-000448 | APPROVED |  | NA | NA |  |  | on 9/4/2026 due to VPN Connection issue, Aconex service is not available. IFC - waiting for kapitol advise. KPTG-IntCorr-000448. No Review required, Register and distribute | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-001284 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-09 | Auspan-TRANSMIT-000200 | NA | Trade Partner | Re: Precast shop drawings for construction. Ground floor and level 1. | 43 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | on 9/4/2026 due to VPN Connection issue, Aconex service is not available. IFC - As advise by Kapitol PC, no review required; Register and distribute |  | 2026-04-10 | KPTG-TRANSMIT-001278 | Closed | 43 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-10 | Auspan-TRANSMIT-000201 | NA | Trade Partner | Update already IFCed shop drawings. | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - As advise by Kapitol PC, no review required; Register and distribute |  | 2026-04-10 | KPTG-TRANSMIT-001280 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-10 | LVPG-TRANSMIT-000029 | NA | Trade Partner | LVPG - Tech Data Submittals | 0 | 2 | 0 | NA | APPROVED | 2026-04-10 | WF-000372 | NA | 2026-04-15 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-001421 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-12 | RDSBIM-TRANSMIT-000127 | NA | Trade Partner | LINDRUM ¦ GROUND AND MEZZANINE LEVEL CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | NA | APPROVED | 2025-12-12 |  | 486 | 2026-01-07 |  |  | 2026-02-02 | 2026-02-02 | KPTG-SADV-002827 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-10 | INDS-TRANSMIT-000017 | NA | Trade Partner | Level 7 Hydraulic Calc (Pump Curve) | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | No Review required, forward to all consultants - |  | 2026-04-10 | KPTG-TRANSMIT-001250 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-10 | Auspan-TRANSMIT-000184 | NA | Trade Partner | Precast shop drawings for construction. Ground floor and level 1. | 25 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - As advise by Kapitol PC, no review required; Register and distribute - |  | 2026-04-10 | KPTG-TRANSMIT-001254 | Closed | 25 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-10 | POTTSENG-TRANSMIT-000020 | NA | Trade Partner | MAC: HYDRAULIC SERVICES - PENETRATION - GROUND - ZONE 2 LAYOU | 1 | 0 | 0 | KPTG-IntCorr-000450 | APPROVED |  | NA | 699 | 2026-04-17 |  | IFC - Waiting for advise KPTG-IntCorr-000450 | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-001332 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-10 | ccair-TRANSMIT-000008 | NA | Trade Partner | Ground Floor Mechanical Buildersworks | 1 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 394 | 2026-04-17 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-000937 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-03-19 | GPSElec-TRANSMIT-000009 | NA | Trade Partner | NextDC Stage 9-12 switchboard - MSB-JA-01 drawings - IFA | 32 | 0 | 0 | NA | APPROVED | 2026-03-23 | NA | 499 | 2026-03-31 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-002020 | Closed | 32 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-10 | Tradetec-TRANSMIT-000098 | NA | Trade Partner | Transmittal for HVP7 Shop Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 678 | 2026-04-17 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-002259 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-10 | Tradetec-TRANSMIT-000099 | NA | Trade Partner | Resubmission of TEL pits due to earthing | 8 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 679 | 2026-04-17 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-002267 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-10 | WGAVIC-TRANSMIT-000101 | NA | Consultant | M2 - Stage 11 Steelwork and Level 3 Slab - Issued for Certification | 14 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 681 | 2026-04-17 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-002292 | Closed | 14 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-10 | Tradetec-TRANSMIT-000101 | NA | Trade Partner | Pit Earthing | 0 | 1 | 0 | NA | APPROVED | 2026-04-10 | WF-000471 | NA | 2026-04-22 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-002479 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-10 | GPSElec-TRANSMIT-000013 | NA | Trade Partner | NextDC Stage 9-12 switchboard - MSB-JA-01 drawings - IFC | 32 | 0 | 0 | NA | APPROVED | 2026-04-11 | NA | 673 | 2026-04-17 |  |  | 2026-05-12 | 2026-05-12 | KPTG-TRANSMIT-003042 | Closed | 32 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-12 | Auscool-TRANSMIT-000060 | NA | Trade Partner | Cooling Tower Tech Data Issued For Approval | 0 | 1 | 0 | NA | APPROVED | 2025-12-12 | WF-000525 |  | 2025-12-16 |  |  | 2026-01-30 | 2026-01-30 | KPTG-TRANSMIT-001654 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-10 | DCN-TRANSMIT-000004 | NA | Trade Partner | M2S9 Link Bridge Structural Issued For Approval 01 Drawings Transmittal | 8 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 675 | 2026-04-17 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-002331 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-10 | WilsonPD-TRANSMIT-000012 | NA | Trade Partner | Equipment for approval | 0 | 12 | 0 | NA | APPROVED | 2026-04-10 | WF-000474 | NA | 2026-04-21 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-002516 | Closed | 12 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-10 | WGAVIC-TRANSMIT-000099 | NA | Consultant | M2 - Stage 10 Level 1 Updates - Issued for Construction | 3 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 677 | 2026-04-16 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-002239 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-08 | RDSBIM-TRANSMIT-000126 | NA | Trade Partner | MLC ¦ INDOOR SPORTS CENTRE LEVEL 02 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2026-04-08 | NA | 127 | 2026-04-10 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-002879 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-08 | RDSBIM-TRANSMIT-000127 | NA | Trade Partner | MLCSPR ¦ STAIR 05 PLAN & SECTION | 2 | 0 | 0 | NA | APPROVED | 2026-04-08 | NA | 129 | 2026-04-10 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-002945 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-08 | RDSBIM-TRANSMIT-000128 | NA | Trade Partner | MLCSPR ¦ CARPARK NORTH BLOCKWORK PLAN & ELEVATIONS | 1 | 0 | 0 | 0 | APPROVED | 2026-04-08 | NA | 131 | 2026-04-10 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-002880 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-10 | RDSBIM-TRANSMIT-000129 | NA | Trade Partner | MLCSPR ¦ CHAPEL CARPARK LANDSCAPE KEY PLAN AND SECTION | 4 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 487 | 2026-04-17 |  | KPTG-IntCorr-006793 | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-002864 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-08 | RDSBIM-TRANSMIT-000130 | NA | Trade Partner | MLCSPR ¦ CAR PARK SOUTH PARTITION WALL PLAN AND ELEVATION | 1 | 0 | 0 | NA | APPROVED | 2026-04-08 | NA | 133 | 2026-04-10 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-002915 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-10 | PROLMC-TRANSMIT-000028 | NA | Trade Partner | Proline Drawings IFC | 13 | 0 | 0 | NA | REJECTED | [5 empty] | WRONG DOCUMENT NUMBERING: REQUESTED TO RESUBMIT:KPTG-IntCorr-006799 |  | 2026-04-10 | KPTG-IntCorr-006799 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-10 | ARCH-TRANSMIT-000145 | NA | Trade Partner | MLC - SPR - Outdoor Court - South West Stair | 7 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 488 | 2026-04-15 |  |  | 2026-04-10 | 2026-04-10 | KPTG-SADV-004049 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2025-12-12 | KPTG-SADV-000869 | NA | Trade Partner | Wall penetration detail | 2 | 0 | 0 | NA | APPROVED | 2025-12-12 | WF-000175 |  | 2025-12-17 |  |  |  | 2025-12-19 | KPTG-TRANSMIT-000662 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-10 | TGRF-TRANSMIT-000103 | NA | Trade Partner | Fwd: Updated Plans | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Document Number and Title of drawings are incorrect, requested to resubmit: KPTG-SADV-004044 |  | 2026-04-10 | KPTG-SADV-004044 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-08 | Auspan-TRANSMIT-000065 | NA | Trade Partner | Precast shop drawings for construction. | 8 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per the direction from the Ashlin, we have updated these drawings into Document Register, and transmitted to all concerned parties: |  | 2026-04-08 | KPTG-TRANSMIT-002186 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-08 | Metzone-TRANSMIT-000014 | NA | Trade Partner | Ground and L1 Steel Shop Drawings_IFA | 44 | 0 | 0 | NA | REJECTED | [5 empty] | Document numbers of all drawings are incorrect, requested to resubmit:KPTG-SADV-003671 |  | 2026-04-08 | KPTG-SADV-003671 | Closed | 44 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-08 | KETE-TRANSMIT-000117 | NA | Trade Partner | PMU report | 0 | 2 | 0 | NA | APPROVED | 2026-04-08 | WF-000695 | NA | 2026-04-13 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-002263 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-10 | PCForm-TRANSMIT-000070 | NA | Trade Partner | Fwd: Level 2 (Updated), Level 11 to Roof Issued for IFC | 16 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Drawings, just transmitted all concerned parties: KPTG-SADV-003701 |  | 2026-04-10 | KPTG-SADV-003701 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-10 | Metzone-TRANSMIT-000016 | NA | Trade Partner | L10 - Steel Shop Drawings (IFA) | 11 | 0 | 0 | KPTG-IntCorr-000866 | APPROVED | 2026-04-22 | WF-000710 | NA | 2026-04-24 |  | AS PER THE DIRECTION FROM THE ASHLIN, WE ARE HOLDING OFF THESE DRAWINGS:KPTG-IntCorr-000866 As per instriction from Ashlin we terninate the workflow | 2026-04-24 | 2026-04-24 | KPTG-IntCorr-001156 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-08 | Entire M-TRANSMIT-000022 | NA | Trade Partner | VCD Technical Data Issued for Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision of this technical data needs to be c, requested to resubmit:KPTG-IntCorr-000246 |  | 2026-04-08 | KPTG-IntCorr-000246 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-08 | SES AU-TRANSMIT-000006 | NA | Trade Partner | Re: Security Tech Data- IFC | 0 | 18 | 0 | NA | APPROVED | 2026-04-08 | WF-000123 | NA | 2026-04-09 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-000351 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-08 | SES AU-TRANSMIT-000007 | NA | Trade Partner | Cable Containment Tech Data for Approval | 0 | 9 | 0 | NA | APPROVED | 2026-04-08 | WF-000124 | NA | 2026-04-13 |  | WORKFLOW TERMINATED, NEED TO REVISE & RESUBMIT.As per the direction from Mr. Harrison Cole, Substitution requirements are required for all the documents. As per the correspondence: KPTG-SADV-000292, we have terminated the existing workflow:WF-000124. | 2026-04-10 | 2026-04-10 | KPTG-IntCorr-000260 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-08 | SES AU-TRANSMIT-000008 | NA | Trade Partner | NVR Server Tech Data Rev 2 | 0 | 1 | 0 | NA | APPROVED | 2026-04-08 | WF-000125 | NA | 2026-04-13 |  |  | 2026-04-17 | 2026-04-20 | KPTG-TRANSMIT-000404 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-12 | Fyfe-TRANSMIT-000007 | NA | Consultant | Issued For Construction - Civil | 9 | 0 | 0 | NA | APPROVED | 2025-12-12 | WF-000094 | 187 | 2025-12-17 |  | Review void. |  | 2025-12-16 | NA | Closed | 9 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-08 | SES AU-TRANSMIT-000009 | NA | Trade Partner | TYPE J CABLE TECH DATA | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected: substitution form is required:KPTG-DA-000036 |  | 2026-04-08 | KPTG-DA-000036 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-08 | JCI-TRANSMIT-000013 | NA | Trade Partner | MEL11 - COLO 5 - Authorization to Ship forms | 0 | 3 | 0 | NA | APPROVED | 2026-04-08 | WF-000126 | NA | 2026-04-09 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-000348 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-08 | INGEN3D-TRANSMIT-000025 | NA | Trade Partner | Level 3-5 - Cast in Dowel & Precast Columns | 61 | 0 | 0 | NA | APPROVED | 2026-04-08 | WF-000297 | NA | 2026-04-13 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-001214 | Closed | 61 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-08 | INGEN3D-TRANSMIT-000026 | NA | Trade Partner | Level 2-4 - PC0200 - IFA Resubmission | 3 | 0 | 0 | NA | APPROVED | 2026-04-08 | WF-000296 | NA | 2026-04-13 |  | Total 3 dwgs - 1 already recived tx 25, WF-000296 (2) | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-001126 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-08 | INGEN3D-TRANSMIT-000023 | NA | Trade Partner | Level 3 - Cast In Dowels & Precast Columns - Revised IFC | 33 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | register updated |  | 2026-04-08 | NA | Closed | 33 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-08 | INGEN3D-TRANSMIT-000024 | NA | Trade Partner | Level 3 - Cast in Dowels - No longer in use | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | register updated - NO LONGER IN USE |  | 2026-04-08 | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-08 | Civilex-TRANSMIT-000064 | NA | Trade Partner | Swivel Joint PVC | 0 | 1 | 0 | NA | APPROVED | 2026-04-08 | WF-000300 | NA | 2026-04-14 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-001120 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-08 | Civilex-TRANSMIT-000065 | NA | Trade Partner | Micropile Design Package Rev 3 | 0 | 1 | 0 | NA | APPROVED | 2026-04-08 | WF-000298 | NA | 2026-04-14 |  | Terminated due to new revision - Civilex-TRANSMIT-000072 |  | 2026-04-11 | Civilex-TRANSMIT-000072 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-08 | Resonate-TRANSMIT-000013 | NA | Trade Partner | Updated acoustic report | 0 | 1 | 0 | NA | APPROVED | 2026-04-08 | WF-000301 | NA | 2026-04-14 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-002236 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-08 | Entire M-TRANSMIT-000023 | NA | Trade Partner | Mechanical shop drawings re-issued for approval | 2 | 0 | 0 | NA | APPROVED | 2026-04-08 | WF-000128 | NA | 2026-04-13 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-000417 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-01 | PARR-TRANSMIT-000019 | N/A | Trade Partner | Fuel Services - FUEL RETICULATION LOWER GROUND GA | 1 | 0 | 0 | KPTG-IntCorr-000712 | APPROVED | 2025-12-02 | N/A | 677 | 2025-12-08 |  |  | 2026-01-13 | 2026-01-13 | KPTG-TRANSMIT-002386 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-12 | Auspan-TRANSMIT-000032 | NA | Trade Partner | Precast shop drawings for approval. Zone 3 ground floor. | 21 | 0 | 0 | NA | APPROVED | 2025-12-12 | WF-000096 | 191 | 2025-12-18 |  |  |  | 2026-01-12 | KPTG-TRANSMIT-000373 | Closed | 21 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-08 | Entire M-TRANSMIT-000024 | NA | Trade Partner | Mechanical shop drawings IFC | 26 | 0 | 0 | NA | APPROVED | 2026-04-08 | WF-000127 | NA | 2026-04-10 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-000345 | Closed | 26 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-08 | ETNInd-TRANSMIT-000011 | NA | Trade Partner | Eaton UPS Quality Orientation PPT - For Information | 0 | 1 | 0 | NA | APPROVED | 2026-04-08 | WF-000129 | NA | 2026-04-09 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-000320 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-08 | ETNInd-TRANSMIT-000012 | NA | Trade Partner | Fwd: MEL11 COLO4 & 5 Technical Documents submission for Information | 0 | 13 | 0 | NA | APPROVED | 2026-04-08 | WF-000130 | NA | 2026-04-09 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-000323 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-08 | Entire M-TRANSMIT-000025 | NA | Trade Partner | VCDs Technical Data Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-08 | WF-000120 | NA | 2026-04-10 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-000327 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-08 | PenskePS-TRANSMIT-000009 | NA | Trade Partner | MEL11 COLO4 & 5 - SAT L1 and L2 Scripts | 0 | 2 | 0 | NA | REJECTED | [5 empty] | PC Suggested the resubmission:KPTG-IntCorr-000247 |  | 2026-04-08 | KPTG-IntCorr-000247 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-08 | PenskePS-TRANSMIT-000010 | NA | Trade Partner | MEL11 COLO4 & 5 - SAT L1 and L2 Scripts | 0 | 2 | 0 | NA | APPROVED | 2026-04-08 | WF-000122 | NA | 2026-04-13 |  |  | 2026-04-08 | 2026-04-08 | KPTG-TRANSMIT-000310 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-10 | VAE-Grp-TRANSMIT-000149 | NA | Trade Partner | MECHANICAL - MCS - NETWORK SCHEMATIC | 0 | 1 | 0 | KPTG-TRANSMIT-003378 | APPROVED |  | NA | NA |  |  | FC DOCS - SENT TO ALL PARTIES |  | 2026-04-10 | KPTG-TRANSMIT-003378 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-10 | SKS Tech-TRANSMIT-000179 | NA | Trade Partner | for APPROVAL submittal | 0 | 1 | 0 | NA | APPROVED | 2026-04-10 | WF-000979 | NA | 2026-04-14 |  |  |  | 2026-04-28 | KPTG-SADV-003076 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-10 | PARR-TRANSMIT-000050 | NA | Trade Partner | Fuel Services - BFS FD, BFS SCHEMATIC, FUEL RETIC L4 & L5 GA - IFC | 0 | 1 | 0 | NA | APPROVED | 2026-04-10 | WF-000986 | NA | 2026-04-14 |  |  | 2026-04-30 | 2026-04-30 | KPTG-WTRAN-002046 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-12 | Auspan-TRANSMIT-000031 | NA | Trade Partner | Precast shop drawings for approval. Basement panels in zone 3. | 5 | 0 | 0 | NA | APPROVED | 2025-12-12 | WF-000095 | 189 | 2025-12-18 |  |  |  | 2025-12-18 | Auspan-TRANSMIT-000031 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-10 | PARR-TRANSMIT-000050 | NA | Trade Partner | Fuel Services - BFS FD, BFS SCHEMATIC, FUEL RETIC L4 & L5 GA - IFC | 2 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 1191 | 2026-04-14 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-003407 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-08 | TATE_-TRANSMIT-000015 | NA | Trade Partner | Brush Seal IFC TDS | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision of the document is incorrect, requested to resubmit:KPTG-IntCorr-000250 |  | 2026-04-08 | KPTG-IntCorr-000250 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-08 | TATE_-TRANSMIT-000016 | NA | Trade Partner | Tate - Tech Data - HAC Door Hardware #2 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision of document ia not current, requested to resubmit:KPTG-IntCorr-000251 |  | 2026-04-08 | KPTG-IntCorr-000251 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-10 | TATE_-TRANSMIT-000017 | NA | Trade Partner | Tate - SCEC Pan Penetration Details | 2 | 0 | 0 | NA | APPROVED | 2026-04-10 | WF-000133 | NA | 2026-04-14 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-000566 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-10 | TATE_-TRANSMIT-000018 | NA | Trade Partner | Tate - Tech Data - Blanking Panel - IFC | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision of document is not current, requested them to resubmit:KPTG-IntCorr-000257 |  | 2026-04-10 | KPTG-IntCorr-000257 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-10 | PenskePS-TRANSMIT-000011 | NA | Trade Partner | MEL11 COLO4 & 5 - Enclosure drawings | 2 | 0 | 0 | NA | APPROVED | 2026-04-13 | WF-000136 | NA | 2026-04-16 |  | A SUBMITTED DOCUMENT IS NOT IN PDF FORMAT, REQUESTED TO RESUBMIT:KPTG-IntCorr-000258 | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-000338 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-10 | SES AU-TRANSMIT-000010 | NA | Trade Partner | Indoor dome Tech Data | 0 | 1 | 0 | NA | REJECTED | [5 empty] | PC Mr. Harry cole suggested resubmission: KPTG-SADV-000271 |  | 2026-04-10 | KPTG-SADV-000271 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-10 | Appselec-TRANSMIT-000050 | NA | Trade Partner | MEL11 - Electrical technical data | 0 | 2 | 0 | NA | APPROVED | 2026-04-10 | WF-000132 | NA | 2026-04-13 |  | one tech data is still in review | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000490 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-10 | TATE_-TRANSMIT-000019 | NA | Trade Partner | Brush Seal & Blanking Panel IFC Tech Data | 0 | 2 | 0 | NA | APPROVED | 2026-04-10 | WF-000134 | NA | 2026-04-13 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-000335 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-10 | Appselec-TRANSMIT-000051 | NA | Trade Partner | MELL11C45 - COLO 4 Cell 1 - Electrical Drawings - IFC | 4 | 0 | 0 | NA | APPROVED | 2026-04-10 | WF-000135 | NA | 2026-04-15 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-000341 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-12 | Tradetec-TRANSMIT-000303 | NA | Trade Partner | M3-S4 South Pits - IFA Shop Drawing - CP26, CP27 | 2 | 0 | 0 | NA | APPROVED | 2025-12-12 | NA | 1645 | 2025-12-22 |  |  |  | 2025-12-18 | KPTG-TRANSMIT-011112 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-09 | SMEPS-TRANSMIT-000233 | NA | Trade Partner | POWER & COMMS CONTAINMENT LAYOUT - INGROUND | 2 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 2800 | 2026-04-17 |  |  |  | 2026-05-11 | NA | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-09 | SKS Tech-TRANSMIT-000084 | NA | Trade Partner | SKS - Lighting Compliance Reports | 2 | 0 | 0 | NA | REJECTED | [5 empty] | rejected QA - due to no reference number, resubmitted via SKS Tech-TRANSMIT-000086 |  | 2026-04-10 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-09 | SKS Tech-TRANSMIT-000085 | NA | Trade Partner | Fwd: SKS - LV Submains | 0 | 1 | 0 | NA | APPROVED | [5 empty] | IFC Tech data distributed to trade partners & consultant |  | 2026-04-10 | KPTG-TRANSMIT-015639 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-09 | Tradetec-TRANSMIT-000417 | NA | Trade Partner | IFC - Stage 4 LVP44 | 1 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 2793 | 2026-04-17 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-016069 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-09 | Tradetec-TRANSMIT-000416 | NA | Trade Partner | IFC - Stage 4 Pit | 1 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 2791 | 2026-04-17 |  |  | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-015732 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-09 | SKS Tech-TRANSMIT-000083 | NA | Trade Partner | Retransmit of all equipment drawings | 7 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 2789 | 2026-04-20 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-09 | SKS Tech-TRANSMIT-000080 | NA | Trade Partner | SUBMAIN schedule and Legend update | 0 | 2 | 0 | NA | REJECTED | [5 empty] | due to incorrect type |  | 2026-04-10 | KPTG-TRANSMIT-015632 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-09 | D&E-TRANSMIT-000569 | NA | Trade Partner | ISSUED FOR APPROVAL - FOH & BOH AIR SCHEMATIC | 1 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 2784 | 2026-04-20 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016507 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-09 | D&E-TRANSMIT-000568 | NA | Trade Partner | SFN - Air Vent - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-10 | WF-005223 | NA | 2026-05-01 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-016247 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-09 | D&E-TRANSMIT-000571 | NA | Trade Partner | DX & VRF Air Conditioning - Issued for Approval | 0 | 2 | 0 | NA | APPROVED | 2026-04-10 | WF-005221 | NA | 2026-05-06 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-016434,KPTG-TRANSMIT-016436 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-12 | ARCST-TRANSMIT-000152 | NA | Trade Partner | North C1 Switchroom Secondary Steel - Issued for Approval (Resubmit) | 39 | 0 | 0 | NA | APPROVED | 2025-12-12 | WF-003582 | NA | 2026-01-07 |  | North C1 Switchroom Secondary Steel - Issued for Approval (Resubmit) | 2026-01-02 | 2026-01-29 | KPTG-TRANSMIT-012139 | Closed | 39 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-09 | ADP-TRANSMIT-000299 | NA | Consultant | S4 - Electrical - Updated Lineup Schematics | 4 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 2779 | 2026-04-14 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-017125 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-09 | TTW-TRANSMIT-000168 | NA | Trade Partner | TTW Civil and Traffic Drawings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect document number |  | 2026-04-10 | KPTG-TRANSMIT-015618 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-08 | RDSBIM-TRANSMIT-000129 | NA | Trade Partner | MLCSPR ¦ CHAPEL CARPARK LANDSCAPE KEY PLAN AND SECTION | 4 | 0 | 0 | KPTG-IntCorr-006793 | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-006793 |  | 2026-04-08 | KPTG-IntCorr-006793 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-10 | Civilex-TRANSMIT-000071 | NA | Trade Partner | Hydraulic Shop Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-04-10 | WF-000310, 396 | NA | 2026-04-14 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-001316 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-10 | Civilex-TRANSMIT-000070 | NA | Trade Partner | Micropile Design Addendum | 0 | 1 | 0 | NA | REJECTED | [5 empty] | rejected : covering sheet missing |  | 2026-04-10 | KPTG-TRANSMIT-001088 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-10 | Civilex-TRANSMIT-000069 | NA | Trade Partner | Concrete Mix Design - For Walls | 0 | 1 | 0 | NA | APPROVED | 2026-04-10 | WF-000303 | NA | 2026-04-14 |  |  | 2026-04-14 | 2026-04-14 | KPTG-TRANSMIT-001152 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-10 | RDSBIM-TRANSMIT-000023 | NA | Trade Partner | GROUND FLOOR TO LEVEL 09 STAIR/LIFT CORE 02 CONCRETE PROFILE PLAN SECTION AND ELEVATION | 3 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 398 | 2026-04-20 |  |  | 2026-04-14 | 2026-04-14 | KPTG-TRANSMIT-001148 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-09 | Civilex-TRANSMIT-000066 | NA | Trade Partner | Hydraulic Shop Drawings | 2 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED -due to VPN Issue processed on 10-04-2026 |  | 2026-04-10 | KPTG-TRANSMIT-001080 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-09 | Civilex-TRANSMIT-000067 | NA | Trade Partner | Grout Spec for PT Truncation | 0 | 1 | 0 | NA | APPROVED | 2026-04-10 | WF-000299 | NA | 2026-04-13 |  | due to VPN Issue processed on 10-04-2026 | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-001100 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-09 | WAM-TRANSMIT-000746 | NA | Consultant | Material Finshes Schedule Update | 0 | 1 | 0 | NA | APPROVED | 2026-04-10 | WF-000305 | NA | 2026-04-14 |  | due to VPN Issue processed on 10-04-2026 | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-001283 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-12 | ARCST-TRANSMIT-000153 | NA | Trade Partner | North C1 Switchroom Secondary Steel - Issued for Approval | 2 | 0 | 0 | NA | APPROVED | 2025-12-12 | WF-003582 | NA | 2026-01-07 |  |  |  | 2026-01-29 | KPTG-TRANSMIT-012144 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-09 | WAM-TRANSMIT-000747 | NA | Consultant | Detailed Design - A50 Core Plans sections and details. | 15 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 400 | 2026-04-14 |  | due to VPN Issue processed on 10-04-2026 | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-001198 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-09 | ArcadiaL-TRANSMIT-000003 | NA | Consultant | Landscape Architectural - Tender Documentation Updates | 43 | 0 | 0 | KPTG-IntCorr-000573 | APPROVED | [5 empty] | Clarification from Bradley-due to VPN Issue processed on 10-04-2026 | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-001230 | Closed | 43 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-09 | ArcadiaL-TRANSMIT-000003 | NA | Consultant | Landscape Architectural - Tender Documentation Updates | 0 | 1 | 0 | NA | APPROVED | 2026-04-10 | WF-000307 | NA | 2026-04-14 |  | due to VPN Issue processed on 10-04-2026 | 2026-05-07 | 2026-06-01 | KPTG-TRANSMIT-002053 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-10 | TTW-TRANSMIT-000137 | NA | Consultant | BP8 Construction issue | 15 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 403 | 2026-04-14 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-001332 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-10 | TTW-TRANSMIT-000138 | NA | Consultant | District Docklands Design Surface TIN | 1 | 0 | 0 | KPTG-IntCorr-000574 | APPROVED |  | NA | NA |  |  | clarification from enzo / john,CAD drawing - register updated |  | 2026-04-10 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-10 | TTW-TRANSMIT-000139 | NA | Consultant | Civil Stormwater PDF and DWG | 6 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 405 | 2026-04-14 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-001202 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-10 | TTW-TRANSMIT-000140 | NA | Consultant | BP4 certification update | 45 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 407 | 2026-04-14 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-001207 | Closed | 45 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-08 | SKS Tech-TRANSMIT-000077 | NA | Trade Partner | Fwd: SKS - IFC submissions | 0 | 2 | 0 | KPTG-TRANSMIT-015552 | APPROVED | [7 empty] | 2026-04-13 | KPTG-TRANSMIT-015828 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-08 | D&E-TRANSMIT-000564 | NA | Trade Partner | Re: PQM and Branch Monitoring - Issued for Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | REJECTED DUE TO REVISION NUMBER MISSING |  | 2026-04-08 | KPTG-DA-005878 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-08 | SKS Tech-TRANSMIT-000078 | NA | Trade Partner | Re: SKS - Lighting Compliance Reportsw | 0 | 2 | 0 | NA | APPROVED | [9 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-12 | SMEPS-TRANSMIT-000243 | NA | Trade Partner | SME- IFC Samples Submission - LABELS | 0 | 1 | 0 | NA | APPROVED | 2025-12-12 | WF-000851 | NA | 2025-12-19 |  |  | 2026-01-27 | 2026-01-27 | KPTG-TRANSMIT-002336 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-08 | KPTG-IntCorr-011631 | NA | Trade Partner | M3 S4 - Security Zoning Plans | 2 | 0 | 0 | NA | APPROVED | 2026-04-08 | NA | 2773 | 2026-04-15 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-016362 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-09 | KPTG-TRANSMIT-015611 | NA | Consultant | S4 ¦ SHOP DRAWING ¦ CONSULTANT REVIEW ¦ IFA ¦ ROOF STEEL WORKFLOW | 46 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected- Difference in revision number and revision number appears twice in the revision history. |  | 2026-04-10 | KPTG-TRANSMIT-015679 | Closed | 46 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-09 | KPTG-TRANSMIT-015610 | na | Consultant | STAGE 4 - RED STICK - KAPITOL REVIEW-HDRAus-TRANSMIT-000453-M3 Stage 4 - Document | 4 | 0 | 0 |  | REJECTED |  |  |  |  | 4 | Rejected -revision number and status of the documents appear different in Aconex and inside the documents | 2026-04-10 | 2026-04-10 | KPTG-TRANSMIT-015691 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-04-10 | ENF-TRANSMIT-000008 | NA | Consultant | Structural drawings | 12 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 47 | 2026-04-28 |  | 6 Drawings Superseded ENF-TRANSMIT-000009 8 Drawings will be submitted on 24th | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-000042 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-04-10 | WSP ANZ-TRANSMIT-000006 | NA | Consultant | WSP - 80% Tender Issue Drawings & Specifications (Electrical, Hydraulic, Mechanical & Fire Protection) | 47 | 3 | 0 | NA | REJECTED | [5 empty] | Incorrect attachment (HY Specification) 1 Document, 3 Drawings Superseded with WSP ANZ-TRANSMIT-000008. 1 Drawings Superseded With ANZ-TRANSMIT-000009 |  | 2026-04-13 | KPTG-DA-000107 | Closed | 50 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-13 | Nilsen3-TRANSMIT-000095 | NA | Trade Partner | Re: Copper tape sample submission | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect reference number |  | 2026-04-13 | KPTG-RFI-007253 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-13 | RDSBIM-TRANSMIT-000009 | NA | Trade Partner | MEL05C4 ¦ LEVEL 2 COLO 4 CEILING LAYOUT | 3 | 0 | 0 | NA | APPROVED | 2026-04-13 | WF - 000347 | NA | 2026-04-17 |  | NA | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-000773 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-13 | RDSBIM-TRANSMIT-000010 | NA | Trade Partner | MEL05C4 ¦ LEVEL 02 COLO 04 AREA PARTITION WALL LAYOUT | 3 | 0 | 0 | NA | APPROVED | 2026-04-13 | WF - 000348 | NA | 2026-04-17 |  | WF Terminated | 2026-04-16 | 2026-04-16 | NA | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-13 | SMPS-TRANSMIT-000109 SMPS-TRANSMIT-000111 | NA | Trade Partner | Re: Power Pack Sample Submissions | 0 | 9 | 0 | NA | REJECTED |  | NA | NA |  |  | Wrong file |  | 2026-04-13 | KAPITOL-TRANSMIT-001295 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-13 | NXT-TRANSMIT-001484 |  | Trade Partner | Fwd: M3 Stage 4 FAT reports (Batch 1) | 0 | 5 | 0 | NA | APPROVED |  | NA | NA |  |  | For record |  | 2026-04-13 | KPTG-TRANSMIT-015753 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-12 | SMEPS-TRANSMIT-000123 | NA | Trade Partner | M3 S3 - 22KV Precast Panel & Elevation Shop Drawings - FOA-1 | 5 | 0 | 0 | NA | APPROVED | 2025-12-12 | WF-003583 / WF-003737 |  | 2025-12-30 |  | Workflow terminated and resubmittted - as per requested my Max H |  | 2026-01-29 | KPTG-TRANSMIT-012081 / KPTG-TRANSMIT-012098 | Closed | 5 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-09 | VAE-Grp-TRANSMIT-000148 | NA | Trade Partner | IFA - MECHANICAL - LOUVRES | 3 | 0 | 0 | NA | APPROVED | 2026-04-10 | WF-000989 | NA | 2026-04-14 |  | transmittal processed on 10-04-2026 due to VPN issue | 2026-04-30 | 2026-04-30 | KPTG-WTRAN-002053 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-10 | SKS Tech-TRANSMIT-000180 | NA | Trade Partner | for APPROVAL submittal | 0 | 1 | 0 | KPTG-IntCorr-001156 | APPROVED | 2026-04-15 | WF-001000 | NA | 2026-04-22 |  | Harryto confirm | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-003663 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-09 | RDSBIM-TRANSMIT-000267 | NA | Trade Partner | NXM3S4 GROUND FLOOR & LEVEL 01 SPEED PANEL LAYOUT AND ELEVATION | 2 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 2801 | 2026-04-14 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016158 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-10 | KPTG-TRANSMIT-015615 | NA | Trade Partner | Fwd: IP230-C1-East Eave Gutter Framing-IFA | 27 | 0 | 0 | NA | APPROVED | 2026-04-10 | WF-005240 | NA | 2026-04-24 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-017066 | Closed | 27 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-09 | ZIA-TRANSMIT-000045 | NA | Trade Partner | CSMS Commissioning Plan | 0 | 1 | 0 | NA | APPROVED | 2026-04-10 | WF-000988 | NA | 2026-04-14 |  | transmittal processed on 10-04-2026 due to VPN issue |  | 2026-05-27 | KPTG-TRANSMIT-003553 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-10 | KPTG-TRANSMIT-015616 | NA | Trade Partner | Fwd: NXM3S4: C1-West Eve Gutter Framing-IFA | 26 | 0 | 0 | NA | APPROVED | 2026-04-10 | WF-005244 | NA | 2026-04-25 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-017100 | Closed | 26 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-10 | Nilsen3-TRANSMIT-000093 | NA | Trade Partner | Re: Stage 4 ROPS A & B For Construction | 0 | 1 | 0 |  | APPROVED | [7 empty] | 2026-04-13 | KPTG-TRANSMIT-015841 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-10 | Nilsen3-TRANSMIT-000094 | NA | Trade Partner | Re NXM3S4 Nilsen ELC Shop Drawings - FOA #4 | 5 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 2807 | 2026-04-25 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-018758 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-10 | IVS-TRANSMIT-000359 | NA | Consultant | Stage 4 - Acosutic Screen Construction Issue (Revised as clouded) | 2 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 2809 | 2026-04-14 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-016655 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-11 | Civilex-TRANSMIT-000011 | NA | Trade Partner | Pile Shop Drawing | 6 | 0 | 0 | NA | APPROVED | 2025-12-11 | WF-000074 | NA | 2025-12-15 |  | CLOSED OUT DELAYED, DRAWINGS REVISED AND Closed out with revised sheet | 2026-01-20 | 2026-02-13 | KPTG-TRANSMIT-000439 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-10 | ECBS-TRANSMIT-000030 | NA | Trade Partner | Re: Stage 4 - Shop drawings (speedpanel lintels) for approval | 5 | 0 | 0 | NA | REJECTED | 2026-04-10 |  |  |  |  | REJECTED DUE TO INCORRECT TITLE ON THE ACONEX |  | 2026-04-10 | KPTG-DA-005932 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-13 | SKS Tech-TRANSMIT-000087 | NA | Trade Partner | Roof Power containment and PreFab hanger Details for construction | 4 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 2813 | 2026-04-20 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-016306 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-13 | Nilsen3-TRANSMIT-000096 | NA | Trade Partner | Re: Sample submissions | 0 | 4 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number |  | 2026-04-13 | KPTG-RFI-007261 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-10 | SMEPS-TRANSMIT-000234 | NA | Trade Partner | Re: SME - LIGHTING LUX LEVELS | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected- Difference in document number and document number is not mentioned inside the drawing |  | 2026-04-10 | KPTG-TRANSMIT-015720 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-10 | HDRAus-TRANSMIT-000453 | NA | Consultant | Stage 4 - Document upload - PDF and CAD - | 19 | 0 | 0 | NA | APPROVED | 2026-04-10 | NA | 2811 | 2026-04-14 |  |  |  | 2026-04-13 | KPTG-TRANSMIT-015808 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-13 | RDSBIM-TRANSMIT-000188 | NA | Trade Partner | LEVEL 12 TOWER B PARTITION WALL LAYOUT | 2 | 0 | 0 | NA | APPROVED | [5 empty] | IFC - Issued for construction only. |  |  |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-13 | Nilsen3-TRANSMIT-000098 | NA | Trade Partner | Sample submissions | 0 | 4 | 0 | NA | APPROVED | 2026-04-13 | WF-005256 | NA | 2026-05-04 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-016899 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-13 | RDSBIM-TRANSMIT-000186 | NA | Trade Partner | 511SRC ¦ LEVEL 11 TOWER A PARTITION LAYOUT (L11 to L13 TYPICAL) | 2 | 0 | 0 | NA | APPROVED | [5 empty] | IFC Drawings issued only for distribution. |  |  |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-13 | RDSBIM-TRANSMIT-000187 | NA | Trade Partner | 511SRC ¦ LEVEL 11 TOWER B PARTITION WALL LAYOUT | 2 | 0 | 0 | NA | APPROVED | [5 empty] | IFC drawings only for distribution. |  |  |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-12 | KPTG-IntCorr-001377 | NA | Trade Partner | Sample and Tech data submission | 0 | 11 | 0 | NA | APPROVED | 2025-12-12 | WF-000817 to 00827 | NA | 2025-12-18 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-13 | Tradetec-TRANSMIT-000103 | NA | Trade Partner | Technical Data Submission for Mastic Primer | 0 | 1 | 0 | NA | APPROVED | 2026-04-13 | WF-000486 | NA | 2026-04-24 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-002535 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-13 | D&E-TRANSMIT-000575 | NA | Trade Partner | SFN ITPs - Issued for construction | 0 | 8 | 0 | NA | APPROVED | 2026-04-13 | WF-005257 | NA | 2026-04-22 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-017770 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-07 | ADP-TRANSMIT-000297 | na | Consultant | Re: ADP MEL4561 - Stage 2 Updated drawings (EL & Comms) DOC-2 | 5 | 0 | 0 | NA | APPROVED | 2026-04-07 | na | 4074 | 2026-04-13 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-015734 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-13 | D&E-TRANSMIT-000576 | NA | Trade Partner | PRD - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-13 | WF-005258 | NA | 2026-05-04 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-015974 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-13 | INGEN3D-TRANSMIT-000701 | NA | Trade Partner | I3D-378 Next DC M3 Stage 4 - Level 1 (Zone 6) - MP0209 - IFC (13-04-2026) | 1 | 0 | 0 | NA | APPROVED | 2026-04-13 | WF-005261 | NA | 2026-04-20 |  | As requested by Finlay - The WF has been teminated |  | 2026-04-13 | KPTG-TRANSMIT-015813 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-13 | Stowe-A-TRANSMIT-000552 | NA | Trade Partner | STOWE - SUBMAIN RETICULATION - DATA HALLS - FC-01 | 4 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 4100 | 2026-04-24 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-016645 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-04-13 | W TITE-TRANSMIT-000012 | NA | Trade Partner | 22kV Switchroom Substrate Primer | 0 | 1 | 0 | NA | APPROVED | 2026-04-13 | WF-005262 | NA | 2026-04-24 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-017539 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-13 | PARR-TRANSMIT-000160 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - CLIENT DRAWINGS | 5 | 0 | 0 | NA | APPROVED | 2026-04-13 | WF-005263 | NA | 2026-04-24 |  | NXT-PA-004303 As per requested by Rohit - Terminated |  | 2026-04-15 | KPTG-IntCorr-011873 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-04-13 | Nilsen3-TRANSMIT-000097 | NA | Trade Partner | Nilsen ELC Shop Drawings - FOA Drawing | 0 | 1 | 0 | NA | APPROVED | 2026-04-13 | WF-005264 | NA | 2026-04-16 |  | As per Kian No action required |  |  | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-13 | SMEPS-TRANSMIT-000182 | NA | Trade Partner | 32A Switched Isolators | 0 | 1 | 0 | NA | APPROVED | 2026-04-13 | WF - 000349 | NA | 2026-04-17 |  | NA | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-000735 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-11 | RDSBIM-TRANSMIT-000008 | NA | Trade Partner | MEZZANINE CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2025-12-11 | NA | 145 | 2025-12-15 |  |  | 2026-01-13 | 2026-01-14 | KPTG-TRANSMIT-000273 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-13 | Entire M-TRANSMIT-000029 | NA | Trade Partner | Battery Room Fan Electrical Schematics - IFA | 4 | 0 | 0 | NA | APPROVED | 2026-04-13 | WF - 000350 | NA | 2026-04-17 |  | NA | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-000732 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-13 | D&E-TRANSMIT-000577 | NA | Trade Partner | NXM3S4 - Level 1 - Mechanical Duct Layout Zones - Issued For Approval | 4 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 2832 | 2026-04-21 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016502 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-12 | Nilsen3-TRANSMIT-000059 | NA | Trade Partner | NXM3S4 ¦ Nilsen ELC Shop Drawings - FOA #2 | 3 | 0 | 0 | NA | APPROVED | 2026-03-12 | NA | 2479 | 2026-03-25 |  |  | 2026-04-13 | 2026-04-13 | KPTG-TRANSMIT-015814 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-12 | Nilsen3-TRANSMIT-000059 | NA | Trade Partner | NXM3S4 ¦ Nilsen ELC Shop Drawings - FOA #2 | 3 | 0 | 0 | NA | APPROVED | 2026-03-12 | [8 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-13 | D&E-TRANSMIT-000578 | NA | Trade Partner | Switchroom Fire Dampers - Rev B - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-13 | WF-005266 | NA | 2026-05-04 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-015999 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-13 | SMPS-TRANSMIT-000111 | NA | Trade Partner | Re: Power Pack Sample Submissions | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Incomplete attachments |  | 2026-04-13 | DRAFT-009687 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-13 | SMPS-TRANSMIT-000112 | NA | Trade Partner | Hanwha Power Pack B08 - Electrical Shop Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 399 | 2026-04-16 |  |  | 2026-04-14 | 2026-04-14 | KAPITOL-TRANSMIT-001299 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-13 | Stowe-A-TRANSMIT-000553 | NA | Trade Partner | STOWE - AS-BUILTS - SP3 - 13.04.2026 - REVISION UPDATE - ELC | 6 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 4103 | 2026-04-16 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-016041 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-04-13 | D&E-TRANSMIT-000356 | NA | Trade Partner | SFN - DI Pressure Test Procedure ITP - IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Distribution |  | 2026-04-14 | KPTG-TRANSMIT-002875 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-01 | SMEPS-TRANSMIT-000236 | NA | Trade Partner | SME - IFC Submission | 47 | 0 | 0 | KPTG-IntCorr-002061 | APPROVED | 2025-12-08 | NA | 1292 | 2025-12-15 |  | 35 drawings submitted | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-002649 | Closed | 35 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-12 | KPTG-IntCorr-001378 | NA | Trade Partner | Ardon - sample submissions | 0 | 2 | 0 | NA | APPROVED | 2025-12-12 | WF-000828 to 00829 | NA | 2025-12-18 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-13 | Stowe-A-TRANSMIT-000553 | NA | Trade Partner | STOWE - AS-BUILTS - SP3 - 13.04.2026 - REVISION UPDATE ,TEL | 3 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 4104 | 2026-04-16 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-016041 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-04-13 | D&E-TRANSMIT-000358 | NA | Trade Partner | Fire Matrix - IFC-9 Transmittal | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | D&E-TRANSMIT-000357 is superseded with D&E-TRANSMIT-000358-Distribution |  | 2026-04-14 | KPTG-TRANSMIT-002873 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-13 | Coen-TRANSMIT-000005 | NA | Trade Partner | Precast Sample for Approval. | 0 | 1 | 0 | NA | APPROVED | 2026-04-14 | WF-000028 | NA | 2026-04-23 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-000595 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-13 | Tradetec-TRANSMIT-000104 | NA | Trade Partner | Transmittal of HVP5 & HVP6 Pit Shop Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 691 | 2026-04-20 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-002263 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-13 | TTW-TRANSMIT-000171 | NA | Consultant | TTW Civil and Traffic Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 4106 | 2026-04-15 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-015985 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-13 | Coen-TRANSMIT-000006 | NA | Trade Partner | COEN - Material Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-04-13 | WF-000027 | NA | 2026-04-21 |  |  | 2026-04-28 | 2026-04-29 | KPTG-TRANSMIT-000320 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-09 | Appselec-TRANSMIT-000050 | NA | Trade Partner | MEL11 - Electrical technical data | 0 | 1 | 0 | NA | APPROVED | 2026-04-10 | WF-000131 | NA | 2026-04-17 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000546 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-13 | VIA Arch-TRANSMIT-000096 | NA | Consultant | M2 BRIDGE LINK - ARCHITECTURAL - IFA (UPDATED TITLEBLOCK) | 7 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 689 | 2026-04-16 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-002296 | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-08 | Civilex-TRANSMIT-000009 | NA | Trade Partner | District Living - Stormwater | 0 | 25 | 0 | NA | APPROVED |  | NA | NA |  |  | REGISTER UPDATION ONLY |  |  |  | Closed | 25 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-13 | SKS Tech-TRANSMIT-000181 | NA | Trade Partner | ELECTRICAL IFC LAYOUTS ¦ GENERAL | 4 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 1195 | 2026-04-15 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-003403 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-13 | NXT-TRANSMIT-001488 | NA | Trade Partner | Operation manual for M3S4 | 0 | 1 | 0 | NA | APPROVED | 2026-04-13 | WF-005270 | NA | 2026-04-29 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-13 | SKS Tech-TRANSMIT-000183 | NA | Trade Partner | DATA HALL BLOCK DIAGRAM IFA LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 1197 | 2026-04-15 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-003591 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-13 | CEDWA-TRANSMIT-000010 | NA | Consultant | Updated Civil Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 1193 | 2026-04-15 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-003530 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-13 | PARR-TRANSMIT-000051 | NA | Trade Partner | Fuel Services - FUEL RETICULATION PUMP ROOM A&B | 2 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 1199 | 2026-04-15 |  | TERMINATED | 2026-04-23 | 2026-04-23 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-13 | Altaire-TRANSMIT-000001 | NA | Trade Partner | Re: M2 Stage 9-11 - Altaire Technical Data Transmittal (1) | 0 | 30 | 0 | NA | APPROVED | 2026-04-13 | WF-000488 | NA | 2026-04-23 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-002612 | Closed | 30 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-13 | TATE_-TRANSMIT-000020 | NA | Trade Partner | TATE - SCEC Shop Drawings - IFC - Batch 1 | 21 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing Status need to change, Requested retransmit:KPTG-IntCorr-000270 |  | 2026-04-13 | KPTG-IntCorr-000270 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-13 | PenskePS-TRANSMIT-000012 | NA | Trade Partner | MEL11 COLO4 & 5 - SAT L1 and L2 Scripts | 0 | 2 | 0 | NA | APPROVED | 2026-04-13 | WF-000137 | NA | 2026-04-14 |  |  | 2026-04-14 | 2026-04-14 | KPTG-TRANSMIT-000364 , KPTG-TRANSMIT-000376 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-03-13 | KPTG-IntCorr-003216 | NA | Trade Partner | SME Telecommunications | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Distribution only |  | 2026-04-13 | Awaiting approval | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-13 | Auspan-TRANSMIT-000014 | NA | Consultant | Precast shop drawings for construction. | 23 | 0 | 0 | NA | REJECTED | [5 empty] | title block format difference in the documents |  | 2026-04-13 | DRAFT-001121 | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-12 | Entire M-TRANSMIT-000012 | NA | Trade Partner | Mechanical Shop Drawings Issued for Approal | 5 | 0 | 0 | NA | APPROVED | 2025-12-12 |  |  |  |  | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-13 | JCBa-TRANSMIT-000087 | NA | Consultant | IFC A-41 - EXTERNAL ESCAPE STAIRS | 5 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 695 | 2026-04-15 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-001371 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-13 | JCBa-TRANSMIT-000088 | NA | Consultant | GA Plans Second Floor Overall & Zone Plans | 6 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 697 | 2026-04-15 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-001374 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-13 | 4DW-TRANSMIT-000095 | NA | Consultant | Stair Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 623 | 2026-04-16 |  |  | 2026-04-14 | 2026-04-14 | KPTG-SADV-003737 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-13 | JCBa-TRANSMIT-000089 | NA | Consultant | STRUCTURAL SETOUT PLAN: GROUND FLOOR ZONE 2 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Drawings superseded with JCBa-TRANSMIT-000090 - KPTG-IntCorr-000454 |  | 2026-04-13 | KPTG-IntCorr-000454 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-13 | 4DW-TRANSMIT-000096 | NA | Consultant | Entry Steelwork | 2 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 624 | 2026-04-16 |  |  | 2026-04-14 | 2026-04-14 | KPTG-SADV-003746 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-13 | JCBa-TRANSMIT-000090 | NA | Consultant | STRUCTURAL SETOUT PLAN: GROUND FLOOR ZONE 2 (UPDATE) | 1 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 702 | 2026-04-15 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-001406 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-13 | Auspan-TRANSMIT-000202: | NA | Trade Partner | Resubmit precast shop drawings for approval. Level 1 | 3 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 704 | 2026-04-20 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-001452 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-13 | Auspan-TRANSMIT-000203 | NA | Trade Partner | : Update already IFed shop drawings for construction. | 12 | 0 | 0 | KPTG-IntCorr-000455 | APPROVED |  | NA | NA | 2026-04-14 |  | Waiting for Kapitol Advise - KPTG-IntCorr-000455. Auspan included Rejected drawing for construction. 1 Rejected drawing omitted and resubmitted For Approval: 11 IFC. No Review required, Register and distribute - KPTG-TRANSMIT-001312. |  | 2026-04-14 | KPTG-TRANSMIT-001312. | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-13 | Auspan-TRANSMIT-000204: | NA | Trade Partner | Update already IFCed shop drawings for construction. | 20 | 0 | 0 | KPTG-IntCorr-000456 | APPROVED |  | NA | NA |  |  | Waiting for Kapitol Advise -KPTG-IntCorr-000456. Auspan included Rejected drawing for construction. IFC .No Review required, Register and distribute - KPTG-TRANSMIT-001316 | 2026-04-14 | 2026-04-14 | KPTG-TRANSMIT-001316 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-13 | Auspan-TRANSMIT-000205 | NA | Trade Partner | Resubmit precast shop dawings for approval. Ground floor and level 1. | 8 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 706 | 2026-04-20 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-001455 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-11 | TTW-TRANSMIT-000049 | NA | Consultant | Structural Documentation - Issued for Construction | 38 | 0 | 0 | NA | APPROVED | 2025-12-11 | NA | 148 | 2025-12-15 |  |  | 2025-12-16 | 2025-12-16 | KPTG-TRANSMIT-000259 | Closed | 38 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-13 | Auspan-TRANSMIT-000206 | NA | Trade Partner | Precast shop drawings for approval. Zone 4, 5 level 2 | 73 | 0 | 0 | NA | REJECTED |  | NA |  |  |  | Rejected due to incorrect drawing status, drawing number - |  | 2026-04-13 | KPTG-TRANSMIT-001291 | Closed | 73 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-13 | RDSBIM-TRANSMIT-000051 | NA | Trade Partner | 671CHP BASEMENT 4A TO BASEMENT 1 CORE WALL PLAN AND ELEVATIONS | 3 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 396 | 2026-04-20 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-000833 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-13 | crossfir-TRANSMIT-000005 | NA | Trade Partner | Wet Fire - Penetrations Basement 04 to ground | 4 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 397 | 2026-04-15 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-13 | LGCE-TRANSMIT-000021 | NA | Trade Partner | Basement 4-2 Lighting and power IFC | 6 | 0 | 0 | KPTG-IntCorr-000450 | APPROVED | 2026-04-14 | NA | 401 | 2026-04-21 |  | waiting for KAPITOL advise : KPTG-IntCorr-000450 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-13 | ccair-TRANSMIT-000009 | NA | Trade Partner | Level B1 Mechanical Ductwork & Pipework Layout - IFA | 1 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 399 | 2026-04-20 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000893 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-13 | PCForm-TRANSMIT-000136 | NA | Trade Partner | Revised precast grouting methodology for single height panels | 0 | 1 | 0 | NA | APPROVED | 2026-04-13 | WF-000313 | NA | 2026-04-15 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-001275 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-13 | HVHD-TRANSMIT-000011 | NA | Trade Partner | Updated SMP | 0 | 1 | 0 | NA | APPROVED | 2026-04-13 | WF-000314 | NA | 2026-04-15 |  |  | 2026-04-15 | 2026-04-15 | KPTG-WTRAN-000648 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-13 | Civilex-TRANSMIT-000072 | NA | Trade Partner | Micropile Design Addendum | 0 | 1 | 0 | NA | APPROVED | 2026-04-13 | WF-000312 | NA | 2026-04-15 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-001301 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-13 | INGEN3D-TRANSMIT-000029 | NA | Trade Partner | Ground Floor (Level 1) - Precast Columns - IFC | 80 | 0 | 0 | NA | APPROVED | 2026-04-13 | WF-000315 | NA | 2026-04-14 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-001254 | Closed | 77 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-13 | INGEN3D-TRANSMIT-000031 | NA | Trade Partner | Ground Floor (Level 1) - Cast in Dowels & Precast Column - No longer in use | 74 | 0 | 0 | NA | APPROVED | 2026-04-13 | WF-000316 | NA | 2026-04-14 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-001320 | Closed | 74 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-12 | TATE_-TRANSMIT-000035 | NA | Trade Partner | M2 - Tate - As-Builts - Ceiling / Grille / SCEC | 14 | 4 | 0 | NA | APPROVED | [5 empty] | As-Builts, No review required. Register updated and distributed to the Project Team. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-13 | Rinco-TRANSMIT-000006 | NA | Trade Partner | Level 1 IFA | 6 | 0 | 0 | KPTG-IntCorr-000580 | APPROVED | [5 empty] | victoria to confirm | 2026-05-01 | 2026-05-04 | KPTG-TRANSMIT-001486 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-13 | INGEN3D-TRANSMIT-000030 | NA | Trade Partner | I3D-389 District Living - Ground Floor (Level 1) - Cast in Dowels & Precast Column - No longer in use | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | NO LONGER IN USE - REGISTER UPDATED |  | 2026-04-13 | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-13 | WGAVIC-TRANSMIT-000103 | NA | Consultant | M2 - Stage 9 Plinth - Issued for Certification | 2 | 0 | 0 | NA | APPROVED | 2026-04-13 | NA | 683 | 2026-04-15 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-002243 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-13 | Eneraque-TRANSMIT-000002 | NA | Trade Partner | Bulk Storage Tank Datasheet & Calculation | 0 | 2 | 0 | NA | APPROVED | 2026-04-13 | WF-000484 | NA | 2026-04-23 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-002601 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-13 | EMMA'S EMAIL | NA | Trade Partner | ARCHITECTURAL | 14 | 0 | 0 | NA | APPROVED | 2026-04-13 | WF-000996 | NA | 2026-04-17 |  |  | 2026-04-21 | 2026-04-23 | KPTG-TRANSMIT-003485 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-13 | TGRF-TRANSMIT-000104 | NA | Trade Partner | MLC Pour 3B updated drawings | 5 | 0 | 0 | NA | REJECTED | [5 empty] | DOCUMENT NUMBER AND TITLE ARE INCORRECT:KPTG-SADV-004055 |  | 2026-04-13 | KPTG-SADV-004055 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-13 | Best.-TRANSMIT-000010 | NA | Consultant | Carpark Signage Supergraphic Finish Change | 1 | 0 | 0 | KPTG-IntCorr-006861 | APPROVED | 2026-04-14 | NA | 174 | 2026-05-29 |  | KAPITOL ADVICE AWAITS:KPTG-IntCorr-006861 | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-002916 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-25 | INDS-TRANSMIT-000036 | NA | Trade Partner | Dry Fire - Mezzanine | 1 | 0 | 0 | NA | APPROVED | 2026-03-31 | NA | 617 | 2026-04-06 |  |  | 2026-04-10 | 2026-04-13 | KPTG-SADV-003717 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-14 | DI-TRANSMIT-000156 | NA | Trade Partner | Re: PPT Door hardware schedule | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-04-14 | KAPITOL-TRANSMIT-001297 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-14 | RDSBIM-TRANSMIT-000179 | NA | Trade Partner | LINDRUM ¦ LEVEL 07 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 625 | 2026-04-21 |  |  | 2026-04-20 | 2026-04-20 | KPTG-IntCorr-000891 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-11 | TTW-TRANSMIT-000053 | NA | Consultant | Structural Documentation - Issued for Certification | 1 | 0 | 0 | NA | APPROVED | 2025-12-11 | NA | 148 | 2025-12-15 |  |  | 2025-12-16 | 2025-12-16 | KPTG-TRANSMIT-000259 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-14 | JLM Fenc-TRANSMIT-000002 | NA | Trade Partner | Tech Data- Basement/Carpark Fitout | 0 | 10 | 0 | NA | APPROVED | 2026-04-14 | WF - 000994 | NA | 2026-04-14 |  | File supersede and WF terminated. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-14 | KPTG-WTRAN-009808 | NA | Trade Partner | Waterproofing Compiled Specs Pack | 0 | 1 | 0 | NA | APPROVED | 2026-04-14 | WF-005273 | NA | 2026-04-20 |  | The WF has been generated as requested by Karthik S |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-14 | RDSBIM-TRANSMIT-000189 | NA | Trade Partner | LEVEL 13 TOWER B PARTITION WALL LAYOUT (L13 & L14 TYPICAL) | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC distribution only. |  | 2026-04-16 | KPTG-TRANSMIT-002901 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-14 | Stowe-A-TRANSMIT-000517 | NA | Trade Partner | Stowe - Tech Data Submission - 3PHASE 5 PIN OUTLET | 0 | 1 | 0 | NA | APPROVED | 2026-04-14 | WF-005272 | NA | 2026-04-15 |  | Reinitiated workflow as directed by Rabi David via Teams. | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016103 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-14 | RDSBIM-TRANSMIT-000180 | NA | Trade Partner | LINDRUM ¦ LEVEL 08 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 626 | 2026-04-21 |  |  | 2026-04-20 | 2026-04-20 | KPTG-IntCorr-000892 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-14 | HGP-TRANSMIT-000052 | NA | Trade Partner | Transmittal - Louvre Shop Drawing Rev02 | 14 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-04-14 | KPTG-TRANSMIT-000633 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-14 | D&E-TRANSMIT-000214 | NA | Trade Partner | FIRE MATRIX | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Cover page missing |  | 2026-04-14 | KPTG-TRANSMIT-000634 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-14 | Auspan-TRANSMIT-000014 | NA | Trade Partner | Precast shop drawings for construction | 21 | 0 | 0 | NA | APPROVED | 2026-04-14 | WF-000029 | NA | 2026-04-23 |  | partial close out KPTG-TRANSMIT-000177 (21 Document) | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-000177 | Closed | 21 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-14 | KALLIBRE-TRANSMIT-000004 | SPARK-CRFI-KPG-000623 | Trade Partner | Door Frame Shop Drawings Issued For Approval Rev 2 | 61 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 227 | 2026-04-21 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-001016 | Closed | 61 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-14 | RDSBIM-TRANSMIT-000003 | NA | Trade Partner | NXGE01 ¦ GROUND FLOOR CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Document number and revision number to be corrected. |  | 2026-04-14 | KPTG-SADV-000139 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-12 | DS-TRANSMIT-000080 | NA | Trade Partner | GF H/L Water and L01 Drainage - Issued for approval | 6 | 0 | 0 | NA | REJECTED | [9 empty] | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-02-14 | CLADC-TRANSMIT-000017 | NA | Trade Partner | FSG12 robe hook | 0 | 1 | 0 | NA | APPROVED | 2026-03-26 | WF-000901 | NA | 2026-03-31 |  |  | 2026-04-14 | 2026-04-14 | KPTG-TRANSMIT-002739 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-14 | Auspan-TRANSMIT-000015 | NA | Trade Partner | Update precast dowel layout. | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with drawings status inside the drawing. |  | 2026-04-14 | KPTG-SADV-000140 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-14 | Stowe-A-TRANSMIT-000554 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - SUBMAIN RETICULATION - LOWER ROOF - FC-03 | 2 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 4108 | 2026-04-27 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-016578 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-14 | ARCST-TRANSMIT-000253 | NA | Trade Partner | C3 Switchroom Upper Gantry Handrail | 39 | 0 | 0 | NA | APPROVED | 2026-04-14 | WF-005277 | NA | 2026-04-17 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-017027 | Closed | 39 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-14 | Leemark-TRANSMIT-000024 | NA | Trade Partner | Rev 0 Tech Data Submission-LEEMARK | 0 | 47 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-14 | D&E-TRANSMIT-000579 | NA | Trade Partner | NXM3S2 - Lower Ground - Builders Works Layout + Sections B1 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 4110 | 2026-04-21 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016214 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-14 | HGP-TRANSMIT-000053 | SPARK-CRFI-KPG-000676 | Trade Partner | Transmittal-Louvre Shop Drawing IFA Rev02 | 15 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 228 |  |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-001368 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-14 | Civilex-TRANSMIT-000228 | NA | Trade Partner | Stage 2 - Landscape Planter box shop drawing - Rev B | 1 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 4112 | 2026-04-21 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-016267 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-14 | vdmcons-TRANSMIT-000131 | NA | Trade Partner | ME25 1004: D113 511-537 Sydney Rd Coburg - Shop Drawings & 3D IFC Model - L03 Steel Pavilion Marking Plans - Preliminary Issue - IFA - 2026-04-14 | 17 | 0 | 0 | NA | APPROVED | 2026-04-14 | WF - 000995 | NA | 2026-04-17 |  | File supersede and WF terminated. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-14 | Civilex-TRANSMIT-000229 | NA | Trade Partner | Stage 2 - Sample Submission - Landscape works and materials - updated naming | 0 | 4 | 0 | NA | APPROVED | 2026-04-14 | WF-005281 | NA | 2026-04-30 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-016606 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-12 | ccair-TRANSMIT-000078 | NA | Trade Partner | Level 09 & 10 IFC Mechanical Penetration Drawings | 8 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-14 | M.S.-TRANSMIT-000060 | NA | Trade Partner | IFC shop drawing for MS-24A - MS24B | 2 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-SADV-004066- The review of previous revision are Revise and Resubmit hence it need to be for approval, not a for construction. | 2026-04-14 | 2026-04-14 | KPTG-SADV-004066 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-14 | D&E-TRANSMIT-000580 | NA | Trade Partner | Upper Roof & Roof - CHW Pipe Layout | 1 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 2825 | 2026-04-17 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-016316 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-14 | Hames-TRANSMIT-000149 | NA | Consultant | Door Hardware Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-04-14 | NA | 1201 | 2026-04-16 |  | HS requested to void - due to some urgent revision and as confirmed by Harrison |  | 2026-04-18 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-14 | ASV-TRANSMIT-000166 | NA | Trade Partner | Revised Hydraulic Sample's | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Multiple status and stages in a single transmittal. |  | 2026-04-14 | KPTG-SADV-004799 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-14 | Hames-TRANSMIT-000150 | NA | Consultant | Booster Assembly for coordination | 1 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 1203 | 2026-04-16 |  |  | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-003395 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-26 | Nilsen3-TRANSMIT-000077 | NA | Trade Partner | LV Earth Cable Sample | 0 | 1 | 0 | NA | APPROVED | 2026-03-25 | WF-005030 | NA | 2026-04-16 |  |  | 2026-04-14 | 2026-04-14 | KPTG-TRANSMIT-015889 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-14 | Stowe-A-TRANSMIT-000555 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - LIGHTING LAYOUT - GROUND FLOOR - SP3 | 1 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 4115 | 2026-04-17 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-016037 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-14 | Tradetec-TRANSMIT-000420 | NA | Consultant | IFC - Stage 4 South HVP36 | 1 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 2829 | 2026-04-17 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-016098 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-04-14 | ABB-TRANSMIT-000035 NXT-TRANSMIT-001489 | NA | Trade Partner | Fwd: As Built drawings for M3-22-HVSB-A | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Distributed to boarder team |  | 2026-04-14 | KPTG-TRANSMIT-015880 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-14 | Stowe-A-TRANSMIT-000556 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - MDB SCHEMATICS - 14.04.2026 | 1 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 4117 | 2026-04-23 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-017120 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-12 | Rinco-TRANSMIT-000025 | NA | Consultant | Structural drawings Issued for Construction | 27 | 0 | 0 | NA | APPROVED | 2025-12-12 | WF-000098 | 195 | 2025-12-17 |  |  |  | 2026-01-15 | KPTG-TRANSMIT-000407 | Closed | 27 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-14 | SMEPS-TRANSMIT-000236 | NA | Trade Partner | Stage 4 - Lightning Protection Layout (C04) | 1 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 2866 | 2026-04-24 |  | Old WF- 2835 | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-017890 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-14 | ARCST-TRANSMIT-000254 | NA | Trade Partner | C3 Switchroom Upper Gantry Grating - Issued for Approval | 72 | 0 | 0 | NA | APPROVED | 2026-04-14 | WF-005288 | NA | 2026-04-16 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-14 | KPTG-IntCorr-011841 | NA | Trade Partner | Re: Technical Data | 0 | 2 | 0 | NA | APPROVED | 2026-04-14 | WF-005289 | 0 | 2026-04-17 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-018029 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-14 | Tradetec-TRANSMIT-000421 | NA | Trade Partner | Sitewide - Tech Data - Slip Couplings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Charlie Johnstone requested to hold with proceeding the document as the document contains wrong information. |  | 2026-04-14 | KPTG-IntCorr-011852 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-14 | ARCST-TRANSMIT-000258 | NA | Trade Partner | C1 Roof Stairs - Issued for Approval | 42 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision number in revision history table and difference in title |  | 2026-04-14 | KPTG-TRANSMIT-015906 | Closed | 42 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-14 | HDRAus-TRANSMIT-000455 | NA | Consultant | M3 Stage 4 - Oversized Penetration Infill Details Security Corridor Walls - PDF and CAD | 10 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 2837 | 2026-04-17 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-016079 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-14 | RDSBIM-TRANSMIT-000046 | NA | Trade Partner | GREYSTAR BASEMENT FLOOR CONCRETE PROFILE KEY PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 708 | 2026-04-21 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-001588 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-14 | Auspan-TRANSMIT-000207 | NA | Trade Partner | Precast shop drawings for construction. Ground floor. | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - No Review required, Register and distribute - |  | 2026-04-14 | KPTG-TRANSMIT-001309 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-14 | M.2-TRANSMIT-000019: | NA | Trade Partner | Electrical Services - Revised Ground Zone 1 Penetration layout | 1 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 711 | 2026-04-21 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-001353 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-14 | Auspan-TRANSMIT-000208 | NA | Trade Partner | Updated shop drawings for approval. | 1 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 714 | 2026-04-21 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-001516 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-12 | IVS-TRANSMIT-000298 | NA | Consultant | Stage 4 - Switchroom Plans Zone C3 (Certification Issue) | 9 | 0 | 0 | NA | APPROVED | 2025-12-12 | NA | 1647 | 2025-12-16 |  |  |  | 2025-12-18 |  | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-14 | Auspan-TRANSMIT-000209 | NA | Trade Partner | Re: Precast shop drawings for approval. Zone 4, 5 level 2 | 73 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 716 | 2026-04-21 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-001526 | Closed | 73 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-14 | Auspan-TRANSMIT-000210: | NA | Trade Partner | Update already iFCed shop drawings | 25 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - No Review required, Register and distribute - |  | 2026-04-14 | KPTG-TRANSMIT-001318 | Closed | 25 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-14 | RDSBIM-TRANSMIT-000052 | NA | Trade Partner | 671CHP LEVEL 01 CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 403 | 2026-04-21 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-000878 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-14 | EFP-TRANSMIT-000014 | NA | Trade Partner | EFP Tech Data Issued for Construction | 0 | 15 | 0 | NA | REJECTED | [5 empty] | Rejected: attached document is a reviewed document of Previous revision, requested to resubmit: KPTG-IntCorr-000272 |  | 2026-04-14 | KPTG-IntCorr-000272 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-14 | Tradetec-TRANSMIT-000105 | NA | Trade Partner | Technical Data Submission for Waterproofing Membrane | 0 | 1 | 0 | NA | APPROVED | 2026-04-14 | WF-000491 | NA | 2026-04-21 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-002455 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-14 | Tradetec-TRANSMIT-000106 | NA | Trade Partner | Technical Data Submission for Mudstone (Haul Road) | 0 | 1 | 0 | NA | APPROVED | 2026-04-14 | WF-000489 | NA | 2026-04-24 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-002378 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-14 | VIA Arch-TRANSMIT-000087 | NA | Consultant | M2 S9-S11 Building Permit Issue GA, Signage & Cover Sheet | 3 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 697 | 2026-04-17 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-002582 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-14 | VIA Arch-TRANSMIT-000091 | NA | Consultant | Stage 9 Concrete Profile Plans - Level 1 and 2 | 2 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 698 | 2026-04-17 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-002031 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-14 | VIA Arch-TRANSMIT-000093 | NA | Consultant | M2 S9-11 L1 Design Change General Arrangement Plans | 3 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 695 | 2026-04-17 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-002251 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-14 | VIA Arch-TRANSMIT-000095 | NA | Consultant | M2 S9-11 Building Permit Issue Update | 26 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 694 | 2026-04-17 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-002247 | Closed | 26 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-01 | SMEPS-TRANSMIT-000237 | NA | Trade Partner | SME - IFC Submission | 2 | 0 | 0 | KPTG-IntCorr-002062 | APPROVED | 2025-12-03 | NA | 1281 | 2025-12-10 |  |  | 2025-12-16 | 2025-12-16 | KPTG-TRANSMIT-002201 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-12 | VIA Arch-TRANSMIT-000020 | NA | Consultant | 22kV HVSB Architectural For Construction Package | 48 | 0 | 0 | NA | APPROVED | 2025-12-12 |  |  |  |  | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-14 | VIA Arch-TRANSMIT-000097 | NA | Consultant | Stage 11 Concrete Profile and GA Plans | 2 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 700 | 2026-04-17 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-002139 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-14 | Entire M-TRANSMIT-000028 | NA | Trade Partner | Mechanical shop drawings IFC | 10 | 0 | 0 | NA | APPROVED | 2026-04-14 | WF-000138 | NA | 2026-04-16 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-000414 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-14 | Entire M-TRANSMIT-000029 | NA | Trade Partner | Mechanical shop drawings IFA | 2 | 0 | 0 | NA | APPROVED | 2026-04-14 | WF-000139 | NA | 2026-04-17 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-000432 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-14 | Appselec-TRANSMIT-000052 | NA | Trade Partner | COLO Cable Reel No Longer In Use | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer in use, just transmitted to all parties:KPTG-TRANSMIT-000370 |  | 2026-04-14 | KPTG-TRANSMIT-000370 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-14 | Entire M-TRANSMIT-000030 | NA | Trade Partner | VCD Technical Data IFA Rev C2 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | REVISION SHOULD BE CHTONOLOGICAL ORDER, REQUESTED TO RESUBMIT:KPTG-IntCorr-000274 |  | 2026-04-14 | KPTG-IntCorr-000274 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-14 | PCForm-TRANSMIT-000138 | NA | Trade Partner | Stair a.2 shutter layout stage 1 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED : DRAWING NO. ERROR |  | 2026-04-14 | KPTG-TRANSMIT-001145 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-14 | PCForm-TRANSMIT-000140 | NA | Trade Partner | Stair a.2 shutter layout stage 1 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings re-issued with TX 142 |  | 2026-04-14 | PCForm-TRANSMIT-000142 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-14 | PCForm-TRANSMIT-000141 | NA | Trade Partner | Placing boom 1 footing design IFC | 1 | 0 | 0 | NA | REJECTED | [5 empty] | MERGED DOC - REJECTED |  | 2026-04-14 | KPTG-TRANSMIT-001156 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-14 | PCForm-TRANSMIT-000142 | NA | Trade Partner | PCF core transmittal | 14 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 441 | 2026-04-23 |  | 1 DRAWING - WRONG ATTACHMENT (Total 15)- reissued trn#146 | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-001407 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-14 | KPTG-IntCorr-000583 | NA | Consultant | Landscape - Town Planning Secondary Consent | 54 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | REGISTERED AND FORWARDED TO ALL PARTIES |  | 2026-04-16 | KPTG-TRANSMIT-001190 | Closed | 54 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2025-12-12 | CECPL-TRANSMIT-000011 | NA | Trade Partner | MEPF Issued For Construction Documentation - MEFH | 55 | 0 | 0 | NA | APPROVED | 2025-12-12 |  | 256 | 2025-12-15 |  |  |  | 2025-12-16 | KAPITOL-TRANSMIT-000924 | Closed | 55 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-14 | KPTG-IntCorr-000577 | NA | Consultant | Apartment Matrix Update - Secondary Consent | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | REGISTERED AND FORWARDED TO ALL PARTIES |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-15 | SMEPS-TRANSMIT-000237 | NA | Trade Partner | SME - MSSB Shop Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 2839 | 2026-04-22 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-017074 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-15 | RDSBIM-TRANSMIT-000190 | NA | Trade Partner | ¦ LEVEL 14 TOWER A PARTITION WALL LAYOUT (L14 & L15 TYPICAL) | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC only for distribution. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-15 | INTRFRM-TRANSMIT-000009 | NA | Trade Partner | Geelong Edge - Hydraulic Tech Data (Submission 2) | 0 | 9 | 0 | NA | APPROVED | 2026-04-15 | WF-000030 | NA | 2026-04-23 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000324 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-15 | SKS Tech-TRANSMIT-000090 | NA | Trade Partner | Small Power for data halls | 4 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 2841 | 2026-04-22 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-017384 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-14 | RDSBIM-TRANSMIT-000131 | NA | Trade Partner | MLCSPR ¦ JUNIOR SCHOOL LANDSCAPE PLAN | 5 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 172 | 2026-04-17 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-002826 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-14 | M.S.-TRANSMIT-000003 | NA | Trade Partner | Batch 1 & 2 Shop drawings. | 18 | 0 | 0 | NA | REJECTED | [5 empty] | Title block differs across the drawings |  | 2026-04-15 | KPTG-TRANSMIT-000642 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-15 | MLAW-TRANSMIT-000003 | NA | Trade Partner | THERMACORD SLIDING DOORS - SHOP DRAWINGS | 7 | 0 | 0 | NA | APPROVED | 2026-04-15 | WF-000701 | NA | 2026-04-16 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-002296 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-14 | Mail from lawden - WMI | NA | Consultant | NEL-CNT-WMI-2800-BAR-DPK | 77 | 2 | 0 | NA | APPROVED | [9 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-15 | Mail from Lawden - ELC | NA | Consultant | Electrical | 13 | 2 | 0 | NA | APPROVED |  |  | #229 | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-11 | RDSBIM-TRANSMIT-000024 |  | Trade Partner | MWYCCB ¦ L01 RCP KEY PLAN AND LAYOUT | 5 | 0 | 0 | NA | APPROVED | 2025-12-12 | WF-000102 | 67 | 2025-12-19 |  | KPTG-IntCorr-001132 |  | 2026-06-29 | KPTG-TRANSMIT-001355 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-03 | SMEPS-TRANSMIT-000088 | SPARK-CRFI-KPG-000462 | Trade Partner | IFA - Electrical Sections & Schematics | 0 | 0 | 0 |  | APPROVED | 2025-12-03 | WF-000087 | 49 | 2025-12-10 |  | 1 pending document since january - closed |  | 2026-04-15 | KPTG-TRANSMIT-000638 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-14 | PROLMC-TRANSMIT-000029 | NA | Trade Partner | Sunshade caulking superseeded tech sheet PROLMC-ARCH-SMP-007 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | WRONG ATTACHEMENT:KPTG-SADV-004070 |  | 2026-04-14 | KPTG-SADV-004070 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-14 | Best.-TRANSMIT-000009 | NA | Consultant | Revised schedule and plan | 7 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 174 | 2026-04-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-15 | RDSBIM-TRANSMIT-000004 | NA | Trade Partner | NXGE01 ¦ GROUND FLOOR CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 68 | 2026-04-21 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-000210 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-15 | SMEPS-TRANSMIT-000181 | NA | Trade Partner | PLC | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-04-15 | KPTG-TRANSMIT-000643 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-14 | 4DW-TRANSMIT-000097 | NA | Consultant | Entry Steelwork Update | 2 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 627 | 2026-04-17 |  |  | 2026-04-14 | 2026-04-14 | KPTG-SADV-003748 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-15 | SMEPS-TRANSMIT-000183 | NA | Trade Partner | PLC | 0 | 1 | 0 | NA | REJECTED | [5 empty] | same document received in SMEPS-TRANSMIT-000181 |  | 2026-04-15 | KPTG-TRANSMIT-000643 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-12 | D&E-TRANSMIT-000070 | SPARK-CRFI-KPG-000348 | Trade Partner | D&E-TRANSMIT-000070 | 0 | 1 | 0 | KPTG-IntCorr-001129 | APPROVED |  | NA | NA |  |  | NA |  | 2026-03-04 | KPTG-TRANSMIT-000500 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-15 | Stowe-A-TRANSMIT-000557 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - GF HOUSE CONTAINMENT - B1 - SP3 | 1 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 4120 | 2026-04-20 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-016033 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-15 | SMEPS-TRANSMIT-000182 | NA | Trade Partner | Fire rated cables | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision difference inside document and in Aconex |  | 2026-04-15 | KPTG-TRANSMIT-000644 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-15 | Tradetec-TRANSMIT-000422 | NA | Trade Partner | Sitewide - Tech Data - Slip Couplings | 0 | 1 | 0 | NA | APPROVED | 2026-04-15 | WF-005295 | NA | 2026-04-21 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-016363 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-15 | NXT-TRANSMIT-001491 | NA | Trade Partner | Fwd: NextDC M3 St-4_MSB-FA_FWT result | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For information | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-015924 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-15 | KPTG-TRANSMIT-015917 | NA | Trade Partner | SME Containment WF | 2 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 2843 | 2026-04-23 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-017391 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-15 | SKS Tech-TRANSMIT-000097 | NA | Trade Partner | Removing incorrect submissioms | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | NLIU |  | 2026-04-15 | KPTG-TRANSMIT-015926 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-15 | SMPS-TRANSMIT-000113 | NA | Trade Partner | Power Pack Sample Submissions | 0 | 9 | 0 | NA | APPROVED | 2026-04-15 | WF-000478 | NA | 2026-04-23 |  |  | 2026-04-20 | 2026-04-20 | DRAFT-009758 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-15 | SKS Tech-TRANSMIT-000091 | NA | Trade Partner | Updated Cable Schedule | 0 | 2 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect ref No. |  | 2026-04-15 | KPTG-RFI-007315 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-15 | INTRFRM-TRANSMIT-000010 | NA | Trade Partner | Geelong Edge - Comms & Elec Tech Data (Submission 1) | 0 | 19 | 0 | NA | REJECTED | [5 empty] | Mixed package submissions & Wrong Document numbers |  | 2026-04-15 | KPTG-SADV-000146 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-15 | SMEPS-TRANSMIT-000238 | NA | Trade Partner | SME - BTU IFC Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 2845 | 2026-04-22 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-018071 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-12 | HGP-TRANSMIT-000026 |  | Trade Partner | Ground Floor: Window Wall Frames | 18 | 0 | 0 | NA | REJECTED | [7 empty] | 2025-12-12 | KPTG-TRANSMIT-000303 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-15 | SMEPS-TRANSMIT-000239 | NA | Trade Partner | Re: SME - External structure Roof supports | 5 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED DUE TO REVISION MISSING |  | 2026-04-15 | KPTG-DA-005995 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-15 | D&E-TRANSMIT-000581 | NA | Trade Partner | NXM3S4 - Upper Roof & Roof - CHW Pipe Layout - Zone 2 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 2848 | 2026-04-23 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-016311 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-04-15 | WSP ANZ-TRANSMIT-000009 | NA | Consultant | WSP - Electrical Cover Sheets | 1 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 54 | 2026-04-27 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-000052 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-15 | SKS Tech-TRANSMIT-000092 | NA | Trade Partner | LIGHTING LAYOUT - LEVEL 1 - ZONE C1 | 1 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 2850 | 2026-04-22 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-017375 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-15 | Mail from Lawden - FIR | NA | Consultant | Electrical | 8 | 0 | 0 | NA | APPROVED |  |  | #230 | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-15 | Mail from Lawden - HYD | NA | Consultant | Electrical | 2 | 0 | 0 | NA | APPROVED |  |  | #231 | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-15 | Mail from Lawden - MEC | NA | Consultant | Electrical | 2 | 0 | 0 | NA | APPROVED |  |  | #232 | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-15 | Auspan-TRANSMIT-000016 | NA | Trade Partner | Resubmit precast shop drawings for approval | 36 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with revision number inside the drawings. PP020. |  | 2026-04-15 | KPTG-SADV-000147 | Closed | 36 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-15 | SMEPS-TRANSMIT-000184 | SPARK-CRFI-KPG-000463 | Trade Partner | PLC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-27 | KPTG-TRANSMIT-000737 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-15 | D&E-TRANSMIT-000215 | SPARK-CRFI-KPG-000587 | Trade Partner | VARIABLE SPEED DRIVES | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-12 | HGP-TRANSMIT-000027 |  | Trade Partner | Transmittal-IFC Shop Drawing FT01 CURTAIN WALL REVA | 65 | 0 | 0 | NA | REJECTED | [7 empty] | 2025-12-12 | KPTG-TRANSMIT-000304 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-15 | SMEPS-TRANSMIT-000185 | SPARK-CRFI-KPG-000583 | Trade Partner | Fire rated cables | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-000793 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-15 | Arc Plas-TRANSMIT-000004 | NA | Trade Partner | Tech Data - Framing, Fixings, Sealants | 0 | 5 | 0 | NA | APPROVED | 2026-04-15 | WF-000141 | NA | 2026-04-20 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-000532 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-15 | ARCST-TRANSMIT-000259 | NA | Trade Partner | Roof Screens IFA Drawings | 20 | 0 | 0 | NA | APPROVED | 2026-04-15 | WF-005300 | NA | 2026-05-01 |  |  | 2026-05-08 | 2026-05-14 | KPTG-TRANSMIT-017364 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-15 | ARCST-TRANSMIT-000257 | NA | Trade Partner | Re: M3S4 HV Room Platform - IFA | 74 | 0 | 0 | NA | APPROVED | 2026-04-15 | WF-005305 | NA | 2026-05-11 |  | Incorrect title | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-017048 | Closed | 74 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-15 | D&E-TRANSMIT-000217 | SPARK-CRFI-KPG-000258 | Trade Partner | MWYCCB - GROUND LEVEL - PENETRATION LAYOUT ZONE 8 & ZONE 9 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 233 | 2026-04-22 |  |  | 2026-04-20 | 2026-05-04 | KPTG-TRANSMIT-000795 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-15 | D&E-TRANSMIT-000582 | NA | Trade Partner | NXM3S4 - Ground - Mechanical Duct Layout - Zone 1 - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 2853 | 2026-04-23 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | KPTG-IntCorr-010478 | NA | Consultant | S4 NEXTDC CONSULTANT REVIEW - IFA - KPTG-TRANSMIT-013632 - S4 - C1 Cooling Tower Roof Framing | 135 | 0 | 0 | NA | APPROVED | 2026-03-27 | WF-004692 | NA | 2026-04-15 |  | Remaining 46 drawings are still under review | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-015946 | Closed | 89 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-15 | RDSBIM-TRANSMIT-000011 - | NA | Trade Partner | LEVEL 02 COLO 04 AREA PARTITION WALL LAYOUT AND ELEVATION | 5 | 0 | 0 | NA | APPROVED | 2026-04-15 | WF - 000351 | NA | 2026-04-22 |  | NA | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-000748 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-15 | D&E-TRANSMIT-000216 | NA | Trade Partner | SEISMIC INSTALLATION GUIDE | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Error in revision status |  | 2026-04-15 | KPTG-TRANSMIT-000645 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-15 | D&E-TRANSMIT-000218 | NA | Trade Partner | FIRE MATRIX | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-04-15 | KPTG-TRANSMIT-000646 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-12 | D&E-TRANSMIT-000072 | SPARK-CRFI-KPG-000315 | Trade Partner | ISSUED FOR APPROVAL - LEVEL 1 - PENETRATION LAYOUTS - MECHANICAL SERVICES - ZONES 1-7 | 4 | 0 | 0 | NA | APPROVED | 2025-12-12 | WF-000103 | 68 | 2025-12-19 |  |  |  | 2026-02-16 | KPTG-TRANSMIT-000445 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-15 | ADP-TRANSMIT-000302 | NA | Consultant | ADP MEL4561 - S2 - Updated Fire Detection drawings | 2 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 4124 | 2026-04-17 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-015994 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-15 | Tradetec-TRANSMIT-000423 | NA | Trade Partner | IFC - Stage 4 CP26 | 1 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 2872 | 2026-04-22 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-016269 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-15 | ADP-TRANSMIT-000303 | NA | Consultant | ADP MEL4561 - S2 - Updated Electrical drawing | 1 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 4126 | 2026-04-17 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-015972 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-15 | Schindle-TRANSMIT-000015 | NA | Trade Partner | IFC - Schindler HPI Drawings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Error in document revision |  | 2026-04-15 | KPTG-TRANSMIT-000647 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-15 | INTRFRM-TRANSMIT-000011 | NA | Trade Partner | Geelong Edge - Communications Tech Data (Submission 2) | 0 | 10 | 0 | NA | REJECTED | [5 empty] | Issue with Document and document status in Aconex. |  | 2026-04-15 | DRAFT-001173 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-15 | TATE_-TRANSMIT-000021 | NA | Trade Partner | Tate - Tech Data - Security Fixings & Silicone IFC | 0 | 2 | 0 | NA | APPROVED | 2026-04-15 | WF-000142 | NA | 2026-04-16 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-000393 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-15 | ADP-TRANSMIT-000304 | NA | Consultant | S4 Updated MSSB SCHEMATICS | 1 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 2861 | 2026-04-20 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-15 | INTRFRM-TRANSMIT-000012 | NA | Trade Partner | Geelong Edge - ElectricalTech Data (Submission 2) | 0 | 11 | 0 | NA | REJECTED | [5 empty] | Issue with document number, title and status. |  | 2026-04-15 | DRAFT-001175 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-15 | NXT-TRANSMIT-001495 | NA | Trade Partner | Script_UMTD-FF-A Panel | 1 | 0 | 0 | NA | APPROVED | 2026-04-15 | WF-005307 | NA | 2026-04-21 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-016243 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-12 | D&E-TRANSMIT-000073 | SPARK-CRFI-KPG-000236 | Trade Partner | AIR CONDITIONERS SPLIT TYPE | 0 | 1 | 0 | KPTG-IntCorr-001134 | APPROVED | [7 empty] | 2026-02-13 | KPTG-TRANSMIT-000436 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-15 | HDRAus-TRANSMIT-000458 | NA | Consultant | Stage 1 No Longer in use drawings | 90 | 0 | 0 | NA | APPROVED | [5 empty] | No Longer in Use documents, Updated register and moved to NLIU folder in ACC. Removed from published. |  | 2026-04-15 | KPTG-TRANSMIT-015964 | Closed | 90 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-15 | INTRFRM-TRANSMIT-000013 | NA | Trade Partner | Geelong Edge - Hydraulics Tech Data (Submission 3) | 0 | 4 | 0 | NA | APPROVED | 2026-04-15 | WF-000032 | NA | 2026-04-23 |  |  | 2026-04-28 | 2026-04-29 | KPTG-TRANSMIT-000316 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-15 | Appselec-TRANSMIT-000053 | NA | Trade Partner | Telecom Bill Of Materials For Approval - Wesco & AFL (Rev 1) | 0 | 2 | 0 | NA | APPROVED | 2026-04-15 | WF-000143 | NA | 2026-04-20 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-000464 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-15 | LNCPPL-TRANSMIT-000001 | NA | Trade Partner | BP1 - Electrical in-Ground Services - For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 70 | 2026-04-21 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-000162 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-15 | JCBa-TRANSMIT-000091 | NA | Consultant | 3rd & 4th FLOOR GA PLANS FOR IFC | 12 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 724 | 2026-04-17 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-001416 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-15 | RDSBIM-TRANSMIT-000047 | NA | Trade Partner | GREYSTAR LEVEL 03 CONCRETE PROFILE PLAN | 6 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 720 | 2026-04-21 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-001562 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-15 | Auspan-TRANSMIT-000211 | NA | Trade Partner | : Precast shop drawings for construction. Ground floor, level 1 and level 2 | 24 | 0 | 0 | KPTG-IntCorr-000470 | APPROVED |  | NA | NA |  |  | IFC - waiting for advise from Kapitol - KPTG-IntCorr-000470 - Rejected drawings included in the package and returned to the Trade partner to rectify - KPTG-SADV-001972 |  | 2026-04-17 | KPTG-SADV-001972 | Closed | 24 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-15 | Auspan-TRANSMIT-000212 | NA | Trade Partner | Precast shop drawings for approval. | 5 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 722 | 2026-04-21 |  |  | 2026-04-30 | 2026-04-30 | Auspan-TRANSMIT-000212 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-15 | Auspan-TRANSMIT-000213 | NA | Trade Partner | Ground Floor Zone 2 Panels | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - No Review required, Register and distribute - KPTG-TRANSMIT-001338 | 2026-04-15 | 2026-04-15 | KPTG-TRANSMIT-001338 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-15 | Entire M-TRANSMIT-000031 | NA | Trade Partner | VCDs Technical Data Issued for Approval Rev D | 0 | 1 | 0 | KPTG-IntCorr-000277 | REJECTED | [5 empty] | Revision of Technical Data is incorrect, requested to resubmit: KPTG-IntCorr-000277 |  | 2026-04-15 | KPTG-IntCorr-000277 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-12 | SMEPS-TRANSMIT-000093 | SPARK-CRFI-KPG-000419 | Trade Partner | PV System | 0 | 1 | 0 | KPTG-IntCorr-001136 | APPROVED | [7 empty] | 2026-01-30 | KPTG-TRANSMIT-000383 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-15 | LNCPPL-TRANSMIT-000002 | NA | Trade Partner | BP1 - Telcom In-Ground Services - For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 72 | 2026-04-21 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-000167 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-15 | ccair-TRANSMIT-000010 | NA | Trade Partner | : Level 01 - 19 - Buildersworks Layout - IFA | 7 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 405 | 2026-04-21 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000895 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-15 | RDSBIM-TRANSMIT-000053 | NA | Trade Partner | 671CHP LEVEL 04 CONCRETE PROFILE KEYPLAN AND SECTION | 3 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 407 | 2026-04-21 |  | ACC Review Voided byKapitol DM. | 2026-04-20 | 2026-04-20 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-15 | RDSBIM-TRANSMIT-000054 | NA | Trade Partner | 671CHP LEVEL 02 CONCRETE PROFILE PLAN AND SECTION | 3 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 410 | 2026-04-21 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-000874 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-15 | RDSBIM-TRANSMIT-000055 | NA | Trade Partner | 671CHP LEVEL 03 CONCRETE PROFILE KEYPLAN AND SECTION | 3 | 0 | 0 | NA | APPROVED | 2026-06-11 | NA | 552 | 2026-06-19 |  | Review 412 Voided as advised and initiated 552 | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-001229 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-04-15 | NXT-TRANSMIT-001492 | NA | Trade Partner | Fwd: As Built drawings for M3-22-HVSB-V | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For info |  | 2026-04-15 | KPTG-TRANSMIT-015970 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-15 | SES AU-TRANSMIT-000011 | NA | Trade Partner | MEL11-SESAU-Z-TDS-54-0- Indoor Dome | 0 | 1 | 0 | NA | APPROVED | 2026-04-15 | WF-000140 | NA | 2026-04-21 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-000396 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-15 | ASV-TRANSMIT-000048 | NA | Trade Partner | External Tank Farm Shop drawing | 2 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 702 | 2026-04-23 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-002271 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-15 | SMEPS-TRANSMIT-000025 | NA | Trade Partner | St 09-11 Electrical zone drawings | 1 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 705 | 2026-04-23 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-002359 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-15 | SMEPS-TRANSMIT-000025 | NA | Trade Partner | St 0911 Electrical zone drawings | 1 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 706 | 2026-04-23 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-002404 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-12 | SMEPS-TRANSMIT-000094 |  | Trade Partner | Revised Power & Comms Layouts - Ground Level (EV Conduits) | 3 | 0 | 0 | NA | APPROVED | 2025-12-12 | WF-000104 | 69 | 2025-12-19 |  |  |  | 2026-02-09 | KPTG-TRANSMIT-000422 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-15 | SMEPS-TRANSMIT-000025 | NA | Trade Partner | St 09-11 Telecom zone drawings | 1 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 707 | 2026-04-23 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-002312 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-15 | SMEPS-TRANSMIT-000025 | NA | Trade Partner | St 09-11 Telecom zone drawings | 5 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 708 | 2026-04-23 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-002745 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-15 | GPSElec-TRANSMIT-000014 | NA | Trade Partner | NextDC Stage 9-12 switchboard - MSB-JX-01 | 145 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 710 | 2026-04-23 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-003102 | Closed | 145 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-15 | GPSElec-TRANSMIT-000015 | NA | Trade Partner | NextDC Stage 9-12 switchboard MSB-JA-02 | 62 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 712 | 2026-04-23 |  |  | 2026-05-12 | 2026-05-12 | KPTG-TRANSMIT-003025 | Closed | 62 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-16 | INTRFRM-TRANSMIT-000014 | NA | Trade Partner | Geelong Edge - Communications Tech Data (Submission 3) | 0 | 10 | 0 | NA | APPROVED | 2026-04-16 | WF-000035 | NA | 2026-04-24 |  |  | 2026-04-28 | 2026-04-29 | KPTG-TRANSMIT-000308, KPTG-TRANSMIT-000312 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-16 | INTRFRM-TRANSMIT-000015 | NA | Trade Partner | Geelong Edge - Electrical Tech Data (Submission 3) | 0 | 11 | 0 | NA | APPROVED | 2026-04-16 | WF-000036 | NA | 2026-04-24 |  |  | 2026-04-28 | 2026-04-29 | KPTG-TRANSMIT-000304 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-16 | SKS Tech-TRANSMIT-000185 | NA | Trade Partner | for APPROVAL submittal DB-FS-B-GL-C-01 | 0 | 1 | 0 | NA | APPROVED | 2026-04-16 | WF-001003 | Na | 2026-04-22 |  |  |  | 2026-05-14 | KPTG-TRANSMIT-003679 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-15 | PROLMC-TRANSMIT-000030 | NA | Trade Partner | Re: MLC ¦ Proflex Caulking Sample - revised | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision of Document is not current, requested to resubmit: KPTG-SADV-004086 |  | 2026-04-15 | KPTG-SADV-004086 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-16 | Auspan-TRANSMIT-000017 | NA | Consultant | Precast shop drawings for approval | 38 | 0 | 0 | NA | APPROVED | 2026-04-16 | WF-000037 | NA | 2026-04-27 |  |  |  | 2026-04-27 | KPTG-TRANSMIT-000235 | Closed | 38 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-15 | PROLMC-TRANSMIT-000031 | NA | Trade Partner | Re: Sunshade caulking superseeded tech sheet PROLMC-ARCH-SMP-007 | 0 | 1 | 0 | NA | APPROVED | 2026-04-15 | WF-000927 | NA | 2026-04-21 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-002805 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-01 | SMEPS-TRANSMIT-000238 | NA | Trade Partner | SME - IFA Drawings | 2 | 0 | 0 | KPTG-IntCorr-002063 | APPROVED | 2025-12-04 | NA | 1283 | 2025-12-12 |  |  | 2026-01-20 | 2026-01-20 | KPTG-TRANSMIT-002308 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-12 | Leemark-TRANSMIT-000004 |  | Trade Partner | Updated Tech Data Submission-LEEMARK | 0 | 40 | 0 | KPTG-IntCorr-001143 | APPROVED | [9 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-15 | D&E-TRANSMIT-000012 | NA | Trade Partner | Loading Dock Exhaust Fan LEF-05.02 & Sound Attenuator Tech. Data - IFA | 0 | 1 | 0 | NA | APPROVED | 2026-04-15 | WF-000320 | NA | 2026-04-20 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-002443 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-15 | Jangho-TRANSMIT-000001 | NA | Trade Partner | 001-FT01 &FT02 TOWER VISUAL MOCK-UP SHOP DRAWING-01 | 14 | 0 | 0 | KPTG-TRANSMIT-001172 | REJECTED | [5 empty] | REJECTED |  | 2026-04-15 | KPTG-TRANSMIT-001172 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-15 | RDSBIM-TRANSMIT-000024 | NA | Trade Partner | GROUND FLOOR TO LEVEL 09 STAIR CORE 1 CONCRETE PROFILE PLAN SECTION AND ELEVATION | 3 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 414 | 2026-04-17 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-001471 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-15 | Jangho-TRANSMIT-000003 | NA | Trade Partner | 002_FT01 & FT02 SYSTEM CONCEPT DRAWING-01 | 28 | 0 | 0 | KPTG-TRANSMIT-001174 | REJECTED |  | NA | NA |  |  | REJECTED |  | 2026-04-15 | KPTG-TRANSMIT-001174 | Closed | 28 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-16 | KPTG-TRANSMIT-015523 | NA | Trade Partner | Roller Shutter O&M - Review | 0 | 1 | 0 | NA | APPROVED | 2026-04-16 | WF-005851 | NA | 2026-06-04 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018529 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-15 | Jangho-TRANSMIT-000004 | NA | Trade Partner | 003_FT-07 SYSTEM CONCEPT DRAWING-01 | 19 | 0 | 0 | KPTG-TRANSMIT-001175 | REJECTED |  | NA | NA |  |  | REJECTED |  | 2026-04-15 | KPTG-TRANSMIT-001175 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-15 | Jangho-TRANSMIT-000005 | NA | Trade Partner | 005-FT-07 & FT09 PODIUM VISUAL MOCK-UP SHOP DRAWING-01 | 17 | 0 | 0 | KPTG-TRANSMIT-001176 | REJECTED |  | NA | NA |  |  | REJECTED |  | 2026-04-15 | KPTG-TRANSMIT-001176 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-15 | RDSBIM-TRANSMIT-000134 | NA | Trade Partner | MLCSPR ¦ STAIR 05 PLAN & SECTION | 2 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 180 | 2026-04-21 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-002787 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-15 | Jangho-TRANSMIT-000010 | NA | Trade Partner | 004_FT-09 SYSTEM CONCEPT DRAWING-01 | 16 | 0 | 0 | KPTG-TRANSMIT-001177 | REJECTED |  | NA | NA |  |  | REJECTED |  | 2026-04-15 | KPTG-TRANSMIT-001177 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-15 | Jangho-TRANSMIT-000006 | NA | Trade Partner | S002-STRUCTURAL CALCULATION FOR FT01&FT02 SYSTE MCONCEPT DRAWING | 0 | 1 | 0 | KPTG-TRANSMIT-001178 | REJECTED |  | NA | NA |  |  | REJECTED |  | 2026-04-15 | KPTG-TRANSMIT-001178 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-12 | SSem-TRANSMIT-000003 | N/A | Trade Partner | Assemble SRC_Signage & Wayfinding_100% DD | 0 | 2 | 0 | NA | APPROVED | 2025-12-12 | WF-000830 | NA | 2025-12-18 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-15 | Jangho-TRANSMIT-000008 | NA | Trade Partner | S004-STRUCTURAL CALCULATION FOR FT09 SYSTE MCONCEPT DRAWING | 0 | 1 | 0 | KPTG-TRANSMIT-001179 | REJECTED |  | NA | NA |  |  | REJECTED |  | 2026-04-15 | KPTG-TRANSMIT-001179 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-15 | Jangho-TRANSMIT-000009 | NA | Trade Partner | S003-STRUCTURAL CALCULATION FOR FT07 SYSTE MCONCEPT DRAWING | 0 | 1 | 0 | KPTG-TRANSMIT-001180 | REJECTED |  | NA | NA |  |  | REJECTED |  | 2026-04-15 | KPTG-TRANSMIT-001180 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-16 | Greene-TRANSMIT-000002 | NA | Trade Partner | PR370 - 6x Additional curtains - Shop Drawings Rev 0 | 8 | 0 | 0 | NA | APPROVED | 2026-04-16 | WF - 996 | NA | 2026-04-22 |  | File supersede and WF terminated. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-15 | PCForm-TRANSMIT-000144 | NA | Trade Partner | Placing boom 2 footing design | 1 | 0 | 0 | KPTG-TRANSMIT-001181 | REJECTED |  | NA | NA |  |  | REJECTED |  | 2026-04-15 | KPTG-TRANSMIT-001181 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-15 | PCForm-TRANSMIT-000145 | NA | Trade Partner | Placing boom 1 footing design IFC upload | 1 | 0 | 0 | KPTG-IntCorr-000587 | APPROVED |  | NA | NA |  |  | victoria to clarify Register updated |  | 2026-04-16 | KPTG-IntCorr-000592 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-15 | PCForm-TRANSMIT-000147 | NA | Trade Partner | Formwork design transmittal | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | QA Checked - Register updated as per KPTG-IntCorr-000586 |  | 2026-04-15 | KPTG-IntCorr-000586 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-15 | PCForm-TRANSMIT-000148 | NA | Trade Partner | Level 3 existing precast propping plan | 1 | 0 | 0 | KPTG-IntCorr-000588 | REJECTED |  | NA | NA |  |  | REJETED |  | 2026-04-15 | KPTG-IntCorr-000588 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-15 | Civilex-TRANSMIT-000074 | NA | Trade Partner | Sample - SYM-ST-SMP-011 | 0 | 1 | 0 | NA | APPROVED | 2026-04-15 | WF-000323 | NA | 2026-04-20 |  | Terminated wf000323 - new w/flow 345 - proactive review on 20/04/2026 |  | 2026-04-20 | KPTG-TRANSMIT-001270 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-15 | RDSBIM-TRANSMIT-000132 | NA | Trade Partner | MLC ¦ INDOOR SPORTS CENTRE LEVEL 02 CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 182 | 2026-04-21 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-002884 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-15 | Civilex-TRANSMIT-000073 | NA | Trade Partner | 100mm, 150mm, 300mm Trench Grate | 0 | 1 | 0 | NA | APPROVED | 2026-04-15 | WF-000324 | NA | 2026-04-20 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-001608 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-11 | TTW-TRANSMIT-000051 | NA | Consultant | Structural Documentation - Issued for Certification | 62 | 0 | 0 | NA | APPROVED | 2025-12-11 | NA | 150 | 2025-12-15 |  |  | 2025-12-16 | 2025-12-16 | KPTG-TRANSMIT-000254 | Closed | 62 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-15 | HVHD-TRANSMIT-000012 | NA | Trade Partner | Updated SMP | 0 | 1 | 0 | NA | APPROVED | 2026-04-15 | WF-000325 | NA | 2026-04-20 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-001751 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-15 | RDSBIM-TRANSMIT-000133 | NA | Trade Partner | MLCSPR ¦ AQUATIC CENTRE WEST - LANDSCAPE | 1 | 0 | 0 | NA | APPROVED | 2026-04-15 | NA | 184 | 2026-04-21 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-002827 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-16 | D&E-TRANSMIT-000584 | NA | Trade Partner | L3 Cx Scripts - Issued for Approval | 0 | 18 | 0 | NA | REJECTED |  | NA | NA |  |  | Wrong attachments |  | 2026-04-16 | KPTG-RFI-007339 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-16 | D&E-TRANSMIT-000583 | NA | Trade Partner | Re: L2 Cx Scripts - Issued for Approval | 0 | 13 | 0 | NA | REJECTED |  | NA | NA |  |  | Wrong attachments |  | 2026-04-16 | KPTG-RFI-007338 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-15 | PCForm-TRANSMIT-000146 | NA | Trade Partner | CJF-121 drawing submittal | 1 | 0 | 0 | KPTG-IntCorr-000589 | APPROVED | 2026-04-20 | NA | 441 | 2026-04-23 |  | victoria to clarify | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-001407 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-15 | ArcadiaL-TRANSMIT-000004 | NA | Consultant | Landscape Architectural Updates - L4 and L11 | 10 | 0 | 0 | NA | REJECTED | [5 empty] | QA ERROR |  | 2026-04-17 | KPTG-TRANSMIT-001183 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-15 | KPTG-WTRAN-000655 | NA | Trade Partner | G&C HYDRAULICS SAMPLES | 0 | 4 | 0 | NA | APPROVED | 2026-04-15 | WF-000326 | NA | 2026-04-20 |  | TEAMS MESSAGE |  | 2026-05-06 | KPTG-TRANSMIT-001557 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-15 | KPTG-WTRAN-000656 | NA | Trade Partner | G&C-HY-TEC-014 - Mizu Drift Brass Trapscrew Grate Square 100mm Chrome | 0 | 1 | 0 | NA | APPROVED | 2026-04-15 | WF-000327 | NA | 2026-04-20 |  | TEAMS MESSAGE |  | 2026-05-06 | KPTG-TRANSMIT-001557 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-16 | D&E-TRANSMIT-000585 | NA | Trade Partner | NXM3S4 - Ground - Mechanical Duct Layout - Zone 4 - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 2868 | 2026-04-23 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-017151 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-16 | WEBBAUST-TRANSMIT-000069 | NA | Trade Partner | Webb B18 security drawings update | 3 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 400 | 2026-04-21 |  |  | 2026-04-22 | 2026-04-22 | DRAFT-009785 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-11 | TTW-TRANSMIT-000061 | NA | Consultant | Structural Documentation - Issued for Certification | 5 | 0 | 0 | NA | APPROVED | 2025-12-11 | NA | 150 | 2025-12-15 |  |  | 2025-12-16 | 2025-12-16 | KPTG-TRANSMIT-000254 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-16 | PARR-TRANSMIT-000052 | NA | Trade Partner | Fuel Services - L4 CABLE A&B GA - IFC | 2 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 1205 | 2026-04-20 |  |  | 2026-04-22 | 2026-04-23 | KPTG-TRANSMIT-003486 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-16 | Tradetec-TRANSMIT-000424 | NA | Trade Partner | Re: Stage 4 - IFA Drawings - LV: 36, 37, 50, 51, 52, 53, 54, 55 | 8 | 0 | 0 | NA | REJECTED | [5 empty] | DUE TO INCORRECT TITLE MENTIONED ON ACONEX AND INSIDE DRAWING |  | 2026-04-16 | KPTG-TRANSMIT-015989 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-16 | ECBS-TRANSMIT-000031 | NA | Trade Partner | Shop Drawings For Approval (Batch 1: 10dwgs) | 10 | 0 | 0 | NA | APPROVED | 2026-04-16 | WF-005311 | NA | 2026-04-23 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-16 | ACG-TRANSMIT-000078 | NA | Trade Partner | M3 - Site Wide Drawings - IFC | 1 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 4128 | 2026-04-23 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-016285 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-16 | ACG-TRANSMIT-000079 | NA | Trade Partner | M3 - Stage 2 FOV | 0 | 1 | 0 | NA | APPROVED | 2026-04-16 | WF-005313 | NA | 2026-04-23 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-017700 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-16 | IVS-TRANSMIT-000360 | NA | Consultant | Stage 4 - HV Room and Level 1 Office Canopy Construction Issue | 3 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 2871 | 2026-04-20 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016150 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-16 | Nilsen3-TRANSMIT-000100 | NA | Trade Partner | Dome Nuts sample | 0 | 1 | 0 | NA | APPROVED | 2026-04-16 | WF-005315 | NA | 2026-05-07 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-016876 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-16 | D&E-TRANSMIT-000221 | SPARK-CRFI-KPG-000376 | Trade Partner | FIRE MATRIX | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-16 | D&E-TRANSMIT-000222 | SPARK-CRFI-KPG-000588 | Trade Partner | SEISMIC INSTALLATION GUIDE | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Terminated as per peter advise |  | 2026-08-11 | KPTG-SADV-006374 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-16 | PARR-TRANSMIT-000162 | NA | Trade Partner | Re: P2685 - NDC M3 - Stage 4 - Battery Rooms - Exhausted Fan - EXE Motor | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect document type |  | 2026-04-16 | KPTG-TRANSMIT-016009 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-12 | Altaire-TRANSMIT-000026 | NA | Trade Partner | Altaire- DH11 Handover Documentation | 9 | 0 | 0 | NA | REJECTED |  |  | NA |  |  | Altaire to update drawings and resubmit as per Aurecon comments (KPTG-IntCorr-000333) |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-16 | SKS Tech-TRANSMIT-000099 | NA | Trade Partner | Re: M3-ELC-SKS-SA-C-0400-0016 lighting control IFC | 0 | 1 | 0 | NA | APPROVED | [5 empty] | ITS IFC DOCUMENT SHARED WITH MANAGERS AND SEEKED ADVISE |  | 2026-04-16 | KPTG-IntCorr-011950 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-08 | PenskePS-TRANSMIT-000007 | NA | Trade Partner | MEL11 COLO4 & 5 - FAT & SAT L3 Scripts | 0 | 2 | 0 | NA | APPROVED | 2026-04-08 | WF-000119 | NA | 2026-04-13 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-000390 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-16 | Nilsen3-TRANSMIT-000101 | NA | Trade Partner | Fwd: Dome Nuts sample | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | This document is already been received via Nilsen3-TRANSMIT-000100 and so we have proceeded with that transmittal |  | 2026-04-16 | KPTG-TRANSMIT-016011 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-16 | Civilex-TRANSMIT-000231 | NA | Trade Partner | Sample Submission - Stage 1 - Medium Duty Pavement (20Mpa Concrete) | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with the document number |  | 2026-04-16 | KPTG-SADV-004866 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-04-16 | Nilsen3-TRANSMIT-000102 | NA | Trade Partner | Re: M3 Sitewide SCADA ROPs | 16 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect reference number |  | 2026-04-16 | KPTG-RFI-007350 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-16 | D&E-TRANSMIT-000587 | NA | Trade Partner | NXM3S4 - Ground - Mechanical Duct Layout - Zone 2 - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 2876 | 2026-04-24 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-016470 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-16 | SMEPS-TRANSMIT-000240 | NA | Trade Partner | Re: SME - IFC drawings | 2 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED DUE TO DIFFERENT REVISION NUMBER |  | 2026-04-16 | KPTG-DA-006016 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-16 | Civilex-TRANSMIT-000230 | NA | Trade Partner | Sample Submission - Stage 1 - ASPHALT MIX DESIGN (Boral) | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with the document number |  | 2026-04-16 | KPTG-DA-006015 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-16 | D&E-TRANSMIT-000223 | SPARK-CRFI-KPG-000490, SPARK-CRFI-KPG-000475, SPARK-CRFI-KPG-000525 & SPARK-CRFI-KPG-000572 | Trade Partner | MWYCCB - ROOF & LEVEL 1 / DUCTWORK - PIPEWORK & RCP LAYOUT ZONES - Issued For Approval | 6 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 235 | 2026-04-16 |  |  |  | 2026-05-06 | KPTG-TRANSMIT-000834 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-12 | Nilsen3-TRANSMIT-000119 | NA | Trade Partner | L1 Office - FFE Procurement (alt. Microwave) | 0 | 1 | 0 | NA | APPROVED | 2025-12-12 | WF-000247 |  | 2025-12-15 |  |  |  | 2025-12-12 | KPTG-TRANSMIT-000747 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-16 | D&E-TRANSMIT-000586 | NA | Trade Partner | NXM3S4 - Upper Roof Level - CHW & CCW Pipe Layout Zones + Cooling Tower Sections Sheets - Issued For Approva | 4 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 2877 | 2026-04-24 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-017785 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-16 | SKS Tech-TRANSMIT-000042 | NA | Trade Partner | NDC M3 - Stage 4 - Battery Rooms - Exhausted Fan - EXE Motor | 0 | 1 | 0 | NA | APPROVED | 2026-04-16 | WF-005324 | NA | 2026-04-27 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016500 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-16 | D&E-TRANSMIT-000224 | SPARK-CRFI-KPG-000476 | Trade Partner | MWYCCB - AIR SCHEMATIC MECHANICAL SERVICES SHEET 1 OF 1 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 236 | 2026-04-23 |  |  | 2026-04-20 | 2026-05-04 | KPTG-TRANSMIT-000802 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-16 | D&E-TRANSMIT-000589 | NA | Trade Partner | Carbon Steel Pipework - Issued for Review | 0 | 1 | 0 | NA | APPROVED | 2026-04-16 | WF-005321 | NA | 2026-05-07 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016145 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-16 | D&E-TRANSMIT-000590 | NA | Trade Partner | Variable Speed Drives - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-16 | WF-005323 | 0 | 2026-05-07 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-16 | FNSTR8-TRANSMIT-000002 | NA | Trade Partner | Re: M3 S4 - Stage 2 Facade Samples | 0 | 15 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect reference number |  | 2026-04-16 | KPTG-RFI-007357 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-16 | D&E-TRANSMIT-000588 | NA | Trade Partner | NXM3S2 - Sidestream Filtration Schematic - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 4130 | 2026-04-23 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-016261 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-16 | VAE-Grp-TRANSMIT-000150 | NA | Trade Partner | IFC - MCCs - FAULT LEVEL ADJUSTMENTS | 0 | 7 | 0 | NA | APPROVED |  | NA | NA |  |  | FC DOCS - SENT TO ALL PARTIES |  | 2026-04-16 | KPTG-TRANSMIT-003417 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-16 | Jordan-TRANSMIT-000126 | NA | Trade Partner | Commissioning Manual and Scripts - For Approval | 0 | 7 | 0 | NA | REJECTED | [5 empty] | REJECTED : Document number and rev. errors |  | 2026-04-16 | KPTG-IntCorr-001180 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-16 | NXT-TRANSMIT-001497 | NA | Client | 100222-000588 Climat As Built drawings | 14 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with the revision number. |  | 2026-04-16 | KPTG-DA-006017 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-12 | PFP PL-TRANSMIT-000032 | NA | Trade Partner | Wet Fire As-builts | 12 | 0 | 0 | NA | REJECTED |  |  | NA |  |  | Rejected and returned to correct attachments (KPTG-SADV-001528) |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-16 | Mail from Lawden - ARC | NA | Consultant | Architectural drawings | 77 | 2 | 0 | NA | APPROVED | 2026-04-16 | NA | 234 | 2026-04-23 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-16 | ADP-TRANSMIT-000040 | NA | Consultant | ADP MEL4680 - IFC ISSUE | 89 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-04-16 | KPTG-SADV-000160 | Closed | 89 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-16 | ADP-TRANSMIT-000041 | NA | Consultant | ADP MEL4680 - IFC ISSUE (HYD) | 14 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 75 | 2026-04-21 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-000228 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-16 | SMEPS-TRANSMIT-00024 | NA | Trade Partner | Re: SME - IFA Drawings | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected- documents appear to be schedules within the document, and they have been shared as shop drawings in Aconex. |  |  | KPTG-TRANSMIT-016027 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-16 | Schindle-TRANSMIT-000016 | NA | Trade Partner | Schindler Lift - HPI Drawing IFC | 1 | 0 | 0 | NA | REJECTED | [5 empty] | revision error |  | 2026-04-16 | KPTG-TRANSMIT-000653 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-16 | INTRFRM-TRANSMIT-000016 | NA | Trade Partner | Geelong Edge - StructuralTech Data (Submission 1) | 0 | 6 | 0 | NA | REJECTED | [5 empty] | Issue with document number. |  | 2026-04-16 | KPTG-SADV-000159 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-01 | PSGANZ-TRANSMIT-000010 | NA | Trade Partner | Fire Curtain Tech Data For Review | 0 | 2 | 0 | NA | APPROVED | 2026-05-01 | WF-000734 | NA | 2026-05-05 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-002352 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-16 | Highbu-TRANSMIT-000046 | NA | Trade Partner | Level 2 Penetrations - FOR INFO (Temps Shed Penos Included) | 1 | 0 | 0 | NA | APPROVED | [5 empty] | KPTG-SADV-003783 - As per the instruction from Mark, we don't can action drawing we only update the register. |  | 2026-04-16 | KPTG-SADV-003783 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-16 | Auspan-TRANSMIT-000214 | NA | Trade Partner | Precast shop drawings for construction. Level 1, 2 | 56 | 0 | 0 | KPTG-IntCorr-000477 | APPROVED | [5 empty] | Waiting for Kapitol Advise KPTG-IntCorr-000477 IFC - Register and distribute. |  | 2026-04-17 | KPTG-TRANSMIT-001358 | Closed | 56 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-16 | Auspan-TRANSMIT-000215 | NA | Trade Partner | Precast shop drawings for approval. | 22 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 728 | 2026-04-23 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-001539 | Closed | 22 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-09 | WSP ANZ-TRANSMIT-000022 | NA | Consultant | WSP - PDF Drawings - Issued for Permit Interim-FIP | 121 | 0 | 0 | Wrong Attachment-KPTG-DA-000662 | APPROVED | 2025-12-13 |  | 141 | 2025-12-17 |  |  | 2025-12-19 | 2025-12-22 | KPTG-TRANSMIT-000407 | Closed | 116 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-16 | POTTSENG-TRANSMIT-000021 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - PENETRATION - GROUND - ZONE 2 LAYOUT | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Kapitol PC returned to the TP - KPTG-SADV-001944 |  | 2026-04-16 | KPTG-SADV-001944 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-16 | Auspan-TRANSMIT-000217: | NA | Trade Partner | Re: URGENT - Reo clash | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing revision is not updated in the revision history - |  | 2026-04-16 | DRAFT-005903 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-16 | LVPG-TRANSMIT-000030 | NA | Trade Partner | LVPG - Tech Data Submittals 150mm Basket trap & Aggi Drainage | 0 | 2 | 0 | NA | APPROVED | 2026-04-16 | WF-000393 | NA | 2026-04-21 |  | KPTG-TRANSMIT-001427 | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-001420 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-16 | Auspan-TRANSMIT-000216 | NA | Trade Partner | : Re: RFI 0G5021 Duplicate | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC- No review required; update register.- |  | 2026-04-16 | KPTG-TRANSMIT-001343 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-04-16 | NXT-TRANSMIT-000393 | NA | Client | Patching Schedule for External and Roof | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Kapitol Information only |  | 2026-04-16 | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-16 | PCForm-TRANSMIT-000220 | NA | Trade Partner | Stage 9 Stair Shop Drawings For Review | 4 | 0 | 0 | NA | APPROVED | 2026-04-16 | WF-000500 | NA | 2026-04-20 |  |  | 2026-04-16 | 2026-04-16 | KPTG-TRANSMIT-002191 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-23 | SMEPS-TRANSMIT-000183 | NA | Trade Partner | SME ROIP Drawings IFA 2 | 12 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Update Aconex register only, no need for WF. |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-16 | KPTG-TRANSMIT-000037-ARC | NA | Consultant | Architectural package | 222 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 3 | 2026-04-24 |  |  | 2026-05-08 | 2026-05-08 | NA | Closed | 222 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-16 | KPTG-TRANSMIT-000037-CIV | NA | Consultant | Civil drawings | 54 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 5 | 2026-04-24 |  |  | 2026-05-12 | 2026-05-12 | NA | Closed | 54 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-11 | RDSBIM-TRANSMIT-000037 | NA | Trade Partner | GROUND FLOOR RCP PLAN AND LAYOUT | 5 | 0 | 0 | 0 | APPROVED | 2025-12-11 | WF-000631 | 735 | 2025-12-15 |  |  | 2026-01-15 | 2026-01-15 | KPTG-TRANSMIT-002434 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-16 | KPTG-TRANSMIT-000037-STR | NA | Consultant | STR Drawings | 103 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 7 | 2026-04-24 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000058 | Closed | 103 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-16 | KPTG-TRANSMIT-000037-TEL | NA | Consultant | TEL-Drawings | 33 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 14 | 2026-04-24 |  |  | 2026-05-13 | 2026-05-13 | NA | Closed | 33 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-11 | RDSBIM-TRANSMIT-000038 | NA | Trade Partner | GROUND FLOOR PARTITION WALL PLAN AND ELEVATION | 7 | 0 | 0 | NA | APPROVED | 2025-12-11 | WF-000632 | 737 | 2025-12-15 |  |  | 2026-01-16 | 2026-01-16 | KPTG-TRANSMIT-002438 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-16 | KPTG-TRANSMIT-000037-TP | NA | Consultant | TP-Drawings | 38 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 15 | 2026-04-24 |  |  | 2026-05-12 | 2026-05-12 | NA | Closed | 38 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-16 | KPTG-TRANSMIT-000037-CSMS | NA | Consultant | CSMS-Drawings | 11 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 16 | 2026-04-24 |  |  | 2026-05-12 | 2026-05-12 | NA | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-16 | KPTG-TRANSMIT-000037-COM | NA | Consultant | Com -Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 18 | 2026-04-24 |  |  | 2026-05-12 | 2026-05-12 | NA | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-16 | KPTG-TRANSMIT-000037-ACO | NA | Consultant | Aco-Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 20 | 2026-04-24 |  |  | 2026-05-12 | 2026-05-12 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-16 | KPTG-TRANSMIT-000037-ELC | NA | Consultant | ELC-Drawings | 76 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 22 | 2026-04-24 |  |  | 2026-05-12 | 2026-05-12 | NA | Closed | 76 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-16 | KPTG-TRANSMIT-000037-FIP | NA | Consultant | FIP-Drawings | 30 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 24 | 2026-04-24 |  |  | 2026-05-13 | 2026-05-13 | NA | Closed | 30 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-16 | KPTG-TRANSMIT-000037-MEC | NA | Consultant | MEC-Drawings | 40 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 33 | 2026-04-24 |  |  | 2026-05-13 | 2026-05-13 | NA | Closed | 40 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-16 | KPTG-TRANSMIT-000037-FUL | NA | Consultant | FUL-Drawings | 17 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 27 | 2026-04-24 |  |  | 2026-05-13 | 2026-05-13 | NA | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-02 | Auspan-TRANSMIT-000019 | NA | Trade Partner | Re Preliminary marking plans and elevations for zone 4, 5 for review of panel breakup | 7 | 0 | 0 | NA | APPROVED | 2025-12-02 | WF-000075 | 146 | 2025-12-08 |  | Review Void |  |  | NA | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-11 | VAE-Grp-TRANSMIT-000087 | NA | Trade Partner | MECHANICAL - MCC - MCC-B-LF-05, 06, 07 (CT BOARDS) | 0 | 3 | 0 | NA | APPROVED | 2025-12-11 | WF-000630 | NA | 2025-12-19 |  |  | 2026-01-13 | 2026-01-13 | KPTG-WTRAN-001315 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-16 | KPTG-TRANSMIT-000037-HYD | NA | Consultant | HYD-Drawings | 47 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 29 | 2026-04-24 |  |  | 2026-05-13 | 2026-05-13 | NA | Closed | 47 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-16 | KPTG-TRANSMIT-000037-CIV | NA | Consultant | CIV-Drawings | 0 | 2 | 0 | NA | APPROVED | 2026-04-16 | NA | 30 | 2026-04-24 |  |  | 2026-05-13 | 2026-05-13 | NA | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-16 | Highbu-TRANSMIT-000142 | NA | Trade Partner | Updated drawing per KPTG-SADV-004062 | 1 | 0 | 0 | KPTG-IntCorr-006994 | REJECTED | [7 empty] | 2026-04-17 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-16 | SC-TRANSMIT-000046 | NA | Trade Partner | Operable Wall | 6 | 0 | 0 | KPTG-SADV-004105 | APPROVED | 2026-04-20 | WF-000935 | NA | 2026-04-24 |  | kAPITOL ADVICE AWAITS:KPTG-SADV-004105 | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-002760 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-16 | 4DW-TRANSMIT-000169 | NA | Consultant | Structural Documentation - Retention updates | 17 | 0 | 0 | NA | REJECTED | [5 empty] | selected Mail attribute was wrong, requested them to use Stage- 2 |  | 2026-04-16 | KPTG-SADV-004094 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-16 | 4DW-TRANSMIT-000171 | na | Consultant | Structural Documentation - Retention updates Stage 2 | 16 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 189 | 2026-04-21 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-002778 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-16 | 4DW-TRANSMIT-000170 | NA | Consultant | Updated Stage 2 Retention drawings - western elevation change from PC to Soldiers | 12 | 0 | 0 | NA | REJECTED | [5 empty] | Few Drawings are missed in this Transmit, requested them to retransmit: KPTG-SADV-004104 |  | 2026-04-16 | KPTG-SADV-004104 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol