MLCSPR | 2026-04-16 | CTAGroup-TRANSMIT-000001 | NA | Trade Partner | Re: Fencing dimensioning for Sout East Footings | 4 | 0 | 0 | NA | REJECTED | [5 empty] | SUBMITTED DRAWINGS ARE A ZIP FILE, REQUESTED THEM TO RESUBMIT:KPTG-SADV-004106 |  | 2026-04-16 | KPTG-SADV-004106 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-16 | KPTG-DA-002108 | NA | Trade Partner | Tech Data Alternative - Crommelin Enhance WB Concrete Sealer | 0 | 1 | 0 | NA | APPROVED | 2026-04-16 | WF-000503 | NA | 2026-04-27 |  | Workflow terminated as requested by the Design Manager |  | 2026-04-17 | KPTG-IntCorr-000704 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-11 | Endfire-TRANSMIT-000049 | NA | Trade Partner | EndFire IFC Drawings | 10 | 0 | 0 | KPTG-SADV-001890 -REJECTED | REJECTED |  | NA | NA |  |  | KPTG-SADV-001890 -REJECTED |  |  |  | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-16 | GPSElec-TRANSMIT-000016 | NA | Trade Partner | NextDC Stage 9-12 switchboard - Quality Plan for MSB-JA-01 | 0 | 1 | 0 | NA | APPROVED | 2026-04-16 | WF-000508 | NA | 2026-04-27 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-002712 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-16 | Entire M-TRANSMIT-000032 | NA | Trade Partner | Re: VCDs Technical Data Issued for Approval Rev D | 0 | 1 | 0 | NA | APPROVED | 2026-04-16 | WF-000215 |  | 2026-04-23 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-000616 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-16 | Appselec-TRANSMIT-000054 | NA | Trade Partner | Legrand Communications Tech Data IFA | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document number of document is incorrect. |  | 2026-04-16 | KPTG-TRANSMIT-000389 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | Nilsen3-TRANSMIT-000104 | NA | Trade Partner | Cable Basket Tee Cross Brackets Sample | 0 | 1 | 0 | NA | APPROVED | 2026-04-17 | WF-005329 | NA | 2026-04-08 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-016703 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | HDRAus-TRANSMIT-000459 | NA | Consultant | M3 Stage 4 - Document upload Lift C04 - PDF and CAD | 1 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 2881 | 2026-04-21 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-016333 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-17 | SMEPS-IntCorr-000111 | NA | Trade Partner | - Copper ITP sheets MEL05 | 0 | 1 | 0 | NA | APPROVED | 2026-04-17 | WF - 000352 | NA | 2026-04-23 |  | NA | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-000768 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | SKS Tech-TRANSMIT-000101 | NA | Trade Partner | Re: Lighting Control for Approval | 7 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect revision No. |  | 2026-04-17 | KPTG-RFI-007374 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-17 | D&E-TRANSMIT-000591 | NA | Trade Partner | NXM3S2 - Lower Ground - High Level Mechanical Pipe Layout - Zone 4 - Issued AS BUILT | 1 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 4132 | 2026-04-22 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016218 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-17 | PFP PL-TRANSMIT-000003 | NA | Trade Partner | Level 2 Colo4 Low Level IFC | 1 | 0 | 0 | NA | APPROVED | 2026-04-17 | WF - 000353 | NA | 2026-04-23 |  | NA | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-000737 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-17 | Civilex-TRANSMIT-000232 | NA | Trade Partner | Sample Submission - Stage 1 - Medium Duty Pavement (20Mpa Concrete)- updated naming | 0 | 1 | 0 | NA | APPROVED | 2026-04-17 | WF-005332 | NA | 2026-05-05 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-11 | Hames-TRANSMIT-000087 | NA | Consultant | Latest FC Revisions | 13 | 0 | 0 | NA | APPROVED | 2025-12-12 | WF-000637 | 739 | 2025-12-16 |  |  | 2025-12-18 | 2025-12-18 | KPTG-TRANSMIT-002326 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-17 | Civilex-TRANSMIT-000233 | NA | Trade Partner | Sample Submission - Stage 1 - Asphalt Mix Design - updated naming | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Difference in title in Aconex submission and inside the document. |  | 2026-04-17 | KPTG-SADV-004877 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-17 | ACG-TRANSMIT-000080 | NA | Trade Partner | M3 - Site Wide - Intercom Mounting Details | 1 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 4134 | 2026-04-28 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-019460 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | Nilsen3-TRANSMIT-000076 | NA | Trade Partner | Re: Nilsen IFC Sample Submission | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | SAMPLE FOR IFC HAS SUBMITTED ADVISE SEEKED TO CHARLIE |  | 2026-04-17 | KPTG-IntCorr-012000 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-17 | D&E-TRANSMIT-000225 | SPARK-CRFI-KPG-000313 & SPARK-CRFI-KPG-000474 | Trade Partner | MWYCCB - ROOF LEVEL - PENETRATION LAYOUT ZONES + CHILLED + HEATING HOT WATER SCHEMATICS SHEETS - Issued For Construction | 3 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 237 | 2026-04-24 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-000755 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | SKS Tech-TRANSMIT-000100 | NA | Trade Partner | Re: M3-ELC-SKS-SA-C-0400-0026 IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | “Sample/IFC has been submitted.ADVISE SEEKED TO COORDINATOR |  | 2026-04-17 | KPTG-IntCorr-012004 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | Altaire-TRANSMIT-000103 | NA | Trade Partner | NEXTDC M3S4 - Dry Fire Schematics (For Approval) (1)- | 2 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 2883 | 2026-04-24 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-017176 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | FNSTR8-TRANSMIT-000003 | NA | Trade Partner | Re: Shop Drawings Revision A1 | 7 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect Ref No. |  | 2026-04-17 | KPTG-RFI-007380 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-16 | PCForm-TRANSMIT-000150 | NA | Trade Partner | Placing boom 2 footing design transmittal | 1 | 0 | 0 | KPTG-IntCorr-000587 | APPROVED | [5 empty] | victoria to clarify |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-16 | PCForm-TRANSMIT-000151 | NA | Trade Partner | Jumpform Raft 3 - Pour Sequence Issued for Approval | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-16 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-16 | PCForm-TRANSMIT-000153 | NA | Trade Partner | Jumpform Raft 3 - Pour Sequence Issued for Approval | 3 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 422 | 2026-04-22 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-001550 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-11 | PARR-TRANSMIT-000023 | NA | Trade Partner | P2666 - KPG NDC D1 Stage 2 - Fuel Services - BF SCHEMATIC AND CONTROL SYSTEM - IFC | 10 | 0 | 0 | NA | APPROVED | 2025-12-12 | WF-000638 | 745 | 2025-12-16 |  |  | 2025-12-15 | 2025-12-15 | KPTG-TRANSMIT-002288 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-16 | INGEN3D-TRANSMIT-000025 | NA | Trade Partner | STRUCTURAL DATA | 2 | 0 | 0 | NA | APPROVED | 2026-04-16 | WF-000329 | NA | 2026-04-20 |  | Teams message Nicholas) Re-issue of 2 pcf drawings to TTW for comments update |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-16 | KPTG-IntCorr-000584 | NA | Client | Updated Authority sewer plans | 5 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 419 | 2026-04-22 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-001531 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-16 | WAM-TRANSMIT-000750 | NA | Consultant | Level 11 update | 2 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 418 | 2026-04-22 |  |  | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-001219 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-16 | PCForm-TRANSMIT-000154 | NA | Trade Partner | Jumpform Raft 3 - Pour Sequence Issued for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 425 | 2026-04-22 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-001545 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-16 | PCForm-TRANSMIT-000154 | NA | Trade Partner | Jumpform Raft 3 - Pour Sequence Issued for Construction | 2 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 424 | 2026-04-22 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-001669 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-16 | OveArup-TRANSMIT-000035 | NA | Consultant | Electrical-Arup Early Works Document Transmittal | 8 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 427 | 2026-04-23 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-001615 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-16 | OveArup-TRANSMIT-000035 | NA | Consultant | FIRE-Arup Early Works Document Transmittal | 8 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 429 | 2026-04-23 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-001611 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-16 | OveArup-TRANSMIT-000035 | NA | Consultant | Hydraulic- Arup Early Works Document Transmittal | 2 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 431 | 2026-04-23 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-001582 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-16 | OveArup-TRANSMIT-000035 | NA | Consultant | Mechanical-Arup Early Works Document Transmittal | 7 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 433 | 2026-04-23 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-001586 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | SKS Tech-TRANSMIT-000103 | NA | Trade Partner | Fwd: M3-ELC-SKS-SA-C-0400-0026 IFC | 0 | 1 | 0 | NA | APPROVED | [5 empty] | IFC tech data |  | 2026-04-17 | KPTG-TRANSMIT-016055 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-12 | PARR-TRANSMIT-000024 | NA | Trade Partner | P2666 - KPG NDC D1 Stage 2 - Fuel Services - BF SCHEMATIC AND CONTROL SYSTEM - IFC | 1 | 0 | 0 | NA | APPROVED | 2025-12-12 | NA | 745 | 2025-12-16 |  |  | 2025-12-15 | 2025-12-15 | KPTG-TRANSMIT-002288 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-04-16 | Carr-TRANSMIT-000038 | NA | Consultant | Updated Demolition Drawings for Town Planning Secondary Consent | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Issued for Consent for third party town planning consent, Updated ACC & Aconex as advised |  | 2026-04-17 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-16 | WAM-TRANSMIT-000747 | NA | Consultant | WAM ARCH - Detailed Design - A50 Core Plans sections and details. | 15 | 0 | 0 | NA | APPROVED | 2026-04-16 | NA | 420 | 2026-04-24 |  | Internal SME Review |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-04-16 | ENF-TRANSMIT-000009 | NA | Consultant | Structural drawings | 2 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 46 | 2026-04-28 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-000039 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-17 | LNCPPL-TRANSMIT-000003 | NA | Trade Partner | BP1 - Hydraulic Drainage In-Ground Services - For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 77 | 2026-04-23 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-000181 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | SKS Tech-TRANSMIT-000102 | NA | Trade Partner | Updated lighting layout roof | 3 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 2885 | 2026-04-24 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-017140 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-04 | ENF-CADV-000008 | NA | Consultant | Dynamic Cone Penetrometer (DCP) Testing (Geotech) | 0 | 1 | 0 | NA | APPROVED | 2026-04-16 | WF-000024 | NA | 2026-04-27 |  | Aconex WF - Terminated, the review not required as advised by Renee |  | 2026-08-24 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-17 | SMEPS-TRANSMIT-000187 | SPARK-CRFI-KPG-000168 | Trade Partner | Ground Floor Containment - REV 0 | 5 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 238 | 2026-04-24 |  |  | 2026-04-20 | 2026-05-05 | KPTG-TRANSMIT-000818 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | SMEPS-TRANSMIT-000241 | NA | Trade Partner | Re: SME - IFA Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 2887 | 2026-04-27 |  | As instructed in KPTG-IntCorr-012011, we are processing it accordingly | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-017133 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-17 | INTRFRM-TRANSMIT-000018 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 2) | 0 | 6 | 0 | NA | APPROVED | 2026-04-17 | WF-000040 | NA | 2026-04-27 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000299 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | INGEN3D-TRANSMIT-000691 | NA | Trade Partner | Fwd: M3-ELC-SKS-SA-C-0400-0016 IFC | 0 | 1 | 0 | NA | APPROVED | 2026-04-17 | WF-005339 | NA | 2026-04-24 |  |  | 2026-04-20 | 2026-04-27 | KPTG-TRANSMIT-016489 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-12 | VAE-Grp-TRANSMIT-000091 | NA | Trade Partner | MECHANICAL - SCHED & TECH DATA - FANS L4 & L5 | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | FC - Register updation only |  | 2025-12-12 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-17 | SMEPS-TRANSMIT-000185 | NA | Trade Partner | MEL05 TeleCommunications IFC DWGs | 4 | 0 | 0 | NA | APPROVED | 2026-04-17 | WF - 00354 | NA | 2026-04-21 |  | NA | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-000741 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | NXT-TRANSMIT-001499 | NA | Trade Partner | MSB-FI schematic submission- as per RFI for ATS protocol, SOO & Setting | 1 | 0 | 0 | NA | APPROVED | 2026-04-17 | WF-005337 | NA | 2026-04-05 |  |  | 2026-05-04 | 2026-04-27 | KPTG-TRANSMIT-016786 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | Ardon-TRANSMIT-000029 | NA | Trade Partner | Re: Switchroom Doors - Sho Drawings | 3 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-04-17 | KPTG-TRANSMIT-016067 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-17 | Appselec-TRANSMIT-000056 | NA | Trade Partner | Electrical Services - Shop drawings Issued For Construction | 30 | 0 | 0 | NA | APPROVED | 2026-04-17 | WF-000148 | NA | 2026-04-22 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-000408 | Closed | 30 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | NXT-TRANSMIT-001498 | NA | Client | Fwd: Electrical Services - Load Bank Panel MSB-LB shop drawings - IFA | 2 | 0 | 0 | NA | APPROVED | 2026-04-17 | WF-005338 | NA | 2026-05-05 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-017087 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-17 | Omnii-TRANSMIT-000006 | NA | Trade Partner | Fire Engineering Report | 0 | 1 | 0 | NA | APPROVED | 2026-04-17 | NA | 1207 | 2026-04-24 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-003526 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-17 | SMEPS-TRANSMIT-000188 | NA | Trade Partner | Ground Floor IFA - REV E | 1 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 239 | 2026-04-24 |  | Terminated as per peter advice |  | 2026-04-20 | KPTG-IntCorr-002718 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-17 | Entire M-TRANSMIT-000033 | NA | Trade Partner | Mechanical pipework shop drawings IFC | 3 | 0 | 0 | NA | APPROVED | 2026-04-17 | WF-000149 | NA | 2026-04-22 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-000418 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-17 | PARR-TRANSMIT-000053 | NA | Trade Partner | Fuel Services - FUEL RETICULATION RISER SECTIONS -IFC | 1 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 1209 | 2026-04-21 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-003587 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-17 | Civilex-TRANSMIT-000235 | NA | Trade Partner | Sample Submission - Stage 1 - Asphalt Mix design - updated naming | 0 | 1 | 0 | NA | APPROVED | 2026-04-17 | WF-005340 | NA | 2026-04-23 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-016916 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-12 | VAE-Grp-TRANSMIT-000092 | NA | Trade Partner | MECHANICAL - SCHED & TECH DATA - FANS LG TO L3 - SPRING CORRECTION | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | FC - Register updation only | 2025-12-12 | 2025-12-12 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-17 | D&E-TRANSMIT-000226 | NA | Trade Partner | MWYCCB - GROUND LEVEL / LEVEL 1 & ROOF - OVERALL LAYOUT PDFS - Issued For INFORMATION | 9 | 0 | 0 | KPTG-IntCorr-002711 | APPROVED | [5 empty] | For Information drawings register updated. |  | 2026-04-20 | KPTG-IntCorr-002714 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-17 | SMEPS-TRANSMIT-000189 | NA | Trade Partner | Ground Floor - Containment Zone 7 - Rev E | 1 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 240 | 2026-04-24 |  | Terminated as per Peter advise |  | 2026-05-01 | KPTG-IntCorr-002873 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-17 | PARR-TRANSMIT-000054 | NA | Trade Partner | Fuel Services - FUEL RETICULATION PUMP ROOM A&B | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected QA error - Drawing Status Wrong |  | 2026-04-17 | KPTG-IntCorr-001184 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | D&E-TRANSMIT-000593 | NA | Trade Partner | Fwd: Switchroom Fire Dampers - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Sample IFC for distribution |  | 2026-04-17 | KPTG-TRANSMIT-016078 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-04 | HDRAus-TRANSMIT-000456 | na | Consultant | M3 Stage 4 - Oversized Penetration Infill Details/Security Corridor Walls - PDF and CAD | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | THE DOCUMENTS ARE PROCEEDED FROM HDRAus-TRANSMIT-000455 |  | 2026-04-04 | HDRAus-TRANSMIT-000455 | Closed | 10 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-17 | Coen-TRANSMIT-000007 | NA | Trade Partner | PVC reglet dimensions | 0 | 1 | 0 | NA | APPROVED | 2026-04-17 | WF-000042 | NA | 2026-04-27 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-000599 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-17 | SMEPS-TRANSMIT-000186 | NA | Trade Partner | Mel05 Communication Details DWGs For IFC | 7 | 0 | 0 | NA | APPROVED | 2026-04-17 | WF - 000355 | NA | 2026-04-21 |  | WF Terminated | 2026-04-20 | 2026-04-20 | NA | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-04 | ARCST-TRANSMIT-000200 | NA | Trade Partner | C3 Cooling Tower Base Framing - Issued for Review | 0 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-004106 | NA | 2026-02-25 |  | remaining 17 documents in ARCST-TRANSMIT-000200 | 2026-04-17 | 2026-04-17 | KPTG-TRANSMIT-016083 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | D&E-TRANSMIT-000595 | NA | Trade Partner | Fwd: Bermad Valves & Water Meters - Issued for construction | 0 | 2 | 0 | NA | APPROVED | [5 empty] | IFC TD FOR SUBMISSION ADVISE SEEKED FOR FURTHER ACTION |  | 2026-04-17 | KPTG-TRANSMIT-016090 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | D&E-TRANSMIT-000594 | NA | Trade Partner | Gas Sensors - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-17 | WF-005341 | NA | 2026-05-07 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-016466 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2025-12-12 | Nilsen3-TRANSMIT-000095 | NA | Trade Partner | Nilsen Telecommunications As-Builts | 12 | 0 | 0 | NA | APPROVED | [5 empty] | No review required. Updated register and distributed to the Project Team. |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | Bee Eng-TRANSMIT-000014 | NA | Trade Partner | Re: Stair C05 shop drawings | 3 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-04-17 | KPTG-DA-006038 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-17 | SMEPS-TRANSMIT-000187 | NA | Trade Partner | Phone Layout Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-04-17 | WF - 000356 | NA | 2026-04-21 |  | NA | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-000742, KPTG-TRANSMIT-000743, KPTG-TRANSMIT-000744 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-17 | Nilsen3-TRANSMIT-000106 | NA | Trade Partner | Stage 2 ROPS 2C & 2D | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with the document number |  | 2026-04-17 | KPTG-SADV-004893 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-17 | D&E-TRANSMIT-000227 | SPARK-CRFI-KPG-000466 | Trade Partner | MWYCCB - LEVEL DUCTWORK / PIPEWORK ZONE 8 & ZONE 9 MECHANICAL SERVICES - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 241 | 2026-04-24 |  |  | 2026-04-20 | 2026-04-24 | KPTG-TRANSMIT-000724 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-17 | Ardon-TRANSMIT-000039 | NA | Trade Partner | Level 11 to 15 - Service Risers - Shop Drawings | 6 | 0 | 0 | NA | APPROVED | 2026-04-20 | WF - 000997 | NA | 2026-04-24 |  | File supersede and WF terminated. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-17 | JCBa-TRANSMIT-000244 | NA | Consultant | L3 BTR Floor Plans - ISSUE FOR INFORMATION | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Drawings revised and submitted in another transmittal. |  |  |  | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | D&E-TRANSMIT-000596 | NA | Trade Partner | ISSUED FOR APPROVAL - GROUND MECHANICAL DUCT LAYOUT -ZONE 3 | 1 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 2890 | 2026-04-27 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-017779 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | Bianco-TRANSMIT-000061 | NA | Trade Partner | Re: Precast IFC | 70 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED DUE TO THE IFA AND IFC DOCUMENTS CAME IN SINGLE TRANSMIT |  | 2026-04-17 | KPTG-DA-006039 | Closed | 70 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | KPTG-WTRAN-009912 | NA | Trade Partner | AS PER REQUESTED BY NED CRUMMY | 0 | 1 | 0 | NA | APPROVED | 2026-04-17 | WF-005342 | NA | 2026-04-29 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-017083 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | KPTG-WTRAN-009913 | NA | Trade Partner | AS PER REQUESTED BY NED CRUMMY (17-4-2026) | 0 | 1 | 0 | NA | APPROVED | 2026-04-17 | WF-005343 | NA | 2026-04-29 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-017081 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-12 | D&E-TRANSMIT-000048 | NA | Trade Partner | NextDC M2 DH11 As-Builts | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Returned to D&E to correct the drawings and resubmit. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-17 | SMEPS-TRANSMIT-000242 | NA | Trade Partner | Revised Jemena Easement Shopdrawing - 17.04.2026 | 2 | 0 | 0 | NA | APPROVED | 2026-04-17 | WF-005345 | NA | 2026-04-24 |  | Workflow terminated by Max Hendrikse for submitting the updated drawings. |  | 2026-04-20 | KPTG-IntCorr-012087 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-17 | ACG-TRANSMIT-000081 | NA | Trade Partner | M3 - Camera Pole Sample | 0 | 1 | 0 | NA | APPROVED | 2026-04-17 | WF-005347 | NA | 2026-04-24 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-018564 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-17 | ADP-TRANSMIT-000043 | NA | Consultant | ADP MEL4680 - CSMS Spec and Appendix | 0 | 5 | 0 | NA | REJECTED | [5 empty] | Issue with document number and missing document number inside specification. |  | 2026-04-17 | KPTG-SADV-000165 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-17 | TTW-TRANSMIT-000172 | NA | Consultant | M3 Stage 1 Civil Drawings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document number and revision |  | 2026-04-17 | KPTG-DA-006040 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-17 | ADP-TRANSMIT-000044 | NA | Consultant | ADP MEL4680 - Fire Protection Specification | 0 | 1 | 0 | NA | APPROVED | 2026-04-17 | NA | 79 | 2026-04-22 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-000662 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-17 | ECBS-TRANSMIT-000032 | NA | Trade Partner | Shop Drawings For Approval (Batch 2: 15dwgs) | 15 | 0 | 0 | NA | APPROVED | 2026-04-17 | WF-005348 | NA | 2026-05-13 |  | TERMINATED AS PER REQUESTED BY ISABELA NEED GO ALL DOCUMENTS IN SAME WORKFLOW |  | 2026-04-23 | NA | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-17 | ADP-TRANSMIT-000042 | NA | Consultant | ADP MEL4680 - IFC ISSUE - Retransmittal | 89 | 0 | 0 | NA | REJECTED | [5 empty] | Difference in the title, inside the drawing and Aconex submission. |  | 2026-04-17 | KPTG-SADV-000164 | Closed | 89 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-17 | Jordan-TRANSMIT-000127 | NA | Trade Partner | Commissioning Manual and Scripts - For Approval | 0 | 7 | 0 | KPTG-IntCorr-001185 | APPROVED |  | NA | NA |  |  | Harry to confirm | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-003731 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-17 | JCBa-TRANSMIT-000092 | NA | Consultant | Re GROUND FLOOR SSP'S FOR IFC | 4 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 731 | 2026-04-24 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-001410 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-12 | Normark-TRANSMIT-000008 | 0 | Trade Partner | Amphitheatre Shop drawing for review | 2 | 0 | 0 | NA | APPROVED | 2025-12-12 |  | 381 | 2025-12-19 |  |  |  | 2026-01-29 | KPTG-SADV-003562 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-17 | Auspan-TRANSMIT-000220 | NA | Trade Partner | : Precast shop drawings for approval. Levels 1, 2. | 17 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 738 | 2026-04-24 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-001542 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-17 | Auspan-TRANSMIT-000218: | NA | Trade Partner | Update already IFCed precast shop drawings. Level 1 | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Register and distribute. |  | 2026-04-17 | KPTG-TRANSMIT-001379 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-17 | Auspan-TRANSMIT-000219 | NA | Trade Partner | Re: URGENT - Reo clash | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Regiser and distribute. |  | 2026-04-17 | KPTG-TRANSMIT-001365 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-17 | JCBa-TRANSMIT-000093 | NA | Trade Partner | FIRST FLOOR SSP'S FOR IFC | 5 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 736 | 2026-04-24 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-001512 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-17 | POTTSENG-TRANSMIT-000022 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - PENETRATION - GROUND - ZONE 2 LAYOUT | 1 | 0 | 0 | PTG-IntCorr-000483 | APPROVED | 2026-04-22 | NA | 770 | 2026-04-29 |  | IFC - Waiting for advise - KPTG-IntCorr-000483 | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-001491 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-17 | crossfir-TRANSMIT-000007 | NA | Trade Partner | Wet Fire - Penetrations Basement 04 to 01, IFC | 4 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 414 | 2026-04-24 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-000990 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-17 | KPTG-TRANSMIT-000797 | NA | Trade Partner | IFC Penetration Layout Electrical | 4 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 416 | 2026-04-24 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-000992 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-17 | POTTSENG-TRANSMIT-000009: | NA | Trade Partner | 671C: HYDRAULIC SERVICES - BASEMENT 2-4 - WATER & BASEMENT 3-4 - PENETRATION LAYOUTS | 5 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 418 | 2026-04-23 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000901 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-17 | RDSBIM-TRANSMIT-000001 | NA | Trade Partner | GROUND FLOOR CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 35 | 2026-04-27 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-000078 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-22 | NXT-TRANSMIT-000341 | NA | Client | Document Register Tidy For Tender | 1 | 6 | 0 | KPTG-IntCorr-000054 | APPROVED |  | NA | NA |  |  | For information |  | 2026-05-22 | NA | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2025-12-02 | KPTG-SADV-000789 | NA | Trade Partner | Signage Package | 1 | 0 | 0 | NA | APPROVED | 2025-12-02 | WF-000166 |  | 2025-12-05 |  |  | 2025-12-03 | 2025-12-03 | KPTG-TRANSMIT-000608 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-12 | Syfon1-TRANSMIT-000019 | 0 | Trade Partner | Updated Syfon Drawings | 2 | 0 | 0 | NA | APPROVED | [5 empty] | IFC Drawing are transmitted to Consultants and Trade Partners |  | 2025-12-12 |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-17 | KPTG-TRANSMIT-000037-Fip | NA | Consultant | FIP drawings | 12 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 37 | 2026-04-27 |  |  | 2026-05-13 | 2026-05-13 | NA | Closed | 12 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-17 | KPTG-TRANSMIT-000037-Com | NA | Consultant | COM drawings | 18 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 39 | 2026-04-27 |  |  | 2026-05-12 | 2026-05-12 | NA | Closed | 18 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-17 | KPTG-TRANSMIT-000040 | NA | Consultant | Steel Drawings B1 Block | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Already submitted |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-17 | WilsonPD-TRANSMIT-000014 | NA | Trade Partner | Chlorine Dosing Pump Set Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-04-17 | WF-000515 | NA | 2026-04-28 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-002524 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-17 | WilsonPD-TRANSMIT-000015 | NA | Trade Partner | Pressure Booster Pump Set Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-04-17 | WF-000516 | NA | 2026-04-28 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-002520 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-17 | WilsonPD-TRANSMIT-000016 | NA | Trade Partner | Rainwater Filtration Pump Set Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-04-17 | WF-000517 | NA | 2026-04-28 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-002544 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-17 | Nilsen3-TRANSMIT-000002 | NA | Trade Partner | Nilsen Sample submissions #1 | 0 | 42 | 0 | NA | APPROVED | 2026-04-17 | WF-000514 | NA | 2026-04-30 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-003347 | Closed | 42 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-17 | Nilsen3-TRANSMIT-000003 | NA | Trade Partner | Sample submission | 0 | 1 | 0 | NA | APPROVED | 2026-04-17 | WF-000514 | NA | 2026-04-30 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-003347 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-17 | Nilsen3-TRANSMIT-000004 | NA | Trade Partner | Nilsen Sample submissions #1 | 0 | 1 | 0 | NA | APPROVED | 2026-04-17 | WF-000514 | NA | 2026-04-30 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-003347 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-17 | Tradetec-TRANSMIT-000113 | NA | Trade Partner | Technical Data Submission for Type A Fill | 0 | 1 | 0 | NA | APPROVED | 2026-04-17 | WF-000518 | NA | 2026-04-29 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-002539 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-12 | ECBS-TRANSMIT-000048 | 0 | Trade Partner | Revised Tech data - IN81 (ProctorWrap™ HTR) for review | 0 | 1 | 0 | NA | APPROVED | 2025-12-12 | WF-000675 |  | 2025-12-16 |  |  |  | 2026-01-15 | KPTG-TRANSMIT-002089 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-17 | TATE_-TRANSMIT-000022 | NA | Trade Partner | Tate - HAC Door Hardware Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-04-17 | WF-000146 | NA | 2026-04-22 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-000431 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-17 | Appselec-TRANSMIT-000057 | NA | Trade Partner | Electrical Services - Equipment Schedules & 22 kV SLDs - Issued For Approval | 4 | 0 | 0 | NA | APPROVED | 2026-04-17 | WF-000147 | NA | 2026-04-22 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-000579 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-17 | Appselec-TRANSMIT-000058 | NA | Trade Partner | Electrical Services - Updated Distribution Boards shop drawings - IFA | 3 | 0 | 0 | NA | APPROVED | 2026-04-30 | WF-000150 | NA | 2026-05-05 |  |  | 2026-04-30 | 2026-05-22 | KPTG-IntCorr-000449 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-17 | Appselec-TRANSMIT-000059 | NA | Trade Partner | MEL11C45 - COLO 4 Cell 2 - Electrical Drawings - IFC | 4 | 0 | 0 | NA | APPROVED | 2026-04-18 | WF-000151 | NA | 2026-04-22 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-000411 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-17 | Appselec-TRANSMIT-000055 | NA | Trade Partner | Communications Technical Data IFA | 0 | 1 | 0 | NA | APPROVED | 2026-04-17 | WF-000145 | NA | 2026-04-22 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-000428 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-17 | CTAGroup-TRANSMIT-000002 | NA | Trade Partner | FC02 Fencing Shop drawings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | SUBMITTED DOCUMENT IS A ZIP FILE, REQUESTED TO RESUBMIT:KPTG-SADV-004120 |  | 2026-04-17 | KPTG-SADV-004120 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-17 | CLADC-TRANSMIT-000021 | NA | Trade Partner | Fwd: Updated tech data and hardware list as requested | 0 | 6 | 0 | NA | APPROVED | 2026-04-17 | WF-000934 | NA | 2026-04-22 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-002802 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-17 | Highbu-TRANSMIT-000143 | NA | Trade Partner | Drawing re-upload | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC DRAWING IS UPDATED TO DOCUMENT REGISTER AND TRANSMITTED TO TRADE & CONSULTANTS |  | 2026-04-17 | KPTG-TRANSMIT-002757 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-17 | 4DW-TRANSMIT-000172 | NA | Consultant | Structural Documentation - Precast walls package | 3 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 193 | 2026-04-22 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-002781 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-17 | 4DW-TRANSMIT-000173 | NA | Consultant | Current Stage 2 precast drawings | 6 | 0 | 0 | NA | REJECTED | [5 empty] | these drawings have been received already. |  | 2026-04-17 | KPTG-SADV-004121 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-15 | Auspan-TRANSMIT-000033 | NA | Trade Partner | Precast shop drawings for approval. Basement 1 | 14 | 0 | 0 | NA | APPROVED | 2025-12-15 | WF-000099 | 197 | 2025-12-22 |  |  |  | 2026-01-12 | KPTG-TRANSMIT-000374 | Closed | 14 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-17 | KPTG-IntCorr-006998 | NA | Trade Partner | FC01 Fencing and Balustrading | 6 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 191 | 2026-04-22 |  |  | 2026-06-18 | 2026-06-18 | KPTG-SADV-004676 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-17 | RDSBIM-TRANSMIT-000181 | NA | Trade Partner | LINDRUM ¦ LEVEL 2 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As per the direction from the ashlin, just instructed to update document register:KPTG-TRANSMIT-002232 |  | 2026-04-17 | KPTG-TRANSMIT-002232 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-17 | RDSBIM-TRANSMIT-000182 | NA | Trade Partner | LINDRUM ¦ LEVEL 02 TO LEVEL 05 COREWALL CONCRETE PROFILE PLAN ELEVATIONS | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Same copy of drawings have been tramitted via RDSBIM-TRANSMIT-000183: KPTG-IntCorr-000885 |  | 2026-04-17 | KPTG-IntCorr-000885 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-17 | RDSBIM-TRANSMIT-000183 | NA | Trade Partner | LINDRUM ¦ LEVEL 02 TO LEVEL 05 COREWALL CONCRETE PROFILE PLAN ELEVATIONS | 2 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 628 | 2026-04-22 |  |  | 2026-04-21 | 2026-04-21 | KPTG-SADV-003826 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-17 | Jangho-TRANSMIT-000011 | NA | Trade Partner | 002_FT-01&FT02 SYSTEM CONCEPT DRAWING-01 | 28 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 438 | 2026-04-24 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-001436 | Closed | 28 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-17 | Jangho-TRANSMIT-000012 | NA | Trade Partner | Structural Calculation For FT01& FT02 System Concept Drawing-01 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected |  | 2026-04-17 | KPTG-SADV-001676 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-17 | PCForm-TRANSMIT-000156 | NA | Trade Partner | Level 3 backpropping design | 1 | 0 | 0 | KPTG-IntCorr-000603 | APPROVED | [5 empty] | Register updated, clarification requested Nicholas |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-17 | INGEN3D-TRANSMIT-000033 | NA | Trade Partner | Level 3-5 - PC0287 - New IFA | 3 | 0 | 0 | NA | APPROVED | 2026-04-17 | WF-000335 | NA |  |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-001305 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-17 | PCForm-TRANSMIT-000157 | NA | Trade Partner | IFC Existing carpark level 3 | 1 | 0 | 0 | KPTG-IntCorr-000602 | APPROVED | [5 empty] | Register updated, clarification requested - Nicholas |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-17 | PCForm-TRANSMIT-000158 | NA | Trade Partner | Scaffold design raft 4 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | rejected |  | 2026-04-17 | KPTG-TRANSMIT-001234 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-15 | ARCST-TRANSMIT-000154 | NA | Trade Partner | Cooling Tower HD Bolt Marking Plan - Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2025-12-15 | WF-003592 | NA | 2026-01-05 |  | The workflow has been terminated and resubmitted as requested by Lola W. NEW WF-004155 |  | 2026-02-05 | WF Terminated | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-17 | INGEN3D-TRANSMIT-000034 | NA | Trade Partner | Level 1-3 - Cast in Dowels & Precast Columns | 71 | 0 | 0 | NA | APPROVED | 2026-04-17 | WF-000338 | NA | 2026-04-29 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-17 | RDSBIM-TRANSMIT-000025 | NA | Trade Partner | LEVEL 02 CONCRETE PROFILE PLAN AND SECTIONS | 4 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 439 | 2026-04-22 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-001255 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-17 | TTW-TRANSMIT-000143 | NA | Consultant | BP4 Update Issue | 21 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 435 | 2026-04-21 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-001387 | Closed | 21 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-17 | TTW-TRANSMIT-000142 | NA | Consultant | CIVIL STORMWATER CAD | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Register updated 5 CAD FILES - SEND TO TRADEPARTNERS |  | 2026-04-17 | KPTG-TRANSMIT-001227 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-17 | INGEN3D-TRANSMIT-000035 | NA | Trade Partner | Level 1-3 - Cast in Dowels & Precast Column - No Longer in Use | 25 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | NO LONGER IN USE - REGISTER UPDATED |  | 2026-04-17 | NA | Closed | 25 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-17 | KPTG-IntCorr-000601 | NA | Trade Partner | Ground Floor (Level 1) - PC0097, PC0129 & PC0135 - Revised IFC | 3 | 0 | 0 | NA | APPROVED | 2026-04-17 | WF-000336 | NA | 2026-04-24 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-001306 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-17 | TTW-TRANSMIT-000141 | NA | Consultant | CIVIL STORMWATER DWG RETRANSMIT | 8 | 0 | 0 | NA | REJECTED | [5 empty] | rejected |  | 2026-04-17 | KPTG-TRANSMIT-001215 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-17 | VAE-Grp-TRANSMIT-000151 | NA | Trade Partner | MECHANICAL SHOP DRAWINGS - AIR SHEMATIC, LG HV ROOM, GND COORD, L2-5 SPEEDPANEL RISER CHANGES, CIRCULAR AMENITIES DIFFUSERS | 8 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 1219 | 2026-04-21 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-003490 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-17 | VAE-Grp-TRANSMIT-000151 | NA | Trade Partner | MECHANICAL SERVICES - SCHEDULES | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  | FC Schedules - forwarded to all parties |  | 2026-04-17 | KPTG-TRANSMIT-003426 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-17 | VAE-Grp-TRANSMIT-000152 | NA | Trade Partner | MECH - SCHEDS - L2, L3, L4 Speedpanel riser changes | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  | FC Schedules - forwarded to all parties |  | 2026-04-17 | KPTG-TRANSMIT-003427 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-15 | RDSBIM-TRANSMIT-000169 | NA | Trade Partner | NXM3S4 ¦ SITE HOIST-1 SETOUT LAYOUT | 1 | 0 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-17 | VAE-Grp-TRANSMIT-000153 | NA | Trade Partner | MECHANICAL - LG BWs + Schedules and L5 Schedules | 1 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 1221 | 2026-04-21 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-003522 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-17 | VAE-Grp-TRANSMIT-000153 | NA | Trade Partner | MECHANICAL - LG BWs + Schedules and L5 Schedules | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | FC Schedules - forwarded to all parties |  | 2026-04-17 | KPTG-TRANSMIT-003428 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-17 | Hames-TRANSMIT-000151 | NA | Consultant | Latest Revision | 1 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 1211 | 2026-04-21 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-003447 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-17 | Hames-TRANSMIT-000151 | NA | Consultant | Latest Revision | 8 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 1213 | 2026-04-21 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-003443 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-17 | Hames-TRANSMIT-000151 | NA | Consultant | Latest Revision | 3 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 1215 | 2026-04-21 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-003439 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-17 | Hames-TRANSMIT-000151 | NA | Consultant | Latest Revision | 4 | 0 | 0 | NA | APPROVED | 2026-04-17 | NA | 1217 | 2026-04-21 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-003435 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-17 | Hames-TRANSMIT-000151 | NA | Consultant | Latest Revision | 11 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Rejected - 1 drawing, Balance 10 dwgs processed with Trn 153 |  | 2026-04-17 | KPTG-IntCorr-001186 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-04-20 | Nilsen3-TRANSMIT-000107 | NA | Trade Partner | M3 Stage-3 SCADA ROPs 4A & 4B | 0 | 1 | 0 | NA | APPROVED | 2026-04-20 | WF-005349 | NA | 2026-04-30 |  |  | 2026-08-17 | 2026-08-17 | KPTG-TRANSMIT-020650 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-20 | Auspan-TRANSMIT-000018 | NA | Trade Partner | Update precast dowel layout for construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-20 | WF-000044 | NA | 2026-04-29 |  | Terminated as advised by Chri Doh for updating the drawings. | 2026-04-29 | 2026-04-29 | KPTG-IntCorr-000172 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-20 | INTRFRM-TRANSMIT-000019 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 3) | 0 | 6 | 0 | NA | APPROVED | 2026-04-20 | WF-000045 | NA | 2026-04-28 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000294 | Open | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-15 | ARCST-TRANSMIT-000156 | NA | Trade Partner | Stage 4 - C1 Switchroom Stage 1 Shop Drawings - Issued for Re-Approval | 97 | 0 | 0 | NA | REJECTED | [5 empty] | There is a duplicate file attached in this submission under reference number M3-STR-ARC-SDRG-C-0401-BR2023 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-17 | SMEPS-TRANSMIT-000188 | NA | Trade Partner | Mel05 TeleCommunication SLD DWG For IFA | 1 | 0 | 0 | NA | APPROVED | 2026-04-20 | WF - 000188 | NA | 2026-04-24 |  | NA | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-000745, KPTG-TRANSMIT-000746, KPTG-TRANSMIT-000747 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-20 | RDSBIM-TRANSMIT-000079 | NA | Trade Partner | LEVEL 1 DH B-1-013 AMBULANT TOILET FLOOR FINISHES LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 1223 | 2026-04-22 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-003644 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-20 | LNCPPL-TRANSMIT-000004 | NA | Trade Partner | In ground Water services BP1 - IFA | 1 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 82 | 2026-04-24 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-000185 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-20 | Auspan-TRANSMIT-000020 | NA | Trade Partner | Precast shop drawings for approval | 36 | 0 | 0 | NA | APPROVED | 2026-04-20 | WF-000047 | NA | 2026-04-29 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-000219 | Closed | 36 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-04-20 | KPTG-IntCorr-003383 | NA | Trade Partner | SME O&M manual | 0 | 1 | 0 | NA | APPROVED | 2026-04-20 | WF-000999 | NA | 2026-04-27 |  | due to One of the reviewers uploaded the wrong document,we resubmitted requested by Andrew broadstock-WF-001000 | 2026-04-29 |  | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-20 | HDRAus-TRANSMIT-000460 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 36 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 2894 | 2026-04-23 |  | 1 doc is still under review (2899) | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-016289 | Closed | 35 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-17 | Hames-TRANSMIT-000151 | NA | Consultant | Latest Revision | 10 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 1229 | 2026-04-22 |  | Out of 11 documents, 10 have been processed along with one document (Hames-TRANSMIT-000153). | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-003514 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-20 | Hames-TRANSMIT-000153 | NA | Consultant | Sheet update | 1 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 1229 | 2026-04-20 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-003518 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-15 | ARCST-TRANSMIT-000157 | NA | Trade Partner | Stage 4 - C1 Switchroom Stage 1 Shop Drawings - Issued for Re-Approval | 98 | 0 | 0 | NA | REJECTED | [5 empty] | There is a duplicate file attached in this submission under reference number M3-STR-ARC-SDRG-C-0401-BR2023. Instead of M3-STR-ARC-SDRG-C-0401-BR2023, the file attached is M3-STR-ARC-SDRG-C-0401-B2023 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-20 | Stowe-A-TRANSMIT-000558 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - LIGHTNING PROTECTION - 20.04.2026 | 1 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 4138 | 2026-05-01 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-016588 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-20 | ECBS-TRANSMIT-000033 | NA | Trade Partner | Shop Drawings For Approval (Batch 3: 19dwgs) | 19 | 0 | 0 | NA | APPROVED | 2026-04-20 | WF-005351 | NA | 2026-04-29 |  | TERMINATED AS PER REQUESTED BY ISABELA NEED GO ALL DOCUMENTS IN SAME WORKFLOW |  | 2026-04-23 | NA | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-20 | ECBS-TRANSMIT-000035 | NA | Trade Partner | Shop Drawings For Approval (Batch 5: 12dwgs) | 12 | 0 | 0 | NA | APPROVED | 2026-04-20 | WF-005354 | NA | 2026-04-29 |  | TERMINATED AS PER REQUESTED BY ISABELA NEED GO ALL DOCUMENTS IN SAME WORKFLOW |  | 2026-04-23 | NA | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-20 | TTW-TRANSMIT-000173 | NA | Trade Partner | M3 Stage 1 Civil Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 4140 | 2026-04-22 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-016964 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-20 | Nilsen3-TRANSMIT-000106 | NA | Trade Partner | ROPS 2C & 2D | 0 | 1 | 0 | NA | APPROVED | 2026-04-20 | WF-005356 | NA | 2026-04-30 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-20 | KPTG-IntCorr-000353 | NA | Trade Partner | Screed tech data review | 0 | 1 | 0 | NA | APPROVED | 2026-04-20 | WF - 000359 | NA | 2026-04-24 |  | NA | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-000750 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-20 | ARCST-TRANSMIT-000261 | NA | Trade Partner | Re: Switchroom Busduct Peno Supports - Issued for Approval | 11 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED SEEMS DIFFERNCE IN SCOPE OF WORK |  | 2026-04-20 | KPTG-DA-006051 | Open | 11 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-20 | ECBS-TRANSMIT-000034 | NA | Trade Partner | Shop Drawings For Approval (Batch 4: 20dwgs) | 20 | 0 | 0 | NA | APPROVED | 2026-04-20 | WF-005352 | NA | 2026-05-05 |  | TERMINATED AS PER REQUESTED BY ISABELA NEED GO ALL DOCUMENTS IN SAME WORKFLOW |  | 2026-04-23 | NA | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-20 | ECBS-TRANSMIT-000036 | NA | Trade Partner | Shop Drawings For Approval (Batch 4: 20dwgs) | 20 | 0 | 0 | NA | APPROVED | 2026-04-20 | WF-005357 | NA | 2026-05-05 |  | TERMINATED AS PER REQUESTED BY ISABELA NEED GO ALL DOCUMENTS IN SAME WORKFLOW |  | 2026-04-23 | NA | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-20 | Stowe-A-TRANSMIT-000559 | NA | Trade Partner | Stowe - Tech Data - IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Tech Data IFC. Distribution only. |  | 2026-04-20 | KPTG-TRANSMIT-016121 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-20 | Nilsen3-TRANSMIT-000113 | NA | Trade Partner | Updated Hot Dipped Gal sample | 0 | 1 | 0 | NA | APPROVED | 2026-04-20 | NA | NA | 2026-05-11 |  | For distribution |  | 2026-04-21 | KPTG-TRANSMIT-016249 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-20 | ARCST-TRANSMIT-000262 | NA | Trade Partner | C1 Cooling Tower Roof Stairs - Issued for Approval | 42 | 0 | 0 | NA | APPROVED | 2026-04-20 | WF-005358 | NA | 2026-05-14 |  |  |  | 2026-06-22 | KPTG-TRANSMIT-018900 | Closed | 24 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-20 | Bianco-TRANSMIT-000062 | NA | Trade Partner | Fwd: Precast Dowel Layout | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | ONLY FOR INFORMING BORDER TEAM |  | 2026-04-20 | KPTG-TRANSMIT-016126 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-20 | D&E-TRANSMIT-000598 | NA | Trade Partner | NXM3S4 - Ground - Mechanical Duct Layout - Zone 8 & IW Tank room - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 2901 | 2026-04-28 |  | As Instructed by Ellie , KPTG-IntCorr-013787 |  | 2026-05-26 | KPTG-IntCorr-013787 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-20 | WGAVIC-IntCorr-000048 | NA | Consultant | CIVIL PACKAGE FOR REVIEW | 24 | 0 | 0 | NA | REJECTED | [5 empty] | Zip file instead of separate file, Drawings status and revision issues. |  | 2026-04-20 | KPTG-DA-000532 | Closed | 24 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-20 | GHD-TRANSMIT-000006 | NA | Consultant | GE1 IFC Security Services Documentation | 17 | 2 | 0 | NA | REJECTED | [5 empty] | Issues with revision number in drawings. Document number and revision number missing in spec and report. |  | 2026-04-20 | KPTG-DA-000533 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-20 | INGEN3D-TRANSMIT-000692 | NA | Trade Partner | Roof and Plant Roof - Water - Issued for construction | 6 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 2905 | 2026-04-27 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016542 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-20 | DS-TRANSMIT-000112 | NA | Trade Partner | Ground Floor and L1 - Drainage - Re-issued for construction | 5 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 2906 | 2026-04-23 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-016589 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-20 | Stowe-A-TRANSMIT-000560 | NA | Trade Partner | Stowe - Tech Data - IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Tech Data IFC. Distribution only. |  | 2026-04-20 | KPTG-TRANSMIT-016138 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-20 | Lat-TRANSMIT-000010 | NA | Consultant | M3 Expansion - Landscape Issued For Tender Drawings | 28 | 1 | 0 | NA | APPROVED | 2026-04-20 | NA | 44 | 2026-04-28 |  |  | 2026-05-13 | 2026-05-13 | NA | Closed | 29 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-15 | Tradetec-TRANSMIT-000305 | NA | Trade Partner | Stage 4 - LVP44 - Shop Drawing | 1 | 0 | 0 | NA | APPROVED | 2025-12-15 | NA | 1651 | 2025-12-23 |  |  |  | 2026-01-06 | KPTG-TRANSMIT-011210 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-20 | PARR-TRANSMIT-000164 | NA | Trade Partner | Fwd: P2685 - NDC M3 - Stage 4 - Battery Rooms - HVAC CACO | 1 | 0 | 0 | NA | APPROVED | 2026-04-20 | WF-005366 | NA | 2026-05-01 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-016738 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-20 | 4DW-TRANSMIT-000023 | NA | Consultant | Structural Documentation: Ground Floor Block 3 (Issued for information). | 4 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 41 | 2026-04-28 |  | 1-old rev is under review | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000059 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-20 | OveArup-TRANSMIT-000009 | NA | Consultant | Stage 6 internal partitions acoustic markup | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Information only |  | 2026-04-20 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-20 | 4DW-TRANSMIT-000024 & 4DW-TRANSMIT-000025 | NA | Consultant | Structural Documentation: Block 1 Precast walls & Foundations (Issued for certification). | 7 | 0 | 0 | KPTG-IntCorr-000057 | APPROVED | 2026-05-07 | NA | 77 | 2026-05-15 |  | Old rev is under review-Tim to confirm | 2026-06-10 | 2026-06-11 | NA | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-20 | SKS Tech-TRANSMIT-000055 | NA | Trade Partner | Switchroom Doors - Sho Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-04-20 | WF-005365 | NA | 2026-04-25 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016496 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-20 | D&E-TRANSMIT-000228 | SPARK-CRFI-KPG-000466, SPARK-CRFI-KPG-000525, SPARK-CRFI-KPG-000313 & SPARK-CRFI-KPG-000315 | Trade Partner | MWYCCB - ROOF / LEVEL 1 / GROUND LEVEL - DUCTWORK / PIPEWORK / PENETRATION & RCP LAYOUT SHEETS ZONES - Issued For Construction | 4 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 242 | 2026-04-27 |  |  | 2026-04-21 | 2026-05-04 | KPTG-TRANSMIT-000790 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-04-20 | NXT-TRANSMIT-000394 | NA | Client | M3S1 Kiosk As-built updated | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As- built-Distribution only |  | 2026-04-20 | Awaiting approval | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-20 | D&E-TRANSMIT-000599 | NA | Trade Partner | Admin office System architecture - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-20 | WF-005364 | NA | 2026-05-04 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-017414 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-20 | NXT-TRANSMIT-000361 | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 03 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For information |  | 2026-04-20 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-20 | D&E-TRANSMIT-000229 | SPARK-CRFI-KPG-000254 | Trade Partner | MWYCCB - GROUND LEVEL - DUCTWORK LAYOUT ZONE 8 & ZONE 9 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 243 | 2026-04-27 |  |  | 2026-04-21 | 2026-04-24 | KPTG-TRANSMIT-000726 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2025-12-12 | RLA-TRANSMIT-000237 | NA | Consultant | External Levels - Preston Laneway - AR-DRW-05 Annotation Correction | 4 | 0 | 0 | NA | APPROVED | 2025-12-15 | NA | 564 | 2025-12-19 |  |  | 2025-12-17 | 2025-12-17 | KPTG-TRANSMIT-002525 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-20 | FNSTR8-TRANSMIT-000005 | NA | Trade Partner | Re: Update Drawing No. | 22 | 0 | 0 | NA | REJECTED | [5 empty] | The drawing received in the transmittal has a few mistakes, so it is sent back to the originator for correction |  | 2026-04-20 | KPTG-TRANSMIT-016166 | Closed | 22 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-04 | ARCST-TRANSMIT-000199 | NA | Trade Partner | C2 Cooling Tower Base Framing - Issued for Review | 0 | 0 | 0 | NA | APPROVED | 2026-02-04 | WF-004112 | NA | 2026-03-02 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016169 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-20 | SES AU-TRANSMIT-000013 | NA | Trade Partner | Security-Level 2 COLO 4 Layouts | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Document Number and revision details of drawings are incorrect, requested to resubmit: KPTG-IntCorr-000289 |  | 2026-04-20 | KPTG-IntCorr-000289 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-20 | EFP-TRANSMIT-000015 | NA | Trade Partner | EFP Tech Data Issued for Construction | 0 | 14 | 0 | NA | APPROVED | 2026-04-20 | WF-000152 | NA | 2026-04-21 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-000448 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-20 | Appselec-TRANSMIT-000060 | NA | Trade Partner | EPMS services - Shop drawings Issued For Approval | 10 | 0 | 0 | NA | APPROVED | 2026-04-20 | WF-000153 | NA | 2026-04-23 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-000480 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-20 | Bianco-TRANSMIT-000063 | NA | Trade Partner | Re: Precast IFC | 67 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due difference in Aconex and drawing |  | 2026-04-20 | KPTG-TRANSMIT-016189 | Closed | 67 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-20 | Appselec-TRANSMIT-000061 | NA | Trade Partner | Communications Services - Shop drawings Issued For Approval | 12 | 0 | 0 | NA | REJECTED | [5 empty] | Title of drawings do not match with what mentioned on the drawings, requested to resubmit:KPTG-IntCorr-000288 |  | 2026-04-20 | KPTG-IntCorr-000288 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-20 | VERTIV-TRANSMIT-000002 | NA | Trade Partner | Next DC GE01 _ For Review and Approval _ 20-04-2026 | 13 | 4 | 0 | NA | REJECTED | [5 empty] | Issue with document number, revision, mixed packages, no cover sheet for sample submission. |  | 2026-04-20 | KPTG-SADV-000179 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-20 | SMEPS-TRANSMIT-000243 | NA | Trade Partner | Revised Jemena Easement Shopdrawing - 20.04.2026 | 2 | 0 | 0 | NA | APPROVED | 2026-04-20 | WF-005369 | NA | 2026-04-27 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-20 | Tradetec-TRANSMIT-000425 | NA | Trade Partner | Tech Data - Sitewide - Multilayer Conduit | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  | Issues with Revision number, KPTG-SADV-004915 |  | 2026-04-20 | KPTG-SADV-004915 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-01 | TTW-TRANSMIT-000043 | 276 | Consultant | L1 Concrete Option & L6 Elements | 5 | 0 | 0 | NA | APPROVED | 2025-12-02 | N/A | 663 | 2025-12-04 |  |  | 2025-12-04 | 2025-12-04 | KPTG-TRANSMIT-002188 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-15 | Altaire-TRANSMIT-000027 | NA | Trade Partner | IFC Shop Drawings Latest Rev | 9 | 0 | 0 | NA | APPROVED | 2025-12-15 | NA | 1316 | 2025-12-19 |  |  |  | 2025-12-18 | KPTG-TRANSMIT-002234 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-20 | NXT-TRANSMIT-001501 | NA | Client | M3S2 Kiosk As-built updated | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-20 | KPTG-TRANSMIT-016194 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-20 | HDRAus-TRANSMIT-000462 | NA | Consultant | Document upload - PDF and CAD | 2 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 2910 | 2026-04-24 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-016339 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | KPTG-IntCorr-010478 | NA | Consultant | S4 NEXTDC CONSULTANT REVIEW - IFA - KPTG-TRANSMIT-013632 - S4 - C1 Cooling Tower Roof Framing | 0 | 0 | 0 | NA | APPROVED | 2026-03-27 | WF-004692 | NA | 2026-04-15 |  | remaining 4 closed | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016198 | Closed | 46 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-20 | ADP-TRANSMIT-000045 | NA | Consultant | MEL4680 - ADP IFC ISSUE | 87 | 2 | 0 | NA | REJECTED | [5 empty] | Issue with the title |  | 2026-04-20 | KPTG-DA-000536 | Closed | 89 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-20 | PARR-TRANSMIT-000163 | NA | Trade Partner | Fwd: P2680 - NDC M3 Stage 4 - Fuel - BF RETIC LAYOUT & SECTIONS | 13 | 0 | 0 | NA | APPROVED | 2026-04-20 | 2915 | NA | 2026-04-29 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-017436 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-20 | ADP-TRANSMIT-000046 | NA | Consultant | ADP MEL4680 - MECH IFC Issue | 28 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with the title |  | 2026-04-20 | KPTG-DA-000535 | Closed | 28 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-20 | fjc-TRANSMIT-000145 | NA | Consultant | Building Permit 6 - Architecturals | 77 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 630 | 2026-04-23 |  |  | 2026-04-22 | 2026-04-23 | KPTG-SADV-003852 | Closed | 77 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-20 | RDSBIM-TRANSMIT-000185 | NA | Trade Partner | LINDRUM ¦ LEVEL 06 TO LEVEL 10 COREWALL CONCRETE PROFILE PLAN ELEVATION | 2 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 629 | 2026-04-23 |  |  | 2026-04-23 | 2026-04-30 | KPTG-SADV-003955 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-20 | RDSBIM-TRANSMIT-000184 | NA | Trade Partner | LINDRUM ¦ LEVEL 03 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-SADV-003805-As per the direction Ashlin, we transmit this document all consultant parti. |  |  | KPTG-SADV-003805 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-20 | JCBa-TRANSMIT-000094 | NA | Consultant | : General Arrangement Plans IFC: L5 & L6 all zones | 10 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 741 | 2026-04-22 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-001519 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-12 | Hames-TRANSMIT-000088 | NA | Consultant | Latest FC DWGS | 20 | 0 | 0 | NA | APPROVED | 2025-12-15 | NA | 747 | 2025-12-17 |  |  | 2025-12-15 | 2025-12-18 | KPTG-TRANSMIT-002339 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-20 | JCBa-TRANSMIT-000097: | NA | Consultant | Structural Setout Plans IFC: 2nd to 5th Floor, Overall Plans | 4 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 752 | 2026-04-22 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-001573 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-20 | RDSBIM-TRANSMIT-000048 | NA | Trade Partner | MAC GROUND FLOOR CONCRETE PROFILE PLAN ZONE 2 | 2 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | NA |  |  | As advised by Kapitol DM, No Review required; Register and distribute- KPTG-TRANSMIT-001382 |  | 2026-04-20 | KPTG-TRANSMIT-001382 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-20 | JCBa-TRANSMIT-000095 | NA | Consultant | Structural Setout Plans IFC: 2nd to 5th Floor, all zones | 20 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 744 | 2026-04-27 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-001567 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-20 | Auspan-TRANSMIT-000221 | NA | Trade Partner | Update already IFCed shop drawings for construction | 18 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | NA |  |  | IFC No review required as advised. KPTG-TRANSMIT-001392 |  | 2026-04-20 | KPTG-TRANSMIT-001392 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-20 | Auspan-TRANSMIT-000222 | NA | Trade Partner | : Resubmit precast shop drawings for approval. Ground floor and level 1 | 13 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect drawing revision. Metadata is not matching with drawing revision. |  | 2026-04-20 | KPTG-SADV-002006 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-20 | Auspan-TRANSMIT-000223 | NA | Trade Partner | Precast shop drawings for construction. Ground floor and level 1 | 32 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC No review required as advised. KPTG-TRANSMIT-001389 |  | 2026-04-20 | KPTG-TRANSMIT-001389 | Closed | 32 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-20 | JCBa-TRANSMIT-000096 | NA | Trade Partner | GA Plans: L5 & L6 Overall Plans | 2 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 748 | 2026-04-27 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-001570 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-20 | POTTSENG-TRANSMIT-000023 | NA | Trade Partner | GMAC HYDRAULIC SERVICES - PENETRATION - GROUND - ZONE 5 LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 746 | 2026-04-27 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-001515 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-20 | Auspan-TRANSMIT-000211 | NA | Trade Partner | Precast shop drawings for construction. Ground floor, level 1 and level 2. | 22 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC No review required as advised. Register and distribute . KPTG-TRANSMIT-001386 |  | 2026-04-20 | KPTG-TRANSMIT-001386 | Closed | 22 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-20 | RDSBIM-TRANSMIT-000056 | NA | Trade Partner | 671CHP BASEMENT 1 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 420 | 2026-04-27 |  | Review voided as advised by kapitol PC, | 2026-05-12 | 2026-05-12 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-15 | ARCST-TRANSMIT-000158 | NA | Trade Partner | Stage 4 - C1 Switchroom Stage 1 Shop Drawings - Issued for Re-Approval | 98 | 0 | 0 | NA | APPROVED | 2025-12-15 | WF-003596 | NA | 2025-12-01 |  |  |  | 2026-02-03 | KPTG-TRANSMIT-012410 | Closed | 17 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-20 | B Smart-TRANSMIT-000070 | NA | Consultant | A04 L1 and L3 revised IFC | 2 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 423 | 2026-04-27 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-000820 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-02-17 | Electro-TRANSMIT-000002: | NA | Trade Partner | Common Areas Specialist Lighting KPTG-WTRAN-000556 WF-000224 | 0 | 3 | 0 | NA | APPROVED | 2026-02-17 | WF-000224 | NA | 2026-02-24 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-000808 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-04-17 | ENF-TRANSMIT-000011 | NA | Consultant | Structural drawings | 1 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 45 | 2026-04-28 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-000039 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-04-20 | WIP Package | NA | Consultant | Structural Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 46 | 2026-04-28 |  |  |  | 2026-05-04 | KPTG-TRANSMIT-000039 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-04-14 | WSP ANZ-TRANSMIT-000006 | NA | Consultant | WSP - 80% Tender Issue Drawings & Specifications (Electrical) | 16 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 55 | 2026-04-27 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-000053 | Closed | 16 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-04-14 | WSP ANZ-TRANSMIT-000006 | NA | Consultant | WSP - 80% Tender Issue Drawings & Specifications (Fire Protection) | 5 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 61 | 2026-04-27 |  | Voided as discussed with Renee, updated drawings available. |  | 2026-05-13 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-04-14 | WSP ANZ-TRANSMIT-000006 | NA | Consultant | WSP - 80% Tender Issue Drawings & Specifications (Hydraulic) | 15 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 57 | 2026-04-27 |  | Voided as advised by Renee 13-05-2026 |  | 2026-05-13 | NA | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-04-14 | WSP ANZ-TRANSMIT-000006 | NA | Consultant | WSP - 80% Tender Issue Drawings & Specifications (Mechanical) | 9 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 59 | 2026-04-27 |  | Voided as advised by Renee 13-05-2026 |  | 2026-05-13 | NA | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-14 | WSP ANZ-TRANSMIT-000005 | NA | Consultant | WSP - Demolition Construction Issue Drawings (Fire Protection) | 5 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 96 | 2026-05-19 |  | Actual received date 4/7/2026 |  | 2026-05-28 | KPTG-TRANSMIT-000107 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-14 | WSP ANZ-TRANSMIT-000005 | NA | Consultant | WSP - Demolition Construction Issue Drawings (Hydraulic) | 3 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 97 | 2026-05-19 |  | Actual received date 4/7/2026 |  | 2026-05-28 | KPTG-TRANSMIT-000104 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-13 | SKS Tech-TRANSMIT-000105 | NA | Trade Partner | 240mm HV Cable resubmission | 0 | 2 | 0 | Rejected - KPTG-TRANSMIT-002274 | APPROVED | 2025-12-16 | WF-000648 | NA | 2025-12-22 |  | Sort out the document problem and Submitted the same docs | 2026-01-23 | 2026-01-23 | KPTG-WTRAN-001426 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-14 | WSP ANZ-TRANSMIT-000005 | NA | Consultant | WSP - Demolition Construction Issue Drawings (Mechanical) | 6 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 98 | 2026-05-19 |  | Actual Received date 4/7/2026 |  | 2026-05-28 | KPTG-TRANSMIT-000107 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-14 | ENF-TRANSMIT-000008 | NA | Consultant | Structural drawings | 3 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 102 | 2026-05-19 |  | Actual Received date 10-04-2026 | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-000191 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-20 | Highbu-TRANSMIT-000144 | NA | Trade Partner | Stage 1 - As builts | 13 | 0 | 0 |  | APPROVED |  | NA | NA |  |  | As built, drawings, just updated document Register. |  | 2026-04-20 | KPTG-TRANSMIT-002763 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-20 | Jangho-TRANSMIT-000014 | NA | Trade Partner | 001-FT01 &FT02 TOWER VISUAL MOCK-UP SHOP DRAWING-01 | 23 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 443 | 2026-04-28 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-001504 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-14 | WSP ANZ-TRANSMIT-000009 | NA | Consultant | WSP - Fire Protection Cover Sheets | 1 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 99 | 2026-05-19 |  | Actual Received date 16-04-2026 |  | 2026-05-28 | KPTG-TRANSMIT-000098 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-14 | WSP ANZ-TRANSMIT-000009 | NA | Consultant | WSP - Hydraulic Cover Sheets | 1 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 100 | 2026-05-19 |  | Actual received date 4/15/2026 |  | 2026-05-28 | KPTG-TRANSMIT-000098 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-20 | INGEN3D-TRANSMIT-000036 | NA | Trade Partner | Level 4-6 - Cast in Dowels - IFA | 9 | 0 | 0 | NA | APPROVED | 2026-04-20 | WF-000348 | NA | 2026-04-23 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-001475 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-20 | INGEN3D-TRANSMIT-000037 | NA | Trade Partner | Level 2-4 - Precast Columns - IFC | 22 | 0 | 0 | NA | APPROVED | 2026-04-20 | WF-000349 | NA | 2026-04-23 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-14 | WSP ANZ-TRANSMIT-000009 | NA | Consultant | WSP - Mechanical Cover Sheets | 1 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 101 | 2026-05-19 |  | Actual Received date 4/15/2026 |  | 2026-05-28 | KPTG-TRANSMIT-000098 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-15 | ACG-TRANSMIT-000040 | NA | Trade Partner | M2 DH11 Variation - Updated Drawings | 6 | 1 | 0 | NA | APPROVED | [5 empty] | As-Builts, No review required. Distributed to the Project Team. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-20 | INGEN3D-TRANSMIT-000038 | NA | Trade Partner | Level 2-4 - Precast Columns - No Longer in Use | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | NO LONGER IN USE - REGISTER UPDATED |  | 2026-04-20 | KPTG-TRANSMIT-001264 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-20 | Rinco-TRANSMIT-000007 | NA | Trade Partner | Level 2 updated slab drawings | 4 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | rejected |  | 2026-04-20 | KPTG-TRANSMIT-001268 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-20 | Rinco-TRANSMIT-000008 | NA | Trade Partner | Mezz - IFC with Reg126 | 4 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 445 | 2026-04-28 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-001665 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-20 | Rinco-TRANSMIT-000009 | NA | Trade Partner | Level 2 updated drawings | 2 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 447 | 2026-04-28 |  |  | 2026-05-01 | 2026-05-04 | KPTG-TRANSMIT-001487 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-04-07 | WSP ANZ-TRANSMIT-000005 | NA | Consultant | WSP - Demolition Construction Issue Drawings Electrical | 10 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 54 | 2026-04-27 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-000052 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-04-14 | WSP ANZ-TRANSMIT-000007 | NA | Consultant | Re: WSP - 80% Tender Issue Specifications Hydraulic | 0 | 1 | 0 | NA | APPROVED | 2026-04-21 | WF-000026 | NA | 2026-04-28 |  | Review Voided - The specification will be reviewed in ACC and re-initiated under ACC #193 |  | 2026-06-02 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-15 | Carr-TRANSMIT-000009 | NA | Consultant | Architectural Current Drawing Set | 8 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 104 | 2026-05-20 |  | Actual Received date 3/24/2026 | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000158 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-15 | Carr-TRANSMIT-000017 | NA | Consultant | 80% DD Architectural Drawing Issue (Ground Floor and Upper Level) | 17 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 115 | 2026-05-20 |  | Actual Received date 27-03-2026 Review Voided as advised by Renee 26-05-2026 |  | 2026-05-26 | NA | Closed | 17 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-15 | NXT-TRANSMIT-001139 | NA | Trade Partner | NEXTDC M3 ST-4- CRAC shop drawing and selection sheet submission | 6 | 0 | 0 | NA | APPROVED | 2025-12-15 | WF-003598 | NA | 2025-12-29 |  |  |  | 2025-12-16 | NXT-WTRAN-001282 | Closed | 6 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-15 | Carr-TRANSMIT-000022 | NA | Consultant | 80% DD Architectural Drawing Issue | 3 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 117 | 2026-05-20 |  | Actual received date 30-03-2026 | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000155 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-30 | Carr-TRANSMIT-000023 | NA | Consultant | 80% DD Architectural Drawing Issue | 1 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 50 | 2026-04-27 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-000049 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-15 | Carr-TRANSMIT-000036 | NA | Consultant | Additional Architectural Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 133 | 2026-05-20 |  | Actual Received date 30-03-2026 | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000152 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-20 | RDSBIM-TRANSMIT-000135 | NA | Trade Partner | MLCSPR ¦ CARPARK NORTH LEVEL 01 RCP | 1 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 196 | 2026-04-24 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-002766 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-15 | Carr-TRANSMIT-000037 | NA | Consultant | Re: 303 Collins Street - Carr Demolition Drawing Set | 3 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 135 | 2026-05-20 |  | Actual received date 14-04-2026 | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-000084 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-04-17 | Carr-TRANSMIT-000040 | NA | Consultant | Architectural Specification, Schedule | 0 | 2 | 0 | NA | APPROVED | 2026-04-21 | WF-000029 | NA | 2026-04-28 |  | Review Terminated- Specification reviewed under #175 |  | 2026-06-26 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-15 | OveArup-TRANSMIT-000140 | NA | Trade Partner | M3 Stage 3 Earthing Study Report IFCN-3 | 0 | 1 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-20 | ECBS-TRANSMIT-000080 | NA | Trade Partner | Submission of Studco Specification/Design | 0 | 9 | 0 | NA | APPROVED |  | NA | NA |  |  | As per thr direction from the Ms. Alexia, No workflow is required: just update to document Register: KPTG-IntCorr-007056 |  | 2026-04-20 | KPTG-IntCorr-007056 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-20 | WGAVIC-TRANSMIT-000104 | NA | Consultant | M2 - Stage 11 Slab - Issued for Certification | 5 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 715 | 2026-04-22 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-002586 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-20 | WGAVIC-TRANSMIT-000105 | NA | Consultant | M2 - Stage 2 Tank Slab - Issued for Certification | 1 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 716 | 2026-04-22 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-002590 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-21 | Nilsen3-TRANSMIT-000116 | NA | Trade Partner | Samples IFC | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-04-21 | KPTG-TRANSMIT-016224 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-14 | Auspan-TRANSMIT-000014 | NA | Trade Partner | Precast shop drawings for construction | 2 | 0 | 0 | NA | APPROVED | 2026-04-14 | WF-000029 | NA | 2026-04-23 |  | partial close out KPTG-TRANSMIT-000177 (21 Document), 20-04-2026, | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-000190 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-21 | Nilsen3-TRANSMIT-000118 Nilsen3-TRANSMIT-000105 | NA | Trade Partner | Penetration Seal Material | 0 | 1 | 0 | NA | APPROVED | 2026-04-21 | WF-005373 | NA | 2026-05-12 |  | The WF has been terminated as requested by Oliver S Material submitted has been banned by NextDC |  | 2026-04-21 | KPTG-TRANSMIT-016275 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-20 | Jangho-TRANSMIT-000013 | NA | Trade Partner | Structural Calculation for FT01& FT02 System Concept Drawing | 0 | 1 | 0 | NA | APPROVED | 2026-04-20 | WF-000352 | NA | 2026-04-24 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-001572 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-20 | PCForm-TRANSMIT-000159 | NA | Trade Partner | Level 2 updated slab drawings | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Rejected |  | 2026-04-20 | KPTG-TRANSMIT-001269 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-20 | D&E-TRANSMIT-000013 | NA | Trade Partner | Variable Speed Drive (VSD) - Loading Dock Exh. Fan LEF-05.02 Tech. Data - IFA | 0 | 1 | 0 | NA | APPROVED | 2026-04-20 | WF-000353 | NA | 2026-04-24 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-001932 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-20 | PCForm-TRANSMIT-000163 | NA | Trade Partner | PCForm-TRANSMIT-000163 | 1 | 0 | 0 | KPTG-IntCorr-000611 | APPROVED | 2026-04-21 | NA | 452 | 2026-04-29 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-001437 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-15 | ARCST-TRANSMIT-000138 | NA | Trade Partner | C1 Switchroom HD Bolts - Issued for Construction | 4 | 0 | 0 | NA | APPROVED | 2025-12-15 | WF-003599 | NA | 2025-12-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-20 | PCForm-TRANSMIT-000162 | NA | Trade Partner | Level 2 updated drawings | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No action taken - Re-transmission of Rinco-TRANSMIT-000009 |  | 2026-04-20 | Rinco-TRANSMIT-000009 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-20 | PCForm-TRANSMIT-000160 | NA | Trade Partner | Concrete mix designs for approval | 0 | 2 | 0 | NA | APPROVED | 2026-04-21 | WF-000358 | NA | 2026-04-23 |  | 1 doc Rejected 2 docs processed along with the resubmitted doc Trn#165 | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-001397 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-20 | PCForm-TRANSMIT-000161 | NA | Trade Partner | Slab curing Aquron 1000 for apporval | 0 | 1 | 0 | NA | APPROVED | 2026-04-20 | WF-000354 | NA | 2026-04-23 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-001398 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-20 | HVHD-TRANSMIT-000013 | NA | Trade Partner | ESD Implementation Matrix Update | 0 | 1 | 0 | NA | APPROVED | 2026-04-20 | WF-000355 | NA | 2026-04-23 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-001279 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-20 | Hames-TRANSMIT-000152 | NA | Consultant | DOOR SCHEDULE | 2 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 1225 | 2026-04-22 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-003624 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-20 | SKS Tech-TRANSMIT-000186 | NA | Trade Partner | for construction status | 4 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 1262 | 2026-05-08 |  | Harry to confirm,KPTG-IntCorr-001194- ELC document has already been reviewed. SKS Tech-TRANSMIT-000160. | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-003715 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-20 | Emma's Email | NA | Trade Partner | INTERNAL GLAZING TECHNICAL DATA SUBMISSION | 0 | 10 | 0 | NA | APPROVED | 2026-04-21 | WF-001018 | NA | 2026-04-24 |  | Terminated and issued via WF-1040 by Luke | 2026-05-01 | 2026-05-01 | WF-001040 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-21 | KPTG-IntCorr-000357 | NA | Trade Partner | - Screed tech data review | 0 | 1 | 0 | NA | APPROVED | 2026-04-21 | WF - 000360 | NA | 2026-04-24 |  | NA | 2026-04-21 | 2026-04-21 | K2TG-TRANSMIT-000751, KPTG-TRANSMIT-000752 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-21 | Tradetec-TRANSMIT-000426 | NA | Trade Partner | Re: IFA - Stage 4 - CP40 CP32 CP20 CP29 | 4 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED DUE TO INCORRECT REVISION NUMBER |  | 2026-04-21 | KPTG-DA-006070 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-21 | SKS Tech-TRANSMIT-000106 | NA | Trade Partner | Fwd: Conduit Hanger M3-ELC-SKS-SA-C-0400-0034 | 0 | 1 | 0 | NA | APPROVED | 2026-04-21 | WF-005377 | NA | 2026-05-04 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-016747 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-11 | PROLMC-TRANSMIT-000015 | NA | Trade Partner | Proline Shop Drawings (11/12/25) | 7 | 0 | 0 | NA | APPROVED |  | NA | 3492 | 2025-12-22 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-21 | Nilsen3-TRANSMIT-000117 | NA | Trade Partner | Fwd: OVERALL EARTHING SCHEMATIC and Energisation | 1 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 2917 | 2026-04-29 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-017327 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-21 | D&E-TRANSMIT-000600 | NA | Trade Partner | Re: Fire matrix IFA-2 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | REJECTED DUE TO INCORRECT DOCUMENT NAMING |  | 2026-04-21 | KPTG-DA-006071 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-21 | D&E-TRANSMIT-000601 | NA | Trade Partner | NXM3S4 - Level 1 - Mechanical Duct Layout - Zone 2 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 2919 | 2026-04-29 |  | As instructed by Ellie , KPTG-IntCorr-013787 |  | 2026-05-26 | KPTG-IntCorr-013787 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-21 | SMPS-TRANSMIT-000114 | NA | Trade Partner | Power Pack Samples- IFC | 0 | 9 | 0 | NA | APPROVED | 2026-04-21 | WF-000482 | NA | 2026-04-29 |  |  | 2026-04-28 | 2026-04-28 | DRAFT-009849 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-21 | Nilsen3-TRANSMIT-000119 | NA | Trade Partner | Nilsen Telecom FOA Drawings | 5 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-04-21 | KPTG-RFI-007436 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-20 | RDSBIM-TRANSMIT-000043 | NA | Trade Partner | MWYCCB ¦ LEVEL 01 INTERNAL FITOUT PLAN - FEMALE END OF TRIP SHEET | 2 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 244 | 2026-04-28 |  | Bim360 review terminated by Moj |  | 2026-06-29 | KPTG-TRANSMIT-001361 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-21 | D&E-TRANSMIT-000602 | NA | Trade Partner | NXM3S4 - Roof Level Switchroom - Mechanical Duct Layout Zones - Issued For Construction | 5 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 2977 | 2026-05-05 |  | As requested by Ellie — Terminated — KPTG-IntCorr-013787 |  | 2026-05-26 | KPTG-IntCorr-013787 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-21 | Ardon-TRANSMIT-000040 | NA | Trade Partner | Spy Hole - Security Viewer - Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-04-21 | WF - 000999 | NA | 2026-04-24 |  | File supersede and WF terminated. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-21 | ccair-TRANSMIT-000116 | NA | Trade Partner | Grille Schedule - IFA | 0 | 1 | 0 | NA | APPROVED | 2026-04-21 | WF - 0001000 | NA | 2026-04-24 |  | File supersede and WF terminated. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-20 | SES AU-TRANSMIT-000014 | NA | Trade Partner | Security-Level 2 COLO 4 Layouts | 2 | 0 | 0 | NA | APPROVED | 2026-04-21 | WF-000154 | NA | 2026-04-27 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-000530 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-15 | SMEPS-SUBADVICE-000297 | NA | Trade Partner | L2 and L3 Scripts Request for TOB & AHF | 0 | 2 | 0 | NA | APPROVED | 2025-12-15 | WF-000855 | NA | 2025-12-19 |  |  |  | 2025-12-17 | KPTG-TRANSMIT-002218 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-21 | Nilsen3-TRANSMIT-000120 | NA | Trade Partner | Fwd Nilsen Telecom FOA Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 2922 | 2026-04-30 |  |  |  | 2026-05-26 | KPTG-TRANSMIT-017859 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-21 | D&E-TRANSMIT-000232 | SPARK-CRFI-KPG-000643 | Trade Partner | COMPRESSED AIR PIPE & JOINTS | 0 | 1 | 0 | NA | APPROVED |  |  |  | 2026-04-21 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-21 | D&E-TRANSMIT-000233 | NA | Trade Partner | SEISMIC DRAWINGS | 10 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-04-21 | KPTG-TRANSMIT-000672 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-21 | KPTG-IntCorr-012102 | NA | Consultant | S4 ¦ SAMPLE AND TECH DATA | 0 | 1 | 0 | NA | APPROVED | 2026-04-21 | WF-005379 | NA | 2026-04-21 |  | AS PER REQUESTED FROM ELI FROM KPTG-IntCorr-012102 | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-016265 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-21 | WGAVIC-TRANSMIT-000008 | NA | Consultant | Civil Drawings for certification | 24 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 89 | 2026-04-24 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-000209 | Closed | 24 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-21 | INTRFRM-TRANSMIT-000021 | NA | Trade Partner | Geelong Edge - Electrical Tech Data (Submission 4) | 0 | 1 | 0 | NA | APPROVED | 2026-04-21 | WF-000050 | NA | 2026-04-29 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000440 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-21 | INTRFRM-TRANSMIT-000022 | NA | Trade Partner | Geelong Edge - Communications Tech Data (Submission 4) | 0 | 1 | 0 | NA | APPROVED | 2026-04-21 | WF-000051 | NA | 2026-04-29 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000303 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-01 | TTW-TRANSMIT-000139 | NA | Consultant | TTW traffic FC pack - Important | 2 | 0 | 0 |  | APPROVED | 2025-12-01 | NA | 1584 | 2025-12-03 |  |  | 2025-12-02 | 2025-12-02 | KPTG-TRANSMIT-010482 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2025-09-28 | KETE-TRANSMIT-000112 | NA | Trade Partner | High ST_ Townhouse Subsill Layout | 21 | 0 | 0 | NA | APPROVED | 2025-10-07 | NA | 546 | 2025-07-17 |  |  | 2025-12-01 | 2025-12-01 | KPTG-TRANSMIT-002371 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-11 | PROLMC-TRANSMIT-000016 | NA | Trade Partner | Proline sealant tech data | 0 | 1 | 0 | NA | APPROVED | 2025-12-11 | WF-003571 | NA | 2025-12-30 |  |  | 2026-03-27 | 2026-03-27 | KPTG-TRANSMIT-015069 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-21 | ASV-TRANSMIT-000168 | NA | Trade Partner | Hydraulic Chiller Module FW Grate | 0 | 1 | 0 | NA | APPROVED | 2026-04-21 | WF-005381 | NA | 2026-05-07 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-017412 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-21 | SMEPS-TRANSMIT-000190 | SPARK-CRFI-KPG-000465 | Trade Partner | Distribution Boards (non-custom) | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-27 | KPTG-TRANSMIT-000733 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-21 | Civilex-TRANSMIT-000237 | NA | Trade Partner | Sample Submission - Pavement Concrete mix design Hytec- Rev FOA-D | 0 | 1 | 0 | NA | APPROVED | 2026-04-21 | WF-005382 | NA | 2026-04-27 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018425 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-21 | KPTG-IntCorr-012143 | NA | Trade Partner | M3 Stage 4 - Tap06 WF | 0 | 1 | 0 | NA | APPROVED | 2026-04-21 | WF-005383 | NA | 2026-04-29 |  |  | 2026-04-22 | 2026-04-22 | KPTG-IntCorr-012143 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-21 | SMEPS-TRANSMIT-000189 | NA | Trade Partner | MEL05 TeleCommunications IFC DWGs | 1 | 0 | 0 | NA | APPROVED | 2026-04-21 | WF - 000361 | NA | 2026-04-24 |  | NA | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-000755 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-21 | D&E-TRANSMIT-000604 | NA | Trade Partner | NXM3S4 - Ground - Builders Works Layout Zones + Ground - Plinth & Equipment Layout Zones - Issued For Construction | 4 | 0 | 0 | NA | APPROVED | 2026-04-21 | WF-005387 | NA | 2026-04-30 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-016440 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-21 | SMEPS-TRANSMIT-000190 | NA | Trade Partner | Mel05 Communication DWGs For IFC | 2 | 0 | 0 | NA | APPROVED | 2026-04-21 | WF - 000363 | NA | 2026-04-24 |  | NA | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-000756, KPTG-TRANSMIT-000757, KPTG-TRANSMIT-000758 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-21 | Nilsen3-TRANSMIT-000121 | NA | Trade Partner | Nilsen IFC- Drawings -ELC | 5 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 2925 | 2026-04-29 |  | A total of 6 drawings are included in this transmittal, comprising 1 telecommunication and 5 electrical drawings. | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-016622 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-21 | Nilsen3-TRANSMIT-000121 | NA | Trade Partner | Nilsen IFC- Drawings -TEL | 1 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 2929 | 2026-04-29 |  | A total of 6 drawings are included in this transmittal, comprising 1 telecommunication and 5 electrical drawings. | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-018054 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-21 | PSGV-TRANSMIT-000008 | NA | Trade Partner | Technical Data submissions | 0 | 7 | 0 | NA | APPROVED | 2026-04-21 | WF-000483 | NA | 2026-04-29 |  |  | 2026-04-29 | 2026-04-29 | DRAFT-009854 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-11 | D&E-TRANSMIT-000309 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - GROUND - MECHANICAL DUCT LAYOUT - ZONE 1 | 1 | 0 | 0 | NA | APPROVED |  | NA | 3484 | 2025-12-18 |  |  | 2026-03-11 | 2026-03-12 | KPTG-TRANSMIT-014223 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-21 | KPTG-IntCorr-000362 | NA | Trade Partner | KPTG-IntCorr-000362 | 0 | 1 | 0 | NA | APPROVED | 2026-04-21 | WF - 000364 | NA | 2026-04-24 |  | File superseded | 2026-06-04 | 2026-06-04 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-21 | RDSBIM-TRANSMIT-000057 | NA | Trade Partner | 671CHP BASEMENT 3 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | waiting Ethan Chait to confirm the review KPTG-IntCorr-000466. No review required. |  | 2026-04-21 | NA | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-21 | INDS-TRANSMIT-000018 | NA | Trade Partner | : Wet Fire - Schematic | 1 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 754 | 2026-04-28 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-001496 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-21 | Auspan-TRANSMIT-000224 | NA | Trade Partner | : Resubmit panel 0G1083 for approval | 1 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 756 | 2026-04-28 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-001598 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-21 | Auspan-TRANSMIT-000225 | NA | Trade Partner | Precast shop drawings for construction. | 15 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC No review required ;register and distribute as advised KPTG-TRANSMIT-001432 |  | 2026-04-21 | KPTG-TRANSMIT-001432 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-21 | Rinco-TRANSMIT-000040 | NA | Trade Partner | L2 - L4 GENERAL ARRANGEMENT PLAN | 15 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 758 | 2026-04-28 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-001577 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-21 | Auspan-TRANSMIT-000226 | NA | Trade Partner | Update precast dowel layout zone 1, 2 ground floor | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC No review required ;register and distribute as advised KPTG-TRANSMIT-001426 |  | 2026-04-21 | KPTG-TRANSMIT-001426 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-21 | Auspan-TRANSMIT-000227 | NA | Trade Partner | Resubmit shop drawings for approval. | 10 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 761 | 2026-04-28 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-001634 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-21 | RDSBIM-TRANSMIT-000186 | NA | Trade Partner | LINDRUM ¦ LEVEL 04 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-000893-We have updated this drawing into our register and transmitted to trade partners, consultant & client as well. |  |  | KPTG-TRANSMIT-002243 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-21 | Auspan-TRANSMIT-000066 | NA | Trade Partner | Precast shop drawings for construction. | 6 | 0 | 0 | NA | APPROVED |  | NA | NA | [5 empty] | KPTG-TRANSMIT-002246 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-11 | D&E-TRANSMIT-000310 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - GROUND LEVEL BUILDERS WORKS SECTIONS - BUILDING B1 (SHEET 2) | 1 | 0 | 0 | NA | APPROVED | 2025-12-11 | NA | 3486 | 2025-12-18 |  |  | 2026-01-23 | 2026-01-23 | KPTG-TRANSMIT-011853 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-21 | Auspan-TRANSMIT-000067 | NA | Trade Partner | Re: Supply of Precast Edge Beams. Shop drawings for approval. | 7 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 631 | 2026-04-24 |  |  | 2026-05-08 | 2026-05-08 | KPTG-SADV-004074 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-21 | JCBa-TRANSMIT-000098 | NA | Consultant | General Arrangement Plans IFC: L7 all zones | 6 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 764 | 2026-04-23 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-001611 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-21 | INDS-TRANSMIT-000037 | NA | Trade Partner | Fire Penetrations, Level 1 to 27 | 27 | 0 | 0 | KPTG-SADV-003832 | APPROVED |  | NA | NA |  |  | KPTG-SADV-003832-The DWFX file was not attached KPTG-IntCorr-001177 - UPDATE REGISTER AND SEND TO RDS,FJC | 2026-07-10 | 2026-07-10 | KPTG-IntCorr-001177 | Closed | 27 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-21 | ZIA-TRANSMIT-000077 | NA | Trade Partner | M3S4 CSMS Network Diagram (FOA-2) | 3 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 2932 | 2026-05-29 |  |  |  | 2026-05-27 | KPTG-TRANSMIT-017928 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-21 | ADP-TRANSMIT-000048 | NA | Consultant | ADP MEL4680 - Hyd Specification | 0 | 1 | 0 | NA | APPROVED | 2026-04-21 | NA | 95 | 2026-04-24 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-000678 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-21 | HDRAus-TRANSMIT-000463 | NA | Consultant | Concrete profile plans - PMJ Types | 7 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 2934 | 2026-04-23 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-016437 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-21 | Bianco-TRANSMIT-000064 | NA | Trade Partner | Re: Precast IFC | 67 | 0 | 0 | NA | REJECTED | [5 empty] | Difference in revision, Same revision received and document number is not mentioned |  | 2026-04-21 | KPTG-TRANSMIT-016274 | Closed | 67 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-21 | ADP-TRANSMIT-000047 | NA | Consultant | ADP MEL4680 - SERVICES IFC ISSUE - CSM | 11 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 98 | 2026-04-24 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-000408 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-21 | ADP-TRANSMIT-000047 | NA | Consultant | ADP MEL4680 - SERVICES IFC ISSUE - ELC | 38 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 99 | 2026-04-24 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-000211 | Closed | 38 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-11 | DS-TRANSMIT-000079 | NA | Trade Partner | HYD SITE - DRAINAGE | 1 | 0 | 0 | NA | APPROVED | 2025-12-11 | NA | 3488 | 2025-12-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-21 | ADP-TRANSMIT-000047 | NA | Consultant | ADP MEL4680 - SERVICES IFC ISSUE - FID | 7 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 100 | 2026-04-24 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-000400 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-21 | ADP-TRANSMIT-000047 | NA | Consultant | ADP MEL4680 - SERVICES IFC ISSUE - FIP | 10 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 101 | 2026-04-24 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-000251 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-21 | ADP-TRANSMIT-000047 | NA | Consultant | ADP MEL4680 - SERVICES IFC ISSUE - MEC | 28 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 124 | 2026-04-28 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000347 | Closed | 28 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-21 | ADP-TRANSMIT-000047 | NA | Consultant | ADP MEL4680 - SERVICES IFC ISSUE - TEL | 11 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 103 | 2026-04-24 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-000386 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-21 | HDRAus-TRANSMIT-000464 | NA | Consultant | Sitewide Movement Joint details - Stage 4 updates | 3 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-04-21 | KPTG-DA-006092 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-21 | Auspan-TRANSMIT-000099 | NA | Trade Partner | As built precast shop drawings. | 130 | 0 | 0 |  | APPROVED |  | NA | NA |  |  | kapitol advice awaits:KPTG-IntCorr-007117 |  | 2026-04-21 | KPTG-IntCorr-007119 | Closed | 140 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-21 | ARCH-TRANSMIT-000146 | NA | Consultant | MLC - SPR - Wellness Garden Drawing update | 4 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 201 | 2026-04-24 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-21 | 4DW-TRANSMIT-000025 | NA | Consultant | Issued for Certification: Stability walls & Foundations - Block 1 | 8 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Old rev is under review |  | 2026-04-23 | KPTG-DA-000160 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-21 | NXT-TRANSMIT-000362 | NA | Client | Structural Documentation IFT - Main Works. | 1 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 46 | 2026-04-29 |  |  | 2026-05-13 | 2026-05-13 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-21 | ADP-TRANSMIT-000047 | NA | Consultant | ADP MEL4680 - SERVICES IFC ISSUE | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with the title and status |  | 2026-04-21 | DRAFT-001284 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-15 | PFP PL-TRANSMIT-000033 | NA | Trade Partner | Wet Fire As-Built Drawings | 3 | 0 | 0 | NA | APPROVED | [5 empty] | As-Built Drawings, No review required. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-21 | Appselec-TRANSMIT-000062 | NA | Trade Partner | Communication Services - Shop Drawings Issued for Approval | 12 | 0 | 0 | NA | APPROVED | 2026-04-21 | WF-000156 | NA | 2026-04-24 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-000509 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-21 | Appselec-TRANSMIT-000063 | NA | Trade Partner | Electrical Services - Panel Schedule Sheet 4 - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-04-21 | WF-000155 | NA | 2026-04-24 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-000422 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-21 | Appselec-TRANSMIT-000064 | NA | Trade Partner | Appselec-TRANSMIT-000064 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision of documents are incorrect,requested to resubmit: KPTG-IntCorr-000297 |  | 2026-04-21 | KPTG-IntCorr-000297 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-21 | Appselec-TRANSMIT-000066 | NA | Trade Partner | Control Cable Nexans Technical Data | 0 | 1 | 0 | NA | APPROVED | 2026-04-21 | WF-000157 | NA | 2026-04-24 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000551 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-21 | ARCST-TRANSMIT-000263 | NA | Trade Partner | Western Acoustic Wall Steel - Issued for Fabrication | 21 | 0 | 0 | NA | APPROVED | 2026-04-21 | WF-005390 | NA | 2026-05-06 |  |  | 2026-08-05 | 2026-08-05 | ⁠KPTG-TRANSMIT-020378 | Closed | 21 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-03-27 | Carr-TRANSMIT-000017 | NA | Consultant | 80% DD Architectural Drawing Issue- Finishes Schedule | 0 | 3 | 0 | NA | APPROVED | 2026-04-21 | WF-000028 | NA | 2026-04-28 |  | Aconex Review Voided, and Review Initiated on ACC as advised by DM |  | 2026-06-17 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-04-10 | WSP ANZ-TRANSMIT-000006 | NA | Consultant | WSP - 80% Tender Issue Drawings & Specifications (Electrical) | 0 | 1 | 0 | NA | APPROVED | 2026-04-21 | WF-000025 | NA | 2026-04-28 |  | Review Voided - The specification will be reviewed in ACC and re-initiated under ACC #188 |  | 2026-06-02 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-04-10 | WSP ANZ-TRANSMIT-000006 | NA | Consultant | WSP - 80% Tender Issue Drawings & Specifications Mechanical | 0 | 1 | 0 | NA | APPROVED | 2026-04-21 | WF-000027 | NA | 2026-04-28 |  | Review Voided - The specification will be reviewed in ACC and re-initiated under ACC #198 |  | 2026-06-02 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-03 | LML- WIP Package | NA | Consultant | Technical Specification New Lift Services | 0 | 1 | 0 | NA | APPROVED | 2026-06-03 | NA | 210 | 2026-06-09 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-21 | KETE-TRANSMIT-000042 | NA | Trade Partner | shop drawing updated-LOUVRE | 17 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 1231 | 2026-04-27 |  |  | 2026-04-09 | 2026-04-29 | KPTG-TRANSMIT-003596 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-15 | Civilex-TRANSMIT-000168 | NA | Trade Partner | Stage 3 - 22KVA Switch Room - Sample Submission Fire Rated Acrylic Caulking Sealant | 0 | 1 | 0 | NA | APPROVED | 2025-12-15 | WF-003603 |  |  |  |  | 2025-12-29 | 2025-12-18 | NXT-WTRAN-001291 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-21 | Emma's Email | NA | Trade Partner | GROUND FLOOR DOOR FRAME DETAILS | 40 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 1234 | 2026-04-27 |  |  | 2026-08-05 | 2026-08-06 | KPTG-TRANSMIT-004204 | Closed | 40 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-21 | DCN-TRANSMIT-000005 | NA | Trade Partner | M2S9 Link Bridge Structural IFC 01 Shop Drawings | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings , No review required |  | 2026-04-21 | KPTG-TRANSMIT-002338 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-21 | Appselec-TRANSMIT-000065 | NA | Trade Partner | ROIP Pack Tech Data IFA | 0 | 1 | 0 | NA | REJECTED | [5 empty] | WRONG ATTACHEMENT, REQUESTED TO RESUBMIT:KPTG-IntCorr-000298 |  | 2026-04-21 | KPTG-IntCorr-000298 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-15 | INGEN3D-TRANSMIT-000674 | NA | Trade Partner | I3D-378 Next DC M3 Stage 4 - Ground Floor Fuel Tank - MP0197, MP0198 & MP0199 - Revised IFA (15-12-2025) | 3 | 0 | 0 | NA | APPROVED | 2025-12-15 | WF-003601 | NA | 2026-01-08 |  |  | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-014051 | Open | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-21 | PCForm-TRANSMIT-000165 | NA | Trade Partner | 40mpa stair concrete mix for approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-21 | WF-000358 | NA | 2026-04-23 |  | submitted with Trn#160 pcf | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-001397 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-22 | RDSBIM-TRANSMIT-000268 | NA | Trade Partner | Fwd: NXM3S4 ¦ ROOF SWITCH ROOM BAFFLE LAYOUT | 1 | 0 | 0 | NA | APPROVED | [5 empty] | For Information drawing distributed to all | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-016296 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-21 | INGEN3D-TRANSMIT-000039 | NA | Trade Partner | Ground Floor (Level 1) - PC0120 & PC0123 - IFC | 2 | 0 | 0 | NA | APPROVED | 2026-04-21 | WF-000359 | NA | 2026-04-23 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-001341 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-21 | INGEN3D-TRANSMIT-000040 | NA | Trade Partner | Ground Floor (Level 1) - PC0097, PC0129 & PC0135 - Revised IFC | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Already processed (WF-000336) |  | 2026-04-21 | INGEN3D-IntCorr-000013 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-22 | D&E-TRANSMIT-000605 | NA | Trade Partner | SFN Pipe Prefab Plan - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-22 | WF-005393 | NA | 2026-05-13 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-21 | KPTG-IntCorr-000614 | NA | Trade Partner | First Nations Traditional Owners Insight Report | 0 | 1 | 0 | NA | APPROVED | 2026-04-21 | NA | 454 | 2026-04-24 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-21 | WAM-TRANSMIT-000752 | NA | Consultant | A40 Signage relocation elevation | 1 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 456 | 2026-04-24 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-001328 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-21 | TTW-TRANSMIT-000144 | NA | Consultant | BP1 - Construction Issue | 18 | 0 | 0 | NA | APPROVED | 2026-04-21 | NA | 458 | 2026-04-24 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-001382 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-15 | PCForm-TRANSMIT-000269 | NA | Trade Partner | Scaffold tie patching sample | 0 | 1 | 0 | NA | APPROVED | 2025-12-15 | WF - 000833 | NA | 2025-12-23 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-21 | PCForm-TRANSMIT-000166 | NA | Trade Partner | Ramp coupler as built | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | rejected |  | 2026-04-21 | KPTG-TRANSMIT-001291 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-15 | KPTG-WTRAN-000650 | NA | Trade Partner | Grouting Methodology - Precast | 0 | 2 | 0 | NA | APPROVED | 2026-04-21 | WF-000321 | NA | 2026-04-21 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-001275 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-21 | KPTG-WTRAN-000700 | NA | Trade Partner | Grouting Methodology - Precast | 0 | 1 | 0 | NA | APPROVED | 2026-04-21 | WF-000356 | NA | 2026-04-23 |  |  | 2026-04-21 | 2026-04-21 | KPTG-TRANSMIT-001287 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-22 | SMEPS-TRANSMIT-000193 | SPARK-CRFI-KPG-000504 | Trade Partner | Sub Mains Cable Schedule Revision C | 1 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 245 | 2026-04-29 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-000769 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-22 | D&E-TRANSMIT-000607 | NA | Trade Partner | Expansion Tanks & Auto Refill Units - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-04-22 | KPTG-TRANSMIT-016303 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-22 | LANSA-TRANSMIT-000104 | NA | Trade Partner | Level 15 Drainage IFC | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC only for distribution. |  | 2026-04-22 | KPTG-TRANSMIT-002911 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-22 | D&E-TRANSMIT-000608 | NA | Trade Partner | Leak Detection - Rev C - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-22 | WF-005399 | NA | 2026-05-18 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-016567 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-22 | Appselec-TRANSMIT-000067 | NA | Trade Partner | Comms Basket Tech Data IFC | 0 | 1 | 0 | NA | APPROVED | 2026-04-22 | WF-000158 | NA | 2026-04-23 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-000453 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-22 | Bianco-TRANSMIT-000065 | NA | Trade Partner | Re: Updated shop drawing - IFC | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Due to partial submission |  | 2026-04-22 | KPTG-TRANSMIT-016304 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-21 | Ayyan's Email - Building Permit | NA | Trade Partner | NO description | 0 | 6 | 0 |  | APPROVED | [5 empty] | Documents registered and transmitted to NEXTDC and Kapitol | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-003595 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-15 | DRLL-TRANSMIT-000050 | NA | Trade Partner | Battery Room Modules - Flooding Sensor Detector Tech Data | 0 | 1 | 0 | NA | APPROVED | 2025-12-15 | WF-000856 | NA | 2025-12-23 |  |  | 2026-01-05 | 2026-01-05 | KPTG-TRANSMIT-002251 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-22 | D&E-TRANSMIT-000609 | NA | Trade Partner | Insulation & Cladding - Rev B - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-22 | WF-005400 | NA | 2026-05-18 |  | The WF has been terminated and reinitiated via new template as requested by William. |  | 2026-04-24 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-22 | D&E-TRANSMIT-000234 | SPARK-CRFI-KPG-000497 | Trade Partner | SEISMIC DRAWINGS | 10 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | #246 | 2026-04-29 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-000922 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-22 | D&E-TRANSMIT-000612 | NA | Trade Partner | SFN - Air Vent - Rev B - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-22 | WF-005401 | NA | 2026-05-18 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-017426 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-22 | D&E-TRANSMIT-000610 | NA | Trade Partner | NXM3S4 - Level 1 - Mechanical Duct Layout Zones - Issued For Approval | 4 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 2941 | 2026-04-30 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-017774 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-22 | VERTIV-TRANSMIT-000003 | NA | Trade Partner | NEXT DC GE01 - ARCHITECTURAL DRAWINGS | 7 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 133 | 2026-04-30 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-000468 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-22 | SES AU-TRANSMIT-000015 | NA | Trade Partner | Re: TYPE J CABLE TECH DATA | 0 | 1 | 0 | NA | APPROVED | 2026-04-22 | WF-000160 | NA | 2026-04-28 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-000456 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-22 | M.S.-TRANSMIT-000005 | NA | Trade Partner | Joinery Shop drawings. | 9 | 0 | 0 | NA | REJECTED | [5 empty] | drawing status is missing |  | 2026-04-22 | KPTG-TRANSMIT-000673 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-22 | D&E-TRANSMIT-000611 | NA | Trade Partner | MaxCool & ANC Panel Drawings - Issued for Construction | 4 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 2943 | 2026-04-30 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-019470 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-22 | SES AU-TRANSMIT-000016 | NA | Trade Partner | Security tech data | 0 | 2 | 0 | NA | APPROVED | 2026-04-22 | WF-000161 | NA | 2026-04-28 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-000470 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-22 | D&E-TRANSMIT-000607 | NA | Trade Partner | Expansion Tanks & Auto Refill Units - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-04-22 | WF-005403 | NA | 2026-05-18 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-016894 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2025-12-15 | WEBBAUST-TRANSMIT-000063 | NA | Consultant | Webb HFF & Powerpack Test update | 10 | 0 | 0 | NA | APPROVED | 2025-12-15 |  | 258 | 2025-12-18 |  |  |  | 2025-12-16 | KAPITOL-TRANSMIT-000925 | Closed | 10 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-22 | Entire M-TRANSMIT-000030 | NA | Trade Partner | Mechanical Seismic Design IFA Rev A | 0 | 1 | 0 | NA | APPROVED | 2026-04-22 | WF - 000366 | NA | 2026-04-27 |  | NA | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000810 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-04-22 | NXT-TRANSMIT-001506 | NA | Trade Partner | Fwd: Stage 3 Switching Station Fire Risk Assessment under AS 2067 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-04-22 | KPTG-TRANSMIT-016315 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-22 | Appselec-TRANSMIT-000068 | NA | Trade Partner | MEL11C45 - COLO 4 Cell 3 - IFC Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-04-22 | WF-000162 | NA | 2026-04-27 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-000435 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-22 | VERTIV-TRANSMIT-000004 | NA | Trade Partner | NEXT DC GE01 - ELECTRICAL MATERIALS AND SHOP DRAWINGS SUBMISSION | 5 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 108 | 2026-04-28 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000452 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-22 | VERTIV-TRANSMIT-000004 | NA | Trade Partner | NEXT DC GE01 - ELECTRICAL MATERIALS AND SHOP DRAWINGS SUBMISSION | 0 | 3 | 0 | NA | APPROVED | 2026-04-22 | WF-000061 | NA | 2026-04-30 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-000519 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-22 | WilsonPD-TRANSMIT-000177 | NA | Trade Partner | Hydraulic Services - General Notes | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Different drawing status inside drawing and in aconex |  | 2026-04-22 | KPTG-TRANSMIT-000674 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-08 | D&E-TRANSMIT-000565 | NA | Trade Partner | NXM3S4 - Ground - CHW Pipe Layout Zones - Issued For Construction | 7 | 0 | 0 | NA | APPROVED | 2026-04-08 | NA | 2765 | 2026-04-22 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-016325 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-22 | SMEPS-TRANSMIT-000244 | NA | Trade Partner | SME - IFA SAMPLE SUBMISSION | 0 | 1 | 0 | NA | APPROVED | 2026-04-22 | WF-005404 | NA | 2026-05-13 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-017008 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-22 | Entire M-TRANSMIT-000035 | NA | Trade Partner | Mechanical pipework shop drawings IFC | 1 | 0 | 0 | NA | APPROVED | 2026-04-22 | WF-000163 | NA | 2026-04-24 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-09 | WilsonPD-TRANSMIT-000104 | NA | Trade Partner | Hot water circulating/return pumps | 0 | 1 | 0 | NA | APPROVED | 2026-04-10 | WF - 000992 | NA | 2026-04-15 |  | NA | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-002916 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-02 | TATE_-TRANSMIT-000027 | NA | Trade Partner | Iccons Strike Anchor Tech data for approval | 0 | 1 | 0 | NA | APPROVED | 2025-12-02 | WF-000822 | NA | 2025-12-12 |  |  | 2025-12-09 | 2025-12-09 | KPTG-TRANSMIT-002164 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-15 | Nilsen3-TRANSMIT-000120 | NA | Trade Partner | Nilsen - Stage 3 Level 1 Office As-builts | 10 | 0 | 0 | NA | APPROVED | [5 empty] | As-Builts, No review required. Updated and distributed to the Project Team. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-22 | D&E-TRANSMIT-000613 | NA | Trade Partner | NXM3S4 - Level 1 - Mechanical Duct Layout - Zone 1 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 2945 | 2026-04-30 |  | As instructed by Ellie , KPTG-IntCorr-013787 |  | 2026-05-26 | KPTG-IntCorr-013787. | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-22 | ZIA-TRANSMIT-000078 | NA | Trade Partner | Re: M3S4 Sample Data Submission | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-04-22 | KPTG-RFI-007463 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-22 | Bianco-TRANSMIT-000066 | NA | Trade Partner | Precast IFC | 67 | 0 | 0 | NA | APPROVED | 2026-04-22 | WF-005409 | NA | 2026-04-29 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018498 | Closed | 67 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-22 | PARR-TRANSMIT-000056 | NA | Trade Partner | Fuel Services - FUEL RETICULATION PUMP ROOM A&B | 2 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 1236 | 2026-04-28 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-003572 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-22 | D&E-TRANSMIT-000614 | NA | Trade Partner | UMG-800 Design Change Request - Issued for approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-22 | WF-005411 | NA | 2026-05-13 |  | as per requested by Eli salmon workflow is terminated and superseeded KPTG-IntCorr-012463 |  | 2026-04-29 | KPTG-IntCorr-012472 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-22 | PARR-TRANSMIT-000165 | NA | Trade Partner | Re: P2685 - NDC M3 - Stage 4 - Battery Rooms - BRIC MODBUS REGISTER | 0 | 1 | 0 | NA | APPROVED | 2026-04-23 | WF-005412 | NA | 2026-05-01 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-016757 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-22 | NXT-TRANSMIT-001508 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - BRIC MODBUS REGISTER | 1 | 0 | 0 | NA | APPROVED | 2026-04-22 | WF-005412 | NA | 2026-05-05 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-22 | ZIA-TRANSMIT-000079 | NA | Trade Partner | Re: M3S4 Sample Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-04-22 | WF-005413 | NA | 2026-05-06 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-016829 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-22 | SMEPS-TRANSMIT-000194 | SPARK-CRFI-KPG-000662 | Trade Partner | MTS (Manual Transfer Switch) - Terminal Box | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-000792 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-15 | DS-TRANSMIT-000081 | NA | Trade Partner | STAGE 4- IFC - HYDRAULIC & FIRE (INGROUNDS) - CONSULTANT REVIEW-SHOP DRAWING | 2 | 0 | 0 | NA | APPROVED | 2025-12-15 | NA | 1655 | 2025-12-22 |  | The workflow has been terminated as per requested by Charlie- ACC1655 |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-22 | VERTIV-TRANSMIT-000005 | NA | Trade Partner | NEXT DC GE01 - MECHANICAL MATERIAL AND SHOP DRAWING SUBMISSION | 1 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 110 | 2026-04-28 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000457 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-22 | VERTIV-TRANSMIT-000005 | NA | Trade Partner | NEXT DC GE01 - MECHANICAL MATERIAL AND SHOP DRAWING SUBMISSION | 0 | 1 | 0 | NA | APPROVED | 2026-04-22 | WF-000062 | NA | 2026-04-30 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000355 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-22 | WilsonPD-TRANSMIT-000178 | SPARK-CRFI-KPG-000199 | Trade Partner | Hydraulic Services - General Notes | 1 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | #247 | 2026-04-29 |  | Terminated as per Alex advise-KPTG-IntCorr-003463 |  | 2026-07-09 | KPTG-IntCorr-003463 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-22 | Nilsen3-TRANSMIT-000125 | NA | Trade Partner | PSUB & GENERATOR CONSUMER MAINS DETAILS | 1 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 2948 | 2026-04-29 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-018077 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-22 | WilsonPD-TRANSMIT-000179 | NA | Trade Partner | HYDRAULIC SERVICES - DRAINAGE LAYOUT - GROUND ZONE C | 1 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 248 | 2026-04-29 |  | Terminated as per Alex advice |  | 2026-05-25 | KPTG-IntCorr-003039 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-22 | KPTG-SADV-001039 | NA | Trade Partner | Paint sample sign off | 0 | 5 | 0 | NA | APPROVED | 2026-04-22 | WF - 000367 | NA | 2026-04-27 |  | NA | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000779 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-22 | SMEPS-TRANSMIT-000191 | NA | Trade Partner | ELECTRICAL - COLO 4 CELL 1 - PHASE 4 CONTAINMENT LAYOUT | 6 | 0 | 0 | NA | APPROVED | 2026-04-22 | WF - 000368 | NA | 2026-04-28 |  | NA | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-000765 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-22 | ADP-TRANSMIT-000051 | NA | Consultant | ADP Electrical Specification | 0 | 1 | 0 | NA | APPROVED | 2026-04-22 | NA | 114 | 2026-04-27 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-000674 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-22 | D&E-TRANSMIT-000606 | NA | Trade Partner | NXM3S2 - Level 01 - Mechanical Duct Layout Zones 3 & 4 - Issued For Approval | 2 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 4145 | 2026-05-01 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-017116 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-22 | ADP-TRANSMIT-000050 | NA | Consultant | ADP MEL4680 - CSMS Spec and schedule | 0 | 5 | 0 | NA | APPROVED | 2026-04-22 | NA | 116 | 2026-04-27 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-000670 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-12 | B Smart-TRANSMIT-000038 | NA | Consultant | 251211_Architectural Podium Facade IFC Update | 23 | 0 | 0 | KPTG-IntCorr-000268 | APPROVED | 2025-12-16 | WF-000101 | 179 | 2025-12-19 |  | Previous revision is at review; waiting for Waiting for Kapitol advise. KPTG-IntCorr-000268 |  | 2026-01-28 | KPTG-TRANSMIT-000357 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-22 | GHD-TRANSMIT-000007 | NA | Trade Partner | GE1 IFC Security Services Documentation | 17 | 2 | 0 | NA | APPROVED | 2026-04-22 | NA | 117 | 2026-04-27 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-000280 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-22 | ARCST-TRANSMIT-000265 | NA | Trade Partner | Stage 2 North West Stair IFC Shop Drawings | 21 | 0 | 0 | NA | REJECTED | [5 empty] | IFA revision not submitted, directly submitted IFC. |  | 2026-04-22 | KPTG-SADV-004965 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-22 | DS-TRANSMIT-000113 | NA | Trade Partner | HYD SITE - DRAINAGE | 1 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 4148 | 2026-05-05 |  | Terminated as advised by Charlie Johnstone for sending updated drawing. (KPTG-IntCorr-012985). | 2026-05-11 | 2026-05-11 | KPTG-IntCorr-012987 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-22 | HDRAus-TRANSMIT-000465 | NA | Consultant | SW PMJ details | 1 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 4149 | 2026-04-24 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016550 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-22 | NXT-TRANSMIT-001507 | NA | Client | PDU - CONTROL Latest drawings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with the document number and revision number. |  | 2026-04-22 | KPTG-DA-006122 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-22 | Stowe-A-TRANSMIT-000561 | NA | Trade Partner | STOWE - TECH DATA -IFC | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Previous version of the documents is revise and resubmit. |  | 2026-04-22 | KPTG-TRANSMIT-016376 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-22 | DS-TRANSMIT-000114 | NA | Trade Partner | GF and Roof Plant - Drainage Drawings - Re-issued for construction | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Revision issue, Mixed status submission. |  | 2026-04-22 | KPTG-DA-006123 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-22 | KPTG-TRANSMIT-016349 | NA | Trade Partner | SP5 - D & E - O&M Manual Review | 0 | 1 | 0 | NA | APPROVED | 2026-04-22 | WF-005418 | NA | 2026-05-05 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-017326 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-22 | HDRAus-TRANSMIT-000461 | NA | Consultant | Re: Link Corridor | 1 | 0 | 0 | NA | APPROVED | 2026-04-20 | NA | 2899 | 2026-04-22 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-016358 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-22 | Altaire-TRANSMIT-000104 | NA | Trade Partner | M3 S2 - Altaire - Handover Documentation | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with the submitted status and document number. IFC revision not submitted. |  | 2026-04-22 | KPTG-SADV-004966 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-15 | TTW-TRANSMIT-000046 | 280 | Consultant | STR Issue - L4, L5 + Sections and Details Updates | 19 | 0 | 0 | NA | APPROVED | 2026-01-16 | WF-000642 | 830 | 2025-12-17 |  | First created Review 750 dtd 15/12/2025 due to revised part drawings issued via procore re-issued again in Review 830 | 2026-01-28 | 2026-01-28 | KPTG-TRANSMIT-002607 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-22 | Baigents-TRANSMIT-000001 | NA | Trade Partner | Block 01 Dowel location plans IFA | 5 | 0 | 0 | NA | APPROVED | 2026-04-22 |  | 50 | 2026-04-28 |  | Requested by Zoe internal review requirerd | 2026-05-15 | 2026-05-15 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-22 | KPTG-TRANSMIT-000043-SCG | NA | Consultant | M3 Stage 6 - Main Works Issued for Tender - 02 | 58 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 48 | 2026-04-29 |  |  | 2026-05-13 | 2026-05-13 | NA | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-22 | 4DW-TRANSMIT-000028 | NA | Consultant | Structural Documentation: Piling Issued for Construction - Block 1 | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Old rev is under review |  | 2026-04-23 | KPTG-DA-000159 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-22 | Aurecon-TRANSMIT-000106 | NA | Consultant | MCSE Specifications & Schedules | 0 | 17 | 0 | NA | APPROVED |  | NA | NA |  |  | 8 Documents superseded by Aurecon-TRANSMIT-000107-9 documents are schedule |  |  | NA | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-22 | Auspan-TRANSMIT-000021 | NA | Trade Partner | Precast shop drawings for construction | 2 | 0 | 0 | NA | APPROVED | 2026-04-22 | WF-00006 | NA | 2026-04-29 |  |  | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-000200 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-22 | ARCH-TRANSMIT-000039 | NA | Trade Partner | IFI - Concrete Profile Plan - Roof & External Plant | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFI |  | 2026-04-22 | KPTG-TRANSMIT-000204 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-22 | JCBa-TRANSMIT-000099 | NA | Consultant | Structural Setout Plans IFC: 6th Floor Zone Plans | 5 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 768 | 2026-04-24 |  | Review voided as advised by Kapitol DM- "drawings will be superseded" | 2026-05-01 | 2026-05-01 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-22 | KETE-TRANSMIT-000015 | NA | Trade Partner | Kete - Zone 01 Shop Drawing Submission Rev 02 | 90 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 766 | 2026-04-29 |  | Review voided as advised by Kapitol PC- "These drawings are going to be superseded" | 2026-05-01 | 2026-05-01 | NA | Closed | 90 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-22 | Auspan-TRANSMIT-000229: | NA | Trade Partner | Re: Precast shop drawings missing PMJ and TMJ details | 7 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to a Drawing detail is overlapping with document number in the title block. KPTG-TRANSMIT-001458 |  | 2026-04-22 | KPTG-TRANSMIT-001458 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-22 | Auspan-TRANSMIT-000230 | NA | Trade Partner | : Re: Panel 0G2057 Size | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect drawing revisions in Aconex metadata. KPTG-TRANSMIT-001459 |  | 2026-04-22 | KPTG-TRANSMIT-001459 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-15 | TTW-TRANSMIT-000047 | 280 | Consultant | STR Issue - L4, L5 + Sections and Details Updates | 1 | 0 | 0 | NA | APPROVED | 2025-12-15 | NA | 750 | 2025-12-17 |  | review made void - new review 850 | 2026-01-14 | 2026-01-28 | KPTG-TRANSMIT-002607 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-22 | Auscool-TRANSMIT-000017 | NA | Trade Partner | Corridor O-A Penetrations Changes | 15 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 772 | 2026-04-29 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-001481 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-22 | Auscool-TRANSMIT-000018 | NA | Trade Partner | Ground Floor Zone 2 Penetration Rejection – Design Change Update Request | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - to be uploaded to ACC no review required. Distribute. KPTG-TRANSMIT-001446 |  | 2026-04-22 | KPTG-TRANSMIT-001446 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-22 | RBG-TRANSMIT-000060 | NA | Consultant | Latest Structural Drawings for Podium and Tower Steelwork - Issued for Construction | 17 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 426 | 2026-04-24 |  | Review void; drawings updated. | 2026-04-29 | 2026-04-29 | NA | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-22 | RDSBIM-TRANSMIT-000058 | NA | Trade Partner | 671CHP BASEMENT 2 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | [5 empty] | ACC & Aconex register updated. |  | 2026-04-22 | NA | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-22 | B Smart-TRANSMIT-000071 | NA | Consultant | Facade Blind Mullion | 6 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 429 | 2026-04-24 |  | Review Void. | 2026-06-11 | 2026-06-11 | NA | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-22 | WilsonPD-TRANSMIT-000106 | NA | Trade Partner | Potable Cold Tank Fill Valve | 0 | 1 | 0 | NA | APPROVED | 2026-04-22 | WF - 001001 | NA | 2026-04-28 |  | File supersede and WF terminated. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-27 | IGS--TRANSMIT-000034 | NA | Consultant | Revised Building Services Layouts | 13 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 634 | 2026-04-30 |  | Dwfx file is not shared, requested to submit :KPTG-SADV-003846 | 2026-04-30 | 2026-04-30 | KPTG-SADV-003964 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-22 | TGRF-TRANSMIT-000106 | NA | Trade Partner | MLC Pour 3B Updated Drawings | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC DRAWINGS, TRANSMITTED TO ALL CONCERNED PARTIES |  | 2026-04-22 | KPTG-TRANSMIT-002771 | Closed | 5 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-21 | SMEPS-TRANSMIT-000190 | NA | Trade Partner | TELECOMMUNICATIONS - LEVEL 2 COLO ADMIN PATHWAYS LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-04-21 | WF - 000362 | NA | 2026-04-24 |  | NA | 2026-04-22 | 2026-04-22 | KPTG-TRANSMIT-000764 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-21 | Highbu-TRANSMIT-000047 | NA | Trade Partner | HP - Sample046 - GF spark lane & L1 East entry trench grate & HP - Sample047 - GF entry & mezz showers tile insert trench grate | 0 | 2 | 0 | NA | APPROVED | 2026-04-22 | WF-000708 | NA | 2026-04-27 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-002419 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-12 | B Smart-TRANSMIT-000039 | NA | Consultant | B1 concrete profile IFC | 1 | 0 | 0 | NA | APPROVED | 2025-12-15 | WF-000099 | 175 | 2025-12-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-22 | PFP PL-TRANSMIT-000002 | NA | Trade Partner | Fire Protection Tech Data | 0 | 10 | 0 | NA | APPROVED | 2026-04-22 | WF-000524 | NA | 2026-04-24 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-002686 | Closed | 10 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-22 | SMEPS-TRANSMIT-000026 | NA | Trade Partner | M2 SME Sample Submissions | 0 | 8 | 0 | NA | APPROVED | 2026-04-22 | WF-000525 | NA | 2026-05-01 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-002976 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-22 | DCN-TRANSMIT-000006 | NA | Trade Partner | M2 Link Bridge - Window/Handrail/Service Gantry Grating Tech data | 0 | 2 | 0 | NA | APPROVED | 2026-04-22 | WF-000526 | NA | 2026-05-01 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-003919 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-22 | ASV-TRANSMIT-000054 | NA | Trade Partner | Civil Site Plan | 1 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 736 | 2026-04-30 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-002738 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-22 | PARR-TRANSMIT-000055 | NA | Trade Partner | Fuel Services - Cx PLAN & TEMPLATES | 0 | 1 | 0 | NA | APPROVED | 2026-04-22 | WF-001019 | NA | 2026-04-26 |  |  | 2026-05-12 | 2026-05-12 | KPTG-TRANSMIT-003662 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-22 | VAE-Grp-TRANSMIT-000155 | NA | Trade Partner | IFA - MECHANICAL - O&M MANUAL | 0 | 1 | 0 | KPTG-IntCorr-001209 | APPROVED |  | NA | NA |  |  | Clarification from harry - PDF version sent via VAE-Grp-TRANSMIT-000156 |  | 2026-04-27 | VAE-Grp-TRANSMIT-000156 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-22 | RDSBIM-TRANSMIT-000026 | NA | Trade Partner | LEVEL 03 CONCRETE PROFILE PLAN AND SECTIONS | 4 | 0 | 0 | NA | APPROVED | 2026-04-22 | WF-000362 | NA | 2026-04-29 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-22 | Firesafe-TRANSMIT-000002 | NA | Trade Partner | Fire Pump Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-04-22 | WF-000365 | NA | 2026-04-24 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-001399 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-22 | Firesafe-TRANSMIT-000001 | NA | Trade Partner | Schematic & L22 Calc Package | 1 | 0 | 0 | NA | REJECTED | [5 empty] | rejected |  | 2026-04-22 | KPTG-TRANSMIT-001299 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-22 | Jangho-TRANSMIT-000015 | NA | Trade Partner | 003_FT-07&FT-09 SYSTEM CONCEPT DRAWING-01 | 26 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 474 | 2026-04-30 |  | rejected- KPTG-TRANSMIT-001292 | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-001799 | Closed | 26 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-12 | B Smart-TRANSMIT-000042 | NA | Consultant | 251212_Architectural Tower Facade IFC Updates | 8 | 0 | 0 | KPTG-IntCorr-000270 | APPROVED | 2025-12-16 | WF-000102 | 181 | 2025-12-19 |  | Previous revision is under review. Waiting for Kapitol advise. KPTG-IntCorr-000270 |  | 2026-01-23 | KPTG-TRANSMIT-000324 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-22 | Jangho-TRANSMIT-000016 | NA | Trade Partner | 004-FT-07 & FT09 PODIUM VISUAL MOCK-UP SHOP DRAWING-01 | 17 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 463 | 2026-04-30 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-001661 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-23 | WPD-TRANSMIT-000083 | NA | Trade Partner | Re: Powerpack - Tech Data Submission | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-04-23 | DRAFT-009791 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-22 | Jangho-TRANSMIT-000017 | NA | Trade Partner | Structural Calculation for FT07& FT09 System Concept Drawing | 0 | 1 | 0 | NA | APPROVED | 2026-04-22 | WF-000367 | NA | 2026-04-27 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-001571 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-22 | RDSBIM-TRANSMIT-000027 | NA | Trade Partner | LEVEL 03 CONCRETE PROFILE PLAN AND SECTIONS | 4 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 465 | 2026-04-30 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-22 | PCForm-TRANSMIT-000167 | NA | Trade Partner | Ramp coupler as-built | 1 | 0 | 0 | NA | REJECTED | [5 empty] | rejected |  | 2026-04-22 | KPTG-TRANSMIT-001300 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-23 | RDSBIM-TRANSMIT-000059 | NA | Trade Partner | 671CHP GROUND LEVEL TO ROOF CORE WALL LAYOUT AND ELEVATION | 9 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 431 | 2026-04-30 |  | Review Voided by Kapitol PC. ; RDS to issue updated drawings as requested by them. | 2026-05-08 | 2026-05-08 | NA | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-22 | PCForm-TRANSMIT-000169 | NA | Trade Partner | Raft 1 - Pour Sequence for review | 2 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 467 | 2026-04-30 |  |  | 2026-04-30 | 2026-05-01 | KPTG-TRANSMIT-001481 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-22 | AFAC-TRANSMIT-000001 | NA | Trade Partner | Facade Access Strategy Report | 0 | 1 | 0 | NA | APPROVED | 2026-05-04 | WF-000429 | NA | 2026-05-06 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-002568 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-22 | TTW-TRANSMIT-000145 | NA | Consultant | Structural Documentation - Issued for Certification / Information | 1 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 469 | 2026-04-27 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-001393 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-23 | Appselec-TRANSMIT-000069 | NA | Trade Partner | COLO 4 - Comms Drawings (Pathways, CEI, Grounding & Drawing Index - IFA | 4 | 0 | 0 | NA | APPROVED | 2026-04-23 | WF-000164 | NA | 2026-04-29 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-000582 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-13 | HGP-TRANSMIT-000028 |  | Trade Partner | Transmittal- FT01 CURTAIN WALL SHOP DRAWING IFC | 66 | 0 | 0 | NA | REJECTED | [8 empty] | KPTG-TRANSMIT-000305 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-23 | SMEPS-TRANSMIT-000196 | SPARK-CRFI-KPG-000489 | Trade Partner | Distribution Boards DB-16, DB-02, DB-03, DB-04, DB-05, DB-11, DB-17 {B} | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000760 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-23 | Appselec-TRANSMIT-000070 | NA | Trade Partner | COLO 5 - Comms Drawings (Pathways, WIFI, CEI, Grounding, Phones, & Drawing Index) IFA | 11 | 0 | 0 | NA | APPROVED | 2026-04-23 | WF-000165) | NA | 2026-04-29 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-000576 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-23 | RDSBIM-TRANSMIT-000008 | NA | Trade Partner | MEL11C45 ¦ LEVEL 02 COLO 4 AREA PARTITION WALL LAYOUT | 3 | 0 | 0 | NA | APPROVED | 2026-04-23 | WF-000166 | NA | 2026-04-29 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000542 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-17 | KPTG-IntCorr-000601 | NA | Trade Partner | Ground Floor (Level 1) - PC0097, PC0129 & PC0135 - Revised IFC | 0 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | NA | 2026-04-24 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-001340 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-23 | Tradetec-TRANSMIT-000428 | NA | Trade Partner | Re: IFA - Stage 4 - CP40 CP32 CP20 CP29 | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect drawing title & previous revision for this document has already been received. |  | 2026-04-23 | KPTG-TRANSMIT-016382 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-23 | SKS Tech-TRANSMIT-000108 | NA | Trade Partner | M3S4 labels for approval | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 2952 | 2026-05-01 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-017878 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-23 | CRSol-TRANSMIT-000086 | NA | Trade Partner | M3S4 CRS CLN Drawings - Issued for Construction - Zones C1, C2 & C3 - II | 36 | 0 | 0 | NA | APPROVED | 2026-04-08 | NA | 2777 | 2026-04-23 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-016383 | Closed | 36 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-23 | SKS Tech-TRANSMIT-000107 | NA | Trade Partner | Penetration drawings for approval | 36 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 2950 | 2026-04-23 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-017806 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-23 | KPTG-WTRAN-009829 | NA | Trade Partner | Stage 4 - HAMES Review - Switch Room Spandek Cladding | 1 | 0 | 0 | NA | APPROVED | 2026-04-14 | NA | 2830 | 2026-04-23 |  | Review - requested by Karthik (ARC proline doc) | 2026-04-23 |  | KPTG-TRANSMIT-016385 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-23 | SMEPS-TRANSMIT-000252 | NA | Trade Partner | SME - IFA SAMPLE SUBMISSION | 0 | 1 | 0 | NA | APPROVED | 2026-04-23 | WF-005421 | NA | 2026-05-14 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-016856 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-15 | RDSBIM-TRANSMIT-000170 | NA | Trade Partner | NXM3S4 ¦ SITE HOIST-1 SETOUT LAYOUT | 1 | 0 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-23 | D&E-TRANSMIT-000621 | NA | Trade Partner | Retransmitted Design Criteria with revised doc numbr | 0 | 1 | 0 | KPTG-TRANSMIT-016393 | APPROVED | [5 empty] | IFC DOCUMENT advise seeked |  | 2026-04-24 | KPTG-TRANSMIT-016433 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-23 | PFP PL-TRANSMIT-000084 | NA | Trade Partner | Water Mist Pump Plinth Layout DWG IFA | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | 2954 | NA | 2026-05-01 |  | AS PER REQUESTED BY ELI WF IS TERMINATED KPTG-IntCorr-012492 |  | 2026-04-29 | KPTG-IntCorr-012498 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-23 | KPTG-WTRAN-009683 | NA | Trade Partner | M3 - S4 DOCUMENT CONTROL REVIEW - IFA SHOPDRAWING CONSULTANT REVIEW - HDR - HAMES-KAP - AS PER REQUEST BY KARTHIK | 1 | 0 | 0 | NA | APPROVED | 2026-04-08 | NA | 2771 | 2026-04-23 |  | AS PER REQUEST BY KARTHIK | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-016396 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-23 | SES AU-TRANSMIT-000017 | NA | Trade Partner | SCEC ALARM-Status Indicator | 0 | 1 | 0 | NA | APPROVED | 2026-04-23 | WF-000167 | NA | 2026-04-27 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-000459 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-23 | ASV-TRANSMIT-000053 | NA | Trade Partner | Stage 11 External HYD | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 738 | 2026-04-30 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-003419 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-23 | ASV-TRANSMIT-000055 | NA | Trade Partner | Stage 9 Penetration Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 739 | 2026-04-30 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-003423 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-23 | ASV-TRANSMIT-000056 | NA | Trade Partner | Stage 10 penetration | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 740 | 2026-04-30 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-003427 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-23 | ASV-TRANSMIT-000057 | NA | Trade Partner | Stage 11 Penetration | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 741 | 2026-04-30 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-003432 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-23 | D&E-TRANSMIT-000618 | NA | Trade Partner | Re: MCC Schedules IFA Rev G | 0 | 1 | 0 | NA | APPROVED | 2026-04-23 | WF-005423 | NA | 2026-05-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-23 | ASV-TRANSMIT-000050 | NA | Trade Partner | Stage 9 Internal HYD | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 742 | 2026-04-29 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-002734 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-13 | HGP-TRANSMIT-000029 | SPARK-CRFI-KPG-000068 | Trade Partner | TRANSMITTAL-IFC PMU SHOP DRAWING FT01 CW | 19 | 0 | 0 | NA | APPROVED | 2025-12-15 | WF-000107 | 73 | 2025-12-22 |  |  | 2026-05-11 | 2026-05-12 | KPTG-TRANSMIT-000856 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-23 | ASV-TRANSMIT-000051 | NA | Trade Partner | Stage 10 Internal HYD | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 743 | 2026-04-29 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-002729 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-23 | ASV-TRANSMIT-000052 | NA | Trade Partner | Stage 11 Internal HYD | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 744 | 2026-04-29 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-002725 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-23 | D&E-TRANSMIT-000235 | SPARK-CRFI-KPG-000315 | Trade Partner | MWYCCB - LEVEL 1 - PIPEWORK LAYOUT ZONE 6 & ZONE 7 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 249 | 2026-04-30 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000898 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-23 | GEMBA-D-TRANSMIT-000013 | NA | Consultant | External Plant Area ¦ For Construction | 7 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 123 | 2026-04-28 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-000255 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-23 | ELLISAIR-TRANSMIT-000009 | NA | Trade Partner | Technical Data Submission - Heat Exchangers | 0 | 1 | 0 | NA | APPROVED | 2026-04-23 | WF-000529 | NA | 2026-05-05 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-002812 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-23 | KPTG-IntCorr-000367 | NA | Trade Partner | Wet Fire Tech Data | 0 | 4 | 0 | NA | APPROVED | 2026-04-23 | WF - 000369 | NA | 2026-04-27 |  | NA | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-000770 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-23 | KALLIBRE-TRANSMIT-000006 - | NA | Trade Partner | Door by Door Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-04-23 | WF - 000371 | NA | 2026-04-28 |  | NA | 2026-05-15 | 2026-05-15 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-23 | WPD-TRANSMIT-000084 | NA | Trade Partner | Powerpack - Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-04-23 | WF-000485 | NA |  |  | As requested by Isaiah -Terminated |  |  | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-23 | Entire M-TRANSMIT-000036 | NA | Trade Partner | Mechanical BAS Layout shop drawings IFC | 10 | 0 | 0 | NA | APPROVED | 2026-04-23 | WF-000168 | NA | 2026-04-27 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-000487 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-23 | ZIA-TRANSMIT-000080 | NA | Trade Partner | M3S4 Datahall SLA & DP sensor Laytout (FOA-2) | 6 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 2960 | 2026-04-29 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-018551 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2025-12-02 | TATE_-TRANSMIT-000018 | NA | Trade Partner | Iccons Strike Anchor Tech data | 0 | 1 | 0 | NA | APPROVED | 2025-12-02 | WF-000167 |  | 2025-12-05 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-15 | HGP-TRANSMIT-000030 |  | Trade Partner | Re: Ground Floor: Window Wall Frames | 3 | 0 | 0 | NA | APPROVED | 2025-12-15 | WF-000105 | 71 | 2025-12-22 |  | Bim 360 review terminated by moj |  | 2026-06-29 | KPTG-TRANSMIT-001356 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-23 | WPD-TRANSMIT-000085 | NA | Trade Partner | Updated Hydraulic Layout - B08 - Ground Floor | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 402 | 2026-04-28 |  |  | 2026-04-24 | 2026-04-24 | DRAFT-009823 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-04-23 | ASV-TRANSMIT-000169 | NA | Trade Partner | Revised Sample - Double Check Valve | 0 | 1 | 0 | NA | APPROVED | 2026-04-23 | WF-005425 | NA | 2026-05-05 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016560 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-23 | D&E-TRANSMIT-000622 | NA | Trade Partner | Re: Functional Description - Issued for Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect discipline |  | 2026-04-23 | KPTG-RFI-007492 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-04-23 | TTW-TRANSMIT-000175 | NA | Trade Partner | Fwd: M3 Stage 3 Civil Drawings | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | The register has been updated. If any further action is required, the coordinator will inform. |  | 2026-04-23 | KPTG-TRANSMIT-016417 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-23 | KETE-TRANSMIT-000123 | NA | Trade Partner | Submission –sample register | 0 | 1 | 0 | NA | APPROVED | 2026-03-23 | WF-000679 | NA | 2026-03-25 |  |  | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-002268 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-23 | KETE-TRANSMIT-000123 | NA | Trade Partner | Submission –sample register | 0 | 1 | 0 | NA | APPROVED | 2026-03-23 | WF-000679 | NA | 2026-03-25 |  |  | 2026-04-22 | 2026-04-23 | KPTG-TRANSMIT-002271 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-25 | ARCST-TRANSMIT-000216 | NA | Trade Partner | C2 Cooling Tower - Roof & Secondary Steel - Issued for Approval | 0 | 0 | 0 | NA | APPROVED | 2026-02-25 | WF-004471 | NA | 2026-03-23 |  | balance 52 docs (ARCST-TRANSMIT-000216) | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-016418 | Closed | 52 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-23 | Auspan-TRANSMIT-000231 | NA | Trade Partner | Re Dowel Asbuilt. Update IFCed shop drawings. | 15 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - to be uploaded to ACC no review required. Distribute. |  | 2026-04-23 | KPTG-TRANSMIT-001480 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-23 | Auspan-TRANSMIT-000232 | na | Trade Partner | Precast shop drawing panel 1P5110 for approval. Zone 4, 5. | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 776 | 2026-04-30 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-001748 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-23 | Auspan-TRANSMIT-000233 | NA | Trade Partner | Precast shop drawings for approval. Zone 2, 3. | 45 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 780 | 2026-04-30 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-001673 | Closed | 45 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-15 | HGP-TRANSMIT-000031 | SPARK-CRFI-KPG-000068 | Trade Partner | Transmittal-IFC Shop Drawing FT01 Rev.A | 66 | 0 | 0 | NA | APPROVED | 2025-12-15 | WF-000106 | 72 | 2025-12-22 |  |  |  | 2026-01-29 | KPTG-TRANSMIT-000373 | Closed | 66 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-23 | Auspan-TRANSMIT-000234: | NA | Trade Partner | Precast shop drawings for approval. Zone 4, 5 | 85 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect attachment; Incomplete drawings number - RejectedKPTG-SADV-002084 |  | 2026-04-23 | KPTG-SADV-002084 | Closed | 85 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-23 | KETE-TRANSMIT-000016 | NA | Trade Partner | Kete - Zone 02 Shop Drawing Submission Rev 02 | 52 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 778 | 2026-04-30 |  | Review voided as advised by Kapitol PC- "These drawings are going to be superseded" | 2026-05-01 | 2026-05-01 | NA | Closed | 52 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-23 | Auspan-TRANSMIT-000235 | NA | Trade Partner | : Update panels 0G5040 and 0G4055 | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect drawings revision. Auspan need to fix. Rejected - KPTG-SADV-002083 |  | 2026-04-23 | KPTG-SADV-002083 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-23 | Auspan-TRANSMIT-000236 | NA | Trade Partner | : Re: Precast shop drawings missing PMJ and TMJ details. Update already IFCed shop drawings. | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - to be uploaded to ACC no review required. Distribute. KPTG-TRANSMIT-001468 |  | 2026-04-23 | KPTG-TRANSMIT-001468 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-23 | M.2-TRANSMIT-000023 | NA | Trade Partner | Electrical Services Level 1 Zone 1 penetration update | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 783 | 2026-04-30 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-001647 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-23 | Auscool-TRANSMIT-000020 | NA | Trade Partner | REFREGIRANT PIPEWORK PENETRATION - LEVEL 1, ZONE 2 | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 785 | 2026-04-30 |  | Review voided as advised by Kapitol PC Amee | 2026-04-27 | 2026-04-27 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-23 | LVPG-TRANSMIT-000031 | NA | Trade Partner | LVPG-HY-TECH-065 - CORRUGATED HDPE SN8 900mm | 0 | 1 | 0 | NA | APPROVED | 2026-04-23 | WF-000417 | NA | 2026-04-29 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-001535 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-23 | LGCE-TRANSMIT-000022 | NA | Trade Partner | IFC peno drawings rest of building | 3 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 433 | 2026-04-30 |  | Review void as advised by Kapitol Project PC. | 2026-04-29 | 2026-04-29 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-23 | D&E-TRANSMIT-000623 | NA | Trade Partner | ISSUED FOR APPROVAL - GROUND - MECHANICAL DUCT LAYOUT - ZONE 7 | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 2963 | 2026-05-01 |  |  |  | 2026-04-24 | KPTG-TRANSMIT-016458 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-15 | SMEPS-TRANSMIT-000095 | SPARK-CRFI-KPG-0000302 | Trade Partner | IFA - Ground Level Power & Comms & Communications Schematic | 8 | 0 | 0 | NA | APPROVED | 2025-12-15 | WF-000108 | 74 | 2025-12-22 |  |  | 2026-02-25 | 2026-02-25 | KPTG-TRANSMIT-000477 & KPTG-TRANSMIT-000549 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-23 | SCG2014-TRANSMIT-000010 | NA | Consultant | Physical security construction specification - restamped FC-1 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | No document number in the cover sheet | 2026-04-23 | 2026-04-23 | KPTG-DA-006150 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-23 | KPTG-TRANSMIT-016403 | NA | Trade Partner | Fan Wall Unit Steel | 96 | 0 | 0 | NA | APPROVED | 2026-04-23 | 005426 | NA | 2026-04-29 |  | As requested by Peter Z - WF terminated (as there is new drawings coming in) |  | 2026-05-12 | NA | Closed | 96 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-23 | Stowe-A-TRANSMIT-000562 | NA | Trade Partner | Stowe - Tech Data - IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | TD IFC |  | 2026-04-23 | KPTG-TRANSMIT-016427 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-23 | ADP-TRANSMIT-000052 | NA | Consultant | ADP MEL4680 - CMSM drawing update | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 126 | 2026-04-28 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-000412 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-04-23 | SCG2014-TRANSMIT-000005 | NA | Trade Partner | Physical security construction specification - restamped FC-1 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Andrew to confirm |  | 2026-04-24 | Awaiting approval | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-23 | Baigents-TRANSMIT-000002 | NA | Trade Partner | Block 01 - Level 01 Grid 4 Precast Beams IFA | 11 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 52 | 2026-04-30 |  | Voided-Needs to go through internal review |  | 2026-04-24 | NA | Closed | 11 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-23 | Aurecon-TRANSMIT-000107 | NA | Consultant | MCSE Specifications & Schedules | 0 | 8 | 0 | NA | REJECTED |  | NA | NA |  |  | wrong Naming conventions |  | 2026-04-27 | KPTG-DA-000153 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-23 | NXT-TRANSMIT-000363 | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 04 | 8 | 20 | 0 | KPTG-IntCorr-000072 | APPROVED | 2026-04-28 | NA | 54 | 2026-05-06 |  | 3 document submitted. 25 revised | 2026-05-27 | 2026-05-27 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-23 | DS-TRANSMIT-000115 | NA | Trade Partner | GF and Roof Plant - Drainage Drawings - Re-issued for construction | 2 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 4151 | 2026-04-30 |  |  | 2026-06-12 | 2026-06-12 | KPTG-TRANSMIT-018576 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-23 | ADP-TRANSMIT-000054 | NA | Consultant | ADP MEL4680 - Mechanical Specification | 0 | 1 | 0 | NA | APPROVED | 2026-04-23 | NA | 129 | 2026-04-28 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-000666 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-15 | crossfir-TRANSMIT-000043 | NA | Trade Partner | Wet Fire - Level 02, IFC | 2 | 0 | 0 | NA | APPROVED |  | N | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-23 | Hames-TRANSMIT-000154 | NA | Consultant | Revisions re internal markup | 16 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 1238 | 2026-04-27 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-003510 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-23 | ADP-TRANSMIT-000053 | NA | Consultant | Drawing NLIU | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | NLIU |  | 2026-04-23 | KPTG-TRANSMIT-000215 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-23 | Auspan-TRANSMIT-000022 | NA | Consultant | Precast shop drawings for construction. | 11 | 0 | 0 | NA | APPROVED | 2026-04-23 | WF-000072 | NA | 2026-04-28 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-000242, KPTG-TRANSMIT-000247 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-23 | WilsonPD-TRANSMIT-000180 | NA | Trade Partner | Grates for Approval | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Revision number is missing |  | 2026-04-23 | KPTG-TRANSMIT-000681 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-23 | ARCST-TRANSMIT-000266 | NA | Trade Partner | Stage 2 Admin Roof South Screen IFA Drawings | 11 | 0 | 0 | NA | APPROVED | 2026-04-23 | WF-005429 | NA | 2026-05-12 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-017359 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-23 | Auspan-TRANSMIT-000023 | NA | Trade Partner | Precast fish plate for connection between panels PP088 and PP074 | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | WF-000073 | NA | 2026-04-29 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000351 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-02-13 | ARCST-TRANSMIT-000207 | NA | Trade Partner | C2 Switchroom Upper Gantry Primary Steel - IFC Shop Drawings | 0 | 0 | 0 | NA | APPROVED | 2026-02-13 | WF-004267 |  | 2026-03-11 |  | The existing workflow WF-004239 has been terminated and reinitiated via the IFA template, as requested by Lola W. | 2026-04-23 | 2026-04-23 | KPTG-TRANSMIT-016413 | Closed | 41 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-23 | Appselec-TRANSMIT-000072 | NA | Trade Partner | MEL11C45 - COLO 4 Cell 4 & Overall Plans IFC Drawings (Retransmittal) | 12 | 0 | 0 | NA | APPROVED | 2026-04-23 | WF-000169 | NA | 2026-04-29 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-000477 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-23 | Appselec-TRANSMIT-000071 | NA | Trade Partner | MEL11C45 - COLO 4 Cell 4 & Overall Plans IFC Drawings | 12 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings title is incorrect, requested to resubmit:KPTG-IntCorr-000300 |  | 2026-04-23 | KPTG-IntCorr-000300 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-23 | VIA Arch-TRANSMIT-000098 | NA | Consultant | M2 S9-11 CD05 Design Amendment GF & S11 L2 & Above | 15 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 747 | 2026-04-28 |  | Actual receipt date 20/04 | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-002594 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2025-11-25 | M.2-TRANSMIT-000077 | NA | Trade Partner | levels 1 & 2 revised townhouse lighting | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-23 | VIA Arch-TRANSMIT-000099 | NA | Consultant | Architectural Documentation Building Permit Drawings | 31 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 748 | 2026-04-28 |  | Actual Receipt date 20/04 | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-002306 | Closed | 31 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-23 | VIA Arch-TRANSMIT-000101 | NA | Consultant | STAGE 11 LIFT CORE UPDATES | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 753 | 2026-04-28 |  | Actual receipt Date 20/4 | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-002626 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-23 | VIA Arch-TRANSMIT-000102 | NA | Consultant | Stage 9 Concrete Profile Plan L1 & Stage 9 Lift Core | 2 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 754 | 2026-04-28 |  | Actual receipt date 21/04 | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-002364 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-23 | VIA Arch-TRANSMIT-000103 | NA | Consultant | S11 Ground Floor Concrete Profile Plan | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 755 | 2026-04-28 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-002386 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-23 | VIA Arch-TRANSMIT-000104 | NA | Consultant | S9 Door Schedule | 4 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 756 | 2026-04-28 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-002395 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-23 | VIA Arch-TRANSMIT-000105 | NA | Consultant | M2 S9 - Ground Floor Concrete Profile Plan | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 757 | 2026-04-28 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-002647 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-24 | WPD-TRANSMIT-000084 | NA | Trade Partner | Powerpack - Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-04-23 | WF-000487 | NA |  |  | As per Isaiah -WF reinitiated and skipped SCP step | 2026-04-28 | 2026-04-28 | WPD-TRANSMIT-000083 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-24 | LANSA-TRANSMIT-000105 | NA | Trade Partner | Roof Drainage IFC - LANSA-TRANSMIT-000105 | 2 | 0 | 0 | NA | APPROVED | [5 empty] | IFC distribution only. |  | 2026-04-24 | KPTG-TRANSMIT-002920 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-24 | SMEPS-IntCorr-000142 | NA | Trade Partner | Copper ITP sheets MEL05 | 0 | 1 | 0 | NA | APPROVED | 2026-04-24 | WF - 000375 | NA | 2026-04-29 |  | NA | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000782 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-24 | Entire M-TRANSMIT-000032 | NA | Trade Partner | Commissioning Management Plan Issued For Construction | 0 | 1 | 0 | NA | APPROVED | 2026-04-24 | WF - 000376 | NA | 2026-04-28 |  | NA | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-000772 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-15 | OveArup-TRANSMIT-000141 | NA | Trade Partner | M3 Stage 3 Earthing Study Report | 0 | 1 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-24 | NXT-TRANSMIT-001511 | NA | Trade Partner | Fwd: M3 Stage 4 FAT reports (Batch 2) | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-24 | KPTG-TRANSMIT-016432 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-23 | INGEN3D-TRANSMIT-000042 | NA | Trade Partner | Ground Floor-Level 1 - MP0043 - No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No longer in use - Register updated - Send to all parties |  | 2026-04-23 | KPTG-TRANSMIT-001325 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-24 | D&E-TRANSMIT-000609 | NA | Trade Partner | Insulation & Cladding - Rev B - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-22 | WF-005432 | NA | 2026-05-20 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-016762 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-23 | INGEN3D-TRANSMIT-000041 | NA | Trade Partner | Ground Floor-Level 1 - Precast Columns - Revised IFC | 83 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Register Updated |  | 2026-04-23 | Register Updated | Closed | 83 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-23 | Jangho-TRANSMIT-000020 | NA | Trade Partner | FT01&FT02 PMU Comparison Report | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | WF-000370 | NA |  |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-001377 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-23 | Jangho-TRANSMIT-000019 | NA | Trade Partner | FT07&FT09 PMU Comparison Report | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | WF-000371 | NA |  |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-001375 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-24 | WilsonPD-TRANSMIT-000181 | SPARK-CRFI-KPG-000648 | Trade Partner | Grates for Approval | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-000993 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-23 | ArcadiaL-TRANSMIT-000005 | NA | Trade Partner | Landscape Architectural Updates - Minor ACC Design Coordination Issues | 3 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 476 | 2026-04-27 |  | 1 DWG REVISED ArcadiaL-TRANSMIT-000007 - SO SUBMITTED TOGETHER | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-001535 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-23 | ArcadiaL-TRANSMIT-000006 | NA | Trade Partner | Landscape Architectural Updates - Client Updates | 9 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | rejected |  | 2026-04-23 | KPTG-TRANSMIT-001327 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-15 | Entire M-TRANSMIT-000015 | NA | Trade Partner | BMS Drawings, Points List & Functional Description | 3 | 0 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-23 | ArcadiaL-TRANSMIT-000007 | NA | Trade Partner | Landscape Architectural Updates - Client Updates | 2 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 476 | 2026-04-27 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-001540 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-23 | Jangho-TRANSMIT-000021 | NA | Trade Partner | 003_FT-07&FT-09 SYSTEM CONCEPT DRAWING-01 | 4 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 474 | 2026-04-30 |  | 1 DWG REVISED ArcadiaL-TRANSMIT-000005 - SO SUBMITTED TOGETHER | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-001801 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-24 | NXT-TRANSMIT-001510 | NA | Trade Partner | Fwd: P2680 - NDC M3 Stage 4 - Fuel - BFS CACO | 1 | 0 | 0 | NA | APPROVED | 2026-04-24 | WF-005431 | NA | 2026-05-04 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-24 | HDRAus-TRANSMIT-000468 | NA | Consultant | Re: M3 Stage 4 - Document upload - GAs and Fire Egress Plans - PDF and CAD | 6 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due to incorrect revision |  |  |  | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-24 | D&E-TRANSMIT-000624 | NA | Trade Partner | Fans - Rev C - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-24 | WF-005433 | NA | 2026-05-07 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-017382 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-23 | Firesafe-TRANSMIT-000003 | NA | Trade Partner | FIRE SERVICES - SCHEMATIC | 1 | 0 | 0 | NA | APPROVED | 2026-04-23 | NA | 471 | 2026-04-30 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-001527 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-24 | Nilsen3-TRANSMIT-000126 | NA | Trade Partner | Re: TYPICAL NEUTRAL EARTHING SCHEMATIC DRAWINGS FOA | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect Ref. No |  | 2026-04-24 | KPTG-RFI-007507 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-24 | Stowe-A-TRANSMIT-000563 | NA | Trade Partner | Stowe - Tech Data - IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | TD IFC, Distribution only. |  | 2026-04-24 | KPTG-TRANSMIT-016450 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-12 | KPTG-TRANSMIT-002282 | 278 | Consultant | CSMS OUTLINED SPEC MASTER POINTS LIST NEXTDC E&D MAH REV 3.4 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Excel file - Register updated and sent to all parties |  | 2025-12-15 | KPTG-TRANSMIT-002283 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-24 | SKS Tech-TRANSMIT-000109 | NA | Trade Partner | Busduct Layout Data HallsING | 4 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 2965 | 2026-05-04 |  |  |  | 2026-04-24 | KPTG-TRANSMIT-016459 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-24 | MEPS-TRANSMIT-000194 | NA | Trade Partner | TELECOMMUNICATIONS - LEVEL 2 COLO ADMIN PATHWAYS LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-04-24 | WF - 000377 | NA | 2026-04-29 |  | NA | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-000864 | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-24 | D&E-TRANSMIT-000236 | SPARK-CRFI-KPG-000313 | Trade Partner | MWYCCB - GROUND LEVEL - PIPEWORK LAYOUT ZONE 1 & ZONE 3 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 250 | 2026-05-01 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000900 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-24 | SMEPS-TRANSMIT-000192 | NA | Trade Partner | TELECOMMUNICATIONS - SITE TELECOMS VAULT CABLE ROUTING LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-04-24 | WF - 000374 | NA | 2026-04-29 |  | NA | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000783 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-24 | SMEPS-TRANSMIT-000194 | NA | Trade Partner | TELECOMMUNICATIONS - LEVEL 2 COLO ADMIN PATHWAYS LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-04-24 | WF - 000377 | NA | 2026-04-29 |  | NA | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-000805 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-24 | D&E-TRANSMIT-000237 | SPARK-CRFI-KPG-000313 | Trade Partner | MWYCCB - GROUND LEVEL - PIPEWORK LAYOUT ZONE 2 & ZONE 4 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 251 | 2026-05-01 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000902 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-24 | Stowe-A-TRANSMIT-000564 | NA | Trade Partner | Stowe - Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-04-24 | WF-005435 | NA | 2026-05-06 |  |  | 2026-05-12 | 2026-05-12 | KPTG-TRANSMIT-017197 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-24 | Nilsen3-TRANSMIT-000127 | NA | Trade Partner | TYPICAL NEUTRAL EARTHING SCHEMATIC DRAWINGS FOA | 1 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 2967 | 2026-05-04 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-018007 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-24 | SIL-TRANSMIT-000024 | NA | Trade Partner | Documents Missed to Transmit | 0 | 2 | 0 | NA | APPROVED | 2026-03-29 | WF-000100 | NA | 2026-04-04 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-000439 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-25 | SIL-TRANSMIT-000025 | NA | Trade Partner | Re: Documents Missed to Transmit | 0 | 1 | 0 | NA | APPROVED | 2026-03-29 | WF-000101 | NA | 2026-04-04 |  |  | 2026-04-24 | 2026-04-24 | KPTG-TRANSMIT-000442 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-15 | StantecA-TRANSMIT-000287 | NA | Consultant | Updated IFC Documents - Mechanical- Stantec | 53 | 0 | 0 | NA | APPROVED | 2025-12-15 | WF-000102 | 205 | 2025-12-18 |  |  |  | 2025-12-17 | KPTG-TRANSMIT-000355 | Closed | 53 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-24 | Stowe-A-TRANSMIT-000566 | NA | Trade Partner | Stowe - Tech Data - Busduct Rain hood - ASF-021-TYPE-2 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Mismatch in the revision number inside the document and Aconex. |  | 2026-04-24 | KPTG-SADV-005010 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-24 | PARR-TRANSMIT-000166 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - CLIENT DWGS | 4 | 0 | 0 | NA | APPROVED | 2026-04-24 | WF-005439 | NA | 2026-04-24 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-017022 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-24 | Stowe-A-TRANSMIT-000567 | NA | Trade Partner | Re: Stowe - Tech Data Submission - Busduct Rainhood Type 1 | 0 | 1 | 0 | NA | APPROVED | 2026-04-24 | WF-005440 | NA | 2026-05-06 |  |  | 2026-05-18 | 2026-05-13 | KPTG-TRANSMIT-017260 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-24 | Stowe-A-TRANSMIT-000568 | NA | Trade Partner | Re: Stowe - Tech Data Submission - Busduct Rain Hood - Type 2 | 0 | 1 | 0 | NA | APPROVED | 2026-04-24 | WF-005441 | NA | 2026-05-06 |  |  | 2026-05-18 | 2026-05-13 | KPTG-TRANSMIT-017260 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-24 | Auspan-TRANSMIT-000237 | NA | Trade Partner | Update marking plan zone 3 level 3 | 1 | 0 | 0 | KPTG-IntCorr-000520 | APPROVED | 2026-05-06 | NA | 900 | 2026-05-13 |  | Prev. rev. is in review, waiting for advice - KPTG-IntCorr-000517. Wait until the review is completed - KPTG-IntCorr-000520 | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-001877 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-24 | WilsonPD-TRANSMIT-000018 | NA | Trade Partner | Penetration Drawings for Approval | 3 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 760 | 2026-05-01 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-002564 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-24 | RDSBIM-TRANSMIT-000049 | NA | Trade Partner | GREYSTAR GROUND FLOOR CONCRETE PROFILE PLAN ZONE 5 | 2 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 792 | 2026-04-29 |  | Review Voided as requested by RDS to issue an updated drawing | 2026-04-24 | 2026-04-24 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-24 | Tradetec-TRANSMIT-000116 | NA | Trade Partner | HVP11 Pit Shop Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 761 | 2026-05-01 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-002690 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-24 | WGAVIC-TRANSMIT-000009 | NA | Consultant | Civil Package IFC | 24 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 136 | 2026-04-29 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-000259 | Closed | 24 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-24 | WilsonPD-TRANSMIT-000183 | SPARK-CRFI-KPG-000510 | Trade Partner | Hydraulic Services - Drainage Layout - Level 1 - Zone A, B, C & D | 4 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 252 | 2026-05-01 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-000749 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-15 | PARR-TRANSMIT-000025 | NA | Trade Partner | Fuel Services - LOWER GROUND SECTIONS | 6 | 0 | 0 | NA | APPROVED | 2025-12-15 | NA | 752 | 2025-12-18 |  |  | 2026-01-13 | 2026-01-13 | KPTG-TRANSMIT-002390 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-24 | ADP-TRANSMIT-000056 | NA | Consultant | DRAWINGS NLIU - NEW DRAWING NUMBERS WILL BE ISSUED | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | NLIU |  | 2026-04-24 | KPTG-TRANSMIT-000225 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-24 | KPTG-TRANSMIT-002922 | NA | Trade Partner | Tech data & samples: Curtains & Blinds | 0 | 6 | 0 | NA | APPROVED | 2026-04-24 | WF - 001004 | NA | 2026-05-08 |  | File supersede and WF terminated. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-24 | vdmcons-TRANSMIT-000132 | NA | Trade Partner | ME25 1004: D114 511-537 Sydney Rd Coburg - Shop Drawings & 3D IFC Model - L09 Terrace Steel Frames - 2026-04-24 | 28 | 0 | 0 | NA | APPROVED | 2026-04-24 | WF - 001003 | NA | 2026-04-30 |  | File supersede and WF terminated. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-24 | D&E-TRANSMIT-000625 | NA | Trade Partner | ISSUED FOR APPROVAL - GROUND - MECHANICAL DUCT LAYOUT - ZONE 5 | 1 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 2970 | 2026-05-04 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-017705 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-24 | Entire M-TRANSMIT-000037 | NA | Trade Partner | Mechanical Cover sheet IFC | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status of drawing is incorrect, requested to resubmit:KPTG-IntCorr-000304 |  | 2026-04-24 | KPTG-IntCorr-000304 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-24 | WilsonPD-TRANSMIT-000019 | NA | Trade Partner | Water Storage Tanks Tech Data Submission | 0 | 3 | 0 | NA | APPROVED | 2026-04-24 | WF-000552 | NA | 2026-05-05 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-002777 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-24 | Entire M-TRANSMIT-000038 | NA | Trade Partner | Mechanical detail drawing IFA | 1 | 0 | 0 | NA | APPROVED | 2026-04-24 | WF-000284 | NA | 2026-04-30 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-000809 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-24 | PARR-TRANSMIT-000167 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - SCHEMATICS & CP | 3 | 0 | 0 | NA | APPROVED | 2026-04-24 | WF-005443 | NA | 2026-05-04 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018466 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-24 | POTTSENG-TRANSMIT-000024 | NA | Trade Partner | GMAC HYDRAULIC SERVICES - PENETRATION - GROUND - ZONE 1,3,4 LAYOUTS | 3 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 794 | 2026-04-29 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-001641 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-24 | ADP-TRANSMIT-000057 | NA | Consultant | DRAWINGS NLIU - NEW DRAWING NUMBERS WILL BE ISSUED | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | NLIU |  | 2026-04-24 | KPTG-TRANSMIT-000232 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-02 | PARR-TRANSMIT-000045 | NA | Trade Partner | M3 S1 DH7&8 - Fuel - DIESEL FUEL SYSTEM FUNCTIONAL DESCRIPTION | 0 | 2 | 0 | NA | APPROVED | 2025-12-02 | WF-000821 | NA | 2025-12-10 |  |  | 2025-12-17 | 2025-12-17 | KPTG-TRANSMIT-002209 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-15 | PARR-TRANSMIT-000026 | NA | Trade Partner | Fuel Services - LOWER GROUND SECTIONS - IFC | 2 | 0 | 0 | KPTG-IntCorr-000806 | APPROVED |  | NA | NA |  |  | As per KPTG-IntCorr-000802 - Updated registers - (Clarifications requested via KPTG-IntCorr-000806 regarding ACC internal review) ref PARR-TRANSMIT-000030 |  | 2026-02-05 | KPTG-TRANSMIT-002710 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-24 | Auspan-TRANSMIT-000240 | NA | Trade Partner | Resubmit precast shop drawings for approval. Ground floor and level 1 | 12 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 789 | 2026-04-29 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-001666 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-24 | PARR-TRANSMIT-000168 | NA | Trade Partner | Re: P2685 - NDC M3 - Stage 4 - Battery Rooms - SCHEMATICS- IFA | 2 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-04-24 | KPTG-TRANSMIT-016474 | Open | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-24 | WilsonPD-TRANSMIT-000182 | NA | Trade Partner | Hydraulic Services - Level 1 - Zone A & B - Penetration Layouts | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Partial submission |  | 2026-04-24 | KPTG-SADV-004348 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-24 | D&E-TRANSMIT-000626 | NA | Trade Partner | Re: ISSUED FOR APPROVAL - GROUND - MECHANICAL DUCT LAYOUT - ZONE 7 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | This document has already been submitted under a previous transmittal D&E-TRANSMIT-000625 |  | 2026-04-24 | KPTG-RFI-007525 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-24 | 4DW-TRANSMIT-000029 | NA | Consultant | Structural Documentation: Block 2 & Block 3 Ground floor issued for Certification, Block 1 Ground floor issued with construction updates. | 13 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Old Rev is under review |  | 2026-04-24 | KPTG-DA-000158 | Closed | 13 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-24 | 4DW-TRANSMIT-000030 | NA | Consultant | Issued for Certification: Ground Floor Zone 2 Slab | 11 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Old Rev is under review |  | 2026-04-24 | KPTG-DA-000157 | Closed | 11 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-24 | 4DW-TRANSMIT-000031 | NA | Consultant | Issued for Certification: Ground Floor Zone 3 Slab | 8 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Old rev is under review |  | 2026-04-24 | KPTG-DA-000156 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-24 | HDRAus-TRANSMIT-000085 | NA | Consultant | M3 Stage 6 - Town Planning Updates - Revised Retaining Wall | 33 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Old rev is under review |  | 2026-04-24 | KPTG-DA-000155 | Closed | 33 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-24 | Entire M-TRANSMIT-000039 | NA | Trade Partner | Construction Management Plan Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-04-24 | WF-000171 | NA | 2026-04-29 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-000597 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-24 | SES AU-TRANSMIT-000018 | NA | Trade Partner | CAMERA INDOOR DOME-IFC | 0 | 1 | 0 | NA | REJECTED | [5 empty] | UPDATED SUBSTITUTION FORM IS NOT AVAILABLE, REQUESTED TO RESUBMIT:KPTG-IntCorr-000305 |  | 2026-04-24 | KPTG-IntCorr-000305 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-15 | KARE-TRANSMIT-000074 | NA | Trade Partner | Correct data sheet for SMP-025 | 0 | 1 | 0 | NA | APPROVED | 2025-12-15 | WF-000834 | NA | 2025-12-22 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-24 | Stowe-A-TRANSMIT-000565 | NA | Trade Partner | Stowe - Tech Data - Busduct Rain hood - ASF-021-TYPE-1 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with revision |  | 2026-04-24 | KPTG-SADV-005009 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-24 | TTW-TRANSMIT-000176 | NA | Consultant | M3 Stage 2 Civil Drawings | 20 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with status and revision history |  | 2026-04-24 | KPTG-DA-006180 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-24 | ARCH-TRANSMIT-000040 | NA | Consultant | 2026.04.24_Issued for Construction (FC-01) | 67 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-04-24 | KPTG-DA-000560 | Closed | 67 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-24 | WAM-TRANSMIT-000753 | NA | Consultant | FIRE SERVICES - SCHEMATIC | 4 | 0 | 0 | NA | APPROVED | 2026-04-24 |  | 478 | 2026-04-27 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-001460 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-24 | Firesafe-TRANSMIT-000004 | NA | Trade Partner | FIRE SERVICES - Tech Data and Sample / Procurement Register | 0 | 15 | 0 | NA | APPROVED | 2026-04-24 | WF-000375 |  | 2026-04-27 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-001509 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-24 | KPTG-IntCorr-000622 | NA | Consultant | DL - First Nations Traditional Owners Insight Report | 0 | 2 | 0 | NA | APPROVED | 2026-04-24 | WF-000373 |  | 2026-04-27 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-001796 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-24 | TTW-TRANSMIT-000146 | NA | Consultant | BP8 - Issued for Construction | 5 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 480 | 2026-04-27 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-001687 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-24 | TTW-TRANSMIT-000147 | NA | Consultant | BP2a - Issue for construction | 2 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 482 | 2026-04-27 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-001365 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-24 | INGEN3D-TRANSMIT-000043 | NA | Trade Partner | Level 1-3 - Precast Columns - Revised IFC | 60 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | QA VERIFIED REGISTER UPDATED |  | 2026-04-24 | NA | Closed | 60 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-24 | INGEN3D-TRANSMIT-000044 | NA | Trade Partner | Level 2-4 - Precast Columns - Revised IFC | 19 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | QA VERIFIED REGISTER UPDATED |  | 2026-04-24 | NA | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-15 | Hames-TRANSMIT-000089 | NA | Consultant | Latest Revision - Wall Schedules, Sections and Details | 7 | 0 | 0 | NA | APPROVED | 2025-12-16 | WF-000668 | 758 | 2025-12-19 |  | KPTG-TRANSMIT-002287 - Rejected - QA error for 2 drawings | 2025-12-18 | 2025-12-18 | KPTG-TRANSMIT-002335 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-24 | INGEN3D-TRANSMIT-000045 | NA | Trade Partner | District Living - Key Plans - IFC | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | QA VERIFIED REGISTER UPDATED |  | 2026-04-24 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-24 | INGEN3D-TRANSMIT-000046 | NA | Trade Partner | District Living - Key Plan (MP0001) - No longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | NO LONGER IN USE - UPDATED |  | 2026-04-24 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-24 | VIA Arch-TRANSMIT-000107 | NA | Consultant | M2 - BRIDGE LINK - BUILDING PERMIT ISSUE | 7 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 763 | 2026-04-29 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-002651 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-24 | Hames-TRANSMIT-000155 | NA | Consultant | Update HV Room Spacials | 1 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 1240 | 2026-04-28 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-003581 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-24 | Hames-TRANSMIT-000156 | NA | Consultant | Updated Keynote Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-04-24 | NA | 1241 | 2026-04-28 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-003931 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-24 | CLADC-TRANSMIT-000022 | NA | Trade Partner | Re: Updated door shop drawings | 26 | 0 | 0 | NA | REJECTED | [5 empty] | Title of drawings are incorrect, requested to resubmit: KPTG-SADV-004166 |  | 2026-04-24 | KPTG-SADV-004166 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-24 | 4DW-TRANSMIT-000175 | NA | Consultant | Structural Documentation - Landscaping & Operable Wall updates | 5 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 210 | 2026-04-29 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-002904 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-24 | CTAGroup-TRANSMIT-000005 | NA | Trade Partner | Re: Fencing dimensioning for Sout East Footings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Zip file submitted, request to split zip flle and transmit them.KPTG-SADV-004170 |  | 2026-04-24 | KPTG-SADV-004170 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-24 | Auspan-TRANSMIT-000238 | NA | Trade Partner | Re: Update panels 0G5040 and 0G4055 | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - uploaded to ACC no review required. Distribute. |  | 2026-04-24 | KPTG-TRANSMIT-001484 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-24 | Auspan-TRANSMIT-000239 | NA | Trade Partner | Precast shop drawings for construction. | 11 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - uploaded to ACC no review required. Distribute. |  | 2026-04-24 | KPTG-TRANSMIT-001487 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-15 | SKS Tech-TRANSMIT-000106 | NA | Trade Partner | for construction submittals | 0 | 127 | 0 | NA | APPROVED |  | NA | NA |  |  | QA Checked - Register updated |  |  |  | Closed | 127 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-24 | INDS-TRANSMIT-000019 | NA | Trade Partner | Wet Fire - Basement Zone 2 | 1 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 796 | 2026-05-03 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-001549 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-24 | Auspan-TRANSMIT-000241 | NA | Trade Partner | Re Precast shop drawings for approval. Zone 4, 5 | 39 | 0 | 0 | NA | APPROVED | 2026-04-25 | NA | 798 | 2026-05-01 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-001677 | Closed | 39 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-24 | Auspan-TRANSMIT-000242 | NA | Trade Partner | Update precast dowel layout ground floor zone 3 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing Rejected due to incomplete drawings number - KPTG-TRANSMIT-001498 |  | 2026-04-24 | KPTG-TRANSMIT-001498 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-24 | crossfir-TRANSMIT-000008 | NA | Trade Partner | Penetration drawings - Level 01 to 10 | 10 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 435 | 2026-05-01 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-001065 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-27 | KETE-TRANSMIT-000127 | NA | Trade Partner | Updated sample form | 0 | 3 | 0 | NA | REJECTED |  | NA | NA |  |  | The documents were rejected as the revision has not been updated. |  |  | KPTG-SADV-003888 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-27 | HDRAus-TRANSMIT-000469 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 40 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 2973 | 2026-05-01 |  |  | 2026-04-30 | 2026-04-30 | HDRAus-TRANSMIT-000469 | Closed | 40 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-27 | NXT-TRANSMIT-001513 | NA | Client | Fwd: SO 611300382- M3S4- LVSB: FWT script_MSB/USB-FF panel | 0 | 1 | 0 | NA | APPROVED | 2026-04-27 | WF-005460 | NA | 2026-05-05 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-27 | NXT-TRANSMIT-001510 | NA | Trade Partner | Fwd P2680 - NDC M3 Stage 4 - Fuel - BFS CACO | 1 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 2975 | 2026-05-06 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-017752 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-27 | KPTG-IntCorr-000374 | NA | Trade Partner | SME AHU Samples for review | 0 | 1 | 0 | NA | APPROVED | 2026-04-27 | WF - 000378 | NA | 2026-04-30 |  | NA | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-000822 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-15 | SKS Tech-TRANSMIT-000107 | NA | Trade Partner | For construction submittals - TELECOMMUNICATION SYSTEM | 0 | 15 | 0 | NA | APPROVED |  | NA | NA |  |  | 14 Docs updated in the Reg. - updated with SKS Tech-TRANSMIT-000120 |  | 2026-02-04 | KPTG-TRANSMIT-002669 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-27 | GEMBA-D-TRANSMIT-000014 | NA | Consultant | Roof - For Certification issue - Strucutral | 8 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 143 | 2026-04-30 |  |  | 2026-04-30 | 2026-05-04 | KPTG-TRANSMIT-000438 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-27 | ARCH-TRANSMIT-000040 | NA | Consultant | 2026.04.24_Issued for Construction (FC-01) | 62 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 140 | 2026-04-29 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-000365 | Closed | 62 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-27 | ARCH-TRANSMIT-000040 | NA | Consultant | 2026.04.24_Issued for Construction (FC-01) | 0 | 5 | 0 | NA | REJECTED | [5 empty] | Issues with document number. |  | 2026-04-27 | KPTG-DA-000560 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-03 | D&E-TRANSMIT-000467 | na | Trade Partner | SAMPLE AND TECH DATA - CONSULTANT REVIEW - FACAD WORKFLOW - DATA SHEET | 0 | 2 | 0 | NA | APPROVED | 2026-04-27 | wf-004740 | NA | 2026-04-27 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016501 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-27 | D&E-TRANSMIT-000627 | NA | Trade Partner | Sensors - Gas - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-04-27 | WF-005452 | NA | 2026-05-08 |  | As per requested by William K -The WF has been terminated |  |  |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-27 | FNSTR8-TRANSMIT-000006 | NA | Trade Partner | Re: M3 S4 - Stage 4 Facade Samples | 0 | 15 | 0 | NA | REJECTED | [5 empty] | Incorrect document number , revision |  | 2026-04-27 | KPTG-RFI-007546 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-27 | RDSBIM-TRANSMIT-000029 | NA | Trade Partner | GROUND FLOOR TO LEVEL 09 STAIR/LIFT CORE 02 CONCRETE PROFILE PLAN SECTION AND ELEVATION | 3 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 490 | 2026-04-29 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-001519 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-27 | Tradetec-TRANSMIT-000429 | NA | Trade Partner | Re: IFA - Stage 4 - CP40 CP32 CP20 CP29 | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect document number |  | 2026-04-27 | KPTG-RFI-007547 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-27 | D&E-TRANSMIT-000238 | SPARK-CRFI-KPG-000540 | Trade Partner | CONTROL SPECIALIST SENSOR | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-000806 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-27 | TTW-TRANSMIT-000177 | NA | Consultant | M3 Stage 2 Civil Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 4154 | 2026-04-29 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-016690 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-12 | RDSBIM-TRANSMIT-000009 | NA | Trade Partner | GROUND FLOOR TO LEVEL 09 STAIR/LIFT CORE 02 CONCRETE PROFILE PLAN SECTION AND ELEVATION | 3 | 0 | 0 | NA | APPROVED | 2025-12-15 | NA | 154 | 2025-12-17 |  |  | 2026-01-13 | 2026-01-14 | KPTG-TRANSMIT-000274 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-06 | SES AU-TRANSMIT-000019 | NA | Trade Partner | Security Tech Data -WF‑000052-IFC | 0 | 20 | 0 | NA | APPROVED | 2026-05-06 | WF-000209 | NA | 2026-05-06 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-000574 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-27 | D&E-TRANSMIT-000629 | NA | Trade Partner | SFN - IMI Balancing Valves - Issued for approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-27 | WF-005455 | NA | 2026-05-18 |  | AS PER REQUESTED BY ELI SALMOM THE WORKFLOW IS TERMINATED FOR UPDATING DOCUMENTSKPTG-IntCorr-012455 |  | 2026-04-29 | KPTG-IntCorr-012456 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-27 | SES AU-TRANSMIT-000020 | NA | Trade Partner | Security - Lenel Drawer | 0 | 1 | 0 | NA | APPROVED | 2026-04-27 | WF-000174 | NA | 2026-05-01 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000503 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-27 | INTRFRM-TRANSMIT-000024 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 4) | 0 | 4 | 0 | NA | APPROVED | 2026-04-27 | WF-000078 | NA | 2026-05-05 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000328 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-27 | D&E-TRANSMIT-000628 | NA | Trade Partner | MCC-CH-XX Electrical Drawing - Issued for Cosntruction | 1 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 2981 | 2026-05-08 |  | terminated as per requested by elli salmon | 2026-06-23 | 2026-06-23 | KPTG-IntCorr-015058 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-27 | D&E-TRANSMIT-000631 | NA | Trade Partner | HMI Touchscreens, Sensors - Air Side, Sensors - Water Side - Issued for Construction | 0 | 3 | 0 | NA | APPROVED | 2026-04-27 | NA | WF-005457 | 2026-05-18 |  | As per requested by William K -The WF has been terminated |  |  | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-27 | Auspan-TRANSMIT-000024 | NA | Trade Partner | Precast shop drawings for construction. | 18 | 0 | 0 | NA | REJECTED | [5 empty] | LATEST REVISION SEEN AS REVISE AND RESUBMIT |  | 2026-04-27 | KPTG-SADV-000217 | Closed | 18 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-27 | WilsonPD-TRANSMIT-000184 | SPARK-CRFI-KPG-000251 | Trade Partner | Hydraulic Services - Level 1 - Zone A | 1 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 253 | 2026-05-04 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-000785 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-27 | Jangho-TRANSMIT-000023 | NA | Trade Partner | Thermal Calculation Analysis Report of System Diagrams (FT-01 and FT02) | 0 | 1 | 0 | NA | APPROVED | 2026-04-27 | WF-000384 | NA | 2026-04-29 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-001430 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-27 | HDRAus-TRANSMIT-000466 | NA | Consultant | Eave gutter update | 2 | 0 | 0 | NA | REJECTED | [5 empty] | needed clarification on the note mentioned in the document |  | 2026-04-27 | KPTG-DA-006204 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-15 | Civilex-TRANSMIT-000012 | NA | Trade Partner | Foundation Pile Design Rev C3 | 0 | 1 | 0 | KPTG-IntCorr-000164 | APPROVED | 2025-12-16 | WF-000081 | NA | 2025-12-18 |  | Confirmation mail sent for onward submission | 2026-01-20 | 2026-01-20 | KPTG-TRANSMIT-000294 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-27 | Tradetec-TRANSMIT-000430 | NA | Trade Partner | Tech Data - Site Wide - Slip Couplings | 0 | 1 | 0 | NA | APPROVED | 2026-04-27 | WF-005459 | NA | 2026-05-01 |  |  | 2026-04-29 | 2026-05-06 | KPTG-TRANSMIT-016956 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-27 | Jangho-TRANSMIT-000024 | NA | Trade Partner | Thermal Calculation Analysis Report for System Diagrams (FT-07) | 0 | 1 | 0 | NA | APPROVED | 2026-04-27 | WF-000385 | NA | 2026-04-29 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-001510 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-27 | KETE-TRANSMIT-000128 | NA | Trade Partner | Thermal report updated | 0 | 1 | 0 | NA | APPROVED | 2026-04-28 | WF-000722 | NA | 2026-05-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-27 | Jangho-TRANSMIT-000027 | NA | Trade Partner | Structural Calculation for FT04 System Concept Drawing | 0 | 1 | 0 | NA | APPROVED | 2026-04-27 | WF-000389 | NA | 2026-04-30 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-001573 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-27 | Jangho-TRANSMIT-000028 | NA | Trade Partner | Structural Calculation for FT13 System Concept Drawing | 0 | 1 | 0 | NA | APPROVED | 2026-04-27 | WF-000390 | NA | 2026-04-30 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-002223 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-27 | RDSBIM-TRANSMIT-000192 | NA | Trade Partner | LINDRUM ¦ LEVEL 11 TO LEVEL 27 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 632 | 2026-05-02 |  |  | 2026-05-05 | 2026-05-05 | KPTG-SADV-004021 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-27 | RDSBIM-TRANSMIT-000193 | NA | Trade Partner | LINDRUM ¦ LEVEL 09 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 633 | 2026-05-04 |  |  | 2026-05-05 | 2026-05-05 | KPTG-SADV-004022 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-27 | SES AU-TRANSMIT-000021 | NA | Trade Partner | SECURITY-TYPE J CABLE | 0 | 1 | 0 | NA | APPROVED | 2026-04-27 | WF-000175 | NA | 2026-05-01 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-000611 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-27 | SES AU-TRANSMIT-000022 | NA | Trade Partner | SECURITY- CAMERA INDOOR DOME | 0 | 1 | 0 | NA | APPROVED | 2026-04-27 | WF-000176 | NA | 2026-05-01 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000494 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-27 | Appselec-TRANSMIT-000075 | NA | Trade Partner | Comms Tech Data IFC | 0 | 2 | 0 | NA | APPROVED | 2026-04-27 | WF-000178 | NA | 2026-05-01 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000500 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-15 | SMEPS-TRANSMIT-000244 | NA | Trade Partner | SME-IFC PENETRATION DRAWINGS | 2 | 0 | 0 | NA | APPROVED | 2025-12-15 | NA | 1321 | 2025-12-24 |  |  | 2025-12-18 | 2025-12-18 | KPTG-TRANSMIT-002230 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-27 | Schindle-TRANSMIT-000024 | NA | Trade Partner | Lift PL1 - Landing Frames - IFC revision | 2 | 0 | 0 | NA | REJECTED | [5 empty] | No document number inside the drawing, latest revision status is revise and resubmit |  | 2026-04-27 | KPTG-SADV-005037 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-27 | IGS--TRANSMIT-000034 | NA | Consultant | Revised Building Services Layouts | 4 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 635 | 2026-04-30 |  |  | 2026-04-30 | 2026-04-30 | KPTG-SADV-003963 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-27 | IGS--TRANSMIT-000034 | NA | Consultant | Revised Building Services Layouts | 4 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 636 | 2026-04-30 |  |  | 2026-04-30 | 2026-04-30 | KPTG-SADV-003962 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-04-27 | Stulz -TRANSMIT-000037 | NA | Trade Partner | FWU SOO superseded for MXC 2 language | 0 | 1 | 0 | KPTG-IntCorr-003524 | APPROVED |  | NA | NA |  |  | Information only |  | 2026-05-04 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-27 | RDSBIM-TRANSMIT-000189 | NA | Trade Partner | LINDRUM ¦ LEVEL 07 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 637 | 2026-05-04 |  |  | 2026-05-13 | 2026-05-13 | KPTG-SADV-004136 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-27 | RDSBIM-TRANSMIT-000191 | NA | Trade Partner | LINDRUM ¦ LEVEL 08 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 638 | 2026-05-04 |  |  | 2026-05-13 | 2026-05-13 | KPTG-SADV-004137 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-27 | RDSBIM-TRANSMIT-000187 | NA | Trade Partner | LINDRUM ¦ LEVEL 08 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-000919-As per the direction from Ashlin, I have updated this drawing into Document Register and transmitted to all concerned parties. | 2026-04-27 | 2026-04-27 | KPTG-IntCorr-000919 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-27 | RDSBIM-TRANSMIT-000188 | NA | Trade Partner | LINDRUM ¦ LEVEL 04 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-000920-As per the direction from Ashlin, I have updated this drawing into Document Register and transmitted to all concerned parties. | 2026-04-27 | 2026-04-27 | KPTG-IntCorr-000920 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-27 | KPTG-IntCorr-000915 | NA | Trade Partner | Re: Door Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-04-27 | WF-000720 | NA | 2026-04-30 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-002650 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-27 | HDRAus-TRANSMIT-000087 | NA | Consultant | M3 Stage 6 - Town Planning Updates - Revised Retaining Wall | 1 | 0 | 0 | KPTG-IntCorr-000065 | APPROVED |  | NA | NA |  |  |  |  | 2026-04-27 | KPTG-DA-000155 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-15 | SKS Tech-TRANSMIT-000108 | NA | Trade Partner | ELECTRICAL SERVICES - POWER CONTAINMENT FOR LEVEL 3 | 1 | 0 | 0 | NA | APPROVED | 2025-12-15 | NA | 754 | 2025-12-17 |  |  | 2026-01-15 | 2026-01-15 | KPTG-TRANSMIT-002442 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-27 | ARCH-TRANSMIT-000041 | na | Consultant | Re: 2026.04.24_Issued for Construction (FC-01) | 0 | 5 | 0 | NA | REJECTED | [5 empty] | no document number and revision mentioned in the coversheet |  | 2026-04-27 | DRAFT-001401 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-27 | ADP-TRANSMIT-000060 | NA | Consultant | ADP MEL4680 - Electrical drawings ( IFC Issue) | 8 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 147 | 2026-04-30 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-000395 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-27 | ADP-TRANSMIT-000061 | NA | Consultant | ADP MEL4680 - Electrical Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 150 | 2026-04-30 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000343 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-27 | VIA Arch-TRANSMIT-000109 | NA | Consultant | M2 S9-11 L2 & L3 Fire Separation Plans | 1 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 771 | 2026-05-01 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-002655 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-27 | WGAVIC-TRANSMIT-000107 | NA | Consultant | M2 - Fire Stair 01 Updates - Issued for Construction/Certification | 2 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 769 | 2026-05-01 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-002643 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-09-15 | ARCST-TRANSMIT-000105 | NA | Trade Partner | Additional Bracket procurement | 2 | 0 | 0 | NA | APPROVED | 2025-09-24 | WF-002676 | NA | 2025-10-03 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-016554 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-27 | SMEPS-TRANSMIT-000027 | NA | Trade Partner | STAGE 9-11 OVERALL SITE EARTHING & LIGHTNING PROTECTION LAYOUT (FOA-1) | 1 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 767 | 2026-05-04 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-003436 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-27 | WGAVIC-TRANSMIT-000106 | NA | Consultant | M2 - Steelwork Stages 9-11 - Issued for Certification | 28 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 765 | 2026-04-29 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-002639 | Closed | 28 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-04-27 | SMEPS-TRANSMIT-000251 | NA | Trade Partner | Re: 22KV - AS-BUILTS | 5 | 0 | 0 | KPTG-IntCorr-012367 | APPROVED | [5 empty] | ADVISE SEEKED |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-04-27 | SMEPS-TRANSMIT-000249 | NA | Trade Partner | Re: 22KV - IFC drawing set | 22 | 0 | 0 | KPTG-IntCorr-012368 | APPROVED | [5 empty] | ADVISE SEEKED |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2025-12-16 | KPTG-SADV-000885 | NA | Trade Partner | Rack Signage - IFA | 1 | 0 | 0 | NA | APPROVED | 2025-12-16 | WF-000176 |  | 2025-12-24 |  |  |  | 2025-12-17 | KPTG-TRANSMIT-000646 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-27 | Appselec-TRANSMIT-000073 | NA | Trade Partner | MEL11C45 - COLO 5 Cell 3 - Lighting, Power & Earthing Layout - IFC | 3 | 0 | 0 | NA | APPROVED | 2026-04-27 | WF-000172 | NA | 2026-04-30 |  |  | 2026-04-27 | 2026-04-27 | KPTG-TRANSMIT-000473 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-27 | Appselec-TRANSMIT-000074 | NA | Trade Partner | Patch Cords IFC | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision 1 of this document has already been transmitted and reviewed. The Revision of this document needs to be 2. Requested to resubmit: KPTG-IntCorr-000310 |  | 2026-04-27 | KPTG-IntCorr-000310 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-27 | P & R-TRANSMIT-000087 | NA | Trade Partner | Carpark North | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Revision & Drawing status of drawing has not been mentioned, requested to resubmit: KPTG-SADV-004176 |  | 2026-04-27 | KPTG-SADV-004176 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-27 | RED Fire-TRANSMIT-000002 | NA | Consultant | Fire Engineering Report V5 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | The Report is submitted for information, we have transmitted to all concerned parties: |  | 2026-04-27 | KPTG-TRANSMIT-002793 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-27 | SC-TRANSMIT-000048 | NA | Trade Partner | Operable Wall IFC | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC DRAWING, TRANSMITTED TO ALL CONCERNED PARTIES |  | 2026-04-27 | KPTG-TRANSMIT-002791 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-27 | TGRF-TRANSMIT-000109 | NA | Trade Partner | Fwd: IVPT26036 - Stage 2 IFA Plans | 47 | 0 | 0 | NA | REJECTED | [5 empty] | DOCUMENT NUMBERS OF ALL DRAWINGS ARE INCORRECT, REQUESTED TO CORRECT AND RESUBMIT:KPTG-SADV-004184 |  | 2026-04-27 | KPTG-SADV-004184 | Closed | 47 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-27 | JCBa-TRANSMIT-000100 | NA | Consultant | Structural Setout Plans IFC: 7th Floor Zone Plans | 5 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 800 | 2026-04-29 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-001615 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-27 | RDSBIM-TRANSMIT-000050 | NA | Trade Partner | GREYSTAR GROUND FLOOR CONCRETE PROFILE PLAN ZONE 5 | 2 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 802 | 2026-04-30 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-001660 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-27 | Auspan-TRANSMIT-000243 | NA | Trade Partner | Precast shop drawings for construction. | 49 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect drawing number , revision - KPTG-TRANSMIT-001522 |  | 2026-04-28 | KPTG-TRANSMIT-001522 | Closed | 49 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-27 | Auspan-TRANSMIT-000244 | NA | Trade Partner | Resubmit precast shop drawings for approval. | 83 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to QC issues. drawing number , revision history, cloud overlapping etc. KPTG-SADV-002128 |  | 2026-04-27 | KPTG-SADV-002128 | Closed | 83 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-03-18 | Stowe-A-TRANSMIT-000521 | NA | Trade Partner | Stowe - Tech Data Submission - Work station | 0 | 1 | 0 | NA | APPROVED | 2026-03-18 | WF-004863 | NA | 2026-03-31 |  |  | 2026-04-20 | 2026-04-20 | KPTG-TRANSMIT-016115 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-05 | TTW-TRANSMIT-000001 | NA | Consultant | Facade Drawings - Issued For Information IFI-1 | 12 | 0 | 0 | NA | APPROVED | 2025-12-12 |  | 139 | 2025-12-16 |  |  | 2025-12-15 | 2025-12-16 | KPTG-TRANSMIT-000357 | Closed | 12 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-27 | Auspan-TRANSMIT-000245 | NA | Trade Partner | Auspan-TRANSMIT-000245 Precast shop drawings for approval. | 2 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 813 | 2026-05-05 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-001703 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-27 | Auspan-TRANSMIT-000249: | NA | Trade Partner | Re: Update precast dowel layout ground floor zone 3. | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - No Review - update register and transmitt- KPTG-TRANSMIT-001510 |  | 2026-04-27 | KPTG-TRANSMIT-001510 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-27 | INDS-TRANSMIT-000020 | NA | Trade Partner | Wet Fire - Basement Zone 4 | 1 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 810 | 2026-05-05 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-001555 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-27 | StantecA-TRANSMIT-000301 | NA | Trade Partner | IFC Documents Update - Fire Protection - Stantec | 3 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 804 | 2026-04-29 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-001667 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-27 | Auscool-TRANSMIT-000021 | NA | Trade Partner | BASEMET TO LEVEL 7 - TUNDISH LOCATIONS | 44 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 806 | 2026-05-01 |  | Review voided as advised by kapitol PC Amee. Drawings to be superseded by the Trade Partner | 2026-05-01 | 2026-05-01 | NA | Closed | 44 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-27 | Auscool-TRANSMIT-000022 | NA | Trade Partner | BW - TUNDISH LOCATION - LEVEL 1, ZONE 2 | 1 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 808 | 2026-05-05 |  | Review voided as advised by kapitol PC Amee. | 2026-05-01 | 2026-05-01 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-27 | RDSBIM-TRANSMIT-000060 | NA | Trade Partner | 671CHP BASEMENT 3 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - No Review required, update register |  | 2026-04-27 | KPTG-TRANSMIT-000841 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-27 | RDSBIM-TRANSMIT-000061 | NA | Trade Partner | 671CHP BASEMENT 2 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Review required , update register |  | 2026-04-27 | KPTG-TRANSMIT-000839 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-27 | RDSBIM-TRANSMIT-000062 | NA | Trade Partner | 671CHP BASEMENT 4A TO BASEMENT 1 CORE WALL PLAN AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Review required , update register |  | 2026-04-27 | KPTG-TRANSMIT-000842 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-27 | Jangho-TRANSMIT-000047 | NA | Trade Partner | 20260426 671 Chapel St Project VMU NO.2&NO.3 SHOP DRAWINGS[02] | 58 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 437 | 2026-05-05 |  | Review voided; As informed by Kaptol PC , Trade partner is going to supersede the Shop Drawings. | 2026-05-25 | 2026-05-25 | NA | Closed | 58 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-12 | Tradetec-GCOR-000027 |  | Trade Partner | In-Ground Services Shop Drawings – For Review | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Not Uploaded on Aconex-KPTG-TRANSMIT-000347 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-27 | Jangho-TRANSMIT-000026 | NA | Trade Partner | 006_FT-13 SYSTEM CONCEPT DRAWING-01 | 15 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 486 | 2026-05-04 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-002085 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-27 | Jangho-TRANSMIT-000025 | NA | Trade Partner | 005_FT-04 SYSTEM CONCEPT DRAWING-01 | 27 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 484 | 2026-05-04 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-002025 | Closed | 27 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-28 | SMEPS-TRANSMIT-000255 | NA | Trade Partner | SME - IFC Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 2983 | 2026-06-05 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-017070 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-27 | Civilex-TRANSMIT-000077 | NA | Trade Partner | Hydraulic HDPE Pipes | 0 | 2 | 0 | NA | APPROVED | 2026-04-27 | WF-000386 | NA | 2026-04-29 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-001755 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-27 | WAM-TRANSMIT-000754 | NA | Consultant | Fire Control Room - BP Issue | 1 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 492 | 2026-04-30 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-001496 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-27 | INGEN3D-TRANSMIT-000048 | NA | Trade Partner | I3D-389 District Living - Level 5-7 - Precast Columns - IFA | 66 | 0 | 0 | NA | APPROVED | 2026-04-27 | WF-000382 | NA | 2026-04-30 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-001653 | Closed | 66 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-27 | Hollow-TRANSMIT-000010 | NA | Trade Partner | L3 plant room precast structure - PC beams and planks - Shop drawings, issued for approval | 17 | 0 | 0 | NA | APPROVED | 2026-04-27 | NA | 488 | 2026-05-05 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-001402 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-27 | VAE-Grp-TRANSMIT-000156 | NA | Trade Partner | IFA - MECHANICAL - O&M MANUAL | 0 | 1 | 0 | NA | APPROVED | 2026-04-27 | WF-001028 | NA | 2026-05-01 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-003873 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-28 | SMEPS-TRANSMIT-000254 | NA | Trade Partner | SME - DRAWINGS IFA PART SUBMISSIONS | 2 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 2985 | 2026-05-06 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-017850 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-12 | VIA Arch-TRANSMIT-000032 | NA | Consultant | M2 - S9 - 11 Architectural WIP Issue | 62 | 0 | 0 | NA | APPROVED | 2025-12-15 |  | 145 | 2025-12-18 |  |  | 2025-12-18 | 2025-12-21 | KPTG-TRANSMIT-000423 | Closed | 62 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-28 | RDSBIM-TRANSMIT-000005 | NA | Trade Partner | NXGE01 ¦ GROUND FLOOR PLANT AREA CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 152 | 2026-05-01 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-000425 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-04-28 | SMEPS-TRANSMIT-000253 | NA | Trade Partner | SME - IFC drawings | 3 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 2987 | 2026-05-06 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-28 | Auspan-TRANSMIT-000019 | NA | Trade Partner | Precast shop drawings for construction. | 20 | 0 | 0 | NA | APPROVED | 2026-04-28 | WF-000083 | NA | 2026-05-01 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-000278 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-28 | SMEPS-TRANSMIT-000196 | NA | Trade Partner | Mel05 Communication Details DWGs For IFA | 1 | 0 | 0 | NA | APPROVED | 2026-04-28 | WF - 000380 | NA | 2026-05-04 |  | Mel05 Communication Details DWGs For IFA | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000817 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-28 | WilsonPD-TRANSMIT-000020 | NA | Trade Partner | Stage 2 Slab - Water Treatment Plant Set Out | 1 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 773 | 2026-05-05 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-002568 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-04-27 | Carr-TRANSMIT-000041 | NA | Consultant | Secondary Consent - Revision Cloud Updates | 5 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 66 | 2026-04-28 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000036 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-28 | D&E-TRANSMIT-000633 | NA | Trade Partner | Level 1 - Mechanical Duct Layout - Zone 5 - ISSUED FOR CONSTRUCTION | 1 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 2992 | 2026-05-06 |  | As requested by Ellie — Terminated — KPTG-IntCorr-013787 |  | 2026-05-26 | KPTG-IntCorr-013787 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-28 | Auspan-TRANSMIT-000024 | NA | Trade Partner | Precast shop drawings for construction. | 18 | 0 | 0 | NA | APPROVED | 2026-04-28 | WF-000084 | NA | 2026-05-07 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-000287 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-28 | SMEPS-TRANSMIT-000257 | NA | Trade Partner | SME - IFC Submissions | 2 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 2996 | 2026-05-05 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-016892 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-12 | Auspan-TRANSMIT-000021 | NA | Trade Partner | Update precast shop drawings for approval. South panels. | 28 | 0 | 0 |  | REJECTED | [5 empty] | Wrong title Guide- KPTG-TRANSMIT-000352 Kapitol initiated an Internal Workflow-WF-000085 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-28 | Auspan-TRANSMIT-000025 | NA | Trade Partner | Re: Precast shop drawings for construction. | 1 | 0 | 0 | NA | APPROVED | 2026-04-28 | WF-000085 | NA | 2026-05-07 |  | Terminated |  | 2026-04-28 | KPTG-SADV-000223 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-28 | ASV-TRANSMIT-000058 | NA | Trade Partner | Revised CSD Pump Station | 0 | 1 | 0 | NA | APPROVED | 2026-04-28 | WF-000560 | NA | 2026-05-07 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-002969 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-28 | Tradetec-TRANSMIT-000118 | NA | Trade Partner | LVP25 Pit Shop Drawing | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-04-28 | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-26 | KPTG-WTRAN-009314 | NA | Trade Partner | S4 ¦ SAMPLE AND TECH DATA - CONSULTANT REVIEW - FACAD WORKFLOW - Proctorwrap CW | 3 | 0 | 0 | NA | APPROVED | 2026-03-26 | WF-005017 | NA | 2026-04-28 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-016569 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-28 | Tradetec-TRANSMIT-000119 | NA | Trade Partner | LVP25 Pit Shop Drawing | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-04-28 | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-28 | ARCH-TRANSMIT-000042 | NA | Consultant | Re: 2026.04.24_Issued for Construction (FC-01) | 0 | 4 | 0 | NA | APPROVED | 2026-04-28 | NA | 157 | 2026-05-01 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-000369 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-28 | Tradetec-TRANSMIT-000120 | NA | Trade Partner | Re: LVP25 Pit Shop Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 775 | 2026-05-05 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-002694 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-28 | RDSBIM-TRANSMIT-000030 | NA | Trade Partner | GROUND FLOOR TO LEVEL 09 STAIR CORE 04 CONCRETE PROFILE PLAN AND SECTION ELEVATION | 3 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 495 | 2026-04-30 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-001456 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-17 | LTEPRCST-TRANSMIT-000142 | NA | Trade Partner | Structural Drawings - Precast Lids & Stair + Computation Report + REG126 - IFC | 7 | 0 | 0 | NA | APPROVED | 2025-12-18 | NA | WF-003668 | 2026-04-28 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-016579 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-28 | SMEPS-TRANSMIT-000259 | NA | Trade Partner | Revised Jemena Easement Shopdrawing - 28.04.2026 | 2 | 0 | 0 | NA | APPROVED | 2026-04-28 | WF-005474 | NA | 2026-05-05 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-04 | SCG2014-TRANSMIT-000008 | NA | Consultant | Security Services - For Tender-spec and Report | 0 | 5 | 0 | NA | APPROVED | 2025-12-15 |  | 143 | 2025-12-18 |  |  | 2025-12-18 | 2025-12-19 | KPTG-TRANSMIT-000413 | Closed | 5 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-28 | KAPITOL-TRANSMIT-001317 | NA | Trade Partner | HFF - URGENT Security Shop Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 403 | 2026-05-14 |  |  | 2026-06-03 | 2026-06-03 | DRAFT-010115 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-28 | PenskePS-IntCorr-000002 | NA | Trade Partner | MEL05 COLO4 - FAT Report | 0 | 25 | 0 | NA | APPROVED | 2026-04-28 | WF - 000381 | NA | 2026-05-05 |  | NA | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-000899 | Closed | 25 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-28 | Auspan-TRANSMIT-000027 | NA | Trade Partner | Re: Update IFCed shop drawings for construction. | 1 | 0 | 0 | NA | APPROVED | 2026-04-28 | WF-000087 | NA | 2026-05-07 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-000283 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-28 | WilsonPD-TRANSMIT-000021 | NA | Trade Partner | Specified Fixtures for Approval | 0 | 15 | 0 | NA | APPROVED | 2026-04-28 | WF-000564 | NA | 2026-05-07 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-002843 | Closed | 15 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-28 | Auspan-TRANSMIT-000026 | NA | Trade Partner | Update IFCed shop drawings for construction. | 3 | 0 | 0 | NA | APPROVED | 2026-04-28 | WF-000088 | NA | 2026-05-07 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-000274 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-28 | SMEPS-TRANSMIT-000260 | NA | Trade Partner | STAGE 4 - Inground Site Layout (C08) | 1 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 3000 | 2026-05-05 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-016970 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-28 | TATE_-TRANSMIT-000029 | NA | Trade Partner | Ceiling Engineering Report Rev 02 | 0 | 1 | 0 | NA | APPROVED | 2026-04-28 | WF - 000382 | NA | 2026-05-04 |  | NA | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-000807 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-04-28 | KAPITOL-TRANSMIT-001318 | NA | Trade Partner | HFF - URGENT: Security Gates/Fencing Shop Drawings | 7 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 404 | 2026-05-04 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-28 | vdmcons-TRANSMIT-000133 | NA | Trade Partner | ME25 1004: D115 511-537 Sydney Rd Coburg - Shop Drawings & 3D IFC Model - L03 Steel Pavilion - IFF - 2026-04-28 | 72 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by kapitol Update Aconex register only. |  | 2026-04-28 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-28 | Stowe-A-TRANSMIT-000569 | NA | Trade Partner | Stowe - Tech Data Submission - PENETRATION PROTECTION SHOP DRAWING REV D | 0 | 1 | 0 | NA | APPROVED | 2026-04-28 | WF-005473 | NA | 2026-05-06 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-16 | DS-TRANSMIT-000082 | NA | Trade Partner | GF H-L Water and L01 Drainage - Issued for approval | 6 | 0 | 0 | NA | APPROVED | 2025-12-16 | NA | 1678 | 2025-12-24 |  |  |  | 2026-01-05 | KPTG-TRANSMIT-011171 | Closed | 6 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-28 | Stowe-A-TRANSMIT-000570 | NA | Trade Partner | Stowe - Tech Data - IFC - HV SWITCHROOM EARTH BAR TEST LINKS - Shop drawing | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with the status in the register |  | 2026-04-28 | KPTG-SADV-005073 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-28 | NXT-TRANSMIT-001518 | NA | Client | 31679-760 - PDU-EJB6-14 - ITP | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | As-Built |  | 2026-04-28 | KPTG-TRANSMIT-016607 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-28 | D&E-TRANSMIT-000637 | NA | Trade Partner | Fwd: HMI Touchscreens, Sensors - Air Side, Sensors - Water Side - Issued for Construction | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC tech data distributed to all |  | 2026-04-28 | D&E-TRANSMIT-000637 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-28 | KPTG-TRANSMIT-016616 | NA | Trade Partner | Fwd: Sensors - Gas - Issued for Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Tech data |  | 2026-04-28 | KPTG-TRANSMIT-016616 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-28 | Schindle-TRANSMIT-000025 | NA | Trade Partner | Lift PL1 - Landing Frames - IFC revision | 2 | 0 | 0 | NA | REJECTED | [5 empty] | There is an issue with the document number, status, and not the revised status submitted. |  | 2026-04-28 | KPTG-SADV-005083 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-28 | Highbu-TRANSMIT-000048 | NA | Trade Partner | Drainage and Water Drawings - IFC | 26 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 639 | 2026-05-05 |  | KPTG-IntCorr-000978 - As per direction from Mark, the workflow is being terminated since the architect currently does not have the capacity to review the large quantity of drawings.19-05-2026 | 2026-05-19 | 2026-05-19 | KPTG-IntCorr-000978 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-28 | Highbu-TRANSMIT-000049 | NA | Trade Partner | Drainage and Water Drawings - IFA | 35 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 640 | 2026-05-05 |  | KPTG-IntCorr-000980 - As per direction from Mark, the workflow is being terminated since the architect currently does not have the capacity to review the large quantity of drawings.20-05-2026 | 2026-05-20 | 2026-05-20 | KPTG-IntCorr-000980 | Closed | 35 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-28 | HDRAus-TRANSMIT-000470 | NA | Consultant | M3 Stage 4 - Fire compartment plan, Red Zone plan, door schedules - PDF and CAD - | 2 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 2989 | 2026-05-08 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-016694 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-28 | FNSTR8-TRANSMIT-000007 | NA | Trade Partner | Re: Shop Drawings | 7 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due ti incorrect drawing naming |  | 2026-04-28 | KPTG-DA-006222 | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-28 | SMEPS-TRANSMIT-000256 | NA | Trade Partner | TELECOMMUNICATIONS IFA DRAWINGS - | 2 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 2995 | 2026-05-05 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-018180 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-13 | Auspan-TRANSMIT-000022 | NA | Trade Partner | Stage 9 L-Shape Precast ¦ Shop Drawing Review | 30 | 0 | 0 | NA | REJECTED | 2025-12-15 |  |  |  |  | Wrong title Guide- KPTG-TRANSMIT-000346 Kapitol initiated an Internal Workflow-WF-000090 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-28 | FNSTR8-TRANSMIT-000008 | NA | Trade Partner | S4 - Stage 4 Facade Samples | 0 | 15 | 0 | NA | APPROVED | 2026-04-28 | WF-005469 | NA | 2026-05-25 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018369 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-28 | SMEPS-TRANSMIT-000258 | NA | Trade Partner | SME - Hv Structure module drawings SOuth of C3 | 5 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 2998 | 2026-05-06 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-017822 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-28 | D&E-TRANSMIT-000634 | NA | Trade Partner | MF, Temp, DP Sensors - Issued for Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | AS PER THE ELI SALMOMREQUEST THE WORKFLOW TERMINATED KPTG-IntCorr-012433 |  | 2026-04-28 | KPTG-IntCorr-012434 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-28 | Tradetec-TRANSMIT-000431 | NA | Trade Partner | Re: Stage 4 - Pit Shop Drawings | 8 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED DUE TO INCORRECTED DOCUMENT NAMING AND INCORRECT REVISION |  | 2026-04-28 | KPTG-DA-006225 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-28 | D&E-TRANSMIT-000636 | NA | Trade Partner | Sidestream Filtration System - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-28 | WF-005476 | NA | 2026-05-13 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-017145 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-28 | D&E-TRANSMIT-000635 | NA | Trade Partner | CHW - MF, Temp, DP Sensors - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-28 | WF-005477 | NA | 2026-05-15 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-017137 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-28 | Tradetec-TRANSMIT-000432 | NA | Trade Partner | IFA - Stage 4 - CP40 CP32 CP20 CP29 | 4 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 3005 | 2026-05-06 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-018228 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-28 | TTW-TRANSMIT-000148 | NA | Consultant | BP1 - Construction Issue Update | 5 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 497 | 2026-04-30 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-001431 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-28 | KPTG-TRANSMIT-016599 | NA | Trade Partner | M3-ARC-PRL-SDRG-C-0401-0005 - Rev 1 review | 1 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 3007 | 2026-05-06 |  | As requested by Renee - Terminated The updated drawings will be submitted. |  | 2026-05-21 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-28 | WilsonPD-TRANSMIT-000185 | SPARK-CRFI-KPG-000344 | Trade Partner | Updated Civil Shop Drawings | 14 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 254 | 2026-05-02 |  |  | 2026-08-04 | 2026-08-04 | KPTG-TRANSMIT-001567 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-08 | WilsonPD-TRANSMIT-000096 | NA | Trade Partner | Rain Water Re Use system, Tower A&B | 0 | 2 | 0 | NA | APPROVED | 2025-12-16 | WF-000836 | NA | 2025-12-23 |  | File supersede and WF terminated. |  |  | NA | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-28 | INDS-TRANSMIT-000021 | NA | Trade Partner | : Wet Fire - Basement Zone 5 | 1 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 815 | 2026-05-06 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-001558 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-28 | M.2-TRANSMIT-000024 | NA | Trade Partner | Electrical Services Basement Power & Comms - IFC | 5 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 820 | 2026-05-06 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-001585 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-28 | Auspan-TRANSMIT-000250 | NA | Trade Partner | Re Precast shop drawings for construction | 49 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC- No Review - update register and transmit- KPTG-TRANSMIT-001530 |  | 2026-04-28 | KPTG-TRANSMIT-001530 | Closed | 49 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-28 | Auspan-TRANSMIT-000251 | NA | Trade Partner | Re Resubmit precast shop drawings for approval | 83 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 817 | 2026-05-06 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-001725 | Closed | 83 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-28 | KMANZ-TRANSMIT-000005 | NA | Trade Partner | Car stacker shop drawing | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect revision and title in the Aconex metadata. DRAFT-006187 |  | 2026-04-28 | DRAFT-006187 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-28 | ZIA-TRANSMIT-000048 | NA | Trade Partner | Asset Register | 0 | 1 | 0 | KPTG-IntCorr-001238 | APPROVED | 2026-05-12 | WF-001059 | NA | 2026-05-19 |  | Harry to Confirm | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-003738 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-28 | TTW-TRANSMIT-000179 | NA | Consultant | M3 Stage 2 Civil Drawings | 19 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 4158 | 2026-04-30 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-017095 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-28 | Appselec-TRANSMIT-000076 | NA | Trade Partner | Patch Cords IFC | 0 | 1 | 0 | NA | APPROVED | 2026-04-28 | NA | WF-000179 | 2026-04-29 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-28 | Entire M-TRANSMIT-000040 | NA | Trade Partner | Mechanical pipework shop drawings IFC | 2 | 0 | 0 | NA | APPROVED | 2026-04-28 | WF-000181 | NA | 2026-04-30 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-000512 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-28 | KALLIBRE-TRANSMIT-000001 | NA | Trade Partner | MEL11 C4&5 Door Frame Shop Drawings | 42 | 0 | 0 | NA | APPROVED | 2026-04-28 | WF-000182 | NA | 2026-05-06 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-16 | B Smart-TRANSMIT-000043 | NA | Consultant | A08s Draft IFC Amendment For information. | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Register update only. |  | 2025-12-16 |  | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-28 | KALLIBRE-TRANSMIT-000002 | NA | Trade Partner | 6 Hinge Spacing Detail Markup | 1 | 0 | 0 | NA | REJECTED | [5 empty] | DOCUMENT NUMBERING IS INCORRECT, REQUESTED TO RESUBMIT:KPTG-IntCorr-000321 |  | 2026-04-28 | KPTG-IntCorr-000321 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-28 | TGRF-TRANSMIT-000110 | NA | Trade Partner | NO LONGER IN USE DATA: | 1 | 0 | 0 | NA |  |  | NA | NA |  |  | TRANSMITTED TO CONCERNED TRADE PARTIES:KPTG-TRANSMIT-002797 |  | 2026-04-28 | :KPTG-TRANSMIT-002797 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-28 | CLADC-TRANSMIT-000023 | NA | Trade Partner | Re: Updated door leaf drawings | 26 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | DOCUMENT NUMBERINGS ARE INCORRECT, REQUESTED TO RESUBMIT:KPTG-SADV-004188 |  | 2026-04-28 | KPTG-SADV-004188 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-28 | TGRF-TRANSMIT-000111 | NA | Trade Partner | No longer in use : Document Trasnmittal | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No longer in use : Document Trasnmittal, TRANSMITTED TO CONCERNED PARTIES:KPTG-TRANSMIT-002796 |  | 2026-04-28 | KPTG-TRANSMIT-002796 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | KPTG-TRANSMIT-016614 | NA | Trade Partner | Fwd: Balusterstyle Handrails for Core 7 | 3 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect title Ref. Partners-TRANSMIT-000014 |  | 2026-04-29 | KPTG-RFI-007585 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-28 | INGEN3D-TRANSMIT-000049 | NA | Trade Partner | INGEN3D-TRANSMIT-000049 | 8 | 0 | 0 | NA | APPROVED | 2026-04-28 | WF-000394 | NA | 2026-04-30 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-001466 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-28 | Civilex-TRANSMIT-000079 | NA | Trade Partner | Hydraulic Shop Drawings - Water | 1 | 0 | 0 | NA | REJECTED | [5 empty] | rejected: Document Error |  | 2026-04-28 | KPTG-TRANSMIT-001392 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-28 | Firesafe-TRANSMIT-000005 | NA | Trade Partner | Updated calc submission | 0 | 1 | 0 | NA | APPROVED | 2026-04-28 | WF-000380 | NA | 2026-04-29 |  |  | 2026-04-28 | 2026-04-28 | KPTG-TRANSMIT-001400 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-28 | Civilex-TRANSMIT-000078 | NA | Trade Partner | Hydraulic Shop Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 499 | 2026-05-06 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-001749 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-28 | Civilex-TRANSMIT-000080 | NA | Trade Partner | Raft & Void Former Alternative Material | 0 | 1 | 0 | NA | APPROVED | 2026-04-28 | WF-000399 | NA | 2026-05-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-15 | Entire M-TRANSMIT-000017 | NA | Trade Partner | Fan Coil Units & Condensers Technical Data Submittal | 0 | 1 | 0 | NA | APPROVED | 2025-12-15 | WF-003633 / WF-003773 |  | 2026-01-30 |  |  |  | 2026-01-19 | KPTG-TRANSMIT-011568 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-28 | WAM-TRANSMIT-000755 | NA | Consultant | A40.128_4B3 - DETAIL - FACADE APARTMENT VENTILATION | 1 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 501 | 2026-05-01 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-001491 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-29 | Appselec-TRANSMIT-000077 | NA | Trade Partner | Patch Cords IFC | 0 | 1 | 0 | NA | APPROVED | 2026-04-29 | WF-000183 | NA | 2026-04-30 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000497 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | SKS Tech-TRANSMIT-000111 | NA | Trade Partner | Fwd: M3-ELC-SKS-SA-C-0400-003 Earth Bars - Switchrooms IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-04-29 | KPTG-TRANSMIT-016637 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | Nilsen3-TRANSMIT-000122 | NA | Trade Partner | Updated Penetration Seal Material | 0 | 1 | 0 | NA | APPROVED | 2026-04-29 | WF-005481 | NA | 2026-05-05 |  | AS PER REQUESTED BY RENEZ WF IS TERMINATED KPTG-TRANSMIT-016638 |  | 2026-04-29 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | Partners-TRANSMIT-000015 | NA | Trade Partner | Fwd: Balusterstyle Handrails for Core 7 | 3 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect title |  | 2026-04-29 | KPTG-RFI-007588 | Closed | 3 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-29 | INTRFRM-TRANSMIT-000026 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 5) | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Revison is not updated |  | 2026-04-29 | DRAFT-001466 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-29 | INTRFRM-TRANSMIT-000027 | NA | Trade Partner | Geelong Edge - Electrical Tech Data (Submission 5) | 0 | 1 | 0 | NA | APPROVED | 2026-04-29 | WF-000089 | NA | 2026-05-07 |  | Terminated as advised by Evelyn, to update the document. | 2026-04-30 | 2026-04-30 | KPTG-IntCorr-000176 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-29 | Stowe-A-TRANSMIT-000572 | NA | Trade Partner | Stowe - Tech Data Submission - EXTERNAL LIGHTING | 0 | 1 | 0 | NA | APPROVED | 2026-04-29 | WF-005482 | NA | 2026-05-11 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-016708 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | SMEPS-TRANSMIT-000261 | NA | Trade Partner | SME - Lightning Protection Drawings - IFA | 4 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 3009 | 2026-04-29 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-018153 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-29 | Auspan-TRANSMIT-000030 | NA | Consultant | Re: Update precast dowel layout for construction. | 1 | 0 | 0 | NA | APPROVED | 2026-04-29 | WF-000090 | NA | 2026-05-08 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000461 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-01 | ARCST-TRANSMIT-000139 | NA | Consultant | Cooling Tower Grating IFC Shop Drawings | 196 | 0 | 0 | NA | APPROVED |  | WF-003458 | NA | 2025-12-08 |  |  | 2026-02-02 | 2026-02-02 | KPTG-TRANSMIT-012370 | Closed | 196 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-15 | Entire M-TRANSMIT-000019 | NA | Trade Partner | Mechanical Shop Drawings Issued for Approval | 5 | 0 | 0 | NA | APPROVED | 2025-12-15 | WF-003634 |  | 2026-01-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | KPTG-TRANSMIT-016638 | NA | Trade Partner | Nilsen Penetration Seal Material (weather and fire) | 0 | 1 | 0 | NA | APPROVED | 2026-04-29 | WF-005485 | NA | 2026-05-14 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | Partners-TRANSMIT-000016 | NA | Trade Partner | Fwd: Balusterstyle Handrails for Core 7 | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Attachment is missing |  | 2026-04-29 | KPTG-RFI-007593 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-29 | WilsonPD-TRANSMIT-000023 | NA | Trade Partner | Re: Alternative fixtures for approval | 0 | 5 | 0 | NA | APPROVED | 2026-04-29 | WF-000566 | NA | 2026-05-08 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-003079 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-29 | GEMBA-D-TRANSMIT-000015 | NA | Consultant | Cooling tower gantry steelwork - For Certification | 3 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 166 | 2026-05-04 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-000437 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | PARR-TRANSMIT-000168 | NA | Trade Partner | Re P2685 - NDC M3 - Stage 4 - Battery Rooms - SCHEMATICS- IFA | 2 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 3011 | 2026-05-06 |  | The drawings have been submitted via Aconex review as requested by Rohit |  | 2026-05-04 | NA | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-29 | KPTG-SADV-001128 | NA | Trade Partner | Vinyl Skirting Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-04-29 | WF - 000383 | NA | 2026-05-04 |  | NA | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000787 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-29 | Auspan-TRANSMIT-000029 | NA | Trade Partner | Precast shop drawings for construction. | 13 | 0 | 0 | NA | APPROVED | 2026-04-29 | WF-000093 | NA | 2026-05-04 |  |  | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000338 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | INGEN3D-TRANSMIT-000702 | NA | Trade Partner | I3D-378 Next DC M3 Stage 4 - Ground Floor - R20 - IFC (29-04-2026) | 1 | 0 | 0 | NA | APPROVED | 2026-04-29 | WF-005489 | NA | 2026-05-07 |  | As requested by Finlay -WF terminated |  | 2026-06-09 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-29 | HDRAus-TRANSMIT-000471 | NA | Consultant | Stage 1 - Vehicle Trap Feancing | 3 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 4161 | 2026-05-01 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-017674 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-15 | Entire M-TRANSMIT-000018 | NA | Trade Partner | BACnet Gateway Technical Data Submittal | 0 | 1 | 0 | NA | APPROVED | 2025-12-15 | WF-003711 - (WF-003619-terminated) - WF-003772 |  | 2026-01-22 |  |  |  | 2026-01-15 | DRAFT-038785 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-29 | Tradetec-TRANSMIT-000433 | NA | Trade Partner | Tech Data - Site Wide - Pipemakers Multilayer Conduit | 0 | 1 | 0 | NA | APPROVED | 2026-04-29 | WF-005487 | NA | 2026-05-04 |  |  | 2026-05-12 | 2026-05-12 | KPTG-TRANSMIT-017198 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | INGEN3D-TRANSMIT-000703 | NA | Trade Partner | I3D-378 Next DC M3 Stage 4 - Acoustic Wall - R19 - IFC (29-04-2026) | 1 | 0 | 0 | NA | APPROVED | 2026-04-29 | WF-005490 | NA | 2026-05-06 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-019212 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-29 | RDSBIM-TRANSMIT-000006 | NA | Trade Partner | NXGE01 ¦ GROUND FLOOR CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 170 | 2026-05-04 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000442 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-29 | RDSBIM-TRANSMIT-000044 | NA | Trade Partner | MWYCCB ¦ GROUND FLOOR INTERNAL FITOUT PLAN LOBBY | 2 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 255 | 2026-05-04 |  | Bim360 review terminated by Moj |  | 2026-06-29 | KPTG-TRANSMIT-001362 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | D&E-TRANSMIT-000639 | NA | Trade Partner | SFN - IMI Balancing Valves - Issued for approval | 0 | 1 | 0 | NA | APPROVED | 2026-04-29 | WF-005492 | NA | 2026-05-05 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-016849 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | Partners-TRANSMIT-000017 | NA | Trade Partner | Baluster style Handrails for Core 7 | 3 | 0 | 0 | NA | APPROVED | 2026-04-29 | WF-005491 | NA | 2026-05-25 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-017505 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | D&E-TRANSMIT-000640 | NA | Trade Partner | Fwd: DDC Controllers and Modules - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-04-29 | KPTG-TRANSMIT-016652 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-29 | RDSBIM-TRANSMIT-000045 | SPARK-CRFI-KPG-000362 | Trade Partner | MWYCCB ¦ SITE STORAGE BUILDING GF & LEVEL 01 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 256 | 2026-05-04 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-000845 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-29 | SMEPS-TRANSMIT-000197 | NA | Trade Partner | SME Schedule Telecomunications IFC | 0 | 1 | 0 | NA | APPROVED | 2026-04-29 | WF - 000384 | NA | 2026-05-01 |  | NA | 2026-04-29 | 2026-04-29 | KPTG-TRANSMIT-000788 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | SKS Tech-TRANSMIT-000112 | NA | Trade Partner | Busduct Layout Data Halls | 4 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 3017 | 2026-05-07 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-018142 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2025-12-16 | Nilsen3-TRANSMIT-000096 | NA | Trade Partner | Nilsen Shop Drawings - As-Built | 1 | 0 | 0 | NA | APPROVED | [5 empty] | As-Built, No review required. Distributed to Project Team |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | Nilsen3-TRANSMIT-000129 | NA | Trade Partner | Nilsen Shop Drawings - IFC#2 | 20 | 0 | 0 | NA | APPROVED | 2026-04-22 | NA | 3018 | 2026-05-14 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-017171 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-04-29 | Nilsen3-TRANSMIT-000130 | NA | Trade Partner | M3 Stage -3 ROP3A and 3B Updated drawings | 0 | 1 | 0 | NA | APPROVED | 2026-04-29 | WF-005495 | NA | 2026-05-05 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-016983 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-04-29 | KPTG-TRANSMIT-002930 | NA | Trade Partner | Cassette System to bedrooms facing breezeways | 0 | 1 | 0 | NA | APPROVED | 2026-04-29 | WF - 01006 | NA | 2026-05-04 | 0 | File supersede and WF terminated. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | ACG-TRANSMIT-000082 | NA | Trade Partner | Fwd: M3 - Stage 4 Samples - IFC Revision | 0 | 43 | 0 |  | APPROVED | [5 empty] | IFC DOCUMENTS DISTRIBIUTED TO ALL |  | 2026-04-30 | KPTG-TRANSMIT-016721 | Closed | 43 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | ACG-TRANSMIT-000083 | NA | Trade Partner | Stage 4 Samples - IFA Revision | 0 | 1 | 0 | NA | APPROVED | 2026-04-29 | WF-005496 | NA | 2026-05-16 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-017713 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | ECBS-TRANSMIT-000037 | NA | Trade Partner | S4 Corridor Lintels Specification for approval | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Ref Number is missing |  | 2026-04-29 | KPTG-RFI-007603 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-29 | SMEPS-TRANSMIT-000028 | NA | Trade Partner | STAGE 9-11 Electrical Layouts (IFC) | 6 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 777 | 2026-05-06 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-003437 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | Tradetec-TRANSMIT-000434 | NA | Trade Partner | IFA - Stage 4 - HVP21 | 1 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 3020 | 2026-05-07 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-017949 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-29 | Rinco-TRANSMIT-000042 | NA | Consultant | GF and L5 to Roof General arrangement plan | 34 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 822 | 2026-05-08 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-001828 | Closed | 34 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-29 | Auspan-TRANSMIT-000252 | NA | Trade Partner | Update IFCed precast shop drawings for construction. | 16 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | ifc - No Review - update register and transmit KPTG-TRANSMIT-001553 |  | 2026-04-29 | KPTG-TRANSMIT-001553 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-15 | Civilex-TRANSMIT-000170 | NA | Trade Partner | Sample Submission - Stage 3 - 22KVA Switch Room - PascoFlex-PU25 | 0 | 1 | 0 | NA | APPROVED | 2025-12-15 | WF-003618 |  | 2026-01-01 |  |  |  | 2026-01-13 |  | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-29 | POTTSENG-TRANSMIT-000025 | NA | Trade Partner | GMAC HYDRAULIC SERVICES - PENETRATION - GROUND - ZONE 5 LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 824 | 2026-05-08 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-001581 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-29 | SES AU-TRANSMIT-000023 | NA | Trade Partner | SECURITY SERVICES LEVEL 1 COLO 5 FLOOR PLAN | 1 | 0 | 0 |  | REJECTED | [5 empty] | Document Number of the Drawing are incorrect. Requested to resubmit:KPTG-IntCorr-000323 |  | 2026-04-29 | KPTG-IntCorr-000323 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-29 | SES AU-TRANSMIT-000024 | NA | Trade Partner | Re: SECURITY SERVICES LEVEL 1 COLO 5 FLOOR PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-04-29 | WF-000185 | NA | 2026-05-04 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000549 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-29 | ARCH-TRANSMIT-000043 | NA | Consultant | Re: 2026.04.24_Issued for Construction (FC-01) | 0 | 1 | 0 | NA | APPROVED | 2026-04-29 | NA | 175 | 2026-05-04 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-000374 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-29 | M.S.-TRANSMIT-000062 | NA | Trade Partner | IFA Shop drawing MS-26B | 1 | 0 | 0 | KPTG-IntCorr-007331 | APPROVED | 2026-05-02 | NA | 229 | 2026-05-08 |  | KAPITOL ADVICE AWAITS: KPTG-IntCorr-007331 | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-002952 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-29 | M.S.-TRANSMIT-000061 | NA | Trade Partner | IFC Shop drawings for MS-26 | 4 | 0 | 0 | KPTG-IntCorr-007330 | APPROVED |  | na | na |  |  | ifc drawing have been transmitted to all parties:KPTG-TRANSMIT-002810 |  | 2026-04-29 | KPTG-TRANSMIT-002810 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-29 | GHD-TRANSMIT-000008 | NA | Consultant | GE1 IFC Security Services Documentation | 19 | 0 | 0 | NA | REJECTED | [5 empty] | drawings should be reissued as FC-2 drawings should be ‘clean’ i.e. not have ACC issue pins on them drawings should capture the requests from the first ACC review i.e update the backgrounds which are still outdated |  | 2026-04-29 | KPTG-DA-000589 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-29 | ARCH-TRANSMIT-000147 | NA | Consultant | MLC - SPR - Stage 2 & Other Drawing Update | 43 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 217 | 2026-05-04 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-002835 | Closed | 43 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | FNSTR8-TRANSMIT-000010 | NA | Trade Partner | M3 S4 - Stage 4 Facade Additional Samples | 0 | 5 | 0 | NA | APPROVED | 2026-04-29 | WF-005498 | NA | 2026-05-26 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-018085 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-29 | Jangho-TRANSMIT-000050 | NA | Trade Partner | 20260426 671 Chapel St Project PMU shop drawings[02 | 47 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 442 | 2026-05-08 |  | Review voided; As informed by Kaptol PC , Trade partner is going to supersede the Shop Drawings. | 2026-05-25 | 2026-05-25 | NA | Closed | 47 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-11 | Facx-TRANSMIT-000009 | NA | Trade Partner | Expanded Mesh Detail - Rev - 1 | 6 | 1 | 0 | NA | REJECTED | [5 empty] | Two different type of documents in the transmittal |  | 2025-12-11 | KPTG-DA-003884 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-29 | RBG-TRANSMIT-000062 | NA | Consultant | : Structural drawings - Update Steelwork drawings to capture certifier's comments | 7 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 444 | 2026-05-01 |  | Review Void as advised by project coordinator - no review required. | 2026-04-30 | 2026-04-30 | NA | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-29 | RBG-TRANSMIT-000060 | NA | Consultant | Latest Structural Drawings for Podium and Tower Steelwork - Issued for Construction | 10 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 445 | 2026-05-01 |  |  | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-001454 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-29 | KPTG-TRANSMIT-000865 | NA | Trade Partner | Level 01 - Level 20 Penetrations [ LGCE] | 2 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 447 | 2026-05-08 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-001060 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-29 | KETE-TRANSMIT-000130 | NA | Trade Partner | GL-04 sample form updated | 0 | 1 | 0 | NA | APPROVED | 2026-04-29 | WF-000747 | NA | 2026-05-04 |  | KPTG-IntCorr-000958- waiting for latest updation. KPTG-IntCorr-001053-As per instruction from Ashlin, we have terminated the workflow.Reason: The product is being replaced with an alternative in the sample form. | 2026-06-10 | 2026-06-10 | KPTG-IntCorr-001053 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | FNSTR8-TRANSMIT-000011 | NA | Trade Partner | Re: Shop Drawings_Link Bridge | 5 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due to incorrect revision number |  | 2026-04-29 | KPTG-DA-006274 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-29 | Auspan-TRANSMIT-000068 | NA | Trade Partner | Revised shop drawings issued for construction | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-SADV-003929-As per the direction Ashlin, I have updated this drawing into Document Register and transmitted to all concerned parties. | 2026-04-28 | 2026-04-28 | KPTG-SADV-003929 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-30 | Auscool-TRANSMIT-000091 | NA | Trade Partner | Mechanical Shop Drawings updated to suit Cold Shell | 6 | 0 | 0 | NA | APPROVED | 2026-04-30 | NA | 641 | 2026-05-07 |  | KPTG-IntCorr-001004-as instruction from mark we terminate the workflow. | 2026-05-28 | 2026-05-28 | KPTG-IntCorr-001004 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-01 | Highbu-TRANSMIT-000050 | NA | Trade Partner | Levels 3-9 Penetration Layouts - IFA | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-SADV-003952-Waiting for the DWFX file. KPTG-IntCorr-000927-The documents have only been updated in the document register and transmitted to all parties. |  | 2026-05-01 | KPTG-IntCorr-000927 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-19 | KETE-TRANSMIT-000119 | NA | Trade Partner | Kete - Tower IFC Shop Drawing | 71 | 0 | 0 | NA | APPROVED | 2026-03-20 | NA | 608 | 2026-03-24 |  | KPTG-SADV-003934-As per the direction from the ashlin, we have terminated the BIM workflow: If you have any quaries on this, please coordinate with Kapitol Team This is for information.29-04-2026 | 2026-04-29 | 2026-04-29 | KPTG-SADV-003934 | Closed | 71 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-19 | KETE-TRANSMIT-000122 | NA | Trade Partner | Kete - Updated Cast-in Drawings 2nd | 5 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 609 | 2026-03-26 |  | KPTG-SADV-003936-As per the direction from the Ashlin, we have terminated the BIM workflow: If you have any quaries on this, please coordinate with Kapitol Team This is for information.29-04-2026 | 2026-04-29 | 2026-04-29 | KPTG-SADV-003936 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-11 | Tradetec-TRANSMIT-000299 | NA | Trade Partner | Penstock Valve - Shop Drawings - Stage 2 | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with the document number |  | 2025-12-11 | KPTG-DA-003885 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | FNSTR8-TRANSMIT-000012 | NA | Trade Partner | Shop Drawings_Curtain Wall | 13 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 3022 | 2026-04-10 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-017941 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | FNSTR8-TRANSMIT-000013 | NA | Trade Partner | Shop Drawings_Punch Windows | 7 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 3024 | 2026-05-10 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-017954 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-29 | Stowe-A-TRANSMIT-000571 | NA | Trade Partner | Stowe - Tech Data - IFC - HV SWITCHROOM EARTH BAR TEST LINKS - Shop drawing | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2026-04-29 | KPTG-TRANSMIT-016666 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-29 | D&E-TRANSMIT-000239 | SPARK-CRFI-KPG-000313 | Trade Partner | MWYCCB - CHILLED & HEATING HOT WATER SCHEMATICS - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 257 | 2026-05-04 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000904 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-29 | RDSBIM-TRANSMIT-000136 | NA | Trade Partner | MLCSPR ¦ BULK EXCAVATION AND RETENTION PLAN AND EXCAVATION-STAGE 2 | 5 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 215 | 2026-05-04 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-002932 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-29 | TGRF-TRANSMIT-000112 | NA | Trade Partner | Stage 2 IFA Plans | 47 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 286 | 2026-05-04 |  |  | 2026-06-01 | 2026-06-01 | TGRF-TRANSMIT-000112 | Closed | 47 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-29 | KPTG-IntCorr-001200 | NA | Consultant | Building Permits by BCA Concepts | 0 | 4 | 0 | NA | APPROVED |  | NA | NA |  |  | Updated Aconex - Sent to nextdc - |  | 2026-04-29 | KPTG-TRANSMIT-003595 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-29 | VinageC-TRANSMIT-000011 | NA | Trade Partner | Signage Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-04-29 | WF-001033 | NA | 2026-05-04 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-003656 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-30 | Auspan-TRANSMIT-000032 | NA | Trade Partner | Re: Precast shop drawings for construction. | 9 | 0 | 0 | NA | APPROVED | 2026-04-30 | WF-000097 | NA | 2026-05-11 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-000379 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-30 | SMEPS-TRANSMIT-000198 | NA | Trade Partner | SME Shop Drawing Electrical IFC B | 4 | 0 | 0 | NA | APPROVED | 2026-04-30 | WF - 000385 | NA | 2026-05-05 |  | NA | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-000790 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-11 | D&E-TRANSMIT-000311 | NA | Trade Partner | Mechanical IFA Shop Drawing | 1 | 0 | 0 | NA | APPROVED | 2025-12-11 | NA | 3490 | 2025-12-22 |  |  | 2026-01-28 | 2026-01-28 | KPTG-TRANSMIT-012018 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-30 | Nilsen3-TRANSMIT-000131 | NA | Trade Partner | Updated Earth bar samples | 0 | 2 | 0 | NA | APPROVED | 2026-04-30 | WF-005501 | NA | 2026-05-21 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-016841 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-29 | TTW-TRANSMIT-000149 | NA | Consultant | BP4 - Issued for Certification Update | 27 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 503 | 2026-05-01 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-001452 | Closed | 27 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-29 | Firesafe-TRANSMIT-000006 | NA | Consultant | Level 10 Hydraulic Calculation (stage 1) IFA | 0 | 1 | 0 | NA | APPROVED | 2026-04-29 | WF-000402 | NA | 2026-05-01 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-001759 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-29 | Civilex-TRANSMIT-000081 | NA | Consultant | Hydraulic Shop Drawings - Water | 1 | 0 | 0 | NA | APPROVED |  |  | 517 | 2026-05-06 |  | rejected : DRAWING ORIENTATION WRONG AND REVISION HISTORY TABLE MISSING-KPTG-TRANSMIT-001406 | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-001595 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-29 | RED Fire-TRANSMIT-000008 | NA | Consultant | Fire Engineering Report - Draft for review | 0 | 1 | 0 | NA | APPROVED | 2026-04-29 | WF-000403 | NA | 2026-05-01 |  | Terminated and send back as per RED Fire-RTRFI-000105 | 2026-05-25 | 2026-05-25 | DRAFT-009978 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-30 | Auspan-TRANSMIT-000033 | NA | Trade Partner | Precast shop drawings for construction. | 10 | 0 | 0 | NA | REJECTED | [5 empty] | Document number mentioned wrongly |  | 2026-04-30 | KPTG-DA-000592 | Closed | 10 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-30 | KALLIBRE-TRANSMIT-000003 | NA | Trade Partner | 6 Hinged Frames Spacing - Updated Document Number | 1 | 0 | 0 | NA | REJECTED | [5 empty] | DOCUMENT NUMBER HAS NOT BEEN MENTIONED IN THE DRAWING, REQUESTED TO RESUBMIT:KPTG-IntCorr-000331 |  | 2026-04-30 | KPTG-IntCorr-000331 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-30 | SMEPS-TRANSMIT-000200 | NA | Trade Partner | Copper ITP sheets MEL05 | 0 | 1 | 0 | NA | APPROVED | 2026-04-30 | WF - 000386 | NA | 2026-05-05 |  | NA | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-000804 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-30 | KALLIBRE-TRANSMIT-000004 | NA | Trade Partner | 6 Hinged Door Frame Spacing Detail | 1 | 0 | 0 | NA | APPROVED | 2026-04-30 | WF-000186 | NA | 2026-05-08 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-000613 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-30 | SMEPS-TRANSMIT-000199 | NA | Trade Partner | SPLICE AND TEST ITP SHEETS. | 0 | 1 | 0 | NA | APPROVED | 2026-04-30 | WF - 000387 | NA | 2026-05-05 |  | NA | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-000795 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-10 | OveArup-TRANSMIT-000138 | NA | Consultant | M3 Stage 3 HV Interim Supply Drawings Update | 10 | 0 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-30 | ADP-TRANSMIT-000062 | NA | Consultant | Drawing NLIU | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | NLIU |  | 2026-04-30 | KPTG-TRANSMIT-000357 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-29 | WAM-TRANSMIT-000756 | NA | Consultant | A16 Facade Setout Plans - Facade Type Finishes | 26 | 0 | 0 | NA | APPROVED | 2026-04-29 | NA | 505 | 2026-05-01 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-002106 | Closed | 26 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-29 | WAM-TRANSMIT-000756 | NA | Consultant | A16 Facade Setout Plans - Facade Type Finishes | 0 | 1 | 0 | NA | APPROVED | 2026-04-29 | WF-000404 | NA |  |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-002027 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-30 | Entire M-TRANSMIT-000041 | NA | Trade Partner | Mechanical drawings IFC | 10 | 0 | 0 | NA | APPROVED | 2026-04-30 | WF-000187 | NA | 2026-05-04 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-000571 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-30 | NXT-TRANSMIT-001523 | NA | Trade Partner | ABB PDUs - AU-10025007 M3-C-Stage 4 / Ph1 - Quality Documents | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-04-30 | KPTG-TRANSMIT-016679 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-30 | FNSTR8-TRANSMIT-000014 | NA | Trade Partner | Shop Drawings_Link Bridge | 5 | 0 | 0 | NA | APPROVED | 2026-04-30 | NA | 3026 | 2026-05-18 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-017938 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-30 | RDSBIM-TRANSMIT-000010 | NA | Trade Partner | MEL11C45 ¦ LEVEL 02 COLO 4 AREA RCP LAYOUT | 6 | 0 | 0 | NA | APPROVED | 2026-04-30 | WF-000188 | NA | 2026-05-06 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-000590 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-30 | WilsonPD-TRANSMIT-000026 | NA | Trade Partner | Chlorine Dosing Pump Set Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-04-30 | WF-000577 | NA | 2026-05-11 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-002838 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-30 | SMEPS-TRANSMIT-000201 | NA | Trade Partner | SME Shop Drawing Electrical IFC B | 3 | 0 | 0 | NA | APPROVED | 2026-04-30 | WF - 000388 | NA | 2026-05-05 |  | NA | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-000796 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-30 | RDSBIM-TRANSMIT-000009 | NA | Trade Partner | MEL11C45 ¦ LEVEL 01 AND LEVEL 02 COLO 5A, 4 & 5B SCREED LAYOUT | 3 | 0 | 0 | NA | APPROVED | 2026-04-30 | WF-000189 | NA | 2026-05-06 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-000524 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-11 | Tradetec-TRANSMIT-000300 | NA | Trade Partner | Penstock Shop Drawing - PS400 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Revision inside and outside seems different |  | 2025-12-11 | KPTG-DA-003886 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-30 | ASV-TRANSMIT-000170 | NA | Trade Partner | Hydraulic Sample - Hot Water Circulation Pump | 0 | 1 | 0 | NA | APPROVED | 2026-04-30 | WF-005503 | NA | 2026-05-14 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-017368 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-30 | SMEPS-TRANSMIT-000202 | NA | Trade Partner | TELECOMMUNICATIONS - SITE TELECOMS VAULT CABLE ROUTING LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-04-30 | WF - 000389 | NA | 2026-05-05 |  | NA | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-000801 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-30 | VERTIV-TRANSMIT-000006 | NA | Trade Partner | NEXT DC GE01 _ MECHANICAL MATERIAL SUBMISSION | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-04-30 | KPTG-SADV-000253 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-30 | D&E-TRANSMIT-000642 | NA | Trade Partner | NXM3S4 - Upper Roof & Roof - CHW Pipe Layout - Zone 4 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-30 | NA | 3028 | 2026-05-08 |  | As requested by Ellie — Terminated — KPTG-IntCorr-013787 |  | 2026-05-26 | KPTG-IntCorr-013787 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-30 | D&E-TRANSMIT-000643 | NA | Trade Partner | NXM3S4 - Upper Roof - CHW Pipe Layout - Zone 3 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-30 | NA | 3030 | 2026-05-08 |  | As requested by Ellie — Terminated — KPTG-IntCorr-013787 |  | 2026-05-26 | KPTG-IntCorr-013787 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-30 | D&E-TRANSMIT-000644 | NA | Trade Partner | NXM3S4 - Upper Roof & Roof - CHW Pipe Layout Zones - Issued For Construction #3032 | 2 | 0 | 0 | NA | APPROVED | 2026-04-30 | NA | 3032 | 2026-05-08 |  | As requested by Ellie — Terminated — KPTG-IntCorr-013787 |  | 2026-05-26 | KPTG-IntCorr-013787 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-30 | SMEPS-TRANSMIT-000203 - | NA | Trade Partner | 32A Switched Isolators | 0 | 1 | 0 | NA | APPROVED | 2026-04-30 | WF - 000390 | NA | 2026-05-04 |  | NA | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-000825 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-04-30 | RDSBIM-TRANSMIT-000194 | NA | Trade Partner | LINDRUM ¦ GROUND LEVEL - BLOCK WALL ELEVATION PLAN AND ELEVATION | 2 | 0 | 0 | NA | APPROVED | 2026-04-30 | NA | 642 | 2026-05-07 |  | KPTG-IntCorr-000943-As per the direction from Charlie RDS needs to submit latest revision. | 2026-05-06 | 2026-05-06 | KPTG-IntCorr-000943 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-30 | VAE-Grp-TRANSMIT-000157 | NA | Trade Partner | MECHANICAL - GR LAYOUT & L5 LAYOUT + BWS | 3 | 0 | 0 | NA | APPROVED | 2026-04-30 | NA | 1248 | 2026-05-04 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-003640 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-30 | WilsonPD-TRANSMIT-000028 | NA | Trade Partner | Resubmittal of clips, fixing, rod strut tech data | 0 | 1 | 0 | NA | APPROVED | 2026-04-30 | WF-000585 | NA | 2026-05-11 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-002854 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-11 | D&E-TRANSMIT-000313 | NA | Trade Partner | MCC Electrical Drawings - Issued for Review | 3 | 0 | 0 | NA | APPROVED | 2025-12-11 | NA | 3494 | 2025-12-22 |  |  | 2026-02-24 | 2026-02-24 | KPTG-TRANSMIT-013490 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-30 | D&E-TRANSMIT-000645 | NA | Trade Partner | NXM3S4 - Upper Roof & Roof - CHW Pipe Layout Zones + East String Pipe Sections - Issued For Approval | 7 | 0 | 0 | NA | APPROVED | 2026-04-30 | NA | 3036 | 2026-05-08 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-017783 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-30 | D&E-TRANSMIT-000240 | NA | Trade Partner | MECHANICAL SWITCHBOARD DRAWINGS | 0 | 4 | 0 | NA | REJECTED | [5 empty] | Front page is missing |  | 2026-04-30 | KPTG-SADV-004454 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-30 | D&E-TRANSMIT-000241 | SPARK-CRFI-KPG-000386 | Trade Partner | MSSB INTERNAL COMPONENTS | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-04-30 | Entire M-TRANSMIT-000033 | NA | Trade Partner | Battery Room Schematics Issued for Construction | 4 | 0 | 0 | NA | APPROVED | 2026-04-30 | WF - 000392 | NA | 2026-05-05 |  | NA | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-000830 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-30 | Auspan-TRANSMIT-000035 | NA | Trade Partner | Re: Precast shop drawings for constrution. | 4 | 0 | 0 | NA | APPROVED | 2026-04-30 | WF-000098 | NA | 2026-05-11 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-000404 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-30 | WilsonPD-TRANSMIT-000186 | SPARK-CRFI-KPG-000666 | Trade Partner | Cast Iron Pipe | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-000829 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-30 | Auspan-TRANSMIT-000034 | NA | Trade Partner | Update precast shop drawings for construction | 6 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-04-30 | DRAFT-001565 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-30 | Hames-TRANSMIT-000157 | NA | Consultant | Stage 2 - Roof Swale and Gutter Detail | 1 | 0 | 0 | NA | APPROVED | 2026-04-30 | NA | 1250 | 2026-05-04 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-003606 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-30 | Appselec-TRANSMIT-000078 | NA | Trade Partner | AFL Telecom BOM - Issued For Construction | 0 | 1 | 0 | NA | APPROVED | 2026-04-30 | WF-000191 | NA | 2026-05-01 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-000527 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-30 | D&E-TRANSMIT-000242 | NA | Trade Partner | CONTROL VALVES | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document attached is different |  | 2026-04-30 | KPTG-TRANSMIT-000773 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-01 | ARCST-TRANSMIT-000139 | NA | Consultant | Cooling Tower Grating IFC Shop Drawings | 99 | 0 | 0 | NA | APPROVED |  | WF-003459 | NA | 2025-12-08 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-16 | D&E-TRANSMIT-000289 | NA | Trade Partner | Technical Data Submission - Max Cool Sensors | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC, No review required, distributed to the Project Team. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-30 | PARR-TRANSMIT-000170 | NA | Trade Partner | P2649 - KPG NDC M3 - Stage 2 - Fuel - DFS OMM, CERTIFICATE AND WARRANTY | 0 | 3 | 0 | NA | APPROVED | 2026-04-30 | WF-005509 | NA | 2026-05-13 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-017568 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-30 | Baigents-TRANSMIT-000083 | NA | Trade Partner | MCC secondary steel - Baigents | 17 | 0 | 0 | KPTG-SADV-004451 | APPROVED | 2026-05-14 | NA | 282 | 2026-05-21 |  | Actual Date 28/04/2026 IFA & IFR not submitted before IFC |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-30 | D&E-TRANSMIT-000243 | SPARK-CRFI-KPG-000540 | Trade Partner | CONTROL THERMOSTAT | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-05-27 | 2026-05-27 | KPTG-TRANSMIT-000945 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-30 | INTRFRM-TRANSMIT-000028 | NA | Trade Partner | Tech Data Submission - Floor Boxes & Earthbridges | 0 | 1 | 0 | NA | APPROVED | 2026-04-30 | WF-000099 | NA | 2026-05-08 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-000609 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-30 | Schindle-TRANSMIT-000017 | NA | Trade Partner | Schindler - Hall Button Unit - IFC | 1 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-04-30 | KPTG-TRANSMIT-000774 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-30 | INTRFRM-TRANSMIT-000029 | NA | Trade Partner | Tech Data Submission - Strip Drains | 0 | 1 | 0 | NA | APPROVED | 2026-04-30 | WF-000100 | NA | 2026-05-08 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-000604 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-30 | PARR-TRANSMIT-000172 | NA | Trade Partner | NDC M3 - Stage 4 - Battery Rooms - DSH & FIRE SPRINKLER SYSTEM | 0 | 3 | 0 | NA | APPROVED | 2026-04-30 | WF-005515 | NA | 2026-05-06 |  | WF-005510 - Terminated | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-017004 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-30 | PARR-TRANSMIT-000173 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - COG & LIFTING DIAGRAM and PREACTION SYSTEM LAYOU | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Requested for IFA |  | 2026-05-01 | KPTG-RTRFI-004044 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-30 | SMEPS-TRANSMIT-000197 | NA | Trade Partner | Submains cabling | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Disregard as per Peter advise - KPTG-IntCorr-002862 |  | 2026-04-30 | KPTG-IntCorr-002862 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-30 | Syfon1-TRANSMIT-000005 | NA | Trade Partner | Syfon Drawings Issued for Construction | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Error in drawing number |  | 2026-04-30 | KPTG-TRANSMIT-000775 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-11 | D&E-TRANSMIT-000312 | NA | Trade Partner | Updated Mech fans IFA | 0 | 1 | 0 | NA | APPROVED | 2025-12-12 | WF-003574 | NA | 2025-12-26 |  |  | 2026-01-23 | 2026-01-23 | KPTG-TRANSMIT-011831 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-30 | POTTSENG-TRANSMIT-000026 | NA | Trade Partner | HYDRAULIC SERVICES - PENETRATION - GROUND - ZONE 2 LAYOUT | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | ifc - No Review required as advised by Amee. Registered & Distributed.KPTG-TRANSMIT-001594 | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-001594 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-30 | JCBa-TRANSMIT-000101 | NA | Consultant | IFC - A-41 - LIFT CORE 3, STAIR 3 | 2 | 0 | 0 | NA | APPROVED | 2026-04-30 | NA | 827 | 2026-05-11 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-001831 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-30 | Auspan-TRANSMIT-000254 | NA | Trade Partner | Update already IFCed shop drawings for construction | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | ifc - No Review required- update register and transmit - KPTG-TRANSMIT-001566 | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-001566 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-30 | Auspan-TRANSMIT-000255 | NA | Trade Partner | Precast shop drawings for aprpoval | 54 | 0 | 0 | NA | APPROVED | 2026-04-30 | NA | 832 | 2026-05-11 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-001745 | Closed | 54 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-30 | Auspan-TRANSMIT-000256 | NA | Trade Partner | Resubmit precast shop drawing 0G360 for approval | 1 | 0 | 0 | NA | APPROVED | 2026-04-30 | NA | 830 | 2026-05-11 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-001702 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-04-30 | Auspan-TRANSMIT-000257 | NA | Trade Partner | Update already IFCed shop drawings for construction | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | ifc - No Review required- update register and transmit - KPTG-TRANSMIT-001592 | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-001592 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-30 | PARR-TRANSMIT-000171 | NA | Trade Partner | Re: P2680 - NDC M3 Stage 4 - Fuel - BFS SCHEMATIC & PUMP ROOM A/B GA | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect status and previous revisions are not mentioned in revision history |  | 2026-04-30 | KPTG-RFI-007629 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-30 | Appselec-TRANSMIT-000079 | NA | Trade Partner | MEL11C45 - COLO 5 Cell 4 - Lighting, Containment & Earth Layout & Cell 3 - Containment Layout - IFC | 4 | 0 | 0 | NA | APPROVED | 2026-04-30 | WF-000192 | NA | 2026-05-05 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-000518 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-30 | D&E-TRANSMIT-000641 | NA | Trade Partner | HS1 OFFICE AS BUILT DRAWINGS | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with the revision format & IFC not approved before As-Built. |  | 2026-04-30 | KPTG-SADV-005143 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-30 | D&E-TRANSMIT-000646 | NA | Trade Partner | Re: DX Air Conditioning and VRF Air Conditioning - Issued for Construction | 0 | 2 | 0 | NA | REJECTED | [5 empty] | The revision was already received for the previous review |  | 2026-04-30 | KPTG-RFI-007630 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-11 | D&E-TRANSMIT-000308 | NA | Trade Partner | Daikin unit tech data (D&E return comments) | 0 | 1 | 0 | NA | APPROVED | 2025-12-12 | WF-003575 | NA | 2025-12-26 |  |  | 2026-01-28 | 2026-01-28 | KPTG-TRANSMIT-011964 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-30 | Appselec-TRANSMIT-000080 | NA | Trade Partner | MEL11C45 - COLO 5 Cell 4 - Power Layout - IFA | 1 | 0 | 0 | NA | APPROVED | 2026-04-30 | WF-000193 | NA | 2026-05-05 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000560 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-30 | PARR-TRANSMIT-000057 | NA | Trade Partner | Fuel Services - FUEL RETICULATION PUMP ROOMS, LOWER GROUND GA AND L4 SECTIONS PENOS | 5 | 0 | 0 | NA | APPROVED | 2026-04-30 | NA | 1254 | 2026-05-05 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-003632 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-04-30 | NXT-TRANSMIT-000397 | NA | Client | 10693-000231 -As Built issued for Information - type 5 COP-DA Quality plan | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Distribution only |  | 2026-04-30 | Awaiting approval | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-30 | LGCE-TRANSMIT-000022 | NA | Trade Partner | IFC peno drawings rest of building | 1 | 0 | 0 | NA | APPROVED | 2026-04-30 | NA | 448 | 2026-05-07 |  |  | 2026-06-03 | 2026-06-03 | LGCE-TRANSMIT-000022 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-30 | crossfir-TRANSMIT-000009 | NA | Trade Partner | Wet Fire - Schematic | 1 | 0 | 0 | NA | APPROVED | 2026-04-30 | NA | 450 | 2026-05-07 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-000925 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-04-30 | crossfir-TRANSMIT-000010 | NA | Trade Partner | Wet Fire - Penetration Ground IFC | 1 | 0 | 0 | NA | APPROVED | 2026-04-30 | NA | 452 | 2026-05-07 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-001062 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-04-23 | Aurecon-TRANSMIT-000107 | NA | Consultant | MCSE Specifications & Schedules | 0 | 8 | 0 | NA | REJECTED |  | NA | NA |  |  | Naming convensions not matching |  | 2026-04-27 | KPTG-DA-000153 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-30 | Eneraque-TRANSMIT-000011 | NA | Trade Partner | Document Package Submission #1 | 0 | 16 | 0 | NA | APPROVED | 2026-04-30 | WF-000587 | NA | 2026-05-11 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-003089 | Closed | 16 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-30 | SMEPS-TRANSMIT-000029 | NA | Trade Partner | SME Sample Submissions for Approval | 0 | 4 | 0 | NA | APPROVED | 2026-04-30 | WF-000586 | NA | 2026-05-11 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-002970 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-30 | WilsonPD-TRANSMIT-000027 | NA | Trade Partner | Valves & Flow Control Devices Tech Data | 0 | 6 | 0 | NA | APPROVED | 2026-04-30 | WF-000584 | NA | 2026-05-08 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-002847 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-12 | Stowe-A-TRANSMIT-000414 | NA | Trade Partner | Stowe - Drawing Submission - HS1 Office Stage 1 Containment Drawings - 26.11.2025 | 1 | 0 | 0 | NA | APPROVED | 2025-12-12 | NA | 3497 | 2025-12-23 |  |  | 2026-01-12 | 2026-01-13 | KPTG-TRANSMIT-011382 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-30 | WGAVIC-TRANSMIT-000108 | NA | Consultant | M2 - Stage 11 Wall Elevation and Stage 2 Tank Slab - Issued for Construction | 2 | 0 | 0 | NA | APPROVED | 2026-04-30 | NA | 779 | 2026-05-05 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-002760 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-30 | VIA Arch-TRANSMIT-000111 | NA | Consultant | M2 - S11 Wall Setout and RCP CD05 Building Permit Issue | 7 | 0 | 0 | NA | APPROVED | 2026-04-30 | NA | 781 | 2026-05-05 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-002659 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-30 | Auspan-TRANSMIT-000100 | NA | Trade Partner | Update precast marking plans and elevations for approval. | 2 | 0 | 0 | KPTG-SADV-004223 | REJECTED | [5 empty] | Kapitol Advice awaits: KPTG-SADV-004223: Document Needs to be updated:KPTG-SADV-004245 |  | 2026-05-01 | KPTG-SADV-004245 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-04-30 | CLADC-TRANSMIT-000024 | NA | Trade Partner | Door leaf shop drawings | 26 | 0 | 0 | NA | APPROVED | 2026-04-30 | NA | 490 | 2026-05-06 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-002999 | Closed | 26 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-01 | Auspan-TRANSMIT-000036 | na | Trade Partner | Update IFCed precast shop drawings. | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong numbering of document |  | 2026-05-01 | KPTG-SADV-000258 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-01 | INTRFRM-TRANSMIT-000030 | NA | Trade Partner | Tech Data Submission - Floor Wastes | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-000101 | na | 2026-05-11 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-000608 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-29 | Auspan-TRANSMIT-000029 | NA | Trade Partner | Precast shop drawings for construction. | 10 | 0 | 0 | NA | APPROVED | 2026-04-29 | WF-000093 | NA | 2026-05-04 |  |  | 2026-04-30 | 2026-04-30 | KPTG-TRANSMIT-000391, KPTG-TRANSMIT-000416 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-29 | Auspan-TRANSMIT-000029 | NA | Trade Partner | Precast shop drawings for construction. | 3 | 0 | 0 | NA | APPROVED | 2026-04-29 | WF-000093 | NA | 2026-05-04 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-01 | ADP-IntCorr-000314 | NA | Consultant | SME O & M manual | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-001000 | NA | 2026-05-08 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-01 | ACG-TRANSMIT-000084 | NA | Trade Partner | M3 Stage 2 - Anti-Tail Gate Sample - IFC | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-005514 | NA | 2026-05-08 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-017697 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-12 | Stowe-A-TRANSMIT-000414 | NA | Trade Partner | Stowe - Drawing Submission - HS1 Office Stage 1 Containment Drawings - 26.11.2025 - TEL | 1 | 0 | 0 | NA | APPROVED | 2025-12-12 | NA | 3498 | 2025-12-19 |  |  | 2026-02-20 | 2026-02-23 | KPTG-TRANSMIT-013353 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-01 | KPTG-TRANSMIT-002933 | NA | Trade Partner | Bike repair Stand | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF - 01007 | NA | 2026-05-07 |  | File supersede and WF terminated. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-01 | D&E-TRANSMIT-000647 | NA | Trade Partner | MaxCool FD - Issued for Construction | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Stamps in previous version is missing in the document |  | 2026-05-01 | KPTG-SADV-005144 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-01 | D&E-TRANSMIT-000649 | NA | Trade Partner | Sub-Circuit Cable Schedule - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-005516 | NA | 2026-05-22 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-017722 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-01 | TTW-TRANSMIT-000151 | NA | Consultant | BP1 - Issued for Construction update | 5 | 0 | 0 | NA | APPROVED | 2026-04-30 | NA | 509 | 2026-05-05 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-001649 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-01 | D&E-TRANSMIT-000650 | NA | Trade Partner | Sanitary Ball Valves and Sanitary Butterfly Valves - Issued for approval | 0 | 2 | 0 | NA | APPROVED | 2026-05-01 | WF-005517 | NA | 2026-05-25 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-017167 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-27 | D&E-TRANSMIT-000536 | NA | Trade Partner | BMS System Architecture & Points Lists - Issued for Approval | 0 | 5 | 0 | NA | APPROVED | 2026-03-27 | WF-005047 | NA | 2026-04-17 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-01 | Syfon1-TRANSMIT-000006 | SPARK-CRFI-KPG-000467 | Trade Partner | Revised Syfon Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 259 | 2026-05-08 |  | Bim360 review terminated by Lawden Constructed |  | 2026-08-25 | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-01-15 | SKS Tech-TRANSMIT-000003 | NA | Trade Partner | M3-ELC-SKS-SA-C-0400-0004 Subcircuit Cabling | 0 | 1 | 0 | NA | APPROVED | 2026-01-15 | WF-005205 | NA | 2026-05-01 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-016752 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-01 | Appselec-TRANSMIT-000081 | NA | Trade Partner | Wesco BOM (Rev 2) - Issued For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-000195 | NA | 2026-05-07 |  |  | 2026-05-12 | 2026-05-12 | KPTG-TRANSMIT-000601 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-01 | SES AU-TRANSMIT-000025 | NA | Trade Partner | SECURITY SERVICES LEVEL 2 COLO 5 FLOOR PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-05-01 | WF-000196 | NA | 2026-05-07 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000543 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-11-12 | LANSA-TRANSMIT-000058 | NA | Trade Partner | Level 3 Water Issued for Approval | 2 | 0 | 0 | NA | APPROVED | 2025-11-13 | WF-000729 | 465 | 2025-11-20 |  |  | 2025-12-16 | 2025-12-16 | KPTG-DA-002275 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-01 | Tradetec-TRANSMIT-000435 | na | Trade Partner | Tech Data - Stage 2 - Bitac Primer | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Difference in discipline inside the document and Aconex submission |  | 2026-05-01 | KPTG-SADV-005150 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-30 | Jangho-TRANSMIT-000031 | NA | Trade Partner | Window Hardware Sample Submission | 0 | 6 | 0 | NA | APPROVED | 2026-04-30 | WF-000409 | NA | 2026-05-04 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-002013 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-30 | Jangho-TRANSMIT-000032 | NA | Trade Partner | Brick Sample Submission | 0 | 5 | 0 | NA | APPROVED | 2026-04-30 | WF-000408 | NA | 2026-05-05 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-001525 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-30 | Jangho-TRANSMIT-000030 | NA | Trade Partner | FT13 PMU Comparison Report | 0 | 1 | 0 | NA | APPROVED | 2026-04-30 | WF-000407 | NA | 2026-05-05 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-001569 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-30 | Jangho-TRANSMIT-000029 | NA | Trade Partner | FT04 PMU Comparison Report | 0 | 1 | 0 | NA | APPROVED | 2026-04-30 | WF-000406 | NA | 2026-05-05 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-001570 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-01 | VIA Arch-TRANSMIT-000029 | NA | Trade Partner | 22kV Switchroom Door Finishes Update | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | The register has been updated. If any further action is required, the coordinator will inform. |  | 2026-05-01 | KPTG-TRANSMIT-016761 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-30 | INGEN3D-TRANSMIT-000051 | NA | Trade Partner | Level 4-6 - Precast Columns - IFC | 56 | 0 | 0 | NA | APPROVED | 2026-04-30 | WF-000410, WF-000414 | NA | 2026-05-05 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-001619 | Closed | 56 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-30 | INGEN3D-TRANSMIT-000052 | NA | Trade Partner | Level 4-6 - Precast Columns - No Longer In Use | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | no longer in use - forwarded to all parties |  | 2026-04-30 | KPTG-TRANSMIT-001441 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-30 | INGEN3D-TRANSMIT-000053 | NA | Trade Partner | Level 3-5 - Precast Columns - IFC | 56 | 0 | 0 | NA | APPROVED | 2026-04-30 | WF-000411 | NA | 2026-05-05 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-001638 | Closed | 56 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-30 | INGEN3D-TRANSMIT-000054 | NA | Trade Partner | Level 3-5 - PC0180-1 - No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | no longer in use - forwarded to all parties |  | 2026-04-30 | KPTG-TRANSMIT-001442 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-11-17 | LANSA-TRANSMIT-000061 | NA | Trade Partner | LEVEL 09 PENETRATION LAYOUT | 2 | 0 | 0 | NA | APPROVED | 2025-11-18 | WF-000739 | 471 | 2025-11-25 |  |  | 2025-12-16 | 2025-12-16 | KPTG-DA-002278 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-30 | INGEN3D-TRANSMIT-000055 | NA | Trade Partner | Level 3-5 - Precast Columns - IFA Resubmission | 5 | 0 | 0 | NA | APPROVED | 2026-04-30 | WF-000412 | NA | 2026-05-05 |  |  | 2026-05-12 | 2026-05-12 | KPTG-TRANSMIT-001738 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-30 | OveArup-TRANSMIT-000036 | NA | Consultant | Arup Hydraulic Services IFC Update | 27 | 0 | 0 | NA | APPROVED | 2026-04-30 | NA | 507 | 2026-05-07 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-001574 | Closed | 27 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-01 | Auspan-TRANSMIT-000037 | NA | Trade Partner | Re: Update IFCed precast shop drawings. | 2 | 0 | 0 | NA | APPROVED | 2026-05-01 | WF-000102 | NA | 2026-05-12 |  |  | 2026-05-01 | 2026-05-01 | KPTG-TRANSMIT-000426 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-04-30 | Kone-VIC-TRANSMIT-000002 | NA | Trade Partner | Lift 1, 2-4 & 5-6 full layouts for review and approval | 49 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Register updated | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-001766 | Closed | 49 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-01 | Tradetec-TRANSMIT-000436 | NA | Trade Partner | Tech Data - Stage 2 - Bitac Primer | 0 | 1 | 0 | NA | APPROVED | 2026-05-04 | WF-005547 | NA | 2026-05-11 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-017175 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-01 | SMEPS-TRANSMIT-000198 | SPARK-CRFI-KPG-000168 | Trade Partner | Ground Floor IFC - REV 0 | 1 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 260 | 2026-05-08 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000906 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-01 | WilsonPD-TRANSMIT-000002 | NA | Trade Partner | Re: Hydraulic shop drawing issued for Approval | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong document number, requested to resubmit.KPTG-IntCorr-000338 |  | 2026-05-01 | KPTG-IntCorr-000338 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-01 | Nilsen3-TRANSMIT-000008 | NA | Trade Partner | Re: Nilsen Sample submissions #2 | 0 | 16 | 0 | NA | APPROVED | 2026-05-01 | WF-000605 | NA | 2026-05-11 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-003073 | Closed | 16 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-01 | ACG-TRANSMIT-000085 | NA | Consultant | M3 - Stage 2 External Drawings | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Mismatch in revision inside the drawings and Aconex submission |  | 2026-05-01 | KPTG-DA-006331 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-11-17 | LANSA-TRANSMIT-000062 | NA | Trade Partner | LEVEL 04 -06 - TYPICAL WATER SERVICES LAYOUT | 2 | 0 | 0 | NA | APPROVED | 2025-11-18 | WF-000740 | 472 | 2025-11-25 |  |  | 2025-12-16 | 2025-12-16 | KPTG-DA-002277 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-07 | JCBa-TRANSMIT-000245 | NA | Consultant | LEVEL 03 BTR - ISSUE FOR CONSTRUCTION | 11 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 560 | 2026-05-11 |  | File supersede and WF terminated. |  |  | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-01 | D&E-TRANSMIT-000651 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - Ground - Mechanical Duct Layout - Zone 9 | 1 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 3041 | 2026-05-11 |  | As requested by Ellie — Terminated — KPTG-IntCorr-013787. |  | 2026-05-26 | KPTG-IntCorr-013787 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-01 | M.S.-TRANSMIT-000007 | NA | Trade Partner | Revised Shop Drawings for Approval | 36 | 0 | 0 | NA | REJECTED | [5 empty] | Error in drawing number |  | 2026-05-01 | KPTG-TRANSMIT-000787 | Closed | 36 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-01 | WilsonPD-TRANSMIT-000029 | NA | Trade Partner | Fire Penetration Equipment Tech Data | 0 | 2 | 0 | NA | APPROVED | 2026-05-01 | WF-000607 | NA | 2026-05-11 |  |  | 2026-05-12 | 2026-05-12 | KPTG-TRANSMIT-003022 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-01 | Hames-TRANSMIT-000158 | NA | Consultant | 01/05/2026 Revision | 23 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 1258 | 2026-05-05 |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-003613 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-01 | D&E-TRANSMIT-000648 | NA | Trade Partner | Re: MCC Drawings - Issued for Construction | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect document number , revision |  | 2026-05-01 | KPTG-TRANSMIT-016772 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-01 | GHD-TRANSMIT-000009 | na | Consultant | GE1 IFC Security Services Documentation FC-2 | 17 | 2 | 0 | NA | REJECTED | [5 empty] | Previous revision not updated and coversheet not including the document number |  | 2026-05-01 | DRAFT-001608 | Closed | 19 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-01 | IVS-TRANSMIT-000361 | NA | Consultant | Issued For Construction - Secure Corridor | 2 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 3044 | 2026-05-05 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-018093 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-01 | IVS-TRANSMIT-000362 | NA | Consultant | Stage 4 - Acoustic Screen & Office Roof Level (Revised Construction Issue) | 6 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 3046 | 2026-05-05 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-01 | ARCH-TRANSMIT-000044 | NA | Consultant | 2026.05.01_Landscape Drawings FC-01 | 12 | 1 | 0 | NA | APPROVED | 2026-05-01 | NA | 193 | 2026-05-06 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-000510 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-11-25 | LANSA-TRANSMIT-000070 | NA | Trade Partner | LEVEL 7 WATER SERVICES LAYOUT | 2 | 0 | 0 | NA | APPROVED | 2025-12-16 | WF-000837 | 482 | 2025-12-23 |  |  | 2025-12-16 | 2025-12-16 | KPTG-DA-002276 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-01 | HDRAus-TRANSMIT-000475 | NA | Consultant | Re: M3 Stage 4 - Document upload - PDF and CAD | 37 | 0 | 0 | NA | REJECTED | [5 empty] | Document status not mentioned inside the drawing |  | 2026-05-01 | KPTG-TRANSMIT-016774 | Closed | 37 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-01 | PARR-TRANSMIT-000174 | NA | Trade Partner | Re: P2685 - NDC M3 - Stage 4 - Battery Rooms - DS AND PREACTION SYSTEM LAYOUT | 1 | 1 | 0 | NA | REJECTED | [5 empty] | Both tech data and shop drawings have been submitted together. | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-016775 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-01 | KPTG-IntCorr-000386 | NA | Client | ZTN DRB10 - Document Transmittal | 15 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Design drawings for IFC distribution only. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-01 | ADP-TRANSMIT-000063 | NA | Consultant | ADP MEL4680 - FUEL IFC Issue | 9 | 1 | 0 | NA | APPROVED | 2026-05-01 | NA | 195 | 2026-05-06 |  |  | 2026-05-19 | 2026-06-01 | KPTG-TRANSMIT-000705 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-01 | ETNInd-TRANSMIT-000013 | NA | Trade Partner | MEL11 Eaton UPS and Battery Cabinet BIM Models | 3 | 0 | 0 | NA | APPROVED | 2026-05-01 | WF-000197 | NA | 2026-05-05 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000557 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-01 | PSGANZ-TRANSMIT-000001 | NA | Trade Partner | Technical Data submissions | 0 | 4 | 0 | NA | APPROVED | 2026-05-01 | WF-000105 | NA | 2026-05-11 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-000645 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-01 | PSGANZ-TRANSMIT-000001 | NA | Trade Partner | Technical Data submissions | 0 | 15 | 0 | NA | APPROVED | 2026-05-01 | WF-000106 | NA | 2026-05-11 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-000645 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-01 | HDRAus-TRANSMIT-000472 | NA | Consultant | M3 SW - Document upload - PDF and CAD | 1 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 4164 | 2026-05-05 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-017101 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-01 | HDRAus-TRANSMIT-000473 | NA | Consultant | M3_S2_Latest For Construction drawings revison | 7 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 4166 | 2026-05-05 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-017304 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-01 | HDRAus-TRANSMIT-000474 | NA | Consultant | As-Built Drawings for Sparable Portion 3 | 17 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-05-01 | KPTG-DA-006333 | Closed | 17 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-16 | D&E-TRANSMIT-000049 | NA | Trade Partner | NXM2S5D11 - AIR SCHEMATIC / LEVEL GROUND / GROUND FLOOR & ROOF - DUCT & PIPEWORK - Issued AS BUILTS | 6 | 0 | 0 | NA | APPROVED | [5 empty] | As-Builts, No review required. Updated register and distributed to the Project Team. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-30 | Auspan-TRANSMIT-000032 | NA | Trade Partner | Re: Precast shop drawings for construction | 1 | 0 | 0 | NA | APPROVED | 2026-04-30 | WF-000097 | NA | 2026-05-11 |  |  | 2026-04-30 | 2026-05-01 | KPTG-TRANSMIT-000421 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-01 | Appselec-TRANSMIT-000082 | NA | Trade Partner | Fire Rating Materials IFC | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-000198 | NA | 2026-05-05 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000554 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-02-06 | ARCST-TRANSMIT-000201 | NA | Trade Partner | Stage 2 Southern Internal Stair - IFA Package | 10 | 0 | 0 | NA | APPROVED | 2026-02-06 | WF-004168 | NA | 2026-05-24 |  |  | 2026-04-30 |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-01 | JCBa-TRANSMIT-000102 | NA | Consultant | IFC - A-21 - L01-L05 Structural Setout Plans | 25 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 840 | 2026-05-05 |  | 5 documents are terminated | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-001695 | Closed | 25 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-01 | RDSBIM-TRANSMIT-000051 | NA | Trade Partner | GREYSTAR GROUND FLOOR CONCRETE PROFILE PLAN AND SECTION ZONE 1, 3 AND 4 | 8 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 838 | 2026-05-08 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-001774 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-01 | RDSBIM-TRANSMIT-000052 | NA | Trade Partner | GREYSTAR LEVEL 01 CONCRETE PROFILE PLAN ZONE 2 & ZONE 5 | 2 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 841 | 2026-05-08 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-001834 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-01 | Auspan-TRANSMIT-000258 | NA | Trade Partner | : Update already IFCed shop drawings for construction | 38 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to rejected drawings included in the IFC package - KPTG-SADV-002227 |  | 2026-05-01 | KPTG-SADV-002227 | Closed | 38 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-01 | Auspan-TRANSMIT-000259 | NA | Trade Partner | : Resubmit precast shop drawings for approval. Level 2 | 2 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 848 | 2026-05-08 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-001738 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-01 | Rinco-TRANSMIT-000043 | NA | Trade Partner | Structural drawings Issued for Construction | 25 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 850 | 2026-05-05 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-001837 | Closed | 28 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-01 | Auscool-TRANSMIT-000024 | NA | Trade Partner | Ground Floor - Slab Penetration - Zone 2 | 1 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 843 | 2026-05-08 |  | Review voided as advised by Amee | 2026-05-04 | 2026-05-04 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-01 | Stowe-A-TRANSMIT-000392 | NA | Trade Partner | Stowe - Tech Data Submission - Conduit | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2025-12-01 | KPTG-TRANSMIT-010470 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-15 | ADP-TRANSMIT-000146 | NA | Consultant | S4 ¦ ADP MEL4780 - IFC Stage 4 M3 | 130 | 0 | 0 | NA | APPROVED | 2025-12-15 | NA | 1659 - 1662 - 1664 - 1666 - 1724 - 1670 - 1672 | 2025-12-17 |  |  |  | 2025-12-18 | KPTG-TRANSMIT-011107 | Closed | 130 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-01 | KETE-TRANSMIT-000018 | NA | Trade Partner | Kete - Zone 01 Shop Drawings Submission 02 | 90 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 852 | 2026-05-08 |  |  | 2026-05-18 | 2026-05-18 | KPTG-SADV-002534 | Closed | 90 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-01 | POTTSENG-TRANSMIT-000027 | NA | Trade Partner | GMAC HYDRAULIC SERVICES - WATER - BASEMENT 1 - ZONES 1-5 LAYOUTS | 5 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 846 | 2026-05-08 |  |  | 2026-05-12 | 2026-05-12 | KPTG-TRANSMIT-001792 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-01 | KETE-TRANSMIT-000019 | NA | Trade Partner | Kete - Zone 02 Shop Drawings Submission 02 | 53 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 854 | 2026-05-08 |  | Review Voided as advised by Kapitol PC Alex M.- Trade Partner requested to supersede the drawings. KPTG-SADV-002534 | 2026-05-18 | 2026-05-18 | KPTG-SADV-002534 | Closed | 53 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-01 | Auscool-TRANSMIT-000021 | NA | Trade Partner | BASEMET TO LEVEL 7 - TUNDISH LOCATIONS | 43 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 844 | 2026-05-08 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-001734 | Closed | 43 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-01 | Eneraque-TRANSMIT-000011 | NA | Trade Partner | Document Package Submission #1 | 7 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 791 | 2026-05-08 |  | Actual Receipt Date - 30/04/26 | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-003305 | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-01 | ELLISAIR-TRANSMIT-000010 | NA | Trade Partner | Technical data re submission - Pumps | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-000599 | NA | 2026-05-13 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-002816 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-01 | ASV-TRANSMIT-000060 | NA | Trade Partner | Stage 9-10 External HYD | 1 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 788 | 2026-05-08 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-003244 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-01 | ASV-TRANSMIT-000061 | NA | Trade Partner | Hydraulic X Crane Footing | 1 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 789 | 2026-05-08 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-003245 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-01 | BBC P.-TRANSMIT-000006 | NA | Trade Partner | PPG Exterior All Weather | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-000609 | NA | 2026-05-06 |  | Workflow terminated and Rev 2 submitted as per instruction from Project Coordinator (WF-000676) |  | 2026-05-13 | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-01 | BBC P.-TRANSMIT-000001 | NA | Trade Partner | PPG Pure Performance Ceiling - M2-ARC-BBC-TD-0001-279050 | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-000600 | NA | 2026-05-06 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-003062 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-16 | IVS-TRANSMIT-000301 | NA | Consultant | Stage 4 - Roof hobs Zone C1 & Acoustic Screen Construction Issue | 5 | 0 | 0 | NA | APPROVED | 2025-12-16 | NA | 1680 | 2025-12-18 |  |  |  | 2025-12-18 |  | Closed | 5 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-01 | BBC P.-TRANSMIT-000002 | NA | Trade Partner | PPG Pure Performance Prep - M2-ARC-BBC-TD-0001-279550 | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-000601 | NA | 2026-05-06 |  | Workflow terminated and Rev 2 submitted as per instruction from Project Coordinator (WF-000676) |  | 2026-05-13 | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-01 | BBC P.-TRANSMIT-000003 | NA | Trade Partner | PPG Water-Based Enamel - M2-ARC-BBC-TD-0001-121410 | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-000602 | NA | 2026-05-06 |  | Workflow terminated and Rev 2 submitted as per instruction from Project Coordinator (WF-000676) |  | 2026-05-13 | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-01 | BBC P.-TRANSMIT-000004 | NA | Trade Partner | PPG Interior Low Sheen & Matt - M2-ARC-BBC-TD-0001-279250 | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-000603 | NA | 2026-05-06 |  | Workflow terminated and Rev 2 submitted as per instruction from Project Coordinator (WF-000676) |  | 2026-05-13 | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-01 | BBC P.-TRANSMIT-000005 | NA | Trade Partner | PPG 3in1 Prep - M2-ARC-BBC-TD-0001-108100 | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-000604 | NA | 2026-05-06 |  | Workflow terminated and Rev 2 submitted as per instruction from Project Coordinator (WF-000676) |  | 2026-05-13 | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-01 | SMEPS-TRANSMIT-000030 | NA | Trade Partner | SME Sample Submissions for Approval | 0 | 19 | 0 | NA | APPROVED | 2026-05-01 | WF-000606 | NA | 2026-05-06 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-003954 | Closed | 19 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-01 | Highbu-TRANSMIT-000145 | NA | Trade Partner | Updated drawing | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC DRAWING, TRANSMITTED TO EVERYONE |  | 2026-05-01 | KPTG-TRANSMIT-002812 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-01 | CTAGroup-TRANSMIT-000007 | NA | Trade Partner | Re: Fencing dimensioning for Sout East Footings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | ZIP FILE , SUBMITTED, REQUESTED TO RESUBMIT:KPTG-SADV-004247 |  | 2026-05-01 | KPTG-SADV-004247 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-01 | 4DW-TRANSMIT-000176 | NA | Consultant | Structural Documentation - General updates | 9 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 221 | 2026-05-06 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-002922 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-01 | 4DW-TRANSMIT-000177 | NA | Consultant | Re: S009_21, _22, _31 Attribute correction | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Requested to update Attribute status:KPTG-SADV-004248 |  | 2026-05-01 | KPTG-SADV-004248 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-01 | RDSBIM-TRANSMIT-000137 | NA | Trade Partner | MLCSPR ¦ OUTDOOR COURT LEVEL 02 CONCRETE PROFILE PLAN SHEET 5 | 1 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 223 | 2026-05-06 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-002914 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-16 | JCBa-TRANSMIT-000045 | NA | Consultant | Ground Floor Footings Zone 3 - Update as per KPTG-DA-000525 | 1 | 0 | 0 | NA | APPROVED | 2025-12-16 | WF-000106 | 210 | 2025-12-19 |  |  |  | 2026-01-14 | KPTG-TRANSMIT-000394 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-01 | POTTSENG-TRANSMIT-000010 | NA | Trade Partner | 671C: HYDRAULIC SERVICES - LEVELS 01-18 - PENETRATION LAYOUTS | 18 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 454 | 2026-05-08 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-001054 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-01 | Hollow-TRANSMIT-000011 | NA | Consultant | 2336 DISTLV - L3 plant room precast structure - PC beam PCB-04 - Shop drawings, issued for approval | 2 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 511 | 2026-05-08 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-001515 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-01 | Jangho-TRANSMIT-000043 | NA | Consultant | Gasket Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-000460 | NA | 2026-05-04 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-002791 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-01 | Firesafe-TRANSMIT-000007 | NA | Consultant | Ground to Mez penos | 4 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 513 | 2026-05-05 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-001764 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-01 | INGEN3D-TRANSMIT-000056 | NA | Consultant | RANSMIT-000151 Reference Number TTW-TRANSMIT-000151 | 48 | 0 | 0 | NA | APPROVED | 2026-05-01 | WF-000418 | NA | 2026-05-08 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-001902 | Closed | 48 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-01 | Jangho-TRANSMIT-000051 | NA | Trade Partner | Stainless steel bird mesh Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-000457 | NA | 2026-05-05 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-002796 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-01 | Jangho-TRANSMIT-000050 | NA | Trade Partner | Structural Sealant Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-000458 | NA | 2026-05-05 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-002794 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-01 | Jangho-TRANSMIT-000049 | NA | Trade Partner | Backer rod Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-000422 | NA | 2026-05-05 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-01 | Jangho-TRANSMIT-000048 | NA | Trade Partner | Double side type Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-000423 | NA | 2026-05-05 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-001544 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-16 | RDSBIM-TRANSMIT-000005 | NA | Trade Partner | GREYSTAR ¦ BASEMENT CAPPING BEAM PLAN ELEVATION AND SECTION | 6 | 0 | 0 | NA | APPROVED | 2025-12-16 | WF-000107 | 212 | 2025-12-19 |  | Review Void. |  | 2025-12-17 | NA | Closed | 6 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-01 | Jangho-TRANSMIT-000047 | NA | Trade Partner | Insulation Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-000462 | NA | 2026-05-05 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-002785 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-01 | Jangho-TRANSMIT-000046 | NA | Trade Partner | Weather Sealant Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-000463 | NA | 2026-05-05 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-002783 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-01 | Jangho-TRANSMIT-000045 | NA | Trade Partner | Steel Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-000426 | NA | 2026-05-05 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-001554 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-01 | Jangho-TRANSMIT-000044 | NA | Trade Partner | Galvanized steel sheet Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-000427 | NA | 2026-05-05 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-001549 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-01 | Jangho-TRANSMIT-000053 | NA | Trade Partner | Fixing Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-000459 | NA | 2026-05-05 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-002793 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-01 | Jangho-TRANSMIT-000054 | NA | Trade Partner | Brick Sample Submission | 0 | 5 | 0 | NA | REJECTED | [5 empty] | QA ERROR |  | 2026-05-01 | KPTG-TRANSMIT-001480 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-01 | Jangho-TRANSMIT-000056 | NA | Trade Partner | Glass Sample Submission(GL-01 Option 1) | 0 | 1 | 0 | KPTG-IntCorr-000675 | APPROVED | [5 empty] | jaanbir to confirm |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-01 | Jangho-TRANSMIT-000058 | NA | Trade Partner | Glass Sample Submission(GL-01 Option 2) | 0 | 1 | 0 | KPTG-IntCorr-000676 | APPROVED | [5 empty] | jaanbir to confirm | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-001555 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-01 | Jangho-TRANSMIT-000060 | NA | Trade Partner | Swing Door Sample Submission | 0 | 12 | 0 | KPTG-IntCorr-000677 | APPROVED | [5 empty] | jaanbir to confirm | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-001534, 1539 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-01 | Jangho-TRANSMIT-000057 | NA | Trade Partner | 007_FT12 System Concept Drawing-01 | 10 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 519 | 2026-05-11 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-001898 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-16 | Auspan-TRANSMIT-000034 | NA | Trade Partner | Precast shop drawings for construction. Zone 4, 5. | 49 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required, Update register and issue to all consultants. |  | 2025-12-16 | NA | Closed | 49 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-03-31 | Civilex-TRANSMIT-000060 | NA | Trade Partner | Material Procurement Missing | 0 | 1 | 0 | KPTG-IntCorr-000547 | APPROVED | 2026-04-10 | WF-000302 | NA | 2026-04-14 |  | Clarification from ENZO | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-001626 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | SKS Tech-TRANSMIT-000113 | NA | Trade Partner | Fwd: M3-ELC-SKS-SA-C-0400-0034 IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-05-04 | KPTG-TRANSMIT-016781 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-04 | WilsonPD-TRANSMIT-000003 | NA | Trade Partner | Hydraulic shop drawing issued for Approval | 1 | 0 | 0 | NA | APPROVED | 2026-05-04 | WF-000199 | NA | 2026-05-08 |  |  |  | 2026-05-07 | KPTG-TRANSMIT-000585 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | SKS Tech-TRANSMIT-000114 | NA | Trade Partner | Fwd: M3-ELC-SKS-SA-C-0400-0004 IFC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-05-04 | KPTG-TRANSMIT-016783 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-04 | Entire M-TRANSMIT-000043 | NA | Trade Partner | Exhaust Fan Springs Submitted for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-04 | WF-000200 | NA | 2026-05-08 |  |  | 2026-05-12 | 2026-05-15 | KPTG-TRANSMIT-000638 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-04 | KALLIBRE-TRANSMIT-000005 | NA | Trade Partner | MEL11 - Door by Door Hardware Schedule for Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | WRONG NAMING CONVENTION: KPTG-IntCorr-000342 |  | 2026-05-04 | KPTG-IntCorr-000342 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-04 | JCBa-TRANSMIT-000104 | NA | Consultant | Architectural Documentation - Joinery Details & Materials & Finishes Schedule_ID | 13 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 858 | 2026-05-06 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-001698 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-04 | JCBa-TRANSMIT-000104 | NA | Consultant | Architectural Documentation - Joinery Details & Materials & Finishes Schedule_ID | 0 | 1 | 0 | NA | APPROVED | 2026-07-31 | NA | 1610 | 2026-07-31 |  | WF-000453 terminated and ACC review #1610initiated as advised by Kapitol DM ON 31/07/26 | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-003318 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | SMEPS-TRANSMIT-000264 | NA | Trade Partner | SME - IFA Lighting Drawings | 6 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 3048 | 2026-05-12 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-017874 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-04 | SMEPS-TRANSMIT-000199 | SPARK-CRFI-KPG-000168 | Trade Partner | Ground Floor - Containment Zone 7 - Rev 0 | 1 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 262 | 2026-05-11 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000908 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-16 | Fyfe-TRANSMIT-000009 | NA | Consultant | Council Two-Land Road - IFC (For Council Approval) | 17 | 1 | 0 | NA | APPROVED | 2025-12-16 | WF-000108 | 214 | 2025-12-19 |  |  |  | 2026-01-21 | KPTG-TRANSMIT-000441 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-04 | Auscool-TRANSMIT-000092 | NA | Trade Partner | Seismic Design | 0 | 1 | 0 | NA | APPROVED | 2026-05-04 | NA | WF-000735 | 2026-05-06 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-002415 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | NXT-TRANSMIT-001525 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - SCHEMATICS- IFA | 2 | 0 | 0 | NA | APPROVED | 2026-05-04 | WF-005529 | NA | 2026-05-15 |  | PARR-TRANSMIT-000168 | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-017009 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-01 | KPTG-TRANSMIT-003605 | NA | Trade Partner | Aluminium Doors and Window Plan, Elevation, Section and Details | 14 | 0 | 0 | NA | APPROVED | 2026-05-01 | NA | 1246 | 2026-05-04 |  | Mark's Email | 2026-06-04 | 2026-06-05 | KPTG-TRANSMIT-003869 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-04 | GHD-TRANSMIT-000010 | NA | Consultant | GE1 IFC Security Services Documentation FC-2 | 17 | 2 | 0 | NA | APPROVED | 2026-05-04 | NA | 198 | 2026-05-07 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-000553 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-04 | KALLIBRE-TRANSMIT-000006 | NA | Trade Partner | MEL11 Door by Door Hardware Schedule IFA | 0 | 1 | 0 | NA | REJECTED | [5 empty] | WRONG DOCUMENT NUMBERING: KPTG-IntCorr-000343 |  | 2026-05-04 | KPTG-IntCorr-000343 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | SMEPS-TRANSMIT-000263 | NA | Trade Partner | SME - IFC Drawings Lighting | 3 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 3050 | 2026-05-11 |  |  |  | 2026-05-13 | KPTG-TRANSMIT-017226 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | ADP-TRANSMIT-000306 | NA | Consultant | Re: ADP MEL4780 - Updated Electrical Drawings | 30 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-05-04 | KPTG-RFI-007653 | Closed | 30 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-04 | KALLIBRE-TRANSMIT-000007 | NA | Trade Partner | Door by Door Hardware Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-05-04 | WF-000201 | NA | 2026-05-08 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-000718 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-04 | D&E-TRANSMIT-000244 | NA | Trade Partner | LEVEL 1 SEISMIC DRAWINGS | 10 | 0 | 0 | NA | REJECTED | [5 empty] | Error in Date |  | 2026-05-04 | KPTG-TRANSMIT-000801 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | ADP-TRANSMIT-000307 | NA | Consultant | ADP MEL4780 - Updated Electrical Drawings | 27 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 3058 | 2026-05-11 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018446 | Closed | 27 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-16 | Fyfe-TRANSMIT-000010 | NA | Consultant | Updated IFC Documents - Civil - Fyfe | 9 | 0 | 0 | NA | APPROVED | 2025-12-16 | WF-000104 | 208 | 2025-12-18 |  |  |  | 2026-01-21 | KPTG-TRANSMIT-000442 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | PFP PL-TRANSMIT-000086 | NA | Trade Partner | Re: Schematic IFC | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect drawing status |  | 2026-05-04 | KPTG-RFI-007655 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | ADP-TRANSMIT-000308 | NA | Consultant | Re: ADP MEL4780 - Electrical Drawings - Lightning Protection Layouts | 3 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect Status |  | 2026-05-04 | KPTG-RFI-007656 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | PFP PL-TRANSMIT-000087 | NA | Trade Partner | Re: Ground and Level 1 Zone 2 IFC | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect drawing status |  | 2026-05-04 | KPTG-RFI-007657 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-04 | Rinco-TRANSMIT-000044 | NA | Consultant | Structural drawings Issued for Construction | 2 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 866 | 2026-05-12 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-001864 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | SMEPS-TRANSMIT-000267 | NA | Trade Partner | SME - DRAWINGS IFC SUBMISSIONS - SMALL POWER LAYOUTS | 8 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 3062 | 2026-05-06 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-017062 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-04 | KPTG-IntCorr-007433 | NA | Trade Partner | 8th Wonder Safety Strip Sample | 0 | 1 | 0 | NA | APPROVED | 2026-05-04 | WF-000956 | NA | 2026-05-08 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-003019 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-04 | JCBa-TRANSMIT-000105 | NA | Consultant | Structural Setout Plans: L6-L7 IFC | 10 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 868 | 2026-05-12 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-001883 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-04 | M.S.-TRANSMIT-000008 | NA | Trade Partner | Shop Drawings for Approval | 36 | 0 | 0 | NA | REJECTED | [5 empty] | Incomplete title |  | 2026-05-04 | KPTG-TRANSMIT-000813 | Closed | 36 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-04 | Nilsen3-TRANSMIT-000135 | NA | Trade Partner | Stage 3 300mm2 - 500mm2 Straight Terminations | 0 | 1 | 0 | NA | APPROVED | 2026-05-04 | WF-005540 | NA | 2026-05-14 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-018200 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | NXT-TRANSMIT-001527 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - DS AND PREACTION SYSTEM LAYOUT | 1 | 1 | 0 | NA | APPROVED | 2026-05-04 | WF-005541 | NA | 2026-05-15 |  | Terminated by Kap -resubmitted via WF-005583 |  | 2026-05-06 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-16 | DG-TRANSMIT-000054 | NA | Trade Partner | Re: DELTA - HYTEC GWP and Mix Design - For Review | 0 | 1 | 0 | NA | APPROVED | 2025-12-16 | WF-000105 | NA | 2025-12-18 |  |  |  | 2025-12-16 | KPTG-TRANSMIT-000349 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-11-19 | WilsonPD-TRANSMIT-000122 | SPARK-CRFI-KPG-000132 | Trade Partner | Re: IFA Re-submittal Basin and Shower Mixer | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-05-04 | KPTG-TRANSMIT-000808 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-11-19 | WilsonPD-TRANSMIT-000121 | SPARK-CRFI-KPG-000156 | Trade Partner | IFA Re-submittal Basin and Shower Mixer | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-05-04 | KPTG-TRANSMIT-000810 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-04 | Nilsen3-TRANSMIT-000136 | NA | Trade Partner | Stage 3 - 300mm² & 500mm² Elbow Terminations | 1 | 0 | 0 | NA | APPROVED | 2026-05-04 | WF-005543 | NA | 2026-05-20 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-018203 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-04 | Nilsen3-TRANSMIT-000137 | NA | Trade Partner | Stage 3 300mm2 & 500mm2 Coupler | 0 | 1 | 0 | NA | APPROVED | 2026-05-04 | WF-005544 | NA | 2026-05-20 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-018205 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | D&E-TRANSMIT-000655 | NA | Trade Partner | Re: DX Air Conditioning and VRF Air Conditioning - Issued for Approval | 0 | 2 | 0 | NA | REJECTED |  | NA | NA |  |  | Already received the revision before. |  | 2026-05-04 | KPTG-RFI-007664 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-04 | Ardon-TRANSMIT-000042 | NA | Trade Partner | CM-02 - Decorative Ceiling Sample | 0 | 1 | 0 | NA | APPROVED | 2026-05-04 | WF - 01008 | NA | 2026-05-08 |  | File supersede and WF terminated. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | D&E-TRANSMIT-000656 | NA | Trade Partner | NXM3S4 - Level 1 - Mechanical Duct Layout - Zone 4 - Issued For Construction #3066 | 1 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 3066 | 2026-05-12 |  | As requested by Ellie — Terminated — KPTG-IntCorr-013787. |  | 2026-05-26 | KPTG-IntCorr-013787 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-04 | WilsonPD-TRANSMIT-000187 | NA | Trade Partner | Upadated Hydraulic Roof Level - Zone A & B - Drainage & Water Layout | 2 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 264 | 2026-05-11 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | D&E-TRANSMIT-000662 | NA | Trade Partner | DX Air Conditioning and VRF Air Conditioning - Issued for Approval | 0 | 2 | 0 | NA | APPROVED | 2026-05-04 | WF-005548 | NA | 2026-05-25 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | SMEPS-TRANSMIT-000270 | NA | Trade Partner | SME - IFA SAMPLE SUBMISION | 0 | 1 | 0 | NA | APPROVED | 2026-05-04 | WF-005549 | NA | 2026-05-25 |  |  |  | 2026-05-11 | KPTG-TRANSMIT-017156 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-16 | CRSol-TRANSMIT-000066 | NA | Trade Partner | CRS - Tech Data Approval NextDC M3S4 | 0 | 8 | 0 | NA | APPROVED | 2025-12-16 | WF-003630 |  | 2026-01-09 |  |  |  | 2026-02-02 | KPTG-TRANSMIT-012384 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-04 | D&E-TRANSMIT-000245 | SPARK-CRFI-KPG-000497 | Trade Partner | Level 1 Seismic Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 265 | 2026-05-11 |  |  | 2026-06-15 | 2026-06-16 | KPTG-TRANSMIT-001007 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-04 | JCBa-TRANSMIT-000248 | NA | Consultant | CAD's Amenity and EOT | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Update register only. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | ARCST-TRANSMIT-000271 | NA | Trade Partner | Stair 3 & 6 - Issued for Approval | 28 | 0 | 0 | NA | APPROVED | 2026-05-04 | WF-005550 | NA | 2026-05-28 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-018721 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-04 | D&E-TRANSMIT-000661 | NA | Trade Partner | NXM3S2 - Air Schematic - Issued For Construction | 1 | 0 | 0 | NA | REJECTED | [5 empty] | The latest revision of the document which is available with us is FOA-03 which is reviewed with status Rejected. |  | 2026-05-04 | KPTG-SADV-005187 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-04 | KPTG-TRANSMIT-002938 | NA | Trade Partner | Crash Barrier - Traffix & Webber review | 0 | 9 | 0 | NA | APPROVED | 2026-05-04 | WF - 001009 | NA | 2026-05-08 |  | NA | 2026-06-05 | 2026-06-05 | DRAFT-018627 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-04 | WilsonPD-TRANSMIT-000188 | SPARK-CRFI-KPG-000132 | Trade Partner | F.TAP-05 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-000894 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-04 | SMEPS-TRANSMIT-000200 | SPARK-CRFI-KPG-000330 | Trade Partner | Diesel Generator | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-000866 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | D&E-TRANSMIT-000659 | NA | Trade Partner | Re: NXM3S4 - SECURITY GRILLES - Issued For Approval | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect document type |  | 2026-05-04 | KPTG-RFI-007669 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-16 | ccair-TRANSMIT-000079 | NA | Trade Partner | Roof Penetration layout - Mechanical Services - IFA | 2 | 0 | 0 | NA | APPROVED | 2025-12-16 | WF-000838 | 514 | 2025-12-23 |  |  | 2026-02-02 | 2026-02-02 | KPTG-TRANSMIT-002669 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-04 | WilsonPD-TRANSMIT-000189 | SPARK-CRFI-KPG-000132 | Trade Partner | kitchen Mixer | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-05-20 | KPTG-TRANSMIT-000892 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-04 | ETNInd-TRANSMIT-000018 | NA | Trade Partner | MEL05 COLO4 L2&L3 EPMS SCRIPTS | 0 | 26 | 0 | KPTG-IntCorr-000388 | APPROVED |  | NA | NA |  |  | File superseded |  | 2026-04-08 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-04 | D&E-TRANSMIT-000247 | SPARK-CRFI-KPG-000540 | Trade Partner | CONTROL SPECIALIST SENSOR | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | [6 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-04 | SKS Tech-TRANSMIT-000187 | NA | Trade Partner | for constrution status | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | QA error |  | 2026-05-04 | KPTG-IntCorr-001256 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-04 | SKS Tech-TRANSMIT-000188 | NA | Trade Partner | SKS IFC MISC LAYOUTS UPDATE | 5 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 1289 | 2026-06-17 |  | QA ERROR- KPTG-IntCorr-001255- Initially rejected | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-003987 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-04 | D&E-TRANSMIT-000246 | NA | Trade Partner | LEVEL 1 SEISMIC DRAWINGS | 10 | 0 | 0 | NA | REJECTED | [5 empty] | same drawing already received and processed. |  | 2026-05-04 | KPTG-TRANSMIT-000814 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-04 | POTTSENG-TRANSMIT-000028 | NS | Trade Partner | GMAC HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONES 1-5 LAYOUTS | 5 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 860 | 2026-05-12 |  |  | 2026-05-12 | 2026-05-12 | KPTG-TRANSMIT-001790 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-04 | JCBa-TRANSMIT-000103 | NA | Consultant | IFC Drawing Issue: A-23, A-24, A-63 (IFC) | 99 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 856 | 2026-05-12 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-001863 | Closed | 99 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-04 | Auspan-TRANSMIT-000261 | NA | Trade Partner | Precast shop drawings for construction. | 99 | 0 | 0 | KPTG-IntCorr-000543 | REJECTED |  | NA | NA |  |  | IFC - Rejected drawing included. Waiting for advice - KPTG-IntCorr-000543. IFC - Rejected drawing included. Transmittal returned to Auspan to remove rejected drawing. KPTG-SADV-002259 |  | 2026-05-05 | KPTG-SADV-002259 | Closed | 99 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-04 | Auspan-TRANSMIT-000262 | NA | Trade Partner | Resubmit precast shop drawings for approval | 21 | 0 | 0 | KPTG-IntCorr-000544 | APPROVED |  | NA | 870 |  |  | Found difference in Panel number - waiting for kapitol advise - KPTG-IntCorr-000544. Advised excluding above panel and proceed due to urgent requirements.. | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-001816 | Closed | 20 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-01 | Stowe-A-TRANSMIT-000390 | NA | Trade Partner | Stowe - Tech Data Submission - Bakelite Light and Power | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2025-12-01 | KPTG-TRANSMIT-010467 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-16 | INGEN3D-TRANSMIT-000675 | NA | Trade Partner | I3D-378 Next DC M3 Stage 4 - Ground Floor Fuel Tank - Cast in Dowels - IFC | 8 | 0 | 0 | NA | APPROVED | [5 empty] | Oliver (teams)- HI Shahir, please hold fire on these for now. I will let you know when they can be registered |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-04 | POTTSENG-TRANSMIT-000029 | NA | Trade Partner | GMAC HYDRAULIC SERVICES - PENETRATION - LEVEL 1 & 2 - ZONES 1-5 LAYOUTS | 10 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 862 | 2026-05-12 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-001731 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-04 | Auscool-TRANSMIT-000027 | NA | Trade Partner | Ground floor - zone 2 | 1 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 864 |  |  |  | 2026-05-04 | 2026-05-04 | KPTG-TRANSMIT-001644 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | SMEPS-TRANSMIT-000271 | NA | Trade Partner | SME - TEMP GENERATOR CONNECTION PANEL | 1 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 3071 | 2026-05-12 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-018128 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | ADP-TRANSMIT-000309 | NA | Consultant | Re: ADP MEL4780 - Electrical Drawings - Lightning Protection Ground Floor | 3 | 0 | 0 | NA | REJECTED | [5 empty] | IFC has been submitted before IFA |  | 2026-05-04 | KPTG-RTRFI-004083 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | HDRAus-TRANSMIT-000476 | NA | Consultant | M3 Stage 4 - Document upload - PMJ detail and Door schedule update - PDF and CAD | 4 | 0 | 0 | NA | APPROVED |  | NA | 3074 | 2026-05-07 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-016905 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | ARCST-TRANSMIT-000273 | NA | Trade Partner | Re: Switchroom Busduct Peno Supports - Issued for Approval | 11 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing title mentioned seems different -both Aconex and inside drawing |  | 2026-05-04 | KPTG-RFI-007674 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | SMEPS-TRANSMIT-000262 | NA | Trade Partner | Re: SME - IFC Switchboard Drawings | 4 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due to incorrect document issues |  | 2026-05-04 | KPTG-DA-006342 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | ARCST-TRANSMIT-000274 | NA | Trade Partner | Re: Switchroom Busduct Peno Supports - Issued for Approval | 11 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing title mentioned seems different -both Aconex and inside drawing |  | 2026-05-04 | KPTG-RFI-007675 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | ARCST-TRANSMIT-000268 | NA | Trade Partner | Chemical Store Roof - Issued for Re-Approval | 10 | 0 | 0 | NA | APPROVED | 2026-05-04 | WF-005531 | NA | 2026-05-28 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-018893 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | KPTG-IntCorr-012660 | NA | Trade Partner | Core 4 IFC Shop Drawings | 21 | 0 | 0 | NA | APPROVED | 2026-05-04 | WF-005560 | NA | 2026-05-11 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2025-12-16 | RLA-TRANSMIT-000239 | NA | Consultant | External Levels - Preston Laneway - SETOUT CLARIFICATION | 4 | 0 | 0 | NA | APPROVED | 2025-12-16 | NA | 565 | 2025-12-23 |  |  | 2025-12-17 | 2025-12-17 | KPTG-TRANSMIT-002527 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | SMEPS-TRANSMIT-000265 |  | Trade Partner | SME - Busduct IFC Drawings - Roof level | 3 | 0 | 0 | NA | APPROVED | 2026-05-04 | WF-005532 | NA | 2026-05-04 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-017255 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | SMEPS-TRANSMIT-000266 | NA | Trade Partner | SMe - IFC Power containment layouts | 4 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 3056 | 2026-05-28 |  |  |  | 2026-05-13 | KPTG-TRANSMIT-017238 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | SMEPS-TRANSMIT-000268 | NA | Trade Partner | SME - DRAWINGS IFC | 1 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 3061 | 2026-05-29 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-017341 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | D&E-TRANSMIT-000533 | NA | Trade Partner | TELECOMMUNICATIONS IFC DRAWINGS | 2 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 3064 | 2026-05-11 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | D&E-TRANSMIT-000657 | NA | Trade Partner | Re: ISSUED FOR APPROVAL - CH C1 CHW & SFN SCHEMATIC | 1 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-01-04 | KPTG-RFI-007667 | Open | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | D&E-TRANSMIT-000658 | NA | Trade Partner | Re: ISSUED FOR APPROVAL - PLINTH & EQUIPMENT LAYOUTS | 9 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due to incorrect revision number |  |  | KPTG-RFI-007668 | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | D&E-TRANSMIT-000660 | NA | Trade Partner | NXM3S4 - Upper Roof Level - CHW & CCW Pipe Layout - Zone 1 & Zone 3 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 3069 | 2026-05-28 |  | As requested by Ellie — Terminated — KPTG-IntCorr-013787 |  | 2026-05-26 | KPTG-IntCorr-013787 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | INGEN3D-TRANSMIT-000704 | NA | Trade Partner | I3D-378 Next DC M3 Stage 4 - Core 10 - PWS4-1902 & PWS4-1903 - Revised IFC (04-05-2026) | 4 | 0 | 0 | NA | APPROVED | 2026-05-04 | WF-005554 | NA | 2026-05-22 |  | wf is terminated as per requested bt finlay |  | 2026-05-05 | KPTG-TRANSMIT-016893 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | KPTG-TRANSMIT-016843 | NA | Trade Partner | Proline Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-05-04 | WF-005555 | NA | 2026-05-21 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018360 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | KPTG-TRANSMIT-016843 | NA | Trade Partner | Proline Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-05-04 | WF-005556 | NA | 2026-05-21 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-017220 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-16 | CRSol-TRANSMIT-000067 | NA | Trade Partner | SMW Drawings Issued for Approval - C1 / C2 / C3 | 30 | 0 | 0 | NA | APPROVED | 2026-01-06 | WF-003640 | 1724 | 2025-12-24 |  | Resubmitted via ACC 1724 as per requested by Sean | 2026-01-15 | 2026-01-28 | KPTG-TRANSMIT-011987 | Closed | 30 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | KPTG-TRANSMIT-016843 | NA | Trade Partner | Proline Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-05-04 | WF-005557 | NA | 2026-05-21 |  |  |  | 2026-05-22 | KPTG-TRANSMIT-016843 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | KPTG-TRANSMIT-016844 | NA | Trade Partner | Proline Details A and C - | 2 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 3076 | 2026-05-11 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | LTEPRCST-TRANSMIT-000146 | NA | Trade Partner | NECTDC STAGE 04 - CORE 05 IFC | 25 | 0 | 0 | NA | APPROVED | 2026-04-27 | WF-005561 | NA | 2026-05-28 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | ARCST-TRANSMIT-000272 | NA | Trade Partner | Re: C2 West Roof Walkway - Issued for Approval | 298 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing title mentioned seems different -both Aconex and inside drawing |  | 2026-05-04 | KPTG-RFI-007676 | Closed | 298 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-04 | Jangho-TRANSMIT-000054 | NA | Trade Partner | 671 CONCEPT DRAWINGS FT-01 Rev03 | 36 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 459 | 2026-05-12 |  | Review Voided by Kapitol PC. Updated drawings expected. | 2026-06-24 | 2026-06-24 | NA | Closed | 35 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-04 | Jangho-TRANSMIT-000055 | NA | Consultant | 671 CONCEPT DRAWINGS FT-02&FT-20 Rev02 Review Voided by Kapitol PC. Updated drawings expected. | 27 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 461 | 2026-05-12 |  |  | 2026-06-24 | 2026-06-24 | NA | Closed | 27 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-04 | crossfir-TRANSMIT-000011 | NA | Trade Partner | Dry Fire - Basement 04 to 01 , IFA | 4 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 456 | 2026-05-12 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-001100 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-04 | Jangho-TRANSMIT-000056 | NA | Trade Partner | 671 VMU shop drawings Rev01 | 24 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 463 | 2026-05-12 |  | Review voided; As informed by Kaptol PC , Trade partner is going to supersede the Shop Drawings. | 2026-05-25 | 2026-05-25 | NA | Closed | 24 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-04 | KPTG-SADV-000051 | NA | Trade Partner | D1 Test Pit Results | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Upload only |  | 2026-05-04 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-05 | 4DW-TRANSMIT-000032 | NA | Consultant | Structural Documentation: Block 2 Load bearing & NLB Precast walls issued for Certification. | 10 | 0 | 0 | KPTG-IntCorr-000073 | APPROVED | 2026-05-05 | NA | 57 | 2026-05-13 |  | Actual received date 04-05-2026 | 2026-05-13 | 2026-05-13 |  | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-16 | Baigents-TRANSMIT-000060 |  | Trade Partner | MCC roof steel IFF3 (re-issued for fabrication) | 4 | 0 | 0 | NA | REJECTED | [8 empty] | KPTG-TRANSMIT-000307 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-04 | ETNInd-TRANSMIT-000014 | NA | Trade Partner | MEL11 COLO4 COLO5 L2&L3 EPMS SCRIPTS | 0 | 13 | 0 |  | APPROVED | 2026-05-05 | WF-000202 | NA | 2026-05-06 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-000685 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-04 | HDRAus-TRANSMIT-000089 | NA | Consultant | M3 Stage 6 - Town Planning Updates - Revised Retaining Wall | 0 | 5 | 0 | NA | APPROVED |  | NA | NA |  |  | Information only |  | 2026-05-04 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-04 | NXT-TRANSMIT-000398 | NA | Client | DH7&8 - IW Tank - Kapitol Investigation Report | 0 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | currespondance |  | 2026-05-04 | NA | Closed | 0 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-04 | D&E-TRANSMIT-000359 | NA | Trade Partner | Fire Matrix - IFC-10 Transmittal | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | Distribution -IFC |  | 2026-05-04 | Awaiting approval | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-04 | WGAVIC-TRANSMIT-000111 | NA | Consultant | M2 - Stage 11 Level 1 Slab - Construction Issue | 8 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 805 | 2026-05-07 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-002752 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-04 | WGAVIC-TRANSMIT-000112 | NA | Consultant | M2 - Stage 10 Level 1 and Level 2 Slabs - Crane Peno Update - Issued for Certification | 9 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 807 | 2026-05-07 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-002755 | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-04 | VIA Arch-TRANSMIT-000108 | NA | Consultant | Architectural Building Building Permit Documentation | 26 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 800 | 2026-05-07 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-002471 | Closed | 26 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-04 | DLTS-TRANSMIT-000001 | NA | Trade Partner | S9-L1 H Frames IFA package | 36 | 0 | 0 | NA | APPROVED | 2026-05-06 | WF-000631 | NA | 2026-05-14 |  | Previous workflow WF-000610 has been terminated as advised by Project coordinator. | 2026-05-27 | 2026-05-27 | KPTG-TRANSMIT-003576 | Closed | 36 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-04 | VIA Arch-TRANSMIT-000113 | NA | Consultant | Architecture - S11 Ground Concrete Profile & Stairs 03 to 08 | 9 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 803 | 2026-05-07 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-002608 | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-04 | VIA Arch-TRANSMIT-000106 | NA | Consultant | M2 S10 L1 Concrete Profile Plan | 1 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 795 | 2026-05-07 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-002798 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-16 | Baigents-TRANSMIT-000061 | SPARK-CRFI-KPG-000118 | Trade Partner | MCC roof steel IFF3 updated (re-issued for fabrication) | 4 | 0 | 0 | KPTG-IntCorr-001182 | APPROVED |  |  | 273 |  |  |  | 2026-05-27 | 2026-05-27 | KPTG-TRANSMIT-000950 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-04 | WGAVIC-TRANSMIT-000110 | NA | Consultant | M2 - Stages 9-11 Steelwork - Issued for Certification | 30 | 0 | 0 | NA | APPROVED | 2026-05-04 | NA | 794 | 2026-05-07 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-002986 | Closed | 30 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-05 | PMT Sec-TRANSMIT-000011 | NA | Trade Partner | Security services Penetration | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Actual receiving date - 29/04/2026 Error in document number and title |  | 2026-05-05 | KPTG-TRANSMIT-000815 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-05 | VERTIV-TRANSMIT-000007 | NA | Trade Partner | NEXT DC GE01 _ MECHANICAL MATERIAL SUBMISSION _ CRV | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-000110 | NA | 2026-05-13 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-000649 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-04 | Civilex-TRANSMIT-000082 | NA | Trade Partner | Micropile Cap Material | 0 | 2 | 0 | NA | APPROVED | 2026-05-04 | WF-000431 | NA | 2026-05-12 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-001622 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-04 | Jangho-TRANSMIT-000062 | NA | Trade Partner | Extrusion color Electro Medium Bronze Kinetic-Flat Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-04 | WF-000432 | NA | 2026-05-13 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001883 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-04 | Jangho-TRANSMIT-000063 | NA | Trade Partner | Extrusion color Duralloy Surfmist-Matt Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-04 | WF-000433 | NA | 2026-05-13 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001881 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-04 | Jangho-TRANSMIT-000064 | NA | Trade Partner | Extrusion color Duratec Zeus Dune-Matt Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-04 | WF-000434 | NA | 2026-05-13 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001879 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-04 | Jangho-TRANSMIT-000065 | NA | Trade Partner | Extrusion color Duratec Eternity Copper Metallic Kinetic- Matt Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-04 | WF-000435 | NA | 2026-05-13 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001877 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-04 | Jangho-TRANSMIT-000066 | NA | Trade Partner | Extrusion color Electro Pale Bronze Kinetic-Flat Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-04 | WF-000436 | NA | 2026-05-13 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001875 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-16 | Tradetec-TRANSMIT-000307 | NA | Trade Partner | Shop Drawing - Stage 4 - CP20, CP30 | 2 | 0 | 0 | NA | APPROVED | 2025-12-16 | NA | 1683 | 2025-12-18 |  |  |  | 2026-01-20 | KPTG-TRANSMIT-011639 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-04 | Jangho-TRANSMIT-000067 | NA | Trade Partner | Extrusion color Duratec Elements Weathered Steel-Flat Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-04 | WF-000437 | NA | 2026-05-13 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001873 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-04 | Jangho-TRANSMIT-000069 | NA | Trade Partner | Alum sheet color Dulux Electro Medium Bronze Kinetic - Flat Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-04 | WF-000438 | NA | 2026-05-13 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001871 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-04 | Jangho-TRANSMIT-000070 | NA | Trade Partner | Alum sheet color Dulux Electro Pale Bronze Kinetic - Flat Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-04 | WF-000439 | NA | 2026-05-13 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001869 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-05 | Appselec-TRANSMIT-000083 | NA | Trade Partner | COLO Cable Reel Tech Data IFA | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-000204 | NA | 2026-05-12 |  | Substitution form has not been signed by AE Team.KPTG-IntCorr-000450 | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-000730 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-05 | Auspan-TRANSMIT-000041 | NA | Trade Partner | Precast shop drawings for construction | 6 | 0 | 0 | NA | APPROVED | 2026-05-05 | WF-000111 | 0 | 2026-05-14 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000448 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-05 | SKS Tech-TRANSMIT-000115 | NA | Trade Partner | Re: Comms containment earthing layout | 4 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect Ref No. |  | 2026-05-05 | KPTG-RFI-007679 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-05 | PMT Sec-TRANSMIT-000012 | NA | Trade Partner | Security Systems Penetration | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Actual receiving date 29/04/2026 Error in Drawing number, revision and title |  | 2026-05-05 | KPTG-TRANSMIT-000816 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-05 | Appselec-TRANSMIT-000084 | NA | Trade Partner | Cable Ties Tech data Rev 1 IFA | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-000205 | NA | 2026-05-11 |  |  | 2026-05-12 | 2026-05-12 | KPTG-TRANSMIT-000605 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-05 | HDRAus-TRANSMIT-000477 | NA | Consultant | Steel Beam Hob C2-C3 Generator Plinth | 2 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 3078 | 2026-05-07 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-017110 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-05 | Auspan-TRANSMIT-000042 | NA | Trade Partner | Precast shop drawings for approval | 2 | 0 | 0 | NA | APPROVED | 2026-05-05 | WF-000112 | NA | 2026-05-14 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000454 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-16 | ADP-TRANSMIT-000147 | NA | Consultant | ADP MEL4780 - IFC Stage 4 M3 | 12 | 0 | 0 | NA | APPROVED | 2025-12-16 | NA | 1686 | 2025-12-18 |  |  |  | 2025-12-18 | KPTG-TRANSMIT-011212 | Closed | 12 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-05 | D&E-TRANSMIT-000665 | NA | Trade Partner | BMS Valves & Actuators - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-005563 | NA | 2026-05-26 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-017715 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-05 | Stowe-A-TRANSMIT-000573 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - LOWER ROOF TRAY & RETICULATION - 05.05.2026 | 4 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 4168 | 2026-05-18 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-018687 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-05 | D&E-TRANSMIT-000664 | NA | Trade Partner | MaxCool Functional Description - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC, distribution only. |  | 2026-05-05 | KPTG-TRANSMIT-016865 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-05 | D&E-TRANSMIT-000666 | NA | Trade Partner | Water Filters - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-005565 | NA | 2026-05-26 |  | As requested by D&E D&E-IntCorr-000511 missing the relevant technical data. |  | 2026-05-05 | KPTG-TRANSMIT-016873 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-05 | Stowe-A-TRANSMIT-000574 | NA | Trade Partner | Stowe - Tech Data - IFC - Control Cabling | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC TD, Distribution only. |  | 2026-05-05 | KPTG-TRANSMIT-016869 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-05 | SMEPS-TRANSMIT-000273 | NA | Trade Partner | SME - MDB IFC | 2 | 1 | 0 | NA | APPROVED | 2026-05-05 | NA | 3087 | 2026-05-12 |  | Incorrect Rev No. | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-017057 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-05 | SMEPS-TRANSMIT-000272 | NA | Trade Partner | SME- LUX LEVELS | 2 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 3085 | 2026-05-13 |  | As requested by Damian -Combining SMEPS-TRANSMIT-000272 and SMEPS-TRANSMIT-000234 for one WF |  | 2026-05-05 | NA | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-05 | ACG-TRANSMIT-000086 | NA | Trade Partner | M3 - Stage 2 External Drawings - IFA Revision | 4 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 4170 | 2026-05-14 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-019888 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-05 | M.S.-TRANSMIT-000009 | NA | Trade Partner | Shop Drawings for Approval | 11 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 268 | 2026-05-12 |  | Review terminated as per jed advise - To retransmit full pack |  | 2026-05-05 | KPTG-IntCorr-002903 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-05 | Stowe-A-TRANSMIT-000575 | NA | Trade Partner | Stowe - Tech Data - IFC - PENETRATION PROTECTION SHOP DRAWING | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC TD, Distribution only. |  | 2026-05-05 | KPTG-TRANSMIT-016877 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-11 | fjc-TRANSMIT-000117 | N/A | Consultant | Drawing Update | 44 | 0 | 0 | NA | APPROVED | 2025-12-12 |  | 487 | 2025-12-19 |  |  | 2025-12-16 | 2025-12-16 | KPTG-SADV-002521 | Closed | 44 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-05 | D&E-TRANSMIT-000667 | NA | Trade Partner | Water Filters - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-005570 | NA | 2026-05-26 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-017569 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-05 | Inhabit-TRANSMIT-000012 | NA | Trade Partner | FP1.4 Performance Based Design Brief (PBDB) | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-000935-As per the direction from Ashlin documents are updated into document register only and transmitted to all parties. |  | 2026-05-05 | KPTG-IntCorr-000935 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-05 | ACG-TRANSMIT-000087 | NA | Trade Partner | M3 - Stage 2 Basement ABS-02 | 1 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 4172 | 2026-05-08 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-019514 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-05 | Inhabit-TRANSMIT-000013 | NA | Trade Partner | Façade Performance Schedules | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-000936-As per the from Ashlin direction documents are updated into document register only and transmitted to all parties. |  | 2026-05-05 | KPTG-IntCorr-000936 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-05 | VIA Arch-TRANSMIT-000114 | NA | Consultant | Re: Stage 02 Water Tank Slab Setout Design Locations | 2 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 809 | 2026-05-08 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-002893 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-05 | Altaire-TRANSMIT-000104 | NA | Trade Partner | M3 S2 - Altaire - Handover Documentation | 0 | 1 | 0 | NA | APPROVED | 2026-04-28 | WF-005574 | NA | 2026-05-18 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-05 | VIA Arch-TRANSMIT-000115 | NA | Consultant | M2 S9-11 Building Permit issue | 39 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 812 | 2026-05-08 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-002710 | Closed | 39 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-05 | VIA Arch-TRANSMIT-000116 | NA | Consultant | STRUCTURAL STEEL PLANS | 4 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 814 | 2026-05-08 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-003146 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-05 | TTW-TRANSMIT-000012 | NA | Consultant | Facade IFC and reg 126 update | 11 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 817 | 2026-05-08 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-003113 | Closed | 11 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-05 | TTW-TRANSMIT-000013 | NA | Consultant | Facade IFC Title block update | 6 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 817 | 2026-05-08 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-003117 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-16 | RDSBIM-TRANSMIT-000129 | NA | Trade Partner | LINDRUM ¦ BASEMENT B1 LEVEL CONCRETE PROFILE PLAN AND SECTIONS | 2 | 0 | 0 | NA | APPROVED | 2025-12-16 |  | 488 | 2025-12-22 |  |  | 2025-12-16 | 2025-12-16 | KPTG-SADV-002520 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-05 | TTW-TRANSMIT-000014 | NA | Consultant | Facade IFC title update | 1 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 817 | 2026-05-08 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-003121 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-05 | D&E-TRANSMIT-000663 | NA | Trade Partner | NXM3S4 - SECURITY GRILLES - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 3080 | 2026-05-12 |  | As per Ellie - KPTG-IntCorr-012751 |  | 2026-05-05 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-05 | SKS Tech-TRANSMIT-000117 | NA | Trade Partner | Comms containment earthing layout | 4 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 3082 | 2026-05-21 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018530 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-05 | ECBS-TRANSMIT-000039 | NA | Trade Partner | Corridor Lintels Specification for approval | 3 | 0 | 0 | NA | APPROVED | 2026-05-05 | WF-005575 | NA | 2026-05-21 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-05 | ASV-TRANSMIT-000171 | NA | Trade Partner | Hydraulic Sample - IW Meter | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-005576 | NA | 2026-05-26 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-018017 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-05 | D&E-TRANSMIT-000248 |  | Trade Partner | NEL-CNT-DEA-2801-BSV-SAM-0045 - VERTIGO - Supports and Fixings | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Error in document number and title. |  | 2026-05-05 | KPTG-TRANSMIT-000826 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-05 | ARCST-TRANSMIT-000275 | NA | Trade Partner | C2-East & West Eve Gutter Framing-IFA | 36 | 0 | 0 | NA | APPROVED | 2026-05-05 | WF-005577 | NA | 2026-05-29 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-018089 | Closed | 36 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-05 | WilsonPD-TRANSMIT-000036 | NA | Trade Partner | Hot Water Package for approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-000623 | NA | 2026-05-14 |  |  | 2026-05-12 | 2026-05-12 | KPTG-TRANSMIT-002999 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-05 | M.S.-TRANSMIT-000011 | SPARK-CRFI-KPG-000654 | Trade Partner | Shop Drawings for Approval | 36 | 0 | 0 | NA | APPROVED |  | NA | 269 | 2026-05-12 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-000940 | Closed | 36 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-05 | WilsonPD-TRANSMIT-000037 | NA | Trade Partner | Hot Water Plant Alternative Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-000624 | NA | 2026-05-14 |  |  | 2026-05-12 | 2026-05-12 | KPTG-TRANSMIT-003002 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-12 | Facx-TRANSMIT-000010 | NA | Trade Partner | Expanded Mesh Detail - Rev - 1 | 6 | 0 | 0 | NA | APPROVED | 2025-12-12 | NA | 3511 | 2025-12-23 |  |  |  | 2026-02-16 | KPTG-TRANSMIT-012941 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-28 | SMEPS-TRANSMIT-000253 | NA | Trade Partner | SME - IFC drawings | 2 | 0 | 0 | NA | APPROVED | 2026-04-28 | NA | 2987 | 2026-05-05 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-016910 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | ARCST-TRANSMIT-000230 | NA | Trade Partner | C3 Cooling Tower Roof & Secondary Framing - Re-Issued for Approval | 0 | 0 | 0 | NA | APPROVED | 2026-03-16 | WF-004835 |  | 2026-03-10 |  | 161 docs still under review |  | 2026-05-05 | KPTG-TRANSMIT-016917 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-05 | D&E-TRANSMIT-000249 | SPARK-CRFI-KPG-000315 | Trade Partner | MWYCCB - LEVEL 1 - PENETRATION LAYOUT ZONE 1 & ZONE 3 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 270 | 2026-05-12 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000910 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-05 | JCBa-TRANSMIT-000106 | NA | Consultant | Structural Setout Plans: L1-L7 OVERALL PLANS IFC | 7 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 878 | 2026-05-12 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-001886 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-05 | KPTG-TRANSMIT-016909 | na | Trade Partner | SME - LIGHTING LUX LEVELS | 6 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 3090 | 2026-05-18 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-018012 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-05 | Nilsen3-TRANSMIT-000139 | NA | Trade Partner | Fwd: Sample submissions | 0 | 4 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC DOCUMENT FOR INFORMATION |  | 2026-05-05 | KPTG-TRANSMIT-016915 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-05 | Nilsen3-TRANSMIT-000140 | NA | Trade Partner | Sample submissions | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-005579 | NA | 2026-05-20 |  | As requested by Damian- WF terminated KPTG-IntCorr-012755 Nilsen3-IntCorr-000206 |  | 2026-05-06 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-05 | D&E-TRANSMIT-000250 | SPARK-CRFI-KPG-000473 | Trade Partner | MWYCCB - LEVEL 1 - PLINTH LAYOUT ZONE 6 & ZONE 7 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 271 | 2026-05-12 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000912 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-05 | Nilsen3-TRANSMIT-000138 | NA | Trade Partner | Nilsen PDU FRAMEs- | 3 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 3093 | 2026-05-13 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-018094 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-05 | ZIA-TRANSMIT-000083 | NA | Trade Partner | Re: M3S4 Control Cable Sample Data Submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect document number | 2026-05-05 | 2026-05-05 | KPTG-RFI-007701 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-01 | Stowe-A-TRANSMIT-000389 | NA | Trade Partner | Stowe - Tech Data Submission - Lighting Protection | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC |  | 2025-12-01 | KPTG-TRANSMIT-010464 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-16 | RDSBIM-TRANSMIT-000128 | NA | Trade Partner | LINDRUM ¦ BASEMENT B1 TO LEVEL 01 COREWALL CONCRETE PROFILE PLAN ELEVATIONS | 2 | 0 | 0 | NA | APPROVED | 2025-12-16 |  | 491 | 2025-12-23 |  |  | 2025-12-18 | 2025-12-18 | KPTG-SADV-002546 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-05 | Rinco-TRANSMIT-000045 | NA | Consultant | Structural Loading plans Issued for Construction | 7 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 882 | 2026-05-12 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-001889 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-14 | ZIA-TRANSMIT-000076 | NA | Trade Partner | PENSTOCK CONTROL PANEL | 1 | 0 | 0 | NA | APPROVED | 2026-04-28 | WF-005464 | NA | 2026-05-11 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-016922 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-03-30 | TATE_-TRANSMIT-000010 | NA | Trade Partner | Tate Shop Drawings - Revise and Resubmit #1 | 21 | 0 | 0 | NA | APPROVED | 2026-03-31 | WF-000107 | NA | 2026-04-09 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-000561 | Closed | 21 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-05 | PSGANZ-TRANSMIT-000011 | NA | Trade Partner | PREM-FR-SMP-014, Fire Curtain Rev2 | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-000736 | NA | 2026-05-08 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-002443 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-05 | PFP PL-TRANSMIT-000085 | NA | Trade Partner | Wet Fire O&M Manual | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with the document number |  | 2026-05-05 | KPTG-SADV-005213 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-05 | PROLMC-TRANSMIT-000022 |  | Trade Partner | Roofing updated drawings 5/5/26 | 20 | 0 | 0 | NA | REJECTED | [5 empty] | Error in revision |  | 2026-05-05 | KPTG-TRANSMIT-000827 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-05 | Schindle-TRANSMIT-000027 | NA | Trade Partner | Lift PL1 - Landing Reveals - FC-01 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Latest IFA revision not approved before submitting IFC. |  | 2026-05-05 | KPTG-SADV-005214 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-05 | Schindle-TRANSMIT-000026 | NA | Trade Partner | Re: Lift C1,C2 & C3 - Landing Frames - FOA -1 for approval | 1 | 0 | 0 | NA | REJECTED | [5 empty] | INCORRECT DOCUMENT NUMBER |  | 2026-05-05 | KPTG-RFI-007710 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-11 | ARCST-TRANSMIT-000224 | NA | Trade Partner | C3 Cooling Tower Upper Gantry - Issued for Review | 0 | 0 | 0 | NA | APPROVED | 2026-03-11 | WF-004717 |  | 2026-04-06 |  |  | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-016948 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-05 | ECBS-TRANSMIT-000082 | NA | Trade Partner | Additional Lay In Ceiling Tiles for Comms Room as per KPTG-CTD-000500 | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-000957 | NA | 2026-05-11 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-002899 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-12 | Facx-TRANSMIT-000011 | NA | Trade Partner | Expanded Mesh Cladding Computations - Rev - 1 | 0 | 1 | 0 | NA | APPROVED | 2025-12-12 | WF-003591 | NA | 2025-12-29 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-05 | 4DW-TRANSMIT-000178 | NA | Trade Partner | Structural Documentation - S104_102 (No longer in use) | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No longer in use, transmitted to all concerned parties |  | 2026-05-05 | KPTG-TRANSMIT-002824 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-05 | SKS Tech-TRANSMIT-000189 | NA | Trade Partner | For Construction Status | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | FC documents send to all parties |  | 2026-05-05 | KPTG-TRANSMIT-003621 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-05 | Auspan-TRANSMIT-000263 | NA | Trade Partner | Resubmit shop drawings for approval. | 2 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 880 | 2026-05-12 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-001819 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-05 | Auspan-TRANSMIT-000264 | NA | Trade Partner | Update already IFCed shop drawings for construction | 11 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected drawing included in IFC. - KPTG-SADV-002273 |  | 2026-05-05 | KPTG-SADV-002273 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-05 | M.2-TRANSMIT-000025 | NA | Trade Partner | Electrical Services Basement Cable tray and Penetrations | 5 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 873 | 2026-05-12 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-002120 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-05 | Auspan-TRANSMIT-000258 | NA | Trade Partner | Update already IFCed shop drawings for construction | 36 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | NA |  |  | IFC - No review required, update the register and distribute. - KPTG-TRANSMIT-001655 | 2026-05-05 | 2026-05-05 | KPTG-TRANSMIT-001655 | Closed | 36 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-05 | Auspan-TRANSMIT-000266 | NA | Trade Partner | - 0G4026 and 0G5041 | 2 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | NA |  |  | IFC - No review required, update the register and distribute. - KPTG-TRANSMIT-001664 |  | 2026-05-05 | KPTG-TRANSMIT-001664 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-05 | Auspan-TRANSMIT-000265 | NA | Trade Partner | Re Resubmit precast shop drawings for approval | 2 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 884 | 2026-05-12 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-001825 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-05 | Auscool-TRANSMIT-000028 | NA | Trade Partner | Basement - IFA shop drawings | 6 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 886 | 2026-05-12 |  | 1 Drawing was terminated and updated | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-002100 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-05 | RESICOM-TRANSMIT-000008 | NA | Trade Partner | 671 Chapel - Waste Chute Shop Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 865 | 2026-05-12 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-001108 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-12 | Ardon-TRANSMIT-000012 | NA | Trade Partner | Frames - Balance of Ground & Level 1 and Basement | 66 | 0 | 0 | NA | APPROVED | 2025-12-12 | NA | 3505 | 2025-12-23 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-05 | KPTG-TRANSMIT-000899 | NA | Trade Partner | Basement Lighting and Power ACC -LGCE | 6 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 468 | 2026-05-12 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-001245 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-05 | vdmcons-TRANSMIT-000134 | NA | Trade Partner | Re: ME25 1004: D116 511-537 Sydney Rd Coburg - Shop Drawings & 3D IFC Model - L03 West Steel Pavillion - Re-IFF - 2026-05-05 | 13 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update Register only...IFC |  |  | NA | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-05 | WilsonPD-TRANSMIT-000034 | NA | Trade Partner | Rod Sealant Tech Data for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-12 | WF-000666 | NA | 2026-05-19 |  | Resubmitted as advised by PC | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-003265 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-05 | WilsonPD-TRANSMIT-000035 | NA | Trade Partner | Tank Level Sensor tech data | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-000620 | NA | 2026-05-14 |  |  | 2026-05-12 | 2026-05-12 | KPTG-TRANSMIT-003001 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-05 | RDSBIM-TRANSMIT-000013 | NA | Trade Partner | MEL05C4 ¦ LEVEL 02 COLO 04 AREA PARTITION WALL LAYOUT AND ELEVATION | 10 | 0 | 0 | NA | APPROVED | 2026-05-05 | WF - 000395 | NA | 2026-05-08 |  | NA | 2026-05-12 | 2026-05-13 | KPTG-TRANSMIT-000857 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-05 | RDSBIM-TRANSMIT-000014 | NA | Trade Partner | MEL05C4 ¦ LEVEL 2 COLO 4 CEILING LAYOUT | 6 | 0 | 0 | NA | APPROVED | 2026-05-05 | WF - 000394 | NA | 2026-05-11 |  | NA | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-000845 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-05 | KPTG-IntCorr-000389 | NA | Trade Partner | Approved ROIP Drawings – Register Update & Issue to SME | 21 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Consultant previously approved drawings - IFC |  | 2026-05-05 | KPTG-TRANSMIT-000816 | Closed | 21 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-05 | SMEPS-IntCorr-000170 | NA | Trade Partner | Request for ZTN BOM Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF - 000396 | NA | 2026-05-08 |  | NA | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-000841 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-05 | SMEPS-TRANSMIT-000204 | NA | Trade Partner | SME Shop Drawing Telecomunications IFC A | 1 | 0 | 0 | NA | APPROVED | 2026-05-05 | WF - 000397 | NA | 2026-05-10 |  | NA | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-000826 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-05 | RDSBIM-TRANSMIT-000015 | NA | Trade Partner | MEL05C4 ¦ LEVEL 02 COLO 04 SCREED LAYOUT | 2 | 0 | 0 | NA | APPROVED | 2026-05-05 | WF - 000399 | NA | 2026-05-07 |  | NA | 2026-05-12 | 2026-05-12 | KPTG-TRANSMIT-000854 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-12 | KPTG-TRANSMIT-010861 | NA | Trade Partner | VicRoad concrete mix design | 0 | 1 | 0 | NA | APPROVED | 2025-12-12 | WF-003579 | NA | 2025-12-24 |  |  | 2026-01-30 | 2026-01-30 | KPTG-TRANSMIT-012198 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-06 | VERTIV-TRANSMIT-000008 | NA | Trade Partner | NEXT DC GE 01 _ TECHNICAL DATA _ COOLING LOAD CALCULATION | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | WF-000113 | NA | 2026-05-14 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-000538 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-05 | Aurecon-TRANSMIT-000108-COM | NA | Client | MCSE Specifications & Schedules | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | NA | 59 | 2026-05-13 |  |  | 2026-06-11 | 2026-06-11 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-06 | WilsonPD-TRANSMIT-000038 | NA | Trade Partner | Equipment for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | WF-000633 | NA | 2026-05-15 |  |  | 2026-05-12 | 2026-05-12 | KPTG-TRANSMIT-003035 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-05 | PMT Sec-TRANSMIT-000014 | NA | Trade Partner | Security Drawings | 26 | 0 | 0 | NA | REJECTED | [5 empty] | Revision A already received and reviewed |  | 2026-05-05 | KPTG-TRANSMIT-000817 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-12 | RDSBIM-TRANSMIT-000195 | NA | Trade Partner | LINDRUM ¦ LEVEL 06 TO LEVEL 10 COREWALL CONCRETE PROFILE PLAN ELEVATION | 2 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 649 | 2026-05-15 |  | KPTG-IntCorr-000944- Submitted document is not current, requested to resubmit. | 2026-05-15 | 2026-05-15 | KPTG-SADV-004171 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-05 | Jangho-TRANSMIT-000071 | NA | Trade Partner | Alum sheet color Dulux Duralloy Surfmist - Matt Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-000456 | NA | 2026-05-13 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001867 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-05 | Rinco-TRANSMIT-000011 | NA | Trade Partner | GF drawings uploaded on Aconex | 7 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 524 | 2026-05-13 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-001686 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-06 | Nilsen3-TRANSMIT-000141 | NA | Trade Partner | M3 Stage3_Jemena Interface Panel Drawing | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | WF-005584 | NA | 2026-05-11 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-05 | INGEN3D-TRANSMIT-000059 | NA | Trade Partner | Level 4-6 - Precast Columns - IFC | 6 | 0 | 0 | NA | APPROVED | 2026-05-05 | WF-000455 | NA | 2026-05-11 |  |  | 2026-05-12 | 2026-05-12 | KPTG-TRANSMIT-001695 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-12 | NXT-TRANSMIT-001135 | NA | Client | 000563-100222 As built documents | 2 | 1 | 0 | NA | APPROVED | 2025-12-12 | NA | NA |  |  |  |  | 2025-12-12 | KPTG-TRANSMIT-010867 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-05 | INGEN3D-TRANSMIT-000058 | NA | Trade Partner | Level 6-8 - Cast In Dowels - IFA | 5 | 0 | 0 | NA | APPROVED | 2026-05-05 | WF-000454 | NA | 2026-05-11 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-001792 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-05 | Jangho-TRANSMIT-000080 | NA | Trade Partner | Glass Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-000474 | NA | 2026-05-22 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-001594 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-06 | IVS-TRANSMIT-000363 | NA | Consultant | Stage 4 - Acoustic Screen & Office Roof Level (Revised Construction Issue) | 1 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 3098 | 2026-05-11 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-017736 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-05 | Jangho-TRANSMIT-000079 | NA | Trade Partner | Glass Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-000473 | NA | 2026-05-22 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-001599 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-05 | Jangho-TRANSMIT-000078 | NA | Trade Partner | Window handle Option 4 CZS619 Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-000472 | NA | 2026-05-22 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002921 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-06 | Civilex-TRANSMIT-000238 | NA | Trade Partner | Sample Submission - Stage 1 - Concrete Curing Compound | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | WF-005585 | NA | 2026-05-12 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-017609 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-05 | Jangho-TRANSMIT-000077 | NA | Trade Partner | Window handle Option 1 LCZS3320M Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-000471 | NA | 2026-05-21 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-002691 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-05 | Jangho-TRANSMIT-000076 | NA | Trade Partner | Glass Sample Submission(GL-12 Option 2) | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-000470 | NA | 2026-05-21 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-001600 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-05 | Jangho-TRANSMIT-000075 | NA | Trade Partner | Glass Sample Submission(GL-10 Option 1) | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-000469 | NA | 2026-05-21 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-001601 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-05 | Jangho-TRANSMIT-000074 | NA | Trade Partner | Alum sheet color Dulux Duratec Elements Weathered Steel - Flat Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-000468 | NA | 2026-05-21 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001861 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-12 | NXT-TRANSMIT-001136 | NA | Client | 000564-100222 As-Built Documents | 3 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2025-12-12 | KPTG-TRANSMIT-010872 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-05 | Jangho-TRANSMIT-000073 | NA | Trade Partner | Alum sheet color Dulux Duratec Eternity Copper Metallic Kinetic - Matt Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-000467 | NA | 2026-05-21 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001863 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-05 | Jangho-TRANSMIT-000072 | NA | Trade Partner | Alum sheet color Dulux Duratec Zeus Dune - Matt Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-000466 | NA | 2026-05-21 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001865 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-05 | WAM-TRANSMIT-000757 | NA | Consultant | A41 Apartment Details 90% DD | 2 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 526 | 2026-05-09 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-001685 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-05 | PCForm-TRANSMIT-000177 | NA | Trade Partner | Raft 2 pour sequence | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected |  | 2026-05-05 | KPTG-TRANSMIT-001556 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-05 | Rinco-TRANSMIT-000010 | NA | Trade Partner | Level 1 PT Reo drawings IFC | 7 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 522 | 2026-05-13 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-001645 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-05 | RDSBIM-TRANSMIT-000031 | NA | Trade Partner | GROUND FLOOR TO LEVEL 09 LIFT CORE 1 CONCRETE PROFILE PLAN AND SECTIONAL ELEVATIONS | 3 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 529 | 2026-05-14 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-05 | RDSBIM-TRANSMIT-000032 | NA | Trade Partner | GROUND FLOOR CONCRETE PROFILE PLAN AND SECTIONS | 7 | 0 | 0 | NA | APPROVED | 2026-05-05 | NA | 531 | 2026-05-14 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-001684 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-05 | Civilex-TRANSMIT-000083 | NA | Trade Partner | Materials for Underground Water Service | 0 | 4 | 0 | NA | APPROVED | 2026-05-05 | WF-000475 | NA | 2026-05-14 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-001757 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-06 | Auspan-TRANSMIT-000069 | NA | Trade Partner | Revised shop drawing 7C02 issued for construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-SADV-004026-As per the direction from Ashlin, the documents were transmitted to all parties. |  | 2026-05-06 | KPTG-SADV-004026 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-06 | ASV-TRANSMIT-000172 | NA | Trade Partner | Revised - Double Check Valve | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | WF-005587 | NA | 2026-05-18 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-019584 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-12 | NXT-TRANSMIT-001137 | NA | Client | 000565-100222 As-built documentation | 4 | 6 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2025-12-12 | KPTG-TRANSMIT-010875 | Closed | 10 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-06 | ASV-TRANSMIT-000173 | NA | Trade Partner | Hydraulic Sample - Trench Grate | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | WF-005588 | NA | 2026-05-27 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-017348 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-06 | PCForm-TRANSMIT-000163 | NA | Trade Partner | Stair 05 shop drawings | 3 | 0 | 0 | NA | APPROVED | 2026-05-06 | WF-005589 | NA | 2026-06-01 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-017870 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-06 | D&E-TRANSMIT-000668 | NA | Trade Partner | NXM3S4 - Level 1 - Mechanical Duct Layout - Zone 3 - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 3100 | 2026-05-14 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-017791 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-06 | ELLISAIR-TRANSMIT-000013 | NA | Trade Partner | Technical Data Submission - Pipework | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | WF-000635 | NA | 2026-05-18 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-003267 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-06 | Auspan-TRANSMIT-000043 | NA | Trade Partner | Re: oversize panels to be split. Update marking plans and elevations. | 4 | 0 | 0 | NA | APPROVED | 2026-05-06 | WF-000114 | NA | 2026-05-15 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-000493 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-06 | Schindle-TRANSMIT-000028 | NA | Trade Partner | Lift C1, C2 & C3 - Landing Frames - FOA -1 for approval | 1 | 0 | 0 | NA | APPROVED | 2026-05-06 | WF-005592 | NA | 2026-05-27 |  | Revision number is missing |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-06 | Auspan-TRANSMIT-000012 | NA | Trade Partner | Cast in plate and fish plate detail for construction. | 2 | 0 | 0 | NA | APPROVED | 2026-05-06 | WF-000115 | NA | 2026-05-15 |  |  | 2026-05-15 | 2026-05-07 | KPTG-TRANSMIT-000488 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-06 | Auspan-TRANSMIT-000038 | NA | Trade Partner | Re: Precast Panel 28 Pipe Peno Adjustment. Update IFCed precast shop drawings. | 2 | 0 | 0 | NA | APPROVED | 2026-05-06 | WF-000116 | NA | 2026-05-15 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-000483 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-06 | SMEPS-IntCorr-000190 | NA | Trade Partner | Updated AFL Cable BOM | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | WF - 000400 | NA | 2026-05-13 |  | NA | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-000847 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-06 | D&E-TRANSMIT-000669 | NA | Trade Partner | NXM3S4 - Ground - Plinth & Equipment Layout - Zone 8 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 3104 | 2026-05-14 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-017248 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-12 | Tradetec-TRANSMIT-000304 | NA | Trade Partner | Penstock Valves - Shop Drawings | 4 | 0 | 0 | NA | APPROVED | 2025-12-12 | NA | 3509 | 2025-12-17 |  |  |  | 2025-12-19 | KPTG-TRANSMIT-011120 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-05 | ECBS-TRANSMIT-000017 | NA | Trade Partner | Tech data for Access Panel & Versilux for approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-05 | WF-001044 | NA | 2026-05-12 |  |  | 2026-05-13 | 2026-05-13 | KPTG-WTRAN-002105 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-06 | Nilsen3-TRANSMIT-000131 | NA | Trade Partner | Re: Updated Earth bar samples | 0 | 2 | 0 | NA | APPROVED | 2026-05-06 | WF-005594 | NA | 2026-05-27 |  |  | 2026-05-27 | 2026-05-27 | KPTG-TRANSMIT-017904 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-06 | Civilex-TRANSMIT-000085 | NA | Trade Partner | Hydraulic Shop Drawing Sheet 2 IFC | 1 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 533 | 2026-05-14 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-001762 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-06 | WilsonPD-TRANSMIT-000191 | SPARK-CRFI-KPG-000666 | Trade Partner | Cast Iron Pipe & Fittings | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-000864 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-06 | ARCST-TRANSMIT-000276 | NA | Trade Partner | NXM3S4: C3-East & West Eve Gutter Framing-IFA | 36 | 0 | 0 | NA | APPROVED | 2026-05-06 | WF-005600 | NA | 2026-06-01 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-018169 | Closed | 36 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-06 | Civilex-TRANSMIT-000239 | na | Trade Partner | Stage 2 - Sample Submission - Organic Landscape Soil - rev FOA-B | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | WF-005595 | na | 2026-05-22 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-017316 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-06 | D&E-TRANSMIT-000670 | NA | Trade Partner | NXM3S4 - Ground - CHW Pipe Layout - Zones - Issued For Construction | 6 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 3106 | 2026-05-14 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-017290 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-06 | D&E-TRANSMIT-000671 | NA | Trade Partner | NXM3S4 - Ground - CHW Pipe Layout - Zone 3 - Issued For Construction | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-05-06 | KPTG-RFI-007724 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-06 | Nilsen3-TRANSMIT-000096 | NA | Trade Partner | Re: Sample submissions | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision of the document has already been received |  | 2026-05-06 | KPTG-RFI-007723 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-06 | KPTG-TRANSMIT-016971 | NA | Trade Partner | Stowe O&M Manual | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | WF-005597 | NA | 2026-05-19 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-018563 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-12 | TTW-TRANSMIT-000148 | NA | Consultant | M3 Stage 2 Civil Drawings | 2 | 0 | 0 | NA | APPROVED | 2025-12-12 | NA | 3500 | 2025-12-18 |  |  | 2025-12-12 | 2025-12-12 | KPTG-TRANSMIT-010889 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-06 | D&E-TRANSMIT-000672 | NA | Trade Partner | NSM3S4 - Ground - Industrial Water Tank Layouts Zone 8 & 10 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 3108 | 2026-05-14 |  | As requested by Ellie — Terminated — KPTG-IntCorr-013787 |  | 2026-05-26 | KPTG-IntCorr-013787 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-06 | Appselec-TRANSMIT-000085 | NA | Trade Partner | Telecom Labelling Schedule - Issued For Approval | 0 | 1 | 0 | Kapitol Advice Awaits: KPTG-IntCorr-000357 | REJECTED | [5 empty] | Document Title block needs to filled :KPTG-IntCorr-000386 |  | 2026-05-15 | KPTG-IntCorr-000386 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-06 | RDSBIM-TRANSMIT-000138 | NA | Trade Partner | MLCSPR ¦ AQUATIC CENTRE WEST LANDSCAPE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 231 | 2026-05-09 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-002838 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-06 | RDSBIM-TRANSMIT-000139 | NA | Trade Partner | MLCSPR ¦ JUNIOR SCHOOL LANDSCAPE PLAN | 5 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 233 | 2026-05-09 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-002841 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-06 | B4C-TRANSMIT-000005 | NA | Consultant | 260505 MLCSPR Redev Kew VIC DDA Perf Soln PBDB - For Construction Stages 1&2 Amd-I | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | FOR INFORMATION DOCUMENTS, TRANSMITTED TO ALL CONCERNED PARTIES |  | 2026-05-06 | KPTG-TRANSMIT-002829 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-06 | B4C-TRANSMIT-000006 | NA | Consultant | Fwd: 260505 MLCSPR Redev Kew VIC DDA Perf Soln PBDB - For Construction Stages 1&2 Amd-I | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | DUPLICATE TRANSMIT:OF B4C-TRANSMIT-000005 |  | 2026-05-06 | KPTG-TRANSMIT-002830 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-06 | RED Fire-TRANSMIT-000003 | NA | Consultant | Fire Engineering Report V6 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | THIS REPORT HAS BEEN TRANMITTED ATO ALL CONCERNED PARTIES:KPTG-TRANSMIT-002831 |  | 2026-05-06 | KPTG-TRANSMIT-002831 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-06 | D&E-TRANSMIT-000251 | SPARK-CRFI-KPG-000466 | Trade Partner | MWYCCB - LEVEL 1 / ROOF - DUCTWORK LAYOUT ZONE 5 + SOUTH SECTIONS & DETAILS - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 278 | 2026-05-13 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000914 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-06 | Rinco-TRANSMIT-000046 | NA | Consultant | Structural loading plan (Level 1) Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 895 | 2026-05-13 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-001893 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-06 | D&E-TRANSMIT-000252 | SPARK-CRFI-KPG-000491 | Trade Partner | MWYCCB - LEVEL 1 - PIPEWORK LAYOUT ZONE 8 & ZONE 9 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 279 | 2026-05-13 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000916 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-12 | HDRAus-TRANSMIT-000342 | NA | Consultant | M3_S2_OFFICE UPDATES_FFE UPDATES | 17 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings multiple status in a single transmittal |  | 2025-12-12 | KPTG-DA-003911 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-06 | HDRAus-TRANSMIT-000475 | NA | Consultant | Resubmit Re: M3 Stage 4 - Document upload - PDF and CAD | 37 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect drawing status in Aconex |  | 2026-05-06 | KPTG-RTRFI-004136 | Closed | 37 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-06 | WilsonPD-TRANSMIT-000192 | SPARK-CRFI-KPG-000436 | Trade Partner | Hydraulic Services - Water Layouts - Ground & Level 1 | 5 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 280 | 2026-05-13 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000918 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-06 | EFP-TRANSMIT-000016 | NA | Trade Partner | EFP Tech Data Alternative | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | WF-000211 | NA | 2026-05-12 |  | workflow -terminated, sunstitution form is required:KPTG-IntCorr-000358 |  | 2026-05-06 | KPTG-IntCorr-000358 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-06 | VIA Arch-TRANSMIT-000030 | NA | Trade Partner | 22kV Signage update | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-05-06 | KPTG-RFI-007730 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-06 | Auspan-TRANSMIT-000044 | NA | Trade Partner | Re-transmitted shop drawings. | 4 | 0 | 0 | NA | APPROVED | 2026-05-06 | WF-000117 | NA | 2026-05-15 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-000479 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-06 | PROLMC-TRANSMIT-000023 | NA | Trade Partner | Proline updated shop drawings MCC 06/05/2026 | 20 | 0 | 0 | NA | REJECTED | [5 empty] | Error in revision |  | 2026-05-06 | KPTG-TRANSMIT-000839 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-06 | TATE_-TRANSMIT-000030 | NA | Trade Partner | REV 3 CEILING ENGINEERING REPORT | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | WF - 000401 | NA | 2026-05-06 |  | NA | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-000880 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-06 | Civilex-TRANSMIT-000240 | NA | Trade Partner | Sample Submission - ASPHALT - 14mm VP & 10mm Suite of Dense Graded Hot & Warm Mixes - Updated naming | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision not updated |  | 2026-05-06 | KPTG-SADV-005231 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-06 | Leemark-TRANSMIT-000033 | NA | Trade Partner | NEL-CNT-LFP-2801-BSF-SDG-0999 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Different Document number and revision Contains multiple pages |  | 2026-05-06 | KPTG-TRANSMIT-000840 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-11-28 | VIA Arch-TRANSMIT-000022 | NA | Consultant | M2 - S09 Precast [Bridge Link] Package Drawing | 1 | 0 | 0 | NA | APPROVED | 2025-12-01 | NA | 95 | 2025-12-03 |  |  | 2025-12-03 | 2025-12-04 | KPTG-TRANSMIT-000220 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-01 | Stowe-A-TRANSMIT-000385 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - LIGHTING CONTROL - LG & GF - 01.12.2025 | 4 | 0 | 0 | NA | APPROVED | 2025-12-01 | NA | 3387 | 2025-12-11 |  |  | 2025-12-18 | 2025-12-19 | KPTG-TRANSMIT-011121 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-12 | KPTG-TRANSMIT-010866 | NA | Trade Partner | Joinery Shop Drawings | 3 | 0 | 0 | NA | APPROVED | 2025-12-12 | NA | 3507 | 2025-12-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-06 | JCBa-TRANSMIT-000246 | NA | Consultant | Updated Amenity and EOT | 4 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 558 | 2026-05-08 |  | NA | 2026-05-15 | 2026-05-15 | DRAFT-017891 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-06 | D&E-TRANSMIT-000674 | NA | Trade Partner | Fire matrix IFA-3 | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Missing Ref. number |  | 2026-05-06 | KPTG-RFI-007733 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-06 | Ardon-TRANSMIT-000043 | NA | Trade Partner | Push / Pull Handle Hardware Samples | 0 | 3 | 0 | NA | APPROVED | 2026-05-06 | WF - 001011 | NA | 2026-05-12 |  | File supersede and WF terminated. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-06 | D&E-TRANSMIT-000673 | NA | Trade Partner | NXM3S4 - Ground - Mechanical Duct Layout - Zone 1 - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 3114 | 2026-05-20 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-017810 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | ARCST-TRANSMIT-000230 | NA | Trade Partner | C3 Cooling Tower Roof & Secondary Framing - Re-Issued for Approval | 0 | 0 | 0 | NA | APPROVED | 2026-03-16 | WF-004835 | NA | 2026-05-06 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-016975 | Closed | 161 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-06 | SMEPS-TRANSMIT-000274 | NA | Trade Partner | SME - PENETRATION DRAWINGS | 17 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 3102 | 2026-05-27 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018494 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-06 | ARCST-TRANSMIT-000277 | NA | Trade Partner | Upper Roof Bridge Frame Over Gutter IFA Shop Drawings | 6 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-05-06 | KPTG-SADV-005243 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-06 | ZIA-TRANSMIT-000084 | NA | Trade Partner | M3S2 SLA Sensors layout | 6 | 0 | 0 |  | REJECTED | [5 empty] | Issue with the revision format and status inside the register and in the document. |  | 2026-05-07 | KPTG-SADV-005251 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-06 | PROLMC-TRANSMIT-000033 | NA | Trade Partner | GRC IFC shop drawings | 29 | 0 | 0 | NA | REJECTED | [5 empty] | SUBMITTED DRAWINGS ARE DUPLICATED OF OTHER DRAWINGS: KPTG-SADV-004275 |  | 2026-05-06 | KPTG-SADV-004275 | Closed | 29 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-06 | IGS--TRANSMIT-000036 | NA | Trade Partner | Revised Electrical Services PDF + DWFX + DWG Files | 5 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 643 | 2026-05-11 |  |  | 2026-05-13 | 2026-05-13 | KPTG-SADV-004139 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-15 | ASV-TRANSMIT-000123 | NA | Trade Partner | Hydraulic Sample Submission - TMV | 0 | 1 | 0 | NA | APPROVED | 2025-12-15 | WF-003593 | NA | 2025-12-26 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-06 | RDSBIM-TRANSMIT-000053 | NA | Trade Partner | GREYSTAR ¦ GROUND FLOOR CONCRETE PROFILE PLAN ZONE 2 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC - No review required - Register and distribute: |  | 2026-05-06 | KPTG-TRANSMIT-001685 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-06 | RDSBIM-TRANSMIT-000054 | NA | Trade Partner | GREYSTAR LEVEL 01 CONCRETE PROFILE PLAN AND SECTION | 5 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 892 | 2026-05-13 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-001896 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-06 | Auspan-TRANSMIT-000267 | NA | Trade Partner | Precast shop drawings for approval. | 13 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 888 | 2026-05-13 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-001874 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-06 | Auspan-TRANSMIT-000268 | NA | Trade Partner | Precast shop drawings for construction. | 14 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - No review required - Register and distribute : KPTG-TRANSMIT-001683 |  | 2026-05-06 | KPTG-TRANSMIT-001683 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-06 | Auscool-TRANSMIT-000025 | NA | Trade Partner | Updated Auscool design roof layout | 0 | 5 | 0 | NA | APPROVED | 2026-05-06 | WF-000468 | NA | 2026-05-12 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-06 | INDS-TRANSMIT-000022 | NA | Trade Partner | : Wet Fire - Schematic | 1 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 896 | 2026-05-13 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-001751 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-06 | Auspan-TRANSMIT-000269 | NA | Trade Partner | Re Update already IFCed shop drawings for construction. | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC No review required; update register and distribute KPTG-TRANSMIT-001691 |  | 2026-05-06 | KPTG-TRANSMIT-001691 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-06 | Auspan-TRANSMIT-000271 | NA | Trade Partner | Precast shop drawings for approval. Zone 3 level 4. | 63 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect attachment. KPTG-SADV-002302 |  | 2026-05-06 | KPTG-SADV-002302 | Closed | 63 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-06 | INDS-TRANSMIT-000023 | NA | Trade Partner | Wet Fire - Basement Zone 3 | 1 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 899 | 2026-05-13 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-001769 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-06 | Electro-TRANSMIT-000005 | NA | Consultant | Specialist Lighting FC-1 Drawing Set | 13 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Need to revise KPTG-DA-002476 |  | 2026-05-06 | NA | Closed | 13 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-15 | ARCST-TRANSMIT-000159 | NA | Trade Partner | Fuel Compound Stairs - Issued for Re-Approval GR7027 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Partial submission |  | 2025-12-15 | KPTG-DA-003930 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-06 | Electro-TRANSMIT-000006 | NA | Consultant | Specialist Lighting FC-1 Drawing Set | 13 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 823 | 2026-05-11 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-002922 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-06 | POTTSENG-TRANSMIT-000011 | NA | Trade Partner | : 671C: HYDRAULIC SERVICES - BASEMENT 3 - PENETRATION LAYOUT | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required; Update register and transmit. KPTG-TRANSMIT-000910 |  | 2026-05-06 | KPTG-TRANSMIT-000910 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-06 | POTTSENG-TRANSMIT-000012 | NA | Trade Partner | : 671C: HYDRAULIC SERVICES - BASEMENT 1 & 2 - PENETRATION LAYOUTS | 2 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 741 | 2026-05-08 |  |  | 2026-05-06 | 2026-05-06 | KPTG-TRANSMIT-000913 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-06 | RDSBIM-TRANSMIT-000063 | NA | Trade Partner | 671CHP BASEMENT 3 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required; Update register and transmit. KPTG-TRANSMIT-000921 |  | 2026-05-06 | KPTG-TRANSMIT-000921 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-06 | POTTSENG-TRANSMIT-000013 | NA | Trade Partner | 671C: HYDRAULIC SERVICES - BASEMENT 1 & 2 - PENETRATION LAYOUTS | 2 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 475 | 2026-05-13 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-001052 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-06 | VIA Arch-TRANSMIT-000119 | NA | Consultant | M2 - STAGE 11 - EAST ELEVATION | 1 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 825 | 2026-05-11 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-002898 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-06 | ELLISAIR-TRANSMIT-000011 | NA | Trade Partner | PAU Technical Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | WF-000627 | NA | 2026-05-18 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-003264 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-06 | DLTS-TRANSMIT-000002 | NA | Trade Partner | L2 Platform (Antenna Room) IFA Package | 36 | 0 | 0 | NA | APPROVED | 2026-05-06 | WF-000632 | NA | 2026-05-13 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-003546 | Closed | 36 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-06 | WilsonPD-TRANSMIT-000039 | NA | Trade Partner | Siphonic Drainage Tech Data for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | WF-000634 | NA | 2026-05-15 |  |  | 2026-05-12 | 2026-05-12 | KPTG-TRANSMIT-003000 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-06 | RDSBIM-TRANSMIT-000003 | NA | Trade Partner | NXM2S9 ¦ LEVEL 2 HOB AND PLINTH LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 819 | 2026-05-13 |  | Voided as advised by Stuart Knox |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-15 | KPTG-TRANSMIT-010896 | NA | Trade Partner | Joinery Shop Drawings - JN-002 | 2 | 0 | 0 | NA | APPROVED | 2025-12-15 | NA | 3517 | 2025-12-19 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-06 | ACG-TRANSMIT-000032 | NA | Trade Partner | M3 - DH7/8 O&M Manual Rev1 | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | WF-001001 | NA | 2026-05-13 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-06 | ADP-TRANSMIT-000042 | NA | Consultant | ADP MEL4834 - Updted Electrical drawings | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Distribution only-IFC |  | 2026-05-06 | KPTG-TRANSMIT-002897 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-06 | WilsonPD-IntCorr-000087 | NA | Trade Partner | Wilson Plumbing and Drainage - Practical Completion Documentation | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | 1002 | NA | 2026-05-11 |  |  | 2026-05-14 | 2026-05-14 | Awaiting approval | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-06 | INGEN3D-TRANSMIT-000060 | NA | Trade Partner | Level 4 - Cast in Dowels - IFC | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | QA - Register updated |  | 2026-05-06 | NA | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-06 | PCForm-TRANSMIT-000178 | NA | Trade Partner | Raft 3 pour sequence | 1 | 0 | 0 | NA | APPROVED |  | NA | 565 | 2026-05-21 |  | Rejected | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-001909 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-06 | PCForm-TRANSMIT-000179 | NA | Trade Partner | 50mpa 700 spread mix for approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | WF-000485 | NA | 2026-05-11 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-001634 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-06 | PCForm-TRANSMIT-000180 | NA | Trade Partner | PT and Surelok Grout TDS for approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | WF-000486 | NA | 2026-05-11 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-001630 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-06 | WAM-TRANSMIT-000758 | NA | Consultant | Door Details for Review | 2 | 0 | 0 | NA | APPROVED | 2026-05-06 | NA | 535 | 2026-05-12 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-001821 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-07 | 4DW-TRANSMIT-000033 | NA | Consultant | Structural Documentation: Block 1 & 2 - Foundations & Piling (Issued for Certification). Level 1 transfer beam reframing (Coordination). | 1 | 0 | 0 |  | APPROVED | 2026-05-07 | NA | 75 | 2026-05-15 |  | Actual receiving date-04-05-2026 | 2026-05-28 | 2026-06-28 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-16 | Nilsen3-TRANSMIT-000122 | NA | Trade Partner | Nilsen As-builts | 19 | 0 | 0 | NA | APPROVED | [5 empty] | As-Builts, No review required. Distributed to the Project Team. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-06 | Aurecon-TRANSMIT-000108-CSM | NA | Client | MCSE Specifications & Schedules | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | NA | 61 | 2026-05-14 |  |  | 2026-06-11 | 2026-06-11 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-06 | Aurecon-TRANSMIT-000108-ELC | NA | Client | MCSE Specifications & Schedules | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | NA | 63 | 2026-05-14 |  |  | 2026-06-11 | 2026-06-11 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-06 | Aurecon-TRANSMIT-000108-FIP | NA | Client | MCSE Specifications & Schedules | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | NA | 65 | 2026-05-14 |  |  | 2026-06-11 | 2026-06-11 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-06 | Aurecon-TRANSMIT-000108-HYD | NA | Client | MCSE Specifications & Schedules | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | NA | 67 | 2026-05-14 |  |  | 2026-06-11 | 2026-06-11 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-06 | Aurecon-TRANSMIT-000108-MEC | NA | Client | MCSE Specifications & Schedules | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | NA | 69 | 2026-05-14 |  |  | 2026-05-08 | 2026-05-11 | KPTG-TRANSMIT-000064 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-06 | Aurecon-TRANSMIT-000108-TEL | NA | Client | MCSE Specifications & Schedules | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | NA | 71 | 2026-05-14 |  |  | 2026-06-11 | 2026-06-11 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-06 | Aurecon-TRANSMIT-000108-FUL | NA | Client | MCSE Specifications & Schedules | 0 | 1 | 0 | NA | APPROVED | 2026-05-06 | NA | 73 | 2026-05-14 |  |  | 2026-06-11 | 2026-06-11 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-06 | INGEN3D-TRANSMIT-000061 | NA | Trade Partner | Level 4 - Cast in Dowels - No Longer In Use | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | QA - 'No Longer in Use' Register updated |  | 2026-05-06 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-06 | INGEN3D-TRANSMIT-000062 | NA | Trade Partner | Level 4 - CD0151 & MP0084 - Revised IFC | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | QA - Register updated |  | 2026-05-06 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | KPTG-TRANSMIT-016973 | NA | Consultant | Stage 4 - Document upload - PMJ detail and Door schedule update - PDF and CAD | 0 | 2 | 0 | NA | APPROVED | 2026-05-07 | NA | 3116 | 2026-05-16 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-16 | DRLL-TRANSMIT-000052 | NA | Trade Partner | Marshalling Box Drawings - NO LONGER IN USE. | 30 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Drawings updated as No Longer in Use in Aconex |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-07 | GEMBA-D-TRANSMIT-000017 | NA | Consultant | NEXTDC GE1 - Roof slab + cooling tower - For Construction | 18 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 209 | 2026-05-12 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-000505 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-07 | RDSBIM-TRANSMIT-000007 | NA | Trade Partner | NXGE01 ¦ ROOF CONCRETE PROFILE KEY PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 211 | 2026-05-13 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-000530 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-07 | Auspan-TRANSMIT-000045 | NA | Trade Partner | Re: Staging Room Door Opening Height Change - Panel 76, 77, 78 | 1 | 0 | 0 | NA | APPROVED | 2026-05-07 | WF-000120 | NA | 2026-05-18 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-000501 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | Nilsen3-TRANSMIT-000145 | NA | Trade Partner | Cable Cleats | 0 | 1 | 0 | NA | APPROVED | 2026-05-07 | WF-005604 | NA | 2026-05-28 |  | The document has been resubmitted through a new transmittal |  | 2026-05-08 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-07 | Auspan-TRANSMIT-000046 | na | Trade Partner | Re: Staging Room Door Opening Height Change - Panel 76, 77, 78 | 3 | 0 | 0 | NA | APPROVED | 2026-05-07 | WF-000121 | na | 2026-05-18 |  | 03/06/2026 1 doc closed | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-000714 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | Nilsen3-TRANSMIT-000148 | NA | Trade Partner | Ground floor Cable | 6 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-05-07 | KPTG-RFI-007742 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-07 | Civilex-TRANSMIT-000241 | na | Trade Partner | Sample Submission - ASPHALT - 14mm VP & 10mm Suite of Dense Graded Hot & Warm Mixes - Updated naming | 0 | 1 | 0 | NA | APPROVED | 2026-05-07 | WF-005608 | na | 2026-05-13 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-017656 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | Tradetec-TRANSMIT-000437 | NA | Trade Partner | Stage 4 - LVP47 | 1 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 3118 | 2026-05-14 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-017278 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-07 | SMEPS-TRANSMIT-000032 | NA | Trade Partner | M2 - General Power Devices | 0 | 6 | 0 | NA | APPROVED | 2026-05-07 | WF-000642 | NA | 2026-05-15 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-003067 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-06 | ZIA-TRANSMIT-000051 | NA | Trade Partner | IP Address Register | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | harry to confirm-KPTG-IntCorr-001264.Update and send to all parties |  | 2026-05-13 | KPTG-TRANSMIT-003673 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-16 | DRLL-TRANSMIT-000054 | NA | Trade Partner | Marshalling Box Drawings - NO LONGER IN USE | 39 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Drawings status updated as No Longer in Use in Aconex |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-07 | INTRFRM-TRANSMIT-000038 | na | Trade Partner | Geelong Edge - Roof Slab Post Tensioning Shop Drawing | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect document numbering |  | 2026-05-07 | DRAFT-001757 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | SKS Tech-TRANSMIT-000121 | NA | Trade Partner | Power and Comms containment plans | 49 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect attachment |  | 2026-05-07 | KPTG-TRANSMIT-017003 | Closed | 49 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-07 | INTRFRM-TRANSMIT-000039 | NA | Trade Partner | Re: Geelong Edge - Roof Slab Post Tensioning Shop Drawing | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Document number and revision is not mentioned in the drawing |  | 2026-05-07 | DRAFT-001758 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | SKS Tech-TRANSMIT-000130 | NA | Trade Partner | Power and Comms containment layout | 29 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 3133 | 2026-05-15 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-019829 | Closed | 29 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | SKS Tech-TRANSMIT-000130 | NA | Trade Partner | Power and Comms containment layout | 17 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 3136 | 2026-05-15 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-019576 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-07 | D&E-TRANSMIT-000240 | SPARK-CRFI-KPG-000570 | Trade Partner | MECHANICAL SWITCHBOARD DRAWINGS | 0 | 4 | 0 | NA | APPROVED |  | NA | NA |  |  | Reopen to closed out Front page will be added from next revision. |  | 2026-05-07 | KPTG-TRANSMIT-000841 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-07 | ASV-TRANSMIT-000174 | NA | Trade Partner | Hydraulic Sample - Industrial Water Meter | 0 | 1 | 0 | NA | APPROVED | 2026-05-07 | WF-005617 | NA | 2026-05-19 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-017373 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | SKS Tech-TRANSMIT-000131 | NA | Trade Partner | Comms containment layout roof | 3 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 3141 | 2026-05-15 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-018134 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-07 | PROLMC-TRANSMIT-000024 | NA | Trade Partner | Updated Shop Drawings MCC 07/05/2026 | 20 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing title inside the drawing and in Aconex seem different |  | 2026-05-07 | KPTG-TRANSMIT-000843 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-16 | D&E-TRANSMIT-000289 | NA | Trade Partner | Technical Data Submission - Max Cool Sensors FC2 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC, No review required, distributed to the Project Team. |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | D&E-TRANSMIT-000681 | NA | Trade Partner | Functional Description - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-07 | WF-005619 | NA | 2026-05-28 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-018929 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | D&E-TRANSMIT-000676 | NA | Trade Partner | NXM3S4 - SECURITY GRILLES - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 3140 | 2026-05-15 |  | Terminated -instructed by Ellie |  | 2026-05-07 | KPTG-IntCorr-012884 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | NXT-TRANSMIT-001543 | NA | Trade Partner | Fwd: M3 Stage 4 FAT reports (Batch 3&4) | 0 | 10 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-05-07 | KPTG-TRANSMIT-017033 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-10-15 | NXT-TRANSMIT-001005 | NA | Client | EA ROOM MANUALS ISSUED FOR REVIEW | 0 | 1 | 0 | NA | APPROVED | 2026-03-19 | WF-004896 | NA | 2026-03-30 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-017035 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | SMEPS-TRANSMIT-000275 | NA | Trade Partner | SME - DRAWINGS IFA PART SUBMISSIONS | 2 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 3151 | 2026-05-15 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018436 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-07 | SES AU-TRANSMIT-000027 | NA | Trade Partner | SECURITY- COLO 5 SCEC LAYOUTS-IFA | 2 | 0 | 0 | NA | APPROVED | 2026-05-07 | WF-000212 | NA | 2026-05-13 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-000633 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-07 | EFP-TRANSMIT-000017 | NA | Trade Partner | FIRE SERVICES IFC | 16 | 0 | 0 | NA | APPROVED | 2026-05-07 | WF-000213 | NA | 2026-05-08 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-000594 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | SKS Tech-TRANSMIT-000120 | NA | Trade Partner | Lighting Control Gear | 0 | 1 | 0 | NA | APPROVED | 2026-05-07 | WF-005624 | NA | 2026-05-28 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-017484 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-07 | Entire M-TRANSMIT-000044 | NA | Trade Partner | IFA LLDPE Tube Colour for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-07 | WF-000214 | NA | 2026-05-13 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-000640 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-07 | PMT Sec-TRANSMIT-000016 | NA | Trade Partner | Requested updated Data Sheets | 0 | 6 | 0 | NA | REJECTED | [5 empty] | Document number contains revision |  | 2026-05-07 | KPTG-TRANSMIT-000844 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-16 | ACG-TRANSMIT-000013 | NA | Trade Partner | Electronic security IFA | 2 | 0 | 0 | NA | APPROVED | 2025-12-16 | NA | 756 | 2026-06-23 |  |  | 2026-01-07 | 2026-01-07 | KPTG-TRANSMIT-002363 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-29 | Auspan-TRANSMIT-000029 | na | Trade Partner | Precast shop drawings for construction. | 3 | 0 | 0 | NA | APPROVED | 2026-04-29 | WF-000093 | na | 2026-05-04 |  |  | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-000497 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-07 | ZIA-TRANSMIT-000082 | NA | Trade Partner | Re: M3S4 Resubmit Sample data sheet | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Revision No. is missing |  | 2026-05-07 | KPTG-RFI-007755 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-17 | KPTG-TRANSMIT-014498 | NA | Consultant | WF Request - C1 East Lower Gantry | 0 | 0 | 0 | NA | APPROVED | 2026-03-10 | WF-004851 & WF-005527 | NA | 2026-04-07 |  |  |  | 2026-05-07 | KPTG-TRANSMIT-017044 | Closed | 145 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | SKS Tech-TRANSMIT-000122 | NA | Trade Partner | Power containment layout plant - | 3 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 3123 | 2026-05-16 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018502 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | SKS Tech-TRANSMIT-000123 | NA | Trade Partner | Power containment layout | 3 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 3126 | 2026-05-11 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-017294 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | D&E-TRANSMIT-000678 | NA | Trade Partner | NXM3S4 - Ground - CHW Pipe Layout - Zone 3 | 1 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 3128 | 2026-05-11 |  |  | 2026-05-12 | 2026-05-12 | KPTG-TRANSMIT-017193 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | D&E-TRANSMIT-000679 | NA | Trade Partner | Fire matrix IFA-3 | 0 | 1 | 0 | NA | APPROVED | 2026-05-07 | WF-005615 | NA | 2026-05-27 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-017797 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | ZIA-TRANSMIT-000083 | NA | Trade Partner | Re: M3S4 Control Cable Sample Data Submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | REJECTED DUE TO MISSING OF REVISION NUMBER IN INSIDE DRAWING |  | 2026-05-07 | KPTG-RTRFI-004156 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-07 | ARCST-TRANSMIT-000278 | na | Consultant | Upper Roof Bridge Frame Over Gutter IFA Shop Drawings | 6 | 0 | 0 | NA | APPROVED | 2026-05-07 | WF-005625 | na | 2026-05-25 |  | Terminated as advised by William Duffield that further work is required before drawings are updated. (KPTG-IntCorr-012923) | 2026-05-11 | 2026-05-11 | KPTG-IntCorr-012979 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | PARR-TRANSMIT-000175 | NA | Trade Partner | Re: P2685 - NDC M3 - Stage 4 - Battery Rooms - SCHEMATIC -IFC | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Revision not mentioned in history |  | 2026-05-07 | KPTG-RFI-007757 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-16 | Hames-TRANSMIT-000090 | NA | Trade Partner | Fire Wall Update | 2 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED - KPTG-TRANSMIT-002294 |  |  |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-07 | RDSBIM-TRANSMIT-000196 | NA | Trade Partner | LINDRUM ¦ GROUND LEVEL - BLOCK WALL ELEVATION PLAN AND ELEVATION | 2 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-IntCorr-000949-The drawing attached in LIN-KAP-BW-ARC-BL-013 is incorrect and duplicated .the revision also incorrect |  | 2026-05-07 | KPTG-IntCorr-000949 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-07 | 42636706-IntCorr-000015 | NA | Trade Partner | Revised Basement Drawing. | 1 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 644 | 2026-05-14 |  |  | 2026-05-22 | 2026-05-22 | KPTG-SADV-004275 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-07 | MLAW-TRANSMIT-000004 | NA | Trade Partner | THERMACORD SLIDING DOOR - SHOP DRAWINGS REV 1 | 7 | 0 | 0 | NA | APPROVED | 2026-05-07 | WF-000740 | NA | 2026-05-08 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-002495 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-07 | 4DW-TRANSMIT-000098 | NA | Consultant | Ground to Level 01 Updates | 10 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 645 | 2026-05-12 |  |  | 2026-05-08 | 2026-05-08 | KPTG-SADV-004085 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-07 | PCForm-TRANSMIT-000080 | NA | Trade Partner | Fwd: Facade Cast In Drawings | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-000950-JUST FOR INFORMATION. |  | 2026-05-07 | KPTG-IntCorr-000950 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | PARR-TRANSMIT-000176 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - HVAC DATASHEET -IFA | 0 | 2 | 0 | NA | APPROVED | 2026-05-07 | WF-005626 | NA | 2026-05-12 |  |  |  | 2026-05-11 | NXT-PA-004656 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-07 | PARR-TRANSMIT-000058 | NA | Trade Partner | Fuel Services - MODBUS REGISTER & L4 CABLE GA - IFC | 2 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 1264 | 2026-05-11 |  | drawings submitted | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-003711 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-07 | WGAVIC-TRANSMIT-000114 | NA | Consultant | M2 - Stage 10 & 11 Sumps - Issued for Construction | 3 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 830 | 2026-05-12 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-003283 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-07 | WGAVIC-TRANSMIT-000115 | NA | Consultant | M2 - Block Wall Details - Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 831 | 2026-05-12 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-003291 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-07 | PARR-TRANSMIT-000059 | NA | Trade Partner | Fuel Services - FD - IFC | 0 | 1 | 0 | NA | APPROVED | 2026-05-07 | WF-001050 | NA | 2026-05-14 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-003875 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-02 | Fyfe-TRANSMIT-000006 | NA | Consultant | Civil Building Set - For Approval (Reissue) | 9 | 0 | 0 | NA | APPROVED | 2025-12-02 | WF-000076 | 148 | 2025-12-04 |  |  |  | 2025-12-05 | KPTG-TRANSMIT-000263 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-12 | GunAus-TRANSMIT-000006 | NA | Trade Partner | Attack Doors Windows - Details | 18 | 0 | 0 | REJECTED - KPTG-TRANSMIT-002292 | REJECTED | [5 empty] | RCVD 12/12, FORWARDED BY NICK - KPTG-IntCorr-000796 DTD 15/12/2025 |  |  |  | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | SKS Tech-TRANSMIT-000129 | NA | Trade Partner | Data hall section drawings for IFA- | 7 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 3143 | 2026-05-21 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018432 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-07 | HDRAus-TRANSMIT-000480 | NA | Consultant | Eave Gutter Outrigger | 2 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 3149 | 2026-05-11 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-018103 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-07 | SKS Tech-TRANSMIT-000191 | NA | Trade Partner | BASEMENT POWER CONTAINMENT IFC UPDATE | 1 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 1266 | 2026-05-11 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-003707 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-07 | PROLMC-TRANSMIT-000034 | NA | Trade Partner | Re: Highly Important: Action Requires on Re: GRC IFC shop drawings | 29 | 0 | 0 | NA | REJECTED | [5 empty] | Document number of all drawings are duplicate. Requested to resubmit:KPTG-SADV-004284 |  | 2026-05-07 | KPTG-SADV-004284 | Closed | 29 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-07 | 4DW-TRANSMIT-000035 | NA | Consultant | Issued for Construction: Piling & Column amendment packages | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Already submitted-for Kapitol information only |  | 2026-05-07 | NA | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-07 | D&E-TRANSMIT-000677 | NA | Trade Partner | NXM3S2 - Lower Ground - Fuel Tank Pump Room Layout - Issued For Approval | 1 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-05-07 | KPTG-SADV-005259 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-07 | 4DW-TRANSMIT-000036 | NA | Consultant | Issued for Information: 4DW Structural outline plans | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Already submitted-for Kapitol information only |  | 2026-05-07 | NA | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-07 | Eneraque-TRANSMIT-000013 | NA | Trade Partner | Fire Penetration Collar / Intumescent Seal Datasheet & Type Test | 0 | 1 | 0 | NA | APPROVED | 2026-05-07 | WF-000644 | NA | 2026-05-18 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-003346 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-07 | JCBa-TRANSMIT-000107 | NA | Consultant | Updated Architectural Documentation - Overall Plans, GA Plans & Apartment Type Plans | 81 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 912 | 2026-05-11 |  | Review Voided as advised by DM; Consultant to supersede the drawings | 2026-05-19 | 2026-05-19 | NA | Closed | 81 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-07 | Auspan-TRANSMIT-000272 | NA | Trade Partner | Precast Drawings - For Approval | 2 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 908 | 2026-05-14 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-001944 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-16 | GunAus-TRANSMIT-000007 | NA | Trade Partner | Attack Doors Windows - Details | 18 | 0 | 0 | NA | APPROVED | 2025-12-16 | NA | 760 | 2025-12-18 |  |  | 2026-01-13 | 2026-01-13 | KPTG-TRANSMIT-002381 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-07 | Auspan-TRANSMIT-000273 | NA | Trade Partner | Re: Level 2 - Precast Mark-up. Query for penos | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC No review required; update register and distribute - KPTG-TRANSMIT-001724 |  | 2026-05-07 | KPTG-TRANSMIT-001724 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-07 | Auspan-TRANSMIT-000264 | NA | Trade Partner | Update already IFCed shop drawings for construction | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC No review required; update register and distribute - KPTG-TRANSMIT-001715 |  | 2026-05-07 | KPTG-TRANSMIT-001715 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-07 | Auspan-TRANSMIT-000271 | NA | Trade Partner | Precast shop drawings for approval. Zone 3 level 4. | 62 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 910 | 2026-05-14 |  |  | 2026-05-25 | 2026-05-25 | Auspan-TRANSMIT-000271 | Closed | 62 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-07 | JCBa-TRANSMIT-000109 | NA | Consultant | Updated Architectural Documentation - Overall Plans - Ground & Level 1 | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update and Distribute; Reviewed in JCBa-TRANSMIT-000107 - KPTG-TRANSMIT-001718 |  | 2026-05-07 | KPTG-TRANSMIT-001718 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-07 | INDS-TRANSMIT-000024 | NA | Trade Partner | Wet Fire - Basement Zone 1 | 1 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 915 | 2026-05-14 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-001754 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-07 | PARR-TRANSMIT-000058 | NA | Trade Partner | Fuel Services - MODBUS REGISTER | 0 | 2 | 0 | NA | REJECTED | [5 empty] | rejected |  | 2026-05-07 | KPTG-IntCorr-001268 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-08 | Nilsen3-TRANSMIT-000149 | NA | Trade Partner | Cable Cleats | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-05-08 | KPTG-RFI-007766 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-07 | WAM-TRANSMIT-000759 | NA | Consultant | A09 Overall Plans, issued for 100% DD | 18 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 537 | 2026-05-10 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-001682 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-08 | SMEPS-TRANSMIT-000276 | NA | Trade Partner | Revised Jemena Easement Shopdrawing - 08.05.2026 | 1 | 0 | 0 | NA | APPROVED | 2026-05-08 | WF-005632 | NA | 2026-05-15 |  | Terminated as advised by Mark hendrikse | 2026-05-08 | 2026-05-08 | KPTG-IntCorr-012924 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-07 | WAM-TRANSMIT-000760 | NA | Consultant | A02 Demolition plans and Sections - issued for Construction | 9 | 0 | 0 | KPTG-TRANSMIT-001621 | APPROVED | 2026-05-11 | NA | ACC 545 | 2026-05-13 |  | 1 DWG MADE NO LONGER IN USE - PRECESSED 8 DOCS REF: WAM-RTRFI-000289 | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001853 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-16 | RDSBIM-TRANSMIT-000092 | NA | Trade Partner | MLC ¦ AQUATIC CENTER LEVEL 02 WALL PANELING PLAN & ELEVATIONS | 2 | 0 | 0 | NA | APPROVED | 2025-12-16 |  | 379 | 2025-12-23 |  |  |  | 2026-01-20 | KPTG-SADV-003449 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-07 | Civilex-TRANSMIT-000087 | NA | Trade Partner | Water Shop Drawing IFC | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-05-07 | KPTG-TRANSMIT-001620 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-08 | D&E-TRANSMIT-000652 | NA | Trade Partner | ISSUED FOR APPROVAL - CHW & SFN SCHEMATICS | 9 | 0 | 0 | NA | APPROVED | 2026-05-08 | NA |  | 2026-05-18 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018340 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-08 | Entire M-TRANSMIT-000035 | NA | Trade Partner | IFA LLDPE Tube Colour for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-08 | WF - 000408 | NA | 2026-05-15 |  | NA | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-000842 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-08 | RDSBIM-TRANSMIT-000197 | NA | Trade Partner | LINDRUM ¦ GROUND LEVEL - BLOCK WALL ELEVATION PLAN AND ELEVATION | 2 | 0 | 0 | NA | APPROVED | 2026-05-08 | NA | #646 | 2026-05-15 |  |  | 2026-06-01 | 2026-06-01 | KPTG-SADV-004360 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-07 | sMEPS-TRANSMIT-000207 | NA | Trade Partner | AHU Isolator rev 5 | 0 | 1 | 0 | NA | APPROVED | 2026-05-07 | WF - 000402 | NA | 2026-05-13 |  | NA | 2026-05-07 | 2026-05-07 | KPTG-TRANSMIT-000831 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-07 | sMEPS-TRANSMIT-000208 | NA | Trade Partner | SCCR Rack Isolator Sample for review | 0 | 1 | 0 | NA | APPROVED | 2026-05-07 | WF - 000403 | NA | 2026-05-13 |  | NA | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-000836 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-07 | sMEPS-TRANSMIT-000209 | NA | Trade Partner | sMEPS-TRANSMIT-000209 | 0 | 14 | 0 | NA | APPROVED | 2026-05-07 | WF - 000404 | NA | 2026-05-13 |  | NA | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-000853 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-07 | sMEPS-TRANSMIT-000210 | NA | Trade Partner | SME Sample for review | 0 | 1 | 0 | NA | APPROVED | 2026-05-07 | WF - 000406 | NA | 2026-05-13 |  | NA | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-000837 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-07 | JCBa-TRANSMIT-000247 | NA | Consultant | East Pavilion - Issue For Information | 7 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 559 | 2026-05-11 |  | NA | 2026-05-22 | 2026-05-22 | DRAFT-018103 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-16 | KPTG-Intcorr-003680 | NA | Trade Partner | Proline Sunshade Caulking Sample | 0 | 1 | 0 | NA | APPROVED | 2026-01-20 | WF-000733 |  | 2025-12-23 |  |  |  | 2026-01-21 | KPTG-TRANSMIT-002161 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-07 | WDes-TRANSMIT-000054 | NA | Consultant | Updated civil documentation | 4 | 0 | 0 | NA | APPROVED | 2026-05-07 | NA | 561 | 2026-05-11 |  | NA | 2026-05-15 | 2026-05-15 | DRAFT-017892 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-07 | vdmcons-TRANSMIT-000135 | NA | Trade Partner | ME25 1004: D117 511-537 Sydney Rd Coburg - Shop Drawings & 3D IFC Model - L03 West Steel Pavilion - Re-IFF - 2026-05-07 | 13 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC only for distribution. |  |  | KPTG-TRANSMIT-002950 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-07 | vdmcons-TRANSMIT-000136 | NA | Trade Partner | ME25 1004: D118 511-537 Sydney Rd Coburg - Shop Drawings & 3D IFC Model - L09 Terrace Steel Frames - IFF - 2026-05-07 | 22 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC only for distribution. |  |  | KPTG-IntCorr-001699 | Closed | 22 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-08 | INTRFRM-TRANSMIT-000040 | na | Trade Partner | Re: Geelong Edge - Roof Slab Post Tensioning Shop Drawing | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong document numbering |  | 2026-05-08 | DRAFT-001792 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-08 | Nilsen3-TRANSMIT-000150 | NA | Trade Partner | Cable Cleats | 0 | 1 | 0 | NA | APPROVED | 2026-05-08 | WF-005629 | NA | 2026-05-29 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018359 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-08 | RDSBIM-TRANSMIT-000191 | NA | Trade Partner | ¦ LEVEL 07 PARTITION WALL LAYOUT (L07 & L08 TYPICAL) | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - drawings only for distribution. |  |  | KPTG-TRANSMIT-002954 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-08 | SKS Tech-TRANSMIT-000132 | NA | Trade Partner | Supports and hangers layout M3S4 | 8 | 0 | 0 | NA | APPROVED | 2026-05-08 | NA | 3161 | 2026-05-18 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-018223 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-08 | Stowe-A-TRANSMIT-000576 | na | Trade Partner | STOWE - DRAWING SUBMISSION - LOWER ROOF POWER & DATA HALL RETIC | 6 | 0 | 0 | NA | APPROVED | 2026-05-08 | na | 4177 | 2026-05-21 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-018683 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-08 | Stowe-A-TRANSMIT-000577 | na | Trade Partner | Stowe - Tech Data - IFC - EXTERNAL LIGHTING | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Wrong document number |  | 2026-05-08 | KPTG-SADV-005271 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-08 | VERTIV-TRANSMIT-000009 | na | Trade Partner | NEXT DC GE 01 _ CFD ANALYSIS REPORT | 0 | 1 | 0 | NA | APPROVED | 2026-05-08 | WF-000123 | na | 2026-05-18 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-000650 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-16 | VAE-Grp-TRANSMIT-000093 | NA | Trade Partner | MECHANICAL - MECHANICAL CONTROL SYSTEM (MCS) FUNCTIONAL DESCRIPTION | 0 | 1 | 0 | NA | APPROVED | 2025-12-16 | WF-000649 | NA | 2025-12-19 |  |  | 2026-01-27 | 2026-01-27 | KPTG-WTRAN-001443 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-08 | D&E-TRANSMIT-000684 | NA | Trade Partner | NXM3S2 - Lower Ground - Fuel Tank Pump Room Layout - Issued For Approval - #4179 | 1 | 0 | 0 | NA | APPROVED | 2026-05-08 | NA | 4179 | 2026-05-19 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-019056 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-08 | D&E-TRANSMIT-000685 | NA | Trade Partner | NXM3S4 - TYPICAL HAC PIPEWORK LAYOUT - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-05-08 | NA | 3166 | 2026-05-18 |  | As requested by Ellie — Terminated — KPTG-IntCorr-013787 |  | 2026-05-26 | KPTG-IntCorr-013787 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-08 | Stowe-A-TRANSMIT-000579 | na | Trade Partner | Stowe - Tech Data - IFC - PE Enclosure | 0 | 1 | 0 | NA | APPROVED | 2026-05-08 | WF-005636 | na | 2026-05-20 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-08 | Detail-TRANSMIT-000002 | NA | Trade Partner | Re: DOOR HARDAWRE SCHEDULE | 0 | 1 | 0 | NA | REJECTED | [5 empty] | rejected due to incorrect document naming |  | 2026-05-08 | KPTG-TRANSMIT-017086 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-08 | RDSBIM-TRANSMIT-000269 | NA | Trade Partner | NXM3S4 ROOF CONCRETE PROFILE PLAN AND SECTION ZONE C1, C2, C3 | 8 | 0 | 0 | NA | APPROVED | 2026-05-08 | NA | 3164 | 2026-05-21 |  | As instructed by Lachlan S. Terminated |  | 2026-08-13 | KPTG-TRANSMIT-020527 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-08 | Civilex-TRANSMIT-000242 | na | Trade Partner | Sample Submission - Pavement Concrete mix design Pronto - Rev FOA - D | 0 | 1 | 0 | NA | APPROVED | 2026-05-08 | WF-005638 | na | 2026-05-14 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018426 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-08 | SKS Tech-TRANSMIT-000133 | NA | Trade Partner | Re: Equipment Layout | 7 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect drawing status |  | 2026-05-08 | KPTG-RFI-007781 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-08 | SMEPS-TRANSMIT-000211 | NA | Trade Partner | SME Shop Drawing Telecomunications IFA | 1 | 0 | 0 | NA | APPROVED | 2026-05-08 | WF - 000409 | NA | 2026-05-14 |  | NA | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-000864 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-08 | INTSPN-TRANSMIT-000016 | NA | Trade Partner | Re: URGENT - Zone C1 - Pour 5 | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-05-08 | KPTG-TRANSMIT-017091 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-08 | Tradetec-TRANSMIT-000439 | NA | Trade Partner | Re: IFA - STAGE 4 - LVP46, LVP35, CP37 | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect document number |  | 2026-05-08 | KPTG-RFI-007786 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-16 | PROLMC-TRANSMIT-000018 | NA | Trade Partner | Proline updates set of shop drawings (16/12/25) | 17 | 0 | 0 | NA | REJECTED | [5 empty] | Document Revision is mismatched, requested them to resubmit |  | 2025-12-16 | KPTG-SADV-003181 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-08 | SMEPS-TRANSMIT-000277 | NA | Trade Partner | Revised Jemena Easement Shopdrawing - 08.05.2026 | 2 | 0 | 0 | NA | APPROVED | 2026-05-08 | WF-005639 | NA | 2026-05-20 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-017580 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-08 | KPTG-TRANSMIT-017092 | NA | Trade Partner | Ezyframe | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-05-08 | KPTG-IntCorr-012944 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-08 | VAE-Grp-TRANSMIT-000158 | NA | Trade Partner | MECHANICAL - HVAC LAYOUT - LOWER GROUND | 2 | 0 | 0 | NA | APPROVED | 2026-05-08 | NA | 1268 | 2026-05-12 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-003703 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-08 | PARR-TRANSMIT-000177 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - PREACTION SYSTEM LAYOUT - IFA | 1 | 0 | 0 | NA | APPROVED | 2026-05-08 | WF-005640 | NA | 2026-05-21 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-017318 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-08 | D&E-TRANSMIT-000686 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - LEVEL 1 - BUILDERS WORKS LAYOUT - ZONE 3 | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | IFA has not been submitted for review |  | 2026-05-08 | KPTG-RFI-007796 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-05-08 | DI-TRANSMIT-000157 | NA | Trade Partner | Updated PPT documents | 3 | 0 | 0 | NA | APPROVED | 2026-05-08 | NA | 405 | 2026-05-12 |  |  | 2026-05-14 | 2026-05-14 | DRAFT-009977 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-08 | VERTIV-TRANSMIT-000010 | NA | Trade Partner | NEXT DC GE 01 _ CALCULATION SUBMISSIONS_ ELECTRICAL LOAD MAXIMUM DEMAND CALCULATION AND CABLE SIZING & VOLTAGE DROP CALCULATION | 0 | 2 | 0 | NA | APPROVED | 2026-05-08 | WF-000126 | NA | 2026-05-18 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-000562 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-08 | HDRAus-TRANSMIT-000481 | NA | Consultant | Re: M3 SW - Document upload - PDF and CAD | 36 | 0 | 0 | NA | REJECTED | [5 empty] | Different type documents received in same transmittal |  | 2026-05-11 | KPTG-RFI-007813 | Closed | 36 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-08 | INGEN3D-TRANSMIT-000705 | NA | Trade Partner | Re: I3D-378 Next DC M3 Stage 4 - Link Bridge - Cast In Dowels - IFA-Checked (08-05-2026) | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing title is different in both Aconex and drawing |  | 2026-05-08 | KPTG-RFI-007800 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-08 | INGEN3D-TRANSMIT-000706 | NA | Trade Partner | I3D-378 Next DC M3 Stage 4 - Link Bridge - Precast Panels - IFA (08-05-2026) | 39 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing title is different in both Aconex and drawing |  | 2026-05-08 | KPTG-RFI-007801 | Closed | 39 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-15 | ARCH-TRANSMIT-000125 | NA | Consultant | MLC - SPR - AQC - Lvl1 - Ceiling Access panel update | 1 | 0 | 0 | NA | APPROVED | 2025-12-15 |  | 378 | 2025-12-22 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-08 | ZIA-TRANSMIT-000052 | NA | Trade Partner | Cx Level 2 - Installation & Testing Procedures | 0 | 6 | 0 | NA | REJECTED | [5 empty] | QA ERROR REJECTED: Doc # field wrong |  | 2026-05-08 | KPTG-IntCorr-001274 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-08 | D&E-TRANSMIT-000360 | NA | Trade Partner | HX bypass | 0 | 1 | 0 | NA | APPROVED | 2026-05-08 | WF-001003 | NA | 2026-05-20 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-08 | KPTG-TRANSMIT-002350 | NA | Trade Partner | Highrise Documents For approval | 0 | 8 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-000957-The document number inside the drawing is different from the document number in the transmittal. |  | 2026-05-08 | KPTG-IntCorr-000957 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-08 | KPTG-INTCOM-000305 | NA | Trade Partner | Door Hardware Samples | 0 | 8 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-000955 - Unable to register the document in Aconex.it shows that document Number has already been taken. |  | 2026-05-08 | KPTG-IntCorr-000955 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-08 | KMANZ-TRANSMIT-000006 | NA | Trade Partner | Car stacker shop drawings | 6 | 0 | 0 | NA | APPROVED | 2026-05-08 | NA | 477 | 2026-05-14 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-001127 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-08 | crossfir-TRANSMIT-000012 | NA | Trade Partner | Wet Fire - Schematic, IFC | 1 | 0 | 0 | NA | APPROVED | 2026-05-08 | NA | 479 | 2026-05-15 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-08 | POTTSENG-TRANSMIT-000014 | NA | Trade Partner | HYDRAULIC SERVICES - BASEMENT 1 - LEVEL 4 CORE WALL - PENETRATION LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-05-08 | NA | 482 | 2026-05-15 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-001055 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-08 | Entire M-TRANSMIT-000045 | NA | Trade Partner | Mechanical drawings - minor coordination updates | 16 | 0 | 0 | NA | APPROVED | 2026-05-08 | WF-000219 | NA | 2026-05-13 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-000627 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-08 | Auspan-TRANSMIT-000274 | NA | Trade Partner | Precast shop drawings for approval. Zone 1, 2. | 55 | 0 | 0 | NA | APPROVED | 2026-05-08 | NA | 917 | 2026-05-15 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-002000 | Closed | 55 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-08 | Auspan-TRANSMIT-000275 | NA | Trade Partner | Precast shop drawings for construction. | 35 | 0 | 0 | NA | REJECTED | 2026-05-08 |  |  |  |  | Rejected due to several QC issues. - KPTG-SADV-002340 |  | 2026-05-08 | KPTG-SADV-002340 | Closed | 35 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-15 | Normark-TRANSMIT-000009 | NA | Trade Partner | FX02A& B - Alternative bin review and approval. | 0 | 1 | 0 | NA | APPROVED | 2025-12-16 | WF-000688 |  | 2025-12-19 |  |  |  | 2026-01-21 | KPTG-IntCorr-004074 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-08 | POTTSENG-TRANSMIT-000030 | 1 | Trade Partner | : GMAC: HYDRAULIC SERVICES - PENETRATION - GROUND - ZONE 5 LAYOUT | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | ifc - updated Register and distribute; No review required. KPTG-TRANSMIT-001742 |  | 2026-05-08 | KPTG-TRANSMIT-001742 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-08 | POTTSENG-TRANSMIT-000031 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - PENETRATION - GROUND - ZONE 1 LAYOUT | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | ifc - updated Register and distribute; No review required. KPTG-TRANSMIT-001744 |  | 2026-05-08 | KPTG-TRANSMIT-001744 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-08 | SES AU-TRANSMIT-000032 | NA | Trade Partner | SECURITY-Camera Layouts and Containment Plans -IFA | 6 | 0 | 0 | NA | APPROVED | 2026-05-08 | WF-000220 | NA | 2026-05-19 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-000664 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-08 | RDSBIM-TRANSMIT-000011 | NA | Trade Partner | MEL11C45 ¦ LEVEL 02 COLO 4 AREA PARTITION WALL LAYOUT | 4 | 0 | 0 | NA | APPROVED | 2026-05-08 | WF-000221 | NA | 2026-05-14 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-000806 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-08 | DLTS-TRANSMIT-000003 | NA | Trade Partner | South Eave Gutter Frames-IFA Issue-080502026 | 42 | 0 | 0 | NA | APPROVED | 2026-05-08 | WF-000657 | NA | 2026-05-15 |  |  | 2026-05-27 | 2026-05-27 | KPTG-TRANSMIT-003570 | Closed | 42 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-08 | DLTS-TRANSMIT-000004 | NA | Trade Partner | Cooling Tower-HD Bolts-IFA Issue | 2 | 0 | 0 | NA | APPROVED | 2026-05-08 | WF-000658 | NA | 2026-05-15 |  | Workflow WF-000658 terminated as advised by Oliver Schmid as the drawings were revised by Tradepartner and resubmitted on WF-000716 |  | 2026-05-18 | KPTG-IntCorr-000928 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-08 | ELLISAIR-TRANSMIT-000014 | NA | Trade Partner | Technical Data Submission - Refrigeration Pipework | 0 | 1 | 0 | NA | APPROVED | 2026-05-08 | WF-000647 | NA | 2026-05-15 |  |  | 2026-05-12 | 2026-05-12 | KPTG-TRANSMIT-003015 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-08 | INGEN3D-TRANSMIT-000063, INGEN3D-IntCorr-000027 | NA | Trade Partner | Level 7-9 - Precast Columns - IFA (07-05-2026) | 71 | 0 | 0 | NA | APPROVED | 2026-05-08 | WF-000500 | NA | 2026-05-22 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-001938 | Closed | 71 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-08 | INGEN3D-TRANSMIT-000064 | NA | Trade Partner | Level 4-6 - Precast Columns - Revised IFC | 44 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | FC - Register Updated |  | 2026-05-08 | NA | Closed | 44 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-08 | Jangho-TRANSMIT-000088 | NA | Trade Partner | Updated Brick Sample Submission（Red Brick Option 1） | 0 | 1 | 0 | NA | APPROVED | 2026-05-08 | WF-000495 | NA | 2026-05-22 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-001748 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-15 | CAP6-TRANSMIT-000001 | NA | Trade Partner | Classic Architectural Onboarding ¦ MLCSPR | 0 | 4 | 0 | NA | REJECTED | [5 empty] | Revision of this sample is incorrect |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-08 | Jangho-TRANSMIT-000089 | NA | Trade Partner | Updated Brick Sample Submission（Red Brick Option 2） | 0 | 1 | 0 | NA | APPROVED | 2026-05-08 | WF-000496 | NA | 2026-05-22 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-001754 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-08 | Jangho-TRANSMIT-000090 | NA | Trade Partner | Updated Brick Sample Submission(Tan Brick Option 2) | 0 | 1 | 0 | NA | APPROVED | 2026-05-08 | WF-000499 | NA | 2026-05-22 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-001753 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-08 | Jangho-TRANSMIT-000091 | NA | Trade Partner | Updated Brick Sample Submission（Red Brick Option 3） | 0 | 1 | 0 | NA | APPROVED | 2026-05-08 | WF-000497 | NA | 2026-05-22 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001893 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-08 | Jangho-TRANSMIT-000092 | NA | Trade Partner | Updated Brick Sample Submission(Tan Brick Option 1) | 0 | 1 | 0 | NA | APPROVED | 2026-05-08 | WF-000498 | NA | 2026-05-22 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001894 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-08 | WAM-TRANSMIT-000761 | NA | Trade Partner | A10 GA Plans, issued for 100% DD | 28 | 0 | 0 | NA | APPROVED | 2026-05-08 | NA | ACC 539 | 2026-05-13 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001856 | Closed | 28 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-08 | SES AU-TRANSMIT-000028 | NA | Trade Partner | Re: SECURITY-ROOF LEVEL LAYOUTS-IFA | 2 | 0 | 0 | NA | REJECTED | [5 empty] | NO DRAWING STATUS HAS MENTIONED: KPTG-IntCorr-000362 |  | 2026-05-08 | KPTG-IntCorr-000362 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-08 | SES AU-TRANSMIT-000030 | NA | Trade Partner | Re: SECURITY-ROOF LEVEL LAYOUTS-IFA | 2 | 0 | 0 | NA | APPROVED | 2026-05-08 | WF-000222 | NA | 2026-05-19 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-000659 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-08 | SES AU-TRANSMIT-000029 | NA | Trade Partner | SECURITY-COLO 4 AND 5 Schedules, Elevations and SLDs-IFA | 13 | 0 | 0 | NA | REJECTED | [5 empty] | DRAWINGS ARE DUPLICATED: KPTG-IntCorr-000365 |  | 2026-05-08 | KPTG-IntCorr-000365 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-08 | SES AU-TRANSMIT-000031 | NA | Trade Partner | Re: SECURITY-COLO 4 AND 5 Schedules, Elevations and SLDs-IFA | 13 | 0 | 0 | NA | APPROVED | 2026-05-08 | WF-000223 | NA | 2026-05-19 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-000661 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-08 | EFP-TRANSMIT-000018 | NA | Trade Partner | EFP Tech Data Alternative | 0 | 1 | 0 | NA | APPROVED | 2026-05-08 | WF-000216 | NA | 2026-05-15 |  |  | 2026-05-13 | 2026-05-13 | KPTG-IntCorr-000376 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-13 | RDSBIM-TRANSMIT-000090 | NA | Trade Partner | MLCSPR ¦ OUTDOOR COURT LEVEL 02 CONCRETE PROFILE PLAN SHEET 6 | 1 | 0 | 0 | NA | APPROVED | 2025-12-18 |  | 385 | 2025-12-25 |  | KAPITOL ADVICE AWAITS:KPTG-Inrcorr-003637 |  | 2026-02-10 | KPTG-SADV-003664 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-08 | AdntCons-TRANSMIT-000013 | NA | Trade Partner | Level 1 wet fire as built | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As built Drawing, updated document register only.KPTG-SADV-004292 |  | 2026-05-08 | KPTG-SADV-004292 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-08 | PROLMC-TRANSMIT-000035 | NA | Trade Partner | GRC IFC transmit | 29 | 0 | 0 | NA | REJECTED | [5 empty] | DUPLICATE DRAWING: KPTG-SADV-004293 |  | 2026-05-08 | KPTG-SADV-004293 | Closed | 29 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-08 | 4DW-TRANSMIT-000179 | NA | Trade Partner | Structural Documentation - General updates | 5 | 0 | 0 | NA | APPROVED | 2026-05-09 | NA | 237 |  |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-002846 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-08 | TTW-TRANSMIT-000152 | NA | Trade Partner | BP4 - Certification Update | 39 | 0 | 0 | NA | APPROVED | 2026-05-08 | NA | ACC 541 | 2026-05-13 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-001715 | Closed | 39 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-08 | Jangho-TRANSMIT-000083 | NA | Trade Partner | Updated Glass Sample Submission(GL-01 Option 1) | 0 | 1 | 0 | NA | APPROVED | 2026-05-08 | WF-000494 | NA | 2026-05-22 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001891 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-08 | Jangho-TRANSMIT-000084 | NA | Trade Partner | Updated Glass Sample Submission(GL-10 Option 1) | 0 | 1 | 0 | NA | APPROVED | 2026-05-08 | WF-000490 | NA | 2026-05-22 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001889 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-08 | Jangho-TRANSMIT-000085 | NA | Trade Partner | Updated Glass Sample Submission(GL-12 Option 2) | 0 | 1 | 0 | NA | APPROVED | 2026-05-08 | WF-000492 | NA | 2026-05-22 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-001654 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-08 | Jangho-TRANSMIT-000086 | NA | Trade Partner | Updated Glass Sample Submission(GL-10 Option 2) | 0 | 1 | 0 | NA | APPROVED | 2026-05-08 | WF-000491 | NA | 2026-05-22 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-001655 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-08 | Jangho-TRANSMIT-000087 | NA | Trade Partner | Updated Glass Sample Submission(GL-03 Sliding door Option 2) | 0 | 1 | 0 | NA | APPROVED | 2026-05-08 | WF-000493 | NA | 2026-05-22 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-001747 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-08 | Jangho-TRANSMIT-000082 | NA | Trade Partner | Updated Glass Sample Submission(GL-01 Option 2) | 0 | 1 | 0 | NA | APPROVED | 2026-05-08 | WF-000489 | NA | 2026-05-22 |  |  | 2026-05-08 | 2026-05-08 | KPTG-TRANSMIT-001656 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-02 | IVS-TRANSMIT-000285 | NA | Consultant | New Workflow L01 Z06 | 56 | 0 | 0 | NA | APPROVED | 2025-12-02 | WF-003462 | NA | 2025-12-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-13 | RDSBIM-TRANSMIT-000091 | NA | Trade Partner | MLC ¦ AQUATIC CENTER LEVEL 01 WALL PANELING PLAN & ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2025-12-15 |  | 377 | 2025-12-20 |  |  |  | 2026-01-20 | KPTG-SADV-003450 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-08 | Civilex-TRANSMIT-000088 | NA | Trade Partner | Water Shop Drawing IFC | 1 | 0 | 0 | NA | APPROVED | 2026-05-08 | NA | ACC 543 | 2026-05-18 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-001760 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-11 | WilsonPD-TRANSMIT-000004 | NA | Trade Partner | MEL11 - HYD-001 Sample For Review | 0 | 1 | 0 | NA | REJECTED | [5 empty] | SUBMITTED COVERING SHEET IS IN OLDER VERSION:KPTG-IntCorr-000366 |  | 2026-05-11 | KPTG-IntCorr-000366 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | Detail-TRANSMIT-000003 | NA | Trade Partner | DOOR HARDAWRE SCHEDULE | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect Reference No. |  | 2026-05-11 | KPTG-IntCorr-012984 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-11 | fjc-TRANSMIT-000146 | NA | Consultant | Architecturals - EoT/ Ground / Roof | 0 | 2 | 0 | NA | APPROVED | 2026-05-11 | WF-000746 | NA | 2026-05-18 |  | AS PER DIRECTION FROM MARK WE TERMINATE THE WORKFLOW.15-05-2026 | 2026-05-15 | 2026-05-15 | KPTG-SADV-004178 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-11 | fjc-TRANSMIT-000146 | NA | Consultant | Architecturals - EoT/ Ground / Roof | 9 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 647 | 2026-05-14 |  |  | 2026-05-13 | 2026-05-13 | KPTG-SADV-004135 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-11 | D&E-TRANSMIT-000687 | NA | Trade Partner | Condensate Pump - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-11 | WF-005642 | NA | 2026-05-25 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-11 | KPTG-TRANSMIT-003657 | NA | Client | SMOKED MIRROR TECH DATA | 0 | 1 | 0 | NA | APPROVED | 2026-05-11 | WF-001054 | NA | 2026-05-14 |  |  | 2026-05-13 | 2026-05-13 | KPTG-WTRAN-002105 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-16 | VAE-Grp-TRANSMIT-000094 | NA | Trade Partner | MECHANICAL CONTROL SYSTEM - POINTS LIST & NETWORK SCHEMATIC | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | REGISTER UPDATION ONLY - DONE |  | 2025-12-16 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-14 | WSP ANZ-TRANSMIT-000011,006 | NA | Consultant | WSP - Updated 80% Tender Issue Drawings (Hydraulic) | 15 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 94 | 2026-05-19 |  | Actual received date 5/8/2026, Previous revision drawings still under review- Informed to Renee |  | 2026-05-28 | KPTG-TRANSMIT-000101,104 | Closed | 15 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-08 | ENF-TRANSMIT-000013 | NA | Consultant | Structural drawings | 23 | 0 | 0 | KPTG-DA-000206 | APPROVED |  | NA | NA |  |  | This Transmittal is superseded with ENF-TRANSMIT-000016. |  | 2026-05-13 | KPTG-DA-000226 | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-11 | RDSBIM-TRANSMIT-000046 | SPARK-CRFI-KPG-000380 | Trade Partner | MWYCCB ¦ LEVEL 01 CONCRETE PROFILE PLAN | 5 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 281 | 2026-05-18 |  | Actual received date : 09/05/2026 | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-000875 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-11 | DS-TRANSMIT-000117 | NA | Trade Partner | STAGE 2 HYD SITE - DRAINAGE | 1 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 4182 | 2026-05-22 |  |  | 2026-06-15 | 2026-06-22 | KPTG-TRANSMIT-018890 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | Tradetec-TRANSMIT-000440 | NA | Trade Partner | IFA - STAGE 4 - LVP46, LVP35, CP37 | 3 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 3173 | 2026-05-19 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-018235 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-11 | HGP-TRANSMIT-000054 | NA | Trade Partner | L1 Internal Glazing Drawings | 31 | 0 | 0 | NA | REJECTED | [5 empty] | The drawing title inside the drawing and in Aconex seem different. Drawing status inside the drawing and in Aconex seem different. Drawing number in Aconex is incorrect. Multiple status in a single transmittal. |  | 2026-05-11 | KPTG-TRANSMIT-000853 | Closed | 31 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | D&E-TRANSMIT-000688 | NA | Trade Partner | Re: Filters - Issued for Approval | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-05-11 | KPTG-RFI-007814 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-16 | SKS Tech-TRANSMIT-000110 | NA | Trade Partner | TELECOMMUNICATIONS SUBMITTAL FC | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | REGISTER UPDATION ONLY - DONE |  | 2025-12-16 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-11 | D&E-TRANSMIT-000693 | NA | Trade Partner | NXM3S2 - Level 01 - Mechanical Duct Layout - Zone 2 - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 4184 | 2026-05-20 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-019055 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | INGEN3D-TRANSMIT-000708 | NA | Trade Partner | Re: I3D-378 Next DC M3 Stage 4 - Link Bridge - Cast In Dowels - IFA-Checked (08-05-2026) | 4 | 0 | 0 | NA | APPROVED | 2026-05-11 | WF-005651 | NA | 2026-05-04 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-018925 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | INGEN3D-TRANSMIT-000706 | NA | Trade Partner | M3 Stage 4 - Link Bridge - Precast Panels - IFA (08-05-2026) | 39 | 0 | 0 | NA | APPROVED | 2026-05-11 | WF-005649 | NA | 2026-06-04 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | D&E-TRANSMIT-000691 | NA | Trade Partner | Leak Detection Functional Description - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-11 | WF-005655 | NA | 2026-06-01 |  | Ellie - Please remove M3-MEC-DEA-DS-C-0400-0049 from workflow |  | 2026-05-26 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | D&E-TRANSMIT-000690 | NA | Trade Partner | Fwd: Magflow Meter Schedule - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | [5 empty] | IFC techdata |  | 2026-05-11 | KPTG-TRANSMIT-017150 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | ACG-TRANSMIT-000088 | NA | Trade Partner | Re: M3 - Stage 4 External Drawings | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-05-11 | KPTG-RFI-007824 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | SMEPS-TRANSMIT-000278 | NA | Trade Partner | SME - IFA Sample submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-11 | WF-005657 | NA | 2026-06-01 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-017476 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | ACG-TRANSMIT-000089 | NA | Trade Partner | M3 - Stage 4 External Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 3180 | 2026-05-22 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-018803 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | D&E-TRANSMIT-000694 | NA | Trade Partner | Filters - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-11 | WF-005659 | NA | 2026-06-01 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | D&E-TRANSMIT-000694 | NA | Trade Partner | Filters - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-11 | [8 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-16 | SKS Tech-TRANSMIT-000109 | NA | Trade Partner | TELECOMMUNICATIONS SUBMITTAL | 0 | 3 | 0 | NA | APPROVED | 2025-12-16 | WF-000650 | NA | 2025-12-19 |  |  | 2026-01-15 | 2026-01-15 | KPTG-WTRAN-001328 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-11 | WAM-TRANSMIT-000766 | NA | Consultant | Bathroom Prototype Update | 1 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 549 | 2026-05-11 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-001676 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-11 | WAM-TRANSMIT-000765 | NA | Consultant | Bathroom Prototype Update | 1 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 547 | 2026-05-11 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-001679 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | ARCST-TRANSMIT-000280 | NA | Trade Partner | C3 West Roof Walkway - Issued for Approval | 223 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-05-11 | KPTG-TRANSMIT-017158 | Open | 223 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | D&E-TRANSMIT-000696 | NA | Trade Partner | NXM3S4 - Ground - Builders Works Layout Zones - Issued For Construction | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-05-11 | KPTG-RFI-007829 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-11 | Appselec-TRANSMIT-000087 | NA | Trade Partner | MEL11C45 - COLO 5 IFC Drawings | 6 | 0 | 0 | NA | APPROVED | 2026-05-11 | WF-000 | WF-000224 | 2026-05-14 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-000630 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-11 | TTW-TRANSMIT-000183 | NA | Trade Partner | M3 Stage 3 Civil Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | NA |  |  |  |  | 2026-05-11 | KPTG-TRANSMIT-017160 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-11 | RDSBIM-TRANSMIT-000192 | NA | Trade Partner | 511SRC ¦ LEVEL 09 PARTITION WALL LAYOUT | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC drawings update register only. |  | 2026-05-11 | KPTG-TRANSMIT-002960 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-11 | RDSBIM-TRANSMIT-000193 | NA | Trade Partner | 511SRC ¦ LEVEL 10 PARTITION WALL PLAN AND LAYOUT | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC DRAWINGS update register only. |  | 2026-05-11 | KPTG-TRANSMIT-002958 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-11 | Auspan-TRANSMIT-000278 | NA | Trade Partner | Resubmit precast shop drawings for approval | 10 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 931 | 2026-05-18 |  |  | 2026-05-27 | 2026-05-27 | KPTG-TRANSMIT-002015 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-16 | SKS Tech-TRANSMIT-000111 | NA | Trade Partner | Basement GLP | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | REGISTER UPDATION ONLY - DONE - Documents Revised via SKS Tech-TRANSMIT-000117 | 2025-12-18 | 2025-12-18 | SKS Tech-TRANSMIT-000117 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-11 | RDSBIM-TRANSMIT-000194 | NA | Trade Partner | 511SRC ¦ LEVEL 15 TOWER B CONCRETE PROFILE PLAN | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - update register only. |  | 2026-05-11 | KPTG-TRANSMIT-002957 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-11 | RDSBIM-TRANSMIT-000195 | NA | Trade Partner | ROOF TOWER A CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Update register only. |  | 2026-05-11 | RDSBIM-TRANSMIT-000195 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-11 | KETE-TRANSMIT-000043 | NA | Trade Partner | WINDOW SCHEDULE-LEVELS 01(B)-SHEET 18 | 6 | 0 | 0 | NA | APPROVED |  | NA | 564 | 2026-05-15 |  | File supersede and WF terminated. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | ARCST-TRANSMIT-000279 | NA | Trade Partner | Re: C2 West Roof Walkway - Issued for Approval | 298 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect titles |  | 2026-05-11 | KPTG-RFI-007832 | Closed | 298 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-11 | ENF-TRANSMIT-000014 | NA | Consultant | Structural drawing | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Transmittal ENF-TRANSMIT-000014 has been closed and superseded by ENF-TRANSMIT-000016 |  | 2026-05-13 | KPTG-DA-000225 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-11 | Appselec-TRANSMIT-000088 | NA | Trade Partner | Electrical & Telecommunication services - IFC drawings | 4 | 0 | 0 | NA | APPROVED | 2026-05-11 | WF-000225 | NA | 2026-05-14 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-000642 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-11 | Appselec-TRANSMIT-000088 | NA | Trade Partner | Electrical & Telecommunication services - IFC drawings | 14 | 0 | 0 | NA | APPROVED | 2026-05-11 | WF-000226 | NA | 2026-05-14 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-000624 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-11 | Focused-TRANSMIT-000014 | NA | Trade Partner | Revised FER | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | ISSUED FOR INFORMATION DISTRIBUTED ALL PARTIES. | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-002363 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | SKS Tech-TRANSMIT-000134 | NA | Trade Partner | Hangers Cut List - Data Halls | 7 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 3170 | 2026-05-20 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-017814 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-15 | 4DW-TRANSMIT-000078 | NA | Consultant | Foundation & Steelwork Updates | 6 | 0 | 0 | NA | APPROVED | 2025-12-16 |  | 489 | 2025-12-16 |  |  | 2025-12-18 | 2025-12-18 | KPTG-SADV-002542 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | IVS-TRANSMIT-000364 | NA | Consultant | Stage 4 - Precast Elevation (Revised Construction Issue) | 1 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 3174 | 2026-05-20 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-017739 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | D&E-TRANSMIT-000689 | NA | Trade Partner | Re: Leak Detection Functional Description - Issued for Approval | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-05-11 | KPTG-RFI-007816 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | Detail-TRANSMIT-000004 | NA | Trade Partner | Re: DOOR HARDAWRE SCHEDULE | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-05-04 | KPTG-RFI-007817 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | KPTG-IntCorr-012995 | NA | Trade Partner | FACAD WORKFLOW | 0 | 1 | 0 | NA | APPROVED | 2026-05-11 | WF-005656 | NA | 2026-05-20 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | HDRAus-TRANSMIT-000475 | NA | Consultant | Re Resubmit Re M3 Stage 4 - Document upload - PDF and CAD | 37 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 3195,3195 | 2026-05-27 |  | as per requested by isabella seperate wf started |  | 2026-05-18 | KPTG-TRANSMIT-017520 | Closed | 37 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | SMEPS-TRANSMIT-000279 | NA | Trade Partner | Re: SME - IFA SAMPLE SUBMISSION | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-05-11 | KPTG-RFI-007827 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | D&E-TRANSMIT-000695 | NA | Trade Partner | Re MCC-IWP-A Electrical Drawing - Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 3183 | 2026-05-27 |  | As per requested by Ellie - VOID D&E need to update drawing |  | 2026-05-14 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-11 | PARR-TRANSMIT-000178 | NA | Trade Partner | P2649 - KPG NDC M3 - Stage 2 - Fuel - AS-BUILT | 11 | 0 | 0 | NA | REJECTED | [5 empty] | Difference in status |  | 2026-05-11 | KPTG-SADV-005304 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-11 | D&E-TRANSMIT-000697 | NA | Trade Partner | Admin Office Functional Description - Issued for approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision is mentioned in Numerical format |  | 2026-05-11 | KPTG-SADV-005306 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-11 | Altaire-TRANSMIT-000029 | NA | Trade Partner | M3DH78 - Altaire - Practical completion documents | 1 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | NA |  |  | Distributed-Actual incoming transmittal date 12-03-2016 |  | 2026-05-11 | Awaiting approval | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-15 | KETE-TRANSMIT-000103 | NA | Trade Partner | Kete - Updated Drawings Podium IFC Rev B | 34 | 0 | 0 | NA | APPROVED |  |  | 492 |  |  | As per the direction from the Ms Elisa Te, These drawings need to go Aconex Review. Hence, we void this BIM Review on 16.12.2025 | 2025-12-12 | 2025-12-12 | File Superseded | Closed | 34 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-11 | JCBa-TRANSMIT-000110 | NA | Consultant | : Updated Architectural Documentation - Wet Areas - Baseline & Premium Bathrooms | 4 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 922 | 2026-05-13 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-001948 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-11 | Auspan-TRANSMIT-000276 | NA | Trade Partner | Precast shop drawings for construction. | 5 | 0 | 0 | KPTG-IntCorr-000561 | APPROVED | 2026-05-11 | NA | NA |  |  | Waiting for advise from Kapitol PC - KPTG-IntCorr-000561 Precast IFC No review required; update register and distribute KPTG-TRANSMIT-001778 |  | 2026-05-12 | KPTG-TRANSMIT-001778 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-11 | Auspan-TRANSMIT-000277 | NA | Trade Partner | Precast shop drawings for construction | 29 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC No review required; update register and distribute KPTG-TRANSMIT-001761 |  | 2026-05-11 | KPTG-TRANSMIT-001761 | Closed | 29 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-11 | Rinco-TRANSMIT-000047 | NA | Consultant | RL6 to Roof reinforcement plan | 84 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 924 | 2026-05-13 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-001860 | Closed | 84 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-11 | Auspan-TRANSMIT-000190 | NA | Trade Partner | Precast shop drawings for approval. Level 2 - | 56 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 929 | 2026-05-19 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-002069 | Closed | 56 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-11 | Auspan-TRANSMIT-000279 | NA | Trade Partner | Re: Precast shop drawings for construction. Ground floor | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC No review required; update register and distribute - KPTG-TRANSMIT-001764 |  | 2026-05-11 | KPTG-TRANSMIT-001764 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-11 | POTTSENG-TRANSMIT-000032 | NA | Trade Partner | GMAC HYDRAULIC SERVICES - PENETRATION - GROUND - ZONE 3 & 5 LAYOUTS | 2 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 933 | 2026-05-19 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-001796 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-11 | Auscool-TRANSMIT-000029 | NA | Trade Partner | Zone 4 – Revised BW Drawings for R/A Riser Penetration | 7 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 935 | 2026-05-18 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-001799 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-11 | span-TRANSMIT-000281 | NA | Trade Partner | Update already IFCed shop drawings. | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC No review required; update register and distribute KPTG-TRANSMIT-001773 |  | 2026-05-11 | KPTG-TRANSMIT-001773 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-16 | Auscool-TRANSMIT-000061 | NA | Trade Partner | Grille Tech Data Issued For Approval | 0 | 4 | 0 | NA | APPROVED |  | WF-000546 |  |  |  |  | 2026-02-18 | 2026-02-18 | KPTG-TRANSMIT-001845 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-11 | RDSBIM-TRANSMIT-000064 | NA | Trade Partner | 671CHP GROUND LEVEL TO ROOF CORE WALL LAYOUT AND ELEVATION | 9 | 0 | 0 | KPTG-IntCorr-000550 | APPROVED |  | NA | NA |  |  | Waiting for Advice (IFC) No action. Drawings superseded. |  | 2026-05-14 | NA | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-11 | Jordan-TRANSMIT-000129 | NA | Trade Partner | PLUMBING DRAINAGE - LOWER GROUND AND L4 | 2 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 1270 | 2026-05-13 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-003699 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-14 | WSP ANZ-TRANSMIT-000011,006 | NA | Consultant | WSP - Updated 80% Tender Issue Drawings - Fire Protection | 5 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 93 | 2026-05-19 |  | Actual received date 5/8/2026, Previous revision drawings still under review- Informed to Renee |  | 2026-05-28 | KPTG-TRANSMIT-000101,104 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-14 | WSP ANZ-TRANSMIT-000011,006 | NA | Consultant | WSP - Updated 80% Tender Issue Drawings - Mechanical | 9 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 74 | 2026-05-19 |  | Actual Received date 5/8/2026, Voided as discussed 13-05-2026 will be initiated with Simon Hackel. |  | 2026-05-13 | NA | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-11 | HDRAus-TRANSMIT-000093 | NA | Consultant | Documents marked No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer In Use |  | 2026-05-11 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-11 | HDRAus-TRANSMIT-000095 | NA | Consultant | Documents marked No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer In Use |  | 2026-05-11 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-11 | HDRAus-TRANSMIT-000103 | NA | Consultant | Documents marked No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer In Use |  | 2026-05-11 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-17 | SMEPS-TRANSMIT-000114 | NA | Trade Partner | 22KV - Sample register and submittals | 0 | 3 | 0 | NA | APPROVED |  | WF-003819 |  | 2026-01-23 |  | The register has been updated. If any further action is required, the coordinator will inform. |  | 2025-12-18 | NXT-WTRAN-001296 | Closed | 3 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-11 | HDRAus-TRANSMIT-000102 | NA | Consultant | Documents marked No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer In Use |  | 2026-05-11 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-11 | HDRAus-TRANSMIT-000104 | NA | Consultant | Documents marked No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer In Use |  | 2026-05-11 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-11 | HDRAus-TRANSMIT-000106 | NA | Consultant | Documents marked No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer In Use |  | 2026-05-11 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-11 | HDRAus-TRANSMIT-000110 | NA | Consultant | Documents marked No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer In Use |  | 2026-05-11 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-11 | HDRAus-TRANSMIT-000111 | NA | Consultant | Documents marked No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer In Use |  | 2026-05-11 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-11 | HDRAus-TRANSMIT-000114 | NA | Consultant | Documents marked No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer In Use |  | 2026-05-11 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-11 | HDRAus-TRANSMIT-000115 | NA | Consultant | Documents marked No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer In Use |  | 2026-05-11 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-11 | HDRAus-TRANSMIT-000126 | NA | Consultant | Documents marked No Longer In Use-superseded by HDRAus-TRANSMIT-000127 | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer In Use |  | 2026-05-11 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-11 | HDRAus-TRANSMIT-000128 | NA | Consultant | M3 Stage 6 - Architectural Tender Addendum 4 | 143 | 8 | 0 | NA | APPROVED |  | NA | NA |  |  | Drawings revised |  | 2026-05-11 | NA | Closed | 151 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-15 | KETE-TRANSMIT-000104 | NA | Trade Partner | Kete - Tower IFA Submission - Not Including Last Floor Design | 50 | 0 | 0 | NA | APPROVED | 2026-02-16 |  | 560 | 2026-02-23 |  | 493- latest revision of these drawings received today,17-12-2025. 498-As per the direction from Ms. Elisa, i have void this workflow on 16.02.2026 560-as per the direction from Ms. Elisa Te, we have void this workflow dated: 16.02.2026 | 2025-12-17 | 2025-12-17 | KPTG-TRANSMIT-001512 | Closed | 50 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-11 | HDRAus-TRANSMIT-000092 | NA | Consultant | Documents marked No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer In Use |  | 2026-05-11 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-11 | HDRAus-TRANSMIT-000090 | NA | Consultant | Documents marked No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Longer In Use |  | 2026-05-11 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-11 | VIA Arch-TRANSMIT-000117 | NA | Consultant | Architecture - Stage 11 Stair 06 Documentation | 1 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 838 | 2026-05-14 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-003109 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-11 | Outlook mail (Downloaded from Procore) | NA | Trade Partner | Stage 9 EAE Busduct Shop Drawings | 41 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 833 | 2026-05-13 |  | Review terminated as advised by Design Manager. Next revision of same drawings are ssubmitted on another review # 888 |  |  | NA | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-11 | WGAVIC-TRANSMIT-000116 | NA | Consultant | M2 - Civil Main Works Drawings - Issued for Construction | 6 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 835 | 2026-05-14 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-003125 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-11 | Civilex-TRANSMIT-000089 | NA | Consultant | Bathroom Prototype Update | 0 | 2 | 0 | NA | APPROVED | 2026-05-11 | WF-000635 | NA |  |  |  | 2026-06-16 | 2026-06-15 | KPTG-TRANSMIT-002277,KPTG-TRANSMIT-002278 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-11 | TTW-TRANSMIT-000154 | NA | Consultant | Bathroom Prototype Update | 1 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED : REV MISMATCH |  | 2026-05-11 | KPTG-TRANSMIT-001688 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-11 | Jangho-TRANSMIT-000095 | NA | Consultant | Bathroom Prototype Update | 17 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 553 |  |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-001960 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-11 | INGEN3D-TRANSMIT-000066 | NA | Consultant | Bathroom Prototype Update | 42 | 0 | 0 | NA | APPROVED |  |  | NA |  |  | FC - REGISTER UPDATED AND FORWARD TO ALL PARTIES |  | 2026-05-11 | KPTG-TRANSMIT-001694 | Closed | 42 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-11 | Jangho-TRANSMIT-000096, 99 | NA | Consultant | Bathroom Prototype Update | 32 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 584 | 2026-06-26 |  | CORRECTED DRAWING TRN 99 |  | 2026-06-26 | KPTG-TRANSMIT-001677 | Closed | 32 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-02 | TTW-TRANSMIT-000139 | NA | Trade Partner | M3 Stage 4 - Level 1 Zone 7 Panels & Marking Plans Next DC M3 Stage 4 | 68 | 0 | 0 | NA | APPROVED | 2025-12-02 | WF-003464 | NA | 2025-12-18 |  |  |  | 2026-01-07 | KPTG-TRANSMIT-011277 | Closed | 66 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-16 | KETE-TRANSMIT-000105 | NA | Trade Partner | Submission – updated podium shop drawings | 12 | 0 | 0 | NA | APPROVED | 2025-12-18 |  | 493 | 2025-12-23 |  | Podum drngs are in this WF-000535 rest drngs are in BIM WF 493 493-latest revision of these drawings received today,17-12-2025. File Superseded | 2025-12-17 | 2025-12-17 | CLOSED | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-11 | Jangho-TRANSMIT-000093 | NA | Consultant | Bathroom Prototype Update | 28 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 557 |  |  | REJECTED : KPTG-TRANSMIT-001675 | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-002102 | Closed | 26 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-11 | INGEN3D-TRANSMIT-000065 | NA | Consultant | Bathroom Prototype Update | 5 | 0 | 0 | NA | APPROVED |  | NA |  |  |  | FC - REGISTER UPDATED AND FORWARD TO ALL PARTIES |  | 2026-05-11 | KPTG-TRANSMIT-001707 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-11 | Jangho-TRANSMIT-000094 | NA | Consultant | Bathroom Prototype Update | 23 | 0 | 0 | NA | APPROVED |  | NA | 559 |  |  | REJECTED : QA ERROR-KPTG-IntCorr-000698 |  | 2026-05-26 | KPTG-TRANSMIT-001958 | Closed | 22 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-12 | PMT Sec-TRANSMIT-000017 | NA | Trade Partner | Door Elevations | 10 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect drawing number and revision |  | 2026-05-12 | KPTG-TRANSMIT-000855 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | Nilsen3-TRANSMIT-000152 | NA | Trade Partner | Ezyframe | 0 | 1 | 0 | NA | APPROVED | 2026-05-12 | WF-005665 | NA | 2026-06-02 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-017627 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | ARCST-TRANSMIT-000281 | NA | Trade Partner | C2 West Roof Walkway - Issued for Approval - PART 1 | 298 | 0 | 0 | NA | APPROVED | 2026-05-12 | WF-005667 & WF-005669 | NA | 2026-06-05 |  | We can't submit all 298 documents together in the workflow, so the 298 documents have been split: 200 documents in WF-005667 & 98 documents in WF-005669 Additionally, we received the same documents in Transmittals ARCST-TRANSMIT-000282 & ARCST-TRANSMIT-000283 | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-018289 | Closed | 200 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-21 | KPTG-WTRAN-001980 | NA | Trade Partner | Precision doors - Tech Data | 0 | 3 | 0 | NA | APPROVED | 2026-04-21 | WF-001017 | NA | 2026-04-27 |  |  | 2026-05-11 | 2026-05-11 | KPTG-TRANSMIT-003664 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | NXT-TRANSMIT-001547 | NA | Trade Partner | MSB-FI schematic submission- as per RFI for ATS protocol, SOO & Setting | 1 | 0 | 0 | NA | APPROVED | 2026-05-12 | WF-005670 | NA | 2026-05-25 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-17 | KPTG-SADV-001945 | NA | Consultant | Stage 1 MJ Cover Recess | 0 | 1 | 0 | NA | APPROVED | 2025-12-17 | WF-000862 | NA | 2025-12-22 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-12 | JCBa-TRANSMIT-000113 | NA | Consultant | Structural Setout Plans: L00 IFC | 5 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 946 | 2026-05-19 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001912 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | Mirage D-TRANSMIT-000016 | NA | Trade Partner | Re: Stage 4 - Roller Doors - Mirage Doors | 11 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-05-12 | KPTG-RFI-007854 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | Nilsen3-TRANSMIT-000153 | NA | Trade Partner | Typical Label details | 0 | 1 | 0 | NA | APPROVED | 2026-05-12 | WF-005671 | NA | 2026-06-02 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-017854 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-12 | D&E-TRANSMIT-000253 | SPARK-CRFI-KPG-000677 | Trade Partner | Vertigo Fixings for Approval | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-05-18 | KPTG-TRANSMIT-000878 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | D&E-TRANSMIT-000699 | NA | Trade Partner | NXM3S4 - Ground - Mechanical Duct Layout - Zone 4 - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 3194 | 2026-05-20 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018362 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | D&E-TRANSMIT-000700 | NA | Trade Partner | Re: NXM3S4 - Ground - Mechanical Duct Layout - Zone 6 - Issued For Approval | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect drawing status |  | 2026-05-12 | KPTG-RFI-007857 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | ARCST-TRANSMIT-000288 | NA | Trade Partner | We can't submit all 223 documents together in the workflow, so the 223 documents have been split: 100 documents in WF-005675 & 123 documents in WF-005676 | 223 | 0 | 0 | NA | APPROVED | 2026-05-12 | WF-005675 & WF-005676 | NA | 2026-06-05 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-018207 | Closed | 123 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-12 | Auspan-TRANSMIT-000285 | NA | Trade Partner | Resubmit precast shop drawings for approval | 6 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 948 | 2026-05-19 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-002027 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | D&E-TRANSMIT-000064 | NA | Trade Partner | Mechanical As Built update | 1 | 0 | 0 | NA | APPROVED | 2026-05-12 | WF-000491 | NA | 2026-05-25 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-12 | SES AU-TRANSMIT-000034 | NA | Trade Partner | Re: Cable Containment Tech Data for Approval | 0 | 9 | 0 | NA | APPROVED | 2026-05-12 | WF-000227 | NA | 2026-05-16 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-000666 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-17 | RDSBIM-TRANSMIT-000013 | NA | Trade Partner | 671CHP ¦ BASEMENT 2 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2025-12-17 | WF-000106 | 187 | 2025-12-19 |  | Review void as advised during a meeting with Kapitol DM & PCs. |  | 2026-01-22 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | SMEPS-TRANSMIT-000283 | NA | Trade Partner | STAGE 4 - Electrical Pit Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-05-12 | WF-005679 | NA | 2026-06-05 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-019424 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-12 | Altaire-TRANSMIT-000105 | NA | Trade Partner | Re: NEXTDC M3S3 22KV - Cx Plan (For Construction) | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-05-12 | KPTG-RFI-007865 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-05-12 | D&E-TRANSMIT-000064 | NA | Trade Partner | Mechanical As Built update | 1 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 408 | 2026-05-25 |  |  | 2026-07-23 | 2026-07-23 | DRAFT-010430 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-12 | POTTSENG-TRANSMIT-000033 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - PENETRATION - LEVELS 03-05 - ZONES 1-5 LAYOUT | 15 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 952 | 2026-05-19 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-002106 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-12 | RDSBIM-TRANSMIT-000198 | NA | Trade Partner | LINDRUM ¦ LEVEL 05 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 648 | 2026-05-19 |  |  | 2026-05-20 | 2026-05-20 | KPTG-SADV-004222 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | SKS Tech-TRANSMIT-000135 | NA | Trade Partner | Hangers Cut List - Switchrooms | 3 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 3185 | 2026-05-21 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-018175 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | PCForm-TRANSMIT-000165 | NA | Trade Partner | Re: URGENT - Zone C1 - Pour 5 FOR APPROVAL | 1 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due to incorrect company name |  | 2026-05-12 | KPTG-RFI-007845 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | KPTG-TRANSMIT-017184 | NA | Trade Partner | Proline - Box Gutter IFA | 1 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 3188 | 2026-05-12 |  | As requested by Renee - Terminated The updated drawings will be submitted. |  | 2026-05-21 | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-17 | Auspan-TRANSMIT-000034 | NA | Trade Partner | GF shop drawings issued for construction | 2 | 0 | 0 | NA | APPROVED | 2025-12-17 |  | 494 | 2025-12-18 |  |  | 2025-12-18 | 2025-12-18 | KPTG-SADV-002545 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | PCForm-TRANSMIT-000166 | NA | Trade Partner | Re: URGENT - Zone C1 - Pour 5 FOR APPROVAL | 1 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-05-12 | KPTG-RFI-007849 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | SMEPS-TRANSMIT-000281 | NA | Trade Partner | Re: STAGE 4 - Electrical Inground Layout & Pit Schedule | 2 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-05-12 | KPTG-RFI-007855 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-12 | RDSBIM-TRANSMIT-000008 | NA | Trade Partner | NXGE01 ¦ GROUND FLOOR PLANT AREA CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 223 | 2026-05-18 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-000660 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | SKS Tech-TRANSMIT-000136 | NA | Trade Partner | Sections and Isometrics take off box to PDU containment | 2 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 3193 | 2026-05-27 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-018227 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-12 | ACG-TRANSMIT-000090 | NA | Trade Partner | M3 - Stage 2 O&M | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with Document Number. |  | 2026-05-12 | KPTG-DA-006508 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | OveArup-WTRAN-001011 | NA | Trade Partner | Stage 4 - C1 Switch room Upper Gantry Grating - Issued for Approval (Rev 2) | 95 | 0 | 0 | NA | APPROVED | 2026-05-12 | WF-005682 | NA | 2026-05-20 |  | As Requested by Lola As requested by Lola, The WF has been terminated |  | 2026-05-20 | NA | Closed | 95 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | SMEPS-TRANSMIT-000282 | NA | Trade Partner | STAGE 4 - Electrical Inground Layout | 1 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 3207 | 2026-05-20 |  | Previous WF No 3201 NEW WF ALSO TERMINATED AS PER REQUESTED BY CHARLIE J |  | 2026-06-16 | KPTG-TRANSMIT-018676 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | D&E-TRANSMIT-000701 | NA | Trade Partner | NXM3S4 - Ground - Mechanical Duct Layout - Zone 6 - Issued For Approval | 1 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 3204 | 2026-05-28 |  |  |  | 2026-06-03 | KPTG-TRANSMIT-018179 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | Hames-WTRAN-000376 | NA | Trade Partner | C2 Switchroom & Cooling Tower HD Bolts | 4 | 0 | 0 | NA | APPROVED | 2026-05-12 | WF-004147 | NA | 2026-05-27 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-017616 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-12 | Tradetec-TRANSMIT-000441 | NA | Trade Partner | Tech Data - Bitac Primer | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Old document attached and No change in revision. |  | 2026-05-12 | KPTG-IntCorr-013065 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-17 | D&E-TRANSMIT-000317 | NA | Trade Partner | SFN Pipework Material - Issued for Review | 0 | 1 | 0 | NA | APPROVED | 2025-12-17 | WF-003647 | NA | 2026-01-12 |  |  |  | 2026-01-20 | KPTG-TRANSMIT-011621 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-12 | SMEPS-TRANSMIT-000280 | NA | Trade Partner | STAGE 2 - ELECTRIAL INGROUND LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 4186 | 2026-05-25 |  | Terminated as Directed by Charlie Johnstone for submitting the updated drawings. | 2026-06-02 | 2026-06-02 | KPTG-IntCorr-014177 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-12 | INTRFRM-TRANSMIT-000044 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 5) | 0 | 8 | 0 | NA | REJECTED | 2026-05-12 |  |  |  |  | A confidential file in the submission. |  | 2026-05-12 | DRAFT-001866 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-12 | GEMBA-D-TRANSMIT-000018 | NA | Consultant | Roof slab CJ update transmittal | 5 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 225 | 2026-05-15 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-000539 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-12 | HDRAus-TRANSMIT-000483 | NA | Consultant | M3_S2_Roof_Stage 2 to Stage 1 Gantry Crossovers clarification | 5 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 4188 | 2026-05-15 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-018042 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-12 | DbyP-TRANSMIT-000001 | NA | Consultant | Pidgeon Ward 80% Signage Update | 0 | 1 | 0 | KPTG-IntCorr-000118 | APPROVED | 2026-05-15 | NA | 125 | 2026-05-20 |  | Seek advised to Renee | 2026-08-03 | 2026-08-03 | KPTG-TRANSMIT-000259 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-12 | ENF-TRANSMIT-000015 | NA | Consultant | Structural drawings | 2 | 0 | 0 | KPTG-DA-000214 | APPROVED |  | NA | NA |  |  | Transmittal ENF-TRANSMIT-000015, superseded by ENF-TRANSMIT-000016 |  | 2026-05-13 | KPTG-DA-000224 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-12 | Carr-TRANSMIT-000049 | NA | Consultant | GA Plan Update - Architecture | 3 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 113 | 2026-05-19 |  | Received late in the day-Issued for Coordination - Updated on ACC and Aconex. | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000157 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-12 | Carr-TRANSMIT-000050 | NA | Consultant | GA Plan Update - Architecture | 2 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 114 | 2026-05-19 |  | Received late in the day- Issued for coordination | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000156 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-12 | ELLISAIR-TRANSMIT-000017 | NA | Trade Partner | Technical data submission - Stage 9 VRF | 0 | 1 | 0 | NA | APPROVED | 2026-05-12 | WF-000669 | NA | 2026-05-21 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-003445 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-12 | WSP ANZ-TRANSMIT-000069 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit - CSMS | 8 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 846 | 2026-05-15 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-003227 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-17 | D&E-TRANSMIT-000294 | NA | Trade Partner | Technical Data Submission - Corridor AC Units | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC, No review required. Updated and distributed to the Project Team. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-12 | WSP ANZ-TRANSMIT-000069 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit - Electrical | 40 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 847 | 2026-05-15 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-003227 | Closed | 40 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-12 | WSP ANZ-TRANSMIT-000069 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit - FIP | 34 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 848 | 2026-05-15 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-003227 | Closed | 34 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-12 | WSP ANZ-TRANSMIT-000069 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit - Fuel | 9 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 849 | 2026-05-15 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-003196 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-12 | WSP ANZ-TRANSMIT-000069 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit - Mechanical | 19 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 850 | 2026-05-15 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-003227 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-12 | WSP ANZ-TRANSMIT-000069 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit - Telecom | 15 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 851 | 2026-05-15 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-003227 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-12 | LGCE-TRANSMIT-000025 | NA | Trade Partner | B1 IFC final review | 2 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 489 | 2026-05-19 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-001102 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-12 | LGCE-TRANSMIT-000024 | NA | Trade Partner | Comms schematic | 1 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 487 | 2026-05-19 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-001006 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-12 | LGCE-TRANSMIT-000023 | NA | Trade Partner | Ground floor light and power | 2 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 484 | 2026-05-19 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-001174 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-12 | JCBa-TRANSMIT-000111 | NA | Consultant | : Structural Setout Plans: L01 IFC | 5 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 950 | 2026-05-14 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-001925 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-12 | INDS-TRANSMIT-000025 | NA | Trade Partner | Wet Fire - Basement Zone 1, 3 & 4 | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Review required; Update register and distribute - PC |  | 2026-05-12 | . KPTG-TRANSMIT-001786 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-17 | PFP PL-TRANSMIT-000046 | NA | Trade Partner | Generator DWG As Built | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As-Built, No review required, Updated & distributed to the Project Team. |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-12 | INDS-TRANSMIT-000026 | NA | Trade Partner | Wet Fire - Basement Zone 2 & 5 | 2 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 941 | 2026-05-19 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-002110 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-12 | RSBIM-TRANSMIT-000055 | NA | Trade Partner | RDGREYSTAR LEVEL 02 CONCRETE PROFILE PLAN | 6 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 938 | 2026-05-19 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-002024 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-12 | Auspan-TRANSMIT-000282 | NA | Trade Partner | Precast shop drawings for construction. | 27 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Transmittal superseded by Auspan-TRANSMIT-000283. KPTG-SADV-002415 |  | 2026-05-12 | KPTG-SADV-002415 | Closed | 27 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-12 | Auspan-TRANSMIT-000283 | NA | Trade Partner | Precast shop drawings for construction. | 27 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC No review required; update register and distribute - KPTG-TRANSMIT-001789 |  | 2026-05-12 | KPTG-TRANSMIT-001789 | Closed | 27 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-12 | JCBa-TRANSMIT-000112 | NA | Consultant | Structural Setout Plans: L00 IF | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected BY DM- "don't distribute, the clouding is wrong they need to reissue "- KPTG-IntCorr-000567 |  | 2026-05-12 | KPTG-IntCorr-000567 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-12 | RDSBIM-TRANSMIT-000196 | NA | Trade Partner | L15 - TOWER B ¦ CPP ¦ IFC ¦ SUBMISSION | 2 | 0 | 0 | NA | APPROVED |  | NA | NA | 2026-05-15 |  | IFC - Distribution only. |  |  | DRAFT-017748 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-12 | VOGUE-TRANSMIT-000007 | NA | Trade Partner | PLANTER SHOP DRAWINGS - VOGUE GRANGE | 0 | 1 | 0 | NA | APPROVED | 2026-05-12 | WF - 001017 | NA | 2026-05-18 |  | File supersede and WF terminated. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-12 | 4DW-TRANSMIT-000038 | NA | Consultant | Issued for Certification: Ground Floor Zone 2 and 3 Slab | 13 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 81 | 2026-05-20 |  |  | 2026-06-11 | 2026-06-11 | NA | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-12 | JCBa-TRANSMIT-000252 | NA | Consultant | Updated Partition Plans - IFC | 6 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 565 | 2026-05-15 |  | NA | 2026-05-15 | 2026-05-15 | DRAFT - 017886 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-12 | NXT-TRANSMIT-000370-ARC-HDR | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 05 | 143 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 79 | 2026-05-20 |  | Actual submission date 11-05-2026 | 2026-05-28 | 2026-05-28 | NA | Closed | 143 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-16 | ARCST-TRANSMIT-000159 | NA | Trade Partner | Fuel Compound Stairs - Issued for Re-Approval | 60 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with the revision history inside the box |  | 2025-12-16 | KPTG-DA-003959 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-12 | NXT-TRANSMIT-000370-ARC-HDR-SCH | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 05 | 0 | 7 | 0 | NA | APPROVED | 2026-05-12 | NA | 83 | 2026-05-20 |  | Actual submission date 11-05-2026-Voided | 2026-06-11 | 2026-06-11 | NA | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-12 | HDRAus-TRANSMIT-000130 | NA | Consultant | M3S6 Expansion - Site grids setout | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | CAD file updated |  | 2026-05-12 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-12 | SMEPS-TRANSMIT-000212 | NA | Trade Partner | SME Samples for review | 0 | 2 | 0 | NA | APPROVED | 2026-05-12 | WF - 000412 | NA | 2026-05-18 |  | NA | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-000868 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-12 | Entire M-TRANSMIT-000036 | NA | Trade Partner | Commissioning Plan Updated inline with comments | 0 | 1 | 0 | NA | APPROVED | 2026-05-12 | WF - 000411 | NA | 2026-05-18 |  | NA | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-000874 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-12 | PFP PL-TRANSMIT-000004 | NA | Trade Partner | Level 2 Colo 4 IFC | 1 | 0 | 0 | NA | APPROVED | 2026-05-12 | WF - 000413 | NA | 2026-05-15 |  | NA | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-000901 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-12 | TTW-TRANSMIT-000027 | NA | Consultant | M3 Stage 6 - Civil Documentation IFT - Addendum | 8 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 85 | 2026-05-20 |  | Voided requested by katherine |  | 2026-05-13 | NA | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-12 | RDSBIM-TRANSMIT-000016 | NA | Trade Partner | MEL05C4 ¦ LEVEL 02 COLO 04 AREA PARTITION WALL LAYOUT AND ELEVATION | 4 | 0 | 0 | NA | APPROVED | 2026-05-19 | WF - 000415 | NA | 2026-05-18 |  | NA | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-000883 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-12 | KPTG-CONTADV-000244 | NA | Client | Update Document Register MEL05C4 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Design drawings only for Aconex Update |  | 2026-05-12 | KPTG-TRANSMIT-000860 | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-06 | WilsonPD-TRANSMIT-000038 | NA | Trade Partner | Equipment for Approval | 0 | 2 | 0 | NA | APPROVED | 2026-05-12 | WF-000665 | NA | 2026-05-22 |  | Resubmitted as advised by PC | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-003270 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-16 | KPTG-TRANSMIT-010937 | NA | Trade Partner | Joinery Shop Drawings - Entrance Office | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Revision not available inside the drawing |  | 2025-12-16 | KPTG-IntCorr-007786 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-12 | Altaire-TRANSMIT-000002 | NA | Trade Partner | M2 Stage 9-11 - Altaire Technical Data Transmittal | 0 | 1 | 0 | NA | APPROVED | 2026-05-12 | WF-000664 | NA | 2026-05-22 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-003665 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-12 | WilsonPD-TRANSMIT-000041 | NA | Trade Partner | External Water Tanks for Approval/ Coordination | 0 | 1 | 0 | NA | APPROVED | 2026-05-12 | WF-000667 | NA | 2026-05-21 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-003501 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-13 | INTRFRM-TRANSMIT-000046 | NA | Trade Partner | Re: Geelong Edge - Structural Tech Data (Submission 6) | 0 | 8 | 0 | NA | APPROVED | 2026-05-13 | WF-000128 | NA | 2026-05-21 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-000591 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-13 | D&E-TRANSMIT-000702 | na | Trade Partner | NXM3S2 - GROUND FLOOR + LEVEL 01 DATAHALL SFN UNION AND BOLT TORQUE MAPS - Issued For Construction | 7 | 0 | 0 | NA | REJECTED | [5 empty] | document number mismatch |  | 2026-05-13 | KPTG-SADV-005345 | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-13 | RDSBIM-TRANSMIT-000197 | NA | Trade Partner | LEVEL 09 CONCRETE PROFILE PLAN | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - for distribution only. |  | 2026-05-13 | KPTG-IntCorr-001723 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-13 | D&E-TRANSMIT-000254 | NA | Trade Partner | Mechanical Services Seismic Design Drawings Level-01 | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Multiple statuses & Incorrect drawing number. |  | 2026-05-13 | KPTG-TRANSMIT-000860 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-13 | JCBa-TRANSMIT-000249 | NA | Consultant | Communal Gym and Cowork - VM Plan Update | 18 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 566 | 2026-05-15 |  | NA | 2026-05-15 | 2026-05-15 | DRAFT - 017878 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-12 | INGEN3D-TRANSMIT-000067 | NAA | Trade Partner | Level 5-7 - Precast Columns - New IFA | 24 | 0 | 0 | NA | APPROVED | 2026-05-12 | WF-000509 | NA | 2026-05-21 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-001784 | Closed | 24 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-12 | TTW-TRANSMIT-000155 | NA | Consultant | BP8 construction update | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rrjected |  | 2026-05-12 | KPTG-TRANSMIT-001734 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-17 | Entire M-TRANSMIT-000021 | NA | Trade Partner | BMS Drawings and Functional Description re-issued for approval | 2 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-TRANSMIT-010996 - The reference number assigned in Aconex is not mentioned in the document. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-12 | Jangho-TRANSMIT-000097 | NA | Trade Partner | 002_FT-01&FT-02 SYSTEM CONCEPT DRAWING-02 | 2 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 557 | 2026-05-20 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-002102 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-12 | Jangho-TRANSMIT-000098 | NA | Trade Partner | 001-FT01 &FT02 TOWER VISUAL MOCK-UP SHOP DRAWING-02 | 1 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 559, | 2026-05-20 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-001958 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-12 | PCForm-TRANSMIT-000183 | NA | Trade Partner | Level 4 IFC transmittal | 8 | 0 | 0 | NA | APPROVED |  | NA | 571 |  |  | REJECTED- KPTG-TRANSMIT-001736 |  | 2026-05-27 | KPTG-TRANSMIT-001970 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-12 | TTW-TRANSMIT-000156 | NA | Consultant | BP8 - Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 563 | 2026-05-15 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-001797 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-12 | RDSBIM-TRANSMIT-000033 | NA | Trade Partner | GROUND FLOOR TO LEVEL 02, 03, 09, STAIR/LIFT CORE 03 CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-05-12 | NA | 561 | 2026-05-15 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-001928 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-13 | D&E-TRANSMIT-000255 | NA | Trade Partner | Seismic Installation Guide | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Wrong attachment |  | 2026-05-13 | KPTG-TRANSMIT-000861 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-13 | D&E-TRANSMIT-000704 | na | Trade Partner | NXM3S2 - LEVEL 01 - DATAHALL 5 SFN UNION AND BOLT TORQUE MAP - Issued For Construction | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incomplete submission |  | 2026-05-13 | KPTG-SADV-005346 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-13 | SKS Tech-TRANSMIT-000138 | NA | Trade Partner | Re-transmittal of legend and submain cable schedule | 0 | 3 | 0 | NA | APPROVED | 2026-05-13 | WF-005686 | NA | 2026-06-03 |  |  |  | 2026-05-19 | KPTG-RFI-007976 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-02 | IVS-TRANSMIT-000286 | NA | Consultant | RFI #001 - location of bulk tank penetrations | 1 | 0 | 0 | NA | APPROVED | 2025-12-02 | WF-003465 | NA | 2025-12-18 |  |  |  | 2026-01-16 | KPTG-TRANSMIT-010943 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-16 | D&E-TRANSMIT-000315 | NA | Trade Partner | Functional Description Rev B - Issued for Review | 0 | 1 | 0 | NA | APPROVED | 2025-12-16 | WF-003613 | NA | 2025-12-30 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-13 | KPTG-TRANSMIT-017210 | na | Trade Partner | M3 S2 - AXIS Rev2 O&M Manual | 0 | 1 | 0 | NA | APPROVED | 2026-05-13 | WF-005687 | na | 2026-05-21 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-12 | ZIA-TRANSMIT-000051 | NA | Trade Partner | IP Address Register | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Forwarded to all Trades as advised by Harry |  | 2026-05-12 | KPTG-TRANSMIT-003672 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-13 | Auspan-TRANSMIT-000070 | NA | Trade Partner | Shop drawings issued for construction | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-000962-As per the direction from Ashlin, documents are updated into document register and transmitted to all parties. |  | 2026-05-13 | KPTG-IntCorr-000962 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-13 | ECBS-TRANSMIT-000040 | NA | Trade Partner | Fan Wall Unit Steel - Revised Drawings For Approval (Batch 1: 15 drawings) | 15 | 0 | 0 | NA | APPROVED |  | WF-005690 | NA | 2026-06-08 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-13 | KPTG-TRANSMIT-017213 | NA | Trade Partner | M3 S2 - Facadex O&M Manual | 0 | 1 | 0 | NA | APPROVED | 2026-05-13 | WF-005691 | NA | 2026-05-27 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018522 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-13 | RDSBIM-TRANSMIT-000056 | NA | Trade Partner | GREYSTAR GROUND FLOOR CONCRETE PROFILE PLAN AND SECTION ZONE 4 | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required; Register and distribute KPTG-TRANSMIT-001808 |  | 2026-05-13 | KPTG-TRANSMIT-001808 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-13 | Auspan-TRANSMIT-000288 | NA | Trade Partner | Precast shop drawings for construction. This batch includes panel 0G2057 | 104 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC - No Review required; Register and distribute. KPTG-TRANSMIT-001805 |  | 2026-05-13 | KPTG-TRANSMIT-001805 | Closed | 104 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-13 | POTTSENG-TRANSMIT-000035 | NA | Trade Partner | - GMAC: HYDRAULIC SERVICES - WATER - GROUND - ZONE 2 & 5 LAYOUTS | 2 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 954 | 2026-05-19 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-002516 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-13 | POTTSENG-TRANSMIT-000034 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - PENETRATION - LEVEL 01 - ZONE 1, 2 & 5 LAYOUTS | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | ifc - update Register and distribute; No review required. KPTG-TRANSMIT-001804 |  | 2026-05-13 | KPTG-TRANSMIT-001804 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-13 | POTTSENG-TRANSMIT-000036 | NA | Trade Partner | GMAC HYDRAULIC SERVICES - WATER - GROUND - ZONES 1,3 & 4 LAYOUT | 3 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 960 | 2026-05-20 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-002517 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-16 | Tradetec-TRANSMIT-000306 | NA | Trade Partner | Tech Data - Fernco Shear Banded Couplings - Sitewide | 0 | 1 | 0 | NA | APPROVED | 2025-12-16 | WF-003626 | NA | 2025-12-25 |  |  |  | 2025-12-18 | KPTG-TRANSMIT-011084 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-13 | Auspan-TRANSMIT-000071 | NA | Trade Partner | Shop drawings issued for approval | 1 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 650 | 2026-05-13 |  |  | 2026-05-13 | 2026-05-13 | KPTG-SADV-004153 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-13 | Mirage D-TRANSMIT-000017 | NA | Trade Partner | Stage 4 - Roller Doors - Mirage Doors | 11 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 3210 | 2026-05-24 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-017757 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-13 | Stowe-A-TRANSMIT-000580 | na | Trade Partner | Re: Stowe - Tech Data - Fire Rated Junction Box | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Difference in title |  | 2026-05-13 | KPTG-SADV-005355 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-13 | Auspan-TRANSMIT-000287 | NA | Trade Partner | Resubmit precast shop drawings for approval | 13 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 962 | 2026-05-20 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-002065 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-13 | KPTG-IntCorr-000409 | NA | Trade Partner | HEATMAP PHASE 4 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Update register only. |  |  | KPTG-TRANSMIT-000862 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-13 | KPTG-IntCorr-000410 | NA | Trade Partner | MEL04C4 Commissioning Plan | 0 | 1 | 0 | NA | APPROVED | 2026-05-13 | WF - 000417 | NA | 2026-05-19 |  | NA | 2026-06-12 | 2026-06-12 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-13 | Nilsen3-TRANSMIT-000155 | NA | Trade Partner | Nilsen electrical IFC - Drawings | 12 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 3215 | 2026-05-20 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-017547 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-13 | D&E-TRANSMIT-000705 | na | Trade Partner | Re: NXM3S2 - GROUND FLOOR & LEVEL 01 - DATAHALL SFN UNION AND BOLT TORQUE MAP - Issued For Construction | 7 | 0 | 0 | NA | REJECTED | [5 empty] | FOA of the documents not received |  | 2026-05-13 | KPTG-SADV-005358 | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-13 | JCBa-TRANSMIT-000255 | NA | Consultant | Updated Partition Plans - IFC | 38 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 567 | 2026-05-18 |  | NA | 2026-05-15 | 2026-05-15 | DRAFT-017888 | Closed | 38 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-13 | D&E-TRANSMIT-000634 | NA | Trade Partner | MF, Temp, DP Sensors - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-13 | WF-005472 | NA | 2026-06-03 |  | The WF has been reinitiated as per William - KPTG-IntCorr-013175 | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-017761 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-17 | SMEPS-TRANSMIT-000126 | NA | Trade Partner | 22KV - Sample register and submittals | 0 | 1 | 0 | NA | APPROVED | 2025-12-17 | WF-003654 |  | 2026-01-02 |  | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-13 | RDSBIM-TRANSMIT-000012 | NA | Trade Partner | MEL11C45 ¦ LEVEL 01 AND LEVEL 02 COLO 5A, 4 & 5B SCREED LAYOUT | 3 | 0 | 0 | NA | APPROVED | 2026-05-13 | WF-000230 | NA | 2026-05-13 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-000617 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-13 | KPTG-TRANSMIT-017211 | NA | Client | M3 S2 - ACG O&M Manual | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Previous revision is rejected |  | 2026-05-13 | KPTG-SADV-005367 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-13 | Auspan-TRANSMIT-000071 | NA | Trade Partner | Shop drawings issued for approval | 3 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 651 | 2026-05-18 |  |  | 2026-06-02 | 2026-06-02 | KPTG-SADV-004382 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-13 | Stowe-A-TRANSMIT-000582 | NA | Trade Partner | Stowe - Tech Data - Fire Rated Junction Boxes lifts | 0 | 1 | 0 | NA | APPROVED | 2026-05-13 | WF-005697 | NA | 2026-05-25 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-017948 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-13 | PCForm-TRANSMIT-000169 | NA | Trade Partner | Zone C1 - Pour 5 Post tension | 1 | 0 | 0 | NA | APPROVED | 2026-05-13 | WF-005694 | NA | 2026-05-29 |  |  |  | 2026-05-26 | KPTG-TRANSMIT-017849 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-13 | Detail-TRANSMIT-000005 | NA | Trade Partner | DOOR HARDAWRE SCHEDULE | 1 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 3213 | 2026-05-22 |  | The WF has been terminated as requested by Isabella |  | 2026-05-20 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-13 | Nilsen3-TRANSMIT-000154 | NA | Trade Partner | Re Shop Drawing Register Nilsen | 6 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 3206 | 2026-05-18 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-017331 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-13 | POTTSENG-TRANSMIT-000037 | NA | Trade Partner | GMAC HYDRAULIC SERVICES - PENETRATION - LEVEL 01 - ZONE 3 & 4 LAYOUTS | 2 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 969 | 2026-05-20 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-002759 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-13 | M.2-TRANSMIT-000029 | NA | Trade Partner | Electrical Services Penetration layouts - Ground - Level 6 | 18 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 964 | 2026-05-20 |  | 3 drawings were terminated and superseded, review completed | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002829 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-13 | M.2-TRANSMIT-000030 | NA | Trade Partner | Electrical Services Penetration layouts - Level 07 | 5 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 966 | 2026-05-20 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002830 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-16 | IVS-TRANSMIT-000300 | NA | Consultant | Stage 2 - Fuel Compound Construction Issue (revised as clouded) | 3 | 0 | 0 | NA | REJECTED | [7 empty] | 2025-12-16 | KPTG-DA-003961 | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-13 | POTTSENG-TRANSMIT-000038 | NA | Trade Partner | GMAC HYDRAULIC SERVICES - PENETRATION - GROUND - ZONE 3 & 4 LAYOUTS | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | ifc - update Register and distribute; No review required KPTG-TRANSMIT-001814 |  | 2026-05-13 | KPTG-TRANSMIT-001814 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-13 | POTTSENG-TRANSMIT-000039 | NA | Trade Partner | GMAC HYDRAULIC SERVICES - DRAINAGE - GROUND - ZONE 1-5 LAYOUTS | 5 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 971 | 2026-05-20 |  | Review outcome is "Rejected,", | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-002585 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-13 | Auspan-TRANSMIT-000289 | NA | Trade Partner | Update precast shop drawings for construction. 0G5096 and 0G5097 | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast ifc - update Register and distribute; No review required KPTG-TRANSMIT-001824 |  | 2026-05-13 | KPTG-TRANSMIT-001824 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-13 | SCG2014-TRANSMIT-000003 | NA | Consultant | Secure under door seals - removed from scope | 0 | 1 | 0 | NA | APPROVED | 2026-05-13 | NA | 1272 | 2026-05-15 |  |  | 2026-08-05 | 2026-08-06 | KPTG-TRANSMIT-004199 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-13 | Altaire-TRANSMIT-000106 | NA | Trade Partner | Fwd: NEXTDC M3S3 22KV - Cx Plan (For Construction) (Revised) | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | The register has been updated. If any further action is required, the coordinator will inform. |  | 2026-05-13 | KPTG-TRANSMIT-017298 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-13 | OveArup-TRANSMIT-000188 | NA | Trade Partner | OveArup-TRANSMIT-000188 | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Missing Reference number |  | 2026-05-13 | KPTG-TRANSMIT-017299 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-13 | Carr-TRANSMIT-000051 | NA | Consultant | Interiors Update to EOT Joinery and Details | 8 | 0 | 0 | NA | REJECTED | [5 empty] | QA-Rejected - In Consistency in Issue status and Actual drawing status. |  | 2026-05-13 | KPTG-DA-000220 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-13 | ENF-TRANSMIT-000016 | NA | Consultant | Structural drawings | 18 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 85 | 2026-05-18 |  | Review Voided as advised by Renee 22-05-2026 | 2026-05-22 | 2026-05-22 | NA | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-13 | NXT-TRANSMIT-000370-CSM | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 05 | 10 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 87 | 2026-05-21 |  | Actual submission date 11-05-2026 | 2026-06-11 | 2026-06-11 | NA | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-13 | NXT-TRANSMIT-000370-ELC | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 05 | 60 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 89 | 2026-05-21 |  | Actual submission date 11-05-2026 | 2026-06-11 | 2026-06-11 | NA | Closed | 60 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-16 | NXT-TRANSMIT-001147 | NA | Client | 100222-000566 - AS BUILT FIRE SCHEMATICS | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2025-12-16 | KPTG-TRANSMIT-010963 | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-13 | TTW-TRANSMIT-000029 | NA | Consultant | M3 Stage 6 - Civil Documentation IFT - Addendum | 8 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 92 | 2026-05-21 |  |  | 2026-06-11 | 2026-06-11 | NA | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-18 | RBG-TRANSMIT-000002 | NA | Consultant | Tower Crane Drawing Package | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | Actual submission date 13-05-2026-distribution |  | 2026-05-18 | KPTG-TRANSMIT-000086 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-13 | INGEN3D-TRANSMIT-000704 | NA | Consultant | Re: I3D-378 Next DC M3 Stage 4 - Core 10 - PWS4-1902 & PWS4-1903 - Revised IFC (13-05-2026 | 4 | 0 | 0 | NA | APPROVED | 2026-05-13 | WF-005698 | NA | 2026-05-20 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-13 | Appselec-TRANSMIT-000089 | NA | Trade Partner | MEL11C45 TEMPORARY WIFI PLAN REV 3 - For Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | DOCUMENT NUMBER IS NOT MENTIONED:KPTG-IntCorr-000371 |  | 2026-05-13 | KPTG-IntCorr-000371 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-13 | Appselec-TRANSMIT-000090 | NA | Trade Partner | Communications Testing Procedures - For Approval | 0 | 2 | 0 | NA | APPROVED | 2026-05-13 | WF-000229 | NA | 2026-05-19 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-000709 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-13 | KALLIBRE-TRANSMIT-000008 | NA | Trade Partner | MEL11 C4&5 Door Frame Shop Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-05-13 | WF-000228 | NA | 2026-05-19 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-13 | Appselec-TRANSMIT-000091 | NA | Trade Partner | WESCO BILL OF MATERIALS (PHONES) - COLO4 & COLO5 - For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-13 | WF-000231 | NA | 2026-05-19 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-000694 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-13 | Appselec-TRANSMIT-000092 | NA | Trade Partner | MEL11C45 TEMPORARY WIFI PLAN (Rev 3) - For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-13 | WF-000232 | NA | 2026-05-19 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-000710 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-13 | Entire M-TRANSMIT-000047 | NA | Trade Partner | Mechanical IFA Rev B Submission & Comments - Intumescent FDs & Pipe Fittings | 0 | 2 | 0 | NA | APPROVED | 2026-05-13 | WF-000233 | NA | 2026-05-19 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-000724 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-13 | TATE_-TRANSMIT-000023 | NA | Trade Partner | Tate IFC drawing set | 34 | 0 | 0 | NA | APPROVED | 2026-05-28 | WF-000277 | NA | 2026-05-29 |  | Drawing status need to be updated:KPTG-IntCorr-000374 |  | 2026-05-28 | KPTG-TRANSMIT-000764 | Closed | 34 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-17 | VIA Arch-TRANSMIT-000021 | NA | Trade Partner | 22kV Switchroom Signage Package | 4 | 0 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-13 | ARCH-TRANSMIT-000148 | NA | Consultant | MLC - SPR - Tactile drawings update | 5 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 237 | 2026-05-15 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-002851 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-13 | EMBIND-TRANSMIT-000009 | NA | Trade Partner | 10875 - MLC KEW - KPTG-SADV-003781: Re: SD035 - Jazz Essential (Mezzo 8mm) ISC | 0 | 1 | 0 | NA | REJECTED | [5 empty] | DOCUMENT NUMBER OF DOCUMENT IS INCORRECT:KPTG-SADV-004314 |  | 2026-05-13 | KPTG-SADV-004314 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-13 | EMBIND-TRANSMIT-000010 | NA | Trade Partner | : MLC ¦ Vinyl & rubber caulking colour | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected: document number incorrect:KPTG-SADV-004313 |  | 2026-05-13 | KPTG-SADV-004313 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-13 | EMBIND-TRANSMIT-000011 | NA | Trade Partner | Re: MLC ¦ Vinyl & rubber caulking colour | 0 | 1 | 0 | NA | APPROVED | 2026-05-13 | WF-000962 | NA | 2026-05-19 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-002897 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-13 | M.S.-TRANSMIT-000063 | NA | Trade Partner | Revised Shop Drawings for Construction | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC DRAWING, TRANSMITTED TO ALL CONCENED:KPTG-TRANSMIT-002849 |  | 2026-05-13 | KPTG-TRANSMIT-002849 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-13 | SMEPS-TRANSMIT-000037 | NA | Trade Partner | M2 SME Sample Submissions | 0 | 3 | 0 | NA | APPROVED | 2026-05-13 | WF-000674 | NA | 2026-05-25 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-003240 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-13 | Arc Plas-TRANSMIT-000003 | NA | Trade Partner | Updated Speedpanel Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-13 | WF-000675 | NA | 2026-05-20 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-004691 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-13 | CRSol-TRANSMIT-000005 | NA | Trade Partner | M2S9 - updated CRS Ceiling Drawings for Approval | 13 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 853 | 2026-05-18 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-004798 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-13 | BBC P.-TRANSMIT-000008 | NA | Trade Partner | BBC Painting Sample forms. revised and resubmitted. | 0 | 6 | 0 | NA | APPROVED | 2026-05-13 | WF-000676 | NA | 2026-05-18 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-003204 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-13 | ELLISAIR-TRANSMIT-000019 | NA | Trade Partner | Technical Data submission - Stage 9 Fans | 0 | 1 | 0 | NA | APPROVED | 2026-05-13 | WF-000679 | NA | 2026-05-20 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-003369 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-16 | D&E-TRANSMIT-000316 | NA | Trade Partner | NXM3S2 - Upper Roof - Builders Works Layout - B1 & B2 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2025-12-16 | NA | 3526 | 2025-12-23 |  |  | 2026-02-03 | 2026-02-04 | KPTG-TRANSMIT-012488 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-13 | ELLISAIR-TRANSMIT-000021 | NA | Trade Partner | NextDC M2 S9 CCW Pump String drawing issued for Approval. | 1 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 855 | 2026-05-18 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-003385 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-14 | Stowe-A-TRANSMIT-000583 | NA | Trade Partner | STOWE - LEGENDS & COVER SHEETS - 14.05.2026 | 4 | 0 | 0 | NA | REJECTED | [5 empty] | different discipline shared in single transmittal |  | 2026-05-14 | KPTG-SADV-005376 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-14 | Stowe-A-TRANSMIT-000584 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - 14.05.2026 | 3 | 0 | 0 | NA | REJECTED | [5 empty] | difference in status |  | 2026-05-14 | KPTG-SADV-005377 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-14 | Nilsen3-TRANSMIT-000013 | NA | Trade Partner | Roof Support System sample | 0 | 1 | 0 | NA | APPROVED | 2026-05-14 | WF-000681 | NA | 2026-05-26 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-003380 | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-14 | SMEPS-TRANSMIT-000285 | NA | Trade Partner | SME - IFA Sample submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-14 | WF-005701 | NA | 2026-06-04 |  |  | 2026-05-20 | 2026-05-20 | SMEPS-TRANSMIT-000285 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-14 | ELLISAIR-TRANSMIT-000022 | NA | Trade Partner | Technical Data Submission - Ductwork & Insulation | 0 | 1 | 0 | NA | APPROVED | 2026-05-14 | WF-000682 | NA | 2026-05-26 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-003368 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-14 | WilsonPD-TRANSMIT-000006 | NA | Trade Partner | Hydraulic shop drawing issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-05-14 | WF-000235 | NA | 2026-05-15 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-000621 | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-14 | WilsonPD-TRANSMIT-000005 | NA | Trade Partner | SMP-001 - Mechanical Storage Tank 3 | 0 | 1 | 0 | NA | APPROVED | 2026-05-21 | WF-000254 | NA | 2026-05-20 |  |  |  | 2026-05-21 | KPTG-TRANSMIT-000673 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-14 | PARR-TRANSMIT-000179 | NA | Trade Partner | Re: P2680 - NDC M3 Stage 4 - Fuel - BFS SCHEMATIC & PUMP ROOM A/B GA | 3 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | The IFC has been submitted without prior IFA approval |  | 2026-05-14 | KPTG-RFI-007895 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-14 | Stowe-A-TRANSMIT-000585 | NA | Trade Partner | Fwd: STOWE - DRAWING SUBMISSION - BACOP SCHEMATIC - 14.05.2026 | 1 | 0 | 0 | NA | APPROVED | 2026-05-14 | na | 4191 | 2026-05-19 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-017823 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-17 | Entire M-TRANSMIT-000022 | NA | Trade Partner | BMS Functional Description, Points List & Drawings | 3 | 0 | 0 | NA | APPROVED | 2025-12-17 | WF-003653 |  | 2025-12-30 |  | The register has been updated. If any further action is required, the coordinator will inform. |  |  | Terminated | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-14 | Stowe-A-TRANSMIT-000586 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - LINE UP EI SCHEMATIC - 14.05.2026 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incomplete transmittal |  | 2026-05-14 | KPTG-SADV-005383 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-14 | Appselec-TRANSMIT-000093 | NA | Trade Partner | Tech Data IFC | 0 | 1 | 0 | NA | APPROVED | 2026-05-14 | WF-000236 | NA | 2026-05-19 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-000691 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-13 | ZIA-TRANSMIT-000053 | NA | Trade Partner | CSMS Cable Schedule | 0 | 1 | 0 | KPTG-IntCorr-001290 | APPROVED |  | NA | NA |  |  | Harry to confirm- REGISTER UPDATED |  | 2026-06-11 | KPTG-IntCorr-001436 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-11 | Baigents-TRANSMIT-000197 | NA | Trade Partner | BALUSTRADE OUTSIDE HV ROOM MARKING PLAN | 2 | 0 | 0 | NA | APPROVED | 2026-05-11 | WF-001062 | NA | 2026-05-13 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-003675 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-14 | Stowe-A-TRANSMIT-000588 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - TEL - COVER SHEET & DRAWING LIST - 14.05.2026 | 2 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 4195 | 2026-05-25 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018373 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-14 | Stowe-A-TRANSMIT-000587 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - ELC - COVER SHEET & DRAWING LIST - 14.05.2026 | 2 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 4194 | 2026-05-25 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018390 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-14 | Stowe-A-TRANSMIT-000589 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - 0119 / 3122 / 9003 - 14.05.2026 | 3 | 0 | 0 | NA | APPROVED | 2026-05-14 | na | 4197 | 2026-05-21 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-017342 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-14 | Entire M-TRANSMIT-000046 | NA | Trade Partner | MEL11C45 Mechanical Seismic Design Rev A IFA | 0 | 1 | 0 | NA | APPROVED | 2026-05-14 | WF-000238 | NA | 2026-05-20 |  | IT IS NOT REPORT, it look like combined set of shop drawings:KPTG-IntCorr-000381 | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-000773 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-14 | Appselec-TRANSMIT-000094 | NA | Trade Partner | Tech Data IFC | 0 | 2 | 0 | NA | APPROVED | 2026-05-14 | WF-000237 | NA | 2026-05-19 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-000636 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-14 | SMEPS-TRANSMIT-000284 | NA | Trade Partner | 22KV - Lightning protection submittal | 0 | 1 | 0 | NA | APPROVED | 2026-05-14 | WF-005699 | NA | 2026-05-22 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-018883 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2025-12-17 | Nilsen3-TRANSMIT-000097 | NA | Trade Partner | Nilsen Shop Drawings - As-Builts | 19 | 0 | 0 | NA | APPROVED | [5 empty] | As-Builts, No review required, Updated register and distributed to the project Team. |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-14 | Sienergy-TRANSMIT-000021 | NA | Trade Partner | Fwd: M3S4 Kiosk As-built | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-05-14 | KPTG-TRANSMIT-017336 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-14 | KPTG-TRANSMIT-017310 | NA | Client | M3 S2 - AXIS O&M | 0 | 1 | 0 | NA | APPROVED | 2026-05-14 | WF-005709 | na | 2026-05-27 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018395 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-14 | KPTG-TRANSMIT-017317 | NA | Client | M3 S2 - Chiller Module O&M | 0 | 1 | 0 | NA | APPROVED | 2026-05-14 | WF-005848 | NA | 2026-06-04 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018411 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-13 | TTW-TRANSMIT-000157 | NA | Consultant | BP1 - Certification Update | 17 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 567 | 2026-05-18 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-001818 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-14 | SMEPS-TRANSMIT-000286 | NA | Trade Partner | 22KV - LV cable sample | 0 | 1 | 0 | NA | APPROVED | 2026-05-14 | WF-005711 | NA | 2026-05-28 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-017720 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-13 | Jangho-TRANSMIT-000100 | NA | Trade Partner | Glass Sample Submission(GL-03 Sliding door Option1) | 0 | 1 | 0 | NA | APPROVED | 2026-05-18 | WF-000539 | NA | 2026-06-03 |  | aanbir requested to hold | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-002499 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-13 | Jangho-TRANSMIT-000101 | NA | Trade Partner | Structural Calculation For FT01 & 02 System Concept Drawing | 0 | 1 | 0 | NA | APPROVED | 2026-05-18 | WF-000543 | NA | 2026-05-26 |  | Jaanbir requested to hold | 2026-05-25 | 2026-06-10 | KPTG-TRANSMIT-002212 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-13 | Jangho-TRANSMIT-000102 | NA | Trade Partner | Structural Calculation For FT07 & 09 System Concept Drawing | 0 | 1 | 0 | NA | APPROVED | 2026-05-18 | WF-000542 | NA | 2026-05-26 |  | Jaanbir requested to hold | 2026-05-26 | 2026-06-09 | KPTG-TRANSMIT-002191 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-14 | SMEPS-TRANSMIT-000203 | SPARK-CRFI-KPG-000489 | Trade Partner | Distribution Boards DB-16(A), DB-02(A), DB-03(A), DB-04(A), DB-05(A), DB-11(B), DB-17(B), | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | 2026-05-21 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-000869 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-13 | Jangho-TRANSMIT-000103 | NA | Trade Partner | Window handle Option 2 LCZS340 Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-18 | WF-000540 | NA | 2026-06-03 |  | Jaanbir requested to hold | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001885 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-17 | Auspan-TRANSMIT-000035 | NA | Trade Partner | Revised GF shop drawings issued for approval | 5 | 0 | 0 | NA | APPROVED | 2025-12-17 |  | 495 | 2025-12-24 |  |  | 2025-12-18 | 2025-12-18 | KPTG-SADV-002544 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-14 | Civilex-TRANSMIT-000243 | NA | Trade Partner | Re: M3-STR-SYM-TD-S-0301-3068 Sleeper Mix Design | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-05-14 | KPTG-RFI-007903 | Open | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-13 | Jangho-TRANSMIT-000104 | NA | Trade Partner | Window handle Option 3 LCZS341 Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-18 | WF-000541 | NA | 2026-06-03 |  | Jaanbir requested to hold | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001886 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-13 | INGEN3D-TRANSMIT-000068 | NA | Trade Partner | Level 5-7 - Precast Columns - Deleted Drawings | 20 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No longer in use - distributed |  | 2026-05-13 | KPTG-TRANSMIT-001777 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-13 | INGEN3D-TRANSMIT-000070 | NA | Trade Partner | Level 2-4 - Precast Columns - Revised IFC | 19 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Issued to Tradepartners |  | 2026-05-13 | KPTG-TRANSMIT-001773 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-13 | INGEN3D-TRANSMIT-000071 | NA | Trade Partner | Level 3-5 - PC0428 - New IFA | 3 | 0 | 0 | NA | APPROVED | 2026-05-13 | WF-000517 | NA | 2026-05-21 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-001794 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-13 | INGEN3D-TRANSMIT-000072 | NA | Trade Partner | Level 3-5 - PC0217 - No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No longer in use - distributed |  | 2026-05-13 | KPTG-TRANSMIT-001780 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-13 | INGEN3D-TRANSMIT-000073 | NA | Trade Partner | Level 8-10 - Precast Columns - IFA | 43 | 0 | 0 | NA | APPROVED | 2026-05-13 | WF-000518 | NA | 2026-05-21 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-001936 | Closed | 43 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-13 | INGEN3D-TRANSMIT-000074 | NA | Trade Partner | Level 3-5 - Precast Columns - Revised IFC | 35 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Issued to Tradepartners |  | 2026-05-13 | KPTG-TRANSMIT-001775 | Closed | 35 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-11 | TTW-TRANSMIT-000153 | NA | Consultant | BP4 - Issued for Construction | 399 | 0 | 0 | NA | APPROVED | 2026-05-11 | NA | 555 | 2026-05-13 |  |  | 2026-05-13 | 2026-05-13 | KPTG-TRANSMIT-001744 | Closed | 39 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-13 | RDSBIM-TRANSMIT-000034 | NA | Trade Partner | GROUND FLOOR TO LEVEL 09 STAIR/LIFT CORE 02 CONCRETE PROFILE PLAN SECTION AND ELEVATION | 3 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 569 | 2026-05-18 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001829 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-02 | Diadem-TRANSMIT-000003 | NA | Trade Partner | DH7 & DH 8 Wayfinding Signage | 1 | 0 | 0 | NA | APPROVED | 2025-12-02 | WF-000823 | NA | 2025-12-22 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-17 | Tradetec-TRANSMIT-000311 | NA | Trade Partner | IFA - Stage 4 - LVP36, CP32 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect reference number - KPTG-DA-003995 |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-14 | D&E-TRANSMIT-000256 | NA | Trade Partner | Mechanical Services Seismic Level-01 Ductwork | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect drawing number |  | 2026-05-14 | KPTG-TRANSMIT-000868 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-14 | D&E-TRANSMIT-000707 | NA | Trade Partner | Flushing Procedure - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-14 | WF-005704 | NA | 2026-05-28 |  |  | 2026-06-17 | 2026-06-17 | D&E-TRANSMIT-000707 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-14 | ECBS-TRANSMIT-000041 | NA | Trade Partner | Fan Wall Unit Steel - Revised Drawings For Approval (Batch 2: 25 drawings) | 25 | 0 | 0 | NA | APPROVED | 2026-05-14 | WF-005707 | NA | 2026-05-27 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-04 | SMEPS-TRANSMIT-000269 | NA | Trade Partner | SME - TELECOMMUNICATIONS IFC DRAWINGS | 2 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 3064 | 2026-05-11 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-14 | D&E-TRANSMIT-000709 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - GROUND - CHW PIPE LAYOUT ZONE 5 | 1 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 3226 | 2026-05-27 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-017429 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-14 | ACG-TRANSMIT-000092 | NA | Trade Partner | Re: M3 - Stage 2 O&M FOA-2 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | special character in document number |  | 2026-05-14 | KPTG-SADV-005387 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-14 | Altaire-TRANSMIT-000009 | NA | Trade Partner | FIRE DETECTION SERVICES - LEVEL 2 COLO 4 DRY FIRE LOW LEVEL LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-05-14 | WF - 000419 | NA | 2026-05-19 |  | File superseded | 2026-05-14 | 2026-05-14 | NA | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-14 | Tradetec-TRANSMIT-000442 | NA | Trade Partner | Tech Data - Sitewide - Chemset Reo502 Xtrem | 0 | 1 | 0 | NA | APPROVED | 2026-05-14 | WF-005714 | na | 2026-05-21 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-017959 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-14 | ADP-TRANSMIT-000067 | NA | Consultant | ADP MEL4680 - Updated Electrical Drawings (IFC) | 3 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 227 | 2026-05-19 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-000558 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-14 | D&E-TRANSMIT-000708 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - AS BUILT - SCHEMATIC & DUCT LAYOUTS | 16 | 0 | 0 | NA | REJECTED | [5 empty] | Different status in same transmit |  | 2026-05-14 | KPTG-SADV-005390 | Closed | 16 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-11 | GEMBA-D-TRANSMIT-000009 | NA | Consultant | Stage 9 Piling and foundations update | 4 | 0 | 0 |  | APPROVED | 2025-12-18 |  | 155 | 2025-12-22 |  | 2 Drawings on bluebeam review | 2025-12-18 | 2026-01-14 | KPTG-TRANSMIT-000487, KPTG-TRANSMIT-000427 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-14 | D&E-TRANSMIT-000710 | NA | Trade Partner | Re: Stage 2 Fire Matrix Discrepancies | 0 | 1 | 0 | NA | APPROVED | 2026-05-14 | (WF-005715) | NA | 2026-05-28 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018396 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-14 | D&E-TRANSMIT-000706 | NA | Trade Partner | ISSUED FOR APPROVAL - TYPICAL SFN LAYOUT & DETAILS | 1 | 0 | 0 | NA | APPROVED | 2026-05-14 | 0 | 3220 | 2026-05-19 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-018138 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-14 | SKS Tech-TRANSMIT-000139 | NA | Trade Partner | Small Power - Layout Roof | 3 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 3222 | 2026-05-19 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-017356 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-14 | ARCST-TRANSMIT-000289 | NA | Trade Partner | Roof Lower Gantry Stairs | 19 | 0 | 0 | NA | REJECTED | [5 empty] | IFA of the document not received before submission of IFC |  | 2026-05-14 | KPTG-SADV-005393 | Closed | 19 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-14 | Tradetec-TRANSMIT-000443 | NA | Trade Partner | Re: Tech Data - Bitac Primer - Stage 2 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision not updated |  | 2026-05-14 | KPTG-SADV-005394 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-14 | ADP-TRANSMIT-000311 | NA | Consultant | Re: ADP MEL4561 - Various Reports | 0 | 8 | 0 |  | APPROVED | [7 empty] | 2026-05-15 | KPTG-TRANSMIT-017400 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-14 | Stowe-A-TRANSMIT-000590 | NA | Trade Partner | Stowe - Tech Data - IFC Tech Data | 0 | 2 | 0 | NA | APPROVED | [5 empty] | Distributed to client,tradepartners and consultants |  | 2026-05-14 | KPTG-TRANSMIT-017338 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-14 | RDSBIM-TRANSMIT-000065 | NA | Trade Partner | 671CHP GROUND LEVEL TO ROOF CORE WALL LAYOUT AND ELEVATION | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol PC, IFC - no review register and distribute -KPTG-TRANSMIT-000960 |  | 2026-05-14 | KPTG-TRANSMIT-000960 | Open | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-14 | RDSBIM-TRANSMIT-000066 | NA | Trade Partner | 671CHP BASEMENT 2 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol PC , CPP- IFC - no review register and distribute - KPTG-TRANSMIT-000961 |  | 2026-05-14 | KPTG-TRANSMIT-000961 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-14 | LGCE-TRANSMIT-000026 | NA | Trade Partner | : Single line diagrams | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect Aconex Document number - KPTG-SADV-001910 |  | 2026-05-14 | KPTG-SADV-001910 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-08 | NCFGroup-TRANSMIT-000016 | NA | Trade Partner | ISG - S9 Updated Pile Layout and Schedule | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong Naming conventions-KPTG-TRANSMIT-000353 |  | 2025-12-16 |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-14 | LGCE-TRANSMIT-000027 | NA | Trade Partner | Electrical Single line | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to incorrect Aconex Document number - KPTG-SADV-001911 |  | 2026-05-14 | KPTG-SADV-001911 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-14 | B Smart-TRANSMIT-000073 | NA | Consultant | IFC update | 54 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 494 | 2026-05-14 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-001133 | Closed | 54 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-14 | B Smart-TRANSMIT-000073 | NA | Consultant | IFC update | 0 | 1 | 0 | NA | APPROVED | 2026-05-14 | WF-000410 | NA | 2026-05-18 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-001176 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-14 | RDSBIM-TRANSMIT-000057 | NA | Trade Partner | GREYSTAR GROUND FLOOR CONCRETE PROFILE PLAN AND SECTION ZONE 1 AND 3 | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Harris : transmittals received from RDS can be shared with trades, no further review needed for ground -KPTG-TRANSMIT-001844 |  | 2026-05-14 | KPTG-TRANSMIT-001844 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-14 | Auspan-TRANSMIT-000290 | NA | Trade Partner | Update already IFCed shop drawings | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | precast ifc - update Register and distribute; No review required - KPTG-TRANSMIT-001841 |  | 2026-05-14 | KPTG-TRANSMIT-001841 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-14 | M.2-TRANSMIT-000031 | NA | Trade Partner | Electrical Services Ground and Level 1 Lighting layouts | 10 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 976 | 2026-05-21 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-002344 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-14 | LVPG-TRANSMIT-000033 | NA | Trade Partner | LVPG-HY-TECH-067 - Studor AAV | 0 | 1 | 0 | NA | APPROVED | 2026-05-14 | WF-000499 | NA | 2026-05-20 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-14 | Auscool-TRANSMIT-000032 | NA | Trade Partner | Air Schematic Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 980 | 2026-05-21 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-001880 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-14 | Auscool-TRANSMIT-000031 | NA | Trade Partner | Ground Floor - IFA drawings | 5 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 978 | 2026-05-21 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-002705 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-14 | RDSBIM-TRANSMIT-000140 | NA | Trade Partner | MLCSPR ¦ INDOOR SPORTS CENTRE LEVEL 02 PARTITION WALL PLAN | 7 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 241 | 2026-05-19 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-003125 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-11 | PCForm-TRANSMIT-000016 | NA | Trade Partner | Jump from Concrete Envelopes & Wall Elevations - Stage 9 - Core 4 & 2 - Issued for construction | 10 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-TRANSMIT-000345 |  | 2025-12-15 |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-14 | RDSBIM-TRANSMIT-000141 | NA | Trade Partner | MLCSPR ¦ INDOOR SPORTS CENTRE LEVEL 03 CONCRETE PROFILE KEYPLAN | 5 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 243 | 2026-05-19 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-002957 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-14 | NXT-TRANSMIT-000370-FIP | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 05 | 33 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 93 | 2026-05-22 |  | Actual submission date 11-05-2026 | 2026-06-11 | 2026-06-11 | NA | Closed | 33 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-14 | NXT-TRANSMIT-000370-FUL | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 05 | 12 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 97 | 2026-05-22 |  | Actual submission date 11-05-2026 | 2026-06-11 | 2026-06-11 | NA | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-14 | NXT-TRANSMIT-000370-HYD | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 05 | 29 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 99 | 2026-05-22 |  | Actual submission date 11-05-2026 | 2026-06-11 | 2026-06-11 | NA | Closed | 29 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-14 | NXT-TRANSMIT-000370-MEC | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 05 | 29 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 101 | 2026-05-22 |  | Actual submission date 11-05-2026 | 2026-06-11 | 2026-06-11 | NA | Closed | 29 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-14 | Baigents-TRANSMIT-000003 | NA | Trade Partner | Block 01 - Level 01 Precast Beams IFA | 83 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 95 | 2026-05-22 |  | Voided-Drawings are revised |  | 2026-05-22 | NA | Closed | 83 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-14 | HDRAus-TRANSMIT-000133 | NA | Consultant | M3 Stage 6 - Town Planning Updates - Revised Retaining Wall - DWG files | 33 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | CAD Files |  | 2026-05-14 | NA | Closed | 33 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-04 | Baigents-TRANSMIT-000004 | NA | Trade Partner | Hoist Foundation Details IFC | 1 | 0 | 0 | KPTG-IntCorr-000092 | APPROVED |  | NA | NA |  |  | Actual submission date-14/02/2026-Update register only |  | 2026-06-04 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-14 | SMEPS-TRANSMIT-000262 | NA | Trade Partner | Electrical Functional Description | 0 | 1 | 0 | NA | APPROVED | 2026-05-14 | 1004 | NA | 2026-05-21 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-14 | ADP-TRANSMIT-000043 | NA | Consultant | ADP MEL4834 - M3 Stage 1 - A7A8 Powder Extinguishers | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Distributed-IFC |  | 2026-05-14 | Awaiting approval | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2025-12-17 | Nilsen3-TRANSMIT-000098 | NA | Trade Partner | Nilsen Shop Drawings - As-Builts | 5 | 0 | 0 | NA | APPROVED | [5 empty] | As-Builts, No review required, distributed to the Project Team. |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-14 | D&E-TRANSMIT-000361 | NA | Trade Partner | D&E O&M Manual - As built | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Distributed-As built |  | 2026-05-14 | Awaiting approval | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-20 | RDSBIM-TRANSMIT-000009 | NA | Trade Partner | NXM2S9 GROUND FLOOR AMENITIES WEST FLOOR FINISH LAYOUT AND ELEVATIONS | 2 | 0 | 0 | NA | APPROVED | 2026-06-20 | NA | 889 | 2026-06-24 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-005008 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-20 | RDSBIM-TRANSMIT-000010 | NA | Trade Partner | NXM2S9 GROUND FLOOR UNISEX WC FLOOR FINISH LAYOUT AND ELEVATIONS | 1 | 0 | 0 | NA | APPROVED | 2026-06-20 | NA | 890 | 2026-06-24 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-005010 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-14 | WSP ANZ-TRANSMIT-000069 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit - Hydraulic | 31 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 859 | 2026-05-19 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-003227 | Closed | 31 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-14 | PFP PL-TRANSMIT-000003 | NA | Trade Partner | Hydrant Pump Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-05-14 | WF-000688 | NA | 2026-05-26 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-003673 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-14 | VIA Arch-TRANSMIT-000121 | NA | Consultant | M2 S9 GF L1 Fire Separation Plan | 1 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 861 | 2026-05-19 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-003274 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-14 | VIA Arch-TRANSMIT-000122 | NA | Consultant | M2 S9 -11 DDA Comment Amendments | 9 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 864 | 2026-05-19 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-002891 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-14 | VIA Arch-TRANSMIT-000124 | NA | Consultant | M2 S9 West & S11 East Elevations - Building Permit Issue | 2 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 865 | 2026-05-19 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-002910 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-14 | VIA Arch-TRANSMIT-000125 | NA | Consultant | M2 S9-11 CD5 Amendments | 39 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 871 | 2026-05-19 |  |  | 2026-05-24 | 2026-05-24 | KPTG-TRANSMIT-002943 | Closed | 39 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-14 | WGAVIC-TRANSMIT-000118 | NA | Consultant | M2 - Stage 11 L2 Slab and Stage 9 Plinths - Issued for Certification | 6 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 873 | 2026-05-19 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-002984 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-13 | Auspan-TRANSMIT-000023 | NA | Trade Partner | Additional 3 L shape panels for review. | 3 | 0 | 0 | NA | REJECTED | 2025-12-15 |  |  |  |  | Wrong title Guide-KPTG-TRANSMIT-000356 Kapitol initiated an Internal Workflow-WF-000090 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-15 | ADP-TRANSMIT-000066 | NA | Consultant | Fwd: MEL4680 - GE1 ESD Section J-DTS Building Permit Report | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Report for distribution only |  | 2026-05-15 | KPTG-TRANSMIT-000551 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-23 | ARCST-TRANSMIT-000266 | NA | Trade Partner | Stage 2 Admin Roof South Screen IFA Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-04-23 | WF-005429 | NA | 2026-05-12 |  |  |  | 2026-05-15 | KPTG-TRANSMIT-017403 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-04-15 | ARCST-TRANSMIT-000259 | NA | Trade Partner | Roof Screens IFA Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-04-15 | WF-005300 | NA | 2026-05-01 |  |  | 2026-05-08 | 2026-05-15 | KPTG-TRANSMIT-017408 | Closed | 5 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-15 | WilsonPD-TRANSMIT-000007 | NA | Trade Partner | Re: Hydraulic shop drawing issued for Construction | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Drawing template is quite different:KPTG-IntCorr-000384 |  | 2026-05-15 | KPTG-IntCorr-000384 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-15 | Appselec-TRANSMIT-000095 | NA | Trade Partner | ISOLATION TRANSFORMER, EARTH BAR & EARTH PIT GENERAL ARRANGEMENTS & SCHEMATICS ISSUED FOR CONSTRUCTION | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: previous revision history have not been mentioned in the revision history.KPTG-IntCorr-000383 |  | 2026-05-15 | KPTG-IntCorr-000383 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-15 | SMEPS-TRANSMIT-000204 | NA | Trade Partner | Distribution Boards DB-16(A), DB-02(A), DB-03(A), DB-04(A), DB-05(A), DB-11(B), DB-17(B), | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Already received and reviewed revision |  | 2026-05-15 | KPTG-TRANSMIT-000871 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-15 | Altaire-TRANSMIT-000107 | NA | Trade Partner | Sequence of Operations for S2 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | ALREADY IN REVIEW |  | 2026-05-15 | KPTG-SADV-005399 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-15 | SMEPS-TRANSMIT-000205 | NA | Trade Partner | Distribution Boards DB-16(A), DB-02(A), DB-03(A), DB-04(A), DB-05(A), DB-11(B), DB-17(B), | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Already received and reviewed revision. |  | 2026-05-15 | KPTG-TRANSMIT-000872 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-14 | PCForm-TRANSMIT-000186 | NA | Trade Partner | Re-issue | 1 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 571 | 2026-05-22 |  |  | 2026-05-27 | 2026-05-27 | PCForm-TRANSMIT-000186 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-14 | INGEN3D-TRANSMIT-000076 | NA | Trade Partner | Level 5-7 - Precast Columns - IFC | 1 | 0 | 0 | NA | APPROVED | 2026-05-15 | WF-000532 |  | 2026-05-22 |  | NICH TO CONFIRM |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-16 | Auspan-TRANSMIT-000024 | NA | Trade Partner | Resubmit L shape panels for approval and new columns. | 73 | 0 | 0 | NA | REJECTED | 2025-12-16 |  |  |  |  | Wrong title Guide-KPTG-TRANSMIT-000383 Kapitol initiated an Internal Workflow-WF-000094 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-14 | Civilex-TRANSMIT-000090 | NA | Trade Partner | Ardent Copper Pipes | 0 | 1 | 0 | NA | APPROVED | 2026-05-14 | WF-000524 | NA | 2026-05-19 |  |  | 2026-06-12 | 2026-06-15 | KPTG-TRANSMIT-002285 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-14 | Civilex-TRANSMIT-000091 | NA | Trade Partner | KPTG-ST-SMP-016 - PRIME EVAPLOC – Concentrated Aliphatic Alcohol - Spec | 0 | 1 | 0 | NA | APPROVED | 2026-05-14 | WF-000525 | NA | 2026-05-21 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-001899 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-14 | Firesafe-TRANSMIT-000008 | NA | Trade Partner | Levels Ground to L4 (IFA) | 12 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 573 | 2026-05-25 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-002186 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-08 | WAM-TRANSMIT-000767 | NA | Consultant | Common Areas Joinery 80% DD | 26 | 0 | 0 | NA | APPROVED | 2026-05-08 | NA | 551 | 2026-05-14 |  |  | 2026-05-14 | 2026-05-14 | KPTG-TRANSMIT-001783 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-15 | RDSBIM-TRANSMIT-000199 | NA | Trade Partner | LINDRUM ¦ LEVEL 07 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 652 | 2026-05-20 |  |  | 2026-06-02 | 2026-06-02 | KPTG-SADV-004390 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-15 | RDSBIM-TRANSMIT-000200 | NA | Trade Partner | LINDRUM ¦ LEVEL 08 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 653 | 2026-05-20 |  |  | 2026-06-02 | 2026-06-02 | KPTG-SADV-004400 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-15 | RDSBIM-TRANSMIT-000201 | NA | Trade Partner | LINDRUM ¦ LEVEL 09 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 654 | 2026-05-20 |  |  | 2026-06-02 | 2026-06-02 | KPTG-SADV-004401 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-15 | EFP-TRANSMIT-000019 | NA | Trade Partner | Re: EFP Tech Data Alternative | 0 | 1 | 0 | NA | APPROVED | 2026-05-15 | WF-000239 | NA | 2026-05-22 |  | KPTG-IntCorr-000497- reviewed document needs to be updated, wORKFLOWTERMINATED | 2026-06-01 | 2026-07-01 | KPTG-TRANSMIT-000990 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-15 | KPTG-TRANSMIT-017407 | NA | Trade Partner | M3 S2 - Bricklaying OMM | 0 | 1 | 0 | NA | APPROVED | 2026-05-15 | WF-005717 | NA | 2026-05-29 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-017651 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-17 | Entire M-TRANSMIT-000020 | NA | Trade Partner | Fire Matrix Issued for Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The reference number assigned in Aconex is not mentioned in the document. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-15 | Tradetec-TRANSMIT-000444 | NA | Trade Partner | Tech Data - Bitac Primer - Stage 2 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Same revision transmitted again. |  | 2026-05-15 | KPTG-SADV-005404 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-15 | D&E-TRANSMIT-000711 | NA | Trade Partner | Re: Admin Office Functional Description - Issued for approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-15 | WF-005718 | NA | 2026-05-29 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-15 | DS-TRANSMIT-000119 | NA | Trade Partner | Updated Roof penetrations (HYD) | 3 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 3234 | 2026-05-25 |  |  |  | 2026-05-20 | KPTG-IntCorr-013475 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-14 | INGEN3D-TRANSMIT-000075 | NA | Trade Partner | Level 3-5 - PC0428 - IFC | 51 | 0 | 0 | NA | APPROVED | 2026-05-15 | WF-000531 |  | 2026-05-22 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-001913 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-15 | HDRAus-TRANSMIT-000487 | NA | Consultant | M3_S2_AS-BUILT DRAWINGS AND SCHEDULES_SP3_SP5 | 17 | 5 | 0 | NA | REJECTED | [5 empty] | Previous revision rejected for documents |  | 2026-05-15 | KPTG-DA-006557 | Closed | 22 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-15 | WilsonPD-TRANSMIT-000008 | NA | Trade Partner | Re: Hydraulic shop drawing issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-05-15 | WF-000240 | NA | 2026-05-20 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-000714 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-15 | D&E-TRANSMIT-000712 | NA | Trade Partner | ISSUED FOR HANDOVER - GROUND - MECHANICAL PIPE LAYOUT - ZONE 1 | 1 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 4204 | 2026-05-20 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-017815 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-15 | ADP-TRANSMIT-000312 | NA | Consultant | Updated Roof penetrations (HYD) | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-05-15 | KPTG-TRANSMIT-017435 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-15 | Tradetec-TRANSMIT-000445 | NA | Trade Partner | Stage 2 - Tech Data - Bitac Primer | 0 | 1 | 0 | NA | APPROVED |  | WF-005725 | NA | 2026-05-22 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-017509 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-15 | D&E-TRANSMIT-000257 | NA | Trade Partner | Seismic Guide with REG126 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document number is incorrect. |  | 2026-05-15 | KPTG-TRANSMIT-000874 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-15 | WSP ANZ-TRANSMIT-000029 | NA | Consultant | WSP- Earthing Report - M2 ST9-11 - Kapitol Group - Next DC | 0 | 1 | 0 |  | APPROVED | [5 empty] | For Information, No review required. |  | 2025-12-16 |  | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-15 | Auspan-TRANSMIT-000291 | NA | Trade Partner | Precast shop drawings for approval | 79 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 986 | 2026-05-22 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-002097 | Closed | 79 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-15 | D&E-TRANSMIT-000714 | NA | Trade Partner | Re: ISSUED FOR CONSTRUCTION - LEVEL 1 - BUILDERS WORKS LAYOUTS - ZONES 1 - 6 | 6 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-05-15 | KPTG-TRANSMIT-017473 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-15 | PROLMC-TRANSMIT-000025 | NA | Trade Partner | MCC Shop Drawings IFC | 20 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 283 | 2026-05-22 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-15 | VERTIV-TRANSMIT-000011 | NA | Trade Partner | NEXT DC GE 01 _ BATTERY SIZING CALCULATION | 0 | 1 | 0 | NA | APPROVED | 2026-05-15 | WF-000132 | NA | 2026-05-25 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-000724 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-18 | SYNACC-TRANSMIT-000004 | NA | Trade Partner | Transmittal - Facade Access - Level 5 - [P-01] | 2 | 0 | 0 | NA | APPROVED | 2026-05-18 | WF-000759 | NA | 2026-05-22 |  | KPTG-IntCorr-001161 - reason is altitude are not scoped to review drawings. | 2026-05-28 | 2026-05-28 | KPTG-IntCorr-001161 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-15 | HDRAus-TRANSMIT-000488 | NA | Consultant | M3 SW - Document upload | 3 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 4206 | 2026-05-19 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-017667 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-15 | ADP-TRANSMIT-000313 | NA | Consultant | Fwd: ADP MEL4780 - SMP Thermal Performance & Section J report | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-05-15 | KPTG-TRANSMIT-017482 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-15 | SMEPS-TRANSMIT-000214 | NA | Trade Partner | SME Shop Drawing Telecomunications IFC | 1 | 0 | 0 | NA | APPROVED | 2026-05-15 | WF - 000420 | NA | 2026-05-13 |  | NA | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-000871 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-04-28 | KALLIBRE-TRANSMIT-000001 | NA | Trade Partner | MEL11 C4&5 Door Frame Shop Drawings | 37 | 0 | 0 | NA | APPROVED | 2026-04-28 | WF-000182 | NA | 2026-05-06 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-000645 | Closed | 37 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-15 | UBM corp-SUBADVICE-000015 | NA | Trade Partner | Concrete Sealer Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-15 | WF - 001022 | NA | 2026-05-20 |  | NA | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-002994 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-17 | Entire M-TRANSMIT-000023 | NA | Trade Partner | BMS Points List, Drawings and Functional Description Issued for Approval | 3 | 0 | 0 | NA | APPROVED | 2025-12-17 | WF-003655 |  | 2025-12-30 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-15 | HDRAus-TRANSMIT-000489 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 12 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 3238 | 2026-05-19 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-017744 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-15 | DS-TRANSMIT-000118 | NA | Trade Partner | Updated Roof and Upper Roof Drainage shop drawing | 6 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 3236 | 2026-05-22 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018385 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-15 | RDSBIM-TRANSMIT-000272 | NA | Trade Partner | NXM3S4 GROUND FLOOR TO ROOF PRECAST WALL PLAN AND ELEVATION | 23 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 3229 | 2026-05-19 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-018312 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-15 | VAE-Grp-TRANSMIT-000162 | NA | Trade Partner | Louvres - IFC | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  | FC doc send to all parties |  | 2026-05-15 | KPTG-TRANSMIT-003721 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-15 | RDSBIM-TRANSMIT-000058 | NA | Trade Partner | GREYSTAR ¦ LEVEL 01 CONCRETE PROFILE PLAN ZONE 2 & ZONE 5 | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - update Register and distribute -KPTG-TRANSMIT-001852 |  | 2026-05-15 | KPTG-TRANSMIT-001852 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-15 | Auspan-TRANSMIT-000292 | NA | Trade Partner | Precast shop drawings for construction | 40 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | precast IFC - update Register and distribute; No review required -KPTG-TRANSMIT-001851 |  | 2026-05-15 | KPTG-TRANSMIT-001851 | Closed | 40 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-15 | POTTSENG-TRANSMIT-000040 | NA | Trade Partner | GMAC HYDRAULIC SERVICES - WATER - BASEMENT 1 - ZONE 1-5 LAYOUTS | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - update Register and distribute - KPTG-TRANSMIT-001854 |  | 2026-05-15 | KPTG-TRANSMIT-001854 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-15 | POTTSENG-TRANSMIT-000041 | NA | Trade Partner | GMAC HYDRAULIC SERVICES - PENETRATION - LEVEL 02 - ZONE 1-5 LAYOUTS | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC -update Register and distribute KPTG-TRANSMIT-001858 |  | 2026-05-15 | KPTG-TRANSMIT-001858 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-15 | LGCE-TRANSMIT-000028 S | NA | Trade Partner | ingle line diagrams | 4 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 496 | 2026-05-21 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-001005 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-02 | ADP-TRANSMIT-000140 | NA | Consultant | S4 ¦ ADP MEL4780 - Services Specifications - (Tender Issue) | 0 | 5 | 0 | NA | APPROVED |  | NA | NA |  |  | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-17 | fjc-TRANSMIT-000118 | NA | Consultant | Re: LIN ¦ Level 08 ¦ CPP ¦ Request for confirmation on slab dimension discrepancy. | 1 | 0 | 0 | NA | APPROVED | 2025-12-17 |  | 496 | 2025-12-24 |  |  | 2025-12-18 | 2025-12-18 | KPTG-SADV-002543 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-15 | StantecA-TRANSMIT-000026 | NA | Consultant | Fire Protection Construction Set | 40 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Register and Transmit to all trades and consultants. KPTG-TRANSMIT-000970 |  | 2026-05-15 | KPTG-TRANSMIT-000970 | Closed | 41 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-15 | KPTG-TRANSMIT-000973 | NA | Consultant | Landscape Drawings | 23 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update ACC Register; No other action required. |  | 2026-05-15 | NA | Closed | 23 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-15 | NXT-TRANSMIT-000370-sec | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 05 | 73 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 103 | 2026-05-25 |  | Actual submission date 11-05-2026-Voided | 2026-06-11 | 2026-06-11 | NA | Closed | 73 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-15 | NXT-TRANSMIT-000370-Tel | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 05 | 23 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 106 | 2026-05-25 |  | Actual submission date 11-05-2026 | 2026-06-11 | 2026-06-11 | NA | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-15 | NXT-TRANSMIT-000370-Tp | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 05 | 32 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 108 | 2026-05-25 |  | Actual submission date 11-05-2026-Voided | 2026-06-11 | 2026-06-11 | NA | Closed | 32 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-18 | 4DW-TRANSMIT-000039 | NA | Consultant | Structural Documentation: Block 1 - Precast walls & Foundations (Issued for Construction). | 17 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 111 | 2026-05-25 |  | Actual submission date-15-05-2026-Voided | 2026-06-11 | 2026-06-11 | NA | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-15 | HDRAus-TRANSMIT-000135 | NA | Consultant | M3 Stage 6 - Town Planning Updates - Documentation comments response | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | Update register only |  | 2026-05-15 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-15 | HDRAus-TRANSMIT-000133 | NA | Consultant | M3 Stage 6 - Town Planning Updates - Revised Retaining Wall - DWG files | 33 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | HDRAus-TRANSMIT-000132 superseded, CAD files update register only |  | 2026-05-15 | NA | Closed | 33 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-15 | HDRAus-TRANSMIT-000134 | NA | Consultant | M3 Stage 6 - Town Planning Updates - Revised Retaining Wall | 33 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Already submitted |  | 2026-05-15 | NA | Closed | 33 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-18 | HDRAus-TRANSMIT-000136 | NA | Consultant | M3 Stage 6 - Town Planning Updates - Documentation comments response | 2 | 0 | 0 |  | APPROVED | 2026-05-18 | NA | 113 | 2026-05-25 |  | superseded HDRAus-TRANSMIT-000131-Actual submission date 15-05-2026-Voided | 2026-06-11 | 2026-06-11 | NA | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-16 | Auspan-TRANSMIT-000025 | NA | Trade Partner | Update marking plans. | 2 | 0 | 0 | NA | REJECTED | 2025-12-16 |  |  |  |  | Wrong title Guide-KPTG-TRANSMIT-000363 Kapitol initiated an Internal Workflow-WF-000094 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-15 | 4DW-TRANSMIT-000040 | NA | Consultant | Issued for Construction: Precast walls & Foundations - Block 1 | 13 | 0 | 0 | NA | APPROVED | [5 empty] | update register only |  | 2026-05-15 | NA | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-15 | D&E-TRANSMIT-000362 | NA | Trade Partner | O&M Manual - As built | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Distributed-Asbuilt |  | 2026-05-15 | Awaiting approval | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-15 | Altaire-TRANSMIT-000031 | NA | Trade Partner | Dry Fire O&M ABS(B) | 0 | 1 | 0 | NA | APPROVED | [5 empty] | Altaire-TRANSMIT-000030 superseded- Andrew rejected |  | 2026-05-15 | KPTG-SADV-002476 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-15 | ADP-TRANSMIT000044- | NA | Consultant | MEL4834 - ADP ELC Reports | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | For information |  | 2026-05-05 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-15 | ZIA-TRANSMIT-000081 | NA | Trade Partner | M3S1DH78 - Zi-Argus - Practical Completion Documentation | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Distribution only |  | 2026-05-15 | Awaiting approval | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-15 | VIA Arch-TRANSMIT-000129 | NA | Consultant | Architectural Documentation - Stage 10 - Stair 05 | 1 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 878 | 2026-05-20 |  |  | 2026-07-04 | 2026-07-04 | KPTG-DA-003502 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-15 | VIA Arch-TRANSMIT-000130 | NA | Consultant | Stage 2 Tank Slab | 2 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 879 | 2026-05-20 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-003278 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-15 | VIA Arch-TRANSMIT-000131 | NA | Consultant | STAGE 09 _Level 02 Concrete Profile drawings | 1 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 881 | 2026-05-20 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-003165 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-01-23 | OWCCons-TRANSMIT-000016 | NA | Trade Partner | Update Civil drawings - C012 | 1 | 0 | 0 | NA | APPROVED | 2026-01-26 | NA | 409 | 2026-01-30 |  |  | 2026-05-15 | 2026-05-15 | KPTG-SADV-004343 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-15 | RDSBIM-TRANSMIT-000014 | NA | Trade Partner | MEL11C45 ¦ LEVEL 02 COLO 4 AREA RCP LAYOUT | 6 | 0 | 0 | NA | APPROVED | 2026-05-15 | WF-000241 | NA | 2026-05-20 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-000655 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-15 | BLUESF-TRANSMIT-000003 | N/A | Trade Partner | M2-STR-BSF-STAGE 11-PRECAST DRAWINGS-GROUND LEVEL IFA | 280 | 0 | 0 | N/A | REJECTED |  | N/A | N/A |  |  | KPTG-TRANSMIT-000364 |  | 2025-12-17 | KPTG-TRANSMIT-000364 | Closed | 280 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-15 | RDSBIM-TRANSMIT-000013 | na | Trade Partner | MEL11C45 ¦ PARTITION WALL LAYOUT L02 COLO5B | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings need to be approval:KPTG-IntCorr-000388 |  | 2026-05-15 | KPTG-IntCorr-000388 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-06 | DLTS-TRANSMIT-000002 | NA | Trade Partner | L2 Platform (Antenna Room) IFA Package | 31 | 0 | 0 | NA | APPROVED | 2026-05-06 | WF-000632 | NA | 2026-05-13 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-003185 | Closed | 31 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-15 | WilsonPD-TRANSMIT-000044 | NA | Trade Partner | Stage 2 Slab Set out - Water Treatment Plant REV5 | 1 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 875 | 2026-05-22 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-003362 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-15 | Tradetec-TRANSMIT-000134 | NA | Trade Partner | Contaminated Sprinkler Drain Technical Data | 0 | 1 | 0 | NA | APPROVED | 2026-05-15 | WF-000697 | NA | 2026-05-26 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-003374 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-15 | Tradetec-TRANSMIT-000133 | NA | Trade Partner | Roxtec Knockout Sleeve Technical Data | 0 | 1 | 0 | NA | APPROVED | 2026-05-15 | WF-000696 | NA | 2026-05-27 |  |  | 2026-05-27 | 2026-05-27 | KPTG-TRANSMIT-003571 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-15 | Eneraque-TRANSMIT-000015 | NA | Trade Partner | Document Submission | 0 | 6 | 0 | NA | APPROVED | 2026-05-15 | WF-000695 | NA | 2026-05-27 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-004460 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-15 | CRSol-TRANSMIT-000006 | NA | Trade Partner | CRS - Tech Data Submission NextDC M2 S9_11 | 0 | 1 | 0 | NA | APPROVED | 2026-05-15 | WF-000693 | NA | 2026-05-28 |  |  | 2026-07-03 | 2026-07-06 | KPTG-TRANSMIT-005223 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-15 | Altaire-TRANSMIT-000003 | NA | Trade Partner | NEXTDC M2S9 - Ground Level - Shop Drawings + MASDS Calc (FA-1) | 2 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 883 | 2026-05-20 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-003798 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-15 | SMEPS-TRANSMIT-000039 | NA | Trade Partner | STAGE 9 - 11 Telecoms Inground Site Layout (FC-1) | 1 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 884 | 2026-05-20 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-003441 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-15 | Firesafe-TRANSMIT-000009 | NA | Trade Partner | L1 to L4 Peno drawings + Registers IFA | 8 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 578 | 2026-05-22 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-002194 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-17 | Auscool-TRANSMIT-000062 | NA | Trade Partner | Level 9 - 11 Mechanical Shop Drawing IFA | 3 | 0 | 0 | NA | APPROVED | 2026-01-12 |  | 503 | 2026-01-19 |  | WF has not yet started. | 2026-01-15 | 2026-01-15 | KPTG-SADV-002625 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-15 | RDSBIM-TRANSMIT-000035 | NA | Trade Partner | MEZZANINE CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 576 | 2026-05-22 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-001952 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-15 | INGEN3D-TRANSMIT-000076 | NA | Trade Partner | Level 5-7 - Precast Columns - IFC | 51 | 0 | 0 | NA | APPROVED | 2026-05-15 | WF-000533 | NA | 2026-05-29 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-001934 | Closed | 51 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-15 | INGEN3D-TRANSMIT-000077 | NA | Trade Partner | Level 6-8 - Cast In Dowels - IFC | 6 | 0 | 0 | NA | APPROVED | 2026-05-15 | WF-000535 | NA | 2026-05-29 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-001919 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-15 | TTW-TRANSMIT-000159 | NA | Trade Partner | BP2a - Issued for Construction | 2 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 583 | 2026-05-18 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-001849 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-15 | Hollow-TRANSMIT-000012 | NA | Trade Partner | L3 plant room precast structure - PC beams 01 and 03 - Shop drawings, issued for Construction | 2 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 581 | 2026-05-18 |  |  | 2026-05-25 | 2026-05-26 | KPTG-TRANSMIT-001964 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-02 | SKS Tech-TRANSMIT-000160 | NA | Trade Partner | SEISMIC LAYOUTS IFC -TEL | 2 | 0 | 0 | KPTG-TRANSMIT-003037 | REJECTED | [5 empty] | QA ERROR |  | 2026-03-03 | KPTG-TRANSMIT-003715 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-08 | Baigents-TRANSMIT-000196 | NA | Trade Partner | Handrail IFA FOA-1 | 8 | 0 | 0 | NA | APPROVED | 2026-05-11 | WF-001053 | NA | 2026-05-14 |  |  | 2026-05-15 | 2026-05-15 | KPTG-TRANSMIT-003695 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-15 | Baigents-TRANSMIT-000196 | NA | Trade Partner | Handrail IFA FOA-1 | 0 | 0 | 0 | NA | APPROVED | 2026-05-11 | WF-001053 | NA | 2026-05-14 |  | 2 DOCS PENDING ENTRY | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-003752 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-18 | Outlook mail (Downloaded from Procore) | NA | Trade Partner | Stage 09 & 10 EAE Busduct Shop drawings | 55 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 888 | 2026-05-22 |  | Review terminated as advised by Design Manager. Next revision of same drawings are ssubmitted on another review # 970 |  |  | NA | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2025-12-17 | DI-TRANSMIT-000130 | NA | Trade Partner | PPT - Door Schedule | 0 | 1 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-15 | Carr-TRANSMIT-000017 | NA | Consultant | 80% DD Architectural Drawing Issue (Basement Level)) | 17 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 116 | 2026-05-20 |  | Actual Received Date 27-03-2026 | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-000133 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-15 | Carr-TRANSMIT-000009 | NA | Consultant | Architectural Current Drawing Set | 14 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 105 | 2026-05-15 |  | Actual Received date 3/24/2026 Review Voided as advised by Renee 26-05-2026 |  | 2026-05-26 | NA | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-15 | Carr-TRANSMIT-000009 | NA | Consultant | Architectural Current Drawing Set | 2 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 106 | 2026-05-20 |  | Actual Received date 3/24/2026 | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000158 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-15 | Carr-TRANSMIT-000047 | NA | Consultant | Demolition Plans Updated to reflect latest Structural | 5 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 132 | 2026-05-20 |  | Actual Received date 11-05-2026 | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000153 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-03 | Carr-TRANSMIT-000043 | NA | Consultant | Basement Concrete Profile Plans and Core IFA | 2 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 219 | 2026-06-09 |  | Actual Received date 08-05-2026 |  |  |  | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-15 | Carr-TRANSMIT-000058 | NA | Consultant | Updated Ground Floor Retail Tenancy DDA Entry | 1 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 130 | 2026-05-20 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000154 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-15 | Carr-TRANSMIT-000023 | NA | Consultant | 80% DD Architectural Drawing Issue | 3 | 0 | 0 | NA | APPROVED | 2026-05-15 | NA | 120 | 2026-05-20 |  | Actual Received date 27-03-2026 Review Voided as advised by Renee 26-05-2026 |  | 2026-05-26 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-14 | Carr-TRANSMIT-000056 | NA | Consultant | 80pc Facade Update for Coordination | 1 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 112 | 2026-05-20 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000077 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-14 | Carr-TRANSMIT-000053 | NA | Consultant | 80pc Facade Update for Coordination | 9 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 111 | 2026-05-19 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000076 | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-14 | Carr-TRANSMIT-000052 | NA | Consultant | -80pc Facade Update for Coordination | 7 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 110 | 2026-05-19 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000075 | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-17 | D&E-TRANSMIT-000075 | SPARK-CRFI-KPG-000491 | Trade Partner | MWYCCB - LEVEL 1 - PIPEWORK LAYOUT ZONES - Issued For Review | 3 | 0 | 0 | NA | APPROVED | 2025-12-17 | WF-000110 | 75 | 2025-12-24 |  | 2 documents pending - closeout closed - KPTG-TRANSMIT-000544 | 2026-03-10 | 2026-03-10 | KPTG-TRANSMIT-000519 & KPTG-TRANSMIT-000544 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-13 | ENF-TRANSMIT-000012 | NA | Consultant | Structural drawings | 4 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 84 | 2026-05-18 |  | Actual received date 08-05-2026 | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-000121 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-14 | ENF-TRANSMIT-000009 | NA | Consultant | Structural drawings | 2 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 103 | 2026-05-19 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-000190 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-15 | Arco-TRANSMIT-000002 | NA | Trade Partner | ARCO - ROLLER SHUTTERS AND GATES | 9 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-05-15 | KPTG-TRANSMIT-000873 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-18 | RDSBIM-TRANSMIT-000009 | NA | Trade Partner | NXGE01 ¦ ROOF CONCRETE PROFILE KEY PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 229 | 2026-05-22 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-000661 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-18 | INTRFRM-TRANSMIT-000051 | NA | Trade Partner | Geelong Edge - Roof Slab Post Tensioning Shop Drawing | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Additional characters in Document number. |  | 2026-05-18 | DRAFT-001992 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-18 | HGP-TRANSMIT-000055 | NA | Trade Partner | L1 Internal Glazing Drawings | 30 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-05-18 | KPTG-TRANSMIT-000877 | Closed | 30 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-18 | ASV-TRANSMIT-000175 | NA | Trade Partner | Hydraulic Sample - Internal Sewer Magflow | 0 | 1 | 0 | NA | APPROVED | 2026-05-18 | WF-005729 | NA | 2026-06-08 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-017895 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-18 | SMEPS-TRANSMIT-000287 | NA | Trade Partner | SME - IFC drawings | 2 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 3242 | 2026-05-25 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-017708 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-18 | Entire M-TRANSMIT-000048 | NA | Trade Partner | Mech-Elec - Technical Data Package Rev 2 IFC | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision of this document needs to be 3, Hence, Rejected:KPTG-IntCorr-000392 |  | 2026-05-18 | KPTG-IntCorr-000392 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-18 | Entire M-TRANSMIT-000049 | NA | Trade Partner | Mechanical drawings - minor updates | 6 | 0 | 0 | NA | APPROVED | 2026-05-18 | WF-000242 | NA | 2026-05-21 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-000721 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-17 | D&E-TRANSMIT-000076 | SPARK-CRFI-KPG-000473 | Trade Partner | MWYCCB - GROUND LEVEL & LEVEL 1 - PLINTH LAYOUT ZONES - Issued For Review | 4 | 0 | 0 | NA | APPROVED | 2025-12-17 | WF-000111 | 76 | 2025-12-24 |  |  |  |  | KPTG-TRANSMIT-000389 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-14 | WSP ANZ-TRANSMIT-000011 | NA | Consultant | WSP Updated 80% Tender Issue Drawings Electrical | 8 | 0 | 0 | NA | APPROVED | 2026-05-14 | NA | 92 | 2026-05-19 |  | Actual received date 08-05-2026 |  | 2026-05-28 | KPTG-TRANSMIT-000095 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-04-16 | D&E-TRANSMIT-000223 | SPARK-CRFI-KPG-000490 | Trade Partner | MWYCCB - ROOF & LEVEL 1 / DUCTWORK - PIPEWORK & RCP LAYOUT ZONES - Issued For Approval | 0 | 0 | 0 | NA | APPROVED | [5 empty] | SPARK-CRFI-KPG-000490 - NEL-CNT-DEA-2801-BSM-DRG-0206 | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-000881 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-18 | LNCPPL-TRANSMIT-000005 | NA | Trade Partner | TELECOMMUNICATION SERVICES GROUND FLOOR PLANT AREA LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 232 | 2026-05-22 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-000586 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-18 | LNCPPL-TRANSMIT-000006 | NA | Trade Partner | FIRE SERVICES GROUND FLOOR PLANT AREA LAYOUT - INGROUND ONLY | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue in Document number. |  | 2026-05-18 | KPTG-SADV-000402 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-18 | Stowe-A-TRANSMIT-000591 | NA | Trade Partner | Stowe - Tech Data Submission - X1 External Light Poles | 0 | 1 | 0 | NA | APPROVED | 2026-05-18 | WF-005733 | NA | 2026-05-28 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-017576 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-18 | LNCPPL-TRANSMIT-000007 | NA | Trade Partner | FIRE SERVICES GROUND FLOOR PLANT AREA LAYOUT - INGROUND ONLY | 1 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 234 | 2026-05-22 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-000653 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-18 | D&E-TRANSMIT-000715 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - GROUND - CHW PIPE LAYOUTS ZONE 4 & 2 2 | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect document number |  | 2026-05-18 | KPTG-RFI-007953 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-18 | Arco-TRANSMIT-000003 | NA | Trade Partner | ARCO ROLLER SHUTTERS AND GATES | 9 | 0 | 0 | NA | REJECTED | [5 empty] | History block is missing |  | 2026-05-18 | KPTG-TRANSMIT-000883 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-18 | NXT-TRANSMIT-001562 | NA | Trade Partner | Fwd: Separate Zip files with the End of line docs for each of the 10 Q units for Stage 4 | 0 | 12 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-05-18 | KPTG-TRANSMIT-017495 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-18 | NXT-TRANSMIT-001561 | NA | Trade Partner | Fwd: End of Line Quality Docs for 10 Q units for Stage 4 M3 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-05-18 | KPTG-TRANSMIT-017493 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-17 | RDSBIM-TRANSMIT-000006 | NA | Trade Partner | GREYSTAR ¦ BASEMENT CAPPING BEAM PLAN ELEVATION AND SECTION | 6 | 0 | 0 | NA | APPROVED | 2025-12-17 | WF-000109 | 218 | 2025-12-19 |  |  |  | 2026-01-15 | KPTG-TRANSMIT-000399 | Closed | 6 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-01 | D&E-TRANSMIT-000650 | NA | Trade Partner | Sanitary Ball Valves and Sanitary Butterfly Valves - Issued for approval | 0 | 0 | 0 | NA | APPROVED | 2026-05-01 | WF-005517 |  | 2026-05-25 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-017497 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-18 | D&E-TRANSMIT-000716 | NA | Trade Partner | Re: ISSUED FOR CONSTRUCTION - SECURITY GRILLS | 1 | 0 | 0 |  | REJECTED | [5 empty] | IFC was submitted before IFA |  | 2026-05-19 | KPTG-RFI-007994 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-18 | PSGANZ-TRANSMIT-000002 | NA | Trade Partner | Technical Data submissions | 0 | 6 | 0 | NA | REJECTED | [5 empty] | Error in Revision Number. |  | 2026-05-18 | KPTG-SADV-000407 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | D&E-TRANSMIT-000696 | NA | Trade Partner | NXM3S4 - Ground - Builders Works Layout Zones - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 3248 | 2026-05-26 |  | As requested by Ellie — Terminated — KPTG-IntCorr-013787 |  | 2026-05-26 | KPTG-IntCorr-013787 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-11 | D&E-TRANSMIT-000696<br> | NA | Trade Partner | NXM3S4 - Ground - Builders Works Layout Zones - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | [9 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-18 | SMEPS-TRANSMIT-000289 | NA | Trade Partner | SME - IFA Sample submissions | 0 | 1 | 0 | NA | APPROVED | 2026-05-18 | WF-005736 | NA | 2026-06-08 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-018898 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-18 | Civilex-TRANSMIT-000245 | NA | Trade Partner | Re: Southern Retaining Wall Rev K | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-05-18 | KPTG-RFI-007958 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-18 | INTRFRM-TRANSMIT-000052 | NA | Trade Partner | Geelong Edge - Roof Slab Post Tensioning Shop Drawing | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Error in title. |  | 2026-05-18 | KPTG-SADV-000409 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-18 | HGP-TRANSMIT-000056 | NA | Trade Partner | Drawings attached in this transmittal and its previous seem different | 30 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-05-18 | KPTG-TRANSMIT-000884 | Closed | 30 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-05-18 | SMPS-TRANSMIT-000115 | NA | Trade Partner | Electrical DB sample | 0 | 1 | 0 | NA | APPROVED | 2026-05-18 | WF-000492 | NA | 2026-05-26 |  |  | 2026-05-19 | 2026-05-19 | DRAFT-010004 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-17 | LVPG-TRANSMIT-000003 | NA | Trade Partner | LVPG-TRANSMIT-000003 LVPG - In ground Tech Data Submittals | 6 | 1 | 0 | NA | APPROVED | 2025-12-17 | WF-000110 ¦ WF-000111 | NA | 2025-12-24 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-18 | ADP-TRANSMIT-000316 | NA | Consultant | DDL/DDC handover docs for SP5 | 0 | 2 | 0 | NA | APPROVED | [5 empty] | Distribution only. |  | 2026-05-18 | KPTG-TRANSMIT-017504 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-18 | ADP-TRANSMIT-000315 | NA | Consultant | M3 Stage 1 & 4 - Office Fitout Return Brief_BLUEBEAM DESIGN WORKFLOW TO NEXTDC | 5 | 0 | 0 | NA | APPROVED | 2026-05-18 | WF-005739 | NA | 2002-06-08 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-18 | ETNInd-TRANSMIT-000015 | NA | Trade Partner | MEL11 COLO4 & COLO5 EPMS TOPOLOGY OVERVIEW | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected: Document Number of drawings is incorrect, requested to resubmit:KPTG-IntCorr-000396 |  | 2026-05-18 | KPTG-IntCorr-000396 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-18 | Appselec-TRANSMIT-000098 | NA | Trade Partner | Appselec Commissioning Manuals | 0 | 5 | 0 | NA | REJECTED | [5 empty] | Document number of all documents are incorrect: KPTG-IntCorr-000397 |  | 2026-05-18 | KPTG-IntCorr-000397 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-18 | Civilex-TRANSMIT-000244 | NA | Trade Partner | Stage 1 Swale Remedial Planting - Rev D | 1 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 4208 | 2026-05-25 |  | Terminated as requested by Charlie Johnstone for updating the documents. | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-017634 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-18 | MCGC-TRANSMIT-000009 | NA | Consultant | Re: Southwest Stair Drawing Register Update | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Document Number of drawing is incorrect, requested to resubmit-KPTG-SADV-004354 |  | 2026-05-18 | KPTG-SADV-004354 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-18 | D&E-TRANSMIT-000717 | NA | Trade Partner | Functional Description - Issued for Construction | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with the revision format |  | 2026-05-18 | KPTG-SADV-005432 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-18 | ECBS-TRANSMIT-000021 | NA | Trade Partner | Techdata Stratopanel for approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-18 | WF-001064 | NA | 2026-05-22 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-003781 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-18 | ECBS-TRANSMIT-000020 | NA | Trade Partner | Tech data for Access Panel & Versilux for approval | 0 | 2 | 0 | NA | APPROVED | 2026-05-18 | WF-001065 | NA | 2026-05-22 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-003831 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-18 | D&E-TRANSMIT-000718 | NA | Trade Partner | VSDs - Issued for Construction | 0 | 1 | 0 | NA | REJECTED | [5 empty] | IFC submitted for IFA. |  | 2026-05-18 | KPTG-SADV-005433 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-17 | RDSBIM-TRANSMIT-000007: | NA | Trade Partner | GREYSTAR ¦ GROUND FLOOR DOWEL BAR KEYPLAN AND SET OUT PLAN | 2 | 0 | 0 | NA | APPROVED | 2025-12-17 | WF-000112 | 220 | 2025-12-19 |  |  |  | 2026-01-16 | KPTG-TRANSMIT-000414 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-18 | D&E-TRANSMIT-000719 | NA | Trade Partner | AC Split Systems - Issued for construction | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Wrong revision number. |  | 2026-05-18 | KPTG-SADV-005434 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-18 | D&E-TRANSMIT-000720 | NA | Trade Partner | Fans - Issued for Construction | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Wrong revision number. |  | 2026-05-18 | KPTG-SADV-005435 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-18 | D&E-TRANSMIT-000714 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - LEVEL 1 - BUILDERS WORKS LAYOUTS - ZONES 1 | 6 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 3241 | 2026-05-27 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-017648 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-18 | SMEPS-TRANSMIT-000288 | NA | Trade Partner | SME - IFC Drawings-#3244 | 4 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 3244 | 2026-05-28 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-017701 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-18 | ADP-TRANSMIT-000315 | NA | Consultant | Fwd: ADP MEL4780 M3 Stage 1 & 4 - Office Fitout Return Brief | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-05-18 | KPTG-TRANSMIT-017486 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-18 | NXT-TRANSMIT-001559 | NA | Consultant | M3 Stage 4 FER- | 0 | 1 | 0 | NA | APPROVED | 2026-05-18 | 0 | 3247 | 2026-05-28 |  | As instructed by Jan V- Terminated |  | 2026-08-03 | KPTG-IntCorr-017169 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-18 | TTW-TRANSMIT-000184 | NA | Consultant | M3 Stage 2 Civil Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 4210 | 2026-05-20 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-018111 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-18 | RDSBIM-TRANSMIT-000270 | NA | Trade Partner | NXM3S4 ROOF SWITCH ROOM BAFFLE LAYOUT AND ELEVATION | 2 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 3250 | 2026-06-03 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-017748 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-18 | D&E-TRANSMIT-000721 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - INDUSTRIAL WATER SCHEMATIC | 1 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 4212 | 2026-05-25 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-017881 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-18 | ZIA-TRANSMIT-000086 | NA | Trade Partner | Final (WF-005464) S2 I TECH DATA I CONSULTANT REVIEW ¦PENSTOCK CONTROL PANEL | 1 | 0 | 0 | NA | APPROVED | 2026-05-11 | WF-005641 | NA | 2026-05-18 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-017524 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-01 | KETE-TRANSMIT-000014 | NA | Trade Partner | PMU Comparison Report | 0 | 1 | 0 | NA | APPROVED | 2025-12-02 | N/A | 671 | 2025-12-08 |  |  | 2025-12-12 | 2025-12-12 | KPTG-TRANSMIT-002267 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-18 | Stowe-A-TRANSMIT-000592 | NA | Trade Partner | Stowe - Tech Data - IFC - COMMS RACK & PDU | 0 | 1 | 0 | NA | APPROVED | [5 empty] | IFC TD, Distribution only. | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-017528 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-18 | Tradetec-TRANSMIT-000448 | NA | Trade Partner | Sitewide - TD - Penaflow GP Grout | 0 | 1 | 0 | NA | APPROVED | 2026-05-18 | WF-005745 | NA | 2026-05-25 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-017964 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-18 | Entire M-TRANSMIT-000039 | NA | Trade Partner | Battery Room Exhaust Fan Electrical Schematics IFA Rev C | 4 | 0 | 0 | NA | APPROVED | 2026-05-18 | WF -000421 | NA | 2026-05-25 |  | NA | 2026-05-27 | 2026-05-27 | KPTG-TRANSMIT-000910 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-18 | SMEPS-TRANSMIT-000215 | NA | Trade Partner | SME Sample for review | 0 | 1 | 0 | NA | APPROVED | 2026-05-18 | WF - 000422 | NA | 2026-05-25 |  | NA | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000896 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-18 | Entire M-TRANSMIT-000041 | NA | Trade Partner | Mechanical roof shop drawings | 4 | 0 | 0 | NA | APPROVED | 2026-05-18 | WF - 000424 | NA | 2026-05-25 |  | NA | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-000877 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-18 | SMEPS-TRANSMIT-000216 | NA | Trade Partner | SME Samples for review | 0 | 1 | 0 | NA | APPROVED | 2026-05-18 | WF - 000425 | NA | 2026-05-25 |  | NA | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000895 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-18 | RDSBIM-TRANSMIT-000199 | NA | Trade Partner | 511SRC ¦ LEVEL 11 TOWER A PARTITION LAYOUT (L11 to L13 TYPICAL) | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Distribution only. |  | 2026-05-18 | KPTG-TRANSMIT-002982 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-18 | RDSBIM-TRANSMIT-000002 | NA | Trade Partner | GROUND FLOOR CONCRETE PROFILE PLAN, LOADING DOCK DETAILS AND SECTIONS | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | closed out by Originator |  | 2026-05-18 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-16 | Tradetec-TRANSMIT-000308 | NA | Trade Partner | IFC - Stage 2 - HVP08, HVP10, LVP6, CP13 | 4 | 0 | 0 | NA | APPROVED | 2025-12-16 | NA | 3521 | 2025-12-28 |  |  | 2025-12-17 | 2025-12-17 | KPTG-TRANSMIT-011030 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-18 | RDSBIM-TRANSMIT-000200 | NA | Trade Partner | 511SRC ¦ LEVEL 11 TOWER B PARTITION WALL LAYOUT | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Distribution only. |  | 2026-05-18 | KPTG-TRANSMIT-002979 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-18 | RDSBIM-TRANSMIT-000201 | NA | Trade Partner | 511SRC ¦ LEVEL 12 TOWER B PARTITION WALL LAYOUT | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Distribution only |  | 2026-05-18 | KPTG-TRANSMIT-002978 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-18 | NXT-TRANSMIT-000373 | NA | Client | M3 Stage 6 - SCG IFT 3 | 69 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 115 | 2026-05-25 |  |  | 2026-05-27 | 2026-05-27 | NA | Closed | 69 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-18 | RDSBIM-TRANSMIT-000202 | NA | Trade Partner | 511SRC ¦ LEVEL 13 TOWER B PARTITION WALL LAYOUT (L13 & L14 TYPICAL) | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Distribution only. |  | 2026-05-18 | KPTG-TRANSMIT-002976 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-18 | RDSBIM-TRANSMIT-000203 | NA | Trade Partner | 511SRC ¦ LEVEL 14 TOWER A PARTITION WALL LAYOUT (L14 & L15 TYPICAL) | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Distribution only. |  | 2026-05-18 | KPTG-TRANSMIT-002977 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-18 | WilsonPD-TRANSMIT-000109 | NA | Trade Partner | Tech Data for Rain Re-Use Pumps For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-18 | WF - 001023 | NA | 2026-05-25 |  | NA | 2026-06-04 | 2026-06-04 | DRAFT-018575 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-18 | POTTSENG-TRANSMIT-000042 | NA | Trade Partner | GMAC HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONE 1 LAYOUT | 1 | 0 | 0 | NA | APPROVED |  | NA | 992 | 2026-05-26 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-002296 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-18 | Auspan-TRANSMIT-000293 | NA | Trade Partner | Precast fish plate for approval. | 0 | 1 | 0 | KPTG-IntCorr-000586 | APPROVED |  | NA | NA |  |  | Action taken by Kapitol PC - KPTG-TRANSMIT-001899 |  | 2026-05-20 | KPTG-TRANSMIT-001899 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-18 | Rinco-TRANSMIT-000048 | NA | Consultant | RL2 to L5 Reinforcement plans | 28 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 988 | 2026-05-26 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-001929 | Closed | 28 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-18 | JCBa-TRANSMIT-000114 | NA | Trade Partner | New Architectural Documentation - Joinery Schedules | 9 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 990 | 2026-05-26 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-002003 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2025-12-17 | RLA-TRANSMIT-000239 | NA | Consultant | External Levels - Preston Laneway - SETOUT CLARIFICATION | 2 | 0 | 0 | NA | APPROVED | 2025-12-17 | NA | 566 | 2025-12-24 |  |  | 2025-12-18 | 2025-12-18 | KPTG-TRANSMIT-002528 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-18 | Auspan-TRANSMIT-000294 | NA | Trade Partner | Precast shop drawings for construction. | 57 | 0 | 0 | Auspan-TRANSMIT-000294 | APPROVED |  | NA | NA |  |  | Pre Cast IFC - 2 Rejected drawings included KPTG-IntCorr-000587 Precast IFC registered and distributed. KPTG-TRANSMIT-001958 |  | 2026-05-21 | KPTG-TRANSMIT-001958 | Closed | 57 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-18 | Auspan-TRANSMIT-000295 | NA | Trade Partner | Resubmit precast shop drawings for approval. | 68 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | All deleted drawings must be clearly marked as 'Deleted' on the PDF drawing sheets -KPTG-SADV-002539 |  | 2026-05-18 | KPTG-SADV-002539 | Closed | 68 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-18 | WSP ANZ-TRANSMIT-000074 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit - CSMS | 26 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 905 | 2026-05-22 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-003321 | Closed | 26 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-18 | WSP ANZ-TRANSMIT-000074 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit - Electrical | 66 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 906 | 2026-05-22 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-003321 | Closed | 66 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-18 | WSP ANZ-TRANSMIT-000074 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit - FIP | 61 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 907 | 2026-05-22 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-003321 | Closed | 61 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-18 | WSP ANZ-TRANSMIT-000074 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit - Fuel | 10 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 908 | 2026-05-22 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-003321 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-18 | WSP ANZ-TRANSMIT-000074 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit - Mechanical | 37 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 909 | 2026-05-22 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-003321 | Closed | 37 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-18 | WSP ANZ-TRANSMIT-000074 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit - Telecom | 45 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 911 | 2026-05-22 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-003321 | Closed | 45 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-18 | WSP ANZ-TRANSMIT-000074 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit - vertical Transport | 7 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 912 | 2026-05-22 |  |  | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-003321 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-18 | DLTS-TRANSMIT-000006 | NA | Trade Partner | S9-Cooling tower HD bolts-IFA Issue | 3 | 0 | 0 | NA | APPROVED | 2026-05-18 | WF-00071 | NA | 2026-05-25 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-003726 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-17 | crossfir-TRANSMIT-000044 | NA | Trade Partner | Wet Fire - Level 04 South Tower , IFC | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-18 | Eneraque-TRANSMIT-000016 | NA | Trade Partner | Updated Line List | 0 | 1 | 0 | NA | APPROVED | 2026-05-18 | WF-000715 | NA | 2026-05-28 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-004464 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-18 | VIA Arch-TRANSMIT-000132 | NA | Consultant | BUILDING PERMIT ISSUE 15.05.2026 | 43 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 886 | 2026-05-20 |  |  | 2026-05-18 | 2026-05-18 | KPTG-TRANSMIT-003249 | Closed | 43 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-18 | Tradetec-TRANSMIT-000135 | NA | Trade Partner | Civil Stormwater Site Plan IFC | 1 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 901 | 2026-05-21 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-003730 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-18 | VAE-Grp-TRANSMIT-000163 | NA | Trade Partner | MECHANICAL - CMP & MCS FD | 0 | 2 | 0 | KPTG-IntCorr-001299 | APPROVED |  | NA | NA |  |  | Aconex register update for further distribution - 1 doc re-issued VAE-TRA-164 |  | 2026-05-19 | KPTG-TRANSMIT-003891 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-19 | LNCPPL-TRANSMIT-000008 | NA | Trade Partner | HYDRAULIC SERVICES - IN GROUND ONLY FLOOR PLANT AREA | 2 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | 236 | 2026-05-25 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000631 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-19 | RDSBIM-TRANSMIT-000015 | NA | Trade Partner | MEL11C45 ¦ PARTITION WALL LAYOUT L02 COLO5B | 3 | 0 | 0 | NA | APPROVED | 2026-05-19 | WF-000243 | NA | 2026-05-25 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-000803 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-19 | KPTG-IntCorr-000419 | NA | Client | Approved RIOP drawings | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Distributed to SME | 2026-05-19 | 2026-05-19 | KPTG-TRANSMIT-000886 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-19 | RDSBIM-TRANSMIT-000017 | NA | Trade Partner | MEL11C45 ¦ PARTITION WALL LAYOUT L01 COLO4 COLO5A | 3 | 0 | 0 | NA | APPROVED | 2026-05-19 | WF-000244 | NA | 2026-05-25 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-000781,KPTG-TRANSMIT-000791 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-19 | LNCPPL-TRANSMIT-000009 | NA | Trade Partner | ELECTRICAL SERVICES INGROUND ONLY PLANT AREA | 1 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | 238 | 2026-05-25 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000635 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-19 | RDSBIM-TRANSMIT-000016 | NA | Trade Partner | MEL11C45 ¦ PARTITION WALL LAYOUT L01 COLO4 COLO5A | 3 | 0 | 0 | NA | REJECTED | 2026-05-19 |  |  |  |  | RDS HAS INSTRUCTED TO REJECT THIS TRANSMIT:KPTG-IntCorr-000417 |  | 2026-05-19 | KPTG-IntCorr-000417 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-11 | Ardon-TRANSMIT-000016 | NA | Trade Partner | FRAMES - LEVEL 06, 07, 08 & 09 - Shop Drawings | 40 | 0 | 0 | NA | APPROVED | 2025-12-17 | WF-000842 | NA | 2025-12-24 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-18 | procore -TRANSMIT -305 | 305 | Trade Partner | Earthing report Rev 3 | 0 | 1 | 0 | NA | APPROVED | 2026-05-19 | NA | NA |  |  | Aconex register update |  | 2026-05-19 | KPTG-TRANSMIT-003729 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-18 | procore -TRANSMIT -306 | 306 | Trade Partner | PDU Drawings | 9 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | NA |  |  | Aconex register update |  | 2026-05-19 | KPTG-TRANSMIT-003732 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-18 | procore -TRANSMIT -307 | 307 | Trade Partner | PTU DC supply - As Built Drawings | 60 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | NA |  |  | Aconex register update |  | 2026-05-19 | KPTG-TRANSMIT-003733 | Closed | 60 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-18 | procore -TRANSMIT -308 | 308 | Trade Partner | HVSB - As Built Drawings. | 16 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | NA |  |  | Aconex register update |  | 2026-05-19 | KPTG-TRANSMIT-003734 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-19 | ZIA-TRANSMIT-000087 | NA | Trade Partner | M3S4 Resubmit Sample data sheet | 0 | 1 | 0 | NA | APPROVED | 2026-05-19 | WF-005746 | NA | 2026-06-01 |  |  |  | 2026-07-10 | KPTG-TRANSMIT-019568 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-19 | HGP-TRANSMIT-000057 | NA | Trade Partner | Re: L1 INTERNAL DRAWINGS | 6 | 0 | 0 | KPTG-IntCorr-003025 | APPROVED | [5 empty] | Full pack submited |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-19 | PSGANZ-TRANSMIT-000005 | NA | Trade Partner | Technical data resubmissions | 0 | 3 | 0 | NA | APPROVED | 2026-05-19 | WF-000138 | NA | 2026-05-27 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-000985 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-19 | Nilsen3-TRANSMIT-000019 | NA | Trade Partner | Fibre Optic Pigtails OM4 re-submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-19 | WF-000722 | NA | 2026-05-29 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-003715 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-05-19 | SMPS-TRANSMIT-000116 | NA | Trade Partner | Switchboard Modifications on D08-00-DB-02 | 0 | 1 | 0 | NA | APPROVED | 2026-05-19 | WF-000493 | NA | 2026-05-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-05-19 | SMPS-TRANSMIT-000117 | NA | Trade Partner | Electrical Tech Data - IFI | 0 | 1 | 0 | NA | APPROVED | 2026-05-19 | WF-000494 | NA | 2026-05-27 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-11 | Ardon-TRANSMIT-000016 | NA | Trade Partner | FRAMES - LEVEL 06, 07, 08 & 09 - Shop Drawings | 40 | 0 | 0 | NA | APPROVED | 2025-12-17 | WF-000843 | NA | 2025-12-24 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-19 | Arco-TRANSMIT-000004 | NA | Trade Partner | ARCO ROLLER SHUTTERS AND GATES | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status inside the title block and in history block seem different History block is not inside the Title block |  | 2026-05-19 | KPTG-TRANSMIT-000887 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-19 | Entire M-TRANSMIT-000051 | NA | Trade Partner | Mechanical drawings - 1:100 scale | 11 | 0 | 0 | NA | APPROVED | 2026-05-19 | WF-000245 | NA | 2026-05-22 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-000670 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-19 | Entire M-TRANSMIT-000052 | NA | Trade Partner | Mechanical - drawing index IFA | 1 | 0 | 0 | NA | APPROVED | 2026-05-19 | WF-000246 | NA | 2026-05-25 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-000790 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-18 | INGEN3D-TRANSMIT-000079 | NA | Trade Partner | Level 2 - CD157 & PC427 - New IFA | 3 | 0 | 0 | NA | APPROVED | 2026-05-18 | WF-000544 | NA | 2026-05-27 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-001900 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-18 | INGEN3D-TRANSMIT-000080 | NA | Trade Partner | Level 9-11 - Precast Columns - IFA | 66 | 0 | 0 | NA | APPROVED | 2026-05-18 | WF-000547 | NA | 2026-05-26 |  |  | 2026-06-26 | 2026-06-01 | KPTG-TRANSMIT-002062 | Closed | 66 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-18 | TTW-TRANSMIT-000160 | NA | Consultant | Updated Civil Design & Stormwater | 8 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 633 | 2026-05-28 |  | 2 Drawings rejected and processed in TTW-TRANSMIT-000163 |  |  |  | Open | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-18 | RDSBIM-TRANSMIT-000036 | NA | Trade Partner | GROUND FLOOR TO LEVEL 06 LIFT CORE 1 CONCRETE PROFILE PLAN AND SECTIONAL ELEVATIONS | 3 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 586 | 2026-05-21 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-001897 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-18 | PCForm-TRANSMIT-000189 | NA | Trade Partner | Aitken Freeman - Granobond Sample submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-18 | WF-000549 | NA | 2026-05-27 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-001915 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-19 | ETNInd-TRANSMIT-000016 | NA | Trade Partner | Eaton Samsung Battery Cabinets BIM Model - Rev 1 | 0 | 1 | 0 | NA | APPROVED | 2026-05-19 | WF-000247 | NA | 2026-05-20 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-000706 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-11 | Ardon-TRANSMIT-000016 | NA | Trade Partner | FRAMES - LEVEL 06, 07, 08 & 09 - Shop Drawings | 26 | 0 | 0 | NA | APPROVED | 2025-12-17 | WF-000844 | NA | 2025-12-24 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-18 | PCForm-TRANSMIT-000188 | NA | Trade Partner | ULW Concrete patching mortar submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-18 | WF-000550 | NA | 2026-05-27 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-001916 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-18 | PCForm-TRANSMIT-000191 | NA | Trade Partner | Keratrade Self leveller | 0 | 1 | 0 | NA | APPROVED | 2026-05-18 | WF-000551 | NA | 2026-05-27 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-001918 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-19 | Appselec-TRANSMIT-000101 | NA | Trade Partner | Commissioning Manual Docs IFA | 0 | 5 | 0 | NA | APPROVED | 2026-05-19 | WF-000248 | NA | 2026-05-25 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-000688 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-19 | Appselec-TRANSMIT-000100 | NA | Trade Partner | MEL11C45 TELECOM LABELLING SCHEDULE - Issued For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-19 | WF-000249 |  | 2026-05-25 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-000767 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-19 | Appselec-TRANSMIT-000102 | NA | Trade Partner | Commissioning Manual Docs No Longer In Use | 0 | 5 | 0 | NA | APPROVED |  | NA | NA |  |  | Documents are no longer in use. updated document register:KPTG-IntCorr-000421 |  | 2026-05-19 | KPTG-IntCorr-000421 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-19 | ETNInd-TRANSMIT-000020 | NA | Trade Partner | EATON Samsung Battery Cabinet updated BIM Model | 1 | 0 | 0 | NA | APPROVED | 2026-05-19 | WF - 000727 | NA | 2026-05-25 |  | NA | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-000889 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-19 | Danlai-TRANSMIT-000001 | NA | Trade Partner | Technical Data | 0 | 7 | 0 | NA | REJECTED | [5 empty] | Error in Document revision, No coversheet, PDF naming to be corrected. |  | 2026-05-19 | DRAFT-002057 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-19 | NXT-TRANSMIT-001560 | NA | Trade Partner | M3 Stage 2 Protection Study LV SCCS Report IFCN-6 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Only update and distribute as per Fabian. |  | 2026-05-19 | KPTG-TRANSMIT-017556 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-19 | ADP-TRANSMIT-000317 | NA | Consultant | ADP MEL4561 - PDU Whip Calculation Report & Cabling and Busduct Calculation | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | For information, Distribution only. |  | 2026-05-19 | KPTG-TRANSMIT-017558 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-16 | KPTG-TRANSMIT-010960 | NA | Trade Partner | Joinery Shop Drawings - Entrance Office | 4 | 0 | 0 | NA | APPROVED | 2025-12-16 | NA | 3523 | 2025-12-22 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-19 | Appselec-TRANSMIT-000099 | NA | Trade Partner | ROIP Pack IFC | 0 | 1 | 0 | NA | APPROVED | 2026-05-19 | WF-000250 | NA | 2026-05-22 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-000667 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-19 | RDSBIM-TRANSMIT-000003 | NA | Trade Partner | GROUND FLOOR CONCRETE PROFILE PLAN ¦ BLOCK 2 | 4 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | 117 | 2026-05-27 |  |  | 2026-06-10 | 2026-06-11 | KPTG-TRANSMIT-000184 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-19 | D&E-TRANSMIT-000723 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - GROUND - CHW PIPE LAYOUT - ZONES 3,5 & 7 | 3 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | 3260 | 2026-05-28 |  | As requested by Ellie — Terminated — KPTG-IntCorr-013787 |  | 2026-05-26 | KPTG-IntCorr-013787 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-19 | SMEPS-TRANSMIT-000290 | NA | Trade Partner | SME - MSSB Control Schematic Drawing | 4 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | 3255 | 2026-06-04 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-021028 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-19 | SMEPS-TRANSMIT-000291 | NA | Trade Partner | SME - MSSB Shop Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | 3426 | 2026-06-03 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-19 | IVS-TRANSMIT-000365 | NA | Trade Partner | STR - Ground Floor Steel Stairs (Certification Issue) | 2 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | 3286 | 2026-06-04 |  | WF 3262 TERMINATED | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-018107 | Open | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-19 | PARR-TRANSMIT-000180 | NA | Trade Partner | Re: P2680 - NDC M3 Stage 4 - Fuel - BF RETIC LAYOUT & SECTIONS | 12 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED DUE INCORRECT STATUS |  | 2026-05-19 | KPTG-RFI-007992 | Closed | 12 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-16 | Tradetec-TRANSMIT-000309 | NA | Trade Partner | Tech Data - Site Wide - Titan Premix Stabilised Sand | 0 | 1 | 0 | NA | APPROVED | 2025-12-16 | WF-003637 | NA | 2025-12-23 |  |  | 2026-01-21 | 2026-01-21 | KPTG-IntCorr-007802 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-19 | D&E-TRANSMIT-000724 | NA | Trade Partner | ISSUED FOR CONSTRUCTION - GROUND - BUILDERS WORKS LAYOUTS - ZONE 5 & 6 | 2 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | 3264 | 2026-05-28 |  | As requested by Ellie — Terminated — KPTG-IntCorr-013787 |  | 2026-05-26 | KPTG-IntCorr-013787 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-19 | PARR-TRANSMIT-000181 | NA | Trade Partner | NDC M3 Stage 4 - Enclosures - FUEL SCHEMATIC | 1 | 0 | 0 | NA | APPROVED | 2026-05-19 | WF-005753 | NA | 2026-06-03 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-018255 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-18 | Rinco-TRANSMIT-000012 | NA | Trade Partner | Level 4 - Updated drawings with sections | 11 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 673 | 2026-06-01 |  | locked PCF drawings from Rincowitch-KPTG-SADV-002331 | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-002086 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-19 | Auspan-TRANSMIT-000072 | NA | Trade Partner | 9P02 shop drawing issued for construction | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-000977 - AS per instruction from Ashlin, documents are updated into document register only and transmitted to all parties. | 2026-05-19 | 2026-05-19 | KPTG-IntCorr-000977 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-19 | fjc-TRANSMIT-000148 | NA | Trade Partner | Architecturals - Level 05 CPP | 1 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | 655 | 2026-05-22 |  |  | 2026-05-20 | 2026-05-20 | KPTG-SADV-004220 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-19 | ARCST-TRANSMIT-000290 | NA | Trade Partner | C3 South Roof - Stair 7 Issued for Approval | 29 | 0 | 0 | 0 | APPROVED | 2026-05-20 | WF-005758 | NA | 2026-06-10 |  | 14-DOCS PENDING currently under review | 2026-07-31 | 2026-07-31 | KPTG-TRANSMIT-020263 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-19 | Hames-TRANSMIT-000159 | NA | Consultant | Updated Door Hardware Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-05-19 | NA | 1274 |  |  |  | 2026-08-05 | 2026-08-06 | KPTG-TRANSMIT-004212 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-19 | Hames-TRANSMIT-000160 | NA | Consultant | PHASE 1 - FIRE TANK HARDSTAND & STAIR 05 | 10 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | 1276 | 2026-05-21 |  | Terminated 2 dwgs from the DC review by Kapitol hence made void | 2026-06-04 | 2026-06-04 | ACC Review 1281 | Closed | 10 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-19 | WilsonPD-TRANSMIT-000045 | NA | Trade Partner | Containerised Industrial Water Treatment Plant Tech Data | 0 | 1 | 0 | NA | APPROVED | 2026-05-19 | WF-000719 | NA | 2026-05-28 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-003530 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-19 | BBC P.-TRANSMIT-000010 | NA | Trade Partner | Sample Forms resubmitted | 0 | 2 | 0 | NA | APPROVED | 2026-05-19 | WF-000720 | NA | 2026-05-22 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-003629 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-16 | Civilex-TRANSMIT-000014 | NA | Trade Partner | Pile Shop Drawing_Pile Cage F | 1 | 0 | 0 | KPTG-IntCorr-000173 | APPROVED | 2025-12-18 | WF-000085 | NA | 2025-12-20 |  | REJECTED DRAWING- CLOSE OUT DELAYED - NEW DRAWING ISSUED VIA CIVILEX-TRAN#25 | 2026-01-21 | 2026-02-13 | KPTG-TRANSMIT-000439 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-19 | BBC P.-TRANSMIT-000013 | NA | Trade Partner | Sample Forms Armawall system. Primer and Armashield | 0 | 2 | 0 | NA | APPROVED | 2026-05-19 | WF-000721 | NA | 2026-05-22 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-003625 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-19 | Nilsen3-TRANSMIT-000018 | NA | Trade Partner | Nilsen Fibre Samples IFC | 0 | 4 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC Samples, No review required. Updated and Distributed |  | 2026-05-19 | KPTG-TRANSMIT-003299 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-19 | Auspan-TRANSMIT-000300 | NA | Trade Partner | Precast shop drawings for approval. | 2 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | 994 | 2026-05-26 |  | Terminated | 2026-06-11 | 2026-06-11 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-19 | Auspan-TRANSMIT-000298 | NA | Trade Partner | Precast shop drawings for construction. | 8 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC - update Register and distribute; No review required: KPTG-TRANSMIT-001903 |  | 2026-05-19 | KPTG-TRANSMIT-001903 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-19 | POTTSENG-TRANSMIT-000044 | NA | Trade Partner | GMAC HYDRAULIC SERVICES - PENETRATION - LEVEL 01 - ZONE 1-5 LAYOUTS | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Review required; Register and distribute - KPTG-TRANSMIT-001911 |  | 2026-05-19 | KPTG-TRANSMIT-001911 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-19 | Auspan-TRANSMIT-000299 | NA | Trade Partner | Auspan-TRANSMIT-000299 Deleted shop drawings | 16 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | 997 | 2026-05-26 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-002190 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-19 | JCBa-TRANSMIT-00011 | NA | Consultant | 5 Updated Architectural Documentation - FF&E Schedule | 0 | 1 | 0 | NA | APPROVED | 2026-05-19 | WF-000508 | NA | 2026-05-26 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-19 | Auspan-TRANSMIT-000302 | NA | Trade Partner | Precast shop drawings for approval | 1 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | 1001 | 2026-05-27 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-002131 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-19 | RDSBIM-TRANSMIT-000060 | NA | Trade Partner | GREYSTAR GROUND FLOOR CONCRETE PROFILE PLAN ZONE 2 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required; Register and distribute - KPTG-TRANSMIT-001909 |  | 2026-05-19 | KPTG-TRANSMIT-001909 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-19 | Auspan-TRANSMIT-000295 | NA | Trade Partner | Resubmit precast shop drawings for approval | 52 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | 999 | 2026-05-27 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-002193 | Closed | 52 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-01 | SKS Tech-TRANSMIT-000096 | NA | Trade Partner | BASEMENT AND GROUND FLOOR IFC LAYOUTS - ELECTRICAL | 7 | 0 | 0 | NA | APPROVED | 2025-12-02 | N/A | 681 | 2025-12-04 |  | 3 tel drawings in review 683 | 2025-12-03 | 2025-12-05 | KPTG-TRANSMIT-002172 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-17 | Civilex-TRANSMIT-000015 | NA | Trade Partner | Sample Submission - Concrete Mix Design | 0 | 1 | 0 | NA | APPROVED | 2025-12-17 | WF-000082 | NA | 2025-12-20 |  |  | 2026-01-20 | 2026-01-20 | KPTG-TRANSMIT-000295 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-19 | RDSBIM-TRANSMIT-000061 | NA | Trade Partner | GREYSTAR LEVEL 01 CONCRETE PROFILE PLAN AND SECTION ZONE 1, 2, 3, 4 | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Review, Update Register and distribute KPTG-TRANSMIT-001922 |  | 2026-05-19 | KPTG-TRANSMIT-001922 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-19 | Auspan-TRANSMIT-000301 | NA | Trade Partner | Precast shop drawings for construction. | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC - update Register and distribute; No review required KPTG-TRANSMIT-001917 |  | 2026-05-19 | KPTG-TRANSMIT-001917 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-19 | POTTSENG-TRANSMIT-000045 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - DRAINAGE - BASEMENT 1 - ZONE 3-5 LAYOUTS | 3 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | 1006 | 2026-05-27 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-002350 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-19 | POTTSENG-TRANSMIT-000046 | NA | Trade Partner | GMAC HYDRAULIC SERVICES - PENETRATION - GROUND - ZONE 1 LAYOUT | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC No review required; Register and distribute - KPTG-TRANSMIT-001920 |  | 2026-05-19 | KPTG-TRANSMIT-001920 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-19 | KETE-TRANSMIT-000020 | NA | Trade Partner | Kete - Zone 01 & 02 Shop Drawing Submission Rev _IFC A | 210 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | 1010 | 2026-05-27 |  | Review Voided as advised by Kapitol PC | 2026-06-16 | 2026-06-16 | NA | Closed | 210 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-19 | JCBa-TRANSMIT-000116 | NA | Consultant | JCBa-TRANSMIT-000116: Updated Architectural Documentation - Overall Plans, GA Plans & Apartment Type Plans | 82 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | 1012 | 2026-05-21 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-002036 | Closed | 82 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-19 | SMEPS-TRANSMIT-000263 | NA | Trade Partner | Electrical Functional Description | 0 | 1 | 0 | NA | APPROVED | 2026-05-19 | 1004 | NA | 2026-05-26 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-19 | ADP-TRANSMIT-000045 | NA | Consultant | ADP MEL4834 - Cabling and Busduct Calculation & PDU Whip Calculation | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | Distribution only-IFC |  | 2026-05-19 | Awaiting approval | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-19 | D&E-TRANSMIT-000363 | NA | Trade Partner | SFN - Flow Verification ITP - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Distribution only |  | 2026-05-19 | Awaiting approval | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-19 | Highbu-TRANSMIT-000148 | NA | Trade Partner | Stage 2 IFA drawings & status update | 4 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | 253 | 2026-05-22 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-003082 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-17 | Altaire-TRANSMIT-000028 | NA | Trade Partner | Altaire- DH11 Handover Documentation | 10 | 0 | 0 | NA | APPROVED | [5 empty] | As-Built, No review required. Updated and distributed to the Project Team. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-19 | TGRF-TRANSMIT-000114 | NA | Trade Partner | Fwd: IVPT26036 - Stage 2 IFA Plans | 47 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | ISSUED FOR KAPITOL INFORMATION:KPTG-SADV-004368 |  | 2026-05-19 | KPTG-SADV-004368 | Closed | 47 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-19 | Madigan-TRANSMIT-000004 | NA | Trade Partner | Transmit of Stage 2 Survey Control Plan documents | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Document number of drawing is incorrect: KPTG-SADV-004373 |  | 2026-05-19 | KPTG-SADV-004373 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-19 | RDSBIM-TRANSMIT-000067 | NA | Trade Partner | 671CHP BASEMENT 1 CONCRETE PROFILE PLAN | 3 | 0 | 0 | KPTG-IntCorr-000574 | APPROVED |  | NA | 504 | 2026-05-25 |  | waiting for Kapitol PC Choi to advise - KPTG-IntCorr-000574 Review voided; Review voided; RDS to update and supersede the drawings. | 2026-06-05 | 2026-06-05 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-19 | Jangho-TRANSMIT-000061 | NA | Trade Partner | L3~18 shop drawing Rev00 | 75 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | 502 | 2026-05-28 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-001119 | Closed | 75 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-19 | LGCE-TRANSMIT-000030 | NA | Trade Partner | Security shop drawings | 13 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect drawing number + multiple sheets in same PDF. KPTG-IntCorr-000571 |  | 2026-05-19 | KPTG-IntCorr-000571 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-20 | VERTIV-TRANSMIT-000012 | NA | Trade Partner | NEXT DC GE 01_ MATERIAL SUBMISSION_ BATTERY & UPS (FOA-2) | 0 | 2 | 0 | NA | APPROVED | 2026-05-20 | WF-000139 | NA | 2026-05-28 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-000783 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-20 | VERTIV-TRANSMIT-000013 | NA | Trade Partner | NEXT DC GE 01 _ CALCULATION SUBMISSION _ ELECTRICAL LOAD MAXIMUM DEMAND CALCULATION AND CABLE SIZING & VOLTAGE DROP CALCULATION (FOA-2) | 0 | 2 | 0 | NA | APPROVED | 2026-05-20 | WF-000140 | NA | 2026-05-28 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-000729 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-04-30 | INTRFRM-TRANSMIT-000028 | NA | Trade Partner | Tech Data Submission - Floor Boxes & Earthbridges | 0 | 1 | 0 | NA | APPROVED | 2026-04-30 | WF-000099 | NA | 2026-05-08 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-000582 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-20 | KPTG-IntCorr-000389 | NA | Client | SOCFOC RADIO GENERAL REQUIREMENTS | 1 | 0 | 0 | NA | APPROVED |  | NA | NA | 2026-05-20 |  | Approved drawings sent to SME for Issue IFC. |  | 2026-05-20 | KPTG-TRANSMIT-000890 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-20 | RDSBIM-TRANSMIT-000047 | NA | Trade Partner | MWYCCB ¦ LEVEL 01 PARTITION WALL KEY PLAN AND LAYOUT | 5 | 0 | 0 | NA | REJECTED | [5 empty] | The drawing status inside the drawing and in Aconex seem different. Date : 19/5/2026 |  | 2026-05-20 | KPTG-TRANSMIT-000888 | Closed | 5 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-17 | TTW-TRANSMIT-000062 | NA | Consultant | Structural set - issued for certification | 51 | 0 | 0 | NA | APPROVED | 2025-12-17 | NA | 156 | 2025-12-19 |  |  | 2025-12-19 | 2025-12-19 | DRAFT-002280 | Closed | 51 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-20 | ADP-TRANSMIT-000318 | NA | Consultant | ADP MEL4780 - M3S4 LV SCCS Report | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-05-20 | KPTG-TRANSMIT-017584 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-20 | RDSBIM-TRANSMIT-000048 | NA | Trade Partner | MWYCCB ¦ GROUND FLOOR PARTITION WALL KEY PLAN AND LAYOUT | 5 | 0 | 0 | NA | REJECTED | [5 empty] | The drawing status inside the drawing and in Aconex seem different. Date : 19/5/2026 |  | 2026-05-20 | KPTG-TRANSMIT-000889 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-20 | SMEPS-TRANSMIT-000213 | NA | Trade Partner | MEL05C4 Load Bank Plan_B | 0 | 1 | 0 | NA | APPROVED | 2026-05-20 | WF - 000428 | NA | 2026-05-27 |  | NA | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-000939 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-20 | SMEPS-SUBADVICE-000157 | NA | Trade Partner | SME Startup & Energisation Plan | 0 | 1 | 0 | NA | APPROVED | 2026-05-20 | WF - 000429 | NA | 2026-05-20 |  | NA | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-000936 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-20 | Arco-TRANSMIT-000005 | NA | Trade Partner | ARCO Roller SHUTTERS AND GATES | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status inside the drawing and in Aconex seem different |  | 2026-05-20 | KPTG-TRANSMIT-000890 | Closed | 9 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-20 | INTRFRM-TRANSMIT-000055 | NA | Trade Partner | Re: Geelong Edge - Structural Tech Data (Submission 7) - Bondek Alternative | 0 | 1 | 0 | NA | APPROVED | 2026-05-20 | WF-000141 | NA | 2026-06-01 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000622 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-20 | Stowe-A-TRANSMIT-000593 | NA | Trade Partner | Stowe - Tech Data - IFC - X1 External Lighting Light Poles | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC TD, Distribution only. |  | 2026-05-20 | KPTG-TRANSMIT-017593 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-19 | TTW-TRANSMIT-000161 | NA | Consultant | TTW Civil - DWG CAD AND MODEL | 14 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | cad - register updated |  | 2026-05-19 | NA | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-19 | TTW-TRANSMIT-000162 | NA | Consultant | BP4 - Issued for Construction Update | 45 | 0 | 0 | NA | APPROVED | 2026-05-19 | NA | 588 | 2026-05-22 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-001954 | Closed | 45 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-19 | WAM-TRANSMIT-000769 | NA | Consultant | DETAIL - FACADE APARTMENT VENTILATION UPDATE | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-002082 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2025-12-17 | TTW-TRANSMIT-000063 | NA | Consultant | Structural set - issued for Construction | 55 | 0 | 0 | NA | APPROVED | 2025-12-17 | NA | 158 | 2025-12-19 |  |  | 2025-12-19 | 2025-12-19 | KPTG-TRANSMIT-000260 | Closed | 55 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-20 | ADP-TRANSMIT-000319 | NA | Consultant | ADP MEL4561 - Lighting Reports by Area/Zone | 0 | 6 | 0 | NA | APPROVED |  | NA | NA |  |  | For Information, Distribution only. |  | 2026-05-20 | KPTG-TRANSMIT-017598 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-19 | VAE-Grp-TRANSMIT-000164 | NA | Trade Partner | NXD1S2 - IFC - MECH - MCS Functional Description - Rev Correction | 0 | 1 | 0 | KPTG-IntCorr-001306 | APPROVED |  | NA | NA |  |  | Aconex register update for further distribution KPTG-IntCorr-001306 |  | 2026-05-19 | KPTG-TRANSMIT-003894 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-20 | NXT-TRANSMIT-001568 | NA | Trade Partner | M3S4 Ring 1 & 2 L1 check reports (x9 units) | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-05-20 | KPTG-TRANSMIT-017604 | Open | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-20 | Tradetec-TRANSMIT-000449 | NA | Trade Partner | Re: IFA - Stage 4 - HVP22, 23, 24, 25, 26, 35 | 6 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect Revision |  | 2026-05-20 | KPTG-RFI-008022 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-20 | WilsonPD-TRANSMIT-000193 | NA | Trade Partner | Upadated Hydraulic Roof Level - Zone A & B - Drainage & Water Layout | 2 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-05-20 | KPTG-TRANSMIT-000896 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-20 | Entire M-TRANSMIT-000049 | NA | Trade Partner | Fwd: Seismic Drawings Issued for Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-05-20 | KPTG-TRANSMIT-017608 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-20 | Rinco-TRANSMIT-000052 | NA | Consultant | L6 and Roof GA | 2 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 1023 | 2026-05-27 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-002033 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-20 | WilsonPD-TRANSMIT-000194 | SPARK-CRFI-KPG-000511 | Trade Partner | Updated Level 1 Penetration Layout | 1 | 0 | 0 | NA | APPROVED | 2026-05-20 |  | 284 | 2026-05-27 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000920 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-01 | PSGANZ-TRANSMIT-000001 | NA | Trade Partner | Technical Data submissions | 0 | 7 | 0 | NA | APPROVED | 2026-05-01 | WF-000105 | NA | 2026-05-11 |  |  | 2026-05-20 | 2026-05-20 | KPTG-TRANSMIT-000613 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-20 | D&E-TRANSMIT-000725 | NA | Trade Partner | Louvres - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-20 | WF-005761 | NA | 2026-06-15 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-019649 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-17 | Nilsen3-TRANSMIT-000123 | NA | Trade Partner | Nilsen As-built Drawings | 33 | 0 | 0 | NA | APPROVED | [5 empty] | As-Built, No review required. Updated and distributed to the Project Team. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-20 | SMEPS-TRANSMIT-000217 | NA | Trade Partner | SME Shop Drawing Telecomunications IFC B | 1 | 0 | 0 | NA | APPROVED | 2026-05-20 | WF - 000430 | NA | 2026-05-20 |  | Termnated | 2026-05-20 | 2026-05-20 | NA | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-20 | SMEPS-TRANSMIT-000218 | NA | Trade Partner | Approved ROIP Drawings – SOCFOC RADIO GENERAL REQUIREMENTS | 1 | 0 | 0 | NA | APPROVED | 2026-05-20 | WF - 000431 | NA | 2026-05-25 |  | NA | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000894 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-20 | D&E-TRANSMIT-000729 | NA | Trade Partner | Damer Actuators - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-20 | WF-005762 | NA | 2026-06-16 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018474 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-20 | ZIA-TRANSMIT-000090 | NA | Trade Partner | M3S2 SLA Sensors layout | 6 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 4216 | 2026-05-25 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-018830 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-20 | D&E-TRANSMIT-000728 | NA | Trade Partner | NXM3S4 - Ground - CHW Pipe Layout - Zone 9 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 3272 | 2026-05-29 |  | As requested by Ellie — Terminated — KPTG-IntCorr-013787 |  | 2026-05-26 | KPTG-IntCorr-013787 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-20 | Nilsen3-TRANSMIT-000158 | NA | Trade Partner | GVK/ Raychem 300mm 500mm Straight Terminations | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect reference number |  | 2026-05-20 | KPTG-RFI-008027 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-20 | Auscool-TRANSMIT-000036 | NA | Trade Partner | Riser IFA Shop drawings | 5 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 1029 | 2026-05-27 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-002506 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-05-20 | SMPS-TRANSMIT-000118 | NA | Trade Partner | Electrical Switchboard Tech Data - IFC | 0 | 1 | 0 | NA | APPROVED | 2026-05-20 | WF-000495 | NA | 2026-05-28 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-20 | WAM-TRANSMIT-000772 | NA | Consultant | A02_Demoliton IFC updates | 2 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 594 | 2026-05-22 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-20 | Altaire-TRANSMIT-000108 | NA | Trade Partner | M3 S2 SP5 - Altaire - OP Documentation | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected drawings are submitted As builts. |  | 2026-05-20 | KPTG-SADV-005488 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-17 | Nilsen3-TRANSMIT-000124 | NA | Trade Partner | Nilsen Seismic Drawings - As-built and Certifications | 11 | 0 | 0 | NA | APPROVED | [5 empty] | As-Built, No review required, Distributed to the Project Team. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-20 | Civilex-TRANSMIT-000246 | NA | Trade Partner | Sample Submission - Stage 1 - Concrete Curing Compound (Fosroc-Concure-CR) | 0 | 1 | 0 | NA | APPROVED | 2026-05-20 | WF-005767 | NA | 2026-05-26 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018402 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-20 | VERTIV-TRANSMIT-000014 | NA | Trade Partner | NEXT DC GE01 _ MATERIAL SUBMISSION _ FIRE SUPPRESSION AND DETECTION SYSTEM (FOA-1) | 0 | 1 | 0 | NA | REJECTED | [5 empty] | As per Michael De Filippo, the proposed items need to be changed to be compatible with fire system installed by the Fire Service Trade Partner (Premier Services Group). |  | 2026-05-20 | KPTG-SADV-000456 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-20 | WAM-TRANSMIT-000771 | NA | Consultant | A12 CSP - Level 1 to Level 5 - Issue for Construction | 10 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 596 | 2026-05-22 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-20 | GEMBA-D-TRANSMIT-000021 | NA | Consultant | Steelwork structural drawings - Issued for Construction | 4 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 240 | 2026-05-25 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000618 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-20 | SMEPS-IntCorr-000244 | NA | Trade Partner | Request for ZTN BOM Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-20 | WF - 000432 | NA | 2026-05-27 |  | NA | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-000904 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-20 | Danlai-TRANSMIT-000002 | NA | Trade Partner | Technical Data | 0 | 7 | 0 | NA | REJECTED | [5 empty] | Issue with Revision number. |  | 2026-05-20 | KPTG-SADV-000454 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-20 | JCBa-TRANSMIT-000245 | NA | Consultant | LEVEL 03 BTR - ISSUE FOR CONSTRUCTION | 11 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update register only |  | 2026-05-20 | NA | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-20 | WGAVIC-TRANSMIT-000010 | NA | Consultant | Civil Drawings IFC | 5 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 242 | 2026-05-25 |  |  | 2026-05-27 | 2026-05-27 | KPTG-TRANSMIT-000688 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-20 | INTRFRM-TRANSMIT-000056 | NA | Trade Partner | Re: Geelong Edge - Roof Slab Post Tensioning Shop Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-05-20 | WF-000144 | NA | 2026-06-01 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000627 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-20 | ECBS-TRANSMIT-000042 | NA | Trade Partner | Re: O&M NDC M3 Stage 2 SP5_For Approval | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-05-20 | KPTG-RFI-008011 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-18 | ARCST-TRANSMIT-000160 | NA | Trade Partner | C1 Switchroom Upper Gantry Grating - Issued for Fabrication | 154 | 0 | 0 | NA | APPROVED | 2025-12-18 | WF-003659 / WF-003687 | NA | 2026-01-08 |  | One drawing has been closed out – NXT-WTRAN-001623 |  | 2026-02-02 | KPTG-TRANSMIT-012209,KPTG-TRANSMIT-012366 | Closed | 154 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-20 | SKS Tech-TRANSMIT-000142 | NA | Trade Partner | Resubmit lighting control for roof | 3 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 3268 | 2026-06-03 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-019381 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-20 | WAM-TRANSMIT-000774 | NA | Consultant | A14 and A75 Series Issued for construction | 26 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 598 | 2026-05-23 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-20 | Tradetec-TRANSMIT-000450 | NA | Trade Partner | IFA - Stage 4 - CP 28, CP38 | 2 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 3497 | 2026-05-20 |  |  |  | 2026-06-25 | KPTG-TRANSMIT-019058 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-20 | D&E-TRANSMIT-000726 | NA | Trade Partner | IW Pumps - Issued for Approva | 0 | 1 | 0 | NA | APPROVED | 2026-05-20 | WF-005760 | NA | 2026-05-21 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-019151 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-20 | CRSol-TRANSMIT-000087 | NA | Trade Partner | RS HAC Drawings - Issued for Construction - Zone C2, Rev C. | 18 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 3274 | 2026-06-03 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-20 | FNSTR8-TRANSMIT-000015 | NA | Trade Partner | Re: M3 S4 - Stage 4 Facade Additional Sample | 0 | 1 | 0 | NA | APPROVED | 2026-05-20 | WF-005768 | NA | 2026-06-11 |  |  |  | 2026-06-15 | KPTG-TRANSMIT-018632 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-20 | ARCST-TRANSMIT-000291 | NA | Trade Partner | Re: C1 Chiller Skid Supports - Issued for Construction | 18 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect drawing and status |  | 2026-05-20 | KPTG-RFI-008033 | Closed | 18 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-21 | KETE-TRANSMIT-000131 | NA | Trade Partner | Submission – data sheet for GL04 Fritted glass | 0 | 1 | 0 | NA | APPROVED | 2026-05-21 | WF-000764 | NA | 2026-06-01 |  | KPTG-IntCorr-000981- PENDING ASHLIN CREATED THE WF - WF-000764 KPTG-IntCorr-001068 - As per direction from Ashlin, we terminate the workflow.(Reason - Another sample to be submitted in its place) | 2026-06-15 |  | KPTG-IntCorr-001068 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-19 | Omnii-TRANSMIT-000002 | NA | Consultant | Re: Fire Engineering Performance-Based Design Brief Revision B | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-05-20 | DRAFT-000771 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-20 | ARCH-TRANSMIT-000150 | NA | Consultant | Fwd: MLC - SPR - FFE Schedule C04 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC SCHEDULE DOCUMENT-TRANSMITTED TO ALL CONCERNED:KPTG-TRANSMIT-002871 |  | 2026-05-20 | KPTG-TRANSMIT-002871 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-18 | Auspan-TRANSMIT-000036 | NA | Trade Partner | Revised Mezzanine shop drawings issued for approval | 4 | 0 | 0 | NA | APPROVED | 2025-12-18 |  | 497 | 2025-12-25 |  |  | 2025-12-19 | 2025-12-19 | KPTG-SADV-002547 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-20 | Auspan-TRANSMIT-000296 | NA | Trade Partner | CIP detail clarification | 1 | 1 | 0 | NA | APPROVED | 2026-05-20 | WF-000518 | 1025 | 2026-05-27 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-002139 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-20 | Rinco-TRANSMIT-000049 | NA | Consultant | L6 to Roof reo and PT | 84 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 1014 | 2026-05-22 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-002030 | Closed | 84 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-20 | Auspan-TRANSMIT-000303 | NA | Trade Partner | Precast shop drawings for approval | 65 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 1016 | 2026-05-28 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-002309 | Closed | 65 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-20 | Auspan-TRANSMIT-000304 | NA | Trade Partner | Re GF PANELS MISSING IFC - Transmit by midday | 1 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | NA |  |  | Precast IFC - update Register and distribute; No review required |  | 2026-05-20 | KPTG-TRANSMIT-001933 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-20 | Auspan-TRANSMIT-000305 | NA | Trade Partner | Re CIP detail clarification | 3 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 1018 | 2026-05-28 |  | 1 drawing updated | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-002269 | Closed | 3 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-20 | Auspan-TRANSMIT-000306 | NA | Trade Partner | IFC panel 0G1011 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC - update Register and distribute; No review required KPTG-TRANSMIT-001939 |  | 2026-05-20 | KPTG-TRANSMIT-001939 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-20 | Rinco-TRANSMIT-000051 | NA | Trade Partner | L1 to L5 reo and PT drawings | 140 | 0 | 0 | KPTG-IntCorr-000598 | APPROVED |  | NA | 1041 | 2026-05-26 |  | Found Drawings with No previous revisions; waiting for advice from M-Harris KPTG-IntCorr-000598 M. Harris confirmed it is ok to proceed as it is a drawing split. ACC#1041 | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-002049 | Closed | 140 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-20 | Auscool-TRANSMIT-000035 | NA | Trade Partner | Level 01 - IFA Shop Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 1027 | 2026-05-28 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-002503 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-20 | Auspan-TRANSMIT-000307 | NA | Trade Partner | GF PANELS MISSING IFC - Transmit by midday | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC - update Register and distribute; No review required KPTG-TRANSMIT-001942 |  | 2026-05-20 | KPTG-TRANSMIT-001942 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-20 | Auspan-TRANSMIT-000308 | NA | Trade Partner | Re L2 Z5 STAIR CORE - Missing Panel | 4 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 1031 | 2026-05-28 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-002181 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-17 | KETE-TRANSMIT-000107 | NA | Trade Partner | Submission – Updated tower horizontal details. | 7 | 0 | 0 | NA | APPROVED | [5 empty] | Duplicate files. File Superseded | 2025-12-17 | 2025-12-17 | CLOSED | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-20 | crossfir-TRANSMIT-000013 | NA | Trade Partner | Wet Fire - Basement 04 to 01 , IFA | 3 | 0 | 0 | KPTG-IntCorr-000578 | APPROVED | 2026-05-21 | NA | ACC#506 | 2026-05-28 |  | Tayla to advise: KPTG-IntCorr-000578 Review voided for trade partner to update the shop drawings. |  | 2026-05-21 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-20 | Best-TRANSMIT-000011 | NA | Consultant | Signage update for DDA requirements | 17 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status of documents are incorrect, requested to resubmit¦:KPTG-SADV-004385 |  | 2026-05-20 | KPTG-SADV-004385 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-20 | SES AU-TRANSMIT-000036 | NA | Trade Partner | Security- Cable Containment - Substitution Tech Data Rev 3 | 0 | 9 | 0 | NA | REJECTED | [5 empty] | Rejected:Tec data with older version of covering sheet:KPTG-IntCorr-000436 |  | 2026-05-20 | KPTG-IntCorr-000436 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-20 | SES AU-TRANSMIT-000035 | NA | Trade Partner | Security-Typical shop drawings from Stage 1 | 31 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status of drawings has not been mentioned in the Title Bloc, requested to resubmit:KPTG-IntCorr-000437 |  | 2026-05-20 | KPTG-IntCorr-000437 | Closed | 31 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-18 | VAE-Grp-TRANSMIT-000163 | NA | Trade Partner | MECHANICAL - CMP & MCS FD | 0 | 1 | 0 | NA | REJECTED | [5 empty] | rejected : revision error |  | 2026-05-18 | KPTG-TRANSMIT-003730 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-26 | NXT-TRANSMIT-000376 | NA | Client | M3 Stage 6 - Preliminary BCA Report | 0 | 1 | 0 | KPTG-IntCorr-000101 | APPROVED |  | NA | NA |  |  | Actual submission date 20-05-2026-Distributed to all team |  | 2026-05-25 | KPTG-TRANSMIT-000112 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-21 | KPTG-TRANSMIT-000093 | NA | Trade Partner | Safetech Shop Drawings & Updates | 8 | 0 | 0 | KPTG-IntCorr-000102 | APPROVED | 2026-05-21 | NA | 119 | 2026-05-29 |  | Actual submission date-20-05-2026 | 2026-06-03 | 2026-06-04 | KPTG-IntCorr-000102 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-21 | KPTG-TRANSMIT-000089 | NA | Trade Partner | Safetech Specifications | 0 | 4 | 0 | KPTG-IntCorr-000103 | APPROVED | 2026-05-21 | NA | 121 | 2026-05-29 |  | Actual submission date-20-05-2026-Voided |  | 2026-05-22 | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-20 | D&E-TRANSMIT-000365 | NA | Trade Partner | FD, System arch & Panel drawings - As built | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | Distribution only |  | 2026-05-20 | Awaiting approval | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-20 | SMEPS-TRANSMIT-000042 | NA | Trade Partner | Earthing Cables-Rev03 | 0 | 1 | 0 | NA | APPROVED | 2026-05-20 | WF-000733 | NA | 2026-06-01 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-003710 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-18 | INGEN3D-TRANSMIT-000676 | N/A | Trade Partner | I3D-378 Next DC M3 Stage 4 - Ground Floor Fuel Tanks - Precast Panels - Batch 1 - IFC (17-12-2025) | 18 | 0 | 0 | NA | APPROVED | [5 empty] | Oliver - Hi Shahir, we need to close out the workflow formally, please hold fire on transmitting these thanks |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-20 | SMEPS-TRANSMIT-000043 | NA | Trade Partner | SME Single + Multi Core Fr Rated Cable Sample Submissions for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-20 | WF-000734 | NA | 2026-06-01 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-003704 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-20 | WGAVIC-TRANSMIT-000121 | NA | Consultant | M2 - Stage 10 Level 1 Slab - Issued for Construction | 5 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 925 | 2026-05-25 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-003136 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-20 | WGAVIC-TRANSMIT-000122 | NA | Consultant | M2 - Concrete Details - Issued for Construction | 3 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 929 | 2026-05-25 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-003189 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-20 | WGAVIC-TRANSMIT-000123 | NA | Consultant | M2 - Stage 11 Level 2 Slab - Issued for Certification | 10 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 931 | 2026-05-25 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-003192 | Closed | 10 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-20 | WSP ANZ-TRANSMIT-000077 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit (Hydraulic Documents) | 57 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 943 | 2026-05-27 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-004106 | Closed | 57 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-20 | VIA Arch-TRANSMIT-000133 | NA | Consultant | BUILDING PERMIT DRAWINGS from Friday (15.05.26) | 6 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 917 | 2026-05-25 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-003214 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-20 | VIA Arch-TRANSMIT-000135 | NA | Consultant | M2 S9 Finishes Plan & Interior Finish Schedule Amendment | 3 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 919 | 2026-05-25 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-003237 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-20 | VIA Arch-TRANSMIT-000136 | NA | Consultant | Stage 10 L1 Wall Rationalisation Update | 1 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 921 | 2026-05-25 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-003511 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-20 | VIA Arch-TRANSMIT-000137 | NA | Consultant | Architecture - S9 Waterproof Package | 8 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 923 | 2026-05-25 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-003515 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-20 | VIA Arch-TRANSMIT-000139 | NA | Consultant | M2 Loading Dock Concrete Profile Plan Amendment | 1 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 933 | 2026-05-25 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-003520 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-02 | KPTG-TRANSMIT-010517 | NA | Trade Partner | New Workflow L01 Z08 | 67 | 0 | 0 | NA | APPROVED | 2025-12-02 | WF-003467 | NA | 2025-12-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-17 | D&E-TRANSMIT-000295 | NA | Trade Partner | L1 CORRIDOR AC LAYOUT (V-017) - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2025-12-18 | NA | 1327 | 2025-12-24 |  |  | 2026-01-06 | 2026-01-06 | KPTG-TRANSMIT-002259 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-20 | ELLISAIR-TRANSMIT-000027 | NA | Trade Partner | NextDC M2 S9 L1 Duct and Pipe drawings issued for Approval (Drawing Nos. amended). | 4 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 935 | 2026-05-27 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-003542 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-20 | Eneraque-TRANSMIT-000018 | NA | Trade Partner | Fuel Supply RO Datasheet & Pumping Hydraulic Calculation | 0 | 2 | 0 | NA | APPROVED | 2026-05-20 | WF-000735 | NA | 2026-06-01 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-003850 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-20 | Arc Plas-TRANSMIT-000005 | NA | Trade Partner | Updated Tech Data Submissions | 0 | 8 | 0 | NA | APPROVED | 2026-05-20 | WF-000737 | NA | 2026-05-27 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-003652 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-21 | Auspan-TRANSMIT-000101 | NA | Trade Partner | Re: Precast marking plans and elevations for approval. Coen Precast. | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect document Number & Title bloc are not fully mentioned:KPTG-SADV-004389 |  | 2026-05-21 | KPTG-SADV-004389 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-20 | ZIA-TRANSMIT-000054 | NA | Trade Partner | Cx Level 2 Commissioning Test Documents | 0 | 10 | 0 |  | APPROVED | 2026-05-21 | WF-001071 | NA | 2026-05-26 |  | Harry to confirm KPTG-IntCorr-001313 | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-003789 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-21 | SKS Tech-TRANSMIT-000144 | NA | Trade Partner | ELC-SKS-SA-C-0400-0016 Lighting Control Gear | 0 | 1 | 0 | NA | APPROVED | 2026-05-21 | WF-005771 | NA | 2026-06-16 |  | Status revise and resubmit | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-018845 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-21 | RDSBIM-TRANSMIT-000018 | NA | Trade Partner | MEL11C45 ¦ LEVEL 02 COLO 4 AREA RCP LAYOUT | 6 | 0 | 0 | NA | APPROVED | 2026-05-21 | WF-000252 | NA | 2026-05-26 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000676 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-20 | SWIFEN-TRANSMIT-000001 | NA | Trade Partner | Fencing for Review | 3 | 0 | 0 | NA | APPROVED | 2026-05-20 | WF-001070 | NA | 2026-05-26 |  |  | 2026-06-12 | 2026-06-12 | KPTG-TRANSMIT-003907 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-20 | BG&E Fac-TRANSMIT-000005 | NA | Trade Partner | F3P1 Performance Solution Report | 0 | 1 | 0 | NA | APPROVED | 2026-05-20 | WF-001069 | NA | 2026-05-25 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-003940 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-21 | Detail-TRANSMIT-000007 | NA | Trade Partner | Re: DOOR HARDAWRE SCHEDULE | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect details |  | 2026-05-21 | KPTG-RFI-008040 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-18 | IVS-TRANSMIT-000302 | NA | Consultant | Stage 4 - Upper Walkway Switchroom Steelwork Zone C2 & C3 (Construction Issue) | 25 | 0 | 0 | NA | APPROVED | 2025-12-18 | NA | 1690 | 2025-12-22 |  |  |  | 2026-01-15 | KPTG-TRANSMIT-011467 | Closed | 25 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-21 | RDSBIM-TRANSMIT-000049 | SPARK-CRFI-KPG-000178 | Trade Partner | RDSBIM-TRANSMIT-000049 | 1 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 285 | 2026-05-28 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-000928 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-21 | Omnii-TRANSMIT-000003 | NA | Consultant | FIRE ENGINEERING PERFORMANCE BASED DESIGN BRIEF | 0 | 1 | 0 | KPTG-IntCorr-000139 | APPROVED | 2026-05-22 | NA | 137 | 2026-05-27 |  | No Comments - Discussed in meetings and Aconex, Up rev required. Distribution not required as advised. |  | 2026-05-22 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-21 | RDSBIM-TRANSMIT-000019 | NA | Trade Partner | MEL11C45 ¦ LEVEL 01 COLO 5A & LEVEL 02 COLO 5B AREA RCP LAYOUT | 6 | 0 | 0 | NA | APPROVED | 2026-05-21 | WF-000253 | NA | 2026-05-26 |  |  | 2026-05-21 | 2026-05-21 | KPTG-TRANSMIT-000679 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-21 | D&E-TRANSMIT-000731 | NA | Trade Partner | Sanitary Ball and Butterfly Valves Technical Data - Issued for Construction | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-05-21 | KPTG-TRANSMIT-017624 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-21 | D&E-TRANSMIT-000732 | NA | Trade Partner | Fwd: Variable Speed Drives - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-05-21 | KPTG-TRANSMIT-017625 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-21 | RDSBIM-TRANSMIT-000037 | NA | Trade Partner | GROUND FLOOR TO LEVEL 09 STAIR/LIFT CORE 02 CONCRETE PROFILE PLAN SECTION AND ELEVATION | 3 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 600 | 2026-05-23 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-001986 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-21 | Danlai-TRANSMIT-000003 | NA | Trade Partner | Technical Data | 0 | 5 | 0 | NA | APPROVED | 2026-05-21 | WF-000145 | NA | 2026-05-29 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-000832 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-21 | Arco-TRANSMIT-000006 | SPARK-CRFI-KPG-000694 | Trade Partner | ARCO roller shutters and gates | 9 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 286 | 2026-05-28 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-001458 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-20 | WAM-TRANSMIT-000770 | NA | Consultant | Common Areas 80%DD | 34 | 0 | 0 | NA | APPROVED | 2026-05-20 | NA | 593 |  |  | 25 processed - 9 No longer in use. | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-002204 | Closed | 25 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-20 | WAM-TRANSMIT-000773 | NA | Consultant | A00 A01 A03 A04 Issue for construction | 5 | 0 | 0 | NA | REJECTED | [5 empty] | COVERSHEET IS NOT MENTIONED WITH DOCUMENT NUMBER OR REVISION |  | 2026-05-20 | KPTG-TRANSMIT-001905 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-18 | NXT-TRANSMIT-001153 / EAEGROUP-TRANSMIT-000050 | NA | Trade Partner | EAE Busduct (5000A / 2000A) – Flange Connection Shop Drawing | 2 | 0 | 0 | NA | APPROVED | 2025-12-18 | WF-003664 | NA | 2026-01-05 |  |  |  | 2026-01-27 | NXT-WTRAN-001587 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-21 | CRSol-TRANSMIT-000008 | NA | Trade Partner | M2S11 - CRS Ceiling Drawings for Approval - II | 13 | 0 | 0 | NA | APPROVED | 2026-05-21 | WF-000743 | 948 | 2026-05-28 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-004986 | Closed | 13 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-21 | Nilsen3-TRANSMIT-000160 | NA | Trade Partner | Re: Stage 2 ROPS 2C & 2D | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Different document number and wrong revision number. |  | 2026-05-21 | KPTG-SADV-005498 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-21 | ADP-TRANSMIT-000320 | NA | Trade Partner | Functional Description for control of Penstock Valves | 0 | 1 | 0 | NA | APPROVED | 2026-05-21 | WF-005873 | NA | 2026-06-05 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018354 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-21 | SES AU-TRANSMIT-000037 | NA | Trade Partner | Re: Security- Cable Containment - Substitution Tech Data Rev 4 | 0 | 9 | 0 | NA | APPROVED | 2026-05-22 | WF-000257 | NA | 2026-05-28 |  |  |  | 2026-05-22 | KPTG-SADV-000802 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-21 | VERTIV-TRANSMIT-000015 | NA | Trade Partner | Vertiv CRAC Submittals & Coordination | 2 | 1 | 0 | NA | REJECTED | [5 empty] | Error in document number, revision, template, file types, mixed status. |  | 2026-05-21 | KPTG-SADV-000464 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-21 | ECBS-TRANSMIT-000043 | NA | Trade Partner | Fan Wall Unit Steel - Revised Drawings For Approval (Batch 3: 25 drawings) | 25 | 0 | 0 | NA | APPROVED | 2026-05-21 | WF-005781 | NA | 2026-06-24 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-21 | D&E-TRANSMIT-000736 | NA | Trade Partner | Security Fixings - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-21 | WF-005788 | NA | 2026-06-16 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-018028 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-21 | D&E-TRANSMIT-000733 | NA | Trade Partner | Heat Exchangers - IFC | 0 | 1 | 0 | NA | APPROVED | [5 empty] | IFC TD, Distribution only |  | 2026-05-21 | KPTG-TRANSMIT-017636 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-21 | ZIA-TRANSMIT-000093 | NA | Trade Partner | M3S2 CSMS Device Register | 0 | 1 | 0 | NA | APPROVED | [5 empty] | IFC REG, Update register only. |  | 2026-05-21 | KPTG-TRANSMIT-017641 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-21 | D&E-TRANSMIT-000737 | NA | Trade Partner | BMS Switches & Panels - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-21 | WF-005783 | NA | 2026-06-16 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-019009 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2025-12-18 | PFP PL-TRANSMIT-000015 | NA | Trade Partner | Wet Fire As Builts | 5 | 0 | 0 | NA | APPROVED | [5 empty] | As-Builts, No review required. Distributed to the Project Team. |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-20 | VAE-Grp-TRANSMIT-000165 | NA | Trade Partner | NXD1S2 - IFI - MECH SECTION 40 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001315 - Harry to confirm-No action required |  | 2026-06-11 | KPTG-IntCorr-001440 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-21 | PARR-TRANSMIT-000183 | NA | Trade Partner | Re: P2685 - NDC M3 - Stage 4 - Battery Rooms - BATTERY ROOM ENCLOSURE ITP | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Revision not mentioned inside the document |  | 2026-05-21 | KPTG-RFI-008048 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-21 | Civilex-TRANSMIT-000247 | NA | Trade Partner | Southern Retaining Wall Rev K | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected as there is a mismatch in revision number. |  | 2026-05-21 | KPTG-SADV-005500 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-21 | D&E-TRANSMIT-000734 | NA | Trade Partner | Heat Exchangers - IFC | 0 | 1 | 0 | NA | APPROVED | [5 empty] | IFC TD, Distribution only. |  | 2026-05-21 | KPTG-TRANSMIT-017642 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-21 | D&E-TRANSMIT-000735 | NA | Trade Partner | FD - Fans, Split Systems - IFC | 0 | 3 | 0 | NA | APPROVED | [5 empty] | IFC TD, Distribution only. |  | 2026-05-21 | KPTG-TRANSMIT-017645 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-21 | Nilsen3-TRANSMIT-000163 | NA | Trade Partner | Stage 2 ROPS 2C & 2D | 0 | 1 | 0 |  | APPROVED | 2026-05-22 | WF-005794 | NA | 2026-06-05 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-019288 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-21 | INTRFRM-TRANSMIT-000058 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 8) | 0 | 4 | 0 | NA | APPROVED | 2026-05-21 | WF-000146 | NA | 2026-06-02 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-21 | D&E-TRANSMIT-000739 | NA | Trade Partner | NXM3S4 - Level 1 - CHW Pipe Layout - Zone 6 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 3283 | 2026-05-30 |  | As requested by Ellie — Terminated — KPTG-IntCorr-013787 |  | 2026-05-26 | KPTG-IntCorr-013787 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-21 | Civilex-TRANSMIT-000248 | NA | Trade Partner | Stage 1 Swale Restoration Landscape Plan Revision E | 1 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 4220 | 2026-05-28 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018431 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-21 | WAM-TRANSMIT-000775 | NA | Consultant | A19 and A50 | 33 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 602 | 2026-05-25 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-17 | Inhabit-TRANSMIT-000009 | NA | Consultant | Updated Section J Report | 1 | 0 | 0 | NA | APPROVED | 2025-12-17 | WF-000658 | 770 | 2025-12-17 |  |  | 2025-12-18 | 2025-12-18 | KPTG-TRANSMIT-002317 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-21 | ADP-TRANSMIT-000072 | NA | Consultant | ADP MEL4680 - COMMS Specification | 0 | 1 | 0 | NA | APPROVED | 2026-05-21 | NA | 248 | 2026-05-26 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-000682 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-21 | ASV-TRANSMIT-000176 | NA | Trade Partner | Hydraulic Sample - Asset Labels | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Error in document number and Revision. |  | 2026-05-21 | KPTG-SADV-005504 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-21 | D&E-TRANSMIT-000740 | NA | Trade Partner | Fwd: Water Filters - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | [5 empty] | IFC TECH DATA |  | 2026-05-21 | KPTG-TRANSMIT-017660 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-21 | ADP-TRANSMIT-000321 | NA | Consultant | ADP - CAN - Fire Water Storage | 0 | 1 | 0 | NA | APPROVED | [5 empty] | For information, Distibution only. |  | 2026-05-21 | KPTG-TRANSMIT-017662 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-21 | INTRFRM-TRANSMIT-000059 | NA | Trade Partner | Geelong Edge - Electrical Tech Data (Submission 5) | 0 | 2 | 0 | NA | APPROVED | 2026-05-21 | WF-000148 | NA | 2026-05-29 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-000711 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-21 | Detail-TRANSMIT-000002 | NA | Trade Partner | Lindrum - Tech Data Sheets | 0 | 10 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004253- THE DOCUMENT NO IS INCORRECT AND THE TITTLE INSIDE AND OUTSIDE DIFFERENT. | 2026-05-21 | 2026-05-21 | KPTG-SADV-004253 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-21 | KETE-TRANSMIT-000134 | NA | Trade Partner | Kete - L11 - L27 Cast in Channels Layout Drawings IFC | 17 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 656 | 2026-05-28 |  |  | 2026-06-17 | 2026-06-17 | KPTG-SADV-004558 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-21 | Altaire-TRANSMIT-000109 | NA | Trade Partner | Level 1 and Roof Zone Block Plans | 3 | 0 | 0 | NA | REJECTED | [5 empty] | No IFA, IFC submitted, Incorrect title block, Document number missing, history box missing. |  | 2026-05-21 | KPTG-SADV-005509 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-21 | SKS Tech-TRANSMIT-000192 | NA | Trade Partner | for APPROVAL submittal | 0 | 1 | 0 | NA | APPROVED | 2026-05-21 | WF-001072 | NA | 2026-05-27 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-003782 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-21 | Tradetec-TRANSMIT-000451 | NA | Trade Partner | IFA - Stage 4 - HVP22, 23, 24, 25, 26, 35-#3277 | 6 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 3379 | 2026-06-02 |  | AS PER REQUESTED BY THE CHARLI 2 DOC TERMINATED FOR UPDATING | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-018957 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-17 | Inhabit-TRANSMIT-000010 | NA | Consultant | NABERS Energy Rating Estimation Report | 0 | 1 | 0 | NA | APPROVED | 2025-12-17 | NA | 768 |  |  | VOID by Will Mason - expecting new revision | 2025-12-18 | 2025-12-18 | Inhabit-TRANSMIT-000011 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-21 | KPTG-TRANSMIT-017616 | NA | Trade Partner | Re: Leak Detection Technical Data - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | [5 empty] | ONLY FOR INFORM BODER TEAM |  | 2026-05-21 | KPTG-IntCorr-013581 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-22 | KETE-TRANSMIT-000132 | NA | Trade Partner | Kete - Podium and Tower Transition & Interfaces | 12 | 0 | 0 | NA | APPROVED | 2026-05-22 | WF-000763 | NA | 2026-05-26 |  | KPTG-IntCorr-000983 - PENDING ASHLIN CREATED THE WORK FLOW - WF-000763 | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-002610 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-21 | Nilsen3-TRANSMIT-000162 | NA | Trade Partner | Re: Ezyframe Sample IFC | 0 | 1 | 0 | NA | APPROVED | [7 empty] | 2026-05-21 | KPTG-TRANSMIT-017684 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-21 | D&E-TRANSMIT-000738 | NA | Trade Partner | NXM3S4 - Level 1 - CHW Pipe Layout - Zone 5 - Issued For Construction - | 1 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 3285 | 2026-06-04 |  | As requested by Ellie — Terminated — KPTG-IntCorr-013787 |  | 2026-05-26 | KPTG-IntCorr-013787 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-03-04 | SKS Tech-TRANSMIT-000163 | NA | Trade Partner | GENERAL DETAIL DRAWINGS & CABLE TRAY SCHEDULES ¦ IFA | 5 | 0 | 0 | NA | APPROVED | 2026-03-04 | NA | 1256 | 2026-03-12 |  |  | 2026-05-20 | 2026-05-21 | KPTG-TRANSMIT-003739 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-21 | KETE-TRANSMIT-000133 | NA | Trade Partner | Kete - Tower Cast-in Channels Layout Drawings IFC | 17 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004230 - THE REVISION NUMBER IS INCORRECT | 2026-05-21 | 2026-05-21 | KPTG-SADV-004230 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-21 | Auspan-TRANSMIT-000309 | NA | Trade Partner | Precast shop drawings for construction | 28 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | ifc - No Review required- update register and transmit - KPTG-TRANSMIT-001962 |  | 2026-05-21 | KPTG-TRANSMIT-001962 | Closed | 28 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-21 | PCForm-TRANSMIT-000195 | NA | Trade Partner | Raft 3 - Jumpform Drawings Package - Issued for Construction | 16 | 0 | 0 | KPTG-IntCorr-000717 | APPROVED | [5 empty] | Nicholas to confirm | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-001996 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-21 | PCForm-TRANSMIT-000196 | NA | Trade Partner | Raft 2 - Jumpform Drawings Package - Issued for Construction | 16 | 0 | 0 | KPTG-IntCorr-000718 | APPROVED |  | NA | 660 | 2026-05-29 |  | Nicholas to confirm | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-002020 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-21 | PCForm-TRANSMIT-000197 | NA | Trade Partner | Raft 2 & Raft 3 - Pour Sequence Issued for Construction | 2 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 615 | 2026-06-30 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-001948 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-18 | NXT-TRANSMIT-001152 / ETNInd-TRANSMIT-000075 | NA | Trade Partner | UPS Technical Data Submittal | 10 | 0 | 0 | NA | APPROVED | 2025-12-18 | WF-003665 | NA | 2026-01-05 |  |  |  | 2026-01-20 | NXT-WTRAN-001566 | Closed | 10 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-21 | JCBa-TRANSMIT-000117 | NA | Consultant | IFC_A-41 - Stair & Core Drawings | 7 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 1033 | 2026-05-28 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-002046 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-21 | INDS-TRANSMIT-000029 | NA | Trade Partner | Revised Peno Drawings - Ground to L7 | 8 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 1040 | 2026-05-26 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-002165 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-18 | Auspan-TRANSMIT-000294 | NA | Trade Partner | Precast shop drawings for construction. | 2 | 0 | 0 | KPTG-IntCorr-000587 | APPROVED |  | NA | NA |  |  | IFC- 2 Rejected drawings included KPTG-IntCorr-000587 - Drawings superseded. |  | 2026-05-18 | KPTG-IntCorr-000587 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-21 | POTTSENG-TRANSMIT-000016 | NA | Trade Partner | 671C HYDRAULIC SERVICES - BASEMENT 2 - WATER LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 509 | 2026-05-28 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-001106 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-21 | LGCE-TRANSMIT-000034 | NA | Trade Partner | Security drawings | 13 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 512 | 2026-05-28 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-001197 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-21 | LGCE-TRANSMIT-000035 | NA | Trade Partner | : NBN drawings | 23 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 514 | 2026-05-28 |  |  | 2026-06-27 | 2026-06-26 | KPTG-TRANSMIT-001199 | Closed | 23 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-21 | crossfir-TRANSMIT-000014 | NA | Trade Partner | Basement 04 to 01 | 4 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 516 | 2026-05-28 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001261 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-20 | crossfir-TRANSMIT-000013 | NA | Trade Partner | Wet Fire - Basement 04 to 01 , IFA | 1 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 507 | 2026-05-28 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-001082 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-17 | TCL-TRANSMIT-000002 | NA | Consultant | LANDSCAPE IFC DWGS | 11 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected QA Error |  | 2025-12-17 | KPTG-SADV-001936 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-21 | SMEPS-IntCorr-000193 | NA | Trade Partner | MEL05C4 BU Temp Power Plan | 0 | 1 | 0 | NA | APPROVED | 2026-05-21 | WF - 000433 | NA | 2026-05-26 |  | Terminated | 2026-05-26 | 2026-05-26 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-21 | JCBa-CADV-000673 | NA | Consultant | Storage Update to Drawing Set | 55 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Drawing No Mismatch, (DRAFT-018070) |  |  |  | Closed | 55 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-21 | ARCH-TRANSMIT-000151 | NA | Consultant | MLC - SPR - ISC - Capping Beam & Carpark North CPP | 2 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 255 | 2026-05-26 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-002889 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-21 | PFP PL-TRANSMIT-000004 | NA | Trade Partner | S9 Ground Floor IFA | 1 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 945 | 2026-05-26 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-003900 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-21 | PFP PL-TRANSMIT-000004 | NA | Trade Partner | S9 Ground Floor IFA | 0 | 1 | 0 | NA | APPROVED | 2026-05-21 | WF-000740 | NA | 2026-06-02 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-003677 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-21 | Nilsen3-TRANSMIT-000021 | NA | Trade Partner | Nilsen sample Elbow Terminations updated tech data . | 0 | 1 | 0 | NA | APPROVED | 2026-05-21 | WF-000741 | NA | 2026-06-02 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-003700 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-21 | W_TITE-TRANSMIT-000001 | NA | Trade Partner | Waterproofing TDS | 0 | 4 | 0 | NA | APPROVED | 2026-05-21 | WF-000744 | NA | 2026-05-26 |  |  | 2026-05-27 | 2026-05-27 | KPTG-TRANSMIT-003585 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-21 | WSP ANZ-TRANSMIT-000074 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit - CSMS (Aurecon Review) | 26 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 936 | 2026-05-27 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-004132 | Closed | 26 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-21 | WSP ANZ-TRANSMIT-000074 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit - ELC (Aurecon Review) | 66 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 937 | 2026-05-27 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-004084 | Closed | 66 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-21 | WSP ANZ-TRANSMIT-000074 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit - FIP (Aurecon Review) | 61 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 938 | 2026-05-27 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-004095 | Closed | 61 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-18 | Entire M-TRANSMIT-000024 | NA | Trade Partner | Fire Matrix Issued for Approval | 0 | 1 | 0 | NA | APPROVED |  | WF-003666 |  | 2025-12-31 |  |  |  |  | Terminated | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-21 | WSP ANZ-TRANSMIT-000074 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit - FUL (Aurecon Review) | 10 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 939 | 2026-05-27 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-004101 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-21 | WSP ANZ-TRANSMIT-000074 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit - MEC (Aurecon Review) | 37 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 940 | 2026-05-28 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-004136 | Closed | 37 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-21 | WSP ANZ-TRANSMIT-000074 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit - TEL (Aurecon Review) | 45 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 941 | 2026-05-28 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-005239 | Closed | 45 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-21 | WSP ANZ-TRANSMIT-000074 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit - VRT (Aurecon Review) | 7 | 0 | 0 | NA | APPROVED | 2026-05-21 | NA | 942 | 2026-05-28 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-005244 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-22 | RDSBIM-TRANSMIT-000038 | NA | Trade Partner | DISTLV ¦ GROUND FLOOR TO LEVEL 09 STAIR CORE 04 CONCRETE PROFILE PLAN AND SECTION ELEVATION | 3 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 604 | 2026-05-24 |  |  | 2026-05-25 | 2026-05-26 | KPTG-TRANSMIT-001966 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-22 | RDSBIM-TRANSMIT-000204 | NA | Trade Partner | LEVEL 03 EXTERNAL AREA CONCRETE PROFILE PLAN AND SECTIONS - RDSBIM-TRANSMIT-000204 | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Distribution only |  | 2026-05-22 | KPTG-TRANSMIT-002988 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-22 | KALLIBRE-TRANSMIT-000010 | NA | Trade Partner | Kallibre Door Frame Shop Drawings IFC Rev 2 | 43 | 0 | 0 | NA | APPROVED | 2026-05-22 | WF-000256 | NA | 2026-05-27 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-000727 | Closed | 43 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-22 | WAM-TRANSMIT-000776 | NA | Consultant | A41 | 2 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 606 | 2026-05-25 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-22 | Entire M-TRANSMIT-000005 | NA | Trade Partner | Fans & Roof Cowls - Technical Data Submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with document number and Revision number. |  | 2026-05-22 | KPTG-SADV-000473 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-18 | SMEPS-TRANSMIT-000127 | NA | Trade Partner | 22KV - Sample register and submittals | 0 | 1 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  | 2025-12-18 | NXT-WTRAN-001297 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-22 | NXT-TRANSMIT-001578 | NA | Trade Partner | Fwd: SO 611300382- M3 ST4 LVSB- FWT and routine test result (UMTD-FF-A and MSB+USB-FF) | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-05-22 | KPTG-TRANSMIT-017686 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-22 | Entire M-TRANSMIT-000006 | NA | Trade Partner | Grilles & Diffusers - Technical Data Submission | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with document number and revision. |  | 2026-05-22 | KPTG-SADV-000474 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-22 | D&E-TRANSMIT-000742 | NA | Trade Partner | NXM3S4 - Ground - CHW Pipe Layout - Zone 1 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 3290 | 2026-05-31 |  | As requested by Ellie — Terminated — KPTG-IntCorr-013787 |  | 2026-05-26 | KPTG-IntCorr-013787 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-30 | PARR-TRANSMIT-000172 | NA | Trade Partner | NDC M3 - Stage 4 - Battery Rooms - DSH & FIRE SPRINKLER SYSTEM | 0 | 1 | 0 | NA | APPROVED | 2026-04-30 | WF-005515 | NA | 2026-05-06 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-017691 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-22 | NXT-TRANSMIT-001581 | NA | Trade Partner | Fwd: Updated Revision of FI - FJ - FF - FG - UI - UJ and Loadbank | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-05-22 | KPTG-TRANSMIT-017687 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-22 | Entire M-TRANSMIT-000007 | NA | Trade Partner | Return Design Brief | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Error in Document number and revision. |  | 2026-05-22 | KPTG-SADV-000475 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-04-29 | Nilsen3-TRANSMIT-000122 | NA | Trade Partner | Updated Penetration Seal Material | 0 | 1 | 0 | NA | APPROVED | 2026-04-29 | WF-005485 | NA | 2026-05-05 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-017695 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-22 | M.S.-TRANSMIT-000064 | NA | Trade Partner | Shop Drawings for Approval | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Document number is incorrect, requested to resubmit:KPTG-SADV-004404 |  | 2026-05-22 | KPTG-SADV-004404 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-22 | VERTIV-TRANSMIT-000017 | NA | Trade Partner | NEXT DC GE 01_ MATERIAL SUBMISSION _ LV SWITCHBOARD (FOA-2) | 0 | 1 | 0 | NA | APPROVED | 2026-05-22 | WF-000149 | NA | 2026-06-01 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-000779 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-22 | NXT-TRANSMIT-001579 | NA | Trade Partner | Fwd: PDU Functional Description - Doc No Update | 0 | 1 | 0 | NA | APPROVED | [5 empty] | For information, update register only. |  | 2026-05-22 | KPTG-TRANSMIT-017696 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-01 | IVS-TRANSMIT-000286 | NA | Consultant | Stage 4 - Fuel Compound Construction Issue (Revised as clouded) | 11 | 0 | 0 |  | APPROVED | 2025-12-01 | NA | 1586 | 2025-12-03 |  |  |  | 2025-12-05 | KPTG-TRANSMIT-010665 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2025-12-18 | Altaire-TRANSMIT-000017 | NA | Trade Partner | Dry Fire Documents for DHA6-B Handover | 8 | 5 | 0 | NA | APPROVED | [5 empty] | No Review required, distributed to the Project Team. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-22 | Nilsen3-TRANSMIT-000164 | NA | Trade Partner | Re: Stage 3 ROPS 3A & 3B GA and Schematic diagrams | 0 | 1 | 0 | NA | REJECTED | [7 empty] | 2026-05-22 | KPTG-RFI-008067 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-22 | NXT-TRANSMIT-001583 | NA | Trade Partner | Fwd: Type test certificates for M3-22-HVSB-A,B,D,R,U & V | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For dostribution |  | 2026-05-22 | KPTG-TRANSMIT-017719 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-22 | Zinfra-TRANSMIT-000026 | NA | Trade Partner | Re: Revised earth grading drawings for gate redesign | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect Reference number |  | 2026-05-22 | KPTG-RFI-008068 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-22 | WAM-TRANSMIT-000777 | NA | Consultant | A09 and A10 Issue for Construction | 46 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 608 | 2026-05-26 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-002339 | Closed | 46 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-22 | Nilsen3-TRANSMIT-000167 | NA | Trade Partner | Re: Stage 3 ROPS 3A & 3B | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect revision number |  | 2026-05-22 | KPTG-RFI-008070 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-22 | SES AU-TRANSMIT-000038 | NA | Trade Partner | Security-Typical shop drawings from Stage 1 | 31 | 0 | 0 | NA | APPROVED | 2026-05-22 | WF-000258 | NA | 2026-05-25 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-000702 | Closed | 31 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-22 | PARR-TRANSMIT-000184 | NA | Trade Partner | Re: P2685 - NDC M3 - Stage 4 - Battery Rooms - FLOOR DRAINAGE DETAIL | 1 | 0 | 0 | NA | REJECTED | [5 empty] | The IFA for this document has not yet been received for review |  | 2026-05-22 | KPTG-RFI-008071 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-22 | WilsonPD-TRANSMIT-000049 | NA | Trade Partner | Revised Penetration Drawings for approval | 3 | 0 | 0 | NA | APPROVED | 2026-05-22 | WF-000748 | 956 | 2026-05-29 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-003941 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-22 | Nilsen3-TRANSMIT-000165 | NA | Trade Partner | Re: Nilsen Shop Drawings - M3-TEL-NIL-SDRG-C-0400-3223 - IFC | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect revision and status |  | 2026-05-22 | KPTG-RFI-008073 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-01 | PSGANZ-TRANSMIT-000001 | NA | Trade Partner | Technical Data submissions | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-000106 | NA | 2026-05-11 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-000640 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-17 | SMEPS-TRANSMIT-000124 | NA | Trade Partner | JEMENA EASEMENT - SECTION/DETAIL | 2 | 0 | 0 | NA | APPROVED | 2026-01-22 | WF-003924 | NA | 2026-02-03 |  |  | 2026-02-02 | 2026-02-02 | KPTG-TRANSMIT-012389 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-22 | RDSBIM-TRANSMIT-000062 | NA | Trade Partner | GREYSTAR LEVEL 04 CONCRETE PROFILE PLAN | 6 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 1045 | 2026-05-27 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002719 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-22 | WilsonPD-TRANSMIT-000050 | NA | Trade Partner | Coversheet & Legend for approval | 2 | 0 | 0 | NA | APPROVED | 2026-05-22 | WF-000749 | 958 | 2026-05-29 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-003826 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-22 | Jangho-TRANSMIT-000108 | NA | Trade Partner | 008 _PODIUM SHOP DRAWING (1F~5F) -01 | 55 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 668 | 2026-06-05 |  | Mismatch in title for some documents | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-002156 | Closed | 55 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-22 | Detail-TRANSMIT-000008 | NA | Trade Partner | DOOR HARDAWRE SCHEDULE | 1 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 3300 | 2026-05-31 |  | The WF has been TERMINATED as requested by Isabella |  | 2026-06-19 | KPTG-DA-007191 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-22 | M.S.-TRANSMIT-000065 | NA | Trade Partner | Shop Drawings for Approval | 3 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 258 | 2026-05-28 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-002940 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-22 | SC-TRANSMIT-000007 | NA | Trade Partner | Secondary Steel HD-BOLT IFA Drawings | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Incomplete Drawing title |  | 2026-05-22 | KPTG-TRANSMIT-000925 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-22 | JCI-TRANSMIT-000005 | NA | Trade Partner | OFCI BAS Points Schedules | 0 | 4 | 0 | NA | APPROVED | 2026-05-22 | WF - 000434 | NA | 2026-05-28 |  | NA | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-000931 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-22 | ZIA-TRANSMIT-000094 | NA | Trade Partner | Stage 2 - Functional Design Specification | 0 | 1 | 0 | NA | APPROVED | 2026-05-22 | WF-005800 | NA | 2026-06-05 |  |  | 2026-06-16 | 2026-06-23 | KPTG-TRANSMIT-018936 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-22 | Jangho-TRANSMIT-000109 | NA | Trade Partner | 009 _TOWER SHOP DRAWING (6F~16F) -01 | 11 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 671 | 2026-06-08 |  |  | 2026-06-15 | 2026-06-16 | KPTG-TRANSMIT-002306 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-22 | Appselec-TRANSMIT-000049 | NA | Trade Partner | DB Shop Drawings For Approval | 3 | 0 | 0 | NA | APPROVED | 2026-05-22 | WF-000259 | NA | 2026-05-28 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-000330 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-17 | HDRAus-TRANSMIT-000344 | NA | Consultant | M3_S2_Fuel Compound Drawings | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document status in the document register |  | 2025-12-17 | KPTG-DA-003990 | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-22 | Nilsen3-TRANSMIT-000168 | NA | Trade Partner | M3 Stage-3 SCADA ROPs 3A & 3B | 0 | 1 | 0 | NA | APPROVED | 2026-05-22 | WF-005802 | NA | 2026-05-27 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-018913 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-22 | vdmcons-TRANSMIT-000137 | NA | Trade Partner | ME25 1004: D105 511-537 Sydney Rd Coburg - Shop Drawings - Remain Facade Panels - IFF - 2025-12-09 | 53 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Only for Aconex register. |  |  |  | Closed | 53 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-22 | Nilsen3-TRANSMIT-000166 | NA | Trade Partner | M3-TEL-NIL-SDRG-C-0400-0001 | 1 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 3304 | 2026-05-03 |  |  | 2026-08-07 | 2026-08-07 | KPTG-TRANSMIT-020451 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-05-22 | INSULPAK-TRANSMIT-000020 | NA | Trade Partner | Revised drawing Changes to OAF-01 Ductwork | 2 | 0 | 0 | NA | APPROVED | 2026-05-22 | WF-000497 | NA | 2026-05-26 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-22 | TATE_-TRANSMIT-000002 | NA | Trade Partner | MWYCCB - Tate - L1 Raised Floor Shop Drawing | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing number is incorrect & Revision block is missing |  | 2026-05-22 | KPTG-TRANSMIT-000926 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-22 | WAM-TRANSMIT-000778 | NA | Consultant | A21 Exterior Elevation | 10 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 614 | 2026-05-26 |  |  | 2026-05-27 | 2026-05-27 | KPTG-TRANSMIT-001973 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-22 | HDRAus-TRANSMIT-000491 | NA | Consultant | M3 SW - Document upload - PDF and CAD | 3 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 4222 | 2026-05-26 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-018116 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-19 | PSGANZ-TRANSMIT-000005 | NA | Trade Partner | Technical data resubmissions | 0 | 3 | 0 | NA | APPROVED | 2026-05-19 | WF-000138 | NA | 2026-05-27 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-000643 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-22 | KPTG-TRANSMIT-017666 | NA | Consultant | Re: Proline Drawings | 8 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-05-22 | KPTG-RFI-008062 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-22 | D&E-TRANSMIT-000741 | NA | Trade Partner | NXM3S4 - Ground - Builders Works Layout - Zones - Issued For Construction - | 2 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 3288 | 2026-06-01 |  | As requested by Ellie — Terminated — KPTG-IntCorr-013787 |  | 2026-05-26 | KPTG-IntCorr-013787 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-17 | CRSol-TRANSMIT-000051 | NA | Trade Partner | CLN Drawings Issued for Construction | 13 | 0 | 0 | NA | APPROVED | 2025-12-17 | NA | 766 |  |  |  | 2026-01-07 | 2026-01-07 | KPTG-TRANSMIT-002367 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-22 | IVS-TRANSMIT-000366 | NA | Trade Partner | tage 4 - Ground Floor Stelel Stair Part Plan (Revised as clouded) - | 1 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 3292 | 2026-05-22 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-017741 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-22 | NXT-TRANSMIT-001582 | NA | Trade Partner | P2685 - NDC M3 - Stage 4 - Battery Rooms - BATTERY ROOM ENCLOSURE ITP | 0 | 1 | 0 | NA | APPROVED | 2026-05-15 | WF-005792 | NA | 2026-05-28 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-22 | SKS Tech-TRANSMIT-000145 | NA | Trade Partner | Fwd: Roof Power IFC 2 | 3 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | NA | 2026-05-28 |  | ONLY FOR INFORMING BORDER TEAM |  | 2026-05-22 | KPTG-TRANSMIT-017733 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-22 | D&E-TRANSMIT-000743 | NA | Trade Partner | NXM3S4 - Ground - Builders Works Layout ZONES - Issued For Construction | 4 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 3296 | 2026-06-04 |  | workflow is terminated as per requested by elli salmon |  | 2026-05-26 | NA | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-22 | ACG-TRANSMIT-000093 | NA | Trade Partner | M3S4 Drawings DRAWING - | 14 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 3298 | 2026-06-04 |  |  |  | 2026-06-18 | KPTG-IntCorr-014825 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-22 | SKS Tech-TRANSMIT-000146 | NA | Trade Partner | Updated lighting layout and control. Data Halls | 8 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 3303 | 2026-05-27 |  |  | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-019919 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-14 | KPTG-WTRAN-010723 | NA | Trade Partner | Final (WF-005106) S4 ¦ SAMPLE AND TECH DATA - CONSULTANT REVIEW - FACAD WORKFLOW - Promatect | 0 | 2 | 0 | NA | APPROVED | 2026-05-22 | WF-005106 | NA |  |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-017729 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-22 | D&E-TRANSMIT-000744 | NA | Trade Partner | Valves & Actuators - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-05-22 | WF-005803 | NA | 2026-05-28 |  |  |  | 2026-05-26 | KPTG-TRANSMIT-017838 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-22 | Civilex-TRANSMIT-000249 | NA | Trade Partner | Southern Retaining Wall Updated Drawings 14.05.2026 | 2 | 0 | 0 | NA | APPROVED | 2026-05-22 | WF-005806 | NA | 2026-06-09 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-018240 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-22 | KETE-TRANSMIT-000044 | NA | Trade Partner | Updated Horizontal detail drawing for EXS005 2026.05.21 | 1 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 1285 | 2026-06-08 |  | Luke to confirm-KPTG-IntCorr-001327 | 2026-06-18 | 2026-06-22 | KPTG-TRANSMIT-003959 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-17 | Tradetec-TRANSMIT-000310 | NA | Trade Partner | CP7 - IFA - Stage 2 | 1 | 0 | 0 | NA | APPROVED |  | NA | 3530 | 2025-12-26 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-22 | PARR-TRANSMIT-000060 | NA | Trade Partner | Fuel Services - CABLE SCHEDULE BFCP A/B | 0 | 2 | 0 | NA | APPROVED | [5 empty] | FC documents register updated - Harry to Confirm KPTG-IntCorr-001328, Send to all parties |  | 2026-06-12 | KPTG-TRANSMIT-003895 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-22 | WSP ANZ-TRANSMIT-000012 | NA | Consultant | Tender Acoustic Design Report | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Document Registered Incorrectly |  | 2026-05-22 | DRAFT-000826 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-22 | Carr-TRANSMIT-000059 | NA | Consultant | Updated Facade Docs for Coordination | 6 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 139 | 2026-05-28 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000150 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-22 | ZIA-TRANSMIT-000001 | NA | Trade Partner | M2S9 CSMS Layout (FOA-1) | 3 | 0 | 0 | NA | APPROVED | 2026-05-22 | WF-000751 | 961 | 2026-05-29 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-004492 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-22 | Auspan-TRANSMIT-000310 | NA | Trade Partner | Update IFCed precast shop drawings for construction | 48 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | ifc - No Review required- update register and transmit - KPTG-TRANSMIT-001968 |  | 2026-05-22 | KPTG-TRANSMIT-001968 | Closed | 48 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-22 | POTTSENG-TRANSMIT-000047 | NA | Trade Partner | GMAC: HYDRAULIC SERVICES - DRAINAGE & WATER - LEVEL 01 - ZONES 1 | 10 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 1056 | 2026-05-29 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002832 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-22 | JCBa-TRANSMIT-000258 | NA | Consultant | Pod and Paver Updates | 60 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 568 | 2026-05-26 |  | NA | 2026-06-09 | 2026-06-09 | KPTG-DA-002826 | Closed | 60 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-22 | JCBa-TRANSMIT-000259 | NA | Consultant | L3 Terrace Structure | 10 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 569 | 2026-05-26 |  | NA | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-003021 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-22 | KPTG-TRANSMIT-003743 | NA | Trade Partner | HYDRAULIC ITPs | 0 | 4 | 0 | NA | APPROVED | 2026-05-22 | WF-001074 | NA | 2026-05-29 |  |  | 2026-05-29 | 2026-06-26 | WF-001128 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-22 | KPTG-TRANSMIT-003744 | NA | Trade Partner | VERTIV L4 ITP | 0 | 2 | 0 | NA | APPROVED | 2026-05-22 | WF-001073 | NA | 2026-05-29 |  |  | 2026-06-01 | 2026-07-05 | KPTG-TRANSMIT-004036 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-17 | SKS Tech-TRANSMIT-000114 | NA | Trade Partner | Fire rated cable | 0 | 1 | 0 | NA | APPROVED | 2025-12-17 | WF-000656 | NA | 2025-12-22 |  |  | 2026-01-16 | 2026-01-16 | KPTG-WTRAN-001353 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-22 | KPTG-TRANSMIT-003745 | NA | Trade Partner | SKS Cx Plan | 0 | 17 | 0 | NA | APPROVED | 2026-05-22 | WF-001076 | NA | 2026-05-29 |  | submitted along with SKS Tech-IntCorr-000240, 247, 248 | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-003793 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-22 | KPTG-TRANSMIT-003747 | NA | Trade Partner | VERTIV L2 AND L3 ITP | 0 | 4 | 0 | NA | APPROVED | 2026-05-22 | WF-001077 | NA | 2026-05-29 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-003794 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-22 | KPTG-TRANSMIT-003748 | NA | Trade Partner | EATON CX Plan and L3 ITPS | 0 | 5 | 0 | NA | APPROVED | 2026-05-22 | WF-001078 | NA | 2026-05-29 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-003795 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-22 | fjc-TRANSMIT-000149 | NA | Consultant | Architecturals - EoT Walls, Elevations + L5 CPP | 12 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 657 | 2026-05-27 |  |  | 2026-05-25 | 2026-05-25 | KPTG-SADV-004280 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-22 | Auspan-TRANSMIT-000312 | NA | Trade Partner | Cast in plate layout | 10 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 1058 | 2026-05-29 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-002196 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-22 | ENF-TRANSMIT-000017 | NA | Consultant | Structural drawings | 8 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 145 | 2026-06-02 |  | Review Voided As advised By Renee & requested by ENF for updating the drawings ST-101-01, ST-102-01 and ST-300-10 |  | 2026-05-29 | NA | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-25 | Auspan-TRANSMIT-000102 | NA | Trade Partner | Precast marking plans and elevations for approval. Coen Precast. | 2 | 0 | 0 | KPTG-IntCorr-007888 | APPROVED | 2026-05-25 | NA | 263 | 2026-06-04 |  | KAPITOL ADVICE AWAITS:KPTG-IntCorr-007888. Review is completed:KPTG-TRANSMIT-002990 | 2026-06-19 | 2026-06-19 | Review is completed:KPTG-TRANSMIT-002990 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-22 | KETE-TRANSMIT-000021 | NA | Trade Partner | Kete - Zone 04 & 05 Shop Drawing Submission Rev _IFC A | 187 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect attachments and drawings revision issues.KPTG-SADV-002641 |  | 2026-05-22 | KPTG-SADV-002641 | Closed | 187 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-22 | JCBa-TRANSMIT-000118 | NA | Consultant | IFC – B1 THERMAL PERFORMANCE & RCP DRAWING ISSUE | 6 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 1043 | 2026-05-26 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-001979 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-22 | RDSBIM-TRANSMIT-000063 | NA | Trade Partner | GREYSTAR LEVEL 03 CONCRETE PROFILE PLAN | 6 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 1048 | 2026-05-28 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002718 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-17 | Stowe-A-TRANSMIT-000415 | NA | Trade Partner | Stowe - Tech Data Submission - BTU Distribution Boards | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | TD IFC revision |  | 2025-12-17 | KPTG-TRANSMIT-011003 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-22 | Auspan-TRANSMIT-000311 | NA | Trade Partner | Resubmit shop drawings for approval. | 2 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 1052 | 2026-05-29 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-002178 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-22 | M.2-TRANSMIT-000032 | NA | Trade Partner | Electrical Services Level 2-5 Penetration updates | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review required; register and distribute. KPTG-TRANSMIT-001974 |  | 2026-05-22 | KPTG-TRANSMIT-001974 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-22 | JCBa-TRANSMIT-000119 | NA | Consultant | IFC_L01 SSP | 5 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 1055 | 2026-05-29 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-002052 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-22 | Auspan-TRANSMIT-000309 | NA | Trade Partner | Precast shop drawings for construction. | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC - Update register and distribute KPTG-TRANSMIT-001969 |  | 2026-05-22 | KPTG-TRANSMIT-001969 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-20 | RDSBIM-TRANSMIT-000011 | NA | Trade Partner | NXM2S9 GROUND FLOOR CONTRACTOR BREAKOUT FINISHES & RCP LAYOUT | 2 | 0 | 0 | NA | APPROVED | 2026-06-20 | NA | 952 | 2026-06-24 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-005011 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-22 | VIA Arch-TRANSMIT-000140 | NA | Consultant | M2S9-S11 - S9 WEST & S11 EAST ELEVATIONS | 2 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 951 | 2026-05-27 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-003525 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-22 | Altaire-TRANSMIT-000004 | NA | Trade Partner | NEXTDC M2S9 - Level 1 - Shop Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 962 | 2026-05-29 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-003790 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-22 | S.T.S-TRANSMIT-000007 | NA | Trade Partner | Stage 9 Dock Leveller Shop drawings | 8 | 0 | 0 | NA | APPROVED | 2026-05-22 | WF-00047 | NA | 2026-05-29 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-004285 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-22 | Eneraque-TRANSMIT-000020 | NA | Trade Partner | Bulk Storage Tank Datasheet & Calculation | 0 | 2 | 0 | NA | APPROVED | 2026-05-22 | WF-000750 | NA | 2026-06-03 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-004936 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-22 | DLTS-TRANSMIT-000007 | NA | Trade Partner | S9-COOLING TOWER PART 1 | 34 | 0 | 0 | NA | APPROVED | 2026-05-22 | WF-000753 | NA | 2026-06-02 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-003999 | Closed | 34 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-18 | SMEPS-TRANSMIT-000128 | NA | Trade Partner | M3 STAGE 3 22KV- ELEC SHOP DRAWINGS - FOA-1 | 9 | 0 | 0 | NA | APPROVED | 2025-12-18 | WF-003667 |  | 2026-01-05 |  | The register has been updated. If any further action is required, the coordinator will inform. |  | 2026-01-13 | KPTG-TRANSMIT-011397 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-22 | SMEPS-TRANSMIT-000044 | NA | Trade Partner | Electrical Services -Overall Site Plan - In-Ground Services | 1 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 966 | 2026-05-29 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-003978 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-22 | SMEPS-TRANSMIT-000044 | NA | Trade Partner | Telecommunications - Stage 11 - North - In-Ground Services | 1 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 965 | 2026-05-29 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-003731 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-30 | KPTG-WTRAN-002050 | NA | Trade Partner | FIRE SERVICES - COMMISSIONING PLAN | 0 | 1 | 0 | NA | APPROVED | 2026-04-30 | WF-001034 | NA | 2026-05-08 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-003750 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-22 | LGCE-TRANSMIT-000036 | NA | Trade Partner | Level 2 lighting and power | 2 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 520 | 2026-05-28 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-001333 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-22 | LGCE-TRANSMIT-000037 | NA | Trade Partner | Level 1 light and Power | 2 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 522 | 2026-05-28 |  |  | 2026-07-14 | 2026-07-14 | KPTG-TRANSMIT-001336 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-22 | B Smart-TRANSMIT-000074 | NA | Consultant | B2 CPP update | 1 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 518 | 2026-05-26 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-001095 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-11-26 | RDSBIM-TRANSMIT-000083 | NA | Trade Partner | MLCSPR ¦ CAR PARK NORTH LEVEL 01 CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 206 | 2026-04-30 |  |  | 2026-05-22 | 2026-05-22 | KPTG-TRANSMIT-002885 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-22 | Appselec-TRANSMIT-000103 | na | Trade Partner | MEL11C45 - Communications Shop Drawings - IFC | 11 | 0 | 0 | NA | APPROVED | 2026-05-22 | WF-000260 | NA | 2026-05-26 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-000736 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-22 | Appselec-TRANSMIT-000104 | NA | Trade Partner | MEL11C45 - Communications Shop Drawings - re-IFA | 20 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Stamps are placed on the drawing, requested to resubmit:KPTG-IntCorr-000452 |  | 2026-05-22 | KPTG-IntCorr-000452 | Closed | 20 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-22 | KALLIBRE-TRANSMIT-000009 | NA | Trade Partner | KALLIBRE - Door Frame Shop Drawings IFC | 43 | 0 | 0 | NA | REJECTED | [5 empty] | REVISION OF DRAWINGS ARE INCORRECT, REQUESTED TO RESUBMIT: KPTG-IntCorr-000445 |  | 2026-05-22 | KPTG-IntCorr-000445 | Closed | 43 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-17 | Stowe-A-TRANSMIT-000416 | NA | Trade Partner | Stowe - Tech Data Submission - Basket Radius Piece | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | TD with IFC status |  | 2025-12-17 | KPTG-TRANSMIT-011014 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-22 | SC-TRANSMIT-000001 | NA | Trade Partner | STRUCTURE STRENGTHENING STEEL WORKS COLUMNS AND MARKING PLANS | 11 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 616 | 2026-06-01 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-002104 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-22 | D&E-TRANSMIT-000014 | NA | Trade Partner | L-G Woolworths, Dan Murphy & L-5 Car Park Fans Tech. Data | 0 | 1 | 0 | NA | REJECTED | [5 empty] | QA ERROR - NEEDS CORRECTION IN DOC NO AND TITLE OF ACONEX REG. |  | 2026-05-22 | KPTG-TRANSMIT-001924 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-22 | Civilex-TRANSMIT-000092 | NA | Trade Partner | Cover for Sump | 0 | 1 | 0 | NA | APPROVED | 2026-05-22 | WF-000568 | NA | 2026-05-29 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-002070 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-22 | PTA-TRANSMIT-000001 | NA | Consultant | M3 Stage 6 - PTA Arch Documentation issued for coordination | 100 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 123 | 2026-05-29 |  |  | 2026-06-11 | 2026-06-11 | NA | Closed | 100 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-22 | S.T.S-TRANSMIT-000002 | NA | Trade Partner | wrong Naming convention | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong naming convention |  | 2026-05-22 | KPTG-SADV-000124 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-22 | D&E-TRANSMIT-000002 | NA | Trade Partner | Tim to confirm | 2 | 0 | 0 | KPTG-IntCorr-000110 | APPROVED |  | NA | MA |  |  | Aconex Update Only |  | 2026-05-25 | NA | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-22 | RDSBIM-TRANSMIT-000004 | NA | Trade Partner | workflow | 2 | 0 | 0 | NA | APPROVED | 2026-05-22 | NA | 126 | 2026-06-01 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-000193 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-22 | NXT-TRANSMIT-000401 | NA | Client | 110693-000232 - IOM & MDR | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | As built- distribution |  | 2026-05-22 | Awaiting approval | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-22 | D&E-TRANSMIT-000366 | NA | Trade Partner | AIR SCHEMATIC + CHILLED WATER SCHEMATIC - AS BUILTS | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As built distribution |  | 2026-05-22 | Awaiting approval | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-25 | ABB-TRANSMIT-000043 | NA | Trade Partner | Fwd: IOM for 22kV M3-HVSB A,B,D,R,U & V | 0 | 1 | 0 | NA | APPROVED | 2026-05-25 | NA | NA |  |  | For distribution |  | 2026-05-25 | KPTG-TRANSMIT-017756 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-17 | Stowe-A-TRANSMIT-000417 | NA | Trade Partner | Stowe - Tech Data Submission - Fire Rating Materials | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2025-12-17 | KPTG-TRANSMIT-011017 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-25 | Appselec-TRANSMIT-000105 | NA | Trade Partner | Re: MEL11C45 - Communications Shop Drawings - re-IFA | 20 | 0 | 0 | NA | APPROVED | 2026-05-25 | WF-261 | NA |  |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-000837 | Closed | 20 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-25 | RDSBIM-TRANSMIT-000050 | NA | Trade Partner | MWYCCB ¦ GROUND FLOOR AND LEVEL 01 ZONE 1 DOOR LAYOUT & SCHEDULE | 6 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 287 | 2026-06-01 |  | Actual received date - 22/05/2026 |  |  |  | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-25 | Auspan-TRANSMIT-000314 | NA | Trade Partner | Resubmit precast shop drawings for approval | 21 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 1061 | 2026-06-01 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-002199 | Closed | 21 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-25 | Entire M-TRANSMIT-000008 | NA | Trade Partner | Return Design Brief - For Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with Revision number. |  | 2026-05-25 | KPTG-SADV-000482 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-25 | Entire M-TRANSMIT-000009 | NA | Trade Partner | Grilles & Diffusers Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-25 | WF-000150 | NA | 2026-06-02 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-000845 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-25 | Appselec-TRANSMIT-000106 | NA | Trade Partner | MEL11C45 - Communications Shop Drawings - IFC | 1 | 0 | 0 | NA | APPROVED | 2026-05-25 | WF-000262 | NA | 2026-05-29 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-000825 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-25 | KPTG-TRANSMIT-017666 - KPTG-TRANSMIT-017743 | NA | Trade Partner | Proline Drawings | 8 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 3314 | 2026-06-06 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018484 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-25 | Appselec-TRANSMIT-000107 | NA | Trade Partner | Electrical Services - Distribution Board shop drawings - For Approval | 3 | 0 | 0 | NA | APPROVED | 2026-05-25 | WF-000263 | NA | 2026-05-29 |  |  | 2026-05-26 | 2026-05-26 | Appselec-TRANSMIT-000107 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-25 | Novas-TRANSMIT-000007 | NA | Trade Partner | Re: Door Hardware Order, Basement and Fire Stair Doors | 0 | 1 | 0 | NA | APPROVED | 2026-07-08 | WF-000816 | NA | 2026-07-15 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-25 | SMEPS-TRANSMIT-000293 | NA | Trade Partner | 22KV - Earthing shop drawings. | 7 | 0 | 0 | NA | APPROVED | 2026-05-25 | WF-005812 | NA | 2026-05-28 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-018675 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-02 | KPTG-TRANSMIT-010520 | NA | Trade Partner | M3 Stage 4 - Level 1 Zone 9 Panels & Marking Plans Next DC M3 Stage 4 | 57 | 0 | 0 | NA | APPROVED | 2025-12-02 | WF-003468 | NA | 2025-12-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-17 | HDRAus-TRANSMIT-000345 | NA | Consultant | M3_Stage 2_Roof Stairs Drawing 2506 | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document status in register |  | 2025-12-17 | KPTG-DA-003991 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-25 | Entire M-TRANSMIT-000010 | NA | Trade Partner | Fans & Roof Cowls - Technical Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-25 | WF-000151 | NA | 2026-06-02 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-000896 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-25 | SES AU-TRANSMIT-000039 | NA | Trade Partner | Re: Security- Cable Containment - Substitution Tech Data Rev 4 | 0 | 9 | 0 | NA | APPROVED | 2026-05-25 | WF-000264 | NA | 2026-05-29 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-000742 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-01 | PSGANZ-TRANSMIT-000001 | NA | Trade Partner | Technical Data submissions | 0 | 1 | 0 | NA | APPROVED | 2026-05-01 | WF-000105 | NA | 2026-05-11 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-000709 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-25 | D&E-TRANSMIT-000748 | NA | Trade Partner | SFN - MF, Temp, DP Sensors - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-05-25 | WF-005813 | NA | 2026-06-18 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-019432 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-25 | INTRFRM-TRANSMIT-000060 | NA | Trade Partner | Geelong Edge - Roof Slab Post Tensioning Shop Drawing | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong status, Reason and Revision number. |  | 2026-05-25 | KPTG-SADV-000483 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-25 | NXT-TRANSMIT-001585 ABB-TRANSMIT-000042 | NA | Trade Partner | Fwd: ABB PDUs - AU-10025007 - M3-CStage 4/Ph1 - Test Reports & ITPs | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-05-25 | KPTG-TRANSMIT-017768 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-25 | WilsonPD-TRANSMIT-000195 | SPARK-CRFI-KPG-000618 | Trade Partner | Upadated Hydraulic Roof Level - Zone A & B - Drainage & Water Layout | 2 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 288 | 2026-06-01 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-000991 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-25 | Entire M-TRANSMIT-000011 | NA | Trade Partner | Mechanical Dampers - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-25 | WF-000152 | NA | 2026-06-02 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-000892 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-25 | KETE-TRANSMIT-000025 | NA | Trade Partner | Kete - Zone 05 Shop Drawing IFC | 121 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 121 | 2026-06-01 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-002863 | Closed | 121 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-25 | WAM-TRANSMIT-000783 | NA | Consultant | Interior Wet Area Details | 2 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 622 | 2026-05-28 |  |  | 2026-05-27 | 2026-05-27 | KPTG-TRANSMIT-001976 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2025-12-17 | D&E-TRANSMIT-000318 | NA | Trade Partner | Cooling Tower Waffle Pad - Acoustic Report - Issued for review | 0 | 1 | 0 | NA | APPROVED | 2025-12-17 | WF-003651 | NA | 2025-12-31 |  |  | 2026-01-27 | 2026-01-27 | KPTG-TRANSMIT-011921 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-25 | D&E-TRANSMIT-000749 | NA | Trade Partner | NXM3S4 - Level 1 - CHW Pipe Layout - Zone 2 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 3316 | 2026-06-03 |  |  |  | 2026-06-03 | KPTG-TRANSMIT-018184 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-25 | JCBa-TRANSMIT-000254 | NA | Consultant | Fwd: Storage Update to Drawing Set | 7 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 570 | 2026-05-28 |  | NA | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-002972 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-25 | D&E-TRANSMIT-000751 | NA | Trade Partner | NXM3S4 - Level 1 - Builders Works Layout - Zone 1 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 3320 | 2026-06-03 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-22 | WAM-TRANSMIT-000780 | NA | Consultant | A12 CSP - Level 6 to Level 10 - For Construction | 10 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 625 | 2026-05-29 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-002077 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-25 | WAM-TRANSMIT-000784 | NA | Consultant | Apartment Joinery 80% DD | 15 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 626 | 2026-05-28 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-002010 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-25 | WAM-TRANSMIT-000785 | NA | Consultant | A17 and A18 For Information 80% DD | 53 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 628 | 2026-05-28 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-002843 | Closed | 53 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-25 | KETE-TRANSMIT-000024 | NA | Trade Partner | Kete - Zone 04 Shop Drawing IFC | 66 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 1065 | 2026-06-01 |  | Review terminated as advised by Kapitol PC Alex M. Updated drawings are expected to be issued. | 2026-07-20 | 2026-07-20 | NA | Closed | 66 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-25 | WilsonPD-TRANSMIT-000002 | NA | Trade Partner | HYDRAULIC SERVICES - PENETRATION SERVICES ROOF LAYOUT DRAWING FOR APPROVAL | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Error in Revision number and numbering. |  | 2026-05-25 | KPTG-SADV-000487 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-25 | JCBa-TRANSMIT-000121 | NA | Consultant | Updated Architectural Documentation - Door Types and updated GA Basement Zone Plans - IFC | 7 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 1067 | 2026-05-27 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-002055 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-25 | INGEN3D-TRANSMIT-000710 | NA | Trade Partner | I3D-378 Next DC M3 Stage 4 - Ground Floor Fuel Tank - CDS4-36 & MP0183 - Revised IFC (02-02-2026) | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-05-25 | KPTG-RFI-008098 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-18 | IVS-TRANSMIT-000304 | NA | Consultant | Stage 4 - Roof Plinth & Upper Walkway Zone C2 (Construction Issue) | 2 | 0 | 0 | NA | APPROVED | [7 empty] | 2026-01-15 | KPTG-TRANSMIT-011472 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-25 | D&E-TRANSMIT-000753 | NA | Trade Partner | NXM3S2 - Chilled Water & SFN Water Schematic - Ground Floor - Mech Corridor & Data Hall B1 / B3 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 4225 | 2026-05-25 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-017886 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-25 | INGEN3D-TRANSMIT-000684 | NA | Trade Partner | Fwd: I3D-378 Next DC M3 Stage 4 - Ground Floor Fuel Tank - CDS4-36 & MP0183 - Revised IFC (02-02-2026) | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-05-25 | KPTG-TRANSMIT-017805 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-25 | ADP-TRANSMIT-000324 | NA | Consultant | S4 - Electrical - LAYOUT - SITE IN GROUND | 1 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 3333 | 2026-05-27 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-018065 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-25 | WAM-TRANSMIT-000786 | NA | Consultant | IFC Concrete Profile Plans - Level Mezzanine. | 2 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 630 | 2026-05-27 |  |  | 2026-05-27 | 2026-05-27 | KPTG-TRANSMIT-001980 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-25 | TATE_-TRANSMIT-000003 | NA | Trade Partner | MWYCCB - Tate - Technical Data Sheet | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Front page missing |  | 2026-05-25 | KPTG-TRANSMIT-000930 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-25 | TTW-TRANSMIT-000163 | NA | Consultant | Civil Drawing QA Updates | 2 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 633 | 2026-05-27 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-25 | Highbu-TRANSMIT-000051 | NA | Trade Partner | Revised Level 05 Penetration and Drainage Layout | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-SADV-004291 - PLEASE SHARE THE DWFX FILE. KPTG-SADV-004292 - As per the direction from Mark the documents are updated into document register only and transmitted FJC. |  | 2026-05-25 | KPTG-SADV-004292 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2025-12-18 | D&E-TRANSMIT-000025 | NA | Trade Partner | NXM3S1D6 - DATA HALL A6 - AS BUILT DRAWINGS - Issued For Information | 8 | 0 | 0 | NA | APPROVED | [5 empty] | As-Builts, No review required. Distributed to Project Team. |  |  |  | Closed |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-25 | ADP-TRANSMIT-000323 | NA | Consultant | ADP MEL4780 - M3S4 - Updated Electrical Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 3334 | 2026-05-29 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-018064 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-25 | LNCPPL-TRANSMIT-000010 | NA | Trade Partner | IFC - INGROUND PLANT AREA | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Error in revision number, Mixed disciplines submission. |  | 2026-05-25 | KPTG-SADV-000490 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-25 | WilsonPD-TRANSMIT-000003 | NA | Trade Partner | Hydraulic Tech Data Submission | 0 | 19 | 0 | NA | REJECTED | [5 empty] | Error in document number. |  | 2026-05-25 | KPTG-TRANSMIT-000652 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-25 | HVHD-TRANSMIT-000014 | NA | Trade Partner | ESD Implementation Matrix_04 Update | 0 | 1 | 0 | NA | APPROVED | 2026-05-25 | WF-000579 | NA | 2026-05-26 |  |  | 2026-05-26 | 2026-06-01 | KPTG-TRANSMIT-002048 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-25 | HDRAus-TRANSMIT-000492 | NA | Consultant | Stage 4 - Document upload - PDF and CAD | 29 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 3306 | 2026-05-27 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-018049 | Closed | 29 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-25 | D&E-TRANSMIT-000745 | NA | Trade Partner | NXM3S4 - Level 1 - Builders Works Layout - Zones - Issued For Construction | 4 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 3308 | 2026-06-03 |  |  |  | 2026-05-27 | KPTG-IntCorr-013825 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-25 | D&E-TRANSMIT-000746 | NA | Trade Partner | NXM3S4 - Level 1 - CHW Pipe Layout - Zone 7 - Issued For Construction- | 10 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 3310 | 2026-06-03 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-018188 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-25 | DS-TRANSMIT-000120 | NA | Trade Partner | Webforge HYD penetrations | 3 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 3313 | 2026-06-03 |  |  |  | 2026-05-27 | KPTG-IntCorr-013826 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-25 | D&E-TRANSMIT-000747 | NA | Trade Partner | Re: MCC Drawings - Issued for Construction | 6 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due to incorrect revision number |  | 2026-05-25 | KPTG-RFI-008086 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-25 | ARCST-TRANSMIT-000292 | NA | Trade Partner | Re: Acoustic Screen S4 - S1 | 42 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED DUE TO INCORRECT DOCUMENT NAMING |  | 2026-05-25 | KPTG-RFI-008093 | Closed | 42 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-18 | ZIA-TRANSMIT-000067 | NA | Trade Partner | M3S1 CSMS ORMB Location (Datahall A7) | 1 | 0 | 0 | NA | APPROVED | 2025-12-18 | NA | 1331 | 2025-12-24 |  |  | 2026-01-14 | 2026-01-14 | KPTG-TRANSMIT-002270 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-25 | D&E-TRANSMIT-000750 | NA | Trade Partner | NXM3S4 - SECURITY GRILLES - Issued For Approval- | 1 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 3372 | 2026-06-03 |  | As requested by Elllie s- Terminated Security grilles need to go in physical SCEC review with WSP & SCG, not a mech workflow | 2026-07-23 | 2026-07-23 | KPTG-TRANSMIT-019924 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-18 | D&E-TRANSMIT-000752 | NA | Trade Partner | MCC Drawings - Issued for Construction | 6 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 3322 |  |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-019762 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-25 | ADP-TRANSMIT-000322 | NA | Consultant | ADP MEL4780 - Updated COMMS & EL Drawings-TEL | 12 | 0 | 0 | NA | APPROVED | 2026-05-18 | NA | 3327 | 2026-06-03 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-018147 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-25 | ADP-TRANSMIT-000322 | NA | Consultant | ADP MEL4780 - Updated COMMS & EL Drawings - ELE- | 6 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 3328 | 2026-05-25 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-018100 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-25 | D&E-TRANSMIT-000754 | NA | Trade Partner | NXM3S4 - Level 1 - CHW Pipe Layout - Zone 4 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 3331 | 2026-06-03 |  |  |  | 2026-06-03 | KPTG-TRANSMIT-018185 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-25 | VAE-Grp-TRANSMIT-000167 | NA | Trade Partner | MECHANICAL - DETAILS SHEET 6 - ADDITIONAL SECURITY GRILLE TYPES - TITLE CORRECTED | 1 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 1278 | 2026-05-28 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-004076 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-25 | RDSBIM-TRANSMIT-000039 | NA | Trade Partner | GROUND FLOOR TO LEVEL 02, 03, 09, STAIR/LIFT CORE 03 CONCRETE PROFILE PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 620 | 2026-06-01 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-001950 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-25 | Entire M-TRANSMIT-000055 | NA | Trade Partner | Mechanical - drawing update | 1 | 0 | 0 | NA | APPROVED | 2026-05-25 | WF-000265 | NA | 2026-05-28 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-000745 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-25 | Outlook mail (Downloaded from Procore) | NA | Trade Partner | Stage 09 & 10 EAE Busduct Shop drawings | 55 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 970 |  |  | Drawings returned by Kapitol team after review | 2026-05-29 | 2026-05-29 | NA | Closed | 55 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-18 | DRLL-TRANSMIT-000059 | NA | Trade Partner | Battery Room Lineup and Catcher VSD Tech Data Rev 2 | 0 | 1 | 0 | NA | APPROVED | 2025-12-18 | WF-000866 | NA | 2025-12-29 |  |  | 2025-12-19 | 2025-12-19 | KPTG-TRANSMIT-002244 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-25 | PTA-TRANSMIT-000002 | NA | Trade Partner | Stage 6 - PTA Arch Documentation issued for coordination_22/05/2026 | 4 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 131 | 2026-06-02 |  |  | 2026-06-11 | 2026-06-11 | NA | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-25 | KPTG-TRANSMIT-000102 | NA | Trade Partner | Tech Data Sheet - Demo Test - ABCD v2 | 0 | 1 | 0 | NA | APPROVED | 2026-05-25 | NA | 129 | 2026-06-02 |  | voided requested by will Mason |  | 2026-05-26 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-25 | D&E-TRANSMIT-000004 | NA | Trade Partner | Ground Floor Block 1 - Zone 4 - External Precast Penetrations | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update the register only |  | 2026-05-26 | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-25 | D&E-TRANSMIT-000005 | NA | Trade Partner | Ground Floor - Block 1 - Minor Penetration Adjustment | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Update the register only |  | 2026-05-26 | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-25 | KPTG-TRANSMIT-000089 | NA | Trade Partner | Safetech Specifications | 0 | 4 | 0 | NA | APPROVED | 2026-05-25 | NA | 133 | 2026-06-02 |  | Zoe updated the document and request for submission- | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-000417 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-25 | JCBa-TRANSMIT-000120 | NA | Trade Partner | Door Types and updated GA Basement Zone Plans: IFC | 7 | 0 | 0 | NA | REJECTED | [5 empty] | Transmittal returned to the consultant due to drawing status error. KPTG-SADV-002658 |  | 2026-05-25 | KPTG-SADV-002658 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-25 | Auspan-TRANSMIT-000313 | NA | Trade Partner | Update IFCed precast shop drawings. | 13 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC - Update register and distribute KPTG-TRANSMIT-001984 |  | 2026-05-25 | KPTG-TRANSMIT-001984 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-25 | RDSBIM-TRANSMIT-000068 | NA | Trade Partner | 671CHP ¦ BASEMENT 4A TO BASEMENT 1 CORE WALL PLAN AND ELEVATIONS | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No Review; Update register and distribute -KPTG-TRANSMIT-001012 |  | 2026-05-25 | -KPTG-TRANSMIT-001012 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-25 | B Smart-TRANSMIT-000075 | NA | Consultant | B Smart-TRANSMIT-000075 GF concrete profile IFC | 1 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 525 | 2026-05-27 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-001084 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-25 | B Smart-TRANSMIT-000076 | NA | Consultant | Interior_ A14, A16, A18 - IFC updates | 17 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 527 | 2026-05-27 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-001151 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-18 | KARE-TRANSMIT-000075 | NA | Trade Partner | Level 7 and 8 Light and Power Shop Drawings | 4 | 0 | 0 | NA | APPROVED | 2025-12-18 | WF-000848 | 515 | 2025-12-25 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-25 | NXES-TRANSMIT-000073 | NA | Trade Partner | Stage 1 - External Lighting Layout | 1 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 267 | 2026-05-28 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-002892 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-25 | NXES-TRANSMIT-000074 | NA | Trade Partner | Stage 1 - External Security Layout | 1 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 266 | 2026-05-28 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-002894 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-25 | Schindle-TRANSMIT-000011 | NA | Trade Partner | Schindler Lift 1 - As-built | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As built drawing-updated to Document register only. |  | 2026-05-25 | KPTG-SADV-004433 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-25 | WGAVIC-TRANSMIT-000127 | NA | Consultant | M2 - Stage 9 Level 2 Slab - Issued for Certification | 4 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 978 | 2026-05-28 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-003458 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-25 | WGAVIC-TRANSMIT-000119 | NA | Consultant | M2 - Stage 9 Level 1 Slab - Issued for Construction | 3 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 975 | 2026-05-28 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-003056 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-25 | WGAVIC-TRANSMIT-000120 | NA | Consultant | M2 - Stage 9 Level 1 PT and Suspended Slab Details - Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 976 | 2026-05-28 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-003131 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-25 | WGAVIC-TRANSMIT-000124 | NA | Consultant | M2 - Stage 9 Facade Precast - Issued for Certification | 3 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 973 | 2026-05-28 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-003879 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-25 | WGAVIC-TRANSMIT-000125 | NA | Consultant | M2 - Stage 9 Facade Precast - Issued for Construction | 1 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 974 | 2026-05-28 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-003884 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-25 | WGAVIC-TRANSMIT-000129 | NA | Consultant | M2 - Lift and Stair Rooms - Issued for Certification | 3 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 980 | 2026-05-28 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-004059 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-25 | ELLISAIR-TRANSMIT-000028 | NA | Trade Partner | Technical Data Submission | 0 | 2 | 0 | NA | APPROVED | 2026-05-25 | WF-000759 | NA | 2026-06-04 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-003968 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-18 | LVPG-TRANSMIT-000005 | NA | Trade Partner | LVPG - In ground Tech Data Submittals | 6 | 0 | 0 | NA | APPROVED | 2025-12-18 | WF-000113 | NA | 2025-12-25 |  | No ACC review required. |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-25 | ELLISAIR-TRANSMIT-000029 | NA | Trade Partner | SECURITY GRILLE DETAIL SKETCH ISSUED FOR APPROVAL. | 1 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 968 | 2026-06-01 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-003785 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-26 | RDSBIM-TRANSMIT-000142 | NA | Trade Partner | MLCSPR ¦ INDOOR SPORTS CENTRE LEVEL 02 RCP PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 269 | 2026-05-29 |  |  | 2026-08-25 | 2026-08-25 | KPTG-TRANSMIT-003335 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-26 | Appselec-TRANSMIT-000108 | NA | Trade Partner | MEL11C45 - Communications Shop Drawings - IFA | 3 | 0 | 0 | NA | APPROVED | 2026-05-26 | WF-000266 |  | 2026-06-01 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-000828 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-26 | Appselec-TRANSMIT-000109 | NA | Trade Partner | Colo Cable Reel IFC | 0 | 1 | 0 | NA | APPROVED | 2026-05-26 | WF-000267 | NA | 2026-05-29 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-000794 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-26 | SKS Tech-TRANSMIT-000147 | NA | Trade Partner | Re: Issued for construction hangers cut list all data halls | 7 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Wrong attachment |  | 2026-05-26 | KPTG-RFI-008106 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-26 | SMEPS-TRANSMIT-000295 | NA | Trade Partner | SME - IFA Sample re-submissions | 0 | 1 | 0 | NA | APPROVED | 2026-05-26 | WF-005829 | NA | 2026-06-19 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-018771 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-26 | Entire M-TRANSMIT-000012 | NA | Trade Partner | Intumescent Fire Dampers - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | WF-000153 | NA | 2026-06-03 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-000878 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-25 | 4Ki-TRANSMIT-000005 | NA | Trade Partner | JNR009-TURN TABLE | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | QA Error |  | 2026-05-25 | KPTG-IntCorr-001335 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-25 | PDDARWIN-TRANSMIT-000004 | NA | Trade Partner | Internal Roller doors | 0 | 7 | 0 | NA | REJECTED |  | NA | NA |  |  | QA error |  | 2026-05-25 | KPTG-IntCorr-001347 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-25 | KPTG-TRANSMIT-003756 | NA | Trade Partner | BAC Cx ITP L2 and L3 | 0 | 2 | 0 | NA | APPROVED | 2026-05-26 | WF-001081 | NA | 2026-06-02 |  | Terminated issued again WF-1084 | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-003832 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-18 | RDSBIM-TRANSMIT-000014 | NA | Trade Partner | 671CHP ¦ BASEMENT 3 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2025-12-18 | WF-000109 | 190 | 2025-12-23 |  | Review void as advised during a meeting with Kapitol DM & PCs. |  | 2026-01-22 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-25 | RED Fire-TRANSMIT-000009 | NA | Trade Partner | Fire Compartment Drawings - Version 3 | 17 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 618 | 2026-05-29 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-002294 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-25 | SC-TRANSMIT-000002 | NA | Trade Partner | Column IFA Model | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | cad & model register updated |  | 2026-05-25 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-25 | WAM-TRANSMIT-000779 | NA | Consultant | A15 RCP Issue 95% DD | 27 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 638 | 2026-05-29 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-002291 | Closed | 27 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-25 | Jangho-TRANSMIT-000110 | NA | Trade Partner | PODIUM SHOP DRAWING (1F~5F) -01 | 1 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 669 | 2026-06-08 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-002152 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-25 | WAM-TRANSMIT-000781 | NA | Consultant | A31 Sections for Construction | 7 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 640 | 2026-05-29 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-002144 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-25 | WAM-TRANSMIT-000782 | NA | Consultant | Bathroom Types - 80% DD | 7 | 0 | 0 | NA | APPROVED | 2026-05-25 | NA | 642 | 2026-05-29 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-002007 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-25 | D&E-TRANSMIT-000015 | NA | Trade Partner | L-G Woolworths, Dan Murphy & L-5 Car Park Fans Tech. Data | 0 | 1 | 0 | NA | APPROVED | 2026-05-25 | WF-000582 | NA | 2026-06-01 |  |  | 2026-06-04 | 2026-06-09 | KPTG-TRANSMIT-002164 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-26 | RDSBIM-TRANSMIT-000048 | SPARK-CRFI-KPG-000565 | Trade Partner | MWYCCB ¦ GROUND FLOOR PARTITION WALL KEY PLAN AND LAYOUT | 5 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 289 | 2026-05-29 |  |  | 2026-07-22 | 2026-08-03 | KPTG-TRANSMIT-001559 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-26 | VERTIV-TRANSMIT-000019 | NA | Trade Partner | NEXT DC GE 01 _ MATERIAL SUBMISSION _ FIRE RATED GYPSUM BOARD AND FIRE RATED DOOR (FOA-1) | 0 | 2 | 0 | NA | APPROVED | 2026-05-26 | WF-000154 | NA | 2026-06-03 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-000830 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-18 | RBG-TRANSMIT-000045 | NA | Consultant | Structural drawings for Core and In-situ Walls - Issued for Construction | 6 | 0 | 0 | NA | APPROVED | 2025-12-18 | WF-000108 | 191 | 2025-12-18 |  |  |  | 2026-01-23 | KPTG-TRANSMIT-000315 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-26 | RDSBIM-TRANSMIT-000047 | SPARK-CRFI KPG-000565 | Trade Partner | MWYCCB ¦ LEVEL 01 PARTITION WALL KEY PLAN AND LAYOUT | 5 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 290 | 2026-05-29 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-001485 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-26 | RDSBIM-TRANSMIT-000051 | SPARK-CRFI-KPG-000380 | Trade Partner | MWYCCB ¦ LEVEL 01 CONCRETE PROFILE PLAN | 5 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 291 | 2026-05-29 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-000957 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-26 | VERTIV-TRANSMIT-000020 | NA | Trade Partner | NEXT DC GE01 _ MATERIAL SUBMISSION _ STRUCTURAL STEEL (FOA-1) | 0 | 1 | 0 | NA | APPROVED | 2026-05-26 | WF-000155 | NA | 2026-06-03 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-000759 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-25 | INGEN3D-TRANSMIT-000082 | NA | Trade Partner | Level 2 - CD0157 & PC0427 - IFC | 3 | 0 | 0 | NA | APPROVED | 2026-05-25 | WF-000585 | NA | 2026-06-02 |  |  | 2026-06-04 | 2026-06-03 | KPTG-TRANSMIT-002120 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-26 | VERTIV-TRANSMIT-000022 | NA | Trade Partner | NEXT DC GE 01 _ MATERIAL SUBMISSION _ EXHAUST FAN (FOA-1) | 0 | 1 | 0 | NA | APPROVED | 2026-05-26 | WF-000156 | NA | 2026-06-03 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-000808 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-25 | Jangho-TRANSMIT-000114 | NA | Trade Partner | 010_Mini VMU Unit Panel Samples Drawing-01 | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | register updated as per Jaanbir's teams instructions |  | 2026-05-25 | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-26 | VERTIV-TRANSMIT-000021 | NA | Trade Partner | NEXT DC GE 01 _ MATERIAL SUBMISSION _ POWER CABLES AND CABLE TRAY & TRUNKING (FOA-1) | 0 | 1 | 0 | NA | APPROVED | 2026-05-26 | WF-000157 | NA | 2026-06-03 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-000774 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-26 | Entire M-TRANSMIT-000013 | NA | Trade Partner | Entire M-TRANSMIT-000013-Heat Exchangers - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-26 | WF-000158 | NA | 2026-06-03 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000919 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-26 | TATE_-TRANSMIT-000024 | NA | Trade Partner | Re Issue for approval | 11 | 0 | 0 | NA | APPROVED | 2026-05-26 | WF-000268 | NA | 2026-06-05 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-000784 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-26 | Jangho-TRANSMIT-000119 | NA | Trade Partner | Structural Calculation For Podium Shop Drawing At 1F-5F_Rev 01 | 0 | 1 | 0 | NA | APPROVED | 2026-05-26 | WF-000586 | NA | 2026-05-29 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-002019 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-02 | KPTG-TRANSMIT-010526 | NA | Trade Partner | Next DC M3 Stage 4 - Level 1 Zone 10 Panels & Marking Plans Next DC M3 Stage 4 | 54 | 0 | 0 | NA | APPROVED | 2025-12-02 | WF-003470 | NA | 2025-12-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-18 | KARE-TRANSMIT-000075 | NA | Trade Partner | Level 7 and 8 Light and Power Shop Drawings | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-26 | Jangho-TRANSMIT-000120 | NA | Trade Partner | Structural Calculation For Tower Shop Drawing At 6F-16F_Rev 01 | 0 | 1 | 0 | NA | APPROVED | 2026-05-26 | WF-000587 | NA | 2026-05-29 |  |  | 2026-05-25 | 2026-06-09 | KPTG-TRANSMIT-002190 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-26 | SPD-TRANSMIT-000003 | NA | Trade Partner | SPEEDPANEL FIRE COMPLIANCE | 0 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Correspondence |  | 2026-05-26 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-26 | PCForm-TRANSMIT-000202 | NA | Trade Partner | Rincovitch bulk transmittal | 39 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-05-26 | KPTG-TRANSMIT-001945 | Closed | 39 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-26 | ARJAY-TRANSMIT-000004 | NA | Trade Partner | Arjay Sheds - Lunchroom Layout | 0 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | correspondence |  | 2026-05-26 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-26 | D&E-TRANSMIT-000755 | NA | Trade Partner | NXM3S4 - Level 1 - CHW Pipe Layout - Zones 1/3 & 9 - Issued For Construction | 3 | 0 | 0 | NA | APPROVED | 2026-05-26 |  | 3343 | 2026-05-29 |  |  |  | 2026-06-03 | KPTG-TRANSMIT-018186 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-03-10 | SKS Tech-TRANSMIT-000054 | NA | Trade Partner | Schematics | 19 | 0 | 0 | NA | APPROVED | 2026-03-10 | NA | 2428 | 2026-03-18 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-017845 | Closed | 19 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-26 | PMT Sec-TRANSMIT-000019 | SPARK-CRFI-KPG-000629 | Trade Partner | Shop Drawings | 17 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 292 | 2026-05-29 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-000983 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-26 | KPTG-TRANSMIT-017832 | NA | Trade Partner | M3 S2 - Tiling OMM | 0 | 1 | 0 | NA | APPROVED | 2026-05-26 | WF-005833 | NA | 2026-06-05 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018525 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-26 | KPTG-TRANSMIT-017833 | NA | Trade Partner | M3 S2 - ARJAYS O&M | 0 | 1 | 0 | NA | APPROVED | 2026-05-26 | WF-005834 | NA | 2026-06-05 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018528 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-26 | WAM-TRANSMIT-000787 | NA | Consultant | Drawings A14 and A75 Series for Construction updated | 26 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 646 | 2026-05-28 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-002006 | Closed | 26 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-18 | SMEPS-TRANSMIT-000129 | NA | Trade Partner | 22KV - Sample register and submittals | 0 | 1 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-26 | RED Fire-TRANSMIT-000010 | NA | Trade Partner | Fire Engineering Report Version 1 | 0 | 1 | 0 | NA | APPROVED | 2026-05-26 | WF-000589 | NA | 2026-05-28 |  |  | 2026-06-04 | 2026-06-10 | KPTG-TRANSMIT-002210 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-26 | SSem-TRANSMIT-000005 | NA | Trade Partner | Assemble SRC_Signage & Wayfinding_Documentation | 0 | 4 | 0 | NA | APPROVED | 2026-05-26 | WF - 001027 | NA | 2026-05-26 |  | NA | 2026-06-11 | 2026-06-11 | DRAFT-018775 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-26 | RDSBIM-TRANSMIT-000205 | NA | Trade Partner | 511SRC ¦ LEVEL 09 RCP KEY PLAN AND LAYOUT | 12 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Aconex update only. |  | 2026-05-26 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-26 | Appselec-TRANSMIT-000110 | NA | Trade Partner | Electrical Services - Distribution Board shop drawings - IFC | 3 | 0 | 0 | NA | APPROVED | 2026-05-26 | WF-000269 | NA | 2026-05-29 |  |  | 2026-05-27 | 2026-05-27 | KPTG-TRANSMIT-000755 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-26 | SIL-TRANSMIT-000030 | NA | Trade Partner | Loadbank Busway Li 4000A Routing COLO4 and COLO5 | 1 | 0 | 0 | NA | APPROVED | 2026-05-26 | WF-000271 | NA | 2026-06-01 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-000770 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-26 | SIL-TRANSMIT-000030 | NA | Trade Partner | Loadbank Busway Li 4000A Routing COLO4 and COLO5 | 1 | 0 | 0 | NA | APPROVED | 2026-05-26 | (WF-000270 | NA | 2026-05-29 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-000797 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-26 | FNSTR8-TRANSMIT-000016 | NA | Trade Partner | M3 S4 - Stage 4 Facade Additional Shop Drawings | 4 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 3346 | 2026-06-07 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-019477 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-26 | Altaire-IntCorr-000044 | NA | Trade Partner | MEL05 - Fire Matrix IFC (B) | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC- Update register only. |  |  |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-26 | WAM-TRANSMIT-000788 | NA | Consultant | Drawings A19 and A50 Series for Construction updated | 33 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 648 | 2026-05-29 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-002003 | Closed | 33 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-26 | ADP-TRANSMIT-000325 | NA | Consultant | ADP MEL4780 - Telecommunication Drawings | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | The register has been updated. If any further action is required, the coordinator will inform. - KPTG-TRANSMIT-017866 |  | 2026-05-26 | KPTG-TRANSMIT-017866 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-18 | W TITE-TRANSMIT-000004 | NA | Trade Partner | Tremco 250GC Data Sheet | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The reference number is not aligned with S3 project and kindly do not use the space in Aconex reference number. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-26 | PMT Sec-TRANSMIT-000020 | SPARK-CRFI-KPG-000631 | Trade Partner | PMT Elevations | 8 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 293 | 2026-05-29 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-000985 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-26 | PSGANZ-TRANSMIT-000006 | NA | Trade Partner | Technical Data submissions | 0 | 12 | 0 | NA | REJECTED | [5 empty] | Issues with revision number and Mixed discipline submission. |  | 2026-05-26 | DRAFT-002266 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-22 | Entire M-TRANSMIT-000042 | NA | Trade Partner | Fire Matrix updated with minor comments | 0 | 1 | 0 | NA | APPROVED | 2026-05-22 | WF - 000435 | NA | 2026-05-29 |  | NA | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-000907 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-26 | WAM-TRANSMIT-000789 | NA | Consultant | Drawings A41 for Construction updated | 2 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 650 | 2026-05-28 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-002000 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-26 | Ardon-TRANSMIT-000001 | NA | Trade Partner | Door Frame Shop Drawings | 15 | 0 | 0 | NA | APPROVED | 2026-05-26 | WF-000784 | NA | 2026-06-03 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-004235 | Closed | 15 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-26 | PMT Sec-TRANSMIT-000018 | NA | Trade Partner | PMT Transmittal Datasheets Rev 2 | 0 | 6 | 0 | NA | REJECTED |  | NA | NA |  |  | Difference in Revision number inside the documents and in Aconex |  | 2026-05-26 | KPTG-TRANSMIT-000936 | Closed | 6 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-26 | INTRFRM-TRANSMIT-000061 | NA | Trade Partner | Geelong Edge - Electrical Tech Data (Submission 6) - External Plant Area Pits | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with document number. |  | 2026-05-26 | DRAFT-002271 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-04 | ETNInd-TRANSMIT-000014 | NA | Trade Partner | MEL11 COLO4 COLO5 L2&L3 EPMS SCRIPTS | 0 | 13 | 0 | NA | APPROVED | 2026-05-04 | WF-000203 | NA | 2026-05-11 |  | KPTG-TRANSMIT-000744, REVIEW STAMPS ARE MISSING, REQUESTED TO RESUBMIT | 2026-05-26 | 2026-05-27 | KPTG-TRANSMIT-000759 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-26 | SMEPS-TRANSMIT-000207 | NA | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0602,0603,0610,0611,0612,0613 | 6 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Difference in Revision number |  | 2026-05-26 | KPTG-TRANSMIT-000937 | Closed | 6 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-26 | WAM-TRANSMIT-000790 | NA | Consultant | Drawings A00, A01, A03, A04 for Construction updated | 5 | 0 | 0 | NA | REJECTED | [5 empty] | document number not mentioned in coversheet |  | 2026-05-26 | DRAFT-010049 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-17 | RDSBIM-TRANSMIT-000025 | SPARK-CRFI-KPG-000104 | Trade Partner | MWYCCB ¦ GROUND FLOOR ZONE CONCRETE PROFILE PLAN | 5 | 0 | 0 | KPTG-IntCorr-001198 | APPROVED | 2026-01-12 | WF-000115 | 80 | 2026-01-19 |  |  | 2026-04-27 | 2026-05-08 | KPTG-TRANSMIT-000849 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-26 | SMEPS-TRANSMIT-000045 | NA | Trade Partner | Stage 11 - North - In-Ground Services Electrical | 1 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 985 | 2026-06-02 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-004426 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-26 | SMEPS-TRANSMIT-000045 | NA | Trade Partner | Telecommunications - Overall Site Plan - In-Ground Services | 1 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 986 | 2026-06-02 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-004430 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-26 | WAM-TRANSMIT-000791 | NA | Consultant | Drawings A02 Demolition Plans for Construction updated | 2 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 652 | 2026-05-28 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-002072 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-26 | KPTG-IntCorr-000440 | NA | Trade Partner | Temp Wifi Plan | 0 | 1 | 0 | NA | APPROVED | 2026-05-26 | WF - 000437 | NA | 2026-05-26 |  | NA | 2026-06-12 | 2026-06-12 | KPTG-TRANSMIT-000986 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-26 | Carr-TRANSMIT-000063 | NA | Consultant | Updated Lift Entry Reflected Across Plans | 1 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 152 | 2026-06-01 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000147 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-26 | Carr-TRANSMIT-000064 | NA | Consultant | Updated Lift Entry Reflected Across Plans | 3 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 154 | 2026-06-01 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000146 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-26 | Carr-TRANSMIT-000064 | NA | Consultant | Updated Lift Entry Reflected Across Plans | 1 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 156 | 2026-06-01 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000146 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-26 | Omnii-TRANSMIT-000004 | NA | Consultant | Fire Engineering Performance-Based Design Brief Revision D | 0 | 1 | 0 | NA | APPROVED | 2026-05-26 | NA | 158 | 2026-06-01 |  | Review Voided as advised by Renee01-07-2026 |  | 2026-07-01 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-26 | Carr-TRANSMIT-000009 | NA | Consultant | Architectural Current Drawing Set | 13 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 146 | 2026-06-01 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000149 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-26 | Carr-TRANSMIT-000017 | NA | Consultant | 80% DD Architectural Drawing Issue (Ground Floor and Upper Level) | 14 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 147 | 2026-06-01 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-000136 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-17 | RDSBIM-TRANSMIT-000026 |  | Trade Partner | MWYCCB ¦ GROUND FLOOR PRECAST DOWEL PLAN AND LAYOUT | 5 | 0 | 0 | NA | APPROVED | 2025-12-18 | WF-000112 | 77 | 2025-12-25 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-26 | Carr-TRANSMIT-000023 | NA | Consultant | 80% DD Architectural Drawing Issue | 2 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 148 | 2026-06-01 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000148 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-26 | PMT Sec-TRANSMIT-000021 | NA | Trade Partner | PMT Tech Data | 0 | 2 | 0 | NA | REJECTED |  | NA | NA |  |  | Difference in Title |  | 2026-05-26 | KPTG-TRANSMIT-000939 | Closed | 2 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-29 | KPTG-WTRAN-002037 | NA | Trade Partner | SKS ITPS | 0 | 14 | 0 | NA | APPROVED | 2026-04-29 | WF-001032 | NA | 2026-05-04 |  |  | 2026-05-25 | 2026-05-25 | KPTG-TRANSMIT-003758 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-26 | HDRAus-TRANSMIT-000493 | NA | Consultant | Stage 4 - Metalwork Stair Details | 4 | 0 | 0 | NA | REJECTED | [5 empty] | IFC drawings received before IFA drawings |  | 2026-05-26 | KPTG-RFI-008118 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-10-22 | D&E-TRANSMIT-000027 | SPARK-CRFI-KPG-000311 | Trade Partner | FCU STATIC PRESSURE CALCULATIONS | 0 | 1 | 0 | NA | APPROVED |  | NA | NA | 2026-05-25 |  |  | 2026-05-26 | 2026-05-26 | KPTG-TRANSMIT-000932 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-26 | Baigents-TRANSMIT-000203 | NA | Trade Partner | Canopy Assembly updates FC-3 | 6 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | NA |  |  | FC Doc send to all parties-KPTG-IntCorr-001348 |  | 2026-06-02 | KPTG-TRANSMIT-003836 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-26 | Baigents-TRANSMIT-000205 | NA | Trade Partner | 2026-05-26 Canopy 1 FC Model-Marking Plans and Loose Brackets | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001349,FC Doc send to all parties |  | 2026-06-02 | KPTG-TRANSMIT-003837 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-26 | KPTG-TRANSMIT-003761 | NA | Client | EATON ITPS | 0 | 3 | 0 | NA | APPROVED | 2026-05-26 | WF-001083 | NA | 2026-05-29 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-003796 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-26 | ARCH-TRANSMIT-000045 | NA | Trade Partner | Secondary Consent Town Planning Drawings | 16 | 0 | 0 | NA | APPROVED | [5 empty] | Update register, For information only. |  | 2026-05-26 | KPTG-TRANSMIT-000686 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-26 | JCBa-TRANSMIT-000122 | NA | Consultant | Partition Plans IFC: Basement | 5 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 1069 | 2026-06-02 |  |  | 2026-06-12 | 2026-06-12 | KPTG-TRANSMIT-002234 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-18 | Schindle-TRANSMIT-000003 |  | Trade Partner | Schindler Lifts - Full Depth Frame Drawings | 1 | 0 | 0 | NA | REJECTED | [9 empty] | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-26 | Archacce-TRANSMIT-000002 | NA | Trade Partner | STAGE 6 Access & DDA Report - NEXTDC M3 Stage 6 - Access Report 01 IFT Review - Markups and Reference | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Distributed |  | 2026-05-26 | KPTG-TRANSMIT-000118 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-26 | LNCPPL-TRANSMIT-000011 | NA | Trade Partner | IFC - GE1-FIP-LIP-SDRG-A-0100-3001-FIRE SERVICES INGROUND FLOOR PLANT AREA LAYOUT | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document number. |  | 2026-05-26 | DRAFT-002292 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-26 | SKS Tech-TRANSMIT-000149 | NA | Trade Partner | Issued for construction hangers cut list | 7 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 3341 | 2026-06-04 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-26 | Mirage D-TRANSMIT-000019 | NA | Trade Partner | Stage 4 - Roller Doors - Mirage Doors - REV 2 | 10 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 3347 | 2026-06-07 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-020044 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-26 | ARJAY-TRANSMIT-000003 | NA | Trade Partner | Sheds - Lunchroom Layout | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | Rejected due to incorrect naming conventions and numbering |  | 2026-05-26 |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-26 | WGAVIC-TRANSMIT-000126 | NA | Consultant | M2 - Stage 11 Level 2 Slab - Issued for Construction | 4 | 0 | 0 | NA | APPROVED | 2026-05-26 |  | 988 | 2026-05-29 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-003455 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-26 | RDSBIM-TRANSMIT-000005 | NA | Trade Partner | LEVEL 01 CONCRETE PROFILE PLAN ¦ BLOCK 2 | 3 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 135 | 2026-06-03 |  | voided-drawing updates |  | 2026-05-27 | NA | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-26 | WGAVIC-TRANSMIT-000128 | NA | Consultant | M2 - Stage 9 HV Room Update - Issued for Certification | 1 | 0 | 0 | NA | APPROVED | 2026-05-26 |  | 990 | 2026-05-29 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-003461 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-26 | WGAVIC-TRANSMIT-000130 | NA | Consultant | M2 - Structural Details - Issued for Construction | 3 | 0 | 0 | NA | APPROVED | 2026-05-26 |  | 992 | 2026-05-29 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-003467 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-16 | SKS Tech-TRANSMIT-000112 | NA | Trade Partner | LEVEL 5 TELECOM PATHWAY | 1 | 0 | 0 | NA | APPROVED | 2025-12-17 | NA | 762 | 2025-12-20 |  |  | 2026-01-15 | 2026-01-15 | KPTG-TRANSMIT-002447 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-26 | Auscool-TRANSMIT-000093 | NA | Trade Partner | Mezzanine | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-000996 - Requested guidance, but no response received yet. KPTG-SADV-004315-As per instruction from Mark, we ignore this transmittal. | 2026-05-27 | 2026-05-27 | KPTG-SADV-004315 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-26 | Metzone-TRANSMIT-000024 | NA | Trade Partner | Revised shop drawings for ground level steel | 36 | 0 | 0 | NA | APPROVED | 2026-05-26 | WF-000770 | NA | 2026-06-01 |  | WF-000770 - ASHLIN CREATED THE WORK FLOW | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-002526 | Closed | 36 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-26 | Auscool-TRANSMIT-000038 | NA | Trade Partner | BW drawings - Ground floor | 5 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 1073 | 2026-06-02 |  | Review voided as requested by Dm. | 2026-06-04 | 2026-06-04 | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-26 | Auspan-TRANSMIT-000315 | NA | Trade Partner | Resubmit precast shop drawings for approval. | 1 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 1071 | 2026-06-02 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-002186 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-26 | Auspan-TRANSMIT-000317 | NA | Trade Partner | Precast marking plan level 4 zone 4, 5 | 1 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 1075 | 2026-06-02 |  | Terminated | 2026-06-09 | 2026-06-09 | NA | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-26 | Auspan-TRANSMIT-000318 | NA | Trade Partner | Precast shop drawings for construction. | 17 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC - Update register and distribute :KPTG-TRANSMIT-001995 |  | 2026-05-26 | KPTG-TRANSMIT-001995 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-26 | Auspan-TRANSMIT-000319 | NA | Trade Partner | Precast shop drawings for approval. | 57 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 1078 | 2026-06-02 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-002338 | Closed | 57 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-26 | M.2-TRANSMIT-000034 | NA | Trade Partner | Light Fitting Tech Data for review | 0 | 45 | 0 | NA | APPROVED | 2026-05-26 | WF-000544 | NA | 2026-06-02 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-002658 | Closed | 45 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-26 | Auspan-TRANSMIT-000320 | NA | Trade Partner | APrecast shop drawings for approval. | 3 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 1083 | 2026-06-02 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-002274 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-18 | IVS-TRANSMIT-000306 | NA | Consultant | Stage 4 - Eaves Gutter Information Issue | 1 | 0 | 0 | NA | APPROVED | [5 empty] | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-26 | Auspan-TRANSMIT-000321 | NA | Trade Partner | Shop drawing 2P5051 for construction. | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC - Update register and distribute KPTG-TRANSMIT-002009 |  | 2026-05-26 | KPTG-TRANSMIT-002009 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-26 | LGCE-TRANSMIT-000038 | NA | Trade Partner | 600 Series drawings (MSB and Comms) | 6 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 529 | 2026-06-02 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-001111 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-26 | 4DW-TRANSMIT-000181 | NA | Consultant | Structural Documentation - Steelwork updates | 7 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 271 | 2026-05-29 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-002924 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-26 | ARCH-TRANSMIT-000152 | NA | Consultant | MLC - SPR - Updated Drawings | 28 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 273 | 2026-05-29 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-002911 | Closed | 28 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-26 | SES AU-TRANSMIT-000040 | NA | Trade Partner | SECURITY- IFC-COLO 4 FLOOR PLAN LAYOUTS | 2 | 0 | 0 | NA | APPROVED | 2026-05-26 | WF-000272 | NA | 2026-05-28 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-000776 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-26 | WDes-TRANSMIT-000055 | NA | Consultant | Structural - Updated Ground floor - Ross St. brickwall updates | 12 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 571 | 2026-05-29 |  | NA | 2026-06-02 | 2026-06-02 | DRAFT-018524 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-26 | Nilsen3-TRANSMIT-000169 | NA | Trade Partner | Nilsen Shop Drawings - M3-TEL-NIL-SDRG-C-0400-3223 - IFC | 1 | 0 | 0 | NA | APPROVED | 2026-05-26 | NA | 3336 | 2026-06-04 |  |  | 2026-08-19 | 2026-08-19 | KPTG-TRANSMIT-020698 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-26 | KPTG-TRANSMIT-017831 | NA | Trade Partner | ARC Plaster Alt Skirting Chiller Rooms | 0 | 1 | 0 | NA | APPROVED | 2026-05-27 | WF-005828 | NA | 2026-06-16 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018470 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-26 | Civilex-TRANSMIT-000093 | NA | Trade Partner | AWASHAFT Sewer Maintenance Shaft | 0 | 1 | 0 | NA | APPROVED | 2026-05-26 | WF-000593 | NA | 2026-05-28 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-002066 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-26 | PCForm-TRANSMIT-000170 | NA | Trade Partner | Re: Post Tension Roof - Zone C1t | 1 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due to wrong document naming |  | 2026-05-27 | KPTG-RFI-008107 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2025-12-18 | CECPL-TRANSMIT-000012 | N/A | Consultant | Electrical and Mechanical Updated Construction Documentation | 17 | 0 | 0 | NA | APPROVED | 2025-12-18 |  | 260 | 2025-12-21 |  |  |  | 2025-12-19 |  | Closed | 17 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-26 | SKS Tech-TRANSMIT-000148 | NA | Trade Partner | DRAWING-SKS Tech-TRANSMIT-000148 SKS openings layout and sections drawings | 14 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 3425 | 2026-06-04 |  |  | 2026-08-28 | 2026-08-28 | KPTG-TRANSMIT-021067 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-27 | RDSBIM-TRANSMIT-000143 | NA | Trade Partner | MLCSPR ¦ INDOOR SPORTS CENTRE LEVEL 03 PARTITION WALL PLAN-275# | 4 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 275 | 2026-05-30 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-003126 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-27 | VIA Arch-TRANSMIT-000142 | NA | Consultant | M2 S9 Architectural - Building Permit Issue | 68 | 0 | 0 | NA | APPROVED | 2026-05-27 | WF-000791 | 994 | 2026-05-30 |  |  | 2026-05-27 | 2026-05-27 | KPTG-TRANSMIT-003587 | Closed | 68 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-27 | RDSBIM-TRANSMIT-000207 | NA | Trade Partner | LEVEL 09 CONCRETE PROFILE PLAN | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - only for Aconex update and distribution. |  |  | 6 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-27 | WSP ANZ-TRANSMIT-000079 | NA | Consultant | WSP - M2 Building Services Document - Issue for Permit (Fuel Documents) | 3 | 0 | 0 | NA | APPROVED | 2026-05-27 |  | 995 | 2026-05-30 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-003735 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-27 | SIL-TRANSMIT-000036 | NA | Trade Partner | MEL05 C4 - 32PO-41735-T024 Technical Submittals | 0 | 1 | 0 | NA | APPROVED | 2026-05-27 | WF - 000438 | NA | 2026-05-29 |  | NA | 2026-05-27 | 2026-05-27 | KPTG-TRANSMIT-000913 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-27 | D&E-TRANSMIT-000758 | NA | Trade Partner | Fwd: Water System Points List - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-05-27 | KPTG-TRANSMIT-017903 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-27 | D&E-TRANSMIT-000757 | NA | Trade Partner | Fwd: SFN Points List - Issued for Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-05-27 | KPTG-TRANSMIT-017906 | Open | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-27 | WilsonPD-TRANSMIT-000053 | NA | Trade Partner | S9 GF Water Supply and Sewer & Stormwater Layouts for Approval | 2 | 0 | 0 | NA | APPROVED | 2026-05-27 | WF-000789 | 997 | 2026-06-03 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-003863 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-27 | Nilsen3-TRANSMIT-000171 | NA | Trade Partner | 10A Switched pendant outlet | 0 | 1 | 0 | NA | APPROVED | 2026-05-27 | WF-005838 | NA | 2026-06-04 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-019107 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2025-12-18 | DI-TRANSMIT-000132 | NA | Consultant | PH2 - As Built documents | 32 | 0 | 0 | NA | APPROVED | 2025-12-18 |  | 261 | 2025-12-21 |  |  |  | 2025-12-19 |  | Closed | 32 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-27 | Nilsen3-TRANSMIT-000172 | NA | Trade Partner | Nilsen Sample HAC Push Buttons | 0 | 1 | 0 | NA | APPROVED | 2026-05-27 | WF-005839 | NA | 2026-06-04 |  |  | 2026-07-13 | 2026-07-13 | KPTG-TRANSMIT-019610 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-27 | Tradetec-TRANSMIT-000452 | NA | Trade Partner | IFA - Stage 4 - LVP36 and LVP37 | 2 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 3363 | 2026-06-04 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-018915 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-27 | D&E-TRANSMIT-000756 | NA | Trade Partner | e: IW System Points List - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-05-27 |  |  |  |  | FOR INFORMATION ONLY |  | 2026-05-27 | KPTG-IntCorr-013845 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-27 | Altaire-TRANSMIT-000010 | NA | Trade Partner | MEL05 - Fire Matrix IFC (B) | 0 | 1 | 0 | NA | APPROVED | 2026-05-27 | WF - 000439 | NA | 2026-05-29 |  | Terminated | 2026-05-27 | 2026-05-27 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-27 | D&E-TRANSMIT-000759 | NA | Trade Partner | Air System Points List - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-27 | WF-005842 | NA | 2026-06-05 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-019426 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-27 | NXT-TRANSMIT-001587 | NA | Trade Partner | Fwd: Zone C1 FI and FJ Bypass Busduct Shop drawings - IFC | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-05-27 | KPTG-TRANSMIT-017909 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-27 | TTW-TRANSMIT-000016 | NA | Consultant | Facade IFC and Reg 126 update | 5 | 0 | 0 | NA | APPROVED | 2026-05-27 |  | 999 | 2026-06-01 |  |  | 2026-05-27 | 2026-05-27 | KPTG-TRANSMIT-003592 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-27 | TTW-TRANSMIT-000017 | NA | Consultant | Facade Calculation report revision and date update | 0 | 1 | 0 | NA | APPROVED | 2026-05-27 |  | 999 | 2026-06-01 |  |  | 2026-05-27 | 2026-05-27 | KPTG-TRANSMIT-003592 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-27 | Appselec-TRANSMIT-000111 | NA | Trade Partner | EPMS System - Shop drawings - IFC | 10 | 0 | 0 | NA | APPROVED | 2026-05-27 | WF-000273 | NA | 2026-05-28 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-000840 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-27 | RDSBIM-TRANSMIT-000006 | NA | Trade Partner | LEVEL 01 CONCRETE PROFILE KEYPLAN AND SECTION - BLOCK 2 | 3 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 137 | 2026-06-04 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-000192 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-02 | Aurecon-TRANSMIT-000030 |  | Consultant | Updated drawings for HVSB | 3 | 0 | 0 | NA | APPROVED | 2025-12-03 |  |  |  |  | The register has been updated. If any further action is required, the coordinator will inform. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2025-12-18 | DI-TRANSMIT-000131 | NA | Consultant | EMIC - AS BUILT DOCS | 23 | 0 | 0 | NA | APPROVED | [7 empty] | 2025-12-19 |  | Closed | 23 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-27 | Appselec-TRANSMIT-000112 | NA | Trade Partner | Communications services - IDF 1-2-3-4 - IFA | 1 | 0 | 0 | NA | APPROVED | 2026-05-27 | WF-000274 | NA | 2026-06-02 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-000848 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-27 | TTW-TRANSMIT-000031 | NA | Consultant | Stage 6 Civil 3D Digital Model | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Cad file register update |  | 2026-05-27 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-27 | Nilsen3-TRANSMIT-000026 | NA | Trade Partner | Sample submissions - Tricab LV Submains | 0 | 1 | 0 | NA | APPROVED | 2026-05-27 | WF-000790 | NA | 2026-06-05 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-004239 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-27 | RDSBIM-TRANSMIT-000040 | NA | Trade Partner | GROUND FLOOR TO LEVEL 06 LIFT CORE 1 CONCRETE PROFILE PLAN AND SECTIONAL ELEVATIONS | 3 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 654 | 2026-05-29 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-001998 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-27 | SMEPS-TRANSMIT-000209 | SPARK-CRFI KPG-000388 | Trade Partner | Re: NEL-CNT-SME-2801-BSE-SDG-0602,0603,0610,0611,0612,0613 | 7 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 294 | 2026-06-03 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-001338 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-27 | EFP-TRANSMIT-000022 | NA | Trade Partner | EFP Tech Data Respond to Consultant comments | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected: wrong Revision-KPTG-IntCorr-000467 |  | 2026-05-27 | KPTG-IntCorr-000467 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-27 | SES AU-TRANSMIT-000041 | NA | Trade Partner | SECURITY- IFC-COLO 5 FLOOR PLAN LAYOUTS | 4 | 0 | 0 | NA | APPROVED | 2026-05-27 | WF-000275 | NA | 2026-05-29 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-000778 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-27 | PARR-TRANSMIT-000187 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - BFS SCHEMATIC | 1 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 3359 | 2026-06-06 |  |  | 2026-08-26 | 2026-08-26 | KPTG-TRANSMIT-020976 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-27 | Ardon-TRANSMIT-000031 | NA | Trade Partner | Re: Stage 4 door frame shop drawings | 12 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-05-20 | KPTG-RFI-008126 | Closed | 12 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-27 | Nilsen3-TRANSMIT-000173 | NA | Trade Partner | Typical label sample updated | 0 | 1 | 0 | NA | APPROVED | 2026-05-27 | WF-005844 | NA | 2026-06-03 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-019322 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2025-12-18 | KPTG-TRANSMIT-002530 | NA | Trade Partner | A/C Cupboard Additional Signs - O1 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-27 | D&E-TRANSMIT-000760 | NA | Trade Partner | NXM3S4 - Roof - Mech_Elec Layout Zones | 5 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 3370 | 2026-06-17 |  | terminated as per requested by ellie adp reviewer rejected the drawings |  | 2026-06-12 | na | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-27 | SKS Tech-TRANSMIT-000150 | NA | Trade Partner | Typical details labels issued for construction- | 1 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 3354 | 2026-06-04 |  |  | 2026-06-29 | 2026-07-06 | ⁠KPTG-TRANSMIT-019353 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-27 | ADP-TRANSMIT-000327 | NA | Consultant | ADP MEL4780 | 2 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 3361 | 2026-06-05 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-018075 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-27 | LNCPPL-TRANSMIT-000012 | NA | Trade Partner | TELECOMMUNICATION SERVICES GROUND FLOOR PLANT AREA LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 250 | 2026-06-02 |  | Terminated as advised by Chri Doh for submitting the updated document. | 2026-06-12 | 2026-06-12 | KPTG-IntCorr-000246 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-27 | SMEPS-TRANSMIT-000210 | SPARK-CRFI-KPG-000302 | Trade Partner | Re: NEL-CNT-SME-2801-BSE-SDG-0184,0185,0186,0188 | 4 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 295 | 2026-06-03 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-000981 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-27 | LNCPPL-TRANSMIT-000013 | NA | Trade Partner | TELECOMMUNICATION SERVICES INGROUND FLOOR PLANT AREA LAYOUT | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Same drawing already submitted in LNCPPL-TRANSMIT-000012 and processed the submission. Duplicate submission. |  | 2026-05-27 | KPTG-SADV-000508 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-27 | LNCPPL-TRANSMIT-000014 | NA | Trade Partner | HYDRAULIC SERVICES - WATER SERVICES INGROUND FLOOR PLANT AREA LAYOUT | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document number. |  | 2026-05-27 | KPTG-SADV-000503 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-27 | LNCPPL-TRANSMIT-000015 | NA | Trade Partner | HYDRAULIC SERVICES - DRAINAGE SERVICES INGROUND FLOOR PLANT AREA LAYOUT | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document number. |  | 2026-05-27 | KPTG-SADV-000507 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-27 | PSGANZ-TRANSMIT-000008 | NA | Trade Partner | Fire Detection technical data submission | 0 | 8 | 0 | NA | REJECTED | [5 empty] | Issue with revision number for -0012, it should be FOA-02 as FOA-01 is already submitted and revised. |  | 2026-05-27 | KPTG-SADV-000506 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-27 | PSGANZ-TRANSMIT-000009 | NA | Trade Partner | Fire Protection technical data submission | 0 | 4 | 0 | NA | APPROVED | 2026-05-27 | WF-000160 | NA | 2026-06-04 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-002258 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-27 | INTRFRM-TRANSMIT-000062 | NA | Trade Partner | Re: Geelong Edge - Electrical Tech Data (Submission 6) - External Plant Area Pits | 0 | 1 | 0 | NA | APPROVED | 2026-05-27 | WF-000163 | NA | 2026-06-04 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-000713 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-27 | Entire M-TRANSMIT-000014 | NA | Trade Partner | Humidifiers - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-27 | WF-000161 | NA | 2026-06-04 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000923 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-27 | CRSol-TRANSMIT-000088 | NA | Trade Partner | CRS - Tech Data Submission NextDC M3 S4 HAC Tech Data | 0 | 2 | 0 | NA | APPROVED | 2026-05-27 | WF-005855 | NA | 2026-06-22 |  |  | 2026-07-03 | 2026-07-03 | ⁠KPTG-TRANSMIT-019284 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-27 | IVS-TRANSMIT-000367 | NA | Consultant | Stage 2 - Southern Retaining Wall Construction Issue (Revised as clouded) | 1 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 4233 | 2026-06-19 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-019021 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-27 | Entire M-TRANSMIT-000015 | NA | Trade Partner | Return Design Brief - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-27 | WF-000162 | NA | 2026-06-04 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-000883 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-27 | HDRAus-TRANSMIT-000494 | NA | Consultant | KPTG-DA-006778: Re: S4 Chiller Rooms Roof Peno Detail (RE-TRANSMIT PDF and CAD) | 1 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 4230 | 2026-05-29 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-018120 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-27 | SMEPS-TRANSMIT-000211 | NA | Trade Partner | Re: NEL-CNT-SME-2801-BSE-DRG-0187,0189,0181,0182,0183 | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect drawing number |  | 2026-05-27 | KPTG-TRANSMIT-000947 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-27 | PCForm-TRANSMIT-000204 | NA | Trade Partner | Fwd: Level 5 to Level 17 PT Reo | 38 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 656 | 2026-06-04 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-002460 | Closed | 38 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-27 | SMEPS-TRANSMIT-000296 | NA | Trade Partner | SME - IFC Sample submissions | 0 | 8 | 0 | NA | REJECTED | [5 empty] | Revision not updated |  | 2026-05-27 | KPTG-RFI-008134 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-27 | Entire M-TRANSMIT-000056 | NA | Trade Partner | Waffle Pad Technical Data Rev A IFA | 0 | 1 | 0 | NA | APPROVED | 2026-05-27 | WF-000276 | NA | 2026-06-02 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-000821 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-16 | SKS Tech-TRANSMIT-000113 | NA | Trade Partner | LEVEL 1 TO 3 COMMS & COMMS PATHWAYS IFC LAYOUT | 6 | 0 | 0 | NA | APPROVED | 2025-12-17 | NA | 764 | 2025-12-20 |  |  | 2026-01-15 | 2026-01-15 | KPTG-TRANSMIT-002459 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-27 | SMEPS-TRANSMIT-000212 | SPARK-CRFI KPG-000302 | Trade Partner | Re: NEL-CNT-SME-2801-BSE-SDG-0190 | 1 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 296 | 2026-06-03 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-000964 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-27 | CraftedS-TRANSMIT-000004 | NA | Trade Partner | O&MM Maintenance Manual | 0 | 1 | 0 | KPTG-IntCorr-007960 | APPROVED |  | na | na |  |  | kapitol advise awaits: KPTG-IntCorr-007960. Updated Register only.KPTG-IntCorr-007960 |  | 2026-05-27 | KPTG-IntCorr-007960 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-27 | SMEPS-TRANSMIT-000213 | NA | Trade Partner | Multicore cabling - NEL-CNT-SME-2990-ELC-SAM-0020 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect revision |  | 2026-05-27 | KPTG-TRANSMIT-000948 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-27 | Entire M-TRANSMIT-000043 | NA | Trade Partner | Waffle Pad Technical Data Rev A IFA | 0 | 1 | 0 | NA | APPROVED | 2026-05-27 | WF - 000441 | NA | 2026-05-29 |  | NA | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-000921 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-27 | Nilsen3-TRANSMIT-000159 | NA | Trade Partner | Re: Next DC M3-SITEWIDE SCADA INTERFACE DRAWINGS FROM ABB | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-05-27 | KPTG-RFI-008137 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-27 | Highbu-TRANSMIT-000149 | NA | Trade Partner | ISC - IFA drawings | 5 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 278 | 2026-06-01 |  |  | 2026-07-10 | 2026-07-10 | KPTG-TRANSMIT-003084 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-27 | ARCH-TRANSMIT-000153 | na | Consultant | MLC - SPR - ISC - Capping Beam updaet | 1 | 0 | 0 | KPTG-IntCorr-007964 | APPROVED | 2026-05-28 | NA | 280 | 2026-05-29 |  | KPTG-IntCorr-007964" kapitol Advice awaits |  | 2026-05-29 | KPTG-TRANSMIT-002913 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-27 | Civilex-TRANSMIT-000250 | NA | Trade Partner | Stage 2 - Landscape drawing transmittal - Rev D | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with drawing title. |  | 2026-05-27 | KPTG-SADV-005595 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-27 | ARCST-TRANSMIT-000293 | NA | Trade Partner | Nib Wall Riser Cupboards - Issued for Approval | 7 | 0 | 0 | NA | APPROVED | 2026-05-27 | WF-005864 | NA | 2026-06-12 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-18 | JCBa-WTRAN-000542 | NA | Consultant | Architectural Technical data and Sample - Waste Bin-DB-15AS | 0 | 1 | 0 | NA | APPROVED | 2025-12-18 | WF-000846 | NA | 2025-12-25 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-27 | Baigents-TRANSMIT-000085 | NA | Trade Partner | Site Storage Steel - Package 1 - Issued for Construction | 43 | 0 | 0 | NA | REJECTED | [5 empty] | status block is missing inside the drawings IFA not approved, IFC submitted |  | 2026-05-27 | KPTG-TRANSMIT-000949 | Closed | 43 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-27 | ETNInd-TRANSMIT-000017 | NA | Trade Partner | MEL11 COLO4 & COLO5 EPMS TOPOLOGY OVERVIEW | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Rejected: documents need to be transmiited individually:KPTG-IntCorr-000468 |  | 2026-05-27 | KPTG-IntCorr-000468 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-27 | ARCST-TRANSMIT-000294 | NA | Trade Partner | Acoustic Screen S4 - S1: IFA | 41 | 0 | 0 | NA | APPROVED | 2026-05-27 | WF-005857 | NA | 2026-06-10 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018480 | Closed | 34 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-27 | Civilex-TRANSMIT-000251 | NA | Trade Partner | Stage 2 - Irrigation System Layout - Rev B | 1 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 4232 | 2026-06-03 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-018834 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-27 | Ardon-TRANSMIT-000032 | NA | Trade Partner | Re: Stage 4 door frame shop drawing | 12 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due to incorrect title and missing of of details in inside drawing |  | 2026-05-27 | KPTG-RFI-008135 | Closed | 12 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-27 | RDSBIM-TRANSMIT-000206 | NA | Trade Partner | 511SRC ¦ LEVEL 08 RCP KEY PLAN AND LAYOUT | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Aconex update only. |  |  |  | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-27 | Baigents-TRANSMIT-000084 | NA | Trade Partner | MCC - MONORAIL STEEL - ISSUED FOR CONSTRUCTION | 34 | 0 | 0 | KPTG-IntCorr-003082 | REJECTED | [5 empty] | The drawing date and status in history block and Aconex seem different |  | 2026-05-29 | KPTG-TRANSMIT-000956 | Closed | 34 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-27 | Nilsen3-TRANSMIT-000174 | NA | Trade Partner | Site-Wide SCADA Interface Diagram from ABB | 0 | 1 | 0 | NA | APPROVED | 2026-05-27 | WF-005867 | NA | 2026-06-12 |  |  | 2026-08-27 | 2026-08-27 | KPTG-TRANSMIT-021035 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-27 | ADP-TRANSMIT-000328 | NA | Consultant | ADP MEL4561 - S2 ¦ Updated Fire Protection Drawings | 11 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 4235 | 2026-05-29 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-018124 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-27 | Hollow-TRANSMIT-000013 | NA | Trade Partner | L3 plant room precast structure - PC beams 02, 05 and 06 - Shop drawings, issued for Construction | 3 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 663 | 2026-05-29 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-002068 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-18 | KPTG-WTRAN-001875 | NA | Trade Partner | Architectural Technical data and Sample - PV-01 Pod and Paver | 0 | 1 | 0 | NA | APPROVED | 2025-12-18 | WF-000847 | NA | 2025-12-25 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-27 | L.E.S.-TRANSMIT-000002 | NA | Trade Partner | Slab Penetrations - Mezzanine level - IFA resubmission | 2 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 664 | 2026-06-04 |  |  | 2026-06-14 | 2026-06-22 | KPTG-TRANSMIT-002381 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-27 | D&E-TRANSMIT-000761 | NA | Trade Partner | NXM3S4 - Roof Level - CHW Pipe Layout Zones - Issued For Construction | 3 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 3365 | 2026-06-05 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-27 | ADP-TRANSMIT-000326 | NA | Consultant | ADP MEL4780 - BACOP Small Power & Schematic Update | 5 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 3367 | 2026-05-29 |  | TOTAL 7 DOCS received in this transmittal. 5 were processed, and updated version of the remaining 2 were received in ADP-TRANSMIT-000327. |  |  |  | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-27 | WAM-TRANSMIT-000793 | NA | Consultant | Drawings A00, A01, A03, A04 for Construction updated | 5 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 667 | 2026-05-30 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-001993 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-27 | RDSBIM-TRANSMIT-000069 | NA | Trade Partner | 671CHP - LEVEL 02 CONCRETE PROFILE PLAN AND SECTION | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Returned to RDS due to incorrect drawing number - KPTG-SADV-002072 |  | 2026-05-27 | KPTG-SADV-002072 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-27 | crossfir-TRANSMIT-000016 | NA | Trade Partner | Wet Fire - Penetration drawing B04,03,02 &01 | 4 | 0 | 0 | KPTG-IntCorr-000605 | APPROVED |  | NA | 535 | 2026-06-05 |  | Kapitol to advise - KPTG-IntCorr-000605 | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001264 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-27 | Auspan-TRANSMIT-000322 | NA | Trade Partner | Precast shop drawings for construction. | 12 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC - Update register and distribute - KPTG-TRANSMIT-002014 |  | 2026-05-27 | KPTG-TRANSMIT-002014 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-27 | Auspan-TRANSMIT-000323 | NA | Trade Partner | Precast shop drawings for approval | 3 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 1085 | 2026-06-03 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-002275 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-27 | M.2-TRANSMIT-000035 | NA | Trade Partner | MSB shop Drawings | 0 | 2 | 0 | NA | APPROVED | 2026-05-27 | WF-000547 | NA | 2026-06-03 |  |  |  | 2026-06-23 | KPTG-TRANSMIT-002409 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-27 | Auspan-TRANSMIT-00032 | NA | Trade Partner | 4 Precast shop drawings for construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC - Update register and distribute - KPTG-TRANSMIT-002019 |  | 2026-05-27 | KPTG-TRANSMIT-002019 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2025-12-18 | SMEPS-TRANSMIT-000002 | NA | Trade Partner | SME Shop Drawing Review | 10 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-000018 |  |  |  | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-27 | HDRAus-TRANSMIT-000137 | NA | Consultant | M3 Stage 6 - Town Planning Full Current Package | 39 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 139 | 2026-06-04 |  |  | 2026-06-11 | 2026-06-11 | NA | Closed | 39 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-27 | ARJAY-TRANSMIT-000005 | NA | Trade Partner | Arjay Sheds - Lunchroom Layout | 0 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Correspondences |  | 2026-05-27 | NA | Closed | 0 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-27 | PARR-TRANSMIT-000186 | NA | Trade Partner | P2680 - NDC M3 Stage 4 - Fuel - BFS BUILDERS WORKS PENETRATIONS L1 C1 - IFC | 1 | 0 | 0 | NA | APPROVED | 2026-05-27 | NA | 3356 | 2026-05-30 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-017979 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-21 | W_TITE-TRANSMIT-000001 | NA | Trade Partner | Waterproofing TDS | 0 | 1 | 0 | NA | APPROVED | 2026-05-21 | WF-000744 | NA | 2026-05-26 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-003620 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-28 | Nilsen3-TRANSMIT-000175 | NA | Trade Partner | Nilsen ELC Roof small power Shop Drawing FC-03 | 1 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | NA |  |  | only for inform team |  | 2026-05-28 | KPTG-TRANSMIT-017965 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-27 | PenskePS-TRANSMIT-000013 | NA | Trade Partner | IMPORTANT! Modelling Issues COLO 4 & 5 | 1 | 0 | 0 | KPTG-IntCorr-000471 | REJECTED | [5 empty] | KAPITOL ADVICE AWAITS: KPTG-IntCorr-000471, This Document is already reviewed. We need new Revision:KPTG-TRANSMIT-000758 |  | 2026-05-27 | KPTG-TRANSMIT-000758 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-28 | SMEPS-TRANSMIT-000297 | NA | Trade Partner | Re: SME - IFC Sample submissions | 2 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incomplete submission |  | 2026-05-28 | KPTG-RFI-008144 | Open | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-28 | ELLISAIR-TRANSMIT-000034 | NA | Trade Partner | Tech data - Mechanical Electrical | 0 | 6 | 0 | NA | APPROVED | 2026-05-28 | WF-000794 | NA | 2026-06-09 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-004339 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-28 | JCBa-TRANSMIT-000123 | NA | Consultant | Partition Plans IFC: Ground Floor | 5 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 1089 | 2026-06-04 |  | Review void as advised by DM | 2026-06-10 | 2026-06-10 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-28 | RDSBIM-TRANSMIT-000052 | NA | Trade Partner | MWYCCB ¦ LEVEL 01 INTERNAL FITOUT PLAN - UAT WC SHOWER | 1 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 297 | 2026-06-02 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-18 | Inhabit-TRANSMIT-000011 | NA | Consultant | NABERS Energy Rating Estimation Report | 1 | 0 | 0 | NA | APPROVED | 2025-12-18 | NA | 772 | 2025-12-22 |  |  | 2026-01-16 | 2026-01-16 | KPTG-TRANSMIT-002483 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-28 | Entire M-TRANSMIT-000016 | NA | Trade Partner | Mechanical Fire Matrix - Issued for Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with document number in the document. |  | 2026-05-28 | KPTG-SADV-000516 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-28 | RDSBIM-TRANSMIT-000041 | NA | Trade Partner | MEZZANINE CONCRETE PROFILE PLAN PART 4 | 1 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 675 | 2026-05-30 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-001989 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-28 | INTRFRM-TRANSMIT-000063 | NA | Trade Partner | Re: Geelong Edge - Roof Slab Post Tensioning Shop Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-05-28 | WF-000164 | NA | 2026-06-09 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-000770 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-28 | Auspan-TRANSMIT-000325 | NA | Trade Partner | Precast shop drawings for construction. Level 1. | 17 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Recieved 18 drawings, 17 drawings-updated register and distributed. no review for IFC drawings |  | 2026-05-28 | KPTG-TRANSMIT-002021 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-28 | WAM-TRANSMIT-000794 | NA | Consultant | IFC A16 - A21 - A40 & A71 | 13 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 677 | 2026-06-01 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-002141 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-27 | ZIA-TRANSMIT-000055 | NA | Trade Partner | Cx L3 Test Document | 0 | 40 | 0 | NA | APPROVED | 2026-05-28 | WF-001087 | NA | 2026-06-02 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-003827 | Closed | 40 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-28 | INTRFRM-TRANSMIT-000064 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 9) | 0 | 2 | 0 | NA | APPROVED | 2026-05-28 | WF-000165 | NA | 2026-06-05 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-000742 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-28 | Civilex-TRANSMIT-000252 | NA | Trade Partner | Stage 2 - Landscape drawing transmittal - Rev D - Updating Title | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Mismatch in drawings numbers, Inconsistent titles. |  | 2026-05-28 | KPTG-SADV-005609 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-28 | INTRFRM-TRANSMIT-000065 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 1) | 0 | 1 | 0 | NA | APPROVED | 2026-05-28 | WF-000166 | NA | 2026-06-05 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-000804 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-28 | Auscool-TRANSMIT-000039 | NA | Trade Partner | Level 1 - IFA BW drawings | 5 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 1093 | 2026-06-04 |  | 3 drawings already terminated and drawings updated. | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-002511 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-18 | KETE-TRANSMIT-000025 | NA | Trade Partner | Structural Calculation Report | 0 | 1 | 0 | NA | APPROVED | 2025-12-18 | NA | 776 | 2025-12-23 |  |  | 2026-01-15 | 2026-01-15 | KPTG-TRANSMIT-002451 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-28 | Civilex-TRANSMIT-000253 | NA | Trade Partner | Stage 2 - sample submission - Connolly key Joints/Dowel Cradle System | 0 | 2 | 0 | NA | APPROVED | 2026-05-28 | WF-005875 | NA | 2026-06-03 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-28 | PSGANZ-TRANSMIT-000010 | NA | Trade Partner | Fire Detection technical data resubmission | 0 | 2 | 0 | NA | APPROVED | 2026-05-28 | WF-000167 | NA | 2026-06-05 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-000704 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-28 | KPTG-TRANSMIT-002451 | NA | Trade Partner | Kingspan For approval | 0 | 1 | 0 | NA | APPROVED | 2026-05-28 | WF-000773 | NA | 2026-05-29 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-002483 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-28 | KPTG-TRANSMIT-002450 | NA | Trade Partner | Insulation Tech data | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-001002 - The project name and description provided are incorrect. | 2026-05-28 | 2026-05-28 | KPTG-IntCorr-001002 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-28 | IGS--TRANSMIT-000037 | NA | Consultant | Fwd: Revised Building Services Layouts | 21 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004339 - The documents have already been processed. | 2026-05-28 | 2026-05-28 | KPTG-SADV-004339 | Closed | 21 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-27 | WAM-TRANSMIT-000792 | NA | Consultant | ARCHITECTURAL SPEC | 0 | 1 | 0 | NA | REJECTED | [5 empty] | UPLOADED WITH DIFFERENT DOC NO |  | 2026-05-27 | KPTG-TRANSMIT-001984 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-27 | Jangho-TRANSMIT-000122 | NA | Consultant | Extrusion color Electro Medium Bronze Kinetic-Flat Sample Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-27 | WF-000602 | NA | 2026-06-12 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-28 | D&E-TRANSMIT-000765 | NA | Trade Partner | BMS System Architecture - Issued for Approval. | 0 | 1 | 0 | NA | APPROVED | 2026-05-28 | WF-005876 | NA | 2026-06-02 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-019448 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-28 | NWB-TRANSMIT-000017 | NA | Trade Partner | BAC Shop drawings | 8 | 0 | 0 | NA | REJECTED | [5 empty] | Error in document number, title, revision, title block, confidentiality. |  | 2026-05-28 | KPTG-SADV-000524 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-28 | Stowe-A-TRANSMIT-000594 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - LIGHTNING PROTECTION | 4 | 0 | 0 | NA | APPROVED | [5 empty] | Mixed status submission. Seems like they have used unusual status in submission. |  | 2026-05-28 | KPTG-SADV-005614 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-18 | RDSBIM-TRANSMIT-000039 | NA | Trade Partner | LOWER GROUND RCP KEY PLAN | 5 | 0 | 0 | NA | APPROVED | 2025-12-18 | NA | 774 | 2025-12-22 |  |  | 2026-01-21 | 2026-01-21 | KPTG-TRANSMIT-002527 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-28 | Stowe-A-TRANSMIT-000595 | NA | Trade Partner | Stowe - Tech Data - FIRE RATED JUNCTION BOXES LIFTS - AS PER KPTG-SADV-005347 | 0 | 1 | 0 | NA | APPROVED | 2026-05-28 | WF-005877 | NA | 2026-06-09 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-018714 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-27 | KPTG-TRANSMIT-003762 | NA | Trade Partner | CT ITP | 0 | 2 | 0 | NA | APPROVED | 2026-05-27 | WF-001084 | NA | 2026-06-03 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-003832 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-27 | KPTG-TRANSMIT-003763 | NA | Trade Partner | penske ITP | 0 | 1 | 0 | NA | APPROVED | 2026-05-27 | WF-001085 | NA | 2026-06-03 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-003797 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-27 | KPTG-TRANSMIT-003764 | NA | Trade Partner | penske ITP | 0 | 2 | 0 | NA | APPROVED | 2026-05-27 | WF-001085 | NA | 2026-06-03 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-003797 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-27 | Procore TXN 309 | 309 | Trade Partner | Generator Enclosure - Engineering Report | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-05-27 | KPTG-TRANSMIT-003777 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-28 | Baigents-TRANSMIT-000086 | SPARK-CRFI KPG-000118 | Trade Partner | MCC - Revised Steel - Issued for Construction | 6 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 298 | 2026-06-01 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-28 | SC-TRANSMIT-000008 | NA | Trade Partner | HDB IFC | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Error in document number |  | 2026-05-28 | KPTG-TRANSMIT-000954 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-28 | Civilex-TRANSMIT-000254 | NA | Trade Partner | Stage 2 - Landscape drawing transmittal - Rev D - Updating Numbering | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Issues with inconsistent document number and titles. |  | 2026-05-28 | KPTG-SADV-005618 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-28 | SMEPS-TRANSMIT-000214 | SPARK-CRFI KPG-000302 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0187 | 1 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 299 | 2026-06-01 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-000962 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-28 | TATE_-TRANSMIT-000025 | NA | Trade Partner | IFC scec shop drawings | 34 | 0 | 0 | NA | REJECTED | [5 empty] | Same Revision is already processed: KPTG-TRANSMIT-000763 |  | 2026-05-28 | KPTG-TRANSMIT-000763 | Closed | 34 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2025-12-02 | Baigents-TRANSMIT-000057 | NA | Trade Partner | Baigents-TRANSMIT-000057 - DH7-8 Door Penetration Steel - Updated Shop Drawings - For Fabrication | 7 | 0 | 0 | NA | APPROVED | 2025-12-03 | WF-000829 | NA | 2025-12-16 |  | Resubmitted on WF-000829, as discussed with Project Coordinator |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-18 | SKS Tech-TRANSMIT-000115 | NA | Trade Partner | HV cable tech data | 0 | 1 | 0 | NA | APPROVED | [5 empty] | Already received via SKS Tech-TRANSMIT-000105 - So no action - KPTG-IntCorr-000817 | 2026-01-23 | 2026-01-23 | KPTG-WTRAN-001426 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-28 | SMEPS-TRANSMIT-000215 | SPARK-CRFI KPG-000302 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0189 | 1 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 300 | 2026-06-01 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-000960 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-28 | WilsonPD-TRANSMIT-000004 | NA | Trade Partner | NXGEO1 - Wilson Samples resubmitted for approval | 0 | 19 | 0 | NA | REJECTED | [5 empty] | Error in revision number of a document. |  | 2026-05-28 | KPTG-IntCorr-000218 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-28 | PFP PL-TRANSMIT-000005 | NA | Trade Partner | S9 Level 1 IFA | 1 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 1003 | 2026-06-04 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-003901 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-28 | Schindle-TRANSMIT-000012 | NA | Trade Partner | Schindler Lift 2 IFA Drawing | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected. Submitted document is a combined set of shop drawings and resubmission is required |  | 2026-05-28 | KPTG-SADV-004476 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-28 | EFP-TRANSMIT-000023 | NA | Trade Partner | EFP Tech Data response to Consultant comments | 0 | 1 | 0 | NA | APPROVED | 2026-05-28 | WF-000278 | NA | 2026-05-29 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-000789 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-28 | Stowe-A-TRANSMIT-000596 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - LIGHTNING PROTECTION | 1 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 4237 | 2026-06-10 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-019034 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-28 | D&E-TRANSMIT-000762 | NA | Trade Partner | Fwd: NXM3S4 - Chiller Roof - Builders Works Layout Zones - Issued For Construction | 4 | 0 | 0 | NA | APPROVED | [5 empty] | FOR INFORMATION ONLY |  | 2026-05-28 | KPTG-TRANSMIT-017935 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-05-28 | KALLIBRE-TRANSMIT-000011 | NA | Trade Partner | MEL11 - Door Hardware Tech Data - For Approval | 0 | 35 | 0 | NA | REJECTED | [5 empty] | REJECTED: covering pages are not attached: KPTG-IntCorr-000477 |  | 2026-05-28 | KPTG-IntCorr-000477 | Closed | 35 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-28 | Stowe-A-TRANSMIT-000597 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - LIGHTNING PROTECTION - ROLLING SPHERES | 3 | 0 | 0 | NA | APPROVED | [5 empty] | For information only, Updated in Aconex Document Register and ACC as advised by Jaison. |  | 2026-05-28 | KPTG-TRANSMIT-017971 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-28 | L.E.S.-TRANSMIT-000003 | NA | Trade Partner | Electrical inground drawings IFA | 2 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 679 | 2026-06-05 |  |  | 2026-06-21 | 2026-06-22 | KPTG-TRANSMIT-002399 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-17 | Auspan-TRANSMIT-000026 | NA | Trade Partner | Precast shop drawings for construction. | 18 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong title guide-KPTG-TRANSMIT-000382 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-28 | SKS Tech-TRANSMIT-000151 | NA | Trade Partner | Issued for construction lighting layout roof | 3 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 3373 | 2026-06-01 |  |  | 2026-08-24 | 2026-08-24 | KPTG-TRANSMIT-020895 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-28 | PCForm-TRANSMIT-000171 | NA | Trade Partner | Re: Stair 05 shop drawings | 1 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due to missing of revision in inside drawing |  | 2026-05-28 | KPTG-RFI-008147 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-28 | VERTIV-TRANSMIT-000025 | NA | Trade Partner | NEXT DC GE 01 _ MATERIAL SUBMISSION _ FIRE DAMPER (FOA-1) | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Error in document number. |  | 2026-05-28 | KPTG-SADV-000514 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-28 | D&E-TRANSMIT-000763 | NA | Trade Partner | Industrial Water Tanks - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | [5 empty] | ONLY FOR INFORMATION |  | 2026-05-28 | KPTG-IntCorr-013920 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-28 | D&E-TRANSMIT-000766 | NA | Trade Partner | Fwd: NXM3S4 - Cooling Tower Mesh - Builders Works Layout Zones - Issued For Construction | 5 | 0 | 0 | NA | APPROVED | [5 empty] | ONLY FOR INFORM BORDER TEAM |  | 2026-05-28 | KPTG-TRANSMIT-017963 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-28 | VERTIV-TRANSMIT-000024 | NA | Trade Partner | NEXT DC GE 01 _ MATERIAL SUBMISSION _ LOUVRE (FOA-1) | 0 | 1 | 0 | NA | APPROVED | 2026-05-28 | WF-000168 | NA | 2026-06-05 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-000861 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-28 | D&E-TRANSMIT-000764 | NA | Trade Partner | Fwd: Industrial Water Tanks - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | [7 empty] | 2026-05-28 | KPTG-TRANSMIT-017946 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-28 | WAM-TRANSMIT-000795 | NA | Consultant | Architectural Specification - IFC | 0 | 1 | 0 | NA | APPROVED | 2026-05-28 | WF-000607 | NA | 2026-06-01 |  |  | 2026-06-03 | 2026-06-15 | KPTG-TRANSMIT-002271 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-28 | WilsonPD-TRANSMIT-000005 | NA | Trade Partner | HYDRAULIC SERVICES - PENETRATION SERVICES ROOF LAYOUT DRAWING FOR APPROVAL | 1 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 252 | 2026-06-03 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-000974 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-28 | VIA Arch-TRANSMIT-000144 | NA | Consultant | Signage Drawings Issue For Building Permit | 5 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 1006 | 2026-06-02 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-003506 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-17 | SMEPS-TRANSMIT-000002 | NA | Trade Partner | Shop Drawings - Ingrounds Elec and Telecomm | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong Naming convention and revision-KPTG-TRANSMIT-000371 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-28 | Civilex-TRANSMIT-000255 | NA | Trade Partner | Stage 2 - sample submission - Landscape Materials | 0 | 4 | 0 | NA | REJECTED | [5 empty] | Incorrect document number inside a document. |  | 2026-05-28 | KPTG-SADV-005628 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-28 | VIA Arch-TRANSMIT-000149 | NA | Consultant | Architecture - Stage 11 Concrete Profile Plan Level 1 - IFBP-5 | 1 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 1008 | 2026-06-02 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-003872 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-06 | Auspan-TRANSMIT-000012 | NA | Trade Partner | Cast in plate and fish plate detail for construction. | 2 | 0 | 0 | NA | APPROVED | 2026-05-06 | WF-000115 | NA | 2026-05-15 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-000698 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-28 | VIA Arch-TRANSMIT-000148 | NA | Consultant | Architecture - Stage 9 - Concrete Profile Plans - Ground, Level 1 & Level 2 | 3 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 1010 | 2026-06-02 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-003607 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-28 | RDSBIM-TRANSMIT-000043 | NA | Trade Partner | MEZZANINE CONCRETE PROFILE PLAN PART 4 | 1 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 681 | 2026-05-30 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-002064 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-28 | RDSBIM-TRANSMIT-000064 | NA | Trade Partner | GREYSTAR LEVEL 05 CONCRETE PROFILE PLAN | 6 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 1090 | 2026-06-04 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-002845 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-28 | Auspan-TRANSMIT-000327 | NA | Trade Partner | Precast shop drawings for construction. 0G2013 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC - Update register and distribute KPTG-TRANSMIT-002039 |  | 2026-05-28 | KPTG-TRANSMIT-002039 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-28 | Auspan-TRANSMIT-000326 | NA | Trade Partner | OUTSTANDING L1 DRAWINGS | 4 | 0 | 0 | KPTG-IntCorr-000617 | APPROVED |  | NA | NA |  |  | Precast IFC - Update register and distribute -KPTG-TRANSMIT-002042 1 Rejected drawing included waiting for confirmation- KPTG-IntCorr-000617 |  | 2026-05-28 | KPTG-TRANSMIT-002042 | Open | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-28 | TTW-TRANSMIT-000032-Drawings | NA | Consultant | M3 Sage 6 Facade performance specification and drawing | 16 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 145 | 2026-06-05 |  |  | 2026-06-11 | 2026-06-11 | NA | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-28 | TTW-TRANSMIT-000032-Spec | NA | Consultant | M3 Sage 6 Facade performance specification and drawing | 0 | 1 | 0 | NA | APPROVED | 2026-05-28 | NA | 147 | 2026-06-05 |  |  | 2026-06-11 | 2026-06-11 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-17 | WGAVIC-TRANSMIT-000036 | NA | Consultant | Structural Drawings - Level 2 Slab/Steel Structure Above Level 2 - Issued for Information/Certification | 26 | 0 | 0 | NA | APPROVED | 2025-12-18 |  | 149 | 2025-12-23 |  |  |  | 2026-01-12 | KPTG-TRANSMIT-000474 | Closed | 26 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-28 | NXT-TRANSMIT-000348-TRF | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 01 | 0 | 3 | 0 | NA | APPROVED | 2026-05-28 | NA | 141 | 2026-06-05 |  |  | 2026-06-11 | 2026-06-11 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-28 | NXT-TRANSMIT-000348-WAM | NA | Client | M3 Stage 6 - Main Works Issued for Tender - 01 | 0 | 1 | 0 | NA | APPROVED | 2026-05-28 | NA | 143 | 2026-06-05 |  |  | 2026-06-11 | 2026-06-11 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-28 | HDRAus-TRANSMIT-000139-DWG | NA | Consultant | M3 Stage 6 - Architectural Documentation Contract Issue (IFCN) | 211 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 157 | 2026-06-05 |  |  | 2026-06-11 | 2026-06-11 | NA | Closed | 211 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-28 | HDRAus-TRANSMIT-000139-spe | NA | Consultant | M3 Stage 6 - Architectural Documentation Contract Issue (IFCN) | 0 | 9 | 0 | NA | APPROVED | 2026-05-28 | NA | 155 | 2026-06-05 |  |  | 2026-06-11 | 2026-06-11 | NA | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-28 | Auscool-TRANSMIT-000094 | NA | Trade Partner | Mezzanine Mech Shop Drawings For Review | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001004 - requested guidance,but no response received yet. KPTG-IntCorr-001013-As per instructions from Mark, we are not taking any action on this transmit. | 2026-06-01 | 2026-06-01 | KPTG-IntCorr-001013 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-28 | PTA-TRANSMIT-000003 | NA | Consultant | M3 Stage 6 - PTA Arch Documentation issued for coordination | 1 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 151 | 2026-06-05 |  |  | 2026-06-11 | 2026-06-11 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-28 | WOCEP-TRANSMIT-000002 | NA | Trade Partner | tech data sample | 0 | 12 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004346 - DOCUMENT NUMBER AND REVISION ARE INCORRECT | 2026-05-28 | 2026-05-28 | KPTG-SADV-004346 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-15 | INDS-TRANSMIT-000038 | NA | Trade Partner | Dry Fire - Level 12 to Level 20 | 9 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 666 | 2026-06-22 |  | KPTG-IntCorr-001034 - As per instruction from Mark, we hold this transmit. | 2026-06-30 | 2026-06-30 | KPTG-SADV-004711 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-28 | SMEPS-TRANSMIT-000265 | NA | Trade Partner | DH7&8 As Built drawings not on Aconex | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Information |  | 2026-05-28 | NA | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-28 | RDSBIM-TRANSMIT-000070 | NA | Trade Partner | 671CHP LEVEL 02 CONCRETE PROFILE PLAN AND SECTION | 3 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 551 | 2026-06-18 |  | review 531 Void and new review 551 initiated on 10/6/26 | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-001227 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-18 | Endfire-TRANSMIT-000050 | NA | Trade Partner | EndFire IFC Drawings | 11 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED - |  | 2025-12-18 | KPTG-IntCorr-000819 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-28 | RDSBIM-TRANSMIT-000071 | NA | Trade Partner | 671CHP LEVEL 01 CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | NA | APPROVED | 2026-06-10 | NA | 550 | 2026-06-18 |  | Review 533 voided and initiated new review on 10/6/26 | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-001225 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-13 | WSP ANZ-TRANSMIT-000011,06 |  | Consultant | WSP Updated 80% Tender Issue Drawings (Mechanical) | 9 | 0 | 0 | NA | APPROVED | 2026-05-13 | NA | 95 | 2026-05-19 |  |  | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-000104 | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-28 | HGP-TRANSMIT-000001 | NA | Trade Partner | Level 1 Window Shop drawings | 9 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 1013 | 2026-06-04 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-004601 | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-28 | ELLISAIR-TRANSMIT-000040 | NA | Trade Partner | MSSB Cooling strings | 0 | 1 | 0 | NA | APPROVED | 2026-05-28 | WF-000807 | NA | 2026-06-04 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-004036 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-28 | DLTS-TRANSMIT-000009 | NA | Trade Partner | L1 H Frames-Re-IFA | 25 | 0 | 0 | NA | APPROVED | 2026-05-28 | WF-000803 | NA | 2026-06-04 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-003799 | Closed | 25 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-28 | Nilsen3-TRANSMIT-000025 | NA | Trade Partner | Nilsen Shop Drawings for Approval | 23 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 1001 | 2026-06-04 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-003990 | Closed | 23 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-28 | ELLISAIR-TRANSMIT-000039 | NA | Trade Partner | IFA - Filters | 0 | 1 | 0 | NA | APPROVED | 2026-05-28 | WF-000801 | NA | 2026-06-09 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-004028 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-28 | ELLISAIR-TRANSMIT-000038 | NA | Trade Partner | Ductwork & Insulation | 0 | 1 | 0 | NA | APPROVED | 2026-05-28 | WF-000800 | NA | 2026-06-09 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-004024 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-28 | WilsonPD-TRANSMIT-000029 | NA | Trade Partner | Fire Penetration Equipment Tech Data | 0 | 2 | 0 | NA | APPROVED | 2026-05-28 | WF-000799 | NA | 2026-06-08 |  | Resubmitted for Surveyor & Fire Engineer review |  |  |  | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-28 | WilsonPD-TRANSMIT-000021 | NA | Trade Partner | Specified Fixtures for Approval | 0 | 15 | 0 | NA | APPROVED | 2026-05-28 | WF-000798 | NA | 2026-06-02 |  | Resubmitted for VIA review as per Aurecon comments | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-003831 | Closed | 15 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-18 | SKS Tech-TRANSMIT-000116 | NA | Trade Partner | Fire rated wall box | 0 | 1 | 0 | NA | APPROVED | 2025-12-18 | WF-000665 | NA | 2025-12-25 |  |  | 2026-01-16 | 2026-01-16 | KPTG-WTRAN-001351 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-28 | ELLISAIR-TRANSMIT-000037 | NA | Trade Partner | Fans Stage 10 & 11 | 0 | 1 | 0 | NA | APPROVED | 2026-05-28 | WF-000796 | NA | 2026-06-09 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-004582 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-28 | ELLISAIR-TRANSMIT-000031 | NA | Trade Partner | Tech data submission - consumables | 0 | 1 | 0 | NA | APPROVED | 2026-05-28 | WF-000795 | NA | 2026-06-09 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-003972 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-28 | ELLISAIR-TRANSMIT-000036 | NA | Trade Partner | Technical Data Submission - VRF Stages 10 & 11 | 0 | 1 | 0 | NA | APPROVED | 2026-05-28 | WF-000793 | NA | 2026-06-09 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-004727 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-29 | Civilex-TRANSMIT-000256 | NA | Trade Partner | Stage 2 - sample submission - Landscape Materials - Updated naming | 0 | 4 | 0 | NA | APPROVED | 2026-05-29 | WF-005883 | NA | 2026-06-03 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-017995 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-29 | ADP-TRANSMIT-000329 | NA | Consultant | Re: ADP MEL4780 - EL & FID Drawings (Status change only) | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For update the register |  | 2026-05-29 | KPTG-IntCorr-013982 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-29 | INDS-TRANSMIT-000031 | NA | Trade Partner | Wet Fire - Ground | 5 | 0 | 0 | NA | APPROVED | 2026-05-29 | NA | 1098 | 2026-06-05 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-002168 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-29 | INDS-TRANSMIT-000030 | NA | Trade Partner | Updated Floor Penetration Layout | 4 | 0 | 0 | NA | APPROVED | 2026-05-29 | NA | 1100 | 2026-06-05 |  | 2 Drawings already terminated | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-002581 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-29 | GPSElec-TRANSMIT-000019 | NA | Trade Partner | Generator ACB light/siren | 0 | 1 | 0 | NA | APPROVED | 2026-05-29 | WF-000811 | NA | 2026-06-10 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-004448 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-29 | SC-TRANSMIT-000009 | NA | Trade Partner | HDB IFC | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect drawing status, revision and title Status block missing |  | 2026-05-29 | KPTG-TRANSMIT-000955 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-29 | JCBa-TRANSMIT-000124 | NA | Consultant | Updated Architectural Documentation - Robe Joinery Schedules | 3 | 0 | 0 | NA | APPROVED | 2026-05-29 | NA | 1103 | 2026-06-05 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-002216 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-18 | Nilsen3-TRANSMIT-000125 | NA | Trade Partner | Nilsen As-built Documents | 23 | 0 | 0 | NA | APPROVED | [5 empty] | As-Built, No review required. Distributed to the Project Team. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-29 | RDSBIM-TRANSMIT-000065 | NA | Trade Partner | GREYSTAR ¦ LEVEL 01 CONCRETE PROFILE PLAN AND SECTION ZONE 1, 2, 3, 4 | 7 | 0 | 0 | NA | APPROVED | 2026-05-29 | NA | 1106 | 2026-06-05 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-002152 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-05-27 | RDSBIM-TRANSMIT-000273 | NA | Trade Partner | NXM3S3 ¦ GROUND FLOOR GENERAL ARRANGEMENT PLAN | 1 | 0 | 0 | NA | APPROVED |  | NA | NA | [5 empty] | KPTG-IntCorr-013954 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-29 | INTRFRM-TRANSMIT-000066 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 10) | 0 | 1 | 0 | NA | APPROVED | 2026-05-29 | WF-000170 | NA | 2026-06-08 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-000720 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-28 | INGEN3D-TRANSMIT-000083 | NA | Trade Partner | I3D-389 District Living - Level 6-8 - IFA Resubmission (28-05-2026) | 12 | 0 | 0 | NA | APPROVED | 2026-05-28 | WF-000604 | NA | 2026-06-04 |  |  | 2026-06-04 | 2026-06-01 | KPTG-TRANSMIT-002080 | Closed | 12 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-28 | INGEN3D-TRANSMIT-000084 | NA | Trade Partner | I3D-389 District Living - Level 7-9 - PC0403-4 & PC0419 - New IFA (28-05-2026) | 4 | 0 | 0 | NA | APPROVED | 2026-05-28 | WF-000605 | NA | 2026-06-04 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-002055 | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-28 | TTW-TRANSMIT-000164 | NA | Trade Partner | PC7 certification update | 1 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 683 | 2026-05-29 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-002022 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-28 | RDSBIM-TRANSMIT-000042 | NA | Trade Partner | DISTLV - MEZZANINE CONCRETE PROFILE PLAN PART 4 | 1 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-05-28 | KPTG-TRANSMIT-001992 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-28 | Jangho-TRANSMIT-000126 | NA | Trade Partner | Glass Sample Submission(GL-10 Option 3) | 0 | 1 | 0 | NA | APPROVED | 2026-05-28 | WF-000611 | NA | 2026-06-16 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-002931 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-29 | D&E-TRANSMIT-000258 | NA | Trade Partner | Mechanical Services Commissioning Plan Rev-01 | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Incorrect revision |  | 2026-05-29 | KPTG-TRANSMIT-000959 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-28 | PARR-TRANSMIT-000061 | NA | Trade Partner | PARR-TRANSMIT-000061 | 0 | 6 | 0 | NA | APPROVED | 2026-05-28 | WF-001088 | NA | 2026-06-02 |  |  | 2026-06-01 | 2026-06-30 | KPTG-TRANSMIT-003823, KPTG-TRANSMIT-004002 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-18 | SKS Tech-TRANSMIT-000117 | NA | Trade Partner | Basement GLP | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | FC Documents - Register updated |  | 2025-12-18 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-28 | ZIA-TRANSMIT-000056 | NA | Trade Partner | Cx L1 Results - CSMS Software | 0 | 1 | 0 | NA | APPROVED | 2026-05-28 | WF-001089 | NA | 2026-06-03 |  | Terminated as per KPTG-SADV-003354 | 2026-05-29 | 2026-05-29 | KPTG-SADV-003354 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-28 | Baigents-TRANSMIT-000206 | NA | Trade Partner | Level 4 Platform FC-3 Updated Assemblies | 1 | 0 | 0 | KPTG-IntCorr-001360 | APPROVED |  | NA | NA |  |  | Luke to advise - Register updated and forwarded to all parties |  | 2026-06-02 | KPTG-TRANSMIT-003838 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-28 | Jordan-TRANSMIT-000130 | NA | Trade Partner | D1S2 Commissioning Scripts | 0 | 10 | 0 | KPTG-IntCorr-001364 | APPROVED | 2026-05-29 | WF-001091 | NA | 2026-06-03 |  | Ibrahim to Confirm - KPTG-IntCorr-001364 | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-003819 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-28 | ZIA-TRANSMIT-000057 | NA | Consultant | CSMS Design Documentation | 0 | 4 | 0 | KPTG-IntCorr-001361 | APPROVED |  | NA | NA |  |  | Harry to confirm - KPTG-IntCorr-001361 |  | 2026-06-04 | KPTG-IntCorr-001441 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-29 | D&E-TRANSMIT-000259 | NA | Trade Partner | Mechanical Services Commissioning Plan Rev-01 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | No Ineight review needed as per Alex's advise - KPTG-IntCorr-003140 |  | 2026-06-03 | KPTG-IntCorr-003145 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-29 | INGEN3D-TRANSMIT-000086 | NA | Trade Partner | Level 6-8 - Precast Columns - IFC | 39 | 0 | 0 | NA | APPROVED | 2026-05-29 | WF-000612 | NA | 2026-06-08 |  |  | 2026-06-05 | 2026-06-09 | KPTG-TRANSMIT-002187 | Closed | 39 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-29 | Civilex-TRANSMIT-000257 | NA | Trade Partner | Stage 2 - Landscape drawing transmittal - Rev D - Updated naming 29.05.2026 | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Typo error in document. |  | 2026-05-29 | KPTG-TRANSMIT-017991 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-29 | D&E-TRANSMIT-000769 | NA | Trade Partner | NXM3S4 - Ground - Mechanical Duct Layout - Zone 10 & IW Tank Room - Issued For Construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-05-29 | KPTG-TRANSMIT-017992 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-29 | MCGC-TRANSMIT-000010 | NA | Consultant | Transmittal of Updates to Drawing Register - 205, 207, 307 | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: wrong Revision, requested to resubmit:KPTG-SADV-004496 |  | 2026-05-29 | KPTG-SADV-004496 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-29 | Civilex-TRANSMIT-000258 | NA | Trade Partner | Stage 2 - Landscape drawing transmittal - Rev D - Updated naming 29.05.2026 | 9 | 0 | 0 | NA | APPROVED | 2026-05-29 | NA | 4240 | 2026-06-05 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-018953 | Closed | 9 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2025-12-18 | SKS Tech-TRANSMIT-000118 | NA | Trade Partner | TELECOMMUNICATIONS LAYOUT-DAY 1-LEVEL 4 & 5 | 6 | 0 | 0 | NA | APPROVED | 2025-12-18 | WF-000666, 747 | 778,780 | 2025-12-20 |  |  | 2026-01-29 | 2026-01-30 | KPTG-TRANSMIT-002499, KPTG-TRANSMIT-002637 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-29 | P & R-TRANSMIT-000088 | NA | Trade Partner | P&R Commissioning Management Plan MAY 2026 | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | A MANUAL- IFC TRANMITTED TO ALL PARTIES-KPTG-TRANSMIT-002920 |  | 2026-05-29 | KPTG-TRANSMIT-002920 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-29 | TTW-TRANSMIT-000165 | NA | Consultant | BP2a - Issued for Construction | 2 | 0 | 0 | NA | APPROVED | 2026-05-29 | NA | 685 | 2026-06-02 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-002057 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-29 | ZIA-TRANSMIT-000096 | NA | Trade Partner | M3S4 CSMS OS Location Roof & Roof Plant Zone (FOA-1) | 5 | 0 | 0 | NA | APPROVED | 2026-05-29 | NA | 3382 | 2026-06-10 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-020147 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-29 | INTRFRM-TRANSMIT-000067 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 11) | 0 | 1 | 0 | NA | APPROVED | 2026-05-29 | WF-000171 | NA | 2026-06-08 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-000737 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-05-29 | ADP-TRANSMIT-000330 | NA | Consultant | ADMP MEL4561 - CAN-E-03 - Cable Formation & Cleat Compliance | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-05-29 | KPTG-TRANSMIT-018000 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-29 | D&E-TRANSMIT-000770 | NA | Trade Partner | Fwd: NXM3S4 - Upper Roof Level - CHW & CCW Pipe Layout Zone 5 & 7 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-05-29 | KPTG-TRANSMIT-018004 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-29 | Tradetec-TRANSMIT-000453 | NA | Trade Partner | IFA - HVP20,24,25 | 3 | 0 | 0 | NA | APPROVED | 2026-05-29 | NA | 3385 | 2026-06-10 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-018966 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-29 | WilsonPD-TRANSMIT-000006 | NA | Trade Partner | NEXGEO1 - WPD Samples for Approval | 0 | 17 | 0 | NA | APPROVED | 2026-05-29 | WF-000172 | NA | 2026-06-08 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-000766 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-29 | KETE-TRANSMIT-000027 | NA | Trade Partner | KETE-TRANSMIT-000027 Kete - Zone 03 Shop Drawing Submission Rev _IFC A | 107 | 0 | 0 | NA | APPROVED | 2026-05-29 | NA | 1108 | 2026-06-05 |  | Review terminated as advised by Kapitol PC Alex M. Updated drawings are expected to be issued. | 2026-07-20 | 2026-07-20 | NA | Closed | 107 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-29 | Jangho-TRANSMIT-000128 | NA | Trade Partner | Brick Sample Board Submission Option 2 | 0 | 1 | 0 | NA | APPROVED | 2026-05-29 | WF-000614 | NA | 2026-06-16 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-19 | ARCST-TRANSMIT-000162 | NA | Trade Partner | C2 Switchroom & Cooling Tower HD Bolts - Issued for Review | 9 | 0 | 0 | NA | APPROVED | 2025-12-19 | WF-003682 | NA | 2026-01-09 |  |  |  | 2026-01-28 | KPTG-TRANSMIT-011931 KPTG-TRANSMIT-011973 | Closed | 9 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-29 | Jangho-TRANSMIT-000129 | NA | Trade Partner | Brick Sample Board Submission Option 3 | 0 | 1 | 0 | NA | APPROVED | 2026-05-29 | WF-000615 | NA | 2026-06-16 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-29 | Jangho-TRANSMIT-000130 | NA | Trade Partner | Brick Sample Board Submission Option 4 | 0 | 1 | 0 | NA | APPROVED | 2026-05-29 | WF-000616 | NA | 2026-06-16 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-05-29 | D&E-TRANSMIT-000260 | NA | Trade Partner | Mechanical Services Seismic Level-01 Duct & Pipe Drawings | 10 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect date |  | 2026-05-29 | KPTG-TRANSMIT-000966 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-29 | Jangho-TRANSMIT-000132 | NA | Trade Partner | Brick Sample Board Submission Option 6 | 0 | 1 | 0 | NA | APPROVED | 2026-05-29 | WF-000618 | NA | 2026-06-16 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-29 | Jangho-TRANSMIT-000127 | NA | Trade Partner | Brick Sample Board Submission Option 1 | 0 | 1 | 0 | NA | APPROVED | 2026-05-29 | WF-000618 | NA | 2026-06-16 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-29 | L.E.S.-TRANSMIT-000004 | NA | Trade Partner | Slab Penetrations - Level 1 IFA | 2 | 0 | 0 | NA | APPROVED | 2026-05-29 | NA | 687 | 2026-07-08 |  |  | 2026-06-21 | 2026-06-22 | KPTG-TRANSMIT-002410 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-29 | HDRAus-TRANSMIT-000496 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD | 17 | 0 | 0 | NA | APPROVED |  | NA | 3393 | 2026-06-02 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018349 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-05-29 | ccair-TRANSMIT-000018 | NA | Trade Partner | Mechanical Services B4 TO B2 Builders works and Duct & Pipe IFC [0] | 6 | 0 | 0 | NA | APPROVED | 2026-05-29 | NA | 537 | 2026-06-05 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-001240 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-29 | D&E-TRANSMIT-000767 | NA | Trade Partner | Fwd: NXM3S4 - Level 1 - CHW Pipe Layout - Zone 8 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-05-29 |  |  |  |  | ONLY FOR INFORMATION |  | 2026-05-29 | KPTG-TRANSMIT-017976 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-29 | PCForm-RTRFI-000041 | NA | Trade Partner | Re: Stair 05 shop drawings | 1 | 0 | 0 | NA | APPROVED | 2026-05-29 | WF-005884 | NA | 2026-06-10 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2025-12-02 | Leemark-TRANSMIT-000003 | SPARK-CRFI-KPG-000431 & SPARK-CRFI-KPG-000433 | Trade Partner | Tech Data Submission-LEEMARK | 0 | 41 | 0 | KPTG-IntCorr-001018 | APPROVED | [5 empty] | No need further action |  | 2026-01-21 | KPTG-TRANSMIT-000351 | Closed | 39 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2025-12-18 | fjc-TRANSMIT-000119 | NA | Consultant | Re: Substation Mech Openings | 1 | 0 | 0 | NA | APPROVED | 2025-12-19 |  | 499 | 2025-12-26 |  |  | 2026-01-15 | 2026-01-15 | KPTG-SADV-002618 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-29 | Auspan-TRANSMIT-000329 | NA | Trade Partner | Transmit 0G4047 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC - Update register and distribute - KPTG-TRANSMIT-002063 |  | 2026-05-29 | KPTG-TRANSMIT-002063 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-29 | ZIA-TRANSMIT-000095 | NA | Trade Partner | -SHOP DRAWING - ZIA-TRANSMIT-000095 M3S4 CSMS OS & ORMB Location (FOA-1) | 6 | 0 | 0 | NA | APPROVED | 2026-05-29 | NA | 3377 | 2026-06-10 |  |  |  | 2026-06-11 | NA | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-05-29 | Auspan-TRANSMIT-000328 | NA | Trade Partner | Precast shop drawings for construction. Level 1 | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC - Update register and distribute . |  | 2026-05-29 | KPTG-TRANSMIT-002059 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-29 | Ardon-TRANSMIT-000033 | NA | Trade Partner | Re: Stage 4 Door Frame Shop Drawings | 11 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due to missing of lack of details |  | 2026-05-29 | KPTG-RFI-008172 | Closed | 11 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-29 | D&E-TRANSMIT-000771 | NA | Trade Partner | NXM3S4 - Level 1 - Mechanical Duct Layout - Zone 8 - Issued For Approval - | 1 | 0 | 0 | NA | APPROVED | 2026-05-29 | NA | 3394 | 2026-06-11 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-29 | SMEPS-TRANSMIT-000220 | NA | Trade Partner | SME UpRev of Docs for Construction | 13 | 0 | 0 | NA | REJECTED | [5 empty] | The revision number is mismatch and document error |  | 2026-05-29 | KPTG-TRANSMIT-000919 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-29 | JCI-TRANSMIT-000026 | NA | Trade Partner | Alarm Updates To DoO | 2 | 0 | 0 | NA | REJECTED | [5 empty] | The document number and revision number is mismatch |  | 2026-05-29 | KPTG-IntCorr-000456 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-29 | JCI-TRANSMIT-000027 | NA | Trade Partner | Alarm Updates To DoO | 2 | 0 | 0 | NA | REJECTED | [5 empty] | the revision number is mismatching files rejected |  | 2026-05-29 | KPTG-IntCorr-000459 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-05-29 | ETNInd-TRANSMIT-000021 | NA | Trade Partner | MEL05 C4 EPMS DEVICES LIST | 0 | 1 | 0 | NA | APPROVED | 2026-05-29 | WF-000442 | NA | 2026-06-03 |  | NA | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-000942 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-29 | Carr-TRANSMIT-000067 | NA | Consultant | Town Planning Update - Elevations, Sections, Materials | 3 | 0 | 0 | NA | APPROVED | 2026-05-29 | NA | 165 | 2026-06-05 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-000202 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-09 | NXT-TRANSMIT-001123 PenskePS-TRANSMIT-000005 | NA | Trade Partner | M3 STAGE 4 Generator General Arrangement Drawings | 4 | 0 | 0 | NA | APPROVED | 2025-12-09 | WF-003550 | NA | 2025-12-16 |  |  |  | 2025-12-19 | NXT-WTRAN-001299 | Closed | 4 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-29 | WSP ANZ-TRANSMIT-000015 | NA | Consultant | WSP - Electrical, Hydraulic, Mechanical & Fire Protection drawings & Specifications for Approval | 47 | 3 | 0 | NA | REJECTED | [5 empty] | Aconex registered drawing status does not match the actual drawing status. |  | 2026-05-29 | KPTG-DA-000303 | Closed | 50 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-29 | WSP ANZ-TRANSMIT-000014 | NA | Consultant | WSP - Mechanical services updated L1 Demolition drawing | 1 | 0 | 0 | NA | APPROVED | 2026-05-29 | NA | 163 | 2026-06-05 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-000199 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-29 | WSP ANZ-TRANSMIT-000013 | NA | Consultant | WSP - Fire services updated L1 Demolition drawing | 1 | 0 | 0 | NA | APPROVED | 2026-05-29 | NA | 160 | 2026-06-05 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-000196 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-29 | VOGUE-TRANSMIT-000013 | NA | Trade Partner | Vogue Grange Samples Transmittals | 0 | 19 | 0 | NA | REJECTED | [5 empty] | The documenrts and revision number is incorrect |  | 2026-05-29 | KPTG-IntCorr-001793 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-29 | ADP-TRANSMIT-000331 | NA | Consultant | ADP MEL4780 - ME Drawings (Status change only) | 3 | 0 | 0 | KPTG-TRANSMIT-018011 | APPROVED | [5 empty] | Seek advice from Kapitol |  | 2026-06-01 | KPTG-IntCorr-014061 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-29 | LANSA-TRANSMIT-000107 | NA | Trade Partner | Levels 2-8 Water Services Layouts with Breezeway Hose Taps Added | 10 | 0 | 0 | NA | REJECTED | [5 empty] | document number is mismatch |  | 2026-05-29 | KPTG-IntCorr-001797 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-04-22 | PARR-TRANSMIT-000055 | NA | Trade Partner | Fuel Services - Cx PLAN & TEMPLATES | 0 | 13 | 0 | KPTG-IntCorr-001210 | APPROVED | 2026-04-29 | WF-001031 | NA | 2026-06-05 |  | Clarification from harrY | 2026-05-28 | 2026-05-28 | KPTG-TRANSMIT-003779 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-29 | JCBa-TRANSMIT-000260 | NA | Consultant | BTR GF Drawings | 10 | 0 | 0 | NA | REJECTED | [5 empty] | Kindly submit the DWFX file for this below transmittal ASAP. |  | 2026-05-29 | DRAFT-018404 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-29 | W_TITE-TRANSMIT-000003 | NA | Trade Partner | Data Sheet for Waterproofing to Roof | 0 | 1 | 0 | NA | APPROVED | 2026-05-29 | WF-000816 | NA | 2026-06-03 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-003806 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-29 | RDSBIM-TRANSMIT-000007 | NA | Trade Partner | LEVEL 01 CONCRETE PROFILE KEYPLAN AND SECTION - BLOCK 1 | 1 | 0 | 0 | NA | APPROVED | 2026-05-29 | NA | 153 | 2026-06-08 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-000291 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-19 | ARCST-TRANSMIT-000165 | NA | Trade Partner | Stage 4 C1 Upper Gantry Switchroom Handrails - Issued for Construction | 11 | 0 | 0 | NA | APPROVED | 2025-12-19 | WF-003683 | NA | 2025-12-26 |  |  | 2026-03-06 | 2026-03-06 | KPTG-TRANSMIT-013946 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-29 | D&E-TRANSMIT-000006 | NA | Trade Partner | Block 1 - GF Precast Penetrations - Issued for Approval | 4 | 0 | 0 | KPTG-IntCorr-000131 | APPROVED |  | NA | NA |  |  | update only |  | 2026-06-01 | NA | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-29 | WGAVIC-TRANSMIT-000005 | NA | Consultant | M3 S6 Civil Earthworks Drawings - Issued for Construction | 5 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Title block not matching |  | 2026-05-29 | KPTG-DA-000278 | Closed | 5 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-05-29 | TTW-TRANSMIT-000033 | NA | Consultant | Stage 6 - Civil scope handover list | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Model-for information |  | 2026-05-29 | NA | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S1D78 | 2026-05-29 | SMEPS-TRANSMIT-000266 | NA | Trade Partner | SME DH8 Telecommunications AS BUILT | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As built |  | 2026-05-29 | NA | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-29 | ELLISAIR-TRANSMIT-000041 | NA | Trade Partner | Side Stream Filtration & Water Treatment | 0 | 1 | 0 | NA | APPROVED | 2026-05-29 | WF-000817 | NA | 2026-06-10 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-004145 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-29 | Eneraque-TRANSMIT-000022 | NA | Trade Partner | Datasheets | 0 | 6 | 0 | NA | APPROVED | 2026-05-29 | WF-000815 | NA | 2026-06-10 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-004472 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-29 | Arc Plas-TRANSMIT-000009 | NA | Trade Partner | Updated Cortek Frame - Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-05-29 | WF-000808 | NA | 2026-06-03 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-003994 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-29 | fjc-TRANSMIT-000151 | NA | Consultant | Architecturals - Level 01, EoT, Ground Updates + Joinery Schedules | 13 | 4 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-SADV-004355 - The document number inside and outside different. |  | 2026-05-29 | KPTG-SADV-004355 | Closed | 17 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-03-10 | fjc-TRANSMIT-000140 | NA | Consultant | Architectural Updates - RFIs, Facade Assembly Schedules, Wall Review Markup. | 0 | 1 | 0 | NA | APPROVED | 2026-03-11 |  | WF-000659 | 2026-03-17 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-002462 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-05-29 | IGS--TRANSMIT-000038 | NA | Consultant | Electrical Services - L28 Revised Layout | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001008-As per instruction from Mark, we only update the document register, upload the BIM files, and send them to the consultants. |  | 2026-05-29 | KPTG-IntCorr-001008 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-19 | W TITE-TRANSMIT-000005 | NA | Trade Partner | Tremco 250GC Data Sheet | 0 | 1 | 0 | NA | REJECTED | [5 empty] | The PDF file name is incorrect |  | 2025-12-19 |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-29 | VOGUE-TRANSMIT-000014 | NA | Trade Partner | Vogue Grange Sample Submission | 0 | 19 | 0 | NA | REJECTED | [5 empty] | The documenrts and revision number is incorrect |  | 2026-05-29 | DRAFT-018391 | Closed | 19 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-11-20 | RDSBIM-TRANSMIT-000076 | NA | Trade Partner | MLCSPR ¦ CAR PARK NORTH LEVEL 01 CONCRETE PROFILE PLAN | 2 | 0 | 0 | NA | APPROVED | 2026-04-24 | NA | 208 | 2026-04-29 |  |  | 2026-05-29 | 2026-05-29 | KPTG-TRANSMIT-002926 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-05-29 | 4DW-TRANSMIT-000182 | NA | Consultant | Structural Documentation - Capping Beam updates | 2 | 0 | 0 | NA | APPROVED | 2026-05-29 | NA | 283 | 2026-06-03 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-002944 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-29 | INGEN3D-TRANSMIT-000085 | NA | Trade Partner | Level 9-11 - PC0441 - New IFA | 1 | 0 | 0 | NA | APPROVED | 2026-05-29 | WF-000621 | NA | 2026-06-08 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-29 | INGEN3D-TRANSMIT-000089 | NA | Trade Partner | Level 6-8 - Precast Columns - IFC | 54 | 0 | 0 | NA | APPROVED | 2026-05-29 | WF-000622 | NA | 2026-06-08 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-002218 | Closed | 54 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-29 | Jangho-TRANSMIT-000126 | NA | Trade Partner | Glass Sample Submission(GL-10 Option 3) | 0 | 1 | 0 | NA | APPROVED | 2026-05-29 | WF-000618 | NA | 2026-06-16 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-29 | L.E.S.-TRANSMIT-000005 | NA | Trade Partner | Carpark Level 2 and 3 light fitting data sheets | 0 | 3 | 0 | NA | APPROVED | 2026-05-29 | WF-000623 | NA | 2026-07-08 |  |  | 2026-06-11 | 2026-06-11 | KPTG-WTRAN-001377 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-29 | LNCPPL-TRANSMIT-000005 | NA | Trade Partner | Slab Penetrations - Level 1 IFA | 2 | 0 | 0 | NA | REJECTED | [5 empty] | QA ERROR - DOC NO |  | 2026-05-29 | KPTG-TRANSMIT-002030 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2025-12-18 | JP-TRANSMIT-000011 | NA | Consultant | Draft IFC Landscape Issue - Revision G | 24 | 0 | 0 | NA | APPROVED | 2025-12-19 | NA | 568 | 2025-12-25 |  |  | 2026-02-02 | 2026-02-02 | KPTG-TRANSMIT-002553 | Closed | 24 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-29 | Jangho-TRANSMIT-000121 | NA | Trade Partner | Structural Calculation For Channel Embedded Calculation-Rev 01 | 0 | 2 | 0 | NA | APPROVED | 2026-05-29 | WF-000610 | NA | 2026-06-16 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-002034 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-29 | Jangho-TRANSMIT-000131 | NA | Trade Partner | Brick Sample Board Submission Option 5 | 0 | 1 | 0 | NA | APPROVED | 2026-05-29 | WF-000617 | NA | 2026-06-16 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-002972 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-29 | KPTG-TRANSMIT-003785 | NA | Client | FIRE REV3 Cx plan | 0 | 1 | 0 | NA | APPROVED | 2026-05-29 | WF-001090 | NA | 2026-06-03 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-003945 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-29 | Jordan-TRANSMIT-000130 | NA | Trade Partner | Commissioning Scripts | 0 | 10 | 0 | NA | APPROVED | 2026-05-29 | WF-001091 | NA | 2026-06-02 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-003819 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-29 | KPTG-TRANSMIT-003784 | NA | Client | EATON MV ITP L2&L3 | 0 | 2 | 0 | NA | APPROVED | 2026-05-29 | WF-001092 | NA | 2026-06-03 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-003888 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-22 | KPTG-TRANSMIT-003748 | NA | Trade Partner | EATON CX Plan and L3 ITPS | 0 | 1 | 0 | NA | APPROVED | 2026-05-22 | WF-001078 | NA | 2026-05-29 |  |  | 2026-07-17 | 2026-07-17 | KPTG-TRANSMIT-004105 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-29 | ENF-TRANSMIT-000017 | NA | Consultant | Structural Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-05-29 | NA | 161 | 2026-06-05 |  | Review Voided As requested by Renee dated 09-06-2026 and ENF, ENF-IntCorr-000018 |  | 2026-06-09 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-01 | Nilsen3-TRANSMIT-000176 | NA | Trade Partner | Nilsen Shop Drawings - Earth bars IFC | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Incorrect revision |  | 2026-06-01 | KPTG-RFI-008188 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-01 | INTRFRM-TRANSMIT-000068 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 12) | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with document number. |  | 2026-06-01 | DRAFT-002387 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-01 | Entire M-TRANSMIT-000017 | NA | Trade Partner | OAP - Issued For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-01 | WF-000173 | NA | 2026-06-09 |  |  | 2026-06-12 | 2026-06-12 | KPTG-TRANSMIT-000803 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HIGHST | 2025-12-19 | RDSBIM-TRANSMIT-000194 | NA | Trade Partner | LOWER GROUND STAIR & RAMP PLAN & SECTIONS | 6 | 0 | 0 | NA | APPROVED | 2025-12-19 | NA | 567 | 2025-12-25 |  |  | 2026-01-27 | 2026-01-27 | KPTG-TRANSMIT-002546 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-28 | PSGANZ-TRANSMIT-000010 | NA | Trade Partner | Fire Detection technical data resubmission | 0 | 6 | 0 | NA | APPROVED | 2026-05-28 | WF-000167 | NA | 2026-06-05 |  |  | 2026-07-22 | 2026-07-22 | KPTG-TRANSMIT-001228 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-01 | KPTG-SADV-005148 | NA | Trade Partner | Superseded in Aconex as per Brentyn's Advise | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Superseded in Aconex as per Brentyn's Advise |  | 2026-06-01 | KPTG-IntCorr-003111 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-01 | JCBa-TRANSMIT-000126 | NA | Consultant | Partition Plans IFC: First Floor | 5 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 1112 | 2026-06-03 |  | Review void as advised by DM | 2026-06-10 | 2026-06-10 | NA | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-01 | SMEPS-TRANSMIT-000216 | SPARK-CRFI-KPG-000340 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0102 | 1 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 301 | 2026-06-08 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-001015 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-01 | Stowe-A-TRANSMIT-000598 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - LUMINAIRE SCHEDULE - FC-04 - 01.06.2026 | 1 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 4243 | 2026-06-08 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018416 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-01 | KETE-TRANSMIT-000028 | NA | Trade Partner | Kete - Zone 1~5 GF Shop Drawing Submission Rev _02 | 38 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 1114 | 2026-06-08 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-01 | RDSBIM-TRANSMIT-000053 | NA | Trade Partner | MWYCCB ¦ LEVEL 01 INTERNAL FITOUT PLAN - MALE WC | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Actual Received date - 29/05/2026 Drawing duplication |  | 2026-06-01 | KPTG-TRANSMIT-000967 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-06-01 | HIP-TRANSMIT-000025 | NA | Trade Partner | DRAFT-010076 | 11 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Incorrect reference number |  | 2026-06-01 | DRAFT-010076 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-01 | SMEPS-TRANSMIT-000217 | SPARK-CRFI-KPG-000340 & SPARK-CRFI-KPG-000291 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0101,0103,0104,0105,0106,0107,0108,0109,0110,1102,1103 | 11 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 302 | 2026-06-08 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-001013 | Closed | 11 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-01 | RDSBIM-TRANSMIT-000202 | NA | Trade Partner | LINDRUM ¦ LEVEL 11,13,15,17,19,21,23,25,27 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 658 | 2026-06-04 |  |  | 2026-06-05 | 2026-06-05 | KPTG-SADV-004432 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-19 | RDSBIM-TRANSMIT-000131 | NA | Trade Partner | LEVEL 03 PARTITION WALL PLAN | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-01 | WilsonPD-TRANSMIT-000199 | SPARK-CRFI-KPG-000183 | Trade Partner | Updated Hydraulic Layout - Ground Floor Zone C Drainage Layout | 1 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 304 | 2026-06-08 |  |  | 2026-06-02 | 2026-06-03 | KPTG-TRANSMIT-000971 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-01 | Auspan-TRANSMIT-000333 | NA | Trade Partner | Precast shop drawings for approval | 64 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 1116 | 2026-06-08 |  | Received 66 Drawings, 2 Drawings have issue, Initiated with 64 Documents 1 Drawing already terminated | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-002803 | Closed | 64 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-01 | ENF-TRANSMIT-000019 | NA | Consultant | Structural drawing | 4 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 170 | 2026-06-05 |  | Review Voided As requested by Renee dated 09-06-2026 and ENF, ENF-IntCorr-000018 |  | 2026-06-09 | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-01 | SMEPS-TRANSMIT-000218 | NA | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-1101,1104,1105,1106,1107 | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status inside the drawing and in Aconex seem different |  | 2026-06-01 | KPTG-TRANSMIT-000968 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-01 | JCBa-TRANSMIT-000127 | NA | Consultant | IFC: A-41 STAIRS | 3 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 1118 | 2026-06-03 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-002094 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-01 | D&E-TRANSMIT-000773 | NA | Trade Partner | NXM3S2 - Level 01 - Mechanical Duct Layout Zones - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 4245 | 2026-06-12 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-019145 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | WAM-TRANSMIT-000796 | NA | Consultant | A12 Concrete setout Update_Facade Coordination | 10 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 696 | 2026-06-03 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-002138 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | Hollow-TRANSMIT-000014 | NA | Trade Partner | 2336 DISTLV - L3 plant room precast structure - PC beams 04 and 07 - Shop drawings, issued for Construction | 3 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 697 | 2026-06-09 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-002202 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | L.E.S.-TRANSMIT-000006 | NA | Trade Partner | Level 2 and 3 carpark Lux plots | 2 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 700 | 2026-07-09 |  |  | 2026-06-21 | 2026-06-22 | KPTG-TRANSMIT-002401 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-01 | Eneraque-TRANSMIT-000025 | NA | Trade Partner | Re: Ground Floor Penetration Layouts Stage 9, 10, 11 | 3 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 1015 | 2026-06-08 |  |  | 2026-07-09 | 2026-07-09 | KPTG-TRANSMIT-005442 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-19 | ccair-TRANSMIT-000080 | NA | Trade Partner | Level 15 Penetration Layout - Zone 1 | 2 | 0 | 0 | NA | APPROVED | 2025-12-19 | WF-000849 | 516 | 2026-01-19 |  |  | 2026-03-03 | 2026-03-04 | KPTG-TRANSMIT-002777 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-01 | Entire M-TRANSMIT-000018 | NA | Trade Partner | Mechanical Roof Penetration Drawings IFA | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with document number, revision, revision history. |  | 2026-06-01 | KPTG-SADV-000536 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-01 | RDSBIM-TRANSMIT-000274 | NA | Trade Partner | NXM3S4 ¦ ROOF SWITCH ROOM BAFFLE LAYOUT AND ELEVATION | 2 | 0 | 0 | NA | APPROVED | [5 empty] | For Information documents shared to client, consultant, trade partners |  | 2026-06-01 | KPTG-TRANSMIT-018054 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | TTW-TRANSMIT-000167 | NA | Consultant | BP1 - Construction Issue | 1 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 705 | 2026-06-03 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-002089 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-01 | D&E-TRANSMIT-000772 | NA | Trade Partner | NXM3S4 - Level 1 - Mechanical Duct Layout Zones - Issued For Construction | 3 | 0 | 0 | NA | APPROVED | [5 empty] | IFC drawings, distributed to all |  | 2026-06-01 | KPTG-TRANSMIT-018036 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-01 | HDRAus-TRANSMIT-000497 | NA | Consultant | Stage 2 - No longer in use | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | NLIU |  | 2026-06-01 | KPTG-TRANSMIT-018060 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-01 | Auspan-TRANSMIT-000335 | NA | Trade Partner | Resubmit precast shop drawings for approval. Levels 1, 2 | 68 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 1120 | 2026-06-08 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-002383 | Closed | 68 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-01 | SMEPS-TRANSMIT-000219 | SPARK-CRFI KPG-000363 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0129,0130,0131 | 3 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 303 | 2026-06-08 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-001324 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-01 | Auspan-TRANSMIT-000337 | NA | Trade Partner | Resubmit precast shop drawings for approval. Levels 1, 2. | 4 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 1122 | 2026-06-08 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-002278 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-01 | Altaire-TRANSMIT-000006 | NA | Trade Partner | NEXTDC M2S9 - Level 2 - Fire Shop Drawings | 1 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 1023 | 2026-06-09 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-004366 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-01 | SKS Tech-TRANSMIT-000193 | NA | Trade Partner | BASEMENT TELECOMMS IFC UPDATE | 1 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 1280 | 2026-06-03 |  |  | 2026-06-25 | 2026-06-25 | KPTG-TRANSMIT-003991 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-19 | ccair-TRANSMIT-000080 | NA | Trade Partner | Level 15 Buildersworks Drawing Updates | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  | 2025-12-20 | KPTG-TRANSMIT-002555 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-01 | SMEPS-TRANSMIT-000220 | SPARK-CRFI-KPG-000291 | Trade Partner | Re: NEL-CNT-SME-2801-BSE-SDG-1101,1104,1105,1106,1107 | 5 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 305 | 2026-06-08 |  |  | 2026-06-02 | 2026-06-03 | KPTG-TRANSMIT-000973 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-01 | Auspan-TRANSMIT-000336 | NA | Trade Partner | Update precast shop drawings for construction | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Received 11 drawings. One drawing has an issue; the remaining 10 drawings have been distributed, and the register has been updated. No review is required for the precast IFC |  | 2026-06-01 | KPTG-TRANSMIT-002088 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-01 | Auspan-TRANSMIT-000338 | NA | Trade Partner | Re: Precast shop drawings for construction. Levels 1 | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Received 6 drawings. One drawing has an issue; the remaining 5 drawings have been distributed, and the register has been updated. No review is required for the precast IFC |  | 2026-06-01 | KPTG-TRANSMIT-002090 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-01 | GIW-TRANSMIT-000001 | NA | Consultant | J1V3 Report and ESD Markup | 1 | 1 | 0 | NA | REJECTED | [5 empty] | Document numbering not as per the requirement |  | 2026-06-01 | KPTG-IntCorr-000159 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-01 | Auscool-TRANSMIT-000040 | NA | Trade Partner | Re: Precast Missed Penetrations (for Flex Ducts) | 3 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 1127 | 2026-06-08 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-002406 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-01 | TATE_-TRANSMIT-000004 | NA | Trade Partner | MWYCCB - Tate - Technical Data Sheet | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Document revision inside the document and in Aconex seem different |  | 2026-06-01 | KPTG-TRANSMIT-000969 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-01 | ARCH-TRANSMIT-000154 | NA | Consultant | MLC - SPR - ISC - Capping Beam update | 2 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 285 | 2026-06-04 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-002936 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-01 | HDRAus-TRANSMIT-000498 | NA | Consultant | M3 Stage 4 - Document upload - PDF and CAD (Additional Penetrations - KPTG-RFI-008127) | 1 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 3399 | 2026-06-05 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018450 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-01 | SMEPS-TRANSMIT-000003 | NA | Trade Partner | Drawing Submission 1 - TEL | 2 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 256 | 2026-06-05 |  |  | 2026-07-06 | 2026-07-06 | KPTG-TRANSMIT-001046 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-01 | SMEPS-TRANSMIT-000003 | NA | Trade Partner | Drawing Submission 1 - ELC | 13 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 257 | 2026-06-05 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-001057 | Closed | 13 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2025-12-19 | KPTG-TRANSMIT-000037 | NA | Trade Partner | Baigents steel drawings to be re-uploaded and put through Kap review workflow | 5 | 0 | 0 | NA | APPROVED | 2025-12-19 | WF-000003 | NA | 2026-01-16 |  |  | 2026-02-05 | 2026-02-05 | KPTG-WTRAN-000100 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-01 | Syfon1-TRANSMIT-000010 | NA | Trade Partner | Syfon shop drawings IFC | 10 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 3425 | 2026-06-05 |  | 4 DRAWINGS TERMINATED AS PER REQUEST FROM MAX L ANDOTHERE ARE PLACED NEW WF |  | 2026-06-25 | KPTG-TRANSMIT-019060 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-01 | WilsonPD-TRANSMIT-000008 | NA | Trade Partner | NXGEO1 - Wilson Roof Gutter Sample for approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-01 | WF-000176 | NA | 2026-06-09 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-01 | VERTIV-TRANSMIT-000026 | NA | Trade Partner | Next DC - GE1 - CRAC IFA Documentation | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Multiple issues |  | 2026-06-01 | KPTG-SADV-000539 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-01 | Stowe-A-TRANSMIT-000599 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - FUEL COMPOUND DETAILS - FC-03 | 1 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 4248 | 2026-06-08 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018329 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-01 | Tradetec-TRANSMIT-000454 | NA | Trade Partner | Sitewide - Tech Data - Soilworx Thermal Sand | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with the revision number |  | 2026-06-01 | KPTG-SADV-005693 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-01 | Nilsen3-TRANSMIT-000177 | NA | Trade Partner | Re: Nilsen Shop Drawings - Earth bars IFC | 0 | 2 | 0 | NA | APPROVED | [5 empty] | ONLY FOR INFORMATION |  | 2026-06-01 | KPTG-TRANSMIT-018081 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-01 | D&E-TRANSMIT-000775 | NA | Trade Partner | Fwd: NXM3S4 - Upper Roof Level - Cooling Tower Sections - Sheet 3 of 4 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | [5 empty] | IFC drawings, distributed to all |  | 2026-06-01 | KPTG-TRANSMIT-018082 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-01 | D&E-TRANSMIT-000776 | NA | Trade Partner | Fwd: NXM3S4 - Ground - Mechanical Duct Layout - Zone 8 & IW Tank Room - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | [5 empty] | IFC drawings, distributed to all |  | 2026-06-01 | KPTG-TRANSMIT-018083 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-01 | D&E-TRANSMIT-000777 | NA | Trade Partner | Filters - Issued for approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-01 | WF-005898 | NA | 2026-06-01 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018478 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-01 | D&E-TRANSMIT-000779 | NA | Trade Partner | Fwd: NXM3S4 - Ground - Builders Works Layout - Zone 10 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | [5 empty] | FOR INFORMATION ONLY |  | 2026-06-01 | KPTG-TRANSMIT-018086 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2025-12-02 | WPD-TRANSMIT-000050 |  | Trade Partner | Hydraulic Layouts - As Builts | 10 | 0 | 0 | NA | APPROVED | 2025-12-02 |  | 242 | 2025-12-08 |  | The document has been unlocked as requested by - Alex G |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-19 | crossfir-TRANSMIT-000045 | NA | Trade Partner | Wet Fire - Level 04, 05 & 06 , IFC | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As advised by Kapitol no review required for IFC issue, only distribution to all parties. |  |  |  | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-01 | D&E-TRANSMIT-000780 | NA | Trade Partner | Permabond - Issued for Approval NEW | 0 | 1 | 0 | NA | APPROVED | 2026-06-01 | WF-005902 | NA | 2026-06-17 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-01 | Nilsen3-TRANSMIT-000177 | NA | Trade Partner | Fwd: Nilsen Shop Drawings - Earth bars IFC | 0 | 2 | 0 | NA | APPROVED | 2026-06-01 |  |  |  |  | IFC drawings, distributed to all |  | 2026-06-01 | KPTG-TRANSMIT-018092 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-01 | Ardon-TRANSMIT-000035 | NA | Trade Partner | Re: Stage 4 Door Frame Shop Drawings | 2 | 0 | 0 | NA | APPROVED | [5 empty] | They need to make all 3 transmittals of ardon in a same workflow we advise them to transmit in singe pack they will send that |  | 2026-06-01 | KPTG-TRANSMIT-018087 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-01 | Ardon-TRANSMIT-000034 | NA | Trade Partner | Re: Stage 4 Door Frame Shop Drawings Priority 3 | 25 | 0 | 0 | NA | APPROVED | [5 empty] | INFORM ONLY |  | 2026-06-01 | KPTG-IntCorr-014118 | Closed | 25 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-01 | Ardon-TRANSMIT-000036 | NA | Trade Partner | Re: Stage 4 Door Frame Shop Drawings | 23 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | DUE TO MISTAKES ON THE INSIDE DOCUMENT |  | 2026-06-01 | KPTG-IntCorr-014114 | Open | 23 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-01 | KPTG-TRANSMIT-018040 | NA | Trade Partner | M3 S2 - Wet Fire OMM | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with the revision number |  | 2026-06-01 | KPTG-IntCorr-014117 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-01 | JCBa-TRANSMIT-000125 | NA | Consultant | Updated Architectural Documentation - Apartment Wet Area Details, Common Areas Detail Plans & RCP's and Common Area Joinery Details | 48 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect revision and revision history details - KPTG-SADV-002783 |  | 2026-06-01 | KPTG-SADV-002783 | Closed | 48 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-01 | Auspan-TRANSMIT-000334 | NA | Trade Partner | -0G4047 Urgent Review | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC- No review required, update register and distribute: KPTG-TRANSMIT-002072 |  | 2026-06-01 | KPTG-TRANSMIT-002072 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-01 | Auspan-TRANSMIT-000331 | NA | Trade Partner | Precast shop drawings for construction. Level 1. | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC- No review required, update register and distribute : KPTG-TRANSMIT-002075 |  | 2026-06-01 | KPTG-TRANSMIT-002075 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-01 | Auspan-TRANSMIT-000332 | NA | Trade Partner | Precast shop drawings for construction. Levels 2, 3. | 13 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC- No review required, update register and distribute : KPTG-TRANSMIT-002078 |  | 2026-06-01 | KPTG-TRANSMIT-002078 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-17 | RDSBIM-TRANSMIT-000093 | N/A | Trade Partner | MLCSPR ¦ AQUATIC CENTER LEVEL 02 PARTITION WALL | 3 | 0 | 0 | NA | APPROVED | 2025-12-17 |  | 382 | 2025-12-24 |  |  |  | 2026-01-19 | KPTG-SADV-003405 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-01 | Auspan-TRANSMIT-000339 | NA | Trade Partner | Precast shop drawings for approval. Level 1 | 1 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 1129 | 2026-06-08 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-002281 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-01 | Jangho-TRANSMIT-000070 | NA | Trade Partner | PODIUM 1-2F SHOP DRAWINGS Rev00 | 53 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 540 | 2026-06-12 |  | Review is void as advised by Kapitol: "Review completed per Jangho-TRANSMIT-000070 thread" | 2026-07-31 | 2026-07-31 | NA | Closed | 53 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-01 | VOGUE-TRANSMIT-000015 | NA | Trade Partner | VOGUE GRANGE LANDSCAPE SAMPLE SUBMISSIONS | 0 | 19 | 0 | NA | APPROVED | 2026-06-01 | WF - 001030 | NA | 2026-06-05 |  | NA | 2026-07-28 | 2026-07-28 | KPTG-TRANSMIT-003193 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-01 | JCBa-TRANSMIT-000261 | NA | Consultant | BTR GF Drawings | 16 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 572 | 2026-06-03 |  | NA | 2026-06-04 | 2026-06-04 | DRAFT-018582 | Closed | 16 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-01 | KPTG-SADV-006628 | NA | Trade Partner | Linkstone outstanding items | 0 | 2 | 0 | NA | APPROVED | 2026-06-01 | WF - 001033 | NA | 2026-06-04 |  | File supersede and WF terminated. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-01 | KPTG-IntCorr-001798 | NA | Trade Partner | stone shop drawing documents | 69 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Aconex Register only. |  | 2026-06-01 | NA | Closed | 69 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-01 | RDSBIM-TRANSMIT-000208 | NA | Trade Partner | 511SRC ¦ LEVEL10 RCP KEY PLAN AND LAYOUT | 6 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - only for distribution |  | 2026-06-01 | DRAFT-018476 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-01 | RDSBIM-TRANSMIT-000209 | NA | Trade Partner | 511SRC ¦ LEVEL 11 TOWER B RCP KEY PLAN AND LAYOUT | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC only for distribution. |  | 2026-06-01 | DRAFT-018477 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-01 | RDSBIM-TRANSMIT-000210 | NA | Trade Partner | BATHROOM TYPE BLB-01 FINISHES LAYOUT & ELEVATIONS (TYPICAL) | 2 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 573 | 2026-06-05 |  | NA | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-003071 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-01 | SMEPS-TRANSMIT-000221 | NA | Trade Partner | SME Samples for review | 0 | 1 | 0 | NA | APPROVED | 2026-06-01 | WF - 000444 | NA | 2026-06-05 |  | NA | 2026-06-09 | 2026-06-09 | NA | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-17 | ARCH-TRANSMIT-000126 | N/A | Consultant | MLC - SPR - AQC - Wall detail update | 3 | 0 | 0 | NA | APPROVED | 2025-12-17 |  | 384 | 2025-12-24 |  |  | 2025-12-17 | 2025-12-17 | WILL NOTIFY | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-01 | DLTS-TRANSMIT-000010 | NA | Trade Partner | S9-South Eave Gutter-Re Issued for approval | 14 | 0 | 0 | NA | APPROVED | 2026-06-01 | WF-000830 | NA | 2026-06-05 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-003840 | Closed | 14 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-01 | JCI-TRANSMIT-000028 | NA | Trade Partner | Alarm Updates To DoO - JCI-TRANSMIT-000027 | 0 | 1 | 0 | NA | APPROVED | 2026-06-01 | WF - 000443 | NA | 2026-06-08 |  | NA | 2026-06-04 | 2026-06-04 | JCI-TRANSMIT-000026 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-01 | DLTS-TRANSMIT-000011 | NA | Trade Partner | S9-North Eave Gutter Framing-IFA Issue | 25 | 0 | 0 | NA | APPROVED | 2026-06-01 | WF-000831 | NA | 2026-06-10 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-003995 | Closed | 25 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-01 | ELLISAIR-TRANSMIT-000042 | NA | Trade Partner | Technical Data Submission - Butterfly Valves | 0 | 1 | 0 | NA | APPROVED | 2026-06-01 | WF-000832 | NA | 2026-06-11 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-004153 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-01 | WilsonPD-TRANSMIT-000056 | NA | Trade Partner | Leak Detection Tech Data for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-01 | WF-000833 | NA | 2026-06-10 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-004312 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-01 | W_TITE-TRANSMIT-000004 | NA | Trade Partner | Data Sheet for Waterproofing | 0 | 3 | 0 | NA | APPROVED | 2026-06-01 | WF-000835 | NA | 2026-06-01 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-003791 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-01 | WilsonPD-TRANSMIT-000057 | NA | Trade Partner | Water Meters for approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-01 | WF-000836 | NA | 2026-06-10 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-004313 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-15 | CRSol-TRANSMIT-000006 | NA | Trade Partner | CRS - Tech Data Submission NextDC M2 S9_11 | 0 | 2 | 0 | NA | APPROVED | 2026-05-15 | WF-000693 | NA | 2026-05-28 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-003789 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-02 | KPTG-TRANSMIT-003008 | NA | Trade Partner | L3 pavilion integrated dishwasher | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | WF - 01035 | NA | 2026-06-05 |  | File supersede and WF terminated. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-02 | WilsonPD-TRANSMIT-000059 | NA | Trade Partner | Re: Stage 2 Slab Set out - Water Treatment Plant REV6 | 1 | 0 | 0 | NA | APPROVED | 2026-06-02 | WF-000844 | 1021 | 2026-06-09 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-003895 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-19 | ccair-TRANSMIT-000081 | NA | Trade Partner | Apartment transfer air bar grille | 0 | 1 | 0 | NA | APPROVED | 2025-12-19 | WF-000851 | NA | 2026-01-15 |  | File supersede and WF terminated. |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-02 | JCI-TRANSMIT-000016 | NA | Trade Partner | Alarm Updates To DoO | 0 | 2 | 0 | NA | APPROVED | 2026-06-02 | WF-000280 | NA | 2026-06-08 |  |  | 2026-07-29 | 2026-07-29 | KPTG-TRANSMIT-001123 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-02 | Auspan-TRANSMIT-000340 | NA | Trade Partner | Precast shop drawings for construction | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC- No review required, update register and distribute: KPTG-TRANSMIT-002118 |  | 2026-06-02 | KPTG-TRANSMIT-002104 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-02 | Appselec-TRANSMIT-000114 | NA | Trade Partner | Colo 5 - Cell 1 & 2 Electrical Shop Drawings - IFC | 8 | 0 | 0 | NA | APPROVED | 2026-06-02 | WF-000281 | NA | 2026-06-05 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-000831 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-02 | INTRFRM-TRANSMIT-000069 | NA | Trade Partner | Geelong Edge - Hydraulic Tech Data (Submission 3) | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | WF-000177 | NA | 2026-06-10 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-000778 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-02 | Appselec-TRANSMIT-000113 | NA | Trade Partner | Colo 5 Power Layout Level 2 Cell 4 Shop Drawing - IFA | 1 | 0 | 0 | NA | APPROVED | 2026-06-02 | WF-000282 | NA | 2026-06-08 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-000892 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-02 | KPTG-TRANSMIT-018040 | NA | Client | M3 S2 - Wet Fire OMM | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | WF-005906 | NA | 2026-06-15 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-018642 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-02 | D&E-TRANSMIT-000782 | NA | Trade Partner | Security Fixings - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 |  |  | 2026-07-01 |  |  | 2026-07-07 | 2026-07-07 | ⁠KPTG-TRANSMIT-019433 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-02 | D&E-TRANSMIT-000781 | NA | Trade Partner | NXM3S2 - GROUND FLOOR & LEVEL 01 - DATA HALLS SFN UNION AND BOLT TORQUE - Issued For Construction | 7 | 0 | 0 | NA | REJECTED | [5 empty] | For Construction revision submitted without For Approval revision. |  | 2026-06-02 | KPTG-SADV-005694 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-02 | Appselec-TRANSMIT-000116 | NA | Trade Partner | ELECTRICAL SERVICES ISOLATION TRANSFORMER, EARTH BAR & EARTH PIT re-issued For Construction | 3 | 0 | 0 | NA | APPROVED | 2026-06-02 | WF-000283 | NA | 2026-06-05 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-000834 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-02 | Auspan-TRANSMIT-000343 | NA | Trade Partner | Re: Precast shop drawings for approval. Levels 1 | 1 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 1135 | 2026-06-09 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-002286 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2025-12-19 | KAPITOL-TRANSMIT-000944 | NA | Trade Partner | PROLINE (DESIGN INTENT) FACADE SHOP DRAWINGS | 14 | 0 | 0 | NA | APPROVED | 2025-12-19 |  | 263 | 2026-01-01 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-02 | SKS Tech-TRANSMIT-000153 | NA | Trade Partner | Comms containment issued for construction | 3 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 3414 | 2026-07-11 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-02 | D&E-TRANSMIT-000261 | SPARK-CRFI-KPG-000315 | Trade Partner | MWYCCB - LEVEL 1 - PENETRATION LAYOUT ZONE 1 & ZONE 3 MECHANICAL SERVICES - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-06-02 |  | 306 | 2026-06-09 |  |  | 2026-06-02 | 2026-06-03 | KPTG-TRANSMIT-000975 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-02 | SMEPS-TRANSMIT-000221 | NA | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0020,0021,0023,0025,0028,1113,1115,1119,1120 | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing revision & status inside the drawing and in Aconex seem different |  | 2026-06-02 | KPTG-TRANSMIT-000970 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-02 | ARCH-TRANSMIT-000047 | NA | Consultant | GE1 Signage Pack | 2 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 259 | 2026-06-04 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-000790 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-02 | KPTG-TRANSMIT-018132 | NA | Trade Partner | M3 S2 - CSMS OMM | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | WF-005908 | NA | 2026-06-15 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-018643 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-02 | WSP ANZ-TRANSMIT-000016 | NA | Consultant | WSP - Electrical drawings for Approval | 15 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 177 | 2026-06-07 |  | Voided- Updated drawings received from WSP EL-0104 |  | 2026-06-18 | NA | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-02 | Civilex-TRANSMIT-000259 | NA | Trade Partner | Stage 2 - sample submission - Landscape Materials - Utopia 20mm | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | WF-005910 | NA | 2026-06-11 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-018394 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-02 | Altaire-TRANSMIT-000010 | NA | Trade Partner | NEXTDC M2S11 - Ground Level - Shop Drawings (FA-1) (Revised) | 1 | 0 | 0 | NA | APPROVED | 2026-06-02 | WF-000851 | 1027 | 2026-06-09 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-004555 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-02 | WSP ANZ-TRANSMIT-000016 | NA | Consultant | WSP Fire protection drawings for approval | 6 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 179 | 2026-06-07 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-000205 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-02 | Auspan-TRANSMIT-000344 | NA | Trade Partner | Auspan-TRANSMIT-000344 | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC- No review required, update register and distribute: KPTG-TRANSMIT-002118 |  | 2026-06-02 | KPTG-TRANSMIT-002118 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-19 | ccair-TRANSMIT-000082 | NA | Trade Partner | Level 11 & 12 - 14 Buildersworks Drawings - IFA | 8 | 0 | 0 | NA | APPROVED | 2025-12-19 | WF-000850 | 517 | 2026-01-16 |  |  | 2026-03-03 | 2026-03-04 | KPTG-TRANSMIT-002778 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-02 | WSP ANZ-TRANSMIT-000016 | NA | Consultant | WSP Hydraulic drawings for Approval | 16 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 181 | 2026-06-07 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-02 | SMEPS-TRANSMIT-000222 | SPARK-CRFI-KPG-000235 | Trade Partner | NEL-CNT-SME-2801-BSE-SDG-0001 | 1 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 307 | 2026-06-09 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-001454 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-02 | Ardon-TRANSMIT-000037 | NA | Trade Partner | Stage 4 Door Frame Shop Drawings | 3 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 3408 | 2026-06-14 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-018863 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-02 | WSP ANZ-TRANSMIT-000016 | NA | Consultant | WSP Mechanical drawings for Approval | 10 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 183 | 2026-06-08 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-02 | Carr-TRANSMIT-000040 | NA | Consultant | Architectural Specifications | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | NA | 175 | 2026-06-08 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-000145 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-02 | WIP Package- Indesco | NA | Consultant | Facade Performance Specification | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | NA | 172 | 2026-06-08 |  | Review Voided as advised by Renee01-07-2026 |  | 2026-07-01 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-02 | WIP Package- Indesco | NA | Consultant | Weatherproofing Performance Based Design Brief | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | NA | 173 | 2026-06-08 |  | Review Voided as advised by Renee01-07-2026 |  | 2026-07-01 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-01 | ZIA-TRANSMIT-000058 | NA | Trade Partner | Cx L3 Test Documents | 0 | 115 | 0 | KPTG-IntCorr-001391 | APPROVED | 2026-06-04 | WF-001106 | NA | 2026-06-10 |  | IBRAHIM TO CONFIRM | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-004011 | Closed | 115 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-02 | SES AU-TRANSMIT-000042 | NA | Trade Partner | SECURITY-CAMERA LAYOUT PLANS - IFC | 3 | 0 | 0 | NA | APPROVED | 2026-06-02 | WF-000285 | NA | 2026-06-05 |  |  | 2026-06-04 | 2026-06-04 | KPTG-IntCorr-000521 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-02 | WSP ANZ-TRANSMIT-000016 | NA | Consultant | WSP - Electrical Specifications for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | NA | 188 | 2026-06-08 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-17 | PROLMC-TRANSMIT-000019 | NA | Trade Partner | Proline updated set of shop drawings (17/12/25) | 12 | 0 | 0 | NA | APPROVED | 2025-12-17 |  | 383 | 2025-12-24 |  |  |  | 2025-12-17 | KPTG-SADV-003229 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-02 | Civilex-TRANSMIT-000260 | NA | Trade Partner | Stage 2 - Landscape Planter box shop drawing - Rev C | 1 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 4250 | 2026-06-09 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-018892 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-02 | SMEPS-TRANSMIT-000223 | SPARK-CRFI-KPG-000284 & SPARK-CRFI-KPG-000106 | Trade Partner | Re: NEL-CNT-SME-2801-BSE-SDG-0020,0021,0023,0025,0028,1113,1115,1119,1120 | 9 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 308 | 2026-06-09 |  |  | 2026-06-02 | 2026-06-03 | KPTG-TRANSMIT-000977 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-02 | SES AU-TRANSMIT-000043 | NA | Trade Partner | SECURITY-ROOF LAYOUTS-IFC | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status is incorrect, requested to resubmit:KPTG-IntCorr-000504 |  | 2026-06-02 | KPTG-IntCorr-000504 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-02 | Civilex-TRANSMIT-000261 | NA | Trade Partner | Stage 2 - sample submission - Landscape Materials - Pine Bark (12-20mm) | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | WF-005914 | NA | 2026-06-08 |  |  | 2026-06-02 | 2026-06-02 | KPTG-TRANSMIT-018161 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-01 | Baigents-TRANSMIT-000208 | NA | Trade Partner | Loading Dock and Riser Cupboard Handrail FC-1 | 9 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | SENT TO ALL PARTIES |  | 2026-06-01 | KPTG-TRANSMIT-003834 | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-02 | Tradetec-TRANSMIT-000455 | NA | Trade Partner | Tech Data - Soilworx Thermal Sand | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | WF-005915 | NA | 2026-06-08 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-018730 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-01 | KPTG-TRANSMIT-003814 | NA | Trade Partner | Cx L3 Results Documents | 0 | 47 | 0 | NA | APPROVED | 2026-06-01 | WF-001093 | NA | 2026-06-02 |  | terminated -with 'No Approval Required' comment by Ibrahim | 2026-06-29 | 2026-06-29 | KPTG-SADV-003379 | Closed | 47 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-02 | SMEPS-TRANSMIT-000223 | NA | Trade Partner | SME UpRev - SMEPS-TRANSMIT-000223 | 0 | 13 | 0 | NA | APPROVED | 2026-06-02 | WF - 000445 | NA | 2026-06-05 |  | NA | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-000932 | Closed | 13 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-02 | SMEPS-TRANSMIT-000224 | NA | Trade Partner | SME Powered Services Tech Data Sample for review | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | WF - 000446 | NA | 2026-06-05 |  | NA | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-000944 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-02 | PMT Sec-TRANSMIT-000022 | SPARK-CRFI-KPG-000617 | Trade Partner | PMT Tech Data | 0 | 8 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-001009 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-17 | CAP6-TRANSMIT-000003 | NA | Trade Partner | Classic Architectural Onboarding ¦ MLCSPR | 0 | 4 | 0 | NA | APPROVED | 2025-12-17 | WF-000689 |  | 2025-12-22 |  |  |  | 2026-01-19 | KPTG-TRANSMIT-002114 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-02 | Jangho-TRANSMIT-000133 | NA | Trade Partner | 011_LEVEL 1 CAST-IN CHANNEL SHOP DRAWING-01 | 7 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 711 | 2026-06-10 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-02 | WSP ANZ-TRANSMIT-000016 | NA | Consultant | HYDRAULIC SPECIFICATION FOR APPROVAL | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | NA | 193 | 2026-06-08 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-02 | WSP ANZ-TRANSMIT-000016 | NA | Consultant | MECHANICAL SPECIFICATION FOR APPROVAL | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | NA | 198 | 2026-06-08 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-02 | Civilex-TRANSMIT-000097 | NA | Trade Partner | Reflux Valves | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | WF-000637 | NA | 2026-06-04 |  |  | 2026-06-05 | 2026-06-04 | KPTG-TRANSMIT-002130 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | Traf Grp-TRANSMIT-000012 | NA | Trade Partner | Waste Management Plan for approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-01 | WF-000624 | NA | 2026-06-02 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-002051 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-02 | TATE_-TRANSMIT-000027 | NA | Trade Partner | : Brush Seal Performance | 0 | 1 | 0 | NA | REJECTED | [5 empty] | DOCUMENT STATUS INCORRECT:KPTG-IntCorr-000505 |  | 2026-06-02 | KPTG-IntCorr-000505 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | PCForm-TRANSMIT-000211 | NA | Trade Partner | Up-to-Date Level 4 Structural Pack | 10 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | register updated both ACC and Aconex |  | 2026-06-01 | NA | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | PCForm-TRANSMIT-000211 | NA | Trade Partner | Up-to-Date Level 4 Structural Pack | 2 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 703 | 2026-06-15 |  | submitted along with Trn # 217 ACC 703 |  | 2026-06-16 | KPTG-TRANSMIT-002311 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-02 | Entire M-TRANSMIT-000019 | NA | Trade Partner | mechanical Roof Penetration Drawings RE-IFA | 4 | 0 | 0 | NA | REJECTED | [5 empty] | Issue with revision number, status |  | 2026-06-02 | KPTG-SADV-000556 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-02 | SES AU-TRANSMIT-000044 | NA | Trade Partner | SECURITY-ROOF LAYOUTS-IFC | 2 | 0 | 0 | NA | APPROVED | 2026-06-02 | WF-000286 | NA | 2026-06-05 |  |  | 2026-06-04 | 2026-06-04 | KPTG-IntCorr-000520 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-17 | KPTG-IntCorr-003724 | NA | Trade Partner | Revised Wall Type proposal | 0 | 2 | 0 | NA | APPROVED | 2025-12-17 | WF-000684 | NA | 2025-12-19 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-003055 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | PCForm-TRANSMIT-000217 | NA | Trade Partner | Level 4 - Updated Drawings (Rev E) | 4 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 703 | 2026-06-02 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-002309 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-02 | Civilex-TRANSMIT-000096 | NA | Trade Partner | Re: Trench Grate | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | WF-000638 | NA | 2026-06-11 |  |  | 2026-06-17 | 2026-06-15 | KPTG-TRANSMIT-002275 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-05-08 | KETE-TRANSMIT-000042 | NA | Trade Partner | WINDOW SCHEDULE-LEVELS 01 & 02 (B) SHEET 18 | 4 | 0 | 0 | NA | APPROVED | 2026-05-08 | NA | 564 | 2026-05-14 |  | NA | 2026-06-02 | 2026-06-02 | DRAFT-018519 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-21 | INTRFRM-TRANSMIT-000059 | NA | Trade Partner | Geelong Edge - Electrical Tech Data (Submission 5) | 0 | 1 | 0 | NA | APPROVED | 2026-05-21 | WF-000148 | NA | 2026-05-29 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-000733 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-02 | B Smart-TRANSMIT-000077 | NA | Consultant | Ground Floor Driveway and Footpath + L1 CCP update | 3 | 1 | 0 | KPTG-IntCorr-000628 | APPROVED | 2026-06-05 | NA | 546 |  |  | Review Void; Consultant requested to update the drawings. | 2026-06-05 | 2026-06-05 | NA | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-02 | Auspan-TRANSMIT-000341 | NA | Trade Partner | Update IFCed precast shop drawings. | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC- No review required, update register and distribute KPTG-TRANSMIT-002113 |  | 2026-06-02 | KPTG-TRANSMIT-002113 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-02 | Auspan-TRANSMIT-000342 | NA | Trade Partner | Update precast shop drawings for construction | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC- No review required, update register and distribute KPTG-TRANSMIT-002115 |  | 2026-06-02 | KPTG-TRANSMIT-002115 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-02 | Auspan-TRANSMIT-000345 | NA | Trade Partner | : Resubmit shop drawings level 1 for approval | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect drawing revision history. KPTG-SADV-002815 |  | 2026-06-02 | KPTG-SADV-002815 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-02 | KPTG-TRANSMIT-018133 | NA | Trade Partner | M3 S2 - ACG OMM | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | WF-005973 | NA | 2026-06-18 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-018750 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-17 | Arco-TRANSMIT-000007 | NA | Trade Partner | SERIES 2 - ALUMINUM ROLLER SHUTTERS | 5 | 0 | 0 | NA | APPROVED | 2025-12-18 |  | 387 | 2025-12-23 |  |  |  | 2026-01-27 | KPTG-SADV-003535 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-02 | KPTG-TRANSMIT-000140 | NA | Trade Partner | M3 S6 Civil Works - Access Covers Storm Water Pit Shop Drawings | 52 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 159 | 2026-06-10 |  |  | 2026-07-20 | 2026-07-21 | KPTG-TRANSMIT-000628 | Closed | 52 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-02 | WSP ANZ-TRANSMIT-000004 | NA | Consultant | AUDIO VISUAL SPECIFICATION | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | NA | 200 | 2026-06-08 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | OveArup-TRANSMIT-000037 | NA | Consultant | Arup IFC update - Reg 129 FRV response-ELC | 10 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 691 | 2026-06-05 |  |  | 2026-06-14 | 2026-06-22 | KPTG-TRANSMIT-002385 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | OveArup-TRANSMIT-000037 | NA | Consultant | Arup IFC update - Reg 129 FRV response-MEC | 16 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 693 | 2026-06-05 |  |  | 2026-06-14 | 2026-06-22 | KPTG-TRANSMIT-002391 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | OveArup-TRANSMIT-000037 | NA | Consultant | Arup IFC update - Reg 129 FRV response-FIR | 13 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 707 | 2026-06-05 |  |  | 2026-06-14 | 2026-06-22 | KPTG-TRANSMIT-002388 | Closed | 13 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | INGEN3D-TRANSMIT-000088 | NA | Trade Partner | PC 100 - Grout Tube location | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | register updated |  | 2026-06-01 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | PCForm-TRANSMIT-000219 | NA | Trade Partner | Formwork design Level 4 using scaffold on steel beams | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | register updated |  | 2026-06-01 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | PCForm-TRANSMIT-000220 | NA | Trade Partner | Updated backpropping design | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | register updated |  | 2026-06-01 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | INGEN3D-TRANSMIT-000094 | NA | Trade Partner | Level 7-9 - PC0403-4 & PC0419 - IFC | 4 | 0 | 0 | NA | APPROVED | 2026-06-01 | WF-000634 | NA | 2026-06-10 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-002220 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | INGEN3D-TRANSMIT-000093 | NA | Trade Partner | Level 6-8 - Precast Columns - IFC | 4 | 0 | 0 | NA | APPROVED | 2026-06-01 | WF-000633 | NA | 2026-06-10 |  |  | 2026-06-10 | 2026-06-09 | KPTG-TRANSMIT-002177 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-01 | WGAVIC-IntCorr-000147 | NA | Consultant | Certification Package for Stage 9 Pile Caps, Shear Walls and Columns | 30 | 0 | 0 | NA | APPROVED | 2025-12-03 | NA | 99 | 2025-12-08 |  |  | 2025-12-08 | 2025-12-08 | KPTG-TRANSMIT-000284 | Closed | 28 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2025-12-17 | PROLMC-TRANSMIT-000020 | NA | Trade Partner | GRC Updated Shop Drawings (17/12/25) | 12 | 0 | 0 | NA | REJECTED | [5 empty] | DOCUMENT NUMBERS ARE INCOREECT, REQUESTED TO RESUBMIT |  | 2025-12-19 | KPTG-IntCorr-003792 | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | INGEN3D-TRANSMIT-000092 | NA | Trade Partner | Level 8-10 - Precast Columns - IFC | 59 | 0 | 0 | NA | APPROVED | 2026-06-01 | WF-000632 | NA | 2026-06-09 |  |  | 2026-06-09 | 2026-06-10 | KPTG-TRANSMIT-002222 | Closed | 59 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-02 | WAM-TRANSMIT-000797 | NA | Consultant | IFC A12 Mezzanine Level | 2 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 713 | 2026-06-04 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-002134 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | RDSBIM-TRANSMIT-000044 | NA | Trade Partner | LEVEL 04 CONCRETE PROFILE PLAN AND SECTION | 6 | 0 | 0 | NA | APPROVED | 2026-06-01 | NA | 709 | 2026-06-04 |  |  | 2026-06-12 | 2026-06-12 | KPTG-TRANSMIT-002264 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | PCForm-TRANSMIT-000218 | NA | Trade Partner | Level 4 formwork design | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | register updated |  | 2026-06-01 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | INGEN3D-TRANSMIT-000090 | NA | Trade Partner | Level 6-8 - Precast Columns - IFC | 4 | 0 | 0 | NA | APPROVED | 2026-06-01 | WF-000631 | NA | 2026-06-10 |  |  | 2026-06-10 | 2026-06-09 | KPTG-TRANSMIT-002174 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | INGEN3D-TRANSMIT-000091 | NA | Trade Partner | Level 9-11 - PC0398-3 - No Longer In Use | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | NO LONGER IN USE |  | 2026-06-01 | KPTG-TRANSMIT-002096 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-29 | KPTG-WTRAN-001205 | NA | Trade Partner | STRUCTURAL DATA MIX CONCRETE | 0 | 1 | 0 | NA | APPROVED | 2026-05-29 | WF-000530 | NA |  |  |  |  | 2026-06-01 | KPTG-TRANSMIT-002058 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-29 | KPTG-WTRAN-001206 | NA | Trade Partner | STRUCTURAL DATA - MIX CONCRETE | 0 | 1 | 0 | NA | APPROVED | 2026-05-29 | (WF-000520 | NA |  |  |  |  | 2026-06-01 | KPTG-TRANSMIT-002060 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-05-06 | ZIA-TRANSMIT-000050 | NA | Trade Partner | Cx L3 - Startup & Commissioning Procedures | 0 | 3 | 0 |  | APPROVED | 2026-05-07 | WF-001048 | NA | 2026-05-14 |  |  | 2026-06-01 | 2026-06-01 | KPTG-TRANSMIT-003815 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2025-12-19 | vdmcons-TRANSMIT-000013 | NA | Trade Partner | D10 - M3 Stage 3 GIS Building - M3 Stage 3 Switch Room - Shop Drawings & 3D IFC Model - IFF - 2025-12-19 | 202 | 0 | 0 | NA | REJECTED | [5 empty] | There is no approval on the IFA — awaiting response from KG. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-02 | WilsonPD-TRANSMIT-000009 | NA | Trade Partner | NXGEO1 - Wilson Fixture Samples for approval | 0 | 2 | 0 | NA | APPROVED | 2026-06-02 | WF-000179 | NA | 2026-06-12 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-000765 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-02 | PSGANZ-TRANSMIT-000011 | NA | Trade Partner | Fire Detection tech. data submission | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | WF-000180 | NA | 2026-06-10 |  | 1 + 8 docs | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-000987 & KPTG-TRANSMIT-001001 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-02 | ADP-TRANSMIT-000333 | NA | Consultant | ADP MEL4780 - S4 - Mechanical Updated Drawings (FC)- | 24 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 3410 | 2026-06-24 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-020486 | Closed | 24 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-02 | Tradetec-TRANSMIT-000456 | NA | Trade Partner | IFA - Stage 4 - CP42, HVP41, HVP42 | 3 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 3413 |  |  | IFA - Stage 4 - CP42, HVP41, HVP42 | 2026-06-25 | 2026-06-23 | ⁠KPTG-TRANSMIT-018962 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-06-02 | WPD-TRANSMIT-000087 | NA | Trade Partner | AS BUILT REVIEW - SHOP DRAWING | 1 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 411 | 2026-06-17 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-02 | KPTG-TRANSMIT-018159 | NA | Trade Partner | DC ACTION: Ardon 2 of 3 Transmittals | 27 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 3415 | 2026-06-06 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-018644 | Closed | 27 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-02 | INDS-TRANSMIT-000039 | NA | Trade Partner | Wet Fire - Ground | 1 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 659 | 2026-06-09 |  |  | 2026-06-17 | 2026-06-17 | KPTG-SADV-004556 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-02 | INDS-TRANSMIT-000040 | NA | Trade Partner | Dry Fire - Ground | 1 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 660 | 2026-06-09 |  |  | 2026-06-17 | 2026-06-17 | KPTG-SADV-004557 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-02 | WOCEP-TRANSMIT-000004 | NA | Trade Partner | TECH DATA | 0 | 13 | 0 | NA | APPROVED | 2026-06-02 | NA | WF-000777 | 2026-06-08 |  | INSTRUCTION FROM MARK WE AVOID 1 TECH DATA.ONLY PROCESS 12 TECH DATA. | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-002619 | Closed | 12 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-02 | fjc-TRANSMIT-000152 | NA | Consultant | Architecturals - Level 06 CPP | 1 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 661 | 2026-06-05 |  |  | 2026-06-03 | 2026-06-03 | KPTG-SADV-004416 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2025-12-19 | TATE_-TRANSMIT-000009 | NA | Trade Partner | Structural ceiling shop drawings | 5 | 0 | 0 | NA | APPROVED | 2025-12-19 | WF-000004 | NA | 2026-01-15 |  |  |  |  | DEM-WTRAN-000003 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-02 | ACCCA-TRANSMIT-000001 | NA | Trade Partner | Electrical Pit Approval | 6 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 161 | 2026-06-10 |  | Voided-Requested by Zoe-resubmitted #228 |  | 2026-06-19 | NA | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-09 | PTA-TRANSMIT-000004 | NA | Trade Partner | Next DC M3 Stage 6 - PTA Arch Documentation issued for coordination | 1 | 0 | 0 | KPTG-IntCorr-000138 | APPROVED | 2026-06-09 | NA | 180 | 2026-06-17 |  | Actual submission date- 02-06-2026- | 2026-06-18 | 2026-06-19 | KPTG-TRANSMIT-000253 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-02 | GIW-TRANSMIT-000002 | NA | Consultant | J1V3 Report and ESD Markup | 1 | 1 | 0 | NA | APPROVED | [5 empty] | Information only. GIW will revise the document soon as advised by Renee. |  | 2026-06-04 | NA | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-02 | ADP-TRANSMIT-000034 | NA | Consultant | ADP MEL3393 - Updated Fire Protection Drawings | 2 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 288 | 2026-06-05 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-002946 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-02 | Appselec-TRANSMIT-000115 | NA | Trade Partner | MEL11C45 TEMPORARY WIFI PLAN (Rev 3) - For Construction | 0 | 1 | 0 | NA | REJECTED | [5 empty] | RejectedL wrong revision-KPTG-IntCorr-000500 |  | 2026-06-02 | KPTG-IntCorr-000500 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-02 | DEC Tech Data (Outlook mail) | NA | Trade Partner | Floor Finish Tech Data | 0 | 6 | 0 | NA | APPROVED | 2026-06-02 | WF-000848 | NA | 2026-06-05 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-004063 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-02 | Altaire-TRANSMIT-000007 | NA | Trade Partner | NEXTDC M2S9 - Ground Level - Shop Drawings (FA-2) | 1 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 1022 | 2026-06-04 |  |  | 2026-06-17 | 2026-06-17 | Altaire-TRANSMIT-000007 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-02 | ASV-TRANSMIT-000064 | NA | Trade Partner | Revised Hydraulic IFC SD | 6 | 0 | 0 | NA | APPROVED | 2026-06-02 | NA | 1025 | 2026-06-09 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-003979 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-17 | Arc Plas-TRANSMIT-000010 | NA | Trade Partner | Promat Tech Data Submission | 0 | 1 | 0 | NA | APPROVED | 2026-06-17 | WF-000972 | NA | 2026-06-19 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-004695 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-02 | Altaire-TRANSMIT-000009 | NA | Trade Partner | STAGE 9 - MASDS CALCULATIONS / CERTIFICATE | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | WF-000850 | NA | 2026-06-12 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-004237 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-19 | JCBa-TRANSMIT-000046 | NA | Consultant | Lift Core Setout Drawings - IFC | 8 | 0 | 0 | NA | APPROVED | 2025-12-19 | WF-000115 | 122 | 2025-12-23 |  |  |  | 2026-01-15 | KPTG-TRANSMIT-000398 | Closed | 8 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-02 | Eneraque-TRANSMIT-000027 | NA | Trade Partner | Fill Cabinet & Level Transmitter Datasheet | 0 | 2 | 0 | NA | APPROVED | 2026-06-02 | WF-000852 | NA | 2026-06-12 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-004928 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-02 | PFP PL-TRANSMIT-000006 | NA | Trade Partner | S11 Level 1 Mech Corridor Most Remote Calc FOA-2 | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | WF-000854 | NA | 2026-06-12 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-004271 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-03 | RDSBIM-TRANSMIT-000211 | NA | Trade Partner | BATHROOM TYPE BB-01 FINISHES LAYOUT & ELEVATIONS (TYPICAL) | 2 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 574 | 2026-06-09 |  | NA | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-003075 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-03 | KALLIBRE-TRANSMIT-000012 | NA | Trade Partner | 6x Additional COLO5 Doors Shop Drawings - Issued For Approval | 6 | 0 | 0 | NA | APPROVED | 2026-06-03 | WF-000287 | NA | 2026-06-11 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-03 | RDSBIM-TRANSMIT-000204 | NA | Trade Partner | LINDRUM ¦ CPP ¦ L-12,14,16,18,20,22,24&26 ¦ IFC ¦ SUBMISSION | 1 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 662 | 2026-06-06 |  |  | 2026-06-05 | 2026-06-05 | KPTG-SADV-004434 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-03 | Entire M-TRANSMIT-000020 | NA | Trade Partner | Mechanical Penetration Layout RE-IFA | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | QA rejected - Submitted the same rev. |  | 2026-06-03 | KPTG-SADV-000558 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-03 | JCBa-TRANSMIT-000128 | NA | Consultant | NOTE RE-ISSUE: Updated Architectural Documentation - Apartment Wet Area Details, Common Areas Detail Plans & RCP's and Common Area Joinery Details | 24 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 1139 | 2026-06-05 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-002351 | Closed | 24 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-03 | RDSBIM-TRANSMIT-000020 | NA | Trade Partner | MEL11C45 ¦ PW ¦ LEVEL 01 COLO 5A ¦ SUBMISSION | 3 | 0 | 0 | NA | APPROVED | 2026-06-03 | WF-000288 | NA | 2026-06-05 |  |  | 2026-06-03 | 2026-06-03 | KPTG-TRANSMIT-000800 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-03 | D&E-TRANSMIT-000774 | NA | Trade Partner | Victaulic - Valves and Fittings - Issued for Construction | 0 | 1 | 0 | NA | APPROVED | 2026-06-03 | WF-005919 | NA | 2026-06-29 |  |  |  | 2026-06-30 | KPTG-TRANSMIT-019158 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-03 | INDS-TRANSMIT-000032 | NA | Trade Partner | Dry Fire - Ground | 5 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 1142 | 2026-06-10 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-002169 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2025-12-19 | Auspan-TRANSMIT-000036 | NA | Trade Partner | Precast shop drawings for approval. Zone 1, 2. | 47 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2025-12-19 | KPTG-SADV-000498 | Closed | 47 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-06-03 | Entire M-TRANSMIT-000050 | NA | Trade Partner | Toilet Exhaust Technical Data - Minor Update | 0 | 1 | 0 | NA | APPROVED | 2026-06-03 | WF-005921 | NA | 2026-06-16 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-03 | RDSBIM-TRANSMIT-000010 | NA | Trade Partner | NXGE01 ¦ ROOF CONCRETE PROFILE KEY PLAN | 4 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 256 | 2026-06-09 |  | Terminated as directed by Chri Doh for submitting the updated documents. | 2026-07-13 | 2026-07-13 | KPTG-IntCorr-000293 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-03 | WGAVIC-TRANSMIT-000134 | NA | Consultant | M2 - Steel Package - Issued for Construction | 26 | 0 | 0 | NA | APPROVED | 2026-06-03 |  | 1030 | 2026-06-08 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-004386 | Closed | 26 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-03 | D&E-TRANSMIT-000783 | NA | Trade Partner | Fwd: NXM3S4 - Roof level - CHW Pipe Layout Zones + Sections - Issued For Construction | 3 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | As instructed by Ellie-No Action taken |  | 2026-06-03 | KPTG-TRANSMIT-018168 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-06-03 | OveArup-TRANSMIT-000196 | NA | Trade Partner | Fwd: Updated: M3 Stage 3 22kV Inground Cables Heat Rise Calculation Report | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-06-03 | KPTG-TRANSMIT-018171 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-03 | WGAVIC-TRANSMIT-000135 | NA | Consultant | M2 - Civil Ramp Updates - Issued for Construction | 2 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 1032 | 2026-06-08 |  |  | 2026-07-29 | 2026-07-29 | KPTG-DA-004014 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-03 | TATE_-TRANSMIT-000028 | NA | Trade Partner | Tate re-issue for construction | 10 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Duplicate Drawings:KPTG-IntCorr-000509 |  | 2026-06-03 | :KPTG-IntCorr-000509 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-03 | WilsonPD-TRANSMIT-000200 | SPARK-CRFI-KPG-000183 | Trade Partner | Hydraulic Services - Drainage LAyout - Ground Zone B | 1 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 309 | 2026-06-10 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-000988 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-03 | Appselec-TRANSMIT-000118 | NA | Trade Partner | MEL11C45 TEMPORARY WIFI PLAN - IFC | 0 | 1 | 0 | NA | APPROVED | 2026-06-03 | WF-000289 | NA | 2026-06-04 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-000818 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-03 | Auspan-TRANSMIT-000349 | NA | Trade Partner | Precast shop drawings for approval. Level 5 | 15 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 1147 | 2026-06-10 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-002391 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-19 | RDSBIM-TRANSMIT-000015 | NA | Trade Partner | 671CHP ¦ BASEMENT 4A TO BASEMENT 1 CORE WALL PLAN AND ELEVATIONS | 3 | 0 | 0 | NA | APPROVED | 2025-12-19 | WF-000110 | 193 | 2025-12-24 |  | Review void as advised during a meeting with Kapitol DM & PCs. |  | 2026-01-22 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-03 | SES AU-TRANSMIT-000046 | NA | Trade Partner | Re: SECURITY-RISER SCHEDULE AND COLO4 SCEC LAYOUT-IFC | 3 | 0 | 0 | NA | APPROVED | 2026-06-03 | WF-000290 | NA | 2026-06-09 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-000858 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-03 | ADP-TRANSMIT-000334 | NA | Consultant | ADP MEL4780 - S4 - Updated Drawings (CSMS, FID & EL) | 5 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect revision |  | 2026-06-03 | KPTG-RFI-008229 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-03 | WGAVIC-TRANSMIT-000138 | NA | Consultant | M2 - Melbourne Water Issue - Issued for Construction | 6 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 1036 | 2026-06-08 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-004055 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-03 | SES AU-TRANSMIT-000045 | NA | Trade Partner | SECURITY-RISER SCHEDULE AND COLO4 SCEC LAYOUT-IFC | 1 | 0 | 0 | NA | APPROVED | 2026-06-03 | WF-000291 | NA | 2026-06-05 |  | WF-000291 IS TERMINATED | 2026-06-04 | 2026-06-04 | KPTG-IntCorr-000519 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-03 | ARCST-TRANSMIT-000297 | NA | Trade Partner | C1 Cbiller Base Framing - Issued for Construction | 136 | 0 | 0 | NA | REJECTED | [5 empty] | The title is mismatch in the Aconex register and title mentioned inside the pdf file |  | 2026-06-03 | KPTG-RFI-008232 | Closed | 136 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-03 | ARCST-TRANSMIT-000299 | NA | Trade Partner | C3 Chiller Base Framing - Issued for Construction | 97 | 0 | 0 | NA | REJECTED | [5 empty] | The title is mismatch in the Aconex register and title mentioned inside the pdf file. |  | 2026-06-03 | KPTG-RFI-008234 | Closed | 97 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-03 | Stowe-A-TRANSMIT-000602 | NA | Trade Partner | STOWE - DRAWING SUBMISSION - LINEUP SCHEMATICS - FC-04 & FC-06 | 18 | 0 | 0 | NA | APPROVED | [5 empty] | Updated in Document Register and in ACC as directed by Jaison |  | 2026-06-04 | KPTG-TRANSMIT-018220 | Closed | 18 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-03 | IVS-TRANSMIT-000368 | NA | Consultant | Stage 4 - Secure Corridor (Revised as clouded) | 2 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 3420 | 2026-06-07 |  |  |  | 2026-07-28 | NA | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-03 | Jangho-TRANSMIT-000134 | NA | Trade Partner | 004_Podium Visual Mock-UP Shop Drawing_Rev:A | 16 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 733 | 2026-06-11 |  |  | 2026-07-06 | 2026-07-07 | KPTG-TRANSMIT-002744 | Closed | 16 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-03 | D&E-TRANSMIT-000262 | NA | Trade Partner | Mechanical Services Seismic Drawings Level-01 Pipework & Ductwork | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status inside the drawing and in Aconex seem different |  | 2026-06-03 | KPTG-TRANSMIT-000979 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-19 | RDSBIM-TRANSMIT-000016 | NA | Trade Partner | 671CHP ¦ BASEMENT 4 CONCRETE PROFILE PLAN AND SECTIONS | 3 | 0 | 0 | KPTG-IntCorr-000281 | APPROVED | 2026-01-16 | WF-000123 | 208 | 2026-01-20 |  | Previous revision is at review. Review void as advised during a meeting with Kapitol DM & PCs. |  | 2026-01-22 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-03 | D&E-TRANSMIT-000786 | NA | Trade Partner | Fwd: NXM3S4 - Roof Level - Chiller Room 1 Layout + Sections - Issued For Construction | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-06-03 | KPTG-TRANSMIT-018197 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-03 | PARR-TRANSMIT-000188 | NA | Trade Partner | Fwd: NXM3S4 - Roof Level - Chiller Room 1 Layout + Sections - Issued For Construction | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-06-03 | KPTG-TRANSMIT-018198 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-03 | ARCST-TRANSMIT-000298 | NA | Trade Partner | C2 Chiller Base Framing - Issued for Construction | 98 | 0 | 0 | NA | REJECTED | [5 empty] | Incorrect drawing title |  | 2026-06-03 | KPTG-RFI-008237 | Closed | 98 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-03 | SKS Tech-TRANSMIT-000155 | NA | Trade Partner | Hangers Cut List - Switchrooms | 3 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 3424 | 2026-06-08 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-03 | D&E-TRANSMIT-000017 | NA | Trade Partner | LEVEL 2 - PLANT ROOM DUCTWORK SHOP DRAWINGS - IFA | 1 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 717 | 2026-06-11 |  |  | 2026-08-10 | 2026-08-10 | KPTG-TRANSMIT-003342 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-03 | WGAVIC-TRANSMIT-000006 | NA | Consultant | M3 S6 Civil Earthworks Drawings - Issued for Construction | 5 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 163 | 2026-06-11 |  |  | 2026-06-11 | 2026-06-11 | NA | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-03 | ECBS-TRANSMIT-000022 | NA | Trade Partner | Tech data for Versilux for approval (Revision 2) | 0 | 1 | 0 | NA | APPROVED | 2026-06-03 | WF-001097 | NA | 2026-06-09 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-03 | Carr-TRANSMIT-000068 | NA | Consultant | Town Planning Update - Schedule of Changes and Development Summary | 1 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 218 | 2026-06-09 |  | Review Voided as advised By Renee |  | 2026-08-05 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-03 | VAE-Grp-TRANSMIT-000168 | NA | Trade Partner | Capturing Fault Study Commentary / As Constructed Changes | 0 | 14 | 0 | NA | APPROVED |  | NA | NA |  |  | FC doc send to all parties |  | 2026-06-03 | KPTG-TRANSMIT-003839 | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-19 | RDSBIM-TRANSMIT-000017 | NA | Trade Partner | 671CHP ¦ BASEMENT 1 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2025-12-19 | WF-000111 | 195 | 2025-12-24 |  | Review void as advised during a meeting with Kapitol DM & PCs. |  | 2026-01-22 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-03 | SMEPS-TRANSMIT-000301 | NA | Trade Partner | Stage 4 - Lightning protection inground layout | 1 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 3428 | 2026-06-12 |  | workflow terminated by charlie johnstone |  | 2026-06-16 | KPTG-TRANSMIT-018677 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-03 | VAE-Grp-TRANSMIT-000170 | NA | Trade Partner | MCC-B-L4-B-01 - Submain size adjusted | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | FC doc send to all parties |  | 2026-06-03 | KPTG-TRANSMIT-003842 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-03 | Diadem-TRANSMIT-000026 | NA | Consultant | NEXTDC M3 Wayfinding Package | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Submitted as binder |  | 2026-06-03 | KPTG-DA-006897 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-03 | D&E-TRANSMIT-000785 | NA | Trade Partner | NXM3S2 - LEVEL 01 - DATAHALL 6 SFN UNION AND BOLT TORQUE MAP - Issued For Construction | 1 | 0 | 0 | NA | REJECTED | [5 empty] | IFC submitted without IFA |  | 2026-06-03 | KPTG-SADV-005712 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-06-03 | RDSBIM-TRANSMIT-000275 | NA | Trade Partner | Fwd: RDS ¦ NXM3S3 ¦ GF ¦ GENERAL ARRANGEMENT PLAN ¦ IFC ¦ SUBMISSION | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | For distribution |  | 2026-06-03 | KPTG-TRANSMIT-018199 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-03 | 4Ki-TRANSMIT-000009 | NA | Trade Partner | Shop Drawings For Approval - JNR001, JNR004, JNR014, JNR015 | 4 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | QA error rejected |  | 2026-06-03 | KPTG-IntCorr-001392 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-03 | ETNInd-TRANSMIT-000022 | NA | Trade Partner | Foreseer EPMS Documentation for Information | 14 | 0 | 0 | NA | APPROVED |  | NA | na |  |  | Update register only - FYI |  | 2026-06-03 | NA | Closed | 14 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-03 | Electro Light WIP Package | NA | Consultant | LUMINAIRE SCHEDULE | 0 | 1 | 0 | NA | APPROVED | 2026-06-03 | NA | 211 | 2026-06-09 |  | Review voided - Updated version under review #379 |  | 2026-08-28 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-03 | Electro Light WIP Package | NA | Consultant | LIGHTING SPECIFICATION | 0 | 1 | 0 | NA | APPROVED | 2026-06-03 | NA | 213 | 2026-06-09 |  | Review voided - Updated version under review #379 |  | 2026-08-28 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-03 | Electro Light WIP Package | NA | Consultant | LIGHTING CONTROL FUNCTIONALITY BRIEF | 0 | 1 | 0 | NA | APPROVED | 2026-06-03 | NA | 215 | 2026-06-09 |  | Review voided - Updated version under review #379 |  | 2026-08-28 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2025-12-19 | B Smart-TRANSMIT-000044 | NA | Consultant | 251002_A12 Core Elevations _IFC | 5 | 0 | 0 | KPTG-IntCorr-000282 | APPROVED | 2026-01-16 | WF-000124 | 210 | 2026-01-20 |  | Previous revision is at review |  | 2026-01-28 | KPTG-TRANSMIT-000349 | Closed | 5 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-03 | L.E.S.-TRANSMIT-000007 | NA | Trade Partner | Slab Penetrations - level 2 to 4 IFA | 6 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 721 | 2026-06-11 |  |  | 2026-06-21 | 2026-06-22 | KPTG-TRANSMIT-002403 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-03 | SMEPS-TRANSMIT-000300 | NA | Trade Partner | Stage 2, updated electrical site plan (IFC11) | 1 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 4253 | 2026-06-10 |  | Terminated by Charlie Johnstone for submitting updated document. Updated document submitted in SMEPS-TRANSMIT-000339 | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-019483 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-03 | ADP-TRANSMIT-000335 | NA | Consultant | ADP MEL4780 - S4 - Updated Drawings (CSMS) | 1 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 3430 | 2026-06-08 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018512 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-03 | ADP-TRANSMIT-000335 | NA | Consultant | ADP MEL4780 - S4 - Updated Drawings (Electrical) | 1 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 3432 | 2026-06-08 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018489 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-03 | ADP-TRANSMIT-000335 | NA | Consultant | ADP MEL4780 - S4 - Updated Drawings (Fire Detection) | 3 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 3434 | 2026-06-08 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-018559 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-03 | ADP-TRANSMIT-000075 | NA | Consultant | ADP MEL4680 - Updated Electrical Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 264 | 2026-06-08 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-000792 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-03 | Auspan-TRANSMIT-000346 | NA | Trade Partner | Precast shop drawings for construction. Level 5. | 21 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC- No review required, update register and distribute - KPTG-TRANSMIT-002130 |  | 2026-06-03 | KPTG-TRANSMIT-002130 | Closed | 21 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-03 | Auspan-TRANSMIT-000347 | NA | Trade Partner | Update IFCed shop drawing. Panel 1P302 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC- No review required, update register and distribute - KPTG-TRANSMIT-002134 |  | 2026-06-03 | KPTG-TRANSMIT-002134 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-03 | Auspan-TRANSMIT-000348 | NA | Trade Partner | Update IFCed shop drawings for construction. 2P302 and 3P302. | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC- No review required, update register and distribute - KPTG-TRANSMIT-002135 |  | 2026-06-03 | KPTG-TRANSMIT-002135 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-03 | Auspan-TRANSMIT-000350 | NA | Trade Partner | Resubmit shop drawings level 1 for approval | 2 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 1149 | 2026-06-10 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-002289 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M3S1DH6 | 2025-12-19 | Altaire-TRANSMIT-000018 | NA | Trade Partner | Dry Fire Documents for DHA6-B Handover | 0 | 2 | 0 | NA | APPROVED | [5 empty] | As-Built, No review required. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-03 | M.2-TRANSMIT-000036 | NA | Trade Partner | Electrical Services Basement Lighting, Power & Tray/Penetration shop drawings | 15 | 0 | 0 | NA | REJECTED | [5 empty] | Drawings rejected due to incorrect drawing status - KPTG-SADV-002837 |  | 2026-06-03 | KPTG-SADV-002837 | Closed | 15 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-03 | M.2-TRANSMIT-000037 | NA | Trade Partner | Basement Lux Levels | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to incorrect drawing number KPTG-SADV-002837 |  | 2026-06-03 | KPTG-SADV-002837 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-03 | M.2-TRANSMIT-000038 | NA | Trade Partner | Basement Lux Levels | 2 | 0 | 0 | KPTG-IntCorr-000644 | APPROVED | 2026-06-04 | NA | 1152 | 2026-06-12 |  | Waiting for confirmation - KPTG-IntCorr-000644 | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-002184 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-03 | Civilex-TRANSMIT-000098 | NA | Trade Partner | Sewer Inspection Cover | 0 | 1 | 0 | NA | APPROVED | 2026-06-03 | WF-000644 | NA | 2026-06-05 |  |  | 2026-07-03 | 2026-07-03 | KPTG-TRANSMIT-002663 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-03 | Entire M-TRANSMIT-000022 | NA | Trade Partner | Industrial Water System - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-03 | WF-000183 | NA | 2026-06-11 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-000993 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-03 | Entire M-TRANSMIT-000021 | NA | Trade Partner | Mechanical Roof Penetration drawings FOA | 4 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 266 | 2026-06-09 |  | Terminated as advised by Chri Doh for submitting the updated drawings. | 2026-06-12 | 2026-06-12 | KPTG-IntCorr-000245 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-03 | ADP-TRANSMIT-000336 | NA | Consultant | Fwd: MEL4780 - S4 - Mech and Fuel Reports | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  |  |  | 2026-06-03 | KPTG-TRANSMIT-018211 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-03 | Ardon-TRANSMIT-000038 | NA | Trade Partner | Next DC M3 S4 Priority 4 Shop Drawings | 29 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 3436 | 2026-06-03 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-018873 | Closed | 29 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-03 | EAEGROUP-TRANSMIT-000098 | NA | Trade Partner | Fwd: Updated Shop Drawing Revision - GD GE GH GI | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | AS PER CLIENT REQUEST OLD WORKFLOW TERMINATED AND SUPERSED NEW ONE AND SENDED TO ALL PARTIES |  | 2026-06-03 | KPTG-TRANSMIT-018212 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-03 | ARCST-TRANSMIT-000300 | NA | Trade Partner | C1 Cooling Tower Roof Framing - Issued for Construction | 153 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-014208 - The document numbers,revision are incorrect. | 2026-06-03 | 2026-06-03 | KPTG-IntCorr-014208 | Closed | 153 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-11-13 | WSP ANZ-TRANSMIT-000015 | NA | Consultant | WSP - PDF Drawings - GMP For Pricing-VRT | 6 | 0 | 0 | NA | APPROVED | 2025-11-19 | NA | 67 |  |  | NA | 2025-12-01 | 2025-12-02 | KPTG-TRANSMIT-000207 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
M2S5DH11 | 2025-12-19 | GSAEng-TRANSMIT-000057 | NA | Trade Partner | CSMS documents | 2 | 2 | 0 | NA | APPROVED | [5 empty] | As-Built, No review required. Distributed to the Project Team. |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-03 | RDSBIM-TRANSMIT-000203 | NA | Trade Partner | LINDRUM ¦ CPP ¦ L-12,14,16,18,20,22,24&26 ¦ IFC ¦ SUBMISSION | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-001023 - As per instruction from Ashlin, this is a duplicate submission, and I have processed RDSBIM-TRANSMIT-000204. | 2026-06-03 | 2026-06-03 | KPTG-IntCorr-001023 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-15 | INDS-TRANSMIT-000041 | NA | Trade Partner | Dry Fire - Level 21 to Level 27 | 7 | 0 | 0 | NA | APPROVED | 2026-06-15 | NA | 667 | 2026-06-22 |  | KPTG-IntCorr-001033 - As per instruction from Mark, we hold this transmit. | 2026-06-30 | 2026-06-30 | KPTG-SADV-004712 | Closed | 7 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-03 | KPTG-TRANSMIT-002489 | NA | Trade Partner | HPS Sample For Review | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-001026 - The revision number and title are incorrect. | 2026-06-03 | 2026-06-03 | KPTG-IntCorr-001026 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-03 | KPTG-TRANSMIT-002490 | NA | Trade Partner | HPS TAP1 | 0 | 1 | 0 | NA | REJECTED |  | NA | NA |  |  | KPTG-IntCorr-001027 - The title inside the drawing and the title outside are different. | 2026-06-03 | 2026-06-03 | KPTG-IntCorr-001027 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-03 | KPTG-TRANSMIT-002491 | NA | Trade Partner | HPS Sample | 0 | 1 | 0 | NA | APPROVED | 2026-06-03 | 000780 | NA | 2026-06-08 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-03 | ACCCA-TRANSMIT-000002 | NA | Trade Partner | SWP STG 2 | 34 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 167 | 2026-06-11 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-000622 | Closed | 34 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-03 | HDRAus-TRANSMIT-000140 | NA | Consultant | M3 Stage 6 - Architectural Documentation Contract Issue (IFCN) | 2 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 165 | 2026-06-11 |  |  | 2026-06-11 | 2026-06-11 | NA | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-03 | 4DW-TRANSMIT-000183 | NA | Consultant | Structural Documentation - General updates | 6 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 291 | 2026-06-08 |  |  | 2026-06-10 | 2026-06-10 | KPTG-SADV-004602 | Closed | 6 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-03 | CRSol-TRANSMIT-000009 | NA | Trade Partner | CRS - Tech Data Submission NextDC M2 S9_11 | 0 | 1 | 0 | NA | APPROVED | 2026-06-03 | WF-000855 | NA | 2026-06-16 |  |  | 2026-07-03 | 2026-07-06 | KPTG-TRANSMIT-005223 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-03 | Ardon-TRANSMIT-000002 | NA | Trade Partner | M2 S9 Shop Drawings | 5 | 0 | 0 | NA | APPROVED | 2026-06-03 | WF-000857 | NA | 2026-06-11 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-004634 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-09 | WSP ANZ-TRANSMIT-000022 | NA | Consultant | WSP - PDF Drawings - Issued for Permit Interim-MEC | 56 | 0 | 0 | NA | APPROVED | 2025-12-22 |  | 156 | 2025-12-25 |  | As per KG advise, this review is not relevant as there is major design change in M2S9 |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-03 | DLTS-TRANSMIT-000014 | NA | Trade Partner | S9 Cooling Tower Gantry-IFA issue | 200 | 0 | 0 | NA | APPROVED | 2026-06-03 | WF-000858 | NA | 2026-06-12 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-004115 | Closed | 200 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-03 | DLTS-TRANSMIT-000014 | NA | Trade Partner | S9 Cooling Tower Gantry-IFA issue (Part-1) | 88 | 0 | 0 | NA | APPROVED | 2026-06-03 | WF-000859 | NA | 2026-06-12 |  |  | 2026-06-12 | 2026-06-12 | KPTG-TRANSMIT-004195 | Closed | 88 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-03 | ELLISAIR-TRANSMIT-000043 | NA | Trade Partner | IFA - Ball Valves | 0 | 1 | 0 | NA | APPROVED | 2026-06-03 | WF-000860 | NA | 2026-06-15 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-004149 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-03 | ELLISAIR-TRANSMIT-000045 | NA | Trade Partner | IFA - Strainers | 0 | 1 | 0 | NA | APPROVED | 2026-06-03 | WF-000864 | NA | 2026-06-09 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-004273 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-03 | Altaire-TRANSMIT-000011 | NA | Trade Partner | NEXTDC M2S9-11 - Cover, Index & Legend - Shop Drawings (FA-1) | 3 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 1038 | 2026-06-10 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-004559 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-04 | SES AU-TRANSMIT-000047 | NA | Trade Partner | SECURITY - RACK ELEVATIONS - IFC | 3 | 0 | 0 | NA | APPROVED | 2026-06-04 | WF-000292 | NA | 2026-06-08 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-000856 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-02 | PARR-TRANSMIT-000062 | NA | Trade Partner | Fuel Services - Cx TEMPLATES - Update | 0 | 3 | 0 | NA | APPROVED | 2026-06-02 | WF-001103 | NA | 2026-06-08 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-004019 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-02 | Baigents-TRANSMIT-000207 | NA | Trade Partner | LVL 5 Platform FOA-3 | 1 | 0 | 0 | NA | APPROVED | 2026-06-02 | WF-001101 | NA | 2026-06-04 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-003915 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-04 | Auspan-TRANSMIT-000352 | NA | Trade Partner | Precast shop drawings for construction. Level 1 | 12 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC Drawings- No Review: updated register and distributed: KPTG-TRANSMIT-002143 |  | 2026-06-04 | KPTG-TRANSMIT-002143 | Closed | 12 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-02 | D&E-TRANSMIT-000016 | NA | Trade Partner | LEVEL 2 - PLANT ROOM DUCTWORK SHOP DRAWINGS - IFA | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | rejected |  | 2026-06-02 | KPTG-TRANSMIT-002111 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-19 | Auspan-TRANSMIT-000032 | NA | Trade Partner | Precast shop drawings for approval. | 29 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong title Guide-KPTG-TRANSMIT-000412 Kapitol initiated an Internal Workflow-WF-000054 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-04 | SES AU-TRANSMIT-000048 | NA | Trade Partner | SECURITY - SINGLE LINE DIAGRAMS AND VIDEO RISER SCHEDULE -IFA | 7 | 0 | 0 | NA | APPROVED | 2026-06-04 | WF-000293 | NA | 2026-06-10 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-000846 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-02 | PCForm-TRANSMIT-000223 | NA | Trade Partner | Updated Stairform Shop Drawings (Rev.1) | 34 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | rejected QA Error |  | 2026-06-02 | KPTG-TRANSMIT-002124 | Closed | 34 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-02 | INGEN3D-TRANSMIT-000095 | NA | Trade Partner | Level 10-12 - Precast Columns - IFA | 56 | 0 | 0 | NA | APPROVED | 2026-06-02 | WF-000645 | NA | 2026-06-19 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-002446 | Closed | 56 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-04 | RDSBIM-TRANSMIT-000021 | NA | Trade Partner | MEL11C45 ¦ LEVEL 02 COLO 4 AREA PARTITION WALL LAYOUT | 4 | 0 | 0 | NA | APPROVED | 2026-06-04 | WF-000294 | NA | 2026-06-09 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-000812 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-06-04 | Carr-TRANSMIT-000069 | NA | Consultant | Basement Concrete Profile Plans - IFC Issue | 2 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 225 | 2026-06-11 | [5 empty] | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-04 | Auspan-TRANSMIT-000355 | NA | Trade Partner | Precast shop drawings for construction. Levels 3, 4 | 17 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC Drawings: No review, Updated register and distributed- KPTG-TRANSMIT-002146 |  | 2026-06-04 | KPTG-TRANSMIT-002146 | Closed | 17 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-04 | RDSBIM-TRANSMIT-000212 | NA | Trade Partner | 511SRC ¦ LEVEL 11 RCP KEY PLAN AND LAYOUT | 2 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Distribution only. |  | 2026-06-04 | DRAFT-018569 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-04 | ARCH-TRANSMIT-000155 | NA | Consultant | MLC - SPR - ISC - Drawing Update | 5 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 293 | 2026-06-08 |  | One Drawing is terminated from the workflow | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-003007 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-03 | 4Ki-TRANSMIT-000011 | NA | Trade Partner | Shop Drawings For Approval - JNR001, JNR004, JNR014, JNR015 | 3 | 0 | 0 | NA | APPROVED | 2026-06-04 | WF-001104 | NA | 2026-06-09 |  |  | 2026-06-05 | 2026-06-09 | KPTG-TRANSMIT-003874, KPTG-TRANSMIT-003879, KPTG-TRANSMIT-003884 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-04 | Appselec-TRANSMIT-000117 | NA | Trade Partner | AFL BILL OF MATERIALS (ZTN NETWORK) - COLO4 & COLO5 - Issued For Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-04 | WF-000295 | NA | 2026-06-10 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-000874 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-18 | Auspan-TRANSMIT-000031 | NA | Trade Partner | Update marking plan for L shape panels | 1 | 0 | 0 | NA | REJECTED | [5 empty] | Wrong title Guide-KPTG-TRANSMIT-000432 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-04 | Altaire-TRANSMIT-000011 | NA | Trade Partner | MEL05C4 - Fire Cx Plan | 1 | 0 | 0 | NA | APPROVED | 2026-06-04 | WF - 000448 | NA | 2026-06-09 |  | NA | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-000966 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-04 | Schindle-TRANSMIT-000018 | NA | Trade Partner | Lift Drawings IFC | 1 | 0 | 0 | NA | REJECTED | [5 empty] | The drawing number and Title inside the drawing and in Aconex seem different |  | 2026-06-04 | KPTG-TRANSMIT-000980 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-04 | Auspan-TRANSMIT-000353 | NA | Trade Partner | Precast shop drawings for construction. Level 2. | 7 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC drawings: No review, updated register and distributed-KPTG-TRANSMIT-002150 |  | 2026-06-04 | KPTG-TRANSMIT-002150 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-04 | D&E-TRANSMIT-000787 | NA | Trade Partner | NXM3S4 - Ground - Mechanical Duct Layout Zones - Issued For Construction | 3 | 0 | 0 | NA | APPROVED | [5 empty] | IFC Drawings .- distributed to all |  | 2026-06-04 | KPTG-TRANSMIT-018222 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-04 | Entire M-TRANSMIT-000023 | NA | Trade Partner | VRF Airconditioning - Issued for approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-04 | WF-000185 | NA | 2026-06-12 |  |  | 2026-06-12 | 2026-06-11 | KPTG-TRANSMIT-000796 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-04 | Entire M-TRANSMIT-000024 | NA | Trade Partner | Filters - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-04 | WF-000186 | na | 2026-06-12 |  |  | 2026-07-02 | 2026-07-02 | KPTG-TRANSMIT-000997 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-04 | D&E-TRANSMIT-000788 | NA | Trade Partner | NXM3S2 - Chilled Water & SFN Water Schematic - First Floor - Mech Corridor & Data Hall B6 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 4255 | 2026-06-11 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-019093 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-04 | EFP-TRANSMIT-000026 | NA | Trade Partner | EFP Tech Data response to Consultant comments | 0 | 2 | 0 | NA | APPROVED | 2026-06-04 | WF-000296 | NA | 2026-06-05 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-000815 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-04 | RDSBIM-TRANSMIT-000054 | NA | Trade Partner | MCC ¦ LEVEL 01 FINISHES ¦ UAT WC LH ¦ IFA ¦ SUBMISSION | 1 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 310 | 2026-06-11 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-04 | SES AU-TRANSMIT-000049 | NA | Trade Partner | SECURITY- CONTAINMENT PLANS - IFA | 3 | 0 | 0 | NA | APPROVED | 2026-06-04 | WF-000297 | NA | 2026-06-10 |  |  | 2026-06-04 | 2026-06-04 | KPTG-IntCorr-000522 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2025-12-20 | Stowe-A-TRANSMIT-000423 Re: S4 ¦ Stowe IFA - C1 Data Hall Containment layouts | NA | Trade Partner | S4 ¦ Stowe IFA - C1 Data Hall Containment layouts | 7 | 0 | 0 | NA | REJECTED | [5 empty] | the document reference number and aconex reference number do not align with s4 project |  |  |  | Closed |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-04 | VIA Arch-TRANSMIT-000152 | NA | Consultant | Architecture - Stage 9 - Concrete Profile Plans - Level 2 | 1 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 1040 | 2026-06-09 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-003663 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-04 | D&E-TRANSMIT-000789 | NA | Trade Partner | Re: Stage 2 Fire Matrix Discrepancies | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Issue with Revision, mixed status. |  | 2026-06-04 | KPTG-TRANSMIT-018241 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-03 | OveArup-TRANSMIT-000038 - FIR | NA | Consultant | Early works drawing update | 2 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 723 | 2026-06-09 |  |  | 2026-06-21 | 2026-06-22 | KPTG-TRANSMIT-002415 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-03 | OveArup-TRANSMIT-000038 - ELE | NA | Consultant | Early works drawing update | 1 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 725 | 2026-06-09 |  |  | 2026-06-21 | 2026-06-22 | KPTG-TRANSMIT-002420 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-03 | TTW-TRANSMIT-000168 | NA | Consultant | BP4 construction update | 11 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 727 |  |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-002215 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-03 | RDSBIM-TRANSMIT-000032 | NA | Trade Partner | DISTLV - GROUND FLOOR CONCRETE PROFILE PLAN AND SECTIONS | 7 | 0 | 0 | NA | APPROVED | 2026-06-03 | NA | 718 | 2026-06-11 |  | Already closedout but requested to be put in workflow by kapitol | 2026-06-12 | 2026-06-12 | KPTG-TRANSMIT-002262 | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-01 | Civilex-TRANSMIT-000095 | NA | Trade Partner | Re: FW Finish RFI | 0 | 1 | 0 | NA | APPROVED | 2026-06-02 | WF-000639 | NA | 2026-06-04 |  |  | 2026-06-04 | 2026-06-03 | KPTG-TRANSMIT-002118 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-04 | D&E-TRANSMIT-000784 | NA | Trade Partner | M3-BMS-DEA-DS-C-0400-0001 - No longer in use | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | NLIU |  | 2026-06-04 | KPTG-TRANSMIT-018217 | Open | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-03 | ZIA-TRANSMIT-000059 | NA | Trade Partner | CSMS Interface Sheets | 0 | 12 | 0 | KPTG-IntCorr-001406 | APPROVED | [5 empty] | FC DOCS - COMMISSIONING RESULTS - ibrahim to confirm - KPTG-IntCorr-001406 |  |  |  | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-03 | ZIA-TRANSMIT-000060 | NA | Trade Partner | Cx L3 Test Documents - IT Racks & LTMR | 0 | 124 | 0 | NA | APPROVED | 2026-06-03 | WF-001105 | NA | 2026-06-05 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-004006 | Closed | 124 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-18 | WSP ANZ-TRANSMIT-000030 | NA | Consultant | WSP - Electrical PDF Drawings - Issued for Permit Interim (HIGH VOLTAGE) | 12 | 0 | 0 | NA | APPROVED | 2025-12-16 |  | 153 | 2025-12-19 |  |  | 2025-12-19 | 2025-12-22 | KPTG-TRANSMIT-000416 | Closed | 12 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-05-21 | INTRFRM-TRANSMIT-000059 | NA | Trade Partner | Geelong Edge - Electrical Tech Data (Submission 5) | 0 | 5 | 0 | NA | APPROVED | 2026-05-21 | WF-000148 | NA | 2026-05-29 |  |  | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-000747 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-04 | ADP-TRANSMIT-000338 | NA | Consultant | MEL4780 - S4 - Updated Electrical drawings | 6 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 3441 | 2026-06-08 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018521 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-04 | Hames-TRANSMIT-000161 | NA | Consultant | Latest Revision | 4 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 1283 | 2026-06-08 |  |  | 2026-08-05 | 2026-08-06 | KPTG-TRANSMIT-004232 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-04 | vdmcons-TRANSMIT-000138 | NA | Trade Partner | ME25 1004: D120 511-537 Sydney Rd Coburg - Shop Drawings & 3D IFC Model - L03 East Pavilion Redesign - IFF - 2026-06-04 | 52 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | IFC - Aconex register update only. |  | 2026-06-04 | NA | Closed | 52 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-04 | D&E-TRANSMIT-000791 | NA | Trade Partner | NXM3S4 - Level 1 - Plinth & Equipment Layout Zones - Issued For Construction | 8 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | #3447 | 2026-06-25 |  |  |  | 2026-06-11 | NA | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-04 | Jangho-TRANSMIT-000135 | NA | Trade Partner | Re: 004_Podium Visual Mock-UP Shop Drawing_Rev:A | 1 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 730 | 2026-06-12 |  |  | 2026-07-01 | 2026-07-01 | KPTG-TRANSMIT-002630 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-04 | Entire M-TRANSMIT-000025 | NA | Trade Partner | Fire Matrix - Issued for Approval | 0 | 1 | 0 | NA | APPROVED | 2026-06-04 | WF-000187 | NA | 2026-06-12 |  |  | 2026-07-15 | 2026-07-15 | KPTG-TRANSMIT-001136 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-04 | Entire M-TRANSMIT-000044 | NA | Trade Partner | Battery Exhaust Fans Issued for Approval | 4 | 0 | 0 | NA | APPROVED | 2026-06-04 | WF - 000449 | NA | 2026-06-10 |  | NA | 2026-06-23 | 2026-06-23 | Entire M-TRANSMIT-000044 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-04 | ELLISAIR-TRANSMIT-000049 | NA | Trade Partner | Next DC Stage 9 - Level 1 and Level 2 Pipework GA layouts drawings issued for Approval. | 6 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 1042 | 2026-06-11 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-004497 | Closed | 6 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-04 | PCForm-TRANSMIT-000225 | NA | Trade Partner | Updated Profile Plans | 6 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 732 | 2026-06-12 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-002485 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-17 | NCFGroup-TRANSMIT-000020 | NA | Trade Partner | ISG & Rincovitch Stage 10-11 Certificate | 2 | 2 | 0 | NA | REJECTED | [5 empty] | KPTG-TRANSMIT-000418 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-04 | TTW-TRANSMIT-000035 | NA | Consultant | M3 Sage 6 Facade perforamnce specificaiton and drawing | 17 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Drawing status not matching |  | 2026-06-04 | KPTG-DA-000305 | Closed | 17 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-04 | Altaire-TRANSMIT-000013 | NA | Trade Partner | NEXTDC M2S11 - Level 1 - Shop Drawings (FA-1) | 1 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 1044 | 2026-06-11 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-004592 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-04 | NXT-TRANSMIT-000396 | NA | Client | Stage 6 Civil Drawings - Issue for Contract CAD Files | 38 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Cad-Distributed |  | 2026-06-04 | KPTG-TRANSMIT-000153 | Closed | 38 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-04 | SMEPS-TRANSMIT-000225 | NA | Trade Partner | SME Samples for review | 4 | 0 | 0 | NA | APPROVED | 2026-06-04 | WF - 000450 | NA | 2026-06-09 |  | NA | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-000958 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-04 | JCBa-TRANSMIT-000129 | NA | Consultant | Updated Architectural Documentation - Ground Level GA Plans | 2 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 1160 | 2026-06-08 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-002354 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-04 | ADP-TRANSMIT-000339 | NA | Consultant | MEL4561- S2 Reports (CAN Water Supply & Lighting Report) | 0 | 2 | 0 | NA | APPROVED |  | NA | NA |  |  | For information, Updation and distribution only. |  | 2026-06-04 | KPTG-TRANSMIT-018252 | Open | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-04 | RDSBIM-TRANSMIT-000008 | NA | Trade Partner | LEVEL 01 ¦CPP-BLOCK 3¦ IFR¦ FOR SUBMISSION | 2 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 169 | 2026-06-12 |  |  | 2026-06-11 | 2026-06-11 | KPTG-TRANSMIT-000194 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-04 | INTRFRM-TRANSMIT-000071 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 13) | 0 | 1 | 0 | NA | APPROVED | 2026-06-04 | WF-000188 | NA | 2026-06-12 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-000755 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-04 | Civilex-TRANSMIT-000099 | NA | Trade Partner | Re: Pavement Material | 0 | 2 | 0 | NA | REJECTED | [5 empty] | Error in document number |  | 2026-06-04 | KPTG-TRANSMIT-002131 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-04 | SRA-PMQ-TRANSMIT-000001 | NA | Trade Partner | Doc Number & Transmittals | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Issue with Revision number, drawings status, reason and Cover sheet missing. |  | 2026-06-04 | KPTG-SADV-000579 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-15 | PCForm-TRANSMIT-000022 | NA | Trade Partner | Jumpform Concrete Envelopes & Wall Elevations - Stage 9 - Stair 3 - Issued for Construction | 5 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-TRANSMIT-000419 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-04 | D&E-TRANSMIT-000795 | NA | Trade Partner | NXM3S2 - Industrial Water Schematic / Chilled Water & SFN Schematics - Ground + First Floor - Issued For Construction | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Same revision of a drawings in the set is resubmitted. |  | 2026-06-04 | KPTG-SADV-005738 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-04 | RDSBIM-TRANSMIT-000066 | NA | Trade Partner | GREYSTAR GROUND FLOOR CONCRETE PROFILE PLAN ZONE 2 | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | As advised by Michael H, DM - No Action required ; RDS to submit updated drawing. |  | 2026-06-04 | NA | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-04 | Auspan-TRANSMIT-000351 | NA | Trade Partner | Resubmit shop drawings for approval. Level 4 | 3 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 1154 | 2026-06-11 |  |  | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-002314 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-04 | Auspan-TRANSMIT-000354 | NA | Trade Partner | Deleted panel 3P1057 | 1 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 1157 | 2026-06-11 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-002306 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-04 | Auscool-TRANSMIT-000042 & 000043 | NA | Trade Partner | BW Drawings - Including Precast Penetrations | 14 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 1162 | 2026-06-12 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-002299 | Closed | 14 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S3 | 2026-06-04 | Nilsen3-TRANSMIT-000179 | NA | Trade Partner | M3-ELC-NIL-SDRG-S-0301-3102 Drawing updated to FC-3 | 1 | 0 | 0 | NA | APPROVED | 2026-06-04 | WF-005939 | NA | 2026-06-17 |  |  | 2026-07-27 | 2026-07-27 | KPTG-TRANSMIT-020005 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-04 | RDSBIM-TRANSMIT-000055 | NA | Trade Partner | MWYCCB ¦ LEVEL 01 INTERNAL FITOUT PLAN - MALE WC | 2 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 311 | 2026-06-11 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-04 | D&E-TRANSMIT-000794 | NA | Trade Partner | IPT Pipe Fabrication Procedures - Offsite & Onsite Passivation - Issued for Approval | 0 | 2 | 0 | NA | APPROVED | 2026-06-04 | WF-005940 | NA | 2026-06-08 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-04 | LNCPPL-TRANSMIT-000006 | NA | Trade Partner | Mezz Penos - IFA | 2 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 736 | 2026-06-12 |  |  | 2026-06-12 | 2026-06-12 | KPTG-TRANSMIT-002253 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-04 | HVHD-TRANSMIT-000015 | NA | Trade Partner | Upfront Carbon Report Version 02 | 0 | 1 | 0 | NA | APPROVED | 2026-06-04 | WF-000657 | NA | 2026-06-05 |  |  | 2026-06-05 | 2026-06-10 | KPTG-TRANSMIT-002239 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-16 | PCForm-TRANSMIT-000026 | NA | Trade Partner | Jumpform Concrete Envelopes - Stage 10 - Stair 8 - Issued for Construction | 3 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-TRANSMIT-000420 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-04 | D&E-TRANSMIT-000790 | NA | Trade Partner | Fwd: NXM3S4 - Ground - SFN Pipe Layout Zones - Issued For Construction | 7 | 0 | 0 | NA | APPROVED | [5 empty] | CONFIRMATION SEEKED AND AS PER THEIR REQUEST FOR PLACING WORFLOW |  | 2026-06-04 | KPTG-TRANSMIT-018242 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-04 | D&E-TRANSMIT-000792 | NA | Trade Partner | G-NXM3S4 - Level 1 - Plinth & Equipment Layout - Zone 9 & 10 - Issued For Approval | 2 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 3433 | 2026-06-24 |  |  | 2026-07-23 | 2026-07-23 | ⁠KPTG-TRANSMIT-019895 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-04 | D&E-TRANSMIT-000793 | NA | Trade Partner | Fwd: NXM3S4 - Ground - CHW Pipe Layout Zone 2 & 7 - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | [7 empty] | 2026-06-04 | KPTG-TRANSMIT-018258 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-04 | EAEGROUP-TRANSMIT-000099 | NA | Trade Partner | Re: Shop Drawings – GG IT, FH Mech, Loadbank and UJ Catcher Zone C2 Busduct | 4 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-06-04 | KPTG-RFI-008267 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-04 | D&E-TRANSMIT-000790 | NA | Trade Partner | NXM3S4 - Ground - SFN Pipe Layout Zones - Issued For Construction | 7 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 3448 | 2026-06-09 |  |  | 2026-08-20 | 2026-08-20 | KPTG-TRANSMIT-020757 | Closed | 7 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-04 | RDSBIM-TRANSMIT-000205 | NA | Trade Partner | LINDRUM ¦ LEVEL 05 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 663 | 2026-06-09 |  |  | 2026-06-16 | 2026-06-16 | KPTG-SADV-004513 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-04 | Entire M-TRANSMIT-000057 | na | Trade Partner | Document IFCs; Fans, Pipe Fittings, IFDs | 0 | 3 | 0 | NA | REJECTED | [5 empty] | Rejected: Revision of Document is incorrect:KPTG-IntCorr-000514 |  | 2026-06-04 | KPTG-IntCorr-000514 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-04 | PCForm-TRANSMIT-000085 | NA | Trade Partner | Fwd: Level 6 - Updated Drawings | 5 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001030 - As per instruction Ashlin, we only update register and issue out to everyone. | 2026-06-04 | 2026-06-04 | KPTG-IntCorr-001030 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-02 | TATE_-TRANSMIT-000026 | na | Trade Partner | Mel 11-Tate-D-BULB TDS | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Application Guideline document, not a Tech Data Sheet. KPTG-SADV-000973 |  | 2026-06-02 | KPTG-SADV-000973 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-04 | AFAC-TRANSMIT-000005 | NA | Trade Partner | Facade Access Report Update | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | KPTG-IntCorr-001031 - Re: Facade Access Report Update | 2026-06-04 | 2026-06-04 | KPTG-IntCorr-001031 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-17 | PCForm-TRANSMIT-000027 | NA | Trade Partner | Jumpform Wall elevation - Stage 10 - Stair 8 - Issued for Approval | 2 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-TRANSMIT-000421 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-04 | KETE-TRANSMIT-000135 | NA | Trade Partner | Tower East elevation – revised division | 4 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 664 | 2026-06-09 |  |  | 2026-07-29 | 2026-07-29 | KPTG-SADV-005129 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-04 | Arc Plas-TRANSMIT-000012 | NA | Trade Partner | Plasterboard Samples - Proposed Knauf System | 0 | 4 | 0 | NA | APPROVED | 2026-06-04 | WF-000865 | NA | 2026-06-15 |  | Resubmitted as advised by Project Coordinator (Joseph) New workflow # WF-001121 |  | 2026-07-03 | NA | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-04 | DCN-TRANSMIT-000011 | NA | Trade Partner | Link Bridge - Material Tech Data | 0 | 10 | 0 | NA | APPROVED | 2026-06-04 | WF-000866 | NA | 2026-06-09 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-004575 | Closed | 10 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-04 | DCN-TRANSMIT-000011 | NA | Trade Partner | Link Bridge - Material Tech Data | 0 | 8 | 0 | NA | APPROVED | 2026-06-04 | WF-000867 | NA | 2026-06-09 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-004575 | Closed | 8 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-04 | ELLISAIR-TRANSMIT-000048 | NA | Trade Partner | check valves | 0 | 1 | 0 | NA | APPROVED | 2026-06-04 | WF-000868 | NA | 2026-06-16 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-004453 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-04 | ELLISAIR-TRANSMIT-000047 | NA | Trade Partner | Registers | 0 | 1 | 0 | NA | APPROVED | 2026-06-04 | WF-000870 | NA | 2026-06-16 |  |  | 2026-06-26 | 2026-06-26 | KPTG-TRANSMIT-004885 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-04 | Altaire-TRANSMIT-000014 | NA | Trade Partner | NEXTDC M2S11 - MASDS Aspire Calculations (FA-1) | 0 | 1 | 0 | NA | APPROVED | 2026-06-04 | WF-000873 | NA | 2026-06-16 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-004290 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-22 | DCN-TRANSMIT-000006 | NA | Trade Partner | M2 Link Bridge - Window/Handrail/Service Gantry Grating Tech data | 0 | 1 | 0 | NA | APPROVED | 2026-06-03 | WF-000861 | NA | 2026-06-08 |  | Resubmitted for TTW review as advised by PC | 2026-06-17 | 2026-06-17 | KPTG-TRANSMIT-004326 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-04 | RDSBIM-TRANSMIT-000144 | na | Trade Partner | MLCSPR ¦ ATTRIBUTE - STAGE 2 ¦ BULK EXCAVATION LEVEL LAYOUT ¦ FOR SUBMISSION | 1 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 295 | 2026-06-05 |  |  | 2026-06-29 | 2026-06-29 | KPTG-TRANSMIT-003029 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-04-17 | Nilsen3-TRANSMIT-000002 | NA | Trade Partner | Nilsen Sample submission # 1 | 0 | 16 | 0 | NA | APPROVED | 2026-05-29 | WF-000809 | NA | 2026-06-04 |  | Documents resubmitted for WSP review as advised by Lachlan Dowell | 2026-06-04 | 2026-06-04 | KPTG-TRANSMIT-003958 | Closed | 16 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-11-10 | VIA Arch-TRANSMIT-000003 | NA | Consultant | Architectural Specification | 0 | 1 | 0 | NA | APPROVED | 2025-11-20 | NA | 69 | 2025-11-25 |  | NA | 2025-12-01 | 2025-12-02 | KPTG-TRANSMIT-000211 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-18 | PCForm-TRANSMIT-000031 | NA | Trade Partner | S11 - STAIR & LIFT CORES CONCRETE OUTLINE DRAWINGS IFC | 2 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-TRANSMIT-000422 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-28 | PCForm-TRANSMIT-000171 | NA | Trade Partner | Re: Stair 05 shop drawings | 1 | 0 | 0 | 0 | APPROVED | 2026-05-29 | WF-005884 | NA | 2026-06-05 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-018263 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-05 | RED Fire-TRANSMIT-000004 | NA | Consultant | Revised FER (Version: FER7) for approval | 0 | 1 | 0 | NA | APPROVED |  | NA | NA |  |  | Report, issued to all parties |  | 2026-06-05 | KPTG-TRANSMIT-002948 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-05 | ARCH-TRANSMIT-000156 | NA | Consultant | MLC - SPR - AQC - L2 - J93 [Operable door cabinet) | 1 | 0 | 0 | NA | REJECTED | [5 empty] | DOCUMENT NUMBERING IS INCORRECT:KPTG-SADV-004562 |  | 2026-06-05 | KPTG-SADV-004562 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-05 | Rinco-TRANSMIT-000053 | NA | Consultant | GF TMJ Sections | 8 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | 1164 | 2026-06-09 |  |  | 2026-06-19 | 2026-06-19 | KPTG-TRANSMIT-002370 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-05 | ARCH-TRANSMIT-000157 | NA | Consultant | MLC - SPR - AQC - L2 joinery | 1 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | 297 | 2026-06-10 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-002958 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-05 | INTRFRM-TRANSMIT-000072 | NA | Trade Partner | Geelong Edge - Structural Tech Data (Submission 14) | 0 | 2 | 0 | NA | APPROVED | 2026-06-05 | WF-000189 | NA | 2026-06-15 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-000751 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-05 | RDSBIM-TRANSMIT-000213 | NA | Trade Partner | 511SRC ¦ LEVEL13 RCP LAYOUT TOWER B | 2 | 0 | 0 | NA | APPROVED |  | NA | NA | 2026-06-12 |  | IFC - Updated and Distribution only. |  | 2026-06-05 | DRAFT-018611 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-05 | SMEPS-TRANSMIT-000226 | NA | Trade Partner | SME Samples for review | 0 | 2 | 0 | NA | APPROVED | 2026-06-05 | WF - 000452 | NA | 2026-06-12 |  | NA | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-001022 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
303COL | 2026-05-28 | Carr-TRANSMIT-000066 | NA | Consultant | TP Amendment - Updated Plans | 9 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | 228 | 2026-06-12 |  | Review Voided as advised By Renee |  | 2026-08-05 | NA | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-05 | TATE_-TRANSMIT-000005 | SPARK-CRFI-KPG-000697 | Trade Partner | MWYCCB - Tate - Technical Data Sheet | 0 | 3 | 0 | NA | APPROVED |  | NA | NA |  |  |  | 2026-08-13 | 2026-08-13 | KPTG-TRANSMIT-001621 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-19 | WGAVIC-TRANSMIT-000037 | NA | Consultant | Structural Drawings - Stages 10 and 11 - Issued for Information | 27 | 0 | 0 | NA | APPROVED | 2025-12-22 |  | 158 | 2026-01-12 |  | As per KG advise, this review is not relevant as these drawings will get revised due to major design change |  |  |  | Closed |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-05 | SMEPS-TRANSMIT-000227 | NA | Trade Partner | EXTERNAL EPMS BAS ROUTING LAYOUT | 1 | 0 | 0 | NA | APPROVED | 2026-06-05 | WF - 000453 | NA | 2026-06-12 |  | NA | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-000962 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-05 | ACCCA-TRANSMIT-000003 | NA | Trade Partner | Electrical Pit -For Approval | 6 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | 171 | 2026-06-15 |  |  | 2026-07-20 | 2026-07-20 | KPTG-TRANSMIT-000621 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-05 | D&E-TRANSMIT-000796 | NA | Trade Partner | NXM3S4 - Ground - Industrial Water Tank Layout - Zone 8 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | 3451 | 2026-06-14 |  | As instructed by Ellie, - Terminated D&E need to make IFC drawing updates |  | 2026-07-17 | NA | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-05 | KPTG-TRANSMIT-018262 | NA | Trade Partner | S4 Arc Plaster - Proma SupaWrap Tech data Update | 0 | 1 | 0 | NA | APPROVED | 2026-06-05 | WF-005944 | NA | 2026-06-16 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-05 | NXT-TRANSMIT-001599 | NA | Trade Partner | Fwd: 100222 : NEXT DC M3 STAGE 2 - SAMPLE-33 FIRE STROBE CELLING MOUNT | 0 | 1 | 0 | NA | APPROVED | 2026-06-05 | WF-005946 | NA | 2026-06-17 | [5 empty] | Open |  | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-05 | Ardon-TRANSMIT-000039 | NA | Trade Partner | Re: Test Prototype Set for Oversized Roof Chiller Doors | 1 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  |  |  | 2026-06-05 | KPTG-RFI-008275 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-05 | Auspan-TRANSMIT-000356 | NA | Trade Partner | Precast shop drawings for approval. Level 4 | 49 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | 1166 | 2026-06-12 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-002386 | Closed | 49 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-05 | SES AU-TRANSMIT-000050 | NA | Trade Partner | Shop Drawing Drafting Error | 6 | 0 | 0 | NA | APPROVED | 2026-06-05 | WF-000298 | NA | 2026-06-09 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-000897 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-05 | SES AU-TRANSMIT-000050 | NA | Trade Partner | Shop Drawing Drafting Error-WF-02 | 3 | 0 | 0 | NA | APPROVED | 2026-06-05 | WF-000299 | NA | 2026-06-11 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-000854 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-04 | Hollow-TRANSMIT-000015 | NA | Trade Partner | Concrete Mix Design and Packing Shims | 0 | 2 | 0 | NA | REJECTED | [5 empty] | QA ERROR |  | 2026-06-04 | KPTG-IntCorr-000764 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2025-12-23 | RDSBIM-TRANSMIT-000132 | NA | Trade Partner | LEVEL 07 RCP KEY PLAN AND LAYOUT | 10 | 0 | 0 | NA | APPROVED | 2025-12-23 | WF-000852 | 518 | 2026-01-21 |  |  | 2026-01-27 | 2026-01-27 | KPTG-TRANSMIT-002632 | Closed | 10 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-04 | Hollow-TRANSMIT-000016 | NA | Trade Partner | Concrete Mix Design and Packing Shims | 0 | 1 | 0 | NA | APPROVED | 2026-06-04 | WF-000658 | NA | 2026-06-08 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-002303 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-04 | Hollow-TRANSMIT-000015 | NA | Trade Partner | Concrete Mix Design and Packing Shims | 0 | 1 | 0 | NA | APPROVED | 2026-06-04 | WF-000658 | NA | 2026-06-08 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-002303 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-04 | INGEN3D-TRANSMIT-000097 | NA | Trade Partner | Level 6-8 - MP0102 & MP0107 - Revised IFC | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | FC DOCS |  | 2026-06-04 | KPTG-TRANSMIT-002154 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-04 | PCForm-TRANSMIT-000227, 229 | NA | Trade Partner | Stairform - Stair drawings - ifc | 15 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 739 | 2026-06-11 |  |  | 2026-07-06 | 2026-07-07 | KPTG-TRANSMIT-002732,KPTG-TRANSMIT-002734 | Closed | 15 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-04 | PCForm-TRANSMIT-000227, 229 | NA | Trade Partner | Stairform - Stair drawings - ifa | 20 | 0 | 0 | NA | APPROVED | 2026-06-04 | NA | 740 | 2026-06-29 |  |  | 2026-07-06 | 2026-07-07 | KPTG-TRANSMIT-002738 | Closed | 20 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-05 | Auspan-TRANSMIT-000357 | NA | Trade Partner | Precast shop drawings for approval. Level 5 | 77 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | 1168 | 2026-06-12 |  |  | 2026-07-16 | 2026-07-16 | KPTG-TRANSMIT-002809 | Closed | 77 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-05-12 | ARCST-TRANSMIT-000288 | NA | Trade Partner | We can't submit all 223 documents together in the workflow, so the 223 documents have been split: 100 documents in WF-005675 & 123 documents in WF-005676 | 0 | 0 | 0 | NA | APPROVED | 2026-05-12 | WF-005675 | NA | 2026-06-05 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-018270 | Closed | 100 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-05 | Entire M-TRANSMIT-000045 | NA | Trade Partner | Mechanical Shop drawings - Issued for Construction | 6 | 0 | 0 | NA | APPROVED | 2026-06-05 | WF - 000454 | NA | 2026-06-09 |  | NA | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-000963 | Closed | 6 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-05 | Entire M-TRANSMIT-000058 | NA | Trade Partner | Document IFCs; Fans, Pipe Fittings, IFDs | 0 | 3 | 0 | NA | APPROVED | 2026-06-05 | WF-000300 | NA | 2026-06-09 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-000843 | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-04 | INGEN3D-TRANSMIT-000096 | NA | Trade Partner | Level 11-13 - Precast Columns - IFA | 50 | 0 | 0 | NA | APPROVED | 2026-06-04 | WF-000659 | NA | 2026-06-18 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-18 | UNI-TRANSMIT-000003 | NA | Trade Partner | Tower Cranes - Updated Drawings | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Awaiting approval |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-05 | Auspan-TRANSMIT-000358 | NA | Trade Partner | Update IFCed shop drawings for construction. Level 1 | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC Drawings: No review, Updated register and distributed -KPTG-TRANSMIT-002161 |  | 2026-06-05 | KPTG-TRANSMIT-002161 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-05 | NXT-TRANSMIT-001601 | NA | Trade Partner | NXT-TRANSMIT-001601-100222-000589-M3 Stage 2 - EA Room - Architectural Drawings - As Built | 10 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | 4258 | 2026-06-10 |  | WF Terminated as advised by Katherine, as As Built from NEXTDC doesnt needs to be reviewed and can be distributed straight away. | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-018278 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-05 | RDSBIM-TRANSMIT-000067 | NA | Trade Partner | GREYSTAR GROUND FLOOR CONCRETE PROFILE PLAN ZONE 2 | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | No review, Updated Register and distributed-KPTG-TRANSMIT-002163 |  | 2026-06-05 | KPTG-TRANSMIT-002163 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-05 | Civilex-TRANSMIT-000100 | NA | Trade Partner | Re: Pavement Material | 0 | 1 | 0 | NA | APPROVED | 2026-06-05 | WF-000661 | NA | 2026-06-16 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-002280 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXD1S2 | 2026-06-04 | Baigents-TRANSMIT-000213 | NA | Consultant | MP-39_GF EXTERNAL ENTRY (LOBBY) HANDRAIL MARKING PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-06-05 | WF-001109 | NA | 2026-06-08 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-003911 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-05 | D&E-TRANSMIT-000797 | NA | Trade Partner | NXM3S4 - Ground - CHW Pipe Layout - Zone 9 | 1 | 0 | 0 | NA | APPROVED | [5 empty] | IFC - DRAWING |  | 2026-06-05 | KPTG-TRANSMIT-018277 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-05 | D&E-TRANSMIT-000798 | NA | Trade Partner | NXM3S4 - Ground - Industrial Water Tank Layout - Zone 10 - Issued For Construction | 1 | 0 | 0 | NA | APPROVED | [5 empty] | IFC - DRAWING | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-018279 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-05 | NXT-TRANSMIT-001602 | NA | Trade Partner | Fwd: 100222-000590: M3 Stage 2 - EB Room - Architectural As Built Drawings | 10 | 0 | 0 | NA | APPROVED | [5 empty] | As Built, for update in Aconex and ACC and distibution as advised by Katherine. |  | 2026-06-05 | KPTG-TRANSMIT-018282 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-05 | NXT-TRANSMIT-001606 | NA | Trade Partner | Fwd: 100222-000591: M3 Stage 2 - EC Room - Architectural As Built Drawings | 10 | 0 | 0 | NA | APPROVED | [5 empty] | As Builts from NEXTDC can be directly updated in Aconex and ACC and can be distributed as per Katherine. |  | 2026-06-05 | KPTG-TRANSMIT-018286 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-22 | Auspan-TRANSMIT-000033 | NA | Trade Partner | Precast shop drawings for aprpoval. | 9 | 0 | 0 | NA | REJECTED | [5 empty] | KPTG-TRANSMIT-000433 |  |  |  | Closed |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-05 | NXT-TRANSMIT-001607 | NA | Trade Partner | Fwd: 100222-000592: M3 Stage 2 - EP Room - Architectural As Built Drawings | 10 | 0 | 0 | NA | APPROVED | [5 empty] | As Builts from NEXTDC can be directly updated in Aconex and ACC and can be distributed as per Katherine. |  | 2026-06-05 | KPTG-TRANSMIT-018290 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-05 | INTERSIG-TRANSMIT-000001 | NA | Trade Partner | 26-004 Assemble Coburg - STATUTORY SIGNAGE | 1 | 0 | 0 | NA | APPROVED | 2026-06-05 | WF - 001037 | NA | 2026-06-12 |  | NA | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-003124 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-05 | NXT-TRANSMIT-001608 | NA | Trade Partner | NXT-TRANSMIT-001608-Fwd: 100222-000593: M3 Stage 2 - EQ Room - Architectural As Built Drawings | 10 | 0 | 0 | NA | APPROVED | [5 empty] | As Builts from NEXTDC can be directly updated in Aconex and ACC and can be distributed as per Katherine. |  | 2026-06-05 | KPTG-TRANSMIT-018296 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-05 | INTERSIG-TRANSMIT-000002 | NA | Trade Partner | 26-004 Assemble Coburg - PROTOTYPES | 1 | 0 | 0 | NA | APPROVED | 2026-06-05 | WF - 001038 | NA | 2026-06-12 |  | NA | 2026-06-12 | 2026-06-12 | DRAFT-018817 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-05 | NXT-TRANSMIT-001610 | NA | Trade Partner | Fwd: 100222-000595: M3 Stage 2 - Typical Notes, Abbreviations and Symbols - As Built Drawing | 1 | 0 | 0 | NA | APPROVED | [5 empty] | As Builts from NEXTDC can be directly updated in Aconex and ACC and can be distributed as per Katherine. |  | 2026-06-05 | KPTG-TRANSMIT-018301 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-05 | D&E-TRANSMIT-000263 | NA | Trade Partner | Mechanical Services Seismic Level-01 Pipework & Ductwork | 9 | 0 | 0 | NA | REJECTED | [5 empty] | Drawing status inside the drawing and in Aconex seem different. |  | 2026-06-05 | KPTG-TRANSMIT-000987 | Closed | 9 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
HANWHA | 2026-06-05 | WPD-TRANSMIT-000089 | NA | Trade Partner | HYDRAULIC SERVICES - AS BUILTS | 2 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | 413 | 2026-06-11 | [5 empty] | Open |  | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-05 | NXT-TRANSMIT-001609 | NA | Trade Partner | Fwd: 100222-000594: M3 Stage 2 - ER Room - Architectural As Built Drawings | 10 | 0 | 0 | NA | APPROVED | [5 empty] | As Builts from NEXTDC can be directly updated in Aconex and ACC and can be distributed as per Katherine. |  | 2026-06-05 | KPTG-TRANSMIT-018304 | Closed | 10 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MWYCCB | 2026-06-05 | RDSBIM-TRANSMIT-000056 | SPARK-CRFI-KPG-000362 | Trade Partner | MWYCCB ¦ SITE STORAGE BUILDING GF & LEVEL 01 CONCRETE PROFILE PLAN | 1 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | 312 | 2026-06-12 |  |  | 2026-06-23 | 2026-06-23 | KPTG-TRANSMIT-001323 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-05 | SRA-PMQ-TRANSMIT-000002 | NA | Trade Partner | DataStruct Heavy Duty Ceilings For Data Centres | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Difference in Document title in Aconex submission and inside the document. |  | 2026-06-05 | KPTG-SADV-000585 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-24 | BLUESF-TRANSMIT-000006 | N/A | Trade Partner | M2-STR-BSF-SDRG-1101-P1 PRECAST DRAWINGS IFA | 50 | 0 | 0 | NA | REJECTED |  | N/A | N/A |  |  | wrong uploading and Title guide-KPTG-TRANSMIT-000434 |  | 2025-12-29 | KPTG-TRANSMIT-000434 | Closed | 50 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-05 | SRA-PMQ-TRANSMIT-000003 | NA | Trade Partner | Physical Testing Results for New Suspended Data Centre Grid | 0 | 1 | 0 | NA | APPROVED | 2026-06-05 | WF-000190 | NA | 2026-06-15 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-000857 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-05 | SRA-PMQ-TRANSMIT-000004 | NA | Trade Partner | DataStruct Installation Instructions | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Mismatch in title. Type error. |  | 2026-06-05 | KPTG-SADV-000586 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-05 | M.2-TRANSMIT-000039 | NA | Trade Partner | Electrical Services Level 2-7 Lighting layouts | 15 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | 1172 | 2026-06-12 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-002292 | Closed | 15 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-05 | Civilex-TRANSMIT-000262 | NA | Trade Partner | Stage 2 - Rooftop Planter Box Details | 0 | 1 | 0 | NA | REJECTED | [5 empty] | Issue with document title, missing drawings status, revision history. |  | 2026-06-05 | KPTG-SADV-005765 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-05 | WAM-TRANSMIT-000798 | NA | Consultant | IFC A12 CSP Level 4 - RFI-001045 | 2 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | 742 | 2026-06-09 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-002356 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
GREYSTAR | 2026-06-05 | Auspan-TRANSMIT-000359 | NA | Trade Partner | Shop drawing 0G5005 ifc. | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | Precast IFC- No review required, update register and distribute KPTG-TRANSMIT-002170 |  | 2026-06-05 | KPTG-TRANSMIT-002170 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
CHAPEL STREET | 2026-06-05 | RDSBIM-TRANSMIT-000072 | NA | Trade Partner | 671CHP BASEMENT 1 CONCRETE PROFILE PLAN | 3 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | ACC#544 | 2026-06-12 |  | Review voided to update the drawings as requested by RDS and informed by Kapitol. | 2026-06-19 | 2026-06-19 | NA | Closed | 3 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-05 | KPTG-INTCOM-000338 | NA | Trade Partner | Metalzone - Level 5 Angle Shop Drawing | 1 | 0 | 0 | NA | APPROVED | 2026-06-05 | WF-000787 | NA | 2026-06-12 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-002636 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-05 | SKS Tech-TRANSMIT-000156 | NA | Trade Partner | Supports and Hangers layout issued for construction | 8 | 0 | 0 | NA | APPROVED |  | NA | 3454 | 2026-06-08 | [5 empty] | Open |  |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-05 | Entire M-TRANSMIT-000062 | NA | Trade Partner | AHU tagging updates for information | 4 | 0 | 0 | NA | APPROVED | 2026-06-05 | WF-000302 | NA | 2026-06-10 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-000860 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-24 | BLUESF-TRANSMIT-000007 | N/A | Trade Partner | M2-STR-BSF-SDRG-1101-P2 PRECAST DRAWINGS IFA | 49 | 0 | 0 | N/A | REJECTED |  | N/A | N/A |  |  | Wrong uploading and title guide-KPTG-TRANSMIT-000435 |  | 2025-12-29 | KPTG-TRANSMIT-000435 | Closed | 49 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-05 | D&E-TRANSMIT-000799 | NA | Trade Partner | Fwd: BMS Points Lists - Issued for construction | 0 | 3 | 0 | NA | APPROVED | 2026-06-05 | WF-005954 | NA | 2026-06-12 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-019452 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-05 | ARCST-TRANSMIT-000301 | NA | Trade Partner | Re: HV Room - Caged Ladder | 1 | 0 | 0 | NA | REJECTED | [5 empty] | REJECTED DUE IFC SUBMIITED BEFORE IFA |  |  |  | Open |  | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-05 | D&E-TRANSMIT-000801 | NA | Trade Partner | Fwd: NXM3S4 - Roof Level - Chiller Room 5 Layout + Sections - Issued For Construction | 2 | 0 | 0 | NA | APPROVED | [7 empty] | 2026-06-05 | KPTG-TRANSMIT-018317 | Closed | 2 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-05 | HDRAus-TRANSMIT-000499 | NA | Consultant | Re: M3 Stage 4 - Document upload - PDF and CAD | 3 | 0 | 0 | NA | REJECTED | [7 empty] | 2026-06-05 | KPTG-RFI-008285 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-05 | HDRAus-TRANSMIT-000500 | NA | Consultant | Re: M3 Stage 4 - Document upload - PDF and CAD | 3 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected due to an error in the Document number and Revision number |  | 2026-06-05 | KPTG-RFI-008285 | Closed | 3 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S4 | 2026-06-05 | HDRAus-TRANSMIT-000499 | NA | Consultant | M3 Stage 4 - Document upload - PDF and | 21 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | #3463 | 2026-06-18 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-018457 | Closed | 21 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-05 | JCBa-TRANSMIT-000262 | NA | Consultant | IFC - BTR G/F & L3 | 36 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | 575 | 2026-06-11 |  | NA | 2026-06-09 | 2026-06-09 | DRAFT-018654 | Closed | 36 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-12 | JCI-TRANSMIT-000029 | NA | Trade Partner | OFCI BAS Points Schedules IFC | 0 | 8 | 0 | NA | APPROVED | 2026-06-12 | WF - 0000474 | NA | 2026-06-16 |  | NA | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-000995 | Closed | 8 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL05C4 | 2026-06-05 | Altaire-IntCorr-000044 | NA | Trade Partner | MEL05 - Fire Matrix IFC (B) | 0 | 1 | 0 | NA | APPROVED | 2026-06-05 | WF - 000455 | NA | 2026-06-12 |  | NA | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-001000 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-05 | TTW-TRANSMIT-000037 | NA | Consultant | NEXT DC M3 Sage 6 Facade performance specification and drawing | 17 | 0 | 0 | NA | REJECTED |  | NA | NA |  |  | Mismating the drawing status |  | 2026-06-05 | KPTG-DA-000319 | Closed | 17 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-24 | BLUESF-TRANSMIT-000008 | N/A | Trade Partner | M2-STR-BSF-SDRG-1101-P3 PRECAST DRAWINGS IFA | 39 | 0 | 0 | NA | REJECTED |  | N/A | N/A |  |  | Wrong uploading and title guide- KPTG-TRANSMIT-000436 |  | 2025-12-29 | KPTG-TRANSMIT-000436 | Closed | 39 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-05 | 4DW-TRANSMIT-000041 | NA | Consultant | Piling Plan - Tank Slab Part Plan CAD file: Issued for information | 1 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | CAD File |  | 2026-06-05 | KPTG-TRANSMIT-000160 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-05 | RBG-TRANSMIT-000004 | NA | Trade Partner | MSS6 Tower Crane CAD Files | 4 | 0 | 0 | KPTG-IntCorr-000157 | APPROVED |  | NA | NA |  |  | RBG-TRANSMIT-000003 superseded by RBG-TRANSMIT-000004,Actual -Update register only |  | 2026-06-10 | NA | Closed | 4 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S6 | 2026-06-05 | KPTG-TRANSMIT-000162-SME | NA | Consultant | ACC Workflows Required - & SME | 47 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | 173 | 2026-06-12 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-000311 | Closed | 47 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
LINDRUM | 2026-06-05 | fjc-TRANSMIT-000153 | NA | Consultant | Architecturals - Revised Ground Floor | 1 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | 665 | 2026-06-10 |  |  | 2026-06-09 | 2026-06-09 | KPTG-SADV-004456 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-05 | ZIA-TRANSMIT-000004 | NA | Trade Partner | M2S9,10,11 CSMS Sample Data Submission (FOA-1) | 0 | 1 | 0 | NA | APPROVED | 2026-06-05 | WF-000879 | NA | 2026-06-17 |  |  | 2026-06-22 | 2026-06-22 | KPTG-TRANSMIT-004546 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-05 | PFP PL-TRANSMIT-000007 | NA | Trade Partner | Wet Fire Tech data | 0 | 2 | 0 | NA | APPROVED | 2026-06-05 | WF-000880 | NA | 2026-06-17 |  |  | 2026-06-24 | 2026-06-24 | KPTG-TRANSMIT-004708 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-05 | HGP-TRANSMIT-000003 | NA | Trade Partner | Ground Floor Windows | 11 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | 1046 | 2026-06-12 |  |  | 2026-06-18 | 2026-06-18 | KPTG-TRANSMIT-004403 | Closed | 11 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-05 | DLTS-TRANSMIT-000018 | NA | Trade Partner | S9 Cooling Tower-Part 1-Re IFA Issue | 13 | 0 | 0 | NA | APPROVED | 2026-06-05 | WF-000882 | NA | 2026-06-10 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-004109 | Closed | 13 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-05 | DCN-TRANSMIT-000012 | NA | Trade Partner | Link Bridge - Material Tech Data Windows and Glazing | 0 | 1 | 0 | NA | APPROVED | 2026-06-05 | WF-000883 | NA | 2026-06-10 |  |  | 2026-07-07 | 2026-07-07 | KPTG-TRANSMIT-005314 | Closed | 1 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-24 | BLUESF-TRANSMIT-000009 | N/A | Trade Partner | M2-STR-BSF-SDRG-1101-P4 PRECAST DRAWINGS IFA | 68 | 0 | 0 | NA | REJECTED |  | N/A | N/A |  |  | Wrong uploading and Title guide- KPTG-TRANSMIT-000437 |  | 2025-12-29 | KPTG-TRANSMIT-000437 | Closed | 68 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-05-25 | ELLISAIR-TRANSMIT-000028 | NA | Trade Partner | Tech Data Submission | 0 | 2 | 0 | NA | APPROVED | 2026-05-25 | WF-000759 | NA | 2026-06-04 |  |  | 2026-06-16 | 2026-06-16 | KPTG-TRANSMIT-004267 | Closed | 2 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2026-06-01 | DLTS-TRANSMIT-000011 | NA | Trade Partner | S9-North Eave Gutter Framing-IFA Issue | 7 | 0 | 0 | NA | APPROVED | 2026-06-01 | WF-000831 | NA | 2026-06-11 |  |  | 2026-07-08 | 2026-07-08 | KPTG-TRANSMIT-005367 | Closed | 7 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-05 | Jangho-TRANSMIT-000136 | NA | Trade Partner | Structural Calculation For Cast in Channel Calculation-Rev 02 | 0 | 1 | 0 | NA | APPROVED | 2026-06-05 | WF-000660 | NA | 2026-06-09 |  |  | 2026-06-11 | 2026-06-10 | KPTG-TRANSMIT-002207 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-05 | Jangho-TRANSMIT-000137 | NA | Trade Partner | Issues the Thermal Report of FT01 for approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | DOC NO ERROR |  | 2026-06-05 | KPTG-TRANSMIT-002160 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-05 | Jangho-TRANSMIT-000138 | NA | Trade Partner | Issues the Thermal Report of FT02 for approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | DOC NO ERROR |  | 2026-06-05 | KPTG-TRANSMIT-002161 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-05 | Jangho-TRANSMIT-000139 | NA | Trade Partner | Sliding Door AS Standard Requirements | 0 | 1 | 0 | NA | REJECTED | [5 empty] | DOC NO ERROR |  | 2026-06-05 | KPTG-TRANSMIT-002162 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-05 | RDSBIM-TRANSMIT-000045 | NA | Trade Partner | Issues Thermal Report FT07 For Approval | 4 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | 744 | 2026-06-15 |  |  | 2026-06-24 | 2026-06-25 | KPTG-TRANSMIT-002495 | Closed | 4 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-05 | Jangho-TRANSMIT-000140 | NA | Trade Partner | Issues Thermal Report FT07 For Approval | 0 | 1 | 0 | NA | REJECTED | [5 empty] | DOC NO ERROR |  | 2026-06-05 | KPTG-TRANSMIT-002163 | Closed | 1 |  | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-05 | SC-TRANSMIT-000003 | NA | Trade Partner | IFC A12 CSP Level 4 - RFI-001045 | 11 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | 745 | 2026-06-08 |  |  | 2026-06-30 | 2026-06-30 | KPTG-TRANSMIT-002576 | Closed | 11 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-06-05 | Civilex-TRANSMIT-000099 | NA | Trade Partner | Re: Pavement Material - 20mm Class 3 Crushed Concrete | 0 | 1 | 0 | NA | APPROVED | 2026-06-05 | WF-000663 | NA | 2026-06-16 |  |  | 2026-06-15 | 2026-06-15 | KPTG-TRANSMIT-002282 | Closed | 1 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM2S9 | 2025-12-24 | BLUESF-TRANSMIT-000010 | N/A | Trade Partner | M2-STR-BSF-SDRG-1101-P5 PRECAST DRAWINGS IFA | 34 | 0 | 0 | N/A | REJECTED |  | N/A | N/A |  |  | Wrong uploading and Title guide- KPTG-TRANSMIT-000438 |  | 2025-12-29 | KPTG-TRANSMIT-000438 | Closed | 34 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-22 | Jangho-TRANSMIT-000109 | NA | Trade Partner | 009 _TOWER SHOP DRAWING (6F~16F) -01 | 58 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 669 | 2026-06-08 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-002152 | Closed | 58 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
DISTLVG | 2026-05-22 | Jangho-TRANSMIT-000108 | NA | Trade Partner | 008 _PODIUM SHOP DRAWING (1F~5F) -01 | 3 | 0 | 0 | NA | APPROVED | 2026-05-28 | NA | 669 | 2026-06-08 |  |  | 2026-06-05 | 2026-06-05 | KPTG-TRANSMIT-002152 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-05 | ARCH-TRANSMIT-000158 | NA | Consultant | MLC - SRP - AQC - J50 Reception drawing update | 1 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | 299 | 2026-06-10 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-002960 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MLCSPR | 2026-06-05 | 4DW-TRANSMIT-000185 | NA | Consultant | Structural Documentation - General updates | 9 | 0 | 0 | NA | APPROVED | 2026-06-05 | NA | 301 | 2026-06-10 |  |  | 2026-06-10 | 2026-06-10 | KPTG-TRANSMIT-002969 | Closed | 9 | NO | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-05 | Entire M-TRANSMIT-000061 | NA | Trade Partner | AHU tagging updates for construction | 8 | 0 | 0 | NA | APPROVED | 2026-06-05 | WF-000303 | NA | 2026-06-12 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-000866 | Closed | 8 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-05 | Entire M-TRANSMIT-000060 | NA | Trade Partner | Mechanical 1:50 drawings | 3 | 0 | 0 | NA | APPROVED | 2026-06-05 | WF-000304 | NA | 2026-06-12 |  |  | 2026-06-09 | 2026-06-09 | KPTG-TRANSMIT-000863 | Closed | 3 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
MEL11C45 | 2026-06-05 | Entire M-TRANSMIT-000059 | NA | Trade Partner | Mechanical drawings - Issued for construction | 2 | 0 | 0 | NA | REJECTED | [5 empty] | Rejected: Drawing status needs to be "for Approval"-KPTG-IntCorr-000533 |  | 2026-06-05 | KPTG-IntCorr-000533 | Closed | 2 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXM3S2 | 2026-06-09 | HDRAus-TRANSMIT-000501 | NA | Consultant | M3_S2_Updated Stair Details Sheet 1 - Roof Bridge Over Gutter | 1 | 0 | 0 | NA | APPROVED | 2026-06-08 | NA | 4266 | 2026-06-11 |  |  | 2026-07-07 | 2026-08-03 | KPTG-TRANSMIT-020315 | Closed | 1 | YES | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
NXGEO1S1 | 2026-06-09 | SRA-PMQ-TRANSMIT-000005 | NA | Trade Partner | Re: Ceiling Detail Drawings | 5 | 0 | 0 | NA | REJECTED | [5 empty] | rejected due to wrong document naming |  | 2026-06-09 | KPTG-RFI-000269 | Closed | 5 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol
511SRC | 2026-06-09 | RDSBIM-TRANSMIT-000214 | NA | Trade Partner | RCP ¦ LEVEL12 RCP LAYOUT TOWER ¦ IFC ¦ SUBMISSION | 4 | 0 | 0 | NA | APPROVED |  | NA | NA |  |  | NA | 2026-06-09 | 2026-06-09 | DRAFT-018632 | Closed | 4 | NA | Item | sites/RDS-AUS/Lists/DC Daily Report RDS Kapitol